## FAASt - LUMA Exhibit 2, 3 & 4 (hidden)
Puerto Rico Electric Power Authority
FAASt Consolidated Plan - Obligated & Budget Summary
FAASt Obligation Summary
| Total Gross Cost Obligated PW 6099 |  |  |  | 10704730227.54
|  | Less: Insurance Reductions |  |  | -275000000
|  | Available FAASt Balance |  |  | 10429730227.54
FAASt Consolidated - Estimated w/ PREB Filing updates + 70 Projects + Urgent + Incremental
| Entity | 9510 | 10710 | Childs | Total |  | Entity | 9510 | 10710 | Childs | Total
| LUMA | 965111111 | 1655843545 | 2195598436.3767 | 4816553092.3767 |  | LUMA | #REF! | #REF! | #REF! | #REF!
|  |  |  | Total Reductions | 4816553092.3767 |  |  |  |  | Total Reductions | #REF!
[9 empty] | 9510 | 10710
[9 empty] | 965111111 | 1655843545
[8 empty] | Reclass to 428 | #REF! | #REF!
[8 empty] | Reclass to 406 | #REF! | #REF!
[9 empty] | #REF! | #REF! | Pending allocation
| LUMA Child Obligated | [6 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
| PW | LUMA - Obligated | Project Name | 428 | 406 | Total Child | Asset | 428 Cons | 428 from 9510 | 428 from 10710 | Total 428 | 406 from 9510 | 406 from 10710 | New 406 | Total 406 |  | Total Project | Diff | Comments
| 10496 | 174422 | FAASt - Catano-Rebuild 1801(Substation) | 16359899.17 | 6895149.77 | 23255048.94 | Substation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 10499 | 542690 | FAASt Maunabo Streetlighting (Distribution) | 6199877.07 | 243880.33 | 6443757.4 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 10515 | 542517 | FAASt -Luquillo Distribution Streetlighting | 8628667.29 | 181658.08 | 8810325.37 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 10521 | 542687 | FAASt Lajas Streetlighting (Distribution) | 10278336.09 | 426332.48 | 10704668.57 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 10538 | 542756 | FAASt Streetlighting - Guánica (Distribution | 9687238 | 370808 | 10058046 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 10539 | 542688 | FAASt Aguada Streetlighting (Distribution) | 17764494.34 | 807222.04 | 18571716.38 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 10624 | 165225 | FAASt-Substation 2501 Vieques (Substation) | 1209111 | 178309 | 1387420 | Substation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 10626 | 165209 | FAASt-Substation 3801 Culebra (Substation) | 1282218 | 177391 | 1459609 | Substation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 10629 | 334329 | FAASt Distribution Feeders - Ponce Short Term | 316119 | 64134 | 380253 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 10630 | 334323 | FAASt Distribution Feeders - Ponce Short Term | 323692 | 69130 | 392822 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 10632 | 179558 | FAASt - Manatí TC - BRKS 230 kV - (Substation) | 1593443 | 0 | 1593443 | Substation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 10635 | 334488 | FAASt Distribution Feeders - Caguas Short Ter | 142917 | 10826 | 153743 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 10679 | 334468 | FAASt Line 2200 Dos Bocas HP to Dorado TC (T | 1217429 | 0 | 1217429 | Transmission | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 10690 | 542762 | FAASt Distribution Feeders - Arecibo Short Te | 610448 | 157420 | 767868 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 10701 | 334527 | FAASt Distribution Feeders - Caguas Short Term | 108847 | 14874 | 123721 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 10742 | 673839 | FAASt Distribution Pole and Conductor Repair- | 20468 | 5830 | 26298 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 10751 | 673848 | FAASt Distribution Pole and Conductor Repair- | 43725 | 5620 | 49345 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 10764 | 673838 | FAASt Distribution Pole and Conductor Repair | 284349 | 73265 | 357614 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 10773 | 673774 | FAASt Distribution Pole and Conductor Repair | 1408531 | 358420 | 1766951 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 10777 | 673795 | FAASt Distribution Pole and Conductor Repair - | 1425163 | 368954 | 1794117 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 10788 | 169896 | FAASt - Costa Sur SP TC  Equipment Repair and | 23251835 | 0 | 23251835 | Substation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 10800 | 668583 | FAASt Line 13300 GOAB 13301C to Hato Tejas Se | 453597 | 0 | 453597 | Transmission | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 10812 | 673847 | FAASt Distribution Pole and Conductor Repair- | 190570 | 49943 | 240513 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 10821 | 673818 | FAASt Distribution Pole and Conductor Repair | 621804 | 171614 | 793418 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 10824 | 674098 | FAASt Distribution Pole and Conductor Repair | 84433 | 23322 | 107755 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 10827 | 674083 | FAASt Distribution Pole and Conductor Repair | 1747929 | 362533 | 2110462 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 10837 | 550896 | FAASt Line 6700 Martin Peña TC to Villamar Se | 690703 | 0 | 690703 | Transmission | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 10841 | 550910 | FAASt Physical Security - Group 1 (Substatio | 6025270.22 | 665958.96 | 6691229.18 | Substation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 10857 | 660239 | FAASt Streetlighting - Villalba (Distributio | 10190536.05 | 681865.66 | 10872401.71 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | To verify w/ LUMA
| 10858 | 546370 | FAASt - Substation Minor Repairs Group A (Subs | 4482972.51 | 488202.58 | 4971175.09 | Substation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 10864 | 673844 | FAASt Distribution Pole and Conductor Repair | 1072850.98 | 319213.9 | 1392064.88 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 10876 | 659715 | FAASt Distribution Streetlighting - Aibonito | 7074498 | 178787 | 7253285 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 10884 | 659623 | FAASt Distribution Streetlighting - Cataño ( | 16996758 | 565289 | 17562047 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 10891 | 668592 | FAASt Line 9800 Bayamon TC - Guaraguao Sect | 420866 | 0 | 420866 | Transmission | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 10893 | 674092 | FAASt Distribution Pole and Conductor Repair | 441308 | 90422 | 531730 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 10906 | 674072 | FAASt Distribution Pole and Conductor Repair | 872891 | 238203 | 1111094 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 10909 | 673771 | FAASt Distribution Pole and Conductor Repair | 1894033.53 | 472527 | 2366560.53 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 10919 | 673772 | FAASt Distribution Pole and Conductor Repair | 3286536 | 835984 | 4122520 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 10922 | 673843 | FAASt Distribution Pole and Conductor Repair- | 904194 | 227661 | 1131855 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 10933 | 674088 | FAASt Distribution Pole and Conductor Repair | 1412368 | 289653 | 1702021 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 10935 | 674096 | FAASt Distribution Pole and Conductor Repair | 1773428 | 318852 | 2092280 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 10957 | 657300 | FAASt ENERGY MANAGEMENT SYSTEM (EMS) (Teleco | 48941484 | 0 | 48941484 | Telecommunications | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 10962 | 673775 | FAASt Distribution Pole and Conductor Repair | 3575454.81 | 857193.1 | 4432647.91 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 10978 | 168226 | FAASt San Juan 115kV Underground Transmission | 14746039.57 | 0 | 14746039.57 | Transmission | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11041 | 673836 | FAASt Distribution Pole and Conductor Repair- | 4686914.68 | 1064121.8 | 5751036.48 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11045 | 165268 | FAASt Rio Grande Estate Substation CH-2306 (Su | 7098243.76 | 4585370.95 | 11683614.71 | Substation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11089 | 679149 | FAASt Distribution Pole and Conductor Repair - | 129744 | 27443 | 157187 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11095 | 660227 | FAASt Hatillo Streetlight (Distribution) | 18570095.25 | 1764387.7 | 20334482.95 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11096 | 679127 | FAASt Distribution Pole and Conductor Repair | 171152.23 | 46010.58 | 217162.81 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11097 | 660437 | FAASt Manati Streetlight (Distribution) | 27067865 | 1568964 | 28636829 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11098 | 679033 | FAASt Distribution Pole and Conductor Repair | 729040 | 179902 | 908942 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11099 | 659625 | FAASt Distribution Streetlighting - Dorado | 22864972 | 1505645 | 24370617 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11100 | 178503 | FAASt Aguirre TC - BKRS (Substations) | 39034592 | 0 | 39034592 | Substation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11101 | 679025 | FAASt Distribution Pole and Conductor Repair | 243073 | 55558 | 298631 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11103 | 678985 | FAASt Distribution Pole and Conductor Repair- | 353628 | 54317.84 | 407945.84 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11105 | 679457 | FAASt Distribution Pole and Conductor Repair | 589335 | 157153 | 746488 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11106 | 679153 | FAASt Distribution Pole and Conductor Repair | 163846.51 | 51337.5 | 215184.01 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | To verify w/ LUMA
| 11107 | 679026 | FAASt Distribution Pole and | 483786 | 106510 | 590296 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11109 | 679134 | FAASt Distribution Pole and Conductor Repair | 452956.93 | 110600.22 | 563557.15 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11113 | 678988 | FAASt Distribution Pole and Conductor Repair- | 911136.76 | 206650.4 | 1117787.16 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11114 | 679458 | FAASt Distribution Pole and Conductor Repair | 498436 | 95482 | 593918 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11116 | 686471 | FAASt Distribution Pole and Conductor Repair | 250906 | 68700 | 319606 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | To verify w/ LUMA
| 11123 | 682865 | FAASt Distribution Pole and Conductor Repair | 70683 | 21148 | 91831 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11130 | 682882 | FAASt Distribution Pole and Conductor Repair | 545661.24 | 113378.16 | 659039.4 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11136 | 682890 | FAASt Distribution Pole and Conductor Repair | 510067.96 | 102310.67 | 612378.63 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11137 | 682870 | FAASt Distribution Pole and Conductor Repair | 85921.77 | 17491 | 103412.77 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11138 | 685943 | FAASt Distribution Pole and Conductor Repair P | 254972.22 | 63260 | 318232.22 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11143 | 685263 | FAASt Distribution Pole and Conductor Repair - | 537688 | 134695 | 672383 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11145 | 682324 | FAASt Distribution Pole and Conductor Repair | 573047.24 | 136182.31 | 709229.55 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11149 | 682135 | FAASt Distribution Pole and Conductor Repair | 577000.79 | 116779.74 | 693780.53 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | To verify w/ LUMA
| 11150 | 685370 | FAASt Distribution Pole and Conductor Repair | 68823 | 14986 | 83809 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11152 | 686453 | FAASt Distribution Pole and Conductor Repair | 20584 | 4995 | 25579 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11165 | 682373 | FAASt Distribution Pole and Conductor Repair | 65944 | 11661 | 77605 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11166 | 682028 | FAASt Distribution Pole and Conductor Repair | 431381.68 | 105743.62 | 537125.3 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | To verify w/ LUMA
| 11168 | 682180 | FAASt Distribution Pole and Conductor Repair | 43374 | 11028 | 54402 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11169 | 682210 | FAASt Distribution Pole and Conductor Repair - | 198050.74 | 41796.87 | 239847.61 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11171 | 685477 | FAASt Distribution Pole and Conductor Repair - | 355178 | 58304 | 413482 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | To verify w/ LUMA
| 11181 | 682031 | FAASt Distribution Pole and Conductor Repair | 516951 | 108247 | 625198 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11182 | 682172 | FAASt Distribution Pole and Conductor Repair | 208400 | 57671.35 | 266071.35 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | To verify w/ LUMA
| 11183 | 682898 | FAASt Distribution Pole and Conductor Repair | 635326.93 | 108700.19 | 744027.12 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | To verify w/ LUMA
| 11184 | 681672 | FAASt Transmission Priority Pole Replacements | 214124 | 2243 | 216367 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11193 | 688627 | FAASt Distribution Pole and Conductor Repair | 303774 | 72188.49 | 375962.49 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11196 | 682228 | FAASt Distribution Pole and Conductor Repair - | 775779 | 176882.42 | 952661.42 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11201 | 682178 | FAASt Distribution Pole and Conductor Repair | 208544.25 | 53746.06 | 262290.31 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11203 | 682136 | FAASt Distribution Pole and Conductor Repair- | 469650.95 | 95954.05 | 565605 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11207 | 688774 | FAASt Distribution Pole and Conductor Repair | 443331 | 98484 | 541815 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11212 | 682910 | FAASt Distribution Pole and Conductor Repair | 517156 | 105667 | 622823 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | To verify w/ LUMA
| 11214 | 688096 | FAASt Distribution Pole and Conductor Repair | 21408.25 | 5830.39 | 27238.64 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11217 | 688472 | FAASt Distribution Pole and Conductor Repair - | 164908.86 | 14986 | 179894.86 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11229 | 686480 | FAASt Distribution Pole and Conductor Repair - | 523404 | 108652 | 632056 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | To verify w/ LUMA
| 11231 | 691246 | FAASt Distribution Pole and Conductor Repair | 211622.76 | 33717.31 | 245340.07 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11256 | 689071 | FAASt Distribution Pole and Conductor Repair | 59545.08 | 17491.16 | 77036.24 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11257 | 701552 | FAASt Distribution Pole and Conductor Repair | 186321 | 51841 | 238162 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | To verify w/ LUMA
| 11263 | 701495 | FAASt Distribution Pole and Conductor Repair | 19848.36 | 5830.39 | 25678.75 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11264 | 688109 | FAASt Distribution Pole and Conductor Repair | 448719.06 | 114710.2 | 563429.26 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | To verify w/ LUMA
| 11267 | 701679 | FAASt Distribution Pole and Conductor Repair | 64425.44 | 16226.16 | 80651.6 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11268 | 701504 | FAASt Distribution Pole and Conductor Repair | 150345 | 37878 | 188223 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11269 | 701545 | FAASt Distribution Pole and Conductor Repair | 487190 | 129039 | 616229 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11273 | 688630 | FAASt Distribution Pole and Conductor | 42728.41 | 9990.97 | 52719.38 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11275 | 701555 | FAASt Distribution Pole and Conductor Repair | 547010 | 102417 | 649427 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11276 | 688198 | FAASt Distribution Pole and Conductor Repair - | 60838.48 | 16023.76 | 76862.24 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11277 | 688629 | FAASt Distribution Pole and Conductor Repair | 106941.99 | 27886.93 | 134828.92 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11279 | 688625 | FAASt Distribution Pole and Conductor Repair | 710014.69 | 191275.59 | 901290.28 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11311 | 704751 | FAASt Distribution Pole and Conductor Repair - | 338491 | 96676 | 435167 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11312 | 704916 | FAASt [Distribution Pole and Conductor Repair | 273996 | 29974 | 303970 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11314 | 704750 | FAASt Distribution Pole and Conductor Repair - | 486385 | 92244 | 578629 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11317 | 673504 | FAASt [Distribution Streetlighting - Gurabo] | 19208994 | 1533300 | 20742294 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11318 | 659968 | FAASt [San Germán Streetlighting] (Distributio | 30849348 | 4033578 | 34882926 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11319 | 690545 | FAASt Aguadilla Streetlight (Distribution) | 19796809 | 1295775 | 21092584 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11326 | 691702 | FAASt Distribution Streetlighting - Trujillo Alto (Distribution) | 25277347 | 1009578 | 26286925 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | To verify w/ LUMA
| 11340 | 704844 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 16-17-18-19-20] (Distribution) | 320740 | 88558 | 409298 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11344 | 698424 | FAASt Streetlight Florida Distribution | 9311841.53 | 997190 | 10309031.53 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11347 | 169500 | FAASt [Bayamon TC - MC-BKRS-Y1] (Substation) | 2796182 | 3575881 | 6372063 | Substation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11350 | 549764 | FAASt Physical Security - Group 2 (Substation) | 2159012.31 | 224680.68 | 2383692.99 | Substation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11351 | 679039 | FAASt [Distribution Streetlighting - Caguas] (Distribution) | 73737224.58 | 1849344.06 | 75586568.64 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | To verify w/ LUMA
| 11352 | 704755 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 12-13-14] (Distribution) | 438209.69 | 86181.92 | 524391.61 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11365 | 705584 | FAASt [Distribution Pole and Conductor Repair - Ponce Groups 14 &amp;amp; 15] (Distribution) | 1464496 | 378483 | 1842979 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11372 | 551861 | FAASt [Physical Security - Group 3] (Substation) | 3696956.6 | 436383.23 | 4133339.83 | Substation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11385 | 542758 | FAASt Substation Minor Repairs -Group B (Substation) | 2973035 | 439541 | 3412576 | Substation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11402 | 682834 | FAASt [Costa Sur TC - Phase II &amp;amp; III ] (Substation) | 36917509.58 | 0 | 36917509.58 | Substation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11449 | 705527 | FAASt [Distribution Pole and Conductor Repair - San Juan 17-18-19-20-21] (Distribution) | 642721 | 125133 | 767854 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11465 | 704933 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 13-14-15-16] (Distribution) | 1201420 | 224731 | 1426151 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11478 | 546371 | FAASt- Substation Minor Repairs Group C (Substation) | 2648259.06 | 384632.14 | 3032891.2 | Substation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11479 | 169495 | FAASt [Substations - Tapia GIS Rebuilt Equipment Repair &amp;amp; Replacement] (Substations) | 8180049.03 | 7159883.3 | 15339932.33 | Substation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11489 | 169266 | FAASt Centro Medico 1327/1359 Equipment Repair &amp;amp; Replacement (Substation) | 14795324 | 6537037 | 21332361 | Substation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11508 | 708579 | FAASt [Distribution Pole and Conductor Repair - Ponce Group 16, 17, 18 &amp;amp; 19] (Distribution) | 1764568.92 | 389437.84 | 2154006.76 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11518 | 698458 | FAASt [Distribution Streetlighting - Guaynabo] (Distribution) | 9762754.59 | 853056.42 | 10615811.01 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11522 | 671502 | FAASt [Distribution Streetlighting - Yabucoa] (Distribution) | 14918381.07 | 1965608.26 | 16883989.33 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11524 | 704679 | FAASt Coamo Streetlight (Distribution) | 14311922.45 | 2060901.35 | 16372823.8 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11526 | 698439 | FAASt Streetlight - Las Marías (Distribution) | 7073217 | 1287705 | 8360922 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11532 | 678793 | FAASt [Streetlighting - Mayagüez] (Distribution) | 11019180.1 | 1352204.36 | 12371384.46 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11533 | 678789 | FAASt [Distribution Streetlighting - Carolina] (Distribution) | 14865613.02 | 1158946.56 | 16024559.58 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11534 | 710110 | FAASt [Distribution Pole and Conductor Repair - Bayamon Group 2 - Phase 2] (Distribution) | 85296.74 | 2478.06 | 87774.8 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11537 | 551925 | FAASt [SCADA Remote Access and RTU Replacements Group 1] (Telecommunication) | 5962412.52 | 1701923.62 | 7664336.14 | Telecommunications | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11540 | 679780 | FAASt [Distribution Streetlighting - Bayamon] (Distribution) | 20710527 | 1176376 | 21886903 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11555 | 723078 | FAASt - EPC - [San Juan SP TC] (Substation) | 61558468.95 | 0 | 61558468.95 | Substation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11556 | 723077 | FAASt - EPC - [Sabana Llana TC] (Substation) | 46643078.39 | 0 | 46643078.39 | Substation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11557 | 550950 | FAASt - EPC - [Monacillo TC] (Substations) | 58195134.18 | 0 | 58195134.18 | Substation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11560 | 698570 | FAASt [Distribution Streetlighting - Corozal] (Distribution) | 13720208.31 | 2225873.62 | 15946081.93 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | To verify w/ LUMA
| 11566 | 660422 | FAASt [Physical Security - Group 4] (Substation) | 3478518 | 338280 | 3816798 | Substation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11573 | 684920 | FAASt Substation High Voltage Replacement_Group 1 (Substation) | 6929384 | 0 | 6929384 | Substation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11583 | 714654 | FAASt [Advanced Metering Infrastructure (AMI)] (Telecommunications) | 332062581 | 544207595 | 876270176 | Telecommunications | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11627 | 709631 | FAASt [Morovis Streetlighting] (Distribution) | 13486398.85 | 1744482.27 | 15230881.12 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11629 | 698579 | FAASt [Distribution Streetlighting - Orocovis] (Distribution) | 8070964.96 | 1339801.28 | 9410766.24 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11633 | 704938 | FAASt [Distribution Streetlighting - Las Piedras (Distribution) | 13807923.4 | 1807601.11 | 15615524.51 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11636 | 703535 | FAASt [Toa Baja Streetlighting] (Distribution) | 9529190.37 | 620134.69 | 10149325.06 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11639 | 710094 | FAASt [Pole and Conductor Repair - Bayamon Group 1 - Phase 2] (Distribution) | 7096249.5 | 195136.32 | 7291385.82 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11640 | 711888 | FAASt [Pole and Conductor Repair - Caguas Group 1 - Phase 2] (Distribution) | 5425810.57 | 165903.3 | 5591713.87 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11650 | 704868 | FAASt [Ceiba Streetlighting] (Distribution) | 5152111.14 | 716918.6 | 5869029.74 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11652 | 682121 | FAASt - EPC -Aguirre TC-Phase II (Substation) | 82726096.38 | 0 | 82726096.38 | Substation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11658 | 704849 | FAASt [Naguabo Streetlighting] (Distribution) | 11620676.42 | 1669736.97 | 13290413.39 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | To verify w/ LUMA
| 11664 | 704943 | FAASt [Naranjito Streetlighting] (Distribution) | 11644048.43 | 2115538.38 | 13759586.81 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11666 | 712968 | FAASt [Pole and Conductor Repair - Arecibo Group 2 - Phase 2] (Distribution) | 5629060 | 178712.97 | 5807772.97 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | To verify w/ LUMA
| 11671 | 724703 | FAASt [Arroyo Streetlighting] (Distribution) | 5314332 | 740394.01 | 6054726.01 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11673 | 724938 | FAASt [Vega Alta Streetlighting] (Distribution) | 12445015.33 | 1869089.52 | 14314104.85 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11675 | 704921 | FAASt [Barranquitas Streetlighting] (Distribution) | 9430329.22 | 1577046.09 | 11007375.31 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11680 | 698511 | FAASt [Culebra Streetlighting] (Distribution) | 1155804 | 153603 | 1309407 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11682 | 549715 | FAASt Substation Minor Repairs - Group D (Substation) | 2583133.54 | 288123.63 | 2871257.17 | Substation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11686 | 738672 | FAASt [Pole and Conductor Repair - Mayaguez Group 1 - Phase 2] (Distribution) | 10313627 | 306131.37 | 10619758.37 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11696 | 723883 | FAASt [Region 1 -San Juan Group A] (Vegetation) | 6573069.54 | 18371390.02 | 24944459.56 | Vegetation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | To verify w/ LUMA
| 11707 | 549725 | FAASt [Substation Minor Repairs - Group E] (Substation) | 3924015.69 | 579767.52 | 4503783.21 | Substation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11711 | 704927 | FAASt [Añasco Streetlighting] (Distribution) | 12087876.17 | 1820361.92 | 13908238.09 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11712 | 738670 | FAASt [Pole and Conductor Repair - Ponce Group 1 - Phase 2] (Distribution) | 4926640.11 | 147870.9 | 5074511.01 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11714 | 728827 | FAASt [Region 2 -Arecibo Group A] High Density (Vegetation) | 4807675.47 | 13386633.34 | 18194308.81 | Vegetation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | To verify w/ LUMA
| 11715 | 727531 | FAASt [Region 6 -Ponce Group A] High Density (Vegetation) | 6849050.26 | 19064883.85 | 25913934.11 | Vegetation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | To verify w/ LUMA
| 11716 | 742026 | FAASt [Pole and Conductor Repair - San Juan Group 2 - Phase 2] (Distribution) | 1033375.81 | 84035.96 | 1117411.77 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11718 | 728832 | FAASt [Region 5 -Mayaguez Group A] High Density (Vegetation) | 3767690.42 | 10493001.48 | 14260691.9 | Vegetation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | To verify w/ LUMA
| 11719 | 711670 | FAASt [T-Pole Program Line 100] (Transmission) | 94787.57 | 23372.71 | 118160.28 | Transmission | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11723 | 708637 | FAASt T-Pole Program Line 3700] (Transmission) | 303960.92 | 73393.66 | 377354.58 | Transmission | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11724 | 727692 | FAASt [Region 4 -Caguas Group A] High Density (Vegetation) | 7414164.75 | 20637925.62 | 28052090.37 | Vegetation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | To verify w/ LUMA
| 11725 | 724825 | FAASt [Cidra Streetlighting] (Distribution) | 12812478.84 | 1838229.6 | 14650708.44 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11726 | 729286 | FAASt HV Equipment Replacement Group 2 (Substation) | 15413889.89 | 0 | 15413889.89 | Substation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11727 | 701472 | FAASt [Comerio Streetlighting] (Distribution) | 6538769.44 | 862125.75 | 7400895.19 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11734 | 724698 | FAASt [Adjuntas Streetlighting] (Distribution) | 10742462 | 1891152 | 12633614 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11735 | 724600 | FAASt [Jayuya Streetlighting] (Distribution) | 7277670.2 | 1350541.32 | 8628211.52 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11739 | 724601 | FAASt [Salinas Streetlighting] (Distribution) | 12097203.53 | 1611020.9 | 13708224.43 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11746 | 711856 | FAASt [Pole and Conductor Repair - Bayamon Group 3 - Phase 2] (Distribution) | 10940320.91 | 395663.43 | 11335984.34 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11753 | 742070 | FAASt [Pole and Conductor Repair - San Juan Group 1 - Phase 2] (Distribution) | 5461200.05 | 205587.38 | 5666787.43 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11754 | 712980 | FAASt [T-Pole Program Line 3000] (Transmission) | 559076.77 | 72117.49 | 631194.26 | Transmission | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11764 | 743399 | FAASt [High Voltage Equipment Replacement - Group 3] (Substation) | 17307539.01 | 0 | 17307539.01 | Substation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11839 | 745859 | FAASt [Automation Program Group 18: DAR – SAN JUAN 2001- FY24] (Distribution) | 467287.6 | 0 | 467287.6 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11850 | 738120 | FAASt [Pole and Conductor Repair-Carolina Group 2- Phase 2] (Distribution) | 11041271 | 409899.81 | 11451170.81 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11667 | 710099 | FAASt [Pole and Conductor Repair - Arecibo Group 1 - Phase 2] (Distribution) | 6704421.6922 | 239376.93 | 6943798.6222 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11812 | 738971 | FAASt [Pole and Conductor Repair - Caguas Group 2 - Phase 2] (Distribution) | 13884126 | 377123.67 | 14261249.67 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 108001 | 752810 | FAASt [Automation Program Group 20] (TL/Distribution) | 2623262.08 | 0 | 2623262.08 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 108000 | 752808 | FAASt [Automation Program Group 19] (TL/Distribution) | 2753627.24 | 0 | 2753627.24 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 108022 | 755211 | FAASt [Automation Program Group 15] (TL/Distribution) | 643560.85 | 0 | 643560.85 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 107956 | 745856 | FAASt [Automation Program Group 14] (TL/Distribution) | 1640186.96 | 0 | 1640186.96 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 107957 | 745861 | FAASt [Automation Program Group 12] (TL/Distribution) | 3664210.1 | 0 | 3664210.1 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11721 | 178258 | FAASt - [Taft - MC 1105] (Substations) | 9362729.93 | 4123842.4 | 13486572.33 | Substation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 108070 | 790443 | FAASt [Pole and Conductor Repair -San Juan Group 3 Phase 2 (Distribution) | 186697 | 0 | 186697 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 108035 | 757692 | FAASt [Automation Program Group 26] (TL / Distribution) | 938783.6333 | 0 | 938783.6333 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11859 | 551963 | FAASt [Transport Network Group 1] (Telecommunication) | 5490296.8889 |  | 5490296.8889 | Telecommunications | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 108157 | 956349 | FAASt [San Juan Region 1 Line 36800 (115kV) – Canovanas TC to Palmer TC] (Vegetation) | 1364416.1222 |  | 1364416.1222 | Vegetation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 108159 | 956356 | FAASt [Ponce Region 6 Line 39000 (115kV) – Aguas Buenas Substation to Hacienda San Jose] (Vegetation) | 86484.8 | 302418.26 | 388903.06 | Vegetation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 107999 | 752540 | FAASt [Pole and Conductor Repair -Mayaguez Group 4 Phase 2] (Distribution) | 7111613.9111 |  | 7111613.9111 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 107918 | 735474 | FAASt [Pole and Conductor Repair -Caguas Group 3 Phase 2] (Distribution) | 14075641.4222 |  | 14075641.4222 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 107979 | 750692 | FAASt [Pole and Conductor Repair - Mayaguez Group 3 - Phase 2] (Distribution) | 12921047 |  | 12921047 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 107779 | 682645 | FAASt [Maunabo TC] (Substation) | 8292124.9556 |  | 8292124.9556 | Substation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 108134 | 825843 | FAASt [Guanica TC] (Substation) | 2320373.9667 |  | 2320373.9667 | Substation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 108102 | 812569 | FAASt [Feeder Rebuild 3502-02] (Distribution) | 10217566.5444 |  | 10217566.5444 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 108119 | 817956 | FAASt [Feeder Rebuild # 1303-02] (Distribution) | 2054461.7889 |  | 2054461.7889 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 108161 | 956593 | FAASt [Factor Sect 8014 Transformer Replacement] (Substation) | 3751193.6333 |  | 3751193.6333 | Substation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 108163 | 957578 | FAASt [Costa Sur TC Underground Cable Failure Replacement on Transformer Lead Bank #2] (Substation) | 1108989.5111 |  | 1108989.5111 | Substation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 108078 | 800361 | FAASt [Automation Program Group 37] (Distribution) | 1596192.7333 |  | 1596192.7333 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 108041 | 757700 | FAASt [Automation Program Group 35] (TL / Distribution) | 1318515.6667 |  | 1318515.6667 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 108039 | 757698 | FAASt [Automation Program Group 33] (Distribution) | 1888928.2111 |  | 1888928.2111 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 108038 | 757697 | FAASt [Automation Program Group 32] (TL / Distribution) | 1996678.5889 |  | 1996678.5889 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 108037 | 757696 | FAASt [Automation Program Group 31] (Distribution) | 1145457.6111 |  | 1145457.6111 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 108036 | 757694 | FAASt [Automation Program Group 27] (Distribution) | 2314733.7889 |  | 2314733.7889 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 108034 | 757689 | FAASt [Automation Program Group 24] (TL/ Distribution) | 1774822.4 |  | 1774822.4 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 108153 | 956342 | FAASt [Arecibo Region 2 Line 36400 (115Kv) – Ponce TC to Dos Bocas HP] (Vegetation) | 4093248.3889 |  | 4093248.3889 | Vegetation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 108158 | 956353 | FAASt [Arecibo Region 2 Line 36100 (115kV) – Dos Bocas HP to Barrio Pina] (Vegetation) | 3756065.0889 |  | 3756065.0889 | Vegetation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 108074 | 797148 | FAASt [Feeder Rebuild # 8101-03] (Distribution) | 2359895.6333 |  | 2359895.6333 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 108075 | 798275 | FAASt [Feeder Rebuild # 1620-02] (Distribution) | 6711420.9 |  | 6711420.9 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 108083 | 801172 | FAASt [Feeder Rebuild # 1529-15] (Distribution) | 2285961.1333 |  | 2285961.1333 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 108077 | 800286 | FAASt [Automation Program Group 36] (TL / Distribution) | 1703712.8333 |  | 1703712.8333 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 108010 | 753782 | FAASt [Priority Pole Replacement Program (Line 3100 Monacillos TC – Sabana Llana TC)] (Transmission) | 129361.9267 | 2218.84 | 131580.7667 | Transmission | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 108032 | 757662 | FAASt [Automation Program Group 21] (Distribution) | 1710547.9444 |  | 1710547.9444 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 108033 | 757687 | FAASt [Automation Program Group 22] (Distribution) | 2356733.8778 |  | 2356733.8778 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11452 | 673292 | FAASt Telecom Infrastructure - Cerro Puntas (Telecommunication) | 8124106.79 | 49577.82 | 8173684.61 | Telecommunications | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11307 | 167446 | FAASt - Line 36100 (115kV) - Bayamon to Monacillos (Transmission) | 33956314.5889 | 0 | 33956314.5889 | Transmission | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11432 | 176913 | FAASt [Palo Seco SP to Catano Sect 38kV Line- 9500] (Transmission) | 33526671.8667 | 0 | 33526671.8667 | Transmission | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11373 | 176971 | FAASt –38kV Line 8200 - San Juan SP to Catano Sect Line (Transmission) | 21670623.7889 | 0 | 21670623.7889 | Transmission | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11453 | 180052 | FAASt Ponce TC to Salinas Urbano TC- 38kV 100 & 200 (Transmission) | 74520098.4889 | 0 | 74520098.4889 | Transmission | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11708 | 334470 | FAASt [TL 3100 Monacillos TC to Sabana Llana TC] (Transmission) | 47112099.9222 | 0 | 47112099.9222 | Transmission | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11425 | 678800 | FAASt [Telecom Infrastructure – Group B] (Telecommunication) | 13148929.4489 | 55895.84 | 13204825.2889 | Telecommunications | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11877 | 749072 | FAASt [Priority Pole Replacement Program (Line 2700 Aguadilla Hospital Distrito Sect – Mora TC)] (Transmission) | 767377.79 | 59629.81 | 827007.6 | Transmission | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 107970 | 750150 | FAASt [Priority Pole Replacement Program (Line 4800 Santa Isabel TC – Toro Negro 1 HP)] (Transmission) | 125923.5667 | 8224.8 | 134148.3667 | Transmission | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 108040 | 757699 | FAASt [Automation Program Group 34] (Distribution) | 2755939 | 0 | 2755939 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 107972 | 750168 | FAASt [Priority Pole Replacement Program (Line 4800 Santa Isabel TC – Aibonito TO)] (Transmission) | 431757.16 | 37472.84 | 469230 | Transmission | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 108082 | 801166 | FAASt [Feeder Rebuild # 6601-03] (Distribution) | 19826783.47 | 0 | 19826783.47 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 107971 | 750151 | FAASt [Priority Pole Replacement Program (Line 700 Costa Sur SP – Yauco 2 HP)] (Transmission) | 243268.16 | 12563.87 | 255832.03 | Transmission | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11840 | 711819 | FAASt [Transmission Priority Pole Replacement Program Line 13400 San German Sect-La Parguera Sect] (Transmission) | 2202286.53 | 197625.13 | 2399911.66 | Transmission | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 107892 | 727522 | FAASt [Region 3 Bayamon TL - 115kV] (Vegetation) | 778850.12 | 2663231.73 | 3442081.85 | Vegetation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 107893 | 727529 | FAASt [Region 6 Ponce TL - 115kV] (Vegetation) | 1879368.2 | 6426387.93 | 8305756.13 | Vegetation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11720 | 727572 | FAASt [Region 3 -Bayamon Group A] High Density (Vegetation) | 11268772.7 | 31317875.94 | 42586648.64 | Vegetation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | To verify w/ LUMA
| 107898 | 727606 | FAASt [Region 4 Caguas TL - 115kV] (Vegetation) | 900812.92 | 3080276.26 | 3981089.18 | Vegetation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 107899 | 727608 | FAASt [Region 1 San Juan TL - 115kV] (Vegetation) | 1007797.83 | 3446104.8 | 4453902.63 | Vegetation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 107900 | 727657 | FAASt [Region 5 Mayaguez TL - 115kV] (Vegetation) | 577718.5 | 1975474.09 | 2553192.59 | Vegetation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 107901 | 727659 | FAASt [Region 2 Arecibo TL - 115kV] (Vegetation) | 953592.14 | 3260751.68 | 4214343.82 | Vegetation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 107946 | 741105 | FAASt [All Regions TL - 230kV] (Vegetation) | 2430054.31 | 10455751.16 | 12885805.47 | Vegetation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11874 | 749060 | FAASt [Transmission Priority Pole Replacement Program Line 5600 Victoria TC – Añasco TC] (Transmission) | 1175435.49 | 140677.54 | 1316113.03 | Transmission | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11630 | 714641 | FAASt [Rincón Streetlighting] (Distribution) | 10842339.26 | 694470.58 | 11536809.84 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | To verify w/ LUMA
| 11807 | 547251 | FAASt Line 2400 Dos Bocas HP to America Apparel (Transmission) | 50289473.6889 | 0 | 50289473.6889 | Telecommunication | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 107735 | 551926 | FAASt [SCADA Remote Access and RTU Replacements Group 2] (Telecommunication) | 5267467.99 | 1073462.61 | 6340930.6 | Transmission | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 107966 | 750065 | FAASt [Region 3 -Bayamon Group A] Low Density (Vegetation) | 18569923.87 | 51603800.04 | 70173723.91 | Vegetation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | To verify w/ LUMA
| 107967 | 750066 | FAASt [Region 4 -Caguas Group A] Low Density (Vegetation) | 28466485.03 | 79097232.76 | 107563717.79 | Vegetation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | To verify w/ LUMA
| 107968 | 750067 | FAASt [Region 2 -Arecibo Group A] Low Density (Vegetation) | 15030146.18 | 41767142.56 | 56797288.74 | Vegetation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | To verify w/ LUMA
| 107969 | 750068 | FAASt [Region 5 -Mayaguez Group A] Low Density (Vegetation) | 13840548.75 | 38461380.62 | 52301929.37 | Vegetation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | To verify w/ LUMA
| 107959 | 746309 | FAASt [Automation Program Group 30] (Distribution) | 327791.49 | 236273.14 | 564064.63 | Distribution | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| Total LUMA Obligated |  |  | 2195598436.3767 | 734994220.48 | 2764540523.6978 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
LUMA child under formulation
| PW | GM | Project Name | 428 | 406 | Total Child | Asset | 428 Cons | 428 from 9510 | 428 from 10710 | Total 428 | 406 from 9510 | 406 from 10710 | New 406 | Total 406 |  | Total Project | Diff | Comments
| 107206 | 165226 | FAASt [Feeders Vieques & Culebra] (Distribution) | 72211568.14 | 12438987.09 | 84650555.23 | Vieques and Culebra Projects | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 107220 | 169058 | FAASt - Llorens Torres MC 1106 - Equipment Repair & Replacement - (Substations) | 18279001 |  | 18279001 | Substation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 107222 | 169276 | FAASt Substation - Viaducto TC - MC 1100 - Equipment Repair & Replacement (Substation) | 20425907 |  | 20425907 | Substation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11507 | 178577 | FAASt [Cachete – MC 1526] (Substations) | 27557980.5 | 16340158.71 | 43898139.21 | Substation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 107690 | 547187 | FAASt - [Substation Component Replacement Program] (Substation) | 4790316.92 |  | 4790316.92 | Substation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 107714 | 550106 | FAASt [Conquistador CH] (Substation) | 11639958 |  | 11639958 | Substation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11470 | 551914 | FAASt [Caparra 1912 & 1924] (Substation) | 9297455.97 | 5838512.8 | 15135968.77 | Substation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11876 | 682328 | FAASt [Bayamón TC - Rebuild] (Substation) | 2637502.74 |  | 2637502.74 | Substation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 108145 | 956330 | FAASt [Caguas Region 4 - Feeder 3007-03] (Vegetation) | 1914845.33 | 5681119.27 | 7595964.6 | Vegetation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 108146 | 956331 | FAASt [Mayaguez Region 5 Feeder 6014-02] (Vegetation) | 1813962.21 | 5381811.02 | 7195773.23 | Vegetation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 108147 | 956332 | FAASt [San Juan Region 1 - Feeder 2401-01] (Vegetation) | 2664861.34 | 7906327.92 | 10571189.26 | Vegetation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 108148 | 956335 | FAASt [San Juan Region 1 - Feeder 2301-02] (Vegetation) | 1798813.63 | 5336866.97 | 7135680.6 | Vegetation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 108149 | 956337 | FAASt [Mayaguez Region 5 Feeder 6012-02] (Vegetation) | 1378198.73 | 4088952.37 | 5467151.1 | Vegetation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 108150 | 956339 | FAASt [Caguas Region 4 - Feeder 3301-01] (Vegetation) | 2887255.43 | 8566144.83 | 11453400.26 | Vegetation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 108151 | 956340 | FAASt [Ponce Region 6 Feeder 5602-02] (Vegetation) | 1210919.69 | 3592655.29 | 4803574.98 | Vegetation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 108152 | 956341 | FAASt [Ponce Region 6 Feeder 5803-02] (Vegetation) | 23528.65 | 69806.72 | 93335.37 | Vegetation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 108154 | 956343 | FAASt [Ponce Region 6 Line 4800 – Toro Negro to Aibonito, Santa Isabel] (Vegetation) | 183092.65 | 2178489.85 | 2361582.5 | Vegetation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 108155 | 956345 | FAASt [Arecibo Region 2 Line 2400 – Dos Bocas HP to Coronillas 2] (Vegetation) | 53038.75 | 631070.47 | 684109.22 | Vegetation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 108156 | 956348 | FAASt [Bayamon Region 3 Line 10000 – Bayamon Pueblo to Magnolia TO] (Vegetation) | 8718.69 | 103737.61 | 112456.3 | Vegetation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 108160 | 956357 | FAASt [Mayaguez Region 5 Line 1900 – Dos Bocas HP to San Sebastian TC] (Vegetation) | 153906.79 |  | 153906.79 | Vegetation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11241 | 168483 | FAASt - 115kV Line 36400 - Dos Bocas HP to Ponce TC (Transmission) | 106895316 | 8111071 | 115006387 | Transmission | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 107888 | 723002 | FAASt - EPC - Jobos TC (Substation) | 70586386.39 |  | 70586386.39 | Substation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 108030 | 756997 | FAASt [TL 1900 Caguanas to Lares TO] (Transmission) | 40557533.61 |  | 40557533.61 | Transmission | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 108031 | 756999 | FAASt [TL 1900 Lares TO to San Sebastian] (Transmission) | 29319358.78 |  | 29319358.78 | Transmission | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 107965 | 750063 | FAASt [Region 6 -Ponce Group A] Low Density (Vegetation) | 15889515.9 | 44155237.62 | 60044753.52 | Vegetation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | To verify w/ LUMA
| 11244 | 165213 | FAASt – Line 5400 – Rio Blanco HP to Daguao TC to Punta Lima TO to Vieques 2501 to Culebra 3801 (Transmission) | 83734340.49 | 33182392.65 | 116916733.14 | Vieques and Culebra Projects | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 107982 | 751655 | FAASt [Vieques Microgrid] (Transmission) | 0 | 105481956 | 105481956 | Vieques and Culebra Projects | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 107983 | 751656 | FAASt [Culebra Microgrid] (Transmission) | 0 | 39954081 | 39954081 | Vieques and Culebra Projects | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 107742 | 662238 | FAASt [Microwave Point-to-Point Backbone] (Telecommunications) | 14142413.06 | 3014559.92 | 17156972.98 | Telecommunication | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 11824 | 746545 | FAASt [Primary Control Center / Secondary Data Center & Control Room] (Telecommunication) | 115638378 | 15530896 | 131169274 | Telecommunication | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 107960 | 746660 | FAASt [Minor Protection, Automation, and Control [PAC] Replacement] (Substation) | 15096658.56 | 1617375.6 | 16714034.16 | Substation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
| 108242 | 1064452 | FAASt [Priority Pole Replacement Program Line 800 Comsat Sect – Cidra Sect] / Former project 753781 | 726192.42 | 33695.78 | 759888.2 | Transmission | 726192.42 | 0 | 0 | 726192.42 | 0 | 0 | 33695.78 | 33695.78 |  | 759888.2 | 793583.98 | Not included in LUMAs Report
|  | 176954 | FAASt Garzas 1 HP to Garzas 2 HP - 38kV Line 1100 (Transmission) | 3362636 | 4127356 | 7489992 |  | 3362636 | [5 empty] | 4127356 | 4127356 |  | 8254712 |  | New Project - To revise Cost w/ LUMA certifications
|  | 547344 | FAASt [Acacias 6801 TC Relocation] (Substation) | 8874442.51 | 42895135.02 | 51769577.53 |  | 8874442.51 | [5 empty] | 42895135.02 | 42895135.02 |  | 85790270.04 |  | New Project - To revise Cost w/ LUMA certifications
|  | 551260 | Guaynabo Pueblo Substation | 22381506.84 | 10941966.54 | 33323473.38 |  | 22381506.84 | [5 empty] | 10941966.54 | 10941966.54 |  | 21883933.08 |  | New Project - To revise Cost w/ LUMA certifications
|  | 551927 | 551927 SCADA Remote Access and RTU Replacements Group 3 | 19213188.6 | 3299617.88 | 22512806.48 |  | 19213188.6 | [5 empty] | 3299617.88 | 3299617.88 |  | 6599235.76 |  | New Project - To revise Cost w/ LUMA certifications
|  | 757945 | FAASt [Pole and Conductor Repair - Arecibo Group 3 - Phase 2] (Distribution) | 2892589.5 | 15039.03 | 2907628.53 |  | 2892589.5 | [5 empty] | 15039.03 | 15039.03 |  | 30078.06 |  | New Project - To revise Cost w/ LUMA certifications
|  | 790427 | FAASt [Pole and Conductor Repair -Caguas Group 5 Phase 2 (Distribution) | 9241836.74 | 71738.97 | 9313575.71 |  | 9241836.74 | [5 empty] | 71738.97 | 71738.97 |  | 143477.94 |  | New Project - To revise Cost w/ LUMA certifications
|  | 790446 | FAASt [Pole and Conductor Repair -Caguas Group 4 Phase 2 (Distribution) | 4662521.3 | 28582.12 | 4691103.42 |  | 4662521.3 | [5 empty] | 28582.12 | 28582.12 |  | 57164.24 |  | New Project - To revise Cost w/ LUMA certifications
|  | 806935 | FAASt [Pole and Conductor Repair - Caguas Group 6 - Phase 2] (Distribution) | 6120000 | 0 | 6120000 |  | 6120000 | [5 empty] | 0 | 0 |  | 0 |  | New Project - To revise Cost w/ LUMA certifications
|  | 811923 | Transmission Priority Pole Replacement Program Line 16500 Fajardo TC-Dos Marinas] (Transmission) | 260238.98 | 22761.43 | 283000.41 |  | 260238.98 | [5 empty] | 22761.43 | 22761.43 |  | 45522.86 |  | New Project - To revise Cost w/ LUMA certifications
| Total LUMA under formulation |  |  | 673516925.37 | 329235906.49 | 1010242823.86 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF!
LUMA child Exhibit A (70)
| PW | GM | Project Name | 428 | 406 | Total Child | Asset | 428 Cons | 428 from 9510 | 428 from 10710 | Total 428 | 406 from 9510 | 406 from 10710 | New 406 | Total 406 |  | Total Project | Diff | Comments
| 11519 | 666894 | FAASt [San Juan Streetlighting] (Distribution) |  |  |  | 70 Projects | 27201946.76 | 6380570.04 | 976071 | 34558587.8 | 123157.52 | 658009 | 1465463.21 | 2246629.73 | 0 | 36805217.53
| 11527 | 678794 | FAASt [Ponce Streetlighting] (Distribution) |  |  |  | 70 Projects | 10629532.275 | 1713141.92 | 339183 | 12681857.195 | 51717 | 228657 | 655524.41 | 935898.41 | 0 | 13617755.605
| 107884 | 718971 | FAASt [Line 50300 (230kV) from Costa Sur Steam Plant to Aguirre Steam Plant] (Transmission) |  |  |  | 70 Projects | 9936000 | 864000 | 1296000 | 12096000 | 864000 | 3240000 | 5400000 | 9504000 | 0 | 21600000
| 11552 | 690483 | FAASt [Cayey Streetlighting] (Distribution) |  |  |  | 70 Projects | 10093033.82 | 2435204.39 | 503757 | 13031995.21 | 95954.76 | 339603 | 936114.24 | 1371672 | 0 | 14403667.21
| 11576 | 699814 | FAASt [Juana Diaz Streetlighting] (Distribution) |  |  |  | 70 Projects | 13267153.655 | 2795912.01 | 744597 | 16807662.665 | 55146.97 | 501963 | 370784.53 | 927894.5 | 0 | 17735557.165
| 11651 | 704931 | FAASt [Camuy Streetlighting] (Distribution) |  |  |  | 70 Projects | 13069359.5825 | 1972441.141 | 958677 | 16000477.7235 | 107984.699 | 646283 | 220906.9 | 975174.599 | 0 | 16975652.3225
| 11728 | 704862 | FAASt [Fajardo Streetlighting] (Distribution) |  |  |  | 70 Projects | 10758153.95 | 2150579.88 | 315768 | 13224501.83 | 58676.25 | 212872 | 839531.97 | 1111080.22 | 0 | 14335582.05
| 11535 | 678795 | FAASt [Arecibo Streetlighting] (Distribution) |  |  |  | 70 Projects | 11412143.0925 | 1902215.74 | 466962 | 13781320.8325 | 59360 | 314798 | 485336.36 | 859494.36 | 0 | 14640815.1925
| 11638 | 704757 | FAASt [Santa Isabel Streetlighting] (Distribution) |  |  |  | 70 Projects | 8241015.33 | 1562084.58 | 284994 | 10088093.91 | 22536.63 | 192126 | 190912.38 | 405575.01 | 0 | 10493668.92
| 11530 | 671396 | FAASt [Utuado Streetlighting] (Distribution) |  |  |  | 70 Projects | 15515918.205 | 3319870.72 | 1245009 | 20080797.925 | 155072.6 | 839311 | 2012364.47 | 3006748.07 | 0 | 23087545.995
| 107781 | 688623 | FAASt [Automation Program Group 1A] (Distribution) |  |  |  | 70 Projects | 3591270 | 332525 | 465535 | 4389330 | 199515 | 931070 | 1130585 | 2261170 | 0 | 6650500
| 11684 | 724603 | FAASt [Cabo Rojo Streetlighting] (Distribution) |  |  |  | 70 Projects | 6954788.08 | 1689593.17 | 353232 | 8997613.25 | 41489.51 | 238128 | 279702.31 | 559319.82 | 0 | 9556933.07
| 11693 | 701473 | FAASt [Canovanas Streetlighting] (Distribution) |  |  |  | 70 Projects | 11399484.83 | 2377385.56 | 595410 | 14372280.39 | 89359.81 | 401390 | 1119131.43 | 1609881.24 | 0 | 15982161.63
| 11634 | 693543 | FAASt [Juncos Streetlighting] (Distribution) |  |  |  | 70 Projects | 10405292.6975 | 1631297.312 | 589389 | 12625979.0095 | 26436.06 | 397331 | 287804.01 | 711571.07 | 0 | 13337550.0795
| 11529 | 671400 | FAASt [Barceloneta Streetlighting] (Distribution) |  |  |  | 70 Projects | 7024652.0375 | 1206563.5 | 397386 | 8628601.5375 | 50306 | 267894 | 209975.14 | 528175.14 | 0 | 9156776.6775
| 11547 | 693788 | FAASt [Toa Alta Streetlighting] (Distribution) |  |  |  | 70 Projects | 4596792.52 | 1162797.94 | 170595 | 5930185.46 | 17891.57 | 115005 | 82066.81 | 214963.38 | 0 | 6145148.84
| 11668 | 697183 | FAASt [Vega Baja Streetlighting] (Distribution) |  |  |  | 70 Projects | 8233261.46 | 1621313.74 | 369288 | 10223863.2 | 17891.57 | 248952 | 807899.66 | 1074743.23 | 0 | 11298606.43
| 11531 | 690721 | FAASt [Guayama Streetlighting] (Distribution) |  |  |  | 70 Projects | 3974160.015 | 1011463.98 | 133131 | 5118754.995 | 25642.92 | 89749 | 215693.59 | 331085.51 | 0 | 5449840.505
| 11523 | 698432 | FAASt [Hormigueros Streetlighting] (Distribution) |  |  |  | 70 Projects | 5694746.915 | 1362869.66 | 304395 | 7362011.575 | 17724.97 | 205205 | 284606.44 | 507536.41 | 0 | 7869547.985
| 11683 | 690480 | FAASt [Humacao Streetlighting] (Distribution) |  |  |  | 70 Projects | 6175629.8825 | 1006696.36 | 279642 | 7461968.2425 | 29209 | 188518 | 299807.81 | 517534.81 | 0 | 7979503.0525
| 11572 | 686482 | FAASt [Isabela Streetlighting] (Distribution) |  |  |  | 70 Projects | 5745883.39 | 1332970.6 | 259572 | 7338425.99 | 37797.8 | 174988 | 496924.08 | 709709.88 | 0 | 8048135.87
| 107978 | 750503 | FAASt [25 MW BESS Installation and Integration - San Juan] (Substation) |  |  |  | 70 Projects | 0 | 0 | 0 | 0 | 3187811.29 | 28261718.24 | 24053536.03 | 55503065.56 | 0 | 55503065.56
| 107977 | 750502 | FAASt [25 MW BESS Installation and Integration - Aguadilla] (Substation) |  |  |  | 70 Projects | 0 | 0 | 0 | 0 | 3340630.47 | 28261718.24 | 21118171.64 | 52720520.35 | 0 | 52720520.35
| 108002 | 752972 | FAASt [4 x 25 MW BESS Interconnections Manati] (Substation) |  |  |  | 70 Projects | 0 | 0 | 0 | 0 | 3414922.97 | 30416253.08 | 23808829.62 | 57640005.67 | 0 | 57640005.67
| 108015 | 754350 | FAASt [Underground Circuit Feeders - San Juan Group 1] (Distribution) |  |  |  | 70 Projects | 4310111.715 | 362956.776 | 1512.3199 | 4674580.8109 | 812115.7863 | 58980.4761 | 9577521.9267 | 10448618.1891 | 0 | 15123199
| 11819 | 738671 | FAASt [25 MW BESS Installation and Integration - Barceloneta] (Substation) |  |  |  | 70 Projects | 0 | 0 | 0 | 0 | 5211394.35 | 30411453.8 | 20318919.35 | 55941767.5 | 0 | 55941767.5
| 108016 | 754351 | FAASt [Underground Circuit Feeders - San Juan Group 2] (Distribution) |  |  |  | 70 Projects | 2013990.405 | 169599.192 | 706.6633 | 2184296.2603 | 379478.1921 | 27559.8687 | 4475298.6789 | 4882336.7397 | 0 | 7066633
| 107961 | 748180 | FAASt Transm. Advanced Sensors and Wide-Area Monitoring, Protection, and Control (WAMPAC) System (Telecommunication) |  |  |  | 70 Projects | 33071971.884 | 4724567.412 | 3307197.1884 | 41103736.4844 | 472456.7412 | 1417370.2236 | 4086750.8114 | 5976577.7762 | 0 | 47080314.2606
| 107995 | 752277 | FAASt [Substation Ciales 8701] (Substation) |  |  |  | 70 Projects | 3553830.9091 | 349557.1386 | 466076.1848 | 4369464.2325 | 116519.0462 | 815633.3234 | 524335.7079 | 1456488.0775 | 0 | 5825952.31
| 107902 | 727691 | FAASt [Region 1 -San Juan Group C] (Vegetation) |  |  |  | 70 Projects | 1313961.65 | 11049.14 | 0 | 1325010.79 | 121275.67 | 0 | 14439457.84 | 14560733.51 | 0 | 15885744.3
| 107933 | 740406 | FAASt [Region 1-San Juan Group B] (Vegetation) |  |  |  | 70 Projects | 281345.36 | 2365.85 | 0 | 283711.21 | 25967.52 | 0 | 3091775.16 | 3117742.68 | 0 | 3401453.89
| 107936 | 740410 | FAASt [Region 2-Arecibo Group B] (Vegetation) |  |  |  | 70 Projects | 251201.23 | 2112.36 | 0 | 253313.59 | 23185.29 | 0 | 2760513.52 | 2783698.81 | 0 | 3037012.4
| 107935 | 740409 | FAASt [Region 4-Caguas Group B] (Vegetation) |  |  |  | 70 Projects | 715385.11 | 6015.7 | 0 | 721400.81 | 66028.4 | 0 | 7927576.7 | 7993605.1 | 0 | 8715005.91
| 107938 | 740414 | FAASt [Region 6-Ponce Group B] (Vegetation) |  |  |  | 70 Projects | 799358.09 | 6721.82 | 0 | 806079.91 | 73778.93 | 0 | 8784348.55 | 8858127.48 | 0 | 9664207.39
| 107903 | 727694 | FAASt [Region 4 -Caguas Group C] (Vegetation) |  |  |  | 70 Projects | 729380.61 | 6133.39 | 0 | 735514 | 67320.16 | 0 | 8015348.33 | 8082668.49 | 0 | 8818182.49
| 107937 | 740411 | FAASt [Region 5-Mayaguez Group B] (Vegetation) |  |  |  | 70 Projects | 141749.28 | 1191.98 | 0 | 142941.26 | 13083.11 | 0 | 1557718.3 | 1570801.41 | 0 | 1713742.67
| 107897 | 727562 | FAASt [Region 5 -Mayaguez Group C] (Vegetation) |  |  |  | 70 Projects | 2053569.7 | 17268.5 | 0 | 2070838.2 | 189539.83 | 0 | 22567198.56 | 22756738.39 | 0 | 24827576.59
| 107894 | 727530 | FAASt [Region 6 -Ponce Group C] (Vegetation) |  |  |  | 70 Projects | 2278394.76 | 19159.06 | 0 | 2297553.82 | 210290.68 | 0 | 25037858.23 | 25248148.91 | 0 | 27545702.73
| 107895 | 727540 | FAASt [Region 2 -Arecibo Group C] (Vegetation) |  |  |  | 70 Projects | 1842560.72 | 15494.13 | 0 | 1858054.85 | 170064.17 | 0 | 20248367.13 | 20418431.3 | 0 | 22276486.15
| 107934 | 740408 | FAASt [Region 3-Bayamon Group B] (Vegetation) |  |  |  | 70 Projects | 666580.3 | 5605.29 | 0 | 672185.59 | 61523.84 | 0 | 7325219.95 | 7386743.79 | 0 | 8058929.38
| 107896 | 727558 | FAASt [Region 3 -Bayamon Group C] (Vegetation) |  |  |  | 70 Projects | 1322933.13 | 11124.57 | 0 | 1334057.7 | 122103.73 | 0 | 14538047.6 | 14660151.33 | 0 | 15994209.03
| 107939 | 740662 | FAASt [Automation Program Group 2] (Distribution) |  |  |  | 70 Projects | 21843000 | 2022500 | 2831500 | 26697000 | 1213500 | 5663000 | 6876500 | 13753000 | 0 | 40450000
| 107947 | 741678 | FAASt [Automation Program Group 4] (Distribution) |  |  |  | 70 Projects | 16985160 | 1572700 | 2201780 | 20759640 | 943620 | 4403560 | 5347180 | 10694360 | 0 | 31454000
| 107826 | 705657 | FAASt [Automation Program Group 3] (Distribution) |  |  |  | 70 Projects | 13656870 | 1264525 | 1770335 | 16691730 | 758715 | 3540670 | 4299385 | 8598770 | 0 | 25290500
| 11559 | 730657 | FAASt [Line 2200 Dos Bocas HP to Dorado TC ] (Transmission) |  |  |  | 70 Projects | 57872010.7354 | 5032348.7596 | 7548523.1394 | 70452882.6344 | 5032348.7596 | 18871307.8485 | 31452179.7475 | 55355836.3556 | 0 | 125808718.99
| 11691 | 704793 | FAASt [Yauco Streetlighting] (Distribution) |  |  |  | 70 Projects | 12597812.93 | 2540431.6 | 634212 | 15772456.53 | 79529.34 | 427548 | 1160589.76 | 1667667.1 | 0 | 17440123.63
| 11626 | 704744 | FAASt [San Sebastian Streetlighting] (Distribution) |  |  |  | 70 Projects | 19955144.585 | 4057973.95 | 1566129 | 25579247.535 | 94811.81 | 1055791 | 486338.95 | 1636941.76 | 0 | 27216189.295
| 107780 | 685869 | FAASt [Mayagüez TC] (Substation) |  |  |  | 70 Projects | 22073642.86 | 2605555.14 | 13511059.91 | 38190257.91 | 53174.57 | 183120 | 543426.36 | 779720.93 | 0 | 38969978.84
| 108058 | 764707 | FAASt [Feeder Rebuild # 6012-02] (Distribution) |  |  |  | 70 Projects | 16634520 | 5062680 | 1446480 | 23143680 | 241080 | 241080 | 482160 | 964320 | 0 | 24108000
| 108056 | 764705 | FAASt [Feeder Rebuild # 6014-02] (Distribution) |  |  |  | 70 Projects | 23763600 | 7232400 | 2066400 | 33062400 | 344400 | 344400 | 688800 | 1377600 | 0 | 34440000
| 11635 | 704929 | FAASt [San Lorenzo Streetlighting] (Distribution) |  |  |  | 70 Projects | 12867034.6125 | 2944605.83 | 920544 | 16732184.4425 | 60896.29 | 620576 | 347830.72 | 1029303.01 | 0 | 17761487.4525
| 11692 | 724828 | FAASt [Loiza Streetlighting] (Distribution) |  |  |  | 70 Projects | 5936181.88 | 1248099.37 | 276966 | 7461247.25 | 14137.5 | 186714 | 201637.58 | 402489.08 | 0 | 7863736.33
| 11582 | 698522 | FAASt [Vieques Streetlighting] (Distribution) |  |  |  | 70 Projects | 3791271.0575 | 810226.05 | 196686 | 4798183.1075 | 32120.4 | 132594 | 322022.91 | 486737.31 | 0 | 5284920.4175
| 11685 | 693615 | FAASt [Rio Grande Streetlighting] (Distribution) |  |  |  | 70 Projects | 5156073.42 | 1156399.63 | 191334 | 6503807.05 | 21533.62 | 128986 | 268046.05 | 418565.67 | 0 | 6922372.72
| 11525 | 698427 | FAASt [Maricao Streetlighting] (Distribution) |  |  |  | 70 Projects | 4466381.615 | 926826.7734 | 406752 | 5799960.3884 | 43337.3166 | 274208 | 647106.71 | 964652.0266 | 0 | 6764612.415
| 11733 | 724941 | FAASt [Aguas Buenas Streetlighting] (Distribution) |  |  |  | 70 Projects | 11340397.36 | 2036460.34 | 693084 | 14069941.7 | 0 | 467236 | 201510.89 | 668746.89 | 0 | 14738688.59
| 11737 | 704741 | FAASt [Moca Streetlighting] (Distribution) |  |  |  | 70 Projects | 17932518.84 | 3152500.55 | 1190151 | 22275170.39 | 0 | 802329 | 308495.64 | 1110824.64 | 0 | 23385995.03
| 11732 | 724605 | FAASt [Guayanilla Streetlighting] (Distribution) |  |  |  | 70 Projects | 7795083.32 | 1372729.11 | 424146 | 9591958.43 | 0 | 285934 | 183970.54 | 469904.54 | 0 | 10061862.97
| 11738 | 724599 | FAASt [Sabana Grande Streetlighting] (Distribution) |  |  |  | 70 Projects | 10754272.51 | 1906868.06 | 725196 | 13386336.57 | 0 | 488884 | 236814.37 | 725698.37 | 0 | 14112034.94
| 11730 | 724669 | FAASt [Ciales Streetlighting] (Distribution) |  |  |  | 70 Projects | 12013750.42 | 2044738.82 | 741921 | 14800410.24 | 0 | 500159 | 272974.74 | 773133.74 | 0 | 15573543.98
| 11729 | 724716 | FAASt [Quebradillas Streetlighting] (Distribution) |  |  |  | 70 Projects | 10502157.5 | 1872541.02 | 642240 | 13016938.52 | 0 | 432960 | 195150.03 | 628110.03 | 0 | 13645048.55
| 11624 | 713795 | FAASt [Lares Streetlighting] (Distribution) |  |  |  | 70 Projects | 11882095.1 | 1974624.75 | 733893 | 14590612.85 | 0 | 494747 | 217275.01 | 712022.01 | 0 | 15302634.86
| 11731 | 724670 | FAASt [Patillas Streetlighting] (Distribution) |  |  |  | 70 Projects | 8408428.82 | 1456883.53 | 425484 | 10290796.35 | 0 | 286836 | 119750.59 | 406586.59 | 0 | 10697382.94
| 11736 | 724781 | FAASt [Penuelas Streetlighting] (Distribution) |  |  |  | 70 Projects | 7929864.73 | 1433020.87 | 398055 | 9760940.6 | 0 | 268345 | 140145.41 | 408490.41 | 0 | 10169431.01
| 107940 | 741097 | FAASt [Region 1 San Juan Subs/Telecom] (Vegetation) |  |  |  | 70 Projects | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 107941 | 741098 | FAASt [Region 3 Bayamon Subs/Telecom] (Vegetation) |  |  |  | 70 Projects | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 107944 | 741102 | FAASt [Region 5 Mayaguez Subs/Telecom] (Vegetation) |  |  |  | 70 Projects | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 107943 | 741101 | FAASt [Region 2 Arecibo Subs/Telecom] (Vegetation) |  |  |  | 70 Projects | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 107945 | 741104 | FAASt [Region 6 Ponce Subs/Telecom] (Vegetation) |  |  |  | 70 Projects | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 107942 | 741100 | FAASt [Region 4 Caguas Subs/Telecom] (Vegetation) |  |  |  | 70 Projects | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total LUMA under formulation | [6 empty] | 595423815.646 | 101270058.7045 | 56366956.4058 | 753060830.7563 | 29159565.4211 | 170203524.1003 | 317047219.3924 | 516410308.9138 |  | 1269471139.6701
LUMA child Exhibit 3 - Urgent (Incremental)
| PW | GM | Project Name | 428 | 406 | Total Child | Asset | 428 Cons | 428 from 9510 | 428 from 10710 | Total 428 | 406 from 9510 | 406 from 10710 | New 406 | Total 406 |  | Total Project | Diff | Comments
| N/A | N/A | Distribution Automation Program |  |  |  | Incrementral | 178001700 |  |  | 178001700 |  |  | 118667800 | 118667800 |  | 296669500
| N/A | N/A | Hato Rey TC Transformer Replacement |  |  |  | Incrementral | 3763775.37 |  |  | 3763775.37 |  |  | 0 | 0 |  | 3763775.37
| N/A | N/A | Venezuela TC |  |  |  | Incrementral | 2613825.35 |  |  | 2613825.35 |  |  | 0 | 0 |  | 2613825.35
| N/A | N/A | Substation Component Group 2 |  |  |  | Incrementral | 117000000 |  |  | 117000000 |  |  | 13000000 | 13000000 |  | 130000000
| N/A | N/A | Substation Component Group 3 |  |  |  | Incrementral | 279000000 |  |  | 279000000 |  |  | 31000000 | 31000000 |  | 310000000
| N/A | N/A | Substation Component Group 0 |  |  |  | Incrementral | 14145405.55 |  |  | 14145405.55 |  |  | 0 | 0 |  | 14145405.55
| N/A | N/A | 38 kV Reclosers Program |  |  |  | Incrementral | 29631317.7485 |  |  | 29631317.7485 |  |  | 16892557.4215 | 16892557.4215 |  | 46523875.17
| N/A | N/A | Arecibo Sect. Substation Rebuild |  |  |  | Incrementral | 7143527.714 |  |  | 7143527.714 |  |  | 64291749.426 | 64291749.426 |  | 71435277.14
| N/A | N/A | Chardon Sect. Substation Rebuild |  |  |  | Incrementral | 15000000 |  |  | 15000000 |  |  | 10000000 | 10000000 |  | 25000000
| N/A | N/A | FAASt [Region 1 San Juan Distribution sensitive areas] (Vegetation) |  |  |  | Vegetation | 36628489.0485 |  |  | 36628489.0485 |  |  | 100284954.5925 | 100284954.5925 |  | 136913443.641
| N/A | N/A | FAASt [Region 2 Arecibo Distribution sensitive areas] (Vegetation) |  |  |  | Vegetation | 50475597.795 |  |  | 50475597.795 |  |  | 138196883.475 | 138196883.475 |  | 188672481.27
| N/A | N/A | FAASt [Region 3 Bayamon Distribution sensitive areas] (Vegetation) |  |  |  | Vegetation | 9019432.9845 |  |  | 9019432.9845 |  |  | 24694259.8725 | 24694259.8725 |  | 33713692.857
| N/A | N/A | FAASt [Region 4 Caguas Distribution sensitive areas] (Vegetation) |  |  |  | Vegetation | 44176444.227 |  |  | 44176444.227 |  |  | 120950462.835 | 120950462.835 |  | 165126907.062
| N/A | N/A | FAASt [Region 5 Mayaguez Distribution sensitive areas] (Vegetation) |  |  |  | Vegetation | 58319872.8638 |  |  | 58319872.8638 |  |  | 159673684.4437 | 159673684.4437 |  | 217993557.3075
| N/A | N/A | FAASt [Region 6 Ponce Distribution sensitive areas] (Vegetation) |  |  |  | Vegetation | 42926595.5498 |  |  | 42926595.5498 |  |  | 117528508.4737 | 117528508.4737 |  | 160455104.0235
| N/A | N/A | 38kV Transmission Line 100 – Entire Line (Vegetation) |  |  |  | Vegetation | 428416.5893 |  |  | 428416.5893 |  |  | 4708472.9707 | 4708472.9707 |  | 5136889.56
| N/A | N/A | 38kV Transmission Line 200 – Entire Line (Vegetation) |  |  |  | Vegetation | 261066.357 |  |  | 261066.357 |  |  | 2869225.693 | 2869225.693 |  | 3130292.05
| N/A | N/A | 38kV Transmission Line 800 – Entire Line (Vegetation) |  |  |  | Vegetation | 271016.9127 |  |  | 271016.9127 |  |  | 2978586.3573 | 2978586.3573 |  | 3249603.27
| N/A | N/A | 38kV Transmission Line 1200 – Entire Line (Vegetation) |  |  |  | Vegetation | 463333.9901 |  |  | 463333.9901 |  |  | 5092229.4399 | 5092229.4399 |  | 5555563.43
| N/A | N/A | 38kV Transmission Line 1600 – Entire Line (Vegetation) |  |  |  | Vegetation | 513267.6809 |  |  | 513267.6809 |  |  | 5641021.0591 | 5641021.0591 |  | 6154288.74
| N/A | N/A | 38kV Transmission Line 2000 – Entire Line (Vegetation) |  |  |  | Vegetation | 510192.0532 |  |  | 510192.0532 |  |  | 5607218.6568 | 5607218.6568 |  | 6117410.71
| N/A | N/A | 38kV Transmission Line 2100 – Entire Line (Vegetation) |  |  |  | Vegetation | 512182.1657 |  |  | 512182.1657 |  |  | 5629090.8043 | 5629090.8043 |  | 6141272.97
| N/A | N/A | 38kV Transmission Line 2200 – Entire Line (Vegetation) |  |  |  | Vegetation | 1353456.3045 |  |  | 1353456.3045 |  |  | 14875036.5555 | 14875036.5555 |  | 16228492.86
| N/A | N/A | 38kV Transmission Line 2500 – Entire Line (Vegetation) |  |  |  | Vegetation | 409058.2383 |  |  | 409058.2383 |  |  | 4495716.8017 | 4495716.8017 |  | 4904775.04
| N/A | N/A | 38kV Transmission Line 2700 – Entire Line (Vegetation) |  |  |  | Vegetation | 688578.3557 |  |  | 688578.3557 |  |  | 7567756.8443 | 7567756.8443 |  | 8256335.2
| N/A | N/A | 38kV Transmission Line 3000 – Entire Line (Vegetation) |  |  |  | Vegetation | 825534.1669 |  |  | 825534.1669 |  |  | 9072957.0431 | 9072957.0431 |  | 9898491.21
| N/A | N/A | 38kV Transmission Line 3100 – Entire Line (Vegetation) |  |  |  | Vegetation | 1092570.8597 |  |  | 1092570.8597 |  |  | 12007799.1603 | 12007799.1603 |  | 13100370.02
| N/A | N/A | 38kV Transmission Line 3700 – Entire Line (Vegetation) |  |  |  | Vegetation | 790254.9286 |  |  | 790254.9286 |  |  | 8685223.8314 | 8685223.8314 |  | 9475478.76
| N/A | N/A | 38kV Transmission Line 3800 – Entire Line (Vegetation) |  |  |  | Vegetation | 426426.4785 |  |  | 426426.4785 |  |  | 4686600.8415 | 4686600.8415 |  | 5113027.32
| N/A | N/A | 38kV Transmission Line 4000 – Entire Line (Vegetation) |  |  |  | Vegetation | 190146.0419 |  |  | 190146.0419 |  |  | 2089782.5181 | 2089782.5181 |  | 2279928.56
| N/A | N/A | 38kV Transmission Line 4800 – Entire Line (Vegetation) |  |  |  | Vegetation | 719696.4519 |  |  | 719696.4519 |  |  | 7909757.4081 | 7909757.4081 |  | 8629453.86
| N/A | N/A | 38kV Transmission Line 5300 – Entire Line (Vegetation) |  |  |  | Vegetation | 278977.356 |  |  | 278977.356 |  |  | 3066074.874 | 3066074.874 |  | 3345052.23
| N/A | N/A | 38kV Transmission Line 5400 – Entire Line (Vegetation) |  |  |  | Vegetation | 484320.6118 |  |  | 484320.6118 |  |  | 5322880.9682 | 5322880.9682 |  | 5807201.58
| N/A | N/A | 38kV Transmission Line 5600 – Entire Line (Vegetation) |  |  |  | Vegetation | 493366.5711 |  |  | 493366.5711 |  |  | 5422299.7489 | 5422299.7489 |  | 5915666.32
| N/A | N/A | 38kV Transmission Line 6500 – Entire Line (Vegetation) |  |  |  | Vegetation | 752261.9035 |  |  | 752261.9035 |  |  | 8267664.9965 | 8267664.9965 |  | 9019926.9
[8 empty] | 899310108.2182 | 0 | 0 | 899310108.2182 | 0 | 0 | 1041176257.1128 | 1041176257.1128 |  | 1940486365.331
LUMA child Exhibit 4 - 289 (excluding 70 PREB)
| PW | GM | Project Name | 428 | 406 | Total Child | Asset | 428 Cons | 428 from 9510 | 428 from 10710 | Total 428 | 406 from 9510 | 406 from 10710 | New 406 | Total 406 |  | Total Project | Diff | Comments
| 11431 | 166707 | FAASt - Line 51300 (230KV) - Ponce TC to Costa Sur SP TC (Transmission) |  |  |  | 289 (ex 70) | 31809353 | 0 | 0 | 31809353 |  |  | 16781976 | 16781976 |  | 48591329
| 11255 | 166860 | FAASt-Line 37800 (115kV) - Jobos TC to Cayey TC & Cayey TC to Caguas TC (Transmission) |  |  |  | 289 (ex 70) | 82012589 | 0 | 0 | 82012589 |  |  | 19709323 | 19709323 |  | 101721912
| 11451 | 166904 | FAASt Transmission 115kV Line 37800 Caguas TC to Monacillos TC (TRANSMISSION) |  |  |  | 289 (ex 70) | 50400588 | 0 | 0 | 50400588 |  |  | 9229435 | 9229435 |  | 59630023
| 11246 | 167168 | FAASt [Transmission 115kV Line 37100 Costa Sur ST - Acacias TC] (Transmission) |  |  |  | 289 (ex 70) | 106645232 | 0 | 0 | 106645232 |  |  | 24646695 | 24646695 |  | 131291927
| 11251 | 167443 | FAASt - Line 36200 (115KV)- Monacillos TC to Juncos TC (Transmission) |  |  |  | 289 (ex 70) | 69007311 | 0 | 0 | 69007311 |  |  | 15967020 | 15967020 |  | 84974331
| 11250 | 167508 | FAASt Transmission - Line 50100 (230KV)- Cambalache GP TC to Manati TC (Transmission) |  |  |  | 289 (ex 70) | 78788689 | 0 | 0 | 78788689 |  |  | 4609955 | 4609955 |  | 83398644
| 107224 | 169503 | FAASt [Ceiba Baja TRF 7012] (Substation) |  |  |  | 289 (ex 70) | 2700000 | 0 | 0 | 2700000 |  |  | TBD | 0 |  | 2700000
| 107227 | 169804 | FAASt Aguadilla Electric Service Center (Building) |  |  |  | 289 (ex 70) | 3500000 | 0 | 0 | 3500000 |  |  | TBD | 0 |  | 3500000
| 11439 | 176954 | FAASt Garzas 1 HP to Garzas 2 HP - 38kV Line 1100 (Transmission) |  |  |  | 289 (ex 70) | 3362636 | 0 | 0 | 3362636 |  |  | 4127356 | 4127356 |  | 7489992
| 11440 | 177134 | FAASt Guaraguao TC to Comerio TC Line-4100 (Transmission) |  |  |  | 289 (ex 70) | 59675336 | 0 | 0 | 59675336 |  |  | 7821691 | 7821691 |  | 67497027
| 11433 | 177191 | FAASt - 115kV Line 39000 - Aguas Buenas TC to Caguas TC (Transmission) |  |  |  | 289 (ex 70) | 19407885 | 0 | 0 | 19407885 |  |  | 906873 | 906873 |  | 20314758
| 107305 | 179988 | FAASt [Las Lomas – XFMR 1525] (Substation) |  |  |  | 289 (ex 70) | 2400000 | 0 | 0 | 2400000 |  |  | TBD | 0 |  | 2400000
| 11441 | 180326 | FAASt - Line 36800 (115kV) - Sabana Llana TC to Canovanas TC to Palmer-Fajardo TC (Transmission) |  |  |  | 289 (ex 70) | 67238777 | 0 | 0 | 67238777 |  |  | 32488767 | 32488767 |  | 99727544
| 107513 | 334191 | FAASt [Feeders - Mayaguez Short Term Group 3] (Distribution) |  |  |  | 289 (ex 70) | 44675547 | 0 | 0 | 44675547 |  |  | 38483744 | 38483744 |  | 83159291
| 107514 | 334285 | FAASt [Feeders - Mayaguez Short Term Group 2] (Distribution ) |  |  |  | 289 (ex 70) | 48650571 | 0 | 0 | 48650571 |  |  | 35887745 | 35887745 |  | 84538316
| 107516 | 334293 | FAASt [Feeders - 7805-11- Mayaguez Short Term Group 4] (Distribution ) |  |  |  | 289 (ex 70) | 47224922 | 0 | 0 | 47224922 |  |  | 45582792 | 45582792 |  | 92807714
| 107517 | 334308 | FAASt [Feeders - Mayaguez Short Term Group 1] (Distribution ) |  |  |  | 289 (ex 70) | 45321705 | 0 | 0 | 45321705 |  |  | 32030114 | 32030114 |  | 77351819
| 11528 | 334331 | FAASt Line 1900 Dos Bocas HP to San Sebastian (38kV) TC (Transmission) |  |  |  | 289 (ex 70) | 33797391.48 | 0 | 0 | 33797391.48 |  |  | $ - | 0 |  | 33797391.48
| 107519 | 334420 | FAASt [Feeders - Caguas Short Term Group 1] (Distribution) |  |  |  | 289 (ex 70) | 53581787 | 0 | 0 | 53581787 |  |  | 25596317 | 25596317 |  | 79178104
| 107520 | 334443 | FAASt [Feeders - Caguas Short Term Group 2] (Distribution) |  |  |  | 289 (ex 70) | 61792621 | 0 | 0 | 61792621 |  |  | 51954249 | 51954249 |  | 113746870
| 107521 | 334452 | FAASt [Feeders - Caguas Short Term Group 3] (Distribution) |  |  |  | 289 (ex 70) | 45752407 | 0 | 0 | 45752407 |  |  | 20046792 | 20046792 |  | 65799199
| 107522 | 334469 | FAASt [Line 8900 Monacillos TC to Adm. Tribunal Apelaciones] (Transmission) |  |  |  | 289 (ex 70) | 11510000 | 0 | 0 | 11510000 |  |  | TBD | 0 |  | 11510000
| 107523 | 334471 | FAASt [Feeders -1303-01- San Juan Short Term Group 1] (Distribution) |  |  |  | 289 (ex 70) | 42950154 | 0 | 0 | 42950154 |  |  | 26997816 | 26997816 |  | 69947970
| 107524 | 334472 | FAASt [Feeders - San Juan Short Term Group 2] (Distribution) |  |  |  | 289 (ex 70) | 18783750 | 0 | 0 | 18783750 |  |  | 5366655 | 5366655 |  | 24150405
| 107525 | 334473 | FAASt [Feeders - 1806-02- Bayamon Short Term Group 1] (Distribution) |  |  |  | 289 (ex 70) | 17533060.67 | 0 | 0 | 17533060.67 |  |  | 1173247.16 | 1173247.16 |  | 18706307.83
| 107526 | 334474 | FAASt [Feeders - Bayamon Short Term Group 2] (Distribution) |  |  |  | 289 (ex 70) | 1189290 | 0 | 0 | 1189290 |  |  | 659178 | 659178 |  | 1848468
| 107527 | 334475 | FAASt [Feeders - Bayamon Short Term Group 3] (Distribution) |  |  |  | 289 (ex 70) | 50435894 | 0 | 0 | 50435894 |  |  | 17884283 | 17884283 |  | 68320177
| 107528 | 334476 | FAASt [Feeders - Carolina Short Term Group 2] (Distribution) |  |  |  | 289 (ex 70) | 18285383 | 0 | 0 | 18285383 |  |  | 18767542 | 18767542 |  | 37052925
| 107529 | 334477 | FAASt [Feeders - 2402-02 - Carolina Short Term Group 3] (Distribution) |  |  |  | 289 (ex 70) | 22922128 | 0 | 0 | 22922128 |  |  | 23907802 | 23907802 |  | 46829930
| 11450 | 334482 | FAASt [Line 3000 (38 kV) Monacillos TC to Juncos TC] (Transmission) |  |  |  | 289 (ex 70) | 90440000 | 0 | 0 | 90440000 |  |  | TBD | 0 |  | 90440000
| 107530 | 334491 | FAASt [Feeders - Caguas Short Term Group 5] (Distribution) |  |  |  | 289 (ex 70) | 19546933 | 0 | 0 | 19546933 |  |  | 13582684 | 13582684 |  | 33129617
| 107531 | 334497 | FAASt [Feeders - Caguas Short Term Group 6 (Distribution) |  |  |  | 289 (ex 70) | 67950718 | 0 | 0 | 67950718 |  |  | 22180767 | 22180767 |  | 90131485
| 107532 | 334518 | FAASt [Feeders - Caguas Short Term Group 7] (Distribution) |  |  |  | 289 (ex 70) | 12225881 | 0 | 0 | 12225881 |  |  | 7784267 | 7784267 |  | 20010148
| 107551 | 436616 | FAASt [Feeders - Arecibo Short Term Group 1] (Distribution) |  |  |  | 289 (ex 70) | 27194288 | 0 | 0 | 27194288 |  |  | 14494388 | 14494388 |  | 41688676
| 107556 | 546374 | FAASt [Feeders - 1620-02 San Juan Short Term Group 3] (Distribution) |  |  |  | 289 (ex 70) | 21058160 | 0 | 0 | 21058160 |  |  | 12777559 | 12777559 |  | 33835719
| 107558 | 546386 | FAASt [Feeders- El Yunque 2305 - Supply] (Distribution) |  |  |  | 289 (ex 70) | 6564391 | 0 | 0 | 6564391 |  |  | 23252037 | 23252037 |  | 29816428
| 107689 | 547160 | FAASt [Line 1200 Mayaguez GP to Yauco 2 HP] (Transmission) |  |  |  | 289 (ex 70) | 55370000 | 0 | 0 | 55370000 |  |  | TBD | 0 |  | 55370000
| 107692 | 547221 | FAASt [Line 3600 Monacillos TC to Martin Peña TC] (Transmission) |  |  |  | 289 (ex 70) | 39980000 | 0 | 0 | 39980000 |  |  | TBD | 0 |  | 39980000
| 11689 | 547226 | FAASt Barceloneta 11400 TC to Florida TO (Transmission) |  |  |  | 289 (ex 70) | 13810000 | 0 | 0 | 13810000 |  |  | TBD | 0 |  | 13810000
| 11448 | 547241 | FAASt Tallaboa 5402 (Substation) |  |  |  | 289 (ex 70) | 10924436 | 0 | 0 | 10924436 |  |  | 5628609 | 5628609 |  | 16553045
| 107693 | 547243 | FAASt Egozcue - 1109 (Substation) |  |  |  | 289 (ex 70) | 13896445.76 | 0 | 0 | 13896445.76 |  |  | 6952342.26 | 6952342.26 |  | 20848788.02
| 107694 | 547247 | FAASt Cambalache TC Relocation (Substation) |  |  |  | 289 (ex 70) | 5463505.9 | 0 | 0 | 5463505.9 |  |  | 84733286.06 | 84733286.06 |  | 90196791.96
| 107695 | 547248 | FAASt Canas TC 5002 5018 (Substation) |  |  |  | 289 (ex 70) | 1700000 | 0 | 0 | 1700000 |  |  | TBD | 0 |  | 1700000
| 11480 | 547259 | FAASt Line 2700 (38kV) Victoria TC to Quebradillas Sect. (Transmission) |  |  |  | 289 (ex 70) | 70974726 | 0 | 0 | 70974726 |  |  | 55843908 | 55843908 |  | 126818634
| 11481 | 547269 | FAASt Line 2800 (38 kV) Aguadilla Hospital Distrito Sect to T-Bone TO (Transmission) |  |  |  | 289 (ex 70) | 36113917 | 0 | 0 | 36113917 |  |  | 11466633 | 11466633 |  | 47580550
| 107699 | 547273 | FAASt Charco Hondo Substation 8008 Relocation (Substation) |  |  |  | 289 (ex 70) | 16300000 | 0 | 0 | 16300000 |  |  | TBD | 0 |  | 16300000
| 107701 | 547343 | FAASt [Victoria TC 7008 Relocation] (Substation) |  |  |  | 289 (ex 70) | 6846444.9 | 0 | 0 | 6846444.9 |  |  | 54844288.98 | 54844288.98 |  | 61690733.88
| 107702 | 547344 | FAASt [Acacias 6801 TC Relocation] (Substation) |  |  |  | 289 (ex 70) | 8874442.51 | 0 | 0 | 8874442.51 |  |  | 42895135.02 | 42895135.02 |  | 51769577.53
| 11854 | 547350 | FAASt [Line 13300 Bayamon TC to Plaza del Sol] (Transmission) |  |  |  | 289 (ex 70) | 5390000 | 0 | 0 | 5390000 |  |  | TBD | 0 |  | 5390000
| 107705 | 548393 | FAASt Arecibo Region Repairs (Buildings) |  |  |  | 289 (ex 70) | 9226902 | 0 | 0 | 9226902 |  |  | TBD | 0 |  | 9226902
| 107707 | 548440 | FAASt [Mayaguez Region Repairs] (Building) |  |  |  | 289 (ex 70) | 13346360 | 0 | 0 | 13346360 |  |  | TBD | 0 |  | 13346360
| 107708 | 548596 | FAASt [San German Electrical Service Center] (Building) |  |  |  | 289 (ex 70) | 2478182 | 0 | 0 | 2478182 |  |  | TBD | 0 |  | 2478182
| 11494 | 548598 | FAASt [Line 36200 (115 kV) Fajardo to Rio Blanco] (Transmission) |  |  |  | 289 (ex 70) | 42190487 | 0 | 0 | 42190487 |  |  | 15963429 | 15963429 |  | 58153916
| 107709 | 549768 | FAASt Physical Security - Group 5 (Substation) |  |  |  | 289 (ex 70) | 1200000 | 0 | 0 | 1200000 |  |  | TBD | 0 |  | 1200000
| 107710 | 550019 | FAASt [Line 600 Caguas TC to Gautier Benitez Sect.] (Transmission) |  |  |  | 289 (ex 70) | 22133515 | 0 | 0 | 22133515 |  |  | 4035264 | 4035264 |  | 26168779
| 107711 | 550060 | FAASt [Caguas Region Repairs] (Building) |  |  |  | 289 (ex 70) | 14472109 | 0 | 0 | 14472109 |  |  | TBD | 0 |  | 14472109
| 107712 | 550070 | FAASt [Line 4000 Comerio HP to Escuela Francisco Morales] (Transmission) |  |  |  | 289 (ex 70) | 22330000 | 0 | 0 | 22330000 |  |  | TBD | 0 |  | 22330000
| 107713 | 550099 | FAASt [Esc. Industrial M. Such - 1423] (Substation) |  |  |  | 289 (ex 70) | 9916473.34 | 0 | 0 | 9916473.34 |  |  | 6851320.87 | 6851320.87 |  | 16767794.21
| 11813 | 550162 | FAASt [Berwind TC - 1336] (Substation) |  |  |  | 289 (ex 70) | 44950547 | 0 | 0 | 44950547 |  |  | 6718315 | 6718315 |  | 51668862
| 107717 | 550498 | FAASt - [Morovis 8801 (Fuse to Breaker)] (Substation) |  |  |  | 289 (ex 70) | 16300000 | 0 | 0 | 16300000 |  |  | TBD | 0 |  | 16300000
| 107718 | 550500 | FAASt - Ponce Region Repairs (Building) |  |  |  | 289 (ex 70) | 20294279 | 0 | 0 | 20294279 |  |  | TBD | 0 |  | 20294279
| 107719 | 550771 | FAASt [Caguas TC] (Substation) |  |  |  | 289 (ex 70) | 2500000 | 0 | 0 | 2500000 |  |  | TBD | 0 |  | 2500000
| 107720 | 550894 | FAASt [Baldrich - 1422] (Substation) |  |  |  | 289 (ex 70) | 973098 | 0 | 0 | 973098 |  |  | 28669863 | 28669863 |  | 29642961
| 11688 | 550902 | FAASt [Line 9700 Palo Seco SP to Bay View Sect.] (Transmission) |  |  |  | 289 (ex 70) | 2320000 | 0 | 0 | 2320000 |  |  | TBD | 0 |  | 2320000
| 107721 | 550972 | FAASt [Fonalledas GIS Rebuilt 1401 1421] (Substation) |  |  |  | 289 (ex 70) | 31400000 | 0 | 0 | 31400000 |  |  | TBD | 0 |  | 31400000
| 107722 | 550980 | FAASt [Parques y Recreos - 1002] (Substation) |  |  |  | 289 (ex 70) | 11737497.05 | 0 | 0 | 11737497.05 |  |  | 8962734.08 | 8962734.08 |  | 20700231.13
| 107723 | 550986 | FAASt [Condado - 1133] (Substation) |  |  |  | 289 (ex 70) | 10649911 | 0 | 0 | 10649911 |  |  | 5427167 | 5427167 |  | 16077078
| 107724 | 550998 | FAASt [Santurce Planta (Sect) 1116] (Substation) |  |  |  | 289 (ex 70) | 9900000 | 0 | 0 | 9900000 |  |  | TBD | 0 |  | 9900000
| 11687 | 551067 | FAASt [Line 11100 Canovanas Sect. to GOAB 11115] (Transmission) |  |  |  | 289 (ex 70) | 3790000 | 0 | 0 | 3790000 |  |  | TBD | 0 |  | 3790000
| 107725 | 551100 | FAASt [Bayview Sectionalizer 1802 Relocation] (Substation) |  |  |  | 289 (ex 70) | 16700000 | 0 | 0 | 16700000 |  |  | TBD | 0 |  | 16700000
| 107726 | 551242 | FAASt [Bayamon Region Repairs] (Building) |  |  |  | 289 (ex 70) | 15451305 | 0 | 0 | 15451305 |  |  | TBD | 0 |  | 15451305
| 11570 | 551247 | FAASt [Palo Seco South Building Repairs] (Building) |  |  |  | 289 (ex 70) | 11170493 | 0 | 0 | 11170493 |  |  | TBD | 0 |  | 11170493
| 107727 | 551260 | FAASt [Guaynabo Pueblo Substation] (Substation) |  |  |  | 289 (ex 70) | 22381506.84 | 0 | 0 | 22381506.84 |  |  | 10941966.54 | 10941966.54 |  | 33323473.38
| 107732 | 551827 | FAASt [San Juan Region Repair] (Building) |  |  |  | 289 (ex 70) | 31028730 | 0 | 0 | 31028730 |  |  | TBD | 0 |  | 31028730
| 11434 | 551911 | FAASt [Line 9100 (38 kV) - Guaraguao TC to Bayamon Pueblo Sect.] (Transmission) |  |  |  | 289 (ex 70) | 5050000 | 0 | 0 | 5050000 |  |  | TBD | 0 |  | 5050000
| 107733 | 551912 | FAASt [Puerto Nuevo - 1520] (Substation) |  |  |  | 289 (ex 70) | 12192278 | 0 | 0 | 12192278 |  |  | 6035307 | 6035307 |  | 18227585
| 107734 | 551916 | FAASt [Dorado TC Relocation] (Substation) |  |  |  | 289 (ex 70) | 40100000 | 0 | 0 | 40100000 |  |  | TBD | 0 |  | 40100000
| 11409 | 551918 | FAASt [Crematorio - 1512] (Substation) |  |  |  | 289 (ex 70) | 12718285 | 0 | 0 | 12718285 |  |  | 6048401 | 6048401 |  | 18766686
| 107736 | 551927 | FAASt [SCADA Remote Access and RTU Replacements Group 3] (Telecommunication) |  |  |  | 289 (ex 70) | 19213188.6 | 0 | 0 | 19213188.6 |  |  | 3299617.88 | 3299617.88 |  | 22512806.48
| 107753 | 668665 | FAASt [Cybersecurity Program Implementation] (Telecommunication) |  |  |  | 289 (ex 70) | 24587256.13 | 0 | 0 | 24587256.13 |  |  | $ - | 0 |  | 24587256.13
| 107754 | 668669 | FAASt [Line 50500 230kV Mayaguez TC - Mora TC - Cambalache Power Plant] (Transmission) |  |  |  | 289 (ex 70) | 307465 | 0 | 0 | 307465 |  |  | $ - | 0 |  | 307465
| 107764 | 673920 | FAASt [Isla Grande 1101] (Substation) |  |  |  | 289 (ex 70) | 600000 | 0 | 0 | 600000 |  |  | TBD | 0 |  | 600000
| 107765 | 674506 | FAASt [Field Area Network (FAN)] (Telecommunication) |  |  |  | 289 (ex 70) | 330000000 | 0 | 0 | 330000000 |  |  | TBD | 0 |  | 330000000
| 107766 | 675345 | FAASt [IT OT Technology Systems Reparations] Group 1 (Telecommunication) |  |  |  | 289 (ex 70) | 9177181.22 | 0 | 0 | 9177181.22 |  |  | $ - | 0 |  | 9177181.22
| 107767 | 675406 | FAASt [Two-Way Land Mobile Radio Network] (Telecommunication) |  |  |  | 289 (ex 70) | 46200000 | 0 | 0 | 46200000 |  |  | TBD | 0 |  | 46200000
| 11862 | 679006 | FAASt [Test and Technology Laboratory] (Building) |  |  |  | 289 (ex 70) | 13125830 | 0 | 0 | 13125830 |  |  | 8186857 | 8186857 |  | 21312687
| 11861 | 679035 | FAASt [Telecom Infrastructure – Group A] (Telecommunication) |  |  |  | 289 (ex 70) | 5900000 | 0 | 0 | 5900000 |  |  | TBD | 0 |  | 5900000
| 107777 | 682331 | FAASt [RTU and Telecommunication Replacements Group 1 - Mayaguez Area] (Telecommunication) |  |  |  | 289 (ex 70) | 4360000 | 0 | 0 | 4360000 |  |  | TBD | 0 |  | 4360000
| 107825 | 704763 | FAASt [Telecom Infrastructure – Group C] (Telecommunication) |  |  |  | 289 (ex 70) | 2800000 | 0 | 0 | 2800000 |  |  | TBD | 0 |  | 2800000
| 11863 | 704805 | FAASt [Telecom Infrastructure – Group D] (Telecommunication) |  |  |  | 289 (ex 70) | 6905000 | 0 | 0 | 6905000 |  |  | TBD | 0 |  | 6905000
| 11476 | 705503 | FAASt [Pole and Conductor Repair Mayaguez Groups 15,16,17,18 & 19] (Distribution) |  |  |  | 289 (ex 70) | 1617942 | 0 | 0 | 1617942 |  |  | 192105 | 192105 |  | 1810047
| 107848 | 710026 | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 17] (Distribution) |  |  |  | 289 (ex 70) | 1250000 | 0 | 0 | 1250000 |  |  | TBD | 0 |  | 1250000
| 107849 | 710045 | FAASt [Distribution Pole and Conductor Repair -Mayaguez Group 20] (Distribution) |  |  |  | 289 (ex 70) | 1250000 | 0 | 0 | 1250000 |  |  | TBD | 0 |  | 1250000
| 107850 | 710363 | FAASt [Distribution Pole and Conductor Repair - Bayamon Group 15] (Distribution) |  |  |  | 289 (ex 70) | 1250000 | 0 | 0 | 1250000 |  |  | TBD | 0 |  | 1250000
| 107851 | 710498 | FAASt [Distribution Pole and Conductor Repair - Bayamon Group 16] (Distribution) |  |  |  | 289 (ex 70) | 1250000 | 0 | 0 | 1250000 |  |  | TBD | 0 |  | 1250000
| 107856 | 711829 | FAASt [Santa Isabel Sect. - Salinas Sect. 38kV Line 100] (Transmission) |  |  |  | 289 (ex 70) | 1309000 | 0 | 0 | 1309000 |  |  | TBD | 0 |  | 1309000
| 107857 | 711862 | FAASt [TL100 Ponce TC to Santa Isabel Sect](Transmission) |  |  |  | 289 (ex 70) | 1232000 | 0 | 0 | 1232000 |  |  | TBD | 0 |  | 1232000
| 107859 | 711962 | FAASt [Distribution Pole and Conductor Repair -Mayaguez Group 21] (Distribution) |  |  |  | 289 (ex 70) | 1250000 | 0 | 0 | 1250000 |  |  | TBD | 0 |  | 1250000
| 107862 | 712978 | FAASt [Once de Agosto Sect. - San Sebastian TC 38kV Line 2000] (Transmission) |  |  |  | 289 (ex 70) | 1848000 | 0 | 0 | 1848000 |  |  | TBD | 0 |  | 1848000
| 107864 | 712981 | FAASt [Distribution Pole and Conductor Repair - Ponce Group 24] (Distribution) |  |  |  | 289 (ex 70) | 1250000 | 0 | 0 | 1250000 |  |  | TBD | 0 |  | 1250000
| 107865 | 712982 | FAASt [Distribution Pole and Conductor Repair – Mayaguez Group 23] (Distribution) |  |  |  | 289 (ex 70) | 1250000 | 0 | 0 | 1250000 |  |  | TBD | 0 |  | 1250000
| 107877 | 715610 | FAASt [Network Upgrades to Support the Integration of Tranche 1 Utility Scale Renewable Projects] (Transmission) |  |  |  | 289 (ex 70) | 144745493 | 0 | 0 | 144745493 |  |  | $ - | 0 |  | 144745493
| 107882 | 718951 | FAASt [Line 51200- Costa Sur Steam Plant to Cambalache Gas Plant (230kV)] (Transmission) |  |  |  | 289 (ex 70) | 96340724 | 0 | 0 | 96340724 |  |  | 64652304 | 64652304 |  | 160993028
| 107883 | 718955 | FAASt [Line 50200 (230kv) from Manati TC to Bayamon TC] (Transmission) |  |  |  | 289 (ex 70) | 152903037 | 0 | 0 | 152903037 |  |  | 88423396 | 88423396 |  | 241326433
| 107907 | 730513 | FAASt [Feeders-Caguas Short Term Group 4] (Distribution) |  |  |  | 289 (ex 70) | 27818562 | 0 | 0 | 27818562 |  |  | 10929872 | 10929872 |  | 38748434
| 107908 | 730541 | FAASt [Feeders - Caguas Short Term Group 8] (Distribution) |  |  |  | 289 (ex 70) | 14523276 | 0 | 0 | 14523276 |  |  | 18671456 | 18671456 |  | 33194732
| 107909 | 730586 | FAASt [Feeders - Ponce Short Term Group 1] (Distribution) |  |  |  | 289 (ex 70) | 18969808 | 0 | 0 | 18969808 |  |  | 12719346 | 12719346 |  | 31689154
| 107910 | 730784 | FAASt [ Line 6700 Martin Peña TC to Villamar Sect.] (Transmission) |  |  |  | 289 (ex 70) | 6010000 | 0 | 0 | 6010000 |  |  | TBD | 0 |  | 6010000
| 107911 | 730821 | FAASt [Feeders - Arecibo Short Term Group 2] (Distribution) |  |  |  | 289 (ex 70) | 59530905 | 0 | 0 | 59530905 |  |  | 27363279 | 27363279 |  | 86894184
| 107912 | 730824 | FAASt [Feeders - Ponce Short Term Group 2] (Distribution) |  |  |  | 289 (ex 70) | 4115433 | 0 | 0 | 4115433 |  |  | 2840853 | 2840853 |  | 6956286
| 11805 | 734393 | FAASt [Cabo Rojo Streetlighting - Part 2] (Distribution) |  |  |  | 289 (ex 70) | 9689984 | 0 | 0 | 9689984 |  |  | 1016421 | 1016421 |  | 10706405
| 107915 | 734396 | FAASt [Cabo Rojo Streetlighting - Part 3] (Distribution) |  |  |  | 289 (ex 70) | 8681446 | 0 | 0 | 8681446 |  |  | 1169678 | 1169678 |  | 9851124
| 11774 | 734728 | FAASt [Ponce Streetlighting - Part 2] (Distribution) |  |  |  | 289 (ex 70) | 15473821 | 0 | 0 | 15473821 |  |  | 1402396 | 1402396 |  | 16876217
| 11830 | 734760 | FAASt [Ponce Streetlighting - Part 3] (Distribution) |  |  |  | 289 (ex 70) | 16496158 | 0 | 0 | 16496158 |  |  | 1946734 | 1946734 |  | 18442892
| 107916 | 734789 | FAASt [Guayama Streetlighting - Part 3 ] (Distribution) |  |  |  | 289 (ex 70) | 7740886 | 0 | 0 | 7740886 |  |  | 635977 | 635977 |  | 8376863
| 11808 | 734791 | FAASt [Guayama Streetlighting - Part 2] (Distribution) |  |  |  | 289 (ex 70) | 7187688 | 0 | 0 | 7187688 |  |  | 757008 | 757008 |  | 7944696
| 11837 | 734853 | FAASt [Arecibo Streetlighting- Part 3] (Distribution) |  |  |  | 289 (ex 70) | 18601760 | 0 | 0 | 18601760 |  |  | 2684586 | 2684586 |  | 21286346
| 11780 | 734859 | FAASt [Aguadilla Streetlighting - Part 2] (Distribution) |  |  |  | 289 (ex 70) | 10873634 | 0 | 0 | 10873634 |  |  | 1346103 | 1346103 |  | 12219737
| 11773 | 734927 | FAASt [Isabela Streetlighting - Part 2] (Distribution) |  |  |  | 289 (ex 70) | 9842173 | 0 | 0 | 9842173 |  |  | 1301829 | 1301829 |  | 11144002
| 107917 | 734928 | FAASt [Isabela Streetlighting - Part 3] (Distribution) |  |  |  | 289 (ex 70) | 5293882 | 0 | 0 | 5293882 |  |  | TBD | 0 |  | 5293882
| 11775 | 735131 | FAASt [Arecibo Streetlighting - Part 2] (Distribution) |  |  |  | 289 (ex 70) | 13584221 | 0 | 0 | 13584221 |  |  | 1546160 | 1546160 |  | 15130381
| 11834 | 735338 | FAASt [Aguadilla Streetlighting - Part 3] (Distribution) |  |  |  | 289 (ex 70) | 10052144 | 0 | 0 | 10052144 |  |  | 1423703 | 1423703 |  | 11475847
| 11777 | 735357 | FAASt [Mayaguez Streetlighting - Part 2] (Distribution) |  |  |  | 289 (ex 70) | 9099250 | 0 | 0 | 9099250 |  |  | 1097078 | 1097078 |  | 10196328
| 11832 | 735360 | FAASt [Mayaguez Streetlighting - Part 3] (Distribution) |  |  |  | 289 (ex 70) | 16626757 | 0 | 0 | 16626757 |  |  | 2189842 | 2189842 |  | 18816599
| 11804 | 735470 | FAASt [Bayamón Streetlighting - Part 2] (Distribution) |  |  |  | 289 (ex 70) | 20995636 | 0 | 0 | 20995636 |  |  | 1727642 | 1727642 |  | 22723278
| 11833 | 735472 | FAASt [Bayamon Streetlighting - Part 3] (Distribution) |  |  |  | 289 (ex 70) | 21541265 | 0 | 0 | 21541265 |  |  | 2632407 | 2632407 |  | 24173672
| 107919 | 735483 | FAASt [Vega Baja Streetlighting - Part 3] (Distribution) |  |  |  | 289 (ex 70) | 5377685 | 0 | 0 | 5377685 |  |  | TBD | 0 |  | 5377685
| 107920 | 735487 | FAASt [Humacao Streetlighting - Part 3] (Distribution) |  |  |  | 289 (ex 70) | 9528251 | 0 | 0 | 9528251 |  |  | 916292 | 916292 |  | 10444543
| 11799 | 735493 | FAASt [Humacao Streetlighting - Part 2] (Distribution) |  |  |  | 289 (ex 70) | 7901161 | 0 | 0 | 7901161 |  |  | 916292 | 916292 |  | 8817453
| 11835 | 735496 | FAASt [Carolina Streetlighting - Part 3] (Distribution) |  |  |  | 289 (ex 70) | 17520900 | 0 | 0 | 17520900 |  |  | 2019124 | 2019124 |  | 19540024
| 107921 | 735499 | FAASt [Guaynabo Streetlighting - Part 3] (Distribution) |  |  |  | 289 (ex 70) | 7033301 | 0 | 0 | 7033301 |  |  | TBD | 0 |  | 7033301
| 11783 | 735665 | FAASt [Carolina Streetlighting - Part 2] (Distribution) |  |  |  | 289 (ex 70) | 14631273 | 0 | 0 | 14631273 |  |  | 557536 | 557536 |  | 15188809
| 11838 | 735672 | FAASt [Caguas Streetlighting - Part 3] (Distribution) |  |  |  | 289 (ex 70) | 14419460 | 0 | 0 | 14419460 |  |  | 1624355 | 1624355 |  | 16043815
| 11801 | 735677 | FAASt [Guaynabo Streetlighting - Part 2] (Distribution) |  |  |  | 289 (ex 70) | 9325726 | 0 | 0 | 9325726 |  |  | 1014066 | 1014066 |  | 10339792
| 11806 | 735940 | FAASt [Vega Baja Streetlighting - Part 2] (Distribution) |  |  |  | 289 (ex 70) | 9309981 | 0 | 0 | 9309981 |  |  | 1067250 | 1067250 |  | 10377231
| 11831 | 735952 | FAASt [Trujillo Alto Streetlighting - Part 3] (Distribution) |  |  |  | 289 (ex 70) | 8838122 | 0 | 0 | 8838122 |  |  | 1149506 | 1149506 |  | 9987628
| 11772 | 735954 | FAASt [Trujillo Alto Streetlighting - Part 2] (Distribution) |  |  |  | 289 (ex 70) | 8062571 | 0 | 0 | 8062571 |  |  | 884864 | 884864 |  | 8947435
| 107922 | 735959 | FAASt [Toa Baja Streetlighting - Part 3] (Distribution) |  |  |  | 289 (ex 70) | 5878458 | 0 | 0 | 5878458 |  |  | TBD | 0 |  | 5878458
| 11803 | 735960 | FAASt [Toa Baja Streetlighting - Part 2] (Distribution) |  |  |  | 289 (ex 70) | 9782523 | 0 | 0 | 9782523 |  |  | 1238774 | 1238774 |  | 11021297
| 107923 | 737699 | FAASt [Toa Alta Streetlighting - Part 3] (Distribution) |  |  |  | 289 (ex 70) | 5526895 | 0 | 0 | 5526895 |  |  | TBD | 0 |  | 5526895
| 11797 | 737707 | FAASt [Toa Alta Streetlighting - Part 2] (Distribution) |  |  |  | 289 (ex 70) | 8808053 | 0 | 0 | 8808053 |  |  | 979674 | 979674 |  | 9787727
| 11836 | 737712 | FAAST [San Juan Streetlighting - Part 3] (Distribution) |  |  |  | 289 (ex 70) | 31581739 | 0 | 0 | 31581739 |  |  | 3250259 | 3250259 |  | 34831998
| 107924 | 737798 | FAASt [Rio Grande Streetlighting - Part 3] (Distribution) |  |  |  | 289 (ex 70) | 8572353 | 0 | 0 | 8572353 |  |  | 877731 | 877731 |  | 9450084
| 11809 | 737804 | FAASt [Rio Grande Streetlighting - Part 2 ] (Distribution) |  |  |  | 289 (ex 70) | 7692944 | 0 | 0 | 7692944 |  |  | 838135 | 838135 |  | 8531079
| 107927 | 738667 | FAASt [Pole and Conductor Repair - Ponce Group 2 - Phase 2] (Distribution) |  |  |  | 289 (ex 70) | 16618201.69 | 0 | 0 | 16618201.69 |  |  | 33268.04 | 33268.04 |  | 16651469.73
| 107928 | 738674 | FAASt [Pole and Conductor Repair - Mayaguez Group 2 - Phase 2] (Distribution) |  |  |  | 289 (ex 70) | 8935837.49 | 0 | 0 | 8935837.49 |  |  | 28130.53 | 28130.53 |  | 8963968.02
| 107929 | 738692 | FAASt [Pole and Conductor Repair - Carolina Group 1 - Phase 2] (Distribution) |  |  |  | 289 (ex 70) | 5100000 | 0 | 0 | 5100000 |  |  | TBD | 0 |  | 5100000
| 107948 | 744072 | FAASt [Network & Communication Infrastructure Group 2] (Telecommunication) |  |  |  | 289 (ex 70) | 2074582.38 | 0 | 0 | 2074582.38 |  |  | 490438.07 | 490438.07 |  | 2565020.45
| 107953 | 745851 | FAASt [Automation Program Group 11] (Distribution) |  |  |  | 289 (ex 70) | 479854 | 0 | 0 | 479854 |  |  | 1052298 | 1052298 |  | 1532152
| 107954 | 745852 | FAASt [Automation Program Group 13] (Distribution) |  |  |  | 289 (ex 70) | 888426 | 0 | 0 | 888426 |  |  | 1966004 | 1966004 |  | 2854430
| 107955 | 745854 | FAASt [ Automation Program Group 9] (Distribution) |  |  |  | 289 (ex 70) | 546905 | 0 | 0 | 546905 |  |  | 1164604 | 1164604 |  | 1711509
| 107958 | 745871 | FAASt [Automation Program Group 10] (Distribution) |  |  |  | 289 (ex 70) | 278408 | 0 | 0 | 278408 |  |  | 582637 | 582637 |  | 861045
| 11779 | 746108 | FAASt [San Juan Streetlighting - Part 2] (Distribution) |  |  |  | 289 (ex 70) | 30670485 | 0 | 0 | 30670485 |  |  | 3331645 | 3331645 |  | 34002130
| 11778 | 746111 | FAASt [Caguas Streetlighting - Part 2] (Distribution) |  |  |  | 289 (ex 70) | 12311632 | 0 | 0 | 12311632 |  |  | 1317294 | 1317294 |  | 13628926
| 107981 | 750730 | FAASt [Line 500 Ponce TC to Costa Sur SP] (Transmission) |  |  |  | 289 (ex 70) | 36590000 | 0 | 0 | 36590000 |  |  | TBD | 0 |  | 36590000
| 107991 | 752052 | FAASt [Transmission Line 9900 TAP9905A to Rio Blanco HP] (Transmission) |  |  |  | 289 (ex 70) | 32110000 | 0 | 0 | 32110000 |  |  | TBD | 0 |  | 32110000
| 107993 | 752275 | FAASt [Unibon 9501 (Fuse to Breaker)] (Substation) |  |  |  | 289 (ex 70) | 9157533 | 0 | 0 | 9157533 |  |  | TBD | 0 |  | 9157533
| 107994 | 752276 | FAASt [Monterrey 9502 & 9503 (Fuse to Breaker)] (Substation) |  |  |  | 289 (ex 70) | 39664220 | 0 | 0 | 39664220 |  |  | TBD | 0 |  | 39664220
| 107996 | 752500 | FAASt [Automation Program Group 1B] (Distribution) |  |  |  | 289 (ex 70) | 1250000 | 0 | 0 | 1250000 |  |  | TBD | 0 |  | 1250000
| 107997 | 752502 | FAASt [Automation Program Group 1C] (Distribution) |  |  |  | 289 (ex 70) | 1250000 | 0 | 0 | 1250000 |  |  | TBD | 0 |  | 1250000
| 107998 | 752503 | FAASt [Automation Program Group 1D] (Distribution) |  |  |  | 289 (ex 70) | 1250000 | 0 | 0 | 1250000 |  |  | TBD | 0 |  | 1250000
| 108004 | 753302 | FAASt [Telecom Infrastructure Group G] (Telecommunication) |  |  |  | 289 (ex 70) | 8381000 | 0 | 0 | 8381000 |  |  | TBD | 0 |  | 8381000
| 108008 | 753777 | FAASt [Line 1500 - Mayaguez GP to GOAB 1515] (Transmission) |  |  |  | 289 (ex 70) | 58661000 | 0 | 0 | 58661000 |  |  | TBD | 0 |  | 58661000
| 108009 | 753781 | FAASt [Transmission Priority Pole Replacement Program Line 800 Comsat Sect – Cidra Sect] (Transmission) |  |  |  | 289 (ex 70) | 726192.42 | 0 | 0 | 726192.42 |  |  | 33695.78 | 33695.78 |  | 759888.2
| 108011 | 753785 | FAASt [Transmission Priority Pole Replacement Program Line 3300 San Gerardo Sect – Venezuela Sect] (Transmission) |  |  |  | 289 (ex 70) | 336678.78 | 0 | 0 | 336678.78 |  |  | $ - | 0 |  | 336678.78
| 108012 | 753786 | FAASt [Transmission Priority Pole Replacement Program Line 5900 San Juan SP - Crematorio TO] (Transmission) |  |  |  | 289 (ex 70) | 507064.86 | 0 | 0 | 507064.86 |  |  | 24170.88 | 24170.88 |  | 531235.74
| 108013 | 753787 | FAASt [Transmission Priority Pole Replacement Program Line 13700 Mora TC-Isabela TO] (Transmission) |  |  |  | 289 (ex 70) | 623574.49 | 0 | 0 | 623574.49 |  |  | $ - | 0 |  | 623574.49
| 108014 | 753788 | FAASt [Transmission Priority Pole Replacement Program Line 1900 Dos Bocas HP – San Sebastian TC] (Transmission) |  |  |  | 289 (ex 70) | 1057925.6 | 0 | 0 | 1057925.6 |  |  | $ - | 0 |  | 1057925.6
| 108042 | 757945 | FAASt [Pole and Conductor Repair - Arecibo Group 3 - Phase 2] (Distribution) |  |  |  | 289 (ex 70) | 2892589.5 | 0 | 0 | 2892589.5 |  |  | 15039.03 | 15039.03 |  | 2907628.53
| 108045 | 759004 | FAASt [Pole and Conductor - Arecibo Group 4 - Phase 2] (Distribution) |  |  |  | 289 (ex 70) | 9280000 | 0 | 0 | 9280000 |  |  | TBD | 0 |  | 9280000
| 108046 | 759051 | FAASt Pole and Conductor - Bayamon Group 4 - Phase 2 (Distribution) |  |  |  | 289 (ex 70) | 3990000 | 0 | 0 | 3990000 |  |  | TBD | 0 |  | 3990000
| 108048 | 760568 | FAASt [Feeder Rebuild # 1710-01] (Distribution) |  |  |  | 289 (ex 70) | 10467848 | 0 | 0 | 10467848 |  |  | TBD | 0 |  | 10467848
| 108049 | 760571 | FAASt [Feeder Rebuild # 1720-07] (Distribution) |  |  |  | 289 (ex 70) | 18005134 | 0 | 0 | 18005134 |  |  | TBD | 0 |  | 18005134
| 108050 | 760575 | FAASt [Feeder Rebuild # 1716-03] (Distribution) |  |  |  | 289 (ex 70) | 18102407 | 0 | 0 | 18102407 |  |  | TBD | 0 |  | 18102407
| 108051 | 760577 | FAASt [Feeder Rebuild # 1718-02] (Distribution) |  |  |  | 289 (ex 70) | 8421396 | 0 | 0 | 8421396 |  |  | TBD | 0 |  | 8421396
| 108052 | 760579 | FAASt [Feeder Rebuild # 1717-03] (Distribution) |  |  |  | 289 (ex 70) | 14143466 | 0 | 0 | 14143466 |  |  | TBD | 0 |  | 14143466
| 108055 | 761563 | FAASt [San Jose Relocation] (Substation) |  |  |  | 289 (ex 70) | 17000000 | 0 | 0 | 17000000 |  |  | TBD | 0 |  | 17000000
| 108057 | 764706 | FAASt [Feeder Rebuild # 7011-03] (Distribution) |  |  |  | 289 (ex 70) | 9329781.4 | 0 | 0 | 9329781.4 |  |  | TBD | 0 |  | 9329781.4
| 108059 | 764708 | FAASt [Feeder Rebuild # 5602-02] (Distribution) |  |  |  | 289 (ex 70) | 5190387.52 | 0 | 0 | 5190387.52 |  |  | TBD | 0 |  | 5190387.52
| 108060 | 764709 | FAASt [Feeder Rebuild # 1204-05] (Distribution) |  |  |  | 289 (ex 70) | 8740820.93 | 0 | 0 | 8740820.93 |  |  | TBD | 0 |  | 8740820.93
| 108062 | 767005 | FAASt [Feeder Rebuild # 1303-05] (Distribution) |  |  |  | 289 (ex 70) | 12631766 | 0 | 0 | 12631766 |  |  | TBD | 0 |  | 12631766
| 108064 | 767139 | FAASt [Feeder Rebuild # 2906-02] (Distribution) |  |  |  | 289 (ex 70) | 3205041 | 0 | 0 | 3205041 |  |  | TBD | 0 |  | 3205041
| 108067 | 767381 | FAASt [Feeder Rebuild # 1204-04] (Distribution) |  |  |  | 289 (ex 70) | 9998489 | 0 | 0 | 9998489 |  |  | TBD | 0 |  | 9998489
| 108068 | 767387 | FAASt [Feeder Rebuild # 1303-01] (Distribution) |  |  |  | 289 (ex 70) | 4798378.99 | 0 | 0 | 4798378.99 |  |  | TBD | 0 |  | 4798378.99
| 108069 | 790427 | FAASt [Pole and Conductor Repair -Caguas Group 5 Phase 2 (Distribution) |  |  |  | 289 (ex 70) | 9241836.74 | 0 | 0 | 9241836.74 |  |  | 71738.97 | 71738.97 |  | 9313575.71
| 108071 | 790446 | FAASt [Pole and Conductor Repair -Caguas Group 4 Phase 2 (Distribution) |  |  |  | 289 (ex 70) | 4662521.3 | 0 | 0 | 4662521.3 |  |  | 28582.12 | 28582.12 |  | 4691103.42
| 108079 | 800369 | FAASt [Automation Program Group 38] (Distribution) |  |  |  | 289 (ex 70) | 1335000 | 0 | 0 | 1335000 |  |  | TBD | 0 |  | 1335000
| 108080 | 800394 | FAASt [Automation Program Group 39] (Distribution) |  |  |  | 289 (ex 70) | 3084000 | 0 | 0 | 3084000 |  |  | TBD | 0 |  | 3084000
| 108081 | 800399 | FAASt [Automation Program Group 40] (Distribution) |  |  |  | 289 (ex 70) | 2577000 | 0 | 0 | 2577000 |  |  | TBD | 0 |  | 2577000
| 108084 | 801197 | FAASt [Feeder Rebuild # 1204-02] (Distribution) |  |  |  | 289 (ex 70) | 3863358 | 0 | 0 | 3863358 |  |  | TBD | 0 |  | 3863358
| 108085 | 801432 | FAASt [Automation Program Group 41] (Distribution) |  |  |  | 289 (ex 70) | 2391000 | 0 | 0 | 2391000 |  |  | TBD | 0 |  | 2391000
| 108086 | 801437 | FAASt [Automation Program Group 42] (Distribution) |  |  |  | 289 (ex 70) | 2883000 | 0 | 0 | 2883000 |  |  | TBD | 0 |  | 2883000
| 108087 | 801438 | FAASt [Automation Program Group 43] (Distribution) |  |  |  | 289 (ex 70) | 2490000 | 0 | 0 | 2490000 |  |  | TBD | 0 |  | 2490000
| 108088 | 801440 | FAASt [Automation Program Group 44] (Distribution) |  |  |  | 289 (ex 70) | 3902000 | 0 | 0 | 3902000 |  |  | TBD | 0 |  | 3902000
| 108089 | 801441 | FAASt [Automation Program Group 45] (Distribution) |  |  |  | 289 (ex 70) | 2400000 | 0 | 0 | 2400000 |  |  | TBD | 0 |  | 2400000
| 108091 | 805517 | FAASt [38kV Recloser TL 2100 Hatillo TC to Quebradillas Sect.] (Transmission) |  |  |  | 289 (ex 70) | 462411.39 | 0 | 0 | 462411.39 |  |  | 733123.39 | 733123.39 |  | 1195534.78
| 108092 | 805519 | FAASt [38kV Recloser TL 1900 Dos Bocas HP to San Sebastian TC] (Transmission) |  |  |  | 289 (ex 70) | 708408.01 | 0 | 0 | 708408.01 |  |  | 769393.29 | 769393.29 |  | 1477801.3
| 108093 | 805521 | FAASt [38kV Recloser TL 7800 Dorado TC to Vega Alta Sect.] (Transmission) |  |  |  | 289 (ex 70) | 285043.08 | 0 | 0 | 285043.08 |  |  | 725071.07 | 725071.07 |  | 1010114.15
| 108097 | 806935 | FAASt [Pole and Conductor Repair - Caguas Group 6 - Phase 2] (Distribution) |  |  |  | 289 (ex 70) | 6120000 | 0 | 0 | 6120000 |  |  | TBD | 0 |  | 6120000
| 108098 | 806936 | FAASt [Pole and Conductor Repair - Carolina Group 3 - Phase 2] (Distribution) |  |  |  | 289 (ex 70) | 5100000 | 0 | 0 | 5100000 |  |  | TBD | 0 |  | 5100000
| 108099 | 811913 | FAASt [Transmission Priority Pole Replacement Program Line 9600 Bayamon TC – Catano Sect] (Transmission) |  |  |  | 289 (ex 70) | 420203.89 | 0 | 0 | 420203.89 |  |  | 43773.6 | 43773.6 |  | 463977.49
| 108100 | 811923 | FAASt [Transmission Priority Pole Replacement Program Line 16500 Fajardo TC-Dos Marinas] (Transmission) |  |  |  | 289 (ex 70) | 260238.98 | 0 | 0 | 260238.98 |  |  | 22761.43 | 22761.43 |  | 283000.41
| 108101 | 812041 | FAASt [Distribution Feeder Rebuild 9501-02] (Distribution) |  |  |  | 289 (ex 70) | 29244075.05 | 0 | 0 | 29244075.05 |  |  | $ - | 0 |  | 29244075.05
| 108105 | 814792 | FAASt [Telecom Infrastructure – Group E] (Telecommunication) |  |  |  | 289 (ex 70) | 5600000 | 0 | 0 | 5600000 |  |  | TBD | 0 |  | 5600000
| 108106 | 814793 | FAASt [Telecom Infrastructure – Group F] (Telecommunication) |  |  |  | 289 (ex 70) | 4600000 | 0 | 0 | 4600000 |  |  | TBD | 0 |  | 4600000
| 108113 | 817242 | FAASt [Pole and Conductor Repair -Caguas Group 8 - Phase 2] (Distribution) |  |  |  | 289 (ex 70) | 2040000 | 0 | 0 | 2040000 |  |  | TBD | 0 |  | 2040000
| 108114 | 817247 | FAASt [Pole and Conductor Repair -Ponce Group 3 - Phase 2] (Distribution) |  |  |  | 289 (ex 70) | 11650000 | 0 | 0 | 11650000 |  |  | TBD | 0 |  | 11650000
| 108116 | 817249 | FAASt [Pole and Conductor Repair -Caguas Group 7 - Phase 2] (Distribution) |  |  |  | 289 (ex 70) | 5100000 | 0 | 0 | 5100000 |  |  | TBD | 0 |  | 5100000
| 108117 | 817250 | FAASt [Pole and Conductor Repair -San Juan Group 4 - Phase 2] (Distribution) |  |  |  | 289 (ex 70) | 7610000 | 0 | 0 | 7610000 |  |  | TBD | 0 |  | 7610000
| 108120 | 817961 | FAASt [Feeder Rebuild # 2404-06] (Distribution) |  |  |  | 289 (ex 70) | 21344413.71 | 0 | 0 | 21344413.71 |  |  | 399260.06 | 399260.06 |  | 21743673.77
| 108121 | 817962 | FAASt [Feeder Rebuild # 9403-03] (Distribution) |  |  |  | 289 (ex 70) | 5548949 | 0 | 0 | 5548949 |  |  | TBD | 0 |  | 5548949
| 108122 | 817993 | FAASt [Feeder Rebuild # 1801-03] (Distribution) |  |  |  | 289 (ex 70) | 6131846 | 0 | 0 | 6131846 |  |  | TBD | 0 |  | 6131846
| 108123 | 818006 | FAASt [Feeder Rebuild #2402-02] (Distribution) |  |  |  | 289 (ex 70) | 34516477 | 0 | 0 | 34516477 |  |  | TBD | 0 |  | 34516477
| 108124 | 818041 | FAASt [Feeder Rebuild # 3701-03] (Distribution) |  |  |  | 289 (ex 70) | 24349603.89 | 0 | 0 | 24349603.89 |  |  | TBD | 0 |  | 24349603.89
| 108125 | 818055 | FAASt [Feeder Rebuild # 3006-05] (Distribution) |  |  |  | 289 (ex 70) | 8829008 | 0 | 0 | 8829008 |  |  | TBD | 0 |  | 8829008
| 108126 | 818056 | FAASt [Feeder Rebuild # 6305-03] (Distribution) |  |  |  | 289 (ex 70) | 22352214 | 0 | 0 | 22352214 |  |  | TBD | 0 |  | 22352214
| 108144 | 954184 | FAASt [Carolina ESC Building Repairs] (Buildings) |  |  |  | 289 (ex 70) | 2747126.23 | 0 | 0 | 2747126.23 |  |  | $ - | 0 |  | 2747126.23
| 108162 | 956782 | FAASt [Feeder Rebuild #6802-04] (Distribution) |  |  |  | 289 (ex 70) | 21957625.63 | 0 | 0 | 21957625.63 |  |  | 2769954.18 | 2769954.18 |  | 24727579.81
| 108164 | 958367 | FAASt [Feeder Rebuild #6603-01] (Distribution) |  |  |  | 289 (ex 70) | 14474191.76 | 0 | 0 | 14474191.76 |  |  | 1172038.62 | 1172038.62 |  | 15646230.38
[8 empty] | 4231292034.11 | 0 | 0 | 4231292034.11 | 0 | 0 | 1230982467.91 | 1230982467.91 |  | 5462274502.02 | 0
LUMA child Exhibit 4 - Incremental
| PW | GM | Project Name | 428 | 406 | Total Child | Asset | 428 Cons | 428 from 9510 | 428 from 10710 | Total 428 | 406 from 9510 | 406 from 10710 | New 406 | Total 406 |  | Total Project | Diff | Comments
| N/A | N/A | Various |  |  |  | Incremental Exhibit 4 | 1573672930.2447 | 0 | 0 | 1573672930.2447 | 0 | 0 | 357568246.1657 | 357568246.1657 |  | 1931241176.4104

## GP (hidden)
Project # | P/W # | Category | Title | Version # | Event | CRC Net Cost | Total 406 HMP Cost | Total Insurance Reductions | Non-Federal Share | Signed Non-Federal Share | Obligated Federal Share | % Cost Share | Initial Date Obligated | Last Date Obligated | Total Project Cost
751306 | 4739 | F - Utilities | Yabucoa 1-2 Permanent Repairs (Generation) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
750892 | 4735 | B - Emergency Protective Measures | Yabucoa 1-2 (Generation) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
698856 | 3097 | B - Emergency Protective Measures | Vieques & Culebra (Generation) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
1064360 | 5082 | F - Utilities | Transmission Line Number 9700 - 37700 (Transmission) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064374 | 5089 | F - Utilities | Transmission Line Number 8900 - 15300 - 38100 - 38300 - 38400 - 38600 - 38700 - 38900 (Transmission) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064376 | 5091 | F - Utilities | Transmission Line Number 5400 - 36800 (Transmission) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064366 | 5087 | F - Utilities | Transmission Line Number 500 - 1300 - 1500 - 4600 - 4700 (Transmission) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064364 | 5085 | F - Utilities | Transmission Line Number 4800 - 8500 - 9300 - 37800 (Transmission) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064375 | 5090 | F - Utilities | Transmission Line Number 37900 - 38200 - 50800 - 51000 (Transmission) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064362 | 5083 | F - Utilities | Transmission Line Number 37500 (Transmission) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064365 | 5086 | F - Utilities | Transmission Line Number 3700 - 9900 - 40800 (Transmission) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064359 | 5081 | F - Utilities | Transmission Line Number 36100 - 36200 (Transmission) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064363 | 5084 | F - Utilities | Transmission Line Number 3500 - 4900 - 8200 (Transmission) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064373 | 5088 | F - Utilities | Transmission Line Number 300 - 6500 - 7900 - 8300 - 50300 (Transmission) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1063764 | 4946 | F - Utilities | Transmission Line Number 2900 - 8100 - 36400 - 37100 - 50200 (Transmission) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1063769 | 4949 | F - Utilities | Transmission Line Number 2700 - 2800 - 13700 - 37200 (Transmission) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064357 | 5079 | F - Utilities | Transmission Line Number 2400 - 37400 - 50100 (Transmission) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064356 | 5078 | F - Utilities | Transmission Line Number 2300 - 39100 - 51200 (Transmission) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064358 | 5080 | F - Utilities | Transmission Line Number 1900 - 2600 (Transmission) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1063766 | 4947 | F - Utilities | Transmission Line Number 13400 - 15700 (Transmission) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1063768 | 4948 | F - Utilities | Transmission Line Number 1200 - 1600 - 2000 - 5600 - 9200 (Transmission) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
743538 | 4177 | B - Emergency Protective Measures | Traffic Control Post LEOC - Contracts | 0 | 4671DR-PR (4671DR) | 841436.08 | 0 | 0 | 84143.6 | 84143.6 | 757292.48 | 90% | 2024-11-15 18:15 | 2024-11-15 18:15 | 0
743536 | 2630 | B - Emergency Protective Measures | Traffic Control Contract- LEOC | 0 | 4671DR-PR (4671DR) | 257544.54 | 0 | 0 | 0 | 0 | 257544.54 | 100% | 2024-11-15 18:15 | 2024-11-15 18:15 | 0
75790 | 101703 | B - Emergency Protective Measures | Supply Potable Water to the Field Brigade | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
1064416 | 5095 | F - Utilities | Substations - San Juan Region | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064414 | 5093 | F - Utilities | Substations - Ponce Region | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064413 | 5092 | F - Utilities | Substations - Mayaguez Region | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064415 | 5094 | F - Utilities | Substations - Caguas Region | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064417 | 5096 | F - Utilities | Substations - Bayamon Region | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064418 | 5097 | F - Utilities | Substations - Arecibo Region | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
122024 | 106102 | F - Utilities | Substation Sample Project | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
122033 | 106103 | F - Utilities | Substation Outside Sample PH | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
722008 | 4000 | B - Emergency Protective Measures | SPA Emergency Protective Measures Transmission Lines 1500, 3400, 10000, 36100 | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
708626 | 3839 | B - Emergency Protective Measures | SPA - FIONA/MARIA/EQ: Emergency Protective Measures Feeders 9101-01 6010-01 9401-01 6010-02 (Cost share 90%) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
711078 | 3916 | B - Emergency Protective Measures | SPA - Emergency Protective Measures Feeders 1303-05 9801-01 1709-03 3014-01 9403-03 (Cost share 90%) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
711075 | 3915 | B - Emergency Protective Measures | SPA - Emergency Protective Measures Feeders 1303-05 9801-01 1709-03 3014-01 9403-03 (Cost share 100%) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
726140 | 4069 | A - Debris Removal | SPA - Dec 2022 Debris Removal - Feeders 1709-03, 1901-04, 3014-01, 5004-06, 6101-05, 6704-03, 6802-04, 7502-02, 7503-05, 9101-01, and Transmission line 50900 (90% Cost Share) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
726264 | 4071 | A - Debris Removal | SPA - Debris Removal from Jan. 2, 2023 - Jan.31, 2023; Feeders - 2401-01, 5004-06, 6406-02, 7404-06, 7503-05, 7505-05, 9004-08, 9801-01 | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
724404 | 4042 | A - Debris Removal | SPA - Debris Removal Feeders 9403-03, 3014-04, 3014-01, 7502-02, & Transmission Line 50900 (90% Cost Share) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
722985 | 4005 | A - Debris Removal | SPA - Debris Removal 11/7/22-11/16/22- Feeders 3014-01, 3014-04, 6406-02, 9101-01 and TL 50900 (100% Cost Share) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 100% |  |  | 0
742732 | 4167 | B - Emergency Protective Measures | San Juan Region-Materials - Post LEOC - (May-June) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
751276 | 4737 | F - Utilities | San Juan Generation Plant Battery Backup Unit 7 (Generation) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
751287 | 4738 | F - Utilities | San Juan Generation Plant (Generation) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
1064103 | 5014 | F - Utilities | San Juan Area Q-R-S-T Dist. 2002-01 - 2005-10 - 2201-01 - 2201-04 - 2301-01 - 2301-02 - 2305-01 - 2305-02 - 2305-03 - 2305-04 - 2306-01 - 2403-01 - 2501-01 - 3801-02 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
751709 | 4839 | F - Utilities | San Juan Area Q- Las Mercedes 2403(Substation) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
751436 | 4779 | F - Utilities | San Juan Area Q - Rio Grande 13 KV -(Alturas de Rio Grande)-2302(Substation) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
1064104 | 5015 | F - Utilities | San Juan Area P Dist. 2402-02 - 2404-05 - 2404-06 - 2404-08 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064106 | 5016 | F - Utilities | San Juan Area P Dist. 1607-01 - 1602-03 - 1602-04 - 1607-03 - 1607-04 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064094 | 5010 | F - Utilities | San Juan Area P Dist. 2401-01 - 2401-02 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064095 | 5011 | F - Utilities | San Juan Area O Dist. 1646-01 - 1646-02 - 1646-03 - 1646-05 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064098 | 5013 | F - Utilities | San Juan Area O Dist. 1620-02 - 1620-05 - 1652-03 - 1652-04 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064091 | 5008 | F - Utilities | San Juan Area N Dist. 1657-02 - 1658-13 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
751508 | 4813 | F - Utilities | San Juan Area N - Villamar 1657/ 1658(Substation) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
751449 | 4784 | F - Utilities | San Juan Area M- San Fernando 1519 & San Fernando 1521(Substation) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
1064093 | 5009 | F - Utilities | San Juan Area L-M Dist. 1348-06 - 1348-08 - 1421-01 - 1424-08 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064084 | 5002 | F - Utilities | San Juan Area K Dist. 1530-08, 1529-15, 1529-11, 1525-04, 1525-05, 1526-02 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
751711 | 4840 | F - Utilities | San Juan Area H- Llorens Torres 1106 & Llorens Torres 1118(Substation) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
1064148 | 5045 | F - Utilities | San Juan Area G-H Dist. 1115-05 - 1114-01 - 1118-09 - 1118-10 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
751466 | 4793 | F - Utilities | San Juan Area F- Planta de Saturce 1116(Substation) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
1064147 | 5044 | F - Utilities | San Juan Area F Dist. 1119-04 - 1116-03 - 1117-11 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064146 | 5043 | F - Utilities | San Juan Area C-D Dist. 1330-01 - 1345-04 - 1437-03 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064139 | 5040 | F - Utilities | San Juan Area C Dist. 1303-02 - 1303-03 - 1346-02 - 1346-03 - 1346-05 - 1346-06 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064145 | 5042 | F - Utilities | San Juan Area B-C Dist. 1335-01 - 1336-06 - 1301-01 - 1346-04 - 1303-01 - 1303-05 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064142 | 5041 | F - Utilities | San Juan Area A-B Dist. 1201-02 - 1336-07 - 1336-08 - 1334-01 - 1334-02 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064136 | 5039 | F - Utilities | San Juan Area A Dist. 1206-03 - 1203-01 - 1203-02 - 1203-03 1205-02 - 1205-03 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064135 | 5038 | F - Utilities | San Juan Area A Dist. 1204-02 - 1204-03 - 1204-04 - 1204-05 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
959063 | 4926 | B - Emergency Protective Measures | Rentals Enterprise Expenses-Post LEOC | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
959062 | 4925 | B - Emergency Protective Measures | Rentals Enterprise Expenses-LEOC | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
743549 | 4179 | B - Emergency Protective Measures | Rentals Contracts LEOC Period | 0 | 4671DR-PR (4671DR) | 534047.06 | 0 | 0 | 0 | 0 | 534047.06 | 100% | 2025-05-02 21:15 | 2025-05-02 21:15 | 0
743550 | 4180 | B - Emergency Protective Measures | Rental Contracts - Post LEOC | 0 | 4671DR-PR (4671DR) | 1095674.55 | 0 | 0 | 109567.45 | 109567.45 | 986107.1 | 90% | 2024-11-26 16:15 | 2024-11-26 16:15 | 0
736347 | 4126 | B - Emergency Protective Measures | Regional Approach- Labor-(Nov-April)-Post LEOC | 0 | 4671DR-PR (4671DR) | 18221336.02 | 0 | 0 | 1822133.6 | 1822133.6 | 16399202.42 | 90% | 2026-02-27 14:17 | 2026-02-27 14:17 | 0
736350 | 4127 | B - Emergency Protective Measures | Regional Approach Meals and Travel (Oct-Apr) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
49822 | 98 | B - Emergency Protective Measures | PREPA EMERGENCY POWER PLANT FUEL | 2 | 4339DR-PR (4339DR) | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 2017-10-13 | 2017-12-29 13:36 | 0
707331 | 425 | D - Water Control Facilities | PREPA - FIONA/MARIA/EQ: Guamani and Tres Cuartitos Permanent Repairs (Riego/Dam) | 0 | 4671DR-PR (4671DR) | 290726.45 | 34345.78 | 0 | 29072.64 | 0 | 0 | 90% |  |  | 0
956620 | 4918 | F - Utilities | PREPA - Dos bocas transformers | 0 | 4671DR-PR (4671DR) | 8782710.4 | 0 | 0 | 878271.04 | 0 | 0 | 90% |  |  | 0
750844 | 4733 | D - Water Control Facilities | PREPA - Carite Permanent Repairs | 0 | 4671DR-PR (4671DR) | 480000 | 0 | 0 | 48000 | 48000 | 432000 | 90% | 2026-02-25 22:16 | 2026-02-25 22:16 | 0
111292 | 134 | Z - Management Costs | PR Electric Power Authority - Management Costs (Interim) | 1 | 4336DR-PR (4336DR) | 6367.16 |  | 0 | 0 | 0 | 6367.16 | 100% | 2019-10-23 11:20 | 2019-10-22 21:43 | 6367.16
739681 | 11628 | F - Utilities | Power Generation (Generation) | 0 | 4339DR-PR (4339DR) | 372298490 | 0 | 0 | 37229849 | 37229849 | 335068641 | 90% | 2024-03-01 12:30 | 2024-02-29 12:48 | 372298490
243527 | 11129 | B - Emergency Protective Measures | Post Appeal Determination - EMERGENCY PROTECTIVE MEASURE - Force Account Labor 90/10 | 3 | 4339DR-PR (4339DR) | 17607476.97 | 0 | 0 | 1760747.69 | 1758603.84 | 15827434.6 | 90% | 2023-02-21 12:56 | 2025-04-29 18:17 | 17279734.59
742731 | 4166 | B - Emergency Protective Measures | Ponce Region-Materials - Post LEOC - (May-June) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064204 | 5072 | F - Utilities | Ponce Area KK Dist. 5304-01, 5304-02, 5304-03, 5304-05 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064202 | 5070 | F - Utilities | Ponce Area KK Dist. 5302-01, 5302-02, 5302-03, 5302-04 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
749168 | 4278 | F - Utilities | Ponce Area K- Yauco Plaza 5305 (Substation) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
749162 | 4276 | F - Utilities | Ponce Area K Dist. 5602-01, 5602-02, 5602-03 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
749161 | 4275 | F - Utilities | Ponce Area K Dist. 5305-03, 5305-04 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
749160 | 4274 | F - Utilities | Ponce Area K Dist. 5304-01, 5304-02, 5304-03, 5304-05 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
749158 | 4272 | F - Utilities | Ponce Area K Dist. 5302-01, 5302-02, 5302-03, 5302-04 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
1064203 | 5071 | F - Utilities | Ponce Area K Dist. 5301-01, 5303-01, 5305-03, 5305-04 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
749157 | 4271 | F - Utilities | Ponce Area K Dist. 5301-01 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
1063992 | 4951 | F - Utilities | Ponce Area K Dist 5602-01, 5602-02, 5602-03 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
751517 | 4819 | F - Utilities | Ponce Area K - Yauco 2 Hidro 5303(Substation) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
751516 | 4818 | F - Utilities | Ponce Area K - Yauco 1 Hidro - 5301(Substation) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
1064196 | 5067 | F - Utilities | Ponce Area J Dist. 5501-01, 5501-02, 5501-03, 5501-04 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064195 | 5066 | F - Utilities | Ponce Area J Dist. 5402-01, 5402-02, 5403-01, 5403-02 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064192 | 5064 | F - Utilities | Ponce Area J Dist. 5401-01, 5401-02, 5401-03, 5401-04 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064185 | 5063 | F - Utilities | Ponce Area J Dist. 5021-01, 5021-02 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064184 | 5062 | F - Utilities | Ponce Area I Dist. 5019-01, 5019-02 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064183 | 5061 | F - Utilities | Ponce Area I Dist. 5018-01, 5018-02, 5018-03, 5018-04, 5018-05 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064180 | 5059 | F - Utilities | Ponce Area I Dist. 5005-02, 5005-03, 5005-05 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064179 | 5058 | F - Utilities | Ponce Area I Dist. 5002-01, 5002-02, 5002-03, 5002-04 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064178 | 5057 | F - Utilities | Ponce Area H Dist. 5012-01, 5012-02, 5012-03, 5012-04 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064177 | 5056 | F - Utilities | Ponce Area H Dist. 5004-07, 5004-09 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064175 | 5054 | F - Utilities | Ponce Area H Dist. 5004-06 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064176 | 5055 | F - Utilities | Ponce Area H Dist. 5003-01, 5003-02, 5003-03 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064173 | 5053 | F - Utilities | Ponce Area G Dist. 5011-03, 5011--04, 5016-01, 5016-02 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064172 | 5052 | F - Utilities | Ponce Area G Dist. 5008-01, 5008--03, 5008-04, 5010-03 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064157 | 5051 | F - Utilities | Ponce Area G Dist. 5001-02, 5001--05, 5007-01, 5007-02 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064155 | 5049 | F - Utilities | Ponce Area F Dist. 5801-01, 5801--02, 5801-04, 5803-02, 5817-02 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064154 | 5048 | F - Utilities | Ponce Area F Dist. 5013-01, 5013-02, 5013-03 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064153 | 5047 | F - Utilities | Ponce Area E Dist. 5901-01, 5901-02, 5901-03, 5902-03 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064121 | 5027 | F - Utilities | Ponce Area E Dist. 5804-01, 5804-02, 5805-01 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064115 | 5021 | F - Utilities | Ponce Area E Dist. 5802-01, 5802-02, 5802-03, 5802-04, (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
751526 | 4824 | F - Utilities | Ponce Area E - Juana Diaz 4 Kv 5802(Substation) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
1064097 | 5012 | F - Utilities | Ponce Area D Dist. 4602-01, 4602-02, 4602-03, 4603-01, 4603-02 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
749225 | 4327 | F - Utilities | Ponce Area D Dist. 4402-02, 4601-01, 4601-02, 4601-04 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064066 | 5000 | F - Utilities | Ponce Area D Dist. 4401-01, 4401-02, 4401-03, 4401-04 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
749251 | 4340 | F - Utilities | Ponce Area C Dist. 4504-01 - 4504-02 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
749250 | 4339 | F - Utilities | Ponce Area C Dist. 4502-02 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
751417 | 4773 | F - Utilities | Ponce Area B- AES | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
1064065 | 4999 | F - Utilities | Ponce Area B Dist. 4001-03, 4003-01, 4003-02 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
751523 | 4822 | F - Utilities | Ponce Area B - Jobos 4003(Substation) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
1064063 | 4998 | F - Utilities | Ponce Area A Dist. 4301-01, 4301-02, 4301-03, 4301-04 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064062 | 4997 | F - Utilities | Ponce Area A Dist. 4201-01, 4201-02, 4201-03, 4201-04 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064061 | 4996 | F - Utilities | Ponce Area A Dist. 4101-01, 4101-02, 4101-03, 4101-04 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
749254 | 4343 | F - Utilities | Ponce Area A Dist. 4002-01, 4002-02, 4006-02 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
750729 | 107980 | F - Utilities | PLACEHOLDER (Buildings) | 0 | 4339DR-PR (4339DR) | 1251791913.73 | 98935899.3 | 0 | 125179191.37 | 0 | 0 | 90% |  |  | 0
962147 | 1132 | F - Utilities | PLACEHOLDER | 0 | 4473DR-PR (4473DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
686388 | 44 | B - Emergency Protective Measures | Peaking Units - Fiona (Generation) | 0 | 4671DR-PR (4671DR) | 68518319 | 0 | -29691271 | 0 | 0 | 68518319 | 100% | 2023-01-10 13:19 | 2023-01-05 14:30 | 68518319
743541 | 4178 | B - Emergency Protective Measures | Other Services Contracts LEOC | 0 | 4671DR-PR (4671DR) | 1854481.23 | 0 | 0 | 0 | 0 | 1854481.23 | 100% | 2025-04-07 15:15 | 2025-04-07 15:15 | 0
743520 | 4176 | B - Emergency Protective Measures | Other Services Contracts - Post LEOC | 0 | 4671DR-PR (4671DR) | 3661056.31 | 0 | 0 | 366105.63 | 366105.63 | 3294950.68 | 90% | 2025-08-19 15:16 | 2025-08-19 15:16 | 0
713673 | 409 | B - Emergency Protective Measures | Oficina de Majejo de Emergencia y Administración de Desastres (EOC) | 1 | 4671DR-PR (4671DR) | 23199.19 | 0 | 0 | 2319.92 | 2319.92 | 20879.27 | 90% | 2023-05-31 11:39 | 2023-05-30 12:09 | 23199.19
742730 | 4165 | B - Emergency Protective Measures | Multiple Region-Materials - Post LEOC - (May-June) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
743730 | 4190 | B - Emergency Protective Measures | Multiple Region – POST LEOC Period (July-Sept) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
711142 | 1062 | B - Emergency Protective Measures | Mondongo and Melania Emergency Repairs (Riego/Dam) | 1 | 4671DR-PR (4671DR) | 76582.48 | 0 | 0 | 7658.25 | 7658.25 | 68924.23 | 90% | 2023-08-29 11:28 | 2023-08-28 22:07 | 76582.48
91893 | 103493 | F - Utilities | MEPA187 - Water Facilities - Guajataca Dam | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
89439 | 102583 | B - Emergency Protective Measures | MEPA185 Owner Controlled Insurance Program for Mutual Aid Emergency Work Companies | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
102691 | 105245 | B - Emergency Protective Measures | MEPA184 - Aerial inspections of damaged distribution and transmission lines - PREPA - Glide Aviation | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
102792 | 105258 | F - Utilities | MEPA182 - Telecommunications - El Yunque | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
83182 | 1294 | Z - Management Costs | MEPA181-Others- PREPA Management Costs | 1 | 4339DR-PR (4339DR) | 620193956.54 | 0 | 0 | 0 | 0 | 620193956.54 | 100% | 2020-02-05 12:48 | 2023-04-13 20:41 | 620193956.54
102889 | 8937 | B - Emergency Protective Measures | MEPA180-TRANSMISSION-Whitefish Energy | 1 | 4339DR-PR (4339DR) | 104834336.49 | 0 | 0 | 0 | 0 | 111352417 | 100% | 2021-09-09 11:39 | 2021-09-08 12:33 | 104834336.49
77704 | 101757 | F - Utilities | MEPA179-Others- Streetlight Replacement | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
80354 | 101861 | F - Utilities | MEPA178-Substations-Priority Substations for Control Buildings | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
101680 | 105183 | B - Emergency Protective Measures | MEPA174 - SM ELECTRICAL (LC) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
79372 | 101813 | B - Emergency Protective Measures | MEPA173 JVPR Mobility (LC) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
97242 | 1859 | B - Emergency Protective Measures | Mepa170-LC- Pro Energy | 1 | 4339DR-PR (4339DR) | 274009.18 | 0 | 0 | 0 | 0 | 274009.18 | 100% | 2020-05-26 11:24 | 2025-04-04 17:15 | 498747.05
79196 | 101808 | B - Emergency Protective Measures | MEPA169-All Contractor Services (LC) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
79184 | 2045 | B - Emergency Protective Measures | MEPA166-LC- Geodrone | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
49831 | 11211 | B - Emergency Protective Measures | MEPA161-TRANSMISSION-COBRA | 3 | 4339DR-PR (4339DR) | 253845805.78 | 0 | 0 | 25384580.58 | 25384580.58 | 228461225.2 | 90% | 2023-03-28 11:34 | 2025-09-17 18:16 | 233683116.76
66979 | 1109 | B - Emergency Protective Measures | MEPA157 - Eversource (IMT) | 4 | 4339DR-PR (4339DR) | 293190.27 | 0 | 0 | 0 | 0 | 293190.27 | 100% | 2019-09-06 18:36 | 2025-05-13 16:15 | 293863.81
66975 | 1107 | B - Emergency Protective Measures | MEPA153 - Austin (IMT) | 1 | 4339DR-PR (4339DR) | 1632275.2 | 0 | 0 | 0 | 0 | 1632275.2 | 100% | 2019-09-06 18:32 | 2025-04-29 15:16 | 1634032
66974 | 1100 | B - Emergency Protective Measures | MEPA152 - AES (IMT) | 2 | 4339DR-PR (4339DR) | 172372.55 | 0 | 0 | 0 | 0 | 172372.55 | 100% | 2019-11-20 14:32 | 2025-04-10 20:15 | 173664.06
49850 | 496 | F - Utilities | MEPA150-DISTRIBUTION-Power Vieques and Culebra | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 75% |  |  | 0
68753 | 1165 | F - Utilities | MEPA149- A&E Services-PW 01165 | 3 | 4339DR-PR (4339DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% | 2019-09-06 18:37 | 2020-10-13 12:26 | 0
49854 | 518 | B - Emergency Protective Measures | MEPA147 - Power Precast (LC) | 0 | 4339DR-PR (4339DR) | 206870 | 0 | 0 | 0 | 0 | 206870 | 100% | 2019-11-25 12:28 | 2019-11-22 21:48 | 206870
49848 | 466 | B - Emergency Protective Measures | MEPA145-TRANSMISSION-COBRA | 2 | 4339DR-PR (4339DR) | 52691018.87 | 0 | 0 | 0 | 0 | 52691018.87 | 100% | 2018-08-06 | 2025-04-29 18:17 | 51911380.71
49847 | 473 | B - Emergency Protective Measures | MEPA144-DISTRIBUTION-MASTEC NORTH AMERICA | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 75% |  |  | 0
49846 | 489 | B - Emergency Protective Measures | MEPA143 -Transient Recorders | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 75% |  |  | 0
122517 | 106108 | F - Utilities | MEPA138 - 115kV Island Wide Transmission lines system | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
49824 | 483 | F - Utilities | MEPA137 - Repair & Replace Optic & Wireless Equipment (29) | 0 | 4339DR-PR (4339DR) | 0 | 0 | 0 |  | 0 | 0 | 75% |  |  | 0
72322 | 101439 | F - Utilities | MEPA137 - PREPANet Repair and Replace Fiber Optic Infrastructure | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
105054 | 105382 | E - Buildings and Equipment | MEPA136 - Vehicles - Humacao District | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
101710 | 6068 | B - Emergency Protective Measures | MEPA132 - HOSEC (LC) | 2 | 4339DR-PR (4339DR) | 838342 | 0 | 0 | 0 | 0 | 838342 | 100% | 2021-02-25 12:21 | 2025-05-22 18:15 | 846606.26
79190 | 4192 | B - Emergency Protective Measures | MEPA115-LC- Bermudez & Longo | 0 | 4339DR-PR (4339DR) | 857938 | 0 | 0 | 0 | 0 | 857938 | 100% | 2021-02-25 12:21 | 2021-02-24 22:01 | 857938
121357 | 106088 | F - Utilities | MEPA108 - 230kV Island Wide Transmission lines system | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
118361 | 106032 | E - Buildings and Equipment | MEPA107 - Island Wide Buildings | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
116409 | 106006 | F - Utilities | MEPA104-SUBSTATIONS-San Juan Medical District Substations | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
114475 | 105927 | F - Utilities | MEPA103 - Telecommunications | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
110975 | 105826 | F - Utilities | MEPA101-Substations-Priority Substations for Relocation - Pampanos | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
110976 | 105827 | F - Utilities | MEPA100-Substations-Priority Substations for Relocation - San Jose | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
104226 | 105346 | F - Utilities | MEPA098-TRANSMISSION-EASTERN PHARMA CORRIDOR | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
104143 | 105343 | F - Utilities | MEPA097-SUBSTATIONS-EASTERN PHARMA CORRIDOR | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
102803 | 105261 | F - Utilities | MEPA095-Substations-LMM Airport Loop | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
110972 | 105825 | F - Utilities | MEPA094-Substations-Priority Substations for Relocation - Acacias | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
110971 | 105824 | F - Utilities | MEPA093-Substations-Priority Substations for Relocation - Dorado & La Virgencita | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
110970 | 105823 | F - Utilities | MEPA092-Substations-Priority Substations for Relocation - Charco Hondo | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
105791 | 105485 | F - Utilities | MEPA091-Substations-Priority Substations for GIS | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
105790 | 105484 | F - Utilities | MEPA090-Substations-Priority Substations for Relocation - Cambalache | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
106540 | 105576 | F - Utilities | MEPA089 - Island Wide Hydroelectric Systems | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
107106 | 105603 | F - Utilities | MEPA088 - Island Wide Irrigation Channels | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
107075 | 105597 | F - Utilities | MEPA086 - Water Facilities - Patillas Dam | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
106861 | 105583 | F - Utilities | MEPA085 - Island Wide Dams | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
104483 | 105362 | F - Utilities | MEPA083 - Generation - Mayaguez Plant | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
97560 | 104789 | F - Utilities | MEPA079 - Island Wide PREPA Transmission Lines PH | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
136271 | 6099 | F - Utilities | MEPA078 Puerto Rico Electrical Power Authority Island Wide FAASt Project | 80 | 4339DR-PR (4339DR) | 3001509293.97 | 0 | -275000000 | 300150929.39 | 300150929.39 | 2701358364.58 | 90% | 2020-09-24 11:28 | 2026-03-01 20:15 | 5924306661.08
101073 | 105136 | E - Buildings and Equipment | MEPA076 - Buildings - Humacao District | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
101729 | 105189 | F - Utilities | MEPA075-Substations-Humacao District | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
101678 | 2014 | B - Emergency Protective Measures | MEPA061-ACOSTA ELECTRICAL (LC) | 1 | 4339DR-PR (4339DR) | 204048.75 | 0 | 0 | 0 | 0 | 204048.75 | 100% | 2020-03-11 11:43 | 2025-08-12 15:16 | 208432.35
97556 | 1964 | B - Emergency Protective Measures | MEPA060 - Master Link Acquisition Corporation (LC) | 1 | 4339DR-PR (4339DR) | 50000 | 0 | 0 | 0 | 0 | 50000 | 100% | 2019-10-23 11:20 | 2025-04-04 16:15 | 152600
96155 | 104658 | B - Emergency Protective Measures | MEPA059 - JR Industrial (LC) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
95938 | 104612 | F - Utilities | MEPA036 - Island Wide Distribution Lines System | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
49819 | 319 | B - Emergency Protective Measures | MEPA035 - MOU - PW319 (Muni) CUC | 1 | 4339DR-PR (4339DR) | 466245.1 | 0 | 0 | 0 | 0 | 466245.1 | 100% | 2024-05-06 11:05 | 2024-05-03 18:22 | 466245.1
49817 | 328 | B - Emergency Protective Measures | MEPA033 - MOU - PW328 (Muni) NORWICH | 1 | 4339DR-PR (4339DR) | 546468.83 | 0 | 0 | 0 | 0 | 546468.83 | 100% | 2024-05-06 11:05 | 2024-05-03 18:20 | 546468.83
49814 | 304 | B - Emergency Protective Measures | MEPA030 - MOU - PW304 (IOU) XCEL | 2 | 4339DR-PR (4339DR) | 18517325.71 | 0 | 0 | 0 | 0 | 18517325.71 | 100% | 2022-01-21 20:26 | 2025-05-12 22:15 | 17232893.92
49808 | 294 | B - Emergency Protective Measures | MEPA024 - MOU - PW294 (IOU) LGE | 2 | 4339DR-PR (4339DR) | 5781281.34 | 0 | 0 | 0 | 0 | 5781281.34 | 100% | 2021-03-10 12:17 | 2025-05-13 16:15 | 5782326.13
49805 | 301 | B - Emergency Protective Measures | MEPA021 - MOU - PW301 (IOU) DUKE | 6 | 4339DR-PR (4339DR) | 34009716.93 | 0 | 0 | 0 | 0 | 34009716.93 | 100% | 2021-02-19 12:35 | 2024-11-27 16:16 | 30852749.23
49804 | 298 | B - Emergency Protective Measures | MEPA020 - MOU - PW298 (IOU) DTE | 2 | 4339DR-PR (4339DR) | 23413140.09 | 0 | 0 | 0 | 0 | 23413140.09 | 100% | 2025-02-28 19:16 | 2025-02-28 19:16 | 23413140.09
49803 | 300 | B - Emergency Protective Measures | MEPA019 - MOU - PW300 (IOU) DOMINION | 2 | 4339DR-PR (4339DR) | 8043753.62 | 0 | 0 | 0 | 0 | 10115386 | 100% |  | 2018-09-07 15:51 | 7035167.06
751816 | 4860 | B - Emergency Protective Measures | Meals and Travel November 2022 - April 2023 | 0 | 4671DR-PR (4671DR) | 3263850.89 | 0 | 0 | 326385.08 | 326385.08 | 2937465.81 | 90% | 2025-08-19 15:16 | 2025-08-19 15:16 | 0
749985 | 4728 | B - Emergency Protective Measures | Meals and Travel May - June | 0 | 4671DR-PR (4671DR) | 1294070.82 | 0 | 0 | 129407.08 | 129407.08 | 1164663.74 | 90% | 2025-08-19 15:16 | 2025-08-19 15:16 | 0
750209 | 4730 | B - Emergency Protective Measures | Meals and Travel - July - Sept | 0 | 4671DR-PR (4671DR) | 686436.5 | 0 | 0 | 68643.65 | 68643.65 | 617792.85 | 90% | 2025-06-11 18:15 | 2025-06-11 18:15 | 0
742729 | 4164 | B - Emergency Protective Measures | Mayaguez Region-Materials - Post LEOC - (May-June) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
751433 | 4778 | F - Utilities | Mayaguez J - Alturas de Mayaguez 6012(Substations) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
750848 | 4734 | F - Utilities | Mayaguez Generation Plant | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
751442 | 4781 | F - Utilities | Mayaguez D - Atalaya 7303(Substation) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
751419 | 4775 | F - Utilities | Mayaguez C - Aguada 7201(Substation) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
1064060 | 4995 | F - Utilities | Mayaguez Area L Dist. 7503-01, 7503-02, 7503-03, 7503-04, 7503-05 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064059 | 4994 | F - Utilities | Mayaguez Area L Dist. 7502-01, 7502-02, 7502-03, 7502-04, 7505-05 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
751519 | 4820 | F - Utilities | Mayaguez Area K- Zona Libre -6007(Substation) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
965495 | 4934 | F - Utilities | Mayaguez Area K Dist. 6802-01, 6802-02, 6802-04, 6802-05 (Distribution) | 0 | 4671DR-PR (4671DR) | 321221.03 | 58486.12 | 0 | 32122.1 | 32122.1 | 289098.93 | 90% | 2026-02-25 22:16 | 2026-02-25 22:16 | 0
966825 | 4943 | F - Utilities | Mayaguez Area J Dist. 6012-01, 6012-02, 6012-03, 6012-05 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
751721 | 4845 | F - Utilities | Mayaguez Area J - Mayaguez Planta 6005(Substation) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
751807 | 4853 | F - Utilities | Mayaguez Area I- Once de Agosto 6001(Substation) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
966655 | 4940 | F - Utilities | Mayaguez Area I Dist. 6008-02, 6008-04 (Distribution) | 0 | 4671DR-PR (4671DR) | 171547.7 | 22624.26 | 0 | 17154.77 | 17154.77 | 154392.93 | 90% | 2026-02-25 22:16 | 2026-02-25 22:16 | 0
751528 | 4826 | F - Utilities | Mayaguez Area H - Lajas 6601(Substation) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
751773 | 4849 | F - Utilities | Mayaguez Area F - Monte Del Estado 6303(Substation) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
751719 | 4843 | F - Utilities | Mayaguez Area F - Maricao 6301(Substation) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
751706 | 4838 | F - Utilities | Mayaguez Area E- Las Marias 6201(Substation) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
751703 | 4837 | F - Utilities | Mayaguez Area E- Lares 7901 & Lares 7903(Substation) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
1064048 | 4988 | F - Utilities | Mayaguez Area E Dist. 7901-01, 7901-02, 7901-03 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064058 | 4993 | F - Utilities | Mayaguez Area E Dist. 7802-01, 7802-03, 7802-04 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064057 | 4992 | F - Utilities | Mayaguez Area E Dist. 7801-01, 7805-11 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064053 | 4991 | F - Utilities | Mayaguez Area E Dist. 7403-01, 7403-02, 7403-03 (Distribution) | 0 | 4671DR-PR (4671DR) | 181099.07 | 0 | 0 | 18109.9 | 0 | 0 | 90% |  |  | 0
1064051 | 4990 | F - Utilities | Mayaguez Area E Dist. 6201-01 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
751458 | 4790 | F - Utilities | Mayaguez Area E - San Sebastian TC 7805(Substation) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
1064026 | 4970 | F - Utilities | Mayaguez Area D Dist. 7103-04 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1063969 | 4950 | F - Utilities | Mayaguez Area D Dist. 6101-01, 6101-02, 6101-03, 6101-04, 6101-05 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064033 | 4976 | F - Utilities | Mayaguez Area C Dist. 7301-01, 7301-02, 7301-03, 7301-04, 7301-05, 7302-01 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064031 | 4974 | F - Utilities | Mayaguez Area C Dist. 7201-02, 7201-03, 7201-04, 7201-05 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
751810 | 4855 | F - Utilities | Mayaguez Area C - Punta del Mar Prov 730(Substation) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
751806 | 4852 | F - Utilities | Mayaguez Area B- Ojo de Agua 7002(Substation) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
751506 | 4812 | F - Utilities | Mayaguez Area B Victoria 13Kv 7008(Substation) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
1064037 | 4980 | F - Utilities | Mayaguez Area B Dist. 7101-02, 7101-03, 7101-04 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064036 | 4979 | F - Utilities | Mayaguez Area B Dist. 7008-04, 7008-05, 7008-07, 7008-08 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064035 | 4978 | F - Utilities | Mayaguez Area B Dist. 7003-02, 7003-03, 7003-05 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
751473 | 4798 | F - Utilities | Mayaguez Area B - T Bone 7011(Substation) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
1064042 | 4984 | F - Utilities | Mayaguez Area A Dist. 7504-01, 7504-02 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064041 | 4983 | F - Utilities | Mayaguez Area A Dist. 7012-01, 7012-02 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064040 | 4982 | F - Utilities | Mayaguez Area A Dist. 7006-01, 7006-03 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064039 | 4981 | F - Utilities | Mayaguez Area A Dist. 7004-06, 7005-03 (Distribution) | 0 | 4671DR-PR (4671DR) | 49453.7 | 0 | 0 | 4945.37 | 0 | 0 | 90% |  |  | 0
751814 | 4859 | F - Utilities | Mayaguez Area A - Ramey Field 3 7006(Substation) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
751812 | 4857 | F - Utilities | Mayaguez Area A - Ramey Field 1 7004(Substation) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
751813 | 4858 | F - Utilities | Mayaguez Area A - Ramey Field 2 7005(Substation) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
743727 | 4189 | B - Emergency Protective Measures | Materials Small Project Application – Ponce Region (July-Sept) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
743625 | 4187 | B - Emergency Protective Measures | Materials Small Project Application – Mayaguez Region POST LEOC (July-Sept) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
743624 | 4186 | B - Emergency Protective Measures | Materials Small Project Application – Centralized Region POST LECO (July-Sept) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
743620 | 4185 | B - Emergency Protective Measures | Materials Small Project Application – Caguas Region Post LEOC (July-Sept) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
743633 | 4188 | B - Emergency Protective Measures | Materials San Juan Region POST LEOC - (July-Sept) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
743757 | 4194 | B - Emergency Protective Measures | Materials San Juan POST LEOC (Nov-April) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
743755 | 4193 | B - Emergency Protective Measures | Materials Ponce POST LEOC (Nov-April) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
743754 | 4192 | B - Emergency Protective Measures | Materials Multiples POST LEOC (Nov-April) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
743753 | 4191 | B - Emergency Protective Measures | Materials Mayaguez POST LEOC (Nov-April) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
743761 | 4198 | B - Emergency Protective Measures | Materials Centralized Region POST LEOC - (Nov - April) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
743760 | 4197 | B - Emergency Protective Measures | Materials Caguas Region POST LEOC - (Nov - April) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
743759 | 4196 | B - Emergency Protective Measures | Materials Bayamon Region POST LEOC - (Nov - April) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
743758 | 4195 | B - Emergency Protective Measures | Materials Arecibo Region POST LEOC - (Nov - April) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
740093 | 4143 | B - Emergency Protective Measures | Materials - San Juan Region (100% Cost Share) LEOC | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
740090 | 4142 | B - Emergency Protective Measures | Materials - Ponce Region (100% Cost Share) LEOC | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
740061 | 4141 | B - Emergency Protective Measures | Materials - Mayaguez Region (100% Cost Share) LEOC | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
740059 | 4140 | B - Emergency Protective Measures | Materials - Centralized Region (100% Cost Share) LEOC | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
740056 | 4139 | B - Emergency Protective Measures | Materials - Caguas Region (100% Cost Share) LEOC | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
739994 | 4137 | B - Emergency Protective Measures | Materials - Bayamon Region (100% Cost Share) LEOC | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
739991 | 4136 | B - Emergency Protective Measures | Materials - Arecibo Region (100% Cost Share) LEOC | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
744322 | 191 | Z - Management Costs | Management Costs-COVID Project - PR Electric Power Authority | 1 | 4493DR-PR (4493DR) | 158526.75 | 0 | 0 | 0 | 0 | 180286.21 | 100% | 2024-02-26 12:17 | 2024-02-23 12:42 | 180286.21
810316 | 148 | Z - Management Costs | Management Costs | 0 | 4805DR-PR (4805DR) | 11772.79 | 0 | 0 | 0 | 0 | 11772.79 | 100% | 2025-03-05 20:15 | 2025-03-05 20:15 | 0
437384 | 506 | Z - Management Costs | Management Costs | 0 | 4473DR-PR (4473DR) | 15868202.05 | 0 | 0 | 0 | 0 | 15868202.05 | 100% | 2021-11-18 11:26 | 2021-11-17 22:06 | 15868202.05
721698 | 554 | Z - Management Costs | Management Costs | 2 | 4671DR-PR (4671DR) | 5319273.33 | 0 | 0 | 0 | 0 | 5319273.33 | 100% | 2023-06-26 11:40 | 2026-02-25 22:16 | 3453237.35
952321 | 4908 | B - Emergency Protective Measures | LUMA-TEKNIEK-Contract | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
951696 | 4904 | B - Emergency Protective Measures | LUMA-Materials-Nov-April | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
950753 | 4901 | B - Emergency Protective Measures | LUMA-Materials-May-June | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
951699 | 4905 | B - Emergency Protective Measures | LUMA-Materials-LEOC-Sept-Nov | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
950757 | 4902 | B - Emergency Protective Measures | LUMA-Materials-July-September | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
952461 | 4909 | B - Emergency Protective Measures | LUMA-IAPETUS-Contract | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
950926 | 4903 | B - Emergency Protective Measures | LUMA-CERES-Contract | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
951758 | 4906 | B - Emergency Protective Measures | LUMA-BIRD-Contract | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
744432 | 4221 | F - Utilities | LUMA - Substation: SAN_GERMAN-TC 6406 (Cost Share 90%) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
744515 | 4229 | F - Utilities | LUMA - Substation: SAN_GERMAN 6404 (Cost Share 90%) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
744513 | 4228 | F - Utilities | LUMA - Substation: SAN_GERMAN 6401 (Cost Share 90%) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
744433 | 4222 | F - Utilities | LUMA - Substation: SABANA_GRANDE 6501 (Cost Share 90%) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
744464 | 4225 | F - Utilities | LUMA - Substation: La Parguera 6603 (Cost Share 90%) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
744490 | 4227 | F - Utilities | LUMA - Substation: Combate 6704 (Cost Share 90%) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
803001 | 4879 | B - Emergency Protective Measures | LUMA - SPA - WASTE MANGEMENT CONTRACT - RENTALS - POST LEOC PERIOD | 0 | 4671DR-PR (4671DR) | 193306.82 | 0 | 0 | 19330.68 | 19330.68 | 173976.14 | 90% | 2025-08-08 19:16 | 2025-08-08 19:16 | 0
803000 | 4878 | B - Emergency Protective Measures | LUMA - SPA - WASTE MANGEMENT CONTRACT - RENTALS - LEOC PERIOD | 1 | 4671DR-PR (4671DR) | 65276.91 | 0 | 0 | 0 | 0 | 65276.91 | 100% | 2025-06-27 15:16 | 2025-07-09 20:15 | 0
765445 | 4872 | A - Debris Removal | LUMA - SPA - Emergency Debris Contracts - Rentals - Post LEOC Period | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
765431 | 4871 | A - Debris Removal | LUMA - SPA - Emergency Debris Contracts - Rentals - LEOC Period | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
746355 | 4234 | F - Utilities | LUMA - Permanent Work - Distribution/Transmission/Substations (90% cost share) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
744279 | 4213 | F - Utilities | LUMA - 38 kV Sub Transmission Line Number 9200 (Transmission) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
744278 | 4212 | F - Utilities | LUMA - 38 kV Sub Transmission Line Number 6100 (Cost Share 90%) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
744277 | 4211 | F - Utilities | LUMA - 38 kV Sub Transmission Line Number 2800 (Transmission) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
744268 | 4204 | F - Utilities | LUMA - 38 kV Sub Transmission Line Number 1600 (Transmission) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
744272 | 4207 | F - Utilities | LUMA - 38 kV Sub Transmission Line Number 15700 (Transmission) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
744270 | 4206 | F - Utilities | LUMA - 38 kV Sub Transmission Line Number 1500 (Transmission) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
744266 | 4203 | F - Utilities | LUMA - 38 kV Sub Transmission Line Number 13400 (Transmission) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
744273 | 4208 | F - Utilities | LUMA - 38 kV Sub Transmission Line Number 1200 (Transmission) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
744344 | 4216 | F - Utilities | LUMA - 115 kV Transmission Line Number 42100 (Cost Share 90%) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
744269 | 4205 | F - Utilities | LUMA - 115 kV Transmission Line Number 39800 (Transmission) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
744274 | 4209 | F - Utilities | LUMA - 115 kV Transmission Line Number 37200 (Transmission) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
744275 | 4210 | F - Utilities | LUMA - 115 kV Transmission Line Number 36700 (Transmission) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
744429 | 4220 | F - Utilities | LUMA - 4.16 kV Distribution Lines Mayaguez 6404-01, 6404-02, 6404-03, 6404-04 (Distribution) | 0 | 4671DR-PR (4671DR) | 147450.05 | 20629.55 | 0 | 14745 | 14745 | 132705.05 | 90% | 2026-02-25 22:16 | 2026-02-25 22:16 | 0
744413 | 4217 | F - Utilities | LUMA - 4.16 kV Distribution Lines Mayaguez (6401-02, 6401-04) (Distribution) | 0 | 4671DR-PR (4671DR) | 108064.3 | 20742.55 | 0 | 10806.43 | 10806.43 | 0 | 90% |  |  | 0
743376 | 4171 | B - Emergency Protective Measures | Lease & Fleet Maintenance Contract Post-LEOC | 0 | 4671DR-PR (4671DR) | 68576.31 | 0 | 0 | 6857.63 | 6857.63 | 61718.68 | 90% | 2024-11-26 16:15 | 2024-11-26 16:15 | 0
743595 | 4181 | B - Emergency Protective Measures | Labor July-Sept Post LEOC Period | 0 | 4671DR-PR (4671DR) | 10027592.67 | 0 | 0 | 1002759.26 | 1002759.26 | 9024833.41 | 90% | 2026-02-27 14:17 | 2026-02-27 14:17 | 0
740284 | 4145 | B - Emergency Protective Measures | Labor (May-June 2023) All Regions | 0 | 4671DR-PR (4671DR) | 7513895.42 | 0 | 0 | 751389.54 | 751389.54 | 6762505.88 | 90% | 2026-02-27 14:17 | 2026-02-27 14:17 | 0
97630 | 104812 | F - Utilities | Island Wide Reservoir Dredging | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
136274 | 106910 | F - Utilities | Island Wide PREPA Substations (FCE) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
49793 | 53 | B - Emergency Protective Measures | IEPA004 - EPM -Peaking Generator Units | 1 | 4336DR-PR (4336DR) |  |  | 0 |  | 0 | 0 | 75% |  |  | 0
49792 | 100013 | B - Emergency Protective Measures | IEPA003 EMERGENCY PROTECTIVE MEASURES | 1 | 4336DR-PR (4336DR) |  |  | 0 |  | 0 | 0 | 75% |  |  | 0
49789 | 54 | B - Emergency Protective Measures | IEPA001- Emergency Protective Measures | 2 | 4336DR-PR (4336DR) | 127343.27 | 0 | 0 | 31835.82 | 31835.82 | 95507.45 | 75% | 2018-05-19 | 2018-05-19 18:35 | 127343.27
687249 | 2658 | B - Emergency Protective Measures | Genera - Central Aguirre Emergency Repairs | 0 | 4671DR-PR (4671DR) | 48822.5 | 0 | 0 | 4882.25 | 4882.25 | 43940.25 | 90% | 2024-11-15 18:15 | 2024-11-15 18:15 | 0
685599 | 2635 | B - Emergency Protective Measures | Force Account Labor and Equipment | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 100% |  |  | 0
965493 | 4933 | F - Utilities | FIONA/MARIA/EQ: Mayaguez Area K Dist. 6007-02, 6010-01, 6010-02, 6010-03 (Distribution) | 0 | 4671DR-PR (4671DR) | 78173.53 | 31001.02 | 0 | 7817.35 | 7817.35 | 70356.18 | 90% | 2026-02-13 12:15 | 2026-02-13 12:15 | 0
966654 | 4939 | F - Utilities | FIONA/MARIA/EQ: Mayaguez Area I Dist. 6004-02, 6004-05 (Distribution) | 0 | 4671DR-PR (4671DR) | 62113.74 | 10665.63 | 0 | 6211.37 | 6211.37 | 55902.37 | 90% | 2026-02-05 20:16 | 2026-02-05 20:16 | 0
966653 | 4938 | F - Utilities | FIONA/MARIA/EQ: Mayaguez Area I Dist. 6001-01, 6001-02, 6001-03, 6001-05 (Distribution) | 0 | 4671DR-PR (4671DR) | 115159.28 | 29649.54 | 0 | 11515.92 | 11515.92 | 0 | 90% |  |  | 0
965811 | 4937 | F - Utilities | FIONA/MARIA/EQ: Mayaguez Area F Dist. 6305-02, 6306-02, 7902-01 (Distribution) | 0 | 4671DR-PR (4671DR) | 211489.48 | 29765.18 | 0 | 21148.94 | 0 | 0 | 90% |  |  | 0
1064043 | 4985 | F - Utilities | FIONA/MARIA/EQ: Mayaguez Area E Dist. 7805-13 (Distribution) | 0 | 4671DR-PR (4671DR) | 13889.46 | 0 | 0 | 1388.94 | 0 | 0 | 90% |  |  | 0
963100 | 4932 | F - Utilities | FIONA/MARIA/EQ: LUMA: Mayaguez Area H Dist. 6703-01, 6703-2, 6705-01 (Distribution) | 0 | 4671DR-PR (4671DR) | 187588.48 | 32963.23 | 0 | 18758.84 | 18758.84 | 168829.64 | 90% | 2026-02-25 22:16 | 2026-02-25 22:16 | 0
962613 | 4929 | F - Utilities | FIONA/MARIA/EQ: LUMA: Mayaguez Area H Dist. 6601-01, 6601-02, 6601-03, 6601-04 (Distribution) | 0 | 4671DR-PR (4671DR) | 472220.13 | 94587.48 | 0 | 47222.01 | 0 | 0 | 90% |  |  | 0
965496 | 4935 | F - Utilities | FIONA/MARIA/EQ: LUMA-Mayaguez Area K Dist. 6801-01, 6801-02, 6801-03 (Distribution) | 0 | 4671DR-PR (4671DR) | 30247.73 | 10742.73 | 0 | 3024.77 | 3024.77 | 27222.96 | 90% | 2026-02-05 20:16 | 2026-02-05 20:16 | 0
744420 | 4218 | F - Utilities | FIONA/MARIA/EQ: LUMA-4.16 kV Distribution Line Mayaguez (6501-01, 6501-02, 6501-03, 6501-04) (Distribution) | 0 | 4671DR-PR (4671DR) | 1398493.45 | 0 | 0 | 139849.34 | 0 | 0 | 90% |  |  | 0
965810 | 4936 | F - Utilities | FIONA/MARIA/EQ: LUMA Mayaguez Area F Dist. 6301-01, 6301-02 (Distribution) | 0 | 4671DR-PR (4671DR) | 55649.39 | 4191.23 | 0 | 5564.93 | 5564.93 | 50084.46 | 90% | 2026-02-05 20:16 | 2026-02-05 20:16 | 0
967144 | 4944 | F - Utilities | FIONA/MARIA/EQ: LUMA Mayaguez Area D Dist. 7303-02, 7011-01, 7011-03 (Distribution) | 0 | 4671DR-PR (4671DR) | 389500.89 | 0 | 0 | 38950.08 | 0 | 0 | 90% |  |  | 0
966824 | 4942 | F - Utilities | FIONA/MARIA/EQ: LUMA - Mayaguez Area I Dist. 6015-02, 7104-05, 7104-06 (Distribution) | 0 | 4671DR-PR (4671DR) | 109795.36 | 19417.91 | 0 | 10979.53 | 0 | 0 | 90% |  |  | 0
966657 | 4941 | F - Utilities | FIONA/MARIA/EQ: LUMA - Mayaguez Area I Dist. 6014-02, 7002-01, 7002-03, 7002-04 (Distribution) | 0 | 4671DR-PR (4671DR) | 266403.35 | 41278.5 | 0 | 26640.33 | 26640.33 | 0 | 90% |  |  | 0
796595 | 4875 | F - Utilities | FIONA/MARIA/EQ: LUMA - 13.2 kV Distribution Line Mayaguez 6406-04 (Distribution) | 0 | 4671DR-PR (4671DR) | 136798.58 | 18836.9 | 0 | 13679.85 | 13679.85 | 123118.73 | 90% | 2026-02-25 22:16 | 2026-02-25 22:16 | 0
744463 | 4224 | F - Utilities | FIONA/MARIA/EQ: LUMA - 13.2 kV Distribution Line Mayaguez (6704-02, 6704-03) (Distribution) | 0 | 4671DR-PR (4671DR) | 276734.73 | 49585.04 | 0 | 27673.47 | 0 | 0 | 90% |  |  | 0
744462 | 4223 | F - Utilities | FIONA/MARIA/EQ: LUMA - 13.2 kV Distribution Line Mayaguez (6603-01) (Distribution) | 0 | 4671DR-PR (4671DR) | 50155.34 | 10649.57 | 0 | 5015.53 | 5015.53 | 45139.81 | 90% | 2026-01-12 19:15 | 2026-01-12 19:15 | 0
744422 | 4219 | F - Utilities | FIONA/MARIA/EQ: LUMA - 13.2 kV Distribution Line Mayaguez (6406-02) (Distribution) | 0 | 4671DR-PR (4671DR) | 492415.68 | 163354.15 | 0 | 49241.56 | 49241.56 | 443174.12 | 90% | 2026-02-25 22:16 | 2026-02-25 22:16 | 0
688781 | 517 | B - Emergency Protective Measures | FIONA/MARIA/EQ: Guamani Dam Repairs (Riego/Dam) | 0 | 4671DR-PR (4671DR) | 211370 | 0 | 0 | 21137 | 21137 | 190233 | 90% | 2023-06-12 12:17 | 2023-06-09 19:39 | 211370
708624 | 3838 | B - Emergency Protective Measures | FIONA/MARIA/EQ: Emergency Protective Measures Feeders 9101-01 6010-01 9401-01 6010-02 (Cost share 100%) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
687247 | 731 | B - Emergency Protective Measures | FIONA/MARIA/EQ: Central San Juan Emergency Repairs (Generation) | 0 | 4671DR-PR (4671DR) | 684572.22 | 0 | 0 | 0 | 0 | 684572.22 | 100% | 2023-08-03 11:20 | 2023-08-02 12:54 | 684572.22
721302 | 781 | B - Emergency Protective Measures | FIONA/MARIA/EQ: Central Costa Sur Emergency Repairs (Generation) (Cost Share 100%) | 0 | 4671DR-PR (4671DR) | 44690.32 | 0 | 0 | 0 | 0 | 44690.32 | 100% | 2023-08-03 11:20 | 2023-08-02 03:25 | 44690.32
687250 | 788 | B - Emergency Protective Measures | FIONA/MARIA/EQ: Central Costa Sur Emergency Repairs (Cost Share 90%) (Generation) | 2 | 4671DR-PR (4671DR) | 980435.39 | 0 | 0 | 98043.53 | 98043.53 | 882391.86 | 90% | 2023-08-08 11:18 | 2026-01-13 17:15 | 4522706.68
713639 | 532 | B - Emergency Protective Measures | FIONA/MARIA/EQ: Carite Emergency Repairs (Riego/Dam) | 0 | 4671DR-PR (4671DR) | 480970 | 0 | 0 | 48097 | 48097 | 432873 | 90% | 2023-07-19 11:37 | 2023-07-18 19:04 | 480970
710612 | 868 | F - Utilities | FIONA/MARIA/EQ: APP CERT - Jobos 1 Permanent Repairs (Generation) | 0 | 4671DR-PR (4671DR) | 0 | 0 | -5995 | 0 | 0 | 0 | 100% | 2023-10-19 18:19 | 2023-10-19 18:19 | 0
963097 | 4931 | F - Utilities | FIONA/MARIA/EQ-Mayaguez Area H Dist. 6702-04 (Distribution) | 0 | 4671DR-PR (4671DR) | 15881.48 | 4466.45 | 0 | 1588.14 | 1588.14 | 14293.34 | 90% | 2026-02-17 21:16 | 2026-02-17 21:16 | 0
817149 | 4891 | F - Utilities | FIONA/MARIA/EQ Bayamon Area D-Bayamon TC 1711 (Substation) | 0 | 4671DR-PR (4671DR) | 0 | 0 | -123071.84 | 0 | 0 | 0 | 90% | 2026-01-09 17:08 |  | 0
737825 | 107925 | F - Utilities | FAAST[Distribution Pole and Conductor Repair - San Juan Group 1 - Phase 2] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
166860 | 11255 | F - Utilities | FAASt-Line 37800 (115kV) - Jobos TC to Cayey TC & Cayey TC to Caguas TC (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
546371 | 11478 | F - Utilities | FAASt- Substation Minor Repairs Group C (Substation) | 0 | 4339DR-PR (4339DR) | 3032891.2 | 384632.14 | 0 | 303289.12 | 303289.12 | 2729602.08 | 90% | 2023-08-22 11:21 | 2023-08-21 20:03 | 3032891.2
164966 | 107201 | F - Utilities | FAASt- Grid Support Units (Generation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
681672 | 11184 | F - Utilities | FAASt Transmission Priority Pole Replacements –38kV Line 2300 (Transmission) | 1 | 4339DR-PR (4339DR) | 216367 | 2243 | 0 | 21636.7 | 21636.7 | 194730.3 | 90% | 2023-01-31 12:56 | 2023-01-30 17:52 | 216367
708577 | 107840 | F - Utilities | FAASt Transmission Line 4800 (38KV) Santa Isabel TC - Santa Isabel SECT | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
166909 | 107215 | F - Utilities | FAASt Transmission Line 37800 Caguas TC to Buen Pastor SECT (TRANSMISSION) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
708575 | 107839 | F - Utilities | FAASt Transmission Line 37400 (115KV) Cambalache TC - Dos Bocas Hydro Plant | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
706498 | 107832 | F - Utilities | FAASt Transmission and Distribution Automation Program Installation of Intelligent Reclosers, Single Phase Reclosers and Fault Current Indicators Group 4 | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
165208 | 107205 | F - Utilities | FAASt Transmission Access Roads (Environmental) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
166904 | 11451 | F - Utilities | FAASt Transmission 115kV Line 37800 Caguas TC to Monacillos TC (TRANSMISSION) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
167508 | 11250 | F - Utilities | FAASt Transmission - Line 50100 (230KV)- Cambalache GP TC to Manati TC (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
166834 | 107214 | F - Utilities | FAASt Transmission - Line 40100 & 40200 - Aguirre SP TC to Jobos TC (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
748180 | 107961 | F - Utilities | FAASt Transm. Advanced Sensors and Wide-Area Monitoring, Protection, and Control (WAMPAC) System (Telecommunication) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
673292 | 11452 | F - Utilities | FAASt Telecom Infrastructure - Cerro Puntas (Telecommunication) | 0 | 4339DR-PR (4339DR) | 8173684.61 | 49577.82 | 0 | 817368.46 | 817368.46 | 7356316.15 | 90% | 2025-10-30 20:15 | 2025-10-30 20:15 | 0
547241 | 11448 | F - Utilities | FAASt Tallaboa 5402 (Substation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
549715 | 11682 | F - Utilities | FAASt Substation Minor Repairs - Group D (Substation) | 1 | 4339DR-PR (4339DR) | 2871257.17 | 288123.63 | 0 | 287125.72 | 287125.72 | 2584131.45 | 90% | 2024-04-12 11:19 | 2024-04-11 15:43 | 2871257.17
684920 | 11573 | F - Utilities | FAASt Substation High Voltage Replacement_Group 1 (Substation) | 2 | 4339DR-PR (4339DR) | 6929384 | 0 | 0 | 692938.4 | 692938.4 | 6236445.6 | 90% | 2023-12-29 12:31 | 2024-03-07 16:11 | 6929384
169276 | 107222 | F - Utilities | FAASt Substation - Viaducto TC - MC 1100 - Equipment Repair & Replacement (Substation) | 0 | 4339DR-PR (4339DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
168226 | 10978 | F - Utilities | FAASt San Juan 115kV Underground Transmission Loop (Transmission) | 1 | 4339DR-PR (4339DR) | 14746039.57 | 0 | 0 | 1474603.96 | 1474603.96 | 13271435.61 | 90% | 2022-12-21 12:37 | 2022-12-20 13:52 | 14746039.57
547271 | 107698 | F - Utilities | FAASt San Jose Substation 8104 Relocation (Substation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
165268 | 11045 | F - Utilities | FAASt Rio Grande Estate Substation CH-2306 (Substation) | 0 | 4339DR-PR (4339DR) | 11683614.71 | 4585370.95 | 0 | 1168361.47 | 1168361.47 | 10515253.24 | 90% | 2022-12-21 12:37 | 2022-12-20 13:52 | 11683614.71
180052 | 11453 | F - Utilities | FAASt Ponce TC to Salinas Urbano TC- 38kV 100 & 200 (Transmission) | 0 | 4339DR-PR (4339DR) | 74520098.48 | 0 | 0 | 7452009.84 | 7452009.84 | 67068088.64 | 90% | 2025-11-05 16:17 | 2025-11-05 16:17 | 0
759051 | 108046 | F - Utilities | FAASt Pole and Conductor - Bayamon Group 4 - Phase 2 (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
549768 | 107709 | F - Utilities | FAASt Physical Security - Group 5 (Substation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
708734 | 107843 | F - Utilities | FAASt Line 800 Comsat Sect - Cidra Sect. (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
334334 | 107518 | F - Utilities | FAASt Line 500 Ponce TC to Costa Sur SP (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
547269 | 11481 | F - Utilities | FAASt Line 2800 (38 kV) Aguadilla Hospital Distrito Sect to T-Bone TO (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
547259 | 11480 | F - Utilities | FAASt Line 2700 (38kV) Victoria TC to Quebradillas Sect. (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
547251 | 11807 | F - Utilities | FAASt Line 2400 Dos Bocas HP to America Apparel (Transmission) | 0 | 4339DR-PR (4339DR) | 50289473.68 | 0 | 0 | 5028947.36 | 5028947.36 | 45260526.32 | 90% | 2026-02-20 19:15 | 2026-02-20 19:15 | 0
334331 | 11528 | F - Utilities | FAASt Line 1900 Dos Bocas HP to San Sebastian (38kV) TC (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
708630 | 107842 | F - Utilities | FAASt L37400 Dorado TC - Vega Baja TC] (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
729286 | 11726 | F - Utilities | FAASt HV Equipment Replacement Group 2 (Substation) | 1 | 4339DR-PR (4339DR) | 15413889.89 | 0 | 0 | 1541388.99 | 1541388.99 | 13872500.9 | 90% | 2024-07-08 11:28 | 2024-07-05 12:49 | 15413889.89
335207 | 107544 | F - Utilities | FAASt Guineo Reservoir – Dredging (Dams/Hydro) | 0 | 4339DR-PR (4339DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
721184 | 11875 | F - Utilities | FAASt Guayabal Dam Repairs and Mitigation (Dams/Hydro) | 0 | 4339DR-PR (4339DR) | 309926400.44 | 156302821.26 | 0 | 30992640.04 | 0 | 0 | 90% |  |  | 309926400.44
177134 | 11440 | F - Utilities | FAASt Guaraguao TC to Comerio TC Line-4100 (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
164988 | 11855 | F - Utilities | FAASt Generation Fleet Project (Generation) | 1 | 4339DR-PR (4339DR) | 643475586.67 | 0 | 0 | 64347558.66 | 64347558.66 | 579128028.01 | 90% | 2024-09-18 19:15 | 2025-10-30 20:15 | 235670650
176954 | 11439 | F - Utilities | FAASt Garzas 1 HP to Garzas 2 HP - 38kV Line 1100 (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
547243 | 107693 | F - Utilities | FAASt Egozcue - 1109 (Substation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
685943 | 11138 | F - Utilities | FAASt Distribution Pole and Conductor Repair Ponce Group 5(Distribution) | 0 | 4339DR-PR (4339DR) | 318232.22 | 63260 | 0 | 31823.22 | 31823.22 | 286409 | 90% | 2023-01-10 13:19 | 2023-01-05 18:56 | 318232.22
542762 | 10690 | F - Utilities | FAASt Distribution Pole and Conductor Repair – Arecibo Group 2 (Distribution) | 1 | 4339DR-PR (4339DR) | 767868 | 157420 | 0 | 76786.8 | 76786.8 | 691081.2 | 90% | 2022-06-03 11:23 | 2022-06-02 12:52 | 767868
688774 | 11207 | F - Utilities | FAASt Distribution Pole and Conductor Repair - Ponce Group 9 (Distribution) | 0 | 4339DR-PR (4339DR) | 541815 | 98484 | 0 | 54181.5 | 54181.5 | 487633.5 | 90% | 2023-01-31 12:56 | 2023-01-30 17:52 | 541815
685263 | 11143 | F - Utilities | FAASt Distribution Pole and Conductor Repair - Ponce Group 6 (Distribution) | 0 | 4339DR-PR (4339DR) | 672383 | 134695 | 0 | 67238.3 | 67238.3 | 605144.7 | 90% | 2022-12-27 11:53 | 2022-12-23 21:14 | 672383
334329 | 10629 | F - Utilities | FAASt Distribution Pole and Conductor Repair - Ponce Group 2 (Distribution) | 1 | 4339DR-PR (4339DR) | 380253 | 64134 | 0 | 38025.3 | 38025.3 | 342227.7 | 90% | 2022-05-20 12:05 | 2022-05-19 20:09 | 380253
679153 | 11106 | F - Utilities | FAASt Distribution Pole and Conductor Repair - Mayagüez Group 6 (Distribution) | 0 | 4339DR-PR (4339DR) | 215184.01 | 51337.5 | 0 | 21518.4 | 21518.4 | 193665.61 | 90% | 2022-12-27 11:53 | 2022-12-23 21:13 | 215184.01
679149 | 11089 | F - Utilities | FAASt Distribution Pole and Conductor Repair - Mayagüez Group 5 (Distribution) | 0 | 4339DR-PR (4339DR) | 157187 | 27443 | 0 | 15718.7 | 15718.7 | 141468.3 | 90% | 2022-12-27 11:53 | 2022-12-23 21:12 | 157187
673795 | 10777 | F - Utilities | FAASt Distribution Pole and Conductor Repair - Mayaguez Group 4 (Distribution) | 0 | 4339DR-PR (4339DR) | 1794117 | 368954 | 0 | 179411.7 | 179411.7 | 1614705.3 | 90% | 2022-08-02 11:42 | 2022-08-01 20:47 | 1794117
704751 | 11311 | F - Utilities | FAASt Distribution Pole and Conductor Repair - Bayamon Group 11 (Distribution) | 0 | 4339DR-PR (4339DR) | 435167 | 96676 | 0 | 43516.7 | 43516.7 | 391650.3 | 90% | 2023-04-06 11:12 | 2023-04-05 20:55 | 435167
704750 | 11314 | F - Utilities | FAASt Distribution Pole and Conductor Repair - Bayamon Group 10 (Distribution) | 0 | 4339DR-PR (4339DR) | 578629 | 92244 | 0 | 57862.9 | 57862.9 | 520766.1 | 90% | 2023-04-06 11:12 | 2023-04-05 20:55 | 578629
673006 | 10694 | F - Utilities | FAASt Costa Sur 002 -Infrastructure projects (Generation) | 1 | 4339DR-PR (4339DR) | 1021800 | 0 | 0 | 102180 | 102180 | 919620 | 90% | 2022-06-27 11:40 | 2025-03-04 18:15 | 1250000
547273 | 107699 | F - Utilities | FAASt Charco Hondo Substation 8008 Relocation (Substation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
169266 | 11489 | F - Utilities | FAASt Centro Medico 1327/1359 Equipment Repair & Replacement (Substation) | 2 | 4339DR-PR (4339DR) | 21332361 | 6537037 | 0 | 2133236.1 | 2133236.1 | 19199124.9 | 90% | 2023-11-03 11:30 | 2024-03-07 15:57 | 21332361
171118 | 107230 | F - Utilities | FAASt Caridad Substation – XFMR MC 1714 (Substation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
547248 | 107695 | F - Utilities | FAASt Canas TC 5002 5018 (Substation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
547247 | 107694 | F - Utilities | FAASt Cambalache TC Relocation (Substation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
547226 | 11689 | F - Utilities | FAASt Barceloneta 11400 TC to Florida TO (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
169576 | 107225 | E - Buildings and Equipment | FAASt Arecibo Regional Office Building (Building) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
548393 | 107705 | E - Buildings and Equipment | FAASt Arecibo Region Repairs (Buildings) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
169798 | 107226 | E - Buildings and Equipment | FAASt Arecibo Electric Service Center (Building) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
669233 | 10568 | F - Utilities | FAASt Aguirre Power Plant 002 Units 1 & 2 Projects (Generation) | 1 | 4339DR-PR (4339DR) | 20905908.95 | 0 | 0 | 2090590.89 | 2090590.89 | 18815318.06 | 90% | 2022-06-06 21:20 | 2022-10-14 19:23 | 20905908.95
169804 | 107227 | E - Buildings and Equipment | FAASt Aguadilla Electric Service Center (Building) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
335168 | 9510 | F - Utilities | FAASt A&E PREPA | 3 | 4339DR-PR (4339DR) | 1133563562.43 | 0 | 0 | 113356356.24 | 113356356.24 | 1020207206.19 | 90% | 2021-10-07 11:40 | 2025-04-28 19:15 | 1086406842.43
176971 | 11373 | F - Utilities | FAASt –38kV Line 8200 - San Juan SP to Catano Sect Line (Transmission) | 0 | 4339DR-PR (4339DR) | 21670623.78 | 0 | 0 | 2167062.37 | 2167062.37 | 19503561.41 | 90% | 2025-11-05 16:17 | 2025-11-05 16:17 | 15567361
165213 | 11244 | F - Utilities | FAASt – Line 5400 – Rio Blanco HP to Daguao TC to Punta Lima TO to Vieques 2501 to Culebra 3801 (Transmission) | 0 | 4339DR-PR (4339DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
746897 | 11860 | F - Utilities | FAASt – BONUS Nuclear Power Plant Repairs (Dams/Hydro) | 0 | 4339DR-PR (4339DR) | 1579615.43 | 178320.9 | 0 | 157961.54 | 157961.54 | 1421653.89 | 90% | 2025-04-28 19:15 | 2025-04-28 19:15 | 1401294.53
704793 | 11691 | F - Utilities | FAASt [Yauco Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 14713958.38
671502 | 11522 | F - Utilities | FAASt [Yabucoa Streetlighting] (Distribution) | 2 | 4339DR-PR (4339DR) | 16883989.33 | 1965608.26 | 0 | 1688398.93 | 1688398.93 | 15195590.4 | 90% | 2023-12-29 12:31 | 2024-03-07 16:15 | 16883989.33
660239 | 10857 | F - Utilities | FAASt [Villalba Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 10872401.71 | 681865.66 | 0 | 1087240.17 | 1087240.17 | 9785161.54 | 90% | 2022-08-24 10:30 | 2022-08-23 13:06 | 10872401.71
698522 | 11582 | F - Utilities | FAASt [Vieques Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 4810499.79
751655 | 107982 | F - Utilities | FAASt [Vieques Microgrid] (Transmission) | 0 | 4339DR-PR (4339DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1063798 | 108241 | F - Utilities | FAASt [Vieques and Culebra Generator & BOP] (Generation) | 0 | 4339DR-PR (4339DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
547343 | 107701 | F - Utilities | FAASt [Victoria TC 7008 Relocation] (Substation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
697183 | 11668 | F - Utilities | FAASt [Vega Baja Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 9248657.11
735483 | 107919 | F - Utilities | FAASt [Vega Baja Streetlighting - Part 3] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
735940 | 11806 | F - Utilities | FAASt [Vega Baja Streetlighting - Part 2] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 11068034.95
724938 | 11673 | F - Utilities | FAASt [Vega Alta Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 14314104.85 | 1869089.52 | 0 | 1431410.48 | 1431410.48 | 12882694.37 | 90% | 2024-05-10 10:17 | 2024-05-09 14:44 | 14314104.85
671396 | 11530 | F - Utilities | FAASt [Utuado Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 20872249.6
752275 | 107993 | F - Utilities | FAASt [Unibon 9501 (Fuse to Breaker)] (Substation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
754351 | 108016 | F - Utilities | FAASt [Underground Circuit Feeders - San Juan Group 2] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
754350 | 108015 | F - Utilities | FAASt [Underground Circuit Feeders - San Juan Group 1] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
675406 | 107767 | F - Utilities | FAASt [Two-Way Land Mobile Radio Network] (Telecommunication) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
691702 | 11326 | F - Utilities | FAASt [Trujillo Alto Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 26286925 | 1009578 | 0 | 2628692.5 | 2628692.5 | 23658232.5 | 90% | 2023-05-17 11:31 | 2023-05-16 19:37 | 26286925
735952 | 11831 | F - Utilities | FAASt [Trujillo Alto Streetlighting - Part 3] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 7111974
735954 | 11772 | F - Utilities | FAASt [Trujillo Alto Streetlighting - Part 2] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 6426439.39
551963 | 11859 | F - Utilities | FAASt [Transport Network Group 1] (Telecommunication) | 1 | 4339DR-PR (4339DR) | 4489030.64 | 0 | 0 | 448903.06 | 549029.68 | 4941267.2 | 90% | 2025-09-17 18:16 | 2025-09-17 18:16 | 84287009
550896 | 10837 | F - Utilities | FAASt [Transmission Priority Pole Replacements – Line 6700] (Transmission) | 2 | 4339DR-PR (4339DR) | 1070274.56 | 0 | 0 | 107027.45 | 69070.3 | 621632.7 | 90% | 2022-08-08 11:30 | 2022-08-05 17:48 | 690703
334468 | 10679 | F - Utilities | FAASt [Transmission Priority Pole Replacements – Line 2200] (Transmission) | 2 | 4339DR-PR (4339DR) | 1217429 | 0 | 0 | 121742.9 | 121742.9 | 1095686.1 | 90% | 2022-07-13 21:08 | 2022-07-11 18:09 | 1217429
668583 | 10800 | F - Utilities | FAASt [Transmission Priority Pole Replacements – Line 13300] (Transmission) | 1 | 4339DR-PR (4339DR) | 453597 | 0 | 0 | 45359.7 | 45359.7 | 408237.3 | 90% | 2022-08-02 11:42 | 2022-08-01 20:47 | 453597
811913 | 108099 | F - Utilities | FAASt [Transmission Priority Pole Replacement Program Line 9600 Bayamon TC – Catano Sect] (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
753781 | 108009 | F - Utilities | FAASt [Transmission Priority Pole Replacement Program Line 800 Comsat Sect – Cidra Sect] (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
753786 | 108012 | F - Utilities | FAASt [Transmission Priority Pole Replacement Program Line 5900 San Juan SP - Crematorio TO] (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
753785 | 108011 | F - Utilities | FAASt [Transmission Priority Pole Replacement Program Line 3300 San Gerardo Sect – Venezuela Sect] (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
753788 | 108014 | F - Utilities | FAASt [Transmission Priority Pole Replacement Program Line 1900 Dos Bocas HP – San Sebastian TC] (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
811923 | 108100 | F - Utilities | FAASt [Transmission Priority Pole Replacement Program Line 16500 Fajardo TC-Dos Marinas] (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
753787 | 108013 | F - Utilities | FAASt [Transmission Priority Pole Replacement Program Line 13700 Mora TC-Isabela TO] (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
668592 | 10891 | F - Utilities | FAASt [Transmission Priority Pole Replacement – Line 9800] (Transmission) | 0 | 4339DR-PR (4339DR) | 420866 | 0 | 0 | 42086.6 | 42086.6 | 378779.4 | 90% | 2022-09-16 11:54 | 2022-09-15 19:37 | 420866
752052 | 107991 | F - Utilities | FAASt [Transmission Line 9900 TAP9905A to Rio Blanco HP] (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
752051 | 107990 | F - Utilities | FAASt [Transmission Line 9300 Juncos TC to ACB 9301] (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
752050 | 107989 | F - Utilities | FAASt [Transmission Line 9300 Gautier Benitez Sect to ACB 9323] (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
752049 | 107988 | F - Utilities | FAASt [Transmission Line 5600 Hotel Rincon to Rincon Substation7301] (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
752048 | 107987 | F - Utilities | FAASt [Transmission Line 3500 Las Lomas Sect to Monacillos TC] (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
752047 | 107986 | F - Utilities | FAASt [Transmission Line 3300 Chardon Sect to Egozcue Sect] (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
752053 | 107992 | F - Utilities | FAASt [Transmission Line 13400 Boqueron TO to Acacias TC] (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
752039 | 107984 | F - Utilities | FAASt [Transmission Line 10000 Sierra Linda TO to Magnolia TO] (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
752041 | 107985 | F - Utilities | FAASt [Transmission Line 1000 Venezuela Sect to Capuchinos Sect] (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
167168 | 11246 | F - Utilities | FAASt [Transmission 115kV Line 37100 Costa Sur ST - Acacias TC] (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
436468 | 11872 | F - Utilities | FAASt [Toro Negro Hydroelectric System Connection](Dams/Hydro) | 0 | 4339DR-PR (4339DR) | 51984905.83 | 11647277.03 | 0 | 5198490.58 | 0 | 0 | 90% |  |  | 40337628.8
703535 | 11636 | F - Utilities | FAASt [Toa Baja Streetlighting] (Distribution) | 1 | 4339DR-PR (4339DR) | 10149325.06 | 620134.69 | 0 | 1014932.51 | 1014932.51 | 9134392.55 | 90% | 2024-06-18 11:28 | 2024-06-17 13:38 | 10149325.06
735959 | 107922 | F - Utilities | FAASt [Toa Baja Streetlighting - Part 3] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
735960 | 11803 | F - Utilities | FAASt [Toa Baja Streetlighting - Part 2] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 9202952.86
693788 | 11547 | F - Utilities | FAASt [Toa Alta Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 6314386.44
737699 | 107923 | F - Utilities | FAASt [Toa Alta Streetlighting - Part 3] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
737707 | 11797 | F - Utilities | FAASt [Toa Alta Streetlighting - Part 2] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 7066938
711862 | 107857 | F - Utilities | FAASt [TL100 Ponce TC to Santa Isabel Sect](Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
334470 | 11708 | F - Utilities | FAASt [TL 3100 Monacillos TC to Sabana Llana TC] (Transmission) | 0 | 4339DR-PR (4339DR) | 47112099.92 | 0 | 0 | 4711209.99 | 4711209.99 | 42400889.93 | 90% | 2025-11-05 16:17 | 2025-11-05 16:17 | 0
756999 | 108031 | F - Utilities | FAASt [TL 1900 Lares TO to San Sebastian] (Transmission) | 0 | 4339DR-PR (4339DR) | 29319358.78 | 0 | 0 | 2931935.87 | 0 | 0 | 90% |  |  | 0
756997 | 108030 | F - Utilities | FAASt [TL 1900 Caguanas to Lares TO] (Transmission) | 0 | 4339DR-PR (4339DR) | 40557533.61 | 0 | 0 | 4055753.36 | 0 | 0 | 90% |  |  | 0
712979 | 107863 | F - Utilities | FAASt [TL 12600 Humacao TC to Verde Mar] (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
679006 | 11862 | E - Buildings and Equipment | FAASt [Test and Technology Laboratory] (Building) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
753301 | 108003 | F - Utilities | FAASt [Telecom Infrastructure Group H] (Telecommunication) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
753302 | 108004 | F - Utilities | FAASt [Telecom Infrastructure Group G] (Telecommunication) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
713592 | 107874 | F - Utilities | FAASt [Telecom Infrastructure – Group F] (Telecommunications) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
814793 | 108106 | F - Utilities | FAASt [Telecom Infrastructure – Group F] (Telecommunication) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
711291 | 107855 | F - Utilities | FAASt [Telecom Infrastructure – Group E] (Telecommunication) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
704805 | 11863 | F - Utilities | FAASt [Telecom Infrastructure – Group D] (Telecommunication) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
704763 | 107825 | F - Utilities | FAASt [Telecom Infrastructure – Group C] (Telecommunication) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
678800 | 11425 | F - Utilities | FAASt [Telecom Infrastructure – Group B] (Telecommunication) | 0 | 4339DR-PR (4339DR) | 13204825.28 | 55895.84 | 0 | 1320482.52 | 1320482.52 | 11884342.76 | 90% | 2025-11-05 16:17 | 2025-11-05 16:17 | 0
679035 | 11861 | F - Utilities | FAASt [Telecom Infrastructure – Group A] (Telecommunication) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
814792 | 108105 | F - Utilities | FAASt [Telecom Infrastructure – Group E] (Telecommunication) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
708637 | 11723 | F - Utilities | FAASt [T-Pole Program Line 3700] (Transmission) | 1 | 4339DR-PR (4339DR) | 377354.58 | 73393.66 | 0 | 37735.45 | 37735.45 | 339619.13 | 90% | 2024-08-26 10:08 | 2024-12-16 23:15 | 303960.92
712980 | 11754 | F - Utilities | FAASt [T-Pole Program Line 3000] (Transmission) | 0 | 4339DR-PR (4339DR) | 631194.26 | 72117.49 | 0 | 63119.42 | 63119.42 | 568074.84 | 90% | 2024-11-01 15:15 | 2024-11-01 15:15 | 559076.77
711670 | 11719 | F - Utilities | FAASt [T-Pole Program Line 100] (Transmission) | 1 | 4339DR-PR (4339DR) | 118160.28 | 23372.71 | 0 | 11816.03 | 11816.03 | 106344.25 | 90% | 2024-06-18 11:28 | 2024-06-17 13:38 | 118160.28
549725 | 11707 | F - Utilities | FAASt [Substation Minor Repairs - Group E] (Substation) | 0 | 4339DR-PR (4339DR) | 4503783.21 | 579767.52 | 0 | 450378.32 | 450378.32 | 4053404.89 | 90% | 2024-05-10 10:17 | 2024-05-09 14:44 | 4503783.21
713149 | 107867 | F - Utilities | FAASt [Substation Minor Repairs - Group E-1] (Substation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
713497 | 107873 | F - Utilities | FAASt [Substation Minor Repairs - Group C-1] | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
713459 | 107870 | F - Utilities | FAASt [Substation Minor Repairs - Group A-2] (Substation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
713491 | 107871 | F - Utilities | FAASt [Substation Minor Repairs - Group A-1] (Substation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
713496 | 107872 | F - Utilities | FAASt [Substation Minor Repairs - Group - H] (Substations) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
752277 | 107995 | F - Utilities | FAASt [Substation Ciales 8701] (Substation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
435769 | 107547 | F - Utilities | FAASt [South Coast Irrigation District - Canals] (Dams/Hydro) | 0 | 4339DR-PR (4339DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
551927 | 107736 | F - Utilities | FAASt [SCADA Remote Access and RTU Replacements Group 3] (Telecommunication) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
551926 | 107735 | F - Utilities | FAASt [SCADA Remote Access and RTU Replacements Group 2] (Telecommunication) | 0 | 4339DR-PR (4339DR) | 6340930.6 | 1073462.61 | 0 | 634093.06 | 634093.06 | 5706837.54 | 90% | 2026-03-01 18:16 | 2026-03-01 18:16 | 0
551925 | 11537 | F - Utilities | FAASt [SCADA Remote Access and RTU Replacements Group 1] (Telecommunication) | 0 | 4339DR-PR (4339DR) | 7664336.14 | 1701923.62 | 0 | 766433.61 | 766433.61 | 6897902.53 | 90% | 2024-11-01 15:15 | 2024-11-01 15:15 | 16125402.73
550998 | 107724 | F - Utilities | FAASt [Santurce Planta (Sect) 1116] (Substation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
704757 | 11638 | F - Utilities | FAASt [Santa Isabel Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 7956662
704744 | 11626 | F - Utilities | FAASt [San Sebastian Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 22246737.73
704929 | 11635 | F - Utilities | FAASt [San Lorenzo Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 16628674.19
666894 | 11519 | F - Utilities | FAASt [San Juan Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 30550204.86
737712 | 11836 | F - Utilities | FAAST [San Juan Streetlighting - Part 3] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 27223280
746108 | 11779 | F - Utilities | FAASt [San Juan Streetlighting - Part 2] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 26445766.74
551827 | 107732 | F - Utilities | FAASt [San Juan Region Repair] (Building) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
956349 | 108157 | F - Utilities | FAASt [San Juan Region 1 Line 36800 (115kV) – Canovanas TC to Palmer TC] (Vegetation) | 1 | 4339DR-PR (4339DR) | 2077241.3 | 1607206.7 | 0 | 207724.13 | 136441.61 | 1227974.51 | 90% | 2025-09-17 19:15 | 2025-09-17 19:15 | 0
956332 | 108147 | F - Utilities | FAASt [San Juan Region 1 - Feeder 2401-01] (Vegetation) | 0 | 4339DR-PR (4339DR) | 10571189.26 | 7906327.92 | 0 | 1057118.92 | 0 | 0 | 90% |  |  | 0
956335 | 108148 | F - Utilities | FAASt [San Juan Region 1 - Feeder 2301-02] (Vegetation) | 0 | 4339DR-PR (4339DR) | 7135680.6 | 5336866.97 | 0 | 713568.06 | 0 | 0 | 90% |  |  | 0
687480 | 11085 | F - Utilities | FAASt [San Juan Power Plant 002 Units 7 & 8] (Generation) | 1 | 4339DR-PR (4339DR) | 19847861.69 | 0 | 0 | 1984786.16 | 1984786.16 | 17863075.53 | 90% | 2022-12-27 11:53 | 2025-01-07 21:15 | 19847861.69
667744 | 10608 | F - Utilities | FAASt [San Juan Power Plant - Auxiliary Infrastructure] (Generation) | 5 | 4339DR-PR (4339DR) | 3009037 | 0 | 0 | 300903.7 | 300903.7 | 2708133.3 | 90% | 2022-06-16 11:23 | 2026-02-20 19:15 | 3192936
662947 | 10615 | F - Utilities | FAASt [San Juan 001 – Units 5 & 6] (Generation) | 2 | 4339DR-PR (4339DR) | 75093958.51 | 0 | 0 | 7509395.85 | 7509395.85 | 67584562.66 | 90% | 2022-06-16 11:23 | 2024-08-23 22:26 | 75093958.51
761563 | 108055 | F - Utilities | FAASt [San Jose Relocation] (Substation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
659968 | 11318 | F - Utilities | FAASt [San Germán Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 34882926 | 4033578 | 0 | 3488292.6 | 3488292.6 | 31394633.4 | 90% | 2023-05-04 11:30 | 2023-05-03 14:10 | 34882926
548596 | 107708 | E - Buildings and Equipment | FAASt [San German Electrical Service Center] (Building) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
724601 | 11739 | F - Utilities | FAASt [Salinas Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 13708224.43 | 1611020.9 | 0 | 1370822.44 | 1370822.44 | 12337401.99 | 90% | 2024-07-08 11:28 | 2024-07-05 12:59 | 13708224.43
724599 | 11738 | F - Utilities | FAASt [Sabana Grande Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 10744021.82
682331 | 107777 | F - Utilities | FAASt [RTU and Telecommunication Replacements Group 1 - Mayaguez Area] (Telecommunication) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
693615 | 11685 | F - Utilities | FAASt [Rio Grande Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 7076878.32
737798 | 107924 | F - Utilities | FAASt [Rio Grande Streetlighting - Part 3] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
737804 | 11809 | F - Utilities | FAASt [Rio Grande Streetlighting - Part 2 ] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 6104606.88
180723 | 107310 | F - Utilities | FAASt [Rio Blanco Hydroelectric System] (Dams/Hydro) | 0 | 4339DR-PR (4339DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
714641 | 11630 | F - Utilities | FAASt [Rincón Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 11536809.84 | 694470.58 | 0 | 1153680.98 | 1153680.98 | 10383128.86 | 90% | 2026-03-01 18:15 | 2026-03-01 18:15 | 12467409.38
756479 | 108029 | F - Utilities | FAASt [Region 6-Ponce Group B] Low Density (Vegetation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
740414 | 107938 | F - Utilities | FAASt [Region 6-Ponce Group B] (Vegetation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
727529 | 107893 | F - Utilities | FAASt [Region 6 Ponce TL - 115kV] (Vegetation) | 0 | 4339DR-PR (4339DR) | 8305756.13 | 6426387.93 | 0 | 830575.61 | 830575.61 | 7475180.52 | 90% | 2026-03-01 18:15 | 2026-03-01 18:15 | 0
741104 | 107945 | F - Utilities | FAASt [Region 6 Ponce Subs/Telecom] (Vegetation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
727530 | 107894 | F - Utilities | FAASt [Region 6 -Ponce Group C] (Vegetation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
750063 | 107965 | F - Utilities | FAASt [Region 6 -Ponce Group A] Low Density (Vegetation) | 0 | 4339DR-PR (4339DR) | 60044753.52 | 44155237.62 | 0 | 6004475.35 | 6004475.35 | 0 | 90% |  |  | 0
727531 | 11715 | F - Utilities | FAASt [Region 6 -Ponce Group A] High Density (Vegetation) | 0 | 4339DR-PR (4339DR) | 25913934.11 | 19064883.85 | 0 | 2591393.41 | 2591393.41 | 23322540.7 | 90% | 2025-04-28 19:15 | 2025-04-28 19:15 | 20024388.95
756477 | 108028 | F - Utilities | FAASt [Region 5-Mayaguez Group B] Low Density (Vegetation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
740411 | 107937 | F - Utilities | FAASt [Region 5-Mayaguez Group B] (Vegetation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
727657 | 107900 | F - Utilities | FAASt [Region 5 Mayaguez TL - 115kV] (Vegetation) | 0 | 4339DR-PR (4339DR) | 2553192.59 | 1975474.09 | 0 | 255319.25 | 255319.25 | 2297873.34 | 90% | 2026-03-01 18:16 | 2026-03-01 18:16 | 0
741102 | 107944 | F - Utilities | FAASt [Region 5 Mayaguez Subs/Telecom] (Vegetation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
727562 | 107897 | F - Utilities | FAASt [Region 5 -Mayaguez Group C] (Vegetation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
750068 | 107969 | F - Utilities | FAASt [Region 5 -Mayaguez Group A] Low Density (Vegetation) | 0 | 4339DR-PR (4339DR) | 52301929.37 | 38461380.62 | 0 | 5230192.93 | 5230192.93 | 47071736.44 | 90% | 2026-03-01 18:15 | 2026-03-01 18:15 | 0
728832 | 11718 | F - Utilities | FAASt [Region 5 -Mayaguez Group A] High Density (Vegetation) | 0 | 4339DR-PR (4339DR) | 14260691.9 | 10493001.48 | 0 | 1426069.19 | 1426069.19 | 12834622.71 | 90% | 2025-04-28 19:15 | 2025-04-28 19:15 | 17078572.78
756476 | 108027 | F - Utilities | FAASt [Region 4-Caguas Group B] Low Density (Vegetation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
740409 | 107935 | F - Utilities | FAASt [Region 4-Caguas Group B] (Vegetation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
727606 | 107898 | F - Utilities | FAASt [Region 4 Caguas TL - 115kV] (Vegetation) | 0 | 4339DR-PR (4339DR) | 3981089.18 | 3080276.26 | 0 | 398108.91 | 398108.91 | 3582980.27 | 90% | 2026-03-01 18:16 | 2026-03-01 18:16 | 0
741100 | 107942 | F - Utilities | FAASt [Region 4 Caguas Subs/Telecom] (Vegetation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
727694 | 107903 | F - Utilities | FAASt [Region 4 -Caguas Group C] (Vegetation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
750066 | 107967 | F - Utilities | FAASt [Region 4 -Caguas Group A] Low Density (Vegetation) | 0 | 4339DR-PR (4339DR) | 107563717.79 | 79097232.76 | 0 | 10756371.77 | 10756371.77 | 96807346.02 | 90% | 2026-03-01 17:15 | 2026-03-01 17:15 | 0
727692 | 11724 | F - Utilities | FAASt [Region 4 -Caguas Group A] High Density (Vegetation) | 0 | 4339DR-PR (4339DR) | 28052090.37 | 20637925.62 | 0 | 2805209.03 | 2805209.03 | 25246881.34 | 90% | 2025-04-28 19:15 | 2025-04-28 19:15 | 33353341.65
756474 | 108025 | F - Utilities | FAASt [Region 3-Bayamon Group B] Low Density (Vegetation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
740408 | 107934 | F - Utilities | FAASt [Region 3-Bayamon Group B] (Vegetation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
727522 | 107892 | F - Utilities | FAASt [Region 3 Bayamon TL - 115kV] (Vegetation) | 0 | 4339DR-PR (4339DR) | 3442081.85 | 2663231.73 | 0 | 344208.18 | 344208.18 | 3097873.67 | 90% | 2026-03-01 18:16 | 2026-03-01 18:16 | 0
741098 | 107941 | F - Utilities | FAASt [Region 3 Bayamon Subs/Telecom] (Vegetation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
727558 | 107896 | F - Utilities | FAASt [Region 3 -Bayamon Group C] (Vegetation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
750065 | 107966 | F - Utilities | FAASt [Region 3 -Bayamon Group A] Low Density (Vegetation) | 0 | 4339DR-PR (4339DR) | 70173723.91 | 51603800.04 | 0 | 7017372.39 | 7017372.39 | 63156351.52 | 90% | 2026-03-01 18:15 | 2026-03-01 18:15 | 0
727572 | 11720 | F - Utilities | FAASt [Region 3 -Bayamon Group A] High Density (Vegetation) | 0 | 4339DR-PR (4339DR) | 42586648.64 | 31317875.94 | 0 | 4258664.86 | 4258664.86 | 38327983.78 | 90% | 2026-03-01 18:15 | 2026-03-01 18:15 | 29267077.62
756475 | 108026 | F - Utilities | FAASt [Region 2-Arecibo Group B] Low Density (Vegetation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
740410 | 107936 | F - Utilities | FAASt [Region 2-Arecibo Group B] (Vegetation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
727659 | 107901 | F - Utilities | FAASt [Region 2 Arecibo TL - 115kV] (Vegetation) | 0 | 4339DR-PR (4339DR) | 4214343.82 | 3260751.68 | 0 | 421434.38 | 421434.38 | 3792909.44 | 90% | 2026-03-01 18:16 | 2026-03-01 18:16 | 0
741101 | 107943 | F - Utilities | FAASt [Region 2 Arecibo Subs/Telecom] (Vegetation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
727540 | 107895 | F - Utilities | FAASt [Region 2 -Arecibo Group C] (Vegetation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
750067 | 107968 | F - Utilities | FAASt [Region 2 -Arecibo Group A] Low Density (Vegetation) | 0 | 4339DR-PR (4339DR) | 56797288.74 | 41767142.56 | 0 | 5679728.87 | 5679728.87 | 51117559.87 | 90% | 2026-03-01 18:15 | 2026-03-01 18:15 | 0
728827 | 11714 | F - Utilities | FAASt [Region 2 -Arecibo Group A] High Density (Vegetation) | 0 | 4339DR-PR (4339DR) | 18194308.81 | 13386633.34 | 0 | 1819430.88 | 1819430.88 | 16374877.93 | 90% | 2025-04-28 19:15 | 2025-04-28 19:15 | 4339077.99
756472 | 108024 | F - Utilities | FAASt [Region 1-San Juan Group B] Low Density (Vegetation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
740406 | 107933 | F - Utilities | FAASt [Region 1-San Juan Group B] (Vegetation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
727608 | 107899 | F - Utilities | FAASt [Region 1 San Juan TL - 115kV] (Vegetation) | 0 | 4339DR-PR (4339DR) | 4453902.63 | 3446104.8 | 0 | 445390.26 | 445390.26 | 4008512.37 | 90% | 2026-03-01 18:16 | 2026-03-01 18:16 | 0
741097 | 107940 | F - Utilities | FAASt [Region 1 San Juan Subs/Telecom] (Vegetation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
727691 | 107902 | F - Utilities | FAASt [Region 1 -San Juan Group C] (Vegetation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
723883 | 11696 | F - Utilities | FAASt [Region 1 -San Juan Group A] (Vegetation) | 2 | 4339DR-PR (4339DR) | 24944459.56 | 18371390.02 | 0 | 2494445.95 | 2494445.95 | 22450013.61 | 90% | 2024-06-05 11:15 | 2026-03-01 18:16 | 18151116.72
724716 | 11729 | F - Utilities | FAASt [Quebradillas Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 12027498.14
551912 | 107733 | F - Utilities | FAASt [Puerto Nuevo - 1520] (Substation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064452 | 108242 | F - Utilities | FAASt [Priority Pole Replacement Program Line 800 Comsat Sect – Cidra Sect] / Former project 753781(Transmission) | 0 | 4339DR-PR (4339DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
750151 | 107971 | F - Utilities | FAASt [Priority Pole Replacement Program (Line 700 Costa Sur SP – Yauco 2 HP)] (Transmission) | 0 | 4339DR-PR (4339DR) | 255832.03 | 12563.87 | 0 | 25583.2 | 25583.2 | 230248.83 | 90% | 2026-01-16 16:15 | 2026-01-16 16:15 | 0
749060 | 11874 | F - Utilities | FAASt [Priority Pole Replacement Program (Line 5600 Victoria TC – Añasco TC)] (Transmission) | 0 | 4339DR-PR (4339DR) | 1316113.03 | 140677.54 | 0 | 131611.3 | 131611.3 | 1184501.73 | 90% | 2026-03-01 18:16 | 2026-03-01 18:16 | 860152.65
750150 | 107970 | F - Utilities | FAASt [Priority Pole Replacement Program (Line 4800 Santa Isabel TC – Toro Negro 1 HP)] (Transmission) | 0 | 4339DR-PR (4339DR) | 134148.36 | 8224.8 | 0 | 13414.83 | 13414.83 | 120733.53 | 90% | 2025-11-05 16:16 | 2025-11-05 16:16 | 0
750168 | 107972 | F - Utilities | FAASt [Priority Pole Replacement Program (Line 4800 Santa Isabel TC – Aibonito TO)] (Transmission) | 0 | 4339DR-PR (4339DR) | 469229.99 | 37472.84 | 0 | 46922.99 | 46922.99 | 422307 | 90% | 2025-11-25 18:15 | 2025-11-25 18:15 | 0
753782 | 108010 | F - Utilities | FAASt [Priority Pole Replacement Program (Line 3100 Monacillos TC – Sabana Llana TC)] (Transmission) | 0 | 4339DR-PR (4339DR) | 131580.76 | 2218.84 | 0 | 13158.07 | 13158.07 | 118422.69 | 90% | 2025-10-30 20:15 | 2025-10-30 20:15 | 0
749072 | 11877 | F - Utilities | FAASt [Priority Pole Replacement Program (Line 2700 Aguadilla Hospital Distrito Sect – Mora TC)] (Transmission) | 0 | 4339DR-PR (4339DR) | 827007.6 | 59629.81 | 0 | 82700.76 | 82700.76 | 744306.84 | 90% | 2025-11-05 16:16 | 2025-11-05 16:16 | 189251.19
711819 | 11840 | F - Utilities | FAASt [Priority Pole Replacement Program (Line 13400 Acacias TC- San German Sect - La Parguera Sect)] (Transmission) | 0 | 4339DR-PR (4339DR) | 2399911.66 | 197625.13 | 0 | 239991.16 | 239991.16 | 2159920.5 | 90% | 2026-03-01 18:16 | 2026-03-01 18:16 | 1705844
746545 | 11824 | F - Utilities | FAASt [Primary Control Center / Secondary Data Center & Control Room] (Buildings) | 0 | 4339DR-PR (4339DR) | 115638378 | 0 | 0 | 11563837.8 | 0 | 0 | 90% |  |  | 0
551928 | 107737 | E - Buildings and Equipment | FAASt [PRIMARY AND SECONDARY CONTROL CENTERS] (Building) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
817248 | 108115 | F - Utilities | FAASt [Power Plant Repairs & System Restoration] (Generation) | 0 | 4339DR-PR (4339DR) | 89680589.58 | 0 | 0 | 8968058.95 | 8968058.95 | 80712530.63 | 90% | 2025-09-17 18:16 | 2025-09-17 18:16 | 0
678794 | 11527 | F - Utilities | FAASt [Ponce Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 16043135.52
734760 | 11830 | F - Utilities | FAASt [Ponce Streetlighting - Part 3] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 13799462
734728 | 11774 | F - Utilities | FAASt [Ponce Streetlighting - Part 2] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 14401115.78
956343 | 108154 | F - Utilities | FAASt [Ponce Region 6 Line 4800 (38kV) – Toro Negro to Aibonito, Santa Isabel] (Vegetation) | 0 | 4339DR-PR (4339DR) | 2361582.5 | 2178489.85 | 0 | 236158.25 | 236158.25 | 0 | 90% |  |  | 0
956356 | 108159 | F - Utilities | FAASt [Ponce Region 6 Line 39000 (115kV) – Aguas Buenas Substation to Hacienda San Jose] (Vegetation) | 1 | 4339DR-PR (4339DR) | 388903.06 | 302418.26 | 0 | 38890.3 | 38890.3 | 350012.76 | 90% | 2025-09-17 19:15 | 2026-03-01 18:16 | 0
956341 | 108152 | F - Utilities | FAASt [Ponce Region 6 Feeder 5803-02] (Vegetation) | 0 | 4339DR-PR (4339DR) | 93335.37 | 69806.72 | 0 | 9333.53 | 9333.53 | 0 | 90% |  |  | 0
956340 | 108151 | F - Utilities | FAASt [Ponce Region 6 Feeder 5602-02] (Vegetation) | 0 | 4339DR-PR (4339DR) | 4803574.98 | 3592655.29 | 0 | 480357.49 | 0 | 0 | 90% |  |  | 0
738120 | 11850 | F - Utilities | FAASt [Pole and Conductor Repair-Carolina Group 2- Phase 2] (Distribution) | 0 | 4339DR-PR (4339DR) | 11451170.81 | 409899.81 | 0 | 1145117.08 | 1145117.08 | 10306053.73 | 90% | 2024-11-25 16:15 | 2024-11-25 16:15 | 11451170.81
705503 | 11476 | F - Utilities | FAASt [Pole and Conductor Repair Mayaguez Groups 15,16,17,18 & 19] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 1176665.69
817250 | 108117 | F - Utilities | FAASt [Pole and Conductor Repair -San Juan Group 4 - Phase 2] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
790443 | 108070 | F - Utilities | FAASt [Pole and Conductor Repair -San Juan Group 3 Phase 2 (Distribution) | 1 | 4339DR-PR (4339DR) | 251334.89 | 7501.67 | 0 | 25133.48 | 18669.7 | 168027.3 | 90% | 2025-09-03 20:15 | 2025-09-03 20:15 | 0
817247 | 108114 | F - Utilities | FAASt [Pole and Conductor Repair -Ponce Group 3 - Phase 2] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
752540 | 107999 | F - Utilities | FAASt [Pole and Conductor Repair -Mayaguez Group 4 Phase 2] (Distribution) | 0 | 4339DR-PR (4339DR) | 7111613.91 | 0 | 0 | 711161.39 | 711161.39 | 6400452.52 | 90% | 2025-09-25 16:15 | 2025-09-25 16:15 | 0
817242 | 108113 | F - Utilities | FAASt [Pole and Conductor Repair -Caguas Group 8 - Phase 2] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
790427 | 108069 | F - Utilities | FAASt [Pole and Conductor Repair -Caguas Group 5 Phase 2 (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
790446 | 108071 | F - Utilities | FAASt [Pole and Conductor Repair -Caguas Group 4 Phase 2 (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
735474 | 107918 | F - Utilities | FAASt [Pole and Conductor Repair -Caguas Group 3 Phase 2] (Distribution) | 0 | 4339DR-PR (4339DR) | 14075641.42 | 0 | 0 | 1407564.14 | 1407564.14 | 12668077.28 | 90% | 2025-09-17 18:16 | 2025-09-17 18:16 | 0
711856 | 11746 | F - Utilities | FAASt [Pole and Conductor Repair - Bayamon Group 3 - Phase 2] (Distribution) | 1 | 4339DR-PR (4339DR) | 11335984.34 | 395663.43 | 0 | 1133598.43 | 1133598.43 | 10202385.91 | 90% | 2024-08-26 10:08 | 2024-12-16 23:15 | 10940320.91
682028 | 11166 | F - Utilities | FAASt [Pole and Conductor Repair - San Juan Group 8] (Distribution) | 0 | 4339DR-PR (4339DR) | 537125.3 | 105743.62 | 0 | 53712.53 | 53712.53 | 483412.77 | 90% | 2023-01-10 13:19 | 2023-01-05 18:58 | 537125.3
742026 | 11716 | F - Utilities | FAASt [Pole and Conductor Repair - San Juan Group 2 - Phase 2] (Distribution) | 1 | 4339DR-PR (4339DR) | 1117411.77 | 84035.96 | 0 | 111741.18 | 111741.18 | 1005670.59 | 90% | 2024-05-31 11:36 | 2024-05-30 12:36 | 1117411.77
742070 | 11753 | F - Utilities | FAASt [Pole and Conductor Repair - San Juan Group 1 - Phase 2] (Distribution) | 0 | 4339DR-PR (4339DR) | 5666787.43 | 205587.38 | 0 | 566678.74 | 566678.74 | 5100108.69 | 90% | 2024-06-18 11:28 | 2024-06-17 13:38 | 5666787.43
705584 | 11365 | F - Utilities | FAASt [Pole and Conductor Repair - Ponce Groups 14 & 15] (Distribution) | 0 | 4339DR-PR (4339DR) | 1842979 | 378483 | 0 | 184297.9 | 184297.9 | 1658681.1 | 90% | 2023-06-16 12:55 | 2023-06-15 13:07 | 1842979
682228 | 11196 | F - Utilities | FAASt [Pole and Conductor Repair - Ponce Group 8] (Distribution) | 0 | 4339DR-PR (4339DR) | 952661.42 | 176882.42 | 0 | 95266.14 | 95266.14 | 857395.28 | 90% | 2023-01-31 12:56 | 2023-01-30 17:52 | 952661.42
686480 | 11229 | F - Utilities | FAASt [Pole and Conductor Repair - Ponce Group 7] (Distribution) | 0 | 4339DR-PR (4339DR) | 632056 | 108652 | 0 | 63205.6 | 63205.6 | 568850.4 | 90% | 2023-02-16 12:51 | 2023-02-15 12:01 | 632056
738667 | 107927 | F - Utilities | FAASt [Pole and Conductor Repair - Ponce Group 2 - Phase 2] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
708579 | 11508 | F - Utilities | FAASt [Pole and Conductor Repair - Ponce Group 16, 17, 18 & 19] (Distribution) | 1 | 4339DR-PR (4339DR) | 2154006.76 | 389437.84 | 0 | 215400.68 | 215400.68 | 1938606.08 | 90% | 2023-10-23 11:32 | 2023-10-20 18:00 | 2154006.76
701555 | 11275 | F - Utilities | FAASt [Pole and Conductor Repair - Ponce Group 13] (Distribution) | 0 | 4339DR-PR (4339DR) | 649427 | 102417 | 0 | 64942.7 | 64942.7 | 584484.3 | 90% | 2023-03-08 12:36 | 2023-03-07 20:35 | 649427
701552 | 11257 | F - Utilities | FAASt [Pole and Conductor Repair - Ponce Group 12] (Distribution) | 0 | 4339DR-PR (4339DR) | 238162 | 51841 | 0 | 23816.2 | 23816.2 | 214345.8 | 90% | 2023-03-08 12:36 | 2023-03-07 20:33 | 238162
701545 | 11269 | F - Utilities | FAASt [Pole and Conductor Repair - Ponce Group 11] (Distribution) | 0 | 4339DR-PR (4339DR) | 616229 | 129039 | 0 | 61622.9 | 61622.9 | 554606.1 | 90% | 2023-03-08 12:36 | 2023-03-07 20:34 | 616229
688625 | 11279 | F - Utilities | FAASt [Pole and Conductor Repair - Ponce Group 10] (Distribution) | 1 | 4339DR-PR (4339DR) | 901290.28 | 191275.59 | 0 | 90129.03 | 90129.03 | 811161.25 | 90% | 2023-03-20 11:45 | 2023-03-18 00:53 | 901290.28
738670 | 11712 | F - Utilities | FAASt [Pole and Conductor Repair - Ponce Group 1 - Phase 2] (Distribution) | 0 | 4339DR-PR (4339DR) | 5074511.01 | 147870.9 | 0 | 507451.1 | 507451.1 | 4567059.91 | 90% | 2024-11-25 16:15 | 2024-11-25 16:15 | 4926640.11
682210 | 11169 | F - Utilities | FAASt [Pole and Conductor Repair - Mayagüez Group 9] (Distribution) | 0 | 4339DR-PR (4339DR) | 239847.61 | 41796.87 | 0 | 23984.76 | 23984.76 | 215862.85 | 90% | 2023-01-24 13:14 | 2023-01-23 15:18 | 239847.61
685370 | 11150 | F - Utilities | FAASt [Pole and Conductor Repair - Mayagüez Group 8] (Distribution) | 0 | 4339DR-PR (4339DR) | 83809 | 14986 | 0 | 8380.9 | 8380.9 | 75428.1 | 90% | 2023-01-10 13:19 | 2023-01-05 18:57 | 83809
686453 | 11152 | F - Utilities | FAASt [Pole and Conductor Repair - Mayagüez Group 7] (Distribution) | 0 | 4339DR-PR (4339DR) | 25579 | 4995 | 0 | 2557.9 | 2557.9 | 23021.1 | 90% | 2022-12-27 11:53 | 2022-12-23 21:14 | 25579
750692 | 107979 | F - Utilities | FAASt [Pole and Conductor Repair - Mayaguez Group 3 - Phase 2] (Distribution) | 0 | 4339DR-PR (4339DR) | 12921047 | 0 | 0 | 1292104.7 | 1292104.7 | 11628942.3 | 90% | 2025-09-25 16:15 | 2025-09-25 16:15 | 0
738674 | 107928 | F - Utilities | FAASt [Pole and Conductor Repair - Mayaguez Group 2 - Phase 2] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
701495 | 11263 | F - Utilities | FAASt [Pole and Conductor Repair - Mayagüez Group 14] (Distribution) | 0 | 4339DR-PR (4339DR) | 25678.75 | 5830.39 | 0 | 2567.87 | 2567.87 | 23110.88 | 90% | 2023-03-02 12:24 | 2023-03-01 19:03 | 25678.75
688629 | 11277 | F - Utilities | FAASt [Pole and Conductor Repair - Mayagüez Group 13] (Distribution) | 0 | 4339DR-PR (4339DR) | 134828.92 | 27886.93 | 0 | 13482.89 | 13482.89 | 121346.03 | 90% | 2023-03-08 12:36 | 2023-03-07 20:36 | 134828.92
688630 | 11273 | F - Utilities | FAASt [Pole and Conductor Repair - Mayagüez Group 12] (Distribution) | 1 | 4339DR-PR (4339DR) | 52719.38 | 9990.97 | 0 | 5271.94 | 5271.94 | 47447.44 | 90% | 2023-03-08 12:36 | 2023-03-07 20:36 | 52719.38
688472 | 11217 | F - Utilities | FAASt [Pole and Conductor Repair - Mayaguez Group 11] (Distribution) | 1 | 4339DR-PR (4339DR) | 179894.86 | 14986 | 0 | 17989.49 | 17989.49 | 161905.37 | 90% | 2023-02-16 12:51 | 2023-02-15 12:01 | 179894.86
682180 | 11168 | F - Utilities | FAASt [Pole and Conductor Repair - Mayagüez Group 10] (Distribution) | 0 | 4339DR-PR (4339DR) | 54402 | 11028 | 0 | 5440.2 | 5440.2 | 48961.8 | 90% | 2023-01-10 13:19 | 2023-01-05 18:58 | 54402
738672 | 11686 | F - Utilities | FAASt [Pole and Conductor Repair - Mayaguez Group 1 - Phase 2] (Distribution) | 0 | 4339DR-PR (4339DR) | 10619758.37 | 306131.37 | 0 | 1061975.83 | 1061975.83 | 9557782.54 | 90% | 2024-11-25 16:15 | 2024-11-25 16:15 | 10726511.94
806936 | 108098 | F - Utilities | FAASt [Pole and Conductor Repair - Carolina Group 3 - Phase 2] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
738692 | 107929 | F - Utilities | FAASt [Pole and Conductor Repair - Carolina Group 1 - Phase 2] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
806935 | 108097 | F - Utilities | FAASt [Pole and Conductor Repair - Caguas Group 6 - Phase 2] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
738971 | 11812 | F - Utilities | FAASt [Pole and Conductor Repair - Caguas Group 2 - Phase 2] (Distribution) | 0 | 4339DR-PR (4339DR) | 14261249.67 | 377123.67 | 0 | 1426124.96 | 1426124.96 | 12835124.71 | 90% | 2025-02-06 20:16 | 2025-02-06 20:16 | 13884126
711888 | 11640 | F - Utilities | FAASt [Pole and Conductor Repair - Caguas Group 1 - Phase 2] (Distribution) | 1 | 4339DR-PR (4339DR) | 5591713.87 | 165903.3 | 0 | 559171.39 | 559171.39 | 5032542.48 | 90% | 2024-03-22 10:16 | 2024-03-21 20:04 | 5591713.87
710094 | 11639 | F - Utilities | FAASt [Pole and Conductor Repair - Bayamon Group 1 - Phase 2] (Distribution) | 0 | 4339DR-PR (4339DR) | 7291385.82 | 195136.32 | 0 | 729138.58 | 729138.58 | 6562247.24 | 90% | 2024-11-01 15:15 | 2024-11-01 15:15 | 7291385.82
682178 | 11201 | F - Utilities | FAASt [Pole and Conductor Repair - Arecibo Group 7] (Distribution ) | 1 | 4339DR-PR (4339DR) | 262290.31 | 53746.06 | 0 | 26229.03 | 26229.03 | 236061.28 | 90% | 2023-01-31 12:56 | 2023-01-30 17:52 | 262290.31
685477 | 11171 | F - Utilities | FAASt [Pole and Conductor Repair - Arecibo Group 6] (Distribution) | 0 | 4339DR-PR (4339DR) | 413482 | 58304 | 0 | 41348.2 | 41348.2 | 372133.8 | 90% | 2023-01-24 13:14 | 2023-01-23 15:18 | 413482
686471 | 11116 | F - Utilities | FAASt [Pole and Conductor Repair - Arecibo Group 5] (Distribution) | 1 | 4339DR-PR (4339DR) | 319606 | 68700 | 0 | 31960.6 | 31960.6 | 287645.4 | 90% | 2022-12-27 11:53 | 2022-12-23 21:14 | 319606
679133 | 11090 | F - Utilities | FAASt [Pole and Conductor Repair - Arecibo Group 4] (Distribution) | 3 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% | 2022-12-27 11:53 | 2025-09-12 15:16 | 21362
757945 | 108042 | F - Utilities | FAASt [Pole and Conductor Repair - Arecibo Group 3 - Phase 2] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
712968 | 11666 | F - Utilities | FAASt [Pole and Conductor Repair - Arecibo Group 2 - Phase 2] (Distribution) | 0 | 4339DR-PR (4339DR) | 5807772.97 | 178712.97 | 0 | 580777.29 | 580777.29 | 5226995.68 | 90% | 2024-11-01 15:15 | 2024-11-01 15:15 | 5925842.57
704916 | 11312 | F - Utilities | FAASt [Pole and Conductor Repair - Arecibo Group 13-14-15-16] (Distribution) | 0 | 4339DR-PR (4339DR) | 303970 | 29974 | 0 | 30397 | 30397 | 273573 | 90% | 2023-04-06 11:12 | 2023-04-05 20:55 | 303970
701504 | 11268 | F - Utilities | FAASt [Pole and Conductor Repair - Arecibo Group 12] (Distribution) | 0 | 4339DR-PR (4339DR) | 188223 | 37878 | 0 | 18822.3 | 18822.3 | 169400.7 | 90% | 2023-03-08 12:36 | 2023-03-07 20:35 | 188223
689071 | 11256 | F - Utilities | FAASt [Pole and Conductor Repair - Arecibo Group 11] (Distribution) | 0 | 4339DR-PR (4339DR) | 77036.24 | 17491.16 | 0 | 7703.62 | 7703.62 | 69332.62 | 90% | 2023-03-02 12:24 | 2023-03-01 19:03 | 77036.24
688198 | 11276 | F - Utilities | FAASt [Pole and Conductor Repair - Arecibo Group 10] (Distribution) | 0 | 4339DR-PR (4339DR) | 76862.24 | 16023.76 | 0 | 7686.22 | 7686.22 | 69176.02 | 90% | 2023-03-20 11:45 | 2023-03-18 00:54 | 76862.24
710099 | 11667 | F - Utilities | FAASt [Pole and Conductor Repair - Arecibo Group 1 - Phase 2] (Distribution) | 0 | 4339DR-PR (4339DR) | 6943798.62 | 239376.93 | 0 | 694379.86 | 694379.86 | 6249418.76 | 90% | 2025-01-07 23:15 | 2025-01-07 23:15 | 6964837
759004 | 108045 | F - Utilities | FAASt [Pole and Conductor - Arecibo Group 4 - Phase 2] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
948766 | 108136 | F - Utilities | FAASt [Physical Security] (Generation) | 0 | 4339DR-PR (4339DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
551861 | 11372 | F - Utilities | FAASt [Physical Security - Group 3] (Substation) | 0 | 4339DR-PR (4339DR) | 4133339.83 | 436383.23 | 0 | 413333.98 | 413333.98 | 3720005.85 | 90% | 2023-06-16 12:55 | 2023-06-15 13:07 | 4133339.83
549764 | 11350 | F - Utilities | FAASt [Physical Security - Group 2] (Substation) | 1 | 4339DR-PR (4339DR) | 2383692.99 | 224680.68 | 0 | 238369.3 | 238369.3 | 2145323.69 | 90% | 2023-06-16 12:55 | 2023-06-15 13:07 | 2383692.99
550910 | 10841 | F - Utilities | FAASt [Physical Security - Group 1] (Substation) | 1 | 4339DR-PR (4339DR) | 6691229.18 | 665958.96 | 0 | 669122.92 | 669122.92 | 6022106.26 | 90% | 2023-05-04 11:30 | 2023-05-03 14:07 | 6691229.18
724781 | 11736 | F - Utilities | FAASt [Penuelas Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 7948618.17
724670 | 11731 | F - Utilities | FAASt [Patillas Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 8375996.84
550980 | 107722 | F - Utilities | FAASt [Parques y Recreos - 1002] (Substation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
176913 | 11432 | F - Utilities | FAASt [Palo Seco SP to Catano Sect 38kV Line- 9500] (Transmission) | 0 | 4339DR-PR (4339DR) | 33526671.86 | 0 | 0 | 3352667.18 | 3352667.18 | 30174004.68 | 90% | 2025-11-05 16:17 | 2025-11-05 16:17 | 0
551247 | 11570 | E - Buildings and Equipment | FAASt [Palo Seco South Building Repairs] (Building) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
662957 | 10606 | F - Utilities | FAASt [Palo Seco Power Plant –001 Units 3 & 4] (Generation) | 2 | 4339DR-PR (4339DR) | 34466293.86 | 0 | 0 | 3446629.38 | 3446629.38 | 31019664.48 | 90% | 2022-06-16 11:23 | 2025-09-22 16:15 | 28774422.64
671481 | 10609 | F - Utilities | FAASt [Palo Seco 002- Auxiliary Infrastructure Projects] (Generation) | 1 | 4339DR-PR (4339DR) | 5185468 | 0 | 0 | 518546.8 | 518546.8 | 4666921.2 | 90% | 2022-06-16 11:23 | 2025-02-06 20:16 | 5185468
698579 | 11629 | F - Utilities | FAASt [Orocovis Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 9410766.24 | 1339801.28 | 0 | 941076.62 | 941076.62 | 8469689.62 | 90% | 2024-03-22 10:16 | 2024-03-21 20:05 | 9410766.24
712978 | 107862 | F - Utilities | FAASt [Once de Agosto Sect. - San Sebastian TC 38kV Line 2000] (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
715610 | 107877 | F - Utilities | FAASt [Network Upgrades to Support the Integration of Tranche 1 Utility Scale Renewable Projects] (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
744072 | 107948 | F - Utilities | FAASt [Network & Communication Infrastructure Group 2] (Telecommunication) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
704943 | 11664 | F - Utilities | FAASt [Naranjito Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 13759586.8 | 2115538.38 | 0 | 1375958.67 | 1375958.67 | 12383628.13 | 90% | 2024-04-12 11:19 | 2024-04-11 15:42 | 13759586.81
704849 | 11658 | F - Utilities | FAASt [Naguabo Streetlighting] (Distribution) | 1 | 4339DR-PR (4339DR) | 13290413.39 | 1669736.97 | 0 | 1329041.34 | 1329041.34 | 11961372.05 | 90% | 2024-05-10 10:17 | 2024-05-09 14:45 | 13290413.39
709631 | 11627 | F - Utilities | FAASt [Morovis Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 15230881.12 | 1744482.27 | 0 | 1523088.11 | 1523088.11 | 13707793.01 | 90% | 2024-03-22 10:16 | 2024-03-21 19:59 | 15230881.12
752276 | 107994 | F - Utilities | FAASt [Monterrey 9502 & 9503 (Fuse to Breaker)] (Substation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
704741 | 11737 | F - Utilities | FAASt [Moca Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 17686091.97
542758 | 11385 | F - Utilities | FAASt [Minor Repairs -Group B] (Substation) | 0 | 4339DR-PR (4339DR) | 3412576 | 439541 | 0 | 341257.6 | 341257.6 | 3071318.4 | 90% | 2023-07-07 11:35 | 2023-07-06 11:47 | 3412576
746660 | 107960 | F - Utilities | FAASt [Minor Protection, Automation, and Control [PAC] Replacement] (Substation) | 0 | 4339DR-PR (4339DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
712988 | 107866 | F - Utilities | FAASt [Minor Protection, Automation, and Control (PAC) Replacement] (Substation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
662238 | 107742 | F - Utilities | FAASt [Microwave Point-to-Point Backbone] (Telecommunications) | 0 | 4339DR-PR (4339DR) | 28826526.19 | 0 | 0 | 2882652.61 | 0 | 0 | 90% |  |  | 0
685869 | 107780 | F - Utilities | FAASt [Mayagüez TC] (Substation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
678793 | 11532 | F - Utilities | FAASt [Mayagüez Streetlighting] (Distribution) | 2 | 4339DR-PR (4339DR) | 12371384.46 | 1352204.36 | 0 | 1237138.45 | 1237138.45 | 11134246.01 | 90% | 2023-11-03 11:30 | 2024-03-07 16:14 | 12371384.46
735360 | 11832 | F - Utilities | FAASt [Mayaguez Streetlighting - Part 3] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 13951292
735357 | 11777 | F - Utilities | FAASt [Mayaguez Streetlighting - Part 2] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 8465209.58
548440 | 107707 | E - Buildings and Equipment | FAASt [Mayaguez Region Repairs] (Building) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
956357 | 108160 | F - Utilities | FAASt [Mayaguez Region 5 Line 1900 (38kV) – Dos Bocas HP to San Sebastian TC] (Vegetation) | 0 | 4339DR-PR (4339DR) | 1692783.13 | 1561542.33 | 0 | 169278.31 | 0 | 0 | 90% |  |  | 0
956331 | 108146 | F - Utilities | FAASt [Mayaguez Region 5 Feeder 6014-02] (Vegetation) | 0 | 4339DR-PR (4339DR) | 7195773.23 | 5381811.02 | 0 | 719577.32 | 719577.32 | 0 | 90% |  |  | 0
956337 | 108149 | F - Utilities | FAASt [Mayaguez Region 5 Feeder 6012-02] (Vegetation) | 0 | 4339DR-PR (4339DR) | 5467151.1 | 4088952.37 | 0 | 546715.11 | 546715.11 | 0 | 90% |  |  | 0
712963 | 107860 | F - Utilities | FAASt [Mayaguez GP - Leon Sect 38kV Line 1600] (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
682645 | 107779 | F - Utilities | FAASt [Maunabo TC] (Substation) | 0 | 4339DR-PR (4339DR) | 8292124.95 | 0 | 0 | 829212.49 | 829212.49 | 7462912.46 | 90% | 2025-09-17 18:16 | 2025-09-17 18:16 | 0
542690 | 10499 | F - Utilities | FAASt [Maunabo Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 6443757.4 | 243880.33 | 0 | 644375.74 | 644375.74 | 5799381.66 | 90% | 2022-05-05 11:20 | 2022-05-04 19:59 | 6443757.4
335206 | 107543 | F - Utilities | FAASt [Matrullas Reservoir–Dredging] (Dams/Hydro) | 0 | 4339DR-PR (4339DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
698427 | 11525 | F - Utilities | FAASt [Maricao Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 4846034.89
660437 | 11097 | F - Utilities | FAASt [Manati Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 28636829 | 1568964 | 0 | 2863682.9 | 2863682.9 | 25773146.1 | 90% | 2023-01-24 13:14 | 2023-01-23 15:19 | 28636829
542517 | 10515 | F - Utilities | FAASt [Luquillo Streetlighting] (Distribution) | 1 | 4339DR-PR (4339DR) | 8810325.37 | 181658.08 | 0 | 881032.54 | 881032.54 | 7929292.83 | 90% | 2022-05-20 12:05 | 2022-05-19 20:09 | 8810325.37
334773 | 107538 | F - Utilities | FAASt [Lucchetti Reservoir – Dredging] (Dams/Hydro) | 0 | 4339DR-PR (4339DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
724828 | 11692 | F - Utilities | FAASt [Loiza Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 6696269.82
334803 | 107540 | F - Utilities | FAASt [Loco Reservoir Dredging] (Dams/Hydro) | 0 | 4339DR-PR (4339DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
550902 | 11688 | F - Utilities | FAASt [Line 9700 Palo Seco SP to Bay View Sect.] (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
551911 | 11434 | F - Utilities | FAASt [Line 9100 (38 kV) - Guaraguao TC to Bayamon Pueblo Sect.] (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
334469 | 107522 | F - Utilities | FAASt [Line 8900 Monacillos TC to Adm. Tribunal Apelaciones] (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
550019 | 107710 | F - Utilities | FAASt [Line 600 Caguas TC to Gautier Benitez Sect.] (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
718951 | 107882 | F - Utilities | FAASt [Line 51200- Costa Sur Steam Plant to Cambalache Gas Plant (230kV)] (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
668669 | 107754 | F - Utilities | FAASt [Line 50500 230kV Mayaguez TC - Mora TC - Cambalache Power Plant] (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
718955 | 107883 | F - Utilities | FAASt [Line 50200 (230kv) from Manati TC to Bayamon TC] (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
750730 | 107981 | F - Utilities | FAASt [Line 500 Ponce TC to Costa Sur SP] (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
550070 | 107712 | F - Utilities | FAASt [Line 4000 Comerio HP to Escuela Francisco Morales] (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
548598 | 11494 | F - Utilities | FAASt [Line 36200 (115 kV) Fajardo to Rio Blanco] (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
547221 | 107692 | F - Utilities | FAASt [Line 3600 Monacillos TC to Martin Peña TC] (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
435257 | 107545 | F - Utilities | FAASt [Line 3000 Monacillos TC - Bairoa TO] (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
334482 | 11450 | F - Utilities | FAASt [Line 3000 (38 kV) Monacillos TC to Juncos TC] (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
730657 | 11559 | F - Utilities | FAASt [Line 2200 Dos Bocas HP to Dorado TC ] (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
547342 | 107700 | F - Utilities | FAASt [Line 1500 Mayaguez GP to GOAB 1515] (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
753777 | 108008 | F - Utilities | FAASt [Line 1500 - Mayaguez GP to GOAB 1515] (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
547350 | 11854 | F - Utilities | FAASt [Line 13300 Bayamon TC to Plaza del Sol] (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
547160 | 107689 | F - Utilities | FAASt [Line 1200 Mayaguez GP to Yauco 2 HP] (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
551067 | 11687 | F - Utilities | FAASt [Line 11100 Canovanas Sect. to GOAB 11115] (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
704938 | 11633 | F - Utilities | FAASt [Las Piedras Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 15615524.51 | 1807601.11 | 0 | 1561552.45 | 1561552.45 | 14053972.06 | 90% | 2024-04-12 11:19 | 2024-04-11 15:43 | 15615524.51
698439 | 11526 | F - Utilities | FAASt [Las Marias Streetlighting] (Distribution) | 2 | 4339DR-PR (4339DR) | 8360922 | 1287705 | 0 | 836092.2 | 836092.2 | 7524829.8 | 90% | 2023-11-03 11:30 | 2024-03-07 15:58 | 8360922
179988 | 107305 | F - Utilities | FAASt [Las Lomas – XFMR 1525] (Substation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
713795 | 11624 | F - Utilities | FAASt [Lares Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
542687 | 10521 | F - Utilities | FAASt [Lajas Streetlighting] (Distribution) | 1 | 4339DR-PR (4339DR) | 10704668.57 | 426332.48 | 0 | 1070466.86 | 1070466.86 | 9634201.71 | 90% | 2022-05-20 12:05 | 2022-05-19 20:09 | 10704668.57
436462 | 107549 | F - Utilities | FAASt [Lajas Irrigation Canals] (Dams/Hydro) | 0 | 4339DR-PR (4339DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
708599 | 107841 | F - Utilities | FAASt [L700 Costa Sur SP - Yauco 2 HP] (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
708951 | 107846 | F - Utilities | FAASt [L6500 Toro Negro 1 H.P. - Barranquitas T.C.] (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
711172 | 107854 | F - Utilities | FAASt [L3700 Jobos TC - Maunabo TC] (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
708909 | 107845 | F - Utilities | FAASt [L3000 Juncos TC - Rio Blanco HP] (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
712977 | 107861 | F - Utilities | FAASt [L3000 Caguas TC - Caguax Sect] (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
708819 | 107844 | F - Utilities | FAASt [L2000 Once de Agosto Sect. - San Sebastian TC ] (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
693543 | 11634 | F - Utilities | FAASt [Juncos Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 14420422.09
699814 | 11576 | F - Utilities | FAASt [Juana Diaz Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 15781505
724600 | 11735 | F - Utilities | FAASt [Jayuya Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 8628211.52 | 1350541.32 | 0 | 862821.15 | 862821.15 | 7765390.37 | 90% | 2024-05-31 11:36 | 2024-05-30 12:36 | 8628211.52
675345 | 107766 | F - Utilities | FAASt [IT OT Technology Systems Reparations] Group 1 (Telecommunication) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
673920 | 107764 | F - Utilities | FAASt [Isla Grande 1101] (Substation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
686482 | 11572 | F - Utilities | FAASt [Isabela Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 7747459.12
734928 | 107917 | F - Utilities | FAASt [Isabela Streetlighting - Part 3] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
734927 | 11773 | F - Utilities | FAASt [Isabela Streetlighting - Part 2] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
436467 | 107550 | F - Utilities | FAASt [Isabela Irrigation District - Canals] (Dams/Hydro) | 0 | 4339DR-PR (4339DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
690480 | 11683 | F - Utilities | FAASt [Humacao Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 7598892
735487 | 107920 | F - Utilities | FAASt [Humacao Streetlighting - Part 3] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
735493 | 11799 | F - Utilities | FAASt [Humacao Streetlighting - Part 2] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 7190363
698432 | 11523 | F - Utilities | FAASt [Hormigueros Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 6920157.56
660227 | 11095 | F - Utilities | FAASt [Hatillo Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 20334482.95 | 1764387.7 | 0 | 2033448.29 | 2033448.29 | 18301034.66 | 90% | 2023-01-24 13:14 | 2023-01-23 15:19 | 20334482.95
673504 | 11317 | F - Utilities | FAASt [Gurabo Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 20742294 | 1533300 | 0 | 2074229.4 | 2074229.4 | 18668064.6 | 90% | 2023-05-17 11:31 | 2023-05-16 19:38 | 20742294
334798 | 107539 | F - Utilities | FAASt [Guerrero Reservoir – Dredging] (Dams/Hydro) | 0 | 4339DR-PR (4339DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
334813 | 107542 | F - Utilities | FAASt [Guayo Reservoir Dredging] (Dams/Hydro) | 0 | 4339DR-PR (4339DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
698458 | 11518 | F - Utilities | FAASt [Guaynabo Streetlighting] (Distribution) | 2 | 4339DR-PR (4339DR) | 10615811.01 | 853056.42 | 0 | 1061581.1 | 1061581.1 | 9554229.91 | 90% | 2023-11-03 11:30 | 2024-03-07 15:56 | 10615811.01
735499 | 107921 | F - Utilities | FAASt [Guaynabo Streetlighting - Part 3] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
735677 | 11801 | F - Utilities | FAASt [Guaynabo Streetlighting - Part 2] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 7566377
551260 | 107727 | F - Utilities | FAASt [Guaynabo Pueblo Substation] (Substation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
724605 | 11732 | F - Utilities | FAASt [Guayanilla Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 7949936.1
690721 | 11531 | F - Utilities | FAASt [Guayama Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 6480886.39
734789 | 107916 | F - Utilities | FAASt [Guayama Streetlighting - Part 3 ] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
734791 | 11808 | F - Utilities | FAASt [Guayama Streetlighting - Part 2] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 6407828
334772 | 107537 | F - Utilities | FAASt [Guayabal Reservoir – Dredging] (Dams/Hydro) | 0 | 4339DR-PR (4339DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
825843 | 108134 | F - Utilities | FAASt [Guanica TC] (Substation) | 0 | 4339DR-PR (4339DR) | 2320373.96 | 0 | 0 | 232037.39 | 232037.39 | 2088336.57 | 90% | 2025-09-22 16:15 | 2025-09-22 16:15 | 0
542756 | 10538 | F - Utilities | FAASt [Guánica Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 10058046 | 370808 | 0 | 1005804.6 | 1005804.6 | 9052241.4 | 90% | 2022-05-26 11:24 | 2022-05-25 13:16 | 10058046
334771 | 107536 | F - Utilities | FAASt [Guajataca Reservoir – Dredging] (Dams/Hydro) | 0 | 4339DR-PR (4339DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
334770 | 11853 | F - Utilities | FAASt [Guajataca Dam – Permanent Repairs] (Dams/Hydro) | 0 | 4339DR-PR (4339DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
334769 | 107535 | F - Utilities | FAASt [Garzas Reservoir – Dredging] (Dams/Hydro) | 0 | 4339DR-PR (4339DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
550972 | 107721 | F - Utilities | FAASt [Fonalledas GIS Rebuilt 1401 1421] (Substation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
698424 | 11344 | F - Utilities | FAASt [Florida Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 10309031.53 | 997190 | 0 | 1030903.15 | 1030903.15 | 9278128.38 | 90% | 2023-10-23 11:32 | 2023-10-20 18:00 | 10309031.53
674506 | 107765 | F - Utilities | FAASt [Field Area Network (FAN)] (Telecommunication) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
546386 | 107558 | F - Utilities | FAASt [Feeders- El Yunque 2305 - Supply] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
165226 | 107206 | F - Utilities | FAASt [Feeders Vieques & Culebra] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
334471 | 107523 | F - Utilities | FAASt [Feeders -1303-01- San Juan Short Term Group 1] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
334472 | 107524 | F - Utilities | FAASt [Feeders - San Juan Short Term Group 2] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
730824 | 107912 | F - Utilities | FAASt [Feeders - Ponce Short Term Group 2] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
334191 | 107513 | F - Utilities | FAASt [Feeders - Mayaguez Short Term Group 3] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
334285 | 107514 | F - Utilities | FAASt [Feeders - Mayaguez Short Term Group 2] (Distribution ) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
334308 | 107517 | F - Utilities | FAASt [Feeders - Mayaguez Short Term Group 1] (Distribution ) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
334476 | 107528 | F - Utilities | FAASt [Feeders - Carolina Short Term Group 2] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
730541 | 107908 | F - Utilities | FAASt [Feeders - Caguas Short Term Group 8] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
334518 | 107532 | F - Utilities | FAASt [Feeders - Caguas Short Term Group 7] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
334497 | 107531 | F - Utilities | FAASt [Feeders - Caguas Short Term Group 6 (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
334491 | 107530 | F - Utilities | FAASt [Feeders - Caguas Short Term Group 5] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
334452 | 107521 | F - Utilities | FAASt [Feeders - Caguas Short Term Group 3] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
334443 | 107520 | F - Utilities | FAASt [Feeders - Caguas Short Term Group 2] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
334420 | 107519 | F - Utilities | FAASt [Feeders - Caguas Short Term Group 1] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
334475 | 107527 | F - Utilities | FAASt [Feeders - Bayamon Short Term Group 3] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
334474 | 107526 | F - Utilities | FAASt [Feeders - Bayamon Short Term Group 2] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
730821 | 107911 | F - Utilities | FAASt [Feeders - Arecibo Short Term Group 2] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
436616 | 107551 | F - Utilities | FAASt [Feeders - Arecibo Short Term Group 1] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
334293 | 107516 | F - Utilities | FAASt [Feeders - 7805-11- Mayaguez Short Term Group 4] (Distribution ) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
334477 | 107529 | F - Utilities | FAASt [Feeders - 2402-02 - Carolina Short Term Group 3] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
334473 | 107525 | F - Utilities | FAASt [Feeders - 1806-02- Bayamon Short Term Group 1] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
546374 | 107556 | F - Utilities | FAASt [Feeders - 1620-02 San Juan Short Term Group 3] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
812569 | 108102 | F - Utilities | FAASt [Feeder Rebuild 3502-02] (Distribution) | 0 | 4339DR-PR (4339DR) | 10217566.54 | 0 | 0 | 1021756.65 | 1021756.65 | 9195809.89 | 90% | 2025-09-25 16:15 | 2025-09-25 16:15 | 0
956782 | 108162 | F - Utilities | FAASt [Feeder Rebuild #6802-04] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
958367 | 108164 | F - Utilities | FAASt [Feeder Rebuild #6603-01] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
818006 | 108123 | F - Utilities | FAASt [Feeder Rebuild #2402-02] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
817962 | 108121 | F - Utilities | FAASt [Feeder Rebuild # 9403-03] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
818056 | 108126 | F - Utilities | FAASt [Feeder Rebuild # 6305-03] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
764705 | 108056 | F - Utilities | FAASt [Feeder Rebuild # 6014-02] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
818041 | 108124 | F - Utilities | FAASt [Feeder Rebuild # 3701-03] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
818055 | 108125 | F - Utilities | FAASt [Feeder Rebuild # 3006-05] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
817961 | 108120 | F - Utilities | FAASt [Feeder Rebuild # 2404-06] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
817993 | 108122 | F - Utilities | FAASt [Feeder Rebuild # 1801-03] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
760571 | 108049 | F - Utilities | FAASt [Feeder Rebuild # 1720-07] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
760579 | 108052 | F - Utilities | FAASt [Feeder Rebuild # 1717-03] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
760568 | 108048 | F - Utilities | FAASt [Feeder Rebuild # 1710-01] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
817956 | 108119 | F - Utilities | FAASt [Feeder Rebuild # 1303-02] (Distribution) | 0 | 4339DR-PR (4339DR) | 2054461.78 | 0 | 0 | 205446.17 | 205446.17 | 1849015.61 | 90% | 2025-09-25 17:15 | 2025-09-25 17:15 | 0
767387 | 108068 | F - Utilities | FAASt [Feeder Rebuild # 1303-01] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
704862 | 11728 | F - Utilities | FAASt [Fajardo Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 11333806.13
956593 | 108161 | F - Utilities | FAASt [Factor Sect 8014 Transformer Replacement] (Substation) | 0 | 4339DR-PR (4339DR) | 3751193.63 | 0 | 0 | 375119.36 | 375119.36 | 3376074.27 | 90% | 2025-09-22 16:15 | 2025-09-22 16:15 | 0
550099 | 107713 | F - Utilities | FAASt [Esc. Industrial M. Such - 1423] (Substation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
673691 | 10710 | F - Utilities | FAASt [Equipment and Materials] (E&M) | 8 | 4339DR-PR (4339DR) | 3206944731.28 | 0 | 0 | 320694473.12 | 320694473.12 | 2698500487.57 | 90% | 2022-06-10 11:48 | 2025-09-17 18:16 | 1539668063.2
682834 | 11402 | F - Utilities | FAASt [EPC - Costa Sur TC - Phase II & III ] (Substation) | 1 | 4339DR-PR (4339DR) | 36917509.58 | 0 | 0 | 3691750.95 | 3691750.95 | 33225758.63 | 90% | 2024-02-13 12:36 | 2025-09-17 18:16 | 61444255.52
657300 | 10957 | F - Utilities | FAASt [ENERGY MANAGEMENT SYSTEM (EMS)] (Telecommunication) | 1 | 4339DR-PR (4339DR) | 48941484 | 0 | 0 | 4894148.4 | 4894148.4 | 44047335.6 | 90% | 2022-10-17 11:37 | 2022-10-14 19:21 | 164579862
334811 | 107541 | F - Utilities | FAASt [Dos Bocas Reservoir Dredging] (Dams/Hydro) | 0 | 4339DR-PR (4339DR) | 117400543.5 | 0 | 0 | 11740054.35 | 0 | 0 | 90% |  |  | 0
551916 | 107734 | F - Utilities | FAASt [Dorado TC Relocation] (Substation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
659625 | 11099 | F - Utilities | FAASt [Dorado Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 24370617 | 1505645 | 0 | 2437061.7 | 2437061.7 | 21933555.3 | 90% | 2023-01-24 13:14 | 2023-01-23 15:18 | 24370617
673848 | 10751 | F - Utilities | FAASt [Distribution Pole and Conductor Repair-Carolina Group 3] (Distribution) | 0 | 4339DR-PR (4339DR) | 49345 | 5620 | 0 | 4934.5 | 4934.5 | 44410.5 | 90% | 2022-07-12 11:39 | 2022-07-11 18:09 | 49345
673847 | 10812 | F - Utilities | FAASt [Distribution Pole and Conductor Repair-Carolina Group 2] (Distribution) | 0 | 4339DR-PR (4339DR) | 240513 | 49943 | 0 | 24051.3 | 24051.3 | 216461.7 | 90% | 2022-08-08 11:30 | 2022-08-05 17:48 | 240513
682136 | 11203 | F - Utilities | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 9] (Distribution) | 0 | 4339DR-PR (4339DR) | 565605 | 95954.05 | 0 | 56560.5 | 56560.5 | 509044.5 | 90% | 2023-01-31 12:56 | 2023-01-30 17:52 | 565605
682135 | 11149 | F - Utilities | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 8] (Distribution) | 0 | 4339DR-PR (4339DR) | 693780.53 | 116779.74 | 0 | 69378.05 | 69378.05 | 624402.48 | 90% | 2023-01-10 13:19 | 2023-01-05 18:56 | 693780.53
678988 | 11113 | F - Utilities | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 5] (Distribution) | 1 | 4339DR-PR (4339DR) | 1117787.16 | 206650.4 | 0 | 111778.72 | 111778.72 | 1006008.44 | 90% | 2022-12-27 11:53 | 2022-12-23 21:14 | 1117787.16
678985 | 11103 | F - Utilities | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 4] (Distribution) | 0 | 4339DR-PR (4339DR) | 407945.84 | 54317.84 | 0 | 40794.58 | 40794.58 | 367151.26 | 90% | 2022-12-27 11:53 | 2022-12-23 21:13 | 407945.84
673843 | 10922 | F - Utilities | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 3] (Distribution) | 0 | 4339DR-PR (4339DR) | 1131855 | 227661 | 0 | 113185.5 | 113185.5 | 1018669.5 | 90% | 2022-10-17 11:37 | 2022-10-14 19:21 | 1131855
673839 | 10742 | F - Utilities | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 2] (Distribution) | 0 | 4339DR-PR (4339DR) | 26298 | 5830 | 0 | 2629.8 | 2629.8 | 23668.2 | 90% | 2022-07-12 11:39 | 2022-07-11 18:09 | 26298
704755 | 11352 | F - Utilities | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 12-13-14] (Distribution) | 0 | 4339DR-PR (4339DR) | 524391.61 | 86181.92 | 0 | 52439.16 | 52439.16 | 471952.45 | 90% | 2023-05-17 11:31 | 2023-05-16 19:37 | 524391.61
673836 | 11041 | F - Utilities | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 1] (Distribution) | 1 | 4339DR-PR (4339DR) | 5751036.48 | 1064121.8 | 0 | 575103.65 | 575103.65 | 5175932.83 | 90% | 2022-12-21 12:37 | 2022-12-20 13:52 | 5751036.48
705527 | 11449 | F - Utilities | FAASt [Distribution Pole and Conductor Repair – San Juan 17-18-19-20-21] (Distribution) | 0 | 4339DR-PR (4339DR) | 767854 | 125133 | 0 | 76785.4 | 76785.4 | 691068.6 | 90% | 2023-07-28 11:42 | 2023-07-27 20:01 | 767854
712982 | 107865 | F - Utilities | FAASt [Distribution Pole and Conductor Repair – Mayaguez Group 23] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
334527 | 10701 | F - Utilities | FAASt [Distribution Pole and Conductor Repair – Caguas Group 8 (Distribution) | 1 | 4339DR-PR (4339DR) | 123721 | 14874 | 0 | 12372.1 | 12372.1 | 111348.9 | 90% | 2022-06-10 11:48 | 2022-06-09 19:56 | 123721
334488 | 10635 | F - Utilities | FAASt [Distribution Pole and Conductor Repair – Caguas Group 4 (Distribution) | 1 | 4339DR-PR (4339DR) | 153743 | 10826 | 0 | 15374.3 | 15374.3 | 138368.7 | 90% | 2022-05-26 11:24 | 2022-05-25 13:16 | 153743
711962 | 107859 | F - Utilities | FAASt [Distribution Pole and Conductor Repair -Mayaguez Group 21] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
710045 | 107849 | F - Utilities | FAASt [Distribution Pole and Conductor Repair -Mayaguez Group 20] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
682031 | 11181 | F - Utilities | FAASt [Distribution Pole and Conductor Repair - San Juan Group 9] (Distribution) | 0 | 4339DR-PR (4339DR) | 625198 | 108247 | 0 | 62519.8 | 62519.8 | 562678.2 | 90% | 2023-01-31 12:56 | 2023-01-30 17:52 | 625198
682865 | 11123 | F - Utilities | FAASt [Distribution Pole and Conductor Repair - San Juan Group 7] (Distribution) | 0 | 4339DR-PR (4339DR) | 91831 | 21148 | 0 | 9183.1 | 9183.1 | 82647.9 | 90% | 2022-12-27 11:53 | 2022-12-23 21:14 | 91831
682870 | 11137 | F - Utilities | FAASt [Distribution Pole and Conductor Repair - San Juan Group 6] (Distribution) | 1 | 4339DR-PR (4339DR) | 103412.77 | 17491 | 0 | 10341.28 | 10341.28 | 93071.49 | 90% | 2022-12-27 11:53 | 2022-12-23 21:14 | 103412.77
679026 | 11107 | F - Utilities | FAASt [Distribution Pole and Conductor Repair - San Juan Group 5] (Distribution) | 0 | 4339DR-PR (4339DR) | 590296 | 106510 | 0 | 59029.6 | 59029.6 | 531266.4 | 90% | 2022-12-27 11:53 | 2022-12-23 21:13 | 590296
679025 | 11101 | F - Utilities | FAASt [Distribution Pole and Conductor Repair - San Juan Group 4] (Distribution) | 0 | 4339DR-PR (4339DR) | 298631 | 55558 | 0 | 29863.1 | 29863.1 | 268767.9 | 90% | 2022-12-27 11:53 | 2022-12-23 21:13 | 298631
673844 | 10864 | F - Utilities | FAASt [Distribution Pole and Conductor Repair - San Juan Group 3] (Distribution) | 1 | 4339DR-PR (4339DR) | 1392064.88 | 319213.9 | 0 | 139206.49 | 139206.49 | 1252858.39 | 90% | 2022-08-24 10:30 | 2022-08-23 13:06 | 1392064.88
673838 | 10764 | F - Utilities | FAASt [Distribution Pole and Conductor Repair - San Juan Group 2] (Distribution) | 0 | 4339DR-PR (4339DR) | 357614 | 73265 | 0 | 35761.4 | 35761.4 | 321852.6 | 90% | 2022-07-12 11:39 | 2022-07-11 18:09 | 357614
704933 | 11465 | F - Utilities | FAASt [Distribution Pole and Conductor Repair - San Juan Group 13-14-15-16] (Distribution) | 0 | 4339DR-PR (4339DR) | 1426151 | 224731 | 0 | 142615.1 | 142615.1 | 1283535.9 | 90% | 2023-08-04 19:29 | 2023-07-27 20:00 | 1426151
701679 | 11267 | F - Utilities | FAASt [Distribution Pole and Conductor Repair - San Juan Group 12] (Distribution) | 0 | 4339DR-PR (4339DR) | 80651.6 | 16226.16 | 0 | 8065.16 | 8065.16 | 72586.44 | 90% | 2023-03-02 12:24 | 2023-03-01 19:03 | 80651.6
688109 | 11264 | F - Utilities | FAASt [Distribution Pole and Conductor Repair - San Juan Group 11] (Distribution) | 1 | 4339DR-PR (4339DR) | 563429.26 | 114710.2 | 0 | 56342.93 | 56342.93 | 507086.33 | 90% | 2023-03-08 12:36 | 2023-03-07 20:34 | 563429.26
691246 | 11231 | F - Utilities | FAASt [Distribution Pole and Conductor Repair - San Juan Group 10] (Distribution) | 1 | 4339DR-PR (4339DR) | 245340.07 | 33717.31 | 0 | 24534.01 | 24534.01 | 220806.06 | 90% | 2023-02-16 12:51 | 2023-02-15 12:01 | 245340.07
673818 | 10821 | F - Utilities | FAASt [Distribution Pole and Conductor Repair - San Juan Group 1] (Distribution) | 0 | 4339DR-PR (4339DR) | 793418 | 171614 | 0 | 79341.8 | 79341.8 | 714076.2 | 90% | 2022-08-08 11:30 | 2022-08-05 17:48 | 793418
679458 | 11114 | F - Utilities | FAASt [Distribution Pole and Conductor Repair - Ponce Group 4] (Distribution) | 0 | 4339DR-PR (4339DR) | 593918 | 95482 | 0 | 59391.8 | 59391.8 | 534526.2 | 90% | 2023-01-10 13:19 | 2023-01-05 18:56 | 593918
679457 | 11105 | F - Utilities | FAASt [Distribution Pole and Conductor Repair - Ponce Group 3] (Distribution) | 0 | 4339DR-PR (4339DR) | 746488 | 157153 | 0 | 74648.8 | 74648.8 | 671839.2 | 90% | 2022-12-27 11:53 | 2022-12-23 21:13 | 746488
712981 | 107864 | F - Utilities | FAASt [Distribution Pole and Conductor Repair - Ponce Group 24] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
673775 | 10962 | F - Utilities | FAASt [Distribution Pole and Conductor Repair - Mayaguez Group 3] (Distribution) | 0 | 4339DR-PR (4339DR) | 4432647.91 | 857193.1 | 0 | 443264.79 | 443264.79 | 3989383.12 | 90% | 2022-12-27 11:53 | 2022-12-23 21:10 | 4432647.91
673772 | 10919 | F - Utilities | FAASt [Distribution Pole and Conductor Repair - Mayagüez Group 2] (Distribution) | 0 | 4339DR-PR (4339DR) | 4122520 | 835984 | 0 | 412252 | 412252 | 3710268 | 90% | 2022-10-24 11:36 | 2022-10-21 19:11 | 4122520
673774 | 10773 | F - Utilities | FAASt [Distribution Pole and Conductor Repair - Mayaguez Group 1] (Distribution) | 0 | 4339DR-PR (4339DR) | 1766951 | 358420 | 0 | 176695.1 | 176695.1 | 1590255.9 | 90% | 2022-08-02 11:42 | 2022-08-01 20:47 | 1766951
738696 | 107930 | F - Utilities | FAASt [Distribution Pole and Conductor Repair - Carolina Group 2 - Phase 2] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
679033 | 11098 | F - Utilities | FAASt [Distribution Pole and Conductor Repair - Caguas Group 9] (Distribution) | 0 | 4339DR-PR (4339DR) | 908942 | 179902 | 0 | 90894.2 | 90894.2 | 818047.8 | 90% | 2022-12-27 11:53 | 2022-12-23 21:13 | 908942
674098 | 10824 | F - Utilities | FAASt [Distribution Pole and Conductor Repair - Caguas Group 7] (Distribution) | 0 | 4339DR-PR (4339DR) | 107755 | 23322 | 0 | 10775.5 | 10775.5 | 96979.5 | 90% | 2022-08-08 11:30 | 2022-08-05 17:48 | 107755
674096 | 10935 | F - Utilities | FAASt [Distribution Pole and Conductor Repair - Caguas Group 6] (Distribution) | 0 | 4339DR-PR (4339DR) | 2092280 | 318852 | 0 | 209228 | 209228 | 1883052 | 90% | 2022-10-17 11:37 | 2022-10-14 19:21 | 2092280
674092 | 10893 | F - Utilities | FAASt [Distribution Pole and Conductor Repair - Caguas Group 5] (Distribution) | 0 | 4339DR-PR (4339DR) | 531730 | 90422 | 0 | 53173 | 53173 | 478557 | 90% | 2022-09-16 11:54 | 2022-09-15 19:37 | 531730
674088 | 10933 | F - Utilities | FAASt [Distribution Pole and Conductor Repair - Caguas Group 3] (Distribution) | 0 | 4339DR-PR (4339DR) | 1702021 | 289653 | 0 | 170202.1 | 170202.1 | 1531818.9 | 90% | 2022-10-17 11:37 | 2022-10-14 19:21 | 1702021
738972 | 107931 | F - Utilities | FAASt [Distribution Pole and Conductor Repair - Caguas Group 3 - Phase 2] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
674083 | 10827 | F - Utilities | FAASt [Distribution Pole and Conductor Repair - Caguas Group 2] (Distribution) | 0 | 4339DR-PR (4339DR) | 2110462 | 362533 | 0 | 211046.2 | 211046.2 | 1899415.8 | 90% | 2022-08-08 11:30 | 2022-08-05 17:48 | 2110462
704844 | 11340 | F - Utilities | FAASt [Distribution Pole and Conductor Repair - Caguas Group 16-17-18-19-20] (Distribution) | 0 | 4339DR-PR (4339DR) | 409298 | 88558 | 0 | 40929.8 | 40929.8 | 368368.2 | 90% | 2023-05-17 11:31 | 2023-05-16 19:37 | 409298
688096 | 11214 | F - Utilities | FAASt [Distribution Pole and Conductor Repair - Caguas Group 15] (Distribution) | 0 | 4339DR-PR (4339DR) | 27238.64 | 5830.39 | 0 | 2723.86 | 2723.86 | 24514.78 | 90% | 2023-01-31 12:56 | 2023-01-30 17:52 | 27238.64
682373 | 11165 | F - Utilities | FAASt [Distribution Pole and Conductor Repair - Caguas Group 14] (Distribution) | 0 | 4339DR-PR (4339DR) | 77605 | 11661 | 0 | 7760.5 | 7760.5 | 69844.5 | 90% | 2023-01-10 13:19 | 2023-01-05 18:57 | 77605
682324 | 11145 | F - Utilities | FAASt [Distribution Pole and Conductor Repair - Caguas Group 13] (Distribution) | 0 | 4339DR-PR (4339DR) | 709229.55 | 136182.31 | 0 | 70922.95 | 70922.95 | 638306.6 | 90% | 2023-01-10 13:19 | 2023-01-05 18:56 | 709229.55
682890 | 11136 | F - Utilities | FAASt [Distribution Pole and Conductor Repair - Caguas Group 12] (Distribution) | 0 | 4339DR-PR (4339DR) | 612378.63 | 102310.67 | 0 | 61237.86 | 61237.86 | 551140.77 | 90% | 2022-12-27 11:53 | 2022-12-23 21:14 | 612378.63
682882 | 11130 | F - Utilities | FAASt [Distribution Pole and Conductor Repair - Caguas Group 11] (Distribution) | 0 | 4339DR-PR (4339DR) | 659039.4 | 113378.16 | 0 | 65903.94 | 65903.94 | 593135.46 | 90% | 2023-01-10 13:19 | 2023-01-05 18:56 | 659039.4
679134 | 11109 | F - Utilities | FAASt [Distribution Pole and Conductor Repair - Caguas Group 10] (Distribution) | 0 | 4339DR-PR (4339DR) | 563557.15 | 110600.22 | 0 | 56355.71 | 56355.71 | 507201.44 | 90% | 2023-01-10 13:19 | 2023-01-05 18:57 | 563557.15
674072 | 10906 | F - Utilities | FAASt [Distribution Pole and Conductor Repair - Caguas Group 1] (Distribution) | 0 | 4339DR-PR (4339DR) | 1111094 | 238203 | 0 | 111109.4 | 111109.4 | 999984.6 | 90% | 2022-09-16 11:54 | 2022-09-15 19:37 | 1111094
682910 | 11212 | F - Utilities | FAASt [Distribution Pole and Conductor Repair - Bayamón Group 7] (Distribution) | 0 | 4339DR-PR (4339DR) | 622823 | 105667 | 0 | 62282.3 | 62282.3 | 560540.7 | 90% | 2023-01-31 12:56 | 2023-01-30 17:52 | 622823
682898 | 11183 | F - Utilities | FAASt [Distribution Pole and Conductor Repair - Bayamón Group 6] (Distribution) | 0 | 4339DR-PR (4339DR) | 744027.12 | 108700.19 | 0 | 74402.71 | 74402.71 | 669624.41 | 90% | 2023-01-24 13:14 | 2023-01-23 15:20 | 744027.12
710110 | 11534 | F - Utilities | FAASt [Distribution Pole and Conductor Repair - Bayamon Group 2 - Phase 2] (Distribution) | 0 | 4339DR-PR (4339DR) | 87774.8 | 2478.06 | 0 | 8777.48 | 8777.48 | 78997.32 | 90% | 2023-10-23 11:32 | 2023-10-20 17:59 | 87774.8
710498 | 107851 | F - Utilities | FAASt [Distribution Pole and Conductor Repair - Bayamon Group 16] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
710363 | 107850 | F - Utilities | FAASt [Distribution Pole and Conductor Repair - Bayamon Group 15] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
688627 | 11193 | F - Utilities | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 9] (Distribution) | 1 | 4339DR-PR (4339DR) | 375962.49 | 72188.49 | 0 | 37596.25 | 37596.25 | 338366.24 | 90% | 2023-01-31 12:56 | 2023-01-30 17:52 | 375962.49
682172 | 11182 | F - Utilities | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 8] (Distribution) | 0 | 4339DR-PR (4339DR) | 266071.35 | 57671.35 | 0 | 26607.13 | 26607.13 | 239464.22 | 90% | 2023-01-24 13:14 | 2023-01-23 15:18 | 266071.35
679127 | 11096 | F - Utilities | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 3] (Distribution) | 0 | 4339DR-PR (4339DR) | 217162.81 | 46010.58 | 0 | 21716.28 | 21716.28 | 195446.53 | 90% | 2022-12-27 11:53 | 2022-12-23 21:12 | 217162.81
710026 | 107848 | F - Utilities | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 17] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
673771 | 10909 | F - Utilities | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 1] (Distribution) | 0 | 4339DR-PR (4339DR) | 2366560.53 | 472527 | 0 | 236656.05 | 236656.05 | 2129904.48 | 90% | 2022-10-17 11:37 | 2022-10-14 19:21 | 2366560.53
812041 | 108101 | F - Utilities | FAASt [Distribution Feeder Rebuild 9501-02] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
670036 | 107761 | F - Utilities | FAASt [Design Fire Pump for Aguirre Power Complex] (Generation) | 0 | 4339DR-PR (4339DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
436621 | 107552 | F - Utilities | FAASt [Dams Minor Repairs] (Dams/Hydro) | 0 | 4339DR-PR (4339DR) | 22130627 | 8058328 | 0 | 2213062.7 | 0 | 0 | 90% |  |  | 0
668665 | 107753 | F - Utilities | FAASt [Cybersecurity Program Implementation] (Telecommunication) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
698511 | 11680 | F - Utilities | FAASt [Culebra Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 1309407 | 153603 | 0 | 130940.7 | 130940.7 | 1178466.3 | 90% | 2024-04-12 11:19 | 2024-04-11 15:42 | 1309407
751656 | 107983 | F - Utilities | FAASt [Culebra Microgrid] (Transmission) | 0 | 4339DR-PR (4339DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
551918 | 11409 | F - Utilities | FAASt [Crematorio - 1512] (Substation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
957578 | 108163 | F - Utilities | FAASt [Costa Sur TC Underground Cable Failure Replacement on Transformer Lead Bank #2] (Substation) | 0 | 4339DR-PR (4339DR) | 1108989.51 | 0 | 0 | 110898.95 | 110898.95 | 998090.56 | 90% | 2025-09-17 19:15 | 2025-09-17 19:15 | 0
672950 | 10702 | F - Utilities | FAASt [Costa Sur Power Plant Permanent Repairs CS-001] (Generation) | 2 | 4339DR-PR (4339DR) | 47415436.61 | 0 | 0 | 4741543.66 | 4741543.66 | 42673892.95 | 90% | 2022-08-24 10:30 | 2025-09-09 22:16 | 42299738.54
698570 | 11560 | F - Utilities | FAASt [Corozal Streetlighting] (Distribution) | 2 | 4339DR-PR (4339DR) | 15946081.93 | 2225873.62 | 0 | 1594608.19 | 1594608.19 | 14351473.74 | 90% | 2023-12-29 12:31 | 2024-03-07 16:10 | 15946081.93
816612 | 108108 | F - Utilities | FAASt [Continuous Emission Monitoring Systems (CEMS)] (Generation) | 0 | 4339DR-PR (4339DR) | 5008333.19 | 0 | 0 | 500833.31 | 500833.31 | 4507499.88 | 90% | 2025-09-22 16:15 | 2025-09-22 16:15 | 0
550106 | 107714 | F - Utilities | FAASt [Conquistador CH] (Substation) | 0 | 4339DR-PR (4339DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
550986 | 107723 | F - Utilities | FAASt [Condado - 1133] (Substation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
701472 | 11727 | F - Utilities | FAASt [Comerio Streetlighting] (Distribution) | 1 | 4339DR-PR (4339DR) | 7400895.19 | 862125.75 | 0 | 740089.52 | 740089.52 | 6660805.67 | 90% | 2024-05-10 10:17 | 2024-05-09 14:46 | 7400895.19
704679 | 11524 | F - Utilities | FAASt [Coamo Streetlighting] (Distribution) | 2 | 4339DR-PR (4339DR) | 16372823.8 | 2060901.35 | 0 | 1637282.38 | 1637282.38 | 14735541.42 | 90% | 2023-11-03 11:30 | 2024-03-07 16:00 | 16372823.8
724825 | 11725 | F - Utilities | FAASt [Cidra Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 14650708.44 | 1838229.6 | 0 | 1465070.84 | 1465070.84 | 13185637.6 | 90% | 2024-05-10 10:17 | 2024-05-09 14:45 | 14650708.44
724669 | 11730 | F - Utilities | FAASt [Ciales Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 10780496.72
704868 | 11650 | F - Utilities | FAASt [Ceiba Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 5869029.74 | 716918.6 | 0 | 586902.97 | 586902.97 | 5282126.77 | 90% | 2024-07-08 11:28 | 2024-07-05 12:51 | 5869029.74
690483 | 11552 | F - Utilities | FAASt [Cayey Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 14662400.8
659623 | 10884 | F - Utilities | FAASt [Cataño Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 17562047 | 565289 | 0 | 1756204.7 | 1756204.7 | 15805842.3 | 90% | 2022-12-27 11:53 | 2022-12-23 21:10 | 17562047
678789 | 11533 | F - Utilities | FAASt [Carolina Streetlighting] (Distribution) | 2 | 4339DR-PR (4339DR) | 16024559.58 | 1158946.56 | 0 | 1602455.96 | 1602455.96 | 14422103.62 | 90% | 2023-11-03 11:30 | 2024-03-07 16:00 | 16024559.58
735496 | 11835 | F - Utilities | FAASt [Carolina Streetlighting - Part 3] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 14764763
735665 | 11783 | F - Utilities | FAASt [Carolina Streetlighting - Part 2] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 12296300.92
954184 | 108144 | E - Buildings and Equipment | FAASt [Carolina ESC Building Repairs] (Buildings) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
551914 | 11470 | F - Utilities | FAASt [Caparra 1912 & 1924] (Substation) | 0 | 4339DR-PR (4339DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
178722 | 107247 | F - Utilities | FAASt [Caonillas Reservoir - Dredging] (Dams/Hydro) | 0 | 4339DR-PR (4339DR) | 81857757 | 0 | 0 | 8185775.7 | 0 | 0 | 90% |  |  | 0
728260 | 11745 | F - Utilities | FAASt [Caonillas HydroElectric Power Plant No. 1] (Dams/Hydro) | 0 | 4339DR-PR (4339DR) | 2876063.63 | 0 | 0 | 287606.36 | 0 | 0 | 90% |  |  | 2876063.63
728257 | 107904 | F - Utilities | FAASt [Caonillas Dam] (Dams/Hydro) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
701473 | 11693 | F - Utilities | FAASt [Canovanas Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 14314798.95
704931 | 11651 | F - Utilities | FAASt [Camuy Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 17705969.27
663383 | 10607 | F - Utilities | FAASt [Cambalache Power Plant Permanent Repairs] (Generation) | 1 | 4339DR-PR (4339DR) | 2007587.81 | 0 | 0 | 200758.78 | 200758.78 | 1806829.03 | 90% | 2022-05-20 12:05 | 2022-05-19 20:09 | 2007587.81
169340 | 107223 | F - Utilities | FAASt [Cambalache Power Plant – Flood Protection Barrier](Generation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
550771 | 107719 | F - Utilities | FAASt [Caguas TC] (Substation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
679039 | 11351 | F - Utilities | FAASt [Caguas Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 75586568.64 | 1849344.06 | 0 | 7558656.86 | 7558656.86 | 68027911.78 | 90% | 2023-07-05 11:36 | 2023-07-03 19:12 | 75586568.64
735672 | 11838 | F - Utilities | FAASt [Caguas Streetlighting - Part 3] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 11986815
746111 | 11778 | F - Utilities | FAASt [Caguas Streetlighting - Part 2] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 11477605.89
550060 | 107711 | E - Buildings and Equipment | FAASt [Caguas Region Repairs] (Building) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
956339 | 108150 | F - Utilities | FAASt [Caguas Region 4 - Feeder 3301-01] (Vegetation) | 0 | 4339DR-PR (4339DR) | 11453400.26 | 8566144.83 | 0 | 1145340.02 | 1145340.02 | 0 | 90% |  |  | 0
956330 | 108145 | F - Utilities | FAASt [Caguas Region 4 - Feeder 3007-03] (Vegetation) | 0 | 4339DR-PR (4339DR) | 7595964.6 | 5681119.27 | 0 | 759596.46 | 759596.46 | 0 | 90% |  |  | 0
178577 | 11507 | F - Utilities | FAASt [Cachete – MC 1526] (Substations) | 0 | 4339DR-PR (4339DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
724603 | 11684 | F - Utilities | FAASt [Cabo Rojo Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 9017148.04
734396 | 107915 | F - Utilities | FAASt [Cabo Rojo Streetlighting - Part 3] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
734393 | 11805 | F - Utilities | FAASt [Cabo Rojo Streetlighting - Part 2] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 11541259
550162 | 11813 | F - Utilities | FAASt [Berwind TC - 1336] (Substation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
551100 | 107725 | F - Utilities | FAASt [Bayview Sectionalizer 1802 Relocation] (Substation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
682328 | 11876 | F - Utilities | FAASt [Bayamón TC - Rebuild] (Substation) | 0 | 4339DR-PR (4339DR) | 4377673.55 | 0 | 0 | 437767.35 | 0 | 0 | 90% |  |  | 2637502.74
679780 | 11540 | F - Utilities | FAASt [Bayamón Streetlighting] (Distribution) | 2 | 4339DR-PR (4339DR) | 21886903 | 1176376 | 0 | 2188690.3 | 2188690.3 | 19698212.7 | 90% | 2023-11-03 11:30 | 2024-03-11 17:31 | 21886903
735472 | 11833 | F - Utilities | FAASt [Bayamon Streetlighting - Part 3] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 18291400
735470 | 11804 | F - Utilities | FAASt [Bayamón Streetlighting - Part 2] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 19691461
551242 | 107726 | F - Utilities | FAASt [Bayamon Region Repairs] (Building) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
956348 | 108156 | F - Utilities | FAASt [Bayamon Region 3 Line 10000 (38kV) – Bayamon Pueblo to Magnolia TO] (Vegetation) | 0 | 4339DR-PR (4339DR) | 121306.94 | 111902.06 | 0 | 12130.69 | 12130.69 | 0 | 90% |  |  | 0
704921 | 11675 | F - Utilities | FAASt [Barranquitas Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 11007375.31 | 1577046.09 | 0 | 1100737.53 | 1100737.53 | 9906637.78 | 90% | 2024-05-31 11:36 | 2024-05-30 12:36 | 11007375.31
671400 | 11529 | F - Utilities | FAASt [Barceloneta Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 8163052.71
550894 | 107720 | F - Utilities | FAASt [Baldrich - 1422] (Substation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
767305 | 108066 | E - Buildings and Equipment | FAASt [Auxiliary Equipment] (Generation) | 0 | 4339DR-PR (4339DR) | 18912976 | 0 | 0 | 1891297.6 | 1891297.6 | 17021678.4 | 90% | 2025-02-06 20:16 | 2025-02-06 20:16 | 0
801441 | 108089 | F - Utilities | FAASt [Automation Program Group 45] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
801440 | 108088 | F - Utilities | FAASt [Automation Program Group 44] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
801438 | 108087 | F - Utilities | FAASt [Automation Program Group 43] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
801437 | 108086 | F - Utilities | FAASt [Automation Program Group 42] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
801432 | 108085 | F - Utilities | FAASt [Automation Program Group 41] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
800399 | 108081 | F - Utilities | FAASt [Automation Program Group 40] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
741678 | 107947 | F - Utilities | FAASt [Automation Program Group 4] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
800394 | 108080 | F - Utilities | FAASt [Automation Program Group 39] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
800369 | 108079 | F - Utilities | FAASt [Automation Program Group 38] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
800361 | 108078 | F - Utilities | FAASt [Automation Program Group 37] (Distribution) | 0 | 4339DR-PR (4339DR) | 1596192.73 | 0 | 0 | 159619.27 | 159619.27 | 1436573.46 | 90% | 2025-09-17 19:15 | 2025-09-17 19:15 | 0
757700 | 108041 | F - Utilities | FAASt [Automation Program Group 35] (TL / Distribution) | 1 | 4339DR-PR (4339DR) | 2004552.51 | 874476.72 | 0 | 200455.25 | 131851.56 | 1186664.1 | 90% | 2025-09-17 19:15 | 2025-09-17 19:15 | 0
757699 | 108040 | F - Utilities | FAASt [Automation Program Group 34] (Distribution) | 0 | 4339DR-PR (4339DR) | 2755938.99 | 0 | 0 | 275593.89 | 275593.89 | 2480345.1 | 90% | 2025-11-05 16:17 | 2025-11-05 16:17 | 0
757698 | 108039 | F - Utilities | FAASt [Automation Program Group 33] (Distribution) | 0 | 4339DR-PR (4339DR) | 1888928.21 | 0 | 0 | 188892.82 | 188892.82 | 1700035.39 | 90% | 2025-09-25 17:15 | 2025-09-25 17:15 | 0
757697 | 108038 | F - Utilities | FAASt [Automation Program Group 32] (TL / Distribution) | 0 | 4339DR-PR (4339DR) | 1996678.58 | 0 | 0 | 199667.85 | 199667.85 | 1797010.73 | 90% | 2025-09-25 17:15 | 2025-09-25 17:15 | 0
757696 | 108037 | F - Utilities | FAASt [Automation Program Group 31] (Distribution) | 1 | 4339DR-PR (4339DR) | 946338.47 | 0 | 0 | 94633.84 | 114545.76 | 1030911.85 | 90% | 2025-09-17 19:15 | 2025-09-17 19:15 | 0
746309 | 107959 | F - Utilities | FAASt [Automation Program Group 30] (Distribution) | 0 | 4339DR-PR (4339DR) | 564064.63 | 236273.14 | 0 | 56406.46 | 56406.46 | 507658.17 | 90% | 2026-03-01 18:16 | 2026-03-01 18:16 | 0
705657 | 107826 | F - Utilities | FAASt [Automation Program Group 3] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
757694 | 108036 | F - Utilities | FAASt [Automation Program Group 27] (Distribution) | 0 | 4339DR-PR (4339DR) | 2314733.78 | 0 | 0 | 231473.37 | 231473.37 | 2083260.41 | 90% | 2025-09-25 16:16 | 2025-09-25 16:16 | 0
757692 | 108035 | F - Utilities | FAASt [Automation Program Group 26] (TL / Distribution) | 1 | 4339DR-PR (4339DR) | 776231.46 | 0 | 0 | 77623.14 | 93878.36 | 844905.27 | 90% | 2025-09-03 20:15 | 2025-09-03 20:15 | 0
757689 | 108034 | F - Utilities | FAASt [Automation Program Group 24] (TL/ Distribution) | 0 | 4339DR-PR (4339DR) | 1774822.4 | 0 | 0 | 177482.24 | 177482.24 | 1597340.16 | 90% | 2025-09-17 19:15 | 2025-09-17 19:15 | 0
757662 | 108032 | F - Utilities | FAASt [Automation Program Group 21] (Distribution) | 0 | 4339DR-PR (4339DR) | 1710547.94 | 0 | 0 | 171054.79 | 171054.79 | 1539493.15 | 90% | 2025-10-30 20:15 | 2025-10-30 20:15 | 0
752810 | 108001 | F - Utilities | FAASt [Automation Program Group 20] (Distribution) | 1 | 4339DR-PR (4339DR) | 1643793.56 | 0 | 0 | 164379.35 | 262326.2 | 2360935.88 | 90% | 2025-02-06 20:16 | 2025-02-06 20:16 | 0
740662 | 107939 | F - Utilities | FAASt [Automation Program Group 2] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
752503 | 107998 | F - Utilities | FAASt [Automation Program Group 1D] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
752502 | 107997 | F - Utilities | FAASt [Automation Program Group 1C] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
752500 | 107996 | F - Utilities | FAASt [Automation Program Group 1B] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
688623 | 107781 | F - Utilities | FAASt [Automation Program Group 1A] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
752808 | 108000 | F - Utilities | FAASt [Automation Program Group 19] (Distribution) | 1 | 4339DR-PR (4339DR) | 2076544.96 | 723597.72 | 0 | 207654.49 | 275362.72 | 2478264.52 | 90% | 2025-02-06 20:16 | 2025-02-06 20:16 | 0
745859 | 11839 | F - Utilities | FAASt [Automation Program Group 18] (TL/Distribution) | 1 | 4339DR-PR (4339DR) | 422345.48 | 198410.11 | 0 | 42234.54 | 42234.54 | 420558.84 | 90% | 2024-09-18 15:15 | 2024-09-18 15:15 | 467287.6
755211 | 108022 | F - Utilities | FAASt [Automation Program Group 15] (Distribution) | 4 | 4339DR-PR (4339DR) | 527176.83 | 250899.06 | 0 | 52717.68 | 52717.68 | 579204.77 | 90% | 2025-02-06 20:16 | 2025-08-30 04:15 | 0
729522 | 107905 | F - Utilities | FAASt [Automation Program Group 15: San Juan] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
745856 | 107956 | F - Utilities | FAASt [Automation Program Group 14] (TL/Distribution) | 1 | 4339DR-PR (4339DR) | 1410445.2 | 0 | 0 | 141044.52 | 164018.69 | 1476168.27 | 90% | 2025-02-06 20:16 | 2025-02-06 20:16 | 0
745852 | 107954 | F - Utilities | FAASt [Automation Program Group 13] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
745861 | 107957 | F - Utilities | FAASt [Automation Program Group 12] (Distribution) | 1 | 4339DR-PR (4339DR) | 2177655.77 | 0 | 0 | 217765.57 | 366421.01 | 3297789.09 | 90% | 2025-02-06 20:16 | 2025-02-06 20:16 | 0
745851 | 107953 | F - Utilities | FAASt [Automation Program Group 11] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
745871 | 107958 | F - Utilities | FAASt [Automation Program Group 10] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
724703 | 11671 | F - Utilities | FAASt [Arroyo Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 6054726.01 | 740394.01 | 0 | 605472.6 | 605472.6 | 5449253.41 | 90% | 2024-06-18 11:28 | 2024-06-17 13:38 | 6054726.01
678795 | 11535 | F - Utilities | FAASt [Arecibo Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 16121105.57
734853 | 11837 | F - Utilities | FAASt [Arecibo Streetlighting- Part 3] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 15679863.58
735131 | 11775 | F - Utilities | FAASt [Arecibo Streetlighting - Part 2] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 11247096.52
956342 | 108153 | F - Utilities | FAASt [Arecibo Region 2 Line 36400 (115Kv) – Ponce TC to Dos Bocas HP] (Vegetation) | 0 | 4339DR-PR (4339DR) | 4093248.38 | 0 | 0 | 409324.83 | 409324.83 | 3683923.55 | 90% | 2025-09-17 18:16 | 2025-09-17 18:16 | 0
956353 | 108158 | F - Utilities | FAASt [Arecibo Region 2 Line 36100 (115kV) – Dos Bocas HP to Barrio Pina] (Vegetation) | 0 | 4339DR-PR (4339DR) | 3756065.08 | 0 | 0 | 375606.5 | 375606.5 | 3380458.58 | 90% | 2025-09-17 18:16 | 2025-09-17 18:16 | 0
956345 | 108155 | F - Utilities | FAASt [Arecibo Region 2 Line 2400 (38kV) – Dos Bocas HP to Caonillas 2] (Vegetation) | 0 | 4339DR-PR (4339DR) | 738869.51 | 681585.25 | 0 | 73886.95 | 73886.95 | 0 | 90% |  |  | 0
704927 | 11711 | F - Utilities | FAASt [Añasco Streetlighting] (Distribution) | 1 | 4339DR-PR (4339DR) | 13908238.09 | 1820361.92 | 0 | 1390823.81 | 1390823.81 | 12517414.28 | 90% | 2024-07-08 11:28 | 2024-07-05 12:49 | 13908238.09
741105 | 107946 | F - Utilities | FAASt [All Regions TL - 230kV] (Vegetation) | 0 | 4339DR-PR (4339DR) | 12885805.47 | 10455751.16 | 0 | 1288580.54 | 1288580.54 | 11597224.93 | 90% | 2026-03-01 18:15 | 2026-03-01 18:15 | 0
659715 | 10876 | F - Utilities | FAASt [Aibonito Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 7253285 | 178787 | 0 | 725328.5 | 725328.5 | 6527956.5 | 90% | 2022-12-27 11:53 | 2022-12-23 21:10 | 7253285
178503 | 11100 | F - Utilities | FAASt [Aguirre TC - BKRS] (Substations) | 1 | 4339DR-PR (4339DR) | 39034592 | 0 | 0 | 3903459.2 | 3903459.2 | 35131132.8 | 90% | 2022-12-27 11:53 | 2022-12-23 21:15 | 39034592
669815 | 10622 | F - Utilities | FAASt [Aguirre Power Plant 003 Combined Cycle] (Generation) | 4 | 4339DR-PR (4339DR) | 7410085.36 | 0 | 0 | 741008.54 | 638496.54 | 5746468.82 | 90% | 2022-06-16 11:23 | 2024-03-06 20:16 | 6384965.36
669498 | 10571 | F - Utilities | FAASt [Aguirre Power Plant 001 Infrastructure Projects] (Generation) | 5 | 4339DR-PR (4339DR) | 3402594.28 | 0 | 0 | 340259.42 | 340259.42 | 3062334.86 | 90% | 2022-05-26 11:24 | 2025-05-12 19:16 | 3402594.28
724941 | 11733 | F - Utilities | FAASt [Aguas Buenas Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 12947297.84
690545 | 11319 | F - Utilities | FAASt [Aguadilla Streetlighting] (Distribution) | 1 | 4339DR-PR (4339DR) | 21092584 | 1295775 | 0 | 2109258.4 | 2109258.4 | 18983325.6 | 90% | 2023-05-17 11:31 | 2023-05-16 19:39 | 21092584
734859 | 11780 | F - Utilities | FAASt [Aguadilla Streetlighting - Part 2] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 8885681.25
542688 | 10539 | F - Utilities | FAASt [Aguada Streetlighting] (Distribution) | 1 | 4339DR-PR (4339DR) | 18571716.38 | 807222.04 | 0 | 1857171.64 | 1857171.64 | 16714544.74 | 90% | 2022-05-05 12:44 | 2022-04-27 21:49 | 18571716.38
714654 | 11583 | F - Utilities | FAASt [Advanced Metering Infrastructure (AMI)] (Telecommunications) | 2 | 4339DR-PR (4339DR) | 876270176 | 544207595 | 0 | 87627017.6 | 87627017.6 | 788643158.4 | 90% | 2023-12-08 11:19 | 2024-04-30 12:42 | 876270176
724698 | 11734 | F - Utilities | FAASt [Adjuntas Streetlighting] (Distribution) | 0 | 4339DR-PR (4339DR) | 12633614 | 1891152 | 0 | 1263361.4 | 1263361.4 | 11370252.6 | 90% | 2024-06-18 11:28 | 2024-06-17 13:38 | 12633614
547344 | 107702 | F - Utilities | FAASt [Acacias 6801 TC Relocation] (Substation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
752972 | 108002 | F - Utilities | FAASt [4 x 25 MW BESS Interconnections Manati] (Substation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
805521 | 108093 | F - Utilities | FAASt [38kV Recloser TL 7800 Dorado TC to Vega Alta Sect.] (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
805517 | 108091 | F - Utilities | FAASt [38kV Recloser TL 2100 Hatillo TC to Quebradillas Sect.] (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
805519 | 108092 | F - Utilities | FAASt [38kV Recloser TL 1900 Dos Bocas HP to San Sebastian TC] (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
750503 | 107978 | F - Utilities | FAASt [25 MW BESS Installation and Integration - San Juan] (Substation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
738671 | 11819 | F - Utilities | FAASt [25 MW BESS Installation and Integration - Barceloneta] (Substation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
750502 | 107977 | F - Utilities | FAASt [25 MW BESS Installation and Integration - Aguadilla] (Substation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
711909 | 107858 | F - Utilities | FAASt [ TL100 Jobos TC to Guayama TO] (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
713181 | 107869 | F - Utilities | FAASt [ Substation Minor Repairs - Group E-2] (Substation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
713179 | 107868 | F - Utilities | FAASt [ Minor Repairs - Group D-1] (Substation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
730784 | 107910 | F - Utilities | FAASt [ Line 6700 Martin Peña TC to Villamar Sect.] (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
745854 | 107955 | F - Utilities | FAASt [ Automation Program Group 9] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
546370 | 10858 | F - Utilities | FAASt - Substation Minor Repairs Group A (Substation) | 1 | 4339DR-PR (4339DR) | 4971175.09 | 488202.58 | 0 | 497117.51 | 497117.51 | 4474057.58 | 90% | 2024-02-13 12:36 | 2024-02-12 18:53 | 4971175.09
550500 | 107718 | E - Buildings and Equipment | FAASt - Ponce Region Repairs (Building) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
179558 | 10632 | F - Utilities | FAASt - Manatí TC - BRKS 230 kV - (Substation) | 0 | 4339DR-PR (4339DR) | 1593443 | 0 | 0 | 159344.3 | 159344.3 | 1434098.7 | 90% | 2022-05-26 11:24 | 2022-05-25 13:16 | 1593443
169058 | 107220 | F - Utilities | FAASt - Llorens Torres MC 1106 - Equipment Repair & Replacement - (Substations) | 0 | 4339DR-PR (4339DR) | 18279001 | 0 | 0 | 1827900.1 | 0 | 0 | 90% |  |  | 0
180326 | 11441 | F - Utilities | FAASt - Line 36800 (115kV) - Sabana Llana TC to Canovanas TC to Palmer-Fajardo TC (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
167443 | 11251 | F - Utilities | FAASt - Line 36200 (115KV)- Monacillos TC to Juncos TC (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
167446 | 11307 | F - Utilities | FAASt - Line 36100 (115kV) - Bayamon to Monacillos (Transmission) | 0 | 4339DR-PR (4339DR) | 33956314.58 | 0 | 0 | 3395631.45 | 3395631.45 | 30560683.13 | 90% | 2025-11-05 16:17 | 2025-11-05 16:17 | 0
725535 | 11510 | F - Utilities | FAASt - IT/0T System Upgrade for: Aguirre Power Plant, Aguirre Combined Cycle, Cambalache, Mayaguez, Costa Sur, San Juan and Palo Seco (Telecommunication) | 1 | 4339DR-PR (4339DR) | 11423825 | 0 | 0 | 1142382.5 | 1142382.5 | 10281442.5 | 90% | 2023-10-04 11:44 | 2023-10-03 13:56 | 11423825
682121 | 11652 | F - Utilities | FAASt - EPC -Aguirre TC-Phase II (Substation) | 1 | 4339DR-PR (4339DR) | 82726096.38 | 0 | 0 | 8272609.64 | 8272609.64 | 74453486.74 | 90% | 2024-03-22 10:16 | 2024-03-21 20:05 | 82726096.38
165225 | 10624 | F - Utilities | FAASt - EPC - Vieques 2501 substation repairs & New Vieques 2502 substation (Substation) | 1 | 4339DR-PR (4339DR) | 14882946.25 | 178309 | 0 | 1488294.62 | 138742 | 1248678 | 90% | 2022-06-10 11:48 | 2022-06-09 19:56 | 15237167.97
723002 | 107888 | F - Utilities | FAASt - EPC - Jobos TC (Substation) | 0 | 4339DR-PR (4339DR) | 69904580.54 | 0 | 0 | 6990458.05 | 0 | 0 | 90% |  |  | 0
165209 | 10626 | F - Utilities | FAASt - EPC - Culebra Substation 3801 and New Culebra Substation 3802 (Substation) | 1 | 4339DR-PR (4339DR) | 14225437 | 177391 | 0 | 1422543.7 | 145960.9 | 1313648.1 | 90% | 2022-06-10 11:48 | 2022-06-09 19:56 | 13790088.7
723078 | 11555 | F - Utilities | FAASt - EPC - [San Juan SP TC] (Substation) | 0 | 4339DR-PR (4339DR) | 61558468.95 | 0 | 0 | 6155846.89 | 6155846.89 | 55402622.06 | 90% | 2023-12-19 12:23 | 2023-12-18 19:00 | 61558468.95
723077 | 11556 | F - Utilities | FAASt - EPC - [Sabana Llana TC] (Substation) | 1 | 4339DR-PR (4339DR) | 46643078.39 | 0 | 0 | 4664307.83 | 4664307.83 | 41978770.56 | 90% | 2023-12-19 12:23 | 2025-04-28 19:15 | 100686731.41
550950 | 11557 | F - Utilities | FAASt - EPC - [Monacillo TC] (Substations) | 1 | 4339DR-PR (4339DR) | 58195134.17 | 0 | 0 | 5819513.41 | 5819513.41 | 52375620.76 | 90% | 2023-12-19 12:23 | 2025-09-17 18:16 | 88096455.73
825753 | 108133 | F - Utilities | FAASt - EPC - [Guanica TC] (Substation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
169896 | 10788 | F - Utilities | FAASt - Costa Sur SP TC – Equipment Repair and Replacement (Substation) | 0 | 4339DR-PR (4339DR) | 23251835 | 0 | 0 | 2325183.5 | 2325183.5 | 20926651.5 | 90% | 2022-08-02 11:42 | 2022-08-01 20:47 | 23251835
174422 | 10496 | F - Utilities | FAASt - Catano-Rebuild 1801(Substation) | 0 | 4339DR-PR (4339DR) | 23255048.94 | 6895149.77 | 0 | 2325504.89 | 2325504.89 | 20929544.05 | 90% | 2022-05-18 11:30 | 2022-05-17 13:31 | 23255048.94
177191 | 11433 | F - Utilities | FAASt - 115kV Line 39000 - Aguas Buenas TC to Caguas TC (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
168483 | 11241 | F - Utilities | FAASt - 115kV Line 36400 - Dos Bocas HP to Ponce TC (Transmission) | 0 | 4339DR-PR (4339DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
178258 | 11721 | F - Utilities | FAASt - [Taft - MC 1105] (Substations) | 0 | 4339DR-PR (4339DR) | 13486572.33 | 4123842.4 | 0 | 1348657.23 | 1348657.23 | 12137915.1 | 90% | 2025-02-06 20:16 | 2025-02-06 20:16 | 13504745.41
547187 | 107690 | F - Utilities | FAASt - [Substation Component Replacement Program] (Substation) | 0 | 4339DR-PR (4339DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
550498 | 107717 | F - Utilities | FAASt - [Morovis 8801 (Fuse to Breaker)] (Substation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
334323 | 10630 | F - Utilities | FAASt Distribution Pole and Conductor Repair - Ponce Group 1 (Distribution) | 1 | 4339DR-PR (4339DR) | 392822 | 69130 | 0 | 39282.2 | 39282.2 | 353539.8 | 90% | 2022-05-26 11:24 | 2022-05-25 13:16 | 392822
703222 | 107824 | F - Utilities | FAASt [Transmission and Distribution Automation Program Installation of Intelligent Reclosers, Single Phase Reclosers and Fault Current Indicators Group 2] (Transmission and Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
169495 | 11479 | F - Utilities | FAASt [Substations - Tapia GIS Rebuilt Equipment Repair & Replacement] (Substations) | 0 | 4339DR-PR (4339DR) | 15339932.33 | 7159883.3 | 0 | 1533993.23 | 1533993.23 | 13805939.1 | 90% | 2023-08-22 11:21 | 2023-08-21 20:04 | 15339932.33
797148 | 108074 | F - Utilities | FAASt [Feeder Rebuild # 8101-03] (Distribution) | 1 | 4339DR-PR (4339DR) | 2359895.63 | 0 | 0 | 235989.56 | 235989.56 | 2123906.07 | 90% | 2025-09-17 18:16 | 2025-09-17 18:16 | 0
764706 | 108057 | F - Utilities | FAASt [Feeder Rebuild # 7011-03] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
801166 | 108082 | F - Utilities | FAASt [Feeder Rebuild # 6601-03] (Distribution) | 0 | 4339DR-PR (4339DR) | 19826783.47 | 0 | 0 | 1982678.34 | 1982678.34 | 17844105.13 | 90% | 2026-01-08 16:17 | 2026-01-08 16:17 | 0
764707 | 108058 | F - Utilities | FAASt [Feeder Rebuild # 6012-02] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
764708 | 108059 | F - Utilities | FAASt [Feeder Rebuild # 5602-02] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
767139 | 108064 | F - Utilities | FAASt [Feeder Rebuild # 2906-02] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
760577 | 108051 | F - Utilities | FAASt [Feeder Rebuild # 1718-02] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
760575 | 108050 | F - Utilities | FAASt [Feeder Rebuild # 1716-03] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
798275 | 108075 | F - Utilities | FAASt [Feeder Rebuild # 1620-02] (Distribution) | 0 | 4339DR-PR (4339DR) | 6711420.9 | 0 | 0 | 671142.09 | 671142.09 | 6040278.81 | 90% | 2025-09-17 18:16 | 2025-09-17 18:16 | 0
801172 | 108083 | F - Utilities | FAASt [Feeder Rebuild # 1529-15] (Distribution) | 0 | 4339DR-PR (4339DR) | 2285961.13 | 0 | 0 | 228596.11 | 228596.11 | 2057365.02 | 90% | 2025-09-17 18:16 | 2025-09-17 18:16 | 0
767005 | 108062 | F - Utilities | FAASt [Feeder Rebuild # 1303-05] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
764709 | 108060 | F - Utilities | FAASt [Feeder Rebuild # 1204-05] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
767381 | 108067 | F - Utilities | FAASt [Feeder Rebuild # 1204-04] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
801197 | 108084 | F - Utilities | FAASt [Feeder Rebuild # 1204-02] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
169503 | 107224 | F - Utilities | FAASt [Ceiba Baja TRF 7012] (Substation) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
169500 | 11347 | F - Utilities | FAASt [Bayamon TC – MC-BKRS-Y1] (Substation) | 0 | 4339DR-PR (4339DR) | 6372063 | 3575881 | 0 | 637206.3 | 637206.3 | 5734856.7 | 90% | 2023-06-16 12:55 | 2023-06-15 13:07 | 6372063
800286 | 108077 | F - Utilities | FAASt [Automation Program Group 36] (TL / Distribution) | 1 | 4339DR-PR (4339DR) | 2422655.03 | 995016.61 | 0 | 242265.5 | 170371.28 | 1533341.55 | 90% | 2025-09-17 19:15 | 2025-09-17 19:15 | 0
166707 | 11431 | F - Utilities | FAASt - Line 51300 (230KV) - Ponce TC to Costa Sur SP TC (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
743440 | 4174 | B - Emergency Protective Measures | Emergency Restoration Contract LEOC | 0 | 4671DR-PR (4671DR) | 6973559.96 | 0 | 0 | 0 | 0 | 6973559.96 | 100% | 2026-02-27 14:17 | 2026-02-27 14:17 | 0
743449 | 4175 | B - Emergency Protective Measures | Emergency Restoration Contract - Post LEOC | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
719724 | 3971 | B - Emergency Protective Measures | Emergency Protective Measures Transmission Lines 1200, 1600, 2700, 2800, 5600 (100% Cost Share) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
718683 | 3967 | B - Emergency Protective Measures | Emergency Protective Measures Feeders 7505-05, 7503-05, 1801-03, 6703-01, 1717-03 (90% Cost Share) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
715898 | 3964 | B - Emergency Protective Measures | Emergency Protective Measures Feeders 3502-02, 3014-04, 3014-02, 6601-04, 2401-01 (90% Cost Share) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
715896 | 3963 | B - Emergency Protective Measures | Emergency Protective Measures Feeders 3502-02, 3014-04, 3014-02, 6601-04, 2401-01 (100% Cost Share) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
714166 | 3934 | B - Emergency Protective Measures | Emergency Protective Measures Feeders 3406-03 9103-01 9201-02 9802-04 8701-04 (Cost share 90%) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
715260 | 3955 | B - Emergency Protective Measures | Emergency Protective Measures Feeders 3406-03 9103-01 9201-02 9802-04 8701-04 (Cost share 100%) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
726294 | 4072 | B - Emergency Protective Measures | Emergency Protective Measures - Río Bayamón (Substation) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
728397 | 4078 | B - Emergency Protective Measures | Emergency Protective Measures - Rincon (Substation) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
723085 | 4008 | B - Emergency Protective Measures | Emergency Protective Measures - Regional Approach composed of seven (7) regions - Arecibo, Bayamón, Caguas, Centralized, Mayaguez, Ponce & San Juan (100% Cost Share) | 0 | 4671DR-PR (4671DR) | 29467153.54 | 0 | 0 | 0 | 0 | 29467153.54 | 100% | 2026-02-27 14:17 | 2026-02-27 14:17 | 0
724010 | 4040 | B - Emergency Protective Measures | Emergency Protective Measures - McKinley (Substation) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
724049 | 4041 | B - Emergency Protective Measures | Emergency Protective Measures - Isabela Pueblo (Substation) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
740490 | 4148 | B - Emergency Protective Measures | Emergency Protective Measures - Incidental Works- Tekniek | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
740499 | 4151 | B - Emergency Protective Measures | Emergency Protective Measures - Incidental Works- IAPETUS | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
740495 | 4150 | B - Emergency Protective Measures | Emergency Protective Measures - Incidental Works- CERES | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
740492 | 4149 | B - Emergency Protective Measures | Emergency Protective Measures - Incidental Works- Bird | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
724909 | 4051 | B - Emergency Protective Measures | Emergency Protective Measures - Hospital Distrito Aguadilla (Substation) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
728732 | 4084 | B - Emergency Protective Measures | Emergency Protective Measures - Coamo 4602 (Substation) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
721591 | 3997 | B - Emergency Protective Measures | Emergency Protective Measures - Canovanas TC Substation | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
726862 | 4075 | B - Emergency Protective Measures | Emergency Protective Measures - Breñas (Substation) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
722524 | 4003 | B - Emergency Protective Measures | Emergency Protective Measures - Berwind TC (Substation) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
703719 | 3465 | B - Emergency Protective Measures | Emergency Protective Measures (Transmission) (Distribution) (Substation) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
703717 | 3463 | B - Emergency Protective Measures | Emergency Protective Measures (Transmission) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
703713 | 3462 | B - Emergency Protective Measures | Emergency Protective Measures (Substation) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
703718 | 3464 | B - Emergency Protective Measures | Emergency Protective Measures (Distribution) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
728937 | 4089 | B - Emergency Protective Measures | Emergency Operations Center - Expenses (Meals & Travel) - Regional Approach (DR-4671 - FIONA) | 0 | 4671DR-PR (4671DR) | 3285133.78 | 0 | 0 | 0 | 0 | 3285133.78 | 100% | 2025-08-19 15:16 | 2025-08-19 15:16 | 0
686436 | 119 | B - Emergency Protective Measures | Emergency Inventory Supply - LNG (Generation) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 100% |  |  | 0
734161 | 4120 | B - Emergency Protective Measures | Emergency Contracts - Post LEOC Period - A&E and Other Services - DR-4671-PR (90% Cost Share) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
734159 | 4119 | B - Emergency Protective Measures | Emergency Contracts - LEOC Period - A&E and Other Services - DR-4671-PR (100% Cost Share) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
743373 | 4170 | B - Emergency Protective Measures | Emergency & Other Services Contracts - Post LEOC - 90% Cost Share | 0 | 4671DR-PR (4671DR) | 4268438 | 0 | 0 | 426843.8 | 426843.8 | 3841594.2 | 90% | 2025-03-28 22:16 | 2025-03-28 22:16 | 0
743439 | 4173 | B - Emergency Protective Measures | Emergency & Other Services Contracts - LEOC | 0 | 4671DR-PR (4671DR) | 16173760.13 | 0 | 0 | 0 | 0 | 16173760.13 | 100% | 2026-02-27 14:17 | 2026-02-27 14:17 | 0
743379 | 4172 | B - Emergency Protective Measures | Electrical Services - Contract LEOC | 0 | 4671DR-PR (4671DR) | 5376107.23 | 0 | 0 | 0 | 0 | 5376107.23 | 100% | 2026-02-27 14:17 | 2026-02-27 14:17 | 0
96465 | 150 | B - Emergency Protective Measures | EEPA014 - EMCCO Emergency Protective Measures | 1 | 3384EM-PR (3384EM) | 102773.8 | 0 | 0 | 25693.45 | 25693.45 | 77080.35 | 75% | 2020-01-30 12:34 | 2023-01-12 22:13 | 102773.8
86795 | 149 | B - Emergency Protective Measures | EEPA013 - Retirees (LC) | 0 | 3384EM-PR (3384EM) | 17929 | 0 | 0 | 4482.25 | 4482.25 | 13446.75 | 75% | 2019-12-17 13:42 | 2019-12-16 18:20 | 17929
80518 | 138 | Z - Management Costs | EEPA012- PREPA Management Costs | 1 | 3384EM-PR (3384EM) | 701037.25 | 0 | 0 | 0 | 0 | 701037.25 | 100% | 2019-10-31 11:07 | 2023-06-28 13:28 | 701037.25
91161 | 100025 | B - Emergency Protective Measures | EEPA011 - Bonneville Contracting and Technology Group LLC (LC) | 0 | 3384EM-PR (3384EM) |  |  | 0 |  | 0 | 0 | 75%
79949 | 100023 | B - Emergency Protective Measures | EEPA010 - All Contractors (LC) | 0 | 3384EM-PR (3384EM) | 261195.5 | 0 | 0 | 65298.87 | 0 | 0 | 75% |  |  | 0
79243 | 145 | B - Emergency Protective Measures | EEPA009- C Principe (LC) | 0 | 3384EM-PR (3384EM) | 47256.22 | 0 | 0 | 11814.05 | 11814.05 | 35442.17 | 75% | 2020-01-29 12:26 | 2020-01-28 15:10 | 47256.22
49795 | 98 | B - Emergency Protective Measures | EEPA008 EMERGENCY PROTECTIVE MEASURES | 1 | 3384EM-PR (3384EM) | 7109642 | 0 | 0 | 1777410.5 | 1777410.5 | 5332231.5 | 75% | 2018-07-13 | 2018-07-13 21:29 | 7109642
49794 | 83 | B - Emergency Protective Measures | EEPA005 EMERGENCY PROTECTIVE MEASURES-DISTRIBUTION | 1 | 3384EM-PR (3384EM) | 66616.37 | 0 | 0 | 16654.09 | 16654.09 | 49962.28 | 75% | 2018-05-31 | 2018-05-31 20:42 | 66616.37
49791 | 72 | B - Emergency Protective Measures | EEPA004 - Emergency Protective Measures | 1 | 3384EM-PR (3384EM) | 14166.4 | 0 | 0 | 3541.6 | 3541.6 | 10624.8 | 75% | 2018-04-30 | 2018-04-30 21:08 | 14166.4
137964 | 892 | B - Emergency Protective Measures | Earthquake Temporary Generators | 0 | 4473DR-PR (4473DR) |  |  | 0 |  | 0 | 0 | 75%
147491 | 949 | B - Emergency Protective Measures | Earthquake Safety Inspection | 0 | 4473DR-PR (4473DR) |  |  | 0 |  | 0 | 0 | 75%
137955 | 7 | B - Emergency Protective Measures | Earthquake Peaking Units | 2 | 4473DR-PR (4473DR) | 375140912.3 | 0 | -130681001 | 37514091.23 | 37514091.23 | 337626821.07 | 90% | 2020-10-13 11:15 | 2022-10-14 15:44 | 375140912.3
146915 | 943 | B - Emergency Protective Measures | Earthquake - South Emergency Repairs | 0 | 4473DR-PR (4473DR) |  |  | 0 |  | 0 | 0 | 75%
146684 | 941 | B - Emergency Protective Measures | Earthquake - Hydro Gas Central Mayaguez | 0 | 4473DR-PR (4473DR) |  |  | 0 |  | 0 | 0 | 75%
814595 | 84 | B - Emergency Protective Measures | DR4850 - PREPA_SPA Cat B - Yabucoa, Añasco Municipalities - Distribution (75% Cost Share) | 0 | 4850DR-PR (4850DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
814644 | 94 | B - Emergency Protective Measures | DR4850 - PREPA_SPA Cat B - Villalba Municipality - T&D (75% Cost Share) | 0 | 4850DR-PR (4850DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
814576 | 77 | B - Emergency Protective Measures | DR4850 - PREPA_SPA Cat B - Utuado Municipality - Distribution (75% Cost Share) | 0 | 4850DR-PR (4850DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
814593 | 83 | B - Emergency Protective Measures | DR4850 - PREPA_SPA Cat B - San Lorenzo Municipality - Distribution (75% Cost Share) | 0 | 4850DR-PR (4850DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
814634 | 88 | B - Emergency Protective Measures | DR4850 - PREPA_SPA Cat B - San German, Hormigueros, Las Marias Municipalities - T&D (75% Cost Share) | 0 | 4850DR-PR (4850DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
814639 | 92 | B - Emergency Protective Measures | DR4850 - PREPA_SPA Cat B - Ponce Municipality Distribution- Group 1( 5001/5002/5003/5004/5005/5007/5008) (75% Cost Share) | 0 | 4850DR-PR (4850DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
814591 | 82 | B - Emergency Protective Measures | DR4850 - PREPA_SPA Cat B - Orocovis, Comerio Municipalities - Distribution (75% Cost Share) | 0 | 4850DR-PR (4850DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
814589 | 81 | B - Emergency Protective Measures | DR4850 - PREPA_SPA Cat B - Naguabo Municipality - T&D (75% Cost Share) | 0 | 4850DR-PR (4850DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
814636 | 89 | B - Emergency Protective Measures | DR4850 - PREPA_SPA Cat B - Mayaguez - Distribution Group 1 (75% Cost Share) | 0 | 4850DR-PR (4850DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
814637 | 90 | B - Emergency Protective Measures | DR4850 - PREPA_SPA Cat B - Maricao Municipality - Distribution (75% Cost Share) | 0 | 4850DR-PR (4850DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
814795 | 98 | B - Emergency Protective Measures | DR4850 - PREPA_SPA Cat B - Luquillo Municipality Distribution Group 1 (2201-01/2201-02) (75% Cost Share) | 0 | 4850DR-PR (4850DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
814629 | 86 | B - Emergency Protective Measures | DR4850 - PREPA_SPA Cat B - Lares Municipality - Distribution (75% Cost Share) | 0 | 4850DR-PR (4850DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
814566 | 75 | B - Emergency Protective Measures | DR4850 - PREPA_SPA Cat B - Jayuya Municipality - T&D (75% Cost Share) | 0 | 4850DR-PR (4850DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
814646 | 95 | B - Emergency Protective Measures | DR4850 - PREPA_SPA Cat B - Fajardo Municipality Distribution Group 1( 2001/2002/2003)(75% Cost Share) | 0 | 4850DR-PR (4850DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
814794 | 97 | B - Emergency Protective Measures | DR4850 - PREPA_SPA Cat B - Fajardo Municipality Distribution Group 2 ( 2005/2006/2201) (75% Cost Share) | 0 | 4850DR-PR (4850DR) | 810088.14 | 0 | 0 | 202522.03 | 0 | 0 | 75% |  |  | 0
814581 | 78 | B - Emergency Protective Measures | DR4850 - PREPA_SPA Cat B - Corozal Municipality - Distribution (75% Cost Share) | 0 | 4850DR-PR (4850DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
814638 | 91 | B - Emergency Protective Measures | DR4850 - PREPA_SPA Cat B - Coamo, Arroyo, Maunabo, Santa Isabel Municipalities - Distribution (75% Cost Share) | 0 | 4850DR-PR (4850DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
811895 | 19 | B - Emergency Protective Measures | DR4850 - PREPA_SPA Cat B - Canovanas, Vieques, Loiza Municipalities - T&D (75% Cost Share) | 0 | 4850DR-PR (4850DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
814598 | 85 | B - Emergency Protective Measures | DR4850 - PREPA_SPA Cat B - Cabo Rojo Municipality - Distribution (75% Cost Share) | 0 | 4850DR-PR (4850DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
814586 | 80 | B - Emergency Protective Measures | DR4850 - PREPA_SPA Cat B - Aibonito, Barranquitas Municipalities - Distribution (75% Cost Share) | 0 | 4850DR-PR (4850DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
814584 | 79 | B - Emergency Protective Measures | DR4850 - PREPA_SPA Cat B - Aguas Buenas, Las Piedras Municipalities - T&D (75% Cost Share) | 0 | 4850DR-PR (4850DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
814572 | 76 | B - Emergency Protective Measures | DR4850 - PREPA_SPA Cat B - Adjuntas, Camuy, Manati, Vega Alta Municipalities - Distribution (75% Cost Share) | 0 | 4850DR-PR (4850DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
814642 | 93 | B - Emergency Protective Measures | DR4850 - PREPA_SPA Cat B - Ponce Municipality- Distribution- Group 2 (5011/5012/5013/5018/5021/5805) (75% Cost Share) | 0 | 4850DR-PR (4850DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
816811 | 150 | B - Emergency Protective Measures | DR4850 - PREPA _SPA Cat B - San Sebastian Municipality-Distribution(75% Cost Share) | 0 | 4850DR-PR (4850DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
816804 | 147 | B - Emergency Protective Measures | DR4850 - PREPA _SPA Cat B - Rio Grande Municipality -Distribution Group 1 (2201-04,2301-02, 2302-01, 2302-03,2305-01, 2305-02)(75% Cost Share) | 0 | 4850DR-PR (4850DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
816806 | 148 | B - Emergency Protective Measures | DR4850 - PREPA _SPA Cat B - Mayaguez Municipality- Group 2 (75% Cost Share) | 0 | 4850DR-PR (4850DR) | 746631.06 | 0 | 0 | 186657.76 | 0 | 0 | 75% |  |  | 0
816798 | 145 | B - Emergency Protective Measures | DR4850 - PREPA _SPA Cat B - Luquillo Municipality-Distribution Group 2 (2201-03/2201-04) (75% Cost Share) | 0 | 4850DR-PR (4850DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
816800 | 146 | B - Emergency Protective Measures | DR4850 - PREPA _SPA Cat B - Luquillo Municipality Group 3 (2002-03/ 2305-02) - T&D (75% Cost Share) | 0 | 4850DR-PR (4850DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
816807 | 149 | B - Emergency Protective Measures | DR4850 - PREPA _SPA Cat B - Ceiba Municipality- Distribution (75% Cost Share) | 0 | 4850DR-PR (4850DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
758145 | 36 | B - Emergency Protective Measures | DR4805 - PREPA _SPA Cat B - Yauco Municipality (75% Cost Share) | 0 | 4805DR-PR (4805DR) | 20633.85 | 0 | 0 | 5158.46 | 5158.46 | 15475.39 | 75% | 2025-02-10 20:15 | 2025-02-10 20:15 | 0
758138 | 31 | B - Emergency Protective Measures | DR4805 - PREPA _SPA Cat B - Utuado Municipality (75% Cost Share) | 0 | 4805DR-PR (4805DR) | 46157.86 | 0 | 0 | 11539.46 | 11539.46 | 34618.4 | 75% | 2025-02-10 20:15 | 2025-02-10 20:15 | 0
758139 | 32 | B - Emergency Protective Measures | DR4805 - PREPA _SPA Cat B - Toa Alta Municipality (75% Cost Share) | 0 | 4805DR-PR (4805DR) | 22048.97 | 0 | 0 | 5512.24 | 5512.24 | 16536.73 | 75% | 2025-02-10 20:15 | 2025-02-10 20:15 | 0
758147 | 38 | B - Emergency Protective Measures | DR4805 - PREPA _SPA Cat B - Sabana Grande Municipality (75% Cost Share) | 0 | 4805DR-PR (4805DR) | 7348.17 | 0 | 0 | 1837.04 | 1837.04 | 5511.13 | 75% | 2025-02-10 20:15 | 2025-02-10 20:15 | 0
757742 | 23 | B - Emergency Protective Measures | DR4805 - PREPA _SPA Cat B - Orocovis Municipality (75% Cost Share) | 0 | 4805DR-PR (4805DR) | 10625.48 | 0 | 0 | 2656.37 | 2656.37 | 7969.11 | 75% | 2025-02-10 20:15 | 2025-02-10 20:15 | 0
758140 | 33 | B - Emergency Protective Measures | DR4805 - PREPA _SPA Cat B - Naranjito Municipality (75% Cost Share) | 0 | 4805DR-PR (4805DR) | 27618.33 | 0 | 0 | 6904.58 | 6904.58 | 20713.75 | 75% | 2025-02-10 20:15 | 2025-02-10 20:15 | 0
758144 | 35 | B - Emergency Protective Measures | DR4805 - PREPA _SPA Cat B - Maricao Municipality (75% Cost Share) | 0 | 4805DR-PR (4805DR) | 19096.88 | 0 | 0 | 4774.22 | 4774.22 | 14322.66 | 75% | 2025-02-10 20:15 | 2025-02-10 20:15 | 0
758143 | 34 | B - Emergency Protective Measures | DR4805 - PREPA _SPA Cat B - Luquillo Municipality (75% Cost Share) | 0 | 4805DR-PR (4805DR) | 9710.08 | 0 | 0 | 2427.52 | 2427.52 | 7282.56 | 75% | 2025-02-10 20:15 | 2025-02-10 20:15 | 0
757750 | 25 | B - Emergency Protective Measures | DR4805 - PREPA _SPA Cat B - Las Marias Municipality (75% Cost Share) | 0 | 4805DR-PR (4805DR) | 7512.65 | 0 | 0 | 1878.16 | 1878.16 | 5634.49 | 75% | 2025-02-10 20:15 | 2025-02-10 20:15 | 0
757746 | 24 | B - Emergency Protective Measures | DR4805 - PREPA _SPA Cat B - Lajas Municipality (75% Cost Share) | 0 | 4805DR-PR (4805DR) | 12046.96 | 0 | 0 | 3011.74 | 3011.74 | 9035.22 | 75% | 2025-02-10 20:15 | 2025-02-10 20:15 | 0
758149 | 39 | B - Emergency Protective Measures | DR4805 - PREPA _SPA Cat B - Guanica Municipality (75% Cost Share) | 0 | 4805DR-PR (4805DR) | 9927.68 | 0 | 0 | 2481.92 | 2481.92 | 7445.76 | 75% | 2025-02-10 20:15 | 2025-02-10 20:15 | 0
758146 | 37 | B - Emergency Protective Measures | DR4805 - PREPA _SPA Cat B - Adjuntas Municipality (75% Cost Share) | 0 | 4805DR-PR (4805DR) | 11125.87 | 0 | 0 | 2781.46 | 2781.46 | 8344.41 | 75% | 2025-02-10 20:15 | 2025-02-10 20:15 | 0
758137 | 30 | B - Emergency Protective Measures | DR4805 - PREPA _ SPA Cat B - San Sebastian Municipality (75% Cost Share) | 0 | 4805DR-PR (4805DR) | 31603.13 | 0 | 0 | 7900.78 | 7900.78 | 23702.35 | 75% | 2025-02-10 20:15 | 2025-02-10 20:15 | 0
49790 | 100012 | B - Emergency Protective Measures | Customer Service | 0 | 4336DR-PR (4336DR) |  |  | 0 |  | 0 | 0 | 75%
171512 | 682 | F - Utilities | Costa Sur Tanks | 2 | 4473DR-PR (4473DR) | 8867111.62 | 79617.85 | 0 | 886711.16 | 566059.88 | 5094538.96 | 90% | 2022-03-29 11:51 | 2022-05-12 13:47 | 5660598.85
1064948 | 1134 | F - Utilities | Costa Sur Services | 0 | 4473DR-PR (4473DR) | 300000 | 0 | 0 | 30000 | 0 | 0 | 90% |  |  | 0
169723 | 1088 | F - Utilities | Costa Sur Service Tank #S2 - Distillate #6 (Bunker C) (s-5) | 0 | 4473DR-PR (4473DR) |  |  | 0 |  | 0 | 0 | 75%
171517 | 697 | F - Utilities | Costa Sur Power Plant Discharge Channels | 1 | 4473DR-PR (4473DR) | 5766576.11 | 5700000 | 0 | 576657.61 | 6657.61 | 59918.5 | 90% | 2022-05-09 11:29 | 2022-05-06 19:03 | 66576.11
171515 | 495 | E - Buildings and Equipment | Costa Sur Power Plant Buildings | 3 | 4473DR-PR (4473DR) | 5468891.2 | 356224.78 | 0 | 546889.12 | 546889.12 | 4922002.08 | 90% | 2022-02-09 12:34 | 2025-08-19 15:16 | 529036.3
164458 | 591 | B - Emergency Protective Measures | Costa Sur Emergency Protective Measures | 2 | 4473DR-PR (4473DR) | 7876402.03 | 0 | 0 | 787640.2 | 790859.29 | 7117733.68 | 90% | 2022-01-11 12:51 | 2022-03-21 19:26 | 7908592.97
745569 | 4232 | B - Emergency Protective Measures | Contract Call Center Emergency Center | 0 | 4671DR-PR (4671DR) | 459629.61 | 0 | 0 | 0 | 0 | 459629.61 | 100% | 2024-11-15 18:15 | 2024-11-15 18:15 | 0
49855 | 744 | B - Emergency Protective Measures | Closeout-MEPA146 - WANTO Electric Co. (LC) | 0 | 4339DR-PR (4339DR) | 227767.03 | 0 | 0 | 0 | 0 | 227767.03 | 100% | 2020-03-02 12:36 | 2020-02-28 18:20 | 227767.03
49852 | 517 | B - Emergency Protective Measures | CLOSEOUT-MEPA125-EMCCO (LC) | 1 | 4339DR-PR (4339DR) | 233596.4 | 0 | 0 | 0 | 0 | 233596.4 | 100% | 2020-01-15 13:11 | 2022-08-26 20:05 | 233596.4
49828 | 416 | B - Emergency Protective Measures | CLOSEOUT-MEPA113V1 - Peaking Generator Units (PW00416) | 1 | 4339DR-PR (4339DR) | 142018291 | 0 | 0 | 0 | 0 | 142018291 | 100% | 2018-05-30 | 2018-12-11 19:59 | 142018291
49788 | 56 | B - Emergency Protective Measures | Closeout PEOP01B - EMERGENCY PROTECTIVE MEASURES | 1 | 3384EM-PR (3384EM) | 8806716.36 | 0 | 0 | 2201679.09 | 2201679.09 | 6605037.27 | 75% | 2017-10-10 | 2025-09-19 22:15 | 7447142.23
49830 | 440 | B - Emergency Protective Measures | Closeout MEPA142 - Mega Generators Purchases | 1 | 4339DR-PR (4339DR) | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 2018-05-30 | 2020-08-21 16:07 | 0
79025 | 3907 | B - Emergency Protective Measures | Closeout MEPA121 -LC- Roman Electric | 1 | 4339DR-PR (4339DR) | 200000 | 0 | 0 | 0 | 0 | 200000 | 100% | 2020-04-11 13:09 | 2024-04-02 20:32 | 200000
138670 | 6311 | B - Emergency Protective Measures | CLOSEOUT MEPA079 -LC- MEC Engineering, PSC (90CS) | 1 | 4339DR-PR (4339DR) | 4035781.5 | 0 | 0 | 403578.15 | 403578.15 | 3632203.35 | 90% | 2020-09-18 11:26 | 2025-02-04 16:16 | 4035781.5
49823 | 282 | B - Emergency Protective Measures | CLOSEOUT MEPA077 - Vehicle and Equipment Purchase | 2 | 4339DR-PR (4339DR) | 10172396 | 0 | 0 | 0 | 0 | 10172396 | 100% | 2020-05-14 14:20 | 2023-11-06 22:21 | 10172396
49813 | 306 | B - Emergency Protective Measures | Closeout MEPA029 - MOU - PW306 (IOU) TAMPA | 3 | 4339DR-PR (4339DR) | 5521534.1 | 0 | 0 | 0 | 0 | 7555374 | 100% |  | 2018-09-07 15:59 | 5521534.1
180692 | 9312 | F - Utilities | CLOSEOUT FAASt Mobile Gens Units Purchases (Generation) | 1 | 4339DR-PR (4339DR) | 59740469.92 | 0 | 0 | 5974046.99 | 5974046.99 | 53766422.93 | 90% | 2023-01-10 13:19 | 2023-01-05 18:58 | 59740469.92
49821 | 358 | B - Emergency Protective Measures | Closeout -MEPA039-OTHER-XGL Freight Charges | 2 | 4339DR-PR (4339DR) | 26218410 | 0 | 0 | 0 | 0 | 26218410 | 100% | 2018-07-06 | 2021-12-22 12:02 | 26218410
96165 | 6928 | B - Emergency Protective Measures | Closeout - MEPA186 -LC- MEC Engineering, PSC (100CS) | 0 | 4339DR-PR (4339DR) | 672502.5 | 0 | 0 | 0 | 0 | 672502.5 | 100% | 2020-11-13 12:38 | 2020-11-12 20:19 | 672502.5
91194 | 9904 | B - Emergency Protective Measures | CLOSEOUT - MEPA183 - ST. JAMES SECURITY | 0 | 4339DR-PR (4339DR) | 70119 | 0 | 0 | 0 | 0 | 70119 | 100% | 2021-12-22 10:44 | 2021-12-21 12:12 | 70119
100283 | 2065 | B - Emergency Protective Measures | CLOSEOUT - MEPA177- Galo Services LLC (LC) | 0 | 4339DR-PR (4339DR) | 95925 | 0 | 0 | 0 | 0 | 95925 | 100% | 2020-03-24 11:38 | 2020-03-23 20:54 | 95925
102688 | 4213 | B - Emergency Protective Measures | Closeout - MEPA176-EST Electrical (LC) | 0 | 4339DR-PR (4339DR) | 679971 | 0 | 0 | 0 | 0 | 679971 | 100% | 2020-04-25 11:47 | 2020-04-24 12:46 | 679971
101681 | 4233 | B - Emergency Protective Measures | Closeout - MEPA175-FM TECHNOLOGY GROUP (LC) | 2 | 4339DR-PR (4339DR) | 543046.75 | 0 | 0 | 0 | 0 | 543046.75 | 100% | 2021-04-12 11:59 | 2024-04-02 20:34 | 543046.75
79755 | 2238 | B - Emergency Protective Measures | Closeout - MEPA172 - LC-Retirees | 1 | 4339DR-PR (4339DR) | 813452.02 | 0 | 0 | 0 | 0 | 813452.02 | 100% | 2019-12-23 12:41 | 2024-11-04 22:15 | 813452.02
126170 | 3775 | B - Emergency Protective Measures | CLOSEOUT - MEPA172 - LC - Retirees (90% Cost Share) | 0 | 4339DR-PR (4339DR) | 24927.5 | 0 | 0 | 2492.75 | 2492.75 | 22434.75 | 90% | 2020-04-03 11:20 | 2020-04-02 11:44 | 24927.5
79328 | 3056 | B - Emergency Protective Measures | CLOSEOUT - MEPA171 - Maral Engineer Corp (LC) | 0 | 4339DR-PR (4339DR) | 97336.01 | 0 | 0 | 0 | 0 | 97336.01 | 100% | 2020-03-09 12:00 | 2020-03-06 15:55 | 97336.01
79197 | 4047 | B - Emergency Protective Measures | CLOSEOUT - MEPA168- Perfect Integrated Solutions (LC) | 0 | 4339DR-PR (4339DR) | 69854.55 | 0 | 0 | 0 | 0 | 69854.55 | 100% | 2020-04-03 11:20 | 2020-04-02 11:44 | 69854.55
103768 | 5910 | B - Emergency Protective Measures | Closeout - MEPA167-C PRINCIPE ELECTRICAL (LC) | 1 | 4339DR-PR (4339DR) | 1400000 | 0 | 0 | 0 | 0 | 1400000 | 100% | 2021-04-26 11:39 | 2024-08-26 19:24 | 1400000
75794 | 1230 | B - Emergency Protective Measures | CLOSEOUT - MEPA165 - Manny Crane (LC) | 0 | 4339DR-PR (4339DR) | 47670 | 0 | 0 | 0 | 0 | 47670 | 100% | 2020-01-13 12:34 | 2020-01-10 21:19 | 47670
79441 | 1951 | B - Emergency Protective Measures | Closeout - MEPA164 -LC- Applied Engineering | 0 | 4339DR-PR (4339DR) | 450000 | 0 | 0 | 0 | 0 | 450000 | 100% | 2019-10-23 11:20 | 2019-10-22 11:12 | 450000
76963 | 3264 | B - Emergency Protective Measures | CLOSEOUT - MEPA163 - CRG Engineering Corp (LC) | 1 | 4339DR-PR (4339DR) | 200000 | 0 | 0 | 0 | 0 | 200000 | 100% | 2020-03-09 12:00 | 2024-04-02 20:30 | 200000
100272 | 2021 | B - Emergency Protective Measures | CLOSEOUT - MEPA162 - Galo Concrete LLC (LC) | 0 | 4339DR-PR (4339DR) | 9804 | 0 | 0 | 0 | 0 | 9804 | 100% | 2019-12-31 12:34 | 2019-12-30 18:46 | 9804
66982 | 1112 | B - Emergency Protective Measures | CLOSEOUT - MEPA160 - San Diego Gas & Electric (IMT) | 2 | 4339DR-PR (4339DR) | 124002.59 | 0 | 0 | 0 | 0 | 124002.59 | 100% | 2019-11-18 12:47 | 2025-04-10 20:15 | 124631.34
66981 | 1110 | B - Emergency Protective Measures | Closeout - MEPA159 - IMT - PW1110 Southern California Edison | 0 | 4339DR-PR (4339DR) | 2642414.21 | 0 | 0 | 0 | 0 | 2642414.21 | 100% | 2020-08-03 11:27 | 2020-07-31 12:29 | 2642414.21
66980 | 1105 | B - Emergency Protective Measures | CLOSEOUT - MEPA158 - Pacific Gas & Electric (IMT) | 1 | 4339DR-PR (4339DR) | 1202897.24 | 0 | 0 | 0 | 0 | 1202897.24 | 100% | 2019-09-06 18:36 | 2020-09-24 12:04 | 1202897.24
66978 | 1106 | B - Emergency Protective Measures | Closeout - MEPA156 Edison Electric Institute Incident | 4 | 4339DR-PR (4339DR) | 493768.51 | 0 | 0 | 0 | 0 | 493768.51 | 100% | 2019-09-06 18:34 | 2025-08-11 19:15 | 496388.8
66977 | 1111 | B - Emergency Protective Measures | CLOSEOUT - MEPA155 - SRP (IMT) | 1 | 4339DR-PR (4339DR) | 2172332.26 | 0 | 0 | 0 | 0 | 2172332.26 | 100% | 2019-09-06 18:33 | 2025-04-10 20:15 | 2304056
66976 | 1104 | B - Emergency Protective Measures | CLOSEOUT - MEPA154 - CPS Energy Incident Management team | 3 | 4339DR-PR (4339DR) | 361047.29 | 0 | 0 | 0 | 0 | 361047.29 | 100% | 2019-09-06 18:32 | 2025-05-13 16:16 | 492285
49849 | 508 | B - Emergency Protective Measures | CLOSEOUT - MEPA148 - Central Waste Services, Inc. (LC) for PW508 | 1 | 4339DR-PR (4339DR) | 652556.46 | 0 | 0 | 0 | 0 | 652556.46 | 100% | 2020-04-03 11:20 | 2024-11-04 22:15 | 868649.31
103234 | 3295 | B - Emergency Protective Measures | CLOSEOUT - MEPA133 - LJR (LC) | 0 | 4339DR-PR (4339DR) | 101383 | 0 | 0 | 0 | 0 | 101383 | 100% | 2020-04-08 11:27 | 2020-04-07 19:43 | 101383
49845 | 507 | B - Emergency Protective Measures | Closeout - MEPA131 - ECC (LC) | 1 | 4339DR-PR (4339DR) | 200000 | 0 | 0 | 0 | 0 | 200000 | 100% | 2021-03-04 12:29 | 2025-04-04 16:15 | 252448
49853 | 523 | B - Emergency Protective Measures | CLOSEOUT - MEPA130-CGR (LC) | 0 | 4339DR-PR (4339DR) | 66150 | 0 | 0 | 0 | 0 | 66150 | 100% | 2020-04-30 11:44 | 2020-04-29 11:29 | 66150
77866 | 3207 | B - Emergency Protective Measures | CLOSEOUT - MEPA129 - Caguas Real Utility Co. (LC) | 0 | 4339DR-PR (4339DR) | 47694 | 0 | 0 | 0 | 0 | 47694 | 100% | 2020-02-19 12:37 | 2020-02-14 13:29 | 47694
104897 | 3165 | B - Emergency Protective Measures | CLOSEOUT - MEPA127- Bonneville (LC) | 1 | 4339DR-PR (4339DR) | 400000 | 0 | 0 | 0 | 0 | 400000 | 100% | 2020-04-10 11:42 | 2024-04-02 20:19 | 400000
79188 | 2218 | B - Emergency Protective Measures | CLOSEOUT - MEPA126- Marcelo Electrical (LC) | 1 | 4339DR-PR (4339DR) | 200000 | 0 | 0 | 0 | 0 | 200000 | 100% | 2020-03-11 11:43 | 2024-08-26 19:23 | 200000
49851 | 520 | B - Emergency Protective Measures | CLOSEOUT - MEPA124-Beta Electric (LC) | 0 | 4339DR-PR (4339DR) | 102995.63 | 0 | 0 | 0 | 0 | 102995.63 | 100% | 2020-01-09 12:30 | 2020-01-08 12:04 | 102995.63
78916 | 3216 | B - Emergency Protective Measures | CLOSEOUT - MEPA123 - NAPS (LC) | 0 | 4339DR-PR (4339DR) | 70926.95 | 0 | 0 | 0 | 0 | 70926.95 | 100% | 2020-03-06 12:51 | 2020-03-05 21:50 | 70926.95
101679 | 3111 | B - Emergency Protective Measures | Closeout - MEPA122_BEST_WORK_CONSTRUCTION (LC) | 1 | 4339DR-PR (4339DR) | 200000 | 0 | 0 | 0 | 0 | 200000 | 100% | 2021-04-05 11:37 | 2024-04-03 18:55 | 200000
79401 | 5091 | B - Emergency Protective Measures | Closeout - MEPA120- Rolei Electrical (LC) | 0 | 4339DR-PR (4339DR) | 922400 | 0 | 0 | 0 | 0 | 922400 | 100% | 2020-06-08 11:24 | 2020-06-05 14:43 | 922400
79015 | 6330 | B - Emergency Protective Measures | Closeout - MEPA119- Reyes Electric (LC) | 1 | 4339DR-PR (4339DR) | 250000 | 0 | 0 | 0 | 0 | 250000 | 100% | 2021-04-28 11:38 | 2024-04-30 19:08 | 250000
79183 | 4316 | B - Emergency Protective Measures | CLOSEOUT - MEPA118-Design Build (LC) | 1 | 4339DR-PR (4339DR) | 200000 | 0 | 0 | 0 | 0 | 200000 | 100% | 2020-06-15 11:36 | 2023-11-20 21:55 | 200000
49829 | 448 | B - Emergency Protective Measures | CLOSEOUT - MEPA117 - Coca Cola (LC) | 0 | 4339DR-PR (4339DR) | 10241.2 | 0 | 0 | 0 | 0 | 10241.2 | 100% | 2019-09-04 14:31 | 2019-07-30 21:29 | 10241.2
79194 | 1976 | B - Emergency Protective Measures | Closeout - MEPA116- LORD Electric (LC) | 1 | 4339DR-PR (4339DR) | 790344.34 | 0 | 0 | 0 | 0 | 790344.34 | 100% | 2021-02-25 12:21 | 2025-08-12 15:16 | 790541.84
79320 | 2046 | B - Emergency Protective Measures | Closeout - MEPA112-LC- Kaisen | 0 | 4339DR-PR (4339DR) | 1021069.75 | 0 | 0 | 0 | 0 | 1021069.75 | 100% | 2020-04-25 11:47 | 2020-04-24 16:31 | 1021069.75
49827 | 442 | B - Emergency Protective Measures | CLOSEOUT - MEPA111-Berrios Electric (LC) | 1 | 4339DR-PR (4339DR) | 200000 | 0 | 0 | 0 | 0 | 200000 | 100% | 2020-01-15 13:11 | 2023-11-06 22:22 | 200000
49843 | 514 | B - Emergency Protective Measures | Closeout - MEPA110-WATER FACILITIES-GUAJATACA DAM PO AND CONTRACT(PW00514) | 4 | 4339DR-PR (4339DR) | 4112091.09 | 0 | 0 | 0 | 0 | 4112091.09 | 100% | 2018-07-27 | 2024-10-08 04:16 | 11248571.77
122571 | 7872 | B - Emergency Protective Measures | CLOSEOUT - MEPA109-Power Crane (LC) | 0 | 4339DR-PR (4339DR) | 34675 | 0 | 0 | 0 | 0 | 34675 | 100% | 2020-12-30 12:17 | 2020-12-29 18:53 | 34675
120613 | 5838 | B - Emergency Protective Measures | CLOSEOUT - MEPA102 - Green Planet Recycling Services (LC) | 0 | 4339DR-PR (4339DR) | 256104.8 | 0 | 0 | 25610.48 | 25610.48 | 230494.32 | 90% | 2021-07-20 11:22 | 2021-07-16 21:10 | 256104.8
49826 | 415 | B - Emergency Protective Measures | Closeout - MEPA063-J Candelaria (LC) | 2 | 4339DR-PR (4339DR) | 182067.5 | 0 | 0 | 0 | 0 | 182067.5 | 100% | 2018-06-01 | 2024-11-06 21:15 | 248005
101542 | 7907 | B - Emergency Protective Measures | CLOSEOUT - MEPA058 - All Contractors (LC) | 1 | 4339DR-PR (4339DR) | 662631 | 0 | 0 | 0 | 0 | 662631 | 100% | 2021-01-19 12:14 | 2021-07-16 21:09 | 662631
49825 | 385 | B - Emergency Protective Measures | CLOSEOUT - MEPA037 - Cidra Excavation Emergency Protective Measures (30) | 2 | 4339DR-PR (4339DR) | 90159 | 0 | 0 | 0 | 0 | 90159 | 100% | 2018-05-24 | 2020-03-10 12:01 | 90159
49818 | 329 | B - Emergency Protective Measures | Closeout - MEPA034 - MOU - PW329 (Muni) RICHMOND | 1 | 4339DR-PR (4339DR) | 452631.36 | 0 | 0 | 0 | 0 | 452631.37 | 100% | 2021-03-26 11:20 | 2021-03-25 21:21 | 452631.37
49816 | 318 | B - Emergency Protective Measures | CLOSEOUT - MEPA032 - MOU - PW318 (Muni) SMUD | 1 | 4339DR-PR (4339DR) | 4120942.35 | 0 | 0 | 0 | 0 | 4120942.35 | 100% | 2024-04-24 11:18 | 2024-04-23 20:52 | 4120942.35
49815 | 305 | B - Emergency Protective Measures | CLOSEOUT - MEPA031 - MOU - PW305 (IOU) WEC | 2 | 4339DR-PR (4339DR) | 10816310.05 | 0 | 0 | 0 | 0 | 10816310.05 | 100% | 2021-07-08 11:26 | 2025-09-15 20:15 | 10761861.26
49812 | 295 | B - Emergency Protective Measures | CLOSEOUT - MEPA028 - MOU - PW295 (IOU) SOUTHERN | 1 | 4339DR-PR (4339DR) | 28995396.07 | 0 | 0 | 0 | 0 | 28995396.07 | 100% | 2021-11-05 11:23 | 2021-11-04 16:08 | 28995396.07
49811 | 292 | B - Emergency Protective Measures | CLOSEOUT - MEPA027 - MOU - PW292 (IOU) PPL | 2 | 4339DR-PR (4339DR) | 6473398.1 | 0 | 0 | 0 | 0 | 6473398.1 | 100% | 2025-09-11 14:12 | 2025-05-30 17:16 | 4606377.75
49810 | 303 | B - Emergency Protective Measures | CLOSEOUT - MEPA026 - MOU - PW303 (IOU) ONCOR | 7 | 4339DR-PR (4339DR) | 13912849.67 | 0 | 0 | 0 | 0 | 13912849.67 | 100% | 2021-04-21 11:21 | 2026-01-27 16:16 | 13810966.32
49809 | 323 | B - Emergency Protective Measures | CLOSEOUT - MEPA025 - MOU - PW323 (IOU) OGE | 3 | 4339DR-PR (4339DR) | 13035734.27 | 0 | 0 | 0 | 0 | 13035734.27 | 100% | 2022-01-21 20:19 | 2025-06-04 18:15 | 12991499.84
49807 | 302 | B - Emergency Protective Measures | CLOSEOUT - MEPA023 - MOU - PW302 (IOU) FPL | 2 | 4339DR-PR (4339DR) | 44109931.52 | 0 | 0 | 0 | 0 | 44109931.52 | 100% | 2021-04-08 11:47 | 2021-04-07 17:59 | 44109931.52
49806 | 316 | B - Emergency Protective Measures | CLOSEOUT - MEPA022 - MOU - PW316 (IOU) EXELON | 2 | 4339DR-PR (4339DR) | 42876912.72 | 0 | 0 | 0 | 0 | 42876912.72 | 100% | 2021-08-19 11:29 | 2022-03-24 13:41 | 42876912.72
49802 | 296 | B - Emergency Protective Measures | CLOSEOUT - MEPA018 - MOU - PW296 (IOU) CENTERPOINT | 5 | 4339DR-PR (4339DR) | 13060696.42 | 0 | 0 | 0 | 0 | 13060696.42 | 100% | 2021-05-04 11:13 | 2025-08-29 18:15 | 12855447.34
49801 | 297 | B - Emergency Protective Measures | CLOSEOUT - MEPA017 - MOU - PW297 (IOU) APS | 2 | 4339DR-PR (4339DR) | 11245627.49 | 0 | 0 | 0 | 0 | 11245627.49 | 100% | 2021-04-08 11:47 | 2021-04-07 16:03 | 11245627.49
49800 | 291 | B - Emergency Protective Measures | CLOSEOUT - MEPA016 - MOU - PW291 (IOU) AMEREN | 2 | 4339DR-PR (4339DR) | 22655111.94 | 0 | 0 | 0 | 0 | 22655111.94 | 100% | 2021-05-14 11:32 | 2026-01-13 16:15 | 22563626.92
49799 | 293 | B - Emergency Protective Measures | CLOSEOUT - MEPA015 - MOU - PW293 (IOU) ALLETE | 1 | 4339DR-PR (4339DR) | 2603609.25 | 0 | 0 | 0 | 0 | 2603609.25 | 100% | 2025-08-12 15:16 | 2025-08-12 15:16 | 2603609.25
49798 | 290 | B - Emergency Protective Measures | Closeout - MEPA014 - MOU - PW290 (IOU) AEP | 1 | 4339DR-PR (4339DR) | 32123030 | 0 | 0 | 0 | 0 | 32123030 | 100% |  | 2018-09-07 11:35 | 17476450.2
98516 | 2252 | B - Emergency Protective Measures | Closeout - MEPA 174 - SM-Electrical Contractor (LC) | 0 | 4339DR-PR (4339DR) | 654322.5 | 0 | 0 | 0 | 0 | 654322.5 | 100% | 2020-04-25 11:47 | 2020-04-24 12:46 | 654322.5
79872 | 2167 | B - Emergency Protective Measures | CLOSEOUT - JVPR Mobility (LC) | 0 | 4339DR-PR (4339DR) | 27550 | 0 | 0 | 0 | 0 | 27550 | 100% | 2019-11-25 12:28 | 2019-11-22 21:48 | 27550
334509 | 10080 | F - Utilities | CLOSEOUT - FAASt [Palo Seco Demin Water Tank 4] (Generation) | 2 | 4339DR-PR (4339DR) | 2883352.33 | 0 | 0 | 288335.23 | 288335.23 | 2595017.1 | 90% | 2023-01-10 13:19 | 2025-09-05 21:15 | 2890937.33
663385 | 10455 | F - Utilities | CLOSEOUT - FAASt [Mayaguez Hydro-Gas Power Plant Permanent Repairs] (Generation) | 3 | 4339DR-PR (4339DR) | 21901105.4 | 0 | 0 | 2190110.54 | 2190110.54 | 19710994.86 | 90% | 2022-04-08 12:17 | 2025-10-31 15:15 | 22238212.58
145903 | 638 | B - Emergency Protective Measures | CLOSEOUT - Earthquake Force Account T&D | 1 | 4473DR-PR (4473DR) | 1402550.11 | 0 | 0 | 140255.01 | 140255.01 | 1262295.1 | 90% | 2022-02-18 12:21 | 2022-03-07 19:24 | 1402550.11
171513 | 615 | F - Utilities | Closeout - Costa Sur Work Completed | 3 | 4473DR-PR (4473DR) | 3394562.38 | 0 | 0 | 339456.23 | 339456.23 | 3055106.15 | 90% | 2022-05-13 11:31 | 2026-01-14 16:15 | 3444365.4
708414 | 763 | B - Emergency Protective Measures | Closeout - Central San Juan Emergency Repairs (90% cost share) (Generation) | 2 | 4671DR-PR (4671DR) | 1659870.19 | 0 | 0 | 165987.01 | 165987.01 | 1493883.18 | 90% | 2023-08-09 11:14 | 2025-07-22 20:15 | 5804753.78
49820 | 314 | B - Emergency Protective Measures | Closeout - 314E1 - EPM- Environics | 3 | 4339DR-PR (4339DR) | 200000 | 0 | 0 | 0 | 0 | 200000 | 100% | 2018-03-05 | 2025-08-12 15:16 | 490000
742728 | 4163 | B - Emergency Protective Measures | Centralize Region-Materials - Post LEOC - (May-June) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
742726 | 4162 | B - Emergency Protective Measures | Caguas Region-Materials - Post LEOC - (May-June) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064117 | 5023 | F - Utilities | Caguas Area J Dist. 2901-01, 2901-02, 2901-03, 2901-04, 2906-02 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064114 | 5020 | F - Utilities | Caguas Area I Dist. 2604-01, 2604-03, 2801-02, 2801-03 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064112 | 5018 | F - Utilities | Caguas Area I Dist. 2602-01, 2602-02, 2602-03, 2603-08, 2603-09 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064089 | 5007 | F - Utilities | Caguas Area I Dist. 2601-01, 2601-02, 2601-03, 2601-04 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
751513 | 4816 | F - Utilities | Caguas Area I - Yabucoa TC (Candelero) 2604(Substation) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
1064088 | 5006 | F - Utilities | Caguas Area H Dist. 2605-01, 2605-02, 2702-01, 2701-03 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064087 | 5005 | F - Utilities | Caguas Area G Dist. 3301-01, 3301-02, 3302-02, 3302-03, 3302-04 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064086 | 5004 | F - Utilities | Caguas Area G Dist. 3205-07, 3205-08, 3205-09 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064085 | 5003 | F - Utilities | Caguas Area G Dist. 3101-02, 3101-04, 3102-01, 3201-02, 3201-04 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
751491 | 4807 | F - Utilities | Caguas Area F- Veredas PDS 3103(Substation) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
1064083 | 5001 | F - Utilities | Caguas Area F Dist. 3015-05, 3015-06, 3103-01, 3103-02, 3103-04, 3103-05 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064028 | 4972 | F - Utilities | Caguas Area F Dist. 3013-01, 3013-02 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064027 | 4971 | F - Utilities | Caguas Area F Dist. 3005-02, 3007-03, 3007-04 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
817156 | 4892 | F - Utilities | Caguas Area E-Caguas TC 3006 (Substation) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064024 | 4968 | F - Utilities | Caguas Area E Dist. 3014-01, 3014-02, 3014-04 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064020 | 4965 | F - Utilities | Caguas Area E Dist. 3006-02, 3006-05 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064023 | 4967 | F - Utilities | Caguas Area E Dist. 3004-01, 3004-03, 3008-03, 3008-04, 3009-04 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
751423 | 4777 | F - Utilities | Caguas Area D- Aguas Buenas(Substation) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
751422 | 4776 | F - Utilities | Caguas Area D- Aguas Buenas 3701(Substation) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
1064018 | 4963 | F - Utilities | Caguas Area D Dist. 3701-02, 3701-03, 3701-04 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064019 | 4964 | F - Utilities | Caguas Area D Dist. 3010-01, 3010-04, 3016-03, 3604-06, 3604-07 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064016 | 4961 | F - Utilities | Caguas Area C Dist. 3406-01, 3406-02, 3406-03 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064014 | 4960 | F - Utilities | Caguas Area C Dist. 3405-01, 3405-02, 3405-03 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064017 | 4962 | F - Utilities | Caguas Area C Dist. 3401-01, 3401-02, 3401-03, 3403-01, 3402-05 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064012 | 4959 | F - Utilities | Caguas Area B Dist. 9703-01, 9703-02, 9703-03 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064010 | 4958 | F - Utilities | Caguas Area B Dist. 3601-01, 3601-02, 3601-04, 3602-01, 3602-02, 3602-03 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064009 | 4957 | F - Utilities | Caguas Area B Dist. 3502-01, 3502-02 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064007 | 4956 | F - Utilities | Caguas Area B Dist. 3501-01, 3501-02, 3501-03 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1063999 | 4955 | F - Utilities | Caguas Area A Dist. 9902-01, 9902-02, 9902-03 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1063998 | 4954 | F - Utilities | Caguas Area A Dist. 9605-01, 9605-02, 9901-01, 9901-02 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1063996 | 4953 | F - Utilities | Caguas Area A Dist. 9602-03, 9602-04 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1063993 | 4952 | F - Utilities | Caguas Area A Dist. 9601-01, 9601-02 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
742725 | 4161 | B - Emergency Protective Measures | Bayamon Region-Materials - Post LEOC - (May-June) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
743616 | 4184 | B - Emergency Protective Measures | Bayamon Materials POST LEOC (July-Sept) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064206 | 5073 | F - Utilities | Bayamon Area I Dist. 1713-03 - 1713-05 - 1718-03 - 9203-02 - 9203-03 - 9203-04 - 9207-08 - 9401-01 - 9401-02 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
751485 | 4803 | F - Utilities | Bayamon Area H- Vega Alta Pueblo 9101 & Vega Alta 13Kv 9105(Substation) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
1064198 | 5068 | F - Utilities | Bayamon Area H Dist. 9202-04 - 9206-10 - 9101-01 - 9101-03 - 9101-04 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
751380 | 4755 | F - Utilities | Bayamon Area H Dist. 9103-01 - 9103-04 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064194 | 5065 | F - Utilities | Bayamon Area G Dist. 9801-01 - 9801-03 - 9802-04 - 9503-06 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064237 | 5077 | F - Utilities | Bayamon Area G Dist. 9502-01 - 9502-02 - 9502-03 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064234 | 5076 | F - Utilities | Bayamon Area G Dist. 9501-01 - 9501-02 - 9501-03 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
751805 | 4851 | F - Utilities | Bayamon Area G 9801(Substation) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
751775 | 4850 | F - Utilities | Bayamon Area G - Monterrey - 9502(Substation) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
1064233 | 5075 | F - Utilities | Bayamon Area F Dist. 9403-01 - 9403-03 - 9405-05 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064232 | 5074 | F - Utilities | Bayamon Area F Dist. 1719-15 - 1719-19 - 1734-01 - 1734-02 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064181 | 5060 | F - Utilities | Bayamon Area F Dist. 1710-01 - 1710-03 - 1710-05 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
751383 | 4756 | F - Utilities | Bayamon Area E-H Dist. 1706-03 - 1707-01 - 1707-03 - 9105-06 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064156 | 5050 | F - Utilities | Bayamon Area E Dist.1703-01 - 1703-04 - 1704-01 - 1704-03 - 1704-04 - 1704-05 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064107 | 5017 | F - Utilities | Bayamon Area E Dist. 1705-02 - 1705-03 - 1705-05 - 1717-01 - 1717-03 - 1717-04 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064127 | 5032 | F - Utilities | Bayamon Area D Dist. 1708-02 - 1708-03 - 1708-04 - 1708-05 - 1711-01 - 1711-02 - 1711-04 - 1711-05 - 1714-02 - 1716-03 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064122 | 5028 | F - Utilities | Bayamon Area C Dist. 1801-01 - 1801-03 - 1801-05 - 1803-05 - 1806-02 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064119 | 5025 | F - Utilities | Bayamon Area B Dist. 1709-02 - 1709-03 - 1720-07 - 1903-05 - 1924-01 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064113 | 5019 | F - Utilities | Bayamon Area A Dist. 1343-01 - 1343-05 - 1901-01 - 1901-04 - 1901-05 - 1907-04 - 1908-03 - 1908-05 - 1909-07 - 1909-08 - 1909-09 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
742724 | 4160 | B - Emergency Protective Measures | Arecibo Region-Materials - Post LEOC - (May-June) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
743604 | 4183 | B - Emergency Protective Measures | Arecibo Materials POST LEOC (July-Sept) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064132 | 5036 | F - Utilities | Arecibo Area H Dist. 9003-05 - 9003-06 - 9004-08 - 9004-10 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064133 | 5037 | F - Utilities | Arecibo Area H Dist. 9001-01 - 9001-02 - 9002-01 - 9002-03 - 9201-02 - 1718-02 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
751521 | 4821 | F - Utilities | Arecibo Area G- Jayuya 8301 & Jayuya 8302(Substation) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
1064128 | 5033 | F - Utilities | Arecibo Area G Dist. 8203-01 - 8203-02 - 8602-01 - 8602-03 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064125 | 5030 | F - Utilities | Arecibo Area G Dist. 8202-01 - 8202-02 - 8202-03 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064130 | 5035 | F - Utilities | Arecibo Area G Dist. 8103-01 - 8103-02 - 8104-01 - 8104-02 - 8104-05 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064129 | 5034 | F - Utilities | Arecibo Area G Dist. 8101-01 - 8101-02 - 8101-03 - 8101-04 - 8101-05 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064126 | 5031 | E - Buildings and Equipment | Arecibo Area G Dist. 8005-01 - 8301-01 - 8301-03 - 8302-04 - 8302-05 ( Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064047 | 4987 | F - Utilities | Arecibo Area F Dist. 8701-01 - 8701-03 - 8701-04 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064124 | 5029 | F - Utilities | Arecibo Area F Dist. 8405-01 - 8405-02 - 8405-03 - 8405-04 - 8801-01 - 8801-02 - 8801-04 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064050 | 4989 | F - Utilities | Arecibo Area F Dist. 8401-02 - 8404-02 - 8404-03 - 8404-04 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064044 | 4986 | F - Utilities | Arecibo Area D Dist. 8015-08 - 8011-01 - 8011-02 - 8501-02 - 8014-08 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064034 | 4977 | F - Utilities | Arecibo Area D Dist. 8004-01 - 8004-02 - 8004-03 - 8004-04 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064032 | 4975 | F - Utilities | Arecibo Area C-D Dist. 7702-02 - 7702-03 - 8002-03 - 8015-09 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064025 | 4969 | F - Utilities | Arecibo Area C-8010-01 - 8010-02 - 8010-03 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064030 | 4973 | F - Utilities | Arecibo Area C Dist. 8007-03 - 8013-01 - 8013-02 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
751811 | 4856 | F - Utilities | Arecibo Area B- Quebradillas 7402(Substation) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
1064021 | 4966 | F - Utilities | Arecibo Area B - 7701-01, 7701-02, 7701-03, 7701-04 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064120 | 5026 | F - Utilities | Arecibo Area B - 7601-01, 7601-03, 7601-04, 7601-04, 7602-05 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
1064118 | 5024 | F - Utilities | Arecibo Area B - 7404-06, 7402-01, 7402-02, 7402-05 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
746369 | 2582 | B - Emergency Protective Measures | App. Cert. LUMA - Emergency Protective Measure - Distribution Line 9101-01 (90% cost share) | 0 | 4671DR-PR (4671DR) | 176484.7 | 0 | 0 | 17648.47 | 17648.47 | 158836.23 | 90% | 2025-06-11 18:15 | 2025-06-11 18:15 | 0
745657 | 2557 | B - Emergency Protective Measures | App. Cert. - LUMA - Emergency Protective Measure - Distribution Line 9101-01 (100% cost share) | 0 | 4671DR-PR (4671DR) | 866595.59 | 0 | 0 | 0 | 0 | 866595.59 | 100% | 2024-07-02 11:15 | 2024-07-01 18:32 | 866595.59
710541 | 355 | B - Emergency Protective Measures | App. Cert. - Force account San Juan Power Plant (Generation) | 0 | 4671DR-PR (4671DR) | 125333.29 | 0 | 0 | 0 | 0 | 125333.29 | 100% | 2023-05-02 11:34 | 2023-05-01 13:10 | 125333.29
710544 | 342 | B - Emergency Protective Measures | App. Cert. - Force account Palo Seco and Costa Sur Power Plant (Generation) | 0 | 4671DR-PR (4671DR) | 377031.86 | 0 | 0 | 0 | 0 | 377031.86 | 100% | 2023-05-02 11:34 | 2023-05-01 21:25 | 377031.86
728994 | 1476 | B - Emergency Protective Measures | App. Cert. - Force account HydroGas and Irrigation (90%) (Generation/Riego) | 0 | 4671DR-PR (4671DR) | 27166.31 | 0 | 0 | 2716.63 | 2716.63 | 24449.68 | 90% | 2023-10-05 11:30 | 2023-10-04 19:09 | 27166.31
728993 | 1362 | B - Emergency Protective Measures | App. Cert. - Force account HydroGas and Irrigation (100%) (Generation/Riego) | 0 | 4671DR-PR (4671DR) | 796733.44 | 0 | 0 | 0 | 0 | 796733.44 | 100% | 2023-10-19 11:41 | 2023-10-18 13:06 | 796733.44
738607 | 1945 | B - Emergency Protective Measures | APP CERT- PREPA- Emergency Work Central Aguirre (FAL & Materials) | 0 | 4671DR-PR (4671DR) | 956487.99 | 0 | 0 | 0 | 0 | 956487.99 | 100% | 2023-12-28 12:20 | 2023-12-27 19:25 | 956487.99
738398 | 1913 | B - Emergency Protective Measures | APP CERT- PREPA- Emergency Work Central Aguirre (Cost Share 100%) | 0 | 4671DR-PR (4671DR) | 190306.86 | 0 | 0 | 0 | 0 | 190306.86 | 100% | 2023-12-28 12:20 | 2023-12-27 20:35 | 190306.86
741860 | 2138 | B - Emergency Protective Measures | APP CERT- PREPA Hydro-Gas Divisions Contracts & Materials 90% | 0 | 4671DR-PR (4671DR) | 322502.11 | 0 | 0 | 32250.21 | 32250.21 | 290251.9 | 90% | 2024-01-23 12:31 | 2024-01-22 20:34 | 322502.11
741720 | 2152 | B - Emergency Protective Measures | APP CERT- PREPA Hydro-Gas Divisions Contracts & Materials 100% | 0 | 4671DR-PR (4671DR) | 33376.76 | 0 | 0 | 0 | 0 | 33376.76 | 100% | 2024-02-06 12:37 | 2024-02-05 19:28 | 33376.76
739464 | 1978 | B - Emergency Protective Measures | APP CERT- PREPA Emergency Work Central Aguirre (Cost Share 90%) | 0 | 4671DR-PR (4671DR) | 198134.85 | 0 | 0 | 19813.48 | 19813.48 | 178321.37 | 90% | 2023-12-28 12:20 | 2023-12-27 20:35 | 198134.85
724166 | 989 | B - Emergency Protective Measures | APP CERT - Force Account Emergency Operations Center (EOC) (Generation) | 0 | 4671DR-PR (4671DR) | 49503.47 | 0 | 0 | 0 | 0 | 49503.47 | 100% | 2023-08-09 11:14 | 2023-08-08 20:49 | 49503.47
724415 | 4044 | B - Emergency Protective Measures | Aguirre Power Plant (90%) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
702010 | 350 | B - Emergency Protective Measures | Aguirre Ciclo Combinado (Generation) | 0 | 4671DR-PR (4671DR) | 20863.64 | 0 | 0 | 0 | 0 | 20863.64 | 100% | 2023-05-11 10:55 | 2023-05-10 20:25 | 20863.64
49796 | 75 | B - Emergency Protective Measures | AEE001B EMERGENCY PROTECTIVE MEASURE | 4 | 4339DR-PR (4339DR) | 140271030.52 | 0 | 0 | 0 | 0 | 140271030.52 | 100% | 2017-10-10 | 2025-09-17 18:16 | 137654858.49
721324 | 3995 | Z - Management Costs | Actual Management Costs | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 100% |  |  | 0
694014 | 2923 | B - Emergency Protective Measures | 4671DR-PR-FIONA | 0 | 4671DR-PR (4671DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
741880 | 4157 | B - Emergency Protective Measures | 4671DR-PR PR Electric Power Authority (000-UA2QU-00)- Lodging Regional Approach Period 1 POST LEOC - composed of six (6) regions - Arecibo, Bayamón, Caguas, Mayaguez, Ponce & San Juan (90% Cost Share) | 0 | 4671DR-PR (4671DR) | 6010775.25 | 0 | 0 | 601077.52 | 601077.52 | 5409697.73 | 90% | 2026-02-27 14:17 | 2026-02-27 14:17 | 0
741879 | 4156 | B - Emergency Protective Measures | 4671DR-PR PR Electric Power Authority (000-UA2QU-00)- Lodging Regional Approach Period 1 LEOC - composed of six (6) regions - Arecibo, Bayamón, Caguas, Mayaguez, Ponce & San Juan (100% Cost Share) | 0 | 4671DR-PR (4671DR) | 251447.63 | 0 | 0 | 0 | 0 | 251447.63 | 100% | 2026-02-25 22:16 | 2026-02-25 22:16 | 0
49797 | 251 | B - Emergency Protective Measures | 251E-AEE002-TRANSMISSION-COBRA CONTRACT | 4 | 4339DR-PR (4339DR) | 923373121.77 | 0 | 0 | 0 | 0 | 923373121.77 | 100% | 2017-12-29 | 2023-03-28 15:32 | 923373121.77
958850 | 407 | F - Utilities | [W] DR4850 - PREPA_Cat F - Yabucoa, Añasco Municipalities - Distribution (75% Cost Share) | 0 | 4850DR-PR (4850DR) | 0 |  | 0 | 0 | 0 | 0 | 75% |  |  | 0
958861 | 414 | F - Utilities | [W] DR4850 - PREPA_Cat F - Villalba Municipality - T&D (75% Cost Share) | 0 | 4850DR-PR (4850DR) | 0 |  | 0 | 0 | 0 | 0 | 75% |  |  | 0
958840 | 400 | F - Utilities | [W] DR4850 - PREPA_Cat F - Utuado Municipality - Distribution (75% Cost Share) | 0 | 4850DR-PR (4850DR) | 0 |  | 0 | 0 | 0 | 0 | 75% |  |  | 0
958847 | 406 | F - Utilities | [W] DR4850 - PREPA_Cat F - San Lorenzo Municipality - Distribution (75% Cost Share) | 0 | 4850DR-PR (4850DR) | 0 |  | 0 | 0 | 0 | 0 | 75% |  |  | 0
958855 | 410 | F - Utilities | [W] DR4850 - PREPA_Cat F - San German, Hormigueros, Las Marias Municipalities - T&D (75% Cost Share) | 0 | 4850DR-PR (4850DR) | 0 |  | 0 | 0 | 0 | 0 | 75% |  |  | 0
958883 | 421 | F - Utilities | [W] DR4850 - PREPA_Cat F - Ponce Municipality - Distribution - Group 3 (75% Cost Share) | 0 | 4850DR-PR (4850DR) | 0 |  | 0 | 0 | 0 | 0 | 75% |  |  | 0
958868 | 420 | F - Utilities | [W] DR4850 - PREPA_Cat F - Ponce Municipality - Distribution - Group 2 (5011/5012/5013/5018/5021/5805) (75% Cost Share) | 0 | 4850DR-PR (4850DR) | 0 |  | 0 | 0 | 0 | 0 | 75% |  |  | 0
958846 | 405 | F - Utilities | [W] DR4850 - PREPA_Cat F - Orocovis, Comerio Municipalities - Distribution (75% Cost Share) | 0 | 4850DR-PR (4850DR) | 0 |  | 0 | 0 | 0 | 0 | 75% |  |  | 0
958844 | 404 | F - Utilities | [W] DR4850 - PREPA_Cat F - Naguabo Municipality - T&D (75% Cost Share) | 0 | 4850DR-PR (4850DR) | 0 |  | 0 | 0 | 0 | 0 | 75% |  |  | 0
958858 | 411 | F - Utilities | [W] DR4850 - PREPA_Cat F - Mayaguez, San Sebastian Municipalities - Distribution (75% Cost Share) | 0 | 4850DR-PR (4850DR) | 0 |  | 0 | 0 | 0 | 0 | 75% |  |  | 0
958859 | 412 | F - Utilities | [W] DR4850 - PREPA_Cat F - Maricao Municipality - Distribution (75% Cost Share) | 0 | 4850DR-PR (4850DR) | 0 |  | 0 | 0 | 0 | 0 | 75% |  |  | 0
958864 | 417 | F - Utilities | [W] DR4850 - PREPA_Cat F - Luquillo Municipality T&D (75% Cost Share) | 0 | 4850DR-PR (4850DR) | 0 |  | 0 | 0 | 0 | 0 | 75% |  |  | 0
958854 | 409 | F - Utilities | [W] DR4850 - PREPA_Cat F - Lares Municipality - Distribution (75% Cost Share) | 0 | 4850DR-PR (4850DR) | 0 |  | 0 | 0 | 0 | 0 | 75% |  |  | 0
958802 | 398 | F - Utilities | [W] DR4850 - PREPA_Cat F - Jayuya Municipality - T&D (75% Cost Share) | 0 | 4850DR-PR (4850DR) | 0 |  | 0 | 0 | 0 | 0 | 75% |  |  | 0
958866 | 418 | F - Utilities | [W] DR4850 - PREPA_Cat F - Fajardo Municipality - T&D (75% Cost Share) | 0 | 4850DR-PR (4850DR) | 0 |  | 0 | 0 | 0 | 0 | 75% |  |  | 0
958841 | 401 | F - Utilities | [W] DR4850 - PREPA_Cat F - Corozal Municipality - Distribution (75% Cost Share) | 0 | 4850DR-PR (4850DR) | 0 |  | 0 | 0 | 0 | 0 | 75% |  |  | 0
958860 | 413 | F - Utilities | [W] DR4850 - PREPA_Cat F - Coamo, Arroyo, Maunabo, Santa Isabel Municipalities - Distribution (75% Cost Share) | 0 | 4850DR-PR (4850DR) | 0 |  | 0 | 0 | 0 | 0 | 75% |  |  | 0
958549 | 396 | F - Utilities | [W] DR4850 - PREPA_Cat F - Canovanas, Vieques, Loiza Municipalities - T&D (75% Cost Share) | 0 | 4850DR-PR (4850DR) | 0 |  | 0 | 0 | 0 | 0 | 75% |  |  | 0
958852 | 408 | F - Utilities | [W] DR4850 - PREPA_Cat F - Cabo Rojo Municipality - Distribution (75% Cost Share) | 0 | 4850DR-PR (4850DR) | 0 |  | 0 | 0 | 0 | 0 | 75% |  |  | 0
958843 | 403 | F - Utilities | [W] DR4850 - PREPA_Cat F - Aibonito, Barranquitas Municipalities - Distribution (75% Cost Share) | 0 | 4850DR-PR (4850DR) | 0 |  | 0 | 0 | 0 | 0 | 75% |  |  | 0
958842 | 402 | F - Utilities | [W] DR4850 - PREPA_Cat F - Aguas Buenas, Las Piedras Municipalities - T&D (75% Cost Share) | 0 | 4850DR-PR (4850DR) | 0 |  | 0 | 0 | 0 | 0 | 75% |  |  | 0
958803 | 399 | F - Utilities | [W] DR4850 - PREPA_Cat F - Adjuntas, Camuy, Manati, Vega Alta Municipalities - Distribution (75% Cost Share) | 0 | 4850DR-PR (4850DR) | 0 |  | 0 | 0 | 0 | 0 | 75% |  |  | 0
958867 | 419 | F - Utilities | [W] DR4850 - PREPA_ Cat F - Ponce Municipality Distribution - Group 1 (5001/5002/5003/5004/5005/5007/5008) (75% Cost Share) | 0 | 4850DR-PR (4850DR) | 0 |  | 0 | 0 | 0 | 0 | 75% |  |  | 0
814562 | 74 | B - Emergency Protective Measures | [W] DR4850 - PREPA _SPA Cat B - Jayuya Municipality - Transmission (75% Cost Share) | 0 | 4850DR-PR (4850DR) | 0 |  | 0 | 0 | 0 | 0 | 75% |  |  | 0
958863 | 416 | F - Utilities | [W] DR4850 - PREPA _Cat F - Rio Grande Municipality - T&D (75% Cost Share) | 0 | 4850DR-PR (4850DR) | 0 |  | 0 | 0 | 0 | 0 | 75% |  |  | 0
958862 | 415 | F - Utilities | [W] DR4850 - PREPA _Cat F - Ceiba Municipality - T&D (75% Cost Share) | 0 | 4850DR-PR (4850DR) | 0 |  | 0 | 0 | 0 | 0 | 75% |  |  | 0
136441 | 4 | B - Emergency Protective Measures | **Project CLOSED** PREPA Emegency Protective Measures COVID-19 | 4 | 4493DR-PR (4493DR) | 3181984.68 | 0 | 0 | 0 | 0 | 3181984.68 | 100% | 2020-05-26 11:24 | 2025-05-22 15:16 | 3605724.1
481859 | 99 | F - Utilities | (PW# 99) AEPON-09 Public Utilities | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
481857 | 98 | B - Emergency Protective Measures | (PW# 98) AETBA-05 Protective Measures | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
480162 | 978 | D - Water Control Facilities | (PW# 978) Water Facilities PREPA-07 | 1 | 1798DR-PR (1798DR) | 349149 | 16392.76 | 0 | 87287.25 | 87287.25 | 261861.75 | 75% |  | 2014-10-28 18:32 | 349149
974966 | 976 | F - Utilities | (PW# 976) AEE039 Utilities | 0 | 1946DR-PR (1946DR) | 1211.1 | 0 | 0 | 302.77 | 302.77 | 908.33 | 75% | 2011-07-21 14:05 | 2011-07-25 19:42 | 0
477950 | 973 | F - Utilities | (PW# 973) PUBLIC UTILITIES | 0 | 1552DR-PR (1552DR) | 99208.84 | 0 | 0 | 24802.21 | 24802.21 | 74406.63 | 75% |  | 2005-02-03 14:19 | 0
974965 | 971 | F - Utilities | (PW# 971) AEE041 Utilities | 0 | 1946DR-PR (1946DR) | 1444.53 | 0 | 0 | 361.13 | 361.13 | 1083.4 | 75% | 2011-07-21 14:05 | 2011-07-25 19:42 | 0
477949 | 970 | B - Emergency Protective Measures | (PW# 970) EMERGENCY PROTECTIVE MEASURES | 1 | 1552DR-PR (1552DR) | 1225870.65 | 0 | 0 | 306467.66 | 306467.66 | 919402.99 | 75% |  | 2013-04-22 15:26 | 0
974964 | 970 | F - Utilities | (PW# 970) AEE042 Utilities | 0 | 1946DR-PR (1946DR) | 1577.98 | 0 | 0 | 394.49 | 394.49 | 1183.49 | 75% | 2011-07-21 14:05 | 2011-07-25 19:42 | 0
481858 | 97 | F - Utilities | (PW# 97) AEGNC-03 Public Utilities | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
477948 | 969 | B - Emergency Protective Measures | (PW# 969) EMERGENCY PROTECTIVE MEASURES | 1 | 1552DR-PR (1552DR) | 2610537.84 | 0 | 0 | 0 | 0 | 2610537.84 | 100% |  | 2013-04-22 15:26 | 0
481853 | 96 | B - Emergency Protective Measures | (PW# 96) AEDOR-05 Public Utilities | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
974963 | 950 | F - Utilities | (PW# 950) AEE040 Utilities | 0 | 1946DR-PR (1946DR) | 4139.35 | 0 | 0 | 1034.84 | 1034.84 | 3104.51 | 75% | 2011-07-21 14:05 | 2011-07-25 19:42 | 0
481856 | 95 | B - Emergency Protective Measures | (PW# 95) AEPON04 Protective Measures | 0 | 3326EM-PR (3326EM) | 4294.44 | 0 | 0 | 1073.61 | 1073.61 | 3220.83 | 75% |  | 2012-03-22 11:45 | 4294.44
974962 | 949 | F - Utilities | (PW# 949) AEE043 Utilities | 0 | 1946DR-PR (1946DR) | 1736.46 | 0 | 0 | 434.11 | 434.11 | 1302.35 | 75% | 2011-08-09 14:10 | 2011-10-12 11:50 | 0
974961 | 948 | A - Debris Removal | (PW# 948) AEE052 Debris Removal | 0 | 1946DR-PR (1946DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
481852 | 94 | F - Utilities | (PW# 94) AEGYL-06 Public Utilities | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
994302 | 934 | B - Emergency Protective Measures | (PW# 934) A-AE-CAN01 Protective Measures | 0 | 4017DR-PR (4017DR) | 1791.89 | 0 | 0 | 447.97 | 447.97 | 1343.92 | 75% | 2011-12-06 00:01 | 2011-12-09 21:15 | 0
974960 | 933 | F - Utilities | (PW# 933) AEE030 Utilities | 0 | 1946DR-PR (1946DR) | 1323.57 | 0 | 0 | 330.89 | 330.89 | 992.68 | 75% | 2011-07-21 14:05 | 2011-07-25 19:42 | 0
974959 | 932 | F - Utilities | (PW# 932) AEE031 Utilities | 0 | 1946DR-PR (1946DR) | 1988.63 | 0 | 0 | 497.16 | 497.16 | 1491.47 | 75% | 2011-07-21 14:05 | 2011-07-25 19:42 | 0
974958 | 931 | F - Utilities | (PW# 931) AEE032 Utilities | 0 | 1946DR-PR (1946DR) | 1260 | 0 | 0 | 315 | 315 | 945 | 75% | 2011-07-21 14:05 | 2011-07-25 19:42 | 0
974957 | 930 | A - Debris Removal | (PW# 930) AEE038 Debris Removal | 0 | 1946DR-PR (1946DR) | 1786.4 | 0 | 0 | 446.6 | 446.6 | 1339.8 | 75% | 2011-07-21 14:05 | 2011-07-25 19:42 | 0
481855 | 93 | B - Emergency Protective Measures | (PW# 93) AEPON-03 Protective Measures | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
481854 | 92 | B - Emergency Protective Measures | (PW# 92) AEDOR-06 Protective Measures | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
481846 | 91 | B - Emergency Protective Measures | (PW# 91) AEPON10 Protective Measures | 0 | 3326EM-PR (3326EM) | 7492.04 | 0 | 0 | 1873.01 | 1873.01 | 5619.03 | 75% |  | 2012-03-22 11:45 | 7492.04
481850 | 90 | B - Emergency Protective Measures | (PW# 90) AEAGL-02 Protective Measures | 0 | 3326EM-PR (3326EM) | 8238.31 | 0 | 0 | 2059.58 | 2059.58 | 6178.73 | 75% |  | 2012-03-22 11:45 | 8238.31
481851 | 89 | B - Emergency Protective Measures | (PW# 89) AEHAT-03 Protective Measures | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
974956 | 884 | F - Utilities | (PW# 884) AEE029 Utilities | 0 | 1946DR-PR (1946DR) | 3310.45 | 0 | 0 | 827.61 | 827.61 | 2482.84 | 75% | 2011-06-09 12:40 | 2011-06-09 12:44 | 0
481849 | 88 | B - Emergency Protective Measures | (PW# 88) AESSE-03 Protective Measures | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
974955 | 875 | A - Debris Removal | (PW# 875) AEE028 Debris Removal | 0 | 1946DR-PR (1946DR) | 1146.91 | 0 | 0 | 286.73 | 286.73 | 860.18 | 75% | 2011-06-09 12:40 | 2011-06-09 12:44 | 0
974954 | 874 | A - Debris Removal | (PW# 874) AEE027 Debris Removal | 0 | 1946DR-PR (1946DR) | 3015.53 | 0 | 0 | 753.88 | 753.88 | 2261.65 | 75% | 2011-06-09 12:40 | 2011-06-09 12:44 | 0
974953 | 873 | A - Debris Removal | (PW# 873) AEE026 Debris Removal | 0 | 1946DR-PR (1946DR) | 4044 | 0 | 0 | 1011 | 1011 | 3033 | 75% | 2011-06-09 12:40 | 2011-06-09 12:44 | 0
974952 | 872 | F - Utilities | (PW# 872) AEE025 Utilities | 0 | 1946DR-PR (1946DR) | 1759.07 | 0 | 0 | 439.77 | 439.77 | 1319.3 | 75% | 2011-06-09 12:40 | 2011-06-09 12:44 | 0
974951 | 871 | F - Utilities | (PW# 871) AEE024 Utilities | 0 | 1946DR-PR (1946DR) | 2087.82 | 0 | 0 | 521.95 | 521.95 | 1565.87 | 75% | 2011-06-09 12:40 | 2011-06-09 12:44 | 0
974950 | 870 | F - Utilities | (PW# 870) AEE019 Utilities | 0 | 1946DR-PR (1946DR) | 3219.32 | 0 | 0 | 804.83 | 804.83 | 2414.49 | 75% | 2011-06-09 12:40 | 2011-06-09 12:44 | 0
481848 | 87 | F - Utilities | (PW# 87) AEHAT-04 Public Utilities | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
974949 | 869 | F - Utilities | (PW# 869) AEE017 Utilities | 0 | 1946DR-PR (1946DR) | 8867.41 | 0 | 0 | 2216.85 | 2216.85 | 6650.56 | 75% | 2011-06-09 12:40 | 2011-06-09 12:44 | 0
974948 | 867 | F - Utilities | (PW# 867) AEE020 Utilities | 0 | 1946DR-PR (1946DR) | 1215.34 | 0 | 0 | 303.83 | 303.83 | 911.51 | 75% | 2011-06-09 12:40 | 2011-06-09 12:44 | 0
974947 | 866 | F - Utilities | (PW# 866) AEE023 Utlities | 0 | 1946DR-PR (1946DR) | 6642.75 | 0 | 0 | 1660.69 | 1660.69 | 4982.06 | 75% | 2011-06-09 12:40 | 2011-06-09 12:44 | 0
974946 | 865 | F - Utilities | (PW# 865) AEE 018 Utilities | 0 | 1946DR-PR (1946DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
481847 | 86 | F - Utilities | (PW# 86) AETBA-02 Public Utilities | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
481844 | 85 | F - Utilities | (PW# 85) AEDOR-03 Public Utilities | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
481845 | 84 | F - Utilities | (PW# 84) AETBA-03 Public Utilities | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
481836 | 82 | F - Utilities | (PW# 82) AEDOR02 Public Utilities | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
974945 | 817 | F - Utilities | (PW# 817) AEE014 Utilities | 0 | 1946DR-PR (1946DR) | 5969.32 | 0 | 0 | 1492.33 | 1492.33 | 4476.99 | 75% | 2011-05-04 19:49 | 2011-05-05 12:19 | 0
481840 | 81 | B - Emergency Protective Measures | (PW# 81) AEDOR-04 Protective Measures | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
974944 | 809 | F - Utilities | (PW# 809) AEE016 Utilities | 0 | 1946DR-PR (1946DR) | 4103.39 | 0 | 0 | 1025.85 | 1025.85 | 3077.54 | 75% | 2011-05-04 19:49 | 2011-05-05 12:19 | 0
974943 | 800 | F - Utilities | (PW# 800) AEE012 Utilities | 0 | 1946DR-PR (1946DR) | 6889.19 | 0 | 0 | 1722.3 | 1722.3 | 5166.89 | 75% | 2011-05-04 19:49 | 2011-05-05 12:19 | 0
481843 | 80 | B - Emergency Protective Measures | (PW# 80) AEAG-L03 Protective Measures | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
481798 | 8 | B - Emergency Protective Measures | (PW# 8) AEVAL-04 Protective Measures | 0 | 3326EM-PR (3326EM) | 5265.22 | 0 | 0 | 1316.3 | 1316.3 | 3948.92 | 75% |  | 2012-03-22 11:45 | 5265.22
974942 | 799 | A - Debris Removal | (PW# 799) AEE015 Debris Removal | 0 | 1946DR-PR (1946DR) | 1768.93 | 0 | 0 | 442.23 | 442.23 | 1326.7 | 75% | 2011-05-04 19:49 | 2011-05-05 12:19 | 0
974941 | 798 | F - Utilities | (PW# 798) AEE011 Utilities | 0 | 1946DR-PR (1946DR) | 3009.23 | 0 | 0 | 752.31 | 752.31 | 2256.92 | 75% | 2011-05-04 19:49 | 2011-05-05 12:19 | 0
974940 | 797 | F - Utilities | (PW# 797) AEE010 Utilities | 0 | 1946DR-PR (1946DR) | 1893.95 | 0 | 0 | 473.49 | 473.49 | 1420.46 | 75% | 2011-05-04 19:49 | 2011-05-05 12:19 | 0
481842 | 79 | F - Utilities | (PW# 79) AETAL-03 Public Utilities | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
974939 | 788 | A - Debris Removal | (PW# 788) AEE013 Protective Measures | 0 | 1946DR-PR (1946DR) | 3375.89 | 0 | 0 | 843.97 | 843.97 | 2531.92 | 75% | 2011-05-04 19:49 | 2011-05-05 12:19 | 0
974938 | 787 | F - Utilities | (PW# 787) AEE008 Utilities | 0 | 1946DR-PR (1946DR) | 1860.59 | 0 | 0 | 465.15 | 465.15 | 1395.44 | 75% | 2011-05-04 19:49 | 2011-05-05 12:19 | 0
974937 | 780 | A - Debris Removal | (PW# 780) AEE022 Debris Removal | 0 | 1946DR-PR (1946DR) | 3471.19 | 0 | 0 | 867.8 | 867.8 | 2603.39 | 75% | 2011-05-04 19:49 | 2011-05-05 12:19 | 0
481838 | 78 | B - Emergency Protective Measures | (PW# 78) AETAL-04 Protective Measures | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
974936 | 779 | F - Utilities | (PW# 779) AEE021 Utilities | 0 | 1946DR-PR (1946DR) | 4360.83 | 0 | 0 | 1090.21 | 1090.21 | 3270.62 | 75% | 2011-05-04 19:49 | 2011-05-05 12:19 | 0
974935 | 778 | F - Utilities | (PW# 778) AEE001 Utilities | 0 | 1946DR-PR (1946DR) | 40596.99 | 0 | 0 | 10149.25 | 10149.25 | 30447.74 | 75% | 2011-05-04 19:49 | 2011-05-05 12:19 | 0
974934 | 777 | F - Utilities | (PW# 777) AEE034 Utilities | 0 | 1946DR-PR (1946DR) | 3472.8 | 0 | 0 | 868.2 | 868.2 | 2604.6 | 75% | 2011-05-04 19:49 | 2011-05-05 12:19 | 0
481839 | 77 | B - Emergency Protective Measures | (PW# 77) AEAG-L04 Protective Measures | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
481841 | 76 | B - Emergency Protective Measures | (PW# 76) AETBAO04 Protective Measures | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
481837 | 75 | B - Emergency Protective Measures | (PW# 75) AEISA02 Protective Measure | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
974933 | 743 | F - Utilities | (PW# 743) AEE035 Utilities | 0 | 1946DR-PR (1946DR) | 1843.98 | 0 | 0 | 460.99 | 460.99 | 1382.99 | 75% | 2011-05-04 19:49 | 2011-05-05 12:19 | 0
974932 | 742 | F - Utilities | (PW# 742) AEE006 Utilities | 0 | 1946DR-PR (1946DR) | 1215.69 | 0 | 0 | 303.92 | 303.92 | 911.77 | 75% | 2011-05-04 19:49 | 2011-05-05 12:19 | 0
974931 | 741 | F - Utilities | (PW# 741) AEE009 Utilities | 0 | 1946DR-PR (1946DR) | 1732.06 | 0 | 0 | 433.01 | 433.01 | 1299.05 | 75% | 2011-05-04 19:49 | 2011-05-05 12:19 | 0
481833 | 74 | B - Emergency Protective Measures | (PW# 74) AETAL02 Protective Measures | 0 | 3326EM-PR (3326EM) | 4500.74 | 0 | 0 | 1125.18 | 1125.18 | 3375.56 | 75% |  | 2012-03-22 11:45 | 4500.74
481835 | 73 | B - Emergency Protective Measures | (PW# 73) AESSE02 Protective Measures | 0 | 3326EM-PR (3326EM) | 7193.25 | 0 | 0 | 1798.31 | 1798.31 | 5394.94 | 75% |  | 2012-03-22 11:45 | 7193.25
974930 | 720 | F - Utilities | (PW# 720) AEE007 Utilities | 0 | 1946DR-PR (1946DR) | 1268.12 | 0 | 0 | 317.03 | 317.03 | 951.09 | 75% | 2011-05-04 19:49 | 2011-05-05 12:19 | 0
481834 | 72 | B - Emergency Protective Measures | (PW# 72) AEAGL-01 Protective Measures | 0 | 3326EM-PR (3326EM) | 4301.74 | 0 | 0 | 1075.43 | 1075.43 | 3226.31 | 75% |  | 2012-03-22 11:45 | 4301.74
481832 | 71 | B - Emergency Protective Measures | (PW# 71) AETAL01 Protective Measures | 0 | 3326EM-PR (3326EM) | 2318.36 | 0 | 0 | 579.59 | 579.59 | 1738.77 | 75% |  | 2012-03-22 11:45 | 2318.36
481830 | 70 | B - Emergency Protective Measures | (PW# 70) AEMOC-01 Protective Measures | 0 | 3326EM-PR (3326EM) | 7482.22 | 0 | 0 | 1870.55 | 1870.55 | 5611.67 | 75% |  | 2012-03-22 11:45 | 7482.22
481797 | 7 | B - Emergency Protective Measures | (PW# 7) AEBCL01 Protective Measures | 0 | 3326EM-PR (3326EM) | 3045.95 | 0 | 0 | 761.49 | 761.49 | 2284.46 | 75% |  | 2012-04-26 19:06 | 3045.95
481728 | 69 | B - Emergency Protective Measures | (PW# 69) Protective Measures-PREPA03 | 0 | 3306EM-PR (3306EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
481831 | 69 | B - Emergency Protective Measures | (PW# 69) AEPON13 Protective Measures | 0 | 3326EM-PR (3326EM) | 6449.55 | 0 | 0 | 1612.39 | 1612.39 | 4837.16 | 75% |  | 2012-03-22 11:45 | 6449.55
481829 | 68 | B - Emergency Protective Measures | (PW# 68) AEMOC02 Protective Measures | 0 | 3326EM-PR (3326EM) | 2069.53 | 0 | 0 | 517.38 | 517.38 | 1552.15 | 75% |  | 2012-03-22 11:45 | 2069.53
481828 | 67 | B - Emergency Protective Measures | (PW# 67) AEPON-07 Protective Measures | 0 | 3326EM-PR (3326EM) | 13149.39 | 0 | 0 | 3287.35 | 3287.35 | 9862.04 | 75% |  | 2012-03-22 11:45 | 13149.39
481826 | 66 | F - Utilities | (PW# 66) AEVAL03 Public Utilities | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
481827 | 65 | B - Emergency Protective Measures | (PW# 65) AEDOR-01 Protective Measures | 0 | 3326EM-PR (3326EM) | 5038.74 | 0 | 0 | 1259.68 | 1259.68 | 3779.06 | 75% |  | 2012-03-22 11:45 | 5038.74
974929 | 640 | F - Utilities | (PW# 640) AEE004 Utilities | 0 | 1946DR-PR (1946DR) | 1257.6 | 0 | 0 | 314.4 | 314.4 | 943.2 | 75% | 2011-05-04 19:49 | 2011-05-05 12:19 | 0
481825 | 64 | B - Emergency Protective Measures | (PW# 64) AEPON-11 Protective Measures | 0 | 3326EM-PR (3326EM) | 12592.48 | 0 | 0 | 3148.12 | 3148.12 | 9444.36 | 75% |  | 2012-03-22 11:45 | 12592.48
974928 | 639 | F - Utilities | (PW# 639) AEE005 Utilities | 0 | 1946DR-PR (1946DR) | 1146.37 | 0 | 0 | 286.59 | 286.59 | 859.78 | 75% | 2011-05-04 19:49 | 2011-05-05 12:19 | 0
481824 | 63 | B - Emergency Protective Measures | (PW# 63) AEISA-01 Protective Measures | 0 | 3326EM-PR (3326EM) | 1975.58 | 0 | 0 | 493.89 | 493.89 | 1481.69 | 75% |  | 2012-03-22 11:45 | 1975.58
481823 | 62 | B - Emergency Protective Measures | (PW# 62) AEHAT02 Protective Measures | 0 | 3326EM-PR (3326EM) | 5295.93 | 0 | 0 | 1323.98 | 1323.98 | 3971.95 | 75% |  | 2012-03-22 11:45 | 5295.93
481822 | 61 | B - Emergency Protective Measures | (PW# 61) AEPON-06 Protective Measures | 0 | 3326EM-PR (3326EM) | 10018.95 | 0 | 0 | 2504.74 | 2504.74 | 7514.21 | 75% |  | 2012-03-22 11:45 | 10018.95
481821 | 60 | B - Emergency Protective Measures | (PW# 60) AEHAT-01 Protective Measures | 0 | 3326EM-PR (3326EM) | 6199.09 | 0 | 0 | 1549.77 | 1549.77 | 4649.32 | 75% |  | 2012-03-22 11:45 | 6199.09
974927 | 598 | F - Utilities | (PW# 598) AEE002 Utilities | 0 | 1946DR-PR (1946DR) | 55021.35 | 0 | 0 | 13755.34 | 13755.34 | 41266.01 | 75% | 2011-05-04 19:49 | 2011-05-05 12:19 | 0
481820 | 59 | B - Emergency Protective Measures | (PW# 59) AETBA-01 Protective Measures | 0 | 3326EM-PR (3326EM) | 5859.98 | 0 | 0 | 1464.99 | 1464.99 | 4394.99 | 75% |  | 2012-03-22 11:45 | 5859.98
974926 | 585 | F - Utilities | (PW# 585) AEE003 Utilities | 0 | 1946DR-PR (1946DR) | 1066.81 | 0 | 0 | 266.7 | 266.7 | 800.11 | 75% | 2011-05-04 19:49 | 2011-05-05 12:19 | 0
481819 | 58 | B - Emergency Protective Measures | (PW# 58) AEMAN-05 Protective Measures | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
481727 | 57 | B - Emergency Protective Measures | (PW# 57) Protective Measures PREPA02 | 0 | 3306EM-PR (3306EM) | 4112.75 | 0 | 0 | 1028.19 | 1028.19 | 3084.56 | 75% |  | 2010-05-17 13:14 | 4112.75
481818 | 57 | F - Utilities | (PW# 57) AEMAN-04 Public Utilities | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
479578 | 565 | B - Emergency Protective Measures | (PW# 565) EMERGENCY PROTECTIVE MEASURES | 1 | 1613DR-PR (1613DR) | 100433.22 | 0 | 0 | 25108.31 | 25108.31 | 75324.91 | 75% |  | 2010-10-27 19:38 | 0
479577 | 560 | F - Utilities | (PW# 560) PUBLIC UTILITIES | 0 | 1613DR-PR (1613DR) | 50384 | 0 | 0 | 12596 | 12596 | 37788 | 75% |  | 2006-06-21 18:22 | 0
479576 | 558 | B - Emergency Protective Measures | (PW# 558) EMERGENCY PROTECTIVE MEASURES | 1 | 1613DR-PR (1613DR) | 75534.85 | 0 | 0 | 18883.72 | 18883.72 | 56651.13 | 75% |  | 2010-10-27 19:38 | 0
479575 | 557 | B - Emergency Protective Measures | (PW# 557) EMERGENCY PROTECTIVE MEASURES | 0 | 1613DR-PR (1613DR) | 11809.82 | 0 | 0 | 2952.45 | 2952.45 | 8857.37 | 75% |  | 2006-05-22 17:44 | 0
479574 | 556 | B - Emergency Protective Measures | (PW# 556) EMERGENCY PROTECTIVE MEASURES | 0 | 1613DR-PR (1613DR) | 8757.7 | 0 | 0 | 2189.42 | 2189.42 | 6568.28 | 75% |  | 2006-05-22 17:44 | 0
479573 | 555 | B - Emergency Protective Measures | (PW# 555) EMERGENCY PROTECTIVE MEASURES | 0 | 1613DR-PR (1613DR) | 25403.89 | 0 | 0 | 6350.97 | 6350.97 | 19052.92 | 75% |  | 2006-06-21 18:22 | 0
479572 | 554 | B - Emergency Protective Measures | (PW# 554) EMERGENCY PROTECTIVE MEASURES | 0 | 1613DR-PR (1613DR) | 9649.9 | 0 | 0 | 2412.47 | 2412.47 | 7237.43 | 75% |  | 2006-05-22 17:44 | 0
479571 | 553 | B - Emergency Protective Measures | (PW# 553) EMERGENCY PROTECTIVE MEASURES | 0 | 1613DR-PR (1613DR) | 53731 | 0 | 0 | 13432.75 | 13432.75 | 40298.25 | 75% |  | 2006-06-21 18:22 | 0
479570 | 552 | B - Emergency Protective Measures | (PW# 552) EMERGENCY PROTECTIVE MEASURES | 0 | 1613DR-PR (1613DR) | 24885.67 | 0 | 0 | 6221.42 | 6221.42 | 18664.25 | 75% |  | 2006-05-22 17:44 | 0
479569 | 551 | B - Emergency Protective Measures | (PW# 551) EMERGENCY PROTECTIVE MEASURES | 0 | 1613DR-PR (1613DR) | 13191.6 | 0 | 0 | 3297.9 | 3297.9 | 9893.7 | 75% |  | 2006-05-22 17:44 | 0
481817 | 53 | B - Emergency Protective Measures | (PW# 53) AEQUE-03 Protective Measures | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
481816 | 52 | F - Utilities | (PW# 52) AEQUE-02 Public Utilities | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
480161 | 518 | D - Water Control Facilities | (PW# 518) Water Control PREPA-03 | 0 | 1798DR-PR (1798DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
481815 | 51 | B - Emergency Protective Measures | (PW# 51) AECAM-03 Protective Measures | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
480160 | 503 | D - Water Control Facilities | (PW# 503) Water Control Prepa-04 | 0 | 1798DR-PR (1798DR) | 42936.35 | 0 | 0 | 10734.09 | 10734.09 | 32202.26 | 75% |  | 2009-01-26 15:30 | 42936.35
481814 | 50 | F - Utilities | (PW# 50) AEGYL-03 Public Utilities | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
481813 | 49 | F - Utilities | (PW# 49) AECAM-02 Public Utilities | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
483019 | 484 | B - Emergency Protective Measures | (PW# 484) AEMOR-02 Protective Measures | 0 | 4004DR-PR (4004DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
483018 | 483 | F - Utilities | (PW# 483) AEUTU-02 Public Utilities | 0 | 4004DR-PR (4004DR) | 15225.79 | 0 | 0 | 3806.45 | 3806.45 | 11419.34 | 75% |  | 2012-03-21 12:50 | 15225.79
483017 | 481 | B - Emergency Protective Measures | (PW# 481) AEMOR-01 Protective Measures | 0 | 4004DR-PR (4004DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
483011 | 480 | F - Utilities | (PW# 480) AEUTU-03 Utilities | 0 | 4004DR-PR (4004DR) | 13050.93 | 0 | 0 | 3262.73 | 3262.73 | 9788.2 | 75% |  | 2012-03-21 12:50 | 13050.93
483016 | 479 | B - Emergency Protective Measures | (PW# 479) AEHAT-08 Public Utilities | 0 | 4004DR-PR (4004DR) | 1186.22 | 0 | 0 | 296.55 | 296.55 | 889.67 | 75% |  | 2012-03-21 12:50 | 1186.22
483015 | 478 | F - Utilities | (PW# 478) AEHAT-12 Public Utilities | 0 | 4004DR-PR (4004DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
483013 | 477 | B - Emergency Protective Measures | (PW# 477) AEHAT-11 Protective Measures | 0 | 4004DR-PR (4004DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
483014 | 476 | F - Utilities | (PW# 476) AEUTU-04 Public Utilities | 0 | 4004DR-PR (4004DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
483012 | 475 | F - Utilities | (PW# 475) PW AEUTU-05 Utilities | 0 | 4004DR-PR (4004DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
483006 | 474 | B - Emergency Protective Measures | (PW# 474) AESSE-01 Protective Measures | 0 | 4004DR-PR (4004DR) | 1667.83 | 0 | 0 | 416.96 | 416.96 | 1250.87 | 75% |  | 2012-03-21 12:50 | 1667.83
483010 | 473 | F - Utilities | (PW# 473) AECAG-05 Public Utilities | 0 | 4004DR-PR (4004DR) | 9983.67 | 0 | 0 | 2495.92 | 2495.92 | 7487.75 | 75% |  | 2012-03-21 12:50 | 9983.67
483009 | 472 | F - Utilities | (PW# 472) AEMOR-03 Public Utilities | 0 | 4004DR-PR (4004DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
483008 | 471 | F - Utilities | (PW# 471) AEANA-01 Public Utilities | 0 | 4004DR-PR (4004DR) | 1645.83 | 0 | 0 | 411.46 | 411.46 | 1234.37 | 75% |  | 2012-03-21 12:50 | 1645.83
483007 | 470 | F - Utilities | (PW# 470) AEUTU-06 Public Utilities | 0 | 4004DR-PR (4004DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
481812 | 47 | B - Emergency Protective Measures | (PW# 47) AECAM01 Protective Measures | 0 | 3326EM-PR (3326EM) | 5011.96 | 0 | 0 | 1252.99 | 1252.99 | 3758.97 | 75% |  | 2012-03-22 11:45 | 5011.96
483005 | 469 | B - Emergency Protective Measures | (PW# 469) AEUTU-01 Protective Measures | 0 | 4004DR-PR (4004DR) | 2920.06 | 0 | 0 | 730.01 | 730.01 | 2190.05 | 75% |  | 2012-03-21 12:50 | 2920.06
483003 | 466 | B - Emergency Protective Measures | (PW# 466) AEMAN-01 Protective Measures | 0 | 4004DR-PR (4004DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
483004 | 463 | F - Utilities | (PW# 463) AECAG-01 Public Utilities | 0 | 4004DR-PR (4004DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
483000 | 462 | B - Emergency Protective Measures | (PW# 462) AECIA-04 Protective Measures | 0 | 4004DR-PR (4004DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
483001 | 461 | F - Utilities | (PW# 461) AECAG-02 Public Utilities | 0 | 4004DR-PR (4004DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
483002 | 460 | B - Emergency Protective Measures | (PW# 460) AESLO-01 Protective Measures | 0 | 4004DR-PR (4004DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
481811 | 46 | B - Emergency Protective Measures | (PW# 46) AEGYL04 Protective Measures | 0 | 3326EM-PR (3326EM) | 5691.78 | 0 | 0 | 1422.94 | 1422.94 | 4268.84 | 75% |  | 2012-03-22 11:45 | 5691.78
482999 | 459 | F - Utilities | (PW# 459) AEBCL-01 Public Utilities | 0 | 4004DR-PR (4004DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
482997 | 458 | F - Utilities | (PW# 458) PW AEJUA-01 Utilities | 0 | 4004DR-PR (4004DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
482998 | 457 | F - Utilities | (PW# 457) AEJUN-01 Public Utilities | 0 | 4004DR-PR (4004DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
482996 | 456 | B - Emergency Protective Measures | (PW# 456) AECIA-05 Protective Measures | 0 | 4004DR-PR (4004DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
482995 | 455 | B - Emergency Protective Measures | (PW# 455) AECIA-02 Protective Measures | 0 | 4004DR-PR (4004DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
482994 | 454 | B - Emergency Protective Measures | (PW# 454) AECIA-03 Protective Measures | 0 | 4004DR-PR (4004DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
482993 | 453 | F - Utilities | (PW# 453) AEGUR-01 Public Utilities | 0 | 4004DR-PR (4004DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
480159 | 452 | A - Debris Removal | (PW# 452) Debris Removal PREPA02 | 1 | 1798DR-PR (1798DR) | 39256.76 | 0 | 0 | 9814.19 | 9814.19 | 29442.57 | 75% |  | 2013-04-04 12:56 | 39256.76
482992 | 452 | F - Utilities | (PW# 452) AECIA-07 Public Utilities | 0 | 4004DR-PR (4004DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
482991 | 451 | F - Utilities | (PW# 451) AESSE-02 Public Utilities | 0 | 4004DR-PR (4004DR) | 3615.22 | 0 | 0 | 903.8 | 903.8 | 2711.42 | 75% |  | 2012-03-21 12:50 | 3615.22
482990 | 450 | F - Utilities | (PW# 450) AEJUA-02 Public Utilities | 0 | 4004DR-PR (4004DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
481810 | 45 | B - Emergency Protective Measures | (PW# 45) AEGNC02 Protective Measures | 0 | 3326EM-PR (3326EM) | 1178.99 | 0 | 0 | 294.75 | 294.75 | 884.24 | 75% |  | 2012-03-22 11:45 | 1178.99
482989 | 449 | F - Utilities | (PW# 449) AESLO-06 Public Utilities | 0 | 4004DR-PR (4004DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
482988 | 447 | B - Emergency Protective Measures | (PW# 447) AEFLO-01 Protective Measures | 0 | 4004DR-PR (4004DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
482987 | 446 | F - Utilities | (PW# 446) AECAG-11 Public Utilities | 0 | 4004DR-PR (4004DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
482986 | 445 | B - Emergency Protective Measures | (PW# 445) AEARE-01 Protective Measures | 0 | 4004DR-PR (4004DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
482985 | 444 | F - Utilities | (PW# 444) AEPON-01 Public Utilities | 0 | 4004DR-PR (4004DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
482976 | 443 | F - Utilities | (PW# 443) AECAG-10 Public Utilities | 0 | 4004DR-PR (4004DR) | 25182.97 | 0 | 0 | 6295.74 | 6295.74 | 18887.23 | 75% |  | 2012-03-21 12:50 | 25182.97
477296 | 442 | D - Water Control Facilities | (PW# 442) WATER CONTROL FACILITIES | 0 | 1501DR-PR (1501DR) | 32089.5 | 0 | 0 | 8022.37 | 8022.37 | 24067.13 | 75% |  | 2004-11-30 13:38 | 0
482984 | 442 | F - Utilities | (PW# 442) AEABU-01 Public Utilities | 0 | 4004DR-PR (4004DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
477295 | 441 | D - Water Control Facilities | (PW# 441) WATER CONTROL FACILITIES | 0 | 1501DR-PR (1501DR) | 50508.06 | 0 | 0 | 12627.01 | 12627.01 | 37881.05 | 75% |  | 2004-11-30 13:38 | 0
482983 | 441 | B - Emergency Protective Measures | (PW# 441) AEVIL-05 Protective Measures | 0 | 4004DR-PR (4004DR) | 768.32 | 0 | 0 | 192.08 | 0 | 0 | 75% |  |  | 0
477294 | 440 | D - Water Control Facilities | (PW# 440) WATER CONTROL FACILITIES | 0 | 1501DR-PR (1501DR) | 9876.24 | 0 | 0 | 2469.06 | 2469.06 | 7407.18 | 75% |  | 2004-11-30 13:38 | 0
482982 | 440 | F - Utilities | (PW# 440) AELPI-05 Public Utilities | 0 | 4004DR-PR (4004DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
482981 | 439 | F - Utilities | (PW# 439) AEJUA-03 Public Utilities | 0 | 4004DR-PR (4004DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
482980 | 436 | F - Utilities | (PW# 436) AEVIL-06 Public Utilities | 0 | 4004DR-PR (4004DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
482979 | 435 | F - Utilities | (PW# 435) AEPON-02 Public Utilities | 0 | 4004DR-PR (4004DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
482978 | 434 | B - Emergency Protective Measures | (PW# 434) AELMA-01 Protective Measures | 0 | 4004DR-PR (4004DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
482977 | 433 | F - Utilities | (PW# 433) AETBA-01 Public Utilities | 0 | 4004DR-PR (4004DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
482975 | 432 | F - Utilities | (PW# 432) AEVIL-07 Public Utilities | 0 | 4004DR-PR (4004DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
482972 | 431 | B - Emergency Protective Measures | (PW# 431) AECIA-06 Protective Measures | 0 | 4004DR-PR (4004DR) | 1017.15 | 0 | 0 | 254.29 | 254.29 | 762.86 | 75% |  | 2012-03-21 12:50 | 1017.15
482974 | 430 | B - Emergency Protective Measures | (PW# 430) AEADJ-01 Protective Measures | 0 | 4004DR-PR (4004DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
481805 | 43 | B - Emergency Protective Measures | (PW# 43) AEGNC01 Protective Measures | 0 | 3326EM-PR (3326EM) | 1638.16 | 0 | 0 | 409.54 | 409.54 | 1228.62 | 75% |  | 2012-03-22 11:45 | 1638.16
482973 | 428 | B - Emergency Protective Measures | (PW# 428) AECAM01 Protective Measures | 0 | 4004DR-PR (4004DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
482971 | 427 | B - Emergency Protective Measures | (PW# 427) AECAG-07 Protective Measures | 0 | 4004DR-PR (4004DR) | 9879.34 | 0 | 0 | 2469.83 | 2469.83 | 7409.51 | 75% |  | 2012-03-21 12:50 | 9879.34
482970 | 425 | F - Utilities | (PW# 425) AECAG-08 Public Utilities | 1 | 4004DR-PR (4004DR) | 0 | 0 | 0 | 0 | 0 | 0 | 0% |  | 2021-04-27 15:15 | 0
482969 | 424 | B - Emergency Protective Measures | (PW# 424) AECAG-03 Protective Measures | 0 | 4004DR-PR (4004DR) | 14032.15 | 0 | 0 | 3508.04 | 3508.04 | 10524.11 | 75% |  | 2012-03-21 12:50 | 14032.15
482968 | 423 | B - Emergency Protective Measures | (PW# 423) AECAG-06 Protective Measures | 0 | 4004DR-PR (4004DR) | 3468.05 | 0 | 0 | 867.01 | 867.01 | 2601.04 | 75% |  | 2012-03-21 12:50 | 3468.05
482967 | 422 | F - Utilities | (PW# 422) AECAG-09 Public Utilities | 0 | 4004DR-PR (4004DR) | 1615.42 | 128.09 | 0 | 403.85 | 403.85 | 1211.57 | 75% |  | 2012-03-21 12:50 | 1615.42
482966 | 421 | F - Utilities | (PW# 421) AECAG-04 Public Utilities | 0 | 4004DR-PR (4004DR) | 16352.02 | 0 | 0 | 4088 | 4088 | 12264.02 | 75% |  | 2012-03-21 12:50 | 16352.02
482965 | 420 | B - Emergency Protective Measures | (PW# 420) AESL - 02 Protective Measures | 0 | 4004DR-PR (4004DR) | 6092.72 | 0 | 0 | 1523.18 | 1523.18 | 4569.54 | 75% |  | 2012-03-21 12:50 | 6092.72
482964 | 419 | F - Utilities | (PW# 419) AESLO05 Public Utilities | 0 | 4004DR-PR (4004DR) | 4575.06 | 0 | 0 | 1143.76 | 1143.76 | 3431.3 | 75% |  | 2012-03-21 12:50 | 4575.06
482963 | 418 | F - Utilities | (PW# 418) AESLO04 Public Utilities | 0 | 4004DR-PR (4004DR) | 2525.52 | 0 | 0 | 631.38 | 631.38 | 1894.14 | 75% |  | 2012-03-21 12:50 | 2525.52
482962 | 416 | B - Emergency Protective Measures | (PW# 416) AELPI-03 Protective Measures | 0 | 4004DR-PR (4004DR) | 2283.92 | 0 | 0 | 570.98 | 570.98 | 1712.94 | 75% |  | 2012-03-21 12:50 | 2283.92
482961 | 415 | F - Utilities | (PW# 415) AESLO-03 Utilities | 0 | 4004DR-PR (4004DR) | 2087.15 | 0 | 0 | 521.79 | 521.79 | 1565.36 | 75% |  | 2012-03-21 12:50 | 2087.15
482960 | 414 | F - Utilities | (PW# 414) AECIA-01 Public Utilities | 1 | 4004DR-PR (4004DR) | 0 | 0 | -432006.01 | 0 | 0 | 0 | 0% |  | 2021-04-27 15:15 | 0
482959 | 408 | F - Utilities | (PW# 408) AEHUM01 Public Utilities | 0 | 4004DR-PR (4004DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
482958 | 407 | F - Utilities | (PW# 407) AENAG01 Public Utilities | 0 | 4004DR-PR (4004DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
482957 | 406 | F - Utilities | (PW# 406) A-AELPI-04 Public Utilities | 0 | 4004DR-PR (4004DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
481809 | 40 | B - Emergency Protective Measures | (PW# 40) AEMAN01 Protective Measures | 0 | 3326EM-PR (3326EM) | 5182.12 | 0 | 0 | 1295.53 | 1295.53 | 3886.59 | 75% |  | 2012-03-22 11:45 | 5182.12
476503 | 394 | C - Roads and Bridges | (PW# 394) ROADS AND BRIDGES | 2 | 1372DR-PR (1372DR) | 325886.97 | 0 | 0 | 81471.74 | 81471.74 | 244415.23 | 75% |  | 2008-12-02 19:11 | 0
482956 | 394 | F - Utilities | (PW# 394) A- AEYAB12 - Public Utilities | 0 | 4004DR-PR (4004DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
482955 | 393 | F - Utilities | (PW# 393) A- AEHAT03 Public Utilities | 0 | 4004DR-PR (4004DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
482954 | 392 | F - Utilities | (PW# 392) A- AEHAT07 Public Utilities | 0 | 4004DR-PR (4004DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
482953 | 391 | F - Utilities | (PW# 391) A- AECIA07 Public Buildings | 0 | 4004DR-PR (4004DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
481808 | 39 | B - Emergency Protective Measures | (PW# 39) AEQUE04 Protective Measures | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
482952 | 389 | F - Utilities | (PW# 389) A- AEHAT06 Public Utilities | 0 | 4004DR-PR (4004DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
480158 | 383 | F - Utilities | (PW# 383) Public Utility PREPA-01 | 1 | 1798DR-PR (1798DR) | 0 | 0 | 0 | 0 | 0 | 0 | 0% |  | 2014-10-28 18:32 | 0
482951 | 381 | F - Utilities | (PW# 381) AEYAB06 Public Utilities | 0 | 4004DR-PR (4004DR) | 3490.22 | 0 | 0 | 872.55 | 872.55 | 2617.67 | 75% |  | 2012-03-21 12:50 | 3490.22
481807 | 38 | B - Emergency Protective Measures | (PW# 38) AEGYL01 Protective Measures | 0 | 3326EM-PR (3326EM) | 3863.87 | 0 | 0 | 965.97 | 965.97 | 2897.9 | 75% |  | 2012-03-22 11:45 | 3863.87
477293 | 373 | D - Water Control Facilities | (PW# 373) WATER CONTROL FACILITIES | 0 | 1501DR-PR (1501DR) | 39544 | 0 | 0 | 9886 | 9886 | 29658 | 75% |  | 2004-02-24 12:41 | 0
477292 | 371 | C - Roads and Bridges | (PW# 371) ROADS AND BRIDGES | 0 | 1501DR-PR (1501DR) | 7075.2 | 0 | 0 | 1768.8 | 1768.8 | 5306.4 | 75% |  | 2004-02-24 12:41 | 0
477291 | 370 | D - Water Control Facilities | (PW# 370) WATER CONTROL FACILITIES | 0 | 1501DR-PR (1501DR) | 2000 | 0 | 0 | 500 | 500 | 1500 | 75% |  | 2004-02-24 12:41 | 0
477290 | 369 | A - Debris Removal | (PW# 369) DEBRIS REMOVAL | 0 | 1501DR-PR (1501DR) | 2442 | 0 | 0 | 610.5 | 610.5 | 1831.5 | 75% |  | 2004-02-24 12:41 | 0
476871 | 362 | B - Emergency Protective Measures | (PW# 362) EMERGENCY PROTECTIVE MEASURES | 1 | 1396DR-PR (1396DR) | 77894.73 | 0 | 0 | 19473.68 | 19473.68 | 58421.05 | 75% |  | 2006-01-30 18:33 | 0
482945 | 360 | B - Emergency Protective Measures | (PW# 360) AELP101 Protective Measures | 0 | 4004DR-PR (4004DR) | 1252.29 | 0 | 0 | 313.07 | 313.07 | 939.22 | 75% |  | 2012-03-21 12:50 | 1252.29
481806 | 36 | B - Emergency Protective Measures | (PW# 36) AEGYL02 Protective Measures | 0 | 3326EM-PR (3326EM) | 3844.41 | 0 | 0 | 961.1 | 961.1 | 2883.31 | 75% |  | 2012-03-22 11:45 | 3844.41
482950 | 358 | F - Utilities | (PW# 358) AEYAB11 Public Utilities | 0 | 4004DR-PR (4004DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
482949 | 352 | B - Emergency Protective Measures | (PW# 352) AEHAT02 Protective Measures | 0 | 4004DR-PR (4004DR) | 1780.54 | 0 | 0 | 445.13 | 445.13 | 1335.41 | 75% |  | 2012-03-21 12:50 | 1780.54
482947 | 351 | F - Utilities | (PW# 351) AELPI02 Public Utilities | 0 | 4004DR-PR (4004DR) | 1877.56 | 0 | 0 | 469.39 | 469.39 | 1408.17 | 75% |  | 2012-03-21 12:50 | 1877.56
482948 | 350 | F - Utilities | (PW# 350) AEHAT10 Public Utilities | 0 | 4004DR-PR (4004DR) | 1339.51 | 0 | 0 | 334.88 | 334.88 | 1004.63 | 75% |  | 2012-03-21 12:50 | 1339.51
482946 | 349 | F - Utilities | (PW# 349) AEHAT05 Public Utilities | 0 | 4004DR-PR (4004DR) | 1255.64 | 0 | 0 | 313.91 | 313.91 | 941.73 | 75% |  | 2012-03-21 12:50 | 1255.64
482944 | 348 | F - Utilities | (PW# 348) AEVIL03 Public Utilities | 0 | 4004DR-PR (4004DR) | 1128.04 | 0 | 0 | 282.01 | 282.01 | 846.03 | 75% |  | 2012-03-21 12:50 | 1128.04
482943 | 347 | B - Emergency Protective Measures | (PW# 347) AEHAT01 Public Utilities | 0 | 4004DR-PR (4004DR) | 1675.3 | 0 | 0 | 418.82 | 418.82 | 1256.48 | 75% |  | 2012-03-21 12:50 | 1675.3
482941 | 346 | F - Utilities | (PW# 346) AEVIL04 Utilities | 0 | 4004DR-PR (4004DR) | 1008.92 | 0 | 0 | 252.23 | 252.23 | 756.69 | 75% |  | 2012-03-21 12:50 | 1008.92
482942 | 345 | F - Utilities | (PW# 345) AEHAT09 Public Utilities | 0 | 4004DR-PR (4004DR) | 1322 | 0 | 0 | 330.5 | 330.5 | 991.5 | 75% |  | 2012-03-21 12:50 | 1322
482940 | 342 | F - Utilities | (PW# 342) AEYAB10 Public Utilities | 0 | 4004DR-PR (4004DR) | 1628.63 | 0 | 0 | 407.16 | 407.16 | 1221.47 | 75% |  | 2012-03-21 12:50 | 1628.63
482939 | 341 | F - Utilities | (PW# 341) AEYAB09 Public Utilities | 0 | 4004DR-PR (4004DR) | 1064.3 | 0 | 0 | 266.07 | 266.07 | 798.23 | 75% |  | 2012-03-21 12:50 | 1064.3
482938 | 340 | F - Utilities | (PW# 340) AEVIL02 Public Utilities | 0 | 4004DR-PR (4004DR) | 2664.28 | 128.09 | 0 | 666.07 | 666.07 | 1998.21 | 75% |  | 2012-03-21 12:50 | 2664.28
482937 | 339 | F - Utilities | (PW# 339) AEVIL01 Public Utilities | 0 | 4004DR-PR (4004DR) | 1632.87 | 0 | 0 | 408.22 | 408.22 | 1224.65 | 75% |  | 2012-03-21 12:50 | 1632.87
482936 | 334 | F - Utilities | (PW# 334) AEYAB08 Public Utilities | 0 | 4004DR-PR (4004DR) | 3641.8 | 0 | 0 | 910.45 | 910.45 | 2731.35 | 75% |  | 2012-03-21 12:50 | 3641.8
482935 | 332 | F - Utilities | (PW# 332) AEYAB07 Public Utilities | 0 | 4004DR-PR (4004DR) | 3491.54 | 0 | 0 | 872.88 | 872.88 | 2618.66 | 75% |  | 2012-03-21 12:50 | 3491.54
482934 | 331 | F - Utilities | (PW# 331) AEYAB05 Public Utilities | 0 | 4004DR-PR (4004DR) | 1457.3 | 128.09 | 0 | 364.32 | 364.32 | 1092.98 | 75% |  | 2012-03-21 12:50 | 1457.3
482933 | 330 | F - Utilities | (PW# 330) AECAM10 Public Utilities | 0 | 4004DR-PR (4004DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
482932 | 329 | F - Utilities | (PW# 329) AEHAT04 Public Utilities | 0 | 4004DR-PR (4004DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
482931 | 328 | F - Utilities | (PW# 328) AECAM11 Public Utilities | 0 | 4004DR-PR (4004DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
482930 | 327 | B - Emergency Protective Measures | (PW# 327) AEYAB04 Protective measures | 0 | 4004DR-PR (4004DR) | 2253.41 | 0 | 0 | 563.35 | 563.35 | 1690.06 | 75% |  | 2012-03-21 12:50 | 2253.41
482929 | 326 | F - Utilities | (PW# 326) AECAM09 Utilities | 0 | 4004DR-PR (4004DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
482928 | 325 | F - Utilities | (PW# 325) AECAM05 Utilities | 0 | 4004DR-PR (4004DR) | 1756.23 | 0 | 0 | 439.06 | 439.06 | 1317.17 | 75% |  | 2012-03-21 12:50 | 1756.23
482926 | 324 | B - Emergency Protective Measures | (PW# 324) AEYAB02 Protective Measures | 0 | 4004DR-PR (4004DR) | 1211.08 | 0 | 0 | 302.77 | 302.77 | 908.31 | 75% |  | 2012-03-21 12:50 | 1211.08
482927 | 323 | B - Emergency Protective Measures | (PW# 323) AEYAB03 Protective Measures | 0 | 4004DR-PR (4004DR) | 1970 | 0 | 0 | 492.5 | 492.5 | 1477.5 | 75% |  | 2012-03-21 12:50 | 1970
482922 | 322 | F - Utilities | (PW# 322) AECAM-07 Public Utilities | 0 | 4004DR-PR (4004DR) | 1576.08 | 0 | 0 | 394.02 | 394.02 | 1182.06 | 75% |  | 2012-03-21 12:50 | 1576.08
482925 | 321 | B - Emergency Protective Measures | (PW# 321) AECAM02 Protective Measures | 0 | 4004DR-PR (4004DR) | 659.02 | 0 | 0 | 164.75 | 0 | 0 | 75% |  |  | 0
482924 | 320 | F - Utilities | (PW# 320) AECAM-04 Utilities | 0 | 4004DR-PR (4004DR) | 1523 | 0 | 0 | 380.75 | 380.75 | 1142.25 | 75% |  | 2012-03-21 12:50 | 1523
481804 | 32 | B - Emergency Protective Measures | (PW# 32) AEQUE01 Protective Measures | 0 | 3326EM-PR (3326EM) | 5634.38 | 0 | 0 | 1408.59 | 1408.59 | 4225.79 | 75% |  | 2012-03-22 11:45 | 5634.38
482923 | 319 | B - Emergency Protective Measures | (PW# 319) AECAM-08 Em. Protective Measures | 0 | 4004DR-PR (4004DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
482921 | 318 | B - Emergency Protective Measures | (PW# 318) AEYAB01 Protective Measures | 0 | 4004DR-PR (4004DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
482920 | 317 | F - Utilities | (PW# 317) AECAM-06 Public Utilities | 0 | 4004DR-PR (4004DR) | 328.17 | 0 | 0 | 82.04 | 0 | 0 | 75% |  |  | 0
482919 | 316 | B - Emergency Protective Measures | (PW# 316) AECAM-03 Protective Measures | 0 | 4004DR-PR (4004DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
481803 | 31 | B - Emergency Protective Measures | (PW# 31) AEMAN03 Protective Measures | 0 | 3326EM-PR (3326EM) | 2226.31 | 0 | 0 | 556.58 | 556.58 | 1669.73 | 75% |  | 2012-03-22 11:45 | 2226.31
481802 | 30 | B - Emergency Protective Measures | (PW# 30) AEMAN02 Protective Measures | 0 | 3326EM-PR (3326EM) | 4095.21 | 0 | 0 | 1023.8 | 1023.8 | 3071.41 | 75% |  | 2012-03-22 11:45 | 4095.21
481705 | 261 | B - Emergency Protective Measures | (PW# 261) PRE001 Protective Measures | 0 | 1919DR-PR (1919DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
994301 | 2581 | A - Debris Removal | (PW# 2581) AEORO-11 Debris Removal | 0 | 4017DR-PR (4017DR) | 44814 | 0 | 0 | 11203.5 | 11203.5 | 33610.5 | 75% | 2012-10-09 16:35 | 2012-10-19 03:29 | 0
994300 | 2576 | F - Utilities | (PW# 2576) AEGYB-22 Public Utilities | 0 | 4017DR-PR (4017DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
994299 | 2575 | B - Emergency Protective Measures | (PW# 2575) AECAY-23 Protective Measures | 0 | 4017DR-PR (4017DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
994298 | 2574 | B - Emergency Protective Measures | (PW# 2574) AECAR-37 Protective Measures | 1 | 4017DR-PR (4017DR) | 0 | 0 | 0 | 0 | 5911.09 | 0 | 75% |  |  | 0
994297 | 2573 | B - Emergency Protective Measures | (PW# 2573) AEFAJ-28 Protective Measures | 1 | 4017DR-PR (4017DR) | 0 | 0 | 0 | 0 | 2678.45 | 0 | 75% |  |  | 0
994296 | 2572 | B - Emergency Protective Measures | (PW# 2572) AERIN-06 Protective Measures | 1 | 4017DR-PR (4017DR) | 0 | 0 | 0 | 0 | 1557.22 | 0 | 75% |  |  | 0
994295 | 2571 | B - Emergency Protective Measures | (PW# 2571) AECEI-08 Protective Measures | 1 | 4017DR-PR (4017DR) | 0 | 0 | 0 | 0 | 839.94 | 0 | 75% |  |  | 0
994294 | 2570 | B - Emergency Protective Measures | (PW# 2570) AESJU-12 Protective Measures | 1 | 4017DR-PR (4017DR) | 0 | 0 | 0 | 0 | 14366.99 | 0 | 75% |  |  | 0
994293 | 2569 | B - Emergency Protective Measures | (PW# 2569) AECAY-27 Protective Measures | 1 | 4017DR-PR (4017DR) | 0 | 0 | 0 | 0 | 3192.76 | 0 | 75% |  |  | 0
994292 | 2568 | B - Emergency Protective Measures | (PW# 2568) AEVBA-13 Protective Measures | 1 | 4017DR-PR (4017DR) | 0 | 0 | 0 | 0 | 7790.2 | 0 | 75% |  |  | 0
994291 | 2567 | B - Emergency Protective Measures | (PW# 2567) AECAR-20 Protective Measures | 1 | 4017DR-PR (4017DR) | 0 | 0 | 0 | 0 | 2958.79 | 0 | 75% |  |  | 0
994290 | 2566 | B - Emergency Protective Measures | (PW# 2566) AESJU-14 Protective Measures | 1 | 4017DR-PR (4017DR) | 0 | 0 | 0 | 0 | 19675.91 | 0 | 75% |  |  | 0
994289 | 2565 | B - Emergency Protective Measures | (PW# 2565) AECAN-04 Protective Measures | 1 | 4017DR-PR (4017DR) | 0 | 0 | 0 | 0 | 1693.61 | 0 | 75% |  |  | 0
994288 | 2564 | F - Utilities | (PW# 2564) Public Utilities AERGR11 | 0 | 4017DR-PR (4017DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
994287 | 2563 | B - Emergency Protective Measures | (PW# 2563) AECAN21 Protective Measures | 0 | 4017DR-PR (4017DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
994286 | 2561 | B - Emergency Protective Measures | (PW# 2561) AEFAJ24 Protective Measures | 0 | 4017DR-PR (4017DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
994285 | 2560 | B - Emergency Protective Measures | (PW# 2560) AEBAY29 Protective Measures | 0 | 4017DR-PR (4017DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
994284 | 2406 | F - Utilities | (PW# 2406) AECATF1 Public Utilities | 1 | 4017DR-PR (4017DR) | 5915649.79 | 292595.63 | 0 | 1478912.45 | 1478912.45 | 4436737.34 | 75% | 2012-03-21 22:04 | 2012-11-12 16:23 | 0
994283 | 2405 | B - Emergency Protective Measures | (PW# 2405) AECATB01 Protective Measures | 2 | 4017DR-PR (4017DR) | 1361256.48 | 0 | 0 | 340314.11 | 340314.11 | 1020942.37 | 75% | 2012-03-21 22:04 | 2012-10-19 03:29 | 0
481801 | 24 | B - Emergency Protective Measures | (PW# 24) AEVAL02 Protective Measures | 0 | 3326EM-PR (3326EM) | 4190.85 | 0 | 0 | 1047.71 | 1047.71 | 3143.14 | 75% |  | 2012-03-22 11:45 | 4190.85
994282 | 2296 | F - Utilities | (PW# 2296) AEMOR-03 Public Utilities | 0 | 4017DR-PR (4017DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
994281 | 2246 | B - Emergency Protective Measures | (PW# 2246) AEMOC-03 Protective Measures | 0 | 4017DR-PR (4017DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
994280 | 2241 | B - Emergency Protective Measures | (PW# 2241) PW AECOA-07 Protective Measures | 0 | 4017DR-PR (4017DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
994279 | 2240 | F - Utilities | (PW# 2240) PW AECIA-04 Utilities | 0 | 4017DR-PR (4017DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
994278 | 2237 | B - Emergency Protective Measures | (PW# 2237) AESAL-09 Protective Measures | 0 | 4017DR-PR (4017DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
994277 | 2235 | B - Emergency Protective Measures | (PW# 2235) PW AEMOR-04 Protective Measures | 0 | 4017DR-PR (4017DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
994276 | 2232 | B - Emergency Protective Measures | (PW# 2232) PW AEBAY-05 Protective Measures | 1 | 4017DR-PR (4017DR) | 0 | 0 | 0 | 0 | 634.72 | 0 | 75% |  |  | 0
994275 | 2231 | B - Emergency Protective Measures | (PW# 2231) PW AESIS-05 Protective Measures | 0 | 4017DR-PR (4017DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
994274 | 2228 | B - Emergency Protective Measures | (PW# 2228) PW AEYAU-08 Protective Measures | 0 | 4017DR-PR (4017DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
994273 | 2226 | B - Emergency Protective Measures | (PW# 2226) PW AESAL-08 Em. Protective Measures | 0 | 4017DR-PR (4017DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
994272 | 2225 | B - Emergency Protective Measures | (PW# 2225) PW AECIA-03 Em. Protective Measures | 0 | 4017DR-PR (4017DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
994271 | 2224 | B - Emergency Protective Measures | (PW# 2224) AEFAJ-12 Protective Measures | 0 | 4017DR-PR (4017DR) | 6155.46 | 0 | 0 | 1538.86 | 1538.86 | 4616.6 | 75% | 2012-03-01 12:27 | 2012-03-02 15:17 | 0
994270 | 2223 | B - Emergency Protective Measures | (PW# 2223) PW AESIS-04 Em. Protective Measures | 0 | 4017DR-PR (4017DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
994269 | 2222 | F - Utilities | (PW# 2222) PW AELOI-13 Public Utilities | 1 | 4017DR-PR (4017DR) | 2000.65 | 279.25 | 0 | 500.16 | 500.16 | 1500.49 | 75% | 2012-03-08 21:50 | 2012-06-16 13:04 | 0
994268 | 2221 | F - Utilities | (PW# 2221) AELOI12 Public Utilities | 0 | 4017DR-PR (4017DR) | 1713.93 | 442.66 | 0 | 428.48 | 428.48 | 1285.45 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994267 | 2220 | B - Emergency Protective Measures | (PW# 2220) PW AEYAU-07 Em. Protective Measures | 0 | 4017DR-PR (4017DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
994266 | 2217 | B - Emergency Protective Measures | (PW# 2217) PW AESAL-06 Em. Protective Measures | 0 | 4017DR-PR (4017DR) | 3505.86 | 0 | 0 | 876.46 | 876.46 | 2629.4 | 75% | 2012-03-01 12:27 | 2012-03-02 15:17 | 0
994265 | 2216 | F - Utilities | (PW# 2216) AEARE04 Public Utilities | 0 | 4017DR-PR (4017DR) | 9889.27 | 0 | 0 | 2472.32 | 2472.32 | 7416.95 | 75% | 2012-03-21 22:04 | 2012-03-27 11:22 | 0
994264 | 2215 | B - Emergency Protective Measures | (PW# 2215) AEYAU-02 Protective Measures | 0 | 4017DR-PR (4017DR) | 1571.59 | 0 | 0 | 392.9 | 392.9 | 1178.69 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994263 | 2214 | F - Utilities | (PW# 2214) AEFAJ20 Public Utilities | 0 | 4017DR-PR (4017DR) | 6856.84 | 0 | 0 | 1714.21 | 1714.21 | 5142.63 | 75% | 2012-03-21 22:04 | 2012-03-27 11:22 | 0
994262 | 2213 | B - Emergency Protective Measures | (PW# 2213) AECAN13 Protective Measures | 0 | 4017DR-PR (4017DR) | 5147.53 | 0 | 0 | 1286.88 | 1286.88 | 3860.65 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994261 | 2212 | F - Utilities | (PW# 2212) AEADJ-02 Public Utilities | 0 | 4017DR-PR (4017DR) | 6087 | 0 | 0 | 1521.75 | 1521.75 | 4565.25 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994260 | 2211 | B - Emergency Protective Measures | (PW# 2211) AEPEN-01 Protective Measures | 0 | 4017DR-PR (4017DR) | 2283.93 | 0 | 0 | 570.98 | 570.98 | 1712.95 | 75% | 2012-03-01 12:27 | 2012-03-02 15:17 | 0
994259 | 2210 | B - Emergency Protective Measures | (PW# 2210) AEJAY01 Protective Measures | 0 | 4017DR-PR (4017DR) | 5558.82 | 0 | 0 | 1389.7 | 1389.7 | 4169.12 | 75% | 2012-03-01 12:27 | 2012-03-02 15:17 | 0
994258 | 2209 | F - Utilities | (PW# 2209) AEBAY-04 Utilities | 0 | 4017DR-PR (4017DR) | 6826.42 | 0 | 0 | 1706.6 | 1706.6 | 5119.82 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994257 | 2208 | F - Utilities | (PW# 2208) AECAR-14 Public Utilities | 0 | 4017DR-PR (4017DR) | 8192.14 | 0 | 0 | 2048.03 | 2048.03 | 6144.11 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994256 | 2207 | F - Utilities | (PW# 2207) AEYAU-12 Public Utilities | 0 | 4017DR-PR (4017DR) | 3293.84 | 0 | 0 | 823.46 | 823.46 | 2470.38 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994255 | 2206 | F - Utilities | (PW# 2206) AESIS-08 Public Utilities | 0 | 4017DR-PR (4017DR) | 4247.68 | 0 | 0 | 1061.92 | 1061.92 | 3185.76 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994254 | 2205 | B - Emergency Protective Measures | (PW# 2205) AESAL01 Protective Measures | 0 | 4017DR-PR (4017DR) | 3518.87 | 0 | 0 | 879.72 | 879.72 | 2639.15 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994253 | 2204 | B - Emergency Protective Measures | (PW# 2204) AESAL05 Emergency Protective Measures | 0 | 4017DR-PR (4017DR) | 1110.93 | 0 | 0 | 277.73 | 277.73 | 833.2 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994252 | 2203 | F - Utilities | (PW# 2203) AEFAJ-19 Public Utilities | 0 | 4017DR-PR (4017DR) | 2408.86 | 0 | 0 | 602.21 | 602.21 | 1806.65 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994251 | 2202 | F - Utilities | (PW# 2202) AEYAUU-05 Public Utilities | 0 | 4017DR-PR (4017DR) | 7099.79 | 0 | 0 | 1774.95 | 1774.95 | 5324.84 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994250 | 2201 | F - Utilities | (PW# 2201) AEVBA01 Public Utilities | 0 | 4017DR-PR (4017DR) | 7791.57 | 0 | 0 | 1947.89 | 1947.89 | 5843.68 | 75% | 2012-03-01 12:27 | 2012-03-02 15:17 | 0
994249 | 2200 | F - Utilities | (PW# 2200) AEGYB03 Public Utilities | 0 | 4017DR-PR (4017DR) | 6516.88 | 0 | 0 | 1629.22 | 1629.22 | 4887.66 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994248 | 2199 | F - Utilities | (PW# 2199) AEGUR07 Public Utilities | 0 | 4017DR-PR (4017DR) | 15976.84 | 0 | 0 | 3994.21 | 3994.21 | 11982.63 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994247 | 2197 | B - Emergency Protective Measures | (PW# 2197) AEARE-05 Protective Measures | 0 | 4017DR-PR (4017DR) | 2161 | 0 | 0 | 540.25 | 540.25 | 1620.75 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994246 | 2196 | B - Emergency Protective Measures | (PW# 2196) AEYAU-06 Protective Measures | 0 | 4017DR-PR (4017DR) | 1402.7 | 0 | 0 | 350.67 | 350.67 | 1052.03 | 75% | 2012-03-01 12:27 | 2012-03-02 15:17 | 0
994245 | 2195 | F - Utilities | (PW# 2195) AEBQT-06 Public Utilities | 0 | 4017DR-PR (4017DR) | 1641.76 | 462.22 | 0 | 410.44 | 410.44 | 1231.32 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994244 | 2191 | B - Emergency Protective Measures | (PW# 2191) AEYAU10 Protective Measure | 0 | 4017DR-PR (4017DR) | 3803.23 | 0 | 0 | 950.81 | 950.81 | 2852.42 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994243 | 2190 | B - Emergency Protective Measures | (PW# 2190) AESIS-07 Protective Measures | 0 | 4017DR-PR (4017DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
994242 | 2186 | B - Emergency Protective Measures | (PW# 2186) AECOA-02 Protective Measures | 0 | 4017DR-PR (4017DR) | 6657.01 | 0 | 0 | 1664.25 | 1664.25 | 4992.76 | 75% | 2012-03-01 12:27 | 2012-03-02 15:17 | 0
994241 | 2185 | B - Emergency Protective Measures | (PW# 2185) AEYAU04 Protective Measure | 0 | 4017DR-PR (4017DR) | 7095.99 | 0 | 0 | 1774 | 1774 | 5321.99 | 75% | 2012-03-01 12:27 | 2012-03-02 15:17 | 0
994240 | 2184 | F - Utilities | (PW# 2184) AEAIB-02 Utilities | 0 | 4017DR-PR (4017DR) | 15551.53 | 0 | 0 | 3887.88 | 3887.88 | 11663.65 | 75% | 2012-03-01 12:27 | 2012-03-02 15:17 | 0
994239 | 2183 | B - Emergency Protective Measures | (PW# 2183) AECAR03 Protective Measures | 0 | 4017DR-PR (4017DR) | 4400.78 | 0 | 0 | 1100.19 | 1100.19 | 3300.59 | 75% | 2012-03-01 12:27 | 2012-03-02 15:17 | 0
994238 | 2182 | B - Emergency Protective Measures | (PW# 2182) AESIS02 Protective Measures | 0 | 4017DR-PR (4017DR) | 2798.26 | 0 | 0 | 699.56 | 699.56 | 2098.7 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994237 | 2181 | F - Utilities | (PW# 2181) AEFAJ-15 Utilities | 0 | 4017DR-PR (4017DR) | 2576.39 | 0 | 0 | 644.1 | 644.1 | 1932.29 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994236 | 2180 | B - Emergency Protective Measures | (PW# 2180) AESIS06 Protective Measure | 0 | 4017DR-PR (4017DR) | 2358.19 | 0 | 0 | 589.55 | 589.55 | 1768.64 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994235 | 2179 | B - Emergency Protective Measures | (PW# 2179) AEARE03 Protective Measures | 0 | 4017DR-PR (4017DR) | 1708.9 | 0 | 0 | 427.22 | 427.22 | 1281.68 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994234 | 2178 | B - Emergency Protective Measures | (PW# 2178) AEAMOR01 Protective Measures | 0 | 4017DR-PR (4017DR) | 6264.02 | 0 | 0 | 1566 | 1566 | 4698.02 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994233 | 2177 | B - Emergency Protective Measures | (PW# 2177) AECAR06 Protective Measures | 0 | 4017DR-PR (4017DR) | 1924.91 | 0 | 0 | 481.23 | 481.23 | 1443.68 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994232 | 2176 | B - Emergency Protective Measures | (PW# 2176) AECOA-06 Public Utilities | 0 | 4017DR-PR (4017DR) | 16140.76 | 0 | 0 | 4035.19 | 4035.19 | 12105.57 | 75% | 2012-03-01 12:27 | 2012-03-02 15:17 | 0
994231 | 2175 | B - Emergency Protective Measures | (PW# 2175) AEPEN02 Protective Measure | 0 | 4017DR-PR (4017DR) | 4115.21 | 0 | 0 | 1028.8 | 1028.8 | 3086.41 | 75% | 2012-03-01 12:27 | 2012-03-02 15:17 | 0
994230 | 2174 | F - Utilities | (PW# 2174) AEBQT03 Public Utilities | 0 | 4017DR-PR (4017DR) | 5791.03 | 224.04 | 0 | 1447.76 | 1447.76 | 4343.27 | 75% | 2012-03-21 22:04 | 2012-03-27 11:22 | 0
994229 | 2173 | B - Emergency Protective Measures | (PW# 2173) AESIS01 Protective Measures | 0 | 4017DR-PR (4017DR) | 2837.43 | 0 | 0 | 709.36 | 709.36 | 2128.07 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994228 | 2172 | F - Utilities | (PW# 2172) AEGUR-04 Public Utilities | 0 | 4017DR-PR (4017DR) | 7481 | 0 | 0 | 1870.25 | 1870.25 | 5610.75 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994227 | 2171 | F - Utilities | (PW# 2171) AEFAJ4 Public Utilities | 0 | 4017DR-PR (4017DR) | 1902.54 | 0 | 0 | 475.63 | 475.63 | 1426.91 | 75% | 2012-03-01 12:27 | 2012-03-02 15:17 | 0
994226 | 2170 | F - Utilities | (PW# 2170) AEGUR06 Public Utilities | 0 | 4017DR-PR (4017DR) | 10468.69 | 0 | 0 | 2617.17 | 2617.17 | 7851.52 | 75% | 2012-03-01 12:27 | 2012-03-02 15:17 | 0
994225 | 2169 | F - Utilities | (PW# 2169) AEARE10 Public Buildings | 0 | 4017DR-PR (4017DR) | 9334.21 | 0 | 0 | 2333.55 | 2333.55 | 7000.66 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994224 | 2168 | F - Utilities | (PW# 2168) AEARE06 Public Utilities | 0 | 4017DR-PR (4017DR) | 6262.65 | 0 | 0 | 1565.66 | 1565.66 | 4696.99 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994223 | 2167 | B - Emergency Protective Measures | (PW# 2167) AEANA01 Protective Measures | 0 | 4017DR-PR (4017DR) | 5790.15 | 0 | 0 | 1447.54 | 1447.54 | 4342.61 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994222 | 2166 | F - Utilities | (PW# 2166) AEYAU-09 Public Utilities | 0 | 4017DR-PR (4017DR) | 3212.95 | 0 | 0 | 803.24 | 803.24 | 2409.71 | 75% | 2012-03-01 12:27 | 2012-03-02 15:17 | 0
994221 | 2165 | B - Emergency Protective Measures | (PW# 2165) AEADJ01 Protective Measures | 0 | 4017DR-PR (4017DR) | 1337.35 | 0 | 0 | 334.34 | 334.34 | 1003.01 | 75% | 2012-03-01 12:27 | 2012-03-02 15:17 | 0
994220 | 2164 | B - Emergency Protective Measures | (PW# 2164) AERGR06 Protective Measures | 0 | 4017DR-PR (4017DR) | 4800.53 | 0 | 0 | 1200.13 | 1200.13 | 3600.4 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994219 | 2163 | F - Utilities | (PW# 2163) AEARE02 Public Utilities | 0 | 4017DR-PR (4017DR) | 2708.91 | 0 | 0 | 677.23 | 677.23 | 2031.68 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994218 | 2162 | F - Utilities | (PW# 2162) AEGUR-02 Public Utilities | 0 | 4017DR-PR (4017DR) | 7674.5 | 0 | 0 | 1918.62 | 1918.62 | 5755.88 | 75% | 2012-03-01 12:27 | 2012-03-02 15:17 | 0
994217 | 2161 | F - Utilities | (PW# 2161) AEMOR-03 Public Utilities | 0 | 4017DR-PR (4017DR) | 2994.15 | 0 | 0 | 748.54 | 748.54 | 2245.61 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994216 | 2160 | F - Utilities | (PW# 2160) AEFAJ14 Public Utilities | 0 | 4017DR-PR (4017DR) | 4188.27 | 0 | 0 | 1047.07 | 1047.07 | 3141.2 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994215 | 2159 | B - Emergency Protective Measures | (PW# 2159) AECAR-04 Protective Measures | 0 | 4017DR-PR (4017DR) | 4349.86 | 0 | 0 | 1087.46 | 1087.46 | 3262.4 | 75% | 2012-03-01 12:27 | 2012-03-02 15:17 | 0
994214 | 2158 | B - Emergency Protective Measures | (PW# 2158) AECIA-01 Protective Measures | 0 | 4017DR-PR (4017DR) | 11224.53 | 0 | 0 | 2806.13 | 2806.13 | 8418.4 | 75% | 2012-03-01 12:27 | 2012-03-02 15:17 | 0
994213 | 2156 | F - Utilities | (PW# 2156) AEBAR02 Public Utilities | 0 | 4017DR-PR (4017DR) | 3210.33 | 0 | 0 | 802.58 | 802.58 | 2407.75 | 75% | 2012-03-01 12:27 | 2012-03-02 15:17 | 0
994212 | 2153 | B - Emergency Protective Measures | (PW# 2153) AECAR02 Protective Measure | 0 | 4017DR-PR (4017DR) | 2153.67 | 0 | 0 | 538.42 | 538.42 | 1615.25 | 75% | 2012-03-01 12:27 | 2012-03-02 15:17 | 0
994211 | 2152 | B - Emergency Protective Measures | (PW# 2152) AERGR03 Protective Measure | 0 | 4017DR-PR (4017DR) | 6761.28 | 0 | 0 | 1690.32 | 1690.32 | 5070.96 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994210 | 2151 | F - Utilities | (PW# 2151) AECIA02 Public Utilities | 0 | 4017DR-PR (4017DR) | 4262.38 | 0 | 0 | 1065.59 | 1065.59 | 3196.79 | 75% | 2012-03-01 12:27 | 2012-03-02 15:17 | 0
994209 | 2150 | B - Emergency Protective Measures | (PW# 2150) AECAR09 Protective Measures | 0 | 4017DR-PR (4017DR) | 3899.34 | 0 | 0 | 974.83 | 974.83 | 2924.51 | 75% | 2012-03-01 12:27 | 2012-03-02 15:17 | 0
994208 | 2149 | B - Emergency Protective Measures | (PW# 2149) AEGUR05 Protective Measures | 0 | 4017DR-PR (4017DR) | 8492.7 | 0 | 0 | 2123.17 | 2123.17 | 6369.53 | 75% | 2012-03-01 12:27 | 2012-03-02 15:17 | 0
994207 | 2148 | B - Emergency Protective Measures | (PW# 2148) AECAR-10 Protective Measures | 0 | 4017DR-PR (4017DR) | 2007.69 | 0 | 0 | 501.92 | 501.92 | 1505.77 | 75% | 2012-03-01 12:27 | 2012-03-02 15:17 | 0
994206 | 2147 | F - Utilities | (PW# 2147) AEFAJ-17 Public Utilities | 0 | 4017DR-PR (4017DR) | 2854.4 | 0 | 0 | 713.6 | 713.6 | 2140.8 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994205 | 2146 | F - Utilities | (PW# 2146) AELOI-09 Public Utilities | 0 | 4017DR-PR (4017DR) | 4668.65 | 0 | 0 | 1167.16 | 1167.16 | 3501.49 | 75% | 2012-03-01 12:27 | 2012-03-02 15:17 | 0
994204 | 2145 | F - Utilities | (PW# 2145) AEARE-13 Public Utilities | 0 | 4017DR-PR (4017DR) | 7336.79 | 0 | 0 | 1834.2 | 1834.2 | 5502.59 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994203 | 2144 | B - Emergency Protective Measures | (PW# 2144) AECAR-07 Protective Measures | 0 | 4017DR-PR (4017DR) | 4401.57 | 0 | 0 | 1100.39 | 1100.39 | 3301.18 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994202 | 2143 | B - Emergency Protective Measures | (PW# 2143) AEYAU03 Protective Measures | 0 | 4017DR-PR (4017DR) | 3982.07 | 0 | 0 | 995.52 | 995.52 | 2986.55 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994201 | 2140 | F - Utilities | (PW# 2140) AECAR-11 Public Utilities | 0 | 4017DR-PR (4017DR) | 5738.05 | 0 | 0 | 1434.51 | 1434.51 | 4303.54 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994200 | 2138 | F - Utilities | (PW# 2138) AEFAJ-16 Public Utilities | 0 | 4017DR-PR (4017DR) | 1100.32 | 92.16 | 0 | 275.08 | 275.08 | 825.24 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994199 | 2132 | F - Utilities | (PW# 2132) AEARE-08 Public Utilities | 0 | 4017DR-PR (4017DR) | 6675.73 | 0 | 0 | 1668.93 | 1668.93 | 5006.8 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994198 | 2131 | F - Utilities | (PW# 2131) AELOI-08 Public Utilities | 0 | 4017DR-PR (4017DR) | 4122.44 | 0 | 0 | 1030.61 | 1030.61 | 3091.83 | 75% | 2012-03-01 12:27 | 2012-03-02 15:17 | 0
994197 | 2128 | B - Emergency Protective Measures | (PW# 2128) AELOI-03 Protective Measures | 0 | 4017DR-PR (4017DR) | 4626.19 | 0 | 0 | 1156.55 | 1156.55 | 3469.64 | 75% | 2012-03-01 12:27 | 2012-03-02 15:17 | 0
994196 | 2127 | B - Emergency Protective Measures | (PW# 2127) AEARE-01 Protective Measures | 0 | 4017DR-PR (4017DR) | 1046.48 | 0 | 0 | 261.62 | 261.62 | 784.86 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994195 | 2126 | B - Emergency Protective Measures | (PW# 2126) AEARE-09 Protective Measures | 0 | 4017DR-PR (4017DR) | 1489.69 | 0 | 0 | 372.42 | 372.42 | 1117.27 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994194 | 2124 | B - Emergency Protective Measures | (PW# 2124) AEMOR-02 Protectives Measures | 0 | 4017DR-PR (4017DR) | 4300.66 | 0 | 0 | 1075.16 | 1075.16 | 3225.5 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994193 | 2123 | B - Emergency Protective Measures | (PW# 2123) AECOA-03 Protectives Measures | 0 | 4017DR-PR (4017DR) | 4813.8 | 0 | 0 | 1203.45 | 1203.45 | 3610.35 | 75% | 2012-03-01 12:27 | 2012-03-02 15:17 | 0
994192 | 2122 | B - Emergency Protective Measures | (PW# 2122) AELOI-07 Protective Measures | 0 | 4017DR-PR (4017DR) | 3281.97 | 0 | 0 | 820.49 | 820.49 | 2461.48 | 75% | 2012-03-01 12:27 | 2012-03-02 15:17 | 0
994191 | 2120 | B - Emergency Protective Measures | (PW# 2120) AELOI-04 Protective Measures | 0 | 4017DR-PR (4017DR) | 3522.99 | 0 | 0 | 880.75 | 880.75 | 2642.24 | 75% | 2012-03-01 12:27 | 2012-03-02 15:17 | 0
994190 | 2119 | B - Emergency Protective Measures | (PW# 2119) AECAR-01 Protective Measures | 0 | 4017DR-PR (4017DR) | 3566.11 | 0 | 0 | 891.53 | 891.53 | 2674.58 | 75% | 2012-03-01 12:27 | 2012-03-02 15:17 | 0
994189 | 2118 | B - Emergency Protective Measures | (PW# 2118) AELOI-02 Protective Measures | 0 | 4017DR-PR (4017DR) | 3823.52 | 0 | 0 | 955.88 | 955.88 | 2867.64 | 75% | 2012-03-01 12:27 | 2012-03-02 15:17 | 0
994188 | 2117 | B - Emergency Protective Measures | (PW# 2117) AERGR-04 Protective Measures | 0 | 4017DR-PR (4017DR) | 9248.18 | 0 | 0 | 2312.04 | 2312.04 | 6936.14 | 75% | 2012-03-01 12:27 | 2012-03-02 15:17 | 0
994187 | 2111 | F - Utilities | (PW# 2111) AEARE-11 Public Utilities | 0 | 4017DR-PR (4017DR) | 5578.75 | 0 | 0 | 1394.69 | 1394.69 | 4184.06 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994186 | 2107 | B - Emergency Protective Measures | (PW# 2107) AEGUR-01 Protective Measures | 0 | 4017DR-PR (4017DR) | 10878.67 | 0 | 0 | 2719.67 | 2719.67 | 8159 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994185 | 2078 | B - Emergency Protective Measures | (PW# 2078) AELOI-05 Protective Measures | 0 | 4017DR-PR (4017DR) | 3484.84 | 0 | 0 | 871.21 | 871.21 | 2613.63 | 75% | 2012-03-01 12:27 | 2012-03-02 15:17 | 0
994184 | 2077 | B - Emergency Protective Measures | (PW# 2077) AESAL03 Protective Measures | 0 | 4017DR-PR (4017DR) | 2560.21 | 0 | 0 | 640.05 | 640.05 | 1920.16 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994183 | 2076 | B - Emergency Protective Measures | (PW# 2076) AELOI-06 Protective Measures | 0 | 4017DR-PR (4017DR) | 1032.75 | 0 | 0 | 258.19 | 258.19 | 774.56 | 75% | 2012-03-01 12:27 | 2012-03-02 15:17 | 0
994182 | 2075 | B - Emergency Protective Measures | (PW# 2075) A -AECOA-01 Protective Measures | 0 | 4017DR-PR (4017DR) | 1982.36 | 0 | 0 | 495.59 | 495.59 | 1486.77 | 75% | 2012-03-01 12:27 | 2012-03-02 15:17 | 0
994181 | 2074 | B - Emergency Protective Measures | (PW# 2074) AERGR-05 Protective Measures | 0 | 4017DR-PR (4017DR) | 3038.85 | 0 | 0 | 759.71 | 759.71 | 2279.14 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994180 | 2072 | F - Utilities | (PW# 2072) AEFAJ-10 Public Utilities | 0 | 4017DR-PR (4017DR) | 5935.29 | 0 | 0 | 1483.82 | 1483.82 | 4451.47 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994179 | 2071 | B - Emergency Protective Measures | (PW# 2071) A -AESAL-02 Protective Measures | 0 | 4017DR-PR (4017DR) | 1223.79 | 0 | 0 | 305.95 | 305.95 | 917.84 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994178 | 2069 | B - Emergency Protective Measures | (PW# 2069) AEFAJ-13 Protective Measures | 0 | 4017DR-PR (4017DR) | 8549.98 | 0 | 0 | 2137.49 | 2137.49 | 6412.49 | 75% | 2012-03-01 12:27 | 2012-03-02 15:17 | 0
994177 | 2068 | B - Emergency Protective Measures | (PW# 2068) AEARE-12 Protective Measures | 0 | 4017DR-PR (4017DR) | 2109.63 | 0 | 0 | 527.41 | 527.41 | 1582.22 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994176 | 2067 | B - Emergency Protective Measures | (PW# 2067) AECAR-05 Protective Measures | 0 | 4017DR-PR (4017DR) | 8150.21 | 0 | 0 | 2037.55 | 2037.55 | 6112.66 | 75% | 2012-03-01 12:27 | 2012-03-02 15:17 | 0
994175 | 2062 | B - Emergency Protective Measures | (PW# 2062) AELO-101 Protective Measures | 0 | 4017DR-PR (4017DR) | 2157.86 | 0 | 0 | 539.46 | 539.46 | 1618.4 | 75% | 2012-03-01 12:27 | 2012-03-02 15:17 | 0
994174 | 2050 | B - Emergency Protective Measures | (PW# 2050) A- AECAN-12 Protective Measures | 0 | 4017DR-PR (4017DR) | 1428.29 | 0 | 0 | 357.07 | 357.07 | 1071.22 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994173 | 2035 | B - Emergency Protective Measures | (PW# 2035) AEARE07 Protective Measures | 0 | 4017DR-PR (4017DR) | 5766.98 | 0 | 0 | 1441.74 | 1441.74 | 4325.24 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994172 | 2031 | B - Emergency Protective Measures | (PW# 2031) AEFAJ-11 Protective Measures | 0 | 4017DR-PR (4017DR) | 3104.04 | 0 | 0 | 776.01 | 776.01 | 2328.03 | 75% | 2012-03-01 12:27 | 2012-03-02 15:17 | 0
994171 | 2030 | B - Emergency Protective Measures | (PW# 2030) AEFAJ-01 Protective Measures | 0 | 4017DR-PR (4017DR) | 18673.77 | 0 | 0 | 4668.44 | 4668.44 | 14005.33 | 75% | 2012-03-01 12:27 | 2012-03-02 15:17 | 0
994170 | 2029 | B - Emergency Protective Measures | (PW# 2029) AEFAJ03 Protective Measure | 0 | 4017DR-PR (4017DR) | 7591.84 | 0 | 0 | 1897.96 | 1897.96 | 5693.88 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994169 | 2026 | F - Utilities | (PW# 2026) AECEI05 Public Facilities | 0 | 4017DR-PR (4017DR) | 4024.36 | 0 | 0 | 1006.09 | 1006.09 | 3018.27 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994168 | 2025 | B - Emergency Protective Measures | (PW# 2025) AEFAJ07 Protective Measures | 0 | 4017DR-PR (4017DR) | 1303.82 | 0 | 0 | 325.95 | 325.95 | 977.87 | 75% | 2012-03-01 12:27 | 2012-03-02 15:17 | 0
994167 | 2024 | B - Emergency Protective Measures | (PW# 2024) AEFAJ09 Potective Measures | 0 | 4017DR-PR (4017DR) | 4768.8 | 0 | 0 | 1192.2 | 1192.2 | 3576.6 | 75% | 2012-03-01 12:27 | 2012-03-02 15:17 | 0
994166 | 2017 | B - Emergency Protective Measures | (PW# 2017) AESAL04 Protective Measures | 0 | 4017DR-PR (4017DR) | 2231.1 | 0 | 0 | 557.77 | 557.77 | 1673.33 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994165 | 2016 | B - Emergency Protective Measures | (PW# 2016) A-AELUQ-01 Em. Protective Measures | 0 | 4017DR-PR (4017DR) | 1204.14 | 0 | 0 | 301.03 | 301.03 | 903.11 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994164 | 2015 | B - Emergency Protective Measures | (PW# 2015) A-AEBAY-03 Em. Protective Measures | 0 | 4017DR-PR (4017DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
994163 | 2014 | B - Emergency Protective Measures | (PW# 2014) A-AELUQ-02 Em. Protective Measures | 0 | 4017DR-PR (4017DR) | 1464.72 | 0 | 0 | 366.18 | 366.18 | 1098.54 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994162 | 2009 | B - Emergency Protective Measures | (PW# 2009) AECEI03 Protective Measures | 0 | 4017DR-PR (4017DR) | 4021.34 | 0 | 0 | 1005.33 | 1005.33 | 3016.01 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994161 | 2008 | F - Utilities | (PW# 2008) AECAT02 Public Utilities | 0 | 4017DR-PR (4017DR) | 10293.62 | 0 | 0 | 2573.4 | 2573.4 | 7720.22 | 75% | 2012-03-21 22:04 | 2012-03-27 11:22 | 0
481726 | 19 | B - Emergency Protective Measures | (PW# 19) Protective Measures PREPA01 | 0 | 3306EM-PR (3306EM) | 9412.18 | 0 | 0 | 2353.04 | 2353.04 | 7059.14 | 75% |  | 2010-01-12 17:22 | 9412.18
994160 | 1794 | B - Emergency Protective Measures | (PW# 1794) AEAIB01 Protective Measures | 0 | 4017DR-PR (4017DR) | 11249.43 | 0 | 0 | 2812.36 | 2812.36 | 8437.07 | 75% | 2012-03-21 22:04 | 2012-03-27 11:22 | 0
476502 | 177 | F - Utilities | (PW# 177) PUBLIC UTILITIES | 1 | 1372DR-PR (1372DR) | 60445 | 0 | 0 | 15111.25 | 15111.25 | 45333.75 | 75% |  | 2008-12-02 19:11 | 0
476501 | 176 | F - Utilities | (PW# 176) PUBLIC UTILITIES | 1 | 1372DR-PR (1372DR) | 15786.61 | 0 | 0 | 3946.65 | 3946.65 | 11839.96 | 75% |  | 2008-12-02 19:11 | 0
476500 | 175 | F - Utilities | (PW# 175) PUBLIC UTILITIES | 0 | 1372DR-PR (1372DR) | 27020 | 0 | 0 | 6755 | 6755 | 20265 | 75% |  | 2001-06-26 14:56 | 0
994159 | 1745 | B - Emergency Protective Measures | (PW# 1745) AEVIE-01 Protective Measures | 0 | 4017DR-PR (4017DR) | 9594.09 | 0 | 0 | 2398.52 | 2398.52 | 7195.57 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994158 | 1732 | B - Emergency Protective Measures | (PW# 1732) AECAT01 Protective Measures | 0 | 4017DR-PR (4017DR) | 2368.36 | 0 | 0 | 592.09 | 592.09 | 1776.27 | 75% | 2012-03-21 22:04 | 2012-03-27 11:22 | 0
994157 | 1729 | B - Emergency Protective Measures | (PW# 1729) AEGUR-03 Protective Measures | 0 | 4017DR-PR (4017DR) | 4987.53 | 0 | 0 | 1246.88 | 1246.88 | 3740.65 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994156 | 1728 | F - Utilities | (PW# 1728) AELMA 02 Public Utilities | 0 | 4017DR-PR (4017DR) | 20130.06 | 0 | 0 | 5032.51 | 5032.51 | 15097.55 | 75% | 2012-03-21 22:04 | 2012-03-27 11:22 | 0
994155 | 1727 | F - Utilities | (PW# 1727) AELMA-04 Public Utilities | 0 | 4017DR-PR (4017DR) | 4978.86 | 0 | 0 | 1244.71 | 1244.71 | 3734.15 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
481927 | 172 | B - Emergency Protective Measures | (PW# 172) AEMANO7 Protective Measures | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
994154 | 1715 | F - Utilities | (PW# 1715) AEVIE-03 Public Utilities | 0 | 4017DR-PR (4017DR) | 8213.91 | 0 | 0 | 2053.48 | 2053.48 | 6160.43 | 75% | 2012-03-21 22:04 | 2012-03-27 11:22 | 0
994153 | 1713 | F - Utilities | (PW# 1713) AEBAY-02 Utilities | 0 | 4017DR-PR (4017DR) | 6834.84 | 0 | 0 | 1708.71 | 1708.71 | 5126.13 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
481926 | 171 | B - Emergency Protective Measures | (PW# 171) AEMAY-08 Protective Measures | 0 | 3326EM-PR (3326EM) | 3666.77 | 0 | 0 | 916.69 | 916.69 | 2750.08 | 75% |  | 2012-09-17 12:16 | 3666.77
994152 | 1706 | B - Emergency Protective Measures | (PW# 1706) AEGUR-10 Protective Measures | 0 | 4017DR-PR (4017DR) | 3759.06 | 0 | 0 | 939.76 | 939.76 | 2819.3 | 75% | 2012-03-21 22:04 | 2012-03-27 11:22 | 0
994151 | 1705 | F - Utilities | (PW# 1705) A-AELMA-03 Utilities | 0 | 4017DR-PR (4017DR) | 7594.62 | 0 | 0 | 1898.65 | 1898.65 | 5695.97 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
481925 | 170 | B - Emergency Protective Measures | (PW# 170) AEVAL-07 Protective Measures | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
994150 | 1699 | F - Utilities | (PW# 1699) A - AECEI-01 Public Utilities | 2 | 4017DR-PR (4017DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% | 2012-03-21 22:04 | 2014-02-04 16:36 | 0
481924 | 169 | B - Emergency Protective Measures | (PW# 169) AEPON-21 Protective Measures | 0 | 3326EM-PR (3326EM) | 2352.38 | 0 | 0 | 588.09 | 588.09 | 1764.29 | 75% |  | 2012-09-17 12:16 | 2352.38
481923 | 168 | B - Emergency Protective Measures | (PW# 168) AETBA-06 Protective Measures | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
481922 | 167 | B - Emergency Protective Measures | (PW# 167) AEPON-22 Protective Measures | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
481921 | 165 | F - Utilities | (PW# 165) AEVAL06 Public Utilities | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
481920 | 164 | B - Emergency Protective Measures | (PW# 164) AETAL07 Protective Measures | 0 | 3326EM-PR (3326EM) | 17679.59 | 0 | 0 | 4419.9 | 4419.9 | 13259.69 | 75% |  | 2012-03-22 11:45 | 17679.59
481918 | 163 | F - Utilities | (PW# 163) AETAL-06 Public Utilies | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
481919 | 162 | B - Emergency Protective Measures | (PW# 162) AEVAL05 Protective Measures | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
994149 | 1608 | F - Utilities | (PW# 1608) A- AECUL 02 Public Utilities | 0 | 4017DR-PR (4017DR) | 11169.62 | 0 | 0 | 2792.4 | 2792.4 | 8377.22 | 75% | 2012-03-21 22:04 | 2012-03-27 11:22 | 0
994148 | 1607 | F - Utilities | (PW# 1607) A- AEVIE02 Public Utilities | 0 | 4017DR-PR (4017DR) | 26612.38 | 0 | 0 | 6653.09 | 6653.09 | 19959.29 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
481917 | 160 | F - Utilities | (PW# 160) AETAL08 Public Utilities | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
481916 | 159 | B - Emergency Protective Measures | (PW# 159) AETAL09 Protective Measures | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
994147 | 1587 | B - Emergency Protective Measures | (PW# 1587) A- AECUL 01 Protective Measures | 0 | 4017DR-PR (4017DR) | 2235.94 | 0 | 0 | 558.98 | 558.98 | 1676.96 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
481915 | 157 | F - Utilities | (PW# 157) AESSE-08 Public Utilities | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
994146 | 1566 | F - Utilities | (PW# 1566) A- AEVIE06 Public Utilities | 0 | 4017DR-PR (4017DR) | 6743.1 | 0 | 0 | 1685.77 | 1685.77 | 5057.33 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994145 | 1564 | B - Emergency Protective Measures | (PW# 1564) A- AECAN08 Electrical Distribution System | 0 | 4017DR-PR (4017DR) | 2577.1 | 0 | 0 | 644.27 | 644.27 | 1932.83 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
481914 | 156 | B - Emergency Protective Measures | (PW# 156) AEPON-18 Protective Measures | 0 | 3326EM-PR (3326EM) | 3777.38 | 0 | 0 | 944.34 | 944.34 | 2833.04 | 75% |  | 2012-03-22 11:45 | 3777.38
481913 | 155 | F - Utilities | (PW# 155) AELAR03 Public Utilities | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
481912 | 154 | B - Emergency Protective Measures | (PW# 154) AELAJ01 Protective Measures | 0 | 3326EM-PR (3326EM) | 1023.1 | 0 | 0 | 255.77 | 255.77 | 767.33 | 75% |  | 2012-03-22 11:45 | 1023.1
994144 | 1535 | B - Emergency Protective Measures | (PW# 1535) A-AEVIE-05 Em. Protective Measures | 0 | 4017DR-PR (4017DR) | 3066.01 | 0 | 0 | 766.5 | 766.5 | 2299.51 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
481910 | 153 | F - Utilities | (PW# 153) AESSE-04 Public Utilities | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
481911 | 152 | F - Utilities | (PW# 152) AEAGL06 Public Utilities | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
481909 | 151 | B - Emergency Protective Measures | (PW# 151) AEMAY-03 Protective Measures | 0 | 3326EM-PR (3326EM) | 13423.65 | 0 | 0 | 3355.91 | 3355.91 | 10067.74 | 75% |  | 2012-03-22 11:45 | 13423.65
481908 | 150 | B - Emergency Protective Measures | (PW# 150) AEMAY-04 Protective Measures | 0 | 3326EM-PR (3326EM) | 4770.98 | 0 | 0 | 1192.74 | 1192.74 | 3578.24 | 75% |  | 2012-03-22 11:45 | 4770.98
994143 | 1493 | B - Emergency Protective Measures | (PW# 1493) A-AELMA-01 Em. Protective Measures | 0 | 4017DR-PR (4017DR) | 1618.66 | 0 | 0 | 404.66 | 404.66 | 1214 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
481903 | 149 | B - Emergency Protective Measures | (PW# 149) AEMAY-02 Protective Measures | 0 | 3326EM-PR (3326EM) | 1600.18 | 0 | 0 | 400.04 | 400.04 | 1200.14 | 75% |  | 2012-03-22 11:45 | 1600.18
481907 | 148 | B - Emergency Protective Measures | (PW# 148) AEAGL-09 Protective Measures | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
481906 | 147 | F - Utilities | (PW# 147) AEAGL-05 Public Utilities | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
481905 | 146 | B - Emergency Protective Measures | (PW# 146) AESGE-06 Protective Measures | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
481904 | 145 | B - Emergency Protective Measures | (PW# 145) AESGE-01 Protective Measures | 0 | 3326EM-PR (3326EM) | 5984.82 | 0 | 0 | 1496.2 | 1496.2 | 4488.62 | 75% |  | 2012-03-22 11:45 | 5984.82
481901 | 144 | B - Emergency Protective Measures | (PW# 144) AELAR-01 Protective Measures | 0 | 3326EM-PR (3326EM) | 7031.47 | 0 | 0 | 1757.87 | 1757.87 | 5273.6 | 75% |  | 2012-03-22 11:45 | 7031.47
481902 | 143 | B - Emergency Protective Measures | (PW# 143) AEPON-19 Protective Measures | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
994142 | 1426 | F - Utilities | (PW# 1426) AERGR-02 Utilities | 0 | 4017DR-PR (4017DR) | 14561.78 | 0 | 0 | 3640.44 | 3640.44 | 10921.34 | 75% | 2012-03-01 12:27 | 2012-03-02 15:17 | 0
481899 | 142 | F - Utilities | (PW# 142) AEMAY-07 Public Utilities | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
481900 | 141 | F - Utilities | (PW# 141) AEPON-20 Public Utilities | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
481895 | 140 | B - Emergency Protective Measures | (PW# 140) AECABO-02 Protective Measures | 0 | 3326EM-PR (3326EM) | 4803.25 | 0 | 0 | 1200.81 | 1200.81 | 3602.44 | 75% |  | 2012-03-22 11:45 | 4803.25
994141 | 1398 | B - Emergency Protective Measures | (PW# 1398) A- AECAN07 Protective Measures | 0 | 4017DR-PR (4017DR) | 1069.78 | 0 | 0 | 267.44 | 267.44 | 802.34 | 75% | 2012-03-01 12:27 | 2012-03-02 15:17 | 0
994140 | 1395 | B - Emergency Protective Measures | (PW# 1395) A-AERG01 Em. Protective Measures | 0 | 4017DR-PR (4017DR) | 5720.3 | 0 | 0 | 1430.07 | 1430.07 | 4290.23 | 75% | 2012-03-01 12:27 | 2012-03-02 15:17 | 0
994139 | 1393 | F - Utilities | (PW# 1393) A- AEVAB02 Public Utilities | 0 | 4017DR-PR (4017DR) | 3601.74 | 0 | 0 | 900.43 | 900.43 | 2701.31 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
994138 | 1392 | B - Emergency Protective Measures | (PW# 1392) A-AECAN10 Protective Measures | 0 | 4017DR-PR (4017DR) | 4151.82 | 0 | 0 | 1037.95 | 1037.95 | 3113.87 | 75% | 2012-03-01 12:27 | 2012-03-02 15:17 | 0
481898 | 139 | B - Emergency Protective Measures | (PW# 139) AESSE-07 Protective Measures | 0 | 3326EM-PR (3326EM) | 1203.37 | 0 | 0 | 300.84 | 300.84 | 902.53 | 75% |  | 2012-03-22 11:45 | 1203.37
481897 | 138 | B - Emergency Protective Measures | (PW# 138) AEAGL-08 Protective Measures | 0 | 3326EM-PR (3326EM) | 3696.5 | 0 | 0 | 924.12 | 924.12 | 2772.38 | 75% |  | 2012-03-22 11:45 | 3696.5
481896 | 137 | B - Emergency Protective Measures | (PW# 137) AEAGL-07 Protective Measures | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
481888 | 136 | F - Utilities | (PW# 136) AEHOR-02 Public Utilities | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
481887 | 135 | B - Emergency Protective Measures | (PW# 135) AEHOR-01 Protective Measures | 0 | 3326EM-PR (3326EM) | 1546.04 | 0 | 0 | 386.51 | 386.51 | 1159.53 | 75% |  | 2012-03-22 11:45 | 1546.04
481890 | 134 | B - Emergency Protective Measures | (PW# 134) AEHOR-03 Protective Measures | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
481894 | 133 | B - Emergency Protective Measures | (PW# 133) AESSE-05 Protective Measures | 0 | 3326EM-PR (3326EM) | 3780.86 | 0 | 0 | 945.21 | 945.21 | 2835.65 | 75% |  | 2012-03-22 11:45 | 3780.86
481893 | 132 | B - Emergency Protective Measures | (PW# 132) AEMAY-05 Protective Measures | 0 | 3326EM-PR (3326EM) | 9492.56 | 0 | 0 | 2373.14 | 2373.14 | 7119.42 | 75% |  | 2012-03-22 11:45 | 9492.56
481891 | 131 | B - Emergency Protective Measures | (PW# 131) AEMAY06 Protective Measures | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
994137 | 1309 | F - Utilities | (PW# 1309) A - AEBAY-01 Public Utilities | 0 | 4017DR-PR (4017DR) | 14633.11 | 0 | 0 | 3658.28 | 3658.28 | 10974.83 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
481892 | 130 | B - Emergency Protective Measures | (PW# 130) AEMAY-01 Protective Measures | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
481889 | 129 | F - Utilities | (PW# 129) AELAR-02 Public Utilities | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
994136 | 1287 | B - Emergency Protective Measures | (PW# 1287) A- AECAN03 Protective Measures | 0 | 4017DR-PR (4017DR) | 6267.27 | 0 | 0 | 1566.82 | 1566.82 | 4700.45 | 75% | 2012-03-08 21:50 | 2012-03-09 20:45 | 0
481886 | 128 | B - Emergency Protective Measures | (PW# 128) AESSE-06 Protective Measures | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
481881 | 127 | B - Emergency Protective Measures | (PW# 127) AESGE02 Protective Measures | 0 | 3326EM-PR (3326EM) | 4148.87 | 0 | 0 | 1037.22 | 1037.22 | 3111.65 | 75% |  | 2012-03-22 11:45 | 4148.87
994135 | 1261 | F - Utilities | (PW# 1261) A- AECAN02 Public Utilities | 0 | 4017DR-PR (4017DR) | 2910.59 | 0 | 0 | 727.65 | 727.65 | 2182.94 | 75% | 2012-03-01 12:27 | 2012-03-02 15:17 | 0
481885 | 126 | F - Utilities | (PW# 126) AETAL-05 Public Utilities | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
994134 | 1257 | B - Emergency Protective Measures | (PW# 1257) A- AECAN06 - Protective Meaures | 0 | 4017DR-PR (4017DR) | 2940.38 | 0 | 0 | 735.09 | 735.09 | 2205.29 | 75% | 2012-03-01 12:27 | 2012-03-02 15:17 | 0
481884 | 125 | B - Emergency Protective Measures | (PW# 125) AESGE-05 Protective Measures | 0 | 3326EM-PR (3326EM) | 1822.8 | 0 | 0 | 455.7 | 455.7 | 1367.1 | 75% |  | 2012-03-22 11:45 | 1822.8
481883 | 124 | B - Emergency Protective Measures | (PW# 124) AECAB-01 Protective Measures | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
481882 | 123 | B - Emergency Protective Measures | (PW# 123) AELAJ-03 Protective Measures | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
481880 | 122 | F - Utilities | (PW# 122) AELAJ-02 Public Utilities | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
481876 | 121 | B - Emergency Protective Measures | (PW# 121) AEMOC-05 Protective Measures | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
480175 | 1200 | B - Emergency Protective Measures | (PW# 1200) Protective Measures Prepa20 | 0 | 1798DR-PR (1798DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
481877 | 120 | B - Emergency Protective Measures | (PW# 120) AEMOC-04 Protective Measures | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
480177 | 1199 | B - Emergency Protective Measures | (PW# 1199) Protective Measures - Prepa22 | 1 | 1798DR-PR (1798DR) | 13377.59 | 0 | 0 | 3344.4 | 3344.4 | 10033.19 | 75% |  | 2011-10-12 11:48 | 13377.59
480176 | 1198 | F - Utilities | (PW# 1198) Public Utilities - Prepa21 | 0 | 1798DR-PR (1798DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
480178 | 1197 | F - Utilities | (PW# 1197) Public Utilities Prepa23 | 1 | 1798DR-PR (1798DR) | 37542.73 | 0 | 0 | 9385.68 | 9385.68 | 28157.05 | 75% |  | 2011-10-12 11:48 | 37542.73
480179 | 1196 | B - Emergency Protective Measures | (PW# 1196) Protective Measures - Prepa19 | 0 | 1798DR-PR (1798DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
480180 | 1195 | F - Utilities | (PW# 1195) Public Utilities - Prepa10 | 1 | 1798DR-PR (1798DR) | 31230.42 | 0 | 0 | 7807.6 | 7807.6 | 23422.82 | 75% |  | 2011-12-15 16:32 | 31230.42
480173 | 1193 | B - Emergency Protective Measures | (PW# 1193) Protective Measures Prepa14 | 0 | 1798DR-PR (1798DR) | 212832.67 | 0 | 0 | 53208.17 | 53208.17 | 159624.5 | 75% |  | 2010-06-03 20:56 | 212832.67
480174 | 1192 | B - Emergency Protective Measures | (PW# 1192) Protective Measures Prepa15 | 0 | 1798DR-PR (1798DR) | 29152.01 | 0 | 0 | 7288 | 7288 | 21864.01 | 75% |  | 2010-06-03 20:56 | 29152.01
480172 | 1191 | F - Utilities | (PW# 1191) Public Utilities Prepa12 | 0 | 1798DR-PR (1798DR) | 246222.48 | 0 | 0 | 61555.62 | 61555.62 | 184666.86 | 75% |  | 2010-08-13 14:43 | 246222.48
480171 | 1190 | F - Utilities | (PW# 1190) Public Utilities Prepa11 | 0 | 1798DR-PR (1798DR) | 233703.32 | 0 | 0 | 58425.83 | 58425.83 | 175277.49 | 75% |  | 2010-08-13 14:43 | 233703.32
481879 | 119 | B - Emergency Protective Measures | (PW# 119) AESGE-04 Protective Measures | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
480170 | 1188 | F - Utilities | (PW# 1188) Public Utilities Prepa13 | 0 | 1798DR-PR (1798DR) | 60865.82 | 0 | 0 | 15216.45 | 15216.45 | 45649.37 | 75% |  | 2010-08-13 14:43 | 60865.82
481878 | 118 | B - Emergency Protective Measures | (PW# 118) AEMOC-06 Protective Measures | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
480169 | 1175 | F - Utilities | (PW# 1175) Public Utilities PREPA-16 | 1 | 1798DR-PR (1798DR) | 139911.04 | 0 | 0 | 34977.76 | 34977.76 | 104933.28 | 75% |  | 2014-11-12 17:56 | 139911.04
481875 | 117 | F - Utilities | (PW# 117) AESGE03 Public Utilities | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
481874 | 115 | B - Emergency Protective Measures | (PW# 115) AEMAN-06 Protective Measures | 0 | 3326EM-PR (3326EM) | 2414.21 | 0 | 0 | 603.55 | 603.55 | 1810.66 | 75% |  | 2012-03-22 11:45 | 2414.21
481873 | 114 | B - Emergency Protective Measures | (PW# 114) AEQUE-05 Protective Measures | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
481872 | 113 | B - Emergency Protective Measures | (PW# 113) AEPON-12 Protective Measures | 0 | 3326EM-PR (3326EM) | 6668.31 | 0 | 0 | 1667.08 | 1667.08 | 5001.23 | 75% |  | 2012-03-22 11:45 | 6668.31
481869 | 112 | B - Emergency Protective Measures | (PW# 112) AEPON-16 Protective Measures | 0 | 3326EM-PR (3326EM) | 8016.7 | 0 | 0 | 2004.17 | 2004.17 | 6012.53 | 75% |  | 2012-03-22 11:45 | 8016.7
974925 | 1119 | F - Utilities | (PW# 1119) AEE 047 Utilities | 0 | 1946DR-PR (1946DR) | 1205.19 | 0 | 0 | 301.3 | 301.3 | 903.89 | 75% | 2011-08-09 14:10 | 2011-10-12 11:50 | 0
974924 | 1118 | F - Utilities | (PW# 1118) AEE 072 Utilities | 0 | 1946DR-PR (1946DR) | 1311.71 | 0 | 0 | 327.93 | 327.93 | 983.78 | 75% | 2011-08-09 14:10 | 2011-10-12 11:50 | 0
974923 | 1117 | F - Utilities | (PW# 1117) AEE 045 Utilities | 0 | 1946DR-PR (1946DR) | 3465.94 | 0 | 0 | 866.48 | 866.48 | 2599.46 | 75% | 2011-08-09 14:10 | 2011-10-12 11:50 | 0
974922 | 1116 | F - Utilities | (PW# 1116) AEE 046 Utilities | 0 | 1946DR-PR (1946DR) | 2870.16 | 0 | 0 | 717.54 | 717.54 | 2152.62 | 75% | 2011-08-09 14:10 | 2011-10-12 11:50 | 0
974921 | 1115 | F - Utilities | (PW# 1115) AEE-070 Utilities | 0 | 1946DR-PR (1946DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
974920 | 1114 | F - Utilities | (PW# 1114) AEE 058 Utilities | 0 | 1946DR-PR (1946DR) | 1539.5 | 0 | 0 | 384.87 | 384.87 | 1154.63 | 75% | 2011-08-09 14:10 | 2011-10-12 11:50 | 0
974919 | 1113 | F - Utilities | (PW# 1113) AEE-078 Utilities | 0 | 1946DR-PR (1946DR) | 1399.82 | 0 | 0 | 349.95 | 349.95 | 1049.87 | 75% | 2011-08-09 14:10 | 2011-10-12 11:50 | 0
481871 | 111 | B - Emergency Protective Measures | (PW# 111) AEPON14 Protective Measures | 0 | 3326EM-PR (3326EM) | 16876.61 | 0 | 0 | 4219.15 | 4219.15 | 12657.46 | 75% |  | 2012-03-22 11:45 | 16876.61
480168 | 1109 | F - Utilities | (PW# 1109) Public Utilities PREPA-18 | 1 | 1798DR-PR (1798DR) | 247987.4 | 0 | 0 | 61996.85 | 61996.85 | 185990.55 | 75% |  | 2014-10-28 18:32 | 247987.4
974918 | 1104 | F - Utilities | (PW# 1104) AEE 048 Utilities | 0 | 1946DR-PR (1946DR) | 1445.27 | 0 | 0 | 361.32 | 361.32 | 1083.95 | 75% | 2011-08-09 14:10 | 2011-10-12 11:50 | 0
974917 | 1103 | F - Utilities | (PW# 1103) AEE 073 Utilities | 0 | 1946DR-PR (1946DR) | 2593.89 | 0 | 0 | 648.47 | 648.47 | 1945.42 | 75% | 2011-08-09 14:10 | 2011-10-12 11:50 | 0
477965 | 1100 | C - Roads and Bridges | (PW# 1100) ROADS AND BRIDGES | 1 | 1552DR-PR (1552DR) | 25647.77 | 0 | 0 | 6411.94 | 6411.94 | 19235.83 | 75% |  | 2013-04-22 15:26 | 0
481870 | 110 | B - Emergency Protective Measures | (PW# 110) AEPON08 Protective Measures | 0 | 3326EM-PR (3326EM) | 1975.93 | 0 | 0 | 493.98 | 493.98 | 1481.95 | 75% |  | 2012-03-22 11:45 | 1975.93
481800 | 11 | B - Emergency Protective Measures | (PW# 11) AEFLO-01 Protective Measures | 0 | 3326EM-PR (3326EM) | 6317.22 | 0 | 0 | 1579.3 | 1579.3 | 4737.92 | 75% |  | 2012-03-22 11:45 | 6317.22
477964 | 1093 | B - Emergency Protective Measures | (PW# 1093) EMERGENCY PROTECTIVE MEASURES | 1 | 1552DR-PR (1552DR) | 146648.82 | 0 | 0 | 36662.2 | 36662.2 | 109986.62 | 75% |  | 2013-04-22 15:26 | 0
477963 | 1092 | B - Emergency Protective Measures | (PW# 1092) EMERGENCY PROTECTIVE MEASURES | 1 | 1552DR-PR (1552DR) | 132200.9 | 0 | 0 | 0 | 0 | 132200.9 | 100% |  | 2013-04-22 15:26 | 0
477962 | 1091 | F - Utilities | (PW# 1091) PUBLIC UTILITIES | 1 | 1552DR-PR (1552DR) | 7298675.25 | 0 | 0 | 1824668.82 | 1824668.82 | 5474006.43 | 75% |  | 2013-04-22 15:26 | 0
481868 | 109 | B - Emergency Protective Measures | (PW# 109) APON15 Protective Measures | 0 | 3326EM-PR (3326EM) | 2402.63 | 0 | 0 | 600.66 | 600.66 | 1801.97 | 75% |  | 2012-03-22 11:45 | 2402.63
480167 | 1088 | B - Emergency Protective Measures | (PW# 1088) Protective Measures - Prepa-5 | 0 | 1798DR-PR (1798DR) | 14605.05 | 0 | 0 | 3651.26 | 3651.26 | 10953.79 | 75% |  | 2009-08-17 19:30 | 14605.05
480166 | 1087 | B - Emergency Protective Measures | (PW# 1087) Protective Measures Prepa17 | 1 | 1798DR-PR (1798DR) | 128105.76 | 0 | 0 | 32026.43 | 32026.43 | 96079.33 | 75% |  | 2014-11-12 17:56 | 128105.76
477961 | 1086 | F - Utilities | (PW# 1086) PUBLIC UTILITIES | 1 | 1552DR-PR (1552DR) | 948626.54 | 0 | 0 | 237156.64 | 237156.64 | 711469.9 | 75% |  | 2013-04-22 15:26 | 0
481866 | 108 | B - Emergency Protective Measures | (PW# 108) AEPON01 Portective Measures | 0 | 3326EM-PR (3326EM) | 3190.85 | 0 | 0 | 797.71 | 797.71 | 2393.14 | 75% |  | 2012-03-22 11:45 | 3190.85
477960 | 1079 | F - Utilities | (PW# 1079) PUBLIC UTILITIES | 1 | 1552DR-PR (1552DR) | 495411.66 | 0 | 0 | 123852.91 | 123852.91 | 371558.75 | 75% |  | 2013-04-22 15:26 | 0
477959 | 1078 | A - Debris Removal | (PW# 1078) DEBRIS REMOVAL | 0 | 1552DR-PR (1552DR) | 53000 | 0 | 0 | 13250 | 13250 | 39750 | 75% |  | 2005-02-28 19:25 | 0
477958 | 1075 | F - Utilities | (PW# 1075) PUBLIC UTILITIES | 0 | 1552DR-PR (1552DR) | 103266.27 | 0 | 0 | 25816.57 | 25816.57 | 77449.7 | 75% |  | 2005-03-29 13:58 | 0
477957 | 1074 | B - Emergency Protective Measures | (PW# 1074) EMERGENCY PROTECTIVE MEASURES | 1 | 1552DR-PR (1552DR) | 165181.67 | 0 | 0 | 41295.41 | 41295.41 | 123886.26 | 75% |  | 2013-04-22 15:26 | 0
477956 | 1071 | B - Emergency Protective Measures | (PW# 1071) EMERGENCY PROTECTIVE MEASURES | 1 | 1552DR-PR (1552DR) | 597415.22 | 0 | 0 | 0 | 0 | 597415.22 | 100% |  | 2013-04-22 15:26 | 0
481867 | 107 | B - Emergency Protective Measures | (PW# 107) AESSE-01 Protective Measures | 0 | 3326EM-PR (3326EM) | 2361.89 | 0 | 0 | 590.47 | 590.47 | 1771.42 | 75% |  | 2012-03-22 11:45 | 2361.89
477955 | 1068 | F - Utilities | (PW# 1068) PUBLIC UTILITIES | 0 | 1552DR-PR (1552DR) | 786732.6 | 0 | 0 | 196683.15 | 196683.15 | 590049.45 | 75% |  | 2005-02-28 19:25 | 0
481865 | 106 | B - Emergency Protective Measures | (PW# 106) AEPON-05 Protective Measures | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
974916 | 1052 | B - Emergency Protective Measures | (PW# 1052) AEE080 - Protective Measures | 0 | 1946DR-PR (1946DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
974915 | 1051 | F - Utilities | (PW# 1051) AEE068 - Utilities | 0 | 1946DR-PR (1946DR) | 1997.95 | 0 | 0 | 499.49 | 499.49 | 1498.46 | 75% | 2011-08-09 14:10 | 2011-10-12 11:50 | 0
974914 | 1050 | F - Utilities | (PW# 1050) AEE083 - Utilities | 0 | 1946DR-PR (1946DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
974913 | 1049 | B - Emergency Protective Measures | (PW# 1049) AEE069 - Protective Measures | 0 | 1946DR-PR (1946DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
480165 | 1048 | D - Water Control Facilities | (PW# 1048) Water Facilities - PREPA-09 | 0 | 1798DR-PR (1798DR) | 19338.91 | 0 | 0 | 4834.73 | 4834.73 | 14504.18 | 75% |  | 2009-09-17 16:59 | 19338.91
974912 | 1048 | F - Utilities | (PW# 1048) AEE049 - Utilities | 0 | 1946DR-PR (1946DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
974911 | 1047 | F - Utilities | (PW# 1047) AEE084 - Utilities | 0 | 1946DR-PR (1946DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
974910 | 1045 | B - Emergency Protective Measures | (PW# 1045) AEE082 - Protective Measures | 0 | 1946DR-PR (1946DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
974909 | 1044 | F - Utilities | (PW# 1044) AEE081 - Utilities | 0 | 1946DR-PR (1946DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
974908 | 1043 | F - Utilities | (PW# 1043) AEE044 - Utilities | 0 | 1946DR-PR (1946DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
974907 | 1042 | B - Emergency Protective Measures | (PW# 1042) AEE085 - Protective Measures | 0 | 1946DR-PR (1946DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
974906 | 1040 | F - Utilities | (PW# 1040) AEE033 - Utilities | 0 | 1946DR-PR (1946DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
481864 | 104 | B - Emergency Protective Measures | (PW# 104) AEPON17 Protective Measures | 0 | 3326EM-PR (3326EM) | 10713.45 | 0 | 0 | 2678.36 | 2678.36 | 8035.09 | 75% |  | 2012-03-22 11:45 | 10713.45
974905 | 1039 | F - Utilities | (PW# 1039) AEE036 - Utilities | 0 | 1946DR-PR (1946DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
974904 | 1038 | F - Utilities | (PW# 1038) AEE037 - Utilities | 0 | 1946DR-PR (1946DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
974903 | 1033 | F - Utilities | (PW# 1033) AEE 067 Public Utilities | 0 | 1946DR-PR (1946DR) | 4891.34 | 0 | 0 | 1222.83 | 1222.83 | 3668.51 | 75% | 2011-08-09 14:10 | 2011-10-12 11:50 | 0
477954 | 1032 | A - Debris Removal | (PW# 1032) DEBRIS REMOVAL | 1 | 1552DR-PR (1552DR) | 90473.47 | 0 | 0 | 22618.37 | 22618.37 | 67855.1 | 75% |  | 2013-04-22 15:26 | 0
477953 | 1031 | A - Debris Removal | (PW# 1031) DEBRIS REMOVAL | 1 | 1552DR-PR (1552DR) | 53207.5 | 0 | 0 | 0 | 0 | 53207.5 | 100% |  | 2013-04-22 15:26 | 0
974902 | 1030 | B - Emergency Protective Measures | (PW# 1030) AEE077 Protective Measures | 0 | 1946DR-PR (1946DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
481861 | 103 | B - Emergency Protective Measures | (PW# 103) AEFLO-02 Protective Measures | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
974901 | 1029 | B - Emergency Protective Measures | (PW# 1029) AEE 076 Protective Measures | 0 | 1946DR-PR (1946DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
477952 | 1028 | A - Debris Removal | (PW# 1028) DEBRIS REMOVAL | 0 | 1552DR-PR (1552DR) | 66380 | 0 | 0 | 16595 | 16595 | 49785 | 75% |  | 2005-03-16 20:54 | 0
974900 | 1028 | F - Utilities | (PW# 1028) AEE079 Utilities | 0 | 1946DR-PR (1946DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
477951 | 1027 | A - Debris Removal | (PW# 1027) DEBRIS REMOVAL | 0 | 1552DR-PR (1552DR) | 17320 | 0 | 0 | 0 | 0 | 17320 | 100% |  | 2005-03-16 20:54 | 0
480163 | 1026 | D - Water Control Facilities | (PW# 1026) Water Facilities PREPA-08 | 0 | 1798DR-PR (1798DR) | 10460.7 | 351.2 | 0 | 2615.17 | 2615.17 | 7845.53 | 75% |  | 2009-10-29 18:50 | 10460.7
974899 | 1025 | F - Utilities | (PW# 1025) AEE065 Utilities | 0 | 1946DR-PR (1946DR) | 4921.27 | 0 | 0 | 1230.32 | 1230.32 | 3690.95 | 75% | 2011-08-09 14:10 | 2011-10-12 11:50 | 0
974898 | 1024 | F - Utilities | (PW# 1024) AEE075 Public Utilities | 0 | 1946DR-PR (1946DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
974897 | 1023 | F - Utilities | (PW# 1023) AEE059 Public Utilities | 0 | 1946DR-PR (1946DR) | 4401.99 | 0 | 0 | 1100.5 | 1100.5 | 3301.49 | 75% | 2011-08-09 14:10 | 2011-10-12 11:50 | 0
974896 | 1022 | F - Utilities | (PW# 1022) AEE060 Public Utilities | 0 | 1946DR-PR (1946DR) | 3255.91 | 0 | 0 | 813.98 | 813.98 | 2441.93 | 75% | 2011-08-09 14:10 | 2011-10-12 11:50 | 0
974895 | 1021 | F - Utilities | (PW# 1021) AEE066 Utilities | 0 | 1946DR-PR (1946DR) | 3697.4 | 0 | 0 | 924.35 | 924.35 | 2773.05 | 75% | 2011-08-09 14:10 | 2011-10-12 11:50 | 0
974894 | 1020 | F - Utilities | (PW# 1020) AEE074 Public Utilities | 0 | 1946DR-PR (1946DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
481862 | 102 | F - Utilities | (PW# 102) AEBCL-02 Public Utilities | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
974893 | 1019 | F - Utilities | (PW# 1019) AEE071 Public Utilities | 0 | 1946DR-PR (1946DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
974892 | 1018 | B - Emergency Protective Measures | (PW# 1018) AEE064 Protective Measures | 0 | 1946DR-PR (1946DR) | 4731.4 | 0 | 0 | 1182.85 | 1182.85 | 3548.55 | 75% | 2011-08-09 14:10 | 2011-10-12 11:50 | 0
974891 | 1017 | F - Utilities | (PW# 1017) PW AEE070 Utilities | 0 | 1946DR-PR (1946DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
974890 | 1016 | F - Utilities | (PW# 1016) AEE057 Utilities | 0 | 1946DR-PR (1946DR) | 2661.91 | 0 | 0 | 665.48 | 665.48 | 1996.43 | 75% | 2011-08-09 14:10 | 2011-10-12 11:50 | 0
480164 | 1014 | D - Water Control Facilities | (PW# 1014) Water Faclities Prepa06 | 0 | 1798DR-PR (1798DR) | 14552.62 | 0 | 0 | 3638.15 | 3638.15 | 10914.47 | 75% |  | 2009-08-17 19:30 | 14552.62
974889 | 1013 | A - Debris Removal | (PW# 1013) AEE055 Debris Removal | 0 | 1946DR-PR (1946DR) | 3613.94 | 0 | 0 | 903.48 | 903.48 | 2710.46 | 75% | 2011-08-09 14:10 | 2011-10-12 11:50 | 0
974888 | 1012 | B - Emergency Protective Measures | (PW# 1012) AEE056 Protective Measures | 0 | 1946DR-PR (1946DR) | 1977.11 | 0 | 0 | 494.28 | 494.28 | 1482.83 | 75% | 2011-08-09 14:10 | 2011-10-12 11:50 | 0
974887 | 1011 | F - Utilities | (PW# 1011) AEE054 Public Utilities | 0 | 1946DR-PR (1946DR) | 2012.15 | 0 | 0 | 503.04 | 503.04 | 1509.11 | 75% | 2011-08-09 14:10 | 2011-10-12 11:50 | 0
974886 | 1010 | F - Utilities | (PW# 1010) AEE053 Public Utilities | 0 | 1946DR-PR (1946DR) | 2045.34 | 0 | 0 | 511.33 | 511.33 | 1534.01 | 75% | 2011-08-09 14:10 | 2011-10-12 11:50 | 0
481863 | 101 | B - Emergency Protective Measures | (PW# 101) AEMOC-03 Protective Measures | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
974885 | 1009 | F - Utilities | (PW# 1009) AEE050 Public Utilities | 0 | 1946DR-PR (1946DR) | 1905.64 | 0 | 0 | 476.41 | 476.41 | 1429.23 | 75% | 2011-08-09 14:10 | 2011-10-12 11:50 | 0
974884 | 1008 | F - Utilities | (PW# 1008) AEE062 Public Utilities | 0 | 1946DR-PR (1946DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
974883 | 1007 | F - Utilities | (PW# 1007) AEE063 Public Utilities | 0 | 1946DR-PR (1946DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
974882 | 1006 | F - Utilities | (PW# 1006) AEE061 Public Utilities | 0 | 1946DR-PR (1946DR) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
974881 | 1005 | A - Debris Removal | (PW# 1005) AEE051 Debris Removal | 0 | 1946DR-PR (1946DR) | 1148.02 | 0 | 0 | 287 | 287 | 861.02 | 75% | 2011-08-09 14:10 | 2011-10-12 11:50 | 0
481860 | 100 | B - Emergency Protective Measures | (PW# 100) AEGYL-05 Protective Measures | 0 | 3326EM-PR (3326EM) | 0 | 0 | 0 | 0 | 0 | 0 | 75% |  |  | 0
481799 | 10 | B - Emergency Protective Measures | (PW# 10) A- AEVAL01 Protective Measures | 1 | 3326EM-PR (3326EM) | 3334.46 | 0 | 0 | 833.61 | 833.61 | 2500.85 | 75% |  | 2012-09-17 12:16 | 3334.46
751446 | 4782 | F - Utilities | San Juan Area M- Baldrich 1422(Substation) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
1064149 | 5046 | F - Utilities | San Juan Area H-I-J Dist. 1110-03 - 1105-04 - 1106-04 - 1404-07 - 1520-04 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
751809 | 4854 | F - Utilities | Ponce Area G- Ponce Pueblo 5001(Substation) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
711829 | 107856 | F - Utilities | FAASt [Santa Isabel Sect. - Salinas Sect. 38kV Line 100] (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
754801 | 108019 | F - Utilities | FAASt [Repair Unit 9 San Juan Steam Plant] (Generation) | 0 | 4339DR-PR (4339DR) | 27556615.24 | 0 | 0 | 2755661.52 | 2755661.52 | 24800953.72 | 90% | 2025-09-25 16:15 | 2025-09-25 16:15 | 0
817249 | 108116 | F - Utilities | FAASt [Pole and Conductor Repair -Caguas Group 7 - Phase 2] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
660422 | 11566 | F - Utilities | FAASt [Physical Security - Group 4] (Substation) | 2 | 4339DR-PR (4339DR) | 3816798 | 338280 | 0 | 381679.8 | 381679.8 | 3435118.2 | 90% | 2023-12-29 12:31 | 2024-03-07 16:12 | 3816798
718971 | 107884 | F - Utilities | FAASt [Line 50300 (230kV) from Costa Sur Steam Plant to Aguirre Steam Plant] (Transmission) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
743399 | 11764 | F - Utilities | FAASt [High Voltage Equipment Replacement - Group 3] (Substation) | 0 | 4339DR-PR (4339DR) | 17307539.01 | 0 | 0 | 1730753.9 | 1730753.9 | 15576785.11 | 90% | 2024-08-26 10:08 | 2024-08-23 22:25 | 17307539.01
730513 | 107907 | F - Utilities | FAASt [Feeders-Caguas Short Term Group 4] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
730586 | 107909 | F - Utilities | FAASt [Feeders - Ponce Short Term Group 1] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 0
757687 | 108033 | F - Utilities | FAASt [Automation Program Group 22] (Distribution) | 0 | 4339DR-PR (4339DR) | 2356733.87 | 0 | 0 | 235673.38 | 235673.38 | 2121060.49 | 90% | 2025-10-30 20:15 | 2025-10-30 20:15 | 0
735338 | 11834 | F - Utilities | FAASt [Aguadilla Streetlighting - Part 3] (Distribution) | 0 | 4339DR-PR (4339DR) | 0 |  | 0 | 0 | 0 | 0 | 90% |  |  | 8195391
75951 | 1219 | B - Emergency Protective Measures | CLOSEOUT - MEPA114 -LC- KPM (PW01219) | 1 | 4339DR-PR (4339DR) | 200000 | 0 | 0 | 0 | 0 | 200000 | 100% | 2020-01-23 12:45 | 2024-05-03 18:09 | 200000
1064116 | 5022 | F - Utilities | Caguas Area I Dist. 2803-01, 2803-02, 2803-03 (Distribution) | 0 | 4671DR-PR (4671DR) | 0 | 0 | 0 | 0 | 0 | 0 | 90% |  |  | 0
751723 | 4847 | F - Utilities | Arecibo Area C - Vista Azul (Mirador Azul) 8007(Substation) | 0 | 4671DR-PR (4671DR) | 0 |  | 0 |  | 0 | 0 | 90% |  |  | 0
49844 | 495 | B - Emergency Protective Measures | Closeout-MEPA087-Atlantic Quality (LC) | 2 | 4339DR-PR (4339DR) | 422220.27 | 0 | 0 | 0 | 0 | 422220.27 | 100% | 2018-06-29 | 2023-02-02 22:31 | 422220.27

## Sheet4 (hidden)
Consolidated list
Asset | Project Total
Building | 1
Distribution | 151
Distribution Pole and Conductor Repair | 101
Distribution Streetlighting | 43
Feeders | 6
Vieques and Culebra Projects (6) | 1
Grid Automation | 19
Priority Substation | 3
Substation | 2
Substation Rebuilds | 1
Priority Transmission | 5
Transmission Line Rebuild | 5
Substation | 38
Substation | 13
Substation Rebuilds | 19
Substation Security | 4
Vieques and Culebra Projects (6) | 2
Telecommunication | 8
AMI Implementation Program | 1
IT/OT | 7
Transmission | 23
Transmission Line Rebuild | 5
Transmission Priority Pole Replacements | 15
Vieques and Culebra Projects (6) | 3
Vegetation | 34
Vegetation-DT | 19
Vegetation-TL | 15
Grand Total | 282

## Analisis (CS) (hidden)
project # | 797148
Project title | #REF!
| NEW COST PROVIDED | Submitted to PREB | OBLIGATED | Spend as of 2/28/2026 |  |  | Estimate/Cost change (Y/N) | #REF!
428 Allocation (Without the A&E and E&M) | #REF! | #REF! | #REF! | #REF! | Construction |  | Who confirmed the information? | #REF!
406 Allocation (Without the A&E and E&M) | #REF! | #REF! | #REF! |  |  |  | Obligation Amendment Status | #REF!
428 A&E-PW 9510 | #REF! | #REF! | #REF! | #REF! | A&E |  | New Comment | #REF!
406 A&E-PW 9510 | #REF! | #REF! | #REF! |  |  |  | Comentario revisor | #REF!
428 E&M-PW 10710 | #REF! | #REF! | #REF! | #REF! | E&M FINANCE |  | Revisor | #REF!
406 E&M-PW 10710 | #REF! | #REF! | #REF! | 126860.4375 | E&M GLOBAL |  | Current Versioning Status in Grants Protal | #REF!
sum | #REF! |  | #REF! |  |  |  | Date of Obligation | #REF! | 13199997.56 | #REF!
FORMULA Expected Total Project Cost | #REF! | #REF! | #REF! | #REF! | TOTAL Finance | #REF! | Current Status in Grants Protal | #REF! | #REF!
FORMULA Total 428 Expected cost | #REF! | #REF! | #REF! | #REF! | TOTAL WITH E&M |  | Construction % of Completion as of 2/28/2026 | #REF!
FORMULA Total 406 Expected Cost | #REF! | #REF! | #REF!
[8 empty] | New cost povided is the same as obligated cost. Scope additions are expected.however the cost did not changed. |  | This project has WC,and WTBC the total cost provided is under the current amendment total Also the A&E estimated allocation is$2M lower than the incurred cost.
correct cost (no duplication) | #REF!
[8 empty] | No Cost changes from the Submitted to the PREB. Cost incurred does not exceeds the final estimation. No mayor flags identified in cost. |  | No Cost changes from the Submitted to the PREB. Significant increase from obligated. Incurred cost is 51% of the total cost with only 2% of construction. (406 Duplicity identified)
#REF!
No Cost changes from the Submitted to the PREB. Cost incurred does not exceeds the final estimation. No mayor flags identified in cost.
No Cost changes from the Submitted to the PREB. Cost incurred does not exceeds the final estimation. Construction cost incurred with no N/A construction % . No mayor flags identified in cost.
Final cost provided is same as obligated. However,Amendment in progress reflects a total cost of $3M
Cost difference seems to be contingency cost added to 428. Cost incurred does not exceeds the final estimation. Construction cost incurred with no N/A construction %.
No changes in cost provided to PREB.

## Summary (Updated) (hidden)
Summary - FEMA Funding Overview
| PREB's Resolution (Funds 428) |  | Exhibit 2 | Attachment A | Attachment B | Balance
| Consolidated List | 5793000000 | #VALUE! |  | 110931169 | #VALUE!
| Funds for Attachment A | 636808933 |  | #VALUE! |  | #VALUE!
| Additional Funds from Genera | 1343000000 |  |  |  | 1343000000
|  | 7772808933 |  |  |  | #VALUE!
| PREPA (Funds 428) |  | Exhibit 2 | Attachment A | Attachment B | Balance
| Consolidated List | 5715912674.14 | #VALUE! |  | 110931169 | #VALUE!
| Funds for Attachment A | 636808933 |  | #VALUE! |  | #VALUE!
| Additional Funds from Genera | 1343000000 |  |  |  | 1343000000
|  | 7695721607.14 |  |  |  | #VALUE!
#VALUE!
Projects Obligated | Luma New Projection |  |  |  | Information Submitted to PREB |  |  |  | Variance
Sub Asset | Count Projects | Total 428 | Total 406 | Total 428 + 406 | Count Projects | Total 428 | Total 406 | Total 428 + 406 | Total 428 | Total 406 | Total 428 + 406 | New Projection Validation | PREB Validation
LUMA Exhibit 2
Substation | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Vieques and Culebra Projects (6) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Substation Rebuilds | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
IT/OT | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Distribution Pole and Conductor Repair | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Grid Automation | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Transmission Priority Pole Replacements | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Substation Security | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Transmission Line Rebuild | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Distribution Streetlighting | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Feeders | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Building | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
AMI Implementation Program | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Vegetation-DT | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Vegetation-TL | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Total | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Attachment A
Grid Modernization | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Automation | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Distribution Pole and Conductor Repair | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Distribution Streetlighting | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Vegetation-TL | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Substation Rebuilds | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
IT/OT | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Total | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Attachment B
Transmission Line Rebuild | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Vegetation-TL | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Building | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Vieques and Culebra Projects (6) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Substation | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Vegetation-DL | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Transmission Priority Pole Replacements | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
IT/OT | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Substation Rebuilds | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Distribution Pole and Conductor Repair | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
AMI Implementation Program | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Vegetation | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Distribution Streetlighting | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Grid Automation | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Substation Security | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Feeders | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Streetlighting | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Line Rebuild | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Automation | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Grid Modernization | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Underground | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
N/A | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Rebuild | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Blank | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Total | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Total
Substation | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Vieques and Culebra Projects (6) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Substation Rebuilds | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
IT/OT | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Distribution Pole and Conductor Repair | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Grid Automation | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Transmission Priority Pole Replacements | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Substation Security | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Transmission Line Rebuild | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Distribution Streetlighting | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Feeders | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Building | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
AMI Implementation Program | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Vegetation-DT | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Vegetation-TL | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Grid Modernization | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Automation | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vegetation-DL | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Vegetation | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Streetlighting | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Line Rebuild | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Underground | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
N/A | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Rebuild | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Blank | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Check | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!

## Sheet6 (hidden)
|  | 428 Allocation (Without the A&E and E&M) | 60% Values | 406 Allocation (Without the A&E and E&M) | 60% Values | 428 A&E-PW 9510 | 60% Values | 406 A&E-PW 9510 | 60% Values | 428 E&M-PW 10710 | 406 E&M-PW 10710 | FORMULA Expected Total Project Cost | 60% Values | FORMULA Total 428 Expected cost | 60% Values | FORMULA Total 406 Expected Cost | 60% Values
741105 | FAASt [All Regions TL - 230kV] (Vegetation) | 30099566.86 | 18059740.116 | 127486673.75 | 76492004.25 | 279159.4 | 167495.64 | 1171019.3 | 702611.58 | 0 | 0 | 159036419.31 | 95421851.586 | 30378726.26 | 18227235.756 | 128657693.05 | 77194615.83
956343 | FAASt [Ponce Region 6 Line 4800 – Toro Negro to Aibonito, Santa Isabel] (Vegetation) | 5271329.93 | 3162797.958 | 15672132.45 | 9403279.47 | 437891.18 | 262734.708 | 1201536.52 | 720921.912 | 0 | 0 | 22582890.08 | 13549734.048 | 5709221.11 | 3425532.666 | 16873668.97 | 10124201.382
956357 | FAASt [Mayaguez Region 5 Line 1900 – Dos Bocas HP to San Sebastian TC] (Vegetation) | 3132433.35 | 1879460.01 | 9313002.71 | 5587801.626 | 260212.32 | 156127.392 | 714000.65 | 428400.39 | 0 | 0 | 13419649.03 | 8051789.418 | 3392645.67 | 2035587.402 | 10027003.36 | 6016202.016
956345 | FAASt [Arecibo Region 2 Line 2400 – Dos Bocas HP to Coronillas 2] (Vegetation) | 1805809.83 | 1083485.898 | 5368833.09 | 3221299.854 | 150009.25 | 90005.55 | 411612.69 | 246967.614 | 0 | 0 | 7736264.86 | 4641758.916 | 1955819.08 | 1173491.448 | 5780445.78 | 3468267.468
956349 | FAASt [San Juan Region 1 Transmission Line 36800 – Canovanas TC to Palmer TC] (Vegetation) | 4544973.03 | 2726983.818 | 0 | 0 | 140474.5 | 84284.7 | 0 | 0 | 0 | 0 | 4685447.53 | 2811268.518 | 4685447.53 | 2811268.518 | 0 | 0
727608 | FAASt [Region 1 San Juan TL - 115kV] (Vegetation) | 6184793.01 | 3710875.806 | 21147616.85 | 12688570.11 | 57624.25 | 34574.55 | 195113.65 | 117068.19 | 0 | 0 | 27585147.76 | 16551088.656 | 6242417.26 | 3745450.356 | 21342730.5 | 12805638.3
727659 | FAASt [Region 2 Arecibo TL - 115kV] (Vegetation) | 4422450.6 | 2653470.36 | 15121652.49 | 9072991.494 | 41204.35 | 24722.61 | 139516.47 | 83709.882 | 0 | 0 | 19724823.91 | 11834894.346 | 4463654.95 | 2678192.97 | 15261168.96 | 9156701.376
727606 | FAASt [Region 4 Caguas TL - 115kV] (Vegetation) | 7047710.18 | 4228626.108 | 24098183.23 | 14458909.938 | 65664.12 | 39398.472 | 222336.38 | 133401.828 | 0 | 0 | 31433893.91 | 18860336.346 | 7113374.3 | 4268024.58 | 24320519.61 | 14592311.766
727522 | FAASt [Region 3 Bayamon TL - 115kV] (Vegetation) | 4393410.13 | 2636046.078 | 15022354.59 | 9013412.754 | 40933.78 | 24560.268 | 138600.32 | 83160.192 | 0 | 0 | 19595298.82 | 11757179.292 | 4434343.91 | 2660606.346 | 15160954.91 | 9096572.946
727657 | FAASt [Region 5 Mayaguez TL - 115kV] (Vegetation) | 5174184.24 | 3104510.544 | 17692049 | 10615229.4 | 48208.32 | 28924.992 | 163231.65 | 97938.99 | 0 | 0 | 23077673.21 | 13846603.926 | 5222392.56 | 3133435.536 | 17855280.65 | 10713168.39
956348 | FAASt [Bayamon Region 3 Line 10000 – Bayamon Pueblo to Magnolia TO] (Vegetation) | 294309.16 | 176585.496 | 875007.19 | 525004.314 | 24448.38 | 14669.028 | 67084.2 | 40250.52 | 0 | 0 | 1260848.93 | 756509.358 | 318757.54 | 191254.524 | 942091.39 | 565254.834
727529 | FAASt [Region 6 Ponce TL - 115kV] (Vegetation) | 12958692.91 | 7775215.746 | 44309562.76 | 26585737.656 | 120737.25 | 72442.35 | 408812.06 | 245287.236 | 0 | 0 | 57797804.98 | 34678682.988 | 13079430.16 | 7847658.096 | 44718374.82 | 26831024.892
956356 | FAASt [Ponce Region 6 Transmission Line 39000 – Aguas Buenas Substation to Hacienda San Jose] (Vegetation) | 988951.38 | 593370.828 | 0 | 0 | 30566.17 | 18339.702 | 0 | 0 | 0 | 0 | 1019517.55 | 611710.53 | 1019517.55 | 611710.53 | 0 | 0
956342 | FAASt [Arecibo Region 2 Line 36400 – Ponce TC to Dos Bocas HP] (Vegetation) | 20665564.52 | 12399338.712 | 0 | 0 | 638724.36 | 383234.616 | 0 | 0 | 0 | 0 | 21304288.88 | 12782573.328 | 21304288.88 | 12782573.328 | 0 | 0
956353 | FAASt [Arecibo Region 2 Line 36100 – Dos Bocas HP to Barrio Pina] (Vegetation) | 17401102.05 | 10440661.23 | 0 | 0 | 537827.45 | 322696.47 | 0 | 0 | 0 | 0 | 17938929.5 | 10763357.7 | 17938929.5 | 10763357.7 | 0 | 0

## Sheet7 (hidden)
741105 | FAASt [All Regions TL - 230kV] (Vegetation) | Vegetation | Vegetation-TL | 30099566.86 | 127486673.75 | 279159.4 | 1171019.3 | 0 | 0 | 159036419.31 | 30378726.26 | 128657693.05
956343 | FAASt [Ponce Region 6 Line 4800 – Toro Negro to Aibonito, Santa Isabel] (Vegetation) | Vegetation | Vegetation-TL | 5271329.93 | 15672132.45 | 437891.18 | 1201536.52 | 0 | 0 | 22582890.08 | 5709221.11 | 16873668.97
956357 | FAASt [Mayaguez Region 5 Line 1900 – Dos Bocas HP to San Sebastian TC] (Vegetation) | Vegetation | Vegetation-TL | 3132433.35 | 9313002.71 | 260212.32 | 714000.65 | 0 | 0 | 13419649.03 | 3392645.67 | 10027003.36
956345 | FAASt [Arecibo Region 2 Line 2400 – Dos Bocas HP to Coronillas 2] (Vegetation) | Vegetation | Vegetation-TL | 1805809.83 | 5368833.09 | 150009.25 | 411612.69 | 0 | 0 | 7736264.86 | 1955819.08 | 5780445.78
956349 | FAASt [San Juan Region 1 Transmission Line 36800 – Canovanas TC to Palmer TC] (Vegetation) | Vegetation | Vegetation-TL | 4544973.03 | 0 | 140474.5 | 0 | 0 | 0 | 4685447.53 | 4685447.53 | 0
727608 | FAASt [Region 1 San Juan TL - 115kV] (Vegetation) | Vegetation | Vegetation-TL | 6184793.01 | 21147616.85 | 57624.25 | 195113.65 | 0 | 0 | 27585147.76 | 6242417.26 | 21342730.5
727659 | FAASt [Region 2 Arecibo TL - 115kV] (Vegetation) | Vegetation | Vegetation-TL | 4422450.6 | 15121652.49 | 41204.35 | 139516.47 | 0 | 0 | 19724823.91 | 4463654.95 | 15261168.96
727606 | FAASt [Region 4 Caguas TL - 115kV] (Vegetation) | Vegetation | Vegetation-TL | 7047710.18 | 24098183.23 | 65664.12 | 222336.38 | 0 | 0 | 31433893.91 | 7113374.3 | 24320519.61
727522 | FAASt [Region 3 Bayamon TL - 115kV] (Vegetation) | Vegetation | Vegetation-TL | 4393410.13 | 15022354.59 | 40933.78 | 138600.32 | 0 | 0 | 19595298.82 | 4434343.91 | 15160954.91
727657 | FAASt [Region 5 Mayaguez TL - 115kV] (Vegetation) | Vegetation | Vegetation-TL | 5174184.24 | 17692049 | 48208.32 | 163231.65 | 0 | 0 | 23077673.21 | 5222392.56 | 17855280.65
956348 | FAASt [Bayamon Region 3 Line 10000 – Bayamon Pueblo to Magnolia TO] (Vegetation) | Vegetation | Vegetation-TL | 294309.16 | 875007.19 | 24448.38 | 67084.2 | 0 | 0 | 1260848.93 | 318757.54 | 942091.39
727529 | FAASt [Region 6 Ponce TL - 115kV] (Vegetation) | Vegetation | Vegetation-TL | 12958692.91 | 44309562.76 | 120737.25 | 408812.06 | 0 | 0 | 57797804.98 | 13079430.16 | 44718374.82
956356 | FAASt [Ponce Region 6 Transmission Line 39000 – Aguas Buenas Substation to Hacienda San Jose] (Vegetation) | Vegetation | Vegetation-TL | 988951.38 | 0 | 30566.17 | 0 | 0 | 0 | 1019517.55 | 1019517.55 | 0
956342 | FAASt [Arecibo Region 2 Line 36400 – Ponce TC to Dos Bocas HP] (Vegetation) | Vegetation | Vegetation-TL | 20665564.52 | 0 | 638724.36 | 0 | 0 | 0 | 21304288.88 | 21304288.88 | 0
956353 | FAASt [Arecibo Region 2 Line 36100 – Dos Bocas HP to Barrio Pina] (Vegetation) | Vegetation | Vegetation-TL | 17401102.05 | 0 | 537827.45 | 0 | 0 | 0 | 17938929.5 | 17938929.5 | 0

## Sheet2 (hidden)
711819 | 673847
168226 | 701679
662238 | 673843
657300 | 673848
542758 | 674092
551963 | 682180
551925 | 673774
550950 | 673839
551926 | 679026
678800 | 678985
673292 | 679025
691246
742026
704755
682898
682172
673775
686453
686471
689071
682865
682870
682910
674088
708579
710110
710099
712968
705584
673818
673844
673838
738120
673795
334329
685477
711856
705527
701495
688630
735474
750692
752540
790443
698579
660239
542690
542687
542756
542688
698424
542517
660227
659968
673504
659623
690545
659625
660437
691702
679039
812569
797148
801166
801172
817956
798275
745856
800286
757700
757692
757696
757697
745861
800361
757689
752810
746309
757699
757687
745859
755211
757698
752808
757662
165226

## Reference (hidden)
Internal Version
Business Analyst/Distributed Reports/Internal Version/FAASt Consolidated Plan - RFR 3-25-26_1006AM

## LUMA Exhibit 2 (70) (hidden)
Expected Project Costs Allocation
Project # | Title | Asset | Sub Asset | Obligated (Yes / No) | Process Step | 428 Allocation (Without the A&E and E&M) | 406 Allocation (Without the A&E and E&M) | 428 A&E-PW 9510 | 406 A&E-PW 9510 | 428 E&M-PW 10710 | 406 E&M-PW 10710 | Expected Total Project Cost | Total 428 Expected Cost | Total 406 Expected Cost | Project Status | Expected COR3 Submission Date | Comments | PREPA Note: Cost incurred as reported by LUMA.
666894 | FAASt [San Juan Streetlighting] (Distribution) | Distribution | Streetlighting | No | Inactive | 27201946.76 | 1465463.21 | 6380570.04 | 123157.52 | 976071 | 658009 | 36805217.53 | 34558587.8 | 2246629.73 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. | 1973811.207
678794 | FAASt [Ponce Streetlighting] (Distribution) | Distribution | Streetlighting | No | Inactive | 10629532.275 | 655524.41 | 1713141.92 | 51717 | 339183 | 228657 | 13617755.605 | 12681857.195 | 935898.41 | DSOW – Scope and Cost Update in Progress | Q2 FY2027 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. | 697311.1311
718971 | FAASt [Line 50300 (230kV) from Costa Sur Steam Plant to Aguirre Steam Plant] (Transmission) | Transmission | Line Rebuild | No | Inactive | 9936000 | 5400000 | 864000 | 864000 | 1296000 | 3240000 | 21600000 | 12096000 | 9504000 | DSOW – Pending Design Package for Development | Q3 FY2027 | This line is key for hardening by replacing targeted structures as well as insulators and hardware along the entire line length, with a high-level estimate at $30M. Additional future scope proposed for 406 includes adding a 230/115kV new substation at Santa Isabel TC which would significantly reduce the exposure (probability and likelihood that the facility is not available after a storm) as well as facilitate a pathway for new large-scale renewables being added in the South and Southeast regions. | 460702.448
690483 | FAASt [Cayey Streetlighting] | Distribution | Streetlighting | No | Inactive | 10093033.82 | 936114.24 | 2435204.39 | 95954.76 | 503757 | 339603 | 14403667.21 | 13031995.21 | 1371672 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. | 643269.5581
699814 | FAASt [Juana Diaz Streetlighting] (Distribution) | Distribution | Streetlighting | No | Inactive | 13267153.655 | 370784.53 | 2795912.01 | 55146.97 | 744597 | 501963 | 17735557.165 | 16807662.665 | 927894.5 | DSOW – Scope and Cost Update in Progress | Q1 FY2027 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. | 522847.957
704931 | FAASt [Camuy Streetlighting] (Distribution) | Distribution | Streetlighting | No | Inactive | 13069359.5825 | 220906.9 | 1972441.141 | 107984.699 | 958677 | 646283 | 16975652.3225 | 16000477.7235 | 975174.599 | DSOW – Scope and Cost Update in Progress | Q1 FY2027 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. | 678851.6314
704862 | FAASt [Fajardo Streetlighting] (Distribution) | Distribution | Streetlighting | No | Inactive | 10758153.95 | 839531.97 | 2150579.88 | 58676.25 | 315768 | 212872 | 14335582.05 | 13224501.83 | 1111080.22 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. | 458695.0286
678795 | FAASt [Arecibo Streetlighting] (Distribution) | Distribution | Streetlighting | No | Inactive | 11412143.0925 | 485336.36 | 1902215.74 | 59360 | 466962 | 314798 | 14640815.1925 | 13781320.8325 | 859494.36 | DSOW – Scope and Cost Update in Progress | Q1 FY2027 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. | 646048.0917
704757 | FAASt [Santa Isabel Streetlighting] (Distribution) | Distribution | Streetlighting | No | Inactive | 8241015.33 | 190912.38 | 1562084.58 | 22536.63 | 284994 | 192126 | 10493668.92 | 10088093.91 | 405575.01 | DSOW – Scope and Cost Update in Progress | Q1 FY2027 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. | 306297.5883
671396 | FAASt [Utuado Streetlighting] (Distribution) | Distribution | Streetlighting | No | Inactive | 15515918.205 | 2012364.47 | 3319870.72 | 155072.6 | 1245009 | 839311 | 23087545.995 | 20080797.925 | 3006748.07 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. | 664704.356
688623 | FAASt [Automation Program Group 1A-8 Feeders] (Distribution) | Distribution | Automation | No | Inactive | 3591270 | 1130585 | 332525 | 199515 | 465535 | 931070 | 6650500 | 4389330 | 2261170 | DSOW – Pending Design Package for Development | Q3 FY2027 | Estimate date for the work to be completed portion only. The estimated total per project is considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (23) 3PH Reclosers, (104) 1ph reclosers, (48) cFCi. | 360903.9102
724603 | FAASt [Cabo Rojo Streetlighting] (Distribution) | Distribution | Streetlighting | No | Inactive | 6954788.08 | 279702.31 | 1689593.17 | 41489.51 | 353232 | 238128 | 9556933.07 | 8997613.25 | 559319.82 | DSOW – Scope and Cost Update in Progress | Q1 FY2027 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. | 509029.477
701473 | FAASt [Canovanas Streetlighting] (Distribution) | Distribution | Streetlighting | No | Inactive | 11399484.83 | 1119131.43 | 2377385.56 | 89359.81 | 595410 | 401390 | 15982161.63 | 14372280.39 | 1609881.24 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. | 433154.0521
693543 | FAASt [Juncos Streetlighting] (Distribution) | Distribution | Streetlighting | No | Inactive | 10405292.6975 | 287804.01 | 1631297.312 | 26436.06 | 589389 | 397331 | 13337550.0795 | 12625979.0095 | 711571.07 | DSOW – Scope and Cost Update in Progress | Q1 FY2027 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. | 402911.0913
671400 | FAASt [Barceloneta Streetlighting] (Distribution) | Distribution | Streetlighting | No | Inactive | 7024652.0375 | 209975.14 | 1206563.5 | 50306 | 397386 | 267894 | 9156776.6775 | 8628601.5375 | 528175.14 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. | 416323.1767
693788 | FAASt [Toa Alta Streetlighting] (Distribution) | Distribution | Streetlighting | No | Inactive | 4596792.52 | 82066.81 | 1162797.94 | 17891.57 | 170595 | 115005 | 6145148.84 | 5930185.46 | 214963.38 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. | 272844.9723
697183 | FAASt [Vega Baja Streetlighting] (Distribution) | Distribution | Streetlighting | No | Inactive | 8233261.46 | 807899.66 | 1621313.74 | 17891.57 | 369288 | 248952 | 11298606.43 | 10223863.2 | 1074743.23 | DSOW – Scope and Cost Update in Progress | Q4 FY2027 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. | 273173.1946
690721 | FAASt [Guayama Streetlighting] (Distribution) | Distribution | Streetlighting | No | Inactive | 3974160.015 | 215693.59 | 1011463.98 | 25642.92 | 133131 | 89749 | 5449840.505 | 5118754.995 | 331085.51 | DSOW – Scope and Cost Update in Progress | Q1 FY2027 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. | 329495.4926
698432 | FAASt [Hormigueros Streetlighting] (Distribution) | Distribution | Streetlighting | No | Inactive | 5694746.915 | 284606.44 | 1362869.66 | 17724.97 | 304395 | 205205 | 7869547.985 | 7362011.575 | 507536.41 | DSOW – Scope and Cost Update in Progress | Q4 FY2027 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. | 112819.4583
690480 | FAASt [Humacao Streetlighting] (Distribution) | Distribution | Streetlighting | No | Inactive | 6175629.8825 | 299807.81 | 1006696.36 | 29209 | 279642 | 188518 | 7979503.0525 | 7461968.2425 | 517534.81 | DSOW – Scope and Cost Update in Progress | Q1 FY2027 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. | 297152.2294
686482 | FAASt [Isabela Streetlighting] (Distribution) | Distribution | Streetlighting | No | Inactive | 5745883.39 | 496924.08 | 1332970.6 | 37797.8 | 259572 | 174988 | 8048135.87 | 7338425.99 | 709709.88 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. | 248239.9589
750503 | FAASt [25 MW BESS Installation and Integration - San Juan] (Substation) | Substation | Grid Modernization | No | Inactive |  | 24053536.03 | 0 | 3187811.29 | 0 | 28261718.24 | 55503065.56 | 0 | 55503065.56 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | 406 HM Split 100% As it was last submitted to FEMA. Contingent to FEMA Hazard Mitigation Evaluation and approval. | 341109.662
750502 | FAASt [25 MW BESS Installation and Integration - Aguadilla] (Substation) | Substation | Grid Modernization | No | Inactive |  | 21118171.64 | 0 | 3340630.47 | 0 | 28261718.24 | 52720520.35 | 0 | 52720520.35 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | 406 HM Split 100% As it was last submitted to FEMA | 516373.7564
752972 | FAASt [4 x 25 MW BESS Interconnections Manati] (Substation) | Substation | Grid Modernization | No | Inactive |  | 23808829.62 | 0 | 3414922.97 | 0 | 30416253.08 | 57640005.67 | 0 | 57640005.67 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | 406 HM Split 100% As it was last submitted to FEMA | 246353.4254
754350 | Distribution Underground Circuit Feeders - San Juan Group 1 | Distribution | Underground | No | Inactive | 4310111.715 | 9577521.9267 | 362956.776 | 812115.7863 | 1512.3199 | 58980.4761 | 15123199 | 4674580.8109 | 10448618.1891 | DSOW – Pending Design Package for Development | Q1 FY2028 | Pending Operation Assessment, and design work has not yet been finalized. Further evaluation is required before moving forward. | 54289
738671 | FAASt [25 MW BESS Installation and Integration - Barceloneta] (Substation) | Substation | Grid Modernization | No | Inactive |  | 20318919.35 |  | 5211394.35 |  | 30411453.8 | 55941767.5 | 0 | 55941767.5 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | 406 HM Split 100% As it was last submitted to FEMA | 437835.2415
754351 | ​Distribution Underground Circuit Feeders - San Juan Group 2 | Distribution | Underground | No | Inactive | 2013990.405 | 4475298.6789 | 169599.192 | 379478.1921 | 706.6633 | 27559.8687 | 7066633 | 2184296.2603 | 4882336.7397 | DSOW – Pending Design Package for Development | Q1 FY2028 | Pending Operation Assessment, and design work has not yet been finalized. Further evaluation is required before moving forward. | 41921.5
748180 | Transmission Advanced Sensors and Wide-Area Monitoring, Protection, and Control (WAMPAC) System | IT/OT | N/A | No | Inactive | 33071971.884 | 4086750.8114 | 4724567.412 | 472456.7412 | 3307197.1884 | 1417370.2236 | 47080314.2606 | 41103736.4844 | 5976577.7762 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 |  | 0
752277 | FAASt [Substation Ciales 8701] (Substation) | Substation | Rebuild | No | Inactive | 3553830.9091 | 524335.7079 | 349557.1386 | 116519.0462 | 466076.1848 | 815633.3234 | 5825952.31 | 4369464.2325 | 1456488.0775 | DSOW – Pending Design Package for Development | Q1 FY2028 | New DSOW needs to be developed , Proposed approach focused on replacing critical components: metal-clad, transformers, breakers, communications. | 4061.1901
727691 | FAASt [Region 1 San Juan Transmission 38kV sensitive areas] (Vegetation) | Vegetation | N/A | No | Inactive | 1313961.65 | 14439457.84 | 11049.14 | 121275.67 | 0 | 0 | 15885744.3 | 1325010.79 | 14560733.51 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | Project is developed and will be ready to submit to FEMA as soon as projects are reactivated in Grants Portal | 0
740406 | FAASt[Region 1 San Juan Transmission 38kV - Non-Sensitive (Vegetation)] | Vegetation | N/A | No | Inactive | 281345.36 | 3091775.16 | 2365.85 | 25967.52 | 0 | 0 | 3401453.89 | 283711.21 | 3117742.68 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | Project is developed and will be ready to submit to FEMA as soon as projects are reactivated in Grants Portal | 0
740410 | FAASt[Region 2 Arecibo Transmission 38kV - Non-Sensitive (Vegetation)] | Vegetation | N/A | No | Inactive | 251201.23 | 2760513.52 | 2112.36 | 23185.29 | 0 | 0 | 3037012.4 | 253313.59 | 2783698.81 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | Project is developed and will be ready to submit to FEMA as soon as projects are reactivated in Grants Portal | 0
740409 | FAASt[Region 4 Caguas Transmission 38kV - Non-Sensitive (Vegetation)] | Vegetation | N/A | No | Inactive | 715385.11 | 7927576.7 | 6015.7 | 66028.4 | 0 | 0 | 8715005.91 | 721400.81 | 7993605.1 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | Project is developed and will be ready to submit to FEMA as soon as projects are reactivated in Grants Portal | 0
740414 | FAASt [Region 6 Ponce Transmission 38kV - Non-Sensitive (Vegetation) | Vegetation | N/A | No | Inactive | 799358.09 | 8784348.55 | 6721.82 | 73778.93 | 0 | 0 | 9664207.39 | 806079.91 | 8858127.48 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | Project is developed and will be ready to submit to FEMA as soon as projects are reactivated in Grants Portal | 0
727694 | FAASt [Region 4 Caguas Transmission 38kV sensitive areas] (Vegetation) | Vegetation | N/A | No | Inactive | 729380.61 | 8015348.33 | 6133.39 | 67320.16 | 0 | 0 | 8818182.49 | 735514 | 8082668.49 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | Project is developed and will be ready to submit to FEMA as soon as projects are reactivated in Grants Portal | 0
740411 | FAASt [Region 5 Mayaguez Transmission 38kV - Non-Sensitive (Vegetation)] | Vegetation | N/A | No | Inactive | 141749.28 | 1557718.3 | 1191.98 | 13083.11 | 0 | 0 | 1713742.67 | 142941.26 | 1570801.41 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | Project is developed and will be ready to submit to FEMA as soon as projects are reactivated in Grants Portal | 0
727562 | FAASt [Region 5 Mayaguez Transmission 38kV sensitive areas] (Vegetation) | Vegetation | N/A | No | Inactive | 2053569.7 | 22567198.56 | 17268.5 | 189539.83 | 0 | 0 | 24827576.59 | 2070838.2 | 22756738.39 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | Project is developed and will be ready to submit to FEMA as soon as projects are reactivated in Grants Portal | 0
727530 | FAASt [Region 6 Ponce Transmission 38kV sensitive areas] (Vegetation) | Vegetation | N/A | No | Inactive | 2278394.76 | 25037858.23 | 19159.06 | 210290.68 | 0 | 0 | 27545702.73 | 2297553.82 | 25248148.91 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | Project is developed and will be ready to submit to FEMA as soon as projects are reactivated in Grants Portal | 0
727540 | FAASt [Region 2 Arecibo Transmission 38kV sensitive areas] (Vegetation) | Vegetation | N/A | No | Inactive | 1842560.72 | 20248367.13 | 15494.13 | 170064.17 | 0 | 0 | 22276486.15 | 1858054.85 | 20418431.3 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | Project is developed and will be ready to submit to FEMA as soon as projects are reactivated in Grants Portal | 0
740408 | FAASt[Region 3 Bayamon Transmission 38kV - Non-Sensitive (Vegetation)] | Vegetation | N/A | No | Inactive | 666580.3 | 7325219.95 | 5605.29 | 61523.84 | 0 | 0 | 8058929.38 | 672185.59 | 7386743.79 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | Project is developed and will be ready to submit to FEMA as soon as projects are reactivated in Grants Portal | 0
727558 | FAASt [Region 3 Bayamon Transmission 38kV sensitive areas] (Vegetation) | Vegetation | N/A | No | Inactive | 1322933.13 | 14538047.6 | 11124.57 | 122103.73 | 0 | 0 | 15994209.03 | 1334057.7 | 14660151.33 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | Project is developed and will be ready to submit to FEMA as soon as projects are reactivated in Grants Portal | 0
740662 | [Automation Program Group 2] (TL/ Distribution | Distribution | Automation | No | Inactive | 21843000 | 6876500 | 2022500 | 1213500 | 2831500 | 5663000 | 40450000 | 26697000 | 13753000 | DSOW – Pending Design Package for Development | Q3 FY2027 | Estimate date for the work to be completed portion only. The estimated total per project is considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (145) 3PH Reclosers, (539) 1ph reclosers, (254) cFCi. | 2546994.6399
741678 | [Automation Program Group 4] (TL/Distribution | Distribution | Automation | No | Inactive | 16985160 | 5347180 | 1572700 | 943620 | 2201780 | 4403560 | 31454000 | 20759640 | 10694360 | DSOW – Pending Design Package for Development | Q3 FY2027 | Estimate date for the work to be completed portion only. The estimated total per project is considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (117) 3PH Reclosers, (247) 1ph reclosers, (182) cFCi. | 1802599.6427
705657 | [Automation Program Group 3] (TL/Distribution | Distribution | Automation | No | Inactive | 13656870 | 4299385 | 1264525 | 758715 | 1770335 | 3540670 | 25290500 | 16691730 | 8598770 | DSOW – Pending Design Package for Development | Q3 FY2027 | Estimate date for the work to be completed portion only. The estimated total per project is considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (99) 3PH Reclosers, (316) 1ph reclosers, (212) cFCi. | 1235166.9496
730657 | [Line 2200 Dos Bocas HP to Dorado TC ] (Transmission | Transmission | Line Rebuild | No | Inactive | 57872010.7354 | 31452179.7475 | 5032348.7596 | 5032348.7596 | 7548523.1394 | 18871307.8485 | 125808718.99 | 70452882.6344 | 55355836.3556 | DSOW – Pending Design Package for Development | Q3 FY2027 | The planned scope for this facility is first to rebuild the undersized segment from Manati to Vega Baja to achieve a capacity increase to a minimum of 1160A. The proposed second phase is to restore the out-of-service segment from Dos Bocas to Cambalache. As requested by PMs based on latest value engineering, 3 segments were selected (1, 7 & 8) | 8149571.0366
704793 | [Yauco Streetlighting] (Distribution | Distribution | Streetlighting | No | Inactive | 12597812.93 | 1160589.76 | 2540431.6 | 79529.34 | 634212 | 427548 | 17440123.63 | 15772456.53 | 1667667.1 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. | 234796.0915
704744 | [San Sebastian Streetlighting] (Distribution | Distribution | Streetlighting | No | Inactive | 19955144.585 | 486338.95 | 4057973.95 | 94811.81 | 1566129 | 1055791 | 27216189.295 | 25579247.535 | 1636941.76 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. | 680660.1749
685869 | [Mayagüez TC] (Substation | Substation | Rebuild | No | Inactive | 22073642.86 | 543426.36 | 2605555.14 | 53174.57 | 13511059.91 | 183120 | 38969978.84 | 38190257.91 | 779720.93 | DSOW – Pending Design Package for Development | Q1 FY2027 | Awaiting cable termination and subcontractor. Received quote, started micropurchase. Breakers have already been maintained and transformer fans were replaced. Estimated Submission to COR3/FEMA 6/30/2026. | 391877.4639
764707 | [Feeder Rebuild # 6012-02] (Distribution | Distribution | Rebuild | No | Inactive | 16634520 | 482160 | 5062680 | 241080 | 1446480 | 241080 | 24108000 | 23143680 | 964320 | DSOW – Pending Design Package for Development | FY2029 | Design is about 39% complete. This project is currently classified as withdrawn (T1) and covers 5.74 miles with 239 structures. DSOW – Waiting on the design package to be developed. | 1046942.5037
764705 | [Feeder Rebuild # 6014-02] (Distribution | Distribution | Rebuild | No | Inactive | 23763600 | 688800 | 7232400 | 344400 | 2066400 | 344400 | 34440000 | 33062400 | 1377600 | DSOW – Pending Design Package for Development | FY2029 | Design is about 52% complete. This project is currently classified as withdrawn (T1) and covers 8.20 miles with 343 structures. DSOW – Waiting on the design package to be developed. | 1973511.253
704929 | [San Lorenzo Streetlighting] (Distribution | Distribution | Streetlighting | No | Inactive | 12867034.6125 | 347830.72 | 2944605.83 | 60896.29 | 920544 | 620576 | 17761487.4525 | 16732184.4425 | 1029303.01 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. | 615681.5552
724828 | [Loiza Streetlighting] (Distribution | Distribution | Streetlighting | No | Inactive | 5936181.88 | 201637.58 | 1248099.37 | 14137.5 | 276966 | 186714 | 7863736.33 | 7461247.25 | 402489.08 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. | 174283.6273
698522 | [Vieques Streetlighting] (Distribution | Distribution | Streetlighting | No | Inactive | 3791271.0575 | 322022.91 | 810226.05 | 32120.4 | 196686 | 132594 | 5284920.4175 | 4798183.1075 | 486737.31 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. | 135341.7111
693615 | [Rio Grande Streetlighting] (Distribution | Distribution | Streetlighting | No | Inactive | 5156073.42 | 268046.05 | 1156399.63 | 21533.62 | 191334 | 128986 | 6922372.72 | 6503807.05 | 418565.67 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. | 229464.6486
698427 | [Maricao Streetlighting] (Distribution | Distribution | Streetlighting | No | Inactive | 4466381.615 | 647106.71 | 926826.7734 | 43337.3166 | 406752 | 274208 | 6764612.415 | 5799960.3884 | 964652.0266 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. | 412029.6212
724941 | [Aguas Buenas Streetlighting] (Distribution | Distribution | Streetlighting | No | Inactive | 11340397.36 | 201510.89 | 2036460.34 | 0 | 693084 | 467236 | 14738688.59 | 14069941.7 | 668746.89 | DSOW – Scope and Cost development in progress | Q1 FY2027 | DSOW package complete.Ready to be sumitted, scope consider all construction phases. | 618088.3347
704741 | [Moca Streetlighting] (Distribution | Distribution | Streetlighting | No | Inactive | 17932518.84 | 308495.64 | 3152500.55 | 0 | 1190151 | 802329 | 23385995.03 | 22275170.39 | 1110824.64 | DSOW – Scope and Cost development in progress | Q1 FY2027 | DSOW package complete.Ready to be sumitted, scope consider all construction phases. | 417195.2193
724605 | [Guayanilla Streetlighting] (Distribution | Distribution | Streetlighting | No | Inactive | 7795083.32 | 183970.54 | 1372729.11 | 0 | 424146 | 285934 | 10061862.97 | 9591958.43 | 469904.54 | DSOW – Scope and Cost development in progress | Q1 FY2027 | DSOW package complete.Ready to be sumitted, scope consider all construction phases. | 506612.2788
724599 | [Sabana Grande Streetlighting] (Distribution | Distribution | Streetlighting | No | Inactive | 10754272.51 | 236814.37 | 1906868.06 | 0 | 725196 | 488884 | 14112034.94 | 13386336.57 | 725698.37 | DSOW – Scope and Cost development in progress | Q1 FY2027 | DSOW package complete.Ready to be sumitted, scope consider all construction phases. | 441529.1219
724669 | [Ciales Streetlighting] (Distribution | Distribution | Streetlighting | No | Inactive | 12013750.42 | 272974.74 | 2044738.82 | 0 | 741921 | 500159 | 15573543.98 | 14800410.24 | 773133.74 | DSOW – Scope and Cost development in progress | Q1 FY2027 | DSOW package complete.Ready to be sumitted, scope consider all construction phases. | 400619.9636
724716 | [Quebradillas Streetlighting] (Distribution | Distribution | Streetlighting | No | Inactive | 10502157.5 | 195150.03 | 1872541.02 | 0 | 642240 | 432960 | 13645048.55 | 13016938.52 | 628110.03 | DSOW – Scope and Cost development in progress | Q1 FY2027 | DSOW package complete.Ready to be sumitted, scope consider all construction phases. | 215200.3038
713795 | [Lares Streetlighting] (Distribution | Distribution | Streetlighting | No | Inactive | 11882095.1 | 217275.01 | 1974624.75 | 0 | 733893 | 494747 | 15302634.86 | 14590612.85 | 712022.01 | DSOW – Scope and Cost development in progress | Q1 FY2027 | DSOW package complete.Ready to be sumitted, scope consider all construction phases. | 259135.6296
724670 | [Patillas Streetlighting] (Distribution | Distribution | Streetlighting | No | Inactive | 8408428.82 | 119750.59 | 1456883.53 | 0 | 425484 | 286836 | 10697382.94 | 10290796.35 | 406586.59 | DSOW – Scope and Cost development in progress | Q1 FY2027 | DSOW package complete.Ready to be sumitted, scope consider all construction phases. | 58985.215
724781 | [Penuelas Streetlighting] (Distribution | Distribution | Streetlighting | No | Inactive | 7929864.73 | 140145.41 | 1433020.87 | 0 | 398055 | 268345 | 10169431.01 | 9760940.6 | 408490.41 | DSOW – Scope and Cost development in progress | Q1 FY2027 | DSOW package complete.Ready to be sumitted, scope consider all construction phases. | 88962.1821
741097 | Region 1 San Juan Substation/Telecom | Vegetation | N/A | No | Inactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | DSOW – Pending Design Package for Development | N/A | Vegetation Subs/Telecom projects were withdrawn as substations are under a maintenance cycle and do not require federally funded clearing. These projects will not be reactivated or resubmitted to FEMA. | 0
741098 | Region 3 Bayamon Substation/Telecom | Vegetation | N/A | No | Inactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | DSOW – Pending Design Package for Development | N/A | Vegetation Subs/Telecom projects were withdrawn as substations are under a maintenance cycle and do not require federally funded clearing. These projects will not be reactivated or resubmitted to FEMA. | 0
741102 | Region 5 Mayaguez Substation/Telecom | Vegetation | N/A | No | Inactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | DSOW – Pending Design Package for Development | N/A | Vegetation Subs/Telecom projects were withdrawn as substations are under a maintenance cycle and do not require federally funded clearing. These projects will not be reactivated or resubmitted to FEMA. | 0
741101 | Region 2 Arecibo Substation/Telecom | Vegetation | N/A | No | Inactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | DSOW – Pending Design Package for Development | N/A | Vegetation Subs/Telecom projects were withdrawn as substations are under a maintenance cycle and do not require federally funded clearing. These projects will not be reactivated or resubmitted to FEMA. | 0
741104 | Region 6 Ponce Substation/Telecom | Vegetation | N/A | No | Inactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | DSOW – Pending Design Package for Development | N/A | Vegetation Subs/Telecom projects were withdrawn as substations are under a maintenance cycle and do not require federally funded clearing. These projects will not be reactivated or resubmitted to FEMA. | 0
741100 | Region 4 Caguas Substation/Telecom | Vegetation | N/A | No | Inactive |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | DSOW – Pending Design Package for Development | N/A | Vegetation Subs/Telecom projects were withdrawn as substations are under a maintenance cycle and do not require federally funded clearing. These projects will not be reactivated or resubmitted to FEMA. | 0
[6 empty] | 595423815.646 | 317047219.3924 | 101270058.7045 | 29159565.4211 | 56366956.4058 | 170203524.1003 | 1269471139.6701 | 753060830.7563 | 516410308.9138 |  |  |  | 34985778.9539

## LUMA Exhibit 3 (hidden)
Prioritization Code | High Urgency | Work Completed | Project # | Title | Asset | Sub Asset | Incurred Cost | Project costs * | 428 Allocation * | 406 Allocation * | Additional comments
1 | LUMA has already procured the materials necessary and engineered work order packages for this project utilizing the global FAASt Project Wroksheets (PW's) for equipment & materials (E&M) and arechitecture and engineering (A&E) with expectation to submit Detailed Scopes of Work (DSOWs) to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete for a number of units. If LUMA is unable to get these FAASt projects activated there is a large risk of incurred cost to rate payers these projects carry high reliability impacts. |  | Pending FAASt Number | Distribution Automation Program | Distribution | Automation | 75157137.71 | 296669500 | 178001700 | 118667800 | The Automation Program included here is based on a grouping of projects that LUMA will split to separate groups during the formulation process as DSOWs are submitted to FEMA. This program has Approximately $61 million of cost Incurred to the E&M PW. To be clear, this line does not include "Work Completed" Distribution Automation, as construction has not commenced for the units included herein as we are pending FASST numbers.
1 | Cost already incurred and project complete. | Yes | Pending FAASt Number | Hato Rey TC Transformer Replacement | Substation | Component Replacement | 3763775.37 | 3763775.37 | 3763775.37 | 0 | Transformer purchased and reimbursed to E&M PW ($892,425). Remainder of Installation and Comissioning completed under NFC.
1 | Cost already incurred and project complete. | Yes | Pending FAASt Number | Venezuela TC | Substation | Component Replacement | 2613825.35 | 2613825.35 | 2613825.35 | 0 | Transformer purchased and reimbursed to E&M PW ($1,037,090). Remainder of Installation and Commissioning completed under NFC.
1 | Transformers already purchased with manufacturing and incoming. Project needs to be included in Consolidated Project List to mitigate ratepayer exposure. |  | Pending FAASt Number | Substation Component Group 2 | Substation | Component Replacement | 3133498.208 | 130000000 | 117000000 | 13000000 | Total of 10 substations with 9 transformers, 2 metal clad, 8 PAC Upgrade, 1 cap bank, 1 RTU, 9 Distribution and 8 transmission breakers replacements plus minor repair, grounding and security for all 10 stations. High Level budgetary estimates are around $130 million.
1 | Transformers already procured with manufacturing in various stages and delivery dates from the middle of 2026 through 2028. Commitment to purchase the transformers was made under the FEMA obligated E&M PW due to having funds obligated and expectation of receiving child FASST obligations. Due to changes in COR3 policy around Global PW's, If project is not included in Consolidated Project List there will be large risk to ratepayers as the transformers are incoming. Additionally, these transformer replacements are critical to grid stability. |  | Pending FAASt Number | Substation Component Group 3 | Substation | Component Replacement | 14665406.49 | 310000000 | 279000000 | 31000000 | Scope includes among other things, 31 transformer replacements. Transformers already procured with manufacturing commencing and delivery dates from the middle of 2026 through 2028. Cost incurred is based on progress payments made for transformers to manufacturers to-date, but will increase as production of transformers continues. Additionally, LUMA has committed* $71,868,237.51 for the purchase of these transformers under the Global E&M PW, so there is significant risk to ratepayers if this project is not initiated. These transformer replacements are targeting Out of Service, Capacity Constrained, and Transformer in poor conditions to ensure reliable service to customers and build in added reselience to the system. Due to the aforementioned reasons, this is one of LUMA's top priorities for FEMA initiation and subsequent obligation. *Commitment to purchase the transformers was already made under the federally funded Equipment and Material PW at the time due to having funds obligated for transformers in the global PW and expectation of receiving child FASST obligations in a timely manner.
1 | Equipment costs incurred under Global E&M PW, with labor for installation covered under NFC and DOE. | Yes | Pending FAASt Number | Substation Component Group 0 | Substation | Component Replacement | 14145405.55 | 14145405.55 | 14145405.55 | 0 | Project is a priority to get FEMA obligated. The equipment was purchased under the federal E&M PW but installed with NFC or DOE dollars. LUMA is requesting a FAASt number to be reconciled for the Equipment purchased under E&M PW. All of this equipment cost would put rate payers at risk if it is not reconciled to child PWs. Equipment included in this cost Incurred are the following: 16 Gas Circuit Breakers ($1,036,579), 5 Transformers - Sabana Llana 1646 ($968,203), Mora TC 112 MVA ($2,926,189.87), Caguas 112 MVA ($4,416,882), Isla Grande 112MVA ($2,926,189.87), Hogar Crea 112 MVA ($1,871,361.81)
1 | LUMA has already procured material and engineered work order packages for this project utilizing the global PW's for E&M and A&E with expectation to submit DSOWs to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete for a number of units. If LUMA is unable to get these projects activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. |  | Pending FAASt Number | 38 kV Reclosers Program | Transmission | Automation | 6521828.2 | 46523875.17 | 29631317.7485 | 16892557.4215 | Cost Incurred for 38kV Recloser Program is due to Engineering and Project Management Costs ($3.1M) and Equipment Purchase Cost as the Reclosers for these projects have already been procured under the Equipment & Material PW and are in LUMA's Warehouse ($3.4M). 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review.
1 | Historical Flooding in the Arecibo Pueblo Substation requires it to be relocated to Arecibo Sectionalizer Site. The site is critical to stability of system. Due to relocation, much of the project is expected to be funded by FEMA's Section 406 Hazard Mitigation. |  | Pending FAASt Number | Arecibo Sect. Substation Rebuild | Substation | Substation Rebuild | 0 | 71435277.14 | 7143527.714 | 64291749.426 | Cost Incurred to date is based on project planning exercises and therefore not tied directly to execution of project. High-Level project scope: Rebuild of priority sectionalizing substation including colocated 8015 Arecibo Hospital Distrito and 8003 Arecibo Rural distribution substations and relocation to site of distribution substation 8002 Arecibo Pueblo substation (due to Historical Flooding).
1 | This station has numerous major issues that need to be remediated to ensure reliable service. Among these are the following: 1. GIS problems. 2. Out of service underground transmission lines 3.Reliability Issues 4. Large Flood Risk 5. High Critical Loads |  | Pending FAASt Number | Chardon Sect. Substation Rebuild | Substation | Substation Rebuild | 0 | 25000000 | 15000000 | 10000000 | Cost Incurred to date is based on project planning exercises and therfore not tied directly to execution of project. Rebuild of priority sectionalizing substation; will include in scope the rebuild of distribution substations 1403 Chardon I and 1404 Chardón 2
[7 empty] | 120000876.878 | 900151658.58 | 646299551.7325 | 253852106.8475
Project # | Title | Asset | Sub Asset | Incurred Cost | Project costs * | 428 Allocation * | 406 Allocation * |  |  |  | Project Status
FAASt number pending | FAASt [Region 1 San Juan Distribution sensitive areas] (Vegetation) | Vegetation | N/A | 0 | 136954530 | 36628489.0485 | 100284954.5925 |  |  |  | Pending COR3 reviews on submitted Non-Sensitive Group C projects. Once review is received team will amend if necessary and submit to FEMA directly.
FAASt number pending | FAASt [Region 2 Arecibo Distribution sensitive areas] (Vegetation) | Vegetation | N/A | 0 | 188729100 | 50475597.795 | 138196883.475 |  |  |  | Pending COR3 reviews on submitted Non-Sensitive Group C projects. Once review is received team will amend if necessary and submit to FEMA directly.
FAASt number pending | FAASt [Region 3 Bayamon Distribution sensitive areas] (Vegetation) | Vegetation | N/A | 0 | 33723810 | 9019432.9845 | 24694259.8725 |  |  |  | Pending COR3 reviews on submitted Non-Sensitive Group C projects. Once review is received team will amend if necessary and submit to FEMA directly.
FAASt number pending | FAASt [Region 4 Caguas Distribution sensitive areas] (Vegetation) | Vegetation | N/A | 0 | 165176460 | 44176444.227 | 120950462.835 |  |  |  | Pending COR3 reviews on submitted Non-Sensitive Group C projects. Once review is received team will amend if necessary and submit to FEMA directly.
FAASt number pending | FAASt [Region 5 Mayaguez Distribution sensitive areas] (Vegetation) | Vegetation | N/A | 0 | 218058975 | 58319872.8638 | 159673684.4437 |  |  |  | Pending COR3 reviews on submitted Non-Sensitive Group C projects. Once review is received team will amend if necessary and submit to FEMA directly.
FAASt number pending | FAASt [Region 6 Ponce Distribution sensitive areas] (Vegetation) | Vegetation | N/A | 0 | 160503255 | 42926595.5498 | 117528508.4737 |  |  |  | Pending COR3 reviews on submitted Non-Sensitive Group C projects. Once review is received team will amend if necessary and submit to FEMA directly.
FAASt number pending | 38kV Transmission Line 100 – Entire Line (Vegetation) | Vegetation | N/A | 0 | 5136889.56 | 428416.5893 | 4708472.9707 |  |  |  | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE
FAASt number pending | 38kV Transmission Line 200 – Entire Line (Vegetation) | Vegetation | N/A | 0 | 3130292.05 | 261066.357 | 2869225.693 |  |  |  | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE
FAASt number pending | 38kV Transmission Line 800 – Entire Line (Vegetation) | Vegetation | N/A | 0 | 3249603.27 | 271016.9127 | 2978586.3573 |  |  |  | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE
FAASt number pending | 38kV Transmission Line 1200 – Entire Line (Vegetation) | Vegetation | N/A | 0 | 5555563.43 | 463333.9901 | 5092229.4399 |  |  |  | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE
FAASt number pending | 38kV Transmission Line 1600 – Entire Line (Vegetation) | Vegetation | N/A | 0 | 6154288.74 | 513267.6809 | 5641021.0591 |  |  |  | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE
FAASt number pending | 38kV Transmission Line 2000 – Entire Line (Vegetation) | Vegetation | N/A | 0 | 6117410.71 | 510192.0532 | 5607218.6568 |  |  |  | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE
FAASt number pending | 38kV Transmission Line 2100 – Entire Line (Vegetation) | Vegetation | N/A | 0 | 6141272.97 | 512182.1657 | 5629090.8043 |  |  |  | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE
FAASt number pending | 38kV Transmission Line 2200 – Entire Line (Vegetation) | Vegetation | N/A | 0 | 16228492.86 | 1353456.3045 | 14875036.5555 |  |  |  | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE
FAASt number pending | 38kV Transmission Line 2500 – Entire Line (Vegetation) | Vegetation | N/A | 0 | 4904775.04 | 409058.2383 | 4495716.8017 |  |  |  | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE
FAASt number pending | 38kV Transmission Line 2700 – Entire Line (Vegetation) | Vegetation | N/A | 0 | 8256335.2 | 688578.3557 | 7567756.8443 |  |  |  | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE
FAASt number pending | 38kV Transmission Line 3000 – Entire Line (Vegetation) | Vegetation | N/A | 0 | 9898491.21 | 825534.1669 | 9072957.0431 |  |  |  | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE
FAASt number pending | 38kV Transmission Line 3100 – Entire Line (Vegetation) | Vegetation | N/A | 0 | 13100370.02 | 1092570.8597 | 12007799.1603 |  |  |  | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE
FAASt number pending | 38kV Transmission Line 3700 – Entire Line (Vegetation) | Vegetation | N/A | 0 | 9475478.76 | 790254.9286 | 8685223.8314 |  |  |  | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE
FAASt number pending | 38kV Transmission Line 3800 – Entire Line (Vegetation) | Vegetation | N/A | 0 | 5113027.32 | 426426.4785 | 4686600.8415 |  |  |  | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE
FAASt number pending | 38kV Transmission Line 4000 – Entire Line (Vegetation) | Vegetation | N/A | 0 | 2279928.56 | 190146.0419 | 2089782.5181 |  |  |  | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE
FAASt number pending | 38kV Transmission Line 4800 – Entire Line (Vegetation) | Vegetation | N/A | 0 | 8629453.86 | 719696.4519 | 7909757.4081 |  |  |  | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE
FAASt number pending | 38kV Transmission Line 5300 – Entire Line (Vegetation) | Vegetation | N/A | 0 | 3345052.23 | 278977.356 | 3066074.874 |  |  |  | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE
FAASt number pending | 38kV Transmission Line 5400 – Entire Line (Vegetation) | Vegetation | N/A | 0 | 5807201.58 | 484320.6118 | 5322880.9682 |  |  |  | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE
FAASt number pending | 38kV Transmission Line 5600 – Entire Line (Vegetation) | Vegetation | N/A | 0 | 5915666.32 | 493366.5711 | 5422299.7489 |  |  |  | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE
FAASt number pending | 38kV Transmission Line 6500 – Entire Line (Vegetation) | Vegetation | N/A | 0 | 9019926.9 | 752261.9035 | 8267664.9965 |  |  |  | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE
[5 empty] | 1040605650.59 | 253010556.4857 | 787324150.2653

## EX-4 289 (hidden)
Prioritization Code | Work Completed | Project # | Project Title | Asset | Sub Asset | 428 Cost Estimate** | 406 Cost Estimate** | Project CMI Index*** | PREPA Note: Cost incurred as reported by LUMA.
3 |  | 166707 | FAASt - Line 51300 (230KV) - Ponce TC to Costa Sur SP TC (Transmission) | Transmission | Line Rebuild | 31809353 | 16781976 | - | 3608812.084
3 |  | 166860 | FAASt-Line 37800 (115kV) - Jobos TC to Cayey TC & Cayey TC to Caguas TC (Transmission) | Transmission | Line Rebuild | 82012589 | 19709323 | 1901250 | 3598975.7371
3 |  | 166904 | FAASt Transmission 115kV Line 37800 Caguas TC to Monacillos TC (TRANSMISSION) | Transmission | Line Rebuild | 50400588 | 9229435 | 49144 | 1948376.1788
3 |  | 167168 | FAASt [Transmission 115kV Line 37100 Costa Sur ST - Acacias TC] (Transmission) | Transmission | Line Rebuild | 106645232 | 24646695 | - | 3937552.0535
1 |  | 167443 | FAASt - Line 36200 (115KV)- Monacillos TC to Juncos TC (Transmission) | Transmission | Line Rebuild | 69007311 | 15967020 | 3320494 | 2448557.1254
3 |  | 167508 | FAASt Transmission - Line 50100 (230KV)- Cambalache GP TC to Manati TC (Transmission) | Transmission | Line Rebuild | 78788689 | 4609955 | 5311721 | 1597570.5002
3 |  | 169503 | FAASt [Ceiba Baja TRF 7012] (Substation) | Substation | Rebuild | 2700000 | Unknown at this time* | - | 2833.4086
6 |  | 169804 | FAASt Aguadilla Electric Service Center (Building) | Buildings | N/A | 3500000 | Unknown at this time* | - | 3874.9818
3 |  | 176954 | FAASt Garzas 1 HP to Garzas 2 HP - 38kV Line 1100 (Transmission) | Transmission | Line Rebuild | 3362636 | 4127356 |  | 797928.4651
1 |  | 177134 | FAASt Guaraguao TC to Comerio TC Line-4100 (Transmission) | Transmission | Line Rebuild | 59675336 | 7821691 | 2575209 | 3046937.288
3 |  | 177191 | FAASt - 115kV Line 39000 - Aguas Buenas TC to Caguas TC (Transmission) | Transmission | Line Rebuild | 19407885 | 906873 | - | 2392378.7399
3 |  | 179988 | FAASt [Las Lomas XFMR 1525] (Substation) | Substation | Rebuild | 2400000 | Unknown at this time* | - | 12617.3727
3 |  | 180326 | FAASt - Line 36800 (115kV) - Sabana Llana TC to Canovanas TC to Palmer-Fajardo TC (Transmission) | Transmission | Line Rebuild | 67238777 | 32488767 | - | 3128552.8804
1 |  | 334191 | FAASt [Feeders - Mayaguez Short Term Group 3] (Distribution) | Distribution | Line Rebuild | 44675547 | 38483744 | 31373009 | 6136457.3826
1 |  | 334285 | FAASt [Feeders - Mayaguez Short Term Group 2] (Distribution ) | Distribution | Line Rebuild | 48650571 | 35887745 | 16294175 | 4491909.2427
1 |  | 334293 | FAASt [Feeders - 7805-11- Mayaguez Short Term Group 4] (Distribution ) | Distribution | Line Rebuild | 47224922 | 45582792 | 17240242 | 5316284.9282
1 |  | 334308 | FAASt [Feeders - Mayaguez Short Term Group 1] (Distribution ) | Distribution | Line Rebuild | 45321705 | 32030114 | 36699234 | 1933182.7212
3 |  | 334331 | FAASt Line 1900 Dos Bocas HP to San Sebastian (38kV) TC (Transmission) | Transmission | Line Rebuild | 33797391.48 | $ - | 10902312 | 0
1 |  | 334420 | FAASt [Feeders - Caguas Short Term Group 1] (Distribution) | Distribution | Line Rebuild | 53581787 | 25596317 | 10696639 | 2698708.5795
1 |  | 334443 | FAASt [Feeders - Caguas Short Term Group 2] (Distribution) | Distribution | Line Rebuild | 61792621 | 51954249 | 15174129 | 4209476.9288
1 |  | 334452 | FAASt [Feeders - Caguas Short Term Group 3] (Distribution) | Distribution | Line Rebuild | 45752407 | 20046792 | 28589222 | 1247874.917
3 |  | 334469 | FAASt [Line 8900 Monacillos TC to Adm. Tribunal Apelaciones] (Transmission) | Transmission | Line Rebuild | 11510000 | Unknown at this time* | - | 817564.1495
1 |  | 334471 | FAASt [Feeders -1303-01- San Juan Short Term Group 1] (Distribution) | Distribution | Line Rebuild | 42950154 | 26997816 | 95277611 | 549949.6851
1 |  | 334472 | FAASt [Feeders - San Juan Short Term Group 2] (Distribution) | Distribution | Line Rebuild | 18783750 | 5366655 | 18912627 | 2955902.4688
1 |  | 334473 | FAASt [Feeders - 1806-02- Bayamon Short Term Group 1] (Distribution) | Distribution | Line Rebuild | 17533060.67 | 1173247.16 | 54964333 | 1028088.4592
1 |  | 334474 | FAASt [Feeders - Bayamon Short Term Group 2] (Distribution) | Distribution | Line Rebuild | 1189290 | 659178 | 4238419 | 470696.4415
1 |  | 334475 | FAASt [Feeders - Bayamon Short Term Group 3] (Distribution) | Distribution | Line Rebuild | 50435894 | 17884283 | 26849273 | 2301557.9237
1 |  | 334476 | FAASt [Feeders - Carolina Short Term Group 2] (Distribution) | Distribution | Line Rebuild | 18285383 | 18767542 | 15778657 | 2202834.1349
1 |  | 334477 | FAASt [Feeders - 2402-02 - Carolina Short Term Group 3] (Distribution) | Distribution | Line Rebuild | 22922128 | 23907802 | 26677862 | 650351.0656
3 |  | 334482 | FAASt [Line 3000 (38 kV) Monacillos TC to Juncos TC] (Transmission) | Transmission | Line Rebuild | 90440000 | Unknown at this time* | 11075470 | 3704493.9598
1 |  | 334491 | FAASt [Feeders - Caguas Short Term Group 5] (Distribution) | Distribution | Line Rebuild | 19546933 | 13582684 | 15994807 | 955248.512
1 |  | 334497 | FAASt [Feeders - Caguas Short Term Group 6 (Distribution) | Distribution | Line Rebuild | 67950718 | 22180767 | 22053869 | 3655161.4369
1 |  | 334518 | FAASt [Feeders - Caguas Short Term Group 7] (Distribution) | Distribution | Line Rebuild | 12225881 | 7784267 | 13706359 | 864138.9086
1 |  | 436616 | FAASt [Feeders - Arecibo Short Term Group 1] (Distribution) | Distribution | Line Rebuild | 27194288 | 14494388 | 23615501 | 2810036.8856
1 |  | 546374 | FAASt [Feeders - 1620-02 - San Juan Short Term Group 3] (Distribution) | Distribution | Line Rebuild | 21058160 | 12777559 | 28204028 | 2606114.0224
1 |  | 546386 | FAASt [Feeders- El Yunque 2305 - Supply] (Distribution) | Distribution | Line Rebuild | 6564391 | 23252037 | 1305621 | 1878790.7388
3 |  | 547160 | FAASt [Line 1200 Mayaguez GP to Yauco 2 HP] (Transmission) | Transmission | Line Rebuild | 55370000 | Unknown at this time* | 105412 | 3822411.0079
3 |  | 547221 | FAASt [Line 3600 Monacillos TC to Martin Peña TC] (Transmission) | Transmission | Line Rebuild | 39980000 | Unknown at this time* | 4883154 | 1227208.9192
3 |  | 547226 | FAASt Barceloneta 11400 TC to Florida TO (Transmission) | Transmission | Line Rebuild | 13810000 | Unknown at this time* | 2101152 | 1041841.9612
3 |  | 547241 | FAASt Tallaboa 5402 | Substation | Rebuild | 10924436 | 5628609 | 511368 | 1003746.6064
3 |  | 547243 | FAASt Egozcue - 1109 (Substation) | Substation | Rebuild | 13896445.76 | 6952342.26 | - | 1164148.7407
1 |  | 547247 | Cambalache TC | Substation | Rebuild | 5463505.9 | 84733286.06 | 95438 | 4043392.902
3 |  | 547248 | FAASt Canas TC 5002 5018 (Substation) | Substation | Rebuild | 1700000 | Unknown at this time* | 5779327 | 103034.7219
3 |  | 547259 | FAASt Line 2700 (38kV) Victoria TC to Quebradillas Sect. (Transmission) | Transmission | Line Rebuild | 70974726 | 55843908 | 22389259 | 1874505.4311
3 |  | 547269 | FAASt Line 2800 (38 kV) Aguadilla Hospital Distrito Sect to T-Bone TO (Transmission) | Transmission | Line Rebuild | 36113917 | 11466633 | 681098 | 1432400.6344
3 |  | 547273 | FAASt Charco Hondo Substation 8008 Relocation (Substation) | Substation | Rebuild | 16300000 | Unknown at this time* | 1180531 | 680018.9386
3 |  | 547343 | FAASt [Victoria TC 7008 Relocation] (Substation) | Substation | Rebuild | 6846444.9 | 54844288.98 | - | 3070074.3236
1 |  | 547344 | FAASt [Acacias 6801 TC Relocation] (Substation) | Substation | Rebuild | 8874442.51 | 42895135.02 | 82566 | 608149.9893
3 |  | 547350 | FAASt [Line 13300 Bayamon TC to Plaza del Sol] (Transmission) | Transmission | Line Rebuild | 5390000 | Unknown at this time* | - | 1630434.4546
6 |  | 548393 | FAASt Arecibo Region Repairs (Buildings) | Buildings | N/A | 9226902 | Unknown at this time* | - | 9515.5061
6 |  | 548440 | FAASt [Mayaguez Region Repairs] (Building) | Buildings | N/A | 13346360 | Unknown at this time* | - | 21589.5284
6 |  | 548596 | FAASt [San German Electrical Service Center] (Building) | Buildings | N/A | 2478182 | Unknown at this time* | - | 27536.6464
3 |  | 548598 | FAASt [Line 36200 (115 kV) Fajardo to Rio Blanco] (Transmission) | Transmission | Line Rebuild | 42190487 | 15963429 | - | 1185163.5125
4 |  | 549768 | FAASt Physical Security - Group 5 (Substation) | Substation | Physical Security | 1200000 | Unknown at this time* | - | 82382.7023
3 |  | 550019 | FAASt [Line 600 Caguas TC to Gautier Benitez Sect.] (Transmission) | Transmission | Line Rebuild | 22133515 | 4035264 | 9639076 | 991652.8899
6 |  | 550060 | FAASt [Caguas Region Repairs] (Building) | Buildings | N/A | 14472109 | Unknown at this time* | - | 15980.5363
3 |  | 550070 | FAASt [Line 4000 Comerio HP to Escuela Francisco Morales] (Transmission) | Transmission | Line Rebuild | 22330000 | Unknown at this time* | 1740931 | 805737.1639
1 |  | 550099 | FAASt [Esc. Industrial M. Such - 1423] (Substation) | Substation | Rebuild | 9916473.34 | 6851320.87 | - | 756489.2654
3 |  | 550162 | FAASt [Berwind TC - 1336] (Substation) | Substation | Rebuild | 44950547 | 6718315 | 11831355 | 1583602.3873
3 |  | 550498 | FAASt - [Morovis 8801 (Fuse to Breaker)] (Substation) | Substation | Rebuild | 16300000 | Unknown at this time* | 6286376 | 193805.43
6 |  | 550500 | FAASt - Ponce Region Repairs (Building) | Buildings | N/A | 20294279 | Unknown at this time* | - | 30407.6646
3 |  | 550771 | FAASt [Caguas TC] (Substation) | Substation | Rebuild | 2500000 | Unknown at this time* | 470415 | 183551.475
3 |  | 550894 | FAASt [Baldrich - 1422] (Substation) | Substation | Rebuild | 973098 | 28669863 | 9906 | 1021656.695
3 |  | 550902 | FAASt [Line 9700 Palo Seco SP to Bay View Sect.] (Transmission) | Transmission | Line Rebuild | 2320000 | Unknown at this time* | - | 1134705.5626
3 |  | 550972 | FAASt [Fonalledas GIS Rebuilt 1401 1421] (Substation) | Substation | Rebuild | 31400000 | Unknown at this time* | 405962 | 70535.1059
3 |  | 550980 | FAASt [Parques y Recreos - 1002] (Substation) | Substation | Rebuild | 11737497.05 | 8962734.08 | 32706 | 946949.0106
3 |  | 550986 | FAASt Condado - 1133 | Substation | Rebuild | 10649911 | 5427167 | 563624 | 1085279.5118
3 |  | 550998 | FAASt [Santurce Planta (Sect) 1116] (Substation) | Substation | Rebuild | 9900000 | Unknown at this time* | - | 77750.5326
3 |  | 551067 | FAASt [Line 11100 Canovanas Sect. to GOAB 11115] (Transmission) | Transmission | Line Rebuild | 3790000 | Unknown at this time* | - | 1490350.1041
3 |  | 551100 | FAASt [Bayview Sectionalizer 1802 Relocation] (Substation) | Substation | Rebuild | 16700000 | Unknown at this time* | 144485 | 116459.5442
6 |  | 551242 | FAASt [Bayamon Region Repairs] (Building) | Buildings | N/A | 15451305 | Unknown at this time* | - | 51403.8725
6 |  | 551247 | FAASt [Palo Seco South Building Repairs] (Building) | Buildings | N/A | 11170493 | Unknown at this time* | - | 627910.7671
1 |  | 551260 | Guaynabo Pueblo Substation | Substation | Rebuild | 22381506.84 | 10941966.54 | - | 582355.3529
6 |  | 551827 | FAASt [San Juan Region Repair] (Building) | Buildings | N/A | 31028730 | Unknown at this time* | - | 60115.673
1 |  | 551911 | FAASt [Line 9100 (38 kV) - Guaraguao TC to Bayamon Pueblo Sect.] (Transmission) | Transmission | Line Rebuild | 5050000 | Unknown at this time* | 1026648 | 1436006.8562
3 |  | 551912 | FAASt Puerto Nuevo - 1520 | Substation | Rebuild | 12192278 | 6035307 | 604500 | 926841.3773
1 |  | 551916 | FAASt [Dorado TC Relocation] (Substation) | Substation | Rebuild | 40100000 | Unknown at this time* | 24976 | 156110.8208
3 |  | 551918 | FAASt Crematorio - 1512 | Substation | Rebuild | 12718285 | 6048401 | - | 977307.1031
1 |  | 551927 | 551927 SCADA Remote Access and RTU Replacements Group 3 | IT/OT | N/A | 19213188.6 | 3299617.88 | - | 232985.6099
1 |  | 668665 | Cybersecurity Program Implementation | IT/OT | N/A | 24587256.13 | $ - | - | 1.8
3 |  | 668669 | FAASt [Line 50500 230kV Mayaguez TC - Mora TC - Cambalache Power Plant] (Transmission) | Transmission | Line Rebuild | 307465 | $ - | - | 82887.4247
1 |  | 673920 | FAASt [Isla Grande 1101] (Substation) | Substation | Rebuild | 600000 | Unknown at this time* | - | 75265.8634
4 |  | 674506 | FAASt [Field Area Network (FAN)] (Telecommunication) | Telecommunication | N/A | 330000000 | Unknown at this time* | - | 3007162.9263
1 |  | 675345 | IT OT Technology Systems Reparations Group 1 | IT/OT | N/A | 9177181.22 | $ - | - | 0
4 |  | 675406 | FAASt [Two-Way Land Mobile Radio Network] (Telecommunication) | Telecommunication | N/A | 46200000 | Unknown at this time* | - | 601979.8895
6 |  | 679006 | FAASt [Test and Technology Laboratory] (Building) | Buildings | N/A | 13125830 | 8186857 | - | 808548.9153
1 |  | 679035 | Telecom Infrastructure – Group A | IT/OT | N/A | 5900000 | Unknown at this time* | - | 696459.2847
1 |  | 682331 | FAASt [RTU and Telecommunication Replacements Group 1 - Mayaguez Area] (Telecommunication) | Telecommunication | N/A | 4360000 | Unknown at this time* | - | 247430.5719
3 |  | 704763 | FAASt [Telecom Infrastructure Group C] (Telecommunication) | Telecommunication | N/A | 2800000 | Unknown at this time* | - | 56988.747
1 |  | 704805 | Telecom Infrastructure – Group D | IT/OT | N/A | 6905000 | Unknown at this time* | - | 554625.412
1 |  | 705503 | FAASt [Pole and Conductor Repair Mayaguez Groups 15,16,17,18 & 19] (Distribution) | Distribution | Pole and Conductors | 1617942 | 192105 | 7689242 | 286601.1062
1 |  | 710026 | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 17] (Distribution) | Distribution | Pole and Conductors | 1250000 | Unknown at this time* | 393833 | 4914.4397
1 |  | 710045 | FAASt [Distribution Pole and Conductor Repair -Mayaguez Group 20] (Distribution) | Distribution | Pole and Conductors | 1250000 | Unknown at this time* | 309678 | 2851.2214
1 |  | 710363 | FAASt [Distribution Pole and Conductor Repair - Bayamon Group 15] (Distribution) | Distribution | Pole and Conductors | 1250000 | Unknown at this time* | 964240 | 4537.5183
1 |  | 710498 | FAASt [Distribution Pole and Conductor Repair - Bayamon Group 16] (Distribution) | Distribution | Pole and Conductors | 1250000 | Unknown at this time* | 2650989 | 4796.879
3 |  | 711829 | FAASt [Santa Isabel Sect. - Salinas Sect. 38kV Line 100] (Transmission) | Transmission | Line Rebuild | 1309000 | Unknown at this time* | - | 17828.4
3 |  | 711862 | FAASt [TL100 Ponce TC to Santa Isabel Sect](Transmission) | Transmission | Line Rebuild | 1232000 | Unknown at this time* | 2243657 | 85524.34
1 |  | 711962 | FAASt [Distribution Pole and Conductor Repair -Mayaguez Group 21] (Distribution) | Distribution | Pole and Conductors | 1250000 | Unknown at this time* | 607800 | 1411.39
3 |  | 712978 | FAASt [Once de Agosto Sect. - San Sebastian TC 38kV Line 2000] (Transmission) | Transmission | Line Rebuild | 1848000 | Unknown at this time* | 6510844 | 462632.5925
1 |  | 712981 | FAASt [Distribution Pole and Conductor Repair - Ponce Group 24] (Distribution) | Distribution | Pole and Conductors | 1250000 | Unknown at this time* | 280094 | 3526.6581
1 |  | 712982 | FAASt [Distribution Pole and Conductor Repair “ Mayaguez Group 23] (Distribution) | Distribution | Pole and Conductors | 1250000 | Unknown at this time* | 314700 | 976.3
1 |  | 715610 | FAASt [Network Upgrades to Support the Integration of Tranche 1 Utility Scale Renewable Projects] (Transmission) | Transmission | N/A | 144745493 | $ - | - | 0
3 |  | 718951 | FAASt [Line 51200- Costa Sur Steam Plant to Cambalache Gas Plant (230kV)] (Transmission) | Transmission | Line Rebuild | 96340724 | 64652304 | 70035 | 1355858.3542
3 |  | 718955 | FAASt [Line 50200 (230kv) from Costa Sur SP to Bayamon TC] (Transmission) | Transmission | Line Rebuild | 152903037 | 88423396 | - | 2160662.295
1 |  | 730513 | FAASt [Feeders-Caguas Short Term Group 4] (Distribution) | Distribution | Line Rebuild | 27818562 | 10929872 | 19223158 | 820731.7285
1 |  | 730541 | FAASt [Feeders - Caguas Short Term Group 8] (Distribution) | Distribution | Line Rebuild | 14523276 | 18671456 | 6966428 | 2699976.8293
1 |  | 730586 | FAASt [Feeders - Ponce Short Term Group 1] (Distribution) | Distribution | Line Rebuild | 18969808 | 12719346 | 24497843 | 2520815.2701
3 |  | 730784 | FAASt [ Line 6700 Martin Peña TC to Villamar Sect.] (Transmission) | Transmission | Line Rebuild | 6010000 | Unknown at this time* | - | 553457.1474
1 |  | 730821 | FAASt [Feeders - Arecibo Short Term Group 2] (Distribution) | Distribution | Line Rebuild | 59530905 | 27363279 | 21287510 | 2315424.0192
1 |  | 730824 | FAASt [Feeders - Ponce Short Term Group 2] (Distribution) | Distribution | Line Rebuild | 4115433 | 2840853 | 9020980 | 2469184.0296
5 |  | 734393 | FAASt [Cabo Rojo Streetlighting - Part 2] (Distribution) | Distribution | Streetlighting | 9689984 | 1016421 | - | 368164.5924
5 |  | 734396 | FAASt [Cabo Rojo Streetlighting - Part 3] (Distribution) | Distribution | Streetlighting | 8681446 | 1169678 | - | 279402.37
5 |  | 734728 | FAASt [Ponce Streetlighting - Part 2] (Distribution) | Distribution | Streetlighting | 15473821 | 1402396 | - | 576591.0625
5 |  | 734760 | FAASt [Ponce Streetlighting - Part 3] (Distribution) | Distribution | Streetlighting | 16496158 | 1946734 | - | 700282.6237
5 |  | 734789 | FAASt [Guayama Streetlighting - Part 3 ] (Distribution) | Distribution | Streetlighting | 7740886 | 635977 | - | 284974.0563
5 |  | 734791 | FAASt [Guayama Streetlighting - Part 2] (Distribution) | Distribution | Streetlighting | 7187688 | 757008 | - | 444378.4121
5 |  | 734853 | FAASt [Arecibo Streetlighting- Part 3] (Distribution) | Distribution | Streetlighting | 18601760 | 2684586 | - | 570019.4613
5 |  | 734859 | FAASt [Aguadilla Streetlighting - Part 2] (Distribution) | Distribution | Streetlighting | 10873634 | 1346103 | - | 299181.0955
5 |  | 734927 | FAASt [Isabela Streetlighting - Part 2] (Distribution) | Distribution | Streetlighting | 9842173 | 1301829 | - | 307234.7543
5 |  | 734928 | FAASt [Isabela Streetlighting - Part 3] (Distribution) | Distribution | Streetlighting | 5293882 | Unknown at this time* | - | 325090.2142
5 |  | 735131 | FAASt [Arecibo Streetlighting - Part 2] (Distribution) | Distribution | Streetlighting | 13584221 | 1546160 | - | 502636.2472
5 |  | 735338 | FAASt [Aguadilla Streetlighting - Part 3] (Distribution) | Distribution | Streetlighting | 10052144 | 1423703 | - | 313598.7042
5 |  | 735357 | FAASt [Mayaguez Streetlighting - Part 2] (Distribution) | Distribution | Streetlighting | 9099250 | 1097078 | - | 331496.5971
5 |  | 735360 | FAASt [Mayaguez Streetlighting - Part 3] (Distribution) | Distribution | Streetlighting | 16626757 | 2189842 | - | 934387.4878
5 |  | 735470 | FAASt [Bayamón Streetlighting - Part 2] (Distribution) | Distribution | Streetlighting | 20995636 | 1727642 | - | 704279.1344
5 |  | 735472 | FAASt [Bayamon Streetlighting - Part 3] (Distribution) | Distribution | Streetlighting | 21541265 | 2632407 | - | 732514.3639
5 |  | 735483 | FAASt [Vega Baja Streetlighting - Part 3] (Distribution) | Distribution | Streetlighting | 5377685 | Unknown at this time* | - | 265060.8232
5 |  | 735487 | FAASt [Humacao Streetlighting - Part 3] (Distribution) | Distribution | Streetlighting | 9528251 | 916292 | - | 282001.7815
5 |  | 735493 | FAASt [Humacao Streetlighting - Part 2] (Distribution) | Distribution | Streetlighting | 7901161 | 916292 | - | 323070.3827
5 |  | 735496 | FAASt [Carolina Streetlighting - Part 3] (Distribution) | Distribution | Streetlighting | 17520900 | 2019124 | - | 684269.2404
5 |  | 735499 | FAASt [Guaynabo Streetlighting - Part 3] (Distribution) | Distribution | Streetlighting | 7033301 | Unknown at this time* | - | 375117.0609
5 |  | 735665 | FAASt [Carolina Streetlighting - Part 2] (Distribution) | Distribution | Streetlighting | 14631273 | 557536 | - | 795533.7884
5 |  | 735672 | FAASt [Caguas Streetlighting - Part 3] (Distribution) | Distribution | Streetlighting | 14419460 | 1624355 | - | 752637.6699
5 |  | 735677 | FAASt [Guaynabo Streetlighting - Part 2] (Distribution) | Distribution | Streetlighting | 9325726 | 1014066 | - | 384723.7068
5 |  | 735940 | FAASt [Vega Baja Streetlighting - Part 2] (Distribution) | Distribution | Streetlighting | 9309981 | 1067250 | - | 312934.4556
5 |  | 735952 | FAASt [Trujillo Alto Streetlighting - Part 3] (Distribution) | Distribution | Streetlighting | 8838122 | 1149506 | - | 369426.5196
5 |  | 735954 | FAASt [Trujillo Alto Streetlighting - Part 2] (Distribution) | Distribution | Streetlighting | 8062571 | 884864 | - | 251905.5179
5 |  | 735959 | FAASt [Toa Baja Streetlighting - Part 3] (Distribution) | Distribution | Streetlighting | 5878458 | Unknown at this time* | - | 300482.7232
5 |  | 735960 | FAASt [Toa Baja Streetlighting - Part 2] (Distribution) | Distribution | Streetlighting | 9782523 | 1238774 | - | 310039.3601
5 |  | 737699 | FAASt [Toa Alta Streetlighting - Part 3] (Distribution) | Distribution | Streetlighting | 5526895 | Unknown at this time* | - | 221129.0632
5 |  | 737707 | FAASt [Toa Alta Streetlighting - Part 2] (Distribution) | Distribution | Streetlighting | 8808053 | 979674 | - | 361964.5876
5 |  | 737712 | FAAST [San Juan Streetlighting - Part 3] (Distribution) | Distribution | Streetlighting | 31581739 | 3250259 | - | 1103176.918
5 |  | 737798 | FAASt [Rio Grande Streetlighting - Part 3] (Distribution) | Distribution | Streetlighting | 8572353 | 877731 | - | 239034.4414
5 |  | 737804 | FAASt [Rio Grande Streetlighting - Part 2 ] (Distribution) | Distribution | Streetlighting | 7692944 | 838135 | - | 279296.8181
1 |  | 738667 | FAASt [Pole and Conductor Repair - Ponce Group 2 - Phase 2] (Distribution) | Distribution | Pole and Conductors | 16618201.69 | 33268.04 | 9020080 | 388467.3873
1 |  | 738674 | FAASt [Pole and Conductor Repair - Mayaguez Group 2 - Phase 2] (Distribution) | Distribution | Pole and Conductors | 8935837.49 | 28130.53 | 16214772 | 151666.3849
1 |  | 738692 | FAASt [Pole and Conductor Repair - Carolina Group 1 - Phase 2] (Distribution) | Distribution | Pole and Conductors | 5100000 | Unknown at this time* | 1389009 | 68472.3948
4 |  | 744072 | Network and Communication Infrastructure Group 2 | IT/OT | N/A | 2074582.38 | 490438.07 | - | 0
1 |  | 745851 | FAASt [Automation Program Group 11] (Distribution) | Distribution | Automation | 479854 | 1052298 | 7582100 | 54384.51
1 |  | 745852 | FAASt [Automation Program Group 13] (Distribution) | Distribution | Automation | 888426 | 1966004 | 10542894 | 0
1 |  | 745854 | Automation Program Group 9 | Distribution | Automation | 546905 | 1164604 | 4325227 | 69690.56
1 |  | 745871 | FAASt [Automation Program Group 10] (Distribution) | Distribution | Automation | 278408 | 582637 | 6182284 | 0
5 |  | 746108 | FAASt [San Juan Streetlighting - Part 2] (Distribution) | Distribution | Streetlighting | 30670485 | 3331645 | - | 825087.2097
5 |  | 746111 | FAASt [Caguas Streetlighting - Part 2] (Distribution) | Distribution | Streetlighting | 12311632 | 1317294 | - | 507860.1015
3 |  | 750730 | FAASt [Line 500 Ponce TC to Costa Sur SP] (Transmission) | Transmission | Line Rebuild | 36590000 | Unknown at this time* | 7532939 | 3182054.1984
3 |  | 752052 | FAASt [Transmission Line 9900 TAP9905A to Rio Blanco HP] (Transmission) | Transmission | Line Rebuild | 32110000 | Unknown at this time* | 27200 | 853424.4067
3 |  | 752275 | FAASt [Unibon 9501 (Fuse to Breaker)] (Substation) | Substation | Rebuild | 9157533 | Unknown at this time* | 3238125 | 854707.1284
3 |  | 752276 | FAASt [Monterrey 9502 & 9503 (Fuse to Breaker)] (Substation) | Substation | Rebuild | 39664220 | Unknown at this time* | - | 847073.0607
1 | Yes | 752500 | FAASt [Automation Program Group 1B] (Distribution) | Distribution | Automation | 1250000 | Unknown at this time* | 28178299 | 2351288.8086
1 | Yes | 752502 | FAASt [Automation Program Group 1C] (Distribution) | Distribution | Automation | 1250000 | Unknown at this time* | 26170904 | 2110771.7464
1 | Yes | 752503 | FAASt [Automation Program Group 1D-7 Feeders] (Distribution) | Distribution | Automation | 1250000 | Unknown at this time* | 93732526 | 4598604.8577
3 |  | 753302 | FAASt [Telecom Infrastructure Group G] (Telecommunication) | Telecommunication | N/A | 8381000 | Unknown at this time* | - | 29293.72
1 |  | 753777 | FAASt [Line 1500 - Mayaguez GP to GOAB 1515] (Transmission) | Transmission | Line Rebuild | 58661000 | Unknown at this time* | - | 4315244.0467
1 |  | 753781 | Transmission Priority Pole Replacement Program Line 800 Comsat Sect – Cidra Sect | Transmission | Pole Replacement | 726192.42 | 33695.78 | 980869 | 0
1 |  | 753785 | T-Pole TL 3300 San Gerardo Sect to Venezuela Sect | Transmission | Pole Replacement | 336678.78 | $ - | - | 26858.25
1 |  | 753786 | T-Pole TL 5900 San Juan SP to Crematorio TO | Transmission | Pole Replacement | 507064.86 | 24170.88 | 28167 | 86410.14
1 |  | 753787 | T-Pole TL 13700 Mora TC to Isabela TO | Transmission | Pole Replacement | 623574.49 | $ - | - | 46881.12
1 |  | 753788 | Transmission Priority Pole Replacement Program Line 1900 Dos Bocas HP – San Sebastián TC | Transmission | Pole Replacement | 1057925.6 | $ - | 10902312 | 0
1 |  | 757945 | FAASt [Pole and Conductor Repair - Arecibo Group 3 - Phase 2] (Distribution) | Distribution | Pole and Conductors | 2892589.5 | 15039.03 | 12665270 | 0
1 |  | 759004 | FAASt [Pole and Conductor - Arecibo Group 4 - Phase 2] (Distribution) | Distribution | Pole and Conductors | 9280000 | Unknown at this time* | 9523678 | 137733.46
1 |  | 759051 | FAASt [Pole and Conductor Repair - Bayamon Group 4 - Phase 2] (Distribution) | Distribution | Pole and Conductors | 3990000 | Unknown at this time* | 16876646 | 42022.14
1 |  | 760568 | FAASt [Distribution Feeder Rebuild # 1710-01] (Distribution) | Distribution | Line Rebuild | 10467848 | Unknown at this time* | 13567434 | 1702364.2681
1 |  | 760571 | FAASt [Feeder Rebuild # 1720-07] (Distribution) | Distribution | Line Rebuild | 18005134 | Unknown at this time* | 15729896 | 2431790.6879
1 |  | 760575 | FAASt [Distribution Feeder Rebuild # 1716-03] (Distribution) | Distribution | Line Rebuild | 18102407 | Unknown at this time* | 2915747 | 1997457.6386
1 |  | 760577 | FAASt [Feeder Rebuild # 1718-02] (Distribution) | Distribution | Line Rebuild | 8421396 | Unknown at this time* | 2513970 | 1481789.1831
1 |  | 760579 | FAASt [Distribution Feeder Rebuild # 1717-03] (Distribution) | Distribution | Line Rebuild | 14143466 | Unknown at this time* | 10034779 | 1643782.2004
3 |  | 761563 | FAASt [San Jose Relocation] (Substation) | Substation | Rebuild | 17000000 | Unknown at this time* | 587412 | 771723.4472
1 |  | 764706 | FAASt [Feeder Rebuild # 7011-03] (Distribution) | Distribution | Line Rebuild | 9329781.4 | Unknown at this time* | 3042802 | 1436564.883
1 |  | 764708 | FAASt [Feeder Rebuild # 5602-02] (Distribution) | Distribution | Line Rebuild | 5190387.52 | Unknown at this time* | 2348975 | 1648769.325
1 |  | 764709 | FAASt [Feeder Rebuild # 1204-05] (Distribution) | Distribution | Line Rebuild | 8740820.93 | Unknown at this time* | 20808315 | 1557386.3473
1 |  | 767005 | FAASt [Feeder Rebuild # 1303-05] (Distribution) | Distribution | Line Rebuild | 12631766 | Unknown at this time* | 5017441 | 1715305.6358
1 |  | 767139 | FAASt [Feeder Rebuild # 2906-02] (Distribution) | Distribution | Line Rebuild | 3205041 | Unknown at this time* | 3835226 | 1506271.5511
1 |  | 767381 | FAASt [Feeder Rebuild # 1204-04] (Distribution) | Distribution | Line Rebuild | 9998489 | Unknown at this time* | 35283077 | 1423976.1915
1 |  | 767387 | FAASt # [Distribution Feeder Rebuild # 1303-01] (Distribution) | Distribution | Line Rebuild | 4798378.99 | Unknown at this time* | 3285038 | 1187471.9856
1 |  | 790427 | FAASt [Pole and Conductor Repair -Caguas Group 5 Phase 2 (Distribution) | Distribution | Pole and Conductors | 9241836.74 | 71738.97 | 12943254 | 88.3934
1 |  | 790446 | FAASt [Pole and Conductor Repair -Caguas Group 4 Phase 2 (Distribution) | Distribution | Pole and Conductors | 4662521.3 | 28582.12 | 19223158 | 88.3934
1 |  | 800369 | FAASt [Automation Program Group 38] (Distribution) | Distribution | Automation | 1335000 | Unknown at this time* | 8638511 | 69686.9
1 |  | 800394 | FAASt [Automation Program Group 39] (Distribution) | Distribution | Automation | 3084000 | Unknown at this time* | 8607462 | 100561.8
1 |  | 800399 | FAASt [Automation Program Group 40] (Distribution) | Distribution | Automation | 2577000 | Unknown at this time* | 6258034 | 227154.2
1 |  | 801197 | FAASt [Feeder Rebuild # 1204-02] (Distribution) | Distribution | Line Rebuild | 3863358 | Unknown at this time* | 18018317 | 2496812.9781
1 |  | 801432 | FAASt [Automation Program Group 41] (Distribution) | Distribution | Automation | 2391000 | Unknown at this time* | 3197977 | 39623.66
1 |  | 801437 | FAASt [Automation Program Group 42] (Distribution) | Distribution | Automation | 2883000 | Unknown at this time* | 2266413 | 18513.84
1 |  | 801438 | FAASt [Automation Program Group 43] (Distribution) | Distribution | Automation | 2490000 | Unknown at this time* | 9630972 | 78517.9
1 |  | 801440 | FAASt [Automation Program Group 44] (Distribution) | Distribution | Automation | 3902000 | Unknown at this time* | 2183977 | 45468.15
1 |  | 801441 | FAASt [Automation Program Group 45] (Distribution) | Distribution | Automation | 2400000 | Unknown at this time* | 8098998 | 41020.36
1 |  | 805517 | 38kV Recloser TL 2100 Hatillo TC to Quebradillas Sect. | Transmission | Automation | 462411.39 | 733123.39 | 19981962 | 134840.5723
1 |  | 805519 | 38kV Recloser TL 1900 Dos Bocas HP to San Sebastian TC | Transmission | Automation | 708408.01 | 769393.29 | 10902312 | 125064.6881
1 |  | 805521 | 38 kv Reclosers TL7800 | Transmission | Automation | 285043.08 | 725071.07 | 1863516 | 165238.7885
1 |  | 806935 | FAASt [Pole and Conductor Repair - Caguas Group 6 - Phase 2] (Distribution) | Distribution | Pole and Conductors | 6120000 | Unknown at this time* | 22053869 | 88.3934
1 |  | 806936 | FAASt [Pole and Conductor Repair - Carolina Group 3 - Phase 2] (Distribution) | Distribution | Pole and Conductors | 5100000 | Unknown at this time* | 26677862 | 207522.49
1 |  | 811913 | Transmission Priority Pole Replacement Program Line 9600 Bayamon TC–Catano Sect | Transmission | Pole Replacement | 420203.89 | 43773.6 | - | 41644.47
1 |  | 811923 | Transmission Priority Pole Replacement Program Line 16500 Fajardo TC-Dos Marinas] (Transmission) | Transmission | Pole Replacement | 260238.98 | 22761.43 | 692580 | 3125
1 |  | 812041 | FAASt [Distribution Feeder Rebuild 9501-02] | Distribution | Line Rebuild | 29244075.05 | $ - | 8319083 | 1420346.9842
3 |  | 814792 | FAASt [Telecom Infrastructure – Group E] | Telecommunication | N/A | 5600000 | Unknown at this time* | - | 724644.5569
3 |  | 814793 | FAASt [Telecom Infrastructure – Group F] | Telecommunication | N/A | 4600000 | Unknown at this time* | - | 571502.2365
1 |  | 817242 | FAASt [Pole and Conductor Repair -Caguas Group 8 - Phase 2 | Distribution | Pole and Conductors | 2040000 | Unknown at this time* | 6966428 | 87328.76
1 |  | 817247 | FAASt [Pole and Conductor Repair -Ponce Group 3 - Phase 2 | Distribution | Pole and Conductors | 11650000 | Unknown at this time* | 4881214 | 326824.92
1 |  | 817249 | FAASt [Pole and Conductor Repair -Caguas Group 7 - Phase 2 | Distribution | Pole and Conductors | 5100000 | Unknown at this time* | 13706359 | 189569.15
1 |  | 817250 | FAASt [Pole and Conductor Repair -San Juan Group 4 - Phase 2 | Distribution | Pole and Conductors | 7610000 | Unknown at this time* | 15217191 | 112152.37
1 |  | 817961 | FAASt [Feeder Rebuild # 2404-06] (Distribution) | Distribution | Line Rebuild | 21344413.71 | 399260.06 | 10278350 | 1258259.94
1 |  | 817962 | FAASt # [Distribution Feeder Rebuild # 9403-03] (Distribution) | Distribution | Line Rebuild | 5548949 | Unknown at this time* | 5587305 | 744990.6538
1 |  | 817993 | FAASt # [Distribution Feeder Rebuild # 1801-03] (Distribution) | Distribution | Line Rebuild | 6131846 | Unknown at this time* | 3330173 | 1206246.4546
1 |  | 818006 | FAASt [Feeder Rebuild #2402-02] (Distribution) | Distribution | Line Rebuild | 34516477 | Unknown at this time* | 6951736 | 1551876.9171
1 |  | 818041 | FAASt # [Distribution Feeder Rebuild # 3701-03] (Distribution) | Distribution | Line Rebuild | 24349603.89 | Unknown at this time* | 3621830 | 1726460.0535
1 |  | 818055 | FAASt # [Distribution Feeder Rebuild # 3006-05] (Distribution) | Distribution | Line Rebuild | 8829008 | Unknown at this time* | 3619097 | 1844753.9269
1 |  | 818056 | FAASt # [Distribution Feeder Rebuild # 6305-03] (Distribution) | Distribution | Line Rebuild | 22352214 | Unknown at this time* | 809276 | 1699573.9037
6 |  | 954184 | Carolina Electric Service Center | Buildings | N/A | 2747126.23 | $ - | - | 0
1 |  | 956782 | FAASt [Distribution Feeder Rebuild # 6802-04] (Distribution) | Distribution | Line Rebuild | 21957625.63 | 2769954.18 | 1967764 | 1686843.7527
1 |  | 958367 | FAASt [Distribution Feeder Rebuild #6603-01] (Distribution) | Distribution | Line Rebuild | 14474191.76 | 1172038.62 | 2324294 | 1846415.4454
[6 empty] | 4231292034.11 | 1230982467.91 |  | 218627894.5146
*Projects in the Initial Scope of Work (ISOW) stage do not have a Section 428 vs Section 406 Hazard Mitigation breakdown. The Section 428 and Section 406 split is developed as these projects move forward the FEMA review pipeline and Detailed Scopes of Work (DSOWs) are developed and refined. **Section 428 and 406 Hazard Mitigation cost estimates are derived from currently available project documentation, including Detailed Scopes of Work or Initial Scopes of Work. It is important to note that these cost estimates are subject to change as DSOWs and ISOWs continue to be refined and updated throughout the project development lifecycle. The Section 428 Cost estimates include the costs of the Global FAASt for architecture and engineering (A&E) and equipment and materials (E&M) portions. Once those ISOW and DSOW estimates are refined and ultimately obligated, those portions will be deducted from the already obligated Global FAASt projects. ***The Project CMI Index shows the total customer minutes interrupted for the asset(s) included in the project.
Prioritization Code | Work Completed | Project # | Project Title | Asset | Sub Asset | 428 Cost Estimate** | 406 Cost Estimate** | Project CMI Index*** | PREPA Note: Cost incurred as reported by LUMA.
5 |  | 666894 | FAASt [San Juan Streetlighting] (Distribution) | Distribution | Streetlighting | 35282713 | 3532039 | - | 9298279.867
5 |  | 671396 | FAASt [Utuado Streetlighting] (Distribution) | Distribution | Streetlighting | 21135871 | 2911033 | - | 2590754.716
5 |  | 671400 | FAASt [Barceloneta Streetlighting] (Distribution) | Distribution | Streetlighting | 10053300 | 1109633 | - | 1870270.0067
5 |  | 678794 | FAASt [Ponce Streetlighting] (Distribution) | Distribution | Streetlighting | 18852071 | 1444528 | - | 3449161.3111
5 |  | 678795 | FAASt [Arecibo Streetlighting] (Distribution) | Distribution | Streetlighting | 17274978 | 1527389 | - | 2700117.8517
1 |  | 685869 | FAASt [Mayagüez TC] (Substation) | Substation | Rebuild | 3200000 | Unknown at this time* | - | 1691870.7739
5 |  | 686482 | FAASt [Isabela Streetlighting] (Distribution) | Distribution | Streetlighting | 8712288 | 733835 | - | 1086466.7489
1 | Yes | 688623 | FAASt [Automation Program Group 1A-8 Feeders] (Distribution) | Distribution | Automation | 1005286 | 1877045 | 65601090 | 2196982.6402
5 |  | 690480 | FAASt [Humacao Streetlighting] (Distribution) | Distribution | Streetlighting | 9318022 | 922000 | - | 1201188.8394
5 |  | 690483 | FAASt [Cayey Streetlighting] | Distribution | Streetlighting | 15993979 | 1319139 | - | 2977003.0781
5 |  | 690721 | FAASt [Guayama Streetlighting] (Distribution) | Distribution | Streetlighting | 7045719 | 542958 | - | 1576439.9126
5 |  | 693543 | FAASt [Juncos Streetlighting] (Distribution) | Distribution | Streetlighting | 13468580 | 1643590 | - | 2135253.4613
5 |  | 693615 | FAASt [Rio Grande Streetlighting] (Distribution) | Distribution | Streetlighting | 7956012 | 700108 | - | 963422.2586
5 |  | 693788 | FAASt [Toa Alta Streetlighting] (Distribution) | Distribution | Streetlighting | 7465021 | 481369 | - | 1832461.3423
5 |  | 697183 | FAASt [Vega Baja Streetlighting] (Distribution) | Distribution | Streetlighting | 11188812 | 1117331 | - | 1589561.8546
5 | Yes | 698427 | FAASt [Maricao Streetlighting] (Distribution) | Distribution | Streetlighting | 6223855 | 1028907 | - | 424912.2412
5 | Yes | 698432 | FAASt [Hormigueros Streetlighting] (Distribution) | Distribution | Streetlighting | 8618625 | 968057 | - | 1271792.0483
5 | Yes | 698522 | FAASt [Vieques Streetlighting] (Distribution) | Distribution | Streetlighting | 5760781 | 519326 | - | 1232603.0911
5 |  | 699814 | FAASt [Juana Diaz Streetlighting] (Distribution) | Distribution | Streetlighting | 18680447 | 1909452 | - | 2857940.297
5 |  | 701473 | FAASt [Canovanas Streetlighting] (Distribution) | Distribution | Streetlighting | 16995906 | 1574362 | - | 2143848.1421
5 |  | 704741 | FAASt [Moca Streetlighting] (Distribution) | Distribution | Streetlighting | 22275170.39 | 1110824.64 | - | 569138.8093
5 | Yes | 704744 | FAASt [San Sebastian Streetlighting] (Distribution) | Distribution | Streetlighting | 25971963 | 3663221 | - | 3475900.8049
5 | Yes | 704757 | FAASt [Santa Isabel Streetlighting] (Distribution) | Distribution | Streetlighting | 9707069 | 820333 | - | 2612654.2783
5 | Yes | 704793 | FAASt [Yauco Streetlighting] (Distribution) | Distribution | Streetlighting | 17432028 | 1639888 | - | 3579116.7615
5 | Yes | 704862 | FAASt [Fajardo Streetlighting] (Distribution) | Distribution | Streetlighting | 13631005 | 1104923 | - | 2729086.9486
5 | Yes | 704929 | FAASt [San Lorenzo Streetlighting] (Distribution) | Distribution | Streetlighting | 17124231 | 2284857 | - | 1789937.7352
5 | Yes | 704931 | FAASt [Camuy Streetlighting] (Distribution) | Distribution | Streetlighting | 18265434 | 2269186 | - | 2863205.5514
1 | Yes | 705657 | FAASt [Automation Program Group 3] (TL/Distribution) | Distribution | Automation | 4929019 | 19657460 | 89090626 | 18733892.7796
5 |  | 713795 | FAASt [Lares Streetlighting] (Distribution) | Distribution | Streetlighting | 14590612.85 | 712022.01 | - | 329422.2996
3 |  | 718971 | FAASt [Line 50300 (230kV) from Costa Sur Steam Plant to Aguirre Steam Plant] (Transmission) | Transmission | Line Rebuild | 15889643 | 901810364 | 76187 | 3237481.838
5 |  | 724599 | FAASt [Sabana Grande Streetlighting] (Distribution) | Distribution | Streetlighting | 13386336.57 | 725698.37 | - | 476454.7519
5 |  | 724603 | FAASt [Cabo Rojo Streetlighting] (Distribution) | Distribution | Streetlighting | 11029424 | 1044683 | - | 2396506.337
5 |  | 724605 | FAASt [Guayanilla Streetlighting] (Distribution) | Distribution | Streetlighting | 9591958.43 | 469904.54 | - | 549794.3988
5 |  | 724669 | FAASt [Ciales Streetlighting] (Distribution) | Distribution | Streetlighting | 14800410.24 | 773133.74 | - | 432943.2836
5 |  | 724670 | FAASt [Patillas Streetlighting] (Distribution) | Distribution | Streetlighting | 10290796.35 | 406586.59 | - | 317108.635
5 |  | 724716 | FAASt [Quebradillas Streetlighting] (Distribution) | Distribution | Streetlighting | 13016938.52 | 628110.03 | - | 378917.1938
5 |  | 724781 | FAASt [Penuelas Streetlighting] (Distribution) | Distribution | Streetlighting | 9760940.6 | 408490.41 | - | 283400.0421
5 | Yes | 724828 | FAASt [Loiza Streetlighting] (Distribution) | Distribution | Streetlighting | 8349850 | 816844 | - | 1446366.1873
5 |  | 724941 | FAASt [Aguas Buenas Streetlighting] (Distribution) | Distribution | Streetlighting | 13577880 | 1686477 | - | 656592.3247
2 |  | 727530 | FAASt [Region 6 Ponce Transmission 38kV sensitive areas] (Vegetation) | Vegetation | N/A | $ - | 70421923.26 | - | 5115.75
2 |  | 727540 | FAASt [Region 2 Arecibo Transmission 38kV sensitive areas] (Vegetation) | Vegetation | N/A | $ - | 66510486.76 | - | 4692.54
2 |  | 727558 | FAASt [Region 3 Bayamon Transmission 38kV sensitive areas] (Vegetation) | Vegetation | N/A | $ - | 16374246.76 | - | 3557.75
2 |  | 727562 | FAASt [Region 5 Mayaguez Transmission 38kV sensitive areas] (Vegetation) | Vegetation | N/A | $ - | 84411128.06 | - | 5599.08
2 |  | 727691 | FAASt [Region 1 San Juan Transmission 38kV sensitive areas] (Vegetation) | Vegetation | N/A | $ - | 44200121.5 | - | 38690.58
2 |  | 727694 | FAASt [Region 4 Caguas Transmission 38kV sensitive areas] (Vegetation) | Vegetation | N/A | $ - | 76781710.48 | - | 7762.53
1 |  | 730657 | FAASt [Line 2200 Manati TC to Vega Baja] (Transmission) | Transmission | Line Rebuild | 103800000 | Unknown at this time* | 1461873 | 10122559.5066
1 |  | 738671 | FAASt [25 MW BESS Installation and Integration - Barceloneta] (Substation) | Substation | Grid Modernization | $ - | 55941767.5 | - | 780570.1515
2 |  | 740406 | FAASt[Region 1 San Juan Transmission 38kV - Non-Sensitive (Vegetation)] | Vegetation | N/A | $ - | 5894785.29 | - | 15305.76
2 |  | 740408 | FAASt[Region 3 Bayamon Transmission 38kV - Non-Sensitive (Vegetation)] | Vegetation | N/A | $ - | 11782088.78 | - | 4522.17
2 |  | 740409 | FAASt[Region 4 Caguas Transmission 38kV - Non-Sensitive (Vegetation)] | Vegetation | N/A | $ - | 23846154.02 | - | 8213.12
2 |  | 740410 | FAASt[Region 2 Arecibo Transmission 38kV - Non-Sensitive (Vegetation)] | Vegetation | N/A | $ - | 5425376.76 | - | 8325.36
2 |  | 740411 | FAASt [Region 5 Mayaguez Transmission 38kV - Non-Sensitive (Vegetation)] | Vegetation | N/A | $ - | 3777166.88 | - | 5962.2
2 |  | 740414 | FAASt [Region 6 Ponce Transmission 38kV - Non-Sensitive (Vegetation) | Vegetation | N/A | $ - | 13788400.37 | - | 7859.97
1 | Yes | 740662 | FAASt [Automation Program Group 2] (TL/ Distribution) | Distribution | Automation | 2600293 | 7224272 | 139965750 | 23122671.9099
3 |  | 741097 | Region 1 San Juan Substation/Telecom | Vegetation | N/A | $ - | 1347191.63 | - | 7117.77
3 |  | 741098 | Region 3 Bayamon Substation/Telecom | Vegetation | N/A | $ - | 961518.65 | - | 6241.73
3 |  | 741100 | Region 4 Caguas Substation/Telecom | Vegetation | N/A | $ - | 1428325.86 | - | 3834.42
3 |  | 741101 | Region 2 Arecibo Substation/Telecom | Vegetation | N/A | $ - | 1058188.92 | - | 6452.73
3 |  | 741102 | Region 5 Mayaguez Substation/Telecom | Vegetation | N/A | $ - | 1516985.37 | - | 7244.12
3 |  | 741104 | Region 6 Ponce Substation/Telecom | Vegetation | N/A | $ - | 1992973.53 | - | 4593.01
1 | Yes | 741678 | FAASt [Automation Program Group 4] (TL/Distribution) | Distribution | Automation | 3213239.22 | 10499139.71 | 119761540 | 20078532.7427
4 |  | 748180 | Transmission Advanced Sensors and Wide-Area Monitoring, Protection, and Control (WAMPAC) System | IT/OT | N/A | $ - | 52804979.05 | - | 601196.06
1 |  | 750502 | FAASt [25 MW BESS Installation and Integration - Aguadilla] (Substation) | Substation | Grid Modernization | $ - | 52720520.35 | - | 823738.2364
1 |  | 750503 | FAASt [25 MW BESS Installation and Integration - San Juan] (Substation) | Substation | Grid Modernization | $ - | 55503065.56 | - | 861465.442
3 |  | 752277 | FAASt [Substation Ciales 8701] (Substation) | Substation | Rebuild | 359175.24 | 4177144.45 | - | 436389.6801
1 |  | 752972 | FAASt [4 x 25 MW BESS Interconnections Manati] (Substation) | Substation | Grid Modernization | $ - | 57640005.67 | - | 804353.0754
1 |  | 754350 | Distribution Underground Circuit Feeders - San Juan Group 1 | Distribution | Underground | $ - | 15123199.33 | - | 899680.53
1 |  | 754351 | ​Distribution Underground Circuit Feeders - San Juan Group 2 | Distribution | Underground | $ - | 7066632.8 | - | 733755.15
1 |  | 764705 | FAASt [Distribution Feeder Rebuild #6014-02] (Distribution) | Distribution | Line Rebuild | 13387462.29 | Unknown at this time* | 17760963 | 3059416.973
1 |  | 764707 | FAASt [Feeder Rebuild # 6012-02] (Distribution) | Distribution | Line Rebuild | 5540622.64 | Unknown at this time* | 3340086 | 3032847.3237

## Exhibit 4 (hidden)
Urgency | Project # | Title | Asset | Sub Asset | Process Step | Incurred Cost | Project costs * | 428 Allocation * | 406 Allocation * | Project Status | Additional comments
As LUMA has already procured $61M dollars of this equipment and it is on hand, there is a very high risk to ratepayers if LUMA is unable to get these FASST projects re-activated. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | Automation Program | Distribution | Automation |  | 75157137.71 | 296669500 | 178001700 | 118667800 | Inactive, a few years of engineered work order packages complete, major equipment (reclosers, poles, bypass switches) all procured and in LUMA warehouse. | This Automation Program included here is based on a grouping of projects that LUMA will split to separate groups during the formulation process as DSOW's are submitted to FEMA. $61M cost Incurred to E&M PW
Cost already incurred and project complete | Pending FAASt Number | Hato Rey TC Transformer Replacement | Substation | Component Replacement | Collaboration | 3763775.37 | 3763775.37 | 3763775.37 | 0 |  | Transformer purchased and reimbursed to E&M PW ($892,425). Installation and Comissioning paid under NFC.
Cost already incurred and project complete | Pending FAASt Number | Venezuela TC | Substation | Component Replacement | Collaboration | 2613825.35 | 2613825.35 | 2613825.35 | 0 |  | Project is work Completed, costs are per Work Completed Summary given to PREB. Transformer purchased with E&M PW ($1,037,090).
Cost already incurred and project complete | Pending FAASt Number | Substation Component Group 0 | Substation | Component Replacement | Currently working to prepare functional specifications and plan to discuss with FEMA shortly | 14145405.55 | 14145405.55 | 14145405.55 | 0 | Currently working to prepare functional specifications and plan to discuss with FEMA shortly | Work Completed, Priority to get FEMA obligated, this is equipment purchased under the federal Equipment & Material PW but installed with NFC or DOE dollars, LUMA is requesting a FASST number to be reconciled for the Equipment purchased under E&M PW. All of this equipment cost would put rate payers at risk if it is not reconciled to child PWs. *16 Gas Circuit Breakers ($1,036,579), 5 Transformers - Sabana Llana 1646 ($968,203), Mora TC 112 MVA ($2,926,189.87), Caguas 112 MVA ($4,416,882), Isla Grande 112MVA ($2,926,189.87), Hogar Crea 112 MVA ($1,871,361.81)
Historical Flooding in the Arecibo Pueblo Substation require it to be relocated to Arecibo Sectionalizer Site. Site is critical to stability of system. Due to relocation, much of the project is expected to be funded by FEMA. | Pending FAASt Number | Arecibo Sect. Substation Rebuild | Substation | Substation Rebuild | Project scope to be developed and approved by leadership | 0 | 71435277.14 | 7143527.714 | 64291749.426 | Project scope to be developed and approved by leadership | Rebuild of priority sectionalizing substation including colocated 8015 Arecibo Hospital Distrito and 8003 Arecibo Rural distribution substations and relocation to site of distribution substation 8002 Arecibo Pueblo substation (due to Historical Flooding).
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 6500 Reclosers 38 kV | Transmission | Automation |  | 203930.22 | 981405.16 | 461620.3 | 519784.86 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 2 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 8100 Reclosers 38 kV | Transmission | Automation |  | 224682.71 | 1500763.76 | 730612.8 | 770150.96 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 3 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 1500 Reclosers 38 kV | Transmission | Automation |  | 199953.32 | 944000 | 594720 | 349280 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 2 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 13400 Reclosers 38 kV | Transmission | Automation |  | 207116.84 | 1321485.96 | 579867.07 | 741618.89 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 3 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 800 Reclosers 38 kV | Transmission | Automation |  | 181941.37 | 838354.58 | 614126.79 | 224227.79 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 2 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 12600 Reclosers 38 kV | Transmission | Automation |  | 188541.16 | 1935866.57 | 1448491.28 | 487375.29 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 3 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 2000 Reclosers 38 kV | Transmission | Automation |  | 212415.97 | 1701253.27 | 1309036.7 | 392216.57 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 3 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 4800 Reclosers 38 kV | Transmission | Automation |  | 467207.73 | 2697229.44 | 2013222.35 | 684007.09 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 6 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 100 Reclosers 38 kV | Transmission | Automation |  | 214159.58 | 1213187.43 | 764308.0809 | 448879.3491 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 3 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 3700 Reclosers 38 kV | Transmission | Automation |  | 267304.72 | 1340624.93 | 286655.46 | 1053969.47 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 4 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 1600 Reclosers 38 kV | Transmission | Automation |  | 210875.79 | 1453119.73 | 1063054.49 | 390065.24 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 3 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 2200 Reclosers 38kV | Transmission | Automation |  | 232979.14 | 1416000 | 892080 | 523920 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 3 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 3100 Reclosers 38 kV | Transmission | Automation |  | 234840.63 | 1847899.09 | 1398985.55 | 448913.54 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 3 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 3000 Reclosers 38 kV | Transmission | Automation |  | 256545.43 | 1149274.52 | 724042.9476 | 425231.5724 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 3 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 3600 Reclosers 38 kV | Transmission | Automation |  | 232527.63 | 944000 | 594720 | 349280 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 2 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 8200 Reclosers 38 kV | Transmission | Automation |  | 251402.92 | 944000 | 594720 | 349280 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 2 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 3200 Reclosers 38 kV | Transmission | Automation |  | 210367.39 | 721651.14 | 537627.06 | 184024.08 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 2 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 300 Reclosers 38 kV | Transmission | Automation |  | 142345.67 | 1416000 | 892080 | 523920 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 3 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 500 Reclosers 38 kV | Transmission | Automation |  | 175562.55 | 1888000 | 1189440 | 698560 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 4 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 700 Reclosers 38 kV | Transmission | Automation |  | 182303.58 | 1888000 | 1189440 | 698560 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 4 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 2400 Reclosers 38 kV | Transmission | Automation |  | 96272.4 | 944000 | 594720 | 349280 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 2 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 2600 Reclosers 38 kV | Transmission | Automation |  | 96098.36 | 944000 | 594720 | 349280 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 2 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 2700 Reclosers 38 kV | Transmission | Automation |  | 170382.53 | 1888000 | 1189440 | 698560 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 4 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 2800 Reclosers 38 kV | Transmission | Automation |  | 93434.48 | 944000 | 594720 | 349280 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 2 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 4700 Reclosers 38 kV | Transmission | Automation |  | 98154.58 | 944000 | 594720 | 349280 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 2 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 5200 Reclosers 38 kV | Transmission | Automation |  | 131892.52 | 944000 | 594720 | 349280 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 2 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 5400 Reclosers 38 kV | Transmission | Automation |  | 166496.05 | 1416000 | 892080 | 523920 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 3 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 6000 Reclosers 38 kV | Transmission | Automation |  | 132659.3 | 472000 | 297360 | 174640 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 1 recloser
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 7100 Reclosers 38 kV | Transmission | Automation |  | 134356.27 | 1416000 | 892080 | 523920 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 3 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 8900 Reclosers 38 kV | Transmission | Automation |  | 242439.32 | 2832000 | 1784160 | 1047840 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 6 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 9400 Reclosers 38 kV | Transmission | Automation |  | 141431.54 | 944000 | 594720 | 349280 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 2 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 10000 Reclosers 38 kV | Transmission | Automation |  | 167088.33 | 1888000 | 1189440 | 698560 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 4 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 13700 Reclosers 38 kV | Transmission | Automation |  | 131189.64 | 1416000 | 892080 | 523920 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 3 reclosers
LUMA has already procured material and engineered work order package utilizing the global PW's for E&M and A&E with expectation to submit DSOW to FEMA. Equipment is available in LUMA's warehouse and engineering is substantially complete. If LUMA is unable to get this project activated there is a risk to rate payers due to the cost incurred. Additionally, these projects carry high reliability impacts. | Pending FAASt Number | TL 5600 Reclosers 38 kV | Transmission | Automation |  | 222928.53 | 1389759.59 | 1047506.87 | 342252.72 | Cost Incurred is due to Engineering and Project Management Costs and Equipment Purchase Cost as the Reclosers have already been procured under the Equipment & Material PW and are in LUMA's Warehouse. 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review. | 2 reclosers
This station has numerous major issues that need to be remediated to ensure reliable service. Among these are the following: 1. Out of Service Transformer 2. Out of service underground transmission lines 3.Reliability Issues 4. Large Flood Risk 5. High Critical Loads | Pending FAASt Number | Chardon Sect. Substation Rebuild | Substation | Substation Rebuild | Project scope to be developed and approved by leadership | 0 | 25000000 | 15000000 | 10000000 | Project scope to be developed and approved by leadership | Rebuild of priority sectionalizing substation; will include in scope the rebuild of distribution substations 1403 Chardon I and 1404 Chardón 2
Transformers already purchased and incoming, so if project is not included in Consolidated FASST portfolio there will be large risk to ratepayers as the transformers are incoming. | Pending FAASt Number | Substation Component Group 2 | Substation | Component Replacement | Currently working to prepare functional specifications and plan to discuss with FEMA shortly | 3133498.208 | 130000000 | 123500000 | 6500000 | Currently working to prepare functional specifications and plan to discuss with FEMA shortly | Total of 10 substations with 9 transformers, 2 metal clad, 8 PAC Upgrade, 1 cap bank, 1 RTU, 9 Distribution and 8 transmission breakers replacements plus minor repair, grounding and security for all 10 stations. High Level budgetary estimates are around $130M
Transformers already purchased and incoming, so if project is not included in Consolidated FASST portfolio there will be large risk to ratepayers as the transformers are incoming. | Pending FAASt Number | Substation Component Group 3 | Substation | Component Replacement | Currently working to prepare functional specifications and plan to discuss with FEMA shortly | 14665406.49 | 330000000 | 313500000 | 16500000 | Currently working to prepare functional specifications and plan to discuss with FEMA shortly | 33 Transformer Replacements, Transformers already procured, manufacturing commencing with delivery dates from the middle of 2026 through 2028. Cost incurred is based on progress payments made to-date, but will increase as production of transformers continues. Additionally LUMA has committed* $71,868,237.51 for the purchase of these transformers, so there is significant risk to rate payers if this project is not enstated. These transformer replacements are targeting Out of Service, Capacity Constrained, and Transformer in bad conditions to ensure reliable service to customers and build in added reselience to the system. Due to the aforementioned reasons, this is one of LUMA's top priorities for obligation. *Commitment to purchase the transformers was already made under the federally funded Equipment and Material PW at the time due to having funds obligated and expectation of receiving child FASST obligations
| Pending FAASt Number | FAASt [Region 1 San Juan Distribution sensitive areas] (Vegetation) | Vegetation | N/A |  | 0 | 136954530 | 36628489.0485 | 100284954.5925 | Pending COR3 reviews on submitted Non-Sensitive Group C projects. Once review is received team will amend if necessary and submit to FEMA directly. | 428/406 Splits based on what was agreed to by LUMA and FEMA (Distribution = 26.745% 428, 73.225% 406).
| Pending FAASt Number | FAASt [Region 2 Arecibo Distribution sensitive areas] (Vegetation) | Vegetation | N/A |  | 0 | 188729100 | 50475597.795 | 138196883.475 | Pending COR3 reviews on submitted Non-Sensitive Group C projects. Once review is received team will amend if necessary and submit to FEMA directly. | 428/406 Splits based on what was agreed to by LUMA and FEMA (Distribution = 26.745% 428, 73.225% 406).
| Pending FAASt Number | FAASt [Region 3 Bayamon Distribution sensitive areas] (Vegetation) | Vegetation | N/A |  | 0 | 33723810 | 9019432.9845 | 24694259.8725 | Pending COR3 reviews on submitted Non-Sensitive Group C projects. Once review is received team will amend if necessary and submit to FEMA directly. | 428/406 Splits based on what was agreed to by LUMA and FEMA (Distribution = 26.745% 428, 73.225% 406).
| Pending FAASt Number | FAASt [Region 4 Caguas Distribution sensitive areas] (Vegetation) | Vegetation | N/A |  | 0 | 165176460 | 44176444.227 | 120950462.835 | Pending COR3 reviews on submitted Non-Sensitive Group C projects. Once review is received team will amend if necessary and submit to FEMA directly. | 428/406 Splits based on what was agreed to by LUMA and FEMA (Distribution = 26.745% 428, 73.225% 406).
| Pending FAASt Number | FAASt [Region 5 Mayaguez Distribution sensitive areas] (Vegetation) | Vegetation | N/A |  | 0 | 218058975 | 58319872.8638 | 159673684.4437 | Pending COR3 reviews on submitted Non-Sensitive Group C projects. Once review is received team will amend if necessary and submit to FEMA directly. | 428/406 Splits based on what was agreed to by LUMA and FEMA (Distribution = 26.745% 428, 73.225% 406).
| Pending FAASt Number | FAASt [Region 6 Ponce Distribution sensitive areas] (Vegetation) | Vegetation | N/A |  | 0 | 160503255 | 42926595.5498 | 117528508.4737 | Pending COR3 reviews on submitted Non-Sensitive Group C projects. Once review is received team will amend if necessary and submit to FEMA directly. | 428/406 Splits based on what was agreed to by LUMA and FEMA (Distribution = 26.745% 428, 73.225% 406).
| Pending FAASt Number | 38kV Transmission Line 100 – Entire Line (Vegetation) | Vegetation | N/A |  | 0 | 5136889.56 | 428416.5893 | 4708472.9707 | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE | 428/406 Splits based on what was agreed to by LUMA and FEMA (38kV = 8.34% 428, 91.66% 406).
| Pending FAASt Number | 38kV Transmission Line 200 – Entire Line (Vegetation) | Vegetation | N/A |  | 0 | 3130292.05 | 261066.357 | 2869225.693 | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE | 428/406 Splits based on what was agreed to by LUMA and FEMA (38kV = 8.34% 428, 91.66% 406).
| Pending FAASt Number | 38kV Transmission Line 800 – Entire Line (Vegetation) | Vegetation | N/A |  | 0 | 3249603.27 | 271016.9127 | 2978586.3573 | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE | 428/406 Splits based on what was agreed to by LUMA and FEMA (38kV = 8.34% 428, 91.66% 406).
| Pending FAASt Number | 38kV Transmission Line 1200 – Entire Line (Vegetation) | Vegetation | N/A |  | 0 | 5555563.43 | 463333.9901 | 5092229.4399 | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE | 428/406 Splits based on what was agreed to by LUMA and FEMA (38kV = 8.34% 428, 91.66% 406).
| Pending FAASt Number | 38kV Transmission Line 1600 – Entire Line (Vegetation) | Vegetation | N/A |  | 0 | 6154288.74 | 513267.6809 | 5641021.0591 | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE | 428/406 Splits based on what was agreed to by LUMA and FEMA (38kV = 8.34% 428, 91.66% 406).
| Pending FAASt Number | 38kV Transmission Line 2000 – Entire Line (Vegetation) | Vegetation | N/A |  | 0 | 6117410.71 | 510192.0532 | 5607218.6568 | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE | 428/406 Splits based on what was agreed to by LUMA and FEMA (38kV = 8.34% 428, 91.66% 406).
| Pending FAASt Number | 38kV Transmission Line 2100 – Entire Line (Vegetation) | Vegetation | N/A |  | 0 | 6141272.97 | 512182.1657 | 5629090.8043 | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE | 428/406 Splits based on what was agreed to by LUMA and FEMA (38kV = 8.34% 428, 91.66% 406).
| Pending FAASt Number | 38kV Transmission Line 2200 – Entire Line (Vegetation) | Vegetation | N/A |  | 0 | 16228492.86 | 1353456.3045 | 14875036.5555 | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE | 428/406 Splits based on what was agreed to by LUMA and FEMA (38kV = 8.34% 428, 91.66% 406).
| Pending FAASt Number | 38kV Transmission Line 2500 – Entire Line (Vegetation) | Vegetation | N/A |  | 0 | 4904775.04 | 409058.2383 | 4495716.8017 | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE | 428/406 Splits based on what was agreed to by LUMA and FEMA (38kV = 8.34% 428, 91.66% 406).
| Pending FAASt Number | 38kV Transmission Line 2700 – Entire Line (Vegetation) | Vegetation | N/A |  | 0 | 8256335.2 | 688578.3557 | 7567756.8443 | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE | 428/406 Splits based on what was agreed to by LUMA and FEMA (38kV = 8.34% 428, 91.66% 406).
| Pending FAASt Number | 38kV Transmission Line 3000 – Entire Line (Vegetation) | Vegetation | N/A |  | 0 | 9898491.21 | 825534.1669 | 9072957.0431 | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE | 428/406 Splits based on what was agreed to by LUMA and FEMA (38kV = 8.34% 428, 91.66% 406).
| Pending FAASt Number | 38kV Transmission Line 3100 – Entire Line (Vegetation) | Vegetation | N/A |  | 0 | 13100370.02 | 1092570.8597 | 12007799.1603 | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE | 428/406 Splits based on what was agreed to by LUMA and FEMA (38kV = 8.34% 428, 91.66% 406).
| Pending FAASt Number | 38kV Transmission Line 3700 – Entire Line (Vegetation) | Vegetation | N/A |  | 0 | 9475478.76 | 790254.9286 | 8685223.8314 | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE | 428/406 Splits based on what was agreed to by LUMA and FEMA (38kV = 8.34% 428, 91.66% 406).
| Pending FAASt Number | 38kV Transmission Line 3800 – Entire Line (Vegetation) | Vegetation | N/A |  | 0 | 5113027.32 | 426426.4785 | 4686600.8415 | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE | 428/406 Splits based on what was agreed to by LUMA and FEMA (38kV = 8.34% 428, 91.66% 406).
| Pending FAASt Number | 38kV Transmission Line 4000 – Entire Line (Vegetation) | Vegetation | N/A |  | 0 | 2279928.56 | 190146.0419 | 2089782.5181 | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE | 428/406 Splits based on what was agreed to by LUMA and FEMA (38kV = 8.34% 428, 91.66% 406).
| Pending FAASt Number | 38kV Transmission Line 4800 – Entire Line (Vegetation) | Vegetation | N/A |  | 0 | 8629453.86 | 719696.4519 | 7909757.4081 | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE | 428/406 Splits based on what was agreed to by LUMA and FEMA (38kV = 8.34% 428, 91.66% 406).
| Pending FAASt Number | 38kV Transmission Line 5300 – Entire Line (Vegetation) | Vegetation | N/A |  | 0 | 3345052.23 | 278977.356 | 3066074.874 | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE | 428/406 Splits based on what was agreed to by LUMA and FEMA (38kV = 8.34% 428, 91.66% 406).
| Pending FAASt Number | 38kV Transmission Line 5400 – Entire Line (Vegetation) | Vegetation | N/A |  | 0 | 5807201.58 | 484320.6118 | 5322880.9682 | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE | 428/406 Splits based on what was agreed to by LUMA and FEMA (38kV = 8.34% 428, 91.66% 406).
| Pending FAASt Number | 38kV Transmission Line 5600 – Entire Line (Vegetation) | Vegetation | N/A |  | 0 | 5915666.32 | 493366.5711 | 5422299.7489 | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE | 428/406 Splits based on what was agreed to by LUMA and FEMA (38kV = 8.34% 428, 91.66% 406).
| Pending FAASt Number | 38kV Transmission Line 6500 – Entire Line (Vegetation) | Vegetation | N/A |  | 0 | 9019926.9 | 752261.9035 | 8267664.9965 | Single Line Vegation projects were pulled out of Group B and Group C 38kV Vegetation for submission to DOE | 428/406 Splits based on what was agreed to by LUMA and FEMA (38kV = 8.34% 428, 91.66% 406).
Critical 230kV and 115kV Supply, Failing End Of Life Transformer Assets Require Replacement, Requires Redundancies for Reliability | Pending FAASt Number | Manati TC Substation Rebuild | Substation | Substation Rebuild | Project scope to be developed and approved by leadership | 0 | 90000000 | 54000000 | 36000000 | Project scope to be developed and approved by leadership | Rebuild of priority Transmission Center; will include in scope the rebuild of distribution substation 8404 Manatí TC and new 13.2 kV distribution substation.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair - Arecibo Group 05 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 7642400 | 7260280 | 382120 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 233 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair - Arecibo Group 06 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 15350400 | 14582880 | 767520 | High Level Assesment (HLA) has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 468 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair - Arecibo Group 07 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 10463200 | 9940040 | 523160 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 319 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair - Arecibo Group 08 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 10266400 | 9753080 | 513320 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 313 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair - Arecibo Group 09 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 12792000 | 12152400 | 639600 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 390 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Arecibo Group 10 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 4723200 | 4487040 | 236160 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 144 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Arecibo Group 11 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 10430400 | 9908880 | 521520 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 318 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Arecibo Group 12 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 5936800 | 5639960 | 296840 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 181 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Arecibo Group 13 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 1148000 | 1090600 | 57400 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 35 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Arecibo Group 14 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 5346400 | 5079080 | 267320 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 163 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Arecibo Group 15 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 4428000 | 4206600 | 221400 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 135 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Arecibo Group 16 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 4788800 | 4549360 | 239440 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 146 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Arecibo Group 17 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 1344800 | 1277560 | 67240 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 41 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Arecibo Group 18 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 656000 | 623200 | 32800 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 20 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Bayamon Group 05 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 2591200 | 2461640 | 129560 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 79 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Bayamon Group 06 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 1869600 | 1776120 | 93480 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 57 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Bayamon Group 07 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 18991200 | 18041640 | 949560 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 579 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Bayamon Group 08 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 8593600 | 8163920 | 429680 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 262 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Bayamon Group 09 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 12496800 | 11871960 | 624840 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 381 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Bayamon Group 10 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 8560800 | 8132760 | 428040 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 261 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Bayamon Group 11 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 7216000 | 6855200 | 360800 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 220 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Bayamon Group 12 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 3378400 | 3209480 | 168920 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 103 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Bayamon Group 13 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 3181600 | 3022520 | 159080 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 97 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Bayamon Group 14 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 8659200 | 8226240 | 432960 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 264 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Bayamon Group 15 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 1968000 | 1869600 | 98400 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 60 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Bayamon Group 16 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 1344800 | 1277560 | 67240 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 41 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Bayamon Group 18 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 1541600 | 1464520 | 77080 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 47 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Caguas Group 09 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 13972800 | 13274160 | 698640 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 426 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Caguas Group 10 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 7150400 | 6792880 | 357520 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 218 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Caguas Group 11 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 12070400 | 11466880 | 603520 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 368 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Caguas Group 12 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 8495200 | 8070440 | 424760 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 259 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Caguas Group 13 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 9610400 | 9129880 | 480520 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 293 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Caguas Group 14 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 7642400 | 7260280 | 382120 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 233 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Caguas Group 15 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 9249600 | 8787120 | 462480 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 282 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Caguas Group 16 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 820000 | 779000 | 41000 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 25 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Caguas Group 17 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 2656800 | 2523960 | 132840 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 81 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Caguas Group 18 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 2755200 | 2617440 | 137760 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 84 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Caguas Group 19 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 1902400 | 1807280 | 95120 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 58 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Caguas Group 20 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 1344800 | 1277560 | 67240 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 41 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Mayaguez Group 06 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 10922400 | 10376280 | 546120 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 333 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Mayaguez Group 07 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 6560000 | 6232000 | 328000 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 200 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Mayaguez Group 08 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 7544000 | 7166800 | 377200 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 230 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Mayaguez Group 09 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 7248800 | 6886360 | 362440 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 221 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Mayaguez Group 10 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 23976800 | 22777960 | 1198840 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 731 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Mayaguez Group 11 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 1574400 | 1495680 | 78720 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 48 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Mayaguez Group 12 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 2000800 | 1900760 | 100040 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 61 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Mayaguez Group 13 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 3411200 | 3240640 | 170560 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 104 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Mayaguez Group 14 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 2492800 | 2368160 | 124640 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 76 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Mayaguez Group 15 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 1738400 | 1651480 | 86920 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 53 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Mayaguez Group 16 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 5051200 | 4798640 | 252560 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 154 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Mayaguez Group 17 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 4559200 | 4331240 | 227960 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 139 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Mayaguez Group 18 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 3509600 | 3334120 | 175480 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 107 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Mayaguez Group 19 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 2230400 | 2118880 | 111520 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 68 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Mayaguez Group 20 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 590400 | 560880 | 29520 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 18 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Mayaguez Group 21 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 524800 | 498560 | 26240 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 16 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Mayaguez Group 22 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 557600 | 529720 | 27880 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 17 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Mayaguez Group 23 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 328000 | 311600 | 16400 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 10 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Ponce Group 04 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 8429600 | 8008120 | 421480 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 257 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Ponce Group 05 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 5248000 | 4985600 | 262400 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 160 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Ponce Group 06 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 4034400 | 3832680 | 201720 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 123 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Ponce Group 07 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 984000 | 934800 | 49200 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 30 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Ponce Group 08 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 3509600 | 3334120 | 175480 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 107 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Ponce Group 09 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 13743200 | 13056040 | 687160 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 419 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Ponce Group 10 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 5313600 | 5047920 | 265680 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 162 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Ponce Group 11 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 6494400 | 6169680 | 324720 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 198 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Ponce Group 12 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 4526400 | 4300080 | 226320 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 138 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Ponce Group 13 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 2919200 | 2773240 | 145960 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 89 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Ponce Group 14 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 1377600 | 1308720 | 68880 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 42 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Ponce Group 15 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 3903200 | 3708040 | 195160 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 119 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Ponce Group 16 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 2164800 | 2056560 | 108240 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 66 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Ponce Group 17 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 1148000 | 1090600 | 57400 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 35 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Ponce Group 18 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 1312000 | 1246400 | 65600 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 40 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Ponce Group 19 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 918400 | 872480 | 45920 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 28 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Ponce Group 21 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 2361600 | 2243520 | 118080 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 72 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Ponce Group 22 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 328000 | 311600 | 16400 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 10 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Ponce Group 23 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 295200 | 280440 | 14760 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 9 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-Ponce Group 24 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 1476000 | 1402200 | 73800 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 45 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-San Juan Group 05 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 4100000 | 3895000 | 205000 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 125 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-San Juan Group 06 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 15416000 | 14645200 | 770800 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 470 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-San Juan Group 07 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 7183200 | 6824040 | 359160 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 219 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-San Juan Group 07/San Juan Group 55 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 295200 | 280440 | 14760 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 9 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-San Juan Group 08 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 3870400 | 3676880 | 193520 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 118 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-San Juan Group 09 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 4231200 | 4019640 | 211560 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 129 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-San Juan Group 10 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 2033600 | 1931920 | 101680 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 62 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-San Juan Group 11 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 5018400 | 4767480 | 250920 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 153 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-San Juan Group 11/San Juan Group 55 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 623200 | 592040 | 31160 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 19 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-San Juan Group 12 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 3870400 | 3676880 | 193520 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 118 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-San Juan Group 13 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 262400 | 249280 | 13120 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 8 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-San Juan Group 14 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 5149600 | 4892120 | 257480 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 157 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-San Juan Group 15 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 1115200 | 1059440 | 55760 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 34 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-San Juan Group 16 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 852800 | 810160 | 42640 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 26 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-San Juan Group 17 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 1738400 | 1651480 | 86920 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 53 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-San Juan Group 18 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 6658400 | 6325480 | 332920 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 203 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-San Juan Group 19 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 0 | 0 | 0 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 0 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-San Juan Group 20 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 2853600 | 2710920 | 142680 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 87 poles submitted from HLAs. 428/406 split varies from pole to pole.
High Volume Replacement Work, replacing damaged poles, LUMA has poles on-hand to execute pole replacements and can execute quickly. | Pending FAASt Number | Distribution Pole and Conductor Repair-San Juan Group 21 | Distribution | Pole and Conductors | Pending WOP and DSOW creation | 0 | 3017600 | 2866720 | 150880 | HLA has been submitted to Engineering. The project does not have an active financial account or an FAASt number established. | Project costs based on assumption of $32,800.00 per pole. 92 poles submitted from HLAs. 428/406 split varies from pole to pole.
Maria Damage, Worst Performing Asset, Reliability and Resilience Need, A&E Design Completed, Equipment In Stock | Pending FAASt Number | 36100-DOS BOCAS HP-BARRIO PIÑA SECT- | Transmission | Rebuild |  |  | 73601257.562 | 60353031.2008 | 13248226.3612 |  | Critical line for the 115kV system.
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 1118-08 | Distribution | Line Rebuild |  | 5736.83 | 4205003.39 | 3868603.1188 | 336400.2712 | Under formulation. | Distribution Line Rebuild - 1.4 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 1118-09 | Distribution | Line Rebuild |  | 2651.77 | 4505360.77 | 4144931.9084 | 360428.8616 | Under formulation. | Distribution Line Rebuild - 1.5 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 1206-03 | Distribution | Line Rebuild |  | 1106.28 | 12765188.86 | 11743973.7512 | 1021215.1088 | Under formulation. | Distribution Line Rebuild - 4.25 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 1336-07 | Distribution | Line Rebuild |  | 6263.82 | 11203330.46 | 10307064.0232 | 896266.4368 | Under formulation. | Distribution Line Rebuild - 3.73 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 1346-03 | Distribution | Line Rebuild |  | -445.4 | 8259828.09 | 7599041.8428 | 660786.2472 | Under formulation. | Distribution Line Rebuild - 2.75 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 1529-11 | Distribution | Line Rebuild |  | 0 | 8109649.39 | 7460877.4388 | 648771.9512 | Under formulation. | Distribution Line Rebuild - 2.7 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 1709-02 | Distribution | Line Rebuild |  | 3227.53 | 8259828.09 | 7599041.8428 | 660786.2472 | Under formulation. | Distribution Line Rebuild - 2.75 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 1709-05 | Distribution | Line Rebuild |  | 4728.14 | 11075781 | 10189718.52 | 886062.48 | Under formulation. | Distribution Line Rebuild - 2.5 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 1711-05 | Distribution | Line Rebuild |  | 2665.69 | 6007147.7 | 5526575.884 | 480571.816 | Under formulation. | Distribution Line Rebuild - 2 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 1713-05 | Distribution | Line Rebuild |  | 6189.43 | 12314652.78 | 11329480.5576 | 985172.2224 | Under formulation. | Distribution Line Rebuild - 4.1 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 1714-02 | Distribution | Line Rebuild |  | 0 | 3754467.31 | 3454109.9252 | 300357.3848 | Under formulation. | Distribution Line Rebuild - 1.25 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 1717-01 | Distribution | Line Rebuild |  | 2841.76 | 7508934.63 | 6908219.8596 | 600714.7704 | Under formulation. | Distribution Line Rebuild - 2.5 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 1719-15 | Distribution | Line Rebuild |  | 8753.24 | 7508934.63 | 6908219.8596 | 600714.7704 | Under formulation. | Distribution Line Rebuild - 2.5 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 1719-18 | Distribution | Line Rebuild |  | 1700.06 | 11263401.93 | 10362329.7756 | 901072.1544 | Under formulation. | Distribution Line Rebuild - 3.75 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 1907-05 | Distribution | Line Rebuild |  | 291.25 | 3003573.85 | 2763287.942 | 240285.908 | Under formulation. | Distribution Line Rebuild - 1 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 1908-03 | Distribution | Line Rebuild |  | 54.36 | 20694623.82 | 19039053.9144 | 1655569.9056 | Under formulation. | Distribution Line Rebuild - 6.89 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 2601-01 | Distribution | Line Rebuild |  | 11873.35 | 11263401.93 | 10362329.7756 | 901072.1544 | Under formulation. | Distribution Line Rebuild - 3.75 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 2603-09 | Distribution | Line Rebuild |  | 410.97 | 17661915.49 | 16248962.2508 | 1412953.2392 | Under formulation. | Distribution Line Rebuild - 4.75 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 2604-01 | Distribution | Line Rebuild |  | 3101.36 | 12765188.86 | 11743973.7512 | 1021215.1088 | Under formulation. | Distribution Line Rebuild - 4.25 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 2901-04 | Distribution | Line Rebuild |  | 0 | 12765188.86 | 11743973.7512 | 1021215.1088 | Under formulation. | Distribution Line Rebuild - 4.25 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 3201-02 | Distribution | Line Rebuild |  | 567.35 | 15017869.25 | 13816439.71 | 1201429.54 | Under formulation. | Distribution Line Rebuild - 5 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 3701-02 | Distribution | Line Rebuild |  | 7659.65 | 5256254.23 | 4835753.8916 | 420500.3384 | Under formulation. | Distribution Line Rebuild - 1.75 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 4603-02 | Distribution | Line Rebuild |  | 5265.94 | 12014295.4 | 11053151.768 | 961143.632 | Under formulation. | Distribution Line Rebuild - 4 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 5016-01 | Distribution | Line Rebuild |  | 2015.38 | 11113223.25 | 10224165.39 | 889057.86 | Under formulation. | Distribution Line Rebuild - 3.7 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 5401-02 | Distribution | Line Rebuild |  | 454.35 | 8259828.09 | 7599041.8428 | 660786.2472 | Under formulation. | Distribution Line Rebuild - 2.75 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 5803-02 | Distribution | Line Rebuild |  | 1494.79 | 18021443.09 | 16579727.6428 | 1441715.4472 | Under formulation. | Distribution Line Rebuild - 6 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 6004-02 | Distribution | Line Rebuild |  | 1807.96 | 13816439.71 | 12711124.5332 | 1105315.1768 | Under formulation. | Distribution Line Rebuild - 4.6 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 6010-02 | Distribution | Line Rebuild |  | 285.76 | 15017869.25 | 13816439.71 | 1201429.54 | Under formulation. | Distribution Line Rebuild - 5 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 6101-04 | Distribution | Line Rebuild |  | 8022.88 | 12615010.17 | 11605809.3564 | 1009200.8136 | Under formulation. | Distribution Line Rebuild - 4.2 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 6101-05 | Distribution | Line Rebuild |  | 805.54 | 10512508.47 | 9671507.7924 | 841000.6776 | Under formulation. | Distribution Line Rebuild - 3.5 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 6501-04 | Distribution | Line Rebuild |  | 8026.2 | 9761615.02 | 8980685.8184 | 780929.2016 | Under formulation. | Distribution Line Rebuild - 3.25 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 7201-05 | Distribution | Line Rebuild |  | 13405.44 | 13516082.32 | 12434795.7344 | 1081286.5856 | Under formulation. | Distribution Line Rebuild - 4.5 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 7504-01 | Distribution | Line Rebuild |  | 731.18 | 6908219.86 | 6355562.2712 | 552657.5888 | Under formulation. | Distribution Line Rebuild - 2.3 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 8104-02 | Distribution | Line Rebuild |  | 8736.35 | 12014295.4 | 11053151.768 | 961143.632 | Under formulation. | Distribution Line Rebuild - 4 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 8202-01 | Distribution | Line Rebuild |  | 5594.11 | 4505360.77 | 4144931.9084 | 360428.8616 | Under formulation. | Distribution Line Rebuild - 1.5 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 9004-08 | Distribution | Line Rebuild |  | 1297.28 | 22827161.26 | 21000988.3592 | 1826172.9008 | Under formulation. | Distribution Line Rebuild - 7.6 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 9004-10 | Distribution | Line Rebuild |  | 4771.77 | 21325374.33 | 19619344.3836 | 1706029.9464 | Under formulation. | Distribution Line Rebuild - 7.1 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 9202-04 | Distribution | Line Rebuild |  | 10730.73 | 9761615.02 | 8980685.8184 | 780929.2016 | Under formulation. | Distribution Line Rebuild - 3.25 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 9501-01 | Distribution | Line Rebuild |  | 2032.72 | 11313401.93 | 10408329.7756 | 905072.1544 | Under formulation. | Distribution Line Rebuild - 3.75 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 9503-06 | Distribution | Line Rebuild |  | 14060.58 | 11713938.01 | 10776822.9692 | 937115.0408 | Under formulation. | Distribution Line Rebuild - 3.9 miles
Maria damaged facilities, worst reliability performer | Pending FAASt Number | Distribution Feeder Rebuild # 9605-02 | Distribution | Line Rebuild |  | 55749.64 | 20424302.18 | 18790358.0056 | 1633944.1744 | Under formulation. | Distribution Line Rebuild - 6.8 miles
New Line | Pending FAASt Number | 41200-SABANA LLANA TC-CANOVANAS TC- | Transmission | Rebuild |  |  | 22110644.6664 | 18130728.6264 | 3979916.04 |  | Critical line for the 115kV system.
Out of Service Line Affecting Hydro Generation | Pending FAASt Number | 8700-COSTA SUR SP-GARZAS 1 HP- | Transmission | Rebuild |  |  | 16305882.362 | 13370823.5368 | 2935058.8252 |  | Out of Service line output of a Power Plant.
Required Network Upgrade for Generation (Genera and Tranches) | Pending FAASt Number | 9300-JUNCOS TC-GAUTIER BENITEZ SECT- | Transmission | Rebuild |  |  | 27135375 | 22251007.5 | 4884367.5 |  | Critical line for the system.
Required Network Upgrade for Generation (Tranches and Genera) | Pending FAASt Number | Santa Isabel TC Substation Rebuild | Substation | Substation Rebuild | Project scope to be developed and approved by leadership | 0 | 60000000 | 36000000 | 24000000 | Project scope to be developed and approved by leadership | Rebuild of priority Transmission Center; will include in scope the rebuild of distribution substation 4402 Santa Isabel TC.
Requires a transformer upgrade from 56 MVA to 112 MVA | Pending FAASt Number | Palmer TC Substation Rebuild | Substation | Substation Rebuild | Project scope to be developed and approved by leadership | 0 | 25000000 | 15000000 | 10000000 | Project scope to be developed and approved by leadership | Rebuild of priority Transmission Center; will include in scope the rebuild of distribution substation 2305 Palmer
Underground Out of Service | Pending FAASt Number | 16800-VEGA BAJA TC-VEGA ALTA SECT- | Transmission | Rebuild |  |  | 1033000 | 847060 | 185940 |  | Out of Service line it is is critical for the reliability of the 38 kV system.
Underground Out of Service | Pending FAASt Number | 40600-BAYAMON TC-MONACILLOS TC | Transmission | Rebuild |  |  | 65222221.57 | 53482221.6874 | 11739999.8826 |  | Out of Service line it is critical to the resiliency of the 115 kV system.
Underground Out of Service | Pending FAASt Number | 41600-PALO SECO SP-SAN JUAN SP- | Transmission | Rebuild |  |  | 45999999.54 | 37719999.6228 | 8279999.9172 |  | Out of Service line it is critical to the resiliency of the 115 kV system.
| Pending FAASt Number | 1500-ONCE DE AGOSTO SECT-SABANA GRANDE TO- | Transmission | Pole Replacement |  |  | 2440000 | 2171600 | 268400 |  | Pole Replacements: 13 Critical Repairs: 76
| Pending FAASt Number | 36400-PONCE TC-DOS BOCAS HP- | Transmission | Pole Replacement |  |  | 6240000 | 5553600 | 686400 |  | Pole Replacements: 51 Critical Repairs: 76
| Pending FAASt Number | 500-PONCE TC-COSTA SUR SP-CANAS TC | Transmission | Pole Replacement |  |  | 2495000 | 2220550 | 274450 |  | Pole Replacements: 23 Critical Repairs: 13
| Pending FAASt Number | 2100-HATILLO TC-QUEBRADILLAS SECT- | Transmission | Pole Replacement |  |  | 1315000 | 1170350 | 144650 |  | Pole Replacements: 7 Critical Repairs: 41
| Pending FAASt Number | 9300-JUNCOS TC-GAUTIER BENITEZ SECT- | Transmission | Pole Replacement |  |  | 1365000 | 1214850 | 150150 |  | Pole Replacements: 9 Critical Repairs: 31
| Pending FAASt Number | 2000-ONCE DE AGOSTO SECT-SAN SEBASTIAN TC- | Transmission | Pole Replacement |  |  | 3265000 | 2905850 | 359150 |  | Pole Replacements: 28 Critical Repairs: 31
| Pending FAASt Number | 50900-AGUIRRE SP-AGUAS BUENAS TC- | Transmission | Pole Replacement |  |  | 540000 | 480600 | 59400 |  | Pole Replacements: 0 Critical Repairs: 36
| Pending FAASt Number | 7300-BALDRICH SECT-SAN JOSE TO- | Transmission | Pole Replacement |  |  | 965000 | 858850 | 106150 |  | Pole Replacements: 8 Critical Repairs: 11
| Pending FAASt Number | 50700-AGUIRRE SP-AES PUERTO RICO- | Transmission | Pole Replacement |  |  | 315000 | 280350 | 34650 |  | Pole Replacements: 0 Critical Repairs: 21
| Pending FAASt Number | 1600-LEON SECT-ACACIAS TC- | Transmission | Pole Replacement |  |  | 2020000 | 1797800 | 222200 |  | Pole Replacements: 19 Critical Repairs: 8
| Pending FAASt Number | 51000-AGUAS BUENAS TC-SABANA LLANA TC- | Transmission | Pole Replacement |  |  | 405000 | 360450 | 44550 |  | Pole Replacements: 0 Critical Repairs: 27
| Pending FAASt Number | 37500-RIO BAYAMON SECT-MONACILLOS TC- | Transmission | Pole Replacement |  |  | 1450000 | 1290500 | 159500 |  | Pole Replacements: 13 Critical Repairs: 10
| Pending FAASt Number | 300-TORO NEGRO 1 HP-JUANA DIAZ TC- | Transmission | Pole Replacement |  |  | 2545000 | 2265050 | 279950 |  | Pole Replacements: 19 Critical Repairs: 43
| Pending FAASt Number | 13200-DORADO TC-HATO TEJAS TC- | Transmission | Pole Replacement |  |  | 580000 | 516200 | 63800 |  | Pole Replacements: 4 Critical Repairs: 12
| Pending FAASt Number | 7200-BALDRICH SECT-ESCUELA INDUSTRIAL TO- | Transmission | Pole Replacement |  |  | 370000 | 329300 | 40700 |  | Pole Replacements: 1 Critical Repairs: 18
| Pending FAASt Number | 8100-YAUCO 1 HP-ADJUNTAS TO- | Transmission | Pole Replacement |  |  | 4195000 | 3733550 | 461450 |  | Pole Replacements: 40 Critical Repairs: 13
| Pending FAASt Number | 10500-CHARDON SECT-LAS MONJAS TO- | Transmission | Pole Replacement |  |  | 190000 | 169100 | 20900 |  | Pole Replacements: 1 Critical Repairs: 6
| Pending FAASt Number | 36200-MONACILLOS TC-JUNCOS TC- | Transmission | Pole Replacement |  |  | 5445000 | 4846050 | 598950 |  | Pole Replacements: 51 Critical Repairs: 23
| Pending FAASt Number | 6500-TORO NEGRO 1 HP-BARRANQUITAS TC- | Transmission | Pole Replacement |  |  | 2350000 | 2091500 | 258500 |  | Pole Replacements: 22 Critical Repairs: 10
| Pending FAASt Number | 6100-MAYAGUEZ GP-RADIAL- | Transmission | Pole Replacement |  |  | 1085000 | 965650 | 119350 |  | Pole Replacements: 8 Critical Repairs: 19
| Pending FAASt Number | 1700-GUANICA TC-YAUCO 2 HP- | Transmission | Pole Replacement |  |  | 3950000 | 3515500 | 434500 |  | Pole Replacements: 38 Critical Repairs: 10
| Pending FAASt Number | 9900-RIO BLANCO HP-HUMACAO SECT- | Transmission | Pole Replacement |  |  | 1420000 | 1263800 | 156200 |  | Pole Replacements: 10 Critical Repairs: 28
| Pending FAASt Number | 10100-LAS LOMAS SECT-REPARTO METROPOLITANO TO- | Transmission | Pole Replacement |  |  | 620000 | 551800 | 68200 |  | Pole Replacements: 2 Critical Repairs: 28
| Pending FAASt Number | 2100-DOS BOCAS HP-HATILLO TC- | Transmission | Pole Replacement |  |  | 685000 | 609650 | 75350 |  | Pole Replacements: 4 Critical Repairs: 19
| Pending FAASt Number | 14100-BARCELONETA TC-MERCK- | Transmission | Pole Replacement |  |  | 165000 | 146850 | 18150 |  | Pole Replacements: 0 Critical Repairs: 11
| Pending FAASt Number | 36100-DOS BOCAS HP-BARRIO PIÑA SECT- | Transmission | Pole Replacement |  |  | 1205000 | 1072450 | 132550 |  | Pole Replacements: 8 Critical Repairs: 27
| Pending FAASt Number | 5200-CAGUAS TC-AGUAS BUENAS SECT- | Transmission | Pole Replacement |  |  | 105000 | 93450 | 11550 |  | Pole Replacements: 0 Critical Repairs: 7
| Pending FAASt Number | 16300-CAMBALACHE TC-SUPER ACUEDUCTO- | Transmission | Pole Replacement |  |  | 205000 | 182450 | 22550 |  | Pole Replacements: 1 Critical Repairs: 7
| Pending FAASt Number | 11200-BUENA VISTA SECT-VILLA DEL CARMEN TO- | Transmission | Pole Replacement |  |  | 105000 | 93450 | 11550 |  | Pole Replacements: 0 Critical Repairs: 7
| Pending FAASt Number | 18100-JUNCOS TC-RADIAL- | Transmission | Pole Replacement |  |  | 300000 | 267000 | 33000 |  | Pole Replacements: 0 Critical Repairs: 20
| Pending FAASt Number | 1000-VILLA PRADES SECT-CAPUCHINOS SECT- | Transmission | Pole Replacement |  |  | 210000 | 186900 | 23100 |  | Pole Replacements: 0 Critical Repairs: 14
| Pending FAASt Number | 50300-AGUIRRE SP-COSTA SUR SP- | Transmission | Pole Replacement |  |  | 150000 | 133500 | 16500 |  | Pole Replacements: 0 Critical Repairs: 10
| Pending FAASt Number | 50900-AGUAS BUENAS TC-BAYAMON TC- | Transmission | Pole Replacement |  |  | 390000 | 347100 | 42900 |  | Pole Replacements: 0 Critical Repairs: 26
| Pending FAASt Number | 3100-PALMER TC-FAJARDO TC- | Transmission | Pole Replacement |  |  | 200000 | 178000 | 22000 |  | Pole Replacements: 2 Critical Repairs: 0
| Pending FAASt Number | 3100-CANOVANAS SECT-RIO GRANDE TO- | Transmission | Pole Replacement |  |  | 45000 | 40050 | 4950 |  | Pole Replacements: 0 Critical Repairs: 3
| Pending FAASt Number | 36100-CANA SECT-BAYAMON TC- | Transmission | Pole Replacement |  |  | 150000 | 133500 | 16500 |  | Pole Replacements: 0 Critical Repairs: 10
| Pending FAASt Number | 5600-AÑASCO TC-MAYAGUEZ GP- | Transmission | Pole Replacement |  |  | 100000 | 89000 | 11000 |  | Pole Replacements: 1 Critical Repairs: 0
| Pending FAASt Number | 4700-CANAS TC-ADJUNTAS TO- | Transmission | Pole Replacement |  |  | 1670000 | 1486300 | 183700 |  | Pole Replacements: 14 Critical Repairs: 18
| Pending FAASt Number | 4100-COMERIO TC-GUARAGUAO SECT- | Transmission | Pole Replacement |  |  | 105000 | 93450 | 11550 |  | Pole Replacements: 0 Critical Repairs: 7
| Pending FAASt Number | 38300-MONACILLOS TC-SAN JUAN SP- | Transmission | Pole Replacement |  |  | 680000 | 605200 | 74800 |  | Pole Replacements: 2 Critical Repairs: 32
| Pending FAASt Number | 9200-AÑASCO TC-AÑASCO- | Transmission | Pole Replacement |  |  | 610000 | 542900 | 67100 |  | Pole Replacements: 4 Critical Repairs: 14
| Pending FAASt Number | 5400-RIO BLANCO HP-DAGUAO TC- | Transmission | Pole Replacement |  |  | 350000 | 311500 | 38500 |  | Pole Replacements: 2 Critical Repairs: 10
| Pending FAASt Number | 3800-CIDRA SECT-CAYEY TC- | Transmission | Pole Replacement |  |  | 160000 | 142400 | 17600 |  | Pole Replacements: 1 Critical Repairs: 4
| Pending FAASt Number | 50200-MANATI TC-BAYAMON TC- | Transmission | Pole Replacement |  |  | 165000 | 146850 | 18150 |  | Pole Replacements: 0 Critical Repairs: 11
| Pending FAASt Number | 3600-MONACILLOS TC-SABANA LLANA TC- | Transmission | Pole Replacement |  |  | 175000 | 155750 | 19250 |  | Pole Replacements: 1 Critical Repairs: 5
| Pending FAASt Number | 14400-CAGUAX SECT-VEREDAS SECT- | Transmission | Pole Replacement |  |  | 2115000 | 1882350 | 232650 |  | Pole Replacements: 21 Critical Repairs: 1
| Pending FAASt Number | 14400-VEREDAS SECT-GAUTIER BENITEZ SECT- | Transmission | Pole Replacement |  |  | 300000 | 267000 | 33000 |  | Pole Replacements: 3 Critical Repairs: 0
| Pending FAASt Number | 3100-FAJARDO TC-DAGUAO TC- | Transmission | Pole Replacement |  |  | 105000 | 93450 | 11550 |  | Pole Replacements: 0 Critical Repairs: 7
| Pending FAASt Number | 3600-SABANA LLANA TC-LOS ANGELES SECT- | Transmission | Pole Replacement |  |  | 195000 | 173550 | 21450 |  | Pole Replacements: 0 Critical Repairs: 13
| Pending FAASt Number | 36900-CANAS TC-PONCE TC- | Transmission | Pole Replacement |  |  | 45000 | 40050 | 4950 |  | Pole Replacements: 0 Critical Repairs: 3
| Pending FAASt Number | 5800-SAN FERNANDO SECT-CHARDON SECT- | Transmission | Rebuild |  |  | 11700000 | 9594000 | 2106000 |  | Out of Service underground line it is important for the reliability and resiliency of the system.
| Pending FAASt Number | 3300-CHARDON SECT-BALDRICH SECT- | Transmission | Rebuild |  |  | 6050000 | 4961000 | 1089000 |  | Out of Service underground line it is essential for maintaining system reliability and resiliency.
| Pending FAASt Number | 17100-MARTIN PEÑA TC-COLISEO SECT- | Transmission | Rebuild |  |  | 4125000 | 3382500 | 742500 |  | Out of Service underground line it is vital for reliability and resiliency and also serves as a backup for the Coliseo de Puerto Rico, which functions as an emergency shelter.
| Pending FAASt Number | 40700-BAYAMON TC-PALO SECO SP- | Transmission | Rebuild |  |  | 52222221.7 | 42822221.794 | 9399999.906 |  | Out of Service line significantly impacts the resiliency of the 115 kV system.
| Pending FAASt Number | 7500-TRES MONJITAS SECT-PUERTO NUEVO TO- | Transmission | Rebuild |  |  | 7444575 | 6104551.5 | 1340023.5 |  | Out of Service line it is is critical for the reliability of the 38 kV system.
| Pending FAASt Number | 1000-CAPUCHINOS SECT-VENEZUELA SECT- | Transmission | Rebuild |  |  | 1856100 | 1522002 | 334098 |  | Critical line for the system.
| Pending FAASt Number | 3500-MONACILLOS TC-LAS LOMAS SECT- | Transmission | Rebuild |  |  | 3813075 | 3126721.5 | 686353.5 |  | Critical line for the system.
| Pending FAASt Number | 3300-EGOZCUE SECT-MARTIN PEÑA TC- 3300-MARTIN PEÑA TC-POPULAR SECT- 3300-POPULAR SECT-CHARDON SECT- | Transmission | Rebuild |  |  | 6850000 | 5617000 | 1233000 |  | Fundamental for the 38kV system in the metropolitan area.
| Pending FAASt Number | 36100-BARRIO PIÑA SECT-CANA SECT- | Transmission | Rebuild |  |  | 7108943.1 | 5829333.342 | 1279609.758 |  | Critical line for the 115kV system.
| Pending FAASt Number | 36100-CANA SECT-BAYAMON TC- | Transmission | Rebuild |  |  | 15592281.866 | 12785671.1301 | 2806610.7359 |  | Critical line for the 115kV system.
| Pending FAASt Number | 37400-BARCELONETA TC-CAMBALACHE TC- | Transmission | Rebuild |  |  | 23175154.506 | 19003626.6949 | 4171527.8111 |  | Critical line for the 115kV system.
| Pending FAASt Number | 37400-CAMBALACHE TC-DOS BOCAS HP- | Transmission | Rebuild |  |  | 21516401.116 | 17643448.9151 | 3872952.2009 |  | Critical line for the 115kV system.
| Pending FAASt Number | 37400-DORADO TC-HATO TEJAS TC- | Transmission | Rebuild |  |  | 11611273.73 | 9521244.4586 | 2090029.2714 |  | Critical line for the 115kV system.
| Pending FAASt Number | 37400-DORADO TC-VEGA BAJA TC- | Transmission | Rebuild |  |  | 21326829.3 | 17488000.026 | 3838829.274 |  | Critical line for the 115kV system.
| Pending FAASt Number | 37400-HATO TEJAS TC-BAYAMON TC- | Transmission | Rebuild |  |  | 9123143.645 | 7480977.7889 | 1642165.8561 |  | Critical line for the 115kV system.
| Pending FAASt Number | 37400-MANATI TC-BARCELONETA TC- | Transmission | Rebuild |  |  | 20805506.806 | 17060515.5809 | 3744991.2251 |  | Critical line for the 115kV system.
| Pending FAASt Number | 37400-VEGA BAJA TC-MANATI TC- | Transmission | Rebuild |  |  | 10971468.851 | 8996604.4578 | 1974864.3932 |  | Critical line for the 115kV system.
| Pending FAASt Number | Bayamon Pueblo Sect. Substation Rebuild | Substation | Substation Rebuild | Project scope to be developed and approved by leadership | 0 | 40000000 | 24000000 | 16000000 | Project scope to be developed and approved by leadership | Rebuild of priority sectionalizing substation; will include in scope the rebuild of distribution substation 1715 Bayamón Pueblo II and rebuild and conversion of distribution substation 1701 Bayamón Pueblo to 13.2 kV (only 4.8 kV substation on system).
| Pending FAASt Number | Dos Bocas HP Substation Rebuild | Substation | Substation Rebuild | Project scope to be developed and approved by leadership | 0 | 70000000 | 42000000 | 28000000 | Project scope to be developed and approved by leadership | Rebuild of priority Transmission Center; will include in scope the rebuild of distribution substation 8005 Dos Bocas
| Pending FAASt Number | Falu 1334 Substation Rebuild | Substation | Substation Rebuild | Project scope to be developed and approved by leadership | 0 | 10000000 | 6000000 | 4000000 | Project scope to be developed and approved by leadership | Rebuild of Falú 1334 Distribution Substation
| Pending FAASt Number | Pastillo Substation Rebuild | Substation | Substation Rebuild | Project scope to be developed and approved by leadership | 0 | 20000000 | 3000000 | 17000000 | Project scope to be developed and approved by leadership | Rebuild of sectionalizing substation including colocated 5801 Pastillo distribution substations and rebuild in site distribution substation 5803 Fort Allen (destroyed in fire in early 2021 with loads being supplied by a mobile substation).
| Pending FAASt Number | Ponce TC Substation Rebuild | Substation | Substation Rebuild | Project scope to be developed and approved by leadership | 0 | 60000000 | 36000000 | 24000000 | Project scope to be developed and approved by leadership | Rebuild of priority Transmission Center; will include in scope the rebuild of distribution substations 5001 Ponce Pueblo, 5010 Hostos 4 kV and 5011 Hostos 13 kV.
| Pending FAASt Number | Aguilita 5817 Substation Relocation | Substation | Substation Rebuild | Project scope to be developed and approved by leadership | 0 | 12000000 | 1200000 | 10800000 | Project scope to be developed and approved by leadership | Relocation of substation 5817 due to flooding risk as it is located in area identified by FEMA as floodway.
| Pending FAASt Number | San Lorenzo 3301 Substation Relocation | Substation | Substation Rebuild | Project scope to be developed and approved by leadership | 0 | 20000000 | 2000000 | 18000000 | Project scope to be developed and approved by leadership | Relocation of substation 3301due to flooding risk as it is located in area identified by FEMA as floodway and co-location of new 13.2 kV substation to provide support and redundancy to substations 3205 Juncos TC 13 kV and 2603 Humacao TC 13 kV.
| Pending FAASt Number | New Breñas 13.2 kV Substation | Substation | Substation Rebuild | Project scope to be developed and approved by leadership | 0 | 9000000 | 4500000 | 4500000 | Project scope to be developed and approved by leadership | New 13.2 kV substation in Breñas Sectionalizer to provide support and redundancy to substations 9206 Dorado PDS, 9207 Dorado TC and 9004 Vega Baja TC. Additional land adjacent to Breñas substation in process of being acquired from Dorado Beach Properties. Current scope considers re-using elements from the existing Cataño Substation including transformer, PDS and high side breaker.
| Pending FAASt Number | New Saint Just 13.2 kV Substation | Substation | Substation Rebuild | Project scope to be developed and approved by leadership | 0 | 15000000 | 7500000 | 7500000 | Project scope to be developed and approved by leadership | New 13.2 kV substation and 38 kV sectionalizer adjacent to transmission lines 3100 and 3600 to provide support and redundancy to substations 1204 Conquistador, 1206 Encantada, 1620 Parque Escorial and 1336 Berwind TC. Land targeted for project is within/adjacent to ROW of 3100/3600 Tline adjacent to PR-199.
| Pending FAASt Number | New Yeguada (Camuy) Substation | Substation | Substation Rebuild | Project scope to be developed and approved by leadership | 0 | 6000000 | 3000000 | 3000000 | Project scope to be developed and approved by leadership | New 13.2 kV substation to provide support and redundancy to substations 7601 Camuy, 7602 Camuy Provisional, 7402 Quebradillas and 7404 Quebradillas Provisional. Site already acquired by PREPA.
| Pending FAASt Number | Fiber Optic Replacement Group 1 | IT/OT | N/A | LUMA PM Collaboration Development |  | 13696712.24 | 13420380.74 | 276331.5 | Project in formulation phase, DSOW and cost estimate pending review. | 30% of the design not finish, not approved yet. Original ISOW approved by FEMA for island wide fiber project 200 million
| Pending FAASt Number | Transport Network Group 2, 57 sites | IT/OT | N/A | LUMA PM Collaboration Development |  | $70,021,267.04 | $38,511,696.87 | $31,509,570.17 | Project in formulation stage, pending completion of DSOW and LUMA Project Cost Estimate | 30% design for make ready and telecom equipment have been completed by internal Telecom Engineering. 428 PA and 406 HM split are based on percentages from Group 1 Ver 1, submitted to FEMA.
| Pending FAASt Number | Transport Network Group 3, 60 sites | IT/OT | N/A | Planning Phase | 0 | $73,706,596.88 | $40,538,628.28 | $33,167,968.60 | Planning Phase | 30% design not finish, not approved yet. Cost etsimate is based on cost per site and split calculations from Group 2 estimate.
| Pending FAASt Number | Transport Network Group 4, 60 sites | IT/OT | N/A | Planning Phase | 0 | $73,706,596.88 | $40,538,628.28 | $33,167,968.60 | Planning Phase | 30% design not finish, not approved yet. Cost etsimate is based on cost per site and split calculations from Group 2 estimate.
| Pending FAASt Number | Transport Network Group 5, 60 sites | IT/OT | N/A | Planning Phase | 0 | $73,706,596.88 | $40,538,628.28 | $33,167,968.60 | Planning Phase | 30% design not finish, not approved yet. Cost etsimate is based on cost per site and split calculations from Group 2 estimate.
| Pending FAASt Number | Transport Network Group 6, 60 sites | IT/OT | N/A | Planning Phase | 0 | $73,706,596.88 | $40,538,628.28 | $33,167,968.60 | Planning Phase | 30% design not finish, not approved yet. Cost etsimate is based on cost per site and split calculations from Group 2 estimate.
| Pending FAASt Number | Transport Network Group 7, 68 sites | IT/OT | N/A | Planning Phase | 0 | $83,534,143.14 | $45,943,778.72 | $37,590,364.41 | Planning Phase | 30% design not finish, not approved yet. Cost etsimate is based on cost per site and split calculations from Group 2 estimate.
| Pending FAASt Number | Infrastructure Group I | IT/OT | N/A | Initiation Phase | 0 | 0 | 0 | 0 | Under formulation. | Project under development by engineering.
| Pending FAASt Number | FAASt [Pole and Conductor Repair - Mayaguez Group 5 - Phase 2 | Distribution | Pole and Conductors |  | TBD | 7610000 | TBD | TBD | Under formulation. | WTBC
| Pending FAASt Number | FAASt [Pole and Conductor Repair -Arecibo Group 18-19-20-21 - Phase 3 | Distribution | Pole and Conductors |  | TBD | 7610000 | TBD | TBD | Under formulation. | WTBC
| Pending FAASt Number | Aguadilla Custumer Experince | Buildings | N/A | for COR3 review | TBD | TBD | TBD | TBD | Under formulation by IEM team | WTBC
| 169576 | Arecibo Bulding Repair | Buildings | N/A | for COR3 review | TBD | TBD | TBD | TBD | Under formulation by IEM team | WTBC
| 169798 | Arecibo Electric Service Center | Buildings | N/A | for COR3 review | TBD | TBD | TBD | TBD | Under formulation by IEM team | WTBC
| Pending FAASt Number | Barranquitas Electric Service Center | Buildings | N/A | LUMA Environmental Review | TBD | TBD | TBD | TBD | Under formulation in the Collabroation process (Appian) | WTBC
| Pending FAASt Number | Bayamon Electric Service Center (Minillas) | Buildings | N/A | for COR3 review | TBD | TBD | TBD | TBD | Under formulation by IEM team | WTBC
| Pending FAASt Number | Guayama Electric Service Center | Buildings | N/A | for COR3 review | TBD | TBD | TBD | TBD | Under formulation by IEM team | WTBC
| Pending FAASt Number | Sabana Llana Electric Service Center | Buildings | N/A | for COR3 review | TBD | TBD | TBD | TBD | Under formulation by IEM team | WTBC
| Pending FAASt Number | Toa Alta Electric Service Center | Buildings | N/A | for COR3 review | TBD | TBD | TBD | TBD | Under formulation by IEM team | WTBC
| Pending FAASt Number | Vega Baja Electric Service Center | Buildings | N/A | for COR3 review | TBD | TBD | TBD | TBD | Under formulation by IEM team | WTBC
[6 empty] | 214666.04 | 1946461176.4104 | 1573672930.2447 | 357568246.1657

## MPL (hidden)
Program Brief | P/W | FAASt Number | Major Project Number | Sub Project ID | Financial Project Number | Financial Project Name (Oracle) | Project Status (Finance) | Project Status (Project Online) | Project Budgetary Phase | Project Cost Exceeds 90% of Budget | Grants Portal Process Status | Grants Portal Process Phase | Grants Portal Process Step | A&E Planned Start | A&E Actual Start | DSOW Planned Submittal | DSOW Submittal Date | Date Obligated
CUSTOMER |  |  | 90017 | 90017 | 10N000550000 | WR-5836046Kevin Rolon20-2-0329 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N000560000 | WR-6154396 Temp. JW Marriott | Active
CUSTOMER |  |  | 90017 | 90017 | 10N000570000 | WR-6123751 Marlene Cruz | Active
CUSTOMER |  |  | 90017 | 90017 | 10N000600000 | WR-6176658 Ernier Rodríguez | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N000610000 | WR-6181934 Top Shelf | Active
CUSTOMER |  |  | 90017 | 90017 | 10N000620000 | WR6079873 16-4-1053 PBorinqu | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N000630000 | WR-6183994 ; 20-2-0338 RIG LLC | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N000640000 | WR-5967896 Marisol Rivera | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N000650000 | WR-5894902 Lervia Negron | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N000740000 | WR-6176682 Edwin Rodríguez | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N000830000 | WR-6167745 21-2-0159 J ROMERO | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N000840000 | WR-6108081;Jacobo Ortiz Blanes | Active
CUSTOMER |  |  | 90017 | 90017 | 10N000850000 | WR-6228094 ;REMPLAZO POSTE SUB | Active
CUSTOMER |  |  | 90017 | 90017 | 10N000860000 | WR-6009778;MAS Integ School | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N000870000 | WR-6117690; Vanessa Vazquez | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N000880000 | WR-6151992 SharileilToroDávila | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N000890000 | WR-6241054 Pedro Santiago | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N000900000 | WR-6103054 MValentin 19-4-0028 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N000960000 | WR-6220492 - Ivy Medical | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N000980000 | WR-6174311 (2021-GD-08940) | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N000990000 | WR-22-DCG164 Fomento | Active
CUSTOMER |  |  | 90017 | 90017 | 10N001000000 | WR-6261811 ALUMB PR30 SAL GURB | Active
CUSTOMER |  |  | 90017 | 90017 | 10N001010000 | WR-6115220;Resid Jorge Torres | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001020000 | WR-5845235 ; Benjamín Nieves | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001030000 | WR-6091994 ; Carmen Ramos | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001040000 | WR-6170207 ; José Corchado | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001050000 | WR-6174530;Manuel LucianoPérez | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001060000 | WR-6187820;JEIZABEL CABAN HERN | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001070000 | WR-6226433;Finca Carlos Mendez | Active
CUSTOMER |  |  | 90017 | 90017 | 10N001080000 | WR-6175527 ; CROMA | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001090000 | WR-6232259;Resid Jason Quiles | Active
CUSTOMER |  |  | 90017 | 90017 | 10N001100000 | WR5955659;Seg.9Sol.CarlosLeon | Active
CUSTOMER |  |  | 90017 | 90017 | 10N001110000 | WR-5961118; Borincanna | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001120000 | WR-6237016; Hera Printing | Active
CUSTOMER |  |  | 90017 | 90017 | 10N001130000 | WR6278409;Sabanera Isla Norte | Active
CUSTOMER |  |  | 90017 | 90017 | 10N001140000 | WR-6219987;22-D133HIGHQUALCANN | Active
CUSTOMER |  |  | 90017 | 90017 | 10N001150000 | WR-5974883 ; 21-2-0402 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001160000 | WR-6114262 ; 22-2-0270 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001170000 | WR-6268370 21-2-0165 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001180000 | WR-6169107;AAA PZO R GRANDE II | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001190000 | WR-6187338 ; ISRAEL RAMOS DIAZ | Active
CUSTOMER |  |  | 90017 | 90017 | 10N001200000 | WR-6113297;4 Solares Derling A | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001210000 | WR-6117870;Elisamuel Caraballo | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001220000 | WR-6223792; RES MIGUEL NAZARIO | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001230000 | WR:6276513;RES RAQUEL REYES F | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001240000 | WR-6278148 ; 22-2-0526 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001250000 | WR6149265 22-2-0455 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001260000 | WR-6228337; 22-2-0665 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N001270000 | WR-6228473 Antonio GarcíaGómez | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001280000 | WR-6128986;Las Casitas Corcega | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001290000 | WR-6287234;Omar Ortiz20-4-0044 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N001300000 | WR-6161065 ; 22-2-0444 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001310000 | WR-6271191; 22-2-0828 ACT | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001320000 | WR-6055922;RES LUCAS RODRIGUEZ | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001330000 | WR-6164508 Miguel Cortés | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001340000 | WR-6262234 22-2-0648 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001350000 | WR-6100754 José Martínez | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001360000 | WR6114915 Miguel Nieves | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001370000 | WR6128244 BIOMED | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001380000 | WR6271166 22-2-0709 PABLO CRUZ | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001390000 | WR-6278880 22-DCG190 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N001410000 | WR6285717-PlazoletasGuaynabo | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001420000 | WR6288822 21-3-153 ESC.BENICIA | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001430000 | WR6121042 19-0-001 subscooperv | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001440000 | WR6272612 SubwayAmericasPonce | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001450000 | WR6282899 21-3-061 Plaza JDiaz | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001460000 | WR6220745 22-3-0181-EE Egberto | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001470000 | WR22-DCG168 EDP UNIV.RECO.SUBS | Active
CUSTOMER |  |  | 90017 | 90017 | 10N001480000 | WR- 626824 22-2-0726 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001490000 | WR6294553 23-DCG016 MICROSOFT | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001500000 | WR6163589 22-2-0363 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001510000 | WR6262829 22-2-0698 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001520000 | WR5378397 LabClín F Montañez | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001530000 | WR-6272270 ; LUIS MERCADO | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001540000 | WR6292168DCG009AAA RHONDOCOMER | Active
CUSTOMER |  |  | 90017 | 90017 | 10N001550000 | WR6288411 GMT FREEZER@CAGUAS | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001560000 | WR-6291192 22-2-0854 Milton Ra | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001570000 | WR5700865 WCardona Thre(PREPA) | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001580000 | WR-6293364 Avara Pharmaceutica | Active
CUSTOMER |  |  | 90017 | 90017 | 10N001590000 | WR-6294543 Luis Martínez LPC | Active
CUSTOMER |  |  | 90017 | 90017 | 10N001600000 | WR-6293375 SUB PRIV REP AVERIA | Active
CUSTOMER |  |  | 90017 | 90017 | 10N001610000 | WR6108071 FelipeMaisonetMaldon | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001620000 | WR6288504 RELOC.INFRA@AIBONIT | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001630000 | WR6288392 22-DCG221 AAA@SLOREN | Active
CUSTOMER |  |  | 90017 | 90017 | 10N001640000 | WR5980230 RRamosMiraf11-5-0132 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001650000 | WR6126834 Rafael Zayas Rolon | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001670000 | WR6125621 William Quintana | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001680000 | WR6297190 PARARRAYOS BAHIA URB | Active
CUSTOMER |  |  | 90017 | 90017 | 10N001690000 | WR6228094 Reempl Poste | Active
CUSTOMER |  |  | 90017 | 90017 | 10N001700000 | WR6294166 22-2-0958 Edwin Rodz | Active
CUSTOMER |  |  | 90017 | 90017 | 10N001710000 | WR6288255 22-2-0936 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001720000 | WR6293578 22-2-0451 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001730000 | WR6283207 22-2-0869 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001740000 | WR6272672 22-2-0457 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001750000 | WR6277803 22-1-0294 SAIGONNAIL | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001760000 | WR6288621 22-2-0912 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001770000 | WR6289569 20-6-0042 TRA.C.CAMP | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001780000 | 23-DSJ-0073 AAAMETRO LOIZAVALL | Cancel
CUSTOMER |  |  | 90017 | 90017 | 10N001790000 | 23-1-0047-CC WR6301157 AL.PR-8 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001800000 | 16-6-0426 RE.POST.FAIRFIEL.INN | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001810000 | WR6271790 18-1-004 PSTEM.BUENA | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001820000 | WR6304164 23-2-0164 UPR Cayey | Active
CUSTOMER |  |  | 90017 | 90017 | 10N001830000 | WR6303293 22-2-0909 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001840000 | WR6268038 21-6-0096 BRILLONES | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001850000 | WR6291733 Borincanna Warehouse | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001860000 | WR6008934 03-3-065 HS/EHSGuaya | Active
CUSTOMER |  |  | 90017 | 90017 | 10N001870000 | WR6309453 H.Velez(Baxter-Jayuy | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001880000 | WR6304166 Coabey Site | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001890000 | WR5998644-Liberty CRAN 208 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001900000 | WR6303586-Liberty SJU04-216 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001910000 | WR6156339 THERMO-TK2 16-5-0437 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001920000 | WR6305230 23-3-0083-EEDTOPGuay | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001930000 | WR6307492 21-6-0160 FAAantYunq | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001940000 | WR6070235 VELEROS DEL PUERTO | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001950000 | WR6303704 Antonio Bechara | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001960000 | WR6301072 RemLinPrimCoastGuard | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001970000 | WR6283346 Igl.AndandoEnElEspir | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001980000 | WR6300617 A.Gregory 97-0-482.1 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N001990000 | WR6219807 19-1-216PosteSGERARD | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002000000 | WR6300184 23-4-0054-EE N.Roman | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002010000 | WR6299704 23-7-046-EE Benjamin | Active
CUSTOMER |  |  | 90017 | 90017 | 10N002020000 | WR5681231 20-7-026 BIOMED | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002030000 | WR6295256 Jose Colon | Closed
CUSTOMER |  |  | 90017 | 90017 | 10N002040000 | WR6294353 23-4-0023-EE R.Lopez | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002050000 | WR6304463 Organic Power | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002060000 | 23-4-0098-EE FELUCA LLC | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002070000 | WR6300352 23-4-0055-EE RVARGAS | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002080000 | 9-4-0129 WR6309442 CasCorcega | Active
CUSTOMER |  |  | 90017 | 90017 | 10N002090000 | WR5704295 20-4-0107-EE L.Marin | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002100000 | WR6269090 21-4-0037 QMCTELECOM | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002110000 | WR6275398 22-4-0563-EE W.Perez | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002120000 | 22-4-0649-EE WR6287455 JarvisC | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002130000 | WR6302207 23-5-0174-EE J.Ramos | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002140000 | CComerLEVIT 18-7-104 WR5944196 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N002150000 | WR6083551 22-4-0035-EE CValent | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002160000 | WR6281373 22-1-0893RelLinCubuy | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002170000 | WR6305117 23-4-0087-EE M.Kener | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002180000 | WR6306212 23-4-0106-EE BartCor | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002190000 | WR6306507 23-2-0101 L.Velazq | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002200000 | WR6308651 21-7-209-EE C.Senior | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002210000 | WR6309616 23-5-0072-CC D.Aceve | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002220000 | WR6306224 2-2-0880 FernAyala | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002230000 | WR6310090 23-4-0049-CC CantRod | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002240000 | WR6308646 23-4-0132-EE JMedina | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002250000 | WR6269090 22-4-0524-EE JorReye | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002260000 | WR6308940 23-4-0131-EE VeneraG | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002270000 | WR63020109 23-7-037 EE Colimar | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002280000 | WR6298478 21-2-0401 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N002290000 | WR5528841 15-5-0350CemNacMorov | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002300000 | WR6305804 20-5-0100At&TPonient | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002310000 | WR6307999 21-5-0109 GarrochQMC | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002320000 | WR6313593 23-4-0167-EE JIMMY R | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002330000 | WR6298908 03-5-0483 Marbela Ca | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002340000 | WR-6310681 Antunez & Son | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002350000 | WR-62040369 ARNA 22-1-0359-CC | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002360000 | WR-6178910;Ext linea secundari | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002370000 | WR-6314417 Marbela Casa de Pla | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002380000 | WR6222520 12-3-056 Luchetti Co | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002400000 | WR6285406 12-2-034 Centro Celu | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002410000 | WR6288491 Julio Pérez González | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002420000 | WR6304752 23-4-0099-EE HectorC | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002430000 | WR6306182 23-4-0110-EE JaimeOl | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002440000 | WR6310766 23-4-0145-EE JoseLRa | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002450000 | WR6311801 22-2-0865 Armando Me | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002460000 | WR5987622 20-4-0156 TAI ANA LL | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002470000 | WR5996576 19-3-057 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002480000 | WR6282924 20-2-0130 SJU06-007 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002490000 | WR6301725 23-5-0141-CC SES Ent | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002500000 | WR6303252 22-2-0950 FernandoZa | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002510000 | WR6310145 21-4-0177 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002520000 | WR6311912 21-4-0044 ThreeAPres | Active
CUSTOMER |  |  | 90017 | 90017 | 10N002530000 | WR6312475 23-4-0161EE HectorRu | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002540000 | WR6280526 22-5-0518-EE V.Brusi | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002550000 | WR6284852 22-4-0630-EE MArocho | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002560000 | WR6306499 19-6-0195 HStartCano | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002570000 | WR6308224 16-4-0053 BlvrdLaVia | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002580000 | WR6312928 21-6-0090 H.StartRDS | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002590000 | WR6223677 21-2-0221 MedSanosCg | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002600000 | WR6309937 23-2-0113 SamariCruz | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002620000 | WR6317284 23-DSJ-0162 Tijuanas | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002630000 | WR6311548 22-5-0333-PP ABuirat | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002640000 | WR6304847 22-1-0804 HUB | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002650000 | WR6304823 22-1-0790 HUB | Active
CUSTOMER |  |  | 90017 | 90017 | 10N002660000 | WR6304939 22-1-0791 HUB | Active
CUSTOMER |  |  | 90017 | 90017 | 10N002670000 | WR6287620 22-1-0792 HUB | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002680000 | WR6304953 22-1-0793 HUB | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002690000 | WR6304982 22-1-0797 HUB | Active
CUSTOMER |  |  | 90017 | 90017 | 10N002700000 | WR6287755 22-1-0798 HUB | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002710000 | WR6305001 22-1-0802 HUB | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002720000 | WR6293059 21-7-150 Telecomsite | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002730000 | WR6301900 & WR6301922 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002740000 | WR6313448 21-7-026-EE AutoGrup | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002750000 | WR6309199 22-3-0204 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002760000 | WR6308927 22-2-0967 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002770000 | WR6317392 05-3-198A | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002780000 | WR6168379 22-7-152-EE M.Perez | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002790000 | WR6316316 23-4-0079-EE | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002800000 | WR6317323 23-7-093 LNG Syst | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002820000 | WR6286903 22-4-0647-EE SoniaRo | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002830000 | WR6319890 HdStartEHdStartVLSan | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002840000 | WR6320730 14-2-567 VL | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002850000 | WR6312499 23-4-0034 AIXA BONIL | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002860000 | WR6313654 23-4-0169-EE JoseCar | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002870000 | WR6317951 22-4-0110 SolaresLuc | Active
CUSTOMER |  |  | 90017 | 90017 | 10N002880000 | WR6319451 23-4-0212-EE CarlosP | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002890000 | WR6315044 16-5-0494 Nicolas | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002900000 | WR6317870 23-4-0020 FoodTru | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002910000 | WR6318831 06-3-084 P.BLANK | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002920000 | WR6320056 23-3-0107 SubPUMA | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002930000 | WR6305574 23-4-0105-EE Enit | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002940000 | WR6309338 20-2-0050 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002950000 | WR6320953 23-4-0224-EE Ricardo | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002960000 | WR6300431 19-2-0393 RamonCastr | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002970000 | WR6319043 93-5-0208B CamDelVa | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002980000 | WR6322334 23-7-147-EE GRL LuxC | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N002990000 | WR6319274 23-4-0210-EE StoWaCh | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003000000 | WR6307602 21-2-0463 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N003010000 | WR6319626 23-2-0375 SubPR53Yab | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003020000 | WR6321912 23-4-0231-EE Glenda | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003030000 | WR6322004 23-4-0232-EE Edwin | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003040000 | WR6164210 22-4-0319-EE Miram | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003050000 | WR6317706 15-4-0370 Lajas Site | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003060000 | WR5982006 14-4-0189 HospDOeste | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003070000 | WR6307530 22-4-0194 SolLLanos | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003080000 | WR6316577 20-4-0086 PepinoCan | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003090000 | WR6318023 21-7-015-EE HERAPrin | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003100000 | WR6321879 23-4-0230 Yol.Gonz | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003110000 | WR6316948 99-4-443 Quintas | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003120000 | WR6314612 23-7-137-EE HubAdvNW | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003130000 | WR6320816 23-1-0271-CC JuanMor | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003140000 | WR6309390 99-0-267 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003150000 | WR6314616 SJU04-96 HubAdvNet | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003160000 | WR6287482 22-1-0794 HUB | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003170000 | WR6287708 22-1-0795 HUB | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003180000 | WR5979872 21-2-0435 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003190000 | WR6268616 05-3-270A RdelSur II | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003200000 | WR6288266 22-1-0801 HSJU04_047 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003210000 | WR6323005 07-5-0210 SigSanch | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003220000 | WR6318986 23-5-0453-EE CarmAro | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003230000 | WR6319092 Avara Arecibo | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003240000 | WR6320317 23-4-0220-EE CGonz | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003250000 | WR6322539 23-4-0239-EE C.Reyes | Closed
CUSTOMER |  |  | 90017 | 90017 | 10N003260000 | WR6324906 23-4-0256-EE JorgeG. | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003270000 | WR6319747 23-4-0219-EE HoOrMay | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003280000 | WR6325201 17-5-0338 MitayAsoc | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003290000 | WR6326081 20-3-002 AC Hwy | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003300000 | WR6313939 20-2-0080 LancoSLore | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003310000 | WR6314000 23-4-0173-EE PtaBorP | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003320000 | WR6284272 06-3-033 ComplDeport | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003330000 | WR6319148 23-4-0208-EE CostGua | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003340000 | WR6319383 23-4-0211-EE Eduardo | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003350000 | WR6327420 23-4-0271-EEWilfredo | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003360000 | WR6319960 19-5-0119 SNS TSP | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003370000 | WR6321998 17-5-0324 EgidaSCora | Active
CUSTOMER |  |  | 90017 | 90017 | 10N003380000 | WR6327873 21-4-0058 CASA413 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003390000 | WR5965367 08-3-073 Co.LaurelCo | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003400000 | WR6316009 21-4-0333 Sol.4Reb | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003410000 | WR6325542 06-3-308-EE OllasGas | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003420000 | WR6327352 Res.CristobalNegron | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003430000 | WR6313451 23-7-126-EE AlbertoT | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003440000 | WR6219438 Jose L. Garcia | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003450000 | WR6309929 23-4-0137-EE Rub.Ace | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003460000 | WR6322778 23-4-0240-EE Shell | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003470000 | WR6329849 23-4-0293 CarmenF | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003480000 | WR6329947 23-4-0294-EE NoelFer | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003490000 | WR-6330759 BURG KING ISABELA | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003500000 | WR6330918 21-3-152 EscRamonPur | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003510000 | WR6284245 InstPostAbelCastro | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003520000 | WR6321388 Segr-AngelD.Carrasqu | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003530000 | WR6326838 IslaNorteSegundaCone | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003540000 | WR6329498 InstCajasSecasVander | Active
CUSTOMER |  |  | 90017 | 90017 | 10N003550000 | WR-6332040 23-4-0331-EEPEPBOYS | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003560000 | WR6328332 AUTO STOP SAN GERMAN | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003570000 | WR6312208 LIBERTY SJU09-07222 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003580000 | WR6331088 23-4-0048 HatiK&K-F1 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003590000 | WR6331137 23-4-0048 Ret-HK&KF2 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003600000 | WR-5965029 SULEIMA HIDALGO | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003610000 | WR6190000 07-5-0137 YamilAQui | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003620000 | WR6325371 23-4-0301-EE IsraelR | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003630000 | WR6325609 22-3-0176 CanabisCen | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003640000 | WR6326292 23-2-0507 Reloc.Infr | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003650000 | WR6326366 23-2-0240 EmilioSant | Active
CUSTOMER |  |  | 90017 | 90017 | 10N003660000 | WR6328272 23-4-0281-EE LuisPer | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003670000 | WR6327216 23-4-0269-EE Robert | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003680000 | WR6328750 23-4-0287-EE EscMDF | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003690000 | WR6290512 23-4-0006-EE HectorS | Active
CUSTOMER |  |  | 90017 | 90017 | 10N003700000 | WR6295356 23-4-0030-EE AdrianA | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003710000 | WR6310307 23-2-0158 CarlosAnd | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003720000 | WR6331899 19-0-016-EE JWMarrio | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003730000 | WR6332748 23-3-165 EscElsaCuot | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003740000 | WR6311541 22-4-0478-EE PR-R3 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003750000 | WR6290328 23-4-0005-EE DavidHn | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003760000 | WR6332356 12-4-0130 CGobAguada | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003770000 | WR6336402 23-4-0219B-EE HomeOr | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003780000 | WR6305074 23-2-0156 EpifaniaDi | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003790000 | WR6331900 23-4-0279-EE Maritza | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003800000 | WR6333411 22-4-0197 Pharma Max | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003810000 | WR6332286 15-5-0354 SucnFerRiv | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003820000 | WR5329015 97-5-0416 SucnJuanPJ | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003830000 | WR6316184 22-2-0298 AntCeibCid | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003840000 | WR6331746 23-4-0323-EE YadiraM | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003850000 | WR6053537 20-5-0110A GalateoBa | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N003860000 | WR6334529 20-5-0088 Vaq.Alfred | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N004160000 | WR6336457 23-5-0553-CC JoseDav | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N004170000 | WR6338907 23-5-0721-EE JesusNi | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N004180000 | WR6336545 23-5-0599-CC ZahiraM | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N004190000 | WR6177715 22-4-0365-EE RELOC.P | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N004200000 | WR6275933 19-2-0356 Fun.Shalom | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N004210000 | WR6304637 22-2-0452 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N004220000 | WR6315161 23-2-0127 OlgaColon | Active
CUSTOMER |  |  | 90017 | 90017 | 10N004230000 | WR6318000 19-5-0128 OReillyAut | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N004240000 | WR6329242 23-2-0516 JoseVazque | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N004250000 | WR6334262 23-2-0431 AlexandDia | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N004260000 | WR6337534 23-4-0366-EE Jonath | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N004270000 | WR6336933 16-5-0093.2 Boquill | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N004280000 | WR6337968 23-5-0358-CC SamuelH | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N004290000 | WR6332636 23-5-0525-CC AbChim | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N004300000 | WR6179625 22-4-0375-EE Emanuel | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N004310000 | WR6326390 23-2-0365 FoodTrucks | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N004320000 | WR6283639 21-2-0457 MirelysE.R | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N004330000 | WR6335356 23-4-0373-EE AptsJoh | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N004340000 | WR6327863 23-4-0276-EE EdwinJi | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N004360000 | WR5694410 20-4-0101 MiraderoHi | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N004370000 | WR6168379 22-7-152-EE MarcosPe | Cancel
CUSTOMER |  |  | 90017 | 90017 | 10N004380000 | WR6309345 19-2-0173 QMC134LP | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N004390000 | WR6339649-BayaMedicalCenter | Active
CUSTOMER |  |  | 90017 | 90017 | 10N004400000 | WR4307081 11-3-111 AntElCafeta | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N004410000 | WR6327841 22-5-0567 LauraETorr | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N004420000 | WR6338155 23-5-0568 JoseEGuzm | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N004430000 | 22-1-0855 InstPostMiramarGasSt | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N004440000 | WR6341555 23-4-0406-EE NoelOrt | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N004450000 | WR6340253 96-3-123A Urb.S.C.II | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N004460000 | WR6325923 22-1-0927 DistReserv | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N004470000 | WR6337137 23-2-0659 CarlosSald | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N004480000 | WR6340065 23-5-0498 HectOrteg | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N004490000 | WR6339689 23-4-0382-EE ArnVale | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N004500000 | WR6342804 23-7-146-EE OLDACH | Active
CUSTOMER |  |  | 90017 | 90017 | 10N004510000 | WR6343328 22-7-102-EE Montecas | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N004520000 | WR6344041 23-4-0421-EE Orienta | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N004530000 | WR6341983 23-4-0409-EE YolaVal | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N004540000 | WR6316734 16-5-0195 VillaToled | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N004550000 | WR6342196 23-4-0236 DosVillasR | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N004560000 | WR6344859 22-4-0286 MrSpec.May | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N004570000 | WR6327431 23-2-0509 Fase 1 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N004580000 | WR6327492 23-2-0509 Fase 2 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N004590000 | WR6334207 23-5-0282-CC WowLiqu | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N004600000 | WR6325999 23-3-0174-EE RadaSil | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N004610000 | WR6331369 23-4-0321-EE Milagro | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N004620000 | WR6336424 23-4-0356-EE Rolando | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N004630000 | WR6341839 22-3-0010 MaunHealth | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N004640000 | WR6334821 15-2-179 CarolCespoK | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N004650000 | WR6345569 23-4-0434-EE Coliseo | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N004660000 | WR6337096 17-5-0324 EgidaSCora | Active
CUSTOMER |  |  | 90017 | 90017 | 10N004670000 | WR6318853 23-2-0336 MelvinAya | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N004680000 | WR23-DCG165 Buckeye(GCB 36380) | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N004690000 | WR6346434 20-5-0089 Elv,Marg,M | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N004700000 | WR5992063 17-3-128 WilliamRos | Active
CUSTOMER |  |  | 90017 | 90017 | 10N004710000 | WR6325550 21-7-065-EE JacobOrt | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N004720000 | WR6317026 23-3-0020-EE Prudenc | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N004730000 | WR6344017 23-4-0423-EE William | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N004740000 | WR6343621 98-0-432 Mans.Carrai | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N004750000 | WR6345932 21-4-0095 Ant.Combat | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N004760000 | WR6345737 18-5-0046 Sol.JulLyd | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N004770000 | WR6328324 23-4-0282-EE DianaVe | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N004780000 | WR6317586 22-5-0097 W.Alic.O.S | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N004790000 | WR6321247 23-2-0161 EdwinVal. | Active
CUSTOMER |  |  | 90017 | 90017 | 10N004880000 | WR6345613 23-4-0436-EE EBAS Po | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N004890000 | WR6346988 23-4-0446-EE Des.Cos | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N004900000 | WR6342490 88-9-086C.1 Popeyes | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N004910000 | WR6347731 23-1-0025 Post-Elois | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N004920000 | WR6322498 22-4-0490 Trop.Agric | Active
CUSTOMER |  |  | 90017 | 90017 | 10N005000000 | WR6344962 23-7-339-EE CLFerrer | Active
CUSTOMER |  |  | 90017 | 90017 | 10N005010000 | WR6348600 17-1-243 Mir.L.Casas | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005020000 | WR6338474 15-4-0380 MayV.V.HUB | Active
CUSTOMER |  |  | 90017 | 90017 | 10N005030000 | WR6348467 23-4-0050 PaladarEx | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005040000 | WR6347624 02-4-307 EL PEDREGAL | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005050000 | WR6346146 23-4-0441-EE AlmaRV | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005060000 | WR6349516 10-4-0153 AStopMitAg | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005080000 | WR6347337 23-2-0615 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005090000 | WR6347024 23-2-0759 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N005100000 | WR6301876 23-7-057-EE MRivera | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005110000 | WR6342963 22-5-0162 MsterConcr | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005120000 | WR6306281 23-4-0111A PteLQuile | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005130000 | WR6222497 22-5-0340-CC RamonCo | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005140000 | WR6307838 23-4-0192-EE SamGonz | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005150000 | WR6351638 23-4-0490-EE OsvJime | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005160000 | WR6189913 22-4-0414-EE LuisRos | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005170000 | WR6344031 23-4-0127 HectArcela | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005180000 | WR6343965 23-4-0422-EE GilAcev | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005190000 | WR6347224 23-4-0451-EE R.R.AAA | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005200000 | WR6351470 88-9-086D GuayaBurli | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005210000 | WR6350605 15-5-0350 CemNac.Vet | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005220000 | WR6347205 23-20644 Jose Colon | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005230000 | WR6337343 14-3-177 P.FilC.Laur | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005240000 | WR6342109 19-7-051EE SIMNaranj | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005250000 | WR6348439 20-1-241 Mimosa116 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005260000 | WR6326752 23-2-0470 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005270000 | WR6362547 CX-XI-06-23 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005280000 | WR6099149 23-4-0379-EE RCardon | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005290000 | WR6351003 23-4-0483-EE MConcre | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005300000 | WR6351301 23-4-0050-EE RolFdez | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005310000 | WR6360648 15-4-0687 ToyoAguadi | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005320000 | WR6362086 23-4-0523-EE BurlAg | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005330000 | WR4405046 WR5195296 15-3-286 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N005340000 | WR6350231 22-3-0029 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005350000 | WR6360877 23-1-0283 PrfAsphalt | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005360000 | WR6333721 23-5-0199-CC KarenPl | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005370000 | WR6351935 23-5-0977-CC IsraRam | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005390000 | WR4623426 13-3-156 LCaobosComm | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005400000 | WR6089102 22-2-0163 EdifBilloc | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005410000 | WR6331150 17-3-210 SalinasWate | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005420000 | WR6345208 07-5-0305.1 AngOteGo | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005430000 | WR6092160 23-4-0374-EE Madelin | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005440000 | WR6327211 23-4-0258-EE Jaime | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005450000 | WR6093235 23-4-0259-EE JVarela | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005460000 | WR6337543 23-4-0368-EE JCalero | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005470000 | WR6242031 21-4-0102-EE A.Rodz | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005480000 | WR6351429 20-3-002 PR128 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005490000 | WR6331680 01-3-153C BaskRobbin | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005500000 | WR6336650 23-3-0197Gonz.Borrro | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005510000 | WR6347102 23-4-0449-EE Tim.Sla | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005520000 | WR6315286 05-3-166A 5solares | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005530000 | WR6364947 23-4-0558-EE L.Inv.A | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005540000 | WR6337365 23-2-0650 Rosa Neris | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005560000 | WR6361182 23-4-0520-EE E.Roman | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005570000 | WR6361438 21-3-137 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005580000 | WR6364252 99-0-267 PradRioFlor | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005590000 | WR6362879 23-4-0535-EE AgdllaM | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005600000 | WR6364869 23-4-0556-EE Landing | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005610000 | WR6326871 23-4-0260-EE HMercad | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005620000 | WR6319490 23-4-0213-EE JBenite | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005650000 | WR6348430 23-2-0669 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005660000 | WR6340081 20-5-0058 A.R.LCorde | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005670000 | WR6365085 23-7-445-EE VP PETRO | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005680000 | WR6344088 21-4-0405 Solar.Nita | Active
CUSTOMER |  |  | 90017 | 90017 | 10N005690000 | WR6360245 23-7-265-EE SweeBkry | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005720000 | WR6368279 22-7-093 P.DosifHorm | Active
CUSTOMER |  |  | 90017 | 90017 | 10N005730000 | WR6344976 22-2-0668 COSSMACidr | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005740000 | WR6304312 23-4-0092-EE Natasha | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005750000 | WR6367378 23-4-0576-EE USPS HO | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005760000 | WR6366075 23-4-0567-EE MARIA F | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005770000 | WR6330717 07-4-0393 OceanPala | Active
CUSTOMER |  |  | 90017 | 90017 | 10N005780000 | WR6364628 22-4-0253 SUP AD CAB | Active
CUSTOMER |  |  | 90017 | 90017 | 10N005790000 | WR6367251 23-4-0577-EE Kristop | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005800000 | WR6367004 20-4-0068 OIM VLL RI | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005810000 | WR6359936 23-2-0778 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005820000 | WR6369449 21-7-173-EE Sonnell | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005830000 | WR6368885 CX-VII-10-23 Reina | Active
CUSTOMER |  |  | 90017 | 90017 | 10N005840000 | WR6342300 01-3-0153C Baskin | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005850000 | WR6352141 23-4-0497-EE DI AMAL | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005860000 | WR6350179 23-4-0480-EE GERALDO | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005870000 | WR6076885 22-2-0120 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005880000 | WR6283986 22-2-0778 ReloInfrCi | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005890000 | WR6361443 23-2-1033 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005900000 | WR6360317 23-2-0696 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N005910000 | WR6368316 22-4-0628 JOEL ACVDO | Active
CUSTOMER |  |  | 90017 | 90017 | 10N005920000 | WR6368852 23-4-0580-EE E.LOPEZ | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005930000 | WR6366154 23-2-0603 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005940000 | WR6367255 23-4-0578-EE LuisCor | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005950000 | WR6348991 23-5-0885-EE MuCamuy | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005960000 | WR6364686 23-2-1046 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N005970000 | WR6352763 23-4-0486-EE Christi | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006040000 | WR6365603 22-5-0252 MrSpecial | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006160000 | WR6372910 14-5-0134 Raw Wtr Pu | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006170000 | WR6366321 23-4-0066 DOS SOLARE | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006180000 | WR6372719 19-03-008 Centro Act | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006190000 | WR6347162 23-4-0450-EE H.RAMOS | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006200000 | WR5859194 23-4-0529-EE A.AVILE | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006210000 | WR6360675 17-2-0121 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006230000 | WR6350442 23-3-0304-EE MesserG | Active
CUSTOMER |  |  | 90017 | 90017 | 10N006240000 | WR6371492 22-7-296 Delia Rios | Active
CUSTOMER |  |  | 90017 | 90017 | 10N006250000 | WR6372378 23-7-132-EE B.MERCAD | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006260000 | WR6360993 23-4-0518-EE A.RAMIR | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006270000 | WR6372616 21-1-055-R1 RePostP3 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006280000 | WR6369336 21-1-055-R1 RePostP4 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006290000 | WR6372970 24-3-0025-EE J.BERNI | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006300000 | WR6293169 19-3-039 STA.ISABEL | Active
CUSTOMER |  |  | 90017 | 90017 | 10N006310000 | WR6367617 23-7-423-EE Lydia R | Active
CUSTOMER |  |  | 90017 | 90017 | 10N006320000 | WR6370173 23-4-479-EE M.APONTE | Active
CUSTOMER |  |  | 90017 | 90017 | 10N006330000 | WR5969660 21-2-0433 NarcisoGom | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006340000 | WR6332351 10-3-164 AdnielAlmod | Active
CUSTOMER |  |  | 90017 | 90017 | 10N006350000 | WR6368416 22-3-0008 Rel.EB Tan | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006360000 | WR6091823 22-2-0191 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N006370000 | WR6360152 06-3-194.1 H.STRT NY | Active
CUSTOMER |  |  | 90017 | 90017 | 10N006380000 | WR6344588 23-4-0428-EE E.VELEZ | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006390000 | WR6335040 21-3-096 TorreNATG | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006400000 | WR6362541-6362813 22-7-331-EE | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006410000 | WR6341522 23-2-0697 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006420000 | WR6374438 Garaje Total Levitwn | Active
CUSTOMER |  |  | 90017 | 90017 | 10N006430000 | WR6373495 22-4-0642-EE Gabriel | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006440000 | WR6375151 24-5-0105-CC OceanAm | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006450000 | WR6346956 23-4-0443-EE M.SOTO | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006460000 | WR6374354 24-4-0023-EE APT.ONX | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006470000 | WR6373217 23-7-478-EE CSTAÑAS3 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006480000 | WR6375839 23-7-274 JULIO ABREU | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006490000 | WR6065278 10-4-0333 29 Solares | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006500000 | WR6375170 22-4-0153 RAMEY JOB | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006510000 | WR6373105 23-3-0075 Armando | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006520000 | WR6369260 23-4-0582-EE IRMALIZ | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006530000 | WR6371858 23-2-1217 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006540000 | WR6317568 23-2-0368(23-2-0527) | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006550000 | WR6318809 23-4-0205-EE SHERYL | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006560000 | WR6364117 23-3-0291-EE | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006570000 | WR6374748 21-4-0006 MrSpec.SG | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006580000 | WR6362627 23-7-395-EE CDBG-PR | Active
CUSTOMER |  |  | 90017 | 90017 | 10N006590000 | WR6318950 23-4-0206-EE IBZAN R | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006620000 | WR6376818 24-5-0122-CC Vastago | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006630000 | WR6376917 22-1-0229 VACUUM SWI | Active
CUSTOMER |  |  | 90017 | 90017 | 10N006640000 | WR6376909 22-1-0229 ALBDO MH27 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006650000 | WR5972918 20-4-0171 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006660000 | WR6377608 24-4-0054-EE J.PEREZ | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006670000 | WR6376018 24-4-0044-EE A.MORLS | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006680000 | WR6376904 23-7-277-EE M.A.Edif | Active
CUSTOMER |  |  | 90017 | 90017 | 10N006690000 | WR6376718 24-1-0124-CC Cond609 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N006700000 | WR6374965 Casa Mofongo | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006710000 | WR6375670 22-5-0323 F&F HYDRO | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006720000 | WR6378176 21-1-126 C.ArteyTec. | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006730000 | WR6150643 22-4-0087 LUV LOUNGE | Active
CUSTOMER |  |  | 90017 | 90017 | 10N006740000 | WR6375726 22-7-186-EE CENTRO | Active
CUSTOMER |  |  | 90017 | 90017 | 10N006750000 | WR6367295 23-1-0100-CC IN POST | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006760000 | W36314769 21-3-053 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006770000 | WR6372505 22-7-122-EE CRANPPRP | Active
CUSTOMER |  |  | 90017 | 90017 | 10N006780000 | WR6375994 24-4-0043-EE C.GUTIE | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006790000 | WR6377428 20-7-099-EE Alm.Ikea | Active
CUSTOMER |  |  | 90017 | 90017 | 10N006800000 | WR6379567 24-4-0066-EE NELSON | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006810000 | WR6377059 21-4-0037 LlanosTuna | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006820000 | WR6376215 24-2-0044 Michael | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006830000 | WR6376348 06-4-010 UNIFAMILIAR | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006840000 | WR6379427 21-4-0037 LlaTuTelec | Active
CUSTOMER |  |  | 90017 | 90017 | 10N006850000 | WR6369487 23-2-1127 14-2-615 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006860000 | WR6380082 24-4-0075-EE RESIDEN | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006870000 | WR6304541 23-4-0095-EE FRANKL | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006880000 | WR6360249 23-1-0856-CC JOVITA | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006890000 | WR6370269 23-5-1164 VAGA RHPM | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006900000 | WR6373747 24-5-0119-EE SaulRos | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006910000 | WR6347631 18-4-0101 HAC. DOLLY | Active
CUSTOMER |  |  | 90017 | 90017 | 10N006920000 | WR6374726 24-4-0029-EE MARCO | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006930000 | WR6363535 18-2-0052 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006940000 | WR6336010 99-3-365C | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006950000 | WR6349302 11-4-0171 LEGUISAMO | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006960000 | WR6351912 23-1-0793-CC RicBorg | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006970000 | WR6382117 22-4-0326 B2B Inv | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006980000 | WR6350564 21-5-0100 HOGAR RUTH | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N006990000 | WR6339045 22-4-0339 CARIBBEAN | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007000000 | WR6347056 23-4-0447-EE A.L.S. | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007010000 | WR6379189 13-4-0048(WR4448394) | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007030000 | WR6335923 23-1-0555-CC INS | Active
CUSTOMER |  |  | 90017 | 90017 | 10N007040000 | WR6379615 21-4-0095 ANTENA CP | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007050000 | WR6364584 23-4-0355 GO TROPI | Active
CUSTOMER |  |  | 90017 | 90017 | 10N007060000 | WR6380480 19-7-204-EE QMC TLCM | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007070000 | WR6350488 16-5-0752 OBRAS PUBL | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007080000 | WR5983338 20-4-0020 MIGRANT HC | Active
CUSTOMER |  |  | 90017 | 90017 | 10N007090000 | WR6241801 15-4-0008 T. BALBOA | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007100000 | WR6379211 MCDONALDS SAN PATRI | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007110000 | WR6384138 24-4-0112-EE HCC ISA | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007120000 | WR6375177 13-3-157A SISTEMA AL | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007130000 | WR6384097 24-4-0109-EE | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007140000 | WR6312739 06-4-0171 CAMPING | Active
CUSTOMER |  |  | 90017 | 90017 | 10N007150000 | WR6384968 23-3-0042 QMC-177 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007160000 | WR6382136 23-5-0356 EUSEBIA | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007170000 | WR6379649 24-4-0071-EE RICARDO | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007180000 | WR6378179 24-3-0040-AA | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007190000 | WR6375076 21-5-0143 EARLY HEAD | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007200000 | WR6331435 ELIANA HUERTAS VEGA | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007210000 | WR6373239 21-3-022 INST POSTE | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007220000 | WR6374819 23-1-0545-CC POSTE | Active
CUSTOMER |  |  | 90017 | 90017 | 10N007230000 | WR6383491 24-4-0104-EE Mig.Lop | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007240000 | WR6384728 19-4-0135 RinconHV | Active
CUSTOMER |  |  | 90017 | 90017 | 10N007250000 | WR6384940 24-4-0122-EE GERARDO | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007260000 | WR6385932-WR6083067 H.TAVAREZ | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007270000 | WR6385194 22-1-0735 H.Oliver | Active
CUSTOMER |  |  | 90017 | 90017 | 10N007280000 | WR6381232 24-4-0088-EE JCRESPO | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007290000 | WR6386948 23-1-0764 POSTE P1 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007300000 | WR6386956 23-1-0764 POSTE P2 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007310000 | WR6314611 23-7-136-EE AVE. RIO | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007320000 | WR6388263 22-4-0396-EE | Active
CUSTOMER |  |  | 90017 | 90017 | 10N007330000 | WR6387377 14-3-022 MEJORAS | Active
CUSTOMER |  |  | 90017 | 90017 | 10N007340000 | WR6386133 24-4-0128-EE IGLESIA | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007350000 | WR6385144 24-4-0124-EE PUENTE | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007360000 | WR6389024 21-4-0130 JOYUDA SUR | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007370000 | WR6383513 24-1-0098 JOSE REYES | Active
CUSTOMER |  |  | 90017 | 90017 | 10N007380000 | WR6385474 21-7-094-EE R.PLAZA | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007390000 | WR6383829 24-4-0107-EE EBAS PF | Active
CUSTOMER |  |  | 90017 | 90017 | 10N007400000 | WR6365297 23-4-0565-EE J.GONZA | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007410000 | WR6379725 24-4-0059-EE JOSE A. | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007420000 | WR6385897 24-2-0045 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007430000 | WR6388165 24-1-0234-CC Igl.Cri | Active
CUSTOMER |  |  | 90017 | 90017 | 10N007440000 | WR6348579 23-4-0464-EE M.HORMI | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007450000 | WR6389669 DR-80-IV-2024 INFOSY | Active
CUSTOMER |  |  | 90017 | 90017 | 10N007460000 | WR6387496 24-5-0428-EE NOELIZ | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007470000 | WR6390221 21-1-040-EE HORTA | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007480000 | WR6350616-WR6352659 JOSE AYALA | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007490000 | WR6371266 21-5-0003 FRONTON | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007500000 | WR6381318 21-3-018 QMC BARRERO | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007510000 | WR6372713 24-4-0013-EE N.VARGS | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007520000 | WR6392570 24-4-0184-EE D.SAMOT | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007530000 | WR6385893 18-7-093 V.CITY HALL | Active
CUSTOMER |  |  | 90017 | 90017 | 10N007540000 | WR6379718 24-4-0072-EE MELANIO | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007550000 | WR6371747 22-2-0567 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007560000 | WR6386525 24-2-0209 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007570000 | WR6386223 23-2-1043 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007580000 | WR6391642 24-4-0171-EE M.LUNA | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007590000 | WR6371804 PLAZA LADERAS | Active
CUSTOMER |  |  | 90017 | 90017 | 10N007600000 | WR6383286 23-2-0924 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007610000 | WR6368683 27-7-015-EE CTS Tele | Active
CUSTOMER |  |  | 90017 | 90017 | 10N007620000 | WR6141046 21-2-0024 C.CARIBE | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007640000 | WR6340870 23-2-0667 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N007650000 | WR6373548 24-4-0018-EE J.RODRI | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007660000 | WR6394309 24-3-0138-EE | Active
CUSTOMER |  |  | 90017 | 90017 | 10N007670000 | WR6394290 23-2-0957-23-2-0958 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007710000 | WR6392204 24-4-0175-EE V.MEN | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007720000 | WR6390009 23-2-0303 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007730000 | WR6386164 24-4-0108-EE J.RSRIO | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007740000 | WR6391601 19-2-0475 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007750000 | WR6394539 GLORIA GONZALEZ | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007760000 | WR6389131 23-2-0764 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007770000 | WR6320864 16-3-717 J.CARDONA | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007780000 | WR6367849 23-7-412-EE V.RODZ | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007790000 | WR6384653 22-2-0298 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007800000 | WR6390943 24-4-0167-EE ALJNDRA | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007810000 | WR6397839 20-4-0035 KANAAN CRP | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007820000 | WR6392269 DR-90-IV-2024 IGLESI | Active
CUSTOMER |  |  | 90017 | 90017 | 10N007830000 | WR6364623 REEMPLAZO POSTE | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007840000 | WR6400176 24-7-148 EE N. FRNDZ | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007850000 | WR6395378 22-1-0523 LIBERTY | Active
CUSTOMER |  |  | 90017 | 90017 | 10N007860000 | WR6379023 24-7-053-EE J.FLORES | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007870000 | WR6392109 24-4-0176-EE J.SEDA | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007880000 | WR6398832 24-4-0227-EE | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007890000 | WR6379755 23-2-1111 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007900000 | WR6399495 24-7-080-EE AAA EBAS | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007910000 | WR6380787 21-6-0209 ECOLASTICO | Active
CUSTOMER |  |  | 90017 | 90017 | 10N007920000 | WR6371785 24-4-0006-EE ENOC | Active
CUSTOMER |  |  | 90017 | 90017 | 10N007930000 | WR6399395 17-1-243 MIRADOR | Active
CUSTOMER |  |  | 90017 | 90017 | 10N007940000 | WR6363691 22-1-0650 INN 097 CA | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007950000 | WR6389165 06-3-035A | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007960000 | WR6390148 24-2-0090 P. DAGUAO | Active
CUSTOMER |  |  | 90017 | 90017 | 10N007970000 | WR6402044 24-4-0253-EE RECYCL | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007980000 | WR6388880 24-4-0150-EE | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N007990000 | WR6398599 24-4-0217-EE | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N008000000 | WR6371865 24-4-0008-EE MARIA S | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N008010000 | WR6403001 98-0-150A COLINAS | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N008020000 | WR6383011 23-4-0172 AQUAVILLE | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N008030000 | WR6367434 21-6-0140 HEAD START | Active
CUSTOMER |  |  | 90017 | 90017 | 10N008040000 | WR6385276 05-8-218-EE VISTA | Active
CUSTOMER |  |  | 90017 | 90017 | 10N008050000 | WR6373251 23-2-0232 REEMP POST | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N008060000 | WR6400172 24-4-0235-EE EDGARDO | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N008070000 | WR6369876 20-3-101 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N008080000 | WR6406739 22-7-061-EE Ayala | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N008090000 | WR6377343 21-3-121 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N008100000 | WR6407081 22-5-0419 MiniMarket | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N008110000 | WR6399931 20-1-246-EE MEJ.OLA | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N008120000 | WR6405591 24-3-0114-EE | Active
CUSTOMER |  |  | 90017 | 90017 | 10N008130000 | WR6402998 18-4-0103 C.B.II WR1 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N008140000 | WR6403224 24-4-0015-EE Bal.Apt | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N008150000 | WR6409201 24-1-0590-CC Post.W. | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N008160000 | WR6378850 17-2-0270 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N008170000 | WR6103054 WR6395962 19-4-0028 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N008180000 | WR6403282 23-3-0257 Res.J.R | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N008190000 | WR6402372 24-5-0538-CC BGA | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N008210000 | WR6303596 19-7-123-EE Liberty | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N008220000 | WR6402999 18-4-0103 C.B.II.POC | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N008230000 | WR6404839 24-4-0264-EE Res.K.G | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N008240000 | WR6397369 24-4-0210-EE Eliomar | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N008250000 | WR6378744 15-9-084.1(23-2-0295 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N008260000 | WR6387395 19-6-0085 PteCeiba | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N008270000 | WR6312821 20-3-048 La Palmita | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N008280000 | WR6413786 23-3-0287 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N008290000 | WR6407238 23-5-0167 Squid Bro | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N008300000 | WR6413770 17-7-0105 JI Site | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N008310000 | WR6407080 24-4-0276-EE JOSE CH | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N008320000 | WR6335040 21-3-096 Torre NATG | Cancel
CUSTOMER |  |  | 90017 | 90017 | 10N008330000 | WR6183658 22-4-0393 Jesse Torr | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N008340000 | WR6402023 24-4-0252-EE M. Rios | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N008350000 | WR6268358 22-2-0512 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N008360000 | WR6413942 24-4-0308-EE Elbia | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N008370000 | WR6398988 24-4-0230-EE Res.Mar | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N008380000 | WR6409428 24-7-143-EE Frances | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N008390000 | WR6415690 23-3-0287.1 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N008400000 | WR6376324 23-4-0333-EE Sonia | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N008410000 | WR6406543 22-4-0039 Santa Tere | Active
CUSTOMER |  |  | 90017 | 90017 | 10N008420000 | WR6411143 21-4-0240 Chick-Fil | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N008430000 | WR6395057 24-7-122-EE CL Freed | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N008440000 | WR6407268 20-7-117 Villa Colom | Active
CUSTOMER |  |  | 90017 | 90017 | 10N008460000 | WR6341111 23-4-0404-EE Jose | Active
CUSTOMER |  |  | 90017 | 90017 | 10N008470000 | WR6415679 24-4-0323-EE Luis A. | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N008480000 | WR6383296 21-2-0004(24-2-0137) | Active
CUSTOMER |  |  | 90017 | 90017 | 10N008490000 | WR6409051 24-4-0281-EE Angel E | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N008500000 | WR6416890 16-3-436A | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N008520000 | WR6412836 24-4-0299-EE C.VARGS | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N008530000 | WR6391747 24-2-0315 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N008540000 | WR6401678 23-7-362-EE C.ACEVDO | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N008550000 | WR6382976 22-2-0273 Rem. Poste | Active
CUSTOMER |  |  | 90017 | 90017 | 10N008560000 | WR6416208 23-5-1064 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N008570000 | WR6399391 22-1-0901 Inst Poste | Active
CUSTOMER |  |  | 90017 | 90017 | 10N008580000 | WR6404348 17-4-0208 Res. Bern | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N008590000 | WR6418338 23-2-1170 INST POSTE | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N008600000 | WR6420102 23-2-0093 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N008610000 | WR6404518 24-7-247-EE A.SANCHZ | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N008620000 | WR6393022 24-3-0054 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N008630000 | WR6400613 24-2-0382 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N008650000 | WR6413255-6413564 22-7-074-EE | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N008660000 | WR6405621 22-5-0011 Rel. Pump | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N008670000 | WR6383885 16-7-0890 Est. Gasol | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N008680000 | WR6416898 24-4-0319-EE Engrac | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N008690000 | WR6407100 07-1-718C Casa Metr | Closed
CUSTOMER |  |  | 90017 | 90017 | 10N008700000 | WR6400143 21-7-094-EE Rivr Twn | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N008710000 | WR6175509 22-4-0360-EE Rel Pos | Active
CUSTOMER |  |  | 90017 | 90017 | 10N008720000 | WR6413594 23-4-0336 Nitza | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N008730000 | WR6301655 23-2-0112 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N008750000 | WR6389134 23-4-0016-EE Ramon R | Active
CUSTOMER |  |  | 90017 | 90017 | 10N008780000 | WR6416339-6416349 24-7-180-EE | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N008900000 | WR6425813 22-3-0005 Iglsia San | Active
CUSTOMER |  |  | 90017 | 90017 | 10N008910000 | WR6415451 23-1-0702 Hcda Crbli | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N008920000 | WR6392013 08-3-265 Reemp Poste | Active
CUSTOMER |  |  | 90017 | 90017 | 10N008930000 | WR6423204 21-7-030-EE Mardel | Active
CUSTOMER |  |  | 90017 | 90017 | 10N008940000 | WR6426083 23-4-0512 J. Ramos | Active
CUSTOMER |  |  | 90017 | 90017 | 10N008950000 | WR6426055 24-3-0268-EE Guayama | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N008960000 | WR6421548 21-4-0398 US CUSTMS | Active
CUSTOMER |  |  | 90017 | 90017 | 10N008970000 | WR6424736 24-7-108 Facilidades | Active
CUSTOMER |  |  | 90017 | 90017 | 10N009000000 | WR6427586 24-3-0274-EE | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N009010000 | WR6427471 21-4-0389 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N009020000 | WR6427380 24-3-0234-AA | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N009030000 | WR6426590 23-5-0229 Seg.Hcda | Active
CUSTOMER |  |  | 90017 | 90017 | 10N009040000 | WR6416678 23-3-0159 Reemplazo | Active
CUSTOMER |  |  | 90017 | 90017 | 10N009050000 | WR6426875 23-1-0517 Fair View | Active
CUSTOMER |  |  | 90017 | 90017 | 10N009130000 | WR6421805 12-7-150 R1-EE M.Ctn | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N009140000 | WR6425103 14-2-567 Via Libre | Active
CUSTOMER |  |  | 90017 | 90017 | 10N009150000 | WR6416471 24-5-0734-CC Lillian | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N009160000 | WR6387376 23-5-0598 Res. Crmen | Active
CUSTOMER |  |  | 90017 | 90017 | 10N009170000 | WR6385067 24-2-0055 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N009180000 | WR6382788 19-3-104 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N009210000 | WR6375539 23-1-0110 CDT CNAS | Active
CUSTOMER |  |  | 90017 | 90017 | 10N009220000 | WR6379538 16-2-1645 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N009230000 | WR6425159 24-7-333-EE L.Caldro | Active
CUSTOMER |  |  | 90017 | 90017 | 10N009240000 | WR6383426 23-4-0155 Seg. 8 Sol | Active
CUSTOMER |  |  | 90017 | 90017 | 10N009250000 | WR6427511 19-4-0001 Las Casit | Active
CUSTOMER |  |  | 90017 | 90017 | 10N009260000 | WR6411048 24-4-0301 Luis R. | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N009280000 | WR6425788 85-0741D | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N009290000 | WR6347095 23-4-0448-EE C. Saen | Active
CUSTOMER |  |  | 90017 | 90017 | 10N009300000 | WR6427521 23-4-0420 Aptos. Je | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N009310000 | WR6376329 23-4-0319-EE Edwin A | Active
CUSTOMER |  |  | 90017 | 90017 | 10N009320000 | WR6374844 23-1-0982-CC R.Ramos | Active
CUSTOMER |  |  | 90017 | 90017 | 10N009330000 | WR6384409 24-4-0119-EE | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N009340000 | WR6260822 22-4-0492-EE Nathan | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N009350000 | WR6429105 24-3-0114-EE | Active
CUSTOMER |  |  | 90017 | 90017 | 10N009360000 | WR6399088 24-7-197-EE Rev.Dent | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N009380000 | WR6424107 24-4-0399-EE S.Perez | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N009390000 | WR6387584 24-4-0001-EE W.Waber | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N009400000 | WR6424282 24-5-0758 J.Vazquez | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N009410000 | WR6379261 20-4-0113 Autozone | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N009420000 | WR6429652 24-7-240-EE Galeria | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N009430000 | WR6411560 24-4-0302-EE A.Hndez | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N009440000 | WR6426950 24-2-0724 Reemp. Trs | Active
CUSTOMER |  |  | 90017 | 90017 | 10N009450000 | WR6429024 17-4-0020 Apt.Hector | Active
CUSTOMER |  |  | 90017 | 90017 | 10N009460000 | WR6430347 23-5-0268 Paradiso | Active
CUSTOMER |  |  | 90017 | 90017 | 10N009470000 | WR6413030 24-2-0043 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N009480000 | WR6427968 24-1-0840-CC Iris | Active
CUSTOMER |  |  | 90017 | 90017 | 10N009490000 | WR6413568 14-3-049.1 Aidalys M | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N009510000 | WR6429957 23-3-0287.1 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N009520000 | WR6431364 24-2-0340 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N009530000 | WR6427636 23-5-0734 Vivi Abajo | Active
CUSTOMER |  |  | 90017 | 90017 | 10N009540000 | WR6419992 24-4-0370-EE Y.Roldn | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N009550000 | WR6426982 24-2-0445 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N009560000 | WR6429084 24-4-0446-EE H.Stpns | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N009570000 | WR6425800 14-9-089 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N009590000 | WR6391239 24-4-0169-EE K.DIAZ | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N009600000 | WR6426985 23-4-0255 3 solares | Active
CUSTOMER |  |  | 90017 | 90017 | 10N009620000 | WR6384582 06-2-736 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N009630000 | WR6432644 03-3-131.2 Bella Nva | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N009650000 | WR6370385 23-2-1167 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N009660000 | WR6431774 18-4-0063 20 Solares | Active
CUSTOMER |  |  | 90017 | 90017 | 10N009670000 | WR6432742 24-4-0497-EE Hierba | Active
CUSTOMER |  |  | 90017 | 90017 | 10N009680000 | WR6431016 19-4-0075 LasColinas | Active
CUSTOMER |  |  | 90017 | 90017 | 10N009690000 | WR6380165 24-4-0081-EE Rubi Va | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N009700000 | WR6417048 19-2-0200 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N009780000 | WR6427513 24-5-1077-CC Z.Torrs | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N009790000 | WR6432948 24-3-0114-EE | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N009800000 | WR6428570 04-4-496A Desarrolla | Active
CUSTOMER |  |  | 90017 | 90017 | 10N009810000 | WR6410233 24-7-024-EE Teresa D | Active
CUSTOMER |  |  | 90017 | 90017 | 10N009830000 | WR6435463 11-3-076.1 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N009840000 | WR6425790 15-4-0398 Solares | Active
CUSTOMER |  |  | 90017 | 90017 | 10N009850000 | WR6430779 05-3-166.1 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N009860000 | WR6434771 22-5-0480 ET 2022-03 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N009870000 | WR6431738 24-4-0040 A.Ortiz | Active
CUSTOMER |  |  | 90017 | 90017 | 10N009880000 | WR6425123 24-2-0628 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N009890000 | WR6432735 23-3-0042 QMC Agurre | Active
CUSTOMER |  |  | 90017 | 90017 | 10N009900000 | WR6431535 24-4-0486-EE J.Pagan | Active
CUSTOMER |  |  | 90017 | 90017 | 10N009910000 | WR6419853 07-4-0513 Est.Bombeo | Active
CUSTOMER |  |  | 90017 | 90017 | 10N009920000 | WR6436558 17-4-0031 San German | Active
CUSTOMER |  |  | 90017 | 90017 | 10N009930000 | WR6433109 23-4-0058 Ed.Soto | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N009940000 | WR6435361 23-1-0584 Mimosa 164 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N009950000 | WR6434114 19-1-236 Pedestrian | Active
CUSTOMER |  |  | 90017 | 90017 | 10N009960000 | WR6424736 24-7-108-EE | Active
CUSTOMER |  |  | 90017 | 90017 | 10N009970000 | WR6429909-29966 15-1-054 A-EE | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N009980000 | WR6426515 23-2-1200 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N009990000 | WR6383394 24-4-0101-EE J.CABAN | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N010000000 | WR6434603 24-4-0511-EE Necxiel | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010010000 | WR6424091 24-4-0400-EE M&M Pty | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N010020000 | WR6365721 22-4-0500 Tropical | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010040000 | WR6432066 24-2-0660 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010050000 | WR6435366 23-1-0117 Laguna SJo | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010060000 | WR6435615 19-5-0025 Pnte.Vidal | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010080000 | WR6432851 23-3-0105 Reem. post | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N010090000 | WR6435521 20-4-0030 Micro AT&T | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010100000 | WR6430639 24-4-0466-EE P.Gonz | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N010110000 | WR6433146 24-4-0499-EE Alex Rd | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010120000 | WR6425304 23-7-130-EE R Cumba | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010130000 | WR6392210 23-3-0144 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010140000 | WR1260196A Antena Maga | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010150000 | 24-7-282, EST01,EST02 Y EST03 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N010200000 | WR6434753 24-2-0806 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010210000 | WR6431910 24-4-0280 Hvn Health | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010220000 | WR6430925 21-7-031 R.Rivera | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N010230000 | WR6428649 13-5-0197 C. Ward | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010240000 | WR6429344 24-2-0337 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010250000 | WR6427218 24-4-0421-EE Myrna C | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010260000 | WR6395464 22-3-0165 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010270000 | WR24-7-050 Rodriguez Herrero | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010280000 | WR6431202 22-4-0558 La Maquina | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N010290000 | WR23-5-0132-EST01 Coop Ahorro | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010300000 | WR6426652 23-5-0664 PDDK LLC | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010310000 | WR6360652 14-3-189 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010320000 | WR-CRAR-24-0042-EST-01 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010330000 | WR6390080 23-7-322-EE E.Rafael | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N010340000 | WR6440321 17-4-0031 P.SanGermn | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010350000 | WR6423310&6424415 24-7-7-248 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N010360000 | WR6435465 15-4-0627 MM Mnftng | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010370000 | WR6362627 23-7-395-EE CDBGPR | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010380000 | WRCRAR-24-1323 EST01 J.Virella | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010390000 | WR6441945 23-4-0074 7 Solares | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010400000 | WR6440774 23-4-0548 Solymar | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010410000 | WR6430838 20-4-0075 QSR Dvlpmt | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N010420000 | WR6437308 24-4-0532-EE J.Cruz | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010430000 | WR6400270 18-3-021 Head Start | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010440000 | WR6436281 20-5-0076 Hacienda | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010450000 | WR6428452 22-3-0178 Elite 2022 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010460000 | WR6432835 22-4-0588 TelecomInn | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010470000 | WR22-4-0361-CC-EST-01 CROMA | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010480000 | WR6440664 17-4-0031 Mejoras PN | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010490000 | WR22-7-309 EST01-EST02 Hyundai | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010500000 | WR22-3-0222 Temporera CDT | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010510000 | WR6430345 24-5-0950-CC J.Ayala | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010520000 | WR23-5-1141-EST01 Edificio Mrn | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010530000 | WR24-1-0463-EST01 Amarilys | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010540000 | WR25-2-0002-EST01 Abbot Caguas | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010550000 | WRDRCA-25-0036 Aluminum Corp | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010560000 | WR6390153 24-4-0160-EE J.ORAMA | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010590000 | WR6071212 23-4-0402-EE Yahaira | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010600000 | WR6441829 DR-28-II-2024 Plaza | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010610000 | WR25-4-0005-EE EST01 Ivan A. | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010620000 | WR6421469 24-7-002-EE Jose Abl | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010630000 | WR6409499 21-7-094-EE R.Town | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010640000 | WR6434752 23-4-0343 Boqueron | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010650000 | WR95-4-088-EST-01 Urb Llanos | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010660000 | WR6423883-CDBG-PR-R3-00430 Ani | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010670000 | WR6435512 15-4-0627 MM Mnfrng | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010680000 | WR6432128 24-5-1013-CC Mlagros | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010690000 | WR22-4-0497 Rehab Guerrero II | Closed
CUSTOMER |  |  | 90017 | 90017 | 10N010700000 | WR6373658 10-3-071.1 Mercedes | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010710000 | WR6390249 24-7-157-EE Res.Yari | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010720000 | WR6416752 19-4-0119 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010730000 | WR22-7-18-EE Jose Canto | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010740000 | WR03-3-296-EST-01 Urb.Vistas | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010750000 | WR6428760&6429282 24-7-290 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010760000 | WR6432413 19-3-104 Inst. Corte | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010770000 | WR90-0-163.2-EST02 Baskin | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010780000 | WR24-3-0039-EST01 QMC S.Domi | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010790000 | WR22-7-108-EE Centro Head Strt | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010800000 | WR22-4-0464 EST-POC Guajataca | Closed
CUSTOMER |  |  | 90017 | 90017 | 10N010810000 | WR12-3-048 Gasolinera Gulf | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010820000 | WR24-4-0306-EST01 Felipe Vargs | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010830000 | WR6371791 23-2-1197 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010840000 | WR6426996 21-7-187-EE V.Brava | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010850000 | WR6371788 24-4-0007-EE Ariana | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010860000 | WR6424664 24-7-283-EE Esc. Jul | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010870000 | WR15-4-0687 EST02 Toyota Ag | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010880000 | WR23-1-0969 Elena Residence | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010890000 | WRCRAR-25-5-0078 EST01 J.Vega | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010900000 | WR6425430 24-2-0302 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010910000 | WRCRCA 24-0077-EST01 Placita | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010920000 | WR24-2-0651 EST01 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010930000 | WR90-0-452G1-EST02 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010950000 | WR23-7-470 EST01-EST02 FBC | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N010960000 | WR19-1-080 EST02 El Monte | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010970000 | WR23-5-0935 Antena Arecibo Isl | Active
CUSTOMER |  |  | 90017 | 90017 | 10N010990000 | WR24-5-0414 EST01 Dealer Hydai | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011000000 | WR11-4-0004 Troncal Sanitaria | Closed
CUSTOMER |  |  | 90017 | 90017 | 10N011010000 | WR24-2-0087-EST01 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011020000 | WR6322636 22-1-0263 Ana G. Men | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011030000 | WR23-1-0901 Jardines Palmarejo | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011040000 | WR24-7-402-EE RemodAptoCarr174 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011050000 | WR15-5-0293 Rehabilitacion | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011060000 | WR24-4-0581-EE Mariela Gonzalz | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011070000 | WR24-4-0544-EE Luciano Perez | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011080000 | WR6416659 24-2-0414 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011090000 | WR24-7-282 Parque La Esperanza | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N011100000 | WR23-7-048EST01 Miguel Rodrigu | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N011110000 | WR24-1-0064 Alambrado MH a MH | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011120000 | WR21-3-109 COE Juana Diaz | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011130000 | WR24-2-0478EST01 Reemp pedestl | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011150000 | WR25-5-077 Alexis Luna Camuy | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011160000 | WR21-2-0259 EST01 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011170000 | WR23-7-332-EE Cantera San Anto | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011180000 | WR 19-5-0147 ESTO01 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011200000 | WR 23-2-0756-EST01 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011210000 | WR5943163 21-7-103 Solaris | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011220000 | WR6439211 24-4-0409-EE L.Nievs | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011230000 | WR 23-2-0506-EST01--POC | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011240000 | WR24-7-363 EST01 Vagon Corrujo | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011250000 | WR25-5-0098-EE Milgaros Gonz | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011260000 | WR25-4-0053-EE Sonia Medina | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011280000 | WR22-4-0436-EE Rafael Quiñones | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011290000 | WR24-7-394 Monica Rosado Liza | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N011300000 | WR6224559 22-4-0435 R.Matias | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011310000 | WR6426890 24-2-0743--POC | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011320000 | WR 23-7-1103-EE PEDRO CABRERA | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011330000 | WR24-0090 Jose Jimenez Torres | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011340000 | WR22-2-0844-EST01 Hyundai Cag | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011350000 | WR10-5-0071-EST01 Casa Esmrlda | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011360000 | WR24-5-1348 Gilberto Melendez | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011370000 | WR19-7-071-EST01 Urb La Sabana | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011380000 | WR22-2-0620-EST01 Clotilde Ddo | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011390000 | WR24-1-1029 Poste Familia Diaz | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011400000 | WR21-6-0050 Warehouse Plaza | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N011410000 | WR23-7-190 EST02 Motorambar | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011420000 | WR23-7-167EST01 PTS Facilities | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011430000 | WR99-3-454B2 R.Caballero KIA | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011510000 | WR21-2-0207-EST01 Sky Tower | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011520000 | WR6430168 Cossma Executive | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011530000 | WR23-4-0165 Edificio Caimital | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011540000 | WR21-4-0240.1 Chick fill-A | Closed
CUSTOMER |  |  | 90017 | 90017 | 10N011550000 | WR6427591 21-2-0024 Campo Cari | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011560000 | WR22-3-0202 Churchs Chicken | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011580000 | WR23-5-0708 Estacion de Bombeo | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011590000 | WR23-1-0506 Iglesia Luterana | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011600000 | WR25-4-0148-EE Ronaldo Rosa | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011620000 | WR6434512 NIMAY CAGUAS | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011630000 | WR22-2-0072-EST01 Res.Xavier | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011640000 | WR25-4-0114-EE Angel Rios Gnz | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011650000 | WR23-1-0531-CC Vildon LLC | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011660000 | WR15-5-0515A-EST01 Estadio | Closed
CUSTOMER |  |  | 90017 | 90017 | 10N011670000 | WRCRAR-25-0235 L Villafañe | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011690000 | WR20-2-0355 Villa Tortuga | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011700000 | WR6424646 Piedra Chiquita | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011710000 | WR6431398 Gasolinera Mobil | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011720000 | WR24-2-0340-EST01 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011740000 | WR24-1-0617 Locales comrciales | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011750000 | WR00-1-336 Montehiedra Reserve | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011760000 | WR20-5-0046 Sucn. Jose A Rosas | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011770000 | WRCRAR25-0267 Edward Sanchez | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011780000 | WR24-7-400 EST01 Jani Clean | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011790000 | WR19-7-044 The Dawn at Dorado | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011800000 | WR11-2-560EST01 Luis Santos | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011810000 | WR21-4-0111 Jaslyn Ortega | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011820000 | WR25-5-0181 Transformador | Cancel
CUSTOMER |  |  | 90017 | 90017 | 10N011830000 | WR25-4-0031-EE Madeline Rivera | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011840000 | WR6428432 Tres Palmas Sunset | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011850000 | WR18-3-061 Remod Antiguo ESSO | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011860000 | WR23-2-1119 Janisha Martinez | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011870000 | WR24-2-0509 Norberto Diaz | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011880000 | WR22-5-0536 Com Land Lease Crp | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011890000 | WR19-0-005-EE Puente La Muda | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011900000 | WR23-5-0440 Capaez Telecom | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011920000 | WR6347505 Parque de Bombas | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011930000 | WR10-3-049-EST01 Edif. Anexo | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011940000 | WR14-5-0437 Palma Gorda | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011950000 | WR22-1-0818 HeadStart Villas | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011960000 | WR21-7-123 Industrial Building | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011970000 | WR25-4-0128-EE Lody Isaac | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011980000 | WRCRCA-25-0273 Jose Rivera | Active
CUSTOMER |  |  | 90017 | 90017 | 10N011990000 | WR02-5-0102 Edwin Cardona | Active
CUSTOMER |  |  | 90017 | 90017 | 10N012000000 | WR21-7-104 Advance RoofingDpot | Active
CUSTOMER |  |  | 90017 | 90017 | 10N012010000 | WR6390249 24-7-157 Res.Yaritza | Active
CUSTOMER |  |  | 90017 | 90017 | 10N012020000 | WR22-5-0042 Milka I. Santiago | Active
CUSTOMER |  |  | 90017 | 90017 | 10N012030000 | WR25-0151-EE CRAR Olga Chevere | Active
CUSTOMER |  |  | 90017 | 90017 | 10N012040000 | WR25-5-0021 CRAR25-0038 J.Asta | Active
CUSTOMER |  |  | 90017 | 90017 | 10N012050000 | WR21-7-108-EST01 Elite Tower | Active
CUSTOMER |  |  | 90017 | 90017 | 10N012060000 | WR24-2-0564EST01 Colgate Palmo | Active
CUSTOMER |  |  | 90017 | 90017 | 10N012070000 | WR22-7-034EE EST02 Aireko Cons | Active
CUSTOMER |  |  | 90017 | 90017 | 10N012080000 | WR24-7-089 EST01 Finca Elena | Active
CUSTOMER |  |  | 90017 | 90017 | 10N012090000 | WR23-3-0351-POC Casa Alta | Active
CUSTOMER |  |  | 90017 | 90017 | 10N012100000 | WR24-2-0773EST01 Res A.Berrios | Active
CUSTOMER |  |  | 90017 | 90017 | 10N012110000 | WR25-4-0127-EE Edna Cruz | Active
CUSTOMER |  |  | 90017 | 90017 | 10N012120000 | WR-DRPO25-0047 USARC | Active
CUSTOMER |  |  | 90017 | 90017 | 10N012130000 | WR10-5-0158 Solares P.Roman | Active
CUSTOMER |  |  | 90017 | 90017 | 10N012140000 | WR 24-1-0381 Instal.Poste Cass | Active
CUSTOMER |  |  | 90017 | 90017 | 10N012150000 | WR 23-1-0569 EXT.Lin.Sing.Pha | Active
CUSTOMER |  |  | 90017 | 90017 | 10N012160000 | WR25-4-0065-EE Norma Rodriguez | Active
CUSTOMER |  |  | 90017 | 90017 | 10N012170000 | WRCRBA-24-0088 Ricardo Quiles | Active
CUSTOMER |  |  | 90017 | 90017 | 10N012180000 | WR 21-4-0134 EST 01 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N012190000 | WR24-5-0383 Cabrera Auto Group | Active
CUSTOMER |  |  | 90017 | 90017 | 10N012200000 | WR 23-2-0596 CRCA-24-0105 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N012230000 | WR05-5-0043 Segreg 11 solares | Active
CUSTOMER |  |  | 90017 | 90017 | 10N012240000 | WR21-2-0234 Health&Green Life | Active
CUSTOMER |  |  | 90017 | 90017 | 10N012250000 | WR15-7-391 Iglesia Alianza Cri | Active
CUSTOMER |  |  | 90017 | 90017 | 10N012260000 | WR6429773 Jessica Melendez | Active
CUSTOMER |  |  | 90017 | 90017 | 10N012270000 | WR23-1-0464 Aldebaran 582 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N012280000 | WR20-4-0075 El Meson Site QSR | Closed
CUSTOMER |  |  | 90017 | 90017 | 10N012290000 | WR 24-4-0390-EE NorbertoCortes | Active
CUSTOMER |  |  | 90017 | 90017 | 10N012300000 | WR DRMA-25-0068 PharmaMaxMayag | Active
CUSTOMER |  |  | 90017 | 90017 | 10N012310000 | WR 23-4-0019 Jaime Rosario | Active
CUSTOMER |  |  | 90017 | 90017 | 10N012340000 | WR 06-4-0318A Efrain Ramos | Active
CUSTOMER |  |  | 90017 | 90017 | 10N012350000 | WR 24-4-0040, EST-POC,ALEJ.ORT | Active
CUSTOMER |  |  | 90017 | 90017 | 10N012360000 | WR 23-5-0680 Hardwick Tactical | Active
CUSTOMER |  |  | 90017 | 90017 | 10N012380000 | WR 22-4-0488 TekCel_Las Arenas | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N012390000 | WR6316317 17-4-0334(WR5438026) | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N012400000 | WR24-4-0030-EE Pablo Valentin | Active
CUSTOMER |  |  | 90017 | 90017 | 10N012410000 | WR6370588 23-4-0598 Guillermo | Active
CUSTOMER |  |  | 90017 | 90017 | 10N012420000 | WR21-4-0295 Seg 7 Solares | Active
CUSTOMER |  |  | 90017 | 90017 | 10N012430000 | WR 21-2-0273 Mariana II Antena | Active
CUSTOMER |  |  | 90017 | 90017 | 10N012440000 | WR05-8-218 Cond Vista al Norte | Active
CUSTOMER |  |  | 90017 | 90017 | 10N012450000 | WR20-7-039 Ave. Bobby Capo | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N012460000 | WR25-5-0178 GeneraPR Vega Baja | Active
CUSTOMER |  |  | 90017 | 90017 | 10N012470000 | WR98-3-400A Solares Jose Riv | Active
CUSTOMER |  |  | 90017 | 90017 | 10N012690000 | WR 24-7-437 CDBG PR-R3-02807 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N012700000 | WR 25-5-0239 Edif.EEstremera | Active
CUSTOMER |  |  | 90017 | 90017 | 10N012710000 | WR 22-5-0001 3Pred.DiegoRios | Active
CUSTOMER |  |  | 90017 | 90017 | 10N012720000 | WR10-5-0014 Segre 6 solares J. | Active
CUSTOMER |  |  | 90017 | 90017 | 10N012730000 | WR24-7-049 Eduardo Jimenez Ema | Active
CUSTOMER |  |  | 90017 | 90017 | 10N012950000 | WR23-5-0413 Yabelis Fradera | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013150000 | WR25-7-139 Mun de Corozal | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013160000 | WR25-2-0050-EST01 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013170000 | WR22-2-0575-EST01 Reemp poste | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013180000 | WR 19-7-071-F3 Urb.La Sabana | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013190000 | WR23-2-0385-EST01 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013200000 | WR22-7-025-EST01 Antena Rio | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013210000 | WR23-7-131 EST01 Carmen Ramos | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013220000 | WR22-7-034-EST04 MejorasPR 659 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013230000 | WR23-3-0069-EST01 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013240000 | WR24-7-456 EST01 Liz Yanira | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013250000 | WR21-3-113 Residencia Omy Joel | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013260000 | WR21-4-0011 Solares trailers | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013270000 | WR24-4-0421 Instale poste 35ft | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013280000 | WR5943456 21-4-0250 Iglesia | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013290000 | WR21-4-0134 EST01 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013300000 | WR24-4-0384-EE Heriberto Lopez | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013320000 | WR 25-2-0242-EST01 Interc.Lin | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013330000 | WR25-4-0330-EE MelendezRent | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013340000 | WR 22-4-0621 EST-01 Steph.Pere | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013350000 | WR 25-7-022-EE Angel Santiago | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013360000 | WR 23-2-0333-EST-02 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013370000 | WR DRPO-25-0056 POC | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013380000 | WR 19-5-0176-EST01 Parq.Rec. | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013390000 | WR 19-5-0176-EST02 Parq..reloc | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013400000 | WR 21-2-0251-EST01 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013410000 | WR 24-4-0134 EDIF.APT.L.LASALL | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013420000 | WR 23-2-0130-EST02 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013430000 | WRCRAR-25-0538 Edwin Vazquez | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013440000 | WR19-1-531 Empalmes-EST04 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013450000 | WR24-1-0672 Rmplzo poste-EST01 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013460000 | WR 23-4-0359 EST-01 FomentoSPS | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013470000 | WR 23-4-0396EST01 AguadiAveSPS | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013480000 | WR22-4-0282 EST01 Roberto Toro | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013490000 | WR 19-3-073.1_POC | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013500000 | WR 97-3-167A.2_POC | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013510000 | WR23-2-0963-EST01 Arcadio Rod | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013520000 | WR 25-2-0183-EST01 InstSegAlim | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013530000 | WR25-4-0271-EE EST-POC Sonia | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013540000 | WR 22-4-0283 PoC Sol.Mor.Pnce | Inactive
CUSTOMER |  |  | 90017 | 90017 | 10N013550000 | WR 25-4-0348-EE POC BQN RAMEY | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013560000 | WRCRAR-25-0716 Fac.Raymond H | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013570000 | WR22-2-0497 EST02 Head Start | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013580000 | WR24-4-0467-EE EST-POC Idalis | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013590000 | WR24-4-0406 EST01 Comunidad | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013600000 | WR22-7-088 EST01 TO-CARS KIA | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013610000 | WR16-2-0614 EST02 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013620000 | WR23-2-0957-EST02 Reemp poste | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013630000 | WRCRAR-25-0688 Luis Nieves | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013640000 | WRCRAR-25-0501 Marangelie Lpz | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013650000 | WRCRAR-25-0131 Luis A. Vald | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013660000 | WR19-5-0147.1 Relocalizacion | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013670000 | WR24-1-0216 Reemplazo poste | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013680000 | WR 14-5-0052 Sun Boricua | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013690000 | WR24-7-463-EST01 Almacenes | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013700000 | WR 25-7-142-EE VILMARIE RIVERA | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013710000 | WRDRBA-25-0116 A1 Generator | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013720000 | WR25-2-0282-EST01 Aumento cali | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013730000 | WR25-2-0218-POC Hotel Vista | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013740000 | WR 09-5-0144.1(POC)SolaresHect | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013750000 | WR 09-5-0144.1 EST-01(Ext.Prim | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013760000 | WR23-5-0638 NMA Esperanza Corp | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013780000 | WR20-7-047EST01 The Hub Office | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013790000 | WR22-7-145 Guaynabo Food Cont | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013800000 | WR24-1-0216 Rplzo poste Toyota | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013810000 | WR22-7-021 Paraiso infantil | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013820000 | WR24-4-0156 EST01 VIBES VILLAS | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013830000 | WR25-2-0351 Cristian Arroyo | Active
CUSTOMER |  |  | 90017 | 90017 | 10N013840000 | WR22-5-0395 Reha Water treat | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014080000 | WR01-1-027A-EST02 Ensueño | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014090000 | WR01-1-027A-EST03 Ensueño | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014100000 | WR23-5-0236 Seg Solares Xavier | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014110000 | WR21-3-123 E01Reempl. poste | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014140000 | WR23-2-1107-EST01 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014150000 | WR21-7-028.1 PR Five Vega Alta | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014160000 | WRDRBA-25-0114 Cond Los Caobos | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014170000 | WR19-1-531 Empalmes EST04 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014180000 | WR15-7-391 EST02 Iglesia Alian | Cancel
CUSTOMER |  |  | 90017 | 90017 | 10N014200000 | WR21-5-0142 Oil Energy System | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014210000 | WR22-1-0736-EST01 Federico Cos | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014220000 | WRCRMA25-0259 Jose Soto | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014230000 | WR24-4-0574 EST01 Espico LLC | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014250000 | WR25-2-0107-EST01 Relocalizcn | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014270000 | WRCRMA-25-0205-EST-POC Twin Pi | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014280000 | WR22-1-0160-EST01 Inst. Poste | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014290000 | WR23-4-0198 Telecom. Bo. Tuna | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014300000 | WR23-5-0499 Miramar BBQ LLC | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014310000 | WRCRMA-25-0434 Ritchie Velazqz | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014320000 | WR02-3-0244A EST04 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014330000 | CRMA-25-0450 Velez Feliciano | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014340000 | WR25-7-116-EST01 Multiware Ind | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014360000 | WR19-7-022 EST01 Toa Baja Ped | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014370000 | WR25-5-0502 Elizabeth Huertas | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014380000 | WR23-4-0309 Mayaguez Business | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014390000 | WR23-2-0003-EST01 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014400000 | WR22-5-0100 Job Corps | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014410000 | WR24-2-0515-EST02 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014420000 | WR16-2-1498POC | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014430000 | WR17-4-0207 JI Antena Maya | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014440000 | WR 23-5-0527 Mr.Special V.Alta | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014450000 | WR 24-5-0978 Fac IgnacioNieves | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014460000 | WR 22-5-0433 Reinaldo y Maria | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014470000 | WR 24-4-0235 EST-01 Edif.Alm.R | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014480000 | WR 6386103 LUMA 15-2-555 Nilda | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014490000 | WR25-4-0373-EST POC Yeidy Bos | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014500000 | WRCRMA-25-0651 Hector M. Muniz | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014510000 | WR24-2-0955 CDBG PR-R3-26828 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014520000 | WR23-4-0317 Isabela RAW Water | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014530000 | WR23-5-0937 Antena Arecibo Jun | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014540000 | WR25-5-0056 Panificadora PR Ca | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014550000 | WR21-4-0387CombG.EST-01EST-POC | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014560000 | WR24-2-0079 Francisco Quiles | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014570000 | WR24-2-0188 JOSE COBIAN R3 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014580000 | WRCRMA-25-0021 Raymond Montalv | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014590000 | WR19-4-0100A West End Plaza | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014600000 | WR22-4-0378 Pozo profundo | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014610000 | WR23-4-0172 EST-02 Aquaville | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014620000 | WR23-4-0528 Rogelio Gonzalez | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014640000 | WR21-4-0194 Unlimited Storage | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014650000 | WR23-4-0525 RRT Property Invmt | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014660000 | WR13-2-012 Brisas del Turabo | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014670000 | WR21-7-103-EST02 Solaris Dvlnt | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014680000 | WR04-5-0304.4 Juan Hernandez | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014690000 | WR24-4-0514 EST01 CISS Isabela | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014700000 | WR 25-1-0108 HOGAR S.MARTIN(RC | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014710000 | WRCRMA-25-0742 Jahzan Cruz | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014720000 | WR23-7-177 Res Jovana Rivera | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014730000 | WR07-4-0513 Estacion de bombeo | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014740000 | WR 24-4-0142,EST-01,TRA RECYCL | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014750000 | WR24-4-0440 Solares Roberto M | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014770000 | WR23-4-0058 VillasVacacionales | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014780000 | WR24-7-289 Esc. Antonia Iriza | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014790000 | WR16-4-0797 SolaresRey Santna | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014800000 | WR19-6-0203 EST01 Granja Reyes | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014810000 | WR25-1-0571-AA Inst. poste | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014820000 | WR24-3-0254 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014830000 | WR22-4-0207 Aptos. de Diego#62 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014840000 | WR23-2-0687 Reemplazo poste | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014850000 | WRCRMA-25-0670 Porfiria Zorr | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014860000 | WR24-4-0117 OMME y Policia Mun | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014870000 | WR24-2-0839 Alvin Rodriguez | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014880000 | WR24-4-0377 Prop.Alvin Morales | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014890000 | WR24-2-0994-EST01 Reemp poste | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014900000 | WRCRMA-25-0829 Maniliz Segarra | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014910000 | WR25-7-309 New Perfect China | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014920000 | WRCRMA-25-0178 Jessinia Crrero | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014930000 | WR24-4-0475 Corsica Village | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014940000 | WR02-3-027.1 Rebuild USCG | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014950000 | WRCRCA-25-0258 Instlcion poste | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014960000 | WR22-2-0049 Telcom Inn LaPlata | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014970000 | WR 25-5-0669 Bethel Protective | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014980000 | WR22-5-0100 Punto Cnxn-JobCorp | Active
CUSTOMER |  |  | 90017 | 90017 | 10N014990000 | WR23-4-0124 Miguel Gonzalez | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015000000 | WR23-7-218 Alm Tocars Toyota | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015010000 | WRCRMA-25-0751 Zoraida Mendez | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015020000 | WR-25-7-158 Baseball Park Rio | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015030000 | WR24-5-0147 Artemis Recycling | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015040000 | WR21-5-0085 Ricomini Bakery | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015050000 | WR25-4-0509 Obed Badillo | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015060000 | WR25-7-393-EE EST01 PR-SFM | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015070000 | WR21-4-0400 HS Hostos Maya | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015080000 | WR22-1-0227 Quebrada Negrito | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015090000 | WR23-2-0129 EST01 Rabanal Inn | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015100000 | WR13-3-121 Trunk Sewer | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015110000 | WR25-7-169-EE Zorelis Rivera | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015120000 | WR13-3-119 Trunk Sewer Patilla | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015130000 | WR24-2-791 POC-01 Jagual WTP | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015140000 | WR23-7-2195 Oldach Associates | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015210000 | WR24-4-0603 Isabela Brewing | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015220000 | WRCRAR-25-0154 Jonathan Rivera | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015230000 | WR25-3-0118 JuanMelendez&Maria | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015240000 | WR25-7-095-EE Res.Juan A. Ruiz | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015250000 | WR25-1-0055 Health Management | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015260000 | WR24-1-0226 Hospedaje Medico | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015270000 | WR25-4-0490 Nashaly Ramos | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015280000 | WR23-2-1107 Est gasolina Total | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015380000 | WR24-7-238 O'Reilly Auto Parts | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015390000 | WR22-4-0345 LibertyAntenaLares | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015400000 | WR 25-1-0608-AA Sally Martin | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015410000 | WR 25-4-0221-EE POC.ISRAEL ROJ | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015420000 | WR23-1-0174-EST01 R.PostPVilla | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015430000 | WR CRMA-25-0827,POC,CesarJCand | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015440000 | WR 22-1-0923_LaPolillaMartinPe | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015460000 | WR 25-2-0578-EST-01 CrisApoGon | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015470000 | WR 23-7-001 Torres Ramos Resid | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015480000 | Reha Fronton Water 22-5-0395.1 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015490000 | WR CRMA-25-0920 EST-POC Gilmar | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015500000 | WR 23-2-0964-EST-POC SofritoMo | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015510000 | WR CRMA-25-0318 EST-POC Zullym | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015520000 | WR 08-4-0445 Solar.Danny E-01 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015530000 | WR 22-4-0170 EST-01 San.Sew.Sy | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015540000 | WR 22-3-0232-EST01 JoseMorales | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015550000 | WR 21-7-196-EST02 Enrique-AAA | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015560000 | WR 24-4-0567-EST-01 AdvAutPart | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015570000 | WR 24-7-239 PAC-PRGUO-001Telec | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015580000 | WR 21-3-123 EST02 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015590000 | WR25-4-0559-EE Kevin Hurley | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015600000 | WR18-5-0061 Edificio MAKA | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015610000 | WR 25-2-0069-EST01 BomAAAPaloH | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015620000 | WR 24-2-0812-EST-01 Rempl.Trfm | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015630000 | WR 21-3-097 Est01-Est02 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015650000 | WR19-5-0077 Kandor Manfcturing | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015660000 | WR23-5-0532 Tekcel Bajuras TC | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015670000 | WR19-2-0230 EST-01 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015680000 | WR25-2-0608-EST-01 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015690000 | WR25-4-0588 Aida M.Rivera | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015700000 | WR22-2-0938-EST-01 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015710000 | WR21-4-0287 PGM Head & Early | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015720000 | WR24-7-300 Maria De Lourdes | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015730000 | WR00-5-0242 AC-014066 PR-140 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015740000 | WR24-7-072-EST01 Selectos | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015750000 | WR25-1-0740-AA | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015760000 | WR21-4-0293 CaimitalAguadilla | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015770000 | WRCRMA-25-0765 Iris Rodriguez | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015780000 | WR25-1-0205 PTI-SAN JUAN | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015790000 | WR25-7-165 EST01 Trigo Corp. | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015800000 | WR22-2-0997-EST01 Head Start | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015810000 | WR25-4-0592 VPH OESTE LLC | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015820000 | WR22-7-322 Toa Baja Warehouse | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015830000 | WR25-7-042R1 EST-01 La Famosa | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015840000 | WR20-3-086-EST01 Edif.Calle M | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015850000 | WRCRMA-25-0897 Gaso.Texas Agua | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015860000 | WR24-40524 Solar Solymar Torr | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015870000 | WR25-4-0511-EE Emilio Mendez | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015880000 | WR19-1-236 Pedestrian Bridge | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015890000 | WR22-2-00797-EST 01 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015900000 | WR 22-7-297 EST01-Ferr.Valerie | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015910000 | WR 13-1-498 EST01-B.LasMerced. | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015920000 | WR24-1-0386 O'Reilly Auto Part | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015930000 | WR 24-3-025-EST01 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015940000 | WRCRAR-25-1177 Moises Rodrguez | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015950000 | WR23-7-366 DRD Parque S.Rosa | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015960000 | WRCRCA-25-0491 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N021000000 | WR08-5-0058B-EST01 UrbTerrazas | Active
CUSTOMER |  |  | 90017 | 90017 | 10N021100000 | WR25-4-0123 Juanito Caban | Active
CUSTOMER |  |  | 90017 | 90017 | 10N021200000 | WR24-4-0382 Parque C. Cajigas | Active
CUSTOMER |  |  | 90017 | 90017 | 10N021300000 | WR22-5-0029.1 Manuel A. Vega | Active
CUSTOMER |  |  | 90017 | 90017 | 15N003030000 | WR-6187222 Cayey Shopping Ctr | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003160000 | WR-6220955 AAA Comercial | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003170000 | WR-6175419 -- 22-D117 AAA | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003240000 | WR-6189028; BPPR Las Piedras | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003250000 | WR-6218036; AAA Quntas S.Luis | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003260000 | WR-6220969; (Cuesta los Jobos) | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003270000 | WR-6220982;22-D138 Isaacar Inc | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003300000 | WR-6220576 ASHFORD PRSEBY HOSP | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003320000 | WR-22-CDG155 Plaza Palma Real | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003330000 | WR-6247698-PR CONVENT.CENTER | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003340000 | WR-6247117 - INDULAC | Inactive
CUSTOMER |  |  | 90053 | 90053 | 15N003370000 | WR-22-DCG161 - CG GROUP | Inactive
CUSTOMER |  |  | 90053 | 90053 | 15N003380000 | WR-22-DCG167 AAA Troncal Come | Inactive
CUSTOMER |  |  | 90053 | 90053 | 15N003390000 | WR:6254891: AAA EB BOOSTER SJ | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003400000 | WR:6255095: CRISTO MALL | Inactive
CUSTOMER |  |  | 90053 | 90053 | 15N003410000 | WR:6255947: TORRE CIBELES | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003420000 | WR:6256049;LAS VISTAS SHOP VIL | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003440000 | WR-6251510-Cond. Jesus Sanroma | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003450000 | WR:6256207-CLARO LAS AMERICAS | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003460000 | WR:6256334; CLARO VILLA PRADES | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003470000 | WR-6075671:CONDOMINIO QUINTANA | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003480000 | WR:6236247; TORRE CHARDON | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003490000 | WR-6237345:COND LA LOMA FAJARD | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003500000 | WR-6241060: ARBY'S ESCORIAL | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003510000 | WR:6242398AAA CENT JUDIC CAROL | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003520000 | WR:6246886: CENTURY BUSINESS | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003530000 | WR:6256417: FRESENIUS | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003540000 | WR:6258815:RESTAURANTE ANTONIO | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003550000 | WR:6258914: AKYNA PRO BUILDING | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003560000 | WR:6258961; BURGER KING | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003570000 | WR-6260638 UNIV INTER FAJARDO | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003580000 | WR-6261528 LASVISTAS SHOPPVILL | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003590000 | WR-6261804: MUELLE 8 BAHIA URB | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003600000 | WR-6261961: HUMBERTO VIDAL | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003610000 | WR-6263766 AAA MET EB GUZMAN A | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003620000 | WR6264554-FOMENTO INDUST M0754 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003630000 | WR:6264818: AAA LAS CROABAS | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003670000 | WR:6248641:CONDO FLORAL PARK | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003680000 | WR: 6264322: MEDICOOP | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003690000 | WR-6264504:ESTN TOTAL CNTR CLB | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003700000 | WR-6264782 AAA EL YUNQUE | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003720000 | WR:6231968;ESC REP DE COLOMBIA | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003730000 | WR6236766;ESC ELEM JULIO HENNA | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003740000 | WR:6263695; AAA FARVIEW 3 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003750000 | WR:6258914; CONDADO DEL MAR | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003760000 | WR:6266823;SABANA VILLAGE APTS | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003770000 | WR-22-DCG179 METRO PLAZA | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003780000 | WR-22-DCG193 NELIPAK | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003790000 | WR:6267536; AAA PF CUBUY | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003800000 | WR-6098786 21-2-0286 FUNDESCO | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003810000 | WR-6178946 LUMA # 22-D119 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003820000 | WR-6219987;HIGH QLTY CANN(DES) | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003830000 | WR:6265127;AUT PUERTOS(TALLER) | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003840000 | WR:6267451 AAA EBAS CAROL IND | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003850000 | WR:6267551;AAA PF GUZMAN ARRIB | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003860000 | WR:6267964;CONSEJO COND COSTRS | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003870000 | WR-6269654;ESC LUIS LLORENS TO | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003880000 | WR:6270085;ESC LUIS RODRIG CAB | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003890000 | WR:6271164;ESC CENT ARTES VIS | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003900000 | WR-22-DCG152 ACT PR-53 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003910000 | WR- 22-DCG-185 _ CARMELA FOODS | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003920000 | WR-6155015;TRMNL PUERTO BACARD | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003930000 | WR-6252019; FOMENTO INDUSTRIAL | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003940000 | WR-6299353 LILLY DEL CARIBE | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003950000 | WR-6264832 HOTEL RITZ CARLTON | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003960000 | WR-6268990 AUTOCENTRO TOYOTA | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003970000 | WR-6269754 MARTIN PRINTING | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003980000 | WR-6269826; TRIBUNAL SUPREMO | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N003990000 | WR-6270534; ORIENTAL BANK | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004130000 | WR-22-dcg184 ; AAA Matrullas | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004140000 | WR-22-DCG196 AAA C.Norte | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004150000 | WR-22-DCG201 CERAMCO | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004170000 | WR-6269623-ECONO PLAZACAROLINA | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004180000 | WR-6224544-ALBERGU ANIM-MUN SJ | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004190000 | WR-6225439 CONDOMIN BOLIVIA 33 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004200000 | WR-6237804- CONDO FRENCH PLAZA | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004210000 | WR-6241848;PUENTE PEATNL PR181 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004220000 | WR-6264873- POPEYES CAMPO RICO | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004230000 | WR-6266473- PR ONCOLOGY | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004240000 | WR-6266822;MUELLE NAVY FRONTIE | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004250000 | WR-6267162-CONDO EBAL TERRACE | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004260000 | WR-6269870ENLACE CAÑO MRTN PEÑ | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004270000 | WR-6270387 ESC JOSE SEVERO QUI | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004280000 | WR-6270933-ESC RAFAEL RIVERA O | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004290000 | WR-6271910 ESC ARTURO MORALES | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004300000 | WR-6272468 UNIV INTER EDIF 1 I | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004310000 | WR-6272637 ALMACEN KIKUET | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004320000 | WR-6272780- EDIF MEDICAL ARTS | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004330000 | WR-6273886 ESC DEPORTES CAROLI | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004340000 | WR-6273993 FOMENTO INDL M-1298 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004350000 | WR6275566 22-1-0844-GG L.MARIA | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004360000 | WR-6275637- COOPV ROOSEVELT RD | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004370000 | WR-6276131-ESTACION PEAJE PR-6 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004380000 | WR-6277737- TERMINAL PUERTO BA | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004390000 | WR-6277950-CRIM | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004400000 | WR-6278006-MULTINATIONAL | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004410000 | WR-6279052- LILLY DEL CARIBE | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004420000 | WR-6279239-CONDOM EBAL TERRACE | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004430000 | WR-6280319- PAISAJES DEL RIO | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004440000 | WR-6281296- COND PALMAS MONTEB | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004450000 | WR-6281725-SUPERMAX TRUJILLO A | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004490000 | WR-22-DCG192 ; MERCK | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004500000 | WR-22-DCG206 ; BD HUMACAO | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004510000 | WR-6134044 HolvinMontalvo Cruz | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004520000 | WR-6179630 AREA REC LA ROMANA | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004530000 | WR-6276480;RESI LAS MARGARITAS | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004540000 | WR-6283896 RELPOSTE AVMUÑOZRIV | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004550000 | WR-6284222;COND CONDADOPRINCES | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004560000 | WR-6285807 K-MART BOX DEVELOP | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004570000 | WR-6285821 USDA FOREST SERVICE | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004580000 | WR-6241858 22-DCG158 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004590000 | WR-6269557 19-6-0085 PNTECEIBA | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004610000 | WR22-DCG207 JABIL-NYPRO | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004620000 | WR22-DCG183 ASPEN SURGICAL | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004630000 | WR-22-DCG216 WAPA | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004640000 | WR-22-DCG212 BD Cayey | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004650000 | WR-6282938 CoopRoosevelt Roads | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004660000 | WR6273846 COND. CANALS PARK | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004670000 | WR6284281 BANCO ALIMENTOS PR | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004680000 | WR6284639 CONDADO GARDENS | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004690000 | WR6281253 TMOBILE CAROLI.PHAR | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004700000 | WR6285917 AAA METRO CIUD.JARD | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004720000 | WR6285775 22-1-0566 CREAT.MARB | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004730000 | WR6230684 22-1-0321MON.BRI.PTE | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004740000 | WR6230697 22-1-0321MON.BRIpto | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004750000 | WR6106787 19-1-358 ECOMAX ROOS | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004760000 | WR6291707 USPS CAROLINA | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004770000 | WR6280166 21-1-142 PRO PILOT | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004780000 | WR6153370 21-1-093LEAP TEMP.CL | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004790000 | WR6285475 22-1-0921-AA Subway | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004800000 | WR23-DCG004 BUCKEYE CARIB.TERM | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004810000 | WR-23-DCG008 EST.BOM.SAN.PS-1 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004820000 | WR6287392 AAA PARC CAMPO RICO | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004830000 | WR-6285151 OPTIMA SEGUROS | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004840000 | WR-22-DCG223 Calesa Motors | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004850000 | WR-22-DCG202 Medtronics Humac | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004860000 | WR-22-DCG222 AAA | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004870000 | OWIP-Proj.Mant&Vias Libr-Areci | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004880000 | OWIP-Proj.Mant&Vias Libr-Mayag | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004890000 | OWIP-Proj.Mant&Vias Libr-Ponce | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004900000 | OWIP-Proj.Mant&Vias Libr-Bayam | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004910000 | OWIP-Proj.Mant&Vias Libr-Cagua | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004920000 | OWIP-Proj.Mant&Vias Libres-SJ | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004930000 | WR-22-DCG220 To Ricos | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004940000 | WR-22-DCG221 AAA | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004950000 | WR-22-DCG213 AAA TNQ@S.LORENZO | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004960000 | WR-23-DCG001 PARQ EVARISTO ROL | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004970000 | WR-23-DCG005 AAA EB CARRASQ II | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004980000 | WR-23-DCG010 TERUMO PR MED.CAG | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N004990000 | WR-23-DSJ-0014 MODERN AVIATION | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N005000000 | WR-23-DSJ0015 KIMKO REALTY(COL | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N005010000 | WR-23-DSJ0017 BALN.ISLA VERDE | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N005020000 | WR6117594 05-6-289 RIVERWOODS | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N005030000 | WR6274643 99-6-452 OCEAN DR. 3 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N005040000 | WR6278033 13-6-0338 QMC107COM | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N005060000 | WR-23-DCG007 FIGNA@CAYEY | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N005070000 | WR-23-DCG013 CCI CO. INC@CIDRA | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N005080000 | WR6219792-Bibl.Pub.Antonio Roi | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N005090000 | WR-23-DCG011;REC SUBVIL.CARMEN | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N005100000 | WR-23-DCG012 HOSP.RYDER@HUMAC | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N005110000 | WR-23-DCG014 BCTN DICKN@JUNCOS | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N005120000 | WR6287774 GUARDIA NACIONAL | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N005140000 | WR-23-DSJ-0019 VETERINARIA24-7 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N005150000 | WR-23-DSJ-0020 SALVATION ARMY | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N005160000 | WR23-DSJ-0022 SECT.YOUTH CNTR | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N005170000 | WR6070474 20-1-055 ACTSS | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N005180000 | WR6148870 21-6-0144 FOMEN IND | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N005190000 | WR-6160910 SURFSIDE MANSIONS | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N005200000 | WR6168497 13-6-0356 TORRE LUQ | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N005210000 | WR6179332 JARD.DE TRUJILLO EDI | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N005220000 | WR6180119 19-1-388 HOT ALMOST | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N005230000 | WR:6264810: AAA EBTK EL MILLON | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N005240000 | WR-6269531 ATLANTIC DRIVE G4 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N005250000 | WR-6270263 CONDADO CAMELOT | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N005260000 | WR6271246 02-6-292 SOLEMARE | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N005270000 | WR-6284006 ASHFORD LAGOON 888 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N005280000 | WR6286858 PARROQ.STELLA MARIS | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N005290000 | WR6287413 GPH CORPORATION | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N005300000 | WR-6291424 MARTIN PEÑA | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N005310000 | WR-22-DCG169 CASA PEREYO-HUMAC | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N005320000 | WR22-DCG181 AAAEBAS S.LIMA-NAG | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N005330000 | WR-22-DCG188 TO RICO-LAS PIEDR | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N005340000 | WR-6169576;22-D113HUMB VID CAG | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N005350000 | WR-6224628;ALUMINIOS DE PR | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N005360000 | WR6293051 12-1-119 PLANT LIFE | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N005370000 | WR-22-DCG187 MULTI-VENT-CAGU | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N005380000 | WR6158098 21-1-075 J CULTURE | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N005420000 | WR-23-DSJ-0023 DesRec IngPuert | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N005430000 | WR-22-DCG170 AAA Buena Vista | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N005440000 | 23-DSJ-0018 DES-REC WALGRE 217 | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N005450000 | WR6153811 20-2-0063 SegreO.Riv | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N005620000 | WR-22-DCG147 IFCO Recycling | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N005630000 | WR-22-DCG160-CARIBB.REFRESCOS | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N005640000 | WR-22-DCG165 INRUMEC | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N005650000 | WR6220104 Pure Health | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N005660000 | WR6226443-Progr.Educ.Comunal | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N005680000 | WR6121449 20-2-0350 AntMasasGu | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N005690000 | WR6280360 22-2-0305 FratAlfaSG | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N005740000 | WR6283685 21-2-0005 AntEspanol | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N005750000 | WR6300348 22-2-0369 HdaPortal | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N005810000 | OWIP-Proj.Mant&Vias Libr-Are2 | Active
CUSTOMER |  |  | 90017 | 90017 | 15N005820000 | OWIP-Proj.Mant&Vias Libr-Maya2 | Active
CUSTOMER |  |  | 90017 | 90017 | 15N005830000 | OWIP-Proj.Mant&Vias Libr-Ponc2 | Active
CUSTOMER |  |  | 90017 | 90017 | 15N005840000 | OWIP-Proj.Mant&Vias Libr-SJ2 | Active
CUSTOMER |  |  | 90017 | 90017 | 15N005850000 | OWIP-Proj.Mant&Vias Libr-Bay2 | Active
CUSTOMER |  |  | 90017 | 90017 | 15N005860000 | OWIP-Proj.Mant&Vias Libr-Cag2 | Active
CUSTOMER |  |  | 90017 | 90017 | 15N006250000 | WR6087081 20-1-228 Valet St.BP | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N007040000 | WR24DCG164 Buckeye Caribbean | Inactive
CUSTOMER |  |  | 90017 | 90017 | 15N008710000 | WR 25-2-0540-Est01 - AC-807544 | Active
n/a |  |  | 90037 | 90037 | 10F000180000 | Category B - PREPA Support | Inactive
n/a | 1294 | 83182 | 90058 | 90058 | 10F000210000 | FEMA CatZ Procurement Support | Cancel |  |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  |  | 2020-02-05 12:48
n/a | 1294 | 83182 | 90058 | 90058 | 10F000220000 | FEMA CatZ Legal Support | Cancel |  |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  |  | 2020-02-05 12:48
n/a |  |  | 90047 | 90047 | 10F000230000 | FEMA A&E Legal Support | Inactive
n/a |  |  | 90047 | 90047 | 10F000240000 | FEMA A&E Procurement Support | Inactive
n/a | 1294 | 83182 | 90058 | 90058 | 10F000250000 | FEMA CatZ Project Contr Supp | Cancel |  |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  |  | 2020-02-05 12:48
n/a | 1294 | 83182 | 90058 | 90058 | 10F000260000 | FEMA CatZ Capital PMO Supp | Cancel |  |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  |  | 2020-02-05 12:48
n/a | 1294 | 83182 | 90058 | 90058 | 10F000270000 | FEMA CatZ Cap Proj Mangmt Supp | Cancel |  |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  |  | 2020-02-05 12:48
n/a | 1294 | 83182 | 90058 | 90058 | 10F000280000 | FEMA CatZCapGrants Mngt SupIEM | Cancel |  |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  |  | 2020-02-05 12:48
n/a | 1294 | 83182 | 90058 | 90058 | 10F000290000 | FEMA CatZ Construction Supp | Cancel |  |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  |  | 2020-02-05 12:48
n/a | 1294 | 83182 | 90058 | 90058 | 10F000300000 | FEMA CatZ Eng Trans&Sub Supp | Cancel |  |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  |  | 2020-02-05 12:48
n/a | 1294 | 83182 | 90058 | 90058 | 10F000310000 | FEMA CatZ Warehouse Support | Cancel |  |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  |  | 2020-02-05 12:48
n/a | 1294 | 83182 | 90058 | 90058 | 10F000320000 | FEMA CatZ Regu,Land&Perm,Supp | Cancel |  |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  |  | 2020-02-05 12:48
n/a | 1294 | 83182 | 90058 | 90058 | 10F000330000 | FEMA CatZ HSE Supp | Cancel |  |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  |  | 2020-02-05 12:48
n/a |  |  | 90056 | 90056 | 10F000420000 | Prj.Fiona const.plan,sup.coord | Cancel
n/a | 1294 | 83182 | 90058 | 90058 | 10F000440000 | FEMA CatZ Syst Op. Support | Cancel |  |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  |  | 2020-02-05 12:48
n/a | 1294 | 83182 | 90058 | 90058 | 10F000460000 | FEMA CatZ Eng & Inv Strategies | Cancel |  |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  |  | 2020-02-05 12:48
n/a | 1294 | 83182 | 90058 | 90058 | 10F000470000 | FEMA CatZ Trans & Sub Support | Cancel |  |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  |  | 2020-02-05 12:48
n/a | 1294 | 83182 | 90058 | 90058 | 10F000490000 | FEMA CatZ Cust.Exp. Key Accts. | Cancel |  |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  |  | 2020-02-05 12:48
n/a | 1294 | 83182 | 90058 | 90058 | 10F000520000 | FEMA CatZ LargeProjectSupport | Cancel |  |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  |  | 2020-02-05 12:48
n/a | 1294 | 83182 | 90058 | 90058 | 10F007300000 | FEMA CatZ Project - War Room | Cancel |  |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  |  | 2020-02-05 12:48
n/a |  |  | 90019 | 90019 | 10N000210000 | Safety Equip Purch & Maint | Active
n/a |  |  | 90016 | 90016 | 10N000280000 | Renew CIRO 1 Salinas Intercon | Inactive
n/a |  |  | 90016 | 90016 | 10N000290000 | Renewable XZERTA - Intercon | Active
n/a |  |  | 90016 | 90016 | 10N000500000 | CIRO ONE ENGINEERING REVIEW | Cancel
n/a |  |  | 90016 | 90016 | 10N000530000 | SAN FERMIN INTERCONNEC STUDIES | Inactive
n/a |  |  | 90054 | 90054 | 10N000760000 | Energy Effy/Dmnd Respse Implem | Inactive
n/a |  |  | 60021 | 60021 | 10N007630000 | EATON IPP Fiber Optic Constr | Active
n/a |  |  | 90904 | 90904 | 14E900000000 | Emergency Response General | Cancel
n/a |  |  | 90904 | 90904 | 14E900000001 | Emergency Response - San Juan | Cancel
n/a |  |  | 90904 | 90904 | 14E900000002 | Emergency Response - Bayamon | Cancel
n/a |  |  | 90904 | 90904 | 14E900000003 | Emergency Response - Caguas | Cancel
n/a |  |  | 90904 | 90904 | 14E900000004 | Emergency Response - Arecibo | Cancel
n/a |  |  | 90904 | 90904 | 14E900000005 | Emergency Response - Mayaguez | Cancel
n/a |  |  | 90904 | 90904 | 14E900000006 | Emergency Response - Ponce | Cancel
n/a | 1294 | 83182 | 90058 | 90058 | 14F003180000 | PBCP1 Capital Programs PMO | Cancel |  |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  |  | 2020-02-05 12:48
n/a | 1294 | 83182 | 90058 | 90058 | 14F003190000 | PBCP2 Capital Programs Risk | Cancel |  |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  |  | 2020-02-05 12:48
n/a | 1294 | 83182 | 90058 | 90058 | 14F003200000 | PBCP3 Construction & Commiss | Cancel |  |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  |  | 2020-02-05 12:48
n/a |  |  | 90043 | 90043 | 14F004320000 | HSE Program Management | Inactive
n/a | 1294 | 83182 | 90058 | 90058 | 14F004420000 | FEMA CatZ Finance Support | Cancel |  |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  |  | 2020-02-05 12:48
n/a |  |  | 10216 | 10216 | 14F020270000 | S.StormsFlood.Landslid.Mudslid | Active |  | CAP2
n/a |  |  | 90903 | 90903 | 14F900000000 | Hurr.Fiona - FEMA-3583EM-ER | Closed
n/a |  |  | 90902 | 90902 | 14F900000001 | Hurricane.2022-Distrib.Project | Inactive
n/a |  |  | 90902 | 90902 | 14F900000002 | Hurricane.2022-Transm. Proj. | Cancel
n/a |  |  | 90902 | 90902 | 14F900000003 | Hurricane.2022-Subs.Project | Cancel
n/a |  |  | 90902 | 90902 | 14F900000004 | H.Fiona-Emerg. Resp.-San Juan | Closed
n/a |  |  | 90902 | 90902 | 14F900000005 | H.Fiona-Emerg. Resp.-Bayamon | Closed
n/a |  |  | 90902 | 90902 | 14F900000006 | H.Fiona-Emerg. Resp.-Caguas | Closed
n/a |  |  | 90902 | 90902 | 14F900000007 | H.Fiona-Emerg.Response-Arecibo | Closed
n/a |  |  | 90902 | 90902 | 14F900000008 | H.Fiona-Emerg. Response-Ponce | Closed
n/a |  |  | 90902 | 90902 | 14F900000009 | H.Fiona-Emerg.Response-Mayag. | Closed
n/a |  |  | 90000 | 90000 | 14N000090000 | PBCP1 Capital Progr PMO | Inactive | Inactive
n/a |  |  | 90000 | 90000 | 14N000100000 | PBCP2 Capital Progr Risk | Inactive | Inactive
n/a |  |  | 90000 | 90000 | 14N000110000 | Constr & Commiss Mgmt Office | Inactive | Inactive
n/a |  |  | 90016 | 90016 | 14N000260000 | PREPA Renewable RFP-Tranche 2 | Active
n/a |  |  | 90016 | 90016 | 14N000270000 | PREPA Renewable RFP-Tranche 3 | Active
n/a |  |  | 90016 | 90016 | 14N000280000 | PREPA Renewable RFP-Tranche 1 | Active
n/a |  |  | 90016 | 90016 | 14N001180000 | Jobos Solar AES (A-1-P) | Active
n/a |  |  | 90016 | 90016 | 14N001190000 | Jobos Storage AES (A-2-E) | Active
n/a |  |  | 90016 | 90016 | 14N001200000 | Ciro Two Salinas (AD-1-P) | Inactive
n/a |  |  | 90016 | 90016 | 14N001210000 | Salinas Solar AES (C-1-P) | Active
n/a |  |  | 90016 | 90016 | 14N001220000 | Salinas Storage AES (C-2-E) | Active
n/a |  |  | 90016 | 90016 | 14N001230000 | Guayama Solar Energy (AE-1-P) | Active
n/a |  |  | 90016 | 90016 | 14N001240000 | Tetris Power (AS-1-P) | Active
n/a |  |  | 90016 | 90016 | 14N001250000 | Yabucoa Solar (AK-1-P) | Active
n/a |  |  | 90016 | 90016 | 14N001270000 | ConvergentCoamoEnStorag(I-1-P) | Active
n/a |  |  | 90016 | 90016 | 14N001280000 | PatternBarcelonetaSolar(W-3-P) | Active
n/a |  |  | 90093 | 90093 | 14N001350000 | Proyecto Hostos | Active
n/a |  |  | 90016 | 90016 | 14N001380000 | Yabucoa Energy Park(AT-1-P) | Active
n/a |  |  | 90016 | 90016 | 14N001500000 | Isabela BESS-Tranche 4 | Active
n/a |  |  | 90016 | 90016 | 14N001530000 | Naguabo Energy Park | Active
n/a |  |  | 90016 | 90016 | 14N001550000 | TrancheSanGerman Solar AI-1-P | Active
n/a |  |  | 90079 | 90079 | 14O900000004 | Outage Evnt-Fiona reimb OMA-SJ | Cancel
n/a |  |  | 90079 | 90079 | 14O900000005 | Out Evn-Fiona reimb OMA-Bayamo | Cancel
n/a |  |  | 90079 | 90079 | 14O900000006 | Out Evn-Fiona reimb FEMA-Cagua | Cancel
n/a |  |  | 90079 | 90079 | 14O900000007 | Out Evn-Fiona reimb OMA-Arecib | Cancel
n/a |  |  | 90079 | 90079 | 14O900000008 | Out Evn-Fiona reimb FEMA-Ponce | Cancel
n/a |  |  | 90079 | 90079 | 14O900000009 | Out Even-Fiona reimb FEMA-Maya | Cancel
n/a |  |  | 90102 | 90102 | 15F019960000 | CAT Z - FINANCE - FIONA-DR4671 | Cancel
n/a |  |  | 90102 | 90102 | 15F019970000 | CAT Z - FINANCE - MARIA-DR4339 | Cancel
n/a |  |  | 90079 | 90079 | 15F900000000 | Outage Event-Fiona reimb FEMA | Inactive
n/a |  |  | 10153 | 10153 | 15N000010000 | Monac Outage Invest & Assess | Inactive | Inactive
n/a |  |  | 10153 | 10153 | 15N000020000 | Monacillo 115kV/13.2 Xmer/SG | Inactive | Inactive
n/a |  |  | 60000 | 60000 | 15N000050000 | Voxai Enhacement Project | Inactive
n/a |  |  | 60000 | 60000 | 15N000060000 | STORMS Data Migration | Inactive
n/a |  |  | 90900 | 90900 | 15N000070000 | Tropical Cyclone Six (Fred) | Inactive | Inactive | [7 empty] | 2022-03-08 17:00
n/a |  |  | 90005 | 90005 | 15N000080000 | Distr.Eng.Process Development | Inactive
n/a |  |  | 90005 | 90005 | 15N000090000 | DG Intercon.and Net Meter.Proc | Inactive
n/a |  |  | 90900 | 90900 | 15N000100000 | Tropical Storm Grace | Inactive | Inactive | [7 empty] | 2022-03-08 17:00
n/a |  |  | 90005 | 90005 | 15N000150000 | Trans.&Subst.Eng. Process Dev. | Inactive
n/a |  |  | 90005 | 90005 | 15N000160000 | Trans.& Subs.Eng.O&M work | Inactive
n/a |  |  | 60000 | 60000 | 15N000180000 | SOA Upgrade Project | Inactive
n/a |  |  | 60000 | 60000 | 15N000190000 | Voxai Call Cnter Exp.Repl.Proj | Inactive
n/a |  |  | 90007 | 90007 | 15N000210000 | Regul.Prog.&Compl.Support | Inactive
n/a |  |  | 90007 | 90007 | 15N000220000 | GridcoAssetO&M AgreSOP Imp RPS | Inactive
n/a |  |  | 90005 | 90005 | 15N000240000 | System Operations O&M Work | Inactive
n/a |  |  | 90005 | 90005 | 15N000260000 | Asset Mng-Gen Adm Cost Center | Active
n/a |  |  | 90005 | 90005 | 15N000270000 | AM-Asset Inf:GIS CartogUpdate | Active
n/a |  |  | 90005 | 90005 | 15N000300000 | AM-PAC Ex PAC sett conf chan | Active
n/a |  |  | 90005 | 90005 | 15N000310000 | AM-Asset: Report Generation | Inactive
n/a |  |  | 90005 | 90005 | 15N000320000 | AM-PAC Prov-emg PC equip sett | Inactive
n/a |  |  | 90005 | 90005 | 15N000330000 | AM-Asset: GIS Map Creat | Inactive
n/a |  |  | 90005 | 90005 | 15N000340000 | AM-PAC PAC equip repl and upg | Inactive
n/a |  |  | 90005 | 90005 | 15N000370000 | AM-Asset Strategy: Gover&Qual | Inactive
n/a |  |  | 90005 | 90005 | 15N000380000 | AM-PAC Stand spec dev and rev | Inactive
n/a |  |  | 90005 | 90005 | 15N000400000 | AM-PAC: PAC Technical Support | Inactive
n/a |  |  | 90005 | 90005 | 15N000410000 | AM-Asset Sgy: Distr LAsset Pln | Inactive
n/a |  |  | 90005 | 90005 | 15N000420000 | AM-Rel Wide Area Prot Cd WAPC | Inactive
n/a |  |  | 90005 | 90005 | 15N000430000 | AM-Asset Sgy Transm L-Ast Plan | Inactive
n/a |  |  | 90005 | 90005 | 15N000440000 | AM-Rel Distr Rel Plan An Rep | Inactive
n/a |  |  | 90005 | 90005 | 15N000450000 | AM-Ast Stgy Subs Asset Plan | Inactive
n/a |  |  | 90005 | 90005 | 15N000460000 | AM-Rel Trans RelPlan Any Rep | Inactive
n/a |  |  | 90005 | 90005 | 15N000470000 | AM-Plan Trans Pln Mod Std Proc | Inactive
n/a |  |  | 90005 | 90005 | 15N000490000 | AM-Pln Trans Pln NERC Anl Stud | Inactive
n/a |  |  | 90005 | 90005 | 15N000500000 | AM-Pln Spe Stud Micro Mini Opt | Inactive
n/a |  |  | 90005 | 90005 | 15N000510000 | AM-Planning: Dist Plan | Inactive
n/a |  |  | 90005 | 90005 | 15N000530000 | AM-Pln Dist Pln Mod Std Prcs | Inactive
n/a |  |  | 90005 | 90005 | 15N000540000 | AM-Reliability Out Rep Inv | Active
n/a |  |  | 90010 | 90010 | 15N000550000 | Integr.Safety&Op.Mgmt.Sys.Enha | Active
n/a |  |  | 90029 | 90029 | 15N000590000 | Distribution Hosting Capacity | Inactive
n/a |  |  | 90005 | 90005 | 15N000600000 | DG Portal | Inactive
n/a |  |  | 10144 | 10144 | 15N000650000 | EBS Hypercare (L) | Inactive
n/a |  |  | 10144 | 10144 | 15N000660000 | Workday Hypercare L | Inactive
n/a |  |  | 10144 | 10144 | 15N000670000 | Kronos Hypercare L | Inactive
n/a |  |  | 90007 | 90007 | 15N000680000 | Renewables Integration | Inactive
n/a |  |  | 60002 | 60002 | 15N000710000 | Technology Enablement | Inactive
n/a |  |  | 90029 | 90029 | 15N000950000 | Energy Efficiency Program | Inactive
n/a |  |  | 90029 | 90029 | 15N000960000 | Demand Response Program | Inactive
n/a |  |  | 90030 | 90030 | 15N000990000 | Assess SJ&PSeco gas conv.oppor | Inactive
n/a |  |  | 90030 | 90030 | 15N001000000 | Dev.Bridg.Plan for Frame 5turb | Cancel
n/a |  |  | 90031 | 90031 | 15N001010000 | Dev.GenCo Bdgt.Rep.& Rec.Capab | Cancel
n/a |  |  | 90030 | 90030 | 15N001020000 | Dev.Prog.for Fuel Compli.Monit | Inactive
n/a |  |  | 90031 | 90031 | 15N001030000 | Develop Trans. Serv. Program | Cancel
n/a |  |  | 90030 | 90030 | 15N001040000 | Prioritize backlog NME proj | Inactive
n/a |  |  | 90031 | 90031 | 15N001050000 | Impl Shared Serv Trans Prog | Inactive
n/a |  |  | 90032 | 90032 | 15N001060000 | Validate Plant Perform.Metrics | Cancel
n/a |  |  | 90032 | 90032 | 15N001070000 | Ena.AGC btw.plants&SysDspchCtr | Inactive
n/a |  |  | 90032 | 90032 | 15N001080000 | Estimate Plant Perf. Metrics | Cancel
n/a |  |  | 90033 | 90033 | 15N001110000 | Cntrct Mgmt Proce Trng EndUser | Inactive
n/a |  |  | 90033 | 90033 | 15N001120000 | NewPurchProcesses n Cntrct Tpl | Inactive
n/a |  |  | 90033 | 90033 | 15N001130000 | PBFM3 - Strateg Sourcing Team | Inactive
n/a |  |  | 90029 | 90029 | 15N001180000 | Minigrid Study Dsgn&Implement | Inactive
n/a |  |  | 90029 | 90029 | 15N001190000 | Offshore Wind Study | Cancel
n/a |  |  | 90029 | 90029 | 15N001200000 | P.SecoPP-PrelimEconSittiLannin | Inactive
n/a |  |  | 90029 | 90029 | 15N001210000 | Distr-ESS-ESS/PV NetBenfiAnaly | Inactive
n/a |  |  | 90038 | 90038 | 15N001510000 | Asset Management-Tools & Equip | Inactive
n/a |  |  | 90039 | 90039 | 15N001590000 | Title III and PROMESA Requests | Active
n/a |  |  | 90039 | 90039 | 15N001600000 | FCA/PPCA Inprovements | Inactive
n/a |  |  | 90039 | 90039 | 15N001610000 | Load Fore & Research Impro | Active
n/a |  |  | 90039 | 90039 | 15N001620000 | P3A-PREPA Reporting | Inactive
n/a |  |  | 50001 | 50001 | 15N001630000 | O&M Lighting Work Bayamon Reg. | Inactive
n/a |  |  | 50001 | 50001 | 15N001640000 | O&M Lighting Work SJ Region | Inactive
n/a |  |  | 50001 | 50001 | 15N001650000 | O&M Lighting Work Caguas Reg. | Active
n/a |  |  | 50001 | 50001 | 15N001660000 | O&M Lighting Work Arecibo Reg. | Inactive
n/a |  |  | 50001 | 50001 | 15N001670000 | O&M Lighting Work MayaguezReg. | Active
n/a |  |  | 50001 | 50001 | 15N001680000 | O&M Lighting Work Ponce Region | Active
n/a |  |  | 90021 | 90021 | 15N001700000 | Lands & Permits Operations | Inactive
n/a |  |  | 90021 | 90021 | 15N001710000 | Land & Permit Internal Req. | Inactive
n/a |  |  | 90021 | 90021 | 15N001720000 | Land & Permit External Req. | Inactive
n/a |  |  | 90021 | 90021 | 15N001730000 | Land & Permit Gov.& P.Affairs | Inactive
n/a |  |  | 60008 | 60008 | 15N001740000 | Printer Fleet Implementation | Inactive
n/a |  |  | 90005 | 90005 | 15N001750000 | EV Infrastructure Plan | Inactive
n/a |  |  | 90042 | 90042 | 15N001900000 | IRP Development | Active
n/a |  |  | 90901 | 90901 | 15N001910000 | Flood Emergency-February 2022 | Inactive
n/a |  |  | 90901 | 90901 | 15N001920000 | Major Power Outage Feb-21-2022 | Inactive
n/a |  |  | 90901 | 90901 | 15N001930000 | OUTAGE EVENT(8-3-21_8-4-21) | Inactive
n/a |  |  | 90901 | 90901 | 15N001940000 | OUTAGE EVENT(8-31-21_9-1-21) | Cancel
n/a |  |  | 90901 | 90901 | 15N001950000 | OUTAGE EVENT(9-13-21_9-14-21) | Inactive
n/a |  |  | 90901 | 90901 | 15N001960000 | OUTAGE EVENT(9-17-21_9-18-21) | Cancel
n/a |  |  | 90901 | 90901 | 15N001970000 | OUTAGE EVENT(9-21-21_9-23-21) | Cancel
n/a |  |  | 90901 | 90901 | 15N001980000 | OUTAGE EVENT(10-11-21_10-12-21 | Cancel
n/a |  |  | 90901 | 90901 | 15N001990000 | OUTAGE EVENT(10-13-21_10-14-21 | Cancel
n/a |  |  | 90901 | 90901 | 15N002000000 | OUTAGE EVENT(10-15-21_10-16-21 | Cancel
n/a |  |  | 90901 | 90901 | 15N002010000 | OUTAGE EVENT(11-23-21_11-24-21 | Cancel
n/a |  |  | 90901 | 90901 | 15N002020000 | OUTAGE EVENT(12-1-21_12-4-21) | Cancel
n/a |  |  | 90901 | 90901 | 15N002030000 | OUTAGE EVENT(1-31-22_2-01-22) | Cancel
n/a |  |  | 90902 | 90902 | 15N002050000 | Weather Emergency-July 2, 2022 | Inactive
n/a |  |  | 90039 | 90039 | 15N002060000 | Other Governmental Requests | Inactive
n/a |  |  | 90044 | 90044 | 15N002080000 | PREPA Restructuring | Active
n/a |  |  | 90046 | 90046 | 15N002090000 | LUMA's Perfom Metrics Filing | Inactive
n/a |  |  | 90044 | 90044 | 15N002100000 | COMPLEX ACCOUNTING SUPP PREPA | Active
n/a |  |  | 90039 | 90039 | 15N002150000 | DOE / PR100 | Inactive
n/a |  |  | 90901 | 90901 | 15N002160000 | Major Power Out-Cos Sur-4/6/22 | Inactive
n/a |  |  | 90901 | 90901 | 15N002170000 | Humacao TC 38 kV Outage | Inactive
n/a |  |  | 90048 | 90048 | 15N002180000 | PREPA/GenCo ServiceNow Implem | Inactive
n/a |  |  | 90048 | 90048 | 15N002190000 | VHF Radio Emergency Syst Upgr | Inactive
n/a |  |  | 90048 | 90048 | 15N002200000 | PREPA External Billing Support | Cancel
n/a |  |  | 60012 | 60012 | 15N002220000 | Sys Ops + LUMAPR Improvements | Inactive
n/a |  |  | 30060 | 30060 | 15N002230000 | Federal Grant Planning | Inactive
n/a |  |  | 90902 | 90902 | 15N002250000 | Heavy Rains-July-10-2022 | Inactive
n/a |  |  | 90902 | 90902 | 15N002260000 | Emergency Proj.Hurr.Season2023 | Inactive
n/a |  |  | 90901 | 90901 | 15N002270000 | Earthquake Event August 2022 | Cancel
n/a |  |  | 90902 | 90902 | 15N002280000 | Heavy Rain Event (8-16-2022) | Inactive
n/a |  |  | 40015 | 40015 | 15N002290000 | Explosion Jayuya Substation | Inactive
n/a |  |  | 40016 | 40016 | 15N002300000 | Explosion Santa Isabel Substat | Inactive
n/a |  |  | 90050 | 90050 | 15N002410000 | Distrib.Eng.and Plann.Training | Inactive
n/a |  |  | 90050 | 90050 | 15N002420000 | Transm.and Subst.Eng.Training | Active
n/a |  |  | 61000 | 61000 | 15N002990000 | VM - IT Work Mgmt - FieldNote | Active
n/a |  |  | 90044 | 90044 | 15N003000000 | InterimCostsPREPAbankrupt.Supp | Inactive
n/a |  |  | 60014 | 60014 | 15N003020000 | SMS - Comm GrayscaleApp | Inactive
n/a |  |  | 90901 | 90901 | 15N003070000 | 22-0002 August System Outage | Inactive
n/a |  |  | 90902 | 90902 | 15N003080000 | Heavy Rain Event (8-22-22) | Inactive
n/a |  |  | 30061 | 30061 | 15N003090000 | Distribution EngI O&M Expense | Active
n/a |  |  | 90901 | 90901 | 15N003100000 | Outage Event (9-3-2022) | Inactive
n/a |  |  | 90901 | 90901 | 15N003110000 | Outage Event 9/5/2022 | Inactive
n/a |  |  | 90902 | 90902 | 15N003120000 | Outage Event (Sept 8 2022) | Inactive
n/a |  |  | 90903 | 90903 | 15N003130000 | Tropical Storm - Fiona | Inactive
n/a |  |  | 90902 | 90902 | 15N003140000 | Outage Event (Nov-02-2022) | Cancel
n/a |  |  | 90902 | 90902 | 15N003180000 | Outage Event (Nov-05-2022) | Inactive
n/a |  |  | 90052 | 90052 | 15N003190000 | STEM Project | Inactive
n/a |  |  | 90901 | 90901 | 15N003230000 | Outage Event (05-24-23)* | Inactive
n/a |  |  | 90902 | 90902 | 15N003280000 | Outage Event (Oct-26-2022) | Inactive
n/a |  |  | 90902 | 90902 | 15N003290000 | Outage Event (Oct-30-2022) | Inactive
n/a |  |  | 90901 | 90901 | 15N003640000 | Outage Event (06-03-23) | Inactive
n/a |  |  | 90901 | 90901 | 15N003650000 | Standby Emerg or Outage Proj-1 | Cancel
n/a |  |  | 90901 | 90901 | 15N003660000 | Standby Emerg or Outage Proj-3 | Cancel
n/a |  |  | 90059 | 90059 | 15N004460000 | Interim Costs - Customer Exper | Inactive
n/a |  |  | 90060 | 90060 | 15N004470000 | Interim Costs - Finance | Active
n/a |  |  | 90061 | 90061 | 15N004480000 | O&M Procurement | Inactive
n/a |  |  | 90062 | 90062 | 15N004600000 | Servco Parked items | Cancel
n/a |  |  | 90063 | 90063 | 15N005390000 | Genera Mobilization RFI Supprt | Inactive
n/a |  |  | 90064 | 90064 | 15N005400000 | Shared Serv.Transit & Term Exp | Active
n/a |  |  | 90065 | 90065 | 15N005410000 | FOMB Interim Costs-Corp Serv. | Active
n/a |  |  | 90901 | 90901 | 15N005490000 | Outage Event (8-3-21_8-4-21) | Inactive
n/a |  |  | 90901 | 90901 | 15N005500000 | Outage Event (9-13-21_9-14-21) | Inactive
n/a |  |  | 90901 | 90901 | 15N005510000 | Outage Event (7-2-22) | Inactive
n/a |  |  | 90901 | 90901 | 15N005520000 | Outage Event (7-10-22) | Inactive
n/a |  |  | 90901 | 90901 | 15N005530000 | Outage Event (8-16-22) | Inactive
n/a |  |  | 90901 | 90901 | 15N005540000 | Outage Event (8-22-22) | Inactive
n/a |  |  | 90901 | 90901 | 15N005550000 | Outage Event (9-3-22) | Inactive
n/a |  |  | 90901 | 90901 | 15N005560000 | Outage Event (9-5-22) | Inactive
n/a |  |  | 90901 | 90901 | 15N005570000 | Outage Event (9-8-22) | Inactive
n/a |  |  | 90901 | 90901 | 15N005580000 | Outage Event (11-5-22) | Inactive
n/a |  |  | 90901 | 90901 | 15N005590000 | Outage Event (10-26-22) | Inactive
n/a |  |  | 90901 | 90901 | 15N005600000 | Outage Event (10-30-22) | Cancel
n/a |  |  | 90030 | 90030 | 15N005610000 | Wheeling Work Cost Tracking | Inactive
n/a |  |  | 90901 | 90901 | 15N005670000 | Outage Event (04-05-23) | Inactive
n/a |  |  | 90901 | 90901 | 15N005700000 | Standby Outage Event (TBD) | Inactive
n/a |  |  | 90068 | 90068 | 15N005710000 | 2023 RATE CASE | Active
n/a |  |  | 90069 | 90069 | 15N005720000 | RACER Rapid Restoration | Inactive
n/a |  |  | 90069 | 90069 | 15N005730000 | RACER VOLTTRON Restoration | Active
n/a |  |  | 90070 | 90070 | 15N005760000 | Servco/Manago Co Work | Inactive
n/a |  |  | 90030 | 90030 | 15N005770000 | Generation Stability Plan | Active
n/a |  |  | 91000 | 91000 | 15N005780000 | USFS Grant Application | Inactive
n/a |  |  | 40051 | 40051 | 15N005790000 | AguirreEmer.St.Serv(SharedServ | Inactive
n/a |  |  |  |  | 15N005800000 | Vieques Fiber Damage repair | Inactive
n/a |  |  | 90063 | 90063 | 15N005870000 | Genera Comencement-LEOC | Inactive
n/a |  |  | 90072 | 90072 | 15N005880000 | Large Project Outage Events | Active
n/a |  |  | 60020 | 60020 | 15N005890000 | IT-PLANNED OUTAGES CUST.NOTIFI | Active
n/a |  |  | 90064 | 90064 | 15N005900000 | SharedServ(GeneraPR)Trans&Exit | Active
n/a |  |  | 90064 | 90064 | 15N005910000 | Shared Serv(HoldCo)Trans&Exit | Active
n/a |  |  | 90064 | 90064 | 15N005920000 | Shared Serv(HydroCo)Trans&Exit | Inactive
n/a |  |  | 90064 | 90064 | 15N005930000 | Shared Serv(PropCo)Trans&Exit | Inactive
n/a |  |  | 40053 | 40053 | 15N005950000 | SUBS load shedding support | Inactive
n/a |  |  | 90075 | 90075 | 15N005960000 | LumaCollegeEmpl.Train.R.Arecib | Active
n/a |  |  | 90075 | 90075 | 15N005970000 | LumaCollegeEmpl.Train.R.Mayag | Active
n/a |  |  | 90075 | 90075 | 15N005980000 | LumaCollegeEmpl.Train.R.Ponce | Active
n/a |  |  | 90075 | 90075 | 15N005990000 | LumaCollegeEmpl.Train.Bayamon | Active
n/a |  |  | 90075 | 90075 | 15N006000000 | LumaCollegeEmpl.Train.San Juan | Active
n/a |  |  | 90075 | 90075 | 15N006010000 | LumaCollegeEmpl.Train.Caguas | Active
n/a |  |  | 90075 | 90075 | 15N006020000 | LumaCollegeEmpl.Train.Undergro | Active
n/a |  |  | 90075 | 90075 | 15N006030000 | LumaCollegeEmpTrainTranLinEast | Active
n/a |  |  | 90075 | 90075 | 15N006040000 | LumaCollegeEmpTrainTranLinWest | Active
n/a |  |  | 30068 | 30068 | 15N006050000 | C&M Back up to T&O Arecibo | Active
n/a |  |  | 30068 | 30068 | 15N006060000 | C&M Back up to T&O VBaja/Manat | Active
n/a |  |  | 30068 | 30068 | 15N006070000 | C&M Back up to T&O Utuado | Active
n/a |  |  | 30068 | 30068 | 15N006080000 | C&M Back up to T&O Mayaguez | Active
n/a |  |  | 30068 | 30068 | 15N006090000 | C&M Back up to T&O Aguadi/Sseb | Active
n/a |  |  | 30068 | 30068 | 15N006100000 | C&M Back up to T&O Ponce | Active
n/a |  |  | 30068 | 30068 | 15N006110000 | C&M Back up to T&O Guayama | Active
n/a |  |  | 30068 | 30068 | 15N006120000 | C&M Back up to T&O Yauco | Active
n/a |  |  | 30068 | 30068 | 15N006130000 | C&M Back up to T&O Barran/Caye | Active
n/a |  |  | 30068 | 30068 | 15N006140000 | C&M Back up to T&O Humacao | Active
n/a |  |  | 30068 | 30068 | 15N006150000 | C&M Back up to T&O Caguas | Active
n/a |  |  | 30068 | 30068 | 15N006160000 | C&M Back up to T&O Canovanas | Active
n/a |  |  | 30068 | 30068 | 15N006170000 | C&M Back up to T&O Fajardo | Active
n/a |  |  | 30068 | 30068 | 15N006180000 | C&M Back up to T&O Monacillos | Active
n/a |  |  | 30068 | 30068 | 15N006190000 | C&M Back up to T&O TBaja/Coroz | Active
n/a |  |  | 30068 | 30068 | 15N006200000 | C&M Back up to T&O Guayna/Baya | Active
n/a |  |  | 90075 | 90075 | 15N006210000 | LumaCollegeEmpTrainTran Subs | Active
n/a |  |  | 90076 | 90076 | 15N006220000 | WR Workforce | Active
n/a |  |  | 90072 | 90072 | 15N006230000 | Out Evnt LEOC-ROCCS-Labor Only | Inactive
n/a |  |  | 90078 | 90078 | 15N006240000 | Batt.Emerg.DemandResp.Program | Active
n/a |  |  | 90080 | 90080 | 15N006260000 | Fleet Support - Large Projects | Active
n/a |  |  | 90081 | 90081 | 15N006270000 | Customer RE Enrollment | Active
n/a |  |  | 90082 | 90082 | 15N006280000 | Customer RE Technical Services | Active
n/a |  |  | 40055 | 40055 | 15N006300000 | Vegetation Mngmnt interdprtmnt | Active
n/a |  |  | 90054 | 90054 | 15N006310000 | EE - Education/Outreach | Active
n/a |  |  | 90054 | 90054 | 15N006320000 | EE - Cross-Cutting | Active
n/a |  |  | 90054 | 90054 | 15N006330000 | EE-Residential Rebate Program | Active
n/a |  |  | 90054 | 90054 | 15N006340000 | EE - Business Rebate Program | Active
n/a |  |  | 90054 | 90054 | 15N006350000 | EE - In-Store Discount Program | Active
n/a |  |  | 90083 | 90083 | 15N006360000 | Mtrl Mngmnt Support-Burden Cst | Active
n/a |  |  | 40056 | 40056 | 15N006370000 | SUBS interdepartment works | Active
n/a |  |  | 40056 | 40056 | 15N006380000 | SUBS HUB services and works pd | Active
n/a |  |  | 90084 | 90084 | 15N006390000 | GeneraFinance Knwl Trf-SSTermi | Cancel
n/a |  |  | 90084 | 90084 | 15N006400000 | GeneraIT Knwl Trf-SSTerminatio | Active
n/a |  |  | 90084 | 90084 | 15N006410000 | Genera Ops Knwl Trf-SS Termina | Cancel
n/a |  |  | 90084 | 90084 | 15N006420000 | PREPA Finance Knw Trf-SS Termi | Active
n/a |  |  | 90084 | 90084 | 15N006430000 | PREPA IT Knwl Trf-SS Terminati | Active
n/a |  |  | 90084 | 90084 | 15N006440000 | PREPA Ops Knwl Trf-SS Terminat | Inactive
n/a |  |  | 90085 | 90085 | 15N006450000 | Facilit&Secu Collab-PREPA Only | Active
n/a |  |  | 90085 | 90085 | 15N006460000 | Insuran&Risk Collab-PREPA Only | Inactive
n/a |  |  | 90085 | 90085 | 15N006470000 | OT Collaboration-Genera Only | Active
n/a |  |  | 90085 | 90085 | 15N006480000 | OT Collaboration-PREPA Only | Active
n/a |  |  | 90085 | 90085 | 15N006490000 | Telecom Collaborat-Genera Only | Inactive
n/a |  |  | 90085 | 90085 | 15N006500000 | Telecom Collaborat-PREPA Only | Inactive
n/a |  |  | 40057 | 40057 | 15N006510000 | PMO Hots Spots repairs | Inactive
n/a |  |  | 90086 | 90086 | 15N006520000 | 2023Aud.Supp(Non-LUMA)forPREPA | Active
n/a |  |  | 60000 | 60000 | 15N006530000 | IT Applications Services | Active
n/a |  |  | 90088 | 90088 | 15N006540000 | Contractor Training Program | Inactive
n/a |  |  | 90012 | 90012 | 15N006550000 | Engineering Drawing Mgmt Syst | Active
n/a |  |  | 90089 | 90089 | 15N006560000 | Mat.Mgmt.Supp.Phys.Inv.Sto.Mod | Cancel
n/a |  |  | 90090 | 90090 | 15N006580000 | CC 300MW RFP - Tropigas | Active
n/a |  |  | 60022 | 60022 | 15N006590000 | Accounting Lease Application | Active
n/a |  |  | 60023 | 60023 | 15N006600000 | Check Printing-Oracle | Active
n/a |  |  | 40056 | 40056 | 15N006610000 | BAIROA TRANSFORMER TRSFR MON | Inactive
n/a |  |  | 30004 | 30004 | 15N006620000 | Additional O&M Spend East | Inactive
n/a |  |  | 30073 | 30073 | 15N006630000 | Additional O&M Spend Central | Inactive
n/a |  |  | 30074 | 30074 | 15N006640000 | Additional O&M Spend West | Inactive
n/a |  |  | 90905 | 90905 | 15N006660000 | 2024 - Large Outage Events | Inactive
n/a |  |  | 90905 | 90905 | 15N006670000 | LEOC/ROCC-Activation-Hur.Beryl | Inactive
n/a |  |  | 90091 | 90091 | 15N006680000 | Residential EE Kits | Active
n/a |  |  | 90091 | 90091 | 15N006690000 | Business Kits - EE | Active
n/a |  |  | 90092 | 90092 | 15N006700000 | Conex. Luma Phase 1.1plus | Active
n/a |  |  | 90905 | 90905 | 15N006710000 | LEOC - No Charge Account | Inactive
n/a |  |  | 90905 | 90905 | 15N006730000 | UnpostedMat.ErnestoRegAreci | Inactive
n/a |  |  | 90905 | 90905 | 15N006740000 | Trop.S.Ernesto Pending Trans. | Active
n/a |  |  | n/a | n/a | 15N006750000 | DR Customer Service | Cancel
n/a |  |  | n/a | n/a | 15N006760000 | DR Incentives | Active
n/a |  |  | n/a | n/a | 15N006770000 | ELRP (Emerg. Load Reduc.Prog.) | Active
n/a |  |  | 90095 | 90095 | 15N006780000 | DR Professional Services | Active
n/a |  |  | 90095 | 90095 | 15N006790000 | DR Program Evaluation | Inactive
n/a |  |  | 90095 | 90095 | 15N006800000 | DR Systems Operation | Active
n/a |  |  | 90096 | 90096 | 15N006810000 | EE Cross Cutting Regulatory | Active
n/a |  |  | 90096 | 90096 | 15N006820000 | EE Cross Cutting Shared Servic | Active
n/a |  |  | 94000 | 94000 | 15N006830000 | Customer RE - Shared Services | Active
n/a |  |  | 94000 | 94000 | 15N006840000 | Customer RE Regulatory | Inactive
n/a |  |  | 94000 | 94000 | 15N006850000 | NEM Conex. Luma Phase 2.0 | Inactive
n/a |  |  | 94000 | 94000 | 15N006860000 | NEM Cust.Excellence RE Special | Active
n/a |  |  | 94000 | 94000 | 15N006870000 | NEM Customer RE Platforms | Active
n/a |  |  | 94000 | 94000 | 15N006880000 | NEM Customer RE Project Mgmt | Active
n/a |  |  | 94000 | 94000 | 15N006890000 | NEM Customer RE Quality Assura | Active
n/a |  |  | 94000 | 94000 | 15N006900000 | NEM EX Upgrade | Active
n/a |  |  | n/a | n/a | 15N006910000 | SUBS-Ernesto exp consolidation | Cancel
n/a |  |  | 40056 | 40056 | 15N006920000 | SUBS MEGAPLEX installation | Active
n/a |  |  | 80011 | 80011 | 15N006930000 | LEX Net Metering Cases | Cancel
n/a |  |  | 80012 | 80012 | 15N006940000 | Mi LUMA Website Redesign | Active
n/a |  |  | 90097 | 90097 | 15N006970000 | OE October-Dec 2024 | Inactive
n/a |  |  | n/a | n/a | 15N006980000 | Reserva 1-Engineering (CC 588) | Cancel
n/a |  |  | n/a | n/a | 15N006990000 | Reserva 2 -Operations (CC 900) | Cancel
n/a |  |  | 90103 | 90103 | 15N007020000 | Procurement Workflow Automtn | Inactive
n/a |  |  | 90097 | 90097 | 15N007030000 | OE December 31-2024 | Inactive
n/a |  |  | 90097 | 90097 | 15N007050000 | OE January-March 2025 | Inactive
n/a |  |  | 90017 | 20016-001 | 15N007060000 | Covadonga GIS Repairs- Siemens | Active
n/a |  |  | 80011 | 80011 | 15N007070000 | Plann.Out.SMS-WhatsAppNotif | Cancel
n/a |  |  | 90104 | 90104 | 15N007080000 | Teams and Workday Integrations | Inactive
n/a |  |  | 80012 | 80012 | 15N007090000 | Website Redesign Phase II | Cancel
n/a |  |  | 90105 | 90105 | 15N007100000 | Cost Share Program | Active
n/a |  |  | n/a | n/a | 15N007110000 | GeneraPR BESS-Cambalache | Active
n/a |  |  | 90906 | 90906 | 15N007120000 | GeneraPR BESS & Peakers-C.Sur | Active
n/a |  |  | 90906 | 90906 | 15N007130000 | GeneraPR BESS-Palo Seco | Active
n/a |  |  | 90906 | 90906 | 15N007140000 | GeneraPR BESS&Peakers-Yabucoa | Active
n/a |  |  | 90906 | 90906 | 15N007150000 | GeneraPR BESS-Vega Baja | Active
n/a |  |  | n/a | n/a | 15N007160000 | WebsiteAccess-IndustrialCust. | Active
n/a |  |  | 90906 | 90906 | 15N007170000 | GeneraPR BESS-Aguirre | Active
n/a |  |  | 90097 | 90097 | 15N007180000 | OE April-June 2025 | Inactive
n/a |  |  | 90107 | 90107 | 15N007190000 | 800 MW Interconnection | Active
n/a |  |  | 90108 | 90108 | 15N007200000 | ASAP Battery System | Active
n/a |  |  | 80015 | 80015 | 15N007210000 | Customer Ebill Campaign | Active
n/a |  |  | 90097 | 90097 | 15N007220000 | OE April-16-2025-Major Outage | Active
n/a |  |  | 80016 | 80016 | 15N007230000 | Planned Outage-Website Dvlpmnt | Active
n/a |  |  | 90900 | 90900 | 15N007240000 | Generation Crisis - Admin | Cancel | Inactive | [7 empty] | 2022-03-08 17:00
n/a |  |  | 80017 | 80017 | 15N007250000 | Reporting of SMS/Whatsapp | Active
n/a |  |  | 90110 | 90110 | 15N007260000 | DOE Emergency Order 202-25-2 | Active
n/a |  |  | 90097 | 90097 | 15N007270000 | OE-July-September-2025 | Active
n/a |  |  | 90907 | 90907 | 15N007280000 | Hurricane Erin | Active
n/a |  |  | 90097 | 90097 | 15N007430000 | Hurrican Season FY 26 | Active
n/a |  |  | 60029 | 60029 | 15N007440000 | SharePoint Optimization-EAM St | Active
n/a |  |  | 90111 | 90111 | 15N007450000 | Large Projects Shared Services | Active
n/a |  |  | 50000 | 50000 | 15N007460000 | O&M STREETLIGHTING ARECI.REG. | Inactive | Active | [5 empty] | 2022-01-07 17:00 | 2022-01-07 17:00
n/a |  |  | 50000 | 50000 | 15N007470000 | O&M STREETLIGHTING BAYAM.REG. | Inactive | Active | [5 empty] | 2022-01-07 17:00 | 2022-01-07 17:00
n/a |  |  | 50000 | 50000 | 15N007480000 | O&M STREETLIGHTING CAGUAS REG. | Inactive | Active | [5 empty] | 2022-01-07 17:00 | 2022-01-07 17:00
n/a |  |  | 50000 | 50000 | 15N007490000 | O&M STREETLIGHTING PONCE REG. | Inactive | Active | [5 empty] | 2022-01-07 17:00 | 2022-01-07 17:00
n/a |  |  | 50000 | 50000 | 15N007500000 | O&M STREETLIGHTING S.JUAN REG. | Inactive | Active | [5 empty] | 2022-01-07 17:00 | 2022-01-07 17:00
n/a |  |  | 50000 | 50000 | 15N007510000 | O&M STREETLIGHTING MAYAG. REG. | Inactive | Active | [5 empty] | 2022-01-07 17:00 | 2022-01-07 17:00
n/a |  |  | 80012 | 80012 | 15N007520000 | LEX Integration Web Redesign | Active
n/a |  |  | 90907 | 90907 | 15N007540000 | Emerg.Proj.H.Season-Contracts | Active
n/a |  |  | 80018 | 80018 | 15N007550000 | Overnight Queues | Active
n/a |  |  | 90906 | 90906 | 15N007560000 | GeneraPR BESS & Peakers-Jobos | Active
n/a |  |  | 90906 | 90906 | 15N007570000 | GeneraPR BESS & Peakers Daguao | Active
n/a |  |  | 40091 | 40091 | 15N007580000 | SJ Municipalities Gound Mowing | Active
n/a |  |  | 80019 | 80019 | 15N007590000 | MiLUMA App - Map Correction | Active
n/a |  |  | 80020 | 80020 | 15N007600000 | Goggle Mapping Correction | Active
n/a |  |  | 90097 | 90097 | 15N007610000 | OE-October-December 2025 | Inactive
n/a |  |  | 90097 | 90097 | 15N008720000 | OE January-March 2026 | Active
n/a |  |  | 90079 | 90079 | 15O900000000 | Outage Event-Fiona reimb OMA | Cancel
n/a |  |  | 32003 | 32003 | 15R000000000 | Property Damage Rec.Process SJ | Inactive
n/a |  |  | 32003 | 32003 | 15R000010000 | PropertyDamageRec.Proc.Baya | Inactive
n/a |  |  | 32003 | 32003 | 15R000020000 | Property DamageRec.Process Cag | Inactive
n/a |  |  | 32003 | 32003 | 15R000030000 | Prop Damage Rec ProcessArecibo | Inactive
n/a |  |  | 32003 | 32003 | 15R000040000 | Prop Damage Rec ProcessMayague | Inactive
n/a |  |  | 32003 | 32003 | 15R000050000 | Prop Damage Rec ProcessPonce | Inactive
n/a |  |  | 32003 | 32003 | 15R000060000 | 3rd Party Recovery Arecibo | Inactive
n/a |  |  | 32003 | 32003 | 15R000070000 | 3rd Party Recove V Baja/Manatí | Inactive
n/a |  |  | 32003 | 32003 | 15R000080000 | 3rd Party Recovery Utuado | Inactive
n/a |  |  | 32003 | 32003 | 15R000090000 | 3rd Party Recovery Mayaguez | Inactive
n/a |  |  | 32003 | 32003 | 15R000100000 | 3rd Party RecovAguadilla/Sseba | Inactive
n/a |  |  | 32003 | 32003 | 15R000110000 | 3rd Party Recovery Ponce | Inactive
n/a |  |  | 32003 | 32003 | 15R000120000 | 3rd Party Recovery Guayama | Inactive
n/a |  |  | 32003 | 32003 | 15R000130000 | 3rd Party Recovery Yauco | Inactive
n/a |  |  | 32003 | 32003 | 15R000140000 | 3rd Prt Rec Barranquitas Cayey | Inactive
n/a |  |  | 32003 | 32003 | 15R000150000 | 3rd Party Recovery Humacao | Inactive
n/a |  |  | 32003 | 32003 | 15R000160000 | 3rd Party Recovery Caguas | Inactive
n/a |  |  | 32003 | 32003 | 15R000170000 | 3rd Party Recovery Canovanas | Inactive
n/a |  |  | 32003 | 32003 | 15R000180000 | 3rd Party Recovery Fajardo | Inactive
n/a |  |  | 32003 | 32003 | 15R000190000 | 3rd Party Recovery Monacillos | Inactive
n/a |  |  | 32003 | 32003 | 15R000200000 | 3rd Party Reco T Baja Corozal | Inactive
n/a |  |  | 32003 | 32003 | 15R000210000 | 3rd Party Recov Guaynabo Bayam | Inactive
n/a |  |  | 40058 | 40058 | 15R000220000 | SUBS-Third Party Property Dmge | Inactive
PBCP04 - PM Software & Tools | 1294 | 83182 | 90058 | 90058 | 14F003210000 | PBCP4 Project Management Sof | Cancel |  |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  |  | 2020-02-05 12:48
PBCP04 - PM Software & Tools |  |  | 90000 | 90000 | 14N000120000 | Project Management Software | Active | Inactive
PBCP04 - PM Software & Tools | 1294 | 83182 | 90102 | 90102 | 15F019840000 | CAT Z - PBCP4 | Active |  |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  |  | 2020-02-05 12:48
PBCS01 - Mod Customer Serv. Tec |  |  | 80003 | 80003 | 10N000070000 | Unified Agent Desktop | Inactive
PBCS01 - Mod Customer Serv. Tec |  |  | 80003 | 80003 | 10N000080000 | Contact Center Platform (IVR | Closed
PBCS01 - Mod Customer Serv. Tec |  |  | 80003 | 80003 | 10N000090000 | Contact Center Outbound Dialer | Cancel
PBCS01 - Mod Customer Serv. Tec |  |  | 80003 | 80003 | 10N000100000 | Proactive Outbound Notificatio | Inactive
PBCS01 - Mod Customer Serv. Tec |  |  | 80003 | 80003 | 10N000110000 | Contact Center Chat & Social C | Inactive
PBCS01 - Mod Customer Serv. Tec |  |  | 80003 | 80003 | 15N001830000 | Contact Ctr Unifi.Agt.Desktop | Inactive
PBCS01 - Mod Customer Serv. Tec |  |  | 80003 | 80003 | 15N001840000 | Cont.Ctr.Appt.Booking Assess | Cancel
PBCS01 - Mod Customer Serv. Tec |  |  | 80003 | 80003 | 15N001850000 | Cont.Ctr.Proact.Notif.Capabil. | Cancel
PBCS01 - Mod Customer Serv. Tec |  |  | 80003 | 80003 | 15N001860000 | Cont.Ctr.IVR Voice&Email Platf | Inactive
PBCS02 - Voice of the Customer |  |  | 80004 | 80004 | 10N000120000 | Voice of the Customer | Inactive
PBCS02 - Voice of the Customer |  |  | 80004 | 80004 | 15N001760000 | VOC Speech & Text Analytics | Active
PBCS02 - Voice of the Customer |  |  | 80004 | 80004 | 15N001770000 | Process Improv. Lean Six Sigma | Cancel
PBCS02 - Voice of the Customer |  |  | 80004 | 80004 | 15N001780000 | Q. A. Mystery Shopper Program | Inactive
PBCS02 - Voice of the Customer |  |  | 80004 | 80004 | 15N001790000 | CX Training Program (CX ONLY) | Inactive
PBCS02 - Voice of the Customer |  |  | 80004 | 80004 | 15N001800000 | CX Training Knowl Mgmt Syst | Inactive
PBCS02 - Voice of the Customer |  |  | 80004 | 80004 | 15N001810000 | CX Training (LUMA) | Inactive
PBCS02 - Voice of the Customer |  |  | 80004 | 80004 | 15N001820000 | VOC Customer Surveys | Active
PBCS03 - BillAccuracy&BackOffice |  |  | 80001 | 80001 | 10N000050000 | Billing Accuracy & Back Office | Active
PBCS03 - BillAccuracy&BackOffice |  |  | 80001 | 80001 | 10N000380000 | Billing Accuracy&Back Office | Cancel
PBCS03 - BillAccuracy&BackOffice |  |  | 80009 | 80009 | 10N000800000 | CC&B Opt-User Roles Functions | Active
PBCS03 - BillAccuracy&BackOffice |  |  | 80009 | 80009 | 10N000810000 | UIP CC&B Reporting Analytics | Active
PBCS03 - BillAccuracy&BackOffice |  |  | 80009 | 80009 | 10N000820000 | CC&B Optim - Service Orders | Inactive
PBCS03 - BillAccuracy&BackOffice |  |  | 80009 | 80009 | 10N000970000 | DatalakeRepServOrdrRout&Dashbs | Active
PBCS03 - BillAccuracy&BackOffice |  |  | 80001 | 80001 | 10N001400000 | CC&B Severance Proc Automtn | Closed
PBCS03 - BillAccuracy&BackOffice |  |  | 10145 | 10145 | 14N000130000 | BILL REDESIGN (L) | Inactive
PBCS03 - BillAccuracy&BackOffice |  |  | 80006 | 80006 | 15N001580000 | Cust. Serv. PBCS3 Bill Print | Inactive
PBCS03 - BillAccuracy&BackOffice |  |  | 80009 | 80009 | 15N003220000 | CC&B Optimizat-Meter LifeCycle | Active
PBCS03 - BillAccuracy&BackOffice |  |  | 80010 | 80010 | 15N005050000 | Critical Customer/Service | Inactive
PBCS03 - BillAccuracy&BackOffice |  |  | 80013 | 80013 | 15N006950000 | CC&B Letter Automation | Active
PBCS03 - BillAccuracy&BackOffice |  |  | 80014 | 80014 | 15N006960000 | FA Automation Discovery | Cancel
PBCS04 - Retail Wheeling Program |  |  | 90101 | 90101 | 10N009820000 | WheelingWorkCostTrackingFY2025 | Inactive
PBFM01 - Facilities Dev & Implem |  |  | 10158 | 10158 | 10F000140000 | FMS Aguadilla Contact Center | Cancel
PBFM01 - Facilities Dev & Implem |  |  | 10158 | 10158 | 10F000150000 | FMS Hormigerous Contact Cent | Active
PBFM01 - Facilities Dev & Implem |  |  | 10158 | 10158 | 10F000160000 | FMS Humacao Contact Centre | Cancel
PBFM01 - Facilities Dev & Implem |  |  | 10158 | 10158 | 10F000170000 | FMS Ponce Contact Centre | Cancel
PBFM01 - Facilities Dev & Implem |  |  | 10158 | 10158 | 10F000430000 | FMS-Tenant Broker Rep FF Proj | Active
PBFM01 - Facilities Dev & Implem |  |  | 10158 | 10158 | 10N000310000 | FMS-Tools-carts-dollies & bins | Inactive
PBFM01 - Facilities Dev & Implem |  |  | 10158 | 10158 | 10N000330000 | FMS - Furniture Projects | Inactive
PBFM01 - Facilities Dev & Implem |  |  | 10158 | 10158 | 10N000910000 | Aguadilla Contact Center NME | Cancel
PBFM01 - Facilities Dev & Implem |  |  | 10158 | 10158 | 10N000920000 | Hormigerous Contact Cent NME | Cancel
PBFM01 - Facilities Dev & Implem |  |  | 10158 | 10158 | 10N000930000 | Humacao Contact Centre NME | Cancel
PBFM01 - Facilities Dev & Implem |  |  | 10158 | 10158 | 10N000940000 | Ponce Contact Centre NME | Cancel
PBFM01 - Facilities Dev & Implem |  |  | 10158 | 10158 | 10N000950000 | Isabela Contact Centre NME | Cancel
PBFM01 - Facilities Dev & Implem |  |  | 10158 | 10158 | 10N011270000 | FMS Santurce Parking Rehab | Active
PBFM01 - Facilities Dev & Implem |  |  | 10030 | 10030 | 14F001950000 | FAASt Arecibo Regional Off | Active | Inactive | [7 empty] | 2026-07-13 17:00
PBFM01 - Facilities Dev & Implem |  |  | 10031 | 10031 | 14F001960000 | FAASt Arecibo Electric Serv | Inactive | Inactive | [7 empty] | 2027-02-23 15:24
PBFM01 - Facilities Dev & Implem | 107227 | 169804 | 10032 | 10032 | 14F001970000 | FAASt Aguadilla Electric Serv | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2024-09-26 17:00
PBFM01 - Facilities Dev & Implem | 107708 | 548596 | 10033 | 10033 | 14F001980000 | San Germán ESC. | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2026-01-16 17:00
PBFM01 - Facilities Dev & Implem | 107705 | 548393 | 10034 | 10034 | 14F001990000 | Arecibo Regional Repairs | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued
PBFM01 - Facilities Dev & Implem | 11570 | 551247 | 10035 | 10035 | 14F002000000 | Palo Seco South | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2024-08-14 17:00
PBFM01 - Facilities Dev & Implem | 107726 | 551242 | 10036 | 10036 | 14F002010000 | Bayamon Regional Repairs | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued
PBFM01 - Facilities Dev & Implem | 107711 | 550060 | 10037 | 10037 | 14F002020000 | Caguas Regional Repairs | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued
PBFM01 - Facilities Dev & Implem | 107732 | 551827 | 10038 | 10038 | 14F002030000 | San Juan Regional Repairs | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2024-06-21 17:00
PBFM01 - Facilities Dev & Implem | 107707 | 548440 | 10039 | 10039 | 14F002040000 | Mayaguez Regional Repairs | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2024-09-05 17:00
PBFM01 - Facilities Dev & Implem | 107718 | 550500 | 10040 | 10040 | 14F002050000 | Ponce Regional Repairs | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2024-10-16 17:00
PBFM01 - Facilities Dev & Implem |  |  | 10041 | 10041 | 14F002060000 | Toa Baja Technical Serv | Cancel
PBFM01 - Facilities Dev & Implem |  |  | 10158 | 10158 | 14F003770000 | FMS - Primary Contact Centre | Active
PBFM01 - Facilities Dev & Implem | 11862 | 679006 | 10163 | 10163 | 14F003920000 | Test and Technology Laboratory | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  |  | 2022-11-02
PBFM01 - Facilities Dev & Implem |  |  | 90066 | 90066 | 14F015260000 | FMS-Aviation Hangar BusnssCase | Inactive
PBFM01 - Facilities Dev & Implem |  |  | 10214 | 10214 | 14F017420000 | FMS-LUMA EmerOperCentNewBldng | Inactive
PBFM01 - Facilities Dev & Implem |  |  | 10158 | 10158 | 14N000370000 | FMS San Juan Region Projects | Active
PBFM01 - Facilities Dev & Implem |  |  | 10158 | 10158 | 14N000380000 | FMS Caguas Region Projects | Closed
PBFM01 - Facilities Dev & Implem |  |  | 10158 | 10158 | 14N000390000 | FMS Ponce Region Projects | Active
PBFM01 - Facilities Dev & Implem |  |  | 10158 | 10158 | 14N000400000 | FMS Mayaguez Region Projects | Active
PBFM01 - Facilities Dev & Implem |  |  | 10158 | 10158 | 14N000410000 | FMS Arecibo Region Projects | Active
PBFM01 - Facilities Dev & Implem |  |  | 10158 | 10158 | 14N000420000 | FMS Bayamón Region Projects | Active
PBFM01 - Facilities Dev & Implem |  |  | 10158 | 10158 | 14N000430000 | FMS Generator Acquisitions | Inactive
PBFM01 - Facilities Dev & Implem |  |  | 10158 | 10158 | 14N000440000 | FMS - HVAC Replacements | Active
PBFM01 - Facilities Dev & Implem |  |  | 10158 | 10158 | 14N000450000 | FMS - Water Cisterns | Active
PBFM01 - Facilities Dev & Implem |  |  | 10158 | 10158 | 14N000460000 | FMS Facilities Rebranding Proj | Closed
PBFM01 - Facilities Dev & Implem |  |  | 10158 | 10158 | 14N001010000 | FMS-CAGUAS REGIONAL PROJECT II | Active
PBFM01 - Facilities Dev & Implem | 1294 | 83182 | 90102 | 90102 | 15F019710000 | CAT Z - PBFM1 | Active |  |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  |  | 2020-02-05 12:48
PBFM01 - Facilities Dev & Implem |  |  | 90005 | 90005 | 15N000170000 | UT Technical Training | Inactive
PBFM01 - Facilities Dev & Implem |  |  | 90005 | 90005 | 15N000280000 | Asset Mng-General: Training | Inactive
PBFM01 - Facilities Dev & Implem |  |  | 90005 | 90005 | 15N000360000 | AM-PAC PAC tools templ develop | Inactive
PBFM01 - Facilities Dev & Implem |  |  | 10158 | 10158 | 15N001250000 | FMS-Facilities CapTeam Develop | Active
PBFM01 - Facilities Dev & Implem |  |  | 10158 | 10158 | 15N001260000 | FMS - PPE/FRC for Facilities | Inactive
PBFM01 - Facilities Dev & Implem |  |  | 10158 | 10158 | 15N001270000 | FMS - Facilities Drawings | Active
PBFM01 - Facilities Dev & Implem |  |  | 10158 | 10158 | 15N001280000 | FMS-T&D/Gen co-location study | Inactive
PBFM01 - Facilities Dev & Implem |  |  | 10158 | 10158 | 15N001290000 | FMS-T&D/Gen co-location plann | Inactive
PBFM01 - Facilities Dev & Implem |  |  | 10158 | 10158 | 15N001300000 | Facilities Empl.Training & Dev | Active
PBFM01 - Facilities Dev & Implem |  |  | 10158 | 10158 | 15N001880000 | FMS- DEEP CLEANNING ACTIVITIES | Inactive
PBFM01 - Facilities Dev & Implem |  |  |  |  | 15N002070000 | NEOS Flooding | Inactive
PBFM01 - Facilities Dev & Implem |  |  | 10158 | 10158 | 15N003350000 | FMS -UPS FIRE PROJECT | Inactive
PBFM01 - Facilities Dev & Implem |  |  | 10158 | 10158 | 15N003360000 | Facilities Tech Dev&Implem | Cancel
PBFM01 - Facilities Dev & Implem |  |  | 10158 | 10158 | 15N005480000 | FMS Facilit Tech Devel&Imp-II | Active
PBFM02 - Critical Financial Ctrl |  |  | 90034 | 90034 | 15N001140000 | Int Audit-Role & Resp and Res | Active
PBFM02 - Critical Financial Ctrl |  |  | 90035 | 90035 | 15N001150000 | Finance & Accounting Policies | Active
PBFM02 - Critical Financial Ctrl |  |  | 90035 | 90035 | 15N001160000 | Financial Systems Control | Active
PBFM02 - Critical Financial Ctrl |  |  | 90035 | 90035 | 15N001170000 | Financial Reporting | Active
PBFM04 - Critical Financial Sys |  |  | 60001 | 60001 | 10N000150000 | Oracle Expense Module Implem. | Closed
PBFM04 - Critical Financial Sys |  |  | 60010 | 60010 | 10N000400000 | Oracle Supporting Tools | Inactive
PBFM04 - Critical Financial Sys |  |  | 90049 | 90049 | 10N000520000 | Time Rec. & Process Enhancem. | Active
PBFM04 - Critical Financial Sys |  |  | 60013 | 60013 | 10N000540000 | Procure to Pay-ORACLE Implem. | Inactive
PBFM04 - Critical Financial Sys |  |  | 60015 | 60015 | 10N000790000 | PA Budget and Forecast Tools | Closed
PBFM04 - Critical Financial Sys |  |  | 60019 | 60019 | 15N005130000 | EBS Reporting Tool | Active
PBFM04 - Critical Financial Sys |  |  | 90074 | 90074 | 15N005940000 | Artemis Reporting Tool | Cancel
PBFM04 - Critical Financial Sys |  |  | 60030 | 60030 | 15N007530000 | Account Reconciliation Tool | Active
PBHE01 - HSE & Tech Training |  |  | 90018 | 90018 | 15N000720000 | Employee Tech Train App Prog | Active
PBHE03 - Public Safety Program |  |  | 90011 | 90011 | 15N000610000 | Public Safety Progr. Develop. | Active
PBHE04 - Waste Management |  |  | 90020 | 90020 | 10N002390000 | Storage Containers for Transfo | Closed
PBHE04 - Waste Management |  |  | 90020 | 90020 | 15N000780000 | Waste Management | Inactive
PBHE08 - Emerg Resp Preparedness |  |  | 90024 | 90024 | 10N000250000 | Establish Emergency Op Center | Closed
PBHE08 - Emerg Resp Preparedness |  |  | 90025 | 90025 | 10N000260000 | Emergency Damage Assess Progr | Inactive
PBHE08 - Emerg Resp Preparedness |  |  | 90027 | 90027 | 10N000270000 | Implem In Mngmt Platfo(WEBEOC) | Closed
PBHE08 - Emerg Resp Preparedness |  |  | 90026 | 90026 | 15N000890000 | Develop Business Cont Plan | Inactive
PBHR01 - HR Inf.Syst.&Learn.Plat |  |  | 90009 | 90009 | 10N000160000 | Workday Implementation Modules | Closed
PBHR01 - HR Inf.Syst.&Learn.Plat |  |  | 90009 | 90009 | 10N000300000 | CBA/Recruitment | Closed
PBHR01 - HR Inf.Syst.&Learn.Plat |  |  | 90009 | 90009 | 15N001100000 | PBHR1 Training for all Depts. | Inactive
PBHR01 - HR Inf.Syst.&Learn.Plat |  |  | 90009 | 90009 | 15N001560000 | Employee Engagement (PBHR1) | Cancel
PBHR01 - HR Inf.Syst.&Learn.Plat |  |  | 90057 | 90057 | 15N003710000 | HR Projects-ICIMS | Cancel
PBIT01 - OT Telecom Sys&Network |  |  | 995 | 995 | 10N009270000 | IP Control Network Resliency | Active | Active | [5 empty] | 2024-09-09 08:00 | 2024-09-09 08:00
PBIT01 - OT Telecom Sys&Network |  |  | 60027 | 60027 | 10N012210000 | GuayaToJob.Fib.Enh-AguiToJobTC | Inactive
PBIT01 - OT Telecom Sys&Network |  |  | 60028 | 20015-002 | 10N013850000 | DOE Maunabo to Juan Martin UB | Active | Active | [5 empty] | 2025-05-16 08:00 | 2025-05-16 08:00
PBIT01 - OT Telecom Sys&Network |  |  | 60028 | 60028 | 10N013860000 | DOE Telecom Gen Design&Install | Active | Active | [5 empty] | 2025-07-21 08:00 | 2025-07-21 08:00
PBIT01 - OT Telecom Sys&Network |  |  | 60028 | 20015-003 | 10N013870000 | DOE Pinas GIS to Dorado TC | Active | Active | [5 empty] | 2025-08-07 08:00 | 2025-08-07 08:00
PBIT01 - OT Telecom Sys&Network |  |  | 60028 | 20015-004 | 10N013880000 | DOE Yabucoa to Juan Martin | Inactive | Active | [5 empty] | 2025-05-16 08:00 | 2025-05-16 08:00
PBIT01 - OT Telecom Sys&Network |  |  | 60028 | 20015-001 | 10N014130000 | DOE BayTC toDoraTC OPGWFib.Enh | Active | Active | [5 empty] | 2025-08-07 08:00 | 2025-08-07 08:00
PBIT01 - OT Telecom Sys&Network | 107765 | 674506 | 10044 | 10044 | 14F002090000 | FIELD AREA NETWORK (FAN). | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2025-09-01 17:00
PBIT01 - OT Telecom Sys&Network |  |  | 20002 |  | 14F002100000 | TELECOM INFRASTRUCTUR | Inactive | Active
PBIT01 - OT Telecom Sys&Network | 107742 | 662238 | 20001-001 | 20001-001 | 14F002110000 | MICROWAVE PTP. | Inactive | Active |  |  | Active | Phase 3 - Scoping and Costing | Pending FEMA 406 HMP Completion | 2022-06-15 08:00 | 2022-06-15 08:00 | 2023-05-26 17:00 | 2023-05-23
PBIT01 - OT Telecom Sys&Network | 11859 | 551963 | 10049-001 | 10049-001 | 14F002140000 | Transport Network | Active | Inactive |  |  | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant | 2024-11-05 08:00 | 2024-11-05 08:00 | 2025-03-21 08:00 | 2023-07-29 | 2025-09-17 18:16
PBIT01 - OT Telecom Sys&Network |  |  | 10050 | 10050 | 14F002150000 | IT CORP NETWORK. | Cancel | Inactive
PBIT01 - OT Telecom Sys&Network |  |  | 10157 | 10157 | 14F003600000 | Fiber Optics Replacement -FEMA | Inactive | Inactive | [5 empty] | 2026-02-20 08:00 |  | 2026-04-06 17:00
PBIT01 - OT Telecom Sys&Network | 107767 | 675406 | 10162 | 10162 | 14F003900000 | LMR Two Way Radio | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2025-09-05 12:00
PBIT01 - OT Telecom Sys&Network | 107777 | 682331 | 10164 | 10164 | 14F004430000 | RTU-Telecom ReplGrp1-Mayaguez | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2025-09-22 09:36
PBIT01 - OT Telecom Sys&Network | 107742 | 662238 | 20001-001 | 20001-001 | 14F004500000 | Microwave Network Upgrade | Active | Active |  |  | Active | Phase 3 - Scoping and Costing | Pending FEMA 406 HMP Completion | 2022-06-15 08:00 | 2022-06-15 08:00 | 2023-05-26 17:00 | 2023-05-23
PBIT01 - OT Telecom Sys&Network | 11452 | 673292 | 20002 | 20002 | 14F004510000 | Telecom Infrast-Cerro Puntas | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-06-20 08:00 | 2022-06-20 08:00 | 2025-01-27 17:00 | 2024-02-05 | 2025-10-30 20:15
PBIT01 - OT Telecom Sys&Network | 11861 | 679035 | 20003-001 | 20003-001 | 14F004550000 | El Yunque - Group A | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2025-08-15 17:00
PBIT01 - OT Telecom Sys&Network | 11861 | 679035 | 20003-002 | 20003-002 | 14F004560000 | Santa Ana - Group A | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2025-08-15 17:00
PBIT01 - OT Telecom Sys&Network | 11861 | 679035 | 20003-003 | 20003-003 | 14F004570000 | Santurce Luchetti - Group A | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2025-08-15 17:00
PBIT01 - OT Telecom Sys&Network | 11425 | 678800 | 20004-001 | 20004-001 | 14F004580000 | Atalaya - Group B | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2024-05-14 08:00 | 2024-05-14 | 2025-11-05 16:17
PBIT01 - OT Telecom Sys&Network | 11425 | 678800 | 20004-002 | 20004-002 | 14F004590000 | El Gato - Group B | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2024-05-14 08:00 | 2024-05-14 | 2025-11-05 16:17
PBIT01 - OT Telecom Sys&Network | 11425 | 678800 | 20004-003 | 20004-003 | 14F004600000 | Isabela - Group B | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2024-05-14 08:00 | 2024-05-14 | 2025-11-05 16:17
PBIT01 - OT Telecom Sys&Network | 11425 | 678800 | 20004-004 | 20004-004 | 14F004610000 | La Santa - Group B | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2024-05-14 08:00 | 2024-05-14 | 2025-11-05 16:17
PBIT01 - OT Telecom Sys&Network | 11425 | 678800 | 20004-005 | 20004-005 | 14F004620000 | Manati TC - Group B | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2024-05-14 08:00 | 2024-05-14 | 2025-11-05 16:17
PBIT01 - OT Telecom Sys&Network | 107825 | 704763 | 20005 | 20005 | 14F004640000 | El Maní - Group C | Inactive |  |  |  | Withdrawn | Discontinued | Process Discontinued
PBIT01 - OT Telecom Sys&Network | 107825 | 704763 | 20005-001 | 20005-001 | 14F004650000 | Juana Diaz Loma - Group C | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued
PBIT01 - OT Telecom Sys&Network | 107825 | 704763 | 20005 | 20005 | 14F004660000 | Monacillo TC- Group C | Inactive |  |  |  | Withdrawn | Discontinued | Process Discontinued
PBIT01 - OT Telecom Sys&Network | 11863 | 704805 | 20007-001 | 20007-001 | 14F008600000 | Fajardo Tecnica-Group D | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2025-08-15 17:00
PBIT01 - OT Telecom Sys&Network | 11863 | 704805 | 20007-002 | 20007-002 | 14F008610000 | Humacao Tecnica-Group D | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2025-08-15 17:00
PBIT01 - OT Telecom Sys&Network | 11863 | 704805 | 20007-003 | 20007-003 | 14F008620000 | Mayaguez (Mckinley)-Group D | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2025-08-15 17:00
PBIT01 - OT Telecom Sys&Network | 11863 | 704805 | 20007-004 | 20007-004 | 14F008630000 | Sabana Llana TC-Group D | Inactive |  |  |  | Withdrawn | Discontinued | Process Discontinued
PBIT01 - OT Telecom Sys&Network | 108105 | 814792 | 20008-001 | 20008-001 | 14F008930000 | Mora TC-Group E | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2025-12-22 17:00
PBIT01 - OT Telecom Sys&Network | 108105 | 814792 | 20008-002 | 20008-002 | 14F009010000 | Quebradillas Técnica-Group E | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2025-12-26 17:00
PBIT01 - OT Telecom Sys&Network | 108105 | 814792 | 20008-003 | 20008-003 | 14F009020000 | San Sebastián TC-Group E | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2025-11-20 17:00
PBIT01 - OT Telecom Sys&Network |  |  | 63001 | 63001 | 14F010050000 | Battery Test & Replace | Inactive
PBIT01 - OT Telecom Sys&Network |  |  | 63001 | 63001 | 14F010060000 | Two-Way Radio Assess & Repair | Closed
PBIT01 - OT Telecom Sys&Network |  |  | 63001 | 63001 | 14F010070000 | Microwave Assess & Repair | Inactive
PBIT01 - OT Telecom Sys&Network |  |  | 63001 | 63001 | 14F010080000 | Fiber Assess & Repair | Closed
PBIT01 - OT Telecom Sys&Network |  |  | 63001 | 63001 | 14F010090000 | Program Management | Inactive
PBIT01 - OT Telecom Sys&Network |  |  | 63001 | 63001 | 14F010100000 | Subs Telecom Assess & Repair | Inactive
PBIT01 - OT Telecom Sys&Network |  |  | 63001 | 63001 | 14F010110000 | TWAC Systems Assess & Repair | Inactive
PBIT01 - OT Telecom Sys&Network |  |  | 63001 | 63001 | 14F010120000 | Tower Safety Assess & Repair | Inactive
PBIT01 - OT Telecom Sys&Network | 11863 | 704805 | 20007 | 20007 | 14F012500000 | Telecom Infrastructure Grupo D | Inactive |  |  |  | Withdrawn | Discontinued | Process Discontinued
PBIT01 - OT Telecom Sys&Network |  |  | 60017 | 60017 | 14F013950000 | Culebra 3801 Telecomm Tower | Inactive | Inactive | [7 empty] | 2024-11-06 17:00
PBIT01 - OT Telecom Sys&Network | 108106 | 814793 | 20009-001 | 20009-001 | 14F019040000 | Telco Infra Guanica Group F | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2025-11-18 17:00
PBIT01 - OT Telecom Sys&Network | 108106 | 814793 | 20009-002 | 20009-002 | 14F019050000 | Telco Infra Barranquita GroupF | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2025-11-14 17:00
PBIT01 - OT Telecom Sys&Network | 108106 | 814793 | 20009-003 | 20009-003 | 14F019060000 | Telco Infra Barceloneta GroupF | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2025-10-13 17:00
PBIT01 - OT Telecom Sys&Network |  |  | 60024-001 | 60024-001 | 14F020210000 | Telco Infra AguasBuenasGroup H | Inactive | Inactive | CAP1 | [6 empty] | 2027-04-07 17:00
PBIT01 - OT Telecom Sys&Network |  |  | 60024-002 | 60024-002 | 14F020220000 | Telco Infra Utuado Tec Group H | Inactive | Inactive | CAP1 | [6 empty] | 2026-10-07 17:00
PBIT01 - OT Telecom Sys&Network |  |  | 60024-003 | 60024-003 | 14F020230000 | Telco Infra Manati Tec Group H | Inactive | Inactive | CAP1 | [6 empty] | 2026-04-07 17:00
PBIT01 - OT Telecom Sys&Network | 108004 | 753302 | 60016-001 | 60016-001 | 14F020240000 | Telco Infra Canov TC Group G | Inactive | Inactive | CAP2 |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2026-03-24 17:00
PBIT01 - OT Telecom Sys&Network | 108004 | 753302 | 60016-002 | 60016-002 | 14F020250000 | Telco Infra Juncos TC Group G | Inactive | Inactive | CAP2 |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2026-04-07 17:00
PBIT01 - OT Telecom Sys&Network |  |  | 60016-003 | 60016-003 | 14F020260000 | TelcoInfraS.IsabelTecnicaGrpG | Inactive | Inactive | CAP1 | [6 empty] | 2026-07-10 17:00
PBIT01 - OT Telecom Sys&Network | 11859 | 551963 | 10049-002 | 10049-002 | 14F021890000 | T. Network G1 Aguas Buenas GIS | Active | Active | CAP4 |  | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant |  |  | 2025-03-21 08:00 | 2023-07-29 | 2025-09-17 18:16
PBIT01 - OT Telecom Sys&Network | 11859 | 551963 | 10049-003 | 10049-003 | 14F021900000 | T. Network G1 Monacillos PCC | Active | Active | CAP4 |  | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant |  |  | 2025-03-21 08:00 | 2023-07-29 | 2025-09-17 18:16
PBIT01 - OT Telecom Sys&Network | 11859 | 551963 | 10049-004 | 10049-004 | 14F021910000 | T. Network G1 Sabana Llana TC | Active | Active | CAP4 |  | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant |  |  | 2025-03-21 08:00 | 2023-07-29 | 2025-09-17 18:16
PBIT01 - OT Telecom Sys&Network | 1294 | 83182 | 90102 | 90102 | 15F019740000 | CAT Z - PBIT1 | Active |  |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  |  | 2020-02-05 12:48
PBIT01 - OT Telecom Sys&Network |  |  | 90102 | 90102 | 15F019910000 | CAT Z - PBIT1 (Fiona) | Inactive
PBIT01 - OT Telecom Sys&Network |  |  | 10157 | 10157 | 15N000250000 | Fiber Optics Replacement -OPEX | Inactive | Inactive | [5 empty] | 2026-02-20 08:00 |  | 2026-04-06 17:00
PBIT02 - IT OT Cybersecur. Prog. | 107753 | 668665 | 10042 | 10042 | 14F002070000 | CYBERSECURITY PROGRAM IMPL | Cancel | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2023-01-05 13:38 | 2023-10-31
PBIT02 - IT OT Cybersecur. Prog. |  |  | 10042 | 10042 | 14N000170000 | PBIT2 MFA - Multi-Factor Auth | Closed | Inactive | [7 empty] | 2023-01-05 13:38
PBIT02 - IT OT Cybersecur. Prog. |  |  | 10042 | 10042 | 14N000180000 | PBIT2 Network Perimeter Sec | Closed | Inactive | [7 empty] | 2023-01-05 13:38
PBIT02 - IT OT Cybersecur. Prog. |  |  | 10042 | 10042 | 14N000190000 | PBIT2 PAM-Priv Access Mngmt | Inactive | Inactive | [7 empty] | 2023-01-05 13:38
PBIT02 - IT OT Cybersecur. Prog. |  |  | 10042 | 10042 | 14N000290000 | PBIT2 Improve EndPnt Security | Closed | Inactive | [7 empty] | 2023-01-05 13:38
PBIT02 - IT OT Cybersecur. Prog. |  |  | 10042 | 10042 | 14N000300000 | PBIT2 Network Sec Architecture | Closed | Inactive | [7 empty] | 2023-01-05 13:38
PBIT02 - IT OT Cybersecur. Prog. |  |  | 10042 | 10042 | 14N000950000 | Compliance Mngmnt | Inactive | Inactive | [7 empty] | 2023-01-05 13:38
PBIT02 - IT OT Cybersecur. Prog. |  |  | 10042 | 10042 | 14N000960000 | Data Loss Prevention DLP | Inactive | Inactive | [7 empty] | 2023-01-05 13:38
PBIT02 - IT OT Cybersecur. Prog. |  |  | 10042 | 10042 | 14N000970000 | Endpoint Image Mngmnt | Cancel | Inactive | [7 empty] | 2023-01-05 13:38
PBIT02 - IT OT Cybersecur. Prog. |  |  | 10042 | 10042 | 14N000980000 | Network Segmentation | Cancel | Inactive | [7 empty] | 2023-01-05 13:38
PBIT02 - IT OT Cybersecur. Prog. |  |  | 10042 | 10042 | 14N000990000 | Vuln Mngmt&Scan(OT Devs-SCADA) | Inactive | Inactive | [7 empty] | 2023-01-05 13:38
PBIT02 - IT OT Cybersecur. Prog. |  |  | 10042 | 10042 | 14N001000000 | Unstructured Data Protection | Cancel | Inactive | [7 empty] | 2023-01-05 13:38
PBIT02 - IT OT Cybersecur. Prog. |  |  | 10042 | 10042 | 14N001130000 | Unstruc.DataProtec.&Classif. | Inactive | Inactive | [7 empty] | 2023-01-05 13:38
PBIT02 - IT OT Cybersecur. Prog. |  |  | 10042 | 10042 | 14N001140000 | NetworkOptimization&Reliabilit | Inactive | Inactive | [7 empty] | 2023-01-05 13:38
PBIT02 - IT OT Cybersecur. Prog. |  |  | 10042 | 10042 | 14N001150000 | Network Switches Edge | Inactive | Inactive | [7 empty] | 2023-01-05 13:38
PBIT02 - IT OT Cybersecur. Prog. |  |  | 10042 | 10042 | 15N000560000 | OT Firewalls - OPEX | Cancel | Inactive | [7 empty] | 2023-01-05 13:38
PBIT02 - IT OT Cybersecur. Prog. |  |  | 10042 | 10042 | 15N000570000 | PAM - Privil Access Mang OPEX | Cancel | Inactive | [7 empty] | 2023-01-05 13:38
PBIT02 - IT OT Cybersecur. Prog. |  |  | 10042 | 10042 | 15N000580000 | MFA Multi-Factor Authent OPEX | Cancel | Inactive | [7 empty] | 2023-01-05 13:38
PBIT02 - IT OT Cybersecur. Prog. |  |  | 10042 | 10042 | 15N000700000 | PBIT2 Cybersecurity OPEX | Inactive | Inactive | [7 empty] | 2023-01-05 13:38
PBIT02 - IT OT Cybersecur. Prog. |  |  | 10042 | 10042 | 15N003040000 | Maturity Assessment | Cancel | Inactive | [7 empty] | 2023-01-05 13:38
PBIT02 - IT OT Cybersecur. Prog. |  |  | 10042 | 10042 | 15N003050000 | Network Vulnerability Assessmt | Cancel | Inactive | [7 empty] | 2023-01-05 13:38
PBIT02 - IT OT Cybersecur. Prog. |  |  | 10042 | 10042 | 15N003060000 | Privilege Access Management | Inactive | Inactive | [7 empty] | 2023-01-05 13:38
PBIT02 - IT OT Cybersecur. Prog. |  |  | 10042 | 10042 | 15N003310000 | Forensic & Consulting Hours | Active | Inactive | [7 empty] | 2023-01-05 13:38
PBIT03 - IT OT Enablement Progr. |  |  | 10144 | 10144 | 10N000010000 | Workday Hypercare (L) | Inactive
PBIT03 - IT OT Enablement Progr. |  |  | 10144 | 10144 | 10N000020000 | EBS Hypercare (L) | Inactive
PBIT03 - IT OT Enablement Progr. |  |  | 10144 | 10144 | 10N000030000 | Kronos Hypercare (L) | Inactive
PBIT03 - IT OT Enablement Progr. |  |  | 60004 | 60004 | 10N000220000 | End User Device Management | Inactive
PBIT03 - IT OT Enablement Progr. |  |  | 60004 | 60004 | 15N000740000 | End User Device Managem | Active
PBIT03 - IT OT Enablement Progr. |  |  | 60004 | 60004 | 15N000750000 | Enterp Archi & Proj Manag | Cancel
PBIT03 - IT OT Enablement Progr. |  |  | 60004 | 60004 | 15N000760000 | Service Management | Active
PBIT03 - IT OT Enablement Progr. |  |  | 60004 | 60004 | 15N002340000 | IT Cloud Strategy - OPEX | Inactive
PBIT03 - IT OT Enablement Progr. |  |  | 60004 | 60004 | 15N002350000 | Patch Mgmt Metho - OPEX | Inactive
PBIT03 - IT OT Enablement Progr. |  |  | 60004 | 60004 | 15N007010000 | ITIL4 Foundations & Certific. | Active
PBIT04 - IT OT Asset Management |  |  | 60003 | 60003 | 10F000060000 | Netwk Enhancmts - CAPEX FEMA | Inactive | Active
PBIT04 - IT OT Asset Management |  |  | 60003 | 60003 | 10F000070000 | SDWAN Ntwrk Intg-CAPEX FEMA | Inactive | Active
PBIT04 - IT OT Asset Management |  |  | 60003 | 60003 | 10F000080000 | PBX Replcmnt - CAPEX FEMA | Inactive | Active
PBIT04 - IT OT Asset Management |  |  | 60006 | 60006 | 10F000120000 | Informational Technology | Inactive | Active
PBIT04 - IT OT Asset Management |  |  | 60006 | 60006 | 10F000130000 | Operational Technology (Capex) | Inactive | Active
PBIT04 - IT OT Asset Management |  |  | 60006 | 60006 | 10F000190000 | Mass Storage&Backup Appliances | Inactive | Active
PBIT04 - IT OT Asset Management |  |  | 60006 | 60006 | 10F000200000 | DR(IT)Syst Mig to Cloud-FEMA | Cancel | Active
PBIT04 - IT OT Asset Management |  |  | 60006 | 60006 | 10F000340000 | HW Upg legacy equip-CPEX FEMA | Inactive | Active
PBIT04 - IT OT Asset Management |  |  | 60006 | 60006 | 10F000350000 | TelCom Dev IT sensor-CAP FEMA | Inactive | Active
PBIT04 - IT OT Asset Management |  |  | 60003 | 60003 | 10F000360000 | WiFi 6 Integration- CAPEX | Inactive | Active
PBIT04 - IT OT Asset Management |  |  | 60003 | 60003 | 10F000370000 | GPS Clock install - CAPEX FEMA | Inactive | Active
PBIT04 - IT OT Asset Management |  |  | 60006 | 60006 | 10F000380000 | Situational Awrness CAPEX FEMA | Inactive | Active
PBIT04 - IT OT Asset Management |  |  | 60006 | 60006 | 10F000390000 | Ntwk Prof OMS CAPEX FEMA | Inactive | Active
PBIT04 - IT OT Asset Management |  |  | 60006 | 60006 | 10F000400000 | Map Mgtion-Gtch OMS CPEX FMA | Inactive | Active
PBIT04 - IT OT Asset Management |  |  | 60006 | 60006 | 10F000410000 | Cyber Sec System CAPEX FEMA | Inactive | Active
PBIT04 - IT OT Asset Management |  |  | 60006 | 60006 | 10F000450000 | WFMS Intermediate Comms | Inactive | Active
PBIT04 - IT OT Asset Management |  |  | 60006 | 60006 | 10N000360000 | DR (IT) Facility Relocation | Cancel | Active
PBIT04 - IT OT Asset Management |  |  | 60006 | 60006 | 10N000430000 | Applic. Modernization Roadmap | Inactive | Active
PBIT04 - IT OT Asset Management |  |  | 60006 | 60006 | 10N000440000 | TelecomDeviceMgmtConsol&Integr | Inactive | Active
PBIT04 - IT OT Asset Management |  |  | 60006 | 60006 | 10N000450000 | IT Test& DevMigration to Cloud | Cancel | Active
PBIT04 - IT OT Asset Management |  |  | 60006 | 60006 | 10N000460000 | DR(IT)SYST MIG2CLOUD-NONFEMA | Cancel | Active
PBIT04 - IT OT Asset Management |  |  | 60006 | 60006 | 10N005550000 | Situational Awareness | Closed | Active
PBIT04 - IT OT Asset Management |  |  | 60006 | 60006 | 10N008890000 | Executive Conference Systems | Inactive | Active
PBIT04 - IT OT Asset Management |  |  | 60006 | 60006 | 14F003610000 | DR (IT) Facility Reloc FEMA | Inactive | Active
PBIT04 - IT OT Asset Management |  |  | 10158 | 10158 | 14N000250000 | DR (IT) Facility Reloc NME | Cancel
PBIT04 - IT OT Asset Management |  |  | 60006 | 60006 | 14N000470000 | Operational Technology(Capex) | Inactive | Active
PBIT04 - IT OT Asset Management |  |  | 60006 | 60006 | 14N000670000 | IT ProductionMigration toCloud | Inactive | Active
PBIT04 - IT OT Asset Management |  |  | 60006 | 60006 | 14N001370000 | Workforce Management System | Active | Active
PBIT04 - IT OT Asset Management |  |  | 60006 | 60006 | 14N001390000 | Hardware Legacy Replacement | Active | Active
PBIT04 - IT OT Asset Management |  |  | 60006 | 60006 | 14N001400000 | OSI PI Hardware | Inactive | Active
PBIT04 - IT OT Asset Management | 1294 | 83182 | 90102 | 90102 | 15F019760000 | CAT Z - PBIT4 | Inactive |  |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  |  | 2020-02-05 12:48
PBIT04 - IT OT Asset Management |  |  | 60003 | 60003 | 15N000730000 | Netwk Enhancmts - OPEX | Active | Active
PBIT04 - IT OT Asset Management |  |  | 60006 | 60006 | 15N000970000 | Informational Technology (O&M) | Inactive | Active
PBIT04 - IT OT Asset Management |  |  | 60006 | 60006 | 15N000980000 | Operational Technology | Inactive | Active
PBIT04 - IT OT Asset Management |  |  | 60006 | 60006 | 15N002120000 | WFMS InterCommsTech-ITOPS6 | Active | Active
PBIT04 - IT OT Asset Management |  |  | 60006 | 60006 | 15N002130000 | Cyb.SecSysCIPSeglic.planITOPS2 | Inactive | Active
PBIT04 - IT OT Asset Management |  |  | 60006 | 60006 | 15N002140000 | Networks Profess (OMS)-ITOPS4 | Active | Active
PBIT04 - IT OT Asset Management |  |  | 60006 | 60006 | 15N002310000 | IT Prod Migtion to Cloud-OPEX | Cancel | Active
PBIT04 - IT OT Asset Management |  |  | 60006 | 60006 | 15N002320000 | Mass Storage & Bkp appl - OPEX | Inactive | Active
PBIT04 - IT OT Asset Management |  |  | 60006 | 60006 | 15N002330000 | HW Upg legacy equip - OPEX | Cancel | Active
PBIT04 - IT OT Asset Management |  |  | 60003 | 60003 | 15N002360000 | WiFi 6 Integration- OPEX | Cancel | Active
PBIT04 - IT OT Asset Management |  |  | 60003 | 60003 | 15N002370000 | PBX Replcmnt - OPEX | Cancel | Active
PBIT04 - IT OT Asset Management |  |  | 60003 | 60003 | 15N002380000 | SDWAN Ntw Integration OPEX | Inactive | Active
PBIT04 - IT OT Asset Management |  |  | 60006 | 60006 | 15N002390000 | Telecom Device IT sensor-OPEX | Active | Active
PBIT04 - IT OT Asset Management |  |  | 60006 | 60006 | 15N006650000 | DRC Temporary Relocation | Inactive | Active
PBIT05 - IT OT Collab.& Analytic |  |  | 60005 | 60005 | 10N000230000 | IT OT Collaboration | Inactive
PBIT05 - IT OT Collab.& Analytic |  |  | 60005 | 60005 | 10N000240000 | IT OT Analytics. | Inactive
PBIT05 - IT OT Collab.& Analytic |  |  | 60005 | 60005 | 10N005070000 | Business Intelligence & Report | Inactive
PBIT05 - IT OT Collab.& Analytic |  |  | 60005 | 60005 | 15N000770000 | IT OT Analytics | Inactive
PBOP01 - T&D Fleet |  |  | 70000 | 70000 | 10F000090000 | OPFLT10 FleetShopToolEq(Small) | Inactive
PBOP01 - T&D Fleet |  |  | 90008 | 90008 | 10N000590000 | Fleet Telematics | Inactive
PBOP01 - T&D Fleet |  |  | 70000 | 70000 | 14F003650000 | OPFLT15 Fuel Tank Fleet Shop | Cancel
PBOP01 - T&D Fleet |  |  | 90008 | 90008 | 14N000240000 | Fleet Capital Vehicle Purch. | Active
PBOP01 - T&D Fleet |  |  | 70000 | 70000 | 14N000310000 | OPFLT10 FleetShopToolEq(Large) | Cancel
PBOP01 - T&D Fleet |  |  | 90109 | 90109 | 14N001540000 | Helicopter Capital Repairs | Active
PBOP01 - T&D Fleet | 1294 | 83182 | 90102 | 90102 | 15F019600000 | CAT Z - PBOP1 | Inactive |  |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  |  | 2020-02-05 12:48
PBOP01 - T&D Fleet |  |  | 70000 | 70000 | 15N000900000 | PBOP1 O&M | Active
PBOP03 - Workflow Proc & Track. |  |  | 90028 | 90028 | 15N000920000 | PBOP3 O&M | Inactive
PBOP03 - Workflow Proc & Track. |  |  | 90028 | 90028 | 15N005460000 | Oper Dispatch Outbound Camp | Active
PBOP03 - Workflow Proc & Track. |  |  | 90028 | 90028 | 15N005470000 | Operations Contract ICE | Active
PBOP05 - Tools Repair & Mgmt |  |  | 70002 | 70002 | 14N000330000 | Tools Repair & Management | Active
PBOP05 - Tools Repair & Mgmt |  |  | 40017 | 40017 | 14N000930000 | Operations Tools&Equip-Substat | Active
PBOP05 - Tools Repair & Mgmt |  |  | 70003 | 70003 | 14N000940000 | Tool Crib | Active
PBOP05 - Tools Repair & Mgmt |  |  | 70002 | 70002 | 15N001870000 | TOOL CRIB OPERATIONS | Cancel
PBOP06 - Material Management |  |  | 70001 | 70001 | 10F000100000 | OPMAT8 Fed WOilFiEqOilC(Small) | Inactive
PBOP06 - Material Management |  |  | 70001 | 70001 | 10F000110000 | OPMAT16 Fed-WarFacImpr CapPlan | Inactive
PBOP06 - Material Management | 10710 | 673691 | 90051 | 90051 | 14F008760000 | Long Lead Mat-Mat Handling | Active |  |  |  | Active | Phase 5 - Post Award Phase | Pending Large Project Review |  |  |  |  | 2022-06-10 11:48
PBOP06 - Material Management |  |  | 70001 | 70001 | 14N000320000 | OPMAT8 NME WOilFiEqOilC(Large) | Inactive
PBOP06 - Material Management |  |  | 70001 | 70001 | 14N000780000 | TAShelix Mobile Platf.Implem. | Inactive
PBOP06 - Material Management | 1294 | 83182 | 90102 | 90102 | 15F019730000 | CAT Z - PBOP6 | Active |  |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  |  | 2020-02-05 12:48
PBOP06 - Material Management |  |  | 70001 | 70001 | 15N000940000 | PBOP6 O&M | Inactive
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 107940 | 741097 | 11000 | 11000 | 14F019290000 | Vgtn - SJ - Substations/Tlcom | Cancel | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2024-09-06 08:00 | 2024-09-06 08:00 | 2023-07-18 17:00 | 2023-12-19
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 11696 | 723883 | 11000 | 11000 | 14F019300000 | Vegetation - San Juan-Group A | Inactive | Inactive |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2024-09-06 08:00 | 2024-09-06 08:00 | 2023-07-18 17:00 | 2023-07-18 | 2024-06-05 11:15
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 107899 | 727608 | 11000 | 11000 | 14F019310000 | Vegetation - San Juan - 115kV | Inactive | Inactive |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2024-09-06 08:00 | 2024-09-06 08:00 | 2023-07-18 17:00 | 2023-07-31 | 2026-03-01 18:16
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 107933 | 740406 | 11000 | 11000 | 14F019320000 | Vegetation - SJ - Group B | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2024-09-06 08:00 | 2024-09-06 08:00 | 2023-07-18 17:00 | 2023-12-11
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 107902 | 727691 | 11000 | 11000 | 14F019330000 | Vegetation - SJ - Group C | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2024-09-06 08:00 | 2024-09-06 08:00 | 2023-07-18 17:00 | 2023-07-31
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 107945 | 741104 | 11000 | 11000 | 14F019340000 | Vegetation-Ponce-Substatn/Tele | Cancel | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2024-09-06 08:00 | 2024-09-06 08:00 | 2023-07-18 17:00 | 2023-12-18
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 11715 | 727531 |  |  | 14F019350000 | Vegetation - Ponce - Group A | Inactive |  |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  | 2023-08-03 | 2025-04-28 19:15
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 107893 | 727529 | 11000 | 11000 | 14F019360000 | Vegetation - Ponce - 115kV | Cancel | Inactive |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2024-09-06 08:00 | 2024-09-06 08:00 | 2023-07-18 17:00 | 2023-07-31 | 2026-03-01 18:15
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 107938 | 740414 | 11000 | 11000 | 14F019370000 | Vegetation - Ponce - Group B | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2024-09-06 08:00 | 2024-09-06 08:00 | 2023-07-18 17:00 | 2023-12-19
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 107894 | 727530 | 11000 | 11000 | 14F019380000 | Vegetation - Ponce - Group C | Cancel | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2024-09-06 08:00 | 2024-09-06 08:00 | 2023-07-18 17:00 | 2023-07-31
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 107944 | 741102 | 11000 | 11000 | 14F019390000 | Vegetation-Mayagu-Substn/Tlcom | Cancel | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2024-09-06 08:00 | 2024-09-06 08:00 | 2023-07-18 17:00 | 2023-12-19
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 11718 | 728832 |  |  | 14F019400000 | Vegetation-Mayaguez - Group A | Inactive |  |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  | 2023-08-17 | 2025-04-28 19:15
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 107900 | 727657 | 11000 | 11000 | 14F019410000 | Vegetation - Mayaguez - 115kV | Cancel | Inactive |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2024-09-06 08:00 | 2024-09-06 08:00 | 2023-07-18 17:00 | 2023-07-31 | 2026-03-01 18:16
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 107937 | 740411 | 11000 | 11000 | 14F019420000 | Vegetation - Mayaguez -Group B | Cancel | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2024-09-06 08:00 | 2024-09-06 08:00 | 2023-07-18 17:00 | 2023-12-11
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 107897 | 727562 | 11000 | 11000 | 14F019430000 | Vegetation - Mayaguez-Group C | Cancel | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2024-09-06 08:00 | 2024-09-06 08:00 | 2023-07-18 17:00 | 2023-07-31
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 107942 | 741100 | 11000 | 11000 | 14F019440000 | Vegetation-Caguas-Sbstns/Tlcom | Cancel | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2024-09-06 08:00 | 2024-09-06 08:00 | 2023-07-18 17:00 | 2023-12-19
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 11724 | 727692 |  |  | 14F019450000 | Vegetation - Caguas - Group A | Inactive |  |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  | 2023-08-04 | 2025-04-28 19:15
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 107898 | 727606 | 11000 | 11000 | 14F019460000 | Vegetation - Caguas - 115kV | Cancel | Inactive |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2024-09-06 08:00 | 2024-09-06 08:00 | 2023-07-18 17:00 | 2023-07-31 | 2026-03-01 18:16
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 107935 | 740409 | 11000 | 11000 | 14F019470000 | Vegetation - Caguas - Group B | Cancel | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2024-09-06 08:00 | 2024-09-06 08:00 | 2023-07-18 17:00 | 2023-12-11
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 107903 | 727694 | 11000 | 11000 | 14F019480000 | Vegetation - Caguas - Group C | Cancel | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2024-09-06 08:00 | 2024-09-06 08:00 | 2023-07-18 17:00 | 2023-07-31
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 107941 | 741098 | 11000 | 11000 | 14F019490000 | Vegetation-Bayamon-Sbstn/Tlcom | Cancel | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2024-09-06 08:00 | 2024-09-06 08:00 | 2023-07-18 17:00 | 2023-12-19
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 11720 | 727572 | 11000 | 11000 | 14F019500000 | Vegetation - Bayamon - Group A | Inactive | Inactive |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2024-09-06 08:00 | 2024-09-06 08:00 | 2023-07-18 17:00 | 2023-08-03 | 2026-03-01 18:15
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 107892 | 727522 | 11000 | 11000 | 14F019510000 | Vegetation - Bayamon - 115kV | Inactive | Inactive |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2024-09-06 08:00 | 2024-09-06 08:00 | 2023-07-18 17:00 | 2023-07-31 | 2026-03-01 18:16
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 107934 | 740408 | 11000 | 11000 | 14F019520000 | Vegetation - Bayamon - Group B | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2024-09-06 08:00 | 2024-09-06 08:00 | 2023-07-18 17:00 | 2023-12-11
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 107896 | 727558 | 11000 | 11000 | 14F019530000 | Vegetation - Bayamon - Group C | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2024-09-06 08:00 | 2024-09-06 08:00 | 2023-07-18 17:00 | 2023-07-31
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 107943 | 741101 | 11000 | 11000 | 14F019540000 | Vegetation-Arecibo-Sbstn/Tlcom | Cancel | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2024-09-06 08:00 | 2024-09-06 08:00 | 2023-07-18 17:00 | 2023-12-19
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 11714 | 728827 |  |  | 14F019550000 | Vegetation - Arecibo - Group A | Inactive |  |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  | 2023-08-17 | 2025-04-28 19:15
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 107901 | 727659 | 11000 | 11000 | 14F019560000 | Vegetation - Arecibo - 115kV | Cancel | Inactive |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2024-09-06 08:00 | 2024-09-06 08:00 | 2023-07-18 17:00 | 2023-07-31 | 2026-03-01 18:16
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 107936 | 740410 | 11000 | 11000 | 14F019570000 | Vegetation - Arecibo - Group B | Cancel | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2024-09-06 08:00 | 2024-09-06 08:00 | 2023-07-18 17:00 | 2023-12-11
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 107895 | 727540 | 11000 | 11000 | 14F019580000 | Vegetation - Arecibo - Group C | Cancel | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2024-09-06 08:00 | 2024-09-06 08:00 | 2023-07-18 17:00 | 2023-07-31
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 107946 | 741105 | 11000 | 11000 | 14F019590000 | Vegetation - All Regions-230kV | Cancel | Inactive |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2024-09-06 08:00 | 2024-09-06 08:00 | 2023-07-18 17:00 | 2023-12-18 | 2026-03-01 18:15
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 11715 | 727531 | 11000-001 | 11000-001 | 15F019850000 | Vgtn - Ponce - Group A (HD) | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2025-03-24 08:00 | 2025-03-24 08:00 | 2023-08-03 17:00 | 2023-08-03 | 2025-04-28 19:15
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 11696 | 723883 | 11000 | 11000 | 15F019300000 | Vegetation -San Juan-Group A | Inactive | Inactive |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2024-09-06 08:00 | 2024-09-06 08:00 | 2023-07-18 17:00 | 2023-07-18 | 2024-06-05 11:15
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 11718 | 728832 | 11000-002 | 11000-002 | 15F019860000 | Vgtn - Mayaguez - Group A (HD) | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2025-01-20 08:00 | 2025-01-20 08:00 | 2023-08-17 17:00 | 2023-08-17 | 2025-04-28 19:15
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 11724 | 727692 | 11000-003 | 11000-003 | 15F019870000 | Vgtn - Caguas - Group A (HD) | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2025-01-10 08:00 | 2025-01-10 08:00 | 2023-08-04 08:00 | 2023-08-04 | 2025-04-28 19:15
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 11720 | 727572 | 11000-004 | 11000-004 | 15F019880000 | Vgtn - Bayamon - Group A (HD) | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2026-03-16 17:00 | 46097.7083 | 2023-08-03 17:00 | 2023-08-03 | 2026-03-01 18:15
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 11714 | 728827 | 11000-005 | 11000-005 | 15F019890000 | Vgtn - Arecibo - Group A (HD) | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2025-01-27 08:00 | 2025-01-27 08:00 | 2023-08-17 17:00 | 2023-08-17 | 2025-04-28 19:15
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 107965 | 750063 | 11000-006 | 11000-006 | 15F019350000 | Vegetation -Ponce - Group A | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Pending Large Project Review | 2026-04-30 17:00 |  | 2024-11-21 17:00 | 2024-11-21
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 107969 | 750068 | 11000-007 | 11000-007 | 15F019400000 | Vegetation-Mayaguez -Group A | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2026-05-01 08:00 |  | 2024-11-21 17:00 | 2024-11-21 | 2026-03-01 18:15
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 107967 | 750066 | 11000-008 | 11000-008 | 15F019450000 | Vegetation -Caguas - Group A | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2026-12-01 17:00 |  | 2024-11-21 17:00 | 2024-11-21 | 2026-03-01 17:15
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 107966 | 750065 | 11000-009 | 11000-009 | 15F019500000 | Vegetation -Bayamon - Group A | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2026-04-13 17:00 |  | 2024-11-21 17:00 | 2024-11-21 | 2026-03-01 18:15
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 107968 | 750067 | 11000-010 | 11000-010 | 15F019550000 | Vegetation -Arecibo - Group A | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2026-04-30 17:00 |  | 2024-11-21 17:00 | 2024-11-21 | 2026-03-01 18:15
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 107933 | 740406 | 11000-011 | 11000-011 | 15F019320000 | Vegetation -SJ - Group B | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2026-07-20 08:00 |  | 2023-12-11 08:00 | 2023-12-11
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 107935 | 740409 | 11000-012 | 11000-012 | 15F019470000 | Vegetation -Caguas - Group B | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2026-07-07 08:00 |  | 2023-12-11 17:00 | 2023-12-11
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 107934 | 740408 | 11000-013 | 11000-013 | 15F019520000 | Vegetation -Bayamon - Group B | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2026-07-15 08:00 |  | 2023-12-11 08:00 | 2023-12-11
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 107937 | 740411 | 11000-014 | 11000-014 | 15F019420000 | Vegetation -Mayaguez -Group B | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2026-08-10 08:00 |  | 2023-12-11 17:00 | 2023-12-11
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 107936 | 740410 | 11000-015 | 11000-015 | 15F019570000 | Vegetation -Arecibo - Group B | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2026-07-13 08:00 |  | 2023-12-11 17:00 | 2023-12-11
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 107938 | 740414 | 11000-016 | 11000-016 | 15F019370000 | Vegetation -Ponce - Group B | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2026-07-07 08:00 |  | 2023-12-11 17:00 | 2023-12-19
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 107902 | 727691 | 11000-017 | 11000-017 | 15F019330000 | Vegetation -SJ - Group C | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2026-04-15 08:00 |  | 2025-07-31 08:00 | 2023-07-31
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 108148 | 956335 | 11000-017 | 11000-017 | 15F019990000 | Vgtn2301-02 Distr.SJGroup C | Active | Inactive |  |  | Active | Phase 4 - Final Field Reviews | Pending EHP Review | 2026-04-15 08:00 |  | 2025-07-31 08:00 | 2025-06-27
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 108147 | 956332 | 11000-017 | 11000-017 | 15F020010000 | Vgtn2401-01Distrib.SJ Group C | Active | Inactive |  |  | Active | Phase 4 - Final Field Reviews | Pending EHP Review | 2026-04-15 08:00 |  | 2025-07-31 08:00 | 2025-06-27
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 107903 | 727694 | 11000-018 | 11000-018 | 15F019480000 | Vegetation -Caguas - Group C | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2026-07-27 08:00 |  | 2023-07-31 08:00 | 2023-07-31
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 108145 | 956330 | 11000-018 | 11000-018 | 15F020020000 | Vgtn3007-03Distr.CaguasGroupC | Active | Inactive |  |  | Active | Phase 5 - Post Award Phase | Pending Large Project Review | 2026-07-27 08:00 |  | 2023-07-31 08:00 | 2025-06-27
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 108150 | 956339 | 11000-018 | 11000-018 | 15F020030000 | Vgtn3301-01 Distr.CaguasGroupC | Active | Inactive |  |  | Active | Phase 5 - Post Award Phase | Pending Large Project Review | 2026-07-27 08:00 |  | 2023-07-31 08:00 | 2025-06-27
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 107896 | 727558 | 11000-019 | 11000-019 | 15F019530000 | Vegetation -Bayamon - Group C | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2026-07-27 08:00 |  | 2023-07-31 08:00 | 2023-07-31
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 107897 | 727562 | 11000-020 | 11000-020 | 15F019430000 | Vegetation -Mayaguez-Group C | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2026-07-27 08:00 |  | 2023-07-31 08:00 | 2023-07-31
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 108149 | 956337 | 11000-020 | 11000-020 | 15F020070000 | Vgtn6012-02 Distr.Mayag.GroupC | Active | Inactive |  |  | Active | Phase 5 - Post Award Phase | Pending Large Project Review | 2026-07-27 08:00 |  | 2023-07-31 08:00 | 2025-06-27
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 108146 | 956331 | 11000-020 | 11000-020 | 15F020080000 | Vgtn6014-02 Distr.Mayag.GroupC | Active | Inactive |  |  | Active | Phase 5 - Post Award Phase | Pending Large Project Review | 2026-07-27 08:00 |  | 2023-07-31 08:00 | 2025-06-27
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 107895 | 727540 | 11000-021 | 11000-021 | 15F019580000 | Vegetation -Arecibo - Group C | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2026-08-03 08:00 |  | 2023-07-31 08:00 | 2023-07-31
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 107894 | 727530 | 11000-022 | 11000-022 | 15F019380000 | Vegetation -Ponce - Group C | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2026-07-27 08:00 |  | 2023-07-31 08:00 | 2023-07-31
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 108151 | 956340 | 11000-022 | 11000-022 | 15F020050000 | Vgtn5602-02 Distr.PonceGroup C | Active | Inactive |  |  | Active | Phase 4 - Final Field Reviews | Pending EHP Review | 2026-07-27 08:00 |  | 2023-07-31 08:00 | 2025-06-27
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 108152 | 956341 | 11000-022 | 11000-022 | 15F020060000 | Vgtn5803-02 Distr.PonceGroup C | Active | Inactive |  |  | Active |  | Pending Award | 2026-07-27 08:00 |  | 2023-07-31 08:00 | 2025-06-27
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 1294 | 83182 | 90102 | 90102 | 15F019620000 | CAT Z - PBOP7 | Active |  |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  |  | 2020-02-05 12:48
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 107899 | 727608 | 11000-023 | 11000-023 | 15F019310000 | Vegetation -San Juan - 115kV | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2026-12-01 17:00 |  | 2023-07-31 08:00 | 2023-07-31 | 2026-03-01 18:16
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 107898 | 727606 | 11000-024 | 11000-024 | 15F019460000 | Vegetation -Caguas - 115kV | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2026-04-13 17:00 |  | 2023-07-31 08:00 | 2023-07-31 | 2026-03-01 18:16
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 107892 | 727522 | 11000-025 | 11000-025 | 15F019510000 | Vegetation -Bayamon - 115kV | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2026-12-01 17:00 |  | 2025-07-31 08:00 | 2023-07-31 | 2026-03-01 18:16
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 107900 | 727657 | 11000-026 | 11000-026 | 15F019410000 | Vegetation -Mayaguez - 115kV | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2026-12-01 17:00 |  | 2023-07-31 08:00 | 2023-07-31 | 2026-03-01 18:16
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 107901 | 727659 | 11000-027 | 11000-027 | 15F019560000 | Vegetation -Arecibo - 115kV | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2026-12-01 17:00 |  | 2023-07-31 08:00 | 2023-07-31 | 2026-03-01 18:16
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 107893 | 727529 | 11000-028 | 11000-028 | 15F019360000 | Vegetation -Ponce - 115kV | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2026-12-01 17:00 |  | 2023-07-31 08:00 | 2023-07-31 | 2026-03-01 18:15
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 107940 | 741097 | 11000-029 | 11000-029 | 15F019290000 | Vgtn -SJ - Substations/Tlcom | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2023-12-19 08:00 | 2023-12-19
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 107942 | 741100 | 11000-030 | 11000-030 | 15F019440000 | Vegetation-Cagua-Sbstns/Tlcom | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2023-12-19 08:00 | 2023-12-19
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 107941 | 741098 | 11000-031 | 11000-031 | 15F019490000 | Vegetation-Bayam-Sbstn/Tlcom | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2023-12-19 08:00 | 2023-12-19
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 107944 | 741102 | 11000-032 | 11000-032 | 15F019390000 | Vegetation-Mayag-Substn/Tlcom | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2023-12-19 17:00 | 2023-12-19
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 107943 | 741101 | 11000-033 | 11000-033 | 15F019540000 | Vegetation-Arecib-Sbstn/Tlcom | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2023-12-19 08:00 | 2023-12-19
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 107945 | 741104 | 11000-034 | 11000-034 | 15F019340000 | Vegetation-Ponce-Substat/Tele | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2023-12-18 08:00 | 2023-12-18
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 107946 | 741105 | 11000-035 | 11000-035 | 15F019590000 | Vegetation -All Regions-230kV | Active | Inactive |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2025-09-01 17:00 | 2023-12-18 | 2026-03-01 18:15
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 108160 | 956357 | 11000-039 | 11000-039 | 15F019980000 | Vgtn1900-38KvDosBocasHPS.SebTC | Active | Active |  |  | Active | Phase 4 - Final Field Reviews | Pending Final FEMA Review | 2026-05-01 08:00 |  | 2025-06-26 17:00 | 2025-06-26
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 108155 | 956345 | 11000-041 | 11000-041 | 15F020000000 | Vgtn2400-38kVDosBocHPtoCoroni2 | Active | Active |  |  | Active |  | Pending Award | 2026-05-01 08:00 |  | 2025-06-26 17:00 | 2025-06-26
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 108154 | 956343 | 11000-045 | 11000-045 | 15F020040000 | Vgtn4800-38kVTNeg.Aib.S.Isabel | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Pending Large Project Review | 2026-05-01 08:00 |  | 2025-06-26 17:00 | 2025-06-26
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 108156 | 956348 | 11000-050 | 11000-050 | 15F020090000 | VgtnLn10000-38kVBayPbloToMgnol | Active | Active |  |  | Active |  | Pending Award | 2026-05-06 08:00 |  | 2025-06-26 17:00 | 2025-06-26
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 108158 | 956353 | 11000-051 | 11000-051 | 15F020100000 | Vgtn115kV-36100D.BocasToBoPina | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2025-12-11 17:00 | 2025-12-11 17:00 | 2025-06-26 17:00 | 2025-06-26 | 2025-09-17 18:16
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 108153 | 956342 | 11000-052 | 11000-052 | 15F020110000 | Vgtn115kv-36400PnceTCtoDBocaHP | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2025-09-18 08:00 | 2025-09-18 08:00 | 2025-06-26 17:00 | 2025-06-26 | 2025-09-17 18:16
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 108157 | 956349 | 11000-053 | 11000-053 | 15F020120000 | Vgtn115kv-36800CanovTCtoPalmTC | Active | Active |  |  | Active | Phase 4 - Final Field Reviews | Pending EHP Review | 2025-11-04 08:00 | 2025-11-04 08:00 | 2025-06-26 17:00 | 2025-06-26 | 2025-09-17 19:15
PBOP07 - Veg.Mngmt&Cap.Clear.Imp | 108159 | 956356 | 11000-054 | 11000-054 | 15F020130000 | Vgtn115kV-39000ABuenSubToHSJos | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2025-10-28 08:00 | 2025-10-28 08:00 | 2025-06-26 17:00 | 2025-06-26 | 2025-09-17 19:15
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 71000 | 71000 | 15N000930000 | OPVEG2 Reclamation T&D Sys ROW | Active
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 71000 | 71000 | 15N001520000 | OPVEG2 Vegetation Maint East | Cancel
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 71000 | 71000 | 15N001530000 | OPVEG2 Vegetation Management | Cancel
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 71000 | 71000 | 15N001540000 | OPVEG2 Finance & Adminstration | Cancel
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 71000 | 71000 | 15N001550000 | OPVEG2 Vegetation Maint West | Cancel
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 31000 | 31000 | 15N002430000 | Caguas - VM Dist Main | Active
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 31000 | 31000 | 15N002440000 | Caguas - VM Dist Main - Foliar | Active
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 31000 | 31000 | 15N002450000 | Caguas - VM Dist Main - Patrol | Inactive
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 31000 | 31000 | 15N002460000 | Caguas - VM Dist Reactive | Active
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 31000 | 31000 | 15N002470000 | Caguas - VM Dist-Inter Req | Active
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 31000 | 31000 | 15N002480000 | Caguas - VM Dist-Exter Req | Active
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 31000 | 31000 | 15N002490000 | Caguas - VM Dist Misc. | Inactive
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 31004 | 31004 | 15N002500000 | Ponce - VM Dist Main | Active
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 31004 | 31004 | 15N002510000 | Ponce - VM Dist Main-Foliar | Active
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 31004 | 31004 | 15N002520000 | Ponce - VM Dist Main-Patrol | Active
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 31004 | 31004 | 15N002530000 | Ponce - VM Dist Reactive | Active
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 31004 | 31004 | 15N002540000 | Ponce - VM Dist-Inter Req | Active
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 31004 | 31004 | 15N002550000 | Ponce - VM Dist-Exter Req | Active
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 31004 | 31004 | 15N002560000 | Ponce - VM Dist Misc. | Inactive
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 31001 | 31001 | 15N002570000 | Arecibo - VM Dist Main | Active
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 31001 | 31001 | 15N002580000 | Arecibo - VM Dist Main-Foliar | Active
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 31001 | 31001 | 15N002590000 | Arecibo - VM Dist Main-Patrol | Active
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 31001 | 31001 | 15N002600000 | Arecibo - VM Dist Reactive | Active
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 31001 | 31001 | 15N002610000 | Arecibo - VM Dist-Inter Req | Active
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 31001 | 31001 | 15N002620000 | Arecibo - VM Dist-Exter Req | Active
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 31001 | 31001 | 15N002630000 | Arecibo - VM Dist Misc. | Active
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 31002 | 31002 | 15N002640000 | Bayamon - VM Dist Main | Active
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 31002 | 31002 | 15N002650000 | Bayamon - VM Dist Main-Foliar | Inactive
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 31002 | 31002 | 15N002660000 | Bayamon - VM Dist Main-Patrol | Inactive
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 31002 | 31002 | 15N002670000 | Bayamon - VM Dist Reactive | Active
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 31002 | 31002 | 15N002680000 | Bayamon - VM Dist-Inter Req | Active
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 31002 | 31002 | 15N002690000 | Bayamon - VM Dist-Exter Req | Active
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 31002 | 31002 | 15N002700000 | Bayamon - VM Dist Misc. | Inactive
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 31003 | 31003 | 15N002710000 | Mayaguez - VM Dist Main | Active
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 31003 | 31003 | 15N002720000 | Mayaguez - VM Dist Main-Foliar | Active
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 31003 | 31003 | 15N002730000 | Mayaguez - VM Dist Main-Patrol | Active
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 31003 | 31003 | 15N002740000 | Mayaguez - VM Dist Reactive | Active
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 31003 | 31003 | 15N002750000 | Mayaguez - VM Dist-Inter Req | Active
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 31003 | 31003 | 15N002760000 | Mayaguez - VM Dist-Exter Req | Active
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 31003 | 31003 | 15N002770000 | Mayaguez - VM Dist Misc. | Active
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 31005 | 31005 | 15N002780000 | San Juan - VM Dist Main | Active
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 31005 | 31005 | 15N002790000 | San Juan - VM Dist Main-Foliar | Active
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 31005 | 31005 | 15N002800000 | San Juan - VM Dist Main-Patrol | Active
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 31005 | 31005 | 15N002810000 | San Juan - VM Dist Reactive | Active
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 31005 | 31005 | 15N002820000 | San Juan - VM Dist-Inter Req | Active
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 31005 | 31005 | 15N002830000 | San Juan - VM Dist-Exter Req | Active
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 31005 | 31005 | 15N002840000 | San Juan - VM Dist Misc. | Active
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 41000 | 41000 | 15N002850000 | Sub - VM Sub Maintenance | Active
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 41000 | 41000 | 15N002860000 | Sub - VM Sub Foliar | Active
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 41000 | 41000 | 15N002870000 | Sub - VM Sub Patrol | Active
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 41000 | 41000 | 15N002880000 | Sub - VM Sub Reactive | Active
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 41000 | 41000 | 15N002890000 | Sub - VM Sub Inter Req | Inactive
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 41000 | 41000 | 15N002900000 | Sub - VM Sub Exter Req | Active
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 41000 | 41000 | 15N002910000 | Sub - VM Sub Misc. | Active
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 21000 | 21000 | 15N002920000 | Trans - VM Trans Main | Active
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 21000 | 21000 | 15N002930000 | Trans - VM Trans Foliar | Active
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 21000 | 21000 | 15N002940000 | Trans - VM Trans Patrol | Active
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 21000 | 21000 | 15N002950000 | Trans - VM Trans Reactive | Active
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 21000 | 21000 | 15N002960000 | Trans - VM Trans Inter Req | Active
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 21000 | 21000 | 15N002970000 | Trans - VM Trans Exter Req | Active
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 21000 | 21000 | 15N002980000 | Trans - VM Trans Misc. | Active
PBOP07 - Veg.Mngmt&Cap.Clear.Imp |  |  | 31006 | 31006 | 15N003430000 | FIONA Vegetation Restoration | Active
PBRE01 - Land&Permit Process&Mgm |  |  | 90022 | 90022 | 15N000800000 | Dev Proc for Land Acquisition | Active
PBRE01 - Land&Permit Process&Mgm |  |  | 90022 | 90022 | 15N000810000 | Develop Proced for Land Admin | Active
PBRE01 - Land&Permit Process&Mgm |  |  | 90022 | 90022 | 15N000820000 | Dev Procd for 3rd Party Cross | Active
PBRE01 - Land&Permit Process&Mgm |  |  | 90022 | 90022 | 15N000830000 | Land Dispute Payments | Active
PBRE01 - Land&Permit Process&Mgm |  |  | 90022 | 90022 | 15N000840000 | Land Dispute Opera/Const | Active
PBRE01 - Land&Permit Process&Mgm |  |  | 90022 | 90022 | 15N000850000 | Land Dispute Encroachments | Active
PBRE01 - Land&Permit Process&Mgm |  |  | 90021 | 90021 | 15N000870000 | Dev Proc for New Permit(CC809) | Active
PBRE01 - Land&Permit Process&Mgm |  |  | 90021 | 90021 | 15N000880000 | Develop Record System-Permits | Inactive
PBRE02 - 3rdP Use Aud. Bill Proc |  |  | 50002 | 50002 | 10N002610000 | TPA Pole Repository Capital | Active
PBRE02 - 3rdP Use Aud. Bill Proc | 1294 | 83182 | 90102 | 90102 | 15F019790000 | CAT Z - PBRE2 | Inactive |  |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  |  | 2020-02-05 12:48
PBRE02 - 3rdP Use Aud. Bill Proc |  |  | 90021 | 90021 | 15N000790000 | Dev Proc for New Permit(CC808) | Inactive
PBRE02 - 3rdP Use Aud. Bill Proc |  |  | 50002 | 50002 | 15N002210000 | Third Party Attach ReposSoftw | Active
PBRE02 - 3rdP Use Aud. Bill Proc |  |  | 50002 | 50002 | 15N002240000 | Accenture Prof Serv Contract | Inactive
PBRE02 - 3rdP Use Aud. Bill Proc |  |  | 50002 | 50002 | 15N004000000 | Third Party Attachment Oper | Active
PBRE02 - 3rdP Use Aud. Bill Proc |  |  | 50002 | 50002 | 15N004010000 | TPA-AeroNet Wireless Broadband | Active
PBRE02 - 3rdP Use Aud. Bill Proc |  |  | 50002 | 50002 | 15N004020000 | TPA-Cosotnet Inc. | Active
PBRE02 - 3rdP Use Aud. Bill Proc |  |  | 50002 | 50002 | 15N004030000 | TPA-Critical Hub Networks Inc | Active
PBRE02 - 3rdP Use Aud. Bill Proc |  |  | 50002 | 50002 | 15N004040000 | TPA-DM Wireless, LLC | Active
PBRE02 - 3rdP Use Aud. Bill Proc |  |  | 50002 | 50002 | 15N004050000 | TPA-HUB Advance Networks,LLC | Active
PBRE02 - 3rdP Use Aud. Bill Proc |  |  | 50002 | 50002 | 15N004060000 | TPA-Liberty Communi Puerto Ric | Active
PBRE02 - 3rdP Use Aud. Bill Proc |  |  | 50002 | 50002 | 15N004070000 | TPA-Liberty Mobile Puerto Rico | Active
PBRE02 - 3rdP Use Aud. Bill Proc |  |  | 50002 | 50002 | 15N004080000 | TPA-Neptunomedia Inc Neptuno N | Active
PBRE02 - 3rdP Use Aud. Bill Proc |  |  | 50002 | 50002 | 15N004090000 | TPA-Netwave Equipment Corporat | Inactive
PBRE02 - 3rdP Use Aud. Bill Proc |  |  | 50002 | 50002 | 15N004100000 | TPA-Osnet Wireless Corporation | Active
PBRE02 - 3rdP Use Aud. Bill Proc |  |  | 50002 | 50002 | 15N004110000 | TPA-PR Telephone Comp Claro PR | Active
PBRE02 - 3rdP Use Aud. Bill Proc |  |  | 50002 | 50002 | 15N004120000 | TPA-WorldNet Telecommunication | Active
PBRE02 - 3rdP Use Aud. Bill Proc |  |  | 50002 | 50002 | 15N006290000 | TPA-VPNet Inc | Active
PBRE02 - 3rdP Use Aud. Bill Proc |  |  | 50003 | 50003 | 15N006570000 | TPA Katapult Pro | Inactive
PBRE02 - 3rdP Use Aud. Bill Proc |  |  | 50002 | 50002 | 15N006720000 | TPA Fiber X Inc | Active
PBRE02 - 3rdP Use Aud. Bill Proc |  |  | 50002 | 50002 | 15N007000000 | TPA, ProFiber, LLC | Active
PBRE02 - 3rdP Use Aud. Bill Proc |  |  | 29000 | 20019-001 | 15N007290000 | DOE UtilityPoleLoadingAbatem. | Inactive
PBRE05 - Land Record Management |  |  | 90023 | 90023 | 10N000580000 | Recor System Land | Active
PBRE05 - Land Record Management |  |  | 90023 | 90023 | 15N000860000 | Record System Land | Inactive
PBRE07 - Electric Veh.Impl.Supp. |  |  | 90007 | 90007 | 15N001690000 | Deploy.Electr.Veh.Charg.Infra. | Active
PBUT01 - Compliance & Studies |  |  | 90012 | 90012 | 10F000480000 | Eng Drawing Management System | Cancel
PBUT01 - Compliance & Studies |  |  | 90012 | 90012 | 10F000510000 | Transmiss Planning-Area Plans | Inactive
PBUT01 - Compliance & Studies |  |  | 90016 | 90016 | 10N000190000 | Pta Lima PPA Interconn Studies | Inactive
PBUT01 - Compliance & Studies |  |  | 90041 | 90041 | 10N000410000 | Project Invest Strat and Road | Cancel
PBUT01 - Compliance & Studies |  |  | 90012 | 90012 | 10N000480000 | Investment Strategy | Inactive
PBUT01 - Compliance & Studies |  |  | 90016 | 90016 | 10N000510000 | Distr.Gen.over25kW direct appl | Inactive
PBUT01 - Compliance & Studies |  |  | 40018 | 40018 | 10N000780000 | Substation Grounding AntiTheft | Inactive
PBUT01 - Compliance & Studies |  |  | 90098 | 90098 | 10N009370000 | Wildfire Mitigation | Active
PBUT01 - Compliance & Studies |  |  | 40001 | 40001 | 14F003250000 | Grounding Program Studies | Inactive | Inactive
PBUT01 - Compliance & Studies |  |  | 90900 | 90900 | 14F003380000 | D Subs Sys Asset Plan & Size | Active | Inactive | [7 empty] | 2022-03-08 17:00
PBUT01 - Compliance & Studies |  |  | 90900 | 90900 | 14F003390000 | Dist Line-Sys Lev Plan & Size | Active | Inactive | [7 empty] | 2022-03-08 17:00
PBUT01 - Compliance & Studies |  |  |  |  | 14F003400000 | T Subs Sys Asset Plan & Size | Active
PBUT01 - Compliance & Studies |  |  | 90900 | 90900 | 14F003410000 | T Line-Sys Lev A. Plan & Size | Active | Inactive | [7 empty] | 2022-03-08 17:00
PBUT01 - Compliance & Studies |  |  | 10160 | 10160 | 14F003780000 | Dist Planning - Area Plans | Active | Inactive
PBUT01 - Compliance & Studies |  |  | 90012 | 90012 | 14F018450000 | Distribu Planning - Area Plans | Cancel
PBUT01 - Compliance & Studies |  |  | 90012 | 90012 | 14N000560000 | DG Interconnect.& Net Metering | Active
PBUT01 - Compliance & Studies |  |  | 90012 | 90012 | 14N000600000 | PSSE Dynamic Data Collection | Inactive
PBUT01 - Compliance & Studies | 1294 | 83182 | 90102 | 90102 | 15F019670000 | CAT Z - PBUT1 | Active |  |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  |  | 2020-02-05 12:48
PBUT01 - Compliance & Studies |  |  | 90005 | 90005 | 15N000200000 | Perform.Metrics Regul.Support | Inactive
PBUT01 - Compliance & Studies |  |  | 90005 | 90005 | 15N000390000 | AM-Ast Stgy: Asset Mgnt Pl-Gen | Inactive
PBUT01 - Compliance & Studies |  |  | 90005 | 90005 | 15N000480000 | AM-Rel Subs Rel Plan Any Rep | Inactive
PBUT01 - Compliance & Studies |  |  | 90005 | 90005 | 15N000520000 | AM-Reliability Perfor Metrics | Inactive
PBUT04 - Grid Automation |  |  | 90012 | 90012 | 10F000050000 | Protection & Control Reposi | Inactive
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F0003590000 | DAUT 5303-01 Ponce | Cancel | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F0003600000 | DAUT 5401-02 Ponce | Cancel | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F0003610000 | DAUT 5401-04 Ponce | Cancel | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F0003620000 | DAUT 5901-03 Ponce | Cancel | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F0003630000 | DAUT 3006-02 Caguas | Cancel | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F0003640000 | DAUT 3202-01 Caguas | Cancel | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F0003650000 | DAUT 3405-03 Caguas | Cancel | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F0003660000 | DAUT 3501-02 Caguas | Cancel | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F0003670000 | DAUT 1529-11 Caguas | Cancel | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F0003680000 | DAUT 1529-13 Caguas | Cancel | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F0003690000 | DAUT 1706-01 Bayamon | Cancel | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F0003700000 | DAUT 9501-02 Bayamon | Cancel | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F0003710000 | DAUT 9501-03 Bayamon | Cancel | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F0003720000 | DAUT 1711-02 Bayamon | Cancel | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F0003730000 | DAUT 1711-03 Bayamon | Cancel | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F0003740000 | DAUT 1901-01 Bayamon | Cancel | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F0003750000 | DAUT 1901-03 Bayamon | Cancel | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F000540000 | DAR 1424-06 | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation | 11839 | 745859 | 30059 | 30059-018 | 10F000550000 | DAR 2001-02 | Active | Inactive |  |  | Active |  | Pending Award | 2024-01-11 08:00 | 2024-01-11 08:00 | 2024-03-29 17:00 | 2024-01-31 | 2024-09-18 15:15
PBUT04 - Grid Automation | 107959 | 746309 | 30059 | 30059-030 | 10F000560000 | DAR 9203-03 | Active | Inactive |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2024-01-11 08:00 | 2024-01-11 08:00 | 2024-11-22 17:00 | 2024-04-01 | 2026-03-01 18:16
PBUT04 - Grid Automation | 107956 | 745856 | 30059 | 30059-014 | 10F000570000 | DAR 8404-03 | Active | Inactive |  |  | Active | Phase 3 - Scoping and Costing | Pending FEMA 406 HMP Completion | 2024-02-14 08:00 | 2024-02-14 08:00 | 2024-01-31 08:00 | 2024-01-31 | 2025-02-06 20:16
PBUT04 - Grid Automation | 107956 | 745856 | 30059 | 30059-014 | 10F000580000 | DAR 8404-04 | Active | Inactive |  |  | Active | Phase 3 - Scoping and Costing | Pending FEMA 406 HMP Completion | 2024-02-14 08:00 | 2024-02-14 08:00 | 2024-01-31 08:00 | 2024-01-31 | 2025-02-06 20:16
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F000590000 | DAR 1716-03 | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F000600000 | DAR 1734-01 | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation | 107957 | 745861 | 30059 | 30059-012 | 10F000610000 | DAUT 7402-01 Arecibo | Active | Inactive |  |  | Active | Phase 2 - Intake & Eligibility | Pending PDMG Scope & Cost Routing | 2024-03-07 08:00 | 2024-03-07 08:00 | 2024-09-04 17:00 | 2024-06-20 | 2025-02-06 20:16
PBUT04 - Grid Automation | 107957 | 745861 | 30059 | 30059-012 | 10F000620000 | DAUT 7403-02 Arecibo | Active | Inactive |  |  | Active | Phase 2 - Intake & Eligibility | Pending PDMG Scope & Cost Routing | 2024-03-07 08:00 | 2024-03-07 08:00 | 2024-09-04 17:00 | 2024-06-20 | 2025-02-06 20:16
PBUT04 - Grid Automation | 107957 | 745861 | 30059 | 30059-012 | 10F000630000 | DAUT 7702-02 Arecibo | Active | Inactive |  |  | Active | Phase 2 - Intake & Eligibility | Pending PDMG Scope & Cost Routing | 2024-03-07 08:00 | 2024-03-07 08:00 | 2024-09-04 17:00 | 2024-06-20 | 2025-02-06 20:16
PBUT04 - Grid Automation | 107957 | 745861 | 30059 | 30059-012 | 10F000640000 | DAUT 7702-03 Arecibo | Active | Inactive |  |  | Active | Phase 2 - Intake & Eligibility | Pending PDMG Scope & Cost Routing | 2024-03-07 08:00 | 2024-03-07 08:00 | 2024-09-04 17:00 | 2024-06-20 | 2025-02-06 20:16
PBUT04 - Grid Automation | 108022 | 755211 | 30059 | 30059-015 | 10F000650000 | DAUT 1646-02 San Juan | Active | Inactive |  |  | Active |  | Pending Award | 2024-06-20 08:00 | 2024-06-20 08:00 | 2025-02-06 17:00 | 2024-09-06 | 2025-02-06 20:16
PBUT04 - Grid Automation | 108000 | 752808 | 30059 | 30059-019 | 10F000660000 | DAUT 8801-01 Arecibo | Active | Inactive |  |  | Active | Phase 4 - Final Field Reviews | Pending EHP Review | 2024-04-04 08:00 | 2024-04-04 08:00 | 2024-09-04 17:00 | 2024-09-04 | 2025-02-06 20:16
PBUT04 - Grid Automation | 108000 | 752808 | 30059 | 30059-019 | 10F000670000 | DAUT 8801-02 Arecibo | Active | Inactive |  |  | Active | Phase 4 - Final Field Reviews | Pending EHP Review | 2024-04-04 08:00 | 2024-04-04 08:00 | 2024-09-04 17:00 | 2024-09-04 | 2025-02-06 20:16
PBUT04 - Grid Automation | 108000 | 752808 | 30059 | 30059-019 | 10F000680000 | DAUT 8801-03 Arecibo | Active | Inactive |  |  | Active | Phase 4 - Final Field Reviews | Pending EHP Review | 2024-04-04 08:00 | 2024-04-04 08:00 | 2024-09-04 17:00 | 2024-09-04 | 2025-02-06 20:16
PBUT04 - Grid Automation | 108033 | 757687 | 30059 | 30059-022 | 10F000690000 | DAUT 3010-01 Caguas | Active | Inactive |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2024-02-22 08:00 | 2024-02-22 08:00 | 2025-01-31 17:00 | 2025-01-31 | 2025-10-30 20:15
PBUT04 - Grid Automation | 108033 | 757687 | 30059 | 30059-022 | 10F000700000 | DAUT 3013-01 Caguas | Active | Inactive |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2024-02-22 08:00 | 2024-02-22 08:00 | 2025-01-31 17:00 | 2025-01-31 | 2025-10-30 20:15
PBUT04 - Grid Automation | 108033 | 757687 | 30059 | 30059-022 | 10F000710000 | DAUT 3013-02 Caguas | Active | Inactive |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2024-02-22 08:00 | 2024-02-22 08:00 | 2025-01-31 17:00 | 2025-01-31 | 2025-10-30 20:15
PBUT04 - Grid Automation | 108033 | 757687 | 30059 | 30059-022 | 10F000720000 | DAUT 3013-03 Caguas | Active | Inactive |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2024-02-22 08:00 | 2024-02-22 08:00 | 2025-01-31 17:00 | 2025-01-31 | 2025-10-30 20:15
PBUT04 - Grid Automation | 108035 | 757692 | 30059 | 30059-026 | 10F000730000 | DAUT 9004-08 Arecibo | Active | Inactive |  |  | Active | Phase 2 - Intake & Eligibility | Pending PDMG Scope & Cost Routing | 2024-08-16 08:00 | 2024-08-16 08:00 | 2025-01-31 08:00 | 2025-01-31 | 2025-09-03 20:15
PBUT04 - Grid Automation | 108037 | 757696 | 30059 | 30059-031 | 10F000740000 | DAUT 1803-03 Bayamon | Active | Inactive |  |  | Active | Phase 2 - Intake & Eligibility | Pending PDMG Scope & Cost Routing | 2023-12-21 08:00 | 2023-12-21 08:00 | 2025-01-31 17:00 | 2025-01-31 | 2025-09-17 19:15
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F000750000 | DAUT 1806-01 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F000760000 | DAUT 1806-02 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation | 108037 | 757696 | 30059 | 30059-031 | 10F000770000 | DAUT 1806-03 Bayamon | Active | Inactive |  |  | Active | Phase 2 - Intake & Eligibility | Pending PDMG Scope & Cost Routing | 2023-12-21 08:00 | 2023-12-21 08:00 | 2025-01-31 17:00 | 2025-01-31 | 2025-09-17 19:15
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F000780000 | DAUT 1716-03 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F000790000 | DAUT 1734-01 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F000800000 | DAUT 1710-01 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F000810000 | DAUT 1710-03 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F000820000 | DAUT 1710-04 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F000830000 | DAUT 1710-05 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation | 108039 | 757698 | 30059 | 30059-033 | 10F000840000 | DAUT 1711-01 Bayamon | Active | Inactive |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2023-11-22 08:00 | 2023-11-22 08:00 | 2025-03-11 17:00 | 2025-03-11 | 2025-09-25 17:15
PBUT04 - Grid Automation | 108039 | 757698 | 30059 | 30059-033 | 10F000850000 | DAUT 1711-04 Bayamon | Active | Inactive |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2023-11-22 08:00 | 2023-11-22 08:00 | 2025-03-11 17:00 | 2025-03-11 | 2025-09-25 17:15
PBUT04 - Grid Automation | 108039 | 757698 | 30059 | 30059-033 | 10F000860000 | DAUT 1713-03 Bayamon | Active | Inactive |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2023-11-22 08:00 | 2023-11-22 08:00 | 2025-03-11 17:00 | 2025-03-11 | 2025-09-25 17:15
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F000870000 | DAUT 1714-02 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F000880000 | DAUT 1706-02 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F000890000 | DAUT 1708-03 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F000900000 | DAUT 1708-05 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation | 108041 | 757700 | 30059 | 30059-035 | 10F000910000 | DAUT 1909-07 Bayamon | Active | Inactive |  |  | Active | Phase 3 - Scoping and Costing | Pending FEMA 406 HMP Completion | 2023-11-20 08:00 | 2023-11-20 08:00 | 2025-03-11 17:00 | 2025-03-11 | 2025-09-17 19:15
PBUT04 - Grid Automation | 108041 | 757700 | 30059 | 30059-035 | 10F000920000 | DAUT 1909-08 Bayamon | Active | Inactive |  |  | Active | Phase 3 - Scoping and Costing | Pending FEMA 406 HMP Completion | 2023-11-20 08:00 | 2023-11-20 08:00 | 2025-03-11 17:00 | 2025-03-11 | 2025-09-17 19:15
PBUT04 - Grid Automation | 108041 | 757700 | 30059 | 30059-035 | 10F000930000 | DAUT 1909-09 Bayamon | Active | Inactive |  |  | Active | Phase 3 - Scoping and Costing | Pending FEMA 406 HMP Completion | 2023-11-20 08:00 | 2023-11-20 08:00 | 2025-03-11 17:00 | 2025-03-11 | 2025-09-17 19:15
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F000940000 | DAUT 8701-01 Arecibo | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation | 108079 | 800369 | 30059 | 30059-038 | 10F000950000 | DAUT 8701-02 Arecibo | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued
PBUT04 - Grid Automation | 108079 | 800369 | 30059 | 30059-038 | 10F000960000 | DAUT 8701-03 Arecibo | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued
PBUT04 - Grid Automation | 108079 | 800369 | 30059 | 30059-038 | 10F000970000 | DAUT 9001-01 Arecibo | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F000980000 | DAUT 2603-09 Caguas | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F000990000 | DAUT 2801-03 Caguas | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001000000 | DAUT 2803-01 Caguas | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001010000 | DAUT 2803-03 Caguas | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001020000 | DAUT 8010-01 Arecibo | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001030000 | DAUT 8010-03 Arecibo | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001040000 | DAUT 8013-01 Arecibo | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001050000 | DAUT 8013-02 Arecibo | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001060000 | DAUT 8015-08 Arecibo | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation | 108001 | 752810 | 30059 | 30059-020 | 10F001070000 | DAUT 2601-01 Caguas | Active | Inactive |  |  | Active | Phase 2 - Intake & Eligibility | Pending PDMG Scope & Cost Routing | 2024-02-15 08:00 | 2024-02-15 08:00 | 2024-09-04 17:00 | 2024-09-04 | 2025-02-06 20:16
PBUT04 - Grid Automation | 108001 | 752810 | 30059 | 30059-020 | 10F001080000 | DAUT 2601-03 Caguas | Active | Inactive |  |  | Active | Phase 2 - Intake & Eligibility | Pending PDMG Scope & Cost Routing | 2024-02-15 08:00 | 2024-02-15 08:00 | 2024-09-04 17:00 | 2024-09-04 | 2025-02-06 20:16
PBUT04 - Grid Automation | 108001 | 752810 | 30059 | 30059-020 | 10F001090000 | DAUT 2602-02 Caguas | Active | Inactive |  |  | Active | Phase 2 - Intake & Eligibility | Pending PDMG Scope & Cost Routing | 2024-02-15 08:00 | 2024-02-15 08:00 | 2024-09-04 17:00 | 2024-09-04 | 2025-02-06 20:16
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001100000 | DAUT 2602-03 Caguas | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001110000 | DAUT 2701-03 Caguas | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation | 108001 | 752810 | 30059 | 30059-020 | 10F001120000 | DAUT 2702-01 Caguas | Active | Inactive |  |  | Active | Phase 2 - Intake & Eligibility | Pending PDMG Scope & Cost Routing | 2024-02-15 08:00 | 2024-02-15 08:00 | 2024-09-04 17:00 | 2024-09-04 | 2025-02-06 20:16
PBUT04 - Grid Automation | 108032 | 757662 | 30059 | 30059-021 | 10F001130000 | DAUT 2901-01 Caguas | Active | Inactive |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2024-02-15 08:00 | 2024-02-15 08:00 | 2025-01-31 17:00 | 2025-01-31 | 2025-10-30 20:15
PBUT04 - Grid Automation | 108032 | 757662 | 30059 | 30059-021 | 10F001140000 | DAUT 2901-02 Caguas | Active | Inactive |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2024-02-15 08:00 | 2024-02-15 08:00 | 2025-01-31 17:00 | 2025-01-31 | 2025-10-30 20:15
PBUT04 - Grid Automation | 108032 | 757662 | 30059 | 30059-021 | 10F001150000 | DAUT 2901-03 Caguas | Active | Inactive |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2024-02-15 08:00 | 2024-02-15 08:00 | 2025-01-31 17:00 | 2025-01-31 | 2025-10-30 20:15
PBUT04 - Grid Automation | 108032 | 757662 | 30059 | 30059-021 | 10F001160000 | DAUT 2901-04 Caguas | Active | Inactive |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2024-02-15 08:00 | 2024-02-15 08:00 | 2025-01-31 17:00 | 2025-01-31 | 2025-10-30 20:15
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001170000 | DAUT 3006-03 Caguas | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001180000 | DAUT 3006-05 Caguas | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001190000 | DAUT 3405-01 Caguas | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation | 108034 | 757689 | 30059 | 30059-024 | 10F001200000 | DAUT 3405-02 Caguas | Active | Inactive |  |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval | 2024-03-15 08:00 | 2024-03-15 08:00 | 2025-01-31 08:00 | 2025-01-31 | 2025-09-17 19:15
PBUT04 - Grid Automation | 108034 | 757689 | 30059 | 30059-024 | 10F001210000 | DAUT 3501-01 Caguas | Active | Inactive |  |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval | 2024-03-15 08:00 | 2024-03-15 08:00 | 2025-01-31 08:00 | 2025-01-31 | 2025-09-17 19:15
PBUT04 - Grid Automation | 108034 | 757689 | 30059 | 30059-024 | 10F001220000 | DAUT 3501-03 Caguas | Active | Inactive |  |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval | 2024-03-15 08:00 | 2024-03-15 08:00 | 2025-01-31 08:00 | 2025-01-31 | 2025-09-17 19:15
PBUT04 - Grid Automation | 108036 | 757694 | 30059 | 30059-027 | 10F001230000 | DAUT 9101-03 Arecibo | Active | Inactive |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2024-04-05 08:00 | 2024-04-05 08:00 | 2025-01-31 17:00 | 2025-01-31 | 2025-09-25 16:16
PBUT04 - Grid Automation | 108036 | 757694 | 30059 | 30059-027 | 10F001240000 | DAUT 9101-04 Arecibo | Active | Inactive |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2024-04-05 08:00 | 2024-04-05 08:00 | 2025-01-31 17:00 | 2025-01-31 | 2025-09-25 16:16
PBUT04 - Grid Automation | 108036 | 757694 | 30059 | 30059-027 | 10F001250000 | DAUT 9105-06 Arecibo | Active | Inactive |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2024-04-05 08:00 | 2024-04-05 08:00 | 2025-01-31 17:00 | 2025-01-31 | 2025-09-25 16:16
PBUT04 - Grid Automation | 108036 | 757694 | 30059 | 30059-027 | 10F001260000 | DAUT 9201-02 Arecibo | Active | Inactive |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2024-04-05 08:00 | 2024-04-05 08:00 | 2025-01-31 17:00 | 2025-01-31 | 2025-09-25 16:16
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001270000 | DAUT 9501-01 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001280000 | DAUT 9502-03 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation | 108038 | 757697 | 30059 | 30059-032 | 10F001290000 | DAUT 8005-01 Arecibo | Active | Inactive |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2024-03-21 08:00 | 2024-03-21 08:00 | 2025-01-31 17:00 | 2025-01-31 | 2025-09-25 17:15
PBUT04 - Grid Automation | 108038 | 757697 | 30059 | 30059-032 | 10F001300000 | DAUT 8101-02 Arecibo | Active | Inactive |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2024-03-21 08:00 | 2024-03-21 08:00 | 2025-01-31 17:00 | 2025-01-31 | 2025-09-25 17:15
PBUT04 - Grid Automation | 108038 | 757697 | 30059 | 30059-032 | 10F001310000 | DAUT 8101-03 Arecibo | Active | Inactive |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2024-03-21 08:00 | 2024-03-21 08:00 | 2025-01-31 17:00 | 2025-01-31 | 2025-09-25 17:15
PBUT04 - Grid Automation | 108038 | 757697 | 30059 | 30059-032 | 10F001320000 | DAUT 8103-01 Arecibo | Active | Inactive |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2024-03-21 08:00 | 2024-03-21 08:00 | 2025-01-31 17:00 | 2025-01-31 | 2025-09-25 17:15
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001330000 | DAUT 8103-02 Arecibo | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001340000 | DAUT 8202-02 Arecibo | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation | 108080 | 800394 | 30059 | 30059-039 | 10F001350000 | DAUT 4601-01 Ponce | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001360000 | DAUT 5011-03 Ponce | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001370000 | DAUT 5013-01 Ponce | Active | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001380000 | DAUT 5013-02 Ponce | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001390000 | DAUT 5013-03 Ponce | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001400000 | DAUT 5016-01 Ponce | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001410000 | DAUT 5016-02 Ponce | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation | 108081 | 800399 | 30059 | 30059-040 | 10F001420000 | DAUT 5018-01 Ponce | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001430000 | DAUT 5018-02 Ponce | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001440000 | DAUT 5018-03 Ponce | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001450000 | DAUT 5018-04 Ponce | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation | 108081 | 800399 | 30059 | 30059-040 | 10F001460000 | DAUT 5019-01 Ponce | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001470000 | DAUT 3601-01 Caguas | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation | 108089 | 801441 | 30059 | 30059-045 | 10F001480000 | DAUT 3601-02 Caguas | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued
PBUT04 - Grid Automation | 108089 | 801441 | 30059 | 30059-045 | 10F001490000 | DAUT 3601-03 Caguas | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued
PBUT04 - Grid Automation | 108089 | 801441 | 30059 | 30059-045 | 10F001500000 | DAUT 3601-04 Caguas | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001510000 | DAUT 3602-01 Caguas | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001520000 | DAUT 3602-02 Caguas | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001530000 | DAUT 3604-06 Caguas | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001540000 | DAUT 3604-07 Caguas | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation | 108078 | 800361 | 30059 | 30059-037 | 10F001550000 | DAUT 3701-02 Caguas | Active | Inactive |  |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval | 2024-03-28 08:00 | 2024-03-28 08:00 | 2025-04-28 17:00 | 2025-04-28 | 2025-09-17 19:15
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001560000 | DAUT 3701-04 Caguas | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001570000 | DAUT 3301-02 Caguas | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001580000 | DAUT 3205-09 Caguas | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001590000 | DAUT 3401-01 Caguas | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001600000 | DAUT 1705-01 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001610000 | DAUT 1705-02 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001620000 | DAUT 1705-05 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001630000 | DAUT 4101-03 Ponce | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001640000 | DAUT 3010-03 Caguas | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001650000 | DAUT 1706-03 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001660000 | DAUT 1204-02 San Juan | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001670000 | DAUT 1204-04 San Juan | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001680000 | DAUT 1204-05 San Juan | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001690000 | DAUT 1346-02 San Juan | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001700000 | DAUT 1346-03 San Juan | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001710000 | DAUT 1343-05 San Juan | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001720000 | DAUT 1437-03 San Juan | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001730000 | DAUT 1437-05 San Juan | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001740000 | DAUT 1525-04 San Juan | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059-007 | 10F001750000 | DAUT 1709-02 Bayamon | Inactive | Inactive
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001760000 | DAUT 1709-03 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059-007 | 10F001770000 | DAUT 1709-05 Bayamon | Inactive | Inactive
PBUT04 - Grid Automation |  |  | 30059 | 30059-007 | 10F001780000 | DAUT 1719-15 Bayamon | Inactive | Inactive
PBUT04 - Grid Automation |  |  | 30059 | 30059-007 | 10F001790000 | DAUT 1719-18 Bayamon | Inactive | Inactive
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001800000 | DAUT 1719-19 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001810000 | DAUT 9401-01 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001820000 | DAUT 9401-02 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001830000 | DAUT 9801-01 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001840000 | DAUT 9802-04 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation | 107955 | 745854 | 30059 | 30059-009 | 10F001850000 | DAUT 1703-01 Bayamon | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  |  | 2024-01-31
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001860000 | DAUT 1703-02 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation | 107955 | 745854 | 30059 | 30059-009 | 10F001870000 | DAUT 1703-04 Bayamon | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  |  | 2024-01-31
PBUT04 - Grid Automation | 107955 | 745854 | 30059 | 30059-009 | 10F001880000 | DAUT 1703-05 Bayamon | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  |  | 2024-01-31
PBUT04 - Grid Automation | 107955 | 745854 | 30059 | 30059-009 | 10F001890000 | DAUT 1704-01 Bayamon | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  |  | 2024-01-31
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001900000 | DAUT 1704-02 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001910000 | DAUT 1717-04 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001920000 | DAUT 9503-06 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001930000 | DAUT 1901-04 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation | 107953 | 745851 | 30059 | 30059-011 | 10F001940000 | DAUT 1907-04 Bayamon | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  |  | 2024-01-31
PBUT04 - Grid Automation | 107953 | 745851 | 30059 | 30059-011 | 10F001950000 | DAUT 1907-05 Bayamon | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  |  | 2024-01-31
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001960000 | DAUT 1336-06 San Juan | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001970000 | DAUT 1336-08 San Juan | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001980000 | DAUT 1336-09 San Juan | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F001990000 | DAUT 1336-10 San Juan | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002000000 | DAUT 2403-02 San Juan | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002010000 | DAUT 2404-06 San Juan | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002020000 | DAUT 2404-07 San Juan | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002030000 | DAUT 2404-08 San Juan | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002040000 | DAUT 3102-01 Caguas | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002050000 | DAUT 3201-02 Caguas | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002060000 | DAUT 3201-04 Caguas | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002070000 | DAUT 3301-01 Caguas | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002080000 | DAUT 9901-02 Caguas | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002090000 | DAUT 9902-02 Caguas | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002100000 | DAUT 9902-03 Caguas | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation | 108086 | 801437 | 30059 | 30059-042 | 10F002110000 | DAUT 4001-03 Ponce | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002120000 | DAUT 5602-02 Ponce | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002130000 | DAUT 5602-03 Ponce | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002140000 | DAUT 6601-03 Ponce | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002150000 | DAUT 6601-04 Ponce | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002160000 | DAUT 4003-01 Ponce | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation | 108080 | 800394 | 30059 | 30059-039 | 10F002170000 | DAUT 4003-02 Ponce | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued
PBUT04 - Grid Automation | 108080 | 800394 | 30059 | 30059-039 | 10F002180000 | DAUT 4003-03 Ponce | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002190000 | DAUT 4101-01 Ponce | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002200000 | DAUT 4101-04 Ponce | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002210000 | DAUT 4201-01 Ponce | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002220000 | DAUT 4201-02 Ponce | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002230000 | DAUT 4201-03 Ponce | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002240000 | DAUT 4201-04 Ponce | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002250000 | DAUT 4301-02 Ponce | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002260000 | DAUT 4401-02 Ponce | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002270000 | DAUT 4401-04 Ponce | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation | 108081 | 800399 | 30059 | 30059-040 | 10F002280000 | DAUT 5002-03 Ponce | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002290000 | DAUT 5004-06 Ponce | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002300000 | DAUT 5004-07 Ponce | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002310000 | DAUT 5004-09 Ponce | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002320000 | DAUT 5007-01 Ponce | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation | 108085 | 801432 | 30059 | 30059-041 | 10F002330000 | DAUT 5302-01 Ponce | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002340000 | DAUT 5302-04 Ponce | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation | 108085 | 801432 | 30059 | 30059-041 | 10F002350000 | DAUT 5304-01 Ponce | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued
PBUT04 - Grid Automation | 108085 | 801432 | 30059 | 30059-041 | 10F002360000 | DAUT 5304-03 Ponce | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002370000 | DAUT 5501-01 Ponce | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002380000 | DAUT 5501-02 Ponce | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002390000 | DAUT 5501-03 Ponce | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002400000 | DAUT 5501-04 Ponce | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002410000 | DAUT 5802-03 Ponce | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002420000 | DAUT 5817-02 Ponce | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002430000 | DAUT 5901-01 Ponce | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002440000 | DAUT 5901-02 Ponce | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002450000 | DAUT 3004-01 Caguas | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002460000 | DAUT 3007-03 Caguas | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002470000 | DAUT 3009-01 Caguas | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002480000 | DAUT 3014-01 Caguas | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002490000 | DAUT 3014-04 Caguas | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002500000 | DAUT 3015-06 Caguas | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002510000 | DAUT 3101-02 Caguas | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002520000 | DAUT 3103-01 Caguas | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002530000 | DAUT 3103-05 Caguas | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002540000 | DAUT 3205-07 Caguas | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002550000 | DAUT 3205-08 Caguas | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002560000 | DAUT 3302-03 Caguas | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002570000 | DAUT 3302-04 Caguas | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation | 108088 | 801440 | 30059 | 30059-044 | 10F002580000 | DAUT 3401-02 Caguas | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002590000 | DAUT 3401-03 Caguas | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002600000 | DAUT 3406-02 Caguas | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002610000 | DAUT 3406-03 Caguas | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002620000 | DAUT 3502-01 Caguas | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002630000 | DAUT 3502-02 Caguas | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002640000 | DAUT 9601-01 Caguas | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002650000 | DAUT 9601-02 Caguas | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002660000 | DAUT 1110-03 San Juan | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation | 108077 | 800286 | 30059 | 30059-036 | 10F002670000 | DAUT 1204-03 San Juan | Active | Inactive |  |  | Active | Phase 4 - Final Field Reviews | Pending EHP Review | 2024-02-02 08:00 | 2024-02-02 08:00 | 2025-03-11 17:00 | 2025-04-28 | 2025-09-17 19:15
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002680000 | DAUT 1206-04 San Juan | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002690000 | DAUT 1346-04 San Juan | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002700000 | DAUT 1346-05 San Juan | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002710000 | DAUT 1416-05 San Juan | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002720000 | DAUT 1619-03 San Juan | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002730000 | DAUT 1620-05 San Juan | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002740000 | DAUT 2001-01 San Juan | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002750000 | DAUT 2005-09 San Juan | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002760000 | DAUT 2006-03 San Juan | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002770000 | DAUT 2201-01 San Juan | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002780000 | DAUT 2201-02 San Juan | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002790000 | DAUT 2302-02 San Juan | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002800000 | DAUT 2305-02 San Juan | Active | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002810000 | DAUT 2305-03 San Juan | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002820000 | DAUT 2306-01 San Juan | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation | 108040 | 757699 | 30059 | 30059-034 | 10F002830000 | DAUT 8010-02 Arecibo | Active | Inactive |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2024-03-14 08:00 | 2024-03-14 08:00 | 2025-03-11 17:00 | 2025-03-11 | 2025-11-05 16:17
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002840000 | DAUT 8015-07 Arecibo | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059-047 | 10F002850000 | DAUT 8015-09 Arecibo | Inactive | Inactive
PBUT04 - Grid Automation | 108040 | 757699 | 30059 | 30059-034 | 10F002860000 | DAUT 8101-01 Arecibo | Active | Inactive |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2024-03-14 08:00 | 2024-03-14 08:00 | 2025-03-11 17:00 | 2025-03-11 | 2025-11-05 16:17
PBUT04 - Grid Automation | 108040 | 757699 | 30059 | 30059-034 | 10F002870000 | DAUT 8101-04 Arecibo | Active | Inactive |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2024-03-14 08:00 | 2024-03-14 08:00 | 2025-03-11 17:00 | 2025-03-11 | 2025-11-05 16:17
PBUT04 - Grid Automation | 108040 | 757699 | 30059 | 30059-034 | 10F002880000 | DAUT 8101-05 Arecibo | Active | Inactive |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2024-03-14 08:00 | 2024-03-14 08:00 | 2025-03-11 17:00 | 2025-03-11 | 2025-11-05 16:17
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002890000 | DAUT 8104-02 Arecibo | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002900000 | DAUT 8202-03 Arecibo | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002910000 | DAUT 8203-01 Arecibo | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002920000 | DAUT 8203-02 Arecibo | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002930000 | DAUT 8301-01 Arecibo | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002940000 | DAUT 8301-03 Arecibo | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059-048 | 10F002950000 | DAUT 8404-01 Arecibo | Inactive | Inactive
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002960000 | DAUT 8404-02 Arecibo | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059-048 | 10F002970000 | DAUT 8405-01 Arecibo | Inactive | Inactive
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002980000 | DAUT 8405-02 Arecibo | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F002990000 | DAUT 8405-03 Arecibo | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003000000 | DAUT 8405-04 Arecibo | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003010000 | DAUT 7403-03 Arecibo | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003020000 | DAUT 8303-04 Arecibo | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059-047 | 10F003030000 | DAUT 8501-01 Arecibo | Inactive | Inactive
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003040000 | DAUT 8501-02 Arecibo | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003050000 | DAUT 8501-03 Arecibo | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003060000 | DAUT 8504-03 Arecibo | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003070000 | DAUT 8602-01 Arecibo | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003080000 | DAUT 8602-02 Arecibo | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003090000 | DAUT 8602-03 Arecibo | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059-048 | 10F003100000 | DAUT 8801-04 Arecibo | Inactive | Inactive
PBUT04 - Grid Automation | 108087 | 801438 | 30059 | 30059-043 | 10F003110000 | DAUT 9001-02 Arecibo | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003120000 | DAUT 9002-01 Arecibo | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003130000 | DAUT 9002-03 Arecibo | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003140000 | DAUT 1529-12 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003150000 | DAUT 1701-03 Bayamon | Active | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003160000 | DAUT 1704-03 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003170000 | DAUT 1704-05 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003180000 | DAUT 1707-01 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003190000 | DAUT 1707-04 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003200000 | DAUT 1708-02 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003210000 | DAUT 1708-04 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003220000 | DAUT 1734-02 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003230000 | DAUT 1801-02 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003240000 | DAUT 1801-05 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003250000 | DAUT 1901-02 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003260000 | DAUT 1711-05 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003270000 | DAUT 1717-01 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003280000 | DAUT 1717-03 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003290000 | DAUT 1718-01 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003300000 | DAUT 1718-02 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003310000 | DAUT 1718-03 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003320000 | DAUT 1903-05 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003330000 | DAUT 9202-01 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003340000 | DAUT 9202-03 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003350000 | DAUT 9202-04 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003360000 | DAUT 9203-04 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003370000 | DAUT 9207-08 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003380000 | DAUT 4401-01 Ponce | Active | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003390000 | DAUT 4602-01 Ponce | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003400000 | DAUT 4602-03 Ponce | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003410000 | DAUT 4602-04 Ponce | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003420000 | DAUT 4603-01 Ponce | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003430000 | DAUT 4603-02 Ponce | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation | 108087 | 801438 | 30059 | 30059-043 | 10F003440000 | DAUT 9003-05 Arecibo | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003450000 | DAUT 9003-06 Arecibo | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003460000 | DAUT 9004-10 Arecibo | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003470000 | DAUT 9101-01 Arecibo | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003480000 | DAUT 1118-10 San Juan | Active | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003490000 | DAUT 1646-01 San Juan | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003500000 | DAUT 1646-05 San Juan | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003510000 | DAUT 2403-01 San Juan | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059-046 | 10F003520000 | DAUT 2404-05 San Juan | Active | Inactive
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003530000 | DAUT 3801-01 San Juan | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003540000 | DAUT 3801-02 San Juan | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003550000 | DAUT 1705-03 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003560000 | DAUT 1705-04 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation | 108039 | 757698 | 30059 | 30059-033 | 10F003570000 | DAUT 9801-03 Bayamon | Active | Inactive |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2023-11-22 08:00 | 2023-11-22 08:00 | 2025-03-11 17:00 | 2025-03-11 | 2025-09-25 17:15
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003580000 | DAUT4101-02 Ponce | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003590000 | DAUT-5303-01 Ponce | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003600000 | DAUT-5401-02 Ponce | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003610000 | DAUT-5401-04 Ponce | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003620000 | DAUT-5901-03 Ponce | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003630000 | DAUT-3006-02 Caguas | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003640000 | DAUT-3202-01 Caguas | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003650000 | DAUT-3405-03 Caguas | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003660000 | DAUT-3501-02 Caguas | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003670000 | DAUT-1529-11 Caguas | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003680000 | DAUT-1529-13 Caguas | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003690000 | DAUT-1706-01 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003700000 | DAUT-9501-02 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003710000 | DAUT-9501-03 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003720000 | DAUT-1711-02 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003730000 | DAUT-1711-03 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003740000 | DAUT-1901-01 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003750000 | DAUT-1901-03 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003760000 | DAUT 1901-05 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003770000 | DAUT 9502-01 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003780000 | DAUT 9503-05 Bayamon | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003790000 | DAUT 1114-01 San Juan | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003800000 | DAUT 1114-02 San Juan | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003810000 | DAUT 1114-03 San Juan | Inactive | Inactive | [7 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003820000 | DAUT 1707-05 BAYAMON | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003830000 | DAUT 1707-02 BAYAMON | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003840000 | DAUT 7402-05 ARECIBO | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003850000 | DAUT 7601-04 ARECIBO | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003860000 | DAUT 7602-05 ARECIBO | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation | 108040 | 757699 | 30059 | 30059-034 | 10F003870000 | DAUT 7701-02 ARECIBO | Active | Inactive | CAP4 | ISSUE | Active | Phase 5 - Post Award Phase | Obligated | 2024-03-14 08:00 | 2024-03-14 08:00 | 2025-03-11 17:00 | 2025-03-11 | 2025-11-05 16:17
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003880000 | DAUT 7701-04 ARECIBO | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003890000 | DAUT 8001-01 ARECIBO | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003900000 | DAUT 8001-02 ARECIBO | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003910000 | DAUT 8001-03 ARECIBO | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003920000 | DAUT 8001-04 ARECIBO | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003930000 | DAUT 8002-02 ARECIBO | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059-047 | 10F003940000 | DAUT 8002-05 ARECIBO | Inactive | Inactive | CAP1
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003950000 | DAUT 8007-01 ARECIBO | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003960000 | DAUT 8104-01 ARECIBO | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003970000 | DAUT 8104-05 ARECIBO | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003980000 | DAUT 8401-01 ARECIBO | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F003990000 | DAUT 9002-02 ARECIBO | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004000000 | DAUT 1704-04 BAYAMON | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004010000 | DAUT 1716-01 BAYAMON | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004020000 | DAUT 1717-05 BAYAMON | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004030000 | DAUT 1719-16 BAYAMON | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004040000 | DAUT 1912-07 BAYAMON | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004050000 | DAUT 1912-08 BAYAMON | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004060000 | DAUT 1912-10 BAYAMON | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004070000 | DAUT 9201-01 BAYAMON | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004080000 | DAUT 9206-08 BAYAMON | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004090000 | DAUT 9206-09 BAYAMON | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004100000 | DAUT 9206-10 BAYAMON | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004110000 | DAUT 3005-02 CAGUAS | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004120000 | DAUT 3005-03 CAGUAS | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004130000 | DAUT 3006-01 CAGUAS | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004140000 | DAUT 3007-02 CAGUAS | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004150000 | DAUT 3010-04 CAGUAS | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation | 108077 | 800286 | 30059 | 30059-036 | 10F004160000 | DAUT 1102-03 SAN JUAN | Active | Inactive | CAP4 | ISSUE | Active | Phase 4 - Final Field Reviews | Pending EHP Review | 2024-02-02 08:00 | 2024-02-02 08:00 | 2025-03-11 17:00 | 2025-04-28 | 2025-09-17 19:15
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004170000 | DAUT 1106-01 SAN JUAN | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation | 108077 | 800286 | 30059 | 30059-036 | 10F004180000 | DAUT 1106-05 SAN JUAN | Active | Inactive | CAP4 | ISSUE | Active | Phase 4 - Final Field Reviews | Pending EHP Review | 2024-02-02 08:00 | 2024-02-02 08:00 | 2025-03-11 17:00 | 2025-04-28 | 2025-09-17 19:15
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004190000 | DAUT 1416-01 SAN JUAN | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004200000 | DAUT 1416-03 SAN JUAN | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004210000 | DAUT 1618-01 SAN JUAN | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004220000 | DAUT 1618-03 SAN JUAN | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004230000 | DAUT 1620-01 SAN JUAN | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004240000 | DAUT 1647-10 SAN JUAN | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004250000 | DAUT 1658-14 SAN JUAN | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004260000 | DAUT 2201-03 SAN JUAN | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059-046 | 10F004270000 | DAUT 2201-04 SAN JUAN | Inactive | Inactive | CAP1 | ISSUE
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004280000 | DAUT 2306-02 SAN JUAN | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004290000 | DAUT 7701-03 ARECIBO | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004300000 | DAUT 8007-03 ARECIBO | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004310000 | DAUT 8007-04 ARECIBO | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation | 108079 | 800369 | 30059 | 30059-038 | 10F004320000 | DAUT 8401-03 ARECIBO | Inactive | Inactive | CAP1 |  | Withdrawn | Discontinued | Process Discontinued
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004330000 | DAUT 1924-02 BAYAMON | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004340000 | DAUT 1924-05 BAYAMON | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004350000 | DAUT 9206-07 BAYAMON | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004360000 | DAUT 9206-11 BAYAMON | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004370000 | DAUT 2601-04 CAGUAS | Inactive | Inactive | CAP1 | WARNING | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004380000 | DAUT 2801-01 CAGUAS | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004390000 | DAUT 3008-01 CAGUAS | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004400000 | DAUT 3008-04 CAGUAS | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004410000 | DAUT 1102-01 SAN JUAN | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059-046 | 10F004420000 | DAUT 1658-13 SAN JUAN | Inactive | Inactive | CAP1 | WARNING
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004430000 | DAUT 2002-02 SAN JUAN | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004440000 | DAUT 2402-01 SAN JUAN | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004450000 | DAUT 8002-03 ARECIBO | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004460000 | DAUT 3004-03 CAGUAS | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004470000 | DAUT 7805-13 MAYAGUEZ | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004480000 | DAUT 2003-02 SAN JUAN | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004490000 | DAUT 1334-01 SAN JUAN | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004500000 | DAUT 1106-04 SAN JUAN | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004510000 | DAUT 5803-02 PONCE | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004520000 | DAUT 5802-01 PONCE | Inactive | Inactive | CAP1 | WARNING | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004530000 | DAUT 5305-04 PONCE | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004540000 | DAUT 5010-06 PONCE | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004550000 | DAUT 5005-02 PONCE | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004560000 | DAUT 4502-01 PONCE | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004570000 | DAUT 4301-04 PONCE | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004580000 | DAUT 4002-03 PONCE | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004590000 | DAUT 4002-02 PONCE | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004600000 | DAUT 7901-02 MAYAGUEZ | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004610000 | DAUT 7503-05 MAYAGUEZ | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004620000 | DAUT 7502-02 MAYAGUEZ | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004630000 | DAUT 7201-05 MAYAGUEZ | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004640000 | DAUT 7101-06 MAYAGUEZ | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004650000 | DAUT 7101-04 MAYAGUEZ | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004660000 | DAUT 7101-03 MAYAGUEZ | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004670000 | DAUT 7012-01 MAYAGUEZ | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004680000 | DAUT 6014-03 MAYAGUEZ | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004690000 | DAUT 6012-05 MAYAGUEZ | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004700000 | DAUT 6012-01 MAYAGUEZ | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004710000 | DAUT 6002-05 MAYAGUEZ | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004720000 | DAUT 6002-04 MAYAGUEZ | Inactive | Inactive | CAP1 | WARNING | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004730000 | DAUT 6002-03 MAYAGUEZ | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004740000 | DAUT 9901-01 CAGUAS | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004750000 | DAUT 3701-01 CAGUAS | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation | 108078 | 800361 | 30059 | 30059-037 | 10F004760000 | DAUT 3406-01 CAGUAS | Active | Inactive | CAP4 | ISSUE | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval | 2024-03-28 08:00 | 2024-03-28 08:00 | 2025-04-28 17:00 | 2025-04-28 | 2025-09-17 19:15
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004770000 | DAUT 3403-01 CAGUAS | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004780000 | DAUT 3402-06 CAGUAS | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004790000 | DAUT 3302-01 CAGUAS | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004800000 | DAUT 3301-03 CAGUAS | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004810000 | DAUT 3205-10 CAGUAS | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004820000 | DAUT 3101-04 CAGUAS | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004830000 | DAUT 3015-09 CAGUAS | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004840000 | DAUT 3007-04 CAGUAS | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004850000 | DAUT 3006-04 CAGUAS | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004860000 | DAUT 2702-02 CAGUAS | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004870000 | DAUT 9202-02 BAYAMON | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004880000 | DAUT 1802-01 BAYAMON | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004890000 | DAUT 1717-02 BAYAMON | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004900000 | DAUT 1707-03 BAYAMON | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004910000 | DAUT 7403-01 ARECIBO | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004920000 | DAUT 1530-10 BAYAMON | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004930000 | DAUT 9105-08 ARECIBO | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059-048 | 10F004940000 | DAUT 9004-11 ARECIBO | Inactive | Inactive | CAP1
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004950000 | DAUT 8504-01 ARECIBO | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004960000 | DAUT 8013-04 ARECIBO | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004970000 | DAUT 8013-03 ARECIBO | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004980000 | DAUT 8004-02 ARECIBO | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F004990000 | DAUT 8002-04 ARECIBO | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005000000 | DAUT 7702-01 ARECIBO | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005010000 | DAUT 1102-02 SAN JUAN | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005020000 | DAUT 1102-05 SAN JUAN | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005030000 | DAUT 1203-01 SAN JUAN | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005040000 | DAUT 1203-02 SAN JUAN | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005050000 | DAUT 1203-03 SAN JUAN | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059-046 | 10F005060000 | DAUT 1657-02 SAN JUAN | Inactive | Inactive | CAP1
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005070000 | DAUT 2501-01 SAN JUAN | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005080000 | DAUT 2501-02 SAN JUAN | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005090000 | DAUT 2501-03 SAN JUAN | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005100000 | DAUT 2604-02 CAGUAS | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005110000 | DAUT 2604-03 CAGUAS | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation | 108078 | 800361 | 30059 | 30059-037 | 10F005120000 | DAUT 2701-02 CAGUAS | Active | Inactive | CAP4 | ISSUE | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval | 2024-03-28 08:00 | 2024-03-28 08:00 | 2025-04-28 17:00 | 2025-04-28 | 2025-09-17 19:15
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005130000 | DAUT 2906-02 CAGUAS | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005140000 | DAUT 3005-01 CAGUAS | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005150000 | DAUT 3010-02 CAGUAS | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005160000 | DAUT 3014-02 CAGUAS | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005170000 | DAUT 3014-03 CAGUAS | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005180000 | DAUT 3016-05 CAGUAS | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005190000 | DAUT 3101-01 CAGUAS | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005200000 | DAUT 3103-03 CAGUAS | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005210000 | DAUT 3402-05 CAGUAS | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation | 108078 | 800361 | 30059 | 30059-037 | 10F005220000 | DAUT 3602-03 CAGUAS | Active | Inactive | CAP4 | ISSUE | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval | 2024-03-28 08:00 | 2024-03-28 08:00 | 2025-04-28 17:00 | 2025-04-28 | 2025-09-17 19:15
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005230000 | DAUT 3603-01 CAGUAS | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005240000 | DAUT 3603-02 CAGUAS | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005250000 | DAUT 4301-03 PONCE | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005260000 | DAUT 4501-01 PONCE | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005270000 | DAUT 4501-02 PONCE | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005280000 | DAUT 4501-03 PONCE | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation | 108081 | 800399 | 30059 | 30059-040 | 10F005290000 | DAUT 4501-04 PONCE | Inactive | Inactive | CAP1 | ISSUE | Withdrawn | Discontinued | Process Discontinued
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005300000 | DAUT 4501-05 PONCE | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005310000 | DAUT 4502-02 PONCE | Inactive | Inactive | CAP1 | WARNING | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005320000 | DAUT 4503-02 PONCE | Inactive | Inactive | CAP1 | WARNING | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005330000 | DAUT 5002-01 PONCE | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005340000 | DAUT 5002-02 PONCE | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005350000 | DAUT 5002-04 PONCE | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005360000 | DAUT 5012-04 PONCE | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005370000 | DAUT 5304-02 PONCE | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005380000 | DAUT 5304-05 PONCE | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005390000 | DAUT 5305-03 PONCE | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005400000 | DAUT 5602-01 PONCE | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005410000 | DAUT 5802-05 PONCE | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005420000 | DAUT 5902-03 PONCE | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005430000 | DAUT 6001-01 MAYAGUEZ | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005440000 | DAUT 6001-02 MAYAGUEZ | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005450000 | DAUT 6005-01 MAYAGUEZ | Inactive | Inactive | CAP1 | WARNING | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005460000 | DAUT 6008-02 MAYAGUEZ | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005470000 | DAUT 6401-02 MAYAGUEZ | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005480000 | DAUT 6401-04 MAYAGUEZ | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005490000 | DAUT 6404-01 MAYAGUEZ | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005500000 | DAUT 6404-02 MAYAGUEZ | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005510000 | DAUT 6404-03 MAYAGUEZ | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005520000 | DAUT 6404-04 MAYAGUEZ | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation | 108081 | 800399 | 30059 | 30059-040 | 10F005530000 | DAUT 6601-01 PONCE | Inactive | Inactive | CAP1 | ISSUE | Withdrawn | Discontinued | Process Discontinued
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005540000 | DAUT 6601-02 PONCE | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005550000 | DAUT 7003-01 MAYAGUEZ | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005560000 | DAUT 7003-04 MAYAGUEZ | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005570000 | DAUT 7003-05 MAYAGUEZ | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005580000 | DAUT 7502-01 MAYAGUEZ | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005590000 | DAUT 7503-01 MAYAGUEZ | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005600000 | DAUT 7503-03 MAYAGUEZ | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005610000 | DAUT 7503-04 MAYAGUEZ | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005620000 | DAUT 7801-02 MAYAGUEZ | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005630000 | DAUT 7801-03 MAYAGUEZ | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005640000 | DAUT 7802-03 MAYAGUEZ | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005650000 | DAUT 7802-04 MAYAGUEZ | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005660000 | DAUT 1620-03 SAN JUAN | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005670000 | DAUT 1620-04 SAN JUAN | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005680000 | DAUT 1646-03 SAN JUAN | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005690000 | DAUT 1647-06 SAN JUAN | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005700000 | DAUT 1647-07 SAN JUAN | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059-046 | 10F005710000 | DAUT 1647-08 SAN JUAN | Inactive | Inactive | CAP1
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005720000 | DAUT 1647-09 SAN JUAN | Inactive | Inactive | CAP1 | WARNING | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005730000 | DAUT 1657-01 SAN JUAN | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005740000 | DAUT 1657-03 SAN JUAN | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005750000 | DAUT 1657-04 SAN JUAN | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005760000 | DAUT 1658-15 SAN JUAN | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005770000 | DAUT 1714-03 BAYAMON | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005780000 | DAUT 1714-05 BAYAMON | Active | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005790000 | DAUT 1715-02 BAYAMON | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005800000 | DAUT 1715-03 BAYAMON | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005810000 | DAUT 1715-05 BAYAMON | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005820000 | DAUT 1801-01 BAYAMON | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005830000 | DAUT 1801-03 BAYAMON | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005840000 | DAUT 1802-02 BAYAMON | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005850000 | DAUT 1803-05 BAYAMON | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005860000 | DAUT 1924-01 BAYAMON | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005870000 | DAUT 1924-03 BAYAMON | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005880000 | DAUT 2002-03 SAN JUAN | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation | 108077 | 800286 | 30059 | 30059-036 | 10F005890000 | DAUT 2005-10 SAN JUAN | Active | Inactive | CAP4 | ISSUE | Active | Phase 4 - Final Field Reviews | Pending EHP Review | 2024-02-02 08:00 | 2024-02-02 08:00 | 2025-03-11 17:00 | 2025-04-28 | 2025-09-17 19:15
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005900000 | DAUT 2601-02 CAGUAS | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005910000 | DAUT 2602-01 CAGUAS | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005920000 | DAUT 2604-01 CAGUAS | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005930000 | DAUT 3007-01 CAGUAS | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005940000 | DAUT 3008-03 CAGUAS | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005950000 | DAUT 3009-02 CAGUAS | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005960000 | DAUT 3009-03 CAGUAS | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005970000 | DAUT 3009-04 CAGUAS | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005980000 | DAUT 3016-03 CAGUAS | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F005990000 | DAUT 3101-03 CAGUAS | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006000000 | DAUT 3103-02 CAGUAS | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006010000 | DAUT 4301-01 PONCE | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006020000 | DAUT 5005-01 PONCE | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006030000 | DAUT 5005-03 PONCE | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006040000 | DAUT 5005-04 PONCE | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006050000 | DAUT 5005-05 PONCE | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006060000 | DAUT 5012-01 PONCE | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006070000 | DAUT 5012-02 PONCE | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006080000 | DAUT 5018-05 PONCE | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006090000 | DAUT 5301-01 PONCE | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006100000 | DAUT 5401-01 PONCE | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006110000 | DAUT 5401-03 PONCE | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006120000 | DAUT 5802-02 PONCE | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006130000 | DAUT 5902-02 PONCE | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006140000 | DAUT 6001-03 MAYAGUEZ | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006150000 | DAUT 6001-04 MAYAGUEZ | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006160000 | DAUT 6001-05 MAYAGUEZ | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006170000 | DAUT 6005-02 MAYAGUEZ | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006180000 | DAUT 6008-04 MAYAGUEZ | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006190000 | DAUT 6008-05 MAYAGUEZ | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006200000 | DAUT 6401-01 MAYAGUEZ | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006210000 | DAUT 6401-03 MAYAGUEZ | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006220000 | DAUT 7502-03 MAYAGUEZ | Inactive | Inactive | CAP1 | WARNING | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006230000 | DAUT 7502-04 MAYAGUEZ | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006240000 | DAUT 7503-02 MAYAGUEZ | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006250000 | DAUT 7504-01 MAYAGUEZ | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006260000 | DAUT 7601-01 ARECIBO | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006270000 | DAUT 7601-03 ARECIBO | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006280000 | DAUT 7701-01 ARECIBO | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006290000 | DAUT 7801-04 MAYAGUEZ | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006300000 | DAUT 8004-01 ARECIBO | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006310000 | DAUT 8004-03 ARECIBO | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006320000 | DAUT 8004-04 ARECIBO | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006330000 | DAUT 8011-01 ARECIBO | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006340000 | DAUT 8011-02 ARECIBO | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006350000 | DAUT 8011-04 ARECIBO | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006360000 | DAUT 8401-02 ARECIBO | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006370000 | DAUT 8401-04 ARECIBO | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006380000 | DAUT 8701-04 ARECIBO | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059-048 | 10F006390000 | DAUT 9103-01 ARECIBO | Inactive | Inactive | CAP1
PBUT04 - Grid Automation |  |  | 30059 | 30059-048 | 10F006400000 | DAUT 9103-02 ARECIBO | Inactive | Inactive | CAP1
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006410000 | DAUT 9103-04 ARECIBO | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006420000 | DAUT 9703-01 CAGUAS | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006430000 | DAUT 2003-01 SAN JUAN | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006440000 | DAUT 2001-04 SAN JUAN | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006450000 | DAUT 2001-03 SAN JUAN | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006460000 | DAUT 1620-02 SAN JUAN | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006470000 | DAUT 1619-01 SAN JUAN | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006480000 | DAUT 1618-02 SAN JUAN | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006490000 | DAUT 1607-04 SAN JUAN | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006500000 | DAUT 1416-02 SAN JUAN | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006510000 | DAUT 1416-04 SAN JUAN | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006520000 | DAUT 1348-06 SAN JUAN | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006530000 | DAUT 1346-06 SAN JUAN | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006540000 | DAUT 1346-01 SAN JUAN | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006550000 | DAUT 1334-02 SAN JUAN | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006560000 | DAUT 1301-04 SAN JUAN | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006570000 | DAUT 1301-03 SAN JUAN | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation | 108077 | 800286 | 30059 | 30059-036 | 10F006580000 | DAUT 1301-02 SAN JUAN | Active | Inactive | CAP4 | ISSUE | Active | Phase 4 - Final Field Reviews | Pending EHP Review | 2024-02-02 08:00 | 2024-02-02 08:00 | 2025-03-11 17:00 | 2025-04-28 | 2025-09-17 19:15
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006590000 | DAUT 1301-01 SAN JUAN | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006600000 | DAUT 1106-02 SAN JUAN | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006610000 | DAUT 1102-04 SAN JUAN | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006620000 | DAUT 5805-01 PONCE | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006630000 | DAUT 5802-04 PONCE | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006640000 | DAUT 5012-05 PONCE | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006650000 | DAUT 5010-04 PONCE | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006660000 | DAUT 5010-03 PONCE | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006670000 | DAUT 5003-04 PONCE | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006680000 | DAUT 5003-03 PONCE | Inactive | Inactive | CAP1 | WARNING | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006690000 | DAUT 5003-02 PONCE | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006700000 | DAUT 5003-01 PONCE | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006710000 | DAUT 4503-01 PONCE | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006720000 | DAUT 4006-05 PONCE | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006730000 | DAUT 4006-04 PONCE | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006740000 | DAUT 4006-02 PONCE | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006750000 | DAUT 4002-01 PONCE | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006760000 | DAUT 7903-07 MAYAGUEZ | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006770000 | DAUT 7303-03 MAYAGUEZ | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006780000 | DAUT 7303-02 MAYAGUEZ | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006790000 | DAUT 7201-04 MAYAGUEZ | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006800000 | DAUT 7201-01 MAYAGUEZ | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006810000 | DAUT 7101-02 MAYAGUEZ | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006820000 | DAUT 7012-02 MAYAGUEZ | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006830000 | DAUT 7002-04 MAYAGUEZ | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006840000 | DAUT 7002-03 MAYAGUEZ | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006850000 | DAUT 7002-02 MAYAGUEZ | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006860000 | DAUT 6014-01 MAYAGUEZ | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006870000 | DAUT 6002-02 MAYAGUEZ | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006880000 | DAUT 6002-01 MAYAGUEZ | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006890000 | DAUT 3201-03 CAGUAS | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006900000 | DAUT 3201-01 CAGUAS | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006910000 | DAUT 3102-02 CAGUAS | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006920000 | DAUT 3013-04 CAGUAS | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006930000 | DAUT 3004-04 CAGUAS | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006940000 | DAUT 3004-02 CAGUAS | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006950000 | DAUT 2906-04 CAGUAS | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006960000 | DAUT 2906-03 CAGUAS | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006970000 | DAUT 2605-02 CAGUAS | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006980000 | DAUT 2603-10 CAGUAS | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F006990000 | DAUT 2603-08 CAGUAS | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007000000 | DAUT 2603-07 CAGUAS | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007010000 | DAUT 9404-01 BAYAMON | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007020000 | DAUT 9403-02 BAYAMON | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007030000 | DAUT 9403-01 BAYAMON | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007040000 | DAUT 9401-03 BAYAMON | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007050000 | DAUT 9207-09 BAYAMON | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007060000 | DAUT 9207-05 BAYAMON | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007070000 | DAUT 1924-04 BAYAMON | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007080000 | DAUT 1908-04 BAYAMON | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007090000 | DAUT 1907-03 BAYAMON | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007100000 | DAUT 1903-03 BAYAMON | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007110000 | DAUT 1903-02 BAYAMON | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007120000 | DAUT 1903-01 BAYAMON | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007130000 | DAUT 1803-04 BAYAMON | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007140000 | DAUT 1803-02 BAYAMON | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007150000 | DAUT 1716-02 BAYAMON | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007160000 | DAUT 1713-04 BAYAMON | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007170000 | DAUT 9105-07 ARECIBO | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007180000 | DAUT 8504-02 ARECIBO | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007190000 | DAUT 8302-04 ARECIBO | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007200000 | DAUT 8301-02 ARECIBO | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007210000 | DAUT 8014-07 ARECIBO | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059-047 | 10F007220000 | DAUT 8014-06 ARECIBO | Inactive | Inactive | CAP1
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007230000 | DAUT 8008-02 ARECIBO | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007240000 | DAUT 8008-01 ARECIBO | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059-047 | 10F007250000 | DAUT 8002-01 ARECIBO | Inactive | Inactive | CAP1
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007260000 | DAUT 7404-06 ARECIBO | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007270000 | DAUT 7402-03 ARECIBO | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007280000 | DAUT 7402-02 ARECIBO | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007290000 | DAUT 7002-01 MAYAGUEZ | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation | 107957 | 745861 | 30059 |  | 10F007310000 | DAUT/COMM ARECIBO G-12 | Active | Inactive | CAP4 | ISSUE | Active | Phase 2 - Intake & Eligibility | Pending PDMG Scope & Cost Routing |  |  |  | 2024-06-20 | 2025-02-06 20:16
PBUT04 - Grid Automation | 107956 | 745856 | 30059 |  | 10F007320000 | DAUT/COMM ARECIBO G-14 | Active | Inactive | CAP4 | ISSUE | Active | Phase 3 - Scoping and Costing | Pending FEMA 406 HMP Completion |  |  |  | 2024-01-31 | 2025-02-06 20:16
PBUT04 - Grid Automation | 108022 | 755211 | 30059 |  | 10F007330000 | DAUT/COMM SAN JUAN G-15 | Active | Inactive | CAP4 | ISSUE | Active |  | Pending Award |  |  |  | 2024-09-06 | 2025-02-06 20:16
PBUT04 - Grid Automation | 108000 | 752808 | 30059 |  | 10F007340000 | DAUT/COMM ARECIBO G-19 | Active | Inactive | CAP4 | WARNING | Active | Phase 4 - Final Field Reviews | Pending EHP Review |  |  |  | 2024-09-04 | 2025-02-06 20:16
PBUT04 - Grid Automation | 108001 | 752810 | 30059 |  | 10F007350000 | DAUT/COMM CAGUAS G-20 | Active | Inactive | CAP4 | ISSUE | Active | Phase 2 - Intake & Eligibility | Pending PDMG Scope & Cost Routing |  |  |  | 2024-09-04 | 2025-02-06 20:16
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007360000 | DAUT/COMM BAYAMON G-30 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007450000 | DAUT SAN JUAN 1110-01 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007460000 | DAUT SAN JUAN 1110-02 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007470000 | DAUT SAN JUAN 1110-05 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007480000 | DAUT SAN JUAN 1111-01 | Active | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007490000 | DAUT SAN JUAN 1117-08 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007500000 | DAUT SAN JUAN 1117-09 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007510000 | DAUT SAN JUAN 1401-06 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007520000 | DAUT SAN JUAN 1401-07 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007530000 | DAUT SAN JUAN 1401-08 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007540000 | DAUT SAN JUAN 1401-10 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007550000 | DAUT SAN JUAN 1512-04 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007560000 | DAUT SAN JUAN 1512-05 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007570000 | DAUT SAN JUAN 1530-06 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007580000 | DAUT SAN JUAN 1530-07 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007590000 | DAUT SAN JUAN1530-08 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007600000 | DAUT SAN JUAN 1530-09 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007610000 | DAUT SAN JUAN 1113-01 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007620000 | DAUT SAN JUAN 1113-03 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007630000 | DAUT SAN JUAN 1113-04 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007640000 | DAUT SAN JUAN 1113-05 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007650000 | DAUT SAN JUAN 1115-05 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007660000 | DAUT MAYAGUEZ 7103-01 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007670000 | DAUT MAYAGÜEZ 7103-02 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007680000 | DAUT MAYAGUEZ 7103-04 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007690000 | DAUT MAYAGÜEZ 7504-02 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007700000 | DAUT MAYAGÜEZ 7505-01 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007710000 | DAUT SAN JUAN 1335-01 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007720000 | DAUT SAN JUAN 1335-02 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007730000 | DAUT SAN JUAN 1335-03 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007740000 | DAUT SAN JUAN 1335-04 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007750000 | DAUT SAN JUAN 1335-05 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007760000 | DAUT SAN JUAN 1602-01 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007770000 | DAUT SAN JUAN 1602-02 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007780000 | DAUT SAN JUAN 1602-03 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007790000 | DAUT SAN JUAN 1602-04 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007800000 | DAUT SAN JUAN 1602-05 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007810000 | DAUT SAN JUAN 2301-03 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007820000 | DAUT SAN JUAN 2305-01 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007830000 | DAUT SAN JUAN 2305-04 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007840000 | DAUT SAN JUAN 1119-02 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007850000 | DAUT SAN JUAN 1119-04 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007860000 | DAUT SAN JUAN 1343-02 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007870000 | DAUT SAN JUAN 1343-03 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007880000 | DAUT SAN JUAN 1343-04 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007890000 | DAUT MAYAG. 6702-03 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007900000 | DAUT MAYAG. 6703-02 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007910000 | DAUT MAYAG. 6705-02 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007920000 | DAUT SAN JUAN 1421-01 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007930000 | DAUT SAN JUAN 1421-02 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007940000 | DAUT SAN JUAN 1421-03 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007950000 | DAUT SAN JUAN 1421-04 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007960000 | DAUT SAN JUAN 1421-05 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007970000 | DAUT SAN JUAN 1404-07 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007980000 | DAUT SAN JUAN 1404-09 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F007990000 | DAUT SAN JUAN 1420-02 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F008000000 | DAUT SAN JUAN 1420-03 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F008010000 | DAUT SAN JUAN 2401-02 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F008020000 | DAUT SAN JUAN 2401-03 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F008030000 | DAUT SAN JUAN 1526-01 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F008040000 | DAUT SAN JUAN 1526-02 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F008050000 | DAUT SAN JUAN 1526-03 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F008060000 | DAUT SAN JUAN 1526-04 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 30059 | 30059 | 10F008070000 | DAUT SAN JUAN 1526-05 | Inactive | Inactive | CAP1 | [6 empty] | 2023-04-24 17:00
PBUT04 - Grid Automation |  |  | 10161 | 10161 | 10N000340000 | Feeder 1908-03 Buen Pastor | Inactive
PBUT04 - Grid Automation | 107781 | 688623 | 30059 | 30059-001A | 14F000160000 | Arecibo Short Term Group 1 - D | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  |  | 2023-05-01
PBUT04 - Grid Automation | 107781 | 688623 | 30059 | 30059-001A | 14F000350000 | Bayamon Short Term Group 1 - D | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  |  | 2023-05-01
PBUT04 - Grid Automation | 107939 | 740662 | 30059 | 30059-002 | 14F000800000 | Cagus Short Term Group 1 - Dis | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  |  | 2023-12-13
PBUT04 - Grid Automation |  |  | 30059 |  | 14F000960000 | Distribution Automation | Inactive | Inactive
PBUT04 - Grid Automation | 107996 | 752500 | 30059 | 30059-001B | 14F001290000 | Mayaguez Short Term Group 3 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued
PBUT04 - Grid Automation | 107939 | 740662 | 30059 | 30059-002 | 14F001430000 | Ponce ST2 Dist Automation | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  |  | 2023-12-13
PBUT04 - Grid Automation | 107947 | 741678 | 30059 | 30059-004 | 14F001610000 | San Juan T3 - Dist Automat | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  |  | 2023-12-22
PBUT04 - Grid Automation | 107781 | 688623 | 30059 | 30059-001A | 14F003260000 | Arecibo Short Term Group 2 - D | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  |  | 2023-05-01
PBUT04 - Grid Automation | 107947 | 741678 | 30059 | 30059-004 | 14F003270000 | Bayamon Short Term Group 3 - D | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  |  | 2023-12-22
PBUT04 - Grid Automation |  |  | 30059 |  | 14F003280000 | Bayamon Short Term Group 2 - D | Inactive | Inactive
PBUT04 - Grid Automation | 107947 | 741678 | 30059 | 30059-004 | 14F003290000 | Carolina Short Term Group 2 - | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  |  | 2023-12-22
PBUT04 - Grid Automation | 107947 | 741678 | 30059 | 30059-004 | 14F003300000 | Carolina Short Term Group 3 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  |  | 2023-12-22
PBUT04 - Grid Automation | 107939 | 740662 | 30059 | 30059-002 | 14F003310000 | Mayaguez Short Term Group 1 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  |  | 2023-12-13
PBUT04 - Grid Automation | 107939 | 740662 | 30059 | 30059-002 | 14F003320000 | Mayaguez Short Term Group 2 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  |  | 2023-12-13
PBUT04 - Grid Automation |  |  | 30059 |  | 14F003330000 | Ponce ST1 Dist Automation | Inactive | Inactive
PBUT04 - Grid Automation | 107998 | 752503 | 30059 | 30059-001D | 14F003340000 | San Juan ST1 Dist Automa | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued
PBUT04 - Grid Automation | 107947 | 741678 | 30059 | 30059-004 | 14F003350000 | San Juan ST2 - Dist Automat | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  |  | 2023-12-22
PBUT04 - Grid Automation | 107939 | 740662 | 30059 | 30059-002 | 14F003510000 | Caguas ST G-2 Dist Autom | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  |  | 2023-12-13
PBUT04 - Grid Automation | 107997 | 752502 | 30059 | 30059-001C | 14F003520000 | Caguas ST G-3 Dist Autom | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued
PBUT04 - Grid Automation |  |  | 30059 |  | 14F003530000 | Caguas ST G-4 Distr Automation | Inactive | Inactive
PBUT04 - Grid Automation |  |  | 30059 |  | 14F003540000 | Caguas ST G-5 Dist Automation | Inactive | Inactive
PBUT04 - Grid Automation | 107997 | 752502 | 30059 | 30059-001C | 14F003550000 | Caguas ST G-6 Distr Automation | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued
PBUT04 - Grid Automation | 107939 | 740662 | 30059 | 30059-002 | 14F003560000 | Caguas ST G-7 Distr Automation | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  |  | 2023-12-13
PBUT04 - Grid Automation | 107939 | 740662 | 30059 | 30059-002 | 14F003570000 | Caguas ST G-8 Distr Automation | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  |  | 2023-12-13
PBUT04 - Grid Automation |  |  | 30059 |  | 14F003580000 | Yunque2305-01 Supply Dist Auto | Inactive | Inactive
PBUT04 - Grid Automation | 107826 | 705657 | 30059 | 30059-003 | 14F003590000 | Mayag S T Group 4-Dist Automa | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  |  | 2023-10-31
PBUT04 - Grid Automation |  |  | 30059 |  | 14F004670000 | Arecibo Short TermGroup3 Autom | Inactive | Inactive
PBUT04 - Grid Automation |  |  | 30059 |  | 14F004680000 | Arecibo Short TermGroup4 Autom | Inactive | Inactive
PBUT04 - Grid Automation | 107939 | 740662 | 30059 | 30059-002 | 14F004690000 | Arecibo Short TermGroup5 Autom | Active | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  |  | 2023-12-13
PBUT04 - Grid Automation |  |  | 30059 |  | 14F004700000 | Arecibo Short TermGroup6 Autom | Inactive | Inactive
PBUT04 - Grid Automation | 107939 | 740662 | 30059 | 30059-002 | 14F004710000 | Arecibo Short TermGroup7 Autom | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  |  | 2023-12-13
PBUT04 - Grid Automation |  |  | 30059 |  | 14F004720000 | Arecibo Short TermGroup8 Autom | Inactive | Inactive
PBUT04 - Grid Automation |  |  | 30059 |  | 14F004730000 | Arecibo Short TermGroup9 Autom | Inactive | Inactive
PBUT04 - Grid Automation |  |  | 30059 |  | 14F004740000 | Arecibo Short TermGroup10 Auto | Inactive | Inactive
PBUT04 - Grid Automation |  |  | 30059 |  | 14F004750000 | Arecibo Short TermGroup11 Auto | Inactive | Inactive
PBUT04 - Grid Automation |  |  | 30059 |  | 14F004760000 | Arecibo Short TermGroup12 Auto | Inactive | Inactive
PBUT04 - Grid Automation | 107939 | 740662 | 30059 | 30059-002 | 14F004770000 | Bayamón Short TermGroup4 Autom | Active | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  |  | 2023-12-13
PBUT04 - Grid Automation |  |  | 30059 |  | 14F004780000 | Bayamón Short TermGroup5 Autom | Inactive | Inactive
PBUT04 - Grid Automation |  |  | 30059 |  | 14F004790000 | Bayamón Short TermGroup6 Autom | Inactive | Inactive
PBUT04 - Grid Automation |  |  | 30059 |  | 14F004800000 | Bayamón Short TermGroup7 Autom | Inactive | Inactive
PBUT04 - Grid Automation | 107939 | 740662 | 30059 | 30059-002 | 14F004810000 | Bayamón Short TermGroup8 Autom | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  |  | 2023-12-13
PBUT04 - Grid Automation | 107939 | 740662 | 30059 | 30059-002 | 14F004820000 | Bayamon Short TermGroup9 Autom | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  |  | 2023-12-13
PBUT04 - Grid Automation |  |  | 30059 |  | 14F004830000 | Caguas Short TermGroup9 Autom | Inactive | Inactive
PBUT04 - Grid Automation | 107939 | 740662 | 30059 | 30059-002 | 14F004840000 | Caguas Short TermGroup10 Autom | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  |  | 2023-12-13
PBUT04 - Grid Automation |  |  | 30059 |  | 14F004850000 | Caguas Short TermGroup11 Autom | Inactive | Inactive
PBUT04 - Grid Automation |  |  | 30059 |  | 14F004860000 | Caguas Short TermGroup12 Autom | Inactive | Inactive
PBUT04 - Grid Automation |  |  | 30059 |  | 14F004870000 | Caguas Short TermGroup13 Autom | Inactive | Inactive
PBUT04 - Grid Automation |  |  | 30059 |  | 14F004880000 | Caguas Short TermGroup14 Autom | Inactive | Inactive
PBUT04 - Grid Automation |  |  | 30059 |  | 14F004890000 | Caguas Short TermGroup15 Autom | Inactive | Inactive
PBUT04 - Grid Automation | 107826 | 705657 | 30059 | 30059-003 | 14F004900000 | Mayaguez Short TermGroup5 Aut | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  |  | 2023-10-31
PBUT04 - Grid Automation | 107826 | 705657 | 30059 | 30059-003 | 14F004910000 | Mayaguez Short TermGroup6 Auto | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  |  | 2023-10-31
PBUT04 - Grid Automation | 107826 | 705657 | 30059 | 30059-003 | 14F004920000 | Mayaguez Short TermGroup7 Aut | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  |  | 2023-10-31
PBUT04 - Grid Automation | 107826 | 705657 | 30059 | 30059-003 | 14F004930000 | Mayaguez Short TermGroup8 Aut | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  |  | 2023-10-31
PBUT04 - Grid Automation | 107826 | 705657 | 30059 | 30059-003 | 14F004940000 | Mayaguez Short TermGroup9 Aut | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  |  | 2023-10-31
PBUT04 - Grid Automation | 107826 | 705657 | 30059 | 30059-003 | 14F004950000 | Mayaguez Short TermGroup10 Aut | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  |  | 2023-10-31
PBUT04 - Grid Automation | 107826 | 705657 | 30059 | 30059-003 | 14F004960000 | Mayaguez Short TermGroup11 Aut | Active | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  |  | 2023-10-31
PBUT04 - Grid Automation |  |  | 30059 |  | 14F004970000 | Mayaguez Short TermGroup12 Aut | Inactive | Inactive
PBUT04 - Grid Automation | 107826 | 705657 | 30059 | 30059-003 | 14F004980000 | Mayaguez Short TermGroup13 Aut | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  |  | 2023-10-31
PBUT04 - Grid Automation | 107826 | 705657 | 30059 | 30059-003 | 14F004990000 | Mayaguez Short TermGroup14 Aut | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  |  | 2023-10-31
PBUT04 - Grid Automation |  |  | 30059 |  | 14F005000000 | Ponce Short TermGroup3 Autom | Inactive | Inactive
PBUT04 - Grid Automation |  |  | 30059 |  | 14F005010000 | Ponce Short TermGroup4 Autom | Inactive | Inactive
PBUT04 - Grid Automation |  |  | 30059 |  | 14F005020000 | Ponce Short TermGroup5 Autom | Inactive | Inactive
PBUT04 - Grid Automation |  |  | 30059 |  | 14F005030000 | Ponce Short TermGroup6 Autom | Inactive | Inactive
PBUT04 - Grid Automation |  |  | 30059 |  | 14F005040000 | Ponce Short TermGroup7 Autom | Inactive | Inactive
PBUT04 - Grid Automation |  |  | 30059 |  | 14F005050000 | Ponce Short TermGroup8 Autom | Inactive | Inactive
PBUT04 - Grid Automation |  |  | 30059 |  | 14F005060000 | Ponce Short TermGroup9 Autom | Inactive | Inactive
PBUT04 - Grid Automation |  |  | 30059 |  | 14F005070000 | Ponce Short TermGroup10 Autom | Inactive | Inactive
PBUT04 - Grid Automation | 107939 | 740662 | 30059 | 30059-002 | 14F005080000 | Ponce Short TermGroup11 Autom | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  |  | 2023-12-13
PBUT04 - Grid Automation | 107939 | 740662 | 30059 | 30059-002 | 14F005090000 | Ponce Short TermGroup12 Autom | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  |  | 2023-12-13
PBUT04 - Grid Automation |  |  | 30059 |  | 14F005100000 | Ponce Short TermGroup13 Autom | Inactive | Inactive
PBUT04 - Grid Automation | 107947 | 741678 | 30059 | 30059-004 | 14F005110000 | San Juan Short TermGroup4 Aut | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  |  | 2023-12-22
PBUT04 - Grid Automation | 107947 | 741678 | 30059 | 30059-004 | 14F005120000 | San Juan Short TermGroup5 Aut | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  |  | 2023-12-22
PBUT04 - Grid Automation | 107947 | 741678 | 30059 | 30059-004 | 14F005130000 | San Juan Short TermGroup6 Aut | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  |  | 2023-12-22
PBUT04 - Grid Automation |  |  | 30059 |  | 14F005140000 | San Juan Short TermGroup7 Aut | Inactive | Inactive
PBUT04 - Grid Automation | 107947 | 741678 | 30059 | 30059-004 | 14F005150000 | San Juan Short TermGroup8 Aut | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  |  | 2023-12-22
PBUT04 - Grid Automation | 107781 | 688623 | 30059 | 30059-001A | 14F005160000 | San Juan Short TermGroup9 Aut | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  |  | 2023-05-01
PBUT04 - Grid Automation | 107947 | 741678 | 30059 | 30059-004 | 14F005170000 | San Juan Short TermGroup10 Aut | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  |  | 2023-12-22
PBUT04 - Grid Automation | 107947 | 741678 | 30059 | 30059-004 | 14F005180000 | San Juan Short TermGroup11 Aut | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  |  | 2023-12-22
PBUT04 - Grid Automation | 107947 | 741678 | 30059 | 30059-004 | 14F005190000 | San Juan Short TermGroup12 Aut | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  |  | 2023-12-22
PBUT04 - Grid Automation |  |  | 30059 |  | 14F005200000 | Trans & Distribut Automation | Inactive | Inactive
PBUT04 - Grid Automation |  |  | 20010-001 | 20010-001 | 14F019070000 | 38kV Reclosers Tline 4800 | Inactive | Inactive | [5 empty] | 2025-11-12 08:00 |  | 2026-01-29 17:00
PBUT04 - Grid Automation |  |  | 20010-002 | 20010-002 | 14F019080000 | 38kV Reclosers Tline 1500 | Inactive | Inactive | [5 empty] | 2025-06-16 08:00 | 2025-06-16 08:00 | 2024-12-20 17:00
PBUT04 - Grid Automation |  |  | 20010-003 | 20010-003 | 14F019090000 | 38kV Reclosers TLine 3700 | Inactive | Inactive | [7 empty] | 2025-06-04 17:00
PBUT04 - Grid Automation |  |  | 20010-004 | 20010-004 | 14F019100000 | 38kV Reclosers TLine 15700 | Inactive | Inactive | [7 empty] | 2024-06-21 17:00
PBUT04 - Grid Automation | 108092 | 805519 | 20010-005 | 20010-005 | 14F019110000 | 38kV Reclosers TLine 1900 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2025-03-04 17:00 | 2025-03-04
PBUT04 - Grid Automation | 108091 | 805517 | 20010-006 | 20010-006 | 14F019120000 | 38kV Reclosers TLine 2100 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2025-03-04 17:00 | 2025-03-04
PBUT04 - Grid Automation | 108093 | 805521 | 20010-007 | 20010-007 | 14F019130000 | 38kV Reclosers TLine 7800 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2024-11-22 17:00 | 2025-02-07
PBUT04 - Grid Automation |  |  | 20010-008 | 20010-008 | 14F019140000 | 38kV Reclosers TLine 800 | Inactive | Inactive | [7 empty] | 2026-01-30 17:00
PBUT04 - Grid Automation |  |  | 20010-009 | 20010-009 | 14F019150000 | 38kV Reclosers TLine 13400 | Inactive | Inactive | [7 empty] | 2026-01-29 17:00
PBUT04 - Grid Automation |  |  | 20010-010 | 20010-010 | 14F019160000 | 38kV Reclosers TLine 12600 | Inactive | Inactive | [7 empty] | 2026-01-29 17:00
PBUT04 - Grid Automation |  |  | 20010-011 | 20010-011 | 14F019170000 | 38kV Reclosers TLine 100 | Inactive | Inactive | [7 empty] | 2025-04-18 12:00
PBUT04 - Grid Automation |  |  | 20010-012 | 20010-012 | 14F019180000 | 38kV Reclosers TLine 8100 | Inactive | Inactive | [7 empty] | 2024-12-20 17:00
PBUT04 - Grid Automation |  |  | 20010-013 | 20010-013 | 14F019190000 | 38kV Reclosers TLine 1600 | Inactive | Inactive | [7 empty] | 2025-02-24 17:00
PBUT04 - Grid Automation |  |  | 20010-014 | 20010-014 | 14F019200000 | 38kV Reclosers TLine 2000 | Inactive | Inactive | [7 empty] | 2026-01-29 17:00
PBUT04 - Grid Automation |  |  | 20010-015 | 20010-015 | 14F019210000 | 38kV Reclosers TLine 2200 | Inactive | Inactive | [7 empty] | 2025-04-03 17:00
PBUT04 - Grid Automation |  |  | 20010-016 | 20010-016 | 14F019220000 | 38kV Reclosers TLine 3100 | Inactive | Inactive | [7 empty] | 2025-04-10 17:00
PBUT04 - Grid Automation |  |  | 20010-017 | 20010-017 | 14F019230000 | 38kV Reclosers TLine 3000 | Inactive | Inactive | [7 empty] | 2026-01-30 17:00
PBUT04 - Grid Automation |  |  | 20010-018 | 20010-018 | 14F019240000 | 38kV Reclosers TLine 3600 | Inactive | Inactive | [7 empty] | 2025-04-10 17:00
PBUT04 - Grid Automation |  |  | 20010-019 | 20010-019 | 14F019250000 | 38kV Reclosers TLine 6500 | Inactive | Inactive | [7 empty] | 2024-12-20 17:00
PBUT04 - Grid Automation |  |  | 20010-020 | 20010-020 | 14F019260000 | 38kV Reclosers TLine 5600 | Inactive | Inactive | [7 empty] | 2024-12-20 17:00
PBUT04 - Grid Automation |  |  | 20010-021 | 20010-021 | 14F019270000 | 38kV Reclosers TLine 8200 | Inactive | Inactive | [7 empty] | 2026-01-30 17:00
PBUT04 - Grid Automation |  |  | 20010-022 | 20010-022 | 14F019280000 | 38kV Reclosers TLine 3200 | Inactive | Inactive | [7 empty] | 2025-04-17 17:00
PBUT04 - Grid Automation | 11862 | 679006 | 10163 | 10163 | 14F019640000 | Test Laboratory Equipment | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  |  | 2022-11-02
PBUT04 - Grid Automation |  |  | 20010-023 | 20010-023 | 14F021140000 | 38kv Reclosures TLine 300 | Inactive | Inactive | CAP1 | [6 empty] | 2026-08-05 17:00
PBUT04 - Grid Automation |  |  | 20010-024 | 20010-024 | 14F021150000 | 38kv Reclosures TLine 500 | Inactive | Inactive | CAP1 | [6 empty] | 2026-07-31 17:00
PBUT04 - Grid Automation |  |  | 20010-025 | 20010-025 | 14F021160000 | 38kv Reclosures TLine 700 | Inactive | Inactive | CAP1 | [6 empty] | 2027-08-30 17:00
PBUT04 - Grid Automation |  |  | 20010-026 | 20010-026 | 14F021170000 | 38kv Reclosures TLine 2400 | Inactive | Inactive | CAP1 | [6 empty] | 2026-07-31 17:00
PBUT04 - Grid Automation |  |  | 20010-027 | 20010-027 | 14F021180000 | 38kv Reclosures TLine 2600 | Inactive | Inactive | CAP1 | [6 empty] | 2027-08-30 17:00
PBUT04 - Grid Automation |  |  | 20010-028 | 20010-028 | 14F021190000 | 38kv Reclosures TLine 2700 | Inactive | Inactive | CAP1 | [6 empty] | 2026-07-31 17:00
PBUT04 - Grid Automation |  |  | 20010-029 | 20010-029 | 14F021200000 | 38kv Reclosures TLine 2800 | Inactive | Inactive | CAP1 | [6 empty] | 2026-07-31 17:00
PBUT04 - Grid Automation |  |  | 20010-030 | 20010-030 | 14F021210000 | 38kv Reclosures TLine 4700 | Inactive | Inactive | CAP1 | [6 empty] | 2026-07-31 17:00
PBUT04 - Grid Automation |  |  | 20010-031 | 20010-031 | 14F021220000 | 38kv Reclosures TLine 5200 | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2026-02-06 17:00
PBUT04 - Grid Automation |  |  | 20010-032 | 20010-032 | 14F021230000 | 38kv Reclosures TLine 5400 | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2027-03-01 17:00
PBUT04 - Grid Automation |  |  | 20010-033 | 20010-033 | 14F021240000 | 38kv Reclosures TLine 6000 | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2026-02-06 17:00
PBUT04 - Grid Automation |  |  | 20010-034 | 20010-034 | 14F021250000 | 38kv Reclosures TLine 7100 | Inactive | Inactive | CAP1 | [6 empty] | 2026-07-31 17:00
PBUT04 - Grid Automation |  |  | 20010-035 | 20010-035 | 14F021260000 | 38kv Reclosures TLine 8500 | Inactive | Inactive | CAP1 | [6 empty] | 2026-07-31 17:00
PBUT04 - Grid Automation |  |  | 20010-036 | 20010-036 | 14F021270000 | 38kv Reclosures TLine 8900 | Inactive | Inactive | CAP1 | [6 empty] | 2026-07-31 17:00
PBUT04 - Grid Automation |  |  | 20010-037 | 20010-037 | 14F021280000 | 38kv Reclosures TLine 9400 | Inactive | Inactive | CAP1 | ISSUE | [5 empty] | 2026-02-06 17:00
PBUT04 - Grid Automation |  |  | 20010-038 | 20010-038 | 14F021290000 | 38kv Reclosures TLine 10000 | Inactive | Inactive | CAP1 | [6 empty] | 2026-07-31 17:00
PBUT04 - Grid Automation |  |  | 20010-039 | 20010-039 | 14F021300000 | 38kv Reclosures TLine 13700 | Inactive | Inactive | CAP1 | [6 empty] | 2026-07-31 17:00
PBUT04 - Grid Automation |  | Pending | 30078 | 30078 | 14F021940000 | DOE Distrib.Automation(DOE P5) | Active
PBUT04 - Grid Automation |  |  | 30001 | 30001 | 14N000610000 | Reliability Improvement Ini | Inactive
PBUT04 - Grid Automation |  |  | 30002 | 30002 | 14N000620000 | Distribution Automation NME | Inactive
PBUT04 - Grid Automation |  |  | 30005 | 30005 | 14N000680000 | Fusing Strategy | Active | Inactive
PBUT04 - Grid Automation |  |  | 30001 | 30001 | 14N001050000 | Ln Exten 6705-01/02 Balan Load | Cancel
PBUT04 - Grid Automation |  |  | 30001-001 | 30001-001 | 14N001060000 | Reliability Hotspot Repair | Closed | Inactive
PBUT04 - Grid Automation |  |  | 30001-002 | 30001-002 | 14N001070000 | Worst Performing Feeders | Active | Active
PBUT04 - Grid Automation |  |  | 30001-003 | 30001-003 | 14N001080000 | Reliability Regional Requests | Active | Inactive
PBUT04 - Grid Automation |  |  | 30001-004 | 30001-004 | 14N001160000 | FCI Initiative | Active | Inactive
PBUT04 - Grid Automation |  |  | 30075 | 30075 | 14N001410000 | Fuse Cutout Initiative-NFC | Active
PBUT04 - Grid Automation |  |  | 30005 | 20017-001 | 14N001670000 | DOE Distribution Automation | Active | Inactive | [5 empty] | 2023-05-04 08:00 | 2023-05-04 08:00
PBUT04 - Grid Automation | 1294 | 83182 | 90102 | 90102 | 15F019720000 | CAT Z - PBUT4 | Active |  |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  |  | 2020-02-05 12:48
PBUT05 - Distr Streetlighting |  |  | 80002 | 80002 | 10N000060000 | Street Light Audit/Tracking | Active
PBUT05 - Distr Streetlighting |  |  |  |  | 14F001690000 | Streetlighting Program | Inactive
PBUT05 - Distr Streetlighting |  |  | 50000 |  | 14F001700000 | Streetlight Region Ponce | Cancel | Active
PBUT05 - Distr Streetlighting |  |  | 50000 |  | 14F001710000 | Streetlight Region Mayaguez | Cancel | Active
PBUT05 - Distr Streetlighting |  |  | 50000 |  | 14F001720000 | Streetlight Region Bayamon | Cancel | Active
PBUT05 - Distr Streetlighting |  |  | 50000 |  | 14F001730000 | Streetlight Region Caguas | Cancel | Active
PBUT05 - Distr Streetlighting |  |  | 50000 |  | 14F001740000 | Streetlight Region Arecibo | Cancel | Active
PBUT05 - Distr Streetlighting | 10539 | 542688 | 50000 | 50000-001 | 14F003630000 | Streetlighting Program- Aguada | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2022-03-08 17:00 | 2022-03-08 | 2022-05-05 12:44
PBUT05 - Distr Streetlighting | 10499 | 542690 | 50000 | 50000-005 | 14F003680000 | Streetlighting Prog - Maunabo | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2022-02-04 17:00 | 2022-02-04 | 2022-05-05 11:20
PBUT05 - Distr Streetlighting | 10515 | 542517 | 50000 | 50000-004 | 14F003690000 | Streetlighting Prog - Luquillo | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2022-03-08 17:00 | 2022-03-08 | 2022-05-20 12:05
PBUT05 - Distr Streetlighting | 10521 | 542687 | 50000 | 50000-003 | 14F003700000 | Streetlighting Program - Lajas | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2022-03-08 17:00 | 2022-03-08 | 2022-05-20 12:05
PBUT05 - Distr Streetlighting | 10538 | 542756 | 50000 | 50000-002 | 14F003710000 | Streetlighting Progr - Guánica | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2022-03-08 17:00 | 2022-03-08 | 2022-05-26 11:24
PBUT05 - Distr Streetlighting | 10884 | 659623 | 50000 | 50000-007 | 14F004180000 | Streetlighting Program-Cataño | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2022-07-06 17:00 | 2022-07-07 | 2022-12-27 11:53
PBUT05 - Distr Streetlighting | 11097 | 660437 | 50000 | 50000-010 | 14F004190000 | Streetlighting Program-Manatí | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2022-07-29 17:00 | 2022-07-29 | 2023-01-24 13:14
PBUT05 - Distr Streetlighting | 10857 | 660239 | 50000 | 50000-012 | 14F004200000 | Streetlighting Program-Villalb | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2022-07-01 17:00 | 2022-07-07 | 2022-08-24 10:30
PBUT05 - Distr Streetlighting | 10876 | 659715 | 50000 | 50000-006 | 14F004210000 | Streetlighting Program-Aibonit | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2022-07-01 17:00 | 2022-07-07 | 2022-12-27 11:53
PBUT05 - Distr Streetlighting | 11318 | 659968 | 50000 | 50000-011 | 14F004330000 | Streetlighting Prog-San German | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2023-03-13 17:00 | 2023-03-14 | 2023-05-04 11:30
PBUT05 - Distr Streetlighting | 11095 | 660227 | 50000 | 50000-009 | 14F004340000 | Streetlighting Program-Hatillo | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2022-08-04 08:00 | 2022-08-08 | 2023-01-24 13:14
PBUT05 - Distr Streetlighting | 11099 | 659625 | 50000 | 50000-008 | 14F004350000 | Streetlighting Program-Dorado | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2022-08-18 17:00 | 2022-09-08 | 2023-01-24 13:14
PBUT05 - Distr Streetlighting | 11530 | 671396 | 50000 | 50000-052 | 14F004520000 | Streetlighting Program-Utuado | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2023-06-27 17:00 | 2023-07-01
PBUT05 - Distr Streetlighting | 11522 | 671502 | 50000 | 50000-036 | 14F004530000 | Streetlighting Program-Yabucoa | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2023-06-27 17:00 | 2023-07-01 | 2023-12-29 12:31
PBUT05 - Distr Streetlighting | 11529 | 671400 | 50000 | 50000-021 | 14F004540000 | StreetlightingProg-Barceloneta | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2023-06-27 17:00 | 2023-07-01
PBUT05 - Distr Streetlighting | 11317 | 673504 | 50000 | 50000-013 | 14F004630000 | Streetlighting Program-Gurabo | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2023-02-28 17:00 | 2023-02-28 | 2023-05-17 11:31
PBUT05 - Distr Streetlighting | 11519 | 666894 | 50000 | 50000-014 | 14F008790000 | Streetlighting Prog-San Juan | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2023-06-27 17:00 | 2023-07-01
PBUT05 - Distr Streetlighting | 11351 | 679039 | 50000 | 50000-016 | 14F009270000 | Streetlighting Program-Caguas | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2023-03-30 17:00 | 2023-03-31 | 2023-07-05 11:36
PBUT05 - Distr Streetlighting | 11319 | 690545 | 50000 | 50000-020 | 14F012780000 | Streetlighting Prog-Aguadilla | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2023-03-13 17:00 | 2023-03-13 | 2023-05-17 11:31
PBUT05 - Distr Streetlighting | 11535 | 678795 | 50000 | 50000-015 | 14F012790000 | Streetlighting Program-Arecibo | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2023-06-27 17:00 | 2023-06-30
PBUT05 - Distr Streetlighting | 11540 | 679780 | 50000 | 50000-022 | 14F012800000 | Streetlighting Program-Bayamon | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2023-08-28 17:00 | 2023-08-08 | 2023-11-03 11:30
PBUT05 - Distr Streetlighting | 11533 | 678789 | 50000 | 50000-018 | 14F012810000 | Streetlighting Progra-Carolina | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2023-06-28 17:00 | 2023-07-01 | 2023-11-03 11:30
PBUT05 - Distr Streetlighting | 11552 | 690483 | 50000 | 50000-024 | 14F012820000 | Streetlighting Program - Cayey | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2023-08-28 17:00 | 2023-08-23
PBUT05 - Distr Streetlighting | 11531 | 690721 | 50000 | 50000-025 | 14F012830000 | Streetlighting Program-Guayama | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2023-06-27 17:00 | 2023-07-01
PBUT05 - Distr Streetlighting | 11532 | 678793 | 50000 | 50000-017 | 14F012840000 | Streetlighting Progra-Mayaguez | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2023-06-27 17:00 | 2023-07-01 | 2023-11-03 11:30
PBUT05 - Distr Streetlighting | 11527 | 678794 | 50000 | 50000-019 | 14F012850000 | Streetlighting Program - Ponce | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2023-06-27 17:00 | 2023-06-30
PBUT05 - Distr Streetlighting | 11326 | 691702 | 50000 | 50000-023 | 14F012860000 | Streetlight Prog-Trujillo Alto | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2023-03-13 17:00 | 2023-03-13 | 2023-05-17 11:31
PBUT05 - Distr Streetlighting | 11683 | 690480 | 50000 | 50000-026 | 14F012870000 | Streetlighting Program-Humacao | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2023-09-29 17:00 | 2023-09-28
PBUT05 - Distr Streetlighting | 11572 | 686482 | 50000 | 50000-027 | 14F012880000 | Streetlighting Program-Isabela | Active | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2023-09-29 17:00 | 2023-09-18
PBUT05 - Distr Streetlighting | 11560 | 698570 | 50000 | 50000-035 | 14F013750000 | Streetlighting Program-Corozal | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2023-08-28 17:00 | 2023-08-23 | 2023-12-29 12:31
PBUT05 - Distr Streetlighting | 11727 | 701472 | 50000 | 50000-076 | 14F013760000 | Streetlighting Program-Comerio | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2024-02-28 17:00 | 2024-02-28 | 2024-05-10 10:17
PBUT05 - Distr Streetlighting | 11693 | 701473 | 50000 | 50000-034 | 14F013770000 | Streetlighting Progr-Canovanas | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2023-09-29 12:00 | 2023-09-28
PBUT05 - Distr Streetlighting | 11634 | 693543 | 50000 | 50000-030 | 14F013780000 | Streetlighting Program-Juncos | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2023-11-03 17:00 | 2023-12-01
PBUT05 - Distr Streetlighting | 11582 | 698522 | 50000 | 50000-047 | 14F013790000 | Streetlighting Program-Vieques | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2023-09-29 17:00 | 2023-09-28
PBUT05 - Distr Streetlighting | 11629 | 698579 | 50000 | 50000-077 | 14F013800000 | Streetlighting Progr-Orocovis | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2023-12-01 17:00 | 2023-12-01 | 2024-03-22 10:16
PBUT05 - Distr Streetlighting | 11525 | 698427 | 50000 | 50000-075 | 14F013810000 | Streetlighting Program-Maricao | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2023-06-27 17:00 | 2023-07-01
PBUT05 - Distr Streetlighting | 11526 | 698439 | 50000 | 50000-074 | 14F013820000 | Streetlighting Prog-Las Marias | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2023-06-27 17:00 | 2023-06-30 | 2023-11-03 11:30
PBUT05 - Distr Streetlighting | 11523 | 698432 | 50000 | 50000-072 | 14F013830000 | Streetlighting Prog-Hormiguero | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2023-06-27 17:00 | 2023-06-30
PBUT05 - Distr Streetlighting | 11518 | 698458 | 50000 | 50000-038 | 14F013840000 | Streetlighting ProgR-Guaynabo | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2023-06-27 17:00 | 2023-07-01 | 2023-11-03 11:30
PBUT05 - Distr Streetlighting | 11344 | 698424 | 50000 | 50000-071 | 14F013850000 | Streetlighting Program-Florida | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2023-03-31 17:00 | 2023-03-31 | 2023-10-23 11:32
PBUT05 - Distr Streetlighting | 11668 | 697183 | 50000 | 50000-033 | 14F013860000 | Streetlighting Progr-Vega Baja | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2023-12-27 17:00 | 2023-12-27
PBUT05 - Distr Streetlighting | 11547 | 693788 | 50000 | 50000-031 | 14F013870000 | Streetlighting Progra-Toa Alta | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2023-08-28 17:00 | 2023-08-23
PBUT05 - Distr Streetlighting | 11685 | 693615 | 50000 | 50000-029 | 14F013880000 | Streetlighting Prog-Rio Grande | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2023-09-29 17:00 | 2023-09-28
PBUT05 - Distr Streetlighting | 11636 | 703535 | 50000 | 50000-032 | 14F013890000 | Streetlighting Progra-Toa Baja | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2023-11-03 17:00 | 2023-12-01 | 2024-06-18 11:28
PBUT05 - Distr Streetlighting | 11576 | 699814 | 50000 | 50000-028 | 14F013900000 | Streetlighting Prog-Juana Diaz | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2023-09-29 17:00 | 2023-09-28
PBUT05 - Distr Streetlighting | 11680 | 698511 | 50000 | 50000-067 | 14F013910000 | Streetlighting Program-Culebra | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2023-12-01 17:00 | 2023-12-01 | 2024-04-12 11:19
PBUT05 - Distr Streetlighting | 11691 | 704793 | 50000 | 50000-048 | 14F014590000 | Streetlighting Program - Yauco | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2024-01-19 17:00 | 2024-01-22
PBUT05 - Distr Streetlighting | 11728 | 704862 | 50000 | 50000-054 | 14F014600000 | Streetlighting Program-Fajardo | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2024-02-28 17:00 | 2024-02-28
PBUT05 - Distr Streetlighting | 11633 | 704938 | 50000 | 50000-055 | 14F014610000 | Streetlightng Prog-Las Piedras | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2023-12-01 17:00 | 2023-12-01 | 2024-04-12 11:19
PBUT05 - Distr Streetlighting | 11658 | 704849 | 50000 | 50000-057 | 14F014620000 | Streetlighting Program-Naguabo | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2023-12-27 17:00 | 2023-12-27 | 2024-05-10 10:17
PBUT05 - Distr Streetlighting | 11650 | 704868 | 50000 | 50000-050 | 14F014630000 | Streetlighting Program - Ceiba | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2023-12-27 17:00 | 2023-12-27 | 2024-07-08 11:28
PBUT05 - Distr Streetlighting | 11675 | 704921 | 50000 | 50000-049 | 14F014640000 | Streetlghtng Prog-Barranquitas | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2024-01-19 17:00 | 2024-01-19 | 2024-05-31 11:36
PBUT05 - Distr Streetlighting | 11737 | 704741 | 50000 | 50000-056 | 14F014650000 | Streetlighting Program - Moca | Active | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2024-02-28 17:00 | 2024-02-28
PBUT05 - Distr Streetlighting | 11638 | 704757 | 50000 | 50000-051 | 14F014660000 | Streetlighting Prog-Sta Isabel | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2023-11-03 17:00 | 2023-12-01
PBUT05 - Distr Streetlighting | 11524 | 704679 | 50000 | 50000-042 | 14F014670000 | Streetlighting Program - Coamo | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2023-06-27 17:00 | 2023-06-30 | 2023-11-03 11:30
PBUT05 - Distr Streetlighting | 11651 | 704931 | 50000 | 50000-041 | 14F014680000 | Streetlighting Program - Camuy | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2023-11-03 17:00 | 2023-12-01
PBUT05 - Distr Streetlighting | 11626 | 704744 | 50000 | 50000-044 | 14F014690000 | Streetlighting Prog-San Sebast | Active | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2023-11-03 17:00 | 2023-12-01
PBUT05 - Distr Streetlighting | 11664 | 704943 | 50000 | 50000-045 | 14F014700000 | Streetlighting Prog-Naranjito | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2023-12-27 17:00 | 2023-12-27 | 2024-04-12 11:19
PBUT05 - Distr Streetlighting | 11635 | 704929 | 50000 | 50000-046 | 14F014710000 | Streetlighting Prog-SanLorenzo | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2023-12-01 17:00 | 2023-12-01
PBUT05 - Distr Streetlighting | 11711 | 704927 | 50000 | 50000-053 | 14F014720000 | Streetlighting Program-Añasco | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2024-01-19 17:00 | 2024-01-19 | 2024-07-08 11:28
PBUT05 - Distr Streetlighting | 11624 | 713795 | 50000 | 50000-073 | 14F017010000 | Streetlighting Program - Lares | Active | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2023-12-01 17:00 | 2023-12-01
PBUT05 - Distr Streetlighting | 11630 | 714641 | 50000 | 50000-058 | 14F017260000 | Streetlighting Program-Rincon | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2023-11-03 17:00 | 2023-12-01 | 2026-03-01 18:15
PBUT05 - Distr Streetlighting | 11627 | 709631 | 50000 | 50000-043 | 14F017270000 | Streetlighting Program-Morovis | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2023-12-01 17:00 | 2023-12-01 | 2024-03-22 10:16
PBUT05 - Distr Streetlighting | 11734 | 724698 | 50000 | 50000-070 | 14F017980000 | Streetlighting Progr-Adjuntas | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2024-02-28 17:00 | 2024-02-28 | 2024-06-18 11:28
PBUT05 - Distr Streetlighting | 11671 | 724703 | 50000 | 50000-066 | 14F017990000 | Streetlighting Program-Arroyo | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2023-12-28 17:00 | 2023-12-28 | 2024-06-18 11:28
PBUT05 - Distr Streetlighting | 11733 | 724941 | 50000 | 50000-065 | 14F018000000 | Streetlighting Prog-Aguas Buen | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2024-02-28 17:00 | 2024-02-28
PBUT05 - Distr Streetlighting | 11684 | 724603 | 50000 | 50000-037 | 14F018010000 | Streetlighting Prog-Cabo Rojo | Active | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2024-01-19 17:00 | 2024-01-19
PBUT05 - Distr Streetlighting | 11730 | 724669 | 50000 | 50000-060 | 14F018020000 | Streetlighting Program-Ciales | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2024-02-28 17:00 | 2024-02-28
PBUT05 - Distr Streetlighting | 11725 | 724825 | 50000 | 50000-061 | 14F018030000 | Streetlighting Program - Cidra | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2024-02-28 17:00 | 2024-02-28 | 2024-05-10 10:17
PBUT05 - Distr Streetlighting | 11732 | 724605 | 50000 | 50000-068 | 14F018040000 | Streetlighting Prog-Guayanilla | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2024-02-28 17:00 | 2024-02-28
PBUT05 - Distr Streetlighting | 11735 | 724600 | 50000 | 50000-062 | 14F018050000 | Streetlighting Program-Jayuya | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2024-02-28 17:00 | 2024-02-28 | 2024-05-31 11:36
PBUT05 - Distr Streetlighting | 11692 | 724828 | 50000 | 50000-039 | 14F018060000 | Streetlighting Program - Loíza | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2024-01-19 17:00 | 2024-01-19
PBUT05 - Distr Streetlighting | 11731 | 724670 | 50000 | 50000-078 | 14F018070000 | Streetlighting Prog - Patillas | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2024-02-28 17:00 | 2024-02-28
PBUT05 - Distr Streetlighting | 11736 | 724781 | 50000 | 50000-063 | 14F018080000 | Streetlighting Prog - Peñuelas | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2024-02-28 17:00 | 2024-02-28
PBUT05 - Distr Streetlighting | 11729 | 724716 | 50000 | 50000-069 | 14F018090000 | Streetlighting Prog-Quebradill | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2024-02-28 17:00 | 2024-02-28
PBUT05 - Distr Streetlighting | 11738 | 724599 | 50000 | 50000-059 | 14F018100000 | Streetlighting Prog-Sábana Gra | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2024-02-28 17:00 | 2024-02-28
PBUT05 - Distr Streetlighting | 11739 | 724601 | 50000 | 50000-064 | 14F018110000 | Streetlighting Program-Salinas | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2024-02-28 17:00 | 2024-02-28 | 2024-07-08 11:28
PBUT05 - Distr Streetlighting | 11673 | 724938 | 50000 | 50000-040 | 14F018120000 | Streetlighting Prog-Vega Alta | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2024-01-19 17:00 | 2024-01-22 | 2024-05-10 10:17
PBUT05 - Distr Streetlighting | 11780 | 734859 | 50000 | 50000-086 | 14F018510000 | Streetlighting Prog-AguadillP2 | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2024-03-28 17:00 | 2024-03-27
PBUT05 - Distr Streetlighting | 11834 | 735338 | 50000 | 50000-104 | 14F018520000 | Streetlighting Prog-AguadillP3 | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2024-05-31 17:00 | 2024-05-31
PBUT05 - Distr Streetlighting | 11775 | 735131 | 50000 | 50000-081 | 14F018530000 | Streetlighting Prog-Arecibo P2 | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2024-03-28 17:00 | 2024-03-27
PBUT05 - Distr Streetlighting | 11837 | 734853 | 50000 | 50000-099 | 14F018540000 | Streetlighting Prog-Arecibo P3 | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2024-05-31 17:00 | 2024-05-31
PBUT05 - Distr Streetlighting | 11804 | 735470 | 50000 | 50000-087 | 14F018550000 | Streetlighting Prog-Bayamon P2 | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2024-04-30 17:00 | 2024-04-30
PBUT05 - Distr Streetlighting | 11833 | 735472 | 50000 | 50000-105 | 14F018560000 | Streetlighting Prog-Bayamon P3 | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2024-05-31 17:00 | 2024-05-31
PBUT05 - Distr Streetlighting | 11805 | 734393 | 50000 | 50000-093 | 14F018570000 | Streetlighting Prog-CaboRojoP2 | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2024-04-30 17:00 | 2024-04-30
PBUT05 - Distr Streetlighting | 107915 | 734396 | 50000 | 50000-111 | 14F018580000 | Streetlighting Prog-CaboRojoP3 | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2024-07-12 17:00 | 2024-07-12
PBUT05 - Distr Streetlighting | 11778 | 746111 | 50000 | 50000-082 | 14F018590000 | Streetlighting Prog-Caguas P2 | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2024-03-28 17:00 | 2024-03-27
PBUT05 - Distr Streetlighting | 11838 | 735672 | 50000 | 50000-100 | 14F018600000 | Streetlighting Prog-Caguas P3 | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2024-05-31 17:00 | 2024-05-31
PBUT05 - Distr Streetlighting | 11783 | 735665 | 50000 | 50000-083 | 14F018610000 | Streetlighting Prog-CarolinaP2 | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2024-03-28 17:00 | 2024-03-28
PBUT05 - Distr Streetlighting | 11835 | 735496 | 50000 | 50000-101 | 14F018620000 | Streetlighting Prog-CarolinaP3 | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2024-05-31 17:00 | 2024-05-31
PBUT05 - Distr Streetlighting | 11808 | 734791 | 50000 | 50000-088 | 14F018630000 | Streetlighting Prog-Guayama P2 | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2024-04-30 17:00 | 2024-04-30
PBUT05 - Distr Streetlighting | 107916 | 734789 | 50000 | 50000-106 | 14F018640000 | Streetlighting Prog-Guayama P3 | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2024-08-22 17:00 | 2024-08-22
PBUT05 - Distr Streetlighting | 11801 | 735677 | 50000 | 50000-094 | 14F018650000 | Streetlighting Prog-GuaynaboP2 | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2024-04-30 17:00 | 2024-04-30
PBUT05 - Distr Streetlighting | 107921 | 735499 | 50000 | 50000-112 | 14F018660000 | Streetlighting Prog-GuaynaboP3 | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2025-02-28 17:00
PBUT05 - Distr Streetlighting | 11799 | 735493 | 50000 | 50000-089 | 14F018670000 | Streetlighting Prog-Humacao P2 | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2024-04-30 17:00 | 2024-04-30
PBUT05 - Distr Streetlighting | 107920 | 735487 | 50000 | 50000-107 | 14F018680000 | Streetlighting Prog-Humacao P3 | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2024-08-22 17:00 | 2024-08-22
PBUT05 - Distr Streetlighting | 11773 | 734927 | 50000 | 50000-090 | 14F018690000 | Streetlighting Prog-Isabela P2 | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2024-03-28 17:00 | 2024-03-27
PBUT05 - Distr Streetlighting | 107917 | 734928 | 50000 | 50000-108 | 14F018700000 | Streetlighting Prog-Isabela P3 | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2025-02-28 17:00
PBUT05 - Distr Streetlighting | 11777 | 735357 | 50000 | 50000-079 | 14F018710000 | Streetlighting Prog-MayaguezP2 | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2024-03-28 17:00 | 2024-03-27
PBUT05 - Distr Streetlighting | 11832 | 735360 | 50000 | 50000-097 | 14F018720000 | Streetlighting Prog-MayaguezP3 | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2024-05-31 17:00 | 2024-05-31
PBUT05 - Distr Streetlighting | 11774 | 734728 | 50000 | 50000-084 | 14F018730000 | Streetlighting Prog-Ponce P2 | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2024-03-28 17:00 | 2024-03-27
PBUT05 - Distr Streetlighting | 11830 | 734760 | 50000 | 50000-102 | 14F018740000 | Streetlighting Prog-Ponce P3 | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2024-05-31 17:00 | 2024-05-31
PBUT05 - Distr Streetlighting | 11809 | 737804 | 50000 | 50000-091 | 14F018750000 | Streetlighting Prog-RioGrandP2 | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2024-04-30 17:00 | 2024-04-30
PBUT05 - Distr Streetlighting | 107924 | 737798 | 50000 | 50000-109 | 14F018760000 | Streetlighting Prog-RioGrandP3 | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2024-08-22 17:00 | 2024-08-22
PBUT05 - Distr Streetlighting | 11779 | 746108 | 50000 | 50000-080 | 14F018770000 | Streetlighting Prog-SanJuan P2 | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2024-03-28 17:00 | 2024-03-27
PBUT05 - Distr Streetlighting | 11836 | 737712 | 50000 | 50000-098 | 14F018780000 | Streetlighting Prog-SanJuan P3 | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2024-05-31 17:00 | 2024-05-31
PBUT05 - Distr Streetlighting | 11797 | 737707 | 50000 | 50000-092 | 14F018790000 | Streetlighting Prog-ToaAlta P2 | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2024-04-30 17:00 | 2024-04-30
PBUT05 - Distr Streetlighting | 107923 | 737699 | 50000 | 50000-110 | 14F018800000 | Streetlighting Prog-ToaAlta P3 | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2025-02-28 17:00
PBUT05 - Distr Streetlighting | 11803 | 735960 | 50000 | 50000-095 | 14F018810000 | Streetlighting Prog-ToaBaja P2 | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2024-04-30 17:00 | 2024-04-30
PBUT05 - Distr Streetlighting | 107922 | 735959 | 50000 | 50000-113 | 14F018820000 | Streetlighting Prog-ToaBaja P3 | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2025-02-28 17:00
PBUT05 - Distr Streetlighting | 11772 | 735954 | 50000 | 50000-085 | 14F018830000 | Streetlighting Prog-TrujilloP2 | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2024-03-28 17:00 | 2024-03-27
PBUT05 - Distr Streetlighting | 11831 | 735952 | 50000 | 50000-103 | 14F018840000 | Streetlighting Prog-TrujilloP3 | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2024-05-31 17:00 | 2024-05-31
PBUT05 - Distr Streetlighting | 11806 | 735940 | 50000 | 50000-096 | 14F018850000 | Streetlighting Prog-VegaBajaP2 | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2024-04-30 17:00 | 2024-04-30
PBUT05 - Distr Streetlighting | 107919 | 735483 | 50000 | 50000-114 | 14F018860000 | Streetlighting Prog-VegaBajaP3 | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2025-02-28 17:00
PBUT05 - Distr Streetlighting |  |  |  |  | 14N000640000 | Streetlighting Program NME | Inactive
PBUT05 - Distr Streetlighting | 1294 | 83182 | 90102 | 90102 | 15F019800000 | CAT Z - PBUT5 | Active |  |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  |  | 2020-02-05 12:48
PBUT05 - Distr Streetlighting |  |  | 80005 | 80005 | 15N000690000 | Streetlight Billing | Cancel
PBUT06 - Distr Line Rebuild |  |  | 90053 | 90053 | 10N000660000 | Loiza Street Revitalization | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30069 | 30069 | 10N004800000 | Eladia Cosme-WR6312521 | Active
PBUT06 - Distr Line Rebuild |  |  | 30069 | 30069 | 10N004810000 | Rattan Furniture-WR6273092 | Active
PBUT06 - Distr Line Rebuild |  |  | 30069 | 30069 | 10N004820000 | Pedro Rodriguez Sola-WR6297016 | Active
PBUT06 - Distr Line Rebuild |  |  | 30069 | 30069 | 10N004830000 | YAMIL ORTIZ-WR6304873 | Closed
PBUT06 - Distr Line Rebuild |  |  | 30069 | 30069 | 10N004840000 | Alejandro Torres-WR6311363 | Closed
PBUT06 - Distr Line Rebuild |  |  | 30069 | 30069 | 10N004850000 | SANTOS CACERES-WR6326228 | Active
PBUT06 - Distr Line Rebuild |  |  | 30069 | 30069 | 10N004860000 | JOEL PERDOMO-WR6333657 | Active
PBUT06 - Distr Line Rebuild |  |  | 30069 | 30069 | 10N004870000 | Miguel Fonseca-WR6315192 | Active
PBUT06 - Distr Line Rebuild |  |  | 30003 | 30003-001 | 10N004930000 | Feeder 1115-02 UG Repair | Cancel | Inactive | [7 empty] | 2024-09-30 08:00
PBUT06 - Distr Line Rebuild |  |  | 30003 | 30003-002 | 10N004940000 | Feeder 1115-03 UG Repair | Cancel | Inactive | [7 empty] | 2024-09-30 17:00
PBUT06 - Distr Line Rebuild |  |  | 30003 | 30003-003 | 10N004950000 | Feeder 1115-04 UG Repair | Cancel | Inactive | [7 empty] | 2024-09-30 17:00
PBUT06 - Distr Line Rebuild |  |  | 30003 | 30003-004 | 10N004960000 | Feeder 1117-07 UG Repair | Cancel | Inactive | [7 empty] | 2024-09-30 17:00
PBUT06 - Distr Line Rebuild |  |  | 30003 | 30003-005 | 10N004970000 | Feeder 1424-07 UG Repair | Cancel | Inactive | [7 empty] | 2024-09-30 17:00
PBUT06 - Distr Line Rebuild |  |  | 30003 | 30003-006 | 10N004980000 | Feeder 1424-08 UG Repair | Cancel | Inactive | [7 empty] | 2024-09-30 17:00
PBUT06 - Distr Line Rebuild |  |  | 30003 | 30003 | 10N004990000 | UG Switch Replacement | Active | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30069 | 30069 | 10N005630000 | WR6106088 11-30-2023 Trf(14-01 | Active
PBUT06 - Distr Line Rebuild |  |  | 30071 | 30071 | 10N005640000 | UG Cable Replacement | Active
PBUT06 - Distr Line Rebuild |  |  | 30003 | 30003 | 10N005700000 | Feeder 1657-01 UG Repair | Active | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30003 | 30003 | 10N005710000 | Feeder 1658-13 UG Repair | Active | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30003 | 30003 | 10N005980000 | Martin Peña GIS - 1111-01 UG | Active | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30003 | 30003 | 10N005990000 | Santurce - 1117-08 UG | Cancel | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30003 | 30003 | 10N006000000 | Grana - 1907-05 UG | Active | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30003 | 30003 | 10N006010000 | Canovanas TC - 2404-06 UG | Active | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30003 | 30003 | 10N006020000 | Candelero - 2604-01 UG | Active | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30003 | 30003 | 10N006030000 | Villa del Carmen - 5016-01 UG | Active | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30076 | 30076 | 10N012330000 | System Improv. for Subst. 7301 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N012490000 | DER - Feeder 1203-02 | Active
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N012500000 | DER - Feeder 1204-04 | Active
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N012510000 | DER - Feeder 1301-01 | Active
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N012520000 | DER - Feeder 1342-04 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N012530000 | DER - Feeder 1346-03 | Active
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N012540000 | DER - Feeder 1525-03 | Active
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N012550000 | DER - Feeder 1619-03 | Active
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N012560000 | DER - Feeder 1704-05 | Active
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N012570000 | DER - Feeder 1709-02 | Active
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N012580000 | DER - Feeder 1806-03 | Active
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N012590000 | DER - Feeder 2803-02 | Active
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N012600000 | DER - Feeder 3005-02 | Active
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N012610000 | DER - Feeder 3201-02 | Active
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N012620000 | DER - Feeder 3406-02 | Active
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N012630000 | DER - Feeder 4401-02 | Active
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N012640000 | DER - Feeder 4402-02 | Active
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N012650000 | DER - Feeder 4603-01 | Active
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N012660000 | DER - Feeder 5012-04 | Active
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N012670000 | DER - Feeder 5602-02 | Active
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N012680000 | DER - Feeder 9101-01 | Active
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N012740000 | DER - Feeder 1345-05 | Active
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N012750000 | DER - Feeder 1708-05 | Active
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N012760000 | DER - Feeder 1710-05 | Active
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N012770000 | DER - Feeder 1713-05 | Active
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N012780000 | DER - Feeder 1718-02 | Active
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N012790000 | DER - Feeder 1806-01 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N012800000 | DER - Feeder 1903-03 | Active
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N012810000 | DER - Feeder 2401-01 | Active
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N012820000 | DER - Feeder 2601-01 | Active
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N012830000 | DER - Feeder 2602-02 | Active
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N012840000 | DER - Feeder 2602-03 | Active
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N012850000 | DER - Feeder 2604-03 | Active
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N012860000 | DER - Feeder 2701-01 | Active
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N012870000 | DER - Feeder 2701-02 | Active
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N012880000 | DER - Feeder 3008-03 | Active
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N012900000 | DER - Feeder 3015-05 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N012910000 | DER - Feeder 3201-04 | Active
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N012920000 | DER - Feeder 3205-07 | Active
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N012930000 | DER - Feeder 3502-01 | Active
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N012940000 | DER - Feeder 3013-01 | Active
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N012960000 | DER - Feeder 5003-01 | Active
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N012970000 | DER - Feeder 5802-01 | Active
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N012980000 | DER - Feeder 6012-05 | Active
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N012990000 | DER - Feeder 7003-03 | Active
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N013000000 | DER - Feeder 7402-02 | Active
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N013010000 | DER - Feeder 8602-03 | Active
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N013020000 | DER - Feeder 9203-04 | Active
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N013030000 | DER - Feeder 4503-01 | Active
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N013040000 | DER - Feeder 4006-02 | Active
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N013050000 | DER - Feeder 9002-01 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N013060000 | DER - Feeder 4603-02 | Active
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N013070000 | DER - Feeder 9105-06 | Active
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N013080000 | DER - Feeder 5305-04 | Active
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N013090000 | DER - Feeder 8004-04 | Active
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N013100000 | DER - Feeder 4003-02 | Active
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N013110000 | DER - Feeder 6007-02 | Active
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N013120000 | DER - Feeder 8504-01 | Active
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N013130000 | DER - Feeder 5003-02 | Active
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N013140000 | DER - Feeder 8501-02 | Active
PBUT06 - Distr Line Rebuild | 107551 | 436616 | 10007-004 | 10007-004 | 14F000040000 | 8010-01 Dominguito | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-11-29 08:00 | 2022-11-29 08:00 | 2023-09-01 17:00 | 2023-09-01
PBUT06 - Distr Line Rebuild | 107551 | 436616 | 10007-005 | 10007-005 | 14F000050000 | Manatí 13.2 kV 8404-03 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-11-29 08:00 | 2022-11-29 08:00 | 2023-09-01 17:00 | 2023-09-01
PBUT06 - Distr Line Rebuild | 107551 | 436616 | 10007-007 | 10007-007 | 14F000060000 | Manatí 13.2 kV 8404-04 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-11-29 08:00 | 2022-11-29 08:00 | 2023-09-01 17:00 | 2023-09-01
PBUT06 - Distr Line Rebuild | 107551 | 436616 | 10007-002 | 10007-002 | 14F000070000 | Cruce Davila 8501-02 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-11-29 08:00 | 2022-11-29 08:00 | 2023-09-01 17:00 | 2023-09-01
PBUT06 - Distr Line Rebuild | 107551 | 436616 | 10007-006 | 10007-006 | 14F000080000 | Ciales 8701-01 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-11-29 08:00 | 2022-11-29 08:00 | 2023-09-01 17:00 | 2023-09-01
PBUT06 - Distr Line Rebuild | 107551 | 436616 | 10007-003 | 10007-003 | 14F000090000 | Ciales 8701-02 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-11-29 08:00 | 2022-11-29 08:00 | 2023-09-01 17:00 | 2023-09-01
PBUT06 - Distr Line Rebuild | 108074 | 797148 | 10134-007 | 10134-007 | 14F000100000 | Utuado Pueblo 8101-03 (L) | Active | Active |  |  | Active | Phase 2 - Intake & Eligibility | Pending PDMG Scope & Cost Routing | 2022-09-27 08:00 | 2022-09-27 08:00 | 2023-09-18 17:00 | 2025-01-17 | 2025-09-17 18:16
PBUT06 - Distr Line Rebuild | 107911 | 730821 | 10134-002 | 10134-002 | 14F000110000 | Caguana 8103-01 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-09-27 08:00 | 2022-09-27 08:00 | 2023-09-29 17:00 | 2023-09-29
PBUT06 - Distr Line Rebuild | 107911 | 730821 | 10134-004 | 10134-004 | 14F000120000 | Caguana 8103-02 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2023-09-29 17:00 | 2023-09-29
PBUT06 - Distr Line Rebuild | 107911 | 730821 | 10134-003 | 10134-003 | 14F000130000 | Yahuecas 8203-02 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-09-27 08:00 | 2022-09-27 08:00 | 2023-09-29 17:00 | 2023-09-29
PBUT06 - Distr Line Rebuild | 107911 | 730821 | 10134-006 | 10134-006 | 14F000140000 | Jayuya 8301-03 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-09-27 08:00 | 2022-09-27 08:00 | 2023-09-29 17:00 | 2023-09-29
PBUT06 - Distr Line Rebuild | 107911 | 730821 | 10134-005 | 10134-005 | 14F000150000 | Jayuya II 8302-05 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2021-07-01 08:00 | 2021-07-01 08:00 | 2023-09-29 17:00 | 2023-09-29
PBUT06 - Distr Line Rebuild | 108048 | 760568 | 10008-003 | 10008-003 | 14F000170000 | Cana 1710-01 (L) | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-11-29 08:00 | 2022-11-29 08:00 | 2023-09-29 08:00
PBUT06 - Distr Line Rebuild |  |  | 10008-002 | 10008-002 | 14F000180000 | Cana 1710-03 | Inactive | Inactive | [5 empty] | 2022-11-29 08:00 | 2022-11-29 08:00 | 2023-09-29 08:00
PBUT06 - Distr Line Rebuild | 108050 | 760575 | 10008-007 | 10008-007 | 14F000190000 | Bayamón Tc 13kV #2 1716-03 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-11-29 08:00 | 2022-11-29 08:00 | 2023-09-29 08:00
PBUT06 - Distr Line Rebuild | 108052 | 760579 | 10008-006 | 10008-006 | 14F000200000 | Crea 1717-03 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-11-29 08:00 | 2022-11-29 08:00 | 2023-09-29 08:00
PBUT06 - Distr Line Rebuild | 108051 | 760577 | 10008-008 | 10008-008 | 14F000210000 | Candelaria Arenas 1718-02 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-11-29 08:00 | 2022-11-29 08:00 | 2023-09-29 08:00
PBUT06 - Distr Line Rebuild | 108049 | 760571 | 10008-005 | 10008-005 | 14F000220000 | Rio Bayamón Ii 1720-07 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-11-29 08:00 | 2022-11-29 08:00 | 2023-09-29 08:00
PBUT06 - Distr Line Rebuild | 107525 | 334473 | 10008-004 | 10008-004 | 14F000230000 | Levittown 1806-02 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-11-29 08:00 | 2022-11-29 08:00 | 2023-09-29 08:00 | 2023-09-29
PBUT06 - Distr Line Rebuild | 107527 | 334475 | 10135-005 | 10135-005 | 14F000240000 | Vega Baja 1 9001-02 (L) | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-12-01 08:00 | 2022-12-01 08:00 | 2023-09-01 17:00 | 2023-09-01
PBUT06 - Distr Line Rebuild | 107527 | 334475 | 10135-004 | 10135-004 | 14F000250000 | Toa Alta 9401-01 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-12-01 08:00 | 2022-12-01 08:00 | 2023-09-01 17:00 | 2023-09-01
PBUT06 - Distr Line Rebuild | 108121 | 817962 | 10135-007 | 10135-007 | 14F000260000 | Barrio Piñas 9403-03 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-12-02 08:00 | 2022-12-02 08:00 | 2023-09-01 17:00
PBUT06 - Distr Line Rebuild | 108101 | 812041 | 10135-006 | 10135-006 | 14F000270000 | Unibon 9501-02 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-12-02 08:00 | 2022-12-02 08:00 | 2023-09-01 17:00 | 2025-04-11
PBUT06 - Distr Line Rebuild | 107527 | 334475 | 10135-002 | 10135-002 | 14F000280000 | Monterrey 9502-01 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-12-01 08:00 | 2022-12-01 08:00 | 2023-09-01 17:00 | 2023-09-01
PBUT06 - Distr Line Rebuild | 107527 | 334475 | 10135-003 | 10135-003 | 14F000290000 | Monterrey 9502-02 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-12-02 08:00 | 2022-12-02 08:00 | 2023-09-01 17:00 | 2023-09-01
PBUT06 - Distr Line Rebuild | 108122 | 817993 | 10136-006 | 10136-006 | 14F000300000 | 1801-03 (L) | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-08-30 08:00 | 2022-08-30 08:00 | 2023-06-30 17:00
PBUT06 - Distr Line Rebuild | 107526 | 334474 | 10136-004 | 10136-004 | 14F000310000 | 1801-05 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-08-30 08:00 | 2022-08-30 08:00 | 2023-06-30 17:00 | 2023-07-01
PBUT06 - Distr Line Rebuild | 107526 | 334474 | 10136-002 | 10136-002 | 14F000320000 | 1801-02 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-08-30 08:00 | 2022-08-30 08:00 | 2023-06-30 17:00 | 2023-07-01
PBUT06 - Distr Line Rebuild | 107526 | 334474 | 10136-003 | 10136-003 | 14F000330000 | 1801-01 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-08-30 08:00 | 2022-08-30 08:00 | 2023-06-30 17:00 | 2023-07-01
PBUT06 - Distr Line Rebuild | 107526 | 334474 | 10136-005 | 10136-005 | 14F000340000 | 1801-04 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2021-07-01 08:00 | 2021-07-01 08:00 | 2023-06-30 17:00 | 2023-07-01
PBUT06 - Distr Line Rebuild | 107521 | 334452 | 10147-002 | 10147-002 | 14F000360000 | 3205-07 (L) | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2023-02-07 08:00 | 2023-02-07 08:00 | 2023-09-01 17:00 | 2023-09-01
PBUT06 - Distr Line Rebuild | 107908 | 730541 | 10152-003 | 10152-003 | 14F000370000 | 2603-08 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-10-24 08:00 | 2022-10-24 08:00 | 2023-09-29 08:00 | 2023-09-30
PBUT06 - Distr Line Rebuild | 107531 | 334497 | 10150-004 | 10150-004 | 14F000380000 | 9703-01 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-09-13 08:00 | 2022-09-13 08:00 | 2023-09-01 17:00 | 2023-09-01
PBUT06 - Distr Line Rebuild | 107530 | 334491 | 10149-003 | 10149-003 | 14F000390000 | 3601-02 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2023-07-28 08:00 | 2023-09-01
PBUT06 - Distr Line Rebuild | 107521 | 334452 | 10147-004 | 10147-004 | 14F000400000 | 3301-01 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2023-02-07 08:00 | 2023-02-07 08:00 | 2023-09-01 08:00 | 2023-09-01
PBUT06 - Distr Line Rebuild | 107520 | 334443 | 10146-002 | 10146-002 | 14F000410000 | 9902-01 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2026-01-05 08:00 | 2026-01-05 08:00 | 2023-09-29 17:00 | 2023-09-29
PBUT06 - Distr Line Rebuild | 107530 | 334491 | 10149-005 | 10149-005 | 14F000420000 | 3601-04 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-12-06 08:00 | 2022-12-06 08:00 | 2023-07-28 08:00 | 2023-09-01
PBUT06 - Distr Line Rebuild | 107520 | 334443 | 10146-003 | 10146-003 | 14F000430000 | 9902-02 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-09-27 08:00 | 2022-09-27 08:00 | 2023-09-29 17:00 | 2023-09-29
PBUT06 - Distr Line Rebuild | 107519 | 334420 | 10009-003 | 10009-003 | 14F000440000 | 2605-01 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-12-07 08:00 | 2022-12-07 08:00 | 2023-11-30 08:00 | 2023-09-29
PBUT06 - Distr Line Rebuild | 107531 | 334497 | 10150-003 | 10150-003 | 14F000450000 | 9703-03 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-09-13 08:00 | 2022-09-13 08:00 | 2023-09-01 17:00 | 2023-09-01
PBUT06 - Distr Line Rebuild | 107531 | 334497 | 10150-006 | 10150-006 | 14F000460000 | 3007-03 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-09-15 08:00 | 2022-09-15 08:00 | 2023-09-01 17:00 | 2023-09-01
PBUT06 - Distr Line Rebuild | 107531 | 334497 | 10150-007 | 10150-007 | 14F000470000 | 9703-02 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-09-13 08:00 | 2022-09-13 08:00 | 2023-09-01 17:00 | 2023-09-01
PBUT06 - Distr Line Rebuild | 108125 | 818055 | 10148-002 | 10148-002 | 14F000480000 | 3006-05 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2023-09-29 17:00
PBUT06 - Distr Line Rebuild | 108102 | 812569 | 10149-002 | 10149-002 | 14F000490000 | 3502-02 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-12-06 08:00 | 2022-12-06 08:00 | 2023-07-28 08:00 | 2025-03-19 | 2025-09-25 16:15
PBUT06 - Distr Line Rebuild | 107520 | 334443 | 10146-005 | 10146-005 | 14F000500000 | 9901-02 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-09-27 08:00 | 2022-09-27 08:00 | 2023-09-29 17:00 | 2023-09-29
PBUT06 - Distr Line Rebuild | 108064 | 767139 | 10009-002 | 10009-002 | 14F000510000 | 2906-02 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-12-05 08:00 | 2022-12-05 08:00 | 2023-11-30 08:00
PBUT06 - Distr Line Rebuild | 108124 | 818041 | 10152-002 | 10152-002 | 14F000520000 | 3701-03 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-10-24 08:00 | 2022-10-24 08:00 | 2023-09-29 08:00
PBUT06 - Distr Line Rebuild | 107532 | 334518 | 10151-003 | 10151-003 | 14F000530000 | 3102-01 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-12-06 08:00 | 2022-12-06 08:00 | 2023-09-01 17:00 | 2023-09-01
PBUT06 - Distr Line Rebuild | 107532 | 334518 | 10151-005 | 10151-005 | 14F000540000 | 3103-01 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-12-06 08:00 | 2022-12-06 08:00 | 2023-09-01 17:00 | 2023-09-01
PBUT06 - Distr Line Rebuild | 107521 | 334452 | 10147-003 | 10147-003 | 14F000550000 | 2803-02 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-10-27 08:00 | 2022-10-27 08:00 | 2023-09-01 08:00 | 2023-09-01
PBUT06 - Distr Line Rebuild | 107521 | 334452 | 10147-005 | 10147-005 | 14F000560000 | 3302-02 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2023-02-07 08:00 | 2023-02-07 08:00 | 2023-09-01 17:00 | 2023-09-01
PBUT06 - Distr Line Rebuild | 107520 | 334443 | 10146-007 | 10146-007 | 14F000570000 | 9601-02 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-08-25 08:00 | 2022-08-25 08:00 | 2023-09-29 17:00 | 2023-09-29
PBUT06 - Distr Line Rebuild | 107532 | 334518 | 10151-004 | 10151-004 | 14F000580000 | 3103-04 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-12-06 08:00 | 2022-12-06 08:00 | 2023-09-01 17:00 | 2023-09-01
PBUT06 - Distr Line Rebuild | 107519 | 334420 | 10009-005 | 10009-005 | 14F000590000 | 2602-03 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-12-07 08:00 | 2022-12-07 08:00 | 2023-11-30 08:00 | 2023-09-29
PBUT06 - Distr Line Rebuild | 107530 | 334491 | 10149-006 | 10149-006 | 14F000600000 | 3401-02 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-12-06 08:00 | 2022-12-06 08:00 | 2023-07-28 08:00 | 2023-09-01
PBUT06 - Distr Line Rebuild | 107520 | 334443 | 10146-006 | 10146-006 | 14F000610000 | 9602-04 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-09-27 08:00 | 2022-09-27 08:00 | 2023-09-29 17:00 | 2023-09-29
PBUT06 - Distr Line Rebuild | 107520 | 334443 | 10146-004 | 10146-004 | 14F000620000 | 9601-01 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-07-19 08:00 | 2022-07-19 08:00 | 2023-11-30 17:00 | 2023-09-29
PBUT06 - Distr Line Rebuild | 107907 | 730513 | 10148-006 | 10148-006 | 14F000630000 | 3006-03 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-04-05 08:00 | 2022-04-05 08:00 | 2026-06-17 17:00 | 2023-09-29
PBUT06 - Distr Line Rebuild | 107531 | 334497 | 10150-005 | 10150-005 | 14F000640000 | 3010-01 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-09-13 08:00 | 2022-09-13 08:00 | 2023-09-01 17:00 | 2023-09-01
PBUT06 - Distr Line Rebuild | 107532 | 334518 | 10151-002 | 10151-002 | 14F000650000 | 3103-05 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-12-06 08:00 | 2022-12-06 08:00 | 2023-09-01 17:00 | 2023-09-01
PBUT06 - Distr Line Rebuild | 107531 | 334497 | 10150-002 | 10150-002 | 14F000660000 | 3015-05 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2021-07-08 08:00 | 2021-07-08 08:00 | 2023-09-01 17:00 | 2023-09-01
PBUT06 - Distr Line Rebuild | 107907 | 730513 | 10148-003 | 10148-003 | 14F000670000 | 3013-02 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-11-11 08:00 | 2022-11-11 08:00 | 2023-09-19 17:00 | 2023-09-29
PBUT06 - Distr Line Rebuild | 107519 | 334420 | 10009-006 | 10009-006 | 14F000680000 | 2901-03 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-12-07 08:00 | 2022-12-07 08:00 | 2023-11-30 17:00 | 2023-09-29
PBUT06 - Distr Line Rebuild | 107907 | 730513 | 10148-004 | 10148-004 | 14F000690000 | 3004-01 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-11-11 08:00 | 2022-11-11 08:00 | 2023-09-19 17:00 | 2023-09-29
PBUT06 - Distr Line Rebuild | 107519 | 334420 | 10009-007 | 10009-007 | 14F000700000 | 2701-01 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-12-05 08:00 | 2022-12-05 08:00 | 2023-09-29 08:00 | 2023-09-29
PBUT06 - Distr Line Rebuild | 107519 | 334420 | 10009-004 | 10009-004 | 14F000710000 | 2701-03 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-12-07 08:00 | 2022-12-07 08:00 | 2023-11-30 17:00 | 2023-09-29
PBUT06 - Distr Line Rebuild | 107521 | 334452 | 10147-006 | 10147-006 | 14F000720000 | 2801-03 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2023-02-08 08:00 | 2023-02-08 08:00 | 2023-09-01 08:00 | 2023-09-01
PBUT06 - Distr Line Rebuild | 107530 | 334491 | 10149-007 | 10149-007 | 14F000730000 | 3405-01 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-12-06 08:00 | 2022-12-06 08:00 | 2023-07-28 08:00 | 2023-09-01
PBUT06 - Distr Line Rebuild | 107521 | 334452 | 10147-007 | 10147-007 | 14F000740000 | 2801-02 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2023-02-07 08:00 | 2023-02-07 08:00 | 2023-09-01 17:00 | 2023-09-01
PBUT06 - Distr Line Rebuild | 107530 | 334491 | 10149-004 | 10149-004 | 14F000750000 | 3405-03 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-12-06 08:00 | 2022-12-06 08:00 | 2023-07-28 08:00 | 2023-09-01
PBUT06 - Distr Line Rebuild | 107521 | 334452 | 10147-008 | 10147-008 | 14F000760000 | 3201-04 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2023-02-07 08:00 | 2023-02-07 08:00 | 2023-09-01 17:00 | 2023-09-01
PBUT06 - Distr Line Rebuild | 107532 | 334518 | 10151-006 | 10151-006 | 14F000770000 | 3101-02 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-12-06 08:00 | 2022-12-06 08:00 | 2023-09-01 17:00 | 2023-09-01
PBUT06 - Distr Line Rebuild | 107907 | 730513 | 10148-005 | 10148-005 | 14F000780000 | 3006-02 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-11-11 08:00 | 2022-11-11 08:00 | 2023-09-19 17:00 | 2023-09-29
PBUT06 - Distr Line Rebuild | 107528 | 334476 | 10010-005 | 10010-005 | 14F000810000 | Fajardo Pds 2005-10 (L) | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-10-24 08:00 | 2022-10-24 08:00 | 2024-07-15 17:00 | 2023-11-30
PBUT06 - Distr Line Rebuild | 107528 | 334476 | 10010-003 | 10010-003 | 14F000820000 | Rio Grande 8kV 2301-02 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2023-11-30 08:00 | 2023-11-30
PBUT06 - Distr Line Rebuild | 107528 | 334476 | 10010-004 | 10010-004 | 14F000830000 | Palmer Tc 2305-02 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2024-06-27 08:00 | 2024-06-27 08:00 | 2023-11-30 08:00 | 2023-11-30
PBUT06 - Distr Line Rebuild | 107528 | 334476 | 10010-002 | 10010-002 | 14F000840000 | Canovanas Pueblo 2401-01 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-10-31 08:00 | 2022-10-31 08:00 | 2023-11-30 08:00 | 2023-11-30
PBUT06 - Distr Line Rebuild | 107528 | 334476 | 10010-006 | 10010-006 | 14F000850000 | Las Mercedes 2403-01 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2023-08-25 08:00 | 2023-08-25 08:00 | 2024-06-14 17:00 | 2023-11-30
PBUT06 - Distr Line Rebuild | 107529 | 334477 | 10137-006 | 10137-006 | 14F000860000 | Sabana Llana 13kV 1646-02 (L) | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2024-07-02 08:00 | 2024-07-02 08:00 | 2023-08-30 17:00 | 2023-09-01
PBUT06 - Distr Line Rebuild | 107529 | 334477 | 10137-005 | 10137-005 | 14F000870000 | Villamar 1657-02 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2021-07-01 08:00 | 2021-07-01 08:00 | 2023-08-30 17:00 | 2023-09-01
PBUT06 - Distr Line Rebuild | 108123 | 818006 | 10137-003 | 10137-003 | 14F000880000 | Canovanas T.C. #1 2402-02 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-11-28 08:00 | 2022-11-28 08:00 | 2023-08-30 17:00
PBUT06 - Distr Line Rebuild | 107529 | 334477 | 10137-004 | 10137-004 | 14F000890000 | Canovanas T.C. #1 2402-03 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-12-14 08:00 | 2022-12-14 08:00 | 2023-08-30 17:00 | 2023-09-01
PBUT06 - Distr Line Rebuild | 108120 | 817961 | 10137-002 | 10137-002 | 14F000900000 | Canovanas T.C. #2 2404-06 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2021-07-01 08:00 | 2021-07-01 08:00 | 2023-08-30 17:00 | 2025-07-08
PBUT06 - Distr Line Rebuild | 108058 | 764707 | 10011-003 | 10011-003 | 14F000970000 | Alturas De Mayag 6012-02 (L) | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2021-06-04 08:00 | 2021-06-04 08:00 | 2023-06-30 17:00
PBUT06 - Distr Line Rebuild | 108056 | 764705 | 10011-002 | 10011-002 | 14F000980000 | Once De Agosto 13kV 6014-02 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2021-07-01 08:00 | 2021-07-01 08:00 | 2023-06-30 17:00
PBUT06 - Distr Line Rebuild | 107517 | 334308 | 10011-006 | 10011-006 | 14F000990000 | Victoria 13.2 kV 7008-05 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-12-02 08:00 | 2022-12-02 08:00 | 2023-06-30 17:00 | 2023-07-01
PBUT06 - Distr Line Rebuild | 108057 | 764706 | 10011-004 | 10011-004 | 14F001000000 | T - Bone 7011-03 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-12-02 08:00 | 2022-12-02 08:00 | 2023-06-30 17:00
PBUT06 - Distr Line Rebuild | 107517 | 334308 | 10011-007 | 10011-007 | 14F001010000 | Moca Ii 7104-05 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-12-02 08:00 | 2022-12-02 08:00 | 2023-06-30 08:00 | 2023-07-01
PBUT06 - Distr Line Rebuild | 107517 | 334308 | 10011-005 | 10011-005 | 14F001020000 | Aguada 7201-02 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-12-02 08:00 | 2022-12-02 08:00 | 2023-06-30 08:00 | 2023-07-01
PBUT06 - Distr Line Rebuild | 107517 | 334308 | 10011-009 | 10011-009 | 14F001030000 | Rincón 7301-03 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-12-02 08:00 | 2022-12-02 08:00 | 2023-06-30 17:00 | 2023-07-01
PBUT06 - Distr Line Rebuild | 107517 | 334308 | 10011-008 | 10011-008 | 14F001040000 | Atalaya 7303-01 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-12-02 08:00 | 2022-12-02 08:00 | 2023-06-30 08:00 | 2023-07-01
PBUT06 - Distr Line Rebuild | 107514 | 334285 | 10139-002 | 10139-002 | 14F001050000 | Once De Agosto 6001-05 (L) | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2021-07-21 08:00 | 2021-07-21 08:00 | 2023-06-30 17:00 | 2023-06-30
PBUT06 - Distr Line Rebuild | 107514 | 334285 | 10139-010 | 10139-010 | 14F001060000 | Cerro Las Mesas 6010-01 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2023-09-28 08:00 | 2023-09-28 08:00 | 2023-06-30 17:00 | 2023-06-30
PBUT06 - Distr Line Rebuild | 107514 | 334285 | 10139-005 | 10139-005 | 14F001070000 | Centro Médico 13kV 6015-02 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2023-06-30 17:00 | 2023-06-30
PBUT06 - Distr Line Rebuild | 108126 | 818056 | 10139-008 | 10139-008 | 14F001080000 | Indiera Alta 6305-03 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-12-09 08:00 | 2022-12-09 08:00 | 2023-06-30 17:00
PBUT06 - Distr Line Rebuild | 107514 | 334285 | 10139-009 | 10139-009 | 14F001090000 | Las Vegas 6306-02 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-12-08 08:00 | 2022-12-08 08:00 | 2023-06-30 17:00 | 2023-06-30
PBUT06 - Distr Line Rebuild | 108162 | 956782 | 10139-007 | 10139-007 | 14F001100000 | Acacias 13.2 kV 6802-04 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-12-08 08:00 | 2022-12-08 08:00 | 2023-06-30 17:00 | 2025-06-25
PBUT06 - Distr Line Rebuild | 107514 | 334285 | 10139-003 | 10139-003 | 14F001110000 | Acacias 13.2 kV 6802-05 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-12-08 08:00 | 2022-12-08 08:00 | 2023-06-30 17:00 | 2023-06-30
PBUT06 - Distr Line Rebuild | 107514 | 334285 | 10139-006 | 10139-006 | 14F001120000 | Bartolo 7902-01 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-02-11 08:00 | 2022-02-11 08:00 | 2023-06-30 17:00 | 2023-06-30
PBUT06 - Distr Line Rebuild | 107514 | 334285 | 10139-004 | 10139-004 | 14F001130000 | Bartolo 7902-03 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-12-08 08:00 | 2022-12-08 08:00 | 2023-06-30 17:00 | 2023-06-30
PBUT06 - Distr Line Rebuild | 107513 | 334191 | 10140-002 | 10140-002 | 14F001140000 | San Germán 13kV 6406-02 (L) | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-08-30 08:00 | 2022-08-30 08:00 | 2023-06-30 17:00 | 2023-06-30
PBUT06 - Distr Line Rebuild | 108082 | 801166 | 10140-004 | 10140-004 | 14F001150000 | Lajas 6601-03 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-08-30 08:00 | 2022-08-30 08:00 | 2023-06-30 17:00 | 2025-04-07 | 2026-01-08 16:17
PBUT06 - Distr Line Rebuild | 108164 | 958367 | 10140-005 | 10140-005 | 14F001160000 | Parguera Pds 6603-01 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-08-30 08:00 | 2022-08-30 08:00 | 2023-06-30 17:00 | 2025-07-15
PBUT06 - Distr Line Rebuild | 107513 | 334191 | 10140-007 | 10140-007 | 14F001170000 | Boquerón 6702-01 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-08-30 08:00 | 2022-08-30 08:00 | 2023-06-30 17:00 | 2023-06-30
PBUT06 - Distr Line Rebuild | 107513 | 334191 | 10140-006 | 10140-006 | 14F001180000 | Cabo Rojo 6703-01 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-08-30 08:00 | 2022-08-30 08:00 | 2023-06-30 17:00 | 2023-06-30
PBUT06 - Distr Line Rebuild | 107513 | 334191 | 10140-008 | 10140-008 | 14F001190000 | Combate 6704-02 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-08-30 08:00 | 2022-08-30 08:00 | 2023-06-30 17:00 | 2023-06-30
PBUT06 - Distr Line Rebuild | 107513 | 334191 | 10140-003 | 10140-003 | 14F001200000 | Combate 6704-03 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-08-30 08:00 | 2022-08-30 08:00 | 2023-06-30 17:00 | 2023-06-30
PBUT06 - Distr Line Rebuild | 107513 | 334191 | 10140-009 | 10140-009 | 14F001210000 | Puerto Real 6705-01 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-08-30 08:00 | 2022-08-30 08:00 | 2023-06-30 17:00 | 2023-06-30
PBUT06 - Distr Line Rebuild | 107909 | 730586 | 10012-004 | 10012-004 | 14F001300000 | Rambla 13 kV 5004-06 (L) | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-10-24 08:00 | 2022-10-24 08:00 | 2023-09-29 17:00 | 2023-09-29
PBUT06 - Distr Line Rebuild | 107909 | 730586 | 10012-007 | 10012-007 | 14F001310000 | Rambla 13 kV 5004-07 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-10-24 08:00 | 2022-10-24 08:00 | 2023-09-29 17:00 | 2023-09-29
PBUT06 - Distr Line Rebuild | 107909 | 730586 | 10012-005 | 10012-005 | 14F001320000 | Rambla 13 kV 5004-09 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-10-24 08:00 | 2022-10-24 08:00 | 2023-09-29 17:00 | 2023-09-29
PBUT06 - Distr Line Rebuild | 107909 | 730586 | 10012-008 | 10012-008 | 14F001330000 | Canas T.C. 13 kV 5018-03 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-10-24 08:00 | 2022-10-24 08:00 | 2023-09-29 17:00 | 2023-09-29
PBUT06 - Distr Line Rebuild | 107909 | 730586 | 10012-002 | 10012-002 | 14F001340000 | Yauco Hidro Ii 5303-01 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-10-24 08:00 | 2022-10-24 08:00 | 2023-09-29 17:00 | 2023-09-29
PBUT06 - Distr Line Rebuild | 107909 | 730586 | 10012-006 | 10012-006 | 14F001350000 | Guayanilla Pueblo 5501-04 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-10-24 08:00 | 2022-10-24 08:00 | 2023-09-29 17:00 | 2023-09-29
PBUT06 - Distr Line Rebuild | 108059 | 764708 | 10012-009 | 10012-009 | 14F001360000 | Guanica Tc 5602-02 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-10-24 08:00 | 2022-10-24 08:00 | 2023-09-29 17:00
PBUT06 - Distr Line Rebuild | 107912 | 730824 | 10141-004 | 10141-004 | 14F001370000 | Jobos T.C. 4003-01 (L) | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-12-05 08:00 | 2022-12-05 08:00 | 2023-11-30 08:00 | 2023-11-30
PBUT06 - Distr Line Rebuild | 107912 | 730824 | 10141-005 | 10141-005 | 14F001380000 | Patillas 4201-01 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-02-18 17:00 | 2022-02-18 17:00 | 2028-11-17 17:00 | 2023-11-30
PBUT06 - Distr Line Rebuild | 107912 | 730824 | 10141-007 | 10141-007 | 14F001390000 | Coamo Urbano 4602-01 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-12-05 08:00 | 2022-12-05 08:00 | 2023-12-11 17:00 | 2023-11-30
PBUT06 - Distr Line Rebuild | 107912 | 730824 | 10141-002 | 10141-002 | 14F001400000 | Coamo Pds 4603-01 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-12-05 08:00 | 2022-12-05 08:00 | 2024-06-05 17:00 | 2023-11-30
PBUT06 - Distr Line Rebuild | 107912 | 730824 | 10141-003 | 10141-003 | 14F001410000 | Ponce Distr. Hospital 5012-03 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-12-05 08:00 | 2022-12-05 08:00 | 2024-06-04 17:00 | 2023-11-30
PBUT06 - Distr Line Rebuild | 107912 | 730824 | 10141-006 | 10141-006 | 14F001420000 | Aguilita 4 kV 5817-02 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-02-18 08:00 | 2022-02-18 08:00 | 2026-08-31 17:00 | 2023-11-30
PBUT06 - Distr Line Rebuild | 108084 | 801197 | 10013-004 | 10013-004 | 14F001440000 | Conquistador 1204-02 (L) | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2023-02-24 08:00 | 2023-02-24 08:00 | 2023-09-29 08:00
PBUT06 - Distr Line Rebuild | 107523 | 334471 | 10013-008 | 10013-008 | 14F001450000 | Conquistador 1204-03 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2023-02-24 08:00 | 2023-02-24 08:00 | 2023-09-29 08:00 | 2023-09-29
PBUT06 - Distr Line Rebuild | 108067 | 767381 | 10013-003 | 10013-003 | 14F001460000 | Conquistador 1204-04 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2023-02-24 08:00 | 2023-02-24 08:00 | 2023-09-29 08:00
PBUT06 - Distr Line Rebuild | 108060 | 764709 | 10013-002 | 10013-002 | 14F001470000 | Conquistador 1204-05 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2023-02-24 08:00 | 2023-02-24 08:00 | 2023-09-29 08:00
PBUT06 - Distr Line Rebuild | 108068 | 767387 | 10013-005 | 10013-005 | 14F001480000 | Villa Betina 1303-01 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2023-02-24 08:00 | 2023-02-24 08:00 | 2023-09-29 08:00
PBUT06 - Distr Line Rebuild | 108119 | 817956 | 10013-006 | 10013-006 | 14F001490000 | Villa Betina 1303-02 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval | 2023-02-24 08:00 | 2023-02-24 08:00 | 2023-09-29 08:00 | 2025-05-12 | 2025-09-25 17:15
PBUT06 - Distr Line Rebuild | 108062 | 767005 | 10013-007 | 10013-007 | 14F001500000 | Villa Betina 1303-05 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2023-02-24 08:00 | 2023-02-24 08:00 | 2023-09-29 08:00
PBUT06 - Distr Line Rebuild | 107524 | 334472 | 10142-006 | 10142-006 | 14F001510000 | Monacillo 4kV 1330-01 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-11-14 08:00 | 2022-11-14 08:00 | 2023-08-30 17:00 | 2023-09-01
PBUT06 - Distr Line Rebuild | 107524 | 334472 | 10142-003 | 10142-003 | 14F001520000 | Monacillos 13kV 1346-02 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-11-14 08:00 | 2022-11-14 08:00 | 2023-08-30 17:00 | 2023-09-01
PBUT06 - Distr Line Rebuild | 107524 | 334472 | 10142-002 | 10142-002 | 14F001530000 | Venezuela 13kV 1348-06 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-11-14 08:00 | 2022-11-14 08:00 | 2023-08-30 17:00 | 2023-09-01
PBUT06 - Distr Line Rebuild | 108083 | 801172 | 10142-005 | 10142-005 | 14F001540000 | Cachete 13kV 1529-15 | Active | Active |  |  | Active |  | Pending Amendment Processing | 2022-11-14 08:00 | 2022-11-14 08:00 | 2023-08-30 17:00 | 2025-01-31 | 2025-09-17 18:16
PBUT06 - Distr Line Rebuild | 107524 | 334472 | 10142-004 | 10142-004 | 14F001550000 | Grana Pds Ii 1909-09 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-11-14 08:00 | 2022-11-14 08:00 | 2023-08-30 17:00 | 2023-09-01
PBUT06 - Distr Line Rebuild | 107556 | 546374 | 10143-003 | 10143-003 | 14F001560000 | Santurce Planta 2 1117-11 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2023-02-24 08:00 | 2023-02-24 08:00 | 2023-08-31 08:00 | 2023-08-31
PBUT06 - Distr Line Rebuild | 107556 | 546374 | 10143-002 | 10143-002 | 14F001570000 | Llorens Torres 13kV 1118-10 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2023-02-24 08:00 | 2023-02-24 08:00 | 2023-08-31 08:00 | 2023-08-31
PBUT06 - Distr Line Rebuild | 107556 | 546374 | 10143-006 | 10143-006 | 14F001580000 | Berwind 13kV 1336-06 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2023-02-24 08:00 | 2023-02-24 08:00 | 2023-08-31 08:00 | 2023-08-31
PBUT06 - Distr Line Rebuild | 107556 | 546374 | 10143-004 | 10143-004 | 14F001590000 | Berwind 13kV 1336-08 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2023-02-24 08:00 | 2023-02-24 08:00 | 2023-08-31 08:00 | 2023-08-31
PBUT06 - Distr Line Rebuild | 108075 | 798275 | 10143-005 | 10143-005 | 14F001600000 | Parque Escorial 1620-02 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval | 2023-02-24 08:00 | 2023-02-24 08:00 | 2023-08-31 08:00 | 2025-01-15 | 2025-09-17 18:16
PBUT06 - Distr Line Rebuild | 107516 | 334293 | 10154-003 | 10154-003 | 14F003420000 | Las Marias 6201-01 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-08-25 08:00 | 2022-08-25 08:00 | 2023-06-30 17:00 | 2023-06-30
PBUT06 - Distr Line Rebuild | 107516 | 334293 | 10154-004 | 10154-004 | 14F003430000 | San Sebastian 2 7802-4 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-08-25 08:00 | 2022-08-25 08:00 | 2023-06-30 17:00 | 2023-06-30
PBUT06 - Distr Line Rebuild | 107516 | 334293 | 10154-007 | 10154-007 | 14F003440000 | San Sebastian 7805-13 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-08-25 08:00 | 2022-08-25 08:00 | 2023-06-30 17:00 | 2023-06-30
PBUT06 - Distr Line Rebuild | 107516 | 334293 | 10154-008 | 10154-008 | 14F003450000 | San Sebastian 7805-11 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-08-31 08:00 | 2022-08-31 08:00 | 2023-06-30 08:00 | 2023-06-30
PBUT06 - Distr Line Rebuild | 107516 | 334293 | 10154-005 | 10154-005 | 14F003460000 | Lares 7901-02 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-08-25 08:00 | 2022-08-25 08:00 | 2023-06-30 17:00 | 2023-06-30
PBUT06 - Distr Line Rebuild | 107516 | 334293 | 10154-002 | 10154-002 | 14F003470000 | Lares Prov. 7903-06 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-08-25 08:00 | 2022-08-25 08:00 | 2023-06-30 17:00 | 2023-06-30
PBUT06 - Distr Line Rebuild | 107516 | 334293 | 10154-006 | 10154-006 | 14F003480000 | Lares 7901-01 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-08-25 08:00 | 2022-08-25 08:00 | 2023-06-30 17:00 | 2023-06-30
PBUT06 - Distr Line Rebuild | 107558 | 546386 | 10156-001 | 10156-001 | 14F003490000 | El Yunque 2305-01 Supply | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-10-24 08:00 | 2022-10-24 08:00 | 2024-07-22 17:00 | 2023-10-02
PBUT06 - Distr Line Rebuild |  |  | 30003 | 30003 | 14F004310000 | UG System Repairs - CAPEX FED | Active | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30006 | 30006 | 14F005210000 | Arecibo Distr.Hospital 8001-01 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30006 | 30006 | 14F005220000 | Arecibo Hosp.Distr13KV 8015-09 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30006 | 30006 | 14F005230000 | Cambalache 8004-02 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30006 | 30006 | 14F005240000 | Cambalache 8004-03 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30006 | 30006 | 14F005250000 | Cambalache 8004-04 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30006 | 30006 | 14F005260000 | Dos Bocas 8005-01 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30007 | 30007 | 14F005270000 | Dominguito 8010-02 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30007 | 30007 | 14F005280000 | Dominguito 8010-03 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30007 | 30007 | 14F005290000 | Factor 1 8011-01 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30007 | 30007 | 14F005300000 | Mirador Azul 8007-01 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30007 | 30007 | 14F005310000 | Mirador Azul 8007-03 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30007 | 30007 | 14F005320000 | San Daniel 8013-02 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30008 | 30008 | 14F005330000 | Camuy 7601-03 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30008 | 30008 | 14F005340000 | Camuy 7601-04 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30008 | 30008 | 14F005350000 | Camuy Provisional 7602-06 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30008 | 30008 | 14F005360000 | Factor 13 KV 8014-08 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30008 | 30008 | 14F005370000 | Hatillo 7701-01 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30008 | 30008 | 14F005380000 | Hatillo 7701-03 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30009 | 30009 | 14F005390000 | Guajataca 7403-02 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30009 | 30009 | 14F005400000 | Pajuil 7702-02 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30009 | 30009 | 14F005410000 | Pajuil 7702-03 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30009 | 30009 | 14F005420000 | Quebradilla 7402-01 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30009 | 30009 | 14F005430000 | Quebradilla 7402-05 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30009 | 30009 | 14F005440000 | San Daniel 8013-01 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30010 | 30010 | 14F005450000 | Adjuntas Pueblo 8202-01 | Inactive | Inactive | [7 empty] | 2027-08-12 17:00
PBUT06 - Distr Line Rebuild |  |  | 30010 | 30010 | 14F005460000 | Adjuntas Pueblo 8202-02 | Cancel | Inactive | [7 empty] | 2027-08-12 17:00
PBUT06 - Distr Line Rebuild |  |  | 30010 | 30010 | 14F005470000 | Adjuntas Pueblo 8202-03 | Cancel | Inactive | [7 empty] | 2027-08-12 17:00
PBUT06 - Distr Line Rebuild |  |  | 30010 | 30010 | 14F005480000 | Guajataca 7403-03 | Inactive | Inactive | [7 empty] | 2027-08-12 17:00
PBUT06 - Distr Line Rebuild |  |  | 30010 | 30010 | 14F005490000 | Jayuya 8301-01 | Cancel | Inactive | [7 empty] | 2027-08-12 17:00
PBUT06 - Distr Line Rebuild |  |  | 30010 | 30010 | 14F005500000 | Yahuecas 8203-01 | Cancel | Inactive | [7 empty] | 2027-08-12 17:00
PBUT06 - Distr Line Rebuild |  |  | 30011 | 30011 | 14F005510000 | Jayuya II 8302-04 | Cancel | Inactive | [7 empty] | 2027-08-12 17:00
PBUT06 - Distr Line Rebuild |  |  | 30011 | 30011 | 14F005520000 | San Jose 8104-02 | Inactive | Inactive | [7 empty] | 2027-08-12 17:00
PBUT06 - Distr Line Rebuild |  |  | 30011 | 30011 | 14F005530000 | San Jose 8104-05 | Inactive | Inactive | [7 empty] | 2027-08-12 17:00
PBUT06 - Distr Line Rebuild |  |  | 30011 | 30011 | 14F005540000 | Utuado Pueblo 8101-01 | Cancel | Inactive | [7 empty] | 2027-08-12 17:00
PBUT06 - Distr Line Rebuild |  |  | 30011 | 30011 | 14F005550000 | Utuado Pueblo 8101-04 | Cancel | Inactive | [7 empty] | 2027-08-12 17:00
PBUT06 - Distr Line Rebuild |  |  | 30011 | 30011 | 14F005560000 | Utuado Pueblo 8101-05 | Cancel | Inactive | [7 empty] | 2027-08-12 17:00
PBUT06 - Distr Line Rebuild |  |  | 30012 | 30012 | 14F005570000 | Barceloneta Pueblo 8504-03 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30012 | 30012 | 14F005580000 | Ciales 8701-04 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30012 | 30012 | 14F005590000 | Cruce Davila 8501-01 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30012 | 30012 | 14F005600000 | Florida 8602-01 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30012 | 30012 | 14F005610000 | Florida 8602-03 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30012 | 30012 | 14F005620000 | Manatí Pueblo 8405-01 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30013 | 30013 | 14F005630000 | Manatí 13.2 KV 8404-02 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30013 | 30013 | 14F005640000 | Manatí Pueblo 8405-03 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30013 | 30013 | 14F005650000 | Morovis 8801-01 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30013 | 30013 | 14F005660000 | Morovis 8801-02 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30013 | 30013 | 14F005670000 | Morovis 8801-03 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30013 | 30013 | 14F005680000 | Morovis 8801-04 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30014 | 30014 | 14F005690000 | Breñas 9201-02 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30014 | 30014 | 14F005700000 | Santa Ana 9103-01 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30014 | 30014 | 14F005710000 | Vega Alta 8KV 9101-01 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30014 | 30014 | 14F005720000 | Vega Alta 8KV 9101-03 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30014 | 30014 | 14F005730000 | Vega Alta 8KV 9101-04 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30014 | 30014 | 14F005740000 | Vega Alta 13KV 9105-08 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30014 | 30014 | 14F005750000 | Vega Baja 2 9003-06 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30015 | 30015 | 14F005760000 | San Demetrio 9002-01 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30015 | 30015 | 14F005770000 | San Demetrio 9002-03 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30015 | 30015 | 14F005780000 | Vega Alta 13KV 9105-06 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30015 | 30015 | 14F005790000 | Vega Baja 1 9001-01 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30015 | 30015 | 14F005800000 | Vega Baja 2 9003-05 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30015 | 30015 | 14F005810000 | Vega Baja TC 13KV 9004-08 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30015-002 | 30015-002 | 14F005820000 | Vega Baja TC 13KV 9004-10 | Inactive | Inactive | [7 empty] | 2027-08-12 17:00
PBUT06 - Distr Line Rebuild |  |  | 30017 | 30017 | 14F005830000 | Bayamón TC 13KV #1 1711-04 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30017 | 30017 | 14F005840000 | Bayamón TC 13KV #1 1711-05 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30017 | 30017 | 14F005850000 | Buena Vista 1734-01 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30017 | 30017 | 14F005860000 | Buena Vista 1734-02 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30017-001 | 30017-001 | 14F005870000 | Cana (Interamericana)1719-15 | Inactive | Inactive | [7 empty] | 2027-08-12 17:00
PBUT06 - Distr Line Rebuild |  |  | 30017-002 | 30017-002 | 14F005880000 | Cana (Interamericana)1719-18 | Inactive | Inactive | [7 empty] | 2027-08-12 17:00
PBUT06 - Distr Line Rebuild |  |  | 30018 | 30018 | 14F005890000 | Grana PDS 1907-04 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30018 | 30018 | 14F005900000 | Grana PDS 1907-05 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30018 | 30018 | 14F005910000 | Grana PDS II 1909-08 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30018 | 30018 | 14F005920000 | Guaynabo 1901-01 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30018 | 30018 | 14F005930000 | Guaynabo 1901-04 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30018 | 30018 | 14F005940000 | Unibon 9501-01 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30019 | 30019 | 14F005950000 | Dorado Pueblo 9202-04 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30019 | 30019 | 14F005960000 | Dorado TC 9203-04 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30019 | 30019 | 14F005970000 | Dorado TC PDS 13KV 9207-08 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30019 | 30019 | 14F005980000 | Monterrey 9502-03 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30019 | 30019 | 14F005990000 | Monterrey PDS 13KV 9503-06 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30019 | 30019 | 14F006000000 | Naranjito 9801-01 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30020 | 30020 | 14F006010000 | Barrio Piñas 13KV 9405-05 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30020 | 30020 | 14F006020000 | Barrio Piñas 9403-01 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30020 | 30020 | 14F006030000 | Naranjito 2 9802-04 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30020 | 30020 | 14F006040000 | Naranjito 9801-02 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30020 | 30020 | 14F006050000 | Naranjito 9801-03 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30020 | 30020 | 14F006060000 | Toa Alta 9401-02 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30016 | 30016 | 14F006070000 | Bayamón TC 13KV #1 1711-01 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30016 | 30016 | 14F006080000 | Cana 1710-04 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30016 | 30016 | 14F006090000 | Cana 1710-05 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30016 | 30016 | 14F006100000 | Rio Bayamón 1709-02 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30016 | 30016 | 14F006110000 | Rio Bayamón 1709-05 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30016 | 30016 | 14F006120000 | Rio Bayamón 1709-03 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30021 | 30021 | 14F006130000 | Candelaria Arenas 1718-03 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30021-001 | 30021-001 | 14F006140000 | Crea 1717-01 | Inactive | Inactive | [7 empty] | 2027-08-12 17:00
PBUT06 - Distr Line Rebuild |  |  | 30021 | 30021 | 14F006150000 | Dorado TC 9203-02 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30021 | 30021 | 14F006160000 | Hato Tejas TC 1713-03 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30021-002 | 30021-002 | 14F006170000 | Hato Tejas TC 1713-05 | Inactive | Inactive | [7 empty] | 2027-08-12 17:00
PBUT06 - Distr Line Rebuild |  |  | 30021 | 30021 | 14F006180000 | Levittown 1806-01 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30021 | 30021 | 14F006190000 | Levittown 1806-03 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30022 | 30022 | 14F006200000 | Aguas Buenas 3701-02 | Inactive | Inactive | [7 empty] | 2027-08-12 17:00
PBUT06 - Distr Line Rebuild |  |  | 30022 | 30022 | 14F006210000 | Aguas Buenas 3701-04 | Cancel | Inactive | [7 empty] | 2027-08-12 17:00
PBUT06 - Distr Line Rebuild |  |  | 30022 | 30022 | 14F006220000 | Aibonito 3501-01 | Cancel | Inactive | [7 empty] | 2027-08-12 17:00
PBUT06 - Distr Line Rebuild |  |  | 30022 | 30022 | 14F006230000 | Aibonito 3501-02 | Cancel | Inactive | [7 empty] | 2027-08-12 17:00
PBUT06 - Distr Line Rebuild |  |  | 30022 | 30022 | 14F006240000 | Aibonito 3501-03 | Cancel | Inactive | [7 empty] | 2027-08-12 17:00
PBUT06 - Distr Line Rebuild |  |  | 30022 | 30022 | 14F006250000 | Aibonito PDS 3502-01 | Cancel | Inactive | [7 empty] | 2027-08-12 17:00
PBUT06 - Distr Line Rebuild |  |  | 30023 | 30023 | 14F006260000 | Barranquitas II 9602-03 | Inactive | Inactive | [7 empty] | 2027-08-12 17:00
PBUT06 - Distr Line Rebuild |  |  | 30023 | 30023 | 14F006270000 | Cayey Rural 3405-02 | Inactive | Inactive | [7 empty] | 2027-08-12 17:00
PBUT06 - Distr Line Rebuild |  |  | 30023 | 30023 | 14F006280000 | Cayey T.C. 3401-03 | Cancel | Inactive | [7 empty] | 2027-08-12 17:00
PBUT06 - Distr Line Rebuild |  |  | 30023 | 30023 | 14F006290000 | El Abanico PDS 9605-01 | Inactive | Inactive | [7 empty] | 2027-08-12 17:00
PBUT06 - Distr Line Rebuild |  |  | 30023 | 30023 | 14F006300000 | El Abanico PDS 9605-02 | Inactive | Inactive | [7 empty] | 2027-08-12 17:00
PBUT06 - Distr Line Rebuild |  |  | 30023 | 30023 | 14F006310000 | Jajome 3403-01 | Cancel | Inactive | [7 empty] | 2027-08-12 17:00
PBUT06 - Distr Line Rebuild |  |  | 30024 | 30024 | 14F006320000 | Cidra 3601-01 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30024 | 30024 | 14F006330000 | Cidra 3601-03 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30024 | 30024 | 14F006340000 | Comsat 3406-02 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30024 | 30024 | 14F006350000 | Comsat 3406-03 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30024 | 30024 | 14F006360000 | Las Cruces 3602-01 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30024 | 30024 | 14F006370000 | Las Cruces 3602-02 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30025 | 30025 | 14F006380000 | Caguax 3009-01 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30025 | 30025 | 14F006390000 | Orocovis 9902-03 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30025 | 30025 | 14F006400000 | Rio Cañas 3014-01 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30025 | 30025 | 14F006410000 | Sabanera II 3604-06 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30025 | 30025 | 14F006420000 | Sabanera II 3604-07 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30025 | 30025 | 14F006430000 | Villas de Castro 3013-03 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30026 | 30026 | 14F006440000 | Gurabo 3101-04 | Cancel | Inactive | [7 empty] | 2027-08-12 17:00
PBUT06 - Distr Line Rebuild |  |  | 30026 | 30026 | 14F006450000 | Juncos 2 13.2 KV 3205-08 | Cancel | Inactive | [7 empty] | 2027-08-12 17:00
PBUT06 - Distr Line Rebuild |  |  | 30026 | 30026 | 14F006460000 | Juncos 3201-02 | Inactive | Inactive | [7 empty] | 2027-08-12 17:00
PBUT06 - Distr Line Rebuild |  |  | 30026 | 30026 | 14F006470000 | Rio Cañas 3014-04 | Inactive | Inactive | [7 empty] | 2027-08-12 17:00
PBUT06 - Distr Line Rebuild |  |  | 30026 | 30026 | 14F006480000 | San Lorenzo II 3302-03 | Cancel | Inactive | [7 empty] | 2027-08-12 17:00
PBUT06 - Distr Line Rebuild |  |  | 30026 | 30026 | 14F006490000 | Veredas 3103-02 | Cancel | Inactive | [7 empty] | 2027-08-12 17:00
PBUT06 - Distr Line Rebuild |  |  | 30027 | 30027 | 14F006500000 | Candelero 2604-01 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30027 | 30027 | 14F006510000 | Candelero 2604-02 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30027 | 30027 | 14F006520000 | Candelero 2604-03 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30027 | 30027 | 14F006530000 | Humacao Pueblo 2601-01 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30027 | 30027 | 14F006540000 | Humacao T.C. 13 KV 2603-09 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30027 | 30027 | 14F006550000 | San Lorenzo II 3302-04 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30028 | 30028 | 14F006560000 | Caguax 3009-01. | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30028 | 30028 | 14F006570000 | Orocovis 9902-03. | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30028 | 30028 | 14F006580000 | Rio Cañas 3014-01. | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30028 | 30028 | 14F006590000 | Sabanera II 3604-06. | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30028 | 30028 | 14F006600000 | Sabanera II 3604-07. | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30028 | 30028 | 14F006610000 | Villas de Castro 3013-03. | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30029 | 30029 | 14F006620000 | Aguada 7201-03 | Inactive | Inactive | [7 empty] | 2027-08-12 17:00
PBUT06 - Distr Line Rebuild |  |  | 30029 | 30029 | 14F006630000 | Aguada 7201-05 | Inactive | Inactive | [7 empty] | 2027-08-12 17:00
PBUT06 - Distr Line Rebuild |  |  | 30029 | 30029 | 14F006640000 | Aguadilla Distr.Hosp 7003-02 | Cancel | Inactive | [7 empty] | 2027-08-12 17:00
PBUT06 - Distr Line Rebuild |  |  | 30029 | 30029 | 14F006650000 | Atalaya 7303-02 | Cancel | Inactive | [7 empty] | 2027-08-12 17:00
PBUT06 - Distr Line Rebuild |  |  | 30029 | 30029 | 14F006660000 | Ojo de Agua 7002-03 | Inactive | Inactive | [7 empty] | 2027-08-12 17:00
PBUT06 - Distr Line Rebuild |  |  | 30029 | 30029 | 14F006670000 | Ojo de Agua 7002-04 | Cancel | Inactive | [7 empty] | 2027-08-12 17:00
PBUT06 - Distr Line Rebuild |  |  | 30030 | 30030 | 14F006680000 | Aguadilla Distr.Hosp 7003-03 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30030 | 30030 | 14F006690000 | Ramey Field 2 7005-03 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30030 | 30030 | 14F006700000 | Ramey Field 3 7006-01 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30030 | 30030 | 14F006710000 | Ramey Field 3 7006-03 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30030 | 30030 | 14F006720000 | T-Bone 7011-01 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30030 | 30030 | 14F006730000 | Victoria 13.2 KV 7008-04 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30031 | 30031 | 14F006740000 | Campamento Mora 7502-01 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30031 | 30031 | 14F006750000 | Campamento Mora 7502-02 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30031 | 30031 | 14F006760000 | Campamento Mora 7502-03 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30031 | 30031 | 14F006770000 | Ceiba Baja 7012-01 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30031 | 30031 | 14F006780000 | Isabela 7503-04 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30031 | 30031 | 14F006790000 | T-Bone 7011-02 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30032 | 30032 | 14F006800000 | Isabela 7503-05 | Cancel | Inactive | [7 empty] | 2027-08-12 17:00
PBUT06 - Distr Line Rebuild |  |  | 30032 | 30032 | 14F006810000 | Isabela Planta 3 7504-01 | Inactive | Inactive | [7 empty] | 2027-08-12 17:00
PBUT06 - Distr Line Rebuild |  |  | 30032 | 30032 | 14F006820000 | Lares 7901-03 | Cancel | Inactive | [7 empty] | 2027-08-12 17:00
PBUT06 - Distr Line Rebuild |  |  | 30032 | 30032 | 14F006830000 | Lares 7901-04 | Cancel | Inactive | [7 empty] | 2027-08-12 17:00
PBUT06 - Distr Line Rebuild |  |  | 30032 | 30032 | 14F006840000 | Las Marías 6201-02 | Inactive | Inactive | [7 empty] | 2027-08-12 17:00
PBUT06 - Distr Line Rebuild |  |  | 30032 | 30032 | 14F006850000 | Mora 13.2 KV 7505-05 | Inactive | Inactive | [7 empty] | 2027-08-12 17:00
PBUT06 - Distr Line Rebuild |  |  | 30033 | 30033 | 14F006860000 | Capa 7103-01 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30033 | 30033 | 14F006870000 | Capa 7103-04 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30033 | 30033 | 14F006880000 | Moca 7101-03 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30033 | 30033 | 14F006890000 | Moca II 7104-06 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30033 | 30033 | 14F006900000 | San Sebastían 1 7801-01 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30033 | 30033 | 14F006910000 | San Sebastían 1 7801-03 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30034 | 30034 | 14F006920000 | Añasco 6101-02 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30034 | 30034 | 14F006930000 | Añasco 6101-04 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30034 | 30034 | 14F006940000 | Añasco 6101-05 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30034 | 30034 | 14F006950000 | Boquerón 6702-04 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30034 | 30034 | 14F006960000 | San Sebastían 2 7802-01 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30034 | 30034 | 14F006970000 | San Sebastían 2 7802-03 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30035 | 30035 | 14F006980000 | Acacias 4.16 KV 6801-01 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30035 | 30035 | 14F006990000 | Acacias 4.16 KV 6801-02 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30035 | 30035 | 14F007000000 | Acacias 4.16 KV 6801-03 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30035 | 30035 | 14F007010000 | Acacias 13.2 KV 6802-01 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30035 | 30035 | 14F007020000 | Acacias 13.2 KV 6802-02 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30035 | 30035 | 14F007030000 | Cabo Rojo 6703-03 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30036 | 30036 | 14F007040000 | Centro Médico 6008-04 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30036 | 30036 | 14F007050000 | Cerro las Mesas 6010-02 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30036 | 30036 | 14F007060000 | Cuatro Hermanos 6004-02 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30036 | 30036 | 14F007070000 | Maricao 6301-01 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30036 | 30036 | 14F007080000 | Maricao 6301-02 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30036 | 30036 | 14F007090000 | Once de Agosto 6001-03 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30037 | 30037 | 14F007100000 | Alturas de Mayaguez 6012-03 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30037 | 30037 | 14F007110000 | Alturas de Mayaguez 6012-05 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30037 | 30037 | 14F007120000 | Once de Agosto 13KV 6014-01 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30037 | 30037 | 14F007130000 | Once de Agosto 13KV 6014-03 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30037 | 30037 | 14F007140000 | Rincón 7301-02 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30037 | 30037 | 14F007150000 | Rincón 7301-04 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30038 | 30038 | 14F007160000 | Punta del Mar 7302-01 | Inactive | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30038 | 30038 | 14F007170000 | Rincón 7301-05 | Cancel | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30038 | 30038 | 14F007180000 | San Germán 6401-02 | Cancel | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30038 | 30038 | 14F007190000 | San Germán 6401-04 | Cancel | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30038 | 30038 | 14F007200000 | San Germán Industrial 6404-02 | Cancel | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30038 | 30038 | 14F007210000 | San Germán Industrial 6404-03 | Cancel | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30039 | 30039 | 14F007220000 | Arroyo 4101-01 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30039 | 30039 | 14F007230000 | Arroyo 4101-04 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30039 | 30039 | 14F007240000 | Coamo PDS 4603-02 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30039 | 30039 | 14F007250000 | Coamo Urbano 4602-03 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30039 | 30039 | 14F007260000 | Coamo Urbano 4602-04 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30039 | 30039 | 14F007270000 | Guayama 4001-03 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30040 | 30040 | 14F007280000 | Jobos T.C. 4003-02 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30040 | 30040 | 14F007290000 | Jobos T.C. 4003-03 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30040 | 30040 | 14F007300000 | Maunabo 4301-01 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30040 | 30040 | 14F007310000 | Maunabo 4301-02 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30040 | 30040 | 14F007320000 | Maunabo 4301-03 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30040 | 30040 | 14F007330000 | Patillas 4201-02 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30041 | 30041 | 14F007340000 | BO. Lapas 4504-01 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30041 | 30041 | 14F007350000 | Patillas 4201-03 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30041 | 30041 | 14F007360000 | Patillas 4201-04 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30041 | 30041 | 14F007370000 | Salinas Urbano 4501-01 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30041 | 30041 | 14F007380000 | Salinas Urbano 4501-04 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30041 | 30041 | 14F007390000 | Santa Isabel 4401-01 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30042 | 30042 | 14F007400000 | Fort Allen 13 KV 5803-02 | Inactive | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30042 | 30042 | 14F007410000 | Juana Diaz 4 KV 5802-01 | Cancel | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30042 | 30042 | 14F007420000 | Juana Diaz 4 KV 5802-03 | Cancel | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30042 | 30042 | 14F007430000 | Santa Isabel 4401-02 | Cancel | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30042 | 30042 | 14F007440000 | Usera 4601-01 | Cancel | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30042 | 30042 | 14F007450000 | Usera 4601-04 | Cancel | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30043 | 30043 | 14F007460000 | Ave Hostos 13 KV 5011-03 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30043 | 30043 | 14F007470000 | Ave Hostos 13 KV 5011-04 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30043 | 30043 | 14F007480000 | Buena Vista 5007-01 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30043 | 30043 | 14F007490000 | Canas T.C. 4.16 KV 5002-03 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30043 | 30043 | 14F007500000 | Canas T.C. 4.16 KV 5002-04 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30043 | 30043 | 14F007510000 | Pampanos 5005-03 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30044 | 30044 | 14F007520000 | Canas T.C. 13 KV 5018-02 | Cancel | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30044 | 30044 | 14F007530000 | Canas T.C. 13 KV 5018-04 | Inactive | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30044 | 30044 | 14F007540000 | Inabon 4 KV 5013-01 | Cancel | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30044 | 30044 | 14F007550000 | Inabon 4 KV 5013-02 | Cancel | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30044 | 30044 | 14F007560000 | Inabon 4 KV 5013-03 | Cancel | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30044 | 30044 | 14F007570000 | Villa del Carmen 5016-01 | Inactive | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30045 | 30045 | 14F007580000 | Canas T.C. 13 KV 5018-05 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30045 | 30045 | 14F007590000 | Portugues 4 KV 5021-01 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30045 | 30045 | 14F007600000 | Toa Vaca 5902-02 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30045 | 30045 | 14F007610000 | Villalba 4 KV 5901-01 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30045 | 30045 | 14F007620000 | Villalba 4 KV 5901-02 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30045 | 30045 | 14F007630000 | Villalba 4 KV 5901-03 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30046 | 30046 | 14F007640000 | Guanica TC 5602-01 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30046 | 30046 | 14F007650000 | Guanica TC 5602-03 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30046 | 30046 | 14F007660000 | Guayanilla Pueblo 5501-01 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30046 | 30046 | 14F007670000 | Guayanilla Pueblo 5501-02 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30046 | 30046 | 14F007680000 | Guayanilla Pueblo 5501-03 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30046 | 30046 | 14F007690000 | Lajas 6601-01 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30047 | 30047 | 14F007700000 | Lajas 6601-04 | Cancel | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30047 | 30047 | 14F007710000 | Peñuelas Pueblo 5401-01 | Cancel | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30047 | 30047 | 14F007720000 | Peñuelas Pueblo 5401-02 | Inactive | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30047 | 30047 | 14F007730000 | Peñuelas Pueblo 5401-03 | Cancel | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30047 | 30047 | 14F007740000 | Peñuelas Pueblo 5401-04 | Cancel | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30047 | 30047 | 14F007750000 | Sabana Grande 6501-01 | Inactive | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30048 | 30048 | 14F007760000 | Sabana Grande 6501-02 | Inactive | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30048 | 30048 | 14F007770000 | Sabana Grande 6501-03 | Inactive | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30048 | 30048 | 14F007780000 | Sabana Grande 6501-04 | Inactive | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30048 | 30048 | 14F007790000 | Yauco Hidro 1 5301-01 | Cancel | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30048 | 30048 | 14F007800000 | Yauco Pueblo 1 5302-01 | Cancel | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30048 | 30048 | 14F007810000 | Yauco Pueblo 1 5302-04 | Cancel | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30049 | 30049 | 14F007820000 | Yauco Plaza PDS 5305-03 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30049 | 30049 | 14F007830000 | Yauco Pueblo II 5304-01 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30049 | 30049 | 14F007840000 | Yauco Pueblo II 5304-02 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30049 | 30049 | 14F007850000 | Yauco Pueblo II 5304-03 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30049 | 30049 | 14F007860000 | Yauco Pueblo II 5304-05 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30050 | 30050 | 14F007870000 | Barrazas 2 1607-01 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30050 | 30050 | 14F007880000 | Barrazas 2 1607-03 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30050 | 30050 | 14F007890000 | Canovanas T.C. #2 2404-05 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30050 | 30050 | 14F007900000 | Canovanas T.C. #2 2404-07 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30050 | 30050 | 14F007910000 | Canovanas T.C. #2 2404-08 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30050 | 30050 | 14F007920000 | Ceramica 13KV 1619-01 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30051 | 30051 | 14F007930000 | Ceramica 13 KV 1619-03 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30051 | 30051 | 14F007940000 | Rio Grande 8KV 2301-01 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30051 | 30051 | 14F007950000 | Sabana Llana 13 KV #1 1646-01 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30051 | 30051 | 14F007960000 | Sabana Llana 13 KV #1 1646-03 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30051 | 30051 | 14F007970000 | Sabana Llana 13 KV #1 1646-05 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30051 | 30051 | 14F007980000 | Villamar 1657-03 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30052 | 30052 | 14F007990000 | Alturas RioGrande 13KV 2302-01 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30052 | 30052 | 14F008000000 | Alturas RioGrande 13KV 2302-02 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30052 | 30052 | 14F008010000 | Alturas RioGrande 13KV 2302-03 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30052 | 30052 | 14F008020000 | Daguao 2101-01 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30052 | 30052 | 14F008030000 | Fajardo Pueblo 2002-01 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30052 | 30052 | 14F008040000 | Palmer TC 2305-04 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30053 | 30053 | 14F008050000 | Fajardo PDS 2005-09 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30053 | 30053 | 14F008060000 | Fajardo Pueblo 2002-03 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30053 | 30053 | 14F008070000 | Luquillo 2201-01 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30053 | 30053 | 14F008080000 | Marina Puerto del Rey 2006-03 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30053 | 30053 | 14F008090000 | Monacillos 13 KV 1346-06 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30053 | 30053 | 14F008100000 | Venezuela 13KV 1348-07 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30054 | 30054 | 14F008110000 | Baldrich 13KV 1424-06 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30054 | 30054 | 14F008120000 | Hato Rey GIS 13KV 1404-07 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30054 | 30054 | 14F008130000 | Las Lomas 1525-04 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30054 | 30054 | 14F008140000 | Las Lomas 1525-05 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30054 | 30054 | 14F008150000 | Tres Monjitas 1414-04 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30054 | 30054 | 14F008160000 | Venezula 13KV 1348-08 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30055 | 30055 | 14F008170000 | Buen Pastor 1908-03 | Cancel | Inactive | [7 empty] | 2025-05-16 17:00
PBUT06 - Distr Line Rebuild |  |  | 30055 | 30055 | 14F008180000 | Cachete 4KV 1530-09 | Inactive | Inactive | [7 empty] | 2025-05-16 17:00
PBUT06 - Distr Line Rebuild |  |  | 30055 | 30055 | 14F008190000 | Cachete 13KV 1529-12 | Cancel | Inactive | [7 empty] | 2025-05-16 17:00
PBUT06 - Distr Line Rebuild |  |  | 30055 | 30055 | 14F008200000 | Cachete 13KV 1529-13 | Cancel | Inactive | [7 empty] | 2025-05-16 17:00
PBUT06 - Distr Line Rebuild |  |  | 30055 | 30055 | 14F008210000 | Martin Peña GIS I 1111-01 | Cancel | Inactive | [7 empty] | 2025-05-16 17:00
PBUT06 - Distr Line Rebuild |  |  | 30055 | 30055 | 14F008220000 | Minillas 1114-01 | Cancel | Inactive | [7 empty] | 2025-05-16 17:00
PBUT06 - Distr Line Rebuild |  |  | 30056 | 30056 | 14F008230000 | Falu 1334-01 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30056 | 30056 | 14F008240000 | Isla Grande GIS I 1119-04 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30056-001 | 30056-001 | 14F008250000 | Llorens Torres 13KV 1118-08 | Inactive | Inactive | [7 empty] | 2027-08-12 17:00
PBUT06 - Distr Line Rebuild |  |  | 30056 | 30056 | 14F008260000 | Llorens Torres 13KV 1118-09 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30056 | 30056 | 14F008270000 | Viaducto 13KV 1115-04 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30056 | 30056 | 14F008280000 | Villa Betina 1303-03 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30057 | 30057 | 14F008290000 | Berwind 13KV 1336-07 | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30057 | 30057 | 14F008300000 | La Muda 1343-01 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30057 | 30057 | 14F008310000 | La Muda 1343-05 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30057 | 30057 | 14F008320000 | Monacillos 13KV 1346-03 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30057 | 30057 | 14F008330000 | Monacillos 13KV 1346-04 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30057 | 30057 | 14F008340000 | Monacillos 13KV 1346-05 | Cancel
PBUT06 - Distr Line Rebuild |  |  | 30058 | 30058 | 14F008350000 | Encantada 1206-03 | Inactive | Inactive | [7 empty] | 2025-04-28 17:00
PBUT06 - Distr Line Rebuild |  |  | 30058 | 30058 | 14F008360000 | Encantada 1206-04 | Cancel | Inactive | [7 empty] | 2025-04-28 17:00
PBUT06 - Distr Line Rebuild |  |  | 30058 | 30058 | 14F008370000 | Quebrada Negritos 1205-02 | Cancel | Inactive | [7 empty] | 2025-04-28 17:00
PBUT06 - Distr Line Rebuild |  |  | 30058 | 30058 | 14F008380000 | Quebrada Negritos 1205-03 | Cancel | Inactive | [7 empty] | 2025-04-28 17:00
PBUT06 - Distr Line Rebuild |  |  | 30038 | 30038 | 14F008390000 | San Germán TC 13KV 6406-04 | Cancel | Inactive
PBUT06 - Distr Line Rebuild | 108015 | 754350 | 30003-001 | 30003-001 | 14F020300000 | UG Feeder 1115-02 Santurce | Inactive | Inactive | CAP2 | ISSUE | Withdrawn | Discontinued | Process Discontinued |  |  | 2024-09-30 08:00 | 2024-10-16
PBUT06 - Distr Line Rebuild | 108015 | 754350 | 30003-002 | 30003-002 | 14F020310000 | UG Feeder 1115-03 Santurce | Inactive | Inactive | CAP2 | WARNING | Withdrawn | Discontinued | Process Discontinued |  |  | 2024-09-30 17:00 | 2024-10-16
PBUT06 - Distr Line Rebuild | 108015 | 754350 | 30003-003 | 30003-003 | 14F020320000 | UG Feeder 1115-04 - Santurce | Inactive | Inactive | CAP2 | ISSUE | Withdrawn | Discontinued | Process Discontinued |  |  | 2024-09-30 17:00 | 2024-10-16
PBUT06 - Distr Line Rebuild | 108015 | 754350 | 30003-004 | 30003-004 | 14F020330000 | UG Feeder 1117-07 - Santurce | Inactive | Inactive | CAP2 | ISSUE | Withdrawn | Discontinued | Process Discontinued |  |  | 2024-09-30 17:00 | 2024-10-16
PBUT06 - Distr Line Rebuild | 108015 | 754350 | 30003-007 | 30003-007 | 14F020340000 | UG Feeder 1117-08 - Santurce | Inactive | Inactive | CAP2 |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2024-09-30 17:00 | 2024-10-16
PBUT06 - Distr Line Rebuild | 108016 | 754351 | 30003-005 | 30003-005 | 14F020350000 | UG Feeder 1424-07 - Santurce | Inactive | Inactive | CAP2 | ISSUE | Withdrawn | Discontinued | Process Discontinued |  |  | 2024-09-30 17:00 | 2024-10-22
PBUT06 - Distr Line Rebuild | 108016 | 754351 | 30003-006 | 30003-006 | 14F020360000 | UG Feeder 1424-08 - Santurce | Inactive | Inactive | CAP2 | ISSUE | Withdrawn | Discontinued | Process Discontinued |  |  | 2024-09-30 17:00 | 2024-10-22
PBUT06 - Distr Line Rebuild |  |  | 30003-008 | 30003-008 | 14F020370000 | UG Feeder 1204-02-Conquistador | Inactive | Inactive | CAP1 | [6 empty] | 2025-08-29 17:00
PBUT06 - Distr Line Rebuild |  |  | 30003-009 | 30003-009 | 14F020380000 | UG Feeder 1204-03-Conquistador | Inactive | Inactive | CAP1 | [6 empty] | 2025-08-29 17:00
PBUT06 - Distr Line Rebuild |  |  | 30003-010 | 30003-010 | 14F020390000 | UG Feeder 1204-04-Conquistador | Inactive | Inactive | CAP1 | [6 empty] | 2025-08-29 17:00
PBUT06 - Distr Line Rebuild |  |  | 30003-011 | 30003-011 | 14F020400000 | UG Feeder 1204-05-Conquistador | Inactive | Inactive | CAP1 | [6 empty] | 2025-08-29 17:00
PBUT06 - Distr Line Rebuild |  |  | 30003-012 | 30003-012 | 14F020410000 | UG Feeder 1711-04 - Levittown | Inactive | Inactive | CAP1 | [6 empty] | 2025-08-29 17:00
PBUT06 - Distr Line Rebuild |  |  | 30003-013 | 30003-013 | 14F020420000 | UG Feeder 1717-01 - Levittown | Inactive | Inactive | CAP1 | [6 empty] | 2025-08-29 17:00
PBUT06 - Distr Line Rebuild |  |  | 30003-014 | 30003-014 | 14F020430000 | UG Feeder 1806-01 - Levittown | Inactive | Inactive | CAP1 | [6 empty] | 2025-08-29 17:00
PBUT06 - Distr Line Rebuild |  |  | 30003-015 | 30003-015 | 14F020440000 | UG Feeder 1806-02 - Levittown | Inactive | Inactive | CAP1 | [6 empty] | 2025-08-29 17:00
PBUT06 - Distr Line Rebuild |  |  | 30003-016 | 30003-016 | 14F020450000 | UG Feeder 1806-03 - Levittown | Inactive | Inactive | CAP1 | [6 empty] | 2025-08-29 17:00
PBUT06 - Distr Line Rebuild |  |  | 30000 | 30000 | 14N000490000 | Distrib. Line New Extensions | Closed
PBUT06 - Distr Line Rebuild |  |  | 30003 | 30003 | 14N000660000 | UG System Repairs - NME | Active | Inactive
PBUT06 - Distr Line Rebuild |  |  | 30070 | 30070 | 14N001120000 | T&D New Business | Inactive
PBUT06 - Distr Line Rebuild | 1294 | 83182 | 90102 | 90102 | 15F019680000 | CAT Z - PBUT6 | Active |  |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  |  | 2020-02-05 12:48
PBUT06 - Distr Line Rebuild |  |  | 30003 | 30003 | 15N002040000 | UG System Repairs - O&M | Inactive | Inactive
PBUT07 - Substation Reliability | 11537 | 551925 | 60009 |  | 10F007370000 | Rincon 4kV RTU Replacement | Active |  |  |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval |  |  |  | 2022-07-15 | 2024-11-01 15:15
PBUT07 - Substation Reliability | 11537 | 551925 | 60009 |  | 10F007380000 | Combate7kVSCADARemAcc&RTU-Repl | Active |  |  |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval |  |  |  | 2022-07-15 | 2024-11-01 15:15
PBUT07 - Substation Reliability | 11537 | 551925 | 60009 |  | 10F007390000 | Viaducto SCADA RTU | Active |  |  |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval |  |  |  | 2022-07-15 | 2024-11-01 15:15
PBUT07 - Substation Reliability | 11537 | 551925 | 60009 |  | 10F007400000 | Adjuntas 8kV SCADA Remote RTU | Active |  |  |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval |  |  |  | 2022-07-15 | 2024-11-01 15:15
PBUT07 - Substation Reliability | 11537 | 551925 | 60009 |  | 10F007410000 | San German Indstrial SCADA RTU | Active |  |  |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval |  |  |  | 2022-07-15 | 2024-11-01 15:15
PBUT07 - Substation Reliability | 11537 | 551925 | 60009 |  | 10F007420000 | Centro Medico 4kV SCADA RTU | Active |  |  |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval |  |  |  | 2022-07-15 | 2024-11-01 15:15
PBUT07 - Substation Reliability | 11537 | 551925 | 60009 |  | 10F007430000 | Mayaguez TC SCADA Remote RTU | Active |  |  |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval |  |  |  | 2022-07-15 | 2024-11-01 15:15
PBUT07 - Substation Reliability | 11537 | 551925 | 60009 |  | 10F007440000 | Cuatro Hermanos 4kV SCADA RTU | Active |  |  |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval |  |  |  | 2022-07-15 | 2024-11-01 15:15
PBUT07 - Substation Reliability | 108161 | 956593 | 40008-006 | 40008-006 | 10F008080000 | Factor 8014 Transformer Rplcmt | Active | Active | CAP4 |  | Active | Phase 5 - Post Award Phase | Obligated | 2025-04-09 08:00 | 2025-04-09 08:00 |  | 2025-06-23 | 2025-09-22 16:15
PBUT07 - Substation Reliability | 108134 | 825843 | 40006 | 40006 | 10F008100000 | Guanica TC Transformer Rplcmt | Active | Active | CAP4 |  | Active | Phase 5 - Post Award Phase | Obligated | 2025-02-10 08:00 | 2025-02-10 08:00 |  | 2025-04-09 | 2025-09-22 16:15
PBUT07 - Substation Reliability | 11537 | 551925 |  |  | 10F008110000 | Aguada 4kV SCADA Remote Access | Active |  | CAP4 |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval |  |  |  | 2022-07-15 | 2024-11-01 15:15
PBUT07 - Substation Reliability | 11537 | 551925 |  |  | 10F008120000 | Albergue Olimpico (Barrio Lapa | Active |  | CAP4 |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval |  |  |  | 2022-07-15 | 2024-11-01 15:15
PBUT07 - Substation Reliability | 11537 | 551925 |  |  | 10F008130000 | Alturas de Mayaguez 13 kV SCAD | Active |  | CAP4 |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval |  |  |  | 2022-07-15 | 2024-11-01 15:15
PBUT07 - Substation Reliability | 11537 | 551925 |  |  | 10F008140000 | Capa 4 kV SCADA Remote Access | Active |  | CAP4 |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval |  |  |  | 2022-07-15 | 2024-11-01 15:15
PBUT07 - Substation Reliability | 11537 | 551925 |  |  | 10F008150000 | Carolina Pueblo 4 kV SCADA Rem | Active |  | CAP4 |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval |  |  |  | 2022-07-15 | 2024-11-01 15:15
PBUT07 - Substation Reliability | 11537 | 551925 |  |  | 10F008160000 | Colegio SECT SCADA Remote Acce | Active |  | CAP4 |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval |  |  |  | 2022-07-15 | 2024-11-01 15:15
PBUT07 - Substation Reliability | 11537 | 551925 |  |  | 10F008170000 | Guaraguao 4 kV SCADA Remote Ac | Active |  | CAP4 |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval |  |  |  | 2022-07-15 | 2024-11-01 15:15
PBUT07 - Substation Reliability | 11537 | 551925 |  |  | 10F008180000 | Guayama Rural 4 kV SCADA Remot | Active |  | CAP4 |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval |  |  |  | 2022-07-15 | 2024-11-01 15:15
PBUT07 - Substation Reliability | 11537 | 551925 |  |  | 10F008190000 | Hacienda San Jose 13 kV SCADA | Active |  | CAP4 |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval |  |  |  | 2022-07-15 | 2024-11-01 15:15
PBUT07 - Substation Reliability | 11537 | 551925 |  |  | 10F008200000 | Hospital Distrito Aguadilla 4 | Active |  | CAP4 |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval |  |  |  | 2022-07-15 | 2024-11-01 15:15
PBUT07 - Substation Reliability | 11537 | 551925 |  |  | 10F008210000 | Isabela Pueblo 4 kV SCADA Remo | Active |  | CAP4 |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval |  |  |  | 2022-07-15 | 2024-11-01 15:15
PBUT07 - Substation Reliability | 11537 | 551925 |  |  | 10F008220000 | Juan Martin 13 kV SCADA Remote | Active |  | CAP4 |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval |  |  |  | 2022-07-15 | 2024-11-01 15:15
PBUT07 - Substation Reliability | 11537 | 551925 |  |  | 10F008230000 | Lares 13 kV SCADA Remote Acces | Active |  | CAP4 |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval |  |  |  | 2022-07-15 | 2024-11-01 15:15
PBUT07 - Substation Reliability | 11537 | 551925 |  |  | 10F008240000 | Leon 4kV SCADA Remote Access | Active |  | CAP4 |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval |  |  |  | 2022-07-15 | 2024-11-01 15:15
PBUT07 - Substation Reliability | 11537 | 551925 |  |  | 10F008250000 | Yabucoa TC SCADA Remote Access | Active |  | CAP4 |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval |  |  |  | 2022-07-15 | 2024-11-01 15:15
PBUT07 - Substation Reliability | 11537 | 551925 |  |  | 10F008260000 | Manati TC 13 kV SCADA Remote A | Active |  | CAP4 |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval |  |  |  | 2022-07-15 | 2024-11-01 15:15
PBUT07 - Substation Reliability | 11537 | 551925 |  |  | 10F008270000 | Pueblito del Rio 8kV RTU Repla | Active |  | CAP4 |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval |  |  |  | 2022-07-15 | 2024-11-01 15:15
PBUT07 - Substation Reliability | 11537 | 551925 |  |  | 10F008280000 | Quintana 4 kV SCADA Remote Acc | Active |  | CAP4 |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval |  |  |  | 2022-07-15 | 2024-11-01 15:15
PBUT07 - Substation Reliability | 11537 | 551925 |  |  | 10F008290000 | San Juan Plant SCADA Remote Ac | Active |  | CAP4 |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval |  |  |  | 2022-07-15 | 2024-11-01 15:15
PBUT07 - Substation Reliability | 11537 | 551925 |  |  | 10F008300000 | Santa Ana 8 kV SCADA Remote Ac | Active |  | CAP4 |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval |  |  |  | 2022-07-15 | 2024-11-01 15:15
PBUT07 - Substation Reliability | 11537 | 551925 |  |  | 10F008310000 | T-Bone 13 kV SCADA Remote Acce | Active |  | CAP4 |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval |  |  |  | 2022-07-15 | 2024-11-01 15:15
PBUT07 - Substation Reliability | 11537 | 551925 |  |  | 10F008320000 | Utuado 4 kV SCADA Remote Acces | Active |  | CAP4 |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval |  |  |  | 2022-07-15 | 2024-11-01 15:15
PBUT07 - Substation Reliability | 11537 | 551925 | 60009 | 60009 | 10F008330000 | Vieques PLT SCADA Remote | Inactive |  |  |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval |  |  |  | 2022-07-15 | 2024-11-01 15:15
PBUT07 - Substation Reliability | 11537 | 551925 | 60009 | 60009 | 10F008340000 | Arroyo 4 kV SCADA Remote | Inactive |  |  |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval |  |  |  | 2022-07-15 | 2024-11-01 15:15
PBUT07 - Substation Reliability | 11537 | 551925 | 60009 | 60009 | 10F008350000 | Atalaya 4 kV SCADA Remote Acce | Inactive |  |  |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval |  |  |  | 2022-07-15 | 2024-11-01 15:15
PBUT07 - Substation Reliability | 11537 | 551925 | 60009 | 60009 | 10F008360000 | Barranquitas 8 kV SCADA Remote | Inactive |  |  |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval |  |  |  | 2022-07-15 | 2024-11-01 15:15
PBUT07 - Substation Reliability | 11537 | 551925 | 60009 | 60009 | 10F008370000 | Barrazas II 4 kV SCADA Remote | Inactive |  |  |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval |  |  |  | 2022-07-15 | 2024-11-01 15:15
PBUT07 - Substation Reliability | 11537 | 551925 | 60009 | 60009 | 10F008380000 | Barrio Vega 4 kV SCADA Remote | Inactive |  |  |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval |  |  |  | 2022-07-15 | 2024-11-01 15:15
PBUT07 - Substation Reliability | 11537 | 551925 | 60009 | 60009 | 10F008390000 | Branderi 4kV SCADA Remote | Inactive |  |  |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval |  |  |  | 2022-07-15 | 2024-11-01 15:15
PBUT07 - Substation Reliability | 11537 | 551925 | 60009 | 60009 | 10F008400000 | Buen Pastor 13 kV SCADA | Inactive |  |  |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval |  |  |  | 2022-07-15 | 2024-11-01 15:15
PBUT07 - Substation Reliability | 11537 | 551925 | 60009 | 60009 | 10F008410000 | Caguax 8 kV SCADA Remote | Inactive |  |  |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval |  |  |  | 2022-07-15 | 2024-11-01 15:15
PBUT07 - Substation Reliability | 11537 | 551925 | 60009 | 60009 | 10F008420000 | Centro Medico Prov. 13kV SCADA | Inactive |  |  |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval |  |  |  | 2022-07-15 | 2024-11-01 15:15
PBUT07 - Substation Reliability | 11537 | 551925 | 60009 | 60009 | 10F008430000 | Cerro las Mesas 4 kV SCADA | Inactive |  |  |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval |  |  |  | 2022-07-15 | 2024-11-01 15:15
PBUT07 - Substation Reliability | 11537 | 551925 | 60009 | 60009 | 10F008440000 | Falu 4 kV SCADA Remote | Inactive |  |  |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval |  |  |  | 2022-07-15 | 2024-11-01 15:15
PBUT07 - Substation Reliability | 11537 | 551925 | 60009 | 60009 | 10F008450000 | Humacao 8 kV SCADA Remote | Inactive |  |  |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval |  |  |  | 2022-07-15 | 2024-11-01 15:15
PBUT07 - Substation Reliability | 11537 | 551925 | 60009 | 60009 | 10F008460000 | Indiera Alta 4 kV SCADA Remote | Inactive |  |  |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval |  |  |  | 2022-07-15 | 2024-11-01 15:15
PBUT07 - Substation Reliability | 11537 | 551925 | 60009 | 60009 | 10F008470000 | Lago Guajataca 4 kV SCADA | Inactive |  |  |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval |  |  |  | 2022-07-15 | 2024-11-01 15:15
PBUT07 - Substation Reliability | 11537 | 551925 | 60009 | 60009 | 10F008480000 | Las Marias 4 kV SCADA Remote | Inactive |  |  |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval |  |  |  | 2022-07-15 | 2024-11-01 15:15
PBUT07 - Substation Reliability | 11537 | 551925 | 60009 | 60009 | 10F008490000 | Manati Urbano 13kV SCADARemote | Inactive |  |  |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval |  |  |  | 2022-07-15 | 2024-11-01 15:15
PBUT07 - Substation Reliability | 11537 | 551925 | 60009 | 60009 | 10F008500000 | Moca 4 kV SCADA Remote Access | Inactive |  |  |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval |  |  |  | 2022-07-15 | 2024-11-01 15:15
PBUT07 - Substation Reliability | 11537 | 551925 | 60009 | 60009 | 10F008510000 | Moca SECT SCADA Remote | Inactive |  |  |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval |  |  |  | 2022-07-15 | 2024-11-01 15:15
PBUT07 - Substation Reliability | 11537 | 551925 | 60009 | 60009 | 10F008520000 | Monte del Estado 4 kV SCADA | Inactive |  |  |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval |  |  |  | 2022-07-15 | 2024-11-01 15:15
PBUT07 - Substation Reliability | 11537 | 551925 | 60009 | 60009 | 10F008530000 | Mora 13 kV SCADA Remote Access | Inactive |  |  |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval |  |  |  | 2022-07-15 | 2024-11-01 15:15
PBUT07 - Substation Reliability | 11537 | 551925 | 60009 | 60009 | 10F008540000 | Ojo de Agua 4 kV SCADA Remote | Inactive |  |  |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval |  |  |  | 2022-07-15 | 2024-11-01 15:15
PBUT07 - Substation Reliability | 11537 | 551925 | 60009 | 60009 | 10F008550000 | Parque Escorial 13 kV SCADA | Inactive |  |  |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval |  |  |  | 2022-07-15 | 2024-11-01 15:15
PBUT07 - Substation Reliability | 11537 | 551925 | 60009 | 60009 | 10F008560000 | Puerto del Rey 13 kV SCADA | Inactive |  |  |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval |  |  |  | 2022-07-15 | 2024-11-01 15:15
PBUT07 - Substation Reliability | 11537 | 551925 | 60009 | 60009 | 10F008570000 | Quebradillas 4 kV SCADA Remote | Inactive |  |  |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval |  |  |  | 2022-07-15 | 2024-11-01 15:15
PBUT07 - Substation Reliability | 11537 | 551925 | 60009 | 60009 | 10F008580000 | Saint Just 4 kV SCADA Remote | Inactive |  |  |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval |  |  |  | 2022-07-15 | 2024-11-01 15:15
PBUT07 - Substation Reliability | 11537 | 551925 | 60009 | 60009 | 10F008590000 | Divisoria 4 kV SCADA Remote | Inactive |  |  |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval |  |  |  | 2022-07-15 | 2024-11-01 15:15
PBUT07 - Substation Reliability |  |  | 40006 | 40006 | 10N000200000 | GuanicaTC H.Vol.Eq.Repl.MinRep | Inactive | Active | [5 empty] | 2025-02-10 08:00 | 2025-02-10 08:00
PBUT07 - Substation Reliability |  |  |  |  | 10N000350000 | Grid Reinforcement | Cancel
PBUT07 - Substation Reliability |  |  | 40007 | 40007 | 10N000370000 | Maunabo TC | Active | Active | [5 empty] | 2025-03-19 08:00 | 2025-03-19 08:00 | 2026-07-09 17:00
PBUT07 - Substation Reliability |  |  | 40018 | 40018 | 10N000770000 | Substation Battery Bank repla | Inactive
PBUT07 - Substation Reliability |  |  | 40021 | 40021 | 10N001660000 | High Voltage Equipment Replace | Inactive
PBUT07 - Substation Reliability |  |  | 40054 | 40054 | 10N003870000 | Reliability AdjuntasPueblo | Inactive
PBUT07 - Substation Reliability |  |  | 40054 | 40054 | 10N003880000 | Reliability AltRioGrande | Inactive
PBUT07 - Substation Reliability |  |  | 40054 | 40054 | 10N003890000 | Reliability AreciboHospDist | Inactive
PBUT07 - Substation Reliability |  |  | 40054 | 40054 | 10N003900000 | Reliability HatoReyTC | Inactive
PBUT07 - Substation Reliability |  |  | 40054 | 40054 | 10N003910000 | Reliability CanasTC | Inactive
PBUT07 - Substation Reliability |  |  | 40054 | 40054 | 10N003920000 | Reliability CeibaBaja | Inactive
PBUT07 - Substation Reliability |  |  | 40054 | 40054 | 10N003930000 | Reliability CharcoHondo | Inactive
PBUT07 - Substation Reliability |  |  | 40054 | 40054 | 10N003940000 | Reliability Ciales | Inactive
PBUT07 - Substation Reliability |  |  | 40054 | 40054 | 10N003950000 | Reliability FortAllen | Inactive
PBUT07 - Substation Reliability |  |  | 40054 | 40054 | 10N003960000 | Reliability GuanicaTC | Inactive
PBUT07 - Substation Reliability |  |  | 40054 | 40054 | 10N003970000 | Reliability HumacaoTC | Closed
PBUT07 - Substation Reliability |  |  | 40054 | 40054 | 10N003980000 | Reliability JobosTC | Inactive
PBUT07 - Substation Reliability |  |  | 40054 | 40054 | 10N003990000 | Reliability JuanMartin | Inactive
PBUT07 - Substation Reliability |  |  | 40054 | 40054 | 10N004000000 | Reliability LasPiedras | Inactive
PBUT07 - Substation Reliability |  |  | 40054 | 40054 | 10N004010000 | Reliability ManatiTC | Inactive
PBUT07 - Substation Reliability |  |  | 40054 | 40054 | 10N004020000 | Reliability Monacillos | Inactive
PBUT07 - Substation Reliability |  |  | 40054 | 40054 | 10N004030000 | Reliability OjodeAgua | Inactive
PBUT07 - Substation Reliability |  |  | 40054 | 40054 | 10N004040000 | Reliability PuntadelMar | Inactive
PBUT07 - Substation Reliability |  |  | 40054 | 40054 | 10N004050000 | Reliability BayamonTC | Inactive
PBUT07 - Substation Reliability |  |  | 40054 | 40054 | 10N004060000 | Reliability SanFernando | Inactive
PBUT07 - Substation Reliability |  |  | 40054 | 40054 | 10N004070000 | Reliability SanGermanTC | Inactive
PBUT07 - Substation Reliability |  |  | 40054 | 40054 | 10N004080000 | Reliability VegaAlta9101 | Inactive
PBUT07 - Substation Reliability |  |  | 40054 | 40054 | 10N004090000 | Reliability VegaAlta9105 | Cancel
PBUT07 - Substation Reliability |  |  | 40054 | 40054 | 10N004100000 | Reliability VegaBajaTC | Inactive
PBUT07 - Substation Reliability |  |  | 40054 | 40054 | 10N004110000 | Reliability Venezuela | Inactive
PBUT07 - Substation Reliability |  |  | 40054 | 40054 | 10N004120000 | Reliability Verdemar | Cancel
PBUT07 - Substation Reliability |  |  | 40054 | 40054 | 10N004130000 | Reliability Viaducto | Inactive
PBUT07 - Substation Reliability |  |  | 40054 | 40054 | 10N004140000 | Reliability YaucoPlazaPDS | Inactive
PBUT07 - Substation Reliability |  |  | 40054 | 40054 | 10N004150000 | Reliability YaucoPueb1 | Cancel
PBUT07 - Substation Reliability |  |  | 24000 | 24000 | 10N004350000 | L 51100 prot EcoElec to C Sur | Active
PBUT07 - Substation Reliability |  |  | 40054 | 40054 | 10N006050000 | Reliability Candelero | Inactive
PBUT07 - Substation Reliability |  |  | 40054 | 40054 | 10N006060000 | Reliability RioGrandeEstates | Cancel
PBUT07 - Substation Reliability |  |  | 40054 | 40054 | 10N006070000 | Reliability CanovanasTC | Inactive
PBUT07 - Substation Reliability |  |  | 40054 | 40054 | 10N006080000 | Reliability BerwindTC | Active
PBUT07 - Substation Reliability |  |  | 40054 | 40054 | 10N006090000 | Reliability Aguada | Inactive
PBUT07 - Substation Reliability |  |  | 40054 | 40054 | 10N006100000 | Reliability Cana | Inactive
PBUT07 - Substation Reliability |  |  | 40054 | 40054 | 10N006110000 | Reliability SierraLinda | Inactive
PBUT07 - Substation Reliability |  |  | 40054 | 40054 | 10N006120000 | Reliability Conquistador | Inactive
PBUT07 - Substation Reliability |  |  | 40054 | 40054 | 10N006130000 | Reliability DoradoTC | Cancel
PBUT07 - Substation Reliability |  |  | 40054 | 40054 | 10N006140000 | Reliability Guaynabo | Cancel
PBUT07 - Substation Reliability |  |  | 40054 | 40054 | 10N006150000 | Reliability PargueraPDS | Cancel
PBUT07 - Substation Reliability |  |  | 40008 | 40008 | 10N007020000 | 115kV U/G Mayaguez | Inactive
PBUT07 - Substation Reliability |  |  | 40060 | 40060 | 10N007680000 | Emer.MonacTC115/38kVTransfRepl | Inactive
PBUT07 - Substation Reliability |  |  | 40060 | 40060 | 10N007690000 | Emer.Monaci.TC38kVbrkrRepl/Rep | Cancel
PBUT07 - Substation Reliability |  |  | 40061 | 40061 | 10N007700000 | Emer.S.LLanaTC BrkerRepl.0040 | Cancel
PBUT07 - Substation Reliability |  |  | 40064 | 40064 | 10N008450000 | Maunabo Pueblo 4301-02 CB | Closed
PBUT07 - Substation Reliability |  |  | 40022 | 40022 | 10N008510000 | Arecibo Rural 8003 Transf.Repl | Inactive | Inactive
PBUT07 - Substation Reliability |  |  | 40066 | 40066 | 10N008740000 | Monacillos CB 37810 | Inactive | Inactive
PBUT07 - Substation Reliability |  |  | 40069 | 40069 | 10N008760000 | Yabucoa TC RTU Replacement | Inactive
PBUT07 - Substation Reliability |  |  | 40070 | 40070 | 10N008770000 | San Juan SP RTU Replacement | Inactive
PBUT07 - Substation Reliability |  |  | 40071 | 40071 | 10N008790000 | Lloren Torres 1118-08 DA Relay | Inactive | Inactive
PBUT07 - Substation Reliability |  |  | 40071 | 40071 | 10N008800000 | Minillas 1114 DA Relay Repl | Inactive | Inactive
PBUT07 - Substation Reliability |  |  | 40071 | 40071 | 10N008810000 | BTC-Bayamon 1716-02 DA Relay | Inactive | Inactive
PBUT07 - Substation Reliability |  |  | 40071 | 40071 | 10N008820000 | Naguabo 2701-03 DA Relay Repl | Inactive | Inactive
PBUT07 - Substation Reliability |  |  | 40071 | 40071 | 10N008830000 | Once De Agosto 6014-01 CB | Inactive | Inactive
PBUT07 - Substation Reliability |  |  | 40071 | 40071 | 10N008840000 | Verde Mar 2605-02 DA RelayRepl | Inactive | Inactive
PBUT07 - Substation Reliability |  |  | 40071 | 40071 | 10N008850000 | PlantaSanturce1117-11 DA Relay | Inactive | Inactive
PBUT07 - Substation Reliability |  |  | 40071 | 40071 | 10N008860000 | Villamar 1657 - 02 DA Relay | Inactive | Inactive
PBUT07 - Substation Reliability |  |  | 40072 | 40072 | 10N008870000 | Emergency PAC Replacements | Inactive
PBUT07 - Substation Reliability |  |  | 40074 | 40074 | 10N008880000 | Monacillo Bank#1 & #3 Trf.Repl | Active | Active | [5 empty] | 2024-08-19 08:00 | 2024-08-19 08:00
PBUT07 - Substation Reliability |  |  | 40075 | 40075 | 10N008980000 | Yabucoa 230Kv CB Replcmnt-0040 | Inactive | Inactive
PBUT07 - Substation Reliability |  |  | 40076 | 40076 | 10N008990000 | 11190 Canóvanas Sect. 38kV | Inactive
PBUT07 - Substation Reliability |  |  | 40077 | 40077 | 10N009060000 | AguadillaHosp.Distr.7003-02 CB | Inactive | Inactive
PBUT07 - Substation Reliability |  |  | 40077 | 40077 | 10N009070000 | Dos Bocas 8005-2 CB | Inactive | Inactive
PBUT07 - Substation Reliability |  |  | 40077 | 40077 | 10N009080000 | Manatí 8401-02 CB | Closed | Inactive
PBUT07 - Substation Reliability |  |  | 40077 | 40077 | 10N009090000 | Ojo de Agua 7002-2 CB | Closed | Inactive
PBUT07 - Substation Reliability |  |  | 40077 | 40077 | 10N009100000 | Ojo de Agua 7002-3 CB | Closed | Inactive
PBUT07 - Substation Reliability |  |  | 40077 | 40077 | 10N009110000 | Pajuil 7702-03 CB | Inactive | Inactive
PBUT07 - Substation Reliability |  |  | 40077 | 40077 | 10N009120000 | Peñuelas 5401-01 CB | Inactive | Inactive
PBUT07 - Substation Reliability |  |  | 40078 | 40078 | 10N009190000 | Dorado 9207 TC - CB 7810 | Inactive | Active
PBUT07 - Substation Reliability |  |  | 40078 | 40078 | 10N009200000 | AES 50270 230kV-CB Replacement | Inactive | Active
PBUT07 - Substation Reliability |  |  | 40079 | 40079 | 10N009500000 | Utuado 8101 | Inactive
PBUT07 - Substation Reliability |  |  | 40080 | 40080 | 10N009610000 | Substation Relay Aeropuerto | Inactive
PBUT07 - Substation Reliability |  |  | 40080 | 40080 | 10N009710000 | A.BuenasTranRelayRplcFeed39014 | Inactive
PBUT07 - Substation Reliability |  |  | 40080 | 40080 | 10N009720000 | Cana-InterTranRelayRplFeed0020 | Inactive
PBUT07 - Substation Reliability |  |  | 40080 | 40080 | 10N009730000 | HatilloTCTranRelayRplcFeed2120 | Inactive
PBUT07 - Substation Reliability |  |  | 40080 | 40080 | 10N009740000 | IslaGrandeTranRelFeeder 0010 | Inactive
PBUT07 - Substation Reliability |  |  | 40080 | 40080 | 10N009750000 | JobosTCTranRelFeeder 3750 | Inactive
PBUT07 - Substation Reliability |  |  | 40080 | 40080 | 10N009760000 | LosAngelesTranRelFeeder 3642 | Inactive
PBUT07 - Substation Reliability |  |  | 40080 | 40080 | 10N009770000 | PaloSecoTranRelFeeder 9520 | Inactive
PBUT07 - Substation Reliability |  |  | 40022-002 | 40022-002 | 10N010030000 | Fajardo 6T01 Replacement | Active | Active
PBUT07 - Substation Reliability |  |  | 60026 | 60026 | 10N010160000 | Aguas Buenas Sect 3701 RTU | Inactive
PBUT07 - Substation Reliability |  |  | 60026 | 60026 | 10N010170000 | Arecibo Pueblo - 8002 RTU | Inactive
PBUT07 - Substation Reliability |  |  | 60026 | 60026 | 10N010180000 | Gurabo Substation 3101 RTU | Inactive
PBUT07 - Substation Reliability |  |  | 40021 | 40021 | 10N010190000 | Barceloneta 14120 Tie Switch | Inactive
PBUT07 - Substation Reliability |  |  | 40078 | 40078 | 10N010570000 | Rio Blanco 9960 (38kV) | Inactive | Active
PBUT07 - Substation Reliability |  |  | 40078 | 40078 | 10N010580000 | Capuchinos Sect 1070 (38kV) | Inactive | Active
PBUT07 - Substation Reliability |  |  | 40078 | 40078 | 10N011190000 | Villamar 0020(38kV)Break.Replc | Inactive | Active
PBUT07 - Substation Reliability |  |  | 40078 | 40078 | 10N011570000 | Victoria TC Breaker Replacemnt | Inactive | Active
PBUT07 - Substation Reliability |  |  | 40078 | 40078 | 10N011610000 | Juncos TC Transformer Rplment | Active | Active
PBUT07 - Substation Reliability |  |  | 40082 | 40082 | 10N011680000 | Digital Fault Recorders | Inactive
PBUT07 - Substation Reliability |  |  | 40083 | 40083 | 10N011730000 | Outage Investigation Software | Inactive
PBUT07 - Substation Reliability |  |  | 40066 | 40066 | 10N012220000 | Substation Transm. GCB--SJ SP | Inactive | Inactive
PBUT07 - Substation Reliability |  |  | 40080 | 40080 | 10N012320000 | Yabucoa Pueblo Relay Rplc. | Active
PBUT07 - Substation Reliability |  |  | 40085 | 40085 | 10N012370000 | Bad Measurements | Active
PBUT07 - Substation Reliability |  |  | 40086 | 40086 | 10N012480000 | Subst.Control House Refurb. | Inactive
PBUT07 - Substation Reliability |  |  | 40084 | 40084 | 10N012890000 | Subs. Ops Breaker Replacement | Inactive
PBUT07 - Substation Reliability |  |  | 40087 | 40087 | 10N013310000 | Rio Grande Estates Cntrol Room | Active
PBUT07 - Substation Reliability |  |  | 40084 | 40084 | 10N013770000 | Aguirre 0090 Breaker Replacmnt | Active
PBUT07 - Substation Reliability |  |  | 40088 | 20015-006 | 10N013890000 | DOE Alturas de Rio Grande 2302 | Active | Inactive
PBUT07 - Substation Reliability |  |  | 40088 | 20015-021 | 10N013900000 | DOE 230kv Line Diff Upgrade | Active | Inactive
PBUT07 - Substation Reliability |  |  | 40089 | 40089 | 10N013910000 | DOE Bad Measurements(EMS Impl) | Active
PBUT07 - Substation Reliability |  |  | 40088 | 20015-013 | 10N013920000 | DOE Relay Upgrades Vega Alta | Active | Inactive
PBUT07 - Substation Reliability |  |  | 40088 | 20015-018 | 10N013930000 | DOE DFRs | Active | Inactive
PBUT07 - Substation Reliability |  |  | 40088 | 20015-012 | 10N013940000 | DOE Relay Upds Sabanera 3604-6 | Active | Inactive
PBUT07 - Substation Reliability |  |  | 40088 | 20015-009 | 10N013950000 | DOE Relay Marina2006-3 &2006-4 | Active | Inactive
PBUT07 - Substation Reliability |  |  | 40088 | 20016-002 | 10N013960000 | DOE LlorensT13kVMetalcladReplc | Active | Inactive
PBUT07 - Substation Reliability |  |  | 40088 | 20015-008 | 10N013970000 | DOE RelayUpgrades Cayey 3401-1 | Active | Inactive
PBUT07 - Substation Reliability |  |  | 40088 | 20015-007 | 10N013980000 | DOE Relay Upds Bairoa 3008-4 | Active | Inactive
PBUT07 - Substation Reliability |  |  | 40088 | 20015-020 | 10N013990000 | DOE LTCs | Active | Inactive
PBUT07 - Substation Reliability |  |  | 40088 | 20020-001 | 10N014000000 | DOE-Monacillos 115kV PAC Upgrd | Active | Inactive
PBUT07 - Substation Reliability |  |  | 40088 | 20015-010 | 10N014010000 | DOE Relay Upgrades Minillas | Active | Inactive
PBUT07 - Substation Reliability |  |  | 40088 | 20015-015 | 10N014020000 | DOE RTUs | Active | Inactive | [5 empty] | 2025-05-16 08:00 | 2025-05-16 08:00
PBUT07 - Substation Reliability |  |  | 40088 | 20015-017 | 10N014030000 | DOE Viaducto 115kv PAC Upgrade | Active | Inactive
PBUT07 - Substation Reliability |  |  | 40088 | 20015-011 | 10N014050000 | DOE Relay Upgrades Rio Grande | Active | Inactive
PBUT07 - Substation Reliability |  |  | 40088 | 40088 | 10N014060000 | DOE SEL ICON MUX PROTECTION | Active | Inactive
PBUT07 - Substation Reliability |  |  | 40088 | 40088 | 10N014070000 | Mayaguez TC 115kv cable replac | Active | Inactive
PBUT07 - Substation Reliability |  |  | 40088 | 20015-005 | 10N014120000 | DOE Batteries Critical Sites | Active | Inactive
PBUT07 - Substation Reliability |  |  | 40088 | 20015-022 | 10N014240000 | DOE WAP 230Kv (P6) | Active | Inactive
PBUT07 - Substation Reliability |  |  | 40088 | 20015-019 | 10N014260000 | DOE UFLS Comprehensive Prgm | Active | Inactive
PBUT07 - Substation Reliability |  |  | 40092 | 40092 | 10N014630000 | Substation Ops Emergent Works | Active
PBUT07 - Substation Reliability |  |  | 40093 | 40093 | 10N015640000 | Isla Grande GIS TrfmrReplBank2 | Active | Active
PBUT07 - Substation Reliability |  |  | 00001-002 | 00001-002 | 10X000000000 | EPM Test Project | Inactive | Inactive
PBUT07 - Substation Reliability |  |  | 90003 | 90003 | 14F000146000 | Mobile Sub Repairs | Inactive
PBUT07 - Substation Reliability | 11537 | 551925 | 60009-001 | 60009-001 | 14F002120000 | SCADA Access & RTU Repl.Group1 | Active | Inactive |  |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval | 2022-02-15 08:00 | 2022-02-15 08:00 | 2022-07-18 17:00 | 2022-07-15 | 2024-11-01 15:15
PBUT07 - Substation Reliability | 107735 | 551926 | 60009-002 | 60009-002 | 14F002130000 | SCADA Access & RTU Repl.Group2 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2023-10-27 08:00 | 2023-10-27 08:00 | 2022-07-18 17:00 | 2023-09-29 | 2026-03-01 18:16
PBUT07 - Substation Reliability | 10858 | 546370 | 43001 | 43001-001 | 14F002830000 | Substation Minor Repair San | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  | 2022-05-31 | 2024-02-13 12:36
PBUT07 - Substation Reliability | 10858 | 546370 | 43001 | 43001-001 | 14F002840000 | Subs.Min.Rep.SJ Reg.G-A CanTC | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  | 2022-05-31 | 2024-02-13 12:36
PBUT07 - Substation Reliability | 10858 | 546370 | 43001 | 43001-001 | 14F002860000 | Substation GRP A Isla Grande | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  | 2022-05-31 | 2024-02-13 12:36
PBUT07 - Substation Reliability | 10858 | 546370 | 43001 | 43001-001 | 14F002870000 | Substation GRP A La Muda | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  | 2022-05-31 | 2024-02-13 12:36
PBUT07 - Substation Reliability | 10858 | 546370 | 43001 | 43001-001 | 14F002880000 | Substation GRP A Rio Piedras | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  | 2022-05-31 | 2024-02-13 12:36
PBUT07 - Substation Reliability | 11707 | 549725 | 43001 | 43001-005 | 14F002890000 | Substation GRP E Coamo | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2023-06-30 17:00 | 2023-06-30 | 2024-05-10 10:17
PBUT07 - Substation Reliability | 11707 | 549725 | 43001 | 43001-005 | 14F002900000 | Substation GRP E Guayama | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2023-06-30 17:00 | 2023-06-30 | 2024-05-10 10:17
PBUT07 - Substation Reliability | 11707 | 549725 | 43001 | 43001-005 | 14F002910000 | Substation GRP E Salinas Urb | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2023-06-30 17:00 | 2023-06-30 | 2024-05-10 10:17
PBUT07 - Substation Reliability | 11385 | 542758 | 43001 | 43001-002 | 14F002950000 | Substation GRP B Jayuya | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2022-12-29 17:00 | 2022-07-11 | 2023-07-07 11:35
PBUT07 - Substation Reliability | 11385 | 542758 | 43001 | 43001-002 | 14F002970000 | Substation GRP B Islabela | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2022-12-29 17:00 | 2022-07-11 | 2023-07-07 11:35
PBUT07 - Substation Reliability | 11682 | 549715 | 43001 | 43001-004 | 14F003000000 | Substation GRP D Sabana Gr | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2023-06-30 17:00 | 2023-06-30 | 2024-04-12 11:19
PBUT07 - Substation Reliability | 11682 | 549715 | 43001 | 43001-004 | 14F003010000 | Substation GRP D Capa | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2023-06-30 17:00 | 2023-06-30 | 2024-04-12 11:19
PBUT07 - Substation Reliability | 11682 | 549715 | 43001 | 43001-004 | 14F003020000 | Substation GRP D Punta Del | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2023-06-30 17:00 | 2023-06-30 | 2024-04-12 11:19
PBUT07 - Substation Reliability | 11478 | 546371 | 43001 | 43001-003 | 14F003030000 | Substation GRP C Cana | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2022-06-13 17:00 | 2022-06-17 | 2023-08-22 11:21
PBUT07 - Substation Reliability | 11478 | 546371 | 43001 | 43001-003 | 14F003040000 | Substation GRP C Crea | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2022-06-13 17:00 | 2022-06-17 | 2023-08-22 11:21
PBUT07 - Substation Reliability | 11478 | 546371 | 43001 | 43001-003 | 14F003050000 | Substation GRP C Naranjito | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2022-06-13 17:00 | 2022-06-17 | 2023-08-22 11:21
PBUT07 - Substation Reliability | 11478 | 546371 | 43001 | 43001-003 | 14F003060000 | Substation GRP C Rio Bayam | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2022-06-13 17:00 | 2022-06-17 | 2023-08-22 11:21
PBUT07 - Substation Reliability |  |  | 10110 | 10110 | 14F003070000 | Mobile Substation | Inactive | Inactive
PBUT07 - Substation Reliability | 107736 | 551927 | 60009-003 | 60009-003 | 14F003910000 | SCADA accesRTU Repl.Group 3 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2024-04-25 17:00 | 2024-04-30
PBUT07 - Substation Reliability | 11573 | 684920 | 40014-001 | 40014-001 | 14F008410000 | Breaker Replace 38 Kv & 115Kv | Inactive | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2023-08-01 17:00 | 2023-06-30 | 2023-12-29 12:31
PBUT07 - Substation Reliability |  |  | 43001 |  | 14F008940000 | SubMinorRepair GRP F-Añasco TC | Active | Active
PBUT07 - Substation Reliability |  |  | 43001 |  | 14F008950000 | SubMinorRepar GRP F-Guanica TC | Active | Active
PBUT07 - Substation Reliability |  |  | 43001 |  | 14F008970000 | SubMinorRepr GRP G-SanJuan GIS | Active | Active
PBUT07 - Substation Reliability |  |  | 43001 |  | 14F008980000 | SubMinorRepr GRP G-Chardon GIS | Active | Active
PBUT07 - Substation Reliability |  |  | 43001 |  | 14F008990000 | SubMinorRepr GRP G-Bo PiñasGIS | Active | Active
PBUT07 - Substation Reliability |  |  | 43001 |  | 14F009000000 | SubMinrReprGRP G-Matin PeñaGIS | Active | Active
PBUT07 - Substation Reliability |  |  | 43002 | 43002 | 14F009280000 | Aguas Buenas GIS (6) | Inactive
PBUT07 - Substation Reliability |  |  | 43003 | 43003 | 14F009290000 | Bayamon TC (31) | Inactive
PBUT07 - Substation Reliability |  |  | 43004 | 43004 | 14F009300000 | Central Aguirre (66) | Inactive
PBUT07 - Substation Reliability |  |  | 43005 | 43005 | 14F009310000 | Central Cambalache (67) | Inactive
PBUT07 - Substation Reliability |  |  | 43004 | 43004 | 14F009320000 | Central Costa Sur (68) | Inactive
PBUT07 - Substation Reliability |  |  | 43006 | 43006 | 14F009330000 | Central San Juan (70) | Inactive
PBUT07 - Substation Reliability |  |  | 43003 | 43003 | 14F009340000 | Dorado TC (100) | Inactive
PBUT07 - Substation Reliability |  |  | 43004 | 43004 | 14F009350000 | Jobos TC (155) | Inactive
PBUT07 - Substation Reliability |  |  | 43007 | 43007 | 14F009360000 | Las Acacias TC (169) | Inactive
PBUT07 - Substation Reliability |  |  | 43005 | 43005 | 14F009370000 | Manati TC (184) | Inactive
PBUT07 - Substation Reliability |  |  | 43006 | 43006 | 14F009380000 | Monacillos TC (197) | Inactive
PBUT07 - Substation Reliability |  |  | 43006 |  | 14F009390000 | Sabana Llana TC (240) | Inactive
PBUT07 - Substation Reliability |  |  | 43005 | 43005 | 14F009400000 | San Jose Utuado (254) | Inactive
PBUT07 - Substation Reliability |  |  | 43002 | 43002 | 14F009410000 | San Lorenzo (255) | Inactive
PBUT07 - Substation Reliability |  |  | 43006 | 43006 | 14F009420000 | Viaducto TC (283) | Inactive
PBUT07 - Substation Reliability |  |  | 43007 | 43007 | 14F012340000 | Anasco TC (15) | Inactive
PBUT07 - Substation Reliability |  |  | 43005 | 43005 | 14F012350000 | Barceloneta TC (23) | Inactive
PBUT07 - Substation Reliability |  |  | 43002 | 43002 | 14F012360000 | Barranquitas TC (24) | Inactive
PBUT07 - Substation Reliability |  |  | 43008 | 43008 | 14F012370000 | Substn-Battery Test & Replace | Inactive
PBUT07 - Substation Reliability |  |  | 43006 | 43006 | 14F012380000 | Berwind TC (32) | Inactive
PBUT07 - Substation Reliability |  |  | 43004 | 43004 | 14F012390000 | Canas TC (51) | Inactive
PBUT07 - Substation Reliability |  |  | 43006 | 43006 | 14F012400000 | Canovanas TC (54) | Inactive
PBUT07 - Substation Reliability |  |  | 43002 | 43002 | 14F012410000 | Fajardo TC (111) | Inactive
PBUT07 - Substation Reliability |  |  | 43008 | 43008 | 14F012420000 | Hotspot Remediation | Inactive
PBUT07 - Substation Reliability |  |  | 43007 | 43007 | 14F012430000 | Mayaguez TC (191) | Inactive
PBUT07 - Substation Reliability |  |  | 43007 | 43007 | 14F012440000 | Mora TC (200) | Inactive
PBUT07 - Substation Reliability |  |  | 43008 | 43008 | 14F012450000 | Site Damage Remediation | Inactive
PBUT07 - Substation Reliability |  |  | 43002 | 43002 | 14F012460000 | Yabucoa TC (297) | Inactive
PBUT07 - Substation Reliability |  |  | 43005 | 43005 | 14F012470000 | Yahuecas (298) | Inactive
PBUT07 - Substation Reliability |  |  | 43004 | 43004 | 14F012480000 | Ponce TC (Hostos) (218) | Inactive
PBUT07 - Substation Reliability |  |  | 43003 | 43003 | 14F012490000 | Central Palo Seco (69) | Inactive
PBUT07 - Substation Reliability |  |  | 43005 | 43005 | 14F012770000 | Cambalache TC (47) | Inactive
PBUT07 - Substation Reliability |  |  | 43008 | 43008 | 14F014150000 | Mobile Sub Remediation | Inactive
PBUT07 - Substation Reliability |  |  | 43003 | 43003 | 14F017750000 | Cana Sect (50) | Inactive
PBUT07 - Substation Reliability |  |  | 43005 | 43005 | 14F017760000 | Dos Bocas (101) | Inactive
PBUT07 - Substation Reliability |  |  | 43004 | 43004 | 14F017770000 | Guanica TC (123) | Inactive
PBUT07 - Substation Reliability |  |  | 43002 | 43002 | 14F017780000 | Humacao TC (144) | Inactive
PBUT07 - Substation Reliability |  |  | 43004 | 43004 | 14F017790000 | Monterrey (199) | Inactive
PBUT07 - Substation Reliability |  |  | 43007 | 43007 | 14F017800000 | San German Indust. (251) | Cancel
PBUT07 - Substation Reliability |  |  | 43005 | 43005 | 14F017810000 | Vega Alta Sect. (278) | Inactive
PBUT07 - Substation Reliability |  |  | 43002 | 43002 | 14F017820000 | Veredas (282) | Inactive
PBUT07 - Substation Reliability |  |  | 43006 | 43006 | 14F017830000 | Vistamar (295) | Cancel
PBUT07 - Substation Reliability | 107960 | 746660 | 40017-001 | 40017-001 | 14F019650000 | AMELIA SECT PAC Upgrade | Inactive | Active |  |  | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant |  |  | 2026-03-27 17:00 | 2024-04-11
PBUT07 - Substation Reliability | 107960 | 746660 | 40017-001 | 40017-001 | 14F019660000 | SAN GERMAN SECT PAC Upgrade | Active | Active |  |  | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant |  |  | 2026-03-27 17:00 | 2024-04-11
PBUT07 - Substation Reliability | 107960 | 746660 | 40017-001 | 40017-001 | 14F019670000 | LAS LOMAS TC PAC Upgrade | Active | Active |  |  | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant |  |  | 2026-03-27 17:00 | 2024-04-11
PBUT07 - Substation Reliability | 107960 | 746660 | 40017-001 | 40017-001 | 14F019680000 | CIALES PAC Upgrade | Inactive | Active |  |  | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant |  |  | 2026-03-27 17:00 | 2024-04-11
PBUT07 - Substation Reliability | 107960 | 746660 | 40017-001 | 40017-001 | 14F019690000 | CONQUISTADOR PAC Upgrade | Active | Active |  |  | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant |  |  | 2026-03-27 17:00 | 2024-04-11
PBUT07 - Substation Reliability | 107960 | 746660 | 40017-001 | 40017-001 | 14F019700000 | PALMER TC PAC Upgrade | Active | Active |  |  | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant |  |  | 2026-03-27 17:00 | 2024-04-11
PBUT07 - Substation Reliability | 107960 | 746660 | 40017-001 | 40017-001 | 14F019710000 | DAGUAO TC PAC Upgrade | Active | Active |  |  | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant |  |  | 2026-03-27 17:00 | 2024-04-11
PBUT07 - Substation Reliability | 107960 | 746660 | 40017-001 | 40017-001 | 14F019720000 | ARECIBO SECT PAC Upgrade | Inactive | Active |  |  | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant |  |  | 2026-03-27 17:00 | 2024-04-11
PBUT07 - Substation Reliability | 107960 | 746660 | 40017-001 | 40017-001 | 14F019730000 | VEGA ALTA SECT PAC Upgrade | Active | Active |  |  | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant |  |  | 2026-03-27 17:00 | 2024-04-11
PBUT07 - Substation Reliability | 107960 | 746660 | 40017-001 | 40017-001 | 14F019740000 | COVADONGA TC PAC Upgrade | Active | Active |  |  | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant |  |  | 2026-03-27 17:00 | 2024-04-11
PBUT07 - Substation Reliability | 107960 | 746660 | 40017-001 | 40017-001 | 14F019750000 | ANASCO TC PAC Upgrade | Active | Active |  |  | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant |  |  | 2026-03-27 17:00 | 2024-04-11
PBUT07 - Substation Reliability | 107960 | 746660 | 40017-001 | 40017-001 | 14F019760000 | AGUAS BUENAS TC PAC Upgrade | Inactive | Active |  |  | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant |  |  | 2026-03-27 17:00 | 2024-04-11
PBUT07 - Substation Reliability | 107960 | 746660 | 40017-001 | 40017-001 | 14F019770000 | BARCELONETA TC PAC Upgrade | Inactive | Active |  |  | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant |  |  | 2026-03-27 17:00 | 2024-04-11
PBUT07 - Substation Reliability | 107960 | 746660 | 40017-001 | 40017-001 | 14F019780000 | CANOVANAS SECT | Inactive | Active |  |  | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant |  |  | 2026-03-27 17:00 | 2024-04-11
PBUT07 - Substation Reliability | 107960 | 746660 | 40017-001 | 40017-001 | 14F019790000 | CANOVANAS TC | Inactive | Active |  |  | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant |  |  | 2026-03-27 17:00 | 2024-04-11
PBUT07 - Substation Reliability | 107960 | 746660 | 40017-001 | 40017-001 | 14F019800000 | GAUTIER BENITEZ SECT | Inactive | Active |  |  | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant |  |  | 2026-03-27 17:00 | 2024-04-11
PBUT07 - Substation Reliability | 107960 | 746660 | 40017-001 | 40017-001 | 14F019810000 | GUARAGUAO SECT PAC Upgrade | Inactive | Active |  |  | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant |  |  | 2026-03-27 17:00 | 2024-04-11
PBUT07 - Substation Reliability | 107960 | 746660 | 40017-001 | 40017-001 | 14F019820000 | HUMACAO SECT | Inactive | Active |  |  | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant |  |  | 2026-03-27 17:00 | 2024-04-11
PBUT07 - Substation Reliability | 107960 | 746660 | 40017-001 | 40017-001 | 14F019830000 | HUMACAO TC | Inactive | Active |  |  | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant |  |  | 2026-03-27 17:00 | 2024-04-11
PBUT07 - Substation Reliability | 107960 | 746660 | 40017-001 | 40017-001 | 14F019840000 | MANATI SECT | Inactive | Active |  |  | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant |  |  | 2026-03-27 17:00 | 2024-04-11
PBUT07 - Substation Reliability | 107960 | 746660 | 40017-001 | 40017-001 | 14F019850000 | MIRADOR AZUL SECT | Inactive | Active |  |  | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant |  |  | 2026-03-27 17:00 | 2024-04-11
PBUT07 - Substation Reliability | 107960 | 746660 | 40017-001 | 40017-001 | 14F019860000 | MORA TC | Inactive | Active |  |  | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant |  |  | 2026-03-27 17:00 | 2024-04-11
PBUT07 - Substation Reliability | 107960 | 746660 | 40017-001 | 40017-001 | 14F019870000 | QUEBRADILLAS SECT | Inactive | Active |  |  | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant |  |  | 2026-03-27 17:00 | 2024-04-11
PBUT07 - Substation Reliability | 107960 | 746660 | 40017-001 | 40017-001 | 14F019880000 | SAN SEBASTIAN TC PAC Upgrade | Inactive | Active |  |  | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant |  |  | 2026-03-27 17:00 | 2024-04-11
PBUT07 - Substation Reliability | 107960 | 746660 | 40017-001 | 40017-001 | 14F019890000 | VEGA BAJA SECT | Inactive | Active |  |  | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant |  |  | 2026-03-27 17:00 | 2024-04-11
PBUT07 - Substation Reliability | 107960 | 746660 | 40017-001 | 40017-001 | 14F019900000 | VILLA BETINA SECT | Inactive | Active |  |  | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant |  |  | 2026-03-27 17:00 | 2024-04-11
PBUT07 - Substation Reliability | 107960 | 746660 | 40017-001 | 40017-001 | 14F019910000 | YABUCOA TC | Inactive | Active |  |  | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant |  |  | 2026-03-27 17:00 | 2024-04-11
PBUT07 - Substation Reliability | 11573 | 684920 | 40014-001 | 40014-001 | 14F019930000 | Mora TC 97505 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2023-08-01 17:00 | 2023-06-30 | 2023-12-29 12:31
PBUT07 - Substation Reliability | 11573 | 684920 | 40014-001 | 40014-001 | 14F019940000 | Palmer TC 72305 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2023-08-01 17:00 | 2023-06-30 | 2023-12-29 12:31
PBUT07 - Substation Reliability | 11573 | 684920 | 40014-001 | 40014-001 | 14F019950000 | Anasco TC 76125 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2023-08-01 17:00 | 2023-06-30 | 2023-12-29 12:31
PBUT07 - Substation Reliability | 11573 | 684920 | 40014-001 | 40014-001 | 14F019960000 | Daguao TC 72101 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2023-08-01 17:00 | 2023-06-30 | 2023-12-29 12:31
PBUT07 - Substation Reliability | 11726 | 729286 | 40014-002 | 40014-002 | 14F019970000 | San Sebastian TC 77805 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2023-08-01 17:00 | 2023-09-29 | 2024-07-08 11:28
PBUT07 - Substation Reliability | 11726 | 729286 | 40014-002 | 40014-002 | 14F019980000 | Gautier Benitez S 63007 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2023-08-01 17:00 | 2023-09-29 | 2024-07-08 11:28
PBUT07 - Substation Reliability | 11726 | 729286 | 40014-002 | 40014-002 | 14F019990000 | Guaraguao Sect 61707 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2023-08-01 17:00 | 2023-09-29 | 2024-07-08 11:28
PBUT07 - Substation Reliability | 11726 | 729286 | 40014-002 | 40014-002 | 14F020000000 | GuanicaTC 75602 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2023-08-01 17:00 | 2023-09-29 | 2024-07-08 11:28
PBUT07 - Substation Reliability |  |  | 43009 | 43009 | 14F020020000 | Humacao TC-IWT | Inactive |  | CAP1
PBUT07 - Substation Reliability |  |  | 43009 | 43009 | 14F020030000 | San German TC-IWT | Inactive |  | CAP1
PBUT07 - Substation Reliability |  |  | 43009 | 43009 | 14F020040000 | Vega Baja-IWT | Inactive |  | CAP1
PBUT07 - Substation Reliability | 107690 | 547187 | 40063 | 40063 | 14F020050000 | Atalaya 67303 | Inactive | Active | CAP2 |  | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant |  |  |  | 2025-03-10
PBUT07 - Substation Reliability | 107690 | 547187 | 40063 | 40063 | 14F020060000 | Cana Sect 71710 | Inactive | Active | CAP2 |  | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant |  |  |  | 2025-03-10
PBUT07 - Substation Reliability | 107690 | 547187 | 40063 | 40063 | 14F020070000 | Canovanas TC 72402 | Inactive | Active | CAP2 |  | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant |  |  |  | 2025-03-10
PBUT07 - Substation Reliability | 107690 | 547187 | 40063 | 40063 | 14F020080000 | Cidra Sect 63601 | Inactive | Active | CAP2 |  | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant |  |  |  | 2025-03-10
PBUT07 - Substation Reliability | 107690 | 547187 | 40063 | 40063 | 14F020090000 | Colegio Sect 66006 | Active | Active | CAP2 | ISSUE | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant |  |  |  | 2025-03-10
PBUT07 - Substation Reliability | 11726 | 729286 | 40014-002 | 40014-002 | 14F020100000 | Barceloneta TC 78525 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2023-08-01 17:00 | 2023-09-29 | 2024-07-08 11:28
PBUT07 - Substation Reliability | 107690 | 547187 | 40063 | 40063 | 14F020110000 | Gautier Benitez Sect 63007 | Inactive | Active | CAP2 |  | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant |  |  |  | 2025-03-10
PBUT07 - Substation Reliability | 107690 | 547187 | 40063 | 40063 | 14F020120000 | Grana 71907 | Active | Active | CAP2 | ISSUE | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant |  |  |  | 2025-03-10
PBUT07 - Substation Reliability | 107690 | 547187 | 40063 | 40063 | 14F020130000 | Guayama PDS 64006 | Active | Active | CAP2 | ISSUE | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant |  |  |  | 2025-03-10
PBUT07 - Substation Reliability | 107690 | 547187 | 40063 | 40063 | 14F020140000 | Humacao TC 72603 | Inactive | Active | CAP2 | ISSUE | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant |  |  |  | 2025-03-10
PBUT07 - Substation Reliability | 107690 | 547187 | 40063 | 40063 | 14F020150000 | Manati Urbano 68405 | Inactive | Active | CAP2 |  | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant |  |  |  | 2025-03-10
PBUT07 - Substation Reliability | 107690 | 547187 | 40063 | 40063 | 14F020160000 | Parque Escorial 71620 | Inactive | Active | CAP2 |  | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant |  |  |  | 2025-03-10
PBUT07 - Substation Reliability | 107690 | 547187 | 40063 | 40063 | 14F020170000 | San German Sect 66401 | Inactive | Active | CAP2 |  | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant |  |  |  | 2025-03-10
PBUT07 - Substation Reliability | 107690 | 547187 | 40063 | 40063 | 14F020180000 | Villa Betina 71303 | Active | Active | CAP2 |  | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant |  |  |  | 2025-03-10
PBUT07 - Substation Reliability | 107690 | 547187 | 40063 | 40063 | 14F020190000 | Yauco Plaza 65305 | Active | Active | CAP2 |  | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant |  |  |  | 2025-03-10
PBUT07 - Substation Reliability | 11726 | 729286 | 40014-002 | 40014-002 | 14F020200000 | Las Lomas Sect 61525 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2023-08-01 17:00 | 2023-09-29 | 2024-07-08 11:28
PBUT07 - Substation Reliability |  |  | 43009 | 43009 | 14F020810000 | Las Marias | Inactive
PBUT07 - Substation Reliability |  |  | 43009 | 43009 | 14F020820000 | Mayaguez TC | Inactive
PBUT07 - Substation Reliability |  |  | 43009 | 43009 | 14F020830000 | Mckinley 6002 | Inactive
PBUT07 - Substation Reliability |  |  | 43009 | 43009 | 14F020840000 | Moca 7101/7104 | Inactive
PBUT07 - Substation Reliability |  |  | 43009 | 43009 | 14F020850000 | Monacillo TC | Inactive
PBUT07 - Substation Reliability |  |  | 43009 | 43009 | 14F020860000 | Mora TC | Inactive
PBUT07 - Substation Reliability |  |  | 43009 | 43009 | 14F020870000 | Parguera | Inactive
PBUT07 - Substation Reliability |  |  | 43009 | 43009 | 14F020880000 | Puerto Del Mar 7302 | Inactive
PBUT07 - Substation Reliability |  |  | 43009 | 43009 | 14F020890000 | Rincon | Inactive
PBUT07 - Substation Reliability |  |  | 43009 | 43009 | 14F020900000 | San German 6401 | Inactive
PBUT07 - Substation Reliability |  |  | 43009 | 43009 | 14F020910000 | San German 6404 | Inactive
PBUT07 - Substation Reliability |  |  | 43009 | 43009 | 14F020920000 | San German TC | Inactive
PBUT07 - Substation Reliability |  |  | 43009 | 43009 | 14F020930000 | San Sebastian TC | Inactive
PBUT07 - Substation Reliability |  |  | 43009 | 43009 | 14F020940000 | Tbone 7011 | Inactive
PBUT07 - Substation Reliability |  |  | 43009 | 43009 | 14F020950000 | Victoria TC | Inactive
PBUT07 - Substation Reliability |  |  | 43009 | 43009 | 14F020960000 | Yabucoa TC | Inactive
PBUT07 - Substation Reliability |  |  | 43009 | 43009 | 14F020970000 | Acacias TC | Inactive
PBUT07 - Substation Reliability |  |  | 43009 | 43009 | 14F020980000 | 6501 Sabana Grande | Inactive
PBUT07 - Substation Reliability |  |  | 43009 | 43009 | 14F020990000 | 7702 Pajuil | Inactive
PBUT07 - Substation Reliability |  |  | 43009 | 43009 | 14F021000000 | Aguada 7201 | Inactive
PBUT07 - Substation Reliability |  |  | 43009 | 43009 | 14F021010000 | Aguadilla HospitalDistrict7703 | Inactive
PBUT07 - Substation Reliability |  |  | 43009 | 43009 | 14F021020000 | Aguirre | Inactive
PBUT07 - Substation Reliability |  |  | 43009 | 43009 | 14F021030000 | Alturas Mayaguez | Inactive
PBUT07 - Substation Reliability |  |  | 43009 | 43009 | 14F021040000 | Anasco TC | Inactive
PBUT07 - Substation Reliability |  |  | 43009 | 43009 | 14F021050000 | Arecibo Rural | Inactive
PBUT07 - Substation Reliability |  |  | 43009 | 43009 | 14F021060000 | Bayamon TC | Inactive
PBUT07 - Substation Reliability |  |  | 43009 | 43009 | 14F021070000 | Berwind TC | Inactive
PBUT07 - Substation Reliability |  |  | 43009 | 43009 | 14F021080000 | Canas TC | Inactive
PBUT07 - Substation Reliability |  |  | 43009 | 43009 | 14F021090000 | Colegio | Inactive
PBUT07 - Substation Reliability |  |  | 43009 | 43009 | 14F021100000 | Combate | Inactive
PBUT07 - Substation Reliability |  |  | 43009 | 43009 | 14F021110000 | Dos Bocas 8005 | Inactive
PBUT07 - Substation Reliability | 11726 | 729286 | 40014-002 | 40014-002 | 14F021120000 | Canovanas TC 2404 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2023-08-01 17:00 | 2023-09-29 | 2024-07-08 11:28
PBUT07 - Substation Reliability | 11726 | 729286 | 40014-002 | 40014-002 | 14F021130000 | Humacao TC 2602 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2023-08-01 17:00 | 2023-09-29 | 2024-07-08 11:28
PBUT07 - Substation Reliability | 11764 | 743399 | 40014-003 | 40014-003 | 14F021310000 | Juncos TC 3205 HVE Replacement | Inactive | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2025-01-27 17:00 | 2025-01-27 17:00 | 2024-08-26 17:00 | 2024-03-28 | 2024-08-26 10:08
PBUT07 - Substation Reliability | 11764 | 743399 | 40014-003 | 40014-003 | 14F021320000 | La Rambla Sect HVE Replacement | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2025-01-27 17:00 | 2025-01-27 17:00 | 2024-08-26 17:00 | 2024-03-28 | 2024-08-26 10:08
PBUT07 - Substation Reliability | 11764 | 743399 | 40014-003 | 40014-003 | 14F021330000 | Miramar Sect HVE Replacement | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2025-01-27 17:00 | 2025-01-27 17:00 | 2024-08-26 17:00 | 2024-03-28 | 2024-08-26 10:08
PBUT07 - Substation Reliability | 11764 | 743399 | 40014-003 | 40014-003 | 14F021340000 | Hogar Crea HVE Replacement | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2025-01-27 17:00 | 2025-01-27 17:00 | 2024-08-26 17:00 | 2024-03-28 | 2024-08-26 10:08
PBUT07 - Substation Reliability | 11764 | 743399 | 40014-003 | 40014-003 | 14F021350000 | Hato Tejas Sect HVE Repl. | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2025-01-27 17:00 | 2025-01-27 17:00 | 2024-08-26 17:00 | 2024-03-28 | 2024-08-26 10:08
PBUT07 - Substation Reliability | 11764 | 743399 | 40014-003 | 40014-003 | 14F021360000 | San Fernando Sect HVE Repl. | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2025-01-27 17:00 | 2025-01-27 17:00 | 2024-08-26 17:00 | 2024-03-28 | 2024-08-26 10:08
PBUT07 - Substation Reliability | 11764 | 743399 | 40014-003 | 40014-003 | 14F021370000 | San German HVE Repl. | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2025-01-27 17:00 | 2025-01-27 17:00 | 2024-08-26 17:00 | 2024-03-28 | 2024-08-26 10:08
PBUT07 - Substation Reliability | 11764 | 743399 | 40014-003 | 40014-003 | 14F021380000 | Las Piedras Sect HVE Repl. | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2025-01-27 17:00 | 2025-01-27 17:00 | 2024-08-26 17:00 | 2024-03-28 | 2024-08-26 10:08
PBUT07 - Substation Reliability | 11764 | 743399 | 40014-003 | 40014-003 | 14F021520000 | Bairoa HVE Replacement | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2025-01-27 17:00 | 2025-01-27 17:00 | 2024-08-26 17:00 | 2024-03-28 | 2024-08-26 10:08
PBUT07 - Substation Reliability | 11764 | 743399 | 40014-003 | 40014-003 | 14F021800000 | T-Bone HVE Replacement | Active | Active | CAP4 |  | Active | Phase 5 - Post Award Phase | Obligated | 2025-01-27 17:00 | 2025-01-27 17:00 | 2024-08-26 17:00 | 2024-03-28 | 2024-08-26 10:08
PBUT07 - Substation Reliability | 11764 | 743399 | 40014-003 | 40014-003 | 14F021810000 | Vistamar HVE Replacement | Active | Active | CAP4 |  | Active | Phase 5 - Post Award Phase | Obligated | 2025-01-27 17:00 | 2025-01-27 17:00 | 2024-08-26 17:00 | 2024-03-28 | 2024-08-26 10:08
PBUT07 - Substation Reliability | 11764 | 743399 | 40014-003 | 40014-003 | 14F021820000 | Juan Domingo Sect. HVE Replac. | Active | Active | CAP4 |  | Active | Phase 5 - Post Award Phase | Obligated | 2025-01-27 17:00 | 2025-01-27 17:00 | 2024-08-26 17:00 | 2024-03-28 | 2024-08-26 10:08
PBUT07 - Substation Reliability | 11764 | 743399 | 40014-003 | 40014-003 | 14F021830000 | Caguax Sect. HVE Replacement | Active | Active | CAP4 |  | Active | Phase 5 - Post Award Phase | Obligated | 2025-01-27 17:00 | 2025-01-27 17:00 | 2024-08-26 17:00 | 2024-03-28 | 2024-08-26 10:08
PBUT07 - Substation Reliability | 11764 | 743399 | 40014-003 | 40014-003 | 14F021840000 | Villamar 1 HVE Replacement | Active | Active | CAP4 |  | Active | Phase 5 - Post Award Phase | Obligated | 2025-01-27 17:00 | 2025-01-27 17:00 | 2024-08-26 17:00 | 2024-03-28 | 2024-08-26 10:08
PBUT07 - Substation Reliability | 11764 | 743399 | 40014-003 | 40014-003 | 14F021850000 | Villa Prades Sect. HVE Replac. | Active | Active | CAP4 |  | Active | Phase 5 - Post Award Phase | Obligated | 2025-01-27 17:00 | 2025-01-27 17:00 | 2024-08-26 17:00 | 2024-03-28 | 2024-08-26 10:08
PBUT07 - Substation Reliability | 11764 | 743399 | 40014-003 | 40014-003 | 14F021860000 | Villamil Prades Sect. HVE Repl | Active | Active | CAP4 |  | Active | Phase 5 - Post Award Phase | Obligated | 2025-01-27 17:00 | 2025-01-27 17:00 | 2024-08-26 17:00 | 2024-03-28 | 2024-08-26 10:08
PBUT07 - Substation Reliability | 11764 | 743399 | 40014-003 | 40014-003 | 14F021870000 | Alturas de Mayaguez HVE Replac | Active | Active | CAP4 |  | Active | Phase 5 - Post Award Phase | Obligated | 2025-01-27 17:00 | 2025-01-27 17:00 | 2024-08-26 17:00 | 2024-03-28 | 2024-08-26 10:08
PBUT07 - Substation Reliability | 11764 | 743399 | 40014-003 | 40014-003 | 14F021880000 | Yabucoa TC HVE Replacement | Active | Active | CAP4 |  | Active | Phase 5 - Post Award Phase | Obligated | 2025-01-27 17:00 | 2025-01-27 17:00 | 2024-08-26 17:00 | 2024-03-28 | 2024-08-26 10:08
PBUT07 - Substation Reliability |  |  |  |  | 14N000510000 | Substation Power Transf Repl | Inactive
PBUT07 - Substation Reliability |  |  | 40009 | 40009 | 14N000520000 | PAC New Eq.Repl.&Upgr.(Trans) | Inactive
PBUT07 - Substation Reliability |  |  | 40010 | 40010 | 14N000530000 | PAC New Eq.Repl.& Upgr.(Dist) | Inactive
PBUT07 - Substation Reliability |  |  | 40022 | 40022 | 14N001020000 | Trans Replace-Sabana Llana | Cancel | Inactive
PBUT07 - Substation Reliability |  |  | 40022 | 40022 | 14N001030000 | Transf Replace-El Conquistador | Inactive | Inactive
PBUT07 - Substation Reliability |  |  | 40050 | 40050 | 14N001040000 | Monacillo TCBreak&TransforRep | Inactive | Active
PBUT07 - Substation Reliability |  |  | 40008 | 40008-001 | 14N001110000 | Aguada Transformer Replacement | Inactive
PBUT07 - Substation Reliability |  |  | 40008 | 40008 | 14N001260000 | HV EquipReplac(FY2024Remaining | Inactive
PBUT07 - Substation Reliability |  |  | 10215 | 10215 | 14N001360000 | TRANS MVNT MAUNABO-STA ISABEL | Closed
PBUT07 - Substation Reliability |  |  | 40008 | 40008-003 | 14N001420000 | Bayamon TC - Phase 1 Trnsformr | Active
PBUT07 - Substation Reliability |  |  | 40008 | 40008-005 | 14N001430000 | Caguas TC - Phase 1 Transfrmer | Active
PBUT07 - Substation Reliability |  |  | 40008 | 40008 | 14N001440000 | Centro Medico - Phase 1 Trnsfo | Inactive
PBUT07 - Substation Reliability |  |  | 40008 | 40008-004 | 14N001450000 | Costa Sur - Phase 1 Transfrmer | Inactive
PBUT07 - Substation Reliability |  |  | 40008 | 40008-006 | 14N001460000 | Factor - Phase 1 Transformer | Inactive | [6 empty] | 2025-04-09 08:00 | 2025-04-09 08:00
PBUT07 - Substation Reliability |  |  | 40008 | 40008-007 | 14N001470000 | Mora - Phase 1 Transformer | Active
PBUT07 - Substation Reliability |  |  | 40008 | 40008-002 | 14N001480000 | Sabana Llana - Phase 1 Transfr | Inactive
PBUT07 - Substation Reliability |  |  | 20012 | 20012 | 14N001490000 | Transmission L. Optical Sensor | Inactive
PBUT07 - Substation Reliability |  |  | 40088 | 20015-014 | 14N001640000 | DOE Critical Transm. Breakers | Active | Inactive
PBUT07 - Substation Reliability |  |  | 40088 | 20015-016 | 14N001650000 | DOE-OOS Relays | Active | Inactive
PBUT07 - Substation Reliability |  |  | 40022 | 40022 | 14N001660000 | Veredas Transformer Replac. | Active | Inactive
PBUT07 - Substation Reliability |  |  | 10221 | 10221 | 14N001690000 | Aguadilla - 7003 | Active
PBUT07 - Substation Reliability |  |  | 10221 | 10221 | 14N001700000 | Aguas Buenas - 3701 | Active
PBUT07 - Substation Reliability |  |  | 10221 | 10221 | 14N001710000 | Quebradillas - 7402 | Active
PBUT07 - Substation Reliability |  |  | 10221 | 10221 | 14N001720000 | Rincon TC - 7301 | Active
PBUT07 - Substation Reliability |  |  | 10221 | 10221 | 14N001730000 | Santa Isabel - 4401 | Active
PBUT07 - Substation Reliability | 1294 | 83182 | 90102 | 90102 | 15F019640000 | Cat Z - PBUT7 | Active |  |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  |  | 2020-02-05 12:48
PBUT07 - Substation Reliability |  |  | 90102 | 90102 | 15F019940000 | CAT Z - PBUT7 (Fiona) | Active
PBUT07 - Substation Reliability |  |  |  |  | 15N003010000 | Subs Breaker&Transf Assessment | Inactive
PBUT07 - Substation Reliability |  |  | 40090 | 40090 | 15N007300000 | DOE-PAC-Functional Visual Test | Active
PBUT07 - Substation Reliability |  |  | 43010 | 43010 | 15N007310000 | Relay Elect PM-AR | Active
PBUT07 - Substation Reliability |  |  | 43010 | 43010 | 15N007320000 | Relay Elect PM-BY | Active
PBUT07 - Substation Reliability |  |  | 43010 | 43010 | 15N007330000 | Relay Elect PM-CG | Active
PBUT07 - Substation Reliability |  |  | 43010 | 43010 | 15N007340000 | Relay Elect PM-MY | Active
PBUT07 - Substation Reliability |  |  | 43010 | 43010 | 15N007350000 | Relay Elect PM-PC | Active
PBUT07 - Substation Reliability |  |  | 43010 | 43010 | 15N007360000 | Relay Elect PM-SJ | Active
PBUT07 - Substation Reliability |  |  | 43011 | 43011 | 15N007370000 | Relay Mech PM-AR | Active
PBUT07 - Substation Reliability |  |  | 43011 | 43011 | 15N007380000 | Relay Mech PM-BY | Active
PBUT07 - Substation Reliability |  |  | 43011 | 43011 | 15N007390000 | Relay Mech PM-CG | Active
PBUT07 - Substation Reliability |  |  | 43011 | 43011 | 15N007400000 | Relay Mech PM-MY | Active
PBUT07 - Substation Reliability |  |  | 43011 | 43011 | 15N007410000 | Relay Mech PM-PC | Active
PBUT07 - Substation Reliability |  |  | 43011 | 43011 | 15N007420000 | Relay Mech PM-SJ | Active
PBUT07 - Substation Reliability |  |  | 43012 | 43012 | 15N007620000 | Cap Bank PM - AR | Active
PBUT07 - Substation Reliability |  |  | 43012 | 43012 | 15N007630000 | Cap Bank PM - BY | Active
PBUT07 - Substation Reliability |  |  | 43012 | 43012 | 15N007640000 | Cap Bank PM - CG | Active
PBUT07 - Substation Reliability |  |  | 43012 | 43012 | 15N007650000 | Cap Bank PM - MY | Active
PBUT07 - Substation Reliability |  |  | 43012 | 43012 | 15N007660000 | Cap Bank PM - PC | Active
PBUT07 - Substation Reliability |  |  | 43012 | 43012 | 15N007670000 | Cap Bank PM - SJ | Active
PBUT07 - Substation Reliability |  |  | 43013 | 43013 | 15N007680000 | DC PM - AR | Active
PBUT07 - Substation Reliability |  |  | 43013 | 43013 | 15N007690000 | DC PM - BY | Active
PBUT07 - Substation Reliability |  |  | 43013 | 43013 | 15N007700000 | DC PM - CG | Active
PBUT07 - Substation Reliability |  |  | 43013 | 43013 | 15N007710000 | DC PM - MY | Active
PBUT07 - Substation Reliability |  |  | 43013 | 43013 | 15N007720000 | DC PM - PC | Active
PBUT07 - Substation Reliability |  |  | 43013 | 43013 | 15N007730000 | DC PM - SJ | Active
PBUT07 - Substation Reliability |  |  | 43014 | 43014 | 15N007740000 | Dist CB Test - AR | Active
PBUT07 - Substation Reliability |  |  | 43014 | 43014 | 15N007750000 | Dist CB Test - BY | Active
PBUT07 - Substation Reliability |  |  | 43014 | 43014 | 15N007760000 | Dist CB Test - CG | Active
PBUT07 - Substation Reliability |  |  | 43014 | 43014 | 15N007770000 | Dist CB Test - MY | Active
PBUT07 - Substation Reliability |  |  | 43014 | 43014 | 15N007780000 | Dist CB Test - PC | Active
PBUT07 - Substation Reliability |  |  | 43014 | 43014 | 15N007790000 | Dist CB Test - SJ | Active
PBUT07 - Substation Reliability |  |  | 43015 | 43015 | 15N007800000 | GCB Dielectric - AR | Active
PBUT07 - Substation Reliability |  |  | 43015 | 43015 | 15N007810000 | GCB Dielectric - BY | Active
PBUT07 - Substation Reliability |  |  | 43015 | 43015 | 15N007820000 | GCB Dielectric - CG | Active
PBUT07 - Substation Reliability |  |  | 43015 | 43015 | 15N007830000 | GCB Dielectric - MY | Active
PBUT07 - Substation Reliability |  |  | 43015 | 43015 | 15N007840000 | GCB Dielectric - PC | Active
PBUT07 - Substation Reliability |  |  | 43015 | 43015 | 15N007850000 | GCB Dielectric - SJ | Active
PBUT07 - Substation Reliability |  |  | 43016 | 43016 | 15N007860000 | GCB Ovhl - AR | Active
PBUT07 - Substation Reliability |  |  | 43016 | 43016 | 15N007870000 | GCB Ovhl - BY | Active
PBUT07 - Substation Reliability |  |  | 43016 | 43016 | 15N007880000 | GCB Ovhl - CG | Active
PBUT07 - Substation Reliability |  |  | 43016 | 43016 | 15N007890000 | GCB Ovhl - MY | Active
PBUT07 - Substation Reliability |  |  | 43016 | 43016 | 15N007900000 | GCB Ovhl - PC | Active
PBUT07 - Substation Reliability |  |  | 43016 | 43016 | 15N007910000 | GCB Ovhl - SJ | Active
PBUT07 - Substation Reliability |  |  | 43017 | 43017 | 15N007920000 | GCB Test - AR | Active
PBUT07 - Substation Reliability |  |  | 43017 | 43017 | 15N007930000 | GCB Test - BY | Active
PBUT07 - Substation Reliability |  |  | 43017 | 43017 | 15N007940000 | GCB Test - CG | Active
PBUT07 - Substation Reliability |  |  | 43017 | 43017 | 15N007950000 | GCB Test - MY | Active
PBUT07 - Substation Reliability |  |  | 43017 | 43017 | 15N007960000 | GCB Test - PC | Active
PBUT07 - Substation Reliability |  |  | 43017 | 43017 | 15N007970000 | GCB Test - SJ | Active
PBUT07 - Substation Reliability |  |  | 43018 | 43018 | 15N007980000 | Mobile PM | Active
PBUT07 - Substation Reliability |  |  | 43019 | 43019 | 15N007990000 | MOD PM - AR | Active
PBUT07 - Substation Reliability |  |  | 43019 | 43019 | 15N008000000 | MOD PM - BY | Active
PBUT07 - Substation Reliability |  |  | 43019 | 43019 | 15N008010000 | MOD PM - CG | Active
PBUT07 - Substation Reliability |  |  | 43019 | 43019 | 15N008020000 | MOD PM - MY | Active
PBUT07 - Substation Reliability |  |  | 43019 | 43019 | 15N008030000 | MOD PM - PC | Active
PBUT07 - Substation Reliability |  |  | 43019 | 43019 | 15N008040000 | MOD PM - SJ | Active
PBUT07 - Substation Reliability |  |  | 43020 | 43020 | 15N008050000 | OCB Dielectric - AR | Active
PBUT07 - Substation Reliability |  |  | 43020 | 43020 | 15N008060000 | OCB Dielectric - BY | Active
PBUT07 - Substation Reliability |  |  | 43020 | 43020 | 15N008070000 | OCB Dielectric - CG | Active
PBUT07 - Substation Reliability |  |  | 43020 | 43020 | 15N008080000 | OCB Dielectric - MY | Active
PBUT07 - Substation Reliability |  |  | 43020 | 43020 | 15N008090000 | OCB Dielectric - PC | Active
PBUT07 - Substation Reliability |  |  | 43020 | 43020 | 15N008100000 | OCB Dielectric - SJ | Active
PBUT07 - Substation Reliability |  |  | 43021 | 43021 | 15N008110000 | OCB Ovhl - AR | Active
PBUT07 - Substation Reliability |  |  | 43021 | 43021 | 15N008120000 | OCB Ovhl - BY | Active
PBUT07 - Substation Reliability |  |  | 43021 | 43021 | 15N008130000 | OCB Ovhl - CG | Active
PBUT07 - Substation Reliability |  |  | 43021 | 43021 | 15N008140000 | OCB Ovhl - MY | Active
PBUT07 - Substation Reliability |  |  | 43021 | 43021 | 15N008150000 | OCB Ovhl - PC | Active
PBUT07 - Substation Reliability |  |  | 43021 | 43021 | 15N008160000 | OCB Ovhl - SJ | Active
PBUT07 - Substation Reliability |  |  | 43022 | 43022 | 15N008170000 | OCB Test - AR | Active
PBUT07 - Substation Reliability |  |  | 43022 | 43022 | 15N008180000 | OCB Test - BY | Active
PBUT07 - Substation Reliability |  |  | 43022 | 43022 | 15N008190000 | OCB Test - CG | Active
PBUT07 - Substation Reliability |  |  | 43022 | 43022 | 15N008200000 | OCB Test - MY | Active
PBUT07 - Substation Reliability |  |  | 43022 | 43022 | 15N008210000 | OCB Test - PC | Active
PBUT07 - Substation Reliability |  |  | 43022 | 43022 | 15N008220000 | OCB Test - SJ | Active
PBUT07 - Substation Reliability |  |  | 43023 | 43023 | 15N008230000 | RTU PM - AR | Active
PBUT07 - Substation Reliability |  |  | 43023 | 43023 | 15N008240000 | RTU PM - BY | Active
PBUT07 - Substation Reliability |  |  | 43023 | 43023 | 15N008250000 | RTU PM - CG | Active
PBUT07 - Substation Reliability |  |  | 43023 | 43023 | 15N008260000 | RTU PM - MY | Active
PBUT07 - Substation Reliability |  |  | 43023 | 43023 | 15N008270000 | RTU PM - PC | Active
PBUT07 - Substation Reliability |  |  | 43023 | 43023 | 15N008280000 | RTU PM - SJ | Active
PBUT07 - Substation Reliability |  |  | 43024 | 43024 | 15N008290000 | Sub Inspect & Therm - AR | Active
PBUT07 - Substation Reliability |  |  | 43024 | 43024 | 15N008300000 | Sub Inspect & Therm - BY | Active
PBUT07 - Substation Reliability |  |  | 43024 | 43024 | 15N008310000 | Sub Inspect & Therm - CG | Active
PBUT07 - Substation Reliability |  |  | 43024 | 43024 | 15N008320000 | Sub Inspect & Therm - MY | Active
PBUT07 - Substation Reliability |  |  | 43024 | 43024 | 15N008330000 | Sub Inspect & Therm - PC | Active
PBUT07 - Substation Reliability |  |  | 43024 | 43024 | 15N008340000 | Sub Inspect & Therm - SJ | Active
PBUT07 - Substation Reliability |  |  | 43025 | 43025 | 15N008350000 | Subst. Maintenance Admin - AR | Active
PBUT07 - Substation Reliability |  |  | 43025 | 43025 | 15N008360000 | Subst. Maintenance Admin - BY | Active
PBUT07 - Substation Reliability |  |  | 43025 | 43025 | 15N008370000 | Subst. Maintenance Admin - CG | Active
PBUT07 - Substation Reliability |  |  | 43025 | 43025 | 15N008380000 | Subst. Maintenance Admin - MY | Active
PBUT07 - Substation Reliability |  |  | 43025 | 43025 | 15N008390000 | Subst. Maintenance Admin - PC | Active
PBUT07 - Substation Reliability |  |  | 43025 | 43025 | 15N008400000 | Subst. Maintenance Admin - SJ | Active
PBUT07 - Substation Reliability |  |  | 43026 | 43026 | 15N008410000 | Vessel PM - AR | Active
PBUT07 - Substation Reliability |  |  | 43026 | 43026 | 15N008420000 | Vessel PM - BY | Active
PBUT07 - Substation Reliability |  |  | 43026 | 43026 | 15N008430000 | Vessel PM - CG | Active
PBUT07 - Substation Reliability |  |  | 43026 | 43026 | 15N008440000 | Vessel PM - MY | Active
PBUT07 - Substation Reliability |  |  | 43026 | 43026 | 15N008450000 | Vessel PM - PC | Active
PBUT07 - Substation Reliability |  |  | 43026 | 43026 | 15N008460000 | Vessel PM - SJ | Active
PBUT07 - Substation Reliability |  |  | 43027 | 43027 | 15N008470000 | Xfmr DGA - AR | Active
PBUT07 - Substation Reliability |  |  | 43027 | 43027 | 15N008480000 | Xfmr DGA - BY | Active
PBUT07 - Substation Reliability |  |  | 43027 | 43027 | 15N008490000 | Xfmr DGA - CG | Active
PBUT07 - Substation Reliability |  |  | 43027 | 43027 | 15N008500000 | Xfmr DGA - MY | Active
PBUT07 - Substation Reliability |  |  | 43027 | 43027 | 15N008510000 | Xfmr DGA - PC | Active
PBUT07 - Substation Reliability |  |  | 43027 | 43027 | 15N008520000 | Xfmr DGA - SJ | Active
PBUT07 - Substation Reliability |  |  | 43028 | 43028 | 15N008530000 | Xfmr LTC Ovhl - AR | Active
PBUT07 - Substation Reliability |  |  | 43028 | 43028 | 15N008540000 | Xfmr LTC Ovhl - BY | Active
PBUT07 - Substation Reliability |  |  | 43028 | 43028 | 15N008550000 | Xfmr LTC Ovhl - CG | Active
PBUT07 - Substation Reliability |  |  | 43028 | 43028 | 15N008560000 | Xfmr LTC Ovhl - MY | Active
PBUT07 - Substation Reliability |  |  | 43028 | 43028 | 15N008570000 | Xfmr LTC Ovhl - PC | Active
PBUT07 - Substation Reliability |  |  | 43028 | 43028 | 15N008580000 | Xfmr LTC Ovhl - SJ | Active
PBUT07 - Substation Reliability |  |  | 43029 | 43029 | 15N008590000 | Xfmr LTC PM - AR | Active
PBUT07 - Substation Reliability |  |  | 43029 | 43029 | 15N008600000 | Xfmr LTC PM - BY | Active
PBUT07 - Substation Reliability |  |  | 43029 | 43029 | 15N008610000 | Xfmr LTC PM - CG | Active
PBUT07 - Substation Reliability |  |  | 43029 | 43029 | 15N008620000 | Xfmr LTC PM - MY | Active
PBUT07 - Substation Reliability |  |  | 43029 | 43029 | 15N008630000 | Xfmr LTC PM - PC | Active
PBUT07 - Substation Reliability |  |  | 43029 | 43029 | 15N008640000 | Xfmr LTC PM - SJ | Active
PBUT07 - Substation Reliability |  |  | 43030 | 43030 | 15N008650000 | Xfmr Test - AR | Active
PBUT07 - Substation Reliability |  |  | 43030 | 43030 | 15N008660000 | Xfmr Test - BY | Active
PBUT07 - Substation Reliability |  |  | 43030 | 43030 | 15N008670000 | Xfmr Test - CG | Active
PBUT07 - Substation Reliability |  |  | 43030 | 43030 | 15N008680000 | Xfmr Test - MY | Active
PBUT07 - Substation Reliability |  |  | 43030 | 43030 | 15N008690000 | Xfmr Test - PC | Active
PBUT07 - Substation Reliability |  |  | 43030 | 43030 | 15N008700000 | Xfmr Test - SJ | Active
PBUT08 - Substation Rebuilds |  |  | 90073 | 90073 | 10F000500000 | Add Generation Deployment | Inactive
PBUT08 - Substation Rebuilds | 108163 | 957578 | 10220 | 10220 | 10F008090000 | Costa Sur UG Cable Repair | Active | Active | CAP4 |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2025-07-03 17:00 | 2025-07-15 | 2025-09-17 19:15
PBUT08 - Substation Rebuilds |  |  | 40005 | 40005 | 10N000170000 | Canas TC-Transf.& Breaker Repl | Closed
PBUT08 - Substation Rebuilds |  |  | 40011 | 40011 | 10N000390000 | Building Roof & Floor Repairs | Closed
PBUT08 - Substation Rebuilds |  |  | 40073 | 40073 | 10N008200000 | HatoReyTC-Transf1420 Emer.Repl | Inactive | Inactive
PBUT08 - Substation Rebuilds | 11045 | 165268 | 10055 | 10055 | 14F001750000 | RIO GRANDE ESTATES - CH - 2306 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2021-12-13 08:00 | 2021-12-13 08:00 | 2022-05-20 12:00 | 2022-05-20 | 2022-12-21 12:37
PBUT08 - Substation Rebuilds | 11479 | 169495 | 10059 | 10059 | 14F001760000 | TAPIA GIS REBUILT -1102 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2021-10-20 17:00 | 2021-10-20 17:00 | 2022-05-02 17:00 | 2022-05-31 | 2023-08-22 11:21
PBUT08 - Substation Rebuilds | 107722 | 550980 | 10061 | 10061 | 14F001770000 | Parques y Recreos Metalclad | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2023-01-31 17:00 | 2023-01-31 17:00 | 2023-06-30 17:00 | 2023-06-30
PBUT08 - Substation Rebuilds | 107733 | 551912 | 10074 | 10074 | 14F001780000 | Puerto Nuevo Metalclad 15 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2023-03-02 17:00 | 2023-03-02 17:00 | 2023-06-30 08:00 | 2023-06-30
PBUT08 - Substation Rebuilds | 107720 | 550894 | 10014 | 10014 | 14F001790000 | Baldrich - Metalclad- 1422 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2023-01-13 08:00 | 2023-01-13 08:00 | 2023-09-29 08:00 | 2023-09-29
PBUT08 - Substation Rebuilds | 107723 | 550986 | 10015 | 10015 | 14F001800000 | Condado - Metalclad - 1133 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-12-07 08:00 | 2022-12-07 08:00 | 2023-06-13 17:00 | 2023-06-30
PBUT08 - Substation Rebuilds | 11409 | 551918 | 10016 | 10016 | 14F001810000 | Crematorio - Metalclad - 1512 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-12-02 08:00 | 2022-12-02 08:00 | 2023-06-30 08:00 | 2023-06-30
PBUT08 - Substation Rebuilds | 107693 | 547243 | 10017 | 10017 | 14F001820000 | Egozcue - Metalclad - 1109 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2023-01-23 08:00 | 2023-01-23 08:00 | 2023-06-30 17:00 | 2023-06-30
PBUT08 - Substation Rebuilds | 107713 | 550099 | 10018 | 10018 | 14F001830000 | Esc. Industrial M. Such - Meta | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-12-22 08:00 | 2022-12-22 08:00 | 2023-06-30 08:00 | 2023-06-30
PBUT08 - Substation Rebuilds | 107721 | 550972 | 10019 | 10019 | 14F001840000 | Fonalledas GIS Rebuilt 1401 14 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2025-10-30 08:00 |  | 2026-04-27 17:00
PBUT08 - Substation Rebuilds | 107727 | 551260 | 10020 | 10020 | 14F001850000 | Guaynabo Pueblo Subst. Rebuild | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2023-01-23 08:00 | 2023-01-23 08:00 | 2023-06-30 17:00 | 2023-10-02
PBUT08 - Substation Rebuilds | 107764 | 673920 | 10021 | 10021 | 14F001860000 | Isla Grande 1101 Metalclad | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2026-07-09 08:00 |  | 2026-08-14 17:00
PBUT08 - Substation Rebuilds | 107724 | 550998 | 10022 | 10022 | 14F001870000 | Santurce Planta (Sect) 1116 Me | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2025-06-19 08:00 |  | 2025-12-18 17:00
PBUT08 - Substation Rebuilds | 107690 | 547187 | 10023 | 10023 | 14F001880000 | Arecibo Pueblo 8002 Reloc | Inactive | Inactive |  |  | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant | 2023-06-22 08:00 | 2023-06-22 08:00 | 2026-02-24 17:00 | 2025-03-10
PBUT08 - Substation Rebuilds | 107725 | 551100 | 10024 | 10024 | 14F001890000 | Bayview Sectionalizer 1802 Rel | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2026-03-25 08:00 |  | 2026-05-05 17:00
PBUT08 - Substation Rebuilds | 107699 | 547273 | 10025 | 10025 | 14F001900000 | Charco Hondo 8008 Reloc | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2023-05-16 08:00 | 2023-05-16 08:00 | 2025-10-10 17:00
PBUT08 - Substation Rebuilds |  |  | 10026 | 10026 | 14F001910000 | Pampanos Relocation | Inactive | Inactive | [5 empty] | 2023-05-12 08:00 | 2023-05-12 08:00 | 2026-03-18 17:00
PBUT08 - Substation Rebuilds | 108055 | 761563 | 10027 | 10027 | 14F001920000 | San Jose Relocation | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2023-08-21 08:00 | 2023-08-21 08:00 | 2026-05-13 17:00
PBUT08 - Substation Rebuilds | 11470 | 551914 | 10028 | 10028 | 14F001930000 | Caparra 1911 & 1924 (Elevated | Active | Active |  |  | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant | 2023-04-20 17:00 | 2023-04-20 17:00 | 2024-06-28 17:00 | 2024-06-28
PBUT08 - Substation Rebuilds | 11448 | 547241 | 10029 | 10029 | 14F001940000 | Tallaboa 5402 (Elevated Contr | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-12-21 08:00 | 2022-12-21 08:00 | 2023-06-30 08:00 | 2023-06-30
PBUT08 - Substation Rebuilds | 10626 | 165209 | 10172 | 10172 | 14F002690000 | CULEBRA SUB 3801 | Active | Active |  |  | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant |  |  | 2022-03-25 08:00 | 2022-04-04 | 2022-06-10 11:48
PBUT08 - Substation Rebuilds | 10624 | 165225 | 10171 | 10171 | 14F002700000 | VIEQUES SUB 2501 | Active | Active |  |  | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant | 2021-12-01 17:00 | 2021-12-01 17:00 | 2022-03-25 17:00 | 2023-05-31 | 2022-06-10 11:48
PBUT08 - Substation Rebuilds | 107220 | 169058 | 10097 | 10097 | 14F002710000 | LLORENS TORRES MC 1106 | Active | Active |  |  | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant | 2022-02-03 17:00 | 2022-02-03 17:00 | 2022-05-30 17:00 | 2022-05-04
PBUT08 - Substation Rebuilds | 11489 | 169266 | 10098 | 10098 | 14F002720000 | CENTRO MEDICO 1 & 2 1327 & 1 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2021-09-30 08:00 | 2021-09-30 08:00 | 2022-05-26 17:00 | 2022-05-26 | 2023-11-03 11:30
PBUT08 - Substation Rebuilds | 107222 | 169276 | 10099 | 10099 | 14F002730000 | VIADUCTO TC MC 1100 | Active | Active |  |  | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant | 2021-10-26 17:00 | 2021-10-26 17:00 | 2023-03-31 08:00 | 2023-03-31
PBUT08 - Substation Rebuilds | 11347 | 169500 | 10100 | 10100 | 14F002740000 | BAYAMON TC MC BRKRS Y1 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2021-12-06 08:00 | 2021-12-06 08:00 | 2022-07-25 08:00 | 2022-07-25 | 2023-06-16 12:55
PBUT08 - Substation Rebuilds | 10788 | 169896 | 10101 | 10101 | 14F002750000 | COSTA SUR BKRS P001 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2021-12-11 08:00 | 2021-12-11 08:00 | 2022-06-07 17:00 | 2022-06-07 | 2022-08-02 11:42
PBUT08 - Substation Rebuilds |  |  | 10102 | 10102 | 14F002760000 | CARIDAD MC 1714 | Inactive
PBUT08 - Substation Rebuilds | 10496 | 174422 | 10000 | 10000 | 14F002770000 | CATANO MODER & HARD 1801 (Ele | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2021-07-16 08:00 | 2021-07-16 08:00 | 2021-10-28 17:00 | 2021-10-28 | 2022-05-18 11:30
PBUT08 - Substation Rebuilds | 11721 | 178258 | 10103 | 10103 | 14F002790000 | TAFT MC 1105 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2021-11-05 08:00 | 2021-11-05 08:00 | 2021-06-01 08:00 | 2022-05-31 | 2025-02-06 20:16
PBUT08 - Substation Rebuilds | 11100 | 178503 | 10104 | 10104 | 14F002800000 | AGUIRRE BKRS T018 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2021-12-21 17:00 | 2021-12-21 17:00 | 2022-04-15 17:00 | 2022-10-31 | 2022-12-27 11:53
PBUT08 - Substation Rebuilds | 11507 | 178577 | 10105 | 10105 | 14F002810000 | CACHETE MC 1526 | Active | Active |  |  | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant | 2023-01-13 08:00 | 2023-01-13 08:00 | 2023-10-02 17:00 | 2023-10-02
PBUT08 - Substation Rebuilds | 10632 | 179558 | 10106 | 10106 | 14F002820000 | MANATI TC BKR T005 | Inactive | Inactive |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2021-12-10 08:00 | 2021-12-10 08:00 | 2022-05-02 17:00 | 2022-05-02 | 2022-05-26 11:24
PBUT08 - Substation Rebuilds | 10858 | 546370 | 43001 | 43001-001 | 14F002850000 | Substation GRP A Capuchinos | Inactive | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  | 2022-05-31 | 2024-02-13 12:36
PBUT08 - Substation Rebuilds | 11813 | 550162 | 10107 | 10107 | 14F002920000 | Berwind TC- Metalclad - 1336 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2023-01-12 08:00 | 2023-01-12 08:00 | 2023-10-02 08:00 | 2023-10-02
PBUT08 - Substation Rebuilds | 107719 | 550771 | 10108 | 10108 | 14F002930000 | Caguas TC BKRS 115kV | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2025-10-14 08:00 |  | 2025-11-17 17:00
PBUT08 - Substation Rebuilds | 107695 | 547248 | 10109 | 10109 | 14F002940000 | Canas TC BKRS 115kV | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2025-12-09 17:00 |  | 2026-03-13 17:00
PBUT08 - Substation Rebuilds | 11385 | 542758 | 43001 | 43001-002 | 14F002960000 | Substation GRP B Factor | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2022-12-29 17:00 | 2022-07-11 | 2023-07-07 11:35
PBUT08 - Substation Rebuilds | 11385 | 542758 | 43001 | 43001-002 | 14F002980000 | Substation GRP B Morovis | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2022-12-29 17:00 | 2022-07-11 | 2023-07-07 11:35
PBUT08 - Substation Rebuilds | 11385 | 542758 | 43001 | 43001-002 | 14F002990000 | Substation GRP B Quebradillas | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2022-12-29 17:00 | 2022-07-11 | 2023-07-07 11:35
PBUT08 - Substation Rebuilds | 107224 | 169503 |  |  | 14F003080000 | Ceiba Baja 7012 Transformer Re | Inactive |  |  |  | Withdrawn | Discontinued | Process Discontinued
PBUT08 - Substation Rebuilds | 107305 | 179988 |  |  | 14F003090000 | Las Lomas 1525 Transformer Rep | Inactive |  |  |  | Withdrawn | Discontinued | Process Discontinued
PBUT08 - Substation Rebuilds |  |  | 10113 | 10113 | 14F003100000 | Bartolo 7902 Transformer Repl | Inactive
PBUT08 - Substation Rebuilds |  |  | 10114 | 10114 | 14F003110000 | Sabanera 3603 Transformer Rep | Inactive
PBUT08 - Substation Rebuilds | 107702 | 547344 | 10115 | 10115 | 14F003120000 | Acacias 6801 TC Relocation | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2023-01-17 08:00 | 2023-01-17 08:00 | 2024-03-08 17:00 | 2024-03-08
PBUT08 - Substation Rebuilds | 107694 | 547247 | 10116 | 10116 | 14F003130000 | Cambalache TC Relocation | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2023-02-01 17:00 | 2023-02-01 17:00 | 2024-07-31 17:00 | 2024-07-31
PBUT08 - Substation Rebuilds | 107734 | 551916 | 10117 | 10117 | 14F003140000 | Dorado TC Relocation | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2026-03-03 08:00 |  | 2026-04-16 17:00
PBUT08 - Substation Rebuilds | 11557 | 550950 | 10118 | 10118 | 14F003150000 | Monacillo TC - Breakers | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2023-05-08 08:00 | 2023-05-08 08:00 | 2023-05-31 08:00 | 2023-05-31 | 2023-12-19 12:23
PBUT08 - Substation Rebuilds | 107701 | 547343 | 10119 | 10119 | 14F003160000 | Victoria TC 7008 (Elevated Con | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2023-07-26 08:00 | 2023-07-26 08:00 | 2024-06-28 17:00 | 2024-06-29
PBUT08 - Substation Rebuilds | 107714 | 550106 | 10120 | 10120 | 14F003170000 | Conquistador - CH | Active | Active |  |  | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant | 2022-10-21 17:00 | 2022-10-21 17:00 | 2023-06-30 17:00 | 2023-06-30
PBUT08 - Substation Rebuilds |  |  | 10132 | 10132 | 14F003220000 | Guanica TC - Circuit Switch Re | Inactive | Inactive | [5 empty] | 2026-03-31 08:00 |  | 2026-05-28 17:00
PBUT08 - Substation Rebuilds |  |  | 10133 | 10133 | 14F003230000 | Buen Pastor 115/13.2kV Transfo | Inactive | Inactive | [5 empty] | 2026-01-21 08:00 |  | 2026-04-28 17:00
PBUT08 - Substation Rebuilds |  |  |  |  | 14F003360000 | Substation Inspect | Active
PBUT08 - Substation Rebuilds |  |  | 43001 |  | 14F003370000 | Substation Repair | Inactive | Active
PBUT08 - Substation Rebuilds |  |  | 40004 | 40004 | 14F003500000 | T & G Demarcation | Inactive | Inactive
PBUT08 - Substation Rebuilds |  |  | 43001 |  | 14F003640000 | Aguas Buenas TC | Inactive | Active
PBUT08 - Substation Rebuilds |  |  | 43001 |  | 14F003660000 | Fajardo TC | Inactive | Active
PBUT08 - Substation Rebuilds |  |  | 40013 | 40013 | 14F008400000 | Guajataca substation | Cancel
PBUT08 - Substation Rebuilds | 11402 | 682834 | 10165 | 10165 | 14F008420000 | Costa Sur TC - Phase II | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2023-05-30 17:00 | 2023-05-30 17:00 | 2023-06-01 08:00 | 2023-03-31 | 2024-02-13 12:36
PBUT08 - Substation Rebuilds | 11876 | 682328 | 10168 | 10168 | 14F008430000 | Bayamón TC - Part 2 | Active | Active |  |  | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant | 2024-04-18 08:00 | 2024-04-18 08:00 | 2023-12-14 08:00 | 2023-11-27
PBUT08 - Substation Rebuilds |  |  | 10166 | 10166 | 14F008440000 | Manati TC BRKS - Phase II | Inactive
PBUT08 - Substation Rebuilds | 11652 | 682121 | 10167 | 10167 | 14F008450000 | Aguirre TC - Phase II | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2023-06-05 08:00 | 2023-06-05 08:00 | 2023-06-01 08:00 | 2023-06-01 | 2024-03-22 10:16
PBUT08 - Substation Rebuilds | 10626 | 165209 | 10169 | 10169 | 14F008770000 | New Substation Culebra | Active | Active |  |  | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant | 2023-06-22 08:00 | 2023-06-22 08:00 | 2023-05-31 17:00 | 2022-04-04 | 2022-06-10 11:48
PBUT08 - Substation Rebuilds | 10624 | 165225 | 10170 | 10170 | 14F008780000 | New Substation Vieques | Active | Active |  |  | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant | 2023-06-22 08:00 | 2023-06-22 08:00 | 2023-05-31 17:00 | 2023-05-31 | 2022-06-10 11:48
PBUT08 - Substation Rebuilds |  |  | 43001 |  | 14F008960000 | SubMinorRepr GRP F-Maunabo TC | Active | Active
PBUT08 - Substation Rebuilds |  |  | 10174 | 10174 | 14F009030000 | Viaducto 115kV Prot&ContrlSyst | Inactive | Inactive | [5 empty] | 2021-11-04 08:00 | 2021-11-04 08:00 | 2023-03-31 08:00
PBUT08 - Substation Rebuilds | 11555 | 723078 | 10175 | 10175 | 14F009040000 | San Juan SP TC | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2023-05-18 08:00 | 2023-05-18 08:00 | 2023-06-16 17:00 | 2023-06-16 | 2023-12-19 12:23
PBUT08 - Substation Rebuilds | 107888 | 723002 | 10176 | 10176 | 14F009050000 | Jobos TC | Active | Active |  |  | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant | 2023-06-29 08:00 | 2023-06-29 08:00 | 2023-06-16 08:00 | 2023-06-15
PBUT08 - Substation Rebuilds | 11556 | 723077 | 10179 | 10179 | 14F009060000 | Sabana Llana TC | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2023-06-16 08:00 | 2023-06-16 08:00 | 2023-06-16 08:00 | 2023-06-16 | 2023-12-19 12:23
PBUT08 - Substation Rebuilds |  |  | 10178 | 10178 | 14F009070000 | New Guayanilla TC | Inactive | Inactive | [5 empty] | 2023-06-05 08:00 | 2023-06-05 08:00 | 2023-06-01 08:00
PBUT08 - Substation Rebuilds |  |  | 10177 | 10177 | 14F009080000 | New Salinas TC | Inactive | Inactive | [5 empty] | 2023-06-01 08:00 | 2023-06-01 08:00 | 2023-06-01 08:00
PBUT08 - Substation Rebuilds |  |  | 40023 | 40023 | 14F016560000 | Hato Rey | Active | Inactive | [5 empty] | 2026-12-15 08:00 |  | 2027-01-18 17:00
PBUT08 - Substation Rebuilds | 107779 | 682645 | 40024 | 40024 | 14F016570000 | MAUNABO TC | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2025-04-24 17:00 | 2025-04-24 | 2025-09-17 18:16
PBUT08 - Substation Rebuilds | 107780 | 685869 | 40025 | 40025 | 14F016580000 | Mayaguez | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2024-05-24 08:00 | 2024-05-24 08:00 | 2026-03-05 17:00
PBUT08 - Substation Rebuilds |  |  | 40026 | 40026 | 14F016590000 | Naguabo | Inactive | Inactive | [5 empty] | 2026-01-28 08:00 |  | 2026-03-03 17:00
PBUT08 - Substation Rebuilds |  |  | 40027 | 40027 | 14F016600000 | Palo Seco | Inactive | Inactive | [5 empty] | 2025-10-07 08:00 |  | 2025-12-30 17:00
PBUT08 - Substation Rebuilds |  |  | 40028 | 40028 | 14F016610000 | Punta Lima Sect. | Inactive | Inactive | [5 empty] | 2025-10-15 08:00 |  | 2025-11-20 17:00
PBUT08 - Substation Rebuilds |  |  | 40029 | 40029 | 14F016620000 | San Juan S.P. Rebuild-Phase 2 | Inactive
PBUT08 - Substation Rebuilds |  |  | 40030 | 40030 | 14F016630000 | SanJuan SP New Substat-Phase3 | Inactive
PBUT08 - Substation Rebuilds | 107995 | 752277 | 40031 | 40031 | 14F016640000 | Ciales | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2024-08-12 17:00 | 2024-08-12 17:00 | 2024-10-04 17:00 | 2024-11-26
PBUT08 - Substation Rebuilds | 107993 | 752275 | 40032 | 40032 | 14F016650000 | Unibon (Corozal) | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2024-05-31 08:00 | 2024-05-31 08:00 | 2026-07-27 17:00
PBUT08 - Substation Rebuilds | 107994 | 752276 | 40033 | 40033 | 14F016660000 | Monterey | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2024-05-31 08:00 | 2024-05-31 08:00 | 2026-11-06 12:00
PBUT08 - Substation Rebuilds | 107717 | 550498 | 40034 | 40034 | 14F016670000 | Morovis | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2024-08-13 08:00 | 2024-08-13 08:00 | 2026-03-27 17:00
PBUT08 - Substation Rebuilds |  |  | 40035 | 40035 | 14F016680000 | JAYUYA 1 | Inactive | Inactive | [5 empty] | 2026-02-18 17:00 |  | 2026-06-12 17:00
PBUT08 - Substation Rebuilds |  |  | 40036 | 40036 | 14F016690000 | JUANA DIAZ TC | Inactive | Inactive | [5 empty] | 2027-01-04 08:00 |  | 2027-05-07 17:00
PBUT08 - Substation Rebuilds |  |  | 40037 | 40037 | 14F016700000 | Fort Allen | Inactive
PBUT08 - Substation Rebuilds |  |  | 40038 | 40038 | 14F016710000 | Venezuela | Inactive | Inactive | [5 empty] | 2026-01-29 08:00 |  | 2026-09-03 17:00
PBUT08 - Substation Rebuilds |  |  | 40039 | 40039 | 14F016720000 | Quebrada Negrito | Inactive | Inactive | [7 empty] | 2026-12-18 17:00
PBUT08 - Substation Rebuilds |  |  | 40040 | 40040 | 14F016730000 | Pastillo | Inactive | Inactive | [7 empty] | 2024-07-24 17:00
PBUT08 - Substation Rebuilds |  |  | 40041 | 40041 | 14F016740000 | Ponce TC | Inactive | Inactive | [5 empty] | 2027-02-03 08:00 |  | 2027-04-02 17:00
PBUT08 - Substation Rebuilds |  |  | 40042 | 40042 | 14F016750000 | ONCE DE AGOSTO 13 KV | Inactive | Inactive | [5 empty] | 2025-12-15 08:00 |  | 2026-01-16 17:00
PBUT08 - Substation Rebuilds |  |  | 40043 | 40043 | 14F016760000 | Buena Vista Sec | Inactive | Inactive | [5 empty] | 2029-11-06 08:00 |  | 2029-12-20 17:00
PBUT08 - Substation Rebuilds |  |  | 40044 | 40044 | 14F016770000 | Brenas | Inactive | Inactive | [7 empty] | 2029-12-12 17:00
PBUT08 - Substation Rebuilds |  |  | 40045 | 40045 | 14F016780000 | Rambla Sec | Inactive | Inactive | [5 empty] | 2029-11-06 08:00 |  | 2030-01-02 17:00
PBUT08 - Substation Rebuilds |  |  | 40046 | 40046 | 14F016790000 | Sierra Linda | Inactive | Inactive | [5 empty] | 2025-11-20 08:00 |  | 2026-01-16 17:00
PBUT08 - Substation Rebuilds |  |  | 40047 | 40047 | 14F016800000 | Añasco TC | Inactive | Inactive | [7 empty] | 2026-04-22 17:00
PBUT08 - Substation Rebuilds |  |  | 40048 | 40048 | 14F016810000 | DOS BOCAS HP | Inactive | Inactive | [5 empty] | 2029-11-06 08:00 |  | 2029-12-12 17:00
PBUT08 - Substation Rebuilds |  |  | 40049 | 40049 | 14F016820000 | Isla Grande GIS II | Inactive | Inactive | [5 empty] | 2029-04-11 08:00 |  | 2029-06-01 17:00
PBUT08 - Substation Rebuilds |  |  | 40067 | 40067 | 14F020280000 | Substation Rebuild-Fajardo TC | Inactive |  | CAP1
PBUT08 - Substation Rebuilds |  |  | 40068 | 40068 | 14F020290000 | Santa Rita Sectionalizer | Inactive |  | CAP1
PBUT08 - Substation Rebuilds |  |  | 10121 | 10121 | 14N000000000 | 19908 Construction & Infrast | Inactive
PBUT08 - Substation Rebuilds |  |  |  |  | 14N000010000 | 19738 Viaducto TC New Ctrl | Inactive
PBUT08 - Substation Rebuilds |  |  |  |  | 14N000020000 | 19740 Monacillo TC New Ctrl | Cancel
PBUT08 - Substation Rebuilds |  |  | 10124 | 10124 | 14N000030000 | 16987 Switchyard 38 kV San J | Cancel | Inactive
PBUT08 - Substation Rebuilds |  |  | 10125 | 10125 | 14N000040000 | 8600 Caguas | Cancel | Inactive
PBUT08 - Substation Rebuilds |  |  | 10126 | 10126 | 14N000050000 | 12444 Anasco 115/13.2 kV (L) | Closed | Inactive | [7 empty] | 2022-06-14 17:00
PBUT08 - Substation Rebuilds |  |  | 40004 | 40004 | 14N000540000 | T&G Demarcation | Inactive | Inactive
PBUT08 - Substation Rebuilds |  |  | 40012 | 40012 | 14N000690000 | CostaSur BRK 0082&0074 Replac | Cancel
PBUT08 - Substation Rebuilds |  |  | 40004 | 40004 | 14N000700000 | T & G Demarcation Aguirre | Inactive | Inactive
PBUT08 - Substation Rebuilds |  |  | 40004 | 40004 | 14N000710000 | T & G Demarcation Cambalache | Inactive | Inactive
PBUT08 - Substation Rebuilds |  |  | 40004 | 40004 | 14N000720000 | T & G Demarcation Costa Sur | Inactive | Inactive
PBUT08 - Substation Rebuilds |  |  | 40004 | 40004 | 14N000730000 | T & G Demarcation Hydro | Inactive | Inactive
PBUT08 - Substation Rebuilds |  |  | 40004 | 40004 | 14N000740000 | T & G Demarcation Mayaguez | Inactive | Inactive
PBUT08 - Substation Rebuilds |  |  | 40004 | 40004 | 14N000750000 | T & G Demarcation Palo Seco | Inactive | Inactive
PBUT08 - Substation Rebuilds |  |  | 40004 | 40004 | 14N000760000 | T & G Demarcation Peakers | Inactive | Inactive
PBUT08 - Substation Rebuilds |  |  | 40004 | 40004 | 14N000770000 | T & G Demarcation San Juan | Inactive | Inactive
PBUT08 - Substation Rebuilds |  |  | 40059 | 40059 | 14N001170000 | BayamonTC 230kVTransformerRepl | Active | Active
PBUT08 - Substation Rebuilds | 1294 | 83182 | 90102 | 90102 | 15F019690000 | CAT Z - PBUT8 | Active |  |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  |  | 2020-02-05 12:48
PBUT08 - Substation Rebuilds |  |  | 90102 | 90102 | 15F019950000 | CAT Z - PBUT8 (Fiona) | Active
PBUT13 - T Priority Pole Repl |  |  | 22000 | 22000 | 10N000490000 | Capital Work Trans PoleReplace | Active
PBUT13 - T Priority Pole Repl |  |  | 10131 | 10131 | 10N015150000 | Tpole 3000-CAGUAX-JUNCOS | Active | Active | [5 empty] | 2021-06-01 08:00 | 2022-04-20 17:00
PBUT13 - T Priority Pole Repl |  |  | 10131 | 10131 | 10N015160000 | T-Pole3200MonTC-VenSECT | Active | Active | [5 empty] | 2021-06-01 08:00 | 2022-04-20 17:00
PBUT13 - T Priority Pole Repl |  |  | 10131 | 10131 | 10N015170000 | T-Pole3600SabLlanaTCLAngelSect | Active | Active | [5 empty] | 2021-06-01 08:00 | 2022-04-20 17:00
PBUT13 - T Priority Pole Repl |  |  | 10131 | 10131 | 10N015180000 | TPole 3100CARO-CANOTC | Active | Active | [5 empty] | 2021-06-01 08:00 | 2022-04-20 17:00
PBUT13 - T Priority Pole Repl |  |  | 10131 | 10131 | 10N015190000 | T-Pole3600LlorTorrSECT-MarPe | Active | Active | [5 empty] | 2021-06-01 08:00 | 2022-04-20 17:00
PBUT13 - T Priority Pole Repl |  |  | 10131 | 10131 | 10N015200000 | Tpole 10700HTEJA-BPUEBLO | Active | Active | [5 empty] | 2021-06-01 08:00 | 2022-04-20 17:00
PBUT13 - T Priority Pole Repl |  |  | 10131 | 10131 | 10N015290000 | TPole 1700GuaTC-Yau2 | Active | Active | [5 empty] | 2021-06-01 08:00 | 2022-04-20 17:00
PBUT13 - T Priority Pole Repl |  |  | 10131 | 10131 | 10N015300000 | TPole 700 CostSurSP-Yau2 | Active | Active | [5 empty] | 2021-06-01 08:00 | 2022-04-20 17:00
PBUT13 - T Priority Pole Repl |  |  | 10131 | 10131 | 10N015310000 | TPole 16500FajaTC-DosMar | Active | Active | [5 empty] | 2021-06-01 08:00 | 2022-04-20 17:00
PBUT13 - T Priority Pole Repl |  |  | 10131 | 10131 | 10N015320000 | TPole 800ComSECT-CidSECT | Active | Active | [5 empty] | 2021-06-01 08:00 | 2022-04-20 17:00
PBUT13 - T Priority Pole Repl |  |  | 10131 | 10131 | 10N015330000 | TPole 3000CaTC-CaSECT | Active | Active | [5 empty] | 2021-06-01 08:00 | 2022-04-20 17:00
PBUT13 - T Priority Pole Repl |  |  | 10131 | 10131 | 10N015340000 | TPole 4500CanTC-RamSECT | Active | Active | [5 empty] | 2021-06-01 08:00 | 2022-04-20 17:00
PBUT13 - T Priority Pole Repl |  |  | 10131 | 10131 | 10N015350000 | TPole 3600MonaTC-SaLlanaTC | Active | Active | [5 empty] | 2021-06-01 08:00 | 2022-04-20 17:00
PBUT13 - T Priority Pole Repl |  |  | 10131 | 10131 | 10N015360000 | TPole 3000JunTC-RBlanHP | Active | Active | [5 empty] | 2021-06-01 08:00 | 2022-04-20 17:00
PBUT13 - T Priority Pole Repl |  |  | 10131 | 10131 | 10N015370000 | TPole 3100CanoSECT-RGraTO | Active | Active | [5 empty] | 2021-06-01 08:00 | 2022-04-20 17:00
PBUT13 - T Priority Pole Repl |  |  | 10131 |  | 14F002600000 | 230kV Trans Pole Repl | Inactive | Active
PBUT13 - T Priority Pole Repl |  |  | 10131 |  | 14F002610000 | 115kV Trans Ple Repl | Inactive | Active
PBUT13 - T Priority Pole Repl |  |  | 10131 |  | 14F002620000 | Transmission Priority Pole Rep | Inactive | Active
PBUT13 - T Priority Pole Repl |  |  | 10131 |  | 14F002630000 | 38kV Bayamon Trans Pole Repl | Cancel | Active
PBUT13 - T Priority Pole Repl |  |  | 10131 |  | 14F002640000 | 38kV Mayaguez Trans Pole Repl | Cancel | Active
PBUT13 - T Priority Pole Repl |  |  | 10131 |  | 14F002650000 | 38kV Arecibo Trans Pole Repl | Cancel | Active
PBUT13 - T Priority Pole Repl |  |  | 10131 |  | 14F002660000 | 38kV Caguas Trans Pole Repl | Inactive | Active
PBUT13 - T Priority Pole Repl |  |  | 10131 |  | 14F002670000 | 38kV Ponce Trans Pole Repl | Cancel | Active
PBUT13 - T Priority Pole Repl | 107754 | 668669 | 10131 | 10131-001 | 14F003670000 | T.Priority Pole Repl.Mora50500 | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | #N/A | 2022-04-04
PBUT13 - T Priority Pole Repl | 10679 | 334468 | 10131 | 10131-002 | 14F004440000 | Trans PriorityPoleRepl-Ln2200 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval |  |  | 2022-05-02 17:00 | 2022-05-02 | 2022-07-13 21:08
PBUT13 - T Priority Pole Repl | 10837 | 550896 | 10131 | 10131-003 | 14F004450000 | Trans Priority PoleRepl-Ln6700 | Active | Active |  |  | Active | Phase 2 - Intake & Eligibility | Pending PDMG Scope & Cost Routing |  |  | #N/A | 2022-06-24 | 2022-08-08 11:30
PBUT13 - T Priority Pole Repl | 10891 | 668592 | 10131 | 10131-005 | 14F004460000 | Tran.PriorityPoleRepl.Line9800 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval |  |  | #N/A | 2022-07-07 | 2022-09-16 11:54
PBUT13 - T Priority Pole Repl | 10800 | 668583 | 10131 | 10131-004 | 14F004470000 | TransPriorityPoleReplLine13300 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | #N/A | 2022-06-08 | 2022-08-02 11:42
PBUT13 - T Priority Pole Repl |  |  | 22001 | 22001 | 14F004480000 | PRW Trans PoleRepl-JUL21-JAN22 | Cancel
PBUT13 - T Priority Pole Repl |  |  | 22002 | 22002 | 14F004490000 | PRW Tran PoleRepl-FEB22-MOVFWD | Cancel
PBUT13 - T Priority Pole Repl | 11184 | 681672 | 10131 | 10131-013 | 14F008920000 | TransPriorityPoleRepl.Line2300 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | #N/A | 2022-09-16 | 2023-01-31 12:56
PBUT13 - T Priority Pole Repl |  |  | 23007 | 23007 | 14F009430000 | Line 51200 (Ponce, Arecibo) | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23001 | 23001 | 14F009440000 | Line 50200 (Arecibo, Bayamon) | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23002 | 23002 | 14F009450000 | Line 50300 (Ponce) | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23003 | 23003 | 14F009460000 | Line 50800 (Caguas, Carolina) | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23004 | 23004 | 14F009470000 | Line 50900(Ponce,Caguas,Baya) | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23006 | 23006 | 14F009480000 | Line 51000(Ponce,Caguas,Carol) | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23005 | 23005 | 14F009490000 | Line 50100 (Arecibo) | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23005 | 23005 | 14F010160000 | Cambalache PP-Manati TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23001 | 23001 | 14F010170000 | Costa Sur PP-Manati TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23001 | 23001 | 14F010180000 | Manati TC-Bayamon TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23002 | 23002 | 14F010190000 | Aguirre PP-Costa Sur PP | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23009 | 23009 | 14F010200000 | Mayaguez TC-Mora TC-Cambalache | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23010 | 23010 | 14F010210000 | AES Power Plant-Yabucoa TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23003 | 23003 | 14F010220000 | Sabana Llana TC-Yabucoa TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23004 | 23004 | 14F010230000 | Aguas Buenas GIS-Bayamon TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23004 | 23004 | 14F010240000 | Aguirre-Aguas Buenas GIS 50900 | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23006 | 23006 | 14F010250000 | Aguas BuenasGIS-Sabana LlanaTC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23006 | 23006 | 14F010260000 | Aguirre-Aguas Buenas GIS 51000 | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23011 | 23011 | 14F010270000 | EcoElectrica PP-Costa Sur PP | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23007 | 23007 | 14F010280000 | Costa Sur PP-Cambalache PP | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23012 | 23012 | 14F010290000 | Costa Sur PP-Ponce TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23008 | 23008 | 14F010300000 | Costa Sur PP-Mayaguez TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23010 | 23010 | 14F010310000 | Aguirre PP-AES PP | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23013 | 23013 | 14F010490000 | Dos Bocas HP-Barrio Pina GIS | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23014 | 23014 | 14F010500000 | Fajardo TC-Daguao TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23014 | 23014 | 14F010510000 | Daguao TC-Rio Blanco TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23014 | 23014 | 14F010520000 | Monacillos TC-Juncos TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23016 | 23016 | 14F010530000 | Ponce TC-Dos Bocas HP | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23015 | 23015 | 14F010540000 | Rio Blanco TC-Humacao | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23015 | 23015 | 14F010550000 | Humacao TC-Yabucoa TC 36300 | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23014 | 23014 | 14F010560000 | Rio Blanco TC-Juncos TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23018 | 23018 | 14F010570000 | Sabana Llana TC-Canovanas TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23019 | 23019 | 14F010580000 | Canas TC-Ponce TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23018 | 23018 | 14F010590000 | Canovanas TC-Palmer TC | Inactive
PBUT13 - T Priority Pole Repl | 4210 | 744275 | 23017 | 23017 | 14F010600000 | 36700:Mayaguez PP-Mayaguez TC | Inactive |  |  |  | Withdrawn | Discontinued | Process Discontinued
PBUT13 - T Priority Pole Repl |  |  | 23019 | 23019 | 14F010610000 | Costa Sur PP-Canas | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23023 | 23023 | 14F010620000 | Vega Baja TC-Manati TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23020 | 23020 | 14F010640000 | Costa Sur PP-Ponce TC 37000 | Active
PBUT13 - T Priority Pole Repl |  |  | 23021 | 23021 | 14F010650000 | Guanica TC-Costa Sur PP | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23021 | 23021 | 14F010660000 | San German TC-Guanica TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23022 | 23022 | 14F010670000 | Añasco TC-Victoria TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23023 | 23023 | 14F010680000 | Dorado TC-Vega Baja TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23022 | 23022 | 14F010690000 | Mayaguez TC-Añasco TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23023 | 23023 | 14F010700000 | Dorado TC-Hato Tejas TC | Inactive
PBUT13 - T Priority Pole Repl | 4209 | 744274 | 23017 | 23017 | 14F010710000 | 37200:Mayaguez PP-Mayaguez TC | Inactive |  |  |  | Withdrawn | Discontinued | Process Discontinued
PBUT13 - T Priority Pole Repl |  |  | 23023 | 23023 | 14F010720000 | Hato Tejas TC-Bayamon TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23023 | 23023 | 14F010730000 | Cambalache TC-Dos Bocas HP | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23025 | 23025 | 14F010740000 | Mayaguez PP-Acacias TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23024 | 23024 | 14F010750000 | Victoria TC-Mora TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23029 | 23029 | 14F010760000 | Juncos TC-Humacao TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23026 | 23026 | 14F010770000 | Ponce TC-PWF | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23028 | 23028 | 14F010780000 | Sabana LlanaTC-CanovnsTC 41200 | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23026 | 23026 | 14F010790000 | Humacao TC-Yabucoa TC 41000 | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23026 | 23026 | 14F010800000 | PWF-Santa Isabel TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23030 | 23030 | 14F010810000 | Barrio Piña GIS-Dorado TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23031 | 23031 | 14F010820000 | DosBocasHP-SanSabastianTC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23032 | 23032 | 14F010830000 | HatilloTC-QuebradillasSect | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23032 | 23032 | 14F010840000 | DosBocasHP-HatilloTC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23033 | 23033 | 14F010850000 | MonacillosTC-BarioaTC | Active
PBUT13 - T Priority Pole Repl |  |  | 23033 | 23033 | 14F010860000 | BairoaTO-CaguasTC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23033 | 23033 | 14F010870000 | CaguasTC-CaguaxSect | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23033 | 23033 | 14F010880000 | CaguaxSect-JuncosTC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23033 | 23033 | 14F010890000 | JuncosTC-RioBlancoHP | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23034 | 23034 | 14F010900000 | CANOVANAS SECT-RIO GRANDE | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23035 | 23035 | 14F010910000 | MONACILLOS TC-GUAYNABOSE CT | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23035 | 23035 | 14F010920000 | GuaynaboSect-GuaraguaoSect | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23036 | 23036 | 14F010930000 | MAUNABO TC-HUMACAO TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23036 | 23036 | 14F010940000 | JOBOS TC-MAUNABO TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23037 | 23037 | 14F010950000 | SantaIsabelTC-SantaIsabelSect | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23037 | 23037 | 14F010960000 | SantIsabel TC-ToroNegro 1 HP | Inactive
PBUT13 - T Priority Pole Repl |  |  |  |  | 14F010970000 | SANTA ISABEL TC-AIBONITO TO | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23038 | 23038 | 14F010980000 | RioBlancoHP-DaguaoTC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23042 | 23042 | 14F010990000 | AcaciasTC-SanGerman-LaParguera | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23039 | 23039 | 14F011000000 | BARRANQUITASTC-COMERIOTC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23040 | 23040 | 14F011010000 | YAUCO 1 HP-ADJUNTAS TO | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23039 | 23039 | 14F011020000 | ToroNegro1HP-BarranquitasTC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23039 | 23039 | 14F011030000 | COMERIOTC-AGUAS BUENAS SECT | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23041 | 23041 | 14F011040000 | HUMACAO TC-VERDE MAR | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23043 | 23043 | 14F011050000 | JOBOS TC GUAYAMA TO | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23043 | 23043 | 14F011060000 | ANTA ISABEL-SALINAS SECT | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23043 | 23043 | 14F011070000 | PONCE TC SANTA ISABEL SECT | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23043 | 23043 | 14F011080000 | SALINAS SECT JOBOS TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23044 | 23044 | 14F011090000 | SANTA ISABEL SCT-SALINAS SCT | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23044 | 23044 | 14F011100000 | PONCE TC STA ISABEL SECT- L200 | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23044 | 23044 | 14F011110000 | SALINAS SCT-JOBOS TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23045 | 23045 | 14F011120000 | COSTA SUR SP-YAUCO 2 HP | Active
PBUT13 - T Priority Pole Repl |  |  | 23046 | 23046 | 14F011130000 | SAN GERMAN TO RADIAL | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23046 | 23046 | 14F011140000 | ACACIAS TC-SAN GERMAN | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23046 | 23046 | 14F011150000 | CUATRO HERMANOS-ACACIAS | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23046 | 23046 | 14F011160000 | MAYAGUEZ GP-CUATRO HERMANOS | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23046 | 23046 | 14F011170000 | SAN GERMAN S SAN GERMAN TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23046 | 23046 | 14F011180000 | SAN GERMAN TC-YAUCO 2HP | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23047 | 23047 | 14F011190000 | MAYAGUEZ GP ONCE DE AGOSTO S | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23047 | 23047 | 14F011200000 | ONCE DE AGOSTO-SABANA GRANDE | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23048 | 23048 | 14F011210000 | SAN GERMAN-YAUCO 1 | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23048 | 23048 | 14F011220000 | SAN GERMAN SECT SAN GERMAN TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23048 | 23048 | 14F011230000 | MAYAGUEZ GP LEON SECT | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23048 | 23048 | 14F011240000 | LEON SECT-ACACIAS TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23048 | 23048 | 14F011250000 | ACACIAS TC SAN GERMAN SECT | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23049 | 23049 | 14F011260000 | ONCE DE AGOSTO-SAN SEBASTIAN | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23049 | 23049 | 14F011270000 | MAYAGUEZ GP-COLEGIO ST | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23049 | 23049 | 14F011280000 | COLEGIO-ONCE DE AGOSTO | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23052 | 23052 | 14F011290000 | VEGA BAJA TC VEGA ALTA SECT | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23052 | 23052 | 14F011300000 | VEGA BAJA TC SAN DEMETRIO | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23052 | 23052 | 14F011310000 | VEGA ALTA SECT DORADO TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23052 | 23052 | 14F011320000 | MANATI TC VEGA BAJA TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23052 | 23052 | 14F011330000 | FACTOR SECT BARCELONETA TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23052 | 23052 | 14F011340000 | DOS BOCAS HP CAMBALACHE TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23052 | 23052 | 14F011350000 | BARCELONETA TC-MANATI TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23052 | 23052 | 14F011360000 | CAMBALACHE TC FACTOR SECT | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23034 | 23034 | 14F011370000 | CANOVANAS TC-CANOV SECT -L3100 | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23034 | 23034 | 14F011380000 | FAJARADO TC-DAGUAO TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23034 | 23034 | 14F011390000 | SABANA LLANATC-CAROLINA | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23034 | 23034 | 14F011400000 | RIO GRANDETO-PALMERTC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23034 | 23034 | 14F011410000 | MONACILLOSTC-SABANA LLANATC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23034 | 23034 | 14F011420000 | PALMER TC-FAJARDO TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23034 | 23034 | 14F011430000 | CAROLINA-CANOVANAS TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23050 | 23050 | 14F011440000 | VILLAMAR-LLORENS TORRES | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23050 | 23050 | 14F011450000 | SANANA LLANA-LOS ANGELES | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23050 | 23050 | 14F011460000 | MONACILLOS-SABANNA LLANA | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23050 | 23050 | 14F011470000 | LOS ANGELES-AEROPUERTO | Cancel
PBUT13 - T Priority Pole Repl |  |  | 23050 | 23050 | 14F011480000 | LLORENS TORRES-MARTIN PENA | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23050 | 23050 | 14F011490000 | AEROPUERTO-VILLAMAR | Cancel
PBUT13 - T Priority Pole Repl |  |  | 23051 | 23051 | 14F011500000 | CAMBALACHE-SUPER ACUEDUCTO | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23013 | 23013 | 14F012510000 | Barrio Piña GIS-Cana Sect | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23013 | 23013 | 14F012520000 | Cana Sect-Bayamon TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23013 | 23013 | 14F012530000 | Bayamon TC-Monacillos TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23060 | 23060 | 14F012540000 | ManatiTC-Dupont Bristol Myers | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23053 | 23053 | 14F012550000 | Dos Bocas HP-Caonillas PP | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23017 | 23017 | 14F012560000 | San Sebastian TC-Mayaguez TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23018 | 23018 | 14F012570000 | Palmer TC-Fajardo TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 10131 |  | 14F012580000 | T-Pole Replacement - L36100 | Cancel | Active
PBUT13 - T Priority Pole Repl |  |  | 23023 | 23023 | 14F012590000 | Manati TC-Barceloneta TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23023 | 23023 | 14F012600000 | Barceloneta TC-Cambalache TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23061 | 23061 | 14F012610000 | Humacao TC-Fonroche Solar | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23054 | 23054 | 14F012620000 | Rio Bayamon Sect-Monacillos TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23054 | 23054 | 14F012630000 | Bayamon TC-Rio Bayamon Sect | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23055 | 23055 | 14F012640000 | Bayamon TC-Palo Seco PP | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23056 | 23056 | 14F012650000 | Monacillos TC-San Juan PP | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23057 | 23057 | 14F012660000 | Hacienda San Jose-Caguas TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23057 | 23057 | 14F012670000 | AguasBuenasGIS-HaciendaSanJos | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23057 | 23057 | 14F012680000 | Ponce TC-Juana Diaz TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23057 | 23057 | 14F012690000 | Barranquitas TC-Comerio TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23057 | 23057 | 14F012700000 | Comerio TC-Aguas Buenas GIS | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23057 | 23057 | 14F012710000 | JuanaDiazTC-ToroNegHP-Barranq | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23057 | 23057 | 14F012720000 | Monacillos TC-Aguas Buenas GIS | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23058 | 23058 | 14F012730000 | Costa Sur Power Plant-PPG | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23059 | 23059 | 14F012740000 | Costa Sur PP-Union Carbide | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23026 | 23026 | 14F012750000 | Santa Isabel TC-Aguirre PP | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23121 | 23121 | 14F012760000 | Dos Bocas HP-San Sebastian TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23062 | 23062 | 14F012890000 | CAGUAS TC-GAUTIER BENITEZ SECT | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23063 | 23063 | 14F012900000 | CAYEY TC-COMSAT SECT | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23063 | 23063 | 14F012910000 | COMSAT SECT-CIDRA SECT | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23064 | 23064 | 14F012920000 | CAPUCHINOS SECT-VENEZUELA SECT | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23064 | 23064 | 14F012930000 | VillaPadresSect-CapuchinosSect | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23064 | 23064 | 14F012940000 | SABANA LLANA TC-SAN ANTON TO | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23064 | 23064 | 14F012950000 | SAN ANTON TO-VILLA PRADES SECT | Cancel
PBUT13 - T Priority Pole Repl |  |  | 23065 | 23065 | 14F012960000 | GARZAS1 HP-GARZAS2 HP | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23066 | 23066 | 14F012970000 | 1300_YAUCO1 HP-YAUCO2 HP | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23067 | 23067 | 14F012980000 | 1400_YAUCO1_HP-YAUCO2_HP | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23068 | 23068 | 14F012990000 | ARECIBO ST-CAMBALACHE TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23069 | 23069 | 14F013000000 | DOS BOCAS HP-CAONILLAS2 HP | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23070 | 23070 | 14F013010000 | SAN SEB TC-QUEBRADILLAS SECT | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23071 | 23071 | 14F013020000 | AGUADILLA H. DIS ST-MORA TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23072 | 23072 | 14F013030000 | VIADUCTO TC-EGOZCUE SECT | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23072 | 23072 | 14F013040000 | CHARDON SECT-BALDRICH SECT | Cancel
PBUT13 - T Priority Pole Repl |  |  | 23072 | 23072 | 14F013050000 | EGOZCUE ST-MARTIN PEÑA TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23072 | 23072 | 14F013060000 | MONACILLOS TC-SAN GERARDO ST | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23072 | 23072 | 14F013070000 | MARTIN PEÑA TC-POPULAR ST | Cancel
PBUT13 - T Priority Pole Repl |  |  | 23072 | 23072 | 14F013080000 | POPULAR SECT-CHARDON SECT | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23072 | 23072 | 14F013090000 | SAN GERARDO ST-VENEZUELA ST | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23073 | 23073 | 14F013100000 | MONACILLOS TC-LAS LOMAS ST | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23073 | 23073 | 14F013110000 | CACHETE SECT-CAPARRA SECT | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23073 | 23073 | 14F013120000 | LAS LOMAS SECT-CACHETE SECT | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23074 | 23074 | 14F013130000 | CIDRA SECT-CAYEY TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23074 | 23074 | 14F013140000 | CAYEY RURAL-JAJOME | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23075 | 23075 | 14F013150000 | BAYAMON TC-BAYAMON PUEB ST | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23076 | 23076 | 14F013160000 | CANAS TC-LA RAMBLA SECT | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23077 | 23077 | 14F013170000 | PALO SECO SP-BAYAMON PUEBLO | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23078 | 23078 | 14F013180000 | AGUADILLA H.DIS SECT-T-BONE TO | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23078 | 23078 | 14F013190000 | T-BONE TO-RAMEY FIELD 2 | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23079 | 23079 | 14F013200000 | COMERIO TC-GUARAGUAO SECT | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23080 | 23080 | 14F013210000 | JUNCOS TC-LAS PIEDRAS SECT | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23080 | 23080 | 14F013220000 | LAS PIEDRAS SECT-RADIAL | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23080 | 23080 | 14F013230000 | LAS PIEDRAS SECT-HUMACAO TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23081 | 23081 | 14F013240000 | VICTORIA TC-AÑASCO TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23081 | 23081 | 14F013250000 | AÑASCO TC-MAYAGUEZ GP | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23082 | 23082 | 14F013260000 | SAN JUAN SP-CREMATORIO TO | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23083 | 23083 | 14F013270000 | AGUADILLA H. DIS TO-T-BONE TO | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23084 | 23084 | 14F013280000 | MAYAGUEZ GP-RADIAL | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23085 | 23085 | 14F013290000 | BAY VIEW SECT-AMELIA SECT | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23086 | 23086 | 14F013300000 | VENEZUELA SECT-GANDARA TO | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23087 | 23087 | 14F013310000 | SAN FERN. SECT-PUERTO NUEVO TO | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23088 | 23088 | 14F013320000 | CAMBALACHE TC-MIRADOR AZ SECT | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23089 | 23089 | 14F013330000 | AMELIA SECT-RADIAL | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23090 | 23090 | 14F013340000 | DORADO TC-VEGA ALTA SECT | Active
PBUT13 - T Priority Pole Repl |  |  | 23091 | 23091 | 14F013350000 | GUANICA TC-YAUCO 2 HP | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23092 | 23092 | 14F013360000 | GARZAS 1 HP-PEÑUELAS | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23093 | 23093 | 14F013370000 | AÑASCO TC-AÑASCO | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23094 | 23094 | 14F013380000 | JUNCOS TC-GAUTIER BENITEZ SECT | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23095 | 23095 | 14F013390000 | BAYAMON TC-CATAÑO SECT | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23096 | 23096 | 14F013400000 | 10800-JOBOS TC-PFIZER GUAYAMA | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23097 | 23097 | 14F013410000 | 10900-JOBOS TC-PFIZER GUAYAMA | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23098 | 23098 | 14F013420000 | BUENA VIS. SECT-VILLA D.CARMEN | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23099 | 23099 | 14F013430000 | BARCELONETA TC-FLORIDA TO | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23100 | 23100 | 14F013440000 | 11700-COSTA SUR SP-CORCO 1 SEC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23101 | 23101 | 14F013450000 | 11800-COSTA SUR SP-CORCO 1 SEC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23102 | 23102 | 14F013460000 | BERWIND TC-VILLA PRADES SECT | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23103 | 23103 | 14F013470000 | COSECTA SUR SP-AIR PRODUCTS | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23104 | 23104 | 14F013480000 | BAYAMON TC-HATO TEJAS SECT | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23105 | 23105 | 14F013490000 | ACACIAS TC-CABO ROJO TO | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23106 | 23106 | 14F013500000 | ISABELA TO-ISABELA PUEBLO | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23107 | 23107 | 14F013510000 | JOBOS TC-REYNOLDS METAL | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23108 | 23108 | 14F013520000 | BARCELONETA TC-MERCK | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23109 | 23109 | 14F013530000 | FAJARDO TC-DOS MARINAS | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23110 | 23110 | 14F013540000 | BARRANQUITAS TC-EL ABANICO | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23015 | 23015 | 14F013550000 | Yabucoa TC-Shell | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23015 | 23015 | 14F013560000 | Juan M TC-Jobos TC-Maunabo TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23015 | 23015 | 14F013570000 | Shell-Juan Martin TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23021 | 23021 | 14F013580000 | 37100-Acacias TC-San German TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23111 | 23111 | 14F013590000 | Palo Seco PP-Bayamon TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23112 | 23112 | 14F013600000 | Caguas TC-Buen Pastor Sect | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23112 | 23112 | 14F013610000 | Monacillos TC-Buen Pastor Sect | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23112 | 23112 | 14F013620000 | Cayey TC-Caguas TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23112 | 23112 | 14F013630000 | Cayey TC-Jobos TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23113 | 23113 | 14F013640000 | Monacillos TC-Sabana Llana TC | Active
PBUT13 - T Priority Pole Repl |  |  | 23114 | 23114 | 14F013650000 | Palo Seco PP-Monacillos TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23115 | 23115 | 14F013660000 | Martin Peña GIS-Berwind TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23115 | 23115 | 14F013670000 | Berwind TC-Sabana Llana TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23115 | 23115 | 14F013680000 | Hato Rey TC-Martin Peña GIS | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23024 | 23024 | 14F013690000 | Cambalache TC-Hatillo TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23116 | 23116 | 14F013700000 | 40100 Aguirre PP-Jobos PP | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23117 | 23117 | 14F013710000 | 40200 Aguirre PP-Jobos PP | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23118 | 23118 | 14F013720000 | Barceloneta TC-AbbVie | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23119 | 23119 | 14F013730000 | Cambalache TC-Cambalache PP | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23120 | 23120 | 14F013740000 | Pattern WF-Santa Isabel WF | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23122 | 23122 | 14F013960000 | San Juan PP-Isla Grande | Cancel
PBUT13 - T Priority Pole Repl |  |  | 23123 | 23123 | 14F013970000 | 38100 San Juan PP-Viaducto TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23124 | 23124 | 14F013980000 | 38400 San Juan PP-Viaducto TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23125 | 23125 | 14F013990000 | 38500 San Juan PP-Hato Rey TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23126 | 23126 | 14F014000000 | Bayamon TC-San Juan PP | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23127 | 23127 | 14F014010000 | 38700 Palo Seco PP-San Juan PP | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23128 | 23128 | 14F014020000 | Viaducto TC-Hato Rey TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23129 | 23129 | 14F014030000 | Isla Grande TC-Viaducto TC | Cancel
PBUT13 - T Priority Pole Repl |  |  | 23130 | 23130 | 14F014040000 | 39300 HatoRey TC-MartinPeñaGIS | Cancel
PBUT13 - T Priority Pole Repl |  |  | 23131 | 23131 | 14F014050000 | Viaducto TC-Martin Peña GIS | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23132 | 23132 | 14F014060000 | 40400 San Juan PP-Hato Rey TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23133 | 23133 | 14F014070000 | Monacillos TC-Hato Rey TC | Cancel
PBUT13 - T Priority Pole Repl |  |  | 23134 | 23134 | 14F014080000 | 40600 Bayamon TC-Monacillos TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23135 | 23135 | 14F014090000 | 40700-Bayamon TC-Palo Seco PP | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23136 | 23136 | 14F014100000 | 41600 Palo Seco PP-San Juan PP | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23137 | 23137 | 14F014110000 | 41700 Juncos TC-Amgen | Cancel
PBUT13 - T Priority Pole Repl |  |  | 23138 | 23138 | 14F014120000 | 41800 Juncos TC-Amgen | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23139 | 23139 | 14F014130000 | Daguao TC-Punta Lima WF | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23140 | 23140 | 14F014140000 | Mora TC-Oriana Solar | Cancel
PBUT13 - T Priority Pole Repl |  |  | 23141 | 23141 | 14F014470000 | 3200-HATO REY TC-BALDRICH SECT | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23142 | 23142 | 14F014480000 | 6200: CATAÑO SECT-PUMA | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23143 | 23143 | 14F014490000 | 8000: ISLA GRANDE TC-CROWLEY | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23144 | 23144 | 14F014500000 | CENTRO MEDICO-FONALLEDAS TO | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23145 | 23145 | 14F014510000 | 17900: JUANA DIAZ TC-PASTILLO | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23146 | 23146 | 14F014520000 | 15900: VICTORIA TC-AGUADA TO | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23147 | 23147 | 14F014530000 | 1700: GUANICA TC-YAUCO 2 HP | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23148 | 23148 | 14F014540000 | 2500: SAN SEBASTIAN-VICTORIA | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23149 | 23149 | 14F014550000 | 8600: COSTA SUR SP-GULF | Inactive
PBUT13 - T Priority Pole Repl | 4207 | 744272 | 23150 | 23150 | 14F014560000 | 15700: BOQUERON TO-EL COMBATE | Inactive |  |  |  | Withdrawn | Discontinued | Process Discontinued
PBUT13 - T Priority Pole Repl |  |  | 23151 | 23151 | 14F014570000 | 12900: CORCO SECT-OXO CHEMICAL | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23153 | 23153 | 14F014740000 | 900: PAMPANOS SECT-CANAS TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23153 | 23153 | 14F014750000 | 900: PONCE TC-PAMPANOS SECT | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23154 | 23154 | 14F014760000 | 7200: BALDRICH-ESCUELA INDUSTR | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23155 | 23155 | 14F014770000 | 8500: CAYEY TC-AIBONITO TO | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23144 | 23144 | 14F014780000 | 8900: FONALLEDAS TO-VENEZUELA | Cancel
PBUT13 - T Priority Pole Repl |  |  | 23144 | 23144 | 14F014790000 | 8900: MONACILLOS-CENTRO MEDICO | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23156 | 23156 | 14F014800000 | 15300: BERWIND-LOS ANGELES SEC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23157 | 23157 | 14F014810000 | 17400: BERWIND-SAN JUAN MALL | Cancel
PBUT13 - T Priority Pole Repl |  |  | 23157 | 23157 | 14F014820000 | 17400: SAN JUAN MALL-SAN JOSE | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23158 | 23158 | 14F014990000 | 300: TORO NEGRO HP-JUANA DIAZ | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23158 | 23158 | 14F015000000 | 300: JUANA DIAZ TC-LA RAMBLA | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23159 | 23159 | 14F015010000 | 400: CAGUAS TC-GAUTIER BENITEZ | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23141 | 23141 | 14F015020000 | 3200: VIADUCTO TC-MARTIN PEÑA | Cancel
PBUT13 - T Priority Pole Repl |  |  | 23141 | 23141 | 14F015030000 | 3200: MARTIN PEÑA TC-HATO REY | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23141 | 23141 | 14F015040000 | 3200: MONACILLOS TC-VENEZUELA | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23074 | 23074 | 14F015050000 | 3800: CAYEY TC-COMSAT SECT | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23074 | 23074 | 14F015060000 | 3800: COMERIO TC-CIDRA SECT | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23160 | 23160 | 14F015070000 | 3900: SAN JUAN SP-CAPARRA SECT | Cancel
PBUT13 - T Priority Pole Repl |  |  | 23161 | 23161 | 14F015080000 | 8200: SanJuanSP-AMELIA-CATAÑO | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23162 | 23162 | 14F015090000 | 8400: COSTA SUR SP-GULF | Cancel
PBUT13 - T Priority Pole Repl |  |  | 23163 | 23163 | 14F015100000 | 8700: COSTA SUR SP-GARZAS HP | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23164 | 23164 | 14F015270000 | 500: PONCE-COSTA SUR SP-CANAS | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23068 | 23068 | 14F015280000 | 2300: DOS BOCAS HP-ARECIBO SEC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23165 | 23165 | 14F015290000 | 4600: BUENA VISTA-LA RAMBLA | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23165 | 23165 | 14F015300000 | 4600: PONCE TC-BUENA VISTA SEC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23166 | 23166 | 14F015310000 | 4700: CANAS TC-ADJUNTAS TO | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23167 | 23167 | 14F015320000 | 5800: SAN FERNANDO-CHARDON SEC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23168 | 23168 | 14F015330000 | 10000: MAGNOLIA-SIERRA LINDA | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23168 | 23168 | 14F015340000 | 10000: SIERRA LINDA-HATO TEJAS | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23169 | 23169 | 14F015350000 | 10700: HATO TEJAS-BAYAMON PUEB | Active
PBUT13 - T Priority Pole Repl |  |  | 23169 | 23169 | 14F015360000 | 10700: DORADO TC-HATO TEJAS TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23169 | 23169 | 14F015370000 | 10700: HatoTejasTC-HatoTejasSe | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23170 | 23170 | 14F015380000 | 14700: MANATI TC-MANATI SECT | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23163 | 23163 | 14F015700000 | 6700: SEBORUCO TO-TAPIA TO | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23163 | 23163 | 14F015710000 | 6700: MARTIN PEÑA TC-SEBORUCO | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23163 | 23163 | 14F015720000 | 7100: VIADUCTO TC-EGOZCUE SECT | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23163 | 23163 | 14F015730000 | 9400: DORADO TC-TOA ALTA | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23163 | 23163 | 14F015740000 | 9500: PALO SECO SP-CATAÑO SECT | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23163 | 23163 | 14F015750000 | 9800: BAYAMON TC-GUARAGUAO SEC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23163 | 23163 | 14F015760000 | 10500: CHARDON SECT-LAS MONJAS | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23163 | 23163 | 14F015770000 | 11100: CANOVANAS SE-SAN FERMIN | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23163 | 23163 | 14F015780000 | 13800: DAGUAO TC-INDIA | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23163 | 23163 | 14F015790000 | 17200: DORADO TC-DORADO PUEBLO | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23187 | 23187 | 14F016390000 | 10600: VIADUCTO TC-VILAMIL TO | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23180 | 23180 | 14F016400000 | 1800: PONCE-VILLA DEL CARMEN | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23181 | 23181 | 14F016410000 | 5200: CAGUAS TC-AGUAS BUENAS | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23182 | 23182 | 14F016420000 | 7900: TORO NEGRO HP-JUANA DIAZ | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23185 | 23185 | 14F016430000 | 9700: BAY VIEW SECT-CATAÑO SEC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23185 | 23185 | 14F016440000 | 9700: PALO SECO SP-BAY VIEW | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23186 | 23186 | 14F016450000 | 9900: RIO BLANCO HP-HUMACAO | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23183 | 23183 | 14F016460000 | 8800: PARQ RECR-HOTEL CAR HILT | Cancel
PBUT13 - T Priority Pole Repl |  |  | 23184 | 23184 | 14F016470000 | 9100: GUARAGUAO-BAYAMON PUEBLO | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23168 | 23168 | 14F016480000 | 10000: BAYAMON PUEBLO-MAGNOLIA | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23106 | 23106 | 14F016870000 | 13700: MORA TC-ISABELA TO | Cancel
PBUT13 - T Priority Pole Repl |  |  | 23188 | 23188 | 14F016880000 | 14000: BARCELONETA TC-PFIZER | Cancel
PBUT13 - T Priority Pole Repl |  |  | 23189 | 23189 | 14F016890000 | 14100: BARCELONETA TC-MERCK | Cancel
PBUT13 - T Priority Pole Repl |  |  | 23190 | 23190 | 14F016900000 | 15000: MAUNABO TC-MAUNABO | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23191 | 23191 | 14F016910000 | 17600: CANAS TC-PONCE CEMENT | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23192 | 23192 | 14F016920000 | 2900-ToroNegro1HP-ToroNegro2HP | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23193 | 23193 | 14F016930000 | 6900: MIRADOR AZUL-HATILLO TO | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23194 | 23194 | 14F016940000 | 7300: BALDRICH SEC-SAN JOSE TO | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23195 | 23195 | 14F017240000 | 13200: DORADO TC-HATO TEJAS TC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23196 | 23196 | 14F017250000 | 16400: LAS LOMAS-TREN URBANO | Cancel
PBUT13 - T Priority Pole Repl | 11719 | 711670 | 10131 | 10131-016 | 14F017290000 | T-Pole Program L100 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | #N/A | 2023-12-18 | 2024-06-18 11:28
PBUT13 - T Priority Pole Repl | 107857 | 711862 | 10131 |  | 14F017300000 | Tpole L100 Ponce TC-Sta Isabel | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued
PBUT13 - T Priority Pole Repl | 107856 | 711829 | 10131 |  | 14F017310000 | TPoleL100 SIsabelSecSalinasSec | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued
PBUT13 - T Priority Pole Repl | 11719 | 711670 | 10131 | 10131-019 | 14F017320000 | TPole L100 SalinasSect-JobosTC | Inactive | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | #N/A | 2023-12-18 | 2024-06-18 11:28
PBUT13 - T Priority Pole Repl | 11840 | 711819 | 10131 | 10131-020 | 14F017330000 | TPoleL13400AcaciasSGermanPargu | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | #N/A | 2023-12-21 | 2026-03-01 18:16
PBUT13 - T Priority Pole Repl | 107862 | 712978 | 10131 | 10131-021 | 14F017340000 | Tpole L2000 11AgostoSSebastian | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | #N/A
PBUT13 - T Priority Pole Repl | 11754 | 712980 | 10131 | 10131-022 | 14F017350000 | T-Pole Program L3000 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | #N/A | 2024-01-26 | 2024-11-01 15:15
PBUT13 - T Priority Pole Repl | 11754 | 712980 | 10131 | 10131-023 | 14F017360000 | TPoleL3000 CaguaxSect-JuncosTC | Inactive | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | #N/A | 2024-01-26 | 2024-11-01 15:15
PBUT13 - T Priority Pole Repl | 11754 | 712980 | 10131 | 10131-024 | 14F017370000 | TPoleL3000MonacillosTCBairoaTO | Inactive | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | #N/A | 2024-01-26 | 2024-11-01 15:15
PBUT13 - T Priority Pole Repl | 11754 | 712980 | 10131 | 10131-025 | 14F017380000 | TpoleL3000JuncosTC-RioBlancoHP | Inactive | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | #N/A | 2024-01-26 | 2024-11-01 15:15
PBUT13 - T Priority Pole Repl | 11723 | 708637 | 10131 | 10131-026 | 14F017390000 | TpoleL3700 MaunaboTC-HumacaoTC | Inactive | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | #N/A | 2024-01-12 | 2024-08-26 10:08
PBUT13 - T Priority Pole Repl | 11723 | 708637 | 10131 | 10131-027 | 14F017400000 | T-Pole Program L3700 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | #N/A | 2024-01-12 | 2024-08-26 10:08
PBUT13 - T Priority Pole Repl |  |  | 23197 | 23197 | 14F017620000 | 17800: LAJAS TO-LA PARGUERA SE | Cancel
PBUT13 - T Priority Pole Repl |  |  | 23198 | 23198 | 14F017630000 | 10100: LAS LOMAS-REPARTO METRO | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23199 | 23199 | 14F017640000 | 12500: HUMACAO TC-HUMACAO SECT | Cancel
PBUT13 - T Priority Pole Repl |  |  | 23200 | 23200 | 14F017650000 | 14400: CAGUAX SECT-VEREDAS SEC | Cancel
PBUT13 - T Priority Pole Repl |  |  | 23200 | 23200 | 14F017660000 | 14400: VEREDAS-GAUTIER BENITEZ | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23201 | 23201 | 14F017670000 | 15500: MONACILLOS-CENTRO MEDIC | Cancel
PBUT13 - T Priority Pole Repl |  |  | 23202 | 23202 | 14F017680000 | 18100: JUNCOS TC-RADIAL | Cancel
PBUT13 - T Priority Pole Repl |  |  | 23203 | 23203 | 14F017690000 | 19400: JUNCOS TC-JANSSEN | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23204 | 23204 | 14F017700000 | 4400: SAN JUAN SP-CAPARRA SECT | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23167 | 23167 | 14F017710000 | 5800: SAN JUAN SP-SAN FERNANDO | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23205 | 23205 | 14F017720000 | 7400: HATO REY-TRES MONJITAS | Cancel
PBUT13 - T Priority Pole Repl |  |  | 23206 | 23206 | 14F017730000 | 7500: TRES MONJITAS-PUERTO NUE | Cancel
PBUT13 - T Priority Pole Repl |  |  | 23207 | 23207 | 14F017740000 | 19500: PALMER TC-RADIAL | Cancel
PBUT13 - T Priority Pole Repl |  |  | 23071 | 23071 | 14F017840000 | 2700: MORA TC-QUEBRADILLAS SEC | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23071 | 23071 | 14F017850000 | 2700: VICTORIA-AGUADILLA HOSPI | Inactive
PBUT13 - T Priority Pole Repl | 4211 | 744277 | 23078 | 23078 | 14F017860000 | 2800: VICTORIA-AGUADILLA HOSPI | Inactive |  |  |  | Withdrawn | Discontinued | Process Discontinued
PBUT13 - T Priority Pole Repl |  |  | 23075 | 23075 | 14F017870000 | 4300: BAYAMON TC-JUAN DOMINGO | Cancel
PBUT13 - T Priority Pole Repl |  |  | 23075 | 23075 | 14F017880000 | 4300: JUAN DOMINGO SEC-CAPARRA | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23182 | 23182 | 14F017890000 | 7900: JUANA DIAZ TC-LA RAMBLA | Cancel
PBUT13 - T Priority Pole Repl |  |  | 23208 | 23208 | 14F017900000 | 10200: CANAS TC-CEMEX | Cancel
PBUT13 - T Priority Pole Repl |  |  | 23209 | 23209 | 14F017910000 | 10300: CANOVANASTC-CANOVANASSE | Cancel
PBUT13 - T Priority Pole Repl |  |  | 23195 | 23195 | 14F017920000 | 13200: HATO TEJAS TC-HATO TEJA | Cancel
PBUT13 - T Priority Pole Repl |  |  | 23210 | 23210 | 14F017930000 | 13600: ARECIBO SE-MIRADOR AZUL | Cancel
PBUT13 - T Priority Pole Repl |  |  | 23211 | 23211 | 14F017940000 | 14900: QUEBRADILLAS SECT-QUEBR | Cancel
PBUT13 - T Priority Pole Repl |  |  | 23212 | 23212 | 14F017950000 | 18000: JUANA DIAZ-COTO LAUREL | Cancel
PBUT13 - T Priority Pole Repl |  |  | 23213 | 23213 | 14F017960000 | 19600: BARRANQUITASTC-OROCOVIS | Inactive
PBUT13 - T Priority Pole Repl |  |  | 23214 | 23214 | 14F017970000 | 19900: SALINAS SECT-HORIZON SF | Inactive
PBUT13 - T Priority Pole Repl |  |  | 30064 |  | 14F018460000 | Feeder # 5004-06 (PONCE) | Inactive
PBUT13 - T Priority Pole Repl |  |  | 30064 |  | 14F018470000 | Feeder # 5602-02 (PONCE) | Inactive
PBUT13 - T Priority Pole Repl |  |  | 30064 |  | 14F018480000 | Feeder # 6501-01 (PONCE) | Inactive
PBUT13 - T Priority Pole Repl |  |  | 10131 | 10131 | 14F020470000 | Tpole 10100 Lomas-Reparto | Inactive | Active | CAP1 | ISSUE |  |  |  | 2021-06-01 08:00 | 2022-04-20 17:00
PBUT13 - T Priority Pole Repl |  |  | 10131 | 10131 | 14F020480000 | Tpole 2400 DBocas-Caonill | Inactive | Active | CAP1 | ISSUE |  |  |  | 2021-06-01 08:00 | 2022-04-20 17:00
PBUT13 - T Priority Pole Repl |  |  | 10131 | 10131 | 14F020490000 | Tpole 200 Ponce-StaIsabel | Inactive | Active | CAP1 | ISSUE |  |  |  | 2021-06-01 08:00 | 2022-04-20 17:00
PBUT13 - T Priority Pole Repl |  |  | 10131 | 10131 | 14F020500000 | Tpole 4800 StaIsabel-StaIsabel | Inactive | Active | CAP1 |  |  |  |  | 2021-06-01 08:00 | 2022-04-20 17:00
PBUT13 - T Priority Pole Repl | 108099 | 811913 | 10131 | 10131-062 | 14F020510000 | Tpole 9600 Bayamon-Cataño | Inactive | Active | CAP1 |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2025-09-17 17:00 | 2025-02-17
PBUT13 - T Priority Pole Repl |  |  | 10131 | 10131 | 14F020520000 | Tpole 7800 Dorado-Vega Alta | Inactive | Active | CAP1 |  |  |  |  | 2021-06-01 08:00 | 2022-04-20 17:00
PBUT13 - T Priority Pole Repl |  |  | 10131 | 10131 | 14F020530000 | Tpole 6700 SeborucoTO-TapiaTO | Inactive | Active | CAP1 | ISSUE |  |  |  | 2021-06-01 08:00 | 2022-04-20 17:00
PBUT13 - T Priority Pole Repl |  |  | 10131 | 10131 | 14F020540000 | TPole 7500 3Monjitas-PuertNu | Inactive | Active | CAP1 |  |  |  |  | 2021-06-01 08:00 | 2022-04-20 17:00
PBUT13 - T Priority Pole Repl |  |  | 10131 | 10131 | 14F020550000 | Tpole 10700 HTejas-HTejas | Inactive | Active | CAP1 | ISSUE |  |  |  | 2021-06-01 08:00 | 2022-04-20 17:00
PBUT13 - T Priority Pole Repl | 108242 | 1064452 | 10131 | 10131-035 | 14F020560000 | Tpole 800-COMSAT SECT-CIDRA SE | Inactive | Active | CAP2 | ISSUE | Active | Phase 2 - Intake & Eligibility | Pending PDMG Scope & Cost Routing |  |  | 2025-02-28 17:00 | 2026-01-26
PBUT13 - T Priority Pole Repl | 108100 | 811923 | 10131 | 10131-033 | 14F020570000 | Tpole16500Fajardo-2Marina | Inactive | Active | CAP1 | ISSUE | Withdrawn | Discontinued | Process Discontinued |  |  | 2025-03-07 17:00 | 2025-02-17
PBUT13 - T Priority Pole Repl | 108010 | 753782 | 10131 | 10131-043 | 14F020580000 | Tpole3100MONCILLOSS.LLANA | Active | Active | CAP4 | ISSUE | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2024-10-10 17:00 | 2024-08-23 | 2025-10-30 20:15
PBUT13 - T Priority Pole Repl |  |  | 10131 | 10131 | 14F020590000 | Tpole 1500 11Agosto-SG TO | Inactive | Active | CAP1 | ISSUE |  |  |  | 2021-06-01 08:00 | 2022-04-20 17:00
PBUT13 - T Priority Pole Repl | 108011 | 753785 | 10131 | 10131-055 | 14F020600000 | TPole 3300 SGerardo-Venezuela | Inactive | Active | CAP2 |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2024-09-02 17:00 | 2024-08-23
PBUT13 - T Priority Pole Repl | 108012 | 753786 | 10131 | 10131-061 | 14F020610000 | Tpole 5900SJSP-Crematori | Inactive | Active | CAP2 | ISSUE | Withdrawn | Discontinued | Process Discontinued |  |  | 2025-09-12 17:00 | 2024-08-23
PBUT13 - T Priority Pole Repl |  |  | 10131 | 10131 | 14F020620000 | Tpole1200 SGSt-SG TC-Y2HP | Inactive | Active | CAP1 |  |  |  |  | 2021-06-01 08:00 | 2022-04-20 17:00
PBUT13 - T Priority Pole Repl | 108013 | 753787 | 10131 | 10131-057 | 14F020630000 | TPole 13700 Mora-Isabela | Inactive | Active | CAP2 | WARNING | Withdrawn | Discontinued | Process Discontinued |  |  | 2025-07-14 17:00 | 2024-08-23
PBUT13 - T Priority Pole Repl | 107971 | 750151 | 10131 | 10131-029 | 14F020640000 | TPole 700CostaSur-Yauco2HP | Active | Active | CAP4 |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2024-10-15 17:00 | 2024-06-20 | 2026-01-16 16:15
PBUT13 - T Priority Pole Repl |  |  | 10131 | 10131 | 14F020650000 | Tpole1600LeonSectAcacias | Inactive | Active | CAP1 | ISSUE |  |  |  | 2021-06-01 08:00 | 2022-04-20 17:00
PBUT13 - T Priority Pole Repl | 108031 | 756999 | 10131 | 10131-041 | 14F020660000 | Tpole 19002Bocas-SSbstian | Inactive | Active | CAP2 | ISSUE | Active | Phase 2 - Intake & Eligibility | Pending PDMG Scope & Cost Routing |  |  | 2025-04-07 17:00 | 2024-10-01
PBUT13 - T Priority Pole Repl |  |  | 10131 | 10131 | 14F020670000 | Tpole2000 11AgostoSt-SSTC | Inactive | Active | CAP1 |  |  |  |  | 2021-06-01 08:00 | 2022-04-20 17:00
PBUT13 - T Priority Pole Repl | 11877 | 749072 | 10131 | 10131-032 | 14F020680000 | Tpole2700AGUADILLAH-MORA | Active | Active | CAP4 | ISSUE | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2025-12-19 10:00 | 2024-06-05 | 2025-11-05 16:16
PBUT13 - T Priority Pole Repl |  |  | 10131 | 10131 | 14F020690000 | Tpole6000AguadillaTBone | Inactive | Active | CAP1 | ISSUE |  |  |  | 2021-06-01 08:00 | 2022-04-20 17:00
PBUT13 - T Priority Pole Repl |  |  | 10131 | 10131 | 14F020700000 | Tpole36200MncillosJuncos | Inactive | Active | CAP1 | ISSUE |  |  |  | 2021-06-01 08:00 | 2022-04-20 17:00
PBUT13 - T Priority Pole Repl |  |  | 10131 | 10131 | 14F020710000 | TPole37800CaguasBuenPtSt | Inactive | Active | CAP1 | ISSUE |  |  |  | 2021-06-01 08:00 | 2022-04-20 17:00
PBUT13 - T Priority Pole Repl |  |  | 10131 | 10131 | 14F020720000 | Tpole 37800MCILLOS-PASTOR | Inactive | Active | CAP1 | ISSUE |  |  |  | 2021-06-01 08:00 | 2022-04-20 17:00
PBUT13 - T Priority Pole Repl |  |  | 10131 | 10131 | 14F020730000 | TPole14700Manati-ManatiSe | Inactive | Active | CAP1 | ISSUE |  |  |  | 2021-06-01 08:00 | 2022-04-20 17:00
PBUT13 - T Priority Pole Repl |  |  | 10131 | 10131 | 14F020740000 | TPole 6100 MayaGP-Radial | Inactive | Active | CAP1 | ISSUE |  |  |  | 2021-06-01 08:00 | 2022-04-20 17:00
PBUT13 - T Priority Pole Repl |  |  | 10131 | 10131 | 14F020750000 | TPole 2800 Tbone-RameyField2 | Inactive | Active | CAP1 | ISSUE |  |  |  | 2021-06-01 08:00 | 2022-04-20 17:00
PBUT13 - T Priority Pole Repl |  |  | 10131 | 10131 | 14F020760000 | Tpole 5600 AnascoTC-MayaguezGP | Inactive | Active | CAP1 |  |  |  |  | 2021-06-01 08:00 | 2022-04-20 17:00
PBUT13 - T Priority Pole Repl |  |  | 10131 | 10131 | 14F020770000 | TPole 3500 Cachete-Caparra | Inactive | Active | CAP1 |  |  |  |  | 2021-06-01 08:00 | 2022-04-20 17:00
PBUT13 - T Priority Pole Repl | 11874 | 749060 | 10131 | 10131-028 | 14F020780000 | Tpole5600 VictTcAÑASCOTC | Active | Active | CAP4 | ISSUE | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2024-06-05 08:00 | 2024-06-05 | 2026-03-01 18:16
PBUT13 - T Priority Pole Repl | 107970 | 750150 | 10131 | 10131-034 | 14F020790000 | TPole 4800 StaIsabel-ToroNegro | Active | Active | CAP4 | ISSUE | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2024-10-10 17:00 | 2024-06-20 | 2025-11-05 16:16
PBUT13 - T Priority Pole Repl | 107972 | 750168 | 10131-036 | 10131-036 | 14F020800000 | TPole 4800Sta.Isabel-Aibo | Active |  | CAP4 |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2024-10-10 17:00 | 2024-06-20 | 2025-11-25 18:15
PBUT13 - T Priority Pole Repl |  |  | 10131 | 10131 | 14F021440000 | TPole 500 Ponce-C.Sur-Canas | Inactive | Active | CAP1 | ISSUE |  |  |  | 2021-06-01 08:00 | 2022-04-20 17:00
PBUT13 - T Priority Pole Repl |  |  | 10131 | 10131 | 14F021450000 | TPole 2100-2Boca-Hatillo | Inactive | Active | CAP1 | ISSUE |  |  |  | 2021-06-01 08:00 | 2022-04-20 17:00
PBUT13 - T Priority Pole Repl |  |  | 10131 | 10131 | 14F021460000 | TPole 2100 Hatillo-Quebra | Inactive | Active | CAP1 |  |  |  |  | 2021-06-01 08:00 | 2022-04-20 17:00
PBUT13 - T Priority Pole Repl |  |  | 10131 | 10131 | 14F021470000 | TPole 9300 Juncos-GBenitez | Inactive | Active | CAP1 | WARNING |  |  |  | 2021-06-01 08:00 | 2022-04-20 17:00
PBUT13 - T Priority Pole Repl |  |  | 10131 | 10131 | 14F021480000 | TPole 13500 Acacias-C.Rojo | Inactive | Active | CAP1 | ISSUE |  |  |  | 2021-06-01 08:00 | 2022-04-20 17:00
PBUT13 - T Priority Pole Repl |  |  | 10131 | 10131 | 14F021490000 | TPole 14400 Caguax-Veredas | Inactive | Active | CAP1 | ISSUE |  |  |  | 2021-06-01 08:00 | 2022-04-20 17:00
PBUT13 - T Priority Pole Repl |  |  | 10131 | 10131 | 14F021500000 | TPole 37800-Cayey-Caguas | Inactive | Active | CAP1 |  |  |  |  | 2021-06-01 08:00 | 2022-04-20 17:00
PBUT13 - T Priority Pole Repl |  |  | 10131 | 10131 | 14F021510000 | TPole 37800 Cayey TC-JobTC | Inactive | Active | CAP1 |  |  |  |  | 2021-06-01 08:00 | 2022-04-20 17:00
PBUT13 - T Priority Pole Repl |  |  | 10131 | 10131 | 14F021530000 | TPole 6900MidorAzu-Hatllo | Inactive | Active | CAP1 |  |  |  |  | 2021-06-01 08:00 | 2022-04-20 17:00
PBUT13 - T Priority Pole Repl |  |  | 10131 | 10131 | 14F021540000 | Tpole 6900CAMBTC-MIRAZUL | Active | Active | CAP1 | ISSUE |  |  |  | 2021-06-01 08:00 | 2022-04-20 17:00
PBUT13 - T Priority Pole Repl |  |  | 10131 | 10131 | 14F021550000 | Tpole 7900TNEGROHP-JDIAZ | Inactive | Active | CAP1 |  |  |  |  | 2021-06-01 08:00 | 2022-04-20 17:00
PBUT13 - T Priority Pole Repl |  |  | 10131 | 10131 | 14F021560000 | TPole 8200SJS-AmeSt-CatSt | Inactive | Active | CAP1 |  |  |  |  | 2021-06-01 08:00 | 2022-04-20 17:00
PBUT13 - T Priority Pole Repl |  |  | 10131 | 10131 | 14F021570000 | Tpole 9500PSECOSP-CATAÑO | Inactive | Active | CAP1 | ISSUE |  |  |  | 2021-06-01 08:00 | 2022-04-20 17:00
PBUT13 - T Priority Pole Repl |  |  | 10131 | 10131 | 14F021580000 | TPole 9900RioBlncoHP-Huma | Inactive | Active | CAP1 |  |  |  |  | 2021-06-01 08:00 | 2022-04-20 17:00
PBUT13 - T Priority Pole Repl |  |  | 10131 | 10131 | 14F021590000 | TPole10900JOBOSTC-PFIZERGUAYMA | Inactive | Active | CAP1 |  |  |  |  | 2021-06-01 08:00 | 2022-04-20 17:00
PBUT13 - T Priority Pole Repl |  |  | 10131 | 10131 | 14F021600000 | Tpole 15900-VICTTC-ADATO | Inactive | Active | CAP1 |  |  |  |  | 2021-06-01 08:00 | 2022-04-20 17:00
PBUT13 - T Priority Pole Repl |  |  | 10131 | 10131 | 14F021610000 | TPole14100 BarcelonetaTC-Merck | Inactive | Active | CAP1 |  |  |  |  | 2021-06-01 08:00 | 2022-04-20 17:00
PBUT13 - T Priority Pole Repl |  |  | 10131 | 10131 | 14F021620000 | Tpole TL 4900QBRSec-QBRTo | Inactive | Active | CAP1 |  |  |  |  | 2021-06-01 08:00 | 2022-04-20 17:00
PBUT13 - T Priority Pole Repl |  |  | 10131 | 10131 | 14F021630000 | Tpole 36400Ponce-2BocasHy | Inactive | Active | CAP1 |  |  |  |  | 2021-06-01 08:00 | 2022-04-20 17:00
PBUT13 - T Priority Pole Repl |  |  | 10131 | 10131 | 14F021640000 | Tpole 38900Martin-Berwind | Inactive | Active | CAP1 |  |  |  |  | 2021-06-01 08:00 | 2022-04-20 17:00
PBUT13 - T Priority Pole Repl |  |  | 10131 | 10131 | 14F021660000 | TPole 10300 Canovanas TC-Sect | Inactive | Active | CAP1 |  |  |  |  | 2021-06-01 08:00 | 2022-04-20 17:00
PBUT13 - T Priority Pole Repl |  |  | 10131 | 10131 | 14F021670000 | TPole 10500 Chardon Las Monjas | Inactive | Active | CAP1 |  |  |  |  | 2021-06-01 08:00 | 2022-04-20 17:00
PBUT13 - T Priority Pole Repl |  |  | 10131 | 10131 | 14F021680000 | TPole 13200 DoraHatoT-HatoTS | Inactive | Active | CAP1 |  |  |  |  | 2021-06-01 08:00 | 2022-04-20 17:00
PBUT13 - T Priority Pole Repl |  |  | 10131 |  | 14N000650000 | Trans Priority Pole Repl.NME | Inactive | Active
PBUT13 - T Priority Pole Repl |  |  | 20014 | 20014-006 | 14N001610000 | DOE TL 36100 | Active
PBUT13 - T Priority Pole Repl |  |  | 20014 | 20014-008 | 14N001630000 | DOE TL 38200 | Active
PBUT13 - T Priority Pole Repl | 1294 | 83182 | 90102 | 90102 | 15F019900000 | CAT Z - PBUT13 | Active |  |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  |  | 2020-02-05 12:48
PBUT13 - T Priority Pole Repl |  |  | 90102 | 90102 | 15F019920000 | CAT Z - PBUT13 (Fiona) | Active
PBUT13 - T Priority Pole Repl |  |  | 10131 |  | 15N001890000 | Trans Priority Pole Repl.O&M | Cancel | Active
PBUT13 - T Priority Pole Repl |  |  |  |  | 15N002110000 | O&M Trans Pole Replacements | Cancel
PBUT17 - D Meter Repl & Maint |  |  | 14001 | 14001 | 14F003620000 | Meter Inst(fail.TWACS meters) | Inactive
PBUT17 - D Meter Repl & Maint |  |  | 40000 |  | 14N000140000 | Rhino Ring meter locks | Active | Active
PBUT17 - D Meter Repl & Maint |  |  | 14001 | 14001 | 14N000220000 | TWACS Subst.Comm.Eq.Hardw.Upgr | Active
PBUT17 - D Meter Repl & Maint |  |  | 84001 | 84001 | 14N000630000 | Non-NEM Meter Replacement | Active
PBUT17 - D Meter Repl & Maint |  |  | 94000 | 94000 | 14N001090000 | New Connections | Active
PBUT17 - D Meter Repl & Maint |  |  | 94000 | 94000 | 14N001100000 | Net Metering Meter change | Active
PBUT17 - D Meter Repl & Maint | 1294 | 83182 | 90102 | 90102 | 15F019750000 | CAT Z - PBUT17 | Inactive |  |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  |  | 2020-02-05 12:48
PBUT17 - D Meter Repl & Maint |  |  | 14001 | 14001 | 15N000140000 | TWACS Subs.Comm.Eq.O&M | Active
PBUT18 - SubstationPhys,Security |  |  | 40000 |  | 14F002160000 | PHYSICAL SECURITY FAC ASSES | Inactive | Active
PBUT18 - SubstationPhys,Security |  |  | 40000 |  | 14F003240000 | Physical Security Fence Repl | Inactive | Active
PBUT18 - SubstationPhys,Security | 10841 | 550910 | 40000 | 40000-001 | 14F003720000 | Physical Sec.Group1-Monaci.TC | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2022-04-04 17:00 | 2022-04-04 | 2023-05-04 11:30
PBUT18 - SubstationPhys,Security | 11350 | 549764 | 40000 | 40000-002 | 14F003730000 | Physical Sec.Group2-Mayagu.TC | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2023-05-02 17:00 | 2022-12-14 | 2023-06-16 12:55
PBUT18 - SubstationPhys,Security | 11372 | 551861 | 40000 | 40000-003 | 14F003740000 | Physical SecGroup3-Aguas B.GIS | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2023-04-21 17:00 | 2022-12-14 | 2023-06-16 12:55
PBUT18 - SubstationPhys,Security | 11566 | 660422 | 40000 | 40000-004 | 14F003750000 | Physical Sec.Group 4-Ponce TC | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2023-05-08 17:00 | 2023-06-05 | 2023-12-29 12:31
PBUT18 - SubstationPhys,Security | 107709 | 549768 | 40000 | 40000-005 | 14F003760000 | Physical Sec.Group 5-Bayamo.TC | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2025-04-25 17:00
PBUT18 - SubstationPhys,Security | 10841 | 550910 | 40000 | 40000-001 | 14F003800000 | PHYS SEC Group1 - Hato Rey TC | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2022-04-04 17:00 | 2022-04-04 | 2023-05-04 11:30
PBUT18 - SubstationPhys,Security | 10841 | 550910 | 40000 | 40000-001 | 14F003810000 | PHYS SEC Group 1 - Manati TC | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2022-04-04 17:00 | 2022-04-04 | 2023-05-04 11:30
PBUT18 - SubstationPhys,Security | 10841 | 550910 | 40000 | 40000-001 | 14F003820000 | PHYS SEC GRP 1-Sabana Llana TC | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2022-04-04 17:00 | 2022-04-04 | 2023-05-04 11:30
PBUT18 - SubstationPhys,Security | 10841 | 550910 | 40000 | 40000-001 | 14F003830000 | PHYS SEC Group 1 - Viaducto TC | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2022-04-04 17:00 | 2022-04-04 | 2023-05-04 11:30
PBUT18 - SubstationPhys,Security | 11350 | 549764 | 40000 | 40000-002 | 14F003840000 | PHYS SEC Group 2 - Mora TC | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2023-05-02 17:00 | 2022-12-14 | 2023-06-16 12:55
PBUT18 - SubstationPhys,Security | 11372 | 551861 | 40000 | 40000-003 | 14F003850000 | PHYS SEC Group 3 - Juncos TC | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2023-04-21 17:00 | 2022-12-14 | 2023-06-16 12:55
PBUT18 - SubstationPhys,Security | 11372 | 551861 | 40000 | 40000-003 | 14F003860000 | PHYS SEC Group 3 - Yabucoa TC | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2023-04-21 17:00 | 2022-12-14 | 2023-06-16 12:55
PBUT18 - SubstationPhys,Security | 11566 | 660422 | 40000 | 40000-004 | 14F003870000 | PHYS SEC GRP 4 - Vega Baja TC | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2023-05-08 17:00 | 2023-06-05 | 2023-12-29 12:31
PBUT18 - SubstationPhys,Security | 107709 | 549768 | 40000 | 40000-005 | 14F003880000 | PHYS SEC Group 5 - Caguas TC | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2025-04-25 17:00
PBUT18 - SubstationPhys,Security | 107709 | 549768 | 40000 | 40000-005 | 14F003890000 | PHYS SEC Group 5 - Victoria TC | Inactive | Active |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2025-04-25 17:00
PBUT18 - SubstationPhys,Security | 10858 | 546370 | 43001 | 43001-001 | 14F004360000 | PHYSICAL SECURITY-CANOVANAS TC | Inactive | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  | 2022-05-31 | 2024-02-13 12:36
PBUT18 - SubstationPhys,Security |  |  | 40000 |  | 14F004370000 | PHYSICAL SEC-CAPUCHINOS1329 | Inactive | Active
PBUT18 - SubstationPhys,Security | 10858 | 546370 | 43001 | 43001-001 | 14F004380000 | Physical Security-CovadongaGIS | Inactive | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  | 2022-05-31 | 2024-02-13 12:36
PBUT18 - SubstationPhys,Security | 10858 | 546370 | 43001 | 43001-001 | 14F004390000 | Physical Sec-IslaGrandeGIS | Inactive | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  | 2022-05-31 | 2024-02-13 12:36
PBUT18 - SubstationPhys,Security | 10858 | 546370 | 43001 | 43001-001 | 14F004400000 | Physical Security-La Muda 1343 | Inactive | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  | 2022-05-31 | 2024-02-13 12:36
PBUT18 - SubstationPhys,Security | 10858 | 546370 | 43001 | 43001-001 | 14F004410000 | Physical Sec-RPHeights1345 | Inactive | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  | 2022-05-31 | 2024-02-13 12:36
PBUT18 - SubstationPhys,Security | 11707 | 549725 | 43001 | 43001-005 | 14F015110000 | PHYS SEC GRP E -GuayamaJobosTC | Inactive | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2023-06-30 17:00 | 2023-06-30 | 2024-05-10 10:17
PBUT18 - SubstationPhys,Security | 11707 | 549725 | 43001 | 43001-005 | 14F015120000 | PHYS SEC GRP E - Coamo PDS | Inactive | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2023-06-30 17:00 | 2023-06-30 | 2024-05-10 10:17
PBUT18 - SubstationPhys,Security | 11707 | 549725 | 43001 | 43001-005 | 14F015130000 | PHYS SEC GRP E - SalinasUrbano | Inactive | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2023-06-30 17:00 | 2023-06-30 | 2024-05-10 10:17
PBUT18 - SubstationPhys,Security | 11682 | 549715 | 43001 | 43001-004 | 14F015140000 | PHYS SEC GRP D - PuntaDelMar | Inactive | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2023-06-30 17:00 | 2023-06-30 | 2024-04-12 11:19
PBUT18 - SubstationPhys,Security | 11682 | 549715 | 43001 | 43001-004 | 14F015150000 | PHYS SEC GRP D - Capa | Inactive | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2023-06-30 17:00 | 2023-06-30 | 2024-04-12 11:19
PBUT18 - SubstationPhys,Security | 11682 | 549715 | 43001 | 43001-004 | 14F015160000 | PHYS SEC GRP D - SabanaGrande | Inactive | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2023-06-30 17:00 | 2023-06-30 | 2024-04-12 11:19
PBUT18 - SubstationPhys,Security | 11478 | 546371 | 43001 | 43001-003 | 14F015170000 | PHYS SEC GRP C - RioBayamon | Inactive | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2022-06-13 17:00 | 2022-06-17 | 2023-08-22 11:21
PBUT18 - SubstationPhys,Security | 11478 | 546371 | 43001 | 43001-003 | 14F015180000 | PHYS SEC GRP C - Naranjito | Inactive | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2022-06-13 17:00 | 2022-06-17 | 2023-08-22 11:21
PBUT18 - SubstationPhys,Security | 11478 | 546371 | 43001 | 43001-003 | 14F015190000 | PHYS SEC GRP C - Crea 1717 | Inactive | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2022-06-13 17:00 | 2022-06-17 | 2023-08-22 11:21
PBUT18 - SubstationPhys,Security | 11478 | 546371 | 43001 | 43001-003 | 14F015200000 | PHYS SEC GRP C - Caná 1710 | Inactive | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2022-06-13 17:00 | 2022-06-17 | 2023-08-22 11:21
PBUT18 - SubstationPhys,Security | 11385 | 542758 | 43001 | 43001-002 | 14F015210000 | PHYS SEC GRP B - Quebradillas | Inactive | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2022-12-29 17:00 | 2022-07-11 | 2023-07-07 11:35
PBUT18 - SubstationPhys,Security | 11385 | 542758 | 43001 | 43001-002 | 14F015220000 | PHYS SEC GRP B - Morovis | Inactive | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2022-12-29 17:00 | 2022-07-11 | 2023-07-07 11:35
PBUT18 - SubstationPhys,Security | 11385 | 542758 | 43001 | 43001-002 | 14F015230000 | PHYS SEC GRP B - Isabela 7503 | Inactive | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2022-12-29 17:00 | 2022-07-11 | 2023-07-07 11:35
PBUT18 - SubstationPhys,Security | 11385 | 542758 | 43001 | 43001-002 | 14F015240000 | PHYS SEC GRP B - Factor | Inactive | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2022-12-29 17:00 | 2022-07-11 | 2023-07-07 11:35
PBUT18 - SubstationPhys,Security | 11385 | 542758 | 43001 | 43001-002 | 14F015250000 | PHYS SEC GRP B - Jayuya | Inactive | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  | 2022-12-29 17:00 | 2022-07-11 | 2023-07-07 11:35
PBUT18 - SubstationPhys,Security |  |  |  |  | 14N000150000 | Locks for Distribution switche | Active
PBUT18 - SubstationPhys,Security |  |  |  |  | 14N000160000 | Locks - 15 CIP LOW BES Sites | Active
PBUT18 - SubstationPhys,Security | 1294 | 83182 | 90102 | 90102 | 15F019650000 | CAT Z - PBUT18 | Inactive |  |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  |  | 2020-02-05 12:48
PBUT18 - SubstationPhys,Security |  |  |  |  | 15N001570000 | Landscaping &Veget.Control | Active
PBUT19 - Reg. Ops Phys. Security |  |  | 40000 |  | 10F000010000 | Replace outside CCTV at Arecib | Cancel | Active
PBUT19 - Reg. Ops Phys. Security |  |  | 40000 |  | 10F000020000 | Replace outside CCTV at Bayamo | Inactive | Active
PBUT19 - Reg. Ops Phys. Security |  |  | 40000 |  | 10F000040000 | Repairs to fence at Mayaguez T | Cancel | Active
PBUT19 - Reg. Ops Phys. Security |  |  | 40000 |  | 10N000040000 | Card access to doors Carolina | Cancel | Active
PBUT19 - Reg. Ops Phys. Security |  |  | 40000 |  | 10N000670000 | CCTV&AccessRegOpsPhysSecPBUT19 | Active | Active
PBUT19 - Reg. Ops Phys. Security |  |  | 40000 |  | 10N000680000 | CCTV&accessCustomerExpFacility | Active | Active
PBUT19 - Reg. Ops Phys. Security |  |  |  |  | 10N000690000 | CCTV&accessPaloSeco | Active
PBUT19 - Reg. Ops Phys. Security |  |  |  |  | 10N000700000 | CCTV SatelliteWarehouses | Active
PBUT19 - Reg. Ops Phys. Security |  |  |  |  | 10N000710000 | CCTV&accessRegionalWarehouses | Active
PBUT19 - Reg. Ops Phys. Security |  |  |  |  | 10N000720000 | Fence SatelliteWarehouses | Active
PBUT19 - Reg. Ops Phys. Security |  |  |  |  | 10N000730000 | Fencing & CCTV WorkCamps | Active
PBUT19 - Reg. Ops Phys. Security |  |  | 90071 | 90071 | 10N002810000 | Santurce Complex CCTV | Inactive
PBUT19 - Reg. Ops Phys. Security |  |  | 40000 |  | 15N003150000 | Reg&Tech FacilityCCTV&access | Cancel | Active
PBUT20 - Warehouse Security |  |  | 40000 |  | 10F000030000 | CCTV for Regional Warehouses ( | Cancel | Active
PBUT22 - Critic.Ener.MgmtSysUpgr |  |  | 90004 | 90004 | 10N000180000 | Outage Prediction Model Tool | Cancel | Inactive
PBUT22 - Critic.Ener.MgmtSysUpgr |  |  | 10219 | 10219 | 10N014350000 | EMS Site Readiness | Active
PBUT22 - Critic.Ener.MgmtSysUpgr | 10957 | 657300 | 10128 | 10128 | 14F000020000 | ENERGY MANAGEMENT SYSTEM (EMS) | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval | 2023-09-11 08:00 | 2023-09-11 08:00 |  | 2022-06-27 | 2022-10-17 11:37
PBUT22 - Critic.Ener.MgmtSysUpgr | 10957 | 657300 | 10128 | 10128 | 14F021700000 | Implement Advanced ADMS/DERMS | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Pending Amendment Request Approval | 2023-09-11 08:00 | 2023-09-11 08:00 |  | 2022-06-27 | 2022-10-17 11:37
PBUT22 - Critic.Ener.MgmtSysUpgr |  |  | 10128 | 10128 | 14N000550000 | Operator Log Tool Development | Closed | Active | [5 empty] | 2023-09-11 08:00 | 2023-09-11 08:00
PBUT22 - Critic.Ener.MgmtSysUpgr | 1294 | 83182 | 90102 | 90102 | 15F019770000 | CAT Z - PBUT22 | Inactive |  |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  |  | 2020-02-05 12:48
PBUT22 - Critic.Ener.MgmtSysUpgr |  |  | 90015 | 90015 | 15N000640000 | Gen dispatch proced.devel.&Imp | Cancel
PBUT22 - Critic.Ener.MgmtSysUpgr |  |  | 90015 | 90015 | 15N001230000 | Impr Metr data capt &Collect | Active
PBUT22 - Critic.Ener.MgmtSysUpgr |  |  | 90015 | 90015 | 15N001240000 | SCADA-EMS data validat upda | Inactive
PBUT22 - Critic.Ener.MgmtSysUpgr |  |  | 90036 | 90036 | 15N001400000 | OperRSV (AGC-SSR-SR) Strat&Imp | Inactive
PBUT22 - Critic.Ener.MgmtSysUpgr |  |  | 90036 | 90036 | 15N001500000 | Gene Disp Proced Devel and Imp | Cancel
PBUT22 - Critic.Ener.MgmtSysUpgr |  |  | 60018 | 60018 | 15N004710000 | Call Mngmnt Control Center | Inactive
PBUT24 - Ctrl Ctr Const & Refurb | 11824 | 746545 | 10127 | 10127 | 14F000010000 | New Primary&Backup Ctrl Centrs | Active | Active |  |  | Active | Phase 2 - Intake & Eligibility | Pending PDMG Scope & Cost Routing |  |  | 2023-06-22 08:00 | 2024-04-19
PBUT24 - Ctrl Ctr Const & Refurb | 11824 | 746545 | 10127 | 10127 | 14F019920000 | Secondary Control Center | Active | Active |  |  | Active | Phase 2 - Intake & Eligibility | Pending PDMG Scope & Cost Routing |  |  | 2023-06-22 08:00 | 2024-04-19
PBUT24 - Ctrl Ctr Const & Refurb | 1294 | 83182 | 90102 | 90102 | 15F019780000 | CAT Z - PBUT24 | Inactive |  |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  |  | 2020-02-05 12:48
PBUT25 - Operator Training |  |  | 90014 | 90014 | 15N000630000 | System Operator Training | Inactive
PBUT26 - System Ops Strat & Proc |  |  | 90013 | 90013 | 15N000620000 | Gen Proc Syst Oper Proc Dev | Active
PBUT27 - Asset Data Integrity |  |  | 90004 | 90004 | 10N000130000 | OMS Capital Stabilization | Inactive | Inactive
PBUT27 - Asset Data Integrity |  |  | 90004 | 90004 | 10N000140000 | WayTo Software Implementation | Closed | Inactive
PBUT27 - Asset Data Integrity |  |  | 60007 | 60007 | 10N000320000 | CAP Asset Suite Work Man | Active
PBUT27 - Asset Data Integrity |  |  | 63000 | 63000 | 10N000420000 | Hexagon GIS Setup | Closed | Inactive
PBUT27 - Asset Data Integrity |  |  | 60011 | 60011 | 10N000470000 | OMS- Optimization Project | Closed | Inactive
PBUT27 - Asset Data Integrity |  |  | 30072 | 30072 | 10N006220000 | Customers Without Power | Closed
PBUT27 - Asset Data Integrity |  |  | 90099 | 90099 | 10N009580000 | Asset Tagging | Inactive
PBUT27 - Asset Data Integrity |  |  | 90100 | 90100 | 10N009640000 | GIS Improvements | Inactive
PBUT27 - Asset Data Integrity |  |  | 60028 | 60028 | 10N014190000 | DOE Core Conf. Asset Suite | Active | Active | [5 empty] | 2025-07-21 08:00 | 2025-07-21 08:00
PBUT27 - Asset Data Integrity |  |  | 10043 | 10043 | 14F002080000 | Prelim. Eng. Data Collection | Inactive
PBUT27 - Asset Data Integrity |  |  | 90040 | 90040 | 14N000570000 | P&C Repository-Phase I-Interim | Inactive
PBUT27 - Asset Data Integrity |  |  | 90040 | 90040 | 14N000580000 | Asset Manag Tools&Sys Crossbow | Inactive
PBUT27 - Asset Data Integrity |  |  | 90040 | 90040 | 14N000590000 | Network Model Management (NMM) | Inactive
PBUT27 - Asset Data Integrity | 1294 | 83182 | 90102 | 90102 | 15F019810000 | CAT Z - PBUT27 | Active |  |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  |  | 2020-02-05 12:48
PBUT27 - Asset Data Integrity |  |  | 90004 | 90004 | 15N000030000 | OMS Ops Stabilization | Inactive | Inactive
PBUT27 - Asset Data Integrity |  |  | 90005 | 90005 | 15N000290000 | AM-Asset: AssetSte UDte | Inactive
PBUT27 - Asset Data Integrity |  |  | 90005 | 90005 | 15N000350000 | AM-Asset Net Magnt Tools Syst | Inactive
PBUT27 - Asset Data Integrity |  |  | 60007 | 60007 | 15N001090000 | O&M Asset Suite Work Mang | Inactive
PBUT29 - StandMetering&MeterShop |  |  | 14000 | 14000 | 14N000200000 | On-Site Test Equipment | Active
PBUT29 - StandMetering&MeterShop |  |  | 14000 | 14000 | 14N000210000 | Meter Test Boards | Active
PBUT29 - StandMetering&MeterShop |  |  | 90005 | 90005 | 15N000110000 | Metering Process Devel.& Supp. | Inactive
PBUT29 - StandMetering&MeterShop |  |  | 14000 | 14000 | 15N000120000 | On-Site Test Equipment-O&M | Inactive
PBUT29 - StandMetering&MeterShop |  |  | 14000 | 14000 | 15N000130000 | Meter Test Boards (O&M) | Active
PBUT30 - D Pole & Conductor Repa |  |  | 32003 | 32003 | 10N006600000 | 3rdPartyDamageUrgentPoleRepair | Active
PBUT30 - D Pole & Conductor Repa |  |  | 32002 | 32002 | 10N006610000 | Programmable Repairs | Active
PBUT30 - D Pole & Conductor Repa |  |  | 32000 |  | 14F001620000 | San Juan Region Pole & Cond | Inactive | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 32000 |  | 14F001630000 | Bayamon Region Pole & Cond | Inactive | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 32000 |  | 14F001640000 | Ponce Region Pole & Conduc | Inactive | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 32000 |  | 14F001650000 | Dist Pole and Conductor Repair | Inactive | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 32000 |  | 14F001660000 | Mayaguez Region Pole & Con | Inactive | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 32000 |  | 14F001670000 | Arecibo Region Pole & Cond | Cancel | Inactive
PBUT30 - D Pole & Conductor Repa | 10909 | 673771 | 32000-001 | 32000-001 | 14F003930000 | DPole Arecibo Grp. 1 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-05-24 08:00 | 2022-05-24 08:00 | 2022-07-11 17:00 | 2022-07-11 | 2022-10-17 11:37
PBUT30 - D Pole & Conductor Repa | 10690 | 542762 | 32000-002 | 32000-002 | 14F003940000 | DPole Arecibo Grp. 2 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2021-10-29 08:00 | 2021-10-29 08:00 | 2022-01-28 08:00 | 2022-01-28 | 2022-06-03 11:23
PBUT30 - D Pole & Conductor Repa | 11041 | 673836 | 32000-003 | 32000-003 | 14F003950000 | DPole Bayamon Grp. 1 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-05-27 08:00 | 2022-05-27 08:00 | 2022-07-01 17:00 | 2022-07-01 | 2022-12-21 12:37
PBUT30 - D Pole & Conductor Repa | 10742 | 673839 | 32000-004 | 32000-004 | 14F003960000 | DPole Bayamon Grp. 2 | Inactive | Inactive |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-05-13 08:00 | 2022-05-13 08:00 | 2022-05-31 17:00 | 2022-06-01 | 2022-07-12 11:39
PBUT30 - D Pole & Conductor Repa | 10922 | 673843 | 32000-005 | 32000-005 | 14F003970000 | DPole Bayamon Grp. 3 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-05-27 08:00 | 2022-05-27 08:00 | 2022-07-11 08:00 | 2022-07-11 | 2022-10-17 11:37
PBUT30 - D Pole & Conductor Repa | 10906 | 674072 | 32000-006 | 32000-006 | 14F003980000 | DPole Caguas Grp. 1 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-05-31 08:00 | 2022-05-31 08:00 | 2022-07-06 08:00 | 2022-07-06 | 2022-09-16 11:54
PBUT30 - D Pole & Conductor Repa | 10827 | 674083 | 32000-007 | 32000-007 | 14F003990000 | DPole Caguas Grp. 2 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-05-23 08:00 | 2022-05-23 08:00 | 2022-07-01 17:00 | 2022-07-01 | 2022-08-08 11:30
PBUT30 - D Pole & Conductor Repa | 10933 | 674088 | 32000-008 | 32000-008 | 14F004000000 | DPole Caguas Grp. 3 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-06-06 08:00 | 2022-06-06 08:00 | 2022-07-14 08:00 | 2022-07-14 | 2022-10-17 11:37
PBUT30 - D Pole & Conductor Repa | 10635 | 334488 | 32000-009 | 32000-009 | 14F004010000 | DPole Caguas Grp. 4 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2021-11-10 08:00 | 2021-11-10 08:00 | 2022-02-04 08:00 | 2022-02-04 | 2022-05-26 11:24
PBUT30 - D Pole & Conductor Repa | 10893 | 674092 | 32000-010 | 32000-010 | 14F004020000 | DPole Caguas Grp. 5 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-05-31 08:00 | 2022-05-31 08:00 | 2022-06-24 17:00 | 2022-06-24 | 2022-09-16 11:54
PBUT30 - D Pole & Conductor Repa | 10935 | 674096 | 32000-011 | 32000-011 | 14F004030000 | DPole Caguas Grp. 6 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-05-31 08:00 | 2022-05-31 08:00 | 2022-07-15 08:00 | 2022-07-15 | 2022-10-17 11:37
PBUT30 - D Pole & Conductor Repa | 10824 | 674098 | 32000-012 | 32000-012 | 14F004040000 | DPole Caguas Grp. 7 | Closed | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-05-24 08:00 | 2022-05-24 08:00 | 2022-06-27 08:00 | 2022-06-27 | 2022-08-08 11:30
PBUT30 - D Pole & Conductor Repa | 10701 | 334527 | 32000-013 | 32000-013 | 14F004050000 | DPole Caguas Grp. 8 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2021-11-02 08:00 | 2021-11-02 08:00 | 2022-02-08 08:00 | 2022-02-08 | 2022-06-10 11:48
PBUT30 - D Pole & Conductor Repa |  |  | 32000 |  | 14F004060000 | Dist.Pole&Cond Rep-Carolin G1 | Inactive | Inactive
PBUT30 - D Pole & Conductor Repa | 10812 | 673847 | 32000-015 | 32000-015 | 14F004070000 | DPole Carolina Grp. 2 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-06-07 08:00 | 2022-06-07 08:00 | 2022-06-22 17:00 | 2022-06-22 | 2022-08-08 11:30
PBUT30 - D Pole & Conductor Repa | 10751 | 673848 | 32000-016 | 32000-016 | 14F004080000 | DPole Carolina Grp. 3 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-05-26 08:00 | 2022-05-26 08:00 | 2022-06-02 17:00 | 2022-06-02 | 2022-07-12 11:39
PBUT30 - D Pole & Conductor Repa | 10773 | 673774 | 32000-017 | 32000-017 | 14F004090000 | DPole Mayaguez Grp. 1 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-06-01 08:00 | 2022-06-01 08:00 | 2022-06-10 17:00 | 2022-06-13 | 2022-08-02 11:42
PBUT30 - D Pole & Conductor Repa | 10919 | 673772 | 32000-018 | 32000-018 | 14F004100000 | DPole Mayaguez Grp. 2 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-06-29 08:00 | 2022-06-29 08:00 | 2022-07-19 17:00 | 2022-07-19 | 2022-10-24 11:36
PBUT30 - D Pole & Conductor Repa | 10962 | 673775 | 32000-019 | 32000-019 | 14F004110000 | DPole Mayaguez Grp. 3 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2023-03-30 08:00 | 2023-03-30 08:00 | 2022-07-26 17:00 | 2022-07-26 | 2022-12-27 11:53
PBUT30 - D Pole & Conductor Repa | 10777 | 673795 | 32000-020 | 32000-020 | 14F004120000 | DPole Mayaguez Grp. 4 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-05-27 08:00 | 2022-05-27 08:00 | 2022-06-10 17:00 | 2022-06-13 | 2022-08-02 11:42
PBUT30 - D Pole & Conductor Repa | 10630 | 334323 | 32000-021 | 32000-021 | 14F004130000 | DPole Ponce Grp. 1 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2021-09-13 08:00 | 2021-09-13 08:00 | 2022-01-28 17:00 | 2022-01-28 | 2022-05-26 11:24
PBUT30 - D Pole & Conductor Repa | 10629 | 334329 | 32000-022 | 32000-022 | 14F004140000 | DPole Ponce Grp. 2 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2021-09-10 08:00 | 2021-09-10 08:00 | 2022-01-27 08:00 | 2022-01-28 | 2022-05-20 12:05
PBUT30 - D Pole & Conductor Repa | 10821 | 673818 | 32000-023 | 32000-023 | 14F004150000 | DPole San Juan Grp. 1 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-05-30 08:00 | 2022-05-30 08:00 | 2022-06-30 08:00 | 2022-06-30 | 2022-08-08 11:30
PBUT30 - D Pole & Conductor Repa | 10764 | 673838 | 32000-024 | 32000-024 | 14F004160000 | DPole San Juan Grp. 2 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-05-30 08:00 | 2022-05-30 08:00 | 2022-06-02 17:00 | 2022-06-02 | 2022-07-12 11:39
PBUT30 - D Pole & Conductor Repa | 10864 | 673844 | 32000-025 | 32000-025 | 14F004170000 | DPole San Juan Grp. 3 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-05-30 08:00 | 2022-05-30 08:00 | 2022-07-07 08:00 | 2022-07-07 | 2022-08-24 10:30
PBUT30 - D Pole & Conductor Repa |  |  | 32000 |  | 14F004220000 | Distribution Pole and Cond Rep | Inactive | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 32000 |  | 14F004230000 | Distr Pole and Cond Rep | Inactive | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 32000 |  | 14F004240000 | Distribution Pole and Cond | Inactive | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 32000 |  | 14F004250000 | Distribution Pole and | Inactive | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 32000 |  | 14F004260000 | Distribution Pole | Inactive | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 32000 |  | 14F004270000 | Distribution Pol | Inactive | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 32001 |  | 14F004280000 | PRW Dist.Pole Repl.JUN21-JAN22 | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 32002 |  | 14F004290000 | PRW DistPole ReplFEB22-MOVFWD | Active
PBUT30 - D Pole & Conductor Repa | 11096 | 679127 | 32000-026 | 32000-026 | 14F008480000 | DPole Arecibo Grp. 3 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-07-22 08:00 | 2022-07-22 08:00 | 2022-08-31 17:00 | 2022-08-31 | 2022-12-27 11:53
PBUT30 - D Pole & Conductor Repa | 11103 | 678985 | 32000-027 | 32000-027 | 14F008490000 | DPole Bayamon Grp. 4 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-07-26 17:00 | 2022-07-26 17:00 | 2022-08-30 08:00 | 2022-08-29 | 2022-12-27 11:53
PBUT30 - D Pole & Conductor Repa | 11098 | 679033 | 32000-028 | 32000-028 | 14F008500000 | DPole Caguas Grp. 9 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-07-27 17:00 | 2022-07-27 17:00 | 2022-09-08 08:00 | 2022-09-08 | 2022-12-27 11:53
PBUT30 - D Pole & Conductor Repa | 11089 | 679149 | 32000-029 | 32000-029 | 14F008510000 | DPole Mayaguez Grp. 5 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-07-19 08:00 | 2022-07-19 08:00 | 2022-08-31 17:00 | 2022-09-08 | 2022-12-27 11:53
PBUT30 - D Pole & Conductor Repa | 11105 | 679457 | 32000-030 | 32000-030 | 14F008520000 | DPole Ponce Grp. 3 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-07-26 17:00 | 2022-07-26 17:00 | 2022-09-08 08:00 | 2022-09-08 | 2022-12-27 11:53
PBUT30 - D Pole & Conductor Repa | 11101 | 679025 | 32000-031 | 32000-031 | 14F008530000 | DPole San Juan Grp. 4 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-08-02 08:00 | 2022-08-02 08:00 | 2022-09-08 17:00 | 2022-09-08 | 2022-12-27 11:53
PBUT30 - D Pole & Conductor Repa | 11090 | 679133 | 32000-032 | 32000-032 | 14F008540000 | DPole Arecibo Grp. 4 | Active | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2022-07-22 17:00 | 2022-07-22 17:00 | 2022-09-14 17:00 | 2022-09-14 | 2022-12-27 11:53
PBUT30 - D Pole & Conductor Repa | 11113 | 678988 | 32000-033 | 32000-033 | 14F008550000 | DPole Bayamon Grp. 5 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-07-25 08:00 | 2022-07-25 08:00 | 2022-09-15 08:00 | 2022-09-15 | 2022-12-27 11:53
PBUT30 - D Pole & Conductor Repa | 11109 | 679134 | 32000-034 | 32000-034 | 14F008560000 | DPole Caguas Grp. 10 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-07-29 08:00 | 2022-07-29 08:00 | 2022-09-15 08:00 | 2022-09-15 | 2023-01-10 13:19
PBUT30 - D Pole & Conductor Repa | 11106 | 679153 | 32000-035 | 32000-035 | 14F008570000 | DPole Mayaguez Grp. 6 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-07-20 08:00 | 2022-07-20 08:00 | 2022-09-16 17:00 | 2022-09-16 | 2022-12-27 11:53
PBUT30 - D Pole & Conductor Repa | 11114 | 679458 | 32000-036 | 32000-036 | 14F008580000 | DPole Ponce Grp. 4 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-07-26 08:00 | 2022-07-26 08:00 | 2022-09-15 08:00 | 2022-09-15 | 2023-01-10 13:19
PBUT30 - D Pole & Conductor Repa | 11107 | 679026 | 32000-037 | 32000-037 | 14F008590000 | DPole San Juan Grp. 5 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-08-04 08:00 | 2022-08-04 08:00 | 2022-09-15 17:00 | 2022-09-15 | 2022-12-27 11:53
PBUT30 - D Pole & Conductor Repa | 11116 | 686471 | 32000-038 | 32000-038 | 14F008640000 | DPole Arecibo Grp. 5 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-08-18 08:00 | 2022-08-18 08:00 | 2022-11-17 08:00 | 2022-11-17 | 2022-12-27 11:53
PBUT30 - D Pole & Conductor Repa | 11171 | 685477 | 32000-044 | 32000-044 | 14F008650000 | DPole Arecibo Grp. 6 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-08-19 08:00 | 2022-08-19 08:00 | 2022-11-22 08:00 | 2022-11-22 | 2023-01-24 13:14
PBUT30 - D Pole & Conductor Repa | 11183 | 682898 | 32000-039 | 32000-039 | 14F008660000 | DPole Bayamon Grp. 6 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-08-24 08:00 | 2022-08-24 08:00 | 2022-11-17 08:00 | 2022-11-17 | 2023-01-24 13:14
PBUT30 - D Pole & Conductor Repa | 11212 | 682910 | 32000-045 | 32000-045 | 14F008670000 | DPole Bayamon Grp. 7 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-08-11 08:00 | 2022-08-11 08:00 | 2022-11-18 08:00 | 2022-11-18 | 2023-01-31 12:56
PBUT30 - D Pole & Conductor Repa | 11130 | 682882 | 32000-040 | 32000-040 | 14F008680000 | DPole Caguas Grp. 11 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-08-18 08:00 | 2022-08-18 08:00 | 2022-11-18 08:00 | 2022-11-18 | 2023-01-10 13:19
PBUT30 - D Pole & Conductor Repa | 11136 | 682890 | 32000-046 | 32000-046 | 14F008690000 | DPole Caguas Grp. 12 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-08-23 08:00 | 2022-08-23 08:00 | 2022-11-21 08:00 | 2022-11-21 | 2022-12-27 11:53
PBUT30 - D Pole & Conductor Repa | 11152 | 686453 | 32000-041 | 32000-041 | 14F008700000 | DPole Mayaguez Grp. 7 | Closed | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-08-11 08:00 | 2022-08-11 08:00 | 2022-11-21 17:00 | 2022-11-21 | 2022-12-27 11:53
PBUT30 - D Pole & Conductor Repa | 11150 | 685370 | 32000-047 | 32000-047 | 14F008710000 | DPole Mayaguez Grp. 8 | Closed | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-08-10 08:00 | 2022-08-10 08:00 | 2022-11-20 17:00 | 2022-11-20 | 2023-01-10 13:19
PBUT30 - D Pole & Conductor Repa | 11138 | 685943 | 32000-042 | 32000-042 | 14F008720000 | DPole Ponce Grp. 5 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-08-17 08:00 | 2022-08-17 08:00 | 2022-11-21 08:00 | 2022-11-21 | 2023-01-10 13:19
PBUT30 - D Pole & Conductor Repa | 11143 | 685263 | 32000-048 | 32000-048 | 14F008730000 | DPole Ponce Grp. 6 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-08-19 08:00 | 2022-08-19 08:00 | 2022-11-21 08:00 | 2022-11-21 | 2022-12-27 11:53
PBUT30 - D Pole & Conductor Repa | 11137 | 682870 | 32000-043 | 32000-043 | 14F008740000 | DPole San Juan Grp. 6 | Closed | Inactive |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-08-18 08:00 | 2022-08-18 08:00 | 2022-11-22 08:00 | 2022-11-22 | 2022-12-27 11:53
PBUT30 - D Pole & Conductor Repa | 11123 | 682865 | 32000-049 | 32000-049 | 14F008750000 | DPole San Juan Grp. 7 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-08-17 08:00 | 2022-08-17 08:00 | 2022-11-17 08:00 | 2022-11-17 | 2022-12-27 11:53
PBUT30 - D Pole & Conductor Repa | 11201 | 682178 | 32000-050 | 32000-050 | 14F008800000 | DPole Arecibo Grp. 7 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-10-31 08:00 | 2022-10-31 08:00 | 2022-12-07 17:00 | 2022-12-07 | 2023-01-31 12:56
PBUT30 - D Pole & Conductor Repa | 11182 | 682172 | 32000-056 | 32000-056 | 14F008810000 | DPole Arecibo Grp. 8 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-08-31 08:00 | 2022-08-31 08:00 | 2022-12-16 17:00 | 2022-12-15 | 2023-01-24 13:14
PBUT30 - D Pole & Conductor Repa | 11149 | 682135 | 32000-051 | 32000-051 | 14F008820000 | DPole Bayamon Grp. 8 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-10-24 08:00 | 2022-10-24 08:00 | 2022-11-28 08:00 | 2022-11-28 | 2023-01-10 13:19
PBUT30 - D Pole & Conductor Repa | 11203 | 682136 | 32000-057 | 32000-057 | 14F008830000 | DPole Bayamon Grp. 9 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-10-24 08:00 | 2022-10-24 08:00 | 2022-12-15 08:00 | 2022-12-15 | 2023-01-31 12:56
PBUT30 - D Pole & Conductor Repa | 11145 | 682324 | 32000-052 | 32000-052 | 14F008840000 | DPole Caguas Grp. 13 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-10-27 08:00 | 2022-10-27 08:00 | 2022-11-28 08:00 | 2022-11-28 | 2023-01-10 13:19
PBUT30 - D Pole & Conductor Repa | 11165 | 682373 | 32000-058 | 32000-058 | 14F008850000 | DPole Caguas Grp. 14 | Closed | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-08-25 08:00 | 2022-08-25 08:00 | 2022-12-08 08:00 | 2022-12-08 | 2023-01-10 13:19
PBUT30 - D Pole & Conductor Repa | 11169 | 682210 | 32000-053 | 32000-053 | 14F008860000 | DPole Mayaguez Grp. 9 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-10-24 08:00 | 2022-10-24 08:00 | 2022-12-07 17:00 | 2022-12-07 | 2023-01-24 13:14
PBUT30 - D Pole & Conductor Repa | 11168 | 682180 | 32000-059 | 32000-059 | 14F008870000 | DPole Mayaguez Grp. 10 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-08-10 08:00 | 2022-08-10 08:00 | 2022-12-08 17:00 | 2022-12-08 | 2023-01-10 13:19
PBUT30 - D Pole & Conductor Repa | 11229 | 686480 | 32000-054 | 32000-054 | 14F008880000 | DPole Ponce Grp. 7 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-10-25 08:00 | 2022-10-25 08:00 | 2022-12-07 17:00 | 2022-12-07 | 2023-02-16 12:51
PBUT30 - D Pole & Conductor Repa | 11196 | 682228 | 32000-060 | 32000-060 | 14F008890000 | DPole Ponce Grp. 8 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-11-04 08:00 | 2022-11-04 08:00 | 2022-12-16 17:00 | 2022-12-15 | 2023-01-31 12:56
PBUT30 - D Pole & Conductor Repa | 11166 | 682028 | 32000-055 | 32000-055 | 14F008900000 | DPole San Juan Grp. 8 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-10-21 08:00 | 2022-10-21 08:00 | 2022-12-07 08:00 | 2022-12-07 | 2023-01-10 13:19
PBUT30 - D Pole & Conductor Repa | 11181 | 682031 | 32000-061 | 32000-061 | 14F008910000 | DPole San Juan Grp. 9 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-09-09 08:00 | 2022-09-09 08:00 | 2022-12-19 08:00 | 2022-12-19 | 2023-01-31 12:56
PBUT30 - D Pole & Conductor Repa |  |  | 30066 |  | 14F009090000 | Feeder# 8701-01 (Ciales) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F009100000 | Feeder # 2401-01 (Canovanas) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30063 |  | 14F009110000 | Feeder # 3405-01 (Cayey) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30064 |  | 14F009120000 | Feeder # 5004-06 (Ponce) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30064 |  | 14F009130000 | Feeder # 5004-07 (Ponce) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30064 |  | 14F009140000 | Feeder # 5018-03 (Ponce) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30064 |  | 14F009150000 | Feeder # 5021-01 (Ponce) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30064 |  | 14F009160000 | Feeder # 5401-02 (Penuelas) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30064 |  | 14F009170000 | Feeder # 5602-02 (Guanica) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30065 |  | 14F009180000 | Feeder # 6010-02 (Mayaguez) | Closed
PBUT30 - D Pole & Conductor Repa | 4217 | 744413 | 30065 |  | 14F009190000 | Feeder # 6401-04 (San German) | Inactive |  |  |  | Active |  | Pending Award
PBUT30 - D Pole & Conductor Repa | 4218 | 744420 | 30064 |  | 14F009200000 | Feeder#6501-01(SABANA GRANDE) | Inactive |  |  |  | Active | Phase 3 - Scoping and Costing | Pending FEMA 406 HMP Completion
PBUT30 - D Pole & Conductor Repa | 4218 | 744420 | 30064 |  | 14F009210000 | Feeder#6501-02(Sabana Grande) | Inactive |  |  |  | Active | Phase 3 - Scoping and Costing | Pending FEMA 406 HMP Completion
PBUT30 - D Pole & Conductor Repa | 4218 | 744420 | 30064 |  | 14F009220000 | Feeder #6501-04 (SabanGrande) | Inactive |  |  |  | Active | Phase 3 - Scoping and Costing | Pending FEMA 406 HMP Completion
PBUT30 - D Pole & Conductor Repa |  |  | 30064 |  | 14F009230000 | Feeder # 6601-04 (LAJAS) | Closed
PBUT30 - D Pole & Conductor Repa | 4223 | 744462 | 30064 |  | 14F009240000 | Feeder # 6603-01 (Lajas) | Closed |  |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  |  | 2026-01-12 19:15
PBUT30 - D Pole & Conductor Repa |  |  | 30066 |  | 14F009250000 | Feeder # 7404-06(QUEBRADILLAS) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30066 |  | 14F009260000 | Feeder # 8302-05 (Jayuya) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30063 |  | 14F009500000 | Feeder #9602-03(Barranquitas) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30063 |  | 14F009510000 | Feeder # 9703-01 (Comerio) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30063 |  | 14F009520000 | Feeder # 9703-02 (Comerio) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30067 |  | 14F009530000 | Feeder # 9801-01 (Naranjito) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30067 |  | 14F009540000 | Feeder # 9802-04 (Naranjito) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F009550000 | Feeder # 1303-05 (San Juan) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F009560000 | Feeder # 1414-01 (San Juan) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F009570000 | Feeder # 1512-04 (San Juan) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F009580000 | Feeder # 6601-03 (Lajas) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30065 |  | 14F009590000 | Feeder # 6702-04 (Cabo Rojo) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30065 |  | 14F009600000 | Feeder # 6703-01 (Cabo Rojo) | Inactive
PBUT30 - D Pole & Conductor Repa | 4219 | 744422 | 30065 |  | 14F009610000 | Feeder # 6406-02 (San German) | Inactive |  |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  |  | 2026-02-25 22:16
PBUT30 - D Pole & Conductor Repa | 4224 | 744463 | 30065 |  | 14F009620000 | Feeder # 6704-03 (Cabo Rojo) | Closed |  |  |  | Active | Phase 4 - Final Field Reviews | Pending EHP Review
PBUT30 - D Pole & Conductor Repa | 4224 | 744463 | 30065 |  | 14F009630000 | Feeder # 6704-02 (Cabo Rojo) | Inactive |  |  |  | Active | Phase 4 - Final Field Reviews | Pending EHP Review
PBUT30 - D Pole & Conductor Repa |  |  | 30065 |  | 14F009640000 | Feeder # 7502-02 (Isabela) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30065 |  | 14F009650000 | Feeder # 6802-05 (Hormigueros) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30065 |  | 14F009660000 | Feeder # 6101-05 (Anasco) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30065 |  | 14F009670000 | Feeder # 7503-05 (Isabela) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30065 |  | 14F009680000 | Feeder # 7505-05 (Isabela) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30066 |  | 14F009690000 | Feeder # 8401-02 (Utuado) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30065 |  | 14F009700000 | Feeder # 6014-02 (Mayaguez) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30066 |  | 14F009710000 | Feeder # 9003-06 (Vega Baja) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30066 |  | 14F009720000 | Feeder # 8302-04 (Jayuya) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30066 |  | 14F009730000 | Feeder # 8701-04 (Ciales) | Closed
PBUT30 - D Pole & Conductor Repa | 2557 | 745657 | 30066 |  | 14F009740000 | Feeder # 9101-01 (Vega Alta) | Closed |  |  |  | Active |  | Pending Closeout Completion |  |  |  |  | 2024-07-02 11:15
PBUT30 - D Pole & Conductor Repa |  |  | 30066 |  | 14F009750000 | Feeder # 9103-01 (Vega Alta) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30065 |  | 14F009760000 | Feeder # 6010-01 (Mayaguez) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30066 |  | 14F009770000 | Feeder # 9004-08 (Vega Baja) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30067 |  | 14F009780000 | Feeder # 9403-01 (Toa Alta) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30066 |  | 14F009790000 | Feeder # 8202-01 (Adjuntas) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F009800000 | Feeder # 1512-05 (San Juan) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F009810000 | Feeder # 1620-01 (San Juan) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F009820000 | Feeder # 1620-02 (San Juan) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F009830000 | Feeder # 1620-03 (San Juan) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F009840000 | Feeder # 1620-04 (Carolina | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F009850000 | Feeder # 1620-05 (Carolina) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30067 |  | 14F009860000 | Feeder # 1704-01 (Bayamon) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30067 |  | 14F009870000 | Feeder # 1709-03 (Guaynabo) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30063 |  | 14F009880000 | Feeder # 3014-01 (Caguas) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30063 |  | 14F009890000 | Feeder # 3014-04 (Caguas) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30063 |  | 14F009900000 | Feeder # 3406-02 (Cayey) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30063 |  | 14F009910000 | Feeder # 3406-03 (Cayey) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30063 |  | 14F009920000 | Feeder # 3501-02 (Aibonito) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30063 |  | 14F009930000 | Feeder # 3502-02 (Aibonito) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30063 |  | 14F009940000 | Feeder # 3604-06 (Cidra) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30064 |  | 14F009950000 | Feeder # 5012-03 (Ponce) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30064 |  | 14F009960000 | Feeder # 5501-04 (Guayanilla) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30064 |  | 14F009970000 | Feeder # 5803-02 (Juana Diaz) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30065 |  | 14F009980000 | Feeder # 6001-01 (Mayaguez) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30065 |  | 14F009990000 | Feeder # 6001-02 (Mayaguez) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30065 |  | 14F010000000 | Feeder # 6001-03 (Mayaguez) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30065 |  | 14F010010000 | Feeder # 6001-04 (Mayaguez) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30065 |  | 14F010020000 | Feeder # 6305-03 (Maricao) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30067 |  | 14F010030000 | Feeder # 9502-02 (Corozal) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30063 |  | 14F010040000 | Feeder # 9601-01(Barranquitas) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30066 |  | 14F010130000 | Feeder # 8104-02 (Utuado) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30067 |  | 14F010140000 | Feeder # 9401-01 (Toa Alta) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30067 |  | 14F010150000 | Feeder # 9403-03 (Toa Alta) | Closed
PBUT30 - D Pole & Conductor Repa | 11267 | 701679 | 32000-062 | 32000-062 | 14F010320000 | DPole San Juan Grp. 12 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-12-15 08:00 | 2022-12-15 08:00 | 2023-01-31 08:00 | 2023-01-31 | 2023-03-02 12:24
PBUT30 - D Pole & Conductor Repa | 11264 | 688109 | 32000-063 | 32000-063 | 14F010330000 | DPole San Juan Grp. 11 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-11-07 08:00 | 2022-11-07 08:00 | 2023-01-20 08:00 | 2023-01-20 | 2023-03-08 12:36
PBUT30 - D Pole & Conductor Repa | 11231 | 691246 | 32000-064 | 32000-064 | 14F010340000 | DPole San Juan Grp. 10 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-12-01 08:00 | 2022-12-01 08:00 | 2022-12-21 08:00 | 2022-12-21 | 2023-02-16 12:51
PBUT30 - D Pole & Conductor Repa | 11275 | 701555 | 32000-065 | 32000-065 | 14F010350000 | DPole Ponce Grp. 13 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-12-16 08:00 | 2022-12-16 08:00 | 2023-01-27 17:00 | 2023-01-27 | 2023-03-08 12:36
PBUT30 - D Pole & Conductor Repa | 11257 | 701552 | 32000-066 | 32000-066 | 14F010360000 | DPole Ponce Grp. 12 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-12-21 08:00 | 2022-12-21 08:00 | 2023-01-20 17:00 | 2023-01-20 | 2023-03-08 12:36
PBUT30 - D Pole & Conductor Repa | 11269 | 701545 | 32000-067 | 32000-067 | 14F010370000 | DPole Ponce Grp. 11 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-12-21 17:00 | 2022-12-21 17:00 | 2023-01-20 17:00 | 2023-01-20 | 2023-03-08 12:36
PBUT30 - D Pole & Conductor Repa | 11279 | 688625 | 32000-068 | 32000-068 | 14F010380000 | DPole Ponce Grp. 10 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-11-04 08:00 | 2022-11-04 08:00 | 2023-01-20 17:00 | 2023-01-20 | 2023-03-20 11:45
PBUT30 - D Pole & Conductor Repa | 11207 | 688774 | 32000-069 | 32000-069 | 14F010390000 | DPole Ponce Grp. 9 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-11-04 08:00 | 2022-11-04 08:00 | 2022-12-21 17:00 | 2022-12-21 | 2023-01-31 12:56
PBUT30 - D Pole & Conductor Repa | 11263 | 701495 | 32000-070 | 32000-070 | 14F010400000 | DPole Mayaguez Grp. 14 | Closed | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-08-23 08:00 | 2022-08-23 08:00 | 2023-01-27 17:00 | 2023-01-27 | 2023-03-02 12:24
PBUT30 - D Pole & Conductor Repa | 11277 | 688629 | 32000-071 | 32000-071 | 14F010410000 | DPole Mayaguez Grp. 13 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-11-10 08:00 | 2022-11-10 08:00 | 2023-01-27 17:00 | 2023-01-27 | 2023-03-08 12:36
PBUT30 - D Pole & Conductor Repa | 11273 | 688630 | 32000-072 | 32000-072 | 14F010420000 | DPole Mayaguez Grp. 12 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-11-04 08:00 | 2022-11-04 08:00 | 2023-01-20 17:00 | 2023-01-20 | 2023-03-08 12:36
PBUT30 - D Pole & Conductor Repa | 11217 | 688472 | 32000-073 | 32000-073 | 14F010430000 | DPole Mayaguez Grp. 11 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-11-04 08:00 | 2022-11-04 08:00 | 2022-12-21 17:00 | 2022-12-21 | 2023-02-16 12:51
PBUT30 - D Pole & Conductor Repa | 11214 | 688096 | 32000-075 | 32000-075 | 14F010440000 | DPole Caguas Grp. 15 | Closed | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-11-07 08:00 | 2022-11-07 08:00 | 2022-12-20 08:00 | 2022-12-20 | 2023-01-31 12:56
PBUT30 - D Pole & Conductor Repa | 11268 | 701504 | 32000-079 | 32000-079 | 14F010450000 | DPole Arecibo Grp. 12 | Inactive | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-12-30 08:00 | 2022-12-30 08:00 | 2023-01-27 17:00 | 2023-01-27 | 2023-03-08 12:36
PBUT30 - D Pole & Conductor Repa | 11256 | 689071 | 32000-078 | 32000-078 | 14F010460000 | DPole Arecibo Grp. 11 | Inactive | Inactive |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-11-04 08:00 | 2022-11-04 08:00 | 2023-01-27 17:00 | 2023-01-27 | 2023-03-02 12:24
PBUT30 - D Pole & Conductor Repa | 11276 | 688198 | 32000-077 | 32000-077 | 14F010470000 | DPole Arecibo Grp. 10 | Closed | Inactive |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-11-08 08:00 | 2022-11-08 08:00 | 2023-01-20 17:00 | 2023-01-20 | 2023-03-20 11:45
PBUT30 - D Pole & Conductor Repa | 11193 | 688627 | 32000-076 | 32000-076 | 14F010480000 | DPole Arecibo Grp. 9 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-11-04 08:00 | 2022-11-04 08:00 | 2022-12-20 17:00 | 2022-12-20 | 2023-01-31 12:56
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F010630000 | Feeder # 1530-08 (SAN JUAN) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30066 |  | 14F011510000 | Feeder # 8701-03 (CIALES) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30066 |  | 14F011520000 | Feeder # 8701-02 (CIALES) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30066 |  | 14F011530000 | Feeder # 9004-10 (VEGA BAJA) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30066 |  | 14F011540000 | Feeder # 8203-01 (ADJUNTAS) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30066 |  | 14F011550000 | Feeder # 8101-03 (UTUADO) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30066 |  | 14F011560000 | Feeder # 9201-02 (VEGA ALTA) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30066 |  | 14F011570000 | Feeder # 8005-01 (ARECIBO) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30067 |  | 14F011580000 | Feeder # 1909-09 (GUAYNABO) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30067 |  | 14F011590000 | Feeder # 1713-05 (TOA BAJA) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30067 |  | 14F011600000 | Feeder # 9202-04 (DORADO) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30067 |  | 14F011610000 | Feeder # 9501-02 (COROZAL) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30067 |  | 14F011620000 | Feeder # 1719-15 (BAYAMÓN) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30067 |  | 14F011630000 | Feeder # 1711-05 (BAYAMÓN) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30067 |  | 14F011640000 | Feeder # 1717-01 (TOA BAJA) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30067 |  | 14F011650000 | Feeder # 9503-06 (COROZAL) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30067 |  | 14F011660000 | Feeder # 1717-03 (BAYAMÓN) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30067 |  | 14F011670000 | Feeder # 1720-07 (BAYAMÓN) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30067 |  | 14F011680000 | Feeder # 1710-01 (BAYAMÓN) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30067 |  | 14F011690000 | Feeder # 1801-03 (CATAÑO) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30067 |  | 14F011700000 | Feeder # 1806-02 (TOA BAJA) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30063 |  | 14F011710000 | Feeder # 9703-03 (COMERÍO) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30063 |  | 14F011720000 | Feeder # 3014-02 (CAGUAS) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30063 |  | 14F011730000 | Feeder # 3014-03 (CAGUAS) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30063 |  | 14F011740000 | Feeder # 9605-02(BARRANQUITAS) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30063 |  | 14F011750000 | Feeder # 3301-01 (SAN LORENZO) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30063 |  | 14F011760000 | Feeder # 2906-02 (YABUCOA) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30063 |  | 14F011770000 | Feeder # 2901-04 (YABUCOA) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30063 |  | 14F011780000 | Feeder # 2601-01 (HUMACAO) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30063 |  | 14F011790000 | Feeder # 3701-02(AGUAS BUENAS) | Cancel
PBUT30 - D Pole & Conductor Repa |  |  | 30063 |  | 14F011800000 | Feeder # 9902-01 (OROCOVIS) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30063 |  | 14F011810000 | Feeder # 3102-01 (GURABO) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30063 |  | 14F011820000 | Feeder # 3007-03 (CAGUAS) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30063 |  | 14F011830000 | Feeder # 2605-01 (HUMACAO) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30063 |  | 14F011840000 | Feeder # 2901-03 (YABUCOA) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30063 |  | 14F011850000 | Feeder # 3601-02 (CIDRA) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30063 |  | 14F011860000 | Feeder # 3602-01 (CIDRA) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30063 |  | 14F011870000 | Feeder # 2604-03 (HUMACAO) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30063 |  | 14F011880000 | Feeder # 3405-03 (CAYEY) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30063 |  | 14F011890000 | Feeder # 2603-08 (LAS PIEDRAS) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30063 |  | 14F011900000 | Feeder # 2901-01 (YABUCOA) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30063 |  | 14F011910000 | Feeder # 3701-03(AGUAS BUENAS) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30063 |  | 14F011920000 | Feeder # 2702-01 (NAGUABO) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30065 |  | 14F011930000 | Feeder # 6010-03 (MAYAGÜEZ) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30065 |  | 14F011940000 | Feeder # 6802-04 (HORMIGUEROS) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30065 |  | 14F011950000 | Feeder #7805-13(SAN SEBASTIÁN) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F011960000 | Feeder # 1102-04 (SAN JUAN) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30065 |  | 14F011970000 | Feeder # 6012-02 (MAYAGÜEZ) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30065 |  | 14F011980000 | Feeder #7805-11(SAN SEBASTIÁN) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30065 |  | 14F011990000 | Feeder # 6306-02 (MARICAO) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30065 |  | 14F012000000 | Feeder # 7011-03 (AGUADILLA) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30065 |  | 14F012010000 | Feeder # 6101-04 (AÑASCO) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30065 |  | 14F012020000 | Feeder # 7201-05 (AGUADA) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30065 |  | 14F012030000 | Feeder # 7008-04 (AGUADILLA) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30065 |  | 14F012040000 | Feeder # 7303-01 (RINCÓN) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30065 |  | 14F012050000 | Feeder # 6015-02 (MAYAGÜEZ) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30065 |  | 14F012060000 | Feeder # 7008-05 (AGUADILLA) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30065 |  | 14F012070000 | Feeder # 7104-05 (MOCA) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30063 |  | 14F012080000 | Feeder # 3406-01 (CAYEY) | Inactive
PBUT30 - D Pole & Conductor Repa | 4218 | 744420 | 30064 |  | 14F012090000 | Feeder # 6501-03 (SAB GRANDE) | Inactive |  |  |  | Active | Phase 3 - Scoping and Costing | Pending FEMA 406 HMP Completion
PBUT30 - D Pole & Conductor Repa |  |  | 30064 |  | 14F012100000 | Feeder # 6601-02 (LAJAS) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30064 |  | 14F012110000 | Feeder # 6601-01 (LAJAS) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30064 |  | 14F012120000 | Feeder # 5004-09 (PONCE) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30064 |  | 14F012130000 | Feeder # 5004-08 (PONCE) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30064 |  | 14F012140000 | Feeder # 5004-10 (PONCE) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30064 |  | 14F012150000 | Feeder # 5016-01 (PONCE) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30064 |  | 14F012160000 | Feeder # 4603-02 (COAMO) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F012170000 | Feeder # 1908-03 (SAN JUAN) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F012180000 | Feeder #1204-05(TRUJILLO ALTO) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F012190000 | Feeder #1204-02(TRUJILLO ALTO) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F012200000 | Feeder #1204-03(TRUJILLO ALTO) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F012210000 | Feeder # 1336-08 (SAN JUAN) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F012220000 | Feeder # 2404-06 (CANÓVANAS) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F012230000 | Feeder # 1336-07 (SAN JUAN) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F012240000 | Feeder # 2402-02 (CANÓVANAS) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F012250000 | Feeder #1204-04(TRUJILLO ALTO) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F012260000 | Feeder # 2306-01 (RÍO GRANDE) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F012270000 | Feeder # 1118-08 (SAN JUAN) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F012280000 | Feeder # 2305-03 (RÍO GRANDE) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F012290000 | Feeder # 1529-15 (SAN JUAN) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F012300000 | Feeder # 1346-04 (SAN JUAN) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F012310000 | Feeder # 1118-09 (SAN JUAN) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F012320000 | Feeder # 1529-11 (SAN JUAN) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F012330000 | Feeder #1206-03(TRUJILLO ALTO) | Inactive
PBUT30 - D Pole & Conductor Repa | 11312 | 704916 | 32000-089 | 32000-089 | 14F013920000 | DPole Arecibo Grp. 13-to-16 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2023-01-25 08:00 | 2023-01-25 08:00 | 2023-02-28 17:00 | 2023-02-28 | 2023-04-06 11:12
PBUT30 - D Pole & Conductor Repa | 11314 | 704750 | 32000-087 | 32000-087 | 14F013930000 | DPole Bayamon Grp. 10 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2023-02-02 17:00 | 2023-02-02 17:00 | 2023-02-28 08:00 | 2023-02-28 | 2023-04-06 11:12
PBUT30 - D Pole & Conductor Repa | 11311 | 704751 | 32000-088 | 32000-088 | 14F013940000 | DPole Bayamon Grp. 11 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2023-02-07 08:00 | 2023-02-07 08:00 | 2023-03-01 08:00 | 2023-03-01 | 2023-04-06 11:12
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F014160000 | Feeder # 1336-09 (SAN JUAN) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F014170000 | Feeder #1206-04(TRUJILLO ALTO) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F014180000 | Feeder # 1401-08 (SAN JUAN) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F014190000 | Feeder # 1531-05 (SAN JUAN) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F014200000 | Feeder # 1119-04 (SAN JUAN) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F014210000 | Feeder # 1338-02 (SAN JUAN) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F014220000 | Feeder # 1521-01 (SAN JUAN) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F014230000 | Feeder # 1619-02 (CAROLINA) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F014240000 | Feeder # 1118-10 (SAN JUAN) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F014250000 | Feeder # 1346-06 (SAN JUAN) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F014260000 | Feeder # 1303-01 (SAN JUAN) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F014270000 | Feeder # 1421-01 (SAN JUAN) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F014280000 | Feeder # 1346-05 (SAN JUAN) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F014290000 | Feeder # 1401-06 (SAN JUAN) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F014300000 | Feeder # 1119-02 (SAN JUAN) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F014310000 | Feeder # 1520-04 (SAN JUAN) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F014320000 | Feeder # 1525-02 (SAN JUAN) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F014330000 | Feeder # 1658-13 (CAROLINA) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F014340000 | Feeder # 1348-06 (SAN JUAN) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F014350000 | Feeder # 2305-04 (RÍO GRANDE) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F014360000 | Feeder # 1416-04 (SAN JUAN) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F014370000 | Feeder # 1342-02 (SAN JUAN) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F014380000 | Feeder # 1520-01 (SAN JUAN) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F014390000 | Feeder # 1422-05 (SAN JUAN) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F014400000 | Feeder # 1105-01 (SAN JUAN) | Inactive
PBUT30 - D Pole & Conductor Repa | 11476 | 705503 | 32000-080 | 32000-080 | 14F014410000 | DPole Mayaguez Grp. 15-to-19 | Active | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2023-02-28 08:00 | 2023-02-28 08:00 | 2025-12-31 17:00 | 2023-06-21
PBUT30 - D Pole & Conductor Repa | 11365 | 705584 | 32000-081 | 32000-081 | 14F014420000 | DPole Ponce Grp. 14-15 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2023-02-14 08:00 | 2023-02-14 08:00 | 2023-04-19 08:00 | 2023-04-19 | 2023-06-16 12:55
PBUT30 - D Pole & Conductor Repa | 11449 | 705527 | 32000-082 | 32000-082 | 14F014430000 | DPole San Juan Grp. 17-to-21 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2023-02-13 08:00 | 2023-02-13 08:00 | 2023-04-13 08:00 | 2023-04-13 | 2023-07-28 11:42
PBUT30 - D Pole & Conductor Repa | 11352 | 704755 | 32000-083 | 32000-083 | 14F014440000 | DPole Bayamon Grp. 12-13-14 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2023-02-21 08:00 | 2023-02-21 08:00 | 2023-03-31 08:00 | 2023-03-31 | 2023-05-17 11:31
PBUT30 - D Pole & Conductor Repa | 11340 | 704844 | 32000-084 | 32000-084 | 14F014450000 | DPole Caguas Grp. 16-to-20 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2023-02-09 08:00 | 2023-02-09 08:00 | 2023-03-31 17:00 | 2023-03-31 | 2023-05-17 11:31
PBUT30 - D Pole & Conductor Repa | 11465 | 704933 | 32000-085 | 32000-085 | 14F014460000 | DPole San Juan Grp. 13-to-16 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2023-02-09 08:00 | 2023-02-09 08:00 | 2023-03-31 08:00 | 2023-03-31 | 2023-08-04 19:29
PBUT30 - D Pole & Conductor Repa | 11508 | 708579 | 32000-086 | 32000-086 | 14F014730000 | DPole Ponce Grp. 16-to-19 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2023-03-22 08:00 | 2023-03-22 08:00 | 2023-06-28 08:00 | 2023-06-28 | 2023-10-23 11:32
PBUT30 - D Pole & Conductor Repa |  |  | 30065 |  | 14F014830000 | Feeder # 7901-02 (Lares) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30065 |  | 14F014840000 | Feeder # 6001-05 (Mayaguez) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30065 |  | 14F014850000 | Feeder # 7002-03 (Aguadilla) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30065 |  | 14F014860000 | Feeder # 7005-03 (Aguadilla) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30065 |  | 14F014870000 | Feeder # 7901-01 (Lares) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30065 |  | 14F014880000 | Feeder # 6201-01 (Las Marias) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30067 |  | 14F014890000 | Fiona DistLnRecon Bayamon Ldwn | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30063 |  | 14F014900000 | Fiona DistLnRecon Caguas Ldwn | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30064 |  | 14F014910000 | Fiona DistLnRecon Ponce Ldwn | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30066 |  | 14F014920000 | Fiona DistLnRecon Arecibo Ldwn | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30065 |  | 14F014930000 | Fiona DistLnRecon MayaguezLdwn | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F014940000 | Fiona DistLnRecon San JuanLdwn | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F014950000 | Feeder # 1646-05(Sabana Llana) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F014960000 | Feeder # 1646-01(Sabana Llana) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F014970000 | Feeder # 1646-02(Sabana Llana) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F014980000 | Feeder # 1646-03(Sabana Llana) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30066 |  | 14F015800000 | Feeder # 8404-03 (VEGA BAJA) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30066 |  | 14F015810000 | Feeder # 8405-03 (VEGA BAJA) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30066 |  | 14F015820000 | Feeder # 7403-02 (ARECIBO) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30066 |  | 14F015830000 | Feeder # 8301-03 (UTUADO) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30066 |  | 14F015840000 | Feeder # 9003-05 (VEGA BAJA) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30066 |  | 14F015850000 | Feeder # 8010-01 (ARECIBO) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30066 |  | 14F015860000 | Feeder # 8801-02 (VEGA BAJA) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30067 |  | 14F015870000 | Feeder # 9203-03 (BAYAMON) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30067 |  | 14F015880000 | Feeder # 9203-02 (BAYAMON) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30067 |  | 14F015890000 | Feeder # 9501-01 (BAYAMON) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30067 |  | 14F015900000 | Feeder # 1711-04 (BAYAMON) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30067 |  | 14F015910000 | Feeder # 9207-08 (BAYAMON) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30067 |  | 14F015920000 | Feeder # 1907-04 (BAYAMON) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30067 |  | 14F015930000 | Feeder # 1719-18 (BAYAMON) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30067 |  | 14F015940000 | Feeder # 1708-03 (BAYAMON) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30067 |  | 14F015950000 | Feeder # 1716-03 (BAYAMON) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30067 |  | 14F015960000 | Feeder # 1710-03 (BAYAMON) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30067 |  | 14F015970000 | Feeder # 1709-02 (BAYAMON) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30063 |  | 14F015980000 | Feeder # 2603-09 (HUMACAO) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30063 |  | 14F015990000 | Feeder # 2604-01 (HUMACAO) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30063 |  | 14F016000000 | Feeder # 3205-07 (CAGUAS) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30063 |  | 14F016010000 | Feeder # 2803-02 (HUMACAO) | Active
PBUT30 - D Pole & Conductor Repa |  |  | 30063 |  | 14F016020000 | Feeder # 3205-09 (CAGUAS) | Active
PBUT30 - D Pole & Conductor Repa |  |  | 30063 |  | 14F016030000 | Feeder # 3302-02 (CAGUAS) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30063 |  | 14F016040000 | Feeder # 3103-04 (CAGUAS) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30063 |  | 14F016050000 | Feeder # 3009-04 (CAGUAS) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30063 |  | 14F016060000 | Feeder# 3601-04(BARRANQUITAS) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30063 |  | 14F016070000 | Feeder # 3101-04 (CAGUAS) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30063 |  | 14F016080000 | Feeder # 2801-03 (HUMACAO) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30063 |  | 14F016090000 | Feeder # 3201-02 (CAGUAS) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30063 |  | 14F016100000 | Feeder # 3301-02 (CAGUAS) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30063 |  | 14F016110000 | Feeder # 3006-05 (CAGUAS) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30063 |  | 14F016120000 | Feeder# 9602-04(BARRANQUITAS) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30065 |  | 14F016130000 | Feeder # 6004-02 (MAYAGUEZ) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30065 |  | 14F016140000 | Feeder # 7901-03 (AGUADILLA) | Inactive
PBUT30 - D Pole & Conductor Repa | 4219 | 744422 | 30065 |  | 14F016150000 | Feeder # 6406-04 (MAYAGUEZ) | Inactive |  |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  |  | 2026-02-25 22:16
PBUT30 - D Pole & Conductor Repa |  |  | 30065 |  | 14F016160000 | Feeder # 7303-03 (AGUADILLA) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30065 |  | 14F016170000 | Feeder # 6801-02 (MAYAGUEZ) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30065 |  | 14F016180000 | Feeder # 6705-01 (MAYAGUEZ) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30065 |  | 14F016190000 | Feeder # 6702-02 (MAYAGUEZ) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30065 |  | 14F016200000 | Feeder # 6802-01 (MAYAGUEZ) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30065 |  | 14F016210000 | Feeder # 6008-04 (MAYAGUEZ) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30065 |  | 14F016220000 | Feeder # 7011-01 (AGUADILLA) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30065 |  | 14F016230000 | Feeder # 6305-02 (MAYAGUEZ) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30065 |  | 14F016240000 | Feeder # 6301-02 (MAYAGUEZ) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30065 |  | 14F016250000 | Feeder # 6802-02 (MAYAGUEZ) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30064 |  | 14F016260000 | Feeder # 5602-01 (YAUCO) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30064 |  | 14F016270000 | Feeder # 5302-04 (YAUCO) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30064 |  | 14F016280000 | Feeder # 5901-03 (PONCE) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F016290000 | Feeder # 1346-03 (SAN JUAN) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F016300000 | Feeder # 1348-08 (SAN JUAN) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F016310000 | Feeder # 1115-05 (SAN JUAN) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F016320000 | Feeder # 1346-02 (SAN JUAN) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F016330000 | Feeder # 1112-04 (SAN JUAN) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F016340000 | Feeder # 2305-02 (CANÓVANAS) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F016350000 | Feeder # 1116-03 (SAN JUAN) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F016360000 | Feeder # 1303-02 (SAN JUAN) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F016370000 | Feeder # 2404-05 (CANOVANAS) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F016380000 | Feeder # 1100-01 (SAN JUAN) | Inactive
PBUT30 - D Pole & Conductor Repa | 107851 | 710498 | 32000-090 | 32000-090 | 14F016490000 | DPole Bayamon Grp. 16 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2024-07-15 08:00 |  | 2024-10-14 17:00
PBUT30 - D Pole & Conductor Repa | 107850 | 710363 | 32000-091 | 32000-091 | 14F016500000 | DPole Bayamon Grp. 15 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2025-01-17 17:00
PBUT30 - D Pole & Conductor Repa | 11666 | 712968 | 32000-092 | 32000-092 | 14F016510000 | DPole Arecibo Grp. 2 -Ph. 2 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2023-07-31 08:00 | 2023-07-31 08:00 | 2023-10-31 17:00 | 2023-11-01 | 2024-11-01 15:15
PBUT30 - D Pole & Conductor Repa | 107848 | 710026 | 32000-093 | 32000-093 | 14F016520000 | DPole Arecibo Grp. 17 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2025-01-27 17:00
PBUT30 - D Pole & Conductor Repa | 11667 | 710099 | 32000-094 | 32000-094 | 14F016530000 | DPole Arecibo Grp. 1 -Ph. 2 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2023-08-25 08:00 | 2023-08-25 08:00 | 2023-10-02 17:00 | 2023-10-05 | 2025-01-07 23:15
PBUT30 - D Pole & Conductor Repa | 107849 | 710045 | 32000-095 | 32000-095 | 14F016540000 | DPole Mayaguez Grp. 20 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2025-05-13 17:00
PBUT30 - D Pole & Conductor Repa | 11534 | 710110 | 32000-101 | 32000-101 | 14F016550000 | DPole Bayamon Grp. 2 -Ph. 2 | Closed | Inactive |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2023-07-14 08:00 | 2023-07-14 08:00 | 2023-08-22 17:00 | 2023-08-22 | 2023-10-23 11:32
PBUT30 - D Pole & Conductor Repa | 107859 | 711962 | 32000-097 | 32000-097 | 14F016950000 | DPole Mayaguez Grp. 21 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2025-08-27 17:00
PBUT30 - D Pole & Conductor Repa | 107864 | 712981 | 32000-098 | 32000-098 | 14F016960000 | DPole Ponce Grp. 24 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2025-01-16 17:00
PBUT30 - D Pole & Conductor Repa | 11640 | 711888 | 32000-099 | 32000-099 | 14F016970000 | DPole Caguas Grp. 1 -Ph. 2 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2023-08-15 08:00 | 2023-08-15 08:00 | 2023-10-05 17:00 | 2023-10-05 | 2024-03-22 10:16
PBUT30 - D Pole & Conductor Repa | 11746 | 711856 | 32000-100 | 32000-100 | 14F016980000 | DPole Bayamon Grp. 3 -Ph. 2 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2023-09-21 08:00 | 2023-09-21 08:00 | 2023-12-01 17:00 | 2023-12-01 | 2024-08-26 10:08
PBUT30 - D Pole & Conductor Repa | 11639 | 710094 | 32000-104 | 32000-104 | 14F016990000 | DPole Bayamon Grp. 1 -Ph. 2 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2023-07-31 08:00 | 2023-07-31 08:00 | 2023-08-30 17:00 | 2023-09-06 | 2024-11-01 15:15
PBUT30 - D Pole & Conductor Repa | 107865 | 712982 | 32000-102 | 32000-102 | 14F017000000 | Dist Pole & Cond Rep Mayag G23 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2025-01-03 17:00
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F017020000 | Feeder # 5305-04 (Yauco) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F017030000 | Feeder # 5304-01 (Yauco) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30066 |  | 14F017040000 | Feeder # 8013-01 (HATILLO) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30066 |  | 14F017050000 | Feeder # 8101-04 (UTUADO) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30066 |  | 14F017060000 | Feeder # 8007-01 (ARECIBO) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30066 |  | 14F017070000 | Feeder # 9001-02 (VEGA BAJA) | Active
PBUT30 - D Pole & Conductor Repa |  |  | 30067 |  | 14F017080000 | Feeder # 1709-05 (GUAYNABO) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30067 |  | 14F017090000 | Feeder # 1718-02 (TOA BAJA) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30067 |  | 14F017100000 | Feeder # 1710-05 (BAYAMON) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30067 |  | 14F017110000 | Feeder # 1703-01 (BAYAMON) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30063 |  | 14F017120000 | Feeder # 3015-05 (CAGUAS) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30063 |  | 14F017130000 | Feeder # 3004-01 (CAGUAS) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30065 |  | 14F017140000 | Feeder # 7104-06 (MOCA) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30065 |  | 14F017150000 | Feeder # 6201-03 (LAS MARIAS) | Inactive
PBUT30 - D Pole & Conductor Repa | 4220 | 744429 | 30065 |  | 14F017160000 | Feeder # 6404-03 (SAN GERMAN) | Inactive |  |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  |  | 2026-02-25 22:16
PBUT30 - D Pole & Conductor Repa |  |  | 30065 |  | 14F017170000 | Feeder # 7103-04 (MOCA) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30064 |  | 14F017180000 | Feeder # 5301-01 (PONCE) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F017190000 | Feeder # 2201-02 (LUQUILLO) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F017200000 | Feeder # 2404-07 (CAROLINA) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F017210000 | Feeder # 1525-04 (SAN JUAN) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F017220000 | Feeder # 1652-04 (SAN JUAN) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F017230000 | Feeder # 1301-01 (SAN JUAN) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F017410000 | Feeder # 1100-05 (San Juan) | Closed
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F017430000 | Feeder # 2301-02 (RIO GRANDE) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30066 |  | 14F017440000 | Feeder # 8103-02 (UTUADO) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30066 |  | 14F017450000 | Feeder # 9101-04 (VEGA ALTA) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30066 |  | 14F017460000 | Feeder # 8404-04 (MANATI) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30067 |  | 14F017470000 | Feeder # 1907-05 (GUAYNABO) | Cancel
PBUT30 - D Pole & Conductor Repa |  |  | 30067 |  | 14F017480000 | Feeder # 1710-04 (BAYAMON) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30067 |  | 14F017490000 | Feeder # 1806-01 (TOA BAJA) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30063 |  | 14F017500000 | Feeder # 3103-05 (GURABO) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30063 |  | 14F017510000 | Feeder # 3006-02 (CAGUAS) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30063 |  | 14F017520000 | Feeder # 3302-03 (SAN LORENZO) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30064 |  | 14F017530000 | Feeder # 5602-03 (GUANICA) | Cancel
PBUT30 - D Pole & Conductor Repa |  |  | 30064 |  | 14F017540000 | Feeder # 4603-01 (COAMO) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30064 |  | 14F017550000 | Feeder # 5018-02 (PONCE) | Cancel
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F017560000 | Feeder # 1619-01 (CAROLINA) | Cancel
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F017570000 | Feeder # 1336-06 (SAN JUAN) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F017580000 | Feeder # 2302-01 (RIO GRANDE) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F017590000 | Feeder # 2006-03 (FAJARDO) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F017600000 | Feeder # 1205-02 TRUJILLO ALTO | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F017610000 | Feeder # 2002-03 (FAJARDO) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30063 |  | 14F018130000 | Feeder # 9902-02(BARRANQUITAS) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30063 |  | 14F018140000 | Feeder # 9901-02(BARRANQUITAS) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30063 |  | 14F018150000 | Feeder # 3604-07(BARRANQUITAS) | Cancel
PBUT30 - D Pole & Conductor Repa |  |  | 30063 |  | 14F018160000 | Feeder # 9601-02(BARRANQUITAS) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30067 |  | 14F018170000 | Feeder # 1901-01 (GUAYNABO) | Cancel
PBUT30 - D Pole & Conductor Repa |  |  | 30067 |  | 14F018180000 | Feeder # 1901-04 (GUAYNABO) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30067 |  | 14F018190000 | Feeder # 1909-08 (GUAYNABO) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30067 |  | 14F018200000 | Feeder # 1714-02 (BAYAMON) | Cancel
PBUT30 - D Pole & Conductor Repa |  |  | 30067 |  | 14F018210000 | Feeder # 9801-03 (TOA BAJA) | Cancel
PBUT30 - D Pole & Conductor Repa |  |  | 30067 |  | 14F018220000 | Feeder # 9405-05 (TOA BAJA) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30067 |  | 14F018230000 | Feeder # 9203-04 (TOA BAJA) | Cancel
PBUT30 - D Pole & Conductor Repa |  |  | 30067 |  | 14F018240000 | Feeder # 1806-03 (TOA BAJA) | Cancel
PBUT30 - D Pole & Conductor Repa |  |  | 30065 |  | 14F018250000 | Feeder # 7012-01 (AGUADILLA) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30065 |  | 14F018260000 | Feeder # 7902-03 (AGUADILLA) | Cancel
PBUT30 - D Pole & Conductor Repa |  |  | 30065 |  | 14F018270000 | Feeder # 7901-01 (AGUADILLA) | Cancel
PBUT30 - D Pole & Conductor Repa |  |  | 30065 |  | 14F018280000 | Feeder # 7301-02 (MAYAGUEZ) | Cancel
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F018290000 | Feeder # 1203-02 (SAN JUAN) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F018300000 | Feeder # 1117-11 (SAN JUAN) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F018310000 | Feeder # 1101-01 (SAN JUAN) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F018320000 | Feeder # 2005-09 (FAJARDO) | Cancel
PBUT30 - D Pole & Conductor Repa |  |  | 30062 |  | 14F018330000 | Feeder # 1607-03 (CANÓVANAS) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30064 |  | 14F018340000 | Feeder # 5401-04 (YAUCO) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30064 |  | 14F018350000 | Feeder # 5501-02 (YAUCO) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30064 |  | 14F018360000 | Feeder # 5303-02 (YAUCO) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30064 |  | 14F018370000 | Feeder # 5018-05 (PONCE) | Cancel
PBUT30 - D Pole & Conductor Repa |  |  | 30064 |  | 14F018380000 | Feeder # 5501-03 (GUAYANILLA) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30066 |  | 14F018390000 | Feeder # 8015-09 (ARECIBO) | Cancel
PBUT30 - D Pole & Conductor Repa |  |  | 30066 |  | 14F018400000 | Feeder # 8010-02 (ARECIBO) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30066 |  | 14F018410000 | Feeder # 8013-02 (ARECIBO) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 30066 |  | 14F018420000 | Feeder # 8602-03 (FLORIDA) | Cancel
PBUT30 - D Pole & Conductor Repa |  |  | 30066 |  | 14F018430000 | Feeder # 8801-04 (MOROVIS) | Cancel
PBUT30 - D Pole & Conductor Repa |  |  | 30066 |  | 14F018440000 | Feeder # 8504-03 (BARCELONETA) | Cancel
PBUT30 - D Pole & Conductor Repa | 11812 | 738971 | 32000-105 | 32000-105 | 14F018490000 | Dpole Caguas Grp. 2 -Ph. 2 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2023-11-21 08:00 | 2023-11-21 08:00 | 2024-02-06 08:00 | 2024-02-06 | 2025-02-06 20:16
PBUT30 - D Pole & Conductor Repa | 107918 | 735474 | 32000-106 | 32000-106 | 14F018500000 | Dpole Caguas Grp. 3 -Ph 2 | Active | Active |  |  | Active |  | Pending Amendment Processing | 2024-06-28 08:00 | 2024-06-28 08:00 | 2025-01-31 08:00 | 2025-01-31 | 2025-09-17 18:16
PBUT30 - D Pole & Conductor Repa | 11686 | 738672 | 32000-123 | 32000-123 | 14F018870000 | DistPole&CondRepairMayagG1Ph2 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2023-09-22 08:00 | 2023-09-22 08:00 | 2023-12-04 17:00 | 2023-12-04 | 2024-11-25 16:15
PBUT30 - D Pole & Conductor Repa | 108071 | 790446 | 32000-107 | 32000-107 | 14F018880000 | DPole Caguas Group 4 Ph 2 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2024-07-05 08:00 | 2024-07-05 08:00 | 2025-07-10 08:00 | 2025-07-10
PBUT30 - D Pole & Conductor Repa | 108069 | 790427 | 32000-108 | 32000-108 | 14F018890000 | DPole Caguas Group 5 Ph 2 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2024-09-11 08:00 | 2024-09-11 08:00 | 2025-07-10 08:00 | 2025-07-10
PBUT30 - D Pole & Conductor Repa | 108097 | 806935 | 32000-109 | 32000-109 | 14F018900000 | DPole Caguas Group 6 Ph 2 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2024-10-04 08:00 | 2024-10-04 08:00 | 2025-12-31 08:00
PBUT30 - D Pole & Conductor Repa | 108116 | 817249 | 32000-110 | 32000-110 | 14F018910000 | DPole Caguas Group 7 Ph 2 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2024-11-11 11:00 | 2024-11-11 11:00 | 2026-01-15 08:00
PBUT30 - D Pole & Conductor Repa | 108113 | 817242 | 32000-111 | 32000-111 | 14F018920000 | DPole Caguas Group 8 Ph 2 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2024-11-11 08:00 | 2024-11-11 08:00 | 2025-12-31 08:00
PBUT30 - D Pole & Conductor Repa | 107929 | 738692 | 32000-112 | 32000-112 | 14F018930000 | DPole Carolina Group 1 Ph 2 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2024-12-11 08:00 | 2024-12-11 08:00 | 2025-12-30 08:00
PBUT30 - D Pole & Conductor Repa | 11850 | 738120 | 32000-113 | 32000-113 | 14F018940000 | DPole Carolina Group 2 Ph 2 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2023-12-19 08:00 | 2023-12-19 08:00 | 2024-05-24 17:00 | 2024-05-24 | 2024-11-25 16:15
PBUT30 - D Pole & Conductor Repa | 108098 | 806936 | 32000-114 | 32000-114 | 14F018950000 | DPole Carolina Group 3 Ph 2 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2024-12-27 08:00 | 2024-12-27 08:00 | 2025-12-30 08:00
PBUT30 - D Pole & Conductor Repa | 107928 | 738674 | 32000-115 | 32000-115 | 14F018960000 | DPole Mayaguez Group 2 Ph 2 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2024-01-23 08:00 | 2024-01-23 08:00 | 2024-07-02 17:00 | 2024-07-03
PBUT30 - D Pole & Conductor Repa | 107979 | 750692 | 32000-116 | 32000-116 | 14F018970000 | DPole Mayaguez Group 3 Ph 2 | Active | Active |  |  | Active |  | Pending Amendment Processing | 2024-05-31 08:00 | 2024-05-31 08:00 | 2025-01-31 08:00 | 2025-01-31 | 2025-09-25 16:15
PBUT30 - D Pole & Conductor Repa | 107999 | 752540 | 32000-117 | 32000-117 | 14F018980000 | DPole Mayaguez Group 4 Ph 2 | Active | Active |  |  | Active |  | Pending Amendment Processing | 2024-07-31 08:00 | 2024-07-31 08:00 | 2025-01-31 08:00 | 2025-01-31 | 2025-09-25 16:15
PBUT30 - D Pole & Conductor Repa | 11712 | 738670 | 32000-118 | 32000-118 | 14F018990000 | DPole Ponce Group 1 Ph2 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2023-09-26 08:00 | 2023-09-26 08:00 | 2024-01-19 17:00 | 2024-01-19 | 2024-11-25 16:15
PBUT30 - D Pole & Conductor Repa | 107927 | 738667 | 32000-119 | 32000-119 | 14F019000000 | DPole Ponce Group 2 Ph2 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2024-03-04 08:00 | 2024-03-04 08:00 | 2024-07-15 08:00 | 2024-07-15
PBUT30 - D Pole & Conductor Repa | 11753 | 742070 | 32000-120 | 32000-120 | 14F019010000 | DPole San Juan Group 1 Ph 2 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2023-10-25 08:00 | 2023-10-25 08:00 | 2024-01-05 17:00 | 2024-01-05 | 2024-06-18 11:28
PBUT30 - D Pole & Conductor Repa | 11716 | 742026 | 32000-121 | 32000-121 | 14F019020000 | DPole San Juan Group 2 Ph 2 | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2023-09-22 08:00 | 2023-09-22 08:00 | 2023-12-26 17:00 | 2024-01-04 | 2024-05-31 11:36
PBUT30 - D Pole & Conductor Repa | 108070 | 790443 | 32000-122 | 32000-122 | 14F019030000 | DPole San Juan Group 3 Ph 2 | Active | Active |  |  | Active | Phase 4 - Final Field Reviews | Pending Final FEMA Review | 2024-10-01 08:00 | 2024-10-01 08:00 | 2025-01-31 08:00 | 2025-03-28 | 2025-09-03 20:15
PBUT30 - D Pole & Conductor Repa | 108042 | 757945 |  |  | 14F020460000 | Dist.Pole&Cond.Rep.Are.Grp3Ph2 | Inactive |  | CAP1 | ISSUE | Withdrawn | Discontinued | Process Discontinued |  |  |  | 2025-07-10
PBUT30 - D Pole & Conductor Repa | 108045 | 759004 | 32000-127 | 32000-127 | 14F021390000 | Dpole&Cond.Rep.-Arec.Grp4Phs2 | Inactive | Inactive | CAP1 | ISSUE | Withdrawn | Discontinued | Process Discontinued | 2025-01-21 08:00 | 2025-01-21 08:00 | 2025-12-30 17:00
PBUT30 - D Pole & Conductor Repa |  |  | 32000-124 | 32000-124 | 14F021400000 | Dpole&Cond.Rep.-Mayag.Grp5Phs2 | Inactive | Inactive | CAP1 |  |  |  |  | 2025-03-05 08:00 | 2025-03-05 08:00 | 2026-03-02 08:00
PBUT30 - D Pole & Conductor Repa | 108046 | 759051 | 32000-126 | 32000-126 | 14F021410000 | Dpole&Cond.Rep.-Baya.Grp4Phs2 | Inactive | Inactive | CAP1 | WARNING | Withdrawn | Discontinued | Process Discontinued | 2025-01-21 08:00 | 2025-01-21 08:00 | 2025-10-29 17:00
PBUT30 - D Pole & Conductor Repa | 108117 | 817250 | 32000-125 | 32000-125 | 14F021420000 | Dpole&Cond.Rep.-SJ.Grp4Phs2 | Inactive | Inactive | CAP1 | ISSUE | Withdrawn | Discontinued | Process Discontinued | 2025-01-21 08:00 | 2025-01-21 08:00 | 2025-12-30 08:00
PBUT30 - D Pole & Conductor Repa | 108114 | 817247 | 32000-128 | 32000-128 | 14F021430000 | Dpole&Cond.Rep.-Pnce.Grp3Phs2 | Inactive | Inactive | CAP1 | ISSUE | Withdrawn | Discontinued | Process Discontinued | 2025-01-21 08:00 | 2025-01-21 08:00 | 2025-12-30 17:00
PBUT30 - D Pole & Conductor Repa |  |  | 32000-129 | 32000-129 | 14F021710000 | DPole Arecibo 18-21 Phase 3 | Inactive | Inactive | CAP1 |  |  |  |  | 2025-03-27 08:00 | 2025-03-27 08:00 | 2026-03-02 08:00
PBUT30 - D Pole & Conductor Repa |  |  | 32000-130 | 32000-130 | 14F021720000 | DPole Bayamon 17-25 Phase 3 | Active | Active | CAP1 | ISSUE |  |  |  | 2025-05-31 08:37 | 2025-05-31 08:37 | 2026-04-10 17:00
PBUT30 - D Pole & Conductor Repa |  |  | 32000-131 | 32000-131 | 14F021730000 | DPole Caguas 21-25 Phase 3 | Inactive | Inactive | CAP1 | ISSUE |  |  |  | 2025-05-31 08:37 | 2025-05-31 08:37 | 2026-03-02 17:00
PBUT30 - D Pole & Conductor Repa |  |  | 32000-132 | 32000-132 | 14F021740000 | DPole Mayaguez 24-27 Phase 3 | Inactive | Inactive | CAP1 | ISSUE |  |  |  | 2025-06-30 08:00 | 2025-06-30 08:00 | 2026-03-02 17:00
PBUT30 - D Pole & Conductor Repa |  |  | 32000-133 | 32000-133 | 14F021750000 | DPole Ponce 20-28 Phase 3 | Inactive | Inactive | CAP1 |  |  |  |  | 2025-06-30 08:00 | 2025-06-30 08:00 | 2026-03-02 17:00
PBUT30 - D Pole & Conductor Repa |  |  | 32000-134 | 32000-134 | 14F021760000 | DPole San Juan 22-29 Phase 3 | Inactive | Inactive | CAP1 | ISSUE |  |  |  | 2025-07-10 08:00 | 2025-07-10 08:00 | 2026-03-02 17:00
PBUT30 - D Pole & Conductor Repa |  |  | 32000-135 | 32000-135 | 14F021770000 | DPole San Juan 30-39 Phase 3 | Inactive | Inactive | CAP1 | ISSUE |  |  |  | 2025-05-06 17:00 | 2025-05-06 17:00 | 2026-07-30 08:00
PBUT30 - D Pole & Conductor Repa |  |  | 32000-136 | 32000-136 | 14F021780000 | DPole San Juan 40-54 Phase 3 | Inactive | Inactive | CAP1 |  |  |  |  | 2025-05-07 08:00 | 2025-05-07 08:00 | 2026-08-01 23:57
PBUT30 - D Pole & Conductor Repa |  |  | 32000 | 32000 | 14N000230000 | Dist Pole & Conductor Repair | Inactive | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 32000 | 32000 | 14N000790000 | DistPole&ConducRep-AreciboGRp3 | Cancel | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 32000 | 32000 | 14N000800000 | DistPole&ConducRep-BayamGRp4 | Cancel | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 32000 | 32000 | 14N000810000 | DistPole&ConducRep-CaguasGRp9 | Cancel | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 32000 | 32000 | 14N000820000 | DistPole&ConducRep-MayaguGRp5 | Cancel | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 32000 | 32000 | 14N000830000 | DistPole&ConducRep-PonceGRp3 | Cancel | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 32000 | 32000 | 14N000840000 | DistPole&ConducRep-SanJuanGRp4 | Cancel | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 32000 | 32000 | 14N000850000 | DistPole&ConducRep-AreciboGRp4 | Cancel | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 32000 | 32000 | 14N000860000 | DistPole&ConducRep-BayamGRp5 | Cancel | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 32000 | 32000 | 14N000870000 | DistPole&ConducRep-CaguasGRp10 | Cancel | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 32000 | 32000 | 14N000880000 | DistPole&ConducRep-MayaguGRp6 | Cancel | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 32000 | 32000 | 14N000890000 | DistPole&ConducRep-PonceGRp4 | Cancel | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 32000 | 32000 | 14N000900000 | DistPole&ConducRep-SanJuanGRp5 | Cancel | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 32002 | 32002 | 14N000920000 | PRW-Distr.Pole.Repl.Mar-22-FWD | Active
PBUT30 - D Pole & Conductor Repa | 1294 | 83182 | 90102 | 90102 | 15F019630000 | Cat Z - PBUT30 | Active |  |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  |  | 2020-02-05 12:48
PBUT30 - D Pole & Conductor Repa |  |  | 90102 | 90102 | 15F019930000 | CAT Z - PBUT30 (Fiona) | Inactive
PBUT30 - D Pole & Conductor Repa |  |  | 32000 | 32000 | 15N000230000 | Distr. Pole & Cond. Repair-O&M | Inactive | Inactive
PBUT31 - Loss Recovery Program |  |  | 84000 | 84000 | 14N000340000 | Procu Rev Protect SoftwareTool | Cancel
PBUT31 - Loss Recovery Program |  |  | 84000 | 84000 | 14N000350000 | Procur TheftDetection Tool Set | Inactive
PBUT31 - Loss Recovery Program |  |  | 84000 | 84000 | 14N000360000 | EnhncmntRevProtecToolFieldEqui | Inactive
PBUT31 - Loss Recovery Program |  |  | 84000 | 84000 | 15N000910000 | Theft Detect Field Ins Com Ind | Active
PBUT31 - Loss Recovery Program |  |  | 84000 | 84000 | 15N001220000 | TheftDetectFieldInspResidentia | Active
PBUT31 - Loss Recovery Program |  |  | 80008 | 80008 | 15N003200000 | NTL (Commercial & Industrial) | Active
PBUT31 - Loss Recovery Program |  |  | 80008 | 80008 | 15N003210000 | NTL RedLosRecProg(Residential) | Active
PBUT32 - Assess.of Transm.Lines |  |  | 10218 | 10218 | 10N014040000 | DOE-Intelligence Enhan. P-7 | Inactive
PBUT32 - Assess.of Transm.Lines |  |  | 10130 | 10130 | 14F002550000 | Stage 3d Cathodic Protection | Inactive | Inactive | [7 empty] | 2021-09-24 17:00
PBUT32 - Assess.of Transm.Lines |  |  | 10130 | 10130 | 14F002560000 | Stage 2c Pole Inspection and | Inactive | Inactive | [7 empty] | 2021-09-24 17:00
PBUT32 - Assess.of Transm.Lines |  |  | 10130 | 10130 | 14F002570000 | Stage 3c Anchor and Guy Insp | Inactive | Inactive | [7 empty] | 2021-09-24 17:00
PBUT32 - Assess.of Transm.Lines |  |  | 10130 | 10130 | 14F002580000 | Stage 2d Xray Sleeves | Inactive | Inactive | [7 empty] | 2021-09-24 17:00
PBUT32 - Assess.of Transm.Lines |  |  | 10130 | 10130 | 14F002590000 | Trans Lines High Lvl Assesment | Active | Inactive | [7 empty] | 2021-09-24 17:00
PBUT32 - Assess.of Transm.Lines |  |  | 23000 | 23000 | 14F008460000 | Assesment UG 38 kV Trans Syst | Active | Inactive
PBUT32 - Assess.of Transm.Lines |  |  | 23152 | 23152 | 14F014580000 | Assesment UG Transmission Syst | Active | Active
PBUT32 - Assess.of Transm.Lines | 1294 | 83182 | 90102 | 90102 | 15F019820000 | CAT Z - PBUT32 | Active |  |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  |  | 2020-02-05 12:48
PBUT33 - T Line Rebuild |  |  | 10173 | 10173 | 10N000750000 | Line40600 Baymn-Monac(UG Loop) | Inactive | Inactive | [7 empty] | 2030-02-08 12:00
PBUT33 - T Line Rebuild |  |  | 10131 | 10131 | 10N011910000 | T-Pole 37500RBayaSect-MonaTC | Inactive | Active | [5 empty] | 2021-06-01 08:00 | 2022-04-20 17:00
PBUT33 - T Line Rebuild |  |  | 20014 | 20014-009 | 10N014760000 | DOE TL13100 | Inactive
PBUT33 - T Line Rebuild |  |  | 20014 | 20014 | 10N015450000 | DOE-TL 8700CostSurSP-Gar1HP | Active
PBUT33 - T Line Rebuild | 11453 | 180052 | 10052 | 10052 | 14F002170000 | Existing 38 kV Line 100 Ponce | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-06-13 08:00 | 2022-06-13 08:00 | 2022-07-08 17:00 | 2022-08-30 | 2025-11-05 16:17
PBUT33 - T Line Rebuild | 11453 | 180052 | 10052 | 10052 | 14F002180000 | Existing 38 kV Line 200 Ponce | Cancel | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-06-13 08:00 | 2022-06-13 08:00 | 2022-07-08 17:00 | 2022-08-30 | 2025-11-05 16:17
PBUT33 - T Line Rebuild | 11441 | 180326 | 10054 | 10054 | 14F002190000 | Existing 115kV Line 36800 Pa | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2022-08-30 17:00 | 2022-08-30
PBUT33 - T Line Rebuild | 11244 | 165213 | 10056 | 10056 | 14F002200000 | 5400 RIO BLANCO HP DAGUAO | Active | Active |  |  | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant | 2021-10-21 08:00 | 2021-10-21 08:00 | 2022-11-29 17:00 | 2022-11-29
PBUT33 - T Line Rebuild | 11431 | 166707 | 10057 | 10057 | 14F002210000 | 51300 PONCE COSTA SUR | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2022-11-29 17:00 | 2022-11-29
PBUT33 - T Line Rebuild | 11255 | 166860 | 10058 | 10058 | 14F002220000 | 37800 JOBOS - CAGUAS | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2022-08-30 17:00 | 2022-08-30
PBUT33 - T Line Rebuild | 11451 | 166904 | 10060 | 10060 | 14F002230000 | 37800 CAGUAS MONACILLOS | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2022-08-01 17:00 | 2022-08-01
PBUT33 - T Line Rebuild | 11246 | 167168 | 10062 | 10062 | 14F002240000 | 37100 COSTA SUR ACACIAS | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2022-09-01 08:00 | 2022-09-01
PBUT33 - T Line Rebuild | 11251 | 167443 | 10063 | 10063 | 14F002250000 | 36200 MONACILLOS JUNCOS | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2022-09-02 17:00 | 2022-09-02
PBUT33 - T Line Rebuild | 11307 | 167446 | 10064 | 10064 | 14F002260000 | 36100 DOS BOCAS MONACILLOS | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2021-10-13 08:00 | 2021-10-13 08:00 | 2023-06-30 17:00 | 2023-06-30 | 2025-11-05 16:17
PBUT33 - T Line Rebuild | 11250 | 167508 | 10065 | 10065 | 14F002270000 | 50100 CAMBALACHE MANATI | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2022-11-28 17:00 | 2022-11-28
PBUT33 - T Line Rebuild | 10978 | 168226 | 10066 | 10066 | 14F002280000 | 38000 SAN JUAN ISLA GRANDE | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2021-10-20 08:00 | 2021-10-20 08:00 | 2022-05-02 17:00 | 2022-05-02 | 2022-12-21 12:37
PBUT33 - T Line Rebuild | 11241 | 168483 | 10067 | 10067 | 14F002290000 | 36400 DOS BOCAS PONCE | Active | Active |  |  | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant | 2024-09-16 08:00 | 2024-09-16 08:00 | 2022-08-31 17:00 | 2022-08-29
PBUT33 - T Line Rebuild | 11432 | 176913 | 10068 | 10068 | 14F002300000 | 9500 PALO SECO SP CATANO S | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2021-10-05 08:00 | 2021-10-05 08:00 | 2022-08-02 08:00 | 2022-07-29 | 2025-11-05 16:17
PBUT33 - T Line Rebuild | 11439 | 176954 | 10069 | 10069 | 14F002310000 | 1100 GARZAS 1 HP GARZAS 2 | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2022-08-30 17:00 | 2022-08-29
PBUT33 - T Line Rebuild | 11373 | 176971 | 10070 | 10070 | 14F002320000 | 8200 SAN JUAN SP CATANO SE | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2022-01-19 08:00 | 2022-01-19 08:00 | 2022-07-29 17:00 | 2022-07-29 | 2025-11-05 16:17
PBUT33 - T Line Rebuild | 11440 | 177134 | 10071 | 10071 | 14F002330000 | 4100 GUARAGUO TC COMERIO T | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2022-12-08 17:00 | 2023-06-08
PBUT33 - T Line Rebuild | 11433 | 177191 | 10072 | 10072 | 14F002340000 | 39000 AGUAS BUENAS CAGUAS | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2021-10-12 08:00 | 2021-10-12 08:00 | 2022-09-09 17:00 | 2022-09-08
PBUT33 - T Line Rebuild | 11494 | 548598 | 10073 | 10073 | 14F002350000 | Existing 115 kV - Line 36200 F | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2022-09-02 17:00 | 2023-06-30
PBUT33 - T Line Rebuild | 107522 | 334469 | 10075 | 10075 | 14F002360000 | Existing 38 kV - Line 8900 Mon | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2025-07-22 17:00
PBUT33 - T Line Rebuild | 107689 | 547160 | 10076 | 10076 | 14F002370000 | Existing 38kV - Line 1200 May | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2029-09-17 17:00
PBUT33 - T Line Rebuild | 11559 | 730657 | 10077 | 10077 | 14F002380000 | Existing 38 kV - Line 2200 Dos | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2023-02-23 08:00 | 2023-02-23 08:00 | 2024-09-30 17:00
PBUT33 - T Line Rebuild | 11708 | 334470 | 10078 | 10078 | 14F002390000 | Existing 38 kV - Line 3100 Mon | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2023-09-01 08:00 | 2023-09-01 08:00 | 2024-09-20 08:00 | 2024-09-30 | 2025-11-05 16:17
PBUT33 - T Line Rebuild | 107981 | 750730 | 10079 | 10079 | 14F002400000 | Existing 38 kV - Line 500 Ponc | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2028-07-20 17:00
PBUT33 - T Line Rebuild | 108030 | 756997 | 10080 | 10080 | 14F002410000 | TL 1900 Caguanas to Lares TO | Active |  |  |  | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant |  |  |  | 2024-09-30
PBUT33 - T Line Rebuild | 11480 | 547259 | 10081 | 10081 | 14F002420000 | Existing 38 kV - Line 2700 Vic | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2024-01-12 17:00 | 2023-06-30
PBUT33 - T Line Rebuild | 11481 | 547269 | 10082 | 10082 | 14F002430000 | Existing 38 kV - Line 2800 Agu | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2024-10-29 17:00 | 2023-06-30
PBUT33 - T Line Rebuild | 11450 | 334482 | 10083 | 10083 | 14F002440000 | Existing 38 kV - Line 3000 Mon | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2028-12-11 17:00
PBUT33 - T Line Rebuild | 107692 | 547221 | 10084 | 10084 | 14F002450000 | Existing 38 kV - Line 3600 Mon | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2026-01-28 17:00
PBUT33 - T Line Rebuild | 11854 | 547350 | 10085 | 10085 | 14F002460000 | Existing 38 kV - Line 13300 Ba | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2028-01-07 12:00
PBUT33 - T Line Rebuild | 107710 | 550019 | 10086 | 10086 | 14F002470000 | Existing 38 kV - Line 600 Cagu | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2023-09-25 17:00 | 2023-09-25
PBUT33 - T Line Rebuild | 11807 | 547251 | 10087 | 10087 | 14F002480000 | Existing 38 kV - Line 2400 Dos | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated | 2023-07-03 08:00 | 2023-07-03 08:00 | 2025-07-01 17:00 | 2025-07-01 | 2026-02-20 19:15
PBUT33 - T Line Rebuild | 108008 | 753777 | 10088 | 10088 | 14F002490000 | Existing 38 kV - Line 1500 May | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2026-08-17 17:00
PBUT33 - T Line Rebuild | 107910 | 730784 | 10089 | 10089 | 14F002500000 | Existing 38 kV - Line 6700 Mar | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2026-10-19 17:00
PBUT33 - T Line Rebuild | 107712 | 550070 | 10090 | 10090 | 14F002510000 | Existing 38 kV - Line 4000 Com | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2029-05-15 17:00
PBUT33 - T Line Rebuild | 11434 | 551911 | 10091 | 10091 | 14F002520000 | Existing 38 kV - Line 9100 Gua | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2026-01-08 17:00
PBUT33 - T Line Rebuild | 11688 | 550902 | 10092 | 10092 | 14F002530000 | Existing 38 kV - Line 9700 Pal | Active | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2027-09-22 12:00
PBUT33 - T Line Rebuild | 11687 | 551067 | 10093 | 10093 | 14F002540000 | Existing 38 kV - Line 11100 Ca | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2026-04-06 17:00
PBUT33 - T Line Rebuild | 11689 | 547226 | 10094 | 10094 | 14F002680000 | Existing 38 kV - Line 11400 Ba | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2029-02-02 12:00
PBUT33 - T Line Rebuild |  |  | 10159 | 10159 | 14F003790000 | Distribution Line Rebu-PBUT33 | Active
PBUT33 - T Line Rebuild |  |  | 20006 | 20006 | 14F008470000 | UG Transmission SystemRepairs | Active
PBUT33 - T Line Rebuild | 107991 | 752052 | 10180 | 10180 | 14F015390000 | H Maria L9900 TAP9905A-RBlanco | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2027-10-07 12:00
PBUT33 - T Line Rebuild |  |  |  |  | 14F015400000 | H Maria L-9300 Juncos-ACB 9301 | Inactive
PBUT33 - T Line Rebuild |  |  |  |  | 14F015410000 | H Maria L-9300GBenitez-ACB9323 | Inactive
PBUT33 - T Line Rebuild |  |  | 10182 | 10182 | 14F015420000 | H MariaL700 Costa Sur-Yauco P | Inactive | Inactive | [7 empty] | 2026-09-15 17:00
PBUT33 - T Line Rebuild |  |  | 10183 | 10183 | 14F015430000 | H MariaL-5600 H Rincon-Sub7113 | Inactive | Inactive | [7 empty] | 2031-07-17 12:00
PBUT33 - T Line Rebuild |  |  | 10184 | 10184 | 14F015440000 | HMariaL3700-GOAB3797Arroyo4101 | Inactive | Inactive | [7 empty] | 2026-11-10 17:00
PBUT33 - T Line Rebuild |  |  | 10185 | 10185 | 14F015450000 | H Maria L3500 Lomas-Monacillos | Inactive | Inactive | [7 empty] | 2028-08-10 12:00
PBUT33 - T Line Rebuild |  |  | 10186 | 10186 | 14F015460000 | H Maria L-3300 Chardon-Egozcue | Inactive | Inactive | [7 empty] | 2028-03-16 12:00
PBUT33 - T Line Rebuild |  |  | 10187 | 10187 | 14F015470000 | H Maria L-21000-Humacao-Arroyo | Inactive | Inactive | [7 empty] | 2025-12-08 17:00
PBUT33 - T Line Rebuild |  |  | 10188 | 10188 | 14F015480000 | H Maria L-20900-Bta-Cambalache | Inactive | Inactive | [7 empty] | 2027-02-03 17:00
PBUT33 - T Line Rebuild |  |  | 10189 | 10189 | 14F015490000 | H Maria L20800Canas-BuenaVista | Inactive | Inactive | [7 empty] | 2028-08-28 17:00
PBUT33 - T Line Rebuild |  |  | 10190 | 10190 | 14F015500000 | H Maria L20600-SIsabel-Hamilto | Inactive | Inactive | [7 empty] | 2026-08-07 17:00
PBUT33 - T Line Rebuild |  |  | 10191 | 10191 | 14F015510000 | H Maria L20500-Juncos-Humacao | Inactive | Inactive | [7 empty] | 2028-08-28 17:00
PBUT33 - T Line Rebuild |  |  | 10192 | 10192 | 14F015520000 | H Maria L20300-Juncos-GBenítez | Inactive | Inactive | [7 empty] | 2028-10-18 17:00
PBUT33 - T Line Rebuild |  |  | 10193 | 10193 | 14F015530000 | H Maria L-20200-SGermán-Agosto | Inactive | Inactive | [7 empty] | 2026-08-13 17:00
PBUT33 - T Line Rebuild |  |  | 10194 | 10194 | 14F015540000 | H Maria L13400 Boqueron-Acacia | Inactive | Inactive | [7 empty] | 2027-06-14 17:00
PBUT33 - T Line Rebuild |  |  | 10195 | 10195 | 14F015550000 | H Maria L10000 Sierra-Magnolia | Inactive | Inactive | [7 empty] | 2026-10-07 17:00
PBUT33 - T Line Rebuild |  |  | 10213 | 10213 | 14F015560000 | H Maria 1000 Venez-Capuchinos | Inactive | Inactive | [7 empty] | 2024-07-05 17:00
PBUT33 - T Line Rebuild |  |  | 10196 | 10196 | 14F015570000 | H Maria L42600-SabLlana-Palmer | Inactive
PBUT33 - T Line Rebuild |  |  | 10197 | 10197 | 14F015580000 | H Maria L-39100-Hatillo-Mora | Inactive | Inactive | [7 empty] | 2030-10-10 12:00
PBUT33 - T Line Rebuild |  |  | 10198 | 10198 | 14F015590000 | H Maria L41200 Sabana-Canóvana | Inactive | Inactive | [7 empty] | 2023-06-29 17:00
PBUT33 - T Line Rebuild |  |  | 10199 | 10199 | 14F015600000 | HMaria L42700Monacillo-Canovan | Inactive | Inactive | [7 empty] | 2024-06-25 17:00
PBUT33 - T Line Rebuild | 107884 | 718971 | 10200 | 10200 | 14F015610000 | H MariaL50300 Costa S-Aguirre | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2023-07-11 08:00 | 2023-07-11
PBUT33 - T Line Rebuild | 107882 | 718951 | 10201 | 10201 | 14F015620000 | H Maria L51200 CostaS-Cambala | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2027-06-22 17:00 | 2023-07-11
PBUT33 - T Line Rebuild | 107883 | 718955 | 10202 | 10202 | 14F015630000 | H MariaL50200 Costa Sur-Bay TC | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2028-01-18 12:00 | 2023-07-11
PBUT33 - T Line Rebuild |  |  | 10203 | 10203 | 14F015640000 | H MariaL51000 Aguirre-SLlanaTC | Inactive
PBUT33 - T Line Rebuild |  |  | 10204 | 10204 | 14F015650000 | H MariaL-50900 Aguirre-Bay TC | Inactive
PBUT33 - T Line Rebuild |  |  | 10205 | 10205 | 14F015660000 | H Maria L50700Aguirre-YabuTC¿ | Inactive
PBUT33 - T Line Rebuild |  |  | 10206 | 10206 | 14F015670000 | H Maria L50500-May-Cambalache | Inactive
PBUT33 - T Line Rebuild |  |  | 10207 | 10207 | 14F015680000 | H Maria L-50400-May TC-Costa S | Inactive
PBUT33 - T Line Rebuild |  |  | 10208 | 10208 | 14F015690000 | H Maria L50800SLlanaTC-YabcoaT | Inactive
PBUT33 - T Line Rebuild |  |  | 10209 | 10209 | 14F016830000 | HMariaL2500-Victoria-SSebastia | Inactive
PBUT33 - T Line Rebuild |  |  | 10210 | 10210 | 14F016840000 | H Maria L2600-Ssebast-Quebradi | Inactive
PBUT33 - T Line Rebuild |  |  | 10211 | 10211 | 14F016850000 | H Maria L36700-Mayague-SSebast | Inactive
PBUT33 - T Line Rebuild |  |  | 10212 | 10212 | 14F016860000 | H MariaL36600-SSebast-DosBocas | Inactive
PBUT33 - T Line Rebuild |  |  | 10217 | 10217 | 14F021790000 | TLine4800SanIsaTC-Negro | Inactive |  | CAP1
PBUT33 - T Line Rebuild | 108031 | 756999 | 10080 | 10080 | 14F021920000 | TL1900 Lares to S.Sebast.Seg.3 | Active |  | CAP2 |  | Active | Phase 2 - Intake & Eligibility | Pending PDMG Scope & Cost Routing |  |  |  | 2024-10-01
PBUT33 - T Line Rebuild |  |  | 20000 | 20000 | 14N000500000 | Transm. Line New Extensions | Active
PBUT33 - T Line Rebuild |  |  | 20006 | 20006 | 14N000910000 | UG Transmission Syst Rep- NME | Inactive
PBUT33 - T Line Rebuild |  |  | 22005 | 22005 | 14N001290000 | 36100 Fast Track-NFC Structure | Inactive
PBUT33 - T Line Rebuild |  |  | 20013 | 20013 | 14N001510000 | Restorat.of UG TL Segment 2200 | Active
PBUT33 - T Line Rebuild |  |  | 20013 | 20013 | 14N001520000 | Restorat.of UG TL Segment16800 | Active
PBUT33 - T Line Rebuild |  |  | 20014 | 20014-002 | 14N001560000 | DOE TL 2100 | Inactive
PBUT33 - T Line Rebuild |  |  | 20014 | 20014-001 | 14N001570000 | DOE TL 9100 | Inactive
PBUT33 - T Line Rebuild |  |  | 20014 | 20014-003 | 14N001580000 | DOE TL 4500 | Inactive
PBUT33 - T Line Rebuild |  |  | 20014 | 20014-004 | 14N001590000 | DOE TL 12600 | Inactive
PBUT33 - T Line Rebuild |  |  | 20014 | 20014-005 | 14N001600000 | DOE TL 13600 | Inactive
PBUT33 - T Line Rebuild |  |  | 20014 | 20014-007 | 14N001620000 | DOE TL 9400 | Inactive
PBUT33 - T Line Rebuild | 1294 | 83182 | 90102 | 90102 | 15F019700000 | CAT Z - PBUT33 | Active |  |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  |  | 2020-02-05 12:48
PBUT33 - T Line Rebuild |  |  | 10155 | 10155 | 15N000040000 | L. 40600-Bay to Monac(UG Loop) | Inactive
PBUT33 - T Line Rebuild |  |  | 20006 | 20006 | 15N002400000 | UG Transmission System Rep-O&M | Cancel
PBUT34 - Dist. Lines Assessment |  |  | 32000 | 32000 | 14F001680000 | Distribution Lines Inspect | Active | Inactive
PBUT34 - Dist. Lines Assessment |  |  | 33001 | 33001 | 14F004300000 | UG System Inspection | Active | Inactive
PBUT34 - Dist. Lines Assessment | 1294 | 83182 | 90102 | 90102 | 15F019830000 | CAT Z - PBUT34 | Active |  |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  |  | 2020-02-05 12:48
PBUT36 - AMI Implementation Prog | 11583 | 714654 | 10006 | 10006 | 14F000000000 | Advanced Metering Infrastructu | Active | Active |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  | 2023-07-11 | 2023-12-08 11:19
PBUT36 - AMI Implementation Prog |  | Pending | 14002 | 14002 | 14F021930000 | DOE BehindTheMeterRep(DOE P1) | Active
PBUT36 - AMI Implementation Prog |  |  | 10006 | 10006 | 14N000480000 | AMI Headend | Cancel | Active
PBUT36 - AMI Implementation Prog |  |  | 14002 | 20018-001 | 14N001680000 | DOE BehindTheMeterRepairs(P1) | Inactive
PBUT36 - AMI Implementation Prog | 1294 | 83182 | 90102 | 90102 | 15F019610000 | CAT Z - PBUT36 | Active |  |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  |  | 2020-02-05 12:48
PBUT37 - Microgrid Inst & Integ |  |  | 90077 | 90077 | 10F000530000 | Centro Medico Microgrid | Inactive
PBUT37 - Microgrid Inst & Integ | 107206 | 165226 | 10095-005 | 10095-005 | 14F000910000 | 2501-02 (L) | Active | Active |  |  | Active | Phase 2 - Intake & Eligibility | Pending PDMG Scope & Cost Routing | 2021-09-17 08:00 | 2021-09-17 08:00 | 2022-12-28 08:00 | 2022-12-28
PBUT37 - Microgrid Inst & Integ | 107206 | 165226 | 10095-002 | 10095-002 | 14F000920000 | 2501-03 | Active | Active |  |  | Active | Phase 2 - Intake & Eligibility | Pending PDMG Scope & Cost Routing | 2021-09-17 08:00 | 2021-09-17 08:00 | 2022-12-28 08:00 | 2022-12-28
PBUT37 - Microgrid Inst & Integ | 107206 | 165226 | 10095-003 | 10095-003 | 14F000930000 | 3801-02 | Active | Active |  |  | Active | Phase 2 - Intake & Eligibility | Pending PDMG Scope & Cost Routing | 2021-09-17 08:00 | 2021-09-17 08:00 | 2022-12-28 08:00 | 2022-12-28
PBUT37 - Microgrid Inst & Integ | 107206 | 165226 | 10095-004 | 10095-004 | 14F000940000 | 2501-01 | Active | Active |  |  | Active | Phase 2 - Intake & Eligibility | Pending PDMG Scope & Cost Routing | 2021-09-17 08:00 | 2021-09-17 08:00 | 2022-12-28 08:00 | 2022-12-28
PBUT37 - Microgrid Inst & Integ | 107206 | 165226 | 10095-006 | 10095-006 | 14F000950000 | 3801-01 | Active | Active |  |  | Active | Phase 2 - Intake & Eligibility | Pending PDMG Scope & Cost Routing | 2021-09-17 08:00 | 2021-09-17 08:00 | 2022-12-28 08:00 | 2022-12-28
PBUT37 - Microgrid Inst & Integ |  |  | 90067 | 90067 | 14F017280000 | Vieques & Culebra Microgrid In | Inactive
PBUT37 - Microgrid Inst & Integ | 11819 | 738671 | 90087-004 | 90087-004 | 14F019600000 | 25 MW BESS Instn & Intn Barcel | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2025-04-25 08:00 | 2025-04-25
PBUT37 - Microgrid Inst & Integ | 107978 | 750503 | 90087-003 | 90087-003 | 14F019610000 | 25 MW BESS Instn & Intn San Ju | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2025-06-06 17:00 | 2025-06-06
PBUT37 - Microgrid Inst & Integ | 107977 | 750502 | 90087-002 | 90087-002 | 14F019620000 | 25 MW BESS INST & INTE AGUADIL | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2025-06-06 17:00 | 2025-06-06
PBUT37 - Microgrid Inst & Integ | 108002 | 752972 | 90087-001 | 90087-001 | 14F019630000 | 25 MW BESS Instn & Intn Manati | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued |  |  | 2025-04-25 08:00 | 2025-04-25
PBUT37 - Microgrid Inst & Integ | 107961 | 748180 | 20011 | 20011 | 14F020010000 | TSM, Adv.Sensors & WAMPAC Syst | Inactive | Inactive |  |  | Withdrawn | Discontinued | Process Discontinued | 2024-03-14 08:00 | 2024-03-14 08:00 | 2024-10-30 10:00 | 2024-10-01
PBUT37 - Microgrid Inst & Integ | 107982 | 751655 | 90067-002 | 90067-002 | 14F021650000 | Vieques Microgrid | Active | Active | CAP3 |  | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant | 2024-02-05 08:00 | 2024-02-05 08:00 | 2024-07-19 17:00 | 2024-07-19
PBUT37 - Microgrid Inst & Integ | 107983 | 751656 | 90067-001 | 90067-001 | 14F021690000 | Culebra Microgrid | Active | Active | CAP3 |  | Active | Phase 2 - Intake & Eligibility | Pending Scope & Cost Completion by Applicant | 2024-02-05 08:00 | 2024-02-05 08:00 | 2024-07-19 17:00 | 2024-07-19
PBUT37 - Microgrid Inst & Integ | 1294 | 83182 | 90102 | 90102 | 15F019660000 | Cat Z - PBUT37 | Active |  |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  |  | 2020-02-05 12:48
PBUT38 - New Business Connection |  |  | 90094 | 90094 | 10N008640000 | 14-01 New Transformers Instal. | Active
PBUT38 - New Business Connection |  |  | 30070 | 30070 | 10N010070000 | 17-1-243 WR6351877MCasasFulReh | Closed
PBUT38 - New Business Connection |  |  | 30070 | 30070 | 10N010940000 | 15-5-0293 Los Tubos Beach | Closed
PBUT38 - New Business Connection |  |  | 30070 | 30070 | 10N010980000 | WR6325133-6385841 Terrumo LLC | Closed
PBUT38 - New Business Connection |  |  | 30070 | 30070 | 10N011140000 | Customer Application Builder | Active
PBUT38 - New Business Connection |  |  | 30070 | 30070 | 10N011440000 | ANTENA LIBERTY CRAN 09-165 NPC | Closed
PBUT38 - New Business Connection |  |  | 30070 | 30070 | 10N011450000 | Hacienda Peñonales 20-5-0076 | Closed
PBUT38 - New Business Connection |  |  | 30070 | 30070 | 10N011460000 | HYDROPHONIC LLC | Inactive
PBUT38 - New Business Connection |  |  | 30070 | 30070 | 10N011470000 | La Maquina SG 22-4-0558 | Inactive
PBUT38 - New Business Connection |  |  | 30070 | 30070 | 10N011480000 | UG Repairs Sanchez Osorio Ave | Closed
PBUT38 - New Business Connection |  |  | 30070 | 30070 | 10N011490000 | Virgen M. Ayala 25-4-0007-EE | Closed
PBUT38 - New Business Connection |  |  | 30070 | 30070 | 10N011500000 | Antena Liberty CRAN 09-072 | Inactive
PBUT38 - New Business Connection |  |  | 30070 | 30070 | 14N001300000 | NB-Cust.Contributions(KVA Fee) | Cancel
PBUT38 - New Business Connection |  |  | 30070 | 30070 | 14N001310000 | D&T-NB Evaluations | Active
PBUT38 - New Business Connection |  |  | 30070 | 30070 | 14N001320000 | D&T-NB Endorsements | Active
PBUT38 - New Business Connection |  |  | 30070 | 30070 | 14N001330000 | D&T-NB Inspections | Active
PBUT38 - New Business Connection |  |  | 30070 | 30070 | 14N001340000 | New Business System Upgrades | Inactive
PBUT07 - Substation Reliability |  |  | 40094 | 40094 | 10N015970000 | Crea 1717 Xmer Replacement | Active | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015980000 | WR 21-7-044-R1-EST01 Kuisi.Exp | Active
CUSTOMER |  |  | 90017 | 90017 | 10N015990000 | WR 08-5-0318 VillaVictoria | Active
PBUT33 - T Line Rebuild |  | N/A | 20015 | 20015 | 10F008600000 | DOE 13100 (P3) | Active | Active
PBUT33 - T Line Rebuild |  | N/A | 90016 | 90016 | 10F008610000 | DOE-TL 2100 (P3) | Active
PBUT33 - T Line Rebuild |  | N/A | 90016 | 90016 | 10F008620000 | DOE-TL 4500 (P3) | Active
PBUT33 - T Line Rebuild |  | N/A | 90016 | 90016 | 10F008630000 | DOE-TL 9100 (P3) | Active
PBUT33 - T Line Rebuild |  | N/A | 90016 | 90016 | 10F008640000 | DOE-TL 12600 (P3) | Active
PBUT33 - T Line Rebuild |  | N/A | 90016 | 90016 | 10F008650000 | DOE-TL 13600 (P3) | Active
CUSTOMER |  |  | 90017 | 90017 | 10N016000000 | WR 25-4-0516-EE Juan Jimenez | Active
CUSTOMER |  |  | 90017 | 90017 | 10N016010000 | WR CRMA-25-1044 Adelaida Caban | Active
CUSTOMER |  |  | 90017 | 90017 | 10N016020000 | WR 24-4-0204-EE FrancisCordero | Active
CUSTOMER |  |  | 90017 | 90017 | 10N016030000 | WR 25-2-0704 EST-01 Fco Rivera | Active
CUSTOMER |  |  | 90017 | 90017 | 10N016040000 | WR CRSJ-25-1207-EST_01 AgnesOc | Active
CUSTOMER |  |  | 90017 | 90017 | 10N016050000 | WR 23-2-0971 EST01 | Active
n/a |  |  | 90016 | 90016 | 14N001740000 | Converg.PeñuelasEne.Sto(L-3-E) | Active
CUSTOMER |  |  | 90017 | 90017 | 15N008730000 | WR 24-5-0330 DEX-RECThermoFish | Inactive
PBUT32 - Assess.of Transm.Lines |  | N/A | 10218 | 10218 | 10F008660000 | DOE-Intelligence Enhanc. (P7) | Active
PBUT13 - T Priority Pole Repl |  | N/A | 20017 | 20017 | 10F008670000 | DOE TL 36100 (P6) | Active
PBUT13 - T Priority Pole Repl |  | N/A | 20017 | 20017 | 10F008680000 | DOE TL 36200 (P6) | Active
PBUT13 - T Priority Pole Repl |  | N/A | 20017 | 20017 | 10F008690000 | DOE TL 38200 (P6) | Active
CUSTOMER |  |  | 90017 | 90017 | 10N016060000 | WR 07-1-324-EST01 VimentiSchoo | Active
CUSTOMER |  |  | 90017 | 90017 | 10N016070000 | WR 24-7-189 Bay.Med.Cent. | Active
CUSTOMER |  |  | 90017 | 90017 | 10N016080000 | WR 25-7-283-EE-R1 MaríaECasasL | Active
CUSTOMER |  |  | 90017 | 90017 | 10N016090000 | WR 24-4-0568 Solar Serena Ren | Active
CUSTOMER |  |  | 90017 | 90017 | 10N016100000 | WR 22-4-0143 EstPOC AirStaBori | Active
CUSTOMER |  |  | 90017 | 90017 | 10N016110000 | WR CRMA-25-0668 AngelCruz | Active
CUSTOMER |  |  | 90017 | 90017 | 10N016120000 | WR 25-4-0452-EE ELIAS PAGAN | Active
CUSTOMER |  |  | 90017 | 90017 | 10N016130000 | WR 25-1-0074 KoperFurniture | Active
CUSTOMER |  |  | 90017 | 90017 | 10N016140000 | WR 25-7-475 Elvin Pagan | Active
CUSTOMER |  |  | 90017 | 90017 | 10N016150000 | WR 24-7-487-PH South Park | Active
CUSTOMER |  |  | 90017 | 90017 | 10N016160000 | WR 23-4-0223 Quebrad.FoodTruck | Active
PBRE02 - 3rdP Use Aud. Bill Proc |  | N/A | 90112 | 90112 | 14F021950000 | DOE-Pole Loading Abatement(P8) | Active
PBIT01 - OT Telecom Sys&Network |  |  | 60032 | 60032 | 10N016170000 | TelecomOperationsUBFiberEnhanc | Active
CUSTOMER |  |  | 90017 | 90017 | 10N016180000 | WR 13-2-012 EST03 B.TuraboPhs2 | Active
PBUT06 - Distr Line Rebuild |  |  | 30079 | 30079 | 10N016190000 | Feeder Tie 5004-07 & 5808-02 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N016200000 | WR 25-5-0075 Figueroa Morales | Active
PBUT07 - Substation Reliability |  | N/A | 40095 | 40095 | 10F008700000 | DOE Crit. Batt. Bnk.Rplac.(P6) | Active
PBUT07 - Substation Reliability |  | N/A | 40096 | 40096 | 10F008710000 | DOE OOS LTCs Overhauls (P6) | Active
PBUT07 - Substation Reliability |  | N/A | 40097 | 40097 | 10F008720000 | DOE Viaducto115kV PAC Upgr(P6) | Active
CUSTOMER |  |  | 90017 | 90017 | 10N016210000 | WR 24-7-021 Subs300KVA Dorado | Active
CUSTOMER |  |  | 90017 | 90017 | 10N016220000 | WR 25-2-0684-EST-01 ReginaRive | Active
CUSTOMER |  |  | 90017 | 90017 | 10N016230000 | WR 21-4-0062-EST01 Sol.LuisRam | Active
CUSTOMER |  |  | 90017 | 90017 | 10N016240000 | WR CRCA-25-0604-EST-01 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N016250000 | WR 22-2-0112 HogarJardinDeDios | Active
CUSTOMER |  |  | 90017 | 90017 | 10N016260000 | WR DRBA-26-0027 EscMargaritaJa | Active
PBUT07 - Substation Reliability |  | N/A | 40008 | 40008 | 10F008730000 | DOE Bayamon TC-Phs 1XMER (P6) | Active
PBUT07 - Substation Reliability |  | N/A | 40088 | 40088 | 10F008740000 | DOE DistRelayUpgrdAlt.RioGrand | Active | Inactive
PBUT07 - Substation Reliability |  | N/A | 40088 | 40088 | 10F008750000 | DOE CriticTransBreakers(3)(P6) | Active | Inactive
PBUT07 - Substation Reliability |  | N/A | 40088 | 40088 | 10F008760000 | DOE Dist.RelayUpgrMinillas(P6) | Active | Inactive
PBUT07 - Substation Reliability |  | N/A | 40088 | 40088 | 10F008770000 | DOE DisRelayUpgrSaban3604-6(P6 | Active | Inactive
PBUT07 - Substation Reliability |  | N/A | 40008 | 40008 | 10F008780000 | DOE FajardoTransf.Replc. (P6) | Active
PBUT07 - Substation Reliability |  | N/A | 40088 | 40088 | 10F008790000 | DOE LlorensT.13kVMetalclad(P4) | Active | Inactive
PBUT07 - Substation Reliability |  | N/A | 40088 | 40088 | 10F008800000 | DOE OOS Transm.Relays (P6) | Active | Inactive
PBUT07 - Substation Reliability |  | N/A | 40088 | 40088 | 10F008810000 | DOE DristRelayUpgrMPdelRey(P6) | Active | Inactive
PBUT07 - Substation Reliability |  | N/A | 40088 | 40088 | 10F008820000 | DOE DRelayUpgrBairoa3008-4(P6) | Active | Inactive
PBUT07 - Substation Reliability |  | N/A | 40088 | 40088 | 10F008830000 | DOE D.RelayUpgrCayey3401-1(P6) | Active | Inactive
PBUT07 - Substation Reliability |  | N/A | 40088 | 40088 | 10F008840000 | DOE DRelayUpgRGrande2301-2(P6) | Active | Inactive
PBUT07 - Substation Reliability |  | N/A | 40088 | 40088 | 10F008850000 | DOE RelayUpgrVAlta&PncHost(P6) | Active | Inactive
PBUT07 - Substation Reliability |  | N/A | 40098 | 40098 | 10F008860000 | DOE UFLS ComprehensiveProg(P6) | Active
PBUT07 - Substation Reliability |  | N/A | 40098 | 40098 | 10F008870000 | DOE WAP 230kV (P6) | Active
PBIT01 - OT Telecom Sys&Network |  | N/A | 60028 | 60028 | 10F008880000 | DOE COM GEN DESIGN&INST(P6) | Active | Active | [5 empty] | 2025-07-21 08:00 | 2025-07-21 08:00
CUSTOMER |  |  | 90017 | 90017 | 10N016270000 | WR 00-5-0242 AC014066PR140y642 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N016280000 | WR 25-4-0617 EST-POC, INTEGRA | Active
CUSTOMER |  |  | 90017 | 90017 | 10N016290000 | WR 25-7-297 R1 Instal.CampYGaz | Active
CUSTOMER |  |  | 90017 | 90017 | 10N016300000 | WR 22-5-0018 PRHTC Headquarter | Active
CUSTOMER |  |  | 90017 | 90017 | 10N016310000 | WR PRMA-26-0054-EE,GiovanniFel | Active
CUSTOMER |  |  | 90017 | 90017 | 10N016320000 | WR 24-5-1199 HatoViejoCell | Active
CUSTOMER |  |  | 90017 | 90017 | 10N016330000 | WR 25-4-0481 EST-01 CDT Hormig | Active
CUSTOMER |  |  | 90017 | 90017 | 10N016340000 | WR 23-4-0032-EE POC KeylaSosa | Active
CUSTOMER |  |  | 90017 | 90017 | 10N016350000 | WR CRAR-25-1009 GlendalizColon | Active
CUSTOMER |  |  | 90017 | 90017 | 10N016360000 | WR PRCA-26-0011 Sucn. Fontanez | Active
CUSTOMER |  |  | 90017 | 90017 | 10N016370000 | WR 25-1-0613-AA CanchaCanovana | Active
CUSTOMER |  |  | 90017 | 90017 | 10N016380000 | WR 25-7-258 LMG PR Toa Baja | Active
CUSTOMER |  |  | 90017 | 90017 | 10N016390000 | WR 25-2-0483-EST01,y REV01 | Active
PBIT01 - OT Telecom Sys&Network |  |  | 60033 | 60033 | 10N016400000 | NFC-Telecom GEN & Safety Gear | Active
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N016410000 | DER A&E - Arecibo Region | Active
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N016420000 | DER A&E - Bayamon Region | Active
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N016430000 | DER A&E - Caguas Region | Active
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N016440000 | DER A&E - Mayaguez Region | Active
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N016450000 | DER A&E - Ponce Region | Active
PBUT06 - Distr Line Rebuild |  |  | 30077 | 30077 | 10N016460000 | DER A&E - San Juan Region | Active
CUSTOMER |  |  | 90017 | 90017 | 10N016470000 | WR CRCA-25-0825 & CRCA-25-0826 | Active
n/a |  |  | 90016 | 90016 | 10N016480000 | MarisolPowerSolarIncreaseCapac | Active
CUSTOMER |  |  | 90017 | 90017 | 10N016490000 | WR CRMA-25-1023 BrisasDeJobos | Active
PBUT06 - Distr Line Rebuild |  |  | 30081 | 30081 | 10N016500000 | LoadTransfer7301-02 to 7301-05 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N016510000 | WR 24-1-0456 FLORES CARRAIZO | Active
PBUT06 - Distr Line Rebuild |  |  | 30080 | 30080 | 14N001750000 | Dist WildfireMitigation-PBUT06 | Active
PBUT30 - D Pole & Conductor Repa |  |  | 32000 | 32000 | 14N001760000 | NFC Distrib.Pole & Cond.-PHS 3 | Active | Inactive
n/a | 1294 | 83182 | 90058 | 90058 | 15F019260000 | Grants Cat Z Close Out Maria | Active |  |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  |  | 2020-02-05 12:48
n/a | 1294 | 83182 | 90058 | 90058 | 15F019270000 | Grants Cat Z Formulation Maria | Active |  |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  |  | 2020-02-05 12:48
n/a | 1294 | 83182 | 90058 | 90058 | 15F019280000 | Grants Cat Z Reimburs. Maria | Active |  |  |  | Active | Phase 5 - Post Award Phase | Obligated |  |  |  |  | 2020-02-05 12:48
PBUT07 - Substation Reliability |  | N/A | 40098 | 40098 | 10F008890000 | DOE PAC Funct.VisualTest. (P6) | Active
PBUT07 - Substation Reliability |  | N/A | 40098 | 40098 | 10F008900000 | DOE 230kV Line Diff upgrd (P6) | Active
PBIT01 - OT Telecom Sys&Network |  | N/A | 60028 | 60028 | 10F008910000 | DOE Dorado-BayOPGW F/O Rep(P6) | Active | Active | [5 empty] | 2025-07-21 08:00 | 2025-07-21 08:00
PBIT01 - OT Telecom Sys&Network |  | N/A | 60028 | 60028 | 10F008920000 | DOE Maun-JMartinUB F/O Rep(P6) | Active | Active | [5 empty] | 2025-07-21 08:00 | 2025-07-21 08:00
PBUT07 - Substation Reliability |  | N/A | 40008 | 40008 | 10F008930000 | DOE MonaciBank1&3XfrmReplc(P2) | Active
PBUT07 - Substation Reliability |  | N/A | 40097 | 40097 | 10F008940000 | DOE Monaci115kVBank2PACupgr(P6 | Active
PBUT07 - Substation Reliability |  | N/A | 60028 | 60028 | 10F008950000 | DOE SEL ICON MUX PROTECT. (P6) | Active | Active | [5 empty] | 2025-07-21 08:00 | 2025-07-21 08:00
PBUT07 - Substation Reliability |  | N/A | 40098 | 40098 | 10F008960000 | DOE DFRs (P6) | Active
PBUT07 - Substation Reliability |  | N/A | 60026 | 60026 | 10F008970000 | DOE RTUs (P6) | Active
PBOP05 - Tools Repair & Mgmt |  |  | 90113 | 90113 | 10N016520000 | NFC-PBOP05 TelecomTools&Equip | Active
CUSTOMER |  |  | 90017 | 90017 | 10N016530000 | WR 24-5-0187 Quebradillas Viv. | Active
CUSTOMER |  |  | 90017 | 90017 | 10N016540000 | WR 22-7-013 Dorado Beach Plant | Active
CUSTOMER |  |  | 90017 | 90017 | 10N016550000 | WR 25-2-0045 Edif Inv Alverio | Active
CUSTOMER |  |  | 90017 | 90017 | 10N016560000 | WR PRMA-26-0092 Daniel Lopez | Active
CUSTOMER |  |  | 90017 | 90017 | 10N016570000 | WR 24-4-0482 QMC-179 LaresSite | Active
CUSTOMER |  |  | 90017 | 90017 | 10N016580000 | WR 25-5-0482-AA Victoria Hndz | Active
CUSTOMER |  |  | 90017 | 90017 | 10N016590000 | WR 25-2-0104 Yabucoa SolarFarm | Active
CUSTOMER |  |  | 90017 | 90017 | 10N016600000 | WR 08-5-0173.1-EST02 Palmeras | Active
CUSTOMER |  |  | 90017 | 90017 | 10N016610000 | WR 23-5-0233 Texaco Arecibo | Active
CUSTOMER |  |  | 90017 | 90017 | 10N016620000 | WR 23-5-0305 Benedicto Pabon | Active
PBUT04 - Grid Automation |  |  | 30080 | 30080 | 10N016630000 | Dist WildfireMitigation-PBUT04 | Active
CUSTOMER |  |  | 90017 | 90017 | 10N016640000 | WR CRPO-26-0049 InfinityAdvanc | Active
CUSTOMER |  |  | 90017 | 90017 | 10N016650000 | WR 24-4-0493 14 Apartamentos | Active
CUSTOMER |  |  | 90017 | 90017 | 10N016660000 | WR 08-5-0173.1-EST01 Palmeras | Active
CUSTOMER |  |  | 90017 | 90017 | 10N016670000 | WR 22-7-250 PuentePeatonCoroz
PBUT04 - Grid Automation |  |  | 20010 | 20010 | 10N016680000 | TransmissionAutomationLine3700 |  | Inactive
PBUT13 - T Priority Pole Repl |  |  | 10131 | 10131 | 10N016690000 | T-Pole Program NFC Group 1 |  | Active | [5 empty] | 44348.3333 | 44671.7083
CUSTOMER |  |  | 90017 | 90017 | 10N016700000 | WR 25-3-0087 Carib Chemicals
CUSTOMER |  |  | 90017 | 90017 | 10N016710000 | WR 25-2-0134 Angel Diaz Colon
PBUT33 - T Line Rebuild |  |  | 20018 | 20018 | 10N016720000 | TL-3300 ChardonSect PopularCen
CUSTOMER |  |  | 90017 | 90017 | 10N016730000 | WR 99-3-440.1 PHS Esc. Dental

## Attachment A (Updated) (hidden)
[9 empty] | Estimate Project Costs Allocation (Update) | [8 empty] | Confirmation and Comments |  |  |  |  | PREB Response numbers ( Do not update)
Project # | Title | Should we include the project in the (New List) ? | Submitted to PREPA (Yes/No) | Asset | Sub Asset | Obligated (Yes / No) | Activated by PREPA (Active / Inactive) | Activated by FEMA (Active / Inactive) | 428 Estimate (Without the A&E and E&M) | 406 Estimate (Without the A&E and E&M) | 428 A&E Estimate-PW 9510 | 406 A&E Estimate -PW 9510 | 428 E&M Estimate -PW 10710 | 406 E&M Estimate -PW 10710 | Expected Total Project Estimate Cost | Total 428 Estimate Cost | Total 406 Estimate Cost | Estimate/Cost change (Y/N) | Who confirmed the information? | Obligation Amendment Status | New Comment | Updated Comments | 428 Allocation (Without the A&E and E&M) | 406 Allocation (Without the A&E and E&M) | 428 A&E-PW 9510 | 406 A&E-PW 9510 | 428 E&M-PW 10710 | 406 E&M-PW 10710 | Expected Total Project Cost | Total 428 Expected Cost | Total 406 Expected Cost | Project Status | Expected COR3 Submission Date | Comments | Total NEW LIST | PREPA Note: Cost incurred as reported by LUMA. | Project w Prior Cost Estimate | No File Projects | Shifted Projects | 428 | 406 | DAE Comment
9510 | PBUT34 - Islandwide Feeder Assessments | No | No |  | not found | No | Inactive | Inactive | Not Found | Not Found | Not Found | Not Found | Not Found | Not Found | Not Found | Not Found | Not Found | not found | not found | not found | not found | not found | [14 empty] | 0 | 1 | 0 | 0 | 0
9510 | A&E costs reimbursed related to projects without child | not found | No |  | not found | No | Inactive | Inactive | Not Found | Not Found | Not Found | Not Found | Not Found | Not Found | Not Found | Not Found | Not Found | not found | not found | not found | not found | not found | [14 empty] | 0 | 1 | 0 | 0 | 0
10710 | Reclosers - Without child project (Equipment purchased) | No | No |  | not found | No | Inactive | Inactive | Not Found | Not Found | Not Found | Not Found | Not Found | Not Found | Not Found | Not Found | Not Found | not found | not found | not found | not found | not found | [14 empty] | 0 | 1 | 0 | 0 | 0
TBD35 | Poles- Included in the E&M without child (Poles paid) | not found |  |  | not found | No | Inactive | Inactive | Not Found | Not Found | Not Found | Not Found | Not Found | Not Found | Not Found | Not Found | Not Found | not found | not found | not found | not found | not found | [14 empty] | 0 | 1 | 0 | 0 | 0
750503 | FAASt [25 MW BESS Installation and Integration - San Juan] (Substation) | Yes | No | Substations | Grid Modernization | No | Inactive | Inactive | 0 | 24053536.03 | 0 | 3187811.29 | 0 | 28261718.24 | 55503065.56 | 0 | 55503065.56 | N | Luis Munet |  |  |  | 0 | 24053536.03 | 0 | 3187811.29 | 0 | 28261718.24 | 55503065.56 | 0 | 55503065.56 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | 406 HM Split 100% As it was last submitted to FEMA. Contingent to FEMA Hazard Mitigation Evaluation and approval. |  |  | 1 | 0 | 1 | 0 | 55503065.56
750502 | FAASt [25 MW BESS Installation and Integration - Aguadilla] (Substation) | Yes | No | Substations | Grid Modernization | No | Inactive | Inactive | 0 | 21118171.64 | 0 | 3340630.47 | 0 | 28261718.24 | 52720520.35 | 0 | 52720520.35 | N | Luis Munet |  |  |  | 0 | 21118171.64 | 0 | 3340630.47 | 0 | 28261718.24 | 52720520.35 | 0 | 52720520.35 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | 406 HM Split 100% As it was last submitted to FEMA |  |  | 1 | 0 | 0 | 0 | 52720520.35
752972 | FAASt [4 x 25 MW BESS Interconnections Manati] (Substation) | Yes | No | Substations | Grid Modernization | No | Inactive | Inactive | 0 | 23808829.62 | 0 | 3414922.97 | 0 | 30416253.08 | 57640005.67 | 0 | 57640005.67 | N | Luis Munet |  |  |  | 0 | 23808829.62 | 0 | 3414922.97 | 0 | 30416253.08 | 57640005.67 | 0 | 57640005.67 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | 406 HM Split 100% As it was last submitted to FEMA |  |  | 1 | 0 | 0 | 0 | 57640005.67
738671 | FAASt [25 MW BESS Installation and Integration - Barceloneta] (Substation) | Yes | No | Substations | Grid Modernization | No | Inactive | Inactive | 0 | 20318919.35 | 0 | 5211394.35 | 0 | 30411453.8 | 55941767.5 | 0 | 55941767.5 | N | Luis Munet |  |  |  | 0 | 20318919.35 | 0 | 5211394.35 | 0 | 30411453.8 | 55941767.5 | 0 | 55941767.5 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | 406 HM Split 100% As it was last submitted to FEMA |  |  | 1 | 0 | 0 | 0 | 55941767.5
688623 | FAASt [Automation Program Group 1A-8 Feeders] (Distribution) | No | No | Distribution | Automation | No | Inactive | Inactive | 15682783.16 | 2926805 | 3241962.6 | 516495 | 3708204.4 | 2410310 | 28486560.16 | 22632950.16 | 5853610 | Yes | Victor V. DeCastro Carlo | N/A | Actuals for the "Work Completed" as of March 2026 considered, and Class 5 Estimate for the remaining work. Group 1A with 1B, 1C, and 1D was consolidated into a unique Group 1. The remaining work is based is Class 5 estimated total per project is considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (59) 3PH Reclosers, (266) 1ph reclosers, (165) cFCi. It requires an engineering evaluation once project is reactivated in order to meet current standards. Expenses incurred for partial work, including engineering and studies, which still need to be reconciled. Actuals in Work Completed portion +$11,270,060 as of March 2026 was added to the total project cost. It was split under 428 bucket, "428 Estimate (Without the A&E and E&M)": +$6,385,873.16, "428 A&E Estimate-PW 9510": +$2,381,137.6, "428 E&M Estimate -PW 10710": +$2,503,049.40. | Estimate date for the work to be completed portion only, consolidating Group 1A with 1B, 1C, and 1D into a unique Group 1. This is Class 5 estimated total per project is considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (59) 3PH Reclosers, (266) 1ph reclosers, (165) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions.. Expenses have already been incurred for completed and partial work, including engineering and studies, which still need to be reconciled. The scope requires restructuring and proper formulation to move forward. | 3591270 | 1130585 | 332525 | 199515 | 465535 | 931070 | 6650500 | 4389330 | 2261170 | DSOW – Pending Design Package for Development | Q3 FY2027 | Estimate date for the work to be completed portion only. The estimated total per project is considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (23) 3PH Reclosers, (104) 1ph reclosers, (48) cFCi. |  |  | 1 | 0 | 0 | 0 | 0
740662 | [Automation Program Group 2] (TL/ Distribution | No | No | Distribution | Automation | No | Inactive | Inactive | 36782398.44 | 6876500 | 6277691.02 | 1213500 | 6850965.04 | 5663000 | 63664054.5 | 49911054.5 | 13753000 | No | Victor V. DeCastro Carlo | N/A | Actuals for the "Work Completed" as of March 2026 considered, and Class 5 Estimate for the remaining work. The remaining work is Class 5 estimated total per project is considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (145) 3PH Reclosers, (539) 1ph reclosers, (254) cFCi. It requires an engineering evaluation once project is reactivated in order to meet current standards. Expenses incurred for partial work, including engineering and studies, which still need to be reconciled. Actuals in Work Completed portion is +$23,214,054.50 as of March 2026 was added to the total estimate cost. It was split under 428 bucket, "428 Estimate (Without the A&E and E&M)": +$14,939,398.44, "428 A&E Estimate-PW 9510": + $4,255,191.02, "428 E&M Estimate -PW 10710": +$4,019,465.04. | Estimate date for the work to be completed portion only. This is Class 5 estimated total per project is considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (145) 3PH Reclosers, (539) 1ph reclosers, (254) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions. Expenses have already been incurred for completed and partial work, including engineering and studies, which still need to be reconciled. The scope requires restructuring and proper formulation to move forward. | 21843000 | 6876500 | 2022500 | 1213500 | 2831500 | 5663000 | 40450000 | 26697000 | 13753000 | DSOW – Pending Design Package for Development | Q3 FY2027 | Estimate date for the work to be completed portion only. The estimated total per project is considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (145) 3PH Reclosers, (539) 1ph reclosers, (254) cFCi. |  |  | 1 | 0 | 0 | 0 | 0
741678 | [Automation Program Group 4] (TL/Distribution | No | No | Distribution | Automation | No | Inactive | Inactive | 29500343.61 | 5347180 | 4420325.45 | 943620 | 6946880.68 | 4403560 | 51561909.74 | 40867549.74 | 10694360 | No | Victor V. DeCastro Carlo | N/A | Actuals for the "Work Completed" as of March 2026 considered, and Class 5 Estimate for the remaining work. The remaining work is Class 5 estimated total per project is considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (117) 3PH Reclosers, (247) 1ph reclosers, (182) cFCi. It requires an engineering evaluation once project is reactivated in order to meet current standards. Expenses incurred for partial work, including engineering and studies, which still need to be reconciled. Expenses have already been incurred for completed and partial work, including engineering and studies, which still need to be reconciled. Actuals in Work Completed portion is +$20,107,909.74 as of March 2026 was added to the total estimate cost. It was split under 428 bucket, "428 Estimate (Without the A&E and E&M)": +$12,515,183.61, "428 A&E Estimate-PW 9510": +$2,847,625.45, "428 E&M Estimate -PW 10710": +$4,475,100.68. | Estimate date for the work to be completed portion only. This is Class 5 estimated total per project is considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (117) 3PH Reclosers, (247) 1ph reclosers, (182) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions. Expenses have already been incurred for completed and partial work, including engineering and studies, which still need to be reconciled. The scope requires restructuring and proper formulation to move forward. | 16985160 | 5347180 | 1572700 | 943620 | 2201780 | 4403560 | 31454000 | 20759640 | 10694360 | DSOW – Pending Design Package for Development | Q3 FY2027 | Estimate date for the work to be completed portion only. The estimated total per project is considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (117) 3PH Reclosers, (247) 1ph reclosers, (182) cFCi. |  |  | 1 | 0 | 0 | 0 | 0
705657 | [Automation Program Group 3] (TL/Distribution | No | No | Distribution | Automation | No | Inactive | Inactive | 30089122.78 | 4299385 | 7264119.61 | 758715 | 6881478.06 | 3540670 | 52833490.45 | 44234720.45 | 8598770 | No | Victor V. DeCastro Carlo | N/A | Actuals for the "Work Completed" as of March 2026 considered, and Class 5 Estimate for the remaining work. The remaining work is Class 5 estimated total per project is considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (99) 3PH Reclosers, (316) 1ph reclosers, (212) cFCi.It requires an engineering evaluation once project is reactivated in order to meet current standards. Expenses incurred for partial work, including engineering and studies, which still need to be reconciled. Expenses have already been incurred for completed and partial work, including engineering and studies, which still need to be reconciled. Actuals in Work Completed portion is +$27,542,990.45 as of March 2026 was added to the total estimate cost. It was split under 428 bucket, "428 Estimate (Without the A&E and E&M)": +$16,432,252.78, "428 A&E Estimate-PW 9510": +$5,999,594.61, "428 E&M Estimate -PW 10710": +$5,111,143.06. | Estimate date for the work to be completed portion only. This is Class 5 estimated total per project is considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (99) 3PH Reclosers, (316) 1ph reclosers, (212) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions. Expenses have already been incurred for completed and partial work, including engineering and studies, which still need to be reconciled. The scope requires restructuring and proper formulation to move forward. | 13656870 | 4299385 | 1264525 | 758715 | 1770335 | 3540670 | 25290500 | 16691730 | 8598770 | DSOW – Pending Design Package for Development | Q3 FY2027 | Estimate date for the work to be completed portion only. The estimated total per project is considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (99) 3PH Reclosers, (316) 1ph reclosers, (212) cFCi. |  |  | 1 | 0 | 0 | 0 | 0
800394 | Automation Program Group 39 (Distribution) | Yes | Yes | Distribution | Automation | No | Inactive | Inactive | 1256040 | 395420 | 116300 | 69780 | 162820 | 325640 | 2326000 | 1535160 | 790840 |  | Victor V. DeCastro Carlo | N/A | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (11) 3PH Reclosers, (17) 1ph reclosers, (18) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions. | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (11) 3PH Reclosers, (17) 1ph reclosers, (18) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 1535160 | 790840
800369 | FAASt [Automation Program Group 38 | No | No | Distribution | Automation | No | Inactive | Inactive | 802170 | 252535 | 74275 | 44565 | 103985 | 207970 | 1485500 | 980430 | 505070 |  | Victor V. DeCastro Carlo | N/A | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (4) 3PH Reclosers, (29) 1ph reclosers, (21) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions. | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (4) 3PH Reclosers, (29) 1ph reclosers, (21) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
800399 | FAASt [Automation Program Group 40 | No | No | Distribution | Automation | No | Inactive | Inactive | 1536300 | 483650 | 142250 | 85350 | 199150 | 398300 | 2845000 | 1877700 | 967300 |  | Victor V. DeCastro Carlo | N/A | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (11) 3PH Reclosers, (35) 1ph reclosers, (33) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions. | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (11) 3PH Reclosers, (35) 1ph reclosers, (33) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
401432 | FAASt [Automation Program Group 41 | No | No | Distribution | Automation | No | Inactive | Inactive | 1469610 | 462655 | 136075 | 81645 | 190505 | 381010 | 2721500 | 1796190 | 925310 |  | Victor V. DeCastro Carlo | N/A | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (10) 3PH Reclosers, (39) 1ph reclosers, (18) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions. | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (10) 3PH Reclosers, (39) 1ph reclosers, (18) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
801437 | FAASt [Automation Program Group 42 | No | No | Distribution | Automation | No | Inactive | Inactive | 604800 | 190400 | 56000 | 33600 | 78400 | 156800 | 1120000 | 739200 | 380800 |  | Victor V. DeCastro Carlo | N/A | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (2) 3PH Reclosers, (30) 1ph reclosers, (6) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions. | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (2) 3PH Reclosers, (30) 1ph reclosers, (6) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
801438 | FAASt [Automation Program Group 43 | No | No | Distribution | Automation | No | Inactive | Inactive | 851580 | 268090 | 78850 | 47310 | 110390 | 220780 | 1577000 | 1040820 | 536180 |  | Victor V. DeCastro Carlo | N/A | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (4) 3PH Reclosers, (34) 1ph reclosers, (12) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions. | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (4) 3PH Reclosers, (34) 1ph reclosers, (12) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
801440 | FAASt [Automation Program Group 44 | No | No | Distribution | Automation | No | Inactive | Inactive | 597510 | 188105 | 55325 | 33195 | 77455 | 154910 | 1106500 | 730290 | 376210 |  | Victor V. DeCastro Carlo | N/A | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (5) 3PH Reclosers, (10) 1ph reclosers, (6) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions. | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (5) 3PH Reclosers, (10) 1ph reclosers, (6) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
801441 | FAASt [Automation Program Group 45 | No | No | Distribution | Automation | No | Inactive | Inactive | 1221750 | 384625 | 113125 | 67875 | 158375 | 316750 | 2262500 | 1493250 | 769250 |  | Victor V. DeCastro Carlo | N/A | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (10) 3PH Reclosers, (21) 1ph reclosers, (18) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions. | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (10) 3PH Reclosers, (21) 1ph reclosers, (18) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
745854 | FAASt [Automation Program Group 9 | No | No | Distribution | Automation | No | Inactive | Inactive | 589140 | 185470 | 54550 | 32730 | 76370 | 152740 | 1091000 | 720060 | 370940 |  | Victor V. DeCastro Carlo | N/A | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (4) 3PH Reclosers, (14) 1ph reclosers, (18) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions. | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (4) 3PH Reclosers, (14) 1ph reclosers, (18) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
745871 | FAASt [Automation Program Group 10 | No | No | Distribution | Automation | No | Inactive | Inactive | 713610 | 224655 | 66075 | 39645 | 92505 | 185010 | 1321500 | 872190 | 449310 |  | Victor V. DeCastro Carlo | N/A | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (6) 3PH Reclosers, (11) 1ph reclosers, (12) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions. | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (6) 3PH Reclosers, (11) 1ph reclosers, (12) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
745851 | FAASt [Automation Program Group 11 | No | No | Distribution | Automation | No | Inactive | Inactive | 720630 | 226865 | 66725 | 40035 | 93415 | 186830 | 1334500 | 880770 | 453730 |  | Victor V. DeCastro Carlo | N/A | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (5) 3PH Reclosers, (18) 1ph reclosers, (12) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions. | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (5) 3PH Reclosers, (18) 1ph reclosers, (12) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
745852 | FAASt [Automation Program Group 13 | No | No | Distribution | Automation | No | Inactive | Inactive | 897480 | 282540 | 83100 | 49860 | 116340 | 232680 | 1662000 | 1096920 | 565080 |  | Victor V. DeCastro Carlo | N/A | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (9) 3PH Reclosers, (3) 1ph reclosers, (24) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions. | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (9) 3PH Reclosers, (3) 1ph reclosers, (24) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
790427 (1066737) | Distribution Pole and Conductor Repair - Caguas Group 5 - Phase 2 | Yes | Yes | Distribution | Distribution Pole and Conductor Repair | No | Active | Active | 7522113.13 | 215009.46 | 668118.89 | 35608.17 | 520612.13 | 213636.87 | 9175098.65 | 8710844.15 | 464254.5 |  | Victor V. DeCastro Carlo | N/A | Class 3 estimate has been submitted to COR3 for validation. WOP design is 100% completed, and the DSOW package has been completed. We are currently pending COR3’s review prior to FEMA submission. | Class 3 estimate has been submitted to COR3 for validation. WOP design is 100% completed, and the DSOW package has been completed. We are currently pending COR3’s review prior to FEMA submission. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 8710844.15 | 464254.5 | Anadir numero nuevo
806935 (1066738) | Distribution Pole and Conductor Repair - Caguas Group 6 - Phase 2 | Yes | Yes | Distribution | Distribution Pole and Conductor Repair | No | Active | Active | 7262006.01 | 330225.13 | 645539.7 | 44770.71 | 509451.1 | 208755.9 | 9000748.55 | 8416996.81 | 583751.74 |  | Victor V. DeCastro Carlo | N/A | Class 3 estimate has been submitted to COR3 for validation. WOP design is 100% completed, and the DSOW package has been completed. We are currently pending COR3’s review prior to FEMA submission. | Class 3 estimate has been submitted to COR3 for validation. WOP design is 100% completed, and the DSOW package has been completed. We are currently pending COR3’s review prior to FEMA submission. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 8416996.81 | 583751.74 | Anadir numero nuevo
757945 (1066739) | Distribution Pole and Conductor Repair - Arecibo Group 3 – Phase 2 | Yes | Yes | Distribution | Distribution Pole and Conductor Repair | No | Active | Active | 2039409.93 | 366564.02 | 181779.7 | 35823.76 | 173097.79 | 69460.21 | 2866135.41 | 2394287.42 | 471847.99 |  | Victor V. DeCastro Carlo | N/A | Class 3 estimate has been submitted to COR3 for validation. WOP design is 100% completed, and the DSOW package has been completed. We are currently pending COR3’s review prior to FEMA submission. | Class 3 estimate has been submitted to COR3 for validation. WOP design is 100% completed, and the DSOW package has been completed. We are currently pending COR3’s review prior to FEMA submission. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 2394287.42 | 471847.99 | Anadir numero nuevo
790446 (1066740) | Distribution Pole and Conductor Repair – Caguas Group 4 – Phase 2 | Yes | Yes | Distribution | Distribution Pole and Conductor Repair | No | Active | Active | 3449507.56 | 434031.63 | 308003.3 | 44842.58 | 258899.2 | 105879.8 | 4601164.07 | 4016410.06 | 584754.01 |  | Victor V. DeCastro Carlo | N/A | Class 3 estimate has been submitted to COR3 for validation. WOP design is 100% completed, and the DSOW package has been completed. We are currently pending COR3’s review prior to FEMA submission. | Class 3 estimate has been submitted to COR3 for validation. WOP design is 100% completed, and the DSOW package has been completed. We are currently pending COR3’s review prior to FEMA submission. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 4016410.06 | 584754.01 | Anadir numero nuevo
817249 (1066741) | Distribution Pole and Conductor Repair – Caguas Group 7 – Phase 2 | Yes | Yes | Distribution | Distribution Pole and Conductor Repair | No | Active | Active | 4608333 | 284709.51 | 409935.75 | 36039.36 | 381146.2 | 153938.8 | 5874102.62 | 5399414.95 | 474687.67 |  | Victor V. DeCastro Carlo | N/A | Class 3 estimate has been submitted to COR3 for validation. WOP design is 100% completed, and the DSOW package has been completed. We are currently pending COR3’s review prior to FEMA submission. | Class 3 estimate has been submitted to COR3 for validation. WOP design is 100% completed, and the DSOW package has been completed. We are currently pending COR3’s review prior to FEMA submission. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 5399414.95 | 474687.67 | Anadir numero nuevo
764707 | [Feeder Rebuild # 6012-02] (Distribution | No | No | Distribution | Rebuild | No | Inactive | Inactive | 16634520 | 482160 | 5062680 | 241080 | 1446480 | 241080 | 24108000 | 23143680 | 964320 | No | Victor V. DeCastro Carlo | N/A | This feeder has a CMI of 4.8M, and the design is approximately 39% complete. It includes a total of 239 structures. It is recommended to replace for feeders 1204‑05(CMI 14.6M), 2404‑06(CMI 7.2M), and 1303‑0(CMI 5M), due to their higher CMIs and because their engineering stages are nearing completion for DSOW submission. | This feeder has a CMI of 4.8M, and the design is approximately 39% complete. It includes a total of 239 structures. It is recommended to replace for feeders 1204‑05(CMI 14.6M), 2404‑06(CMI 7.2M), and 1303‑0(CMI 5M), due to their higher CMIs and because their engineering stages are nearing completion for DSOW submission. | 16634520 | 482160 | 5062680 | 241080 | 1446480 | 241080 | 24108000 | 23143680 | 964320 | DSOW – Pending Design Package for Development | FY2029 | Design is about 39% complete. This project is currently classified as withdrawn (T1) and covers 5.74 miles with 239 structures. DSOW – Waiting on the design package to be developed. |  |  | 1 | 0 | 0 | 0 | 0
764705 | [Feeder Rebuild # 6014-02] (Distribution | No | No | Distribution | Rebuild | No | Inactive | Inactive | 23763600 | 688800 | 7232400 | 344400 | 2066400 | 344400 | 34440000 | 33062400 | 1377600 | No | Victor V. DeCastro Carlo | N/A | This feeder has a CMI of 16.8M. Engineering stages are nearing completion for DSOW submission. | This feeder has a CMI of 16.8M. Engineering stages are nearing completion for DSOW submission. | 23763600 | 688800 | 7232400 | 344400 | 2066400 | 344400 | 34440000 | 33062400 | 1377600 | DSOW – Pending Design Package for Development | FY2029 | Design is about 52% complete. This project is currently classified as withdrawn (T1) and covers 8.20 miles with 343 structures. DSOW – Waiting on the design package to be developed. |  |  | 1 | 0 | 0 | 0 | 0
767381 | [Feeder Rebuild # 1204-05] (Distribution | No | No | Distribution | Rebuild | No | Inactive | Inactive | 3880428.29 | 112476.18 | 1180999.92 | 56238.09 | 337428.55 | 56238.09 | 5623809.12 | 5398856.76 | 224952.36 | No | Victor V. DeCastro Carlo | N/A | This feeder has a CMI of 14.6M, Engineering stages are nearing completion for DSOW submission. (Replacement for 6012-02 CMI 4.8M) | This feeder has a CMI of 14.6M, Engineering stages are nearing completion for DSOW submission. (Replacement for 6012-02 CMI 4.8M) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
817961 | [Feeder Rebuild # 2404-06] (Distribution | No | No | Distribution | Rebuild | No | Inactive | Inactive | 18825472.43 | 399260.06 | 1826739.4 | 50231.61 | 692201.89 | 82130.27 | 21876035.66 | 21344413.72 | 531621.94 | No | Victor V. DeCastro Carlo | N/A | This feeder has a CMI of 7.2M, Engineering stages are nearing completion for DSOW submission. (Replacement for 6012-02 CMI 4.8M) | This feeder has a CMI of 7.2M, Engineering stages are nearing completion for DSOW submission. (Replacement for 6012-02 CMI 4.8M) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
767387 | [Feeder Rebuild # 1303-01] (Distribution | No | No | Distribution | Rebuild | No | Inactive | Inactive | 5013491.62 | 145318.6 | 1525845.28 | 72659.3 | 435955.79 | 72659.3 | 7265929.89 | 6975292.69 | 290637.2 | No | Victor V. DeCastro Carlo | N/A | This feeder has a CMI of 5M, Engineering stages are nearing completion for DSOW submission. (Replacement for 6012-02 CMI 4.8M) | This feeder has a CMI of 5M, Engineering stages are nearing completion for DSOW submission. (Replacement for 6012-02 CMI 4.8M) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
666894 | FAASt [San Juan Streetlighting] (Distribution) | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 28178017.76 | 2123472.21 | 6380570.04 | 123157.52 |  |  | 36805217.53 | 34558587.8 | 2246629.73 | N | Victor V. DeCastro Carlo | N/A | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered. | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer. | 27201946.76 | 1465463.21 | 6380570.04 | 123157.52 | 976071 | 658009 | 36805217.53 | 34558587.8 | 2246629.73 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. |  |  | 1 | 0 | 0 | 34558587.8 | 2246629.73
671396 | FAASt [Utuado Streetlighting] (Distribution) | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 16760927.205 | 2851675.47 | 3319870.72 | 155072.6 |  |  | 23087545.995 | 20080797.925 | 3006748.07 | N | Victor V. DeCastro Carlo | N/A | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered. | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. | 15515918.205 | 2012364.47 | 3319870.72 | 155072.6 | 1245009 | 839311 | 23087545.995 | 20080797.925 | 3006748.07 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. |  |  | 1 | 0 | 0 | 20080797.925 | 3006748.07
671400 | FAASt [Barceloneta Streetlighting] (Distribution) | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 7422038.0375 | 477869.14 | 1206563.5 | 50306 |  |  | 9156776.6775 | 8628601.5375 | 528175.14 | N | Victor V. DeCastro Carlo | N/A | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered. | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. | 7024652.0375 | 209975.14 | 1206563.5 | 50306 | 397386 | 267894 | 9156776.6775 | 8628601.5375 | 528175.14 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. |  |  | 1 | 0 | 0 | 8628601.5375 | 528175.14
678794 | FAASt [Ponce Streetlighting] (Distribution) | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 10968715.275 | 884181.41 | 1713141.92 | 51717 |  |  | 13617755.605 | 12681857.195 | 935898.41 | N | Victor V. DeCastro Carlo | N/A | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered. | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. | 10629532.275 | 655524.41 | 1713141.92 | 51717 | 339183 | 228657 | 13617755.605 | 12681857.195 | 935898.41 | DSOW – Scope and Cost Update in Progress | Q2 FY2027 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. |  |  | 1 | 0 | 0 | 12681857.195 | 935898.41
678795 | FAASt [Arecibo Streetlighting] (Distribution) | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 11879105.0925 | 800134.36 | 1902215.74 | 59360 |  |  | 14640815.1925 | 13781320.8325 | 859494.36 | N | Victor V. DeCastro Carlo | N/A | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered. | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. | 11412143.0925 | 485336.36 | 1902215.74 | 59360 | 466962 | 314798 | 14640815.1925 | 13781320.8325 | 859494.36 | DSOW – Scope and Cost Update in Progress | Q1 FY2027 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. |  |  | 1 | 0 | 0 | 13781320.8325 | 859494.36
686482 | FAASt [Isabela Streetlighting] (Distribution) | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 6005455.39 | 671912.08 | 1332970.6 | 37797.8 |  |  | 8048135.87 | 7338425.99 | 709709.88 | N | Victor V. DeCastro Carlo | N/A | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered. | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. | 5745883.39 | 496924.08 | 1332970.6 | 37797.8 | 259572 | 174988 | 8048135.87 | 7338425.99 | 709709.88 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. |  |  | 1 | 0 | 0 | 7338425.99 | 709709.88
690480 | FAASt [Humacao Streetlighting] (Distribution) | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 6455271.8825 | 488325.81 | 1006696.36 | 29209 |  |  | 7979503.0525 | 7461968.2425 | 517534.81 | N | Victor V. DeCastro Carlo | N/A | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered. | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. | 6175629.8825 | 299807.81 | 1006696.36 | 29209 | 279642 | 188518 | 7979503.0525 | 7461968.2425 | 517534.81 | DSOW – Scope and Cost Update in Progress | Q1 FY2027 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. |  |  | 1 | 0 | 1 | 7461968.2425 | 517534.81
690483 | FAASt [Cayey Streetlighting] | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 10596790.82 | 1275717.24 | 2435204.39 | 95954.76 |  |  | 14403667.21 | 13031995.21 | 1371672 | N | Victor V. DeCastro Carlo | N/A | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered. | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. | 10093033.82 | 936114.24 | 2435204.39 | 95954.76 | 503757 | 339603 | 14403667.21 | 13031995.21 | 1371672 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. |  |  | 1 | 0 | 1 | 13031995.21 | 1371672
690721 | FAASt [Guayama Streetlighting] (Distribution) | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 4107291.015 | 305442.59 | 1011463.98 | 25642.92 |  |  | 5449840.505 | 5118754.995 | 331085.51 | N | Victor V. DeCastro Carlo | N/A | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered. | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. | 3974160.015 | 215693.59 | 1011463.98 | 25642.92 | 133131 | 89749 | 5449840.505 | 5118754.995 | 331085.51 | DSOW – Scope and Cost Update in Progress | Q1 FY2027 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. |  |  | 1 | 0 | 1 | 5118754.995 | 331085.51
693543 | FAASt [Juncos Streetlighting] (Distribution) | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 10994681.6975 | 685135.01 | 1631297.312 | 26436.06 |  |  | 13337550.0795 | 12625979.0095 | 711571.07 | N | Victor V. DeCastro Carlo | N/A | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered. | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. | 10405292.6975 | 287804.01 | 1631297.312 | 26436.06 | 589389 | 397331 | 13337550.0795 | 12625979.0095 | 711571.07 | DSOW – Scope and Cost Update in Progress | Q1 FY2027 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. |  |  | 1 | 0 | 1 | 12625979.0095 | 711571.07
693615 | [Rio Grande Streetlighting] (Distribution | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 5347407.42 | 397032.05 | 1156399.63 | 21533.62 |  |  | 6922372.72 | 6503807.05 | 418565.67 | N | Victor V. DeCastro Carlo | N/A | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered. | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. | 5156073.42 | 268046.05 | 1156399.63 | 21533.62 | 191334 | 128986 | 6922372.72 | 6503807.05 | 418565.67 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. |  |  | 1 | 0 | 0 | 6503807.05 | 418565.67
693788 | FAASt [Toa Alta Streetlighting] (Distribution) | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 4767387.52 | 197071.81 | 1162797.94 | 17891.57 |  |  | 6145148.84 | 5930185.46 | 214963.38 | N | Victor V. DeCastro Carlo | N/A | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered. | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. | 4596792.52 | 82066.81 | 1162797.94 | 17891.57 | 170595 | 115005 | 6145148.84 | 5930185.46 | 214963.38 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. |  |  | 1 | 0 | 0 | 5930185.46 | 214963.38
697183 | FAASt [Vega Baja Streetlighting] (Distribution) | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 8602549.46 | 1056851.66 | 1621313.74 | 17891.57 |  |  | 11298606.43 | 10223863.2 | 1074743.23 | N | Victor V. DeCastro Carlo | N/A | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered. | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. | 8233261.46 | 807899.66 | 1621313.74 | 17891.57 | 369288 | 248952 | 11298606.43 | 10223863.2 | 1074743.23 | DSOW – Scope and Cost Update in Progress | Q4 FY2027 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. |  |  | 1 | 0 | 0 | 10223863.2 | 1074743.23
698427 | [Maricao Streetlighting] (Distribution | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 4873133.615 | 921314.71 | 926826.7734 | 43337.3166 |  |  | 6764612.415 | 5799960.3884 | 964652.0266 | N | Victor V. DeCastro Carlo | N/A | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered. | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. | 4466381.615 | 647106.71 | 926826.7734 | 43337.3166 | 406752 | 274208 | 6764612.415 | 5799960.3884 | 964652.0266 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. |  |  | 1 | 0 | 0 | 5799960.3884 | 964652.0266
698432 | FAASt [Hormigueros Streetlighting] (Distribution) | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 5999141.915 | 489811.44 | 1362869.66 | 17724.97 |  |  | 7869547.985 | 7362011.575 | 507536.41 | N | Victor V. DeCastro Carlo | N/A | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered. | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. | 5694746.915 | 284606.44 | 1362869.66 | 17724.97 | 304395 | 205205 | 7869547.985 | 7362011.575 | 507536.41 | DSOW – Scope and Cost Update in Progress | Q4 FY2027 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. |  |  | 1 | 0 | 0 | 7362011.575 | 507536.41
698522 | [Vieques Streetlighting] (Distribution | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 3987957.0575 | 454616.91 | 810226.05 | 32120.4 |  |  | 5284920.4175 | 4798183.1075 | 486737.31 | N | Victor V. DeCastro Carlo | N/A | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered. | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. | 3791271.0575 | 322022.91 | 810226.05 | 32120.4 | 196686 | 132594 | 5284920.4175 | 4798183.1075 | 486737.31 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. |  |  | 1 | 0 | 0 | 4798183.1075 | 486737.31
699814 | FAASt [Juana Diaz Streetlighting] (Distribution) | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 14011750.655 | 872747.53 | 2795912.01 | 55146.97 |  |  | 17735557.165 | 16807662.665 | 927894.5 | N | Victor V. DeCastro Carlo | N/A | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered. | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. | 13267153.655 | 370784.53 | 2795912.01 | 55146.97 | 744597 | 501963 | 17735557.165 | 16807662.665 | 927894.5 | DSOW – Scope and Cost Update in Progress | Q1 FY2027 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. |  |  | 1 | 0 | 0 | 16807662.665 | 927894.5
701473 | FAASt [Canovanas Streetlighting] (Distribution) | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 11994894.83 | 1520521.43 | 2377385.56 | 89359.81 |  |  | 15982161.63 | 14372280.39 | 1609881.24 | N | Victor V. DeCastro Carlo | N/A | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered. | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. | 11399484.83 | 1119131.43 | 2377385.56 | 89359.81 | 595410 | 401390 | 15982161.63 | 14372280.39 | 1609881.24 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. |  |  | 1 | 0 | 0 | 14372280.39 | 1609881.24
704744 | [San Sebastian Streetlighting] (Distribution | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 21521273.585 | 1542129.95 | 4057973.95 | 94811.81 |  |  | 27216189.295 | 25579247.535 | 1636941.76 | N | Victor V. DeCastro Carlo | N/A | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered. | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. | 19955144.585 | 486338.95 | 4057973.95 | 94811.81 | 1566129 | 1055791 | 27216189.295 | 25579247.535 | 1636941.76 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. |  |  | 1 | 0 | 0 | 25579247.535 | 1636941.76
704757 | FAASt [Santa Isabel Streetlighting] (Distribution) | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 8526009.33 | 383038.38 | 1562084.58 | 22536.63 |  |  | 10493668.92 | 10088093.91 | 405575.01 | N | Victor V. DeCastro Carlo | N/A | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered. | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. | 8241015.33 | 190912.38 | 1562084.58 | 22536.63 | 284994 | 192126 | 10493668.92 | 10088093.91 | 405575.01 | DSOW – Scope and Cost Update in Progress | Q1 FY2027 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. |  |  | 1 | 0 | 0 | 10088093.91 | 405575.01
704793 | [Yauco Streetlighting] (Distribution | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 13232024.93 | 1588137.76 | 2540431.6 | 79529.34 |  |  | 17440123.63 | 15772456.53 | 1667667.1 | N | Victor V. DeCastro Carlo | N/A | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered. | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. | 12597812.93 | 1160589.76 | 2540431.6 | 79529.34 | 634212 | 427548 | 17440123.63 | 15772456.53 | 1667667.1 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. |  |  | 1 | 0 | 0 | 15772456.53 | 1667667.1
704862 | FAASt [Fajardo Streetlighting] (Distribution) | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 11073921.95 | 1052403.97 | 2150579.88 | 58676.25 |  |  | 14335582.05 | 13224501.83 | 1111080.22 | N | Victor V. DeCastro Carlo | N/A | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered. | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. | 10758153.95 | 839531.97 | 2150579.88 | 58676.25 | 315768 | 212872 | 14335582.05 | 13224501.83 | 1111080.22 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. |  |  | 1 | 0 | 0 | 13224501.83 | 1111080.22
704929 | [San Lorenzo Streetlighting] (Distribution | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 13787578.6125 | 968406.72 | 2944605.83 | 60896.29 |  |  | 17761487.4525 | 16732184.4425 | 1029303.01 | N | Victor V. DeCastro Carlo | N/A | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered. | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. | 12867034.6125 | 347830.72 | 2944605.83 | 60896.29 | 920544 | 620576 | 17761487.4525 | 16732184.4425 | 1029303.01 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. |  |  | 1 | 0 | 0 | 16732184.4425 | 1029303.01
704931 | FAASt [Camuy Streetlighting] (Distribution) | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 14028036.5825 | 867189.9 | 1972441.141 | 107984.699 |  |  | 16975652.3225 | 16000477.7235 | 975174.599 | N | Victor V. DeCastro Carlo | N/A | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered. | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. | 13069359.5825 | 220906.9 | 1972441.141 | 107984.699 | 958677 | 646283 | 16975652.3225 | 16000477.7235 | 975174.599 | DSOW – Scope and Cost Update in Progress | Q1 FY2027 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. |  |  | 1 | 0 | 0 | 16000477.7235 | 975174.599
724603 | FAASt [Cabo Rojo Streetlighting] (Distribution) | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 7308020.08 | 517830.31 | 1689593.17 | 41489.51 |  |  | 9556933.07 | 8997613.25 | 559319.82 | N | Victor V. DeCastro Carlo | N/A | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered. | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. | 6954788.08 | 279702.31 | 1689593.17 | 41489.51 | 353232 | 238128 | 9556933.07 | 8997613.25 | 559319.82 | DSOW – Scope and Cost Update in Progress | Q1 FY2027 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. |  |  | 1 | 0 | 1 | 8997613.25 | 559319.82
724828 | [Loiza Streetlighting] (Distribution | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 6213147.88 | 388351.58 | 1248099.37 | 14137.5 |  |  | 7863736.33 | 7461247.25 | 402489.08 | N | Victor V. DeCastro Carlo | N/A | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered. | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. | 5936181.88 | 201637.58 | 1248099.37 | 14137.5 | 276966 | 186714 | 7863736.33 | 7461247.25 | 402489.08 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. |  |  | 1 | 0 | 1 | 7461247.25 | 402489.08
724941 | [Aguas Buenas Streetlighting] (Distribution | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 12423846.45 | 585725.31 | 1646095.25 | 83021.58 |  |  | 14738688.59 | 14069941.7 | 668746.89 | N | Victor V. DeCastro Carlo | N/A | DSOW package complete.Ready to be sumitted, scope consider all construction phases. | DSOW package complete.Ready to be sumitted, scope consider all construction phases. | 11340397.36 | 201510.89 | 2036460.34 | 0 | 693084 | 467236 | 14738688.59 | 14069941.7 | 668746.89 | DSOW – Scope and Cost development in progress | Q1 FY2027 | DSOW package complete.Ready to be sumitted, scope consider all construction phases. |  |  | 1 | 0 | 1 | 14069941.7 | 668746.89
704741 | [Moca Streetlighting] (Distribution | Yes | Yes | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 19741562.46 | 976458.2 | 2533607.94 | 134366.43 |  |  | 23385995.03 | 22275170.4 | 1110824.63 | N | Victor V. DeCastro Carlo | N/A | DSOW package complete.Ready to be sumitted, scope consider all construction phases. | DSOW package complete.Ready to be sumitted, scope consider all construction phases. | 17932518.84 | 308495.64 | 3152500.55 | 0 | 1190151 | 802329 | 23385995.03 | 22275170.39 | 1110824.64 | DSOW – Scope and Cost development in progress | Q1 FY2027 | DSOW package complete.Ready to be sumitted, scope consider all construction phases. |  |  | 1 | 0 | 0 | 22275170.4 | 1110824.63
724605 | [Guayanilla Streetlighting] (Distribution | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 8485594.47 | 412336.03 | 1106363.96 | 57568.51 |  |  | 10061862.97 | 9591958.43 | 469904.54 | N | Victor V. DeCastro Carlo | N/A | DSOW package complete.Ready to be sumitted, scope consider all construction phases. | DSOW package complete.Ready to be sumitted, scope consider all construction phases. | 7795083.32 | 183970.54 | 1372729.11 | 0 | 424146 | 285934 | 10061862.97 | 9591958.43 | 469904.54 | DSOW – Scope and Cost development in progress | Q1 FY2027 | DSOW package complete.Ready to be sumitted, scope consider all construction phases. |  |  | 1 | 0 | 1 | 9591958.43 | 469904.54
724599 | [Sabana Grande Streetlighting] (Distribution | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 11849851.49 | 636889.83 | 1536485.07 | 88808.54 |  |  | 14112034.93 | 13386336.56 | 725698.37 | N | Victor V. DeCastro Carlo | N/A | DSOW package complete.Ready to be sumitted, scope consider all construction phases. | DSOW package complete.Ready to be sumitted, scope consider all construction phases. | 10754272.51 | 236814.37 | 1906868.06 | 0 | 725196 | 488884 | 14112034.94 | 13386336.57 | 725698.37 | DSOW – Scope and Cost development in progress | Q1 FY2027 | DSOW package complete.Ready to be sumitted, scope consider all construction phases. |  |  | 1 | 0 | 0 | 13386336.56 | 725698.37
724669 | [Ciales Streetlighting] (Distribution | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 13170687.29 | 682982.51 | 1629722.94 | 90151.24 |  |  | 15573543.98 | 14800410.23 | 773133.75 | N | Victor V. DeCastro Carlo | N/A | DSOW package complete.Ready to be sumitted, scope consider all construction phases. | DSOW package complete.Ready to be sumitted, scope consider all construction phases. | 12013750.42 | 272974.74 | 2044738.82 | 0 | 741921 | 500159 | 15573543.98 | 14800410.24 | 773133.74 | DSOW – Scope and Cost development in progress | Q1 FY2027 | DSOW package complete.Ready to be sumitted, scope consider all construction phases. |  |  | 1 | 0 | 1 | 14800410.23 | 773133.75
724716 | [Quebradillas Streetlighting] (Distribution | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 11505789.6 | 550706.35 | 1511148.92 | 77403.68 |  |  | 13645048.55 | 13016938.52 | 628110.03 | N | Victor V. DeCastro Carlo | N/A | DSOW package complete.Ready to be sumitted, scope consider all construction phases. | DSOW package complete.Ready to be sumitted, scope consider all construction phases. | 10502157.5 | 195150.03 | 1872541.02 | 0 | 642240 | 432960 | 13645048.55 | 13016938.52 | 628110.03 | DSOW – Scope and Cost development in progress | Q1 FY2027 | DSOW package complete.Ready to be sumitted, scope consider all construction phases. |  |  | 1 | 0 | 1 | 13016938.52 | 628110.03
713795 | [Lares Streetlighting] (Distribution | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 13027118.33 | 631320.8 | 1563494.51 | 80701.22 |  |  | 15302634.86 | 14590612.84 | 712022.02 | N | Victor V. DeCastro Carlo | N/A | DSOW package complete.Ready to be sumitted, scope consider all construction phases. | DSOW package complete.Ready to be sumitted, scope consider all construction phases. | 11882095.1 | 217275.01 | 1974624.75 | 0 | 733893 | 494747 | 15302634.86 | 14590612.85 | 712022.01 | DSOW – Scope and Cost development in progress | Q1 FY2027 | DSOW package complete.Ready to be sumitted, scope consider all construction phases. |  |  | 1 | 0 | 0 | 14590612.84 | 712022.02
724670 | [Patillas Streetlighting] (Distribution | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 9123256.82 | 358025.92 | 1167539.54 | 48560.66 |  |  | 10697382.94 | 10290796.36 | 406586.58 | N | Victor V. DeCastro Carlo | N/A | DSOW package complete.Ready to be sumitted, scope consider all construction phases. | DSOW package complete.Ready to be sumitted, scope consider all construction phases. | 8408428.82 | 119750.59 | 1456883.53 | 0 | 425484 | 286836 | 10697382.94 | 10290796.35 | 406586.59 | DSOW – Scope and Cost development in progress | Q1 FY2027 | DSOW package complete.Ready to be sumitted, scope consider all construction phases. |  |  | 1 | 0 | 1 | 10290796.36 | 406586.58
724781 | [Penuelas Streetlighting] (Distribution | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 8600953.35 | 357444.72 | 1159987.24 | 51045.69 |  |  | 10169431 | 9760940.59 | 408490.41 | N | Victor V. DeCastro Carlo | N/A | DSOW package complete.Ready to be sumitted, scope consider all construction phases. | DSOW package complete.Ready to be sumitted, scope consider all construction phases. | 7929864.73 | 140145.41 | 1433020.87 | 0 | 398055 | 268345 | 10169431.01 | 9760940.6 | 408490.41 | DSOW – Scope and Cost development in progress | Q1 FY2027 | DSOW package complete.Ready to be sumitted, scope consider all construction phases. |  |  | 1 | 0 | 1 | 9760940.59 | 408490.41
735357 | FAASt [Mayaguez Streetlighting - Part 2] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 2005600 | 0 | 330319.93 | 0 | 0 | 0 | 2335919.93 | 2335919.93 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 1744 only components scope. Poles location will be reduced, estimated of: 516 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 1744 only components scope. Poles location will be reduced, estimated of: 516 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
746108 | FAASt [San Juan Streetlighting - Part 2] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 7814250 | 0 | 825170.91 | 0 | 0 | 0 | 8639420.91 | 8639420.91 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 6795 only components scope. Poles location will be reduced, estimated of: 1231 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 6795 only components scope. Poles location will be reduced, estimated of: 1231 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
735131 | FAASt [Arecibo Streetlighting - Part 2] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 3149850 | 0 | 503094.78 | 0 | 0 | 0 | 3652944.78 | 3652944.78 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 2739 only components scope. Poles location will be reduced, estimated of: 981 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 2739 only components scope. Poles location will be reduced, estimated of: 981 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
746111 | FAASt [Caguas Streetlighting - Part 2] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 3646650 | 0 | 508288.97 | 0 | 0 | 0 | 4154938.97 | 4154938.97 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 3171 only components scope. Poles location will be reduced, estimated of: 595 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 3171 only components scope. Poles location will be reduced, estimated of: 595 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
735665 | FAASt [Carolina Streetlighting - Part 2] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 4328600 | 0 | 795422.75 | 0 | 0 | 0 | 5124022.75 | 5124022.75 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 3764 only components scope. Poles location will be reduced, estimated of: 258 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 3764 only components scope. Poles location will be reduced, estimated of: 258 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
734728 | FAASt [Ponce Streetlighting - Part 2] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 3681150 | 0 | 576959.77 | 0 | 0 | 0 | 4258109.77 | 4258109.77 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 3201 only components scope. Poles location will be reduced, estimated of: 742 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 3201 only components scope. Poles location will be reduced, estimated of: 742 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
735954 | FAASt [Trujillo Alto Streetlighting - Part 2] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 1817000 | 0 | 251430.18 | 0 | 0 | 0 | 2068430.18 | 2068430.18 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 1580 only components scope. Poles location will be reduced, estimated of: 505 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 1580 only components scope. Poles location will be reduced, estimated of: 505 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
734859 | FAASt [Aguadilla Streetlighting - Part 2] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 2010200 | 0 | 299127.03 | 0 | 0 | 0 | 2309327.03 | 2309327.03 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 1748 only components scope. Poles location will be reduced, estimated of: 859 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 1748 only components scope. Poles location will be reduced, estimated of: 859 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
735470 | FAASt [Bayamón Streetlighting - Part 2] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 5318750 | 0 | 704446.74 | 0 | 0 | 0 | 6023196.74 | 6023196.74 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 4625 only components scope. Poles location will be reduced, estimated of: 710 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 4625 only components scope. Poles location will be reduced, estimated of: 710 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
734791 | FAASt [Guayama Streetlighting - Part 2] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 1756050 | 0 | 444662.71 | 0 | 0 | 0 | 2200712.71 | 2200712.71 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 1527 only components scope. Poles location will be reduced, estimated of: 400 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 1527 only components scope. Poles location will be reduced, estimated of: 400 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
735493 | FAASt [Humacao Streetlighting - Part 2] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 1826200 | 0 | 324830.45 | 0 | 0 | 0 | 2151030.45 | 2151030.45 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 1589 only components scope. Poles location will be reduced, estimated of: 548 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 1589 only components scope. Poles location will be reduced, estimated of: 548 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
734927 | FAASt [Isabela Streetlighting - Part 2] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 1552500 | 0 | 306973.5 | 0 | 0 | 0 | 1859473.5 | 1859473.5 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 1350 only components scope. Poles location will be reduced, estimated of: 846 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 1350 only components scope. Poles location will be reduced, estimated of: 846 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
737804 | FAASt [Rio Grande Streetlighting - Part 2 ] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 1788250 | 0 | 279529.57 | 0 | 0 | 0 | 2067779.57 | 2067779.57 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 1555 only components scope. Poles location will be reduced, estimated of: 451 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 1555 only components scope. Poles location will be reduced, estimated of: 451 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
737707 | FAASt [Toa Alta Streetlighting - Part 2] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 2219500 | 0 | 364572.61 | 0 | 0 | 0 | 2584072.61 | 2584072.61 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 1930 only components scope. Poles location will be reduced, estimated of: 565 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 1930 only components scope. Poles location will be reduced, estimated of: 565 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
734393 | FAASt [Cabo Rojo Streetlighting - Part 2] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 2168900 | 0 | 368432.14 | 0 | 0 | 0 | 2537332.14 | 2537332.14 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 1886 only components scope. Poles location will be reduced, estimated of: 633 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 1886 only components scope. Poles location will be reduced, estimated of: 633 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
735677 | FAASt [Guaynabo Streetlighting - Part 2] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 1935450 | 0 | 384791.84 | 0 | 0 | 0 | 2320241.84 | 2320241.84 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 1683 only components scope. Poles location will be reduced, estimated of: 597 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 1683 only components scope. Poles location will be reduced, estimated of: 597 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
735960 | FAASt [Toa Baja Streetlighting - Part 2] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 1461650 | 0 | 311784.53 | 0 | 0 | 0 | 1773434.53 | 1773434.53 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 1271 only components scope. Poles location will be reduced, estimated of: 767 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 1271 only components scope. Poles location will be reduced, estimated of: 767 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
735940 | FAASt [Vega Baja Streetlighting - Part 2] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 1896350 | 0 | 313451.11 | 0 | 0 | 0 | 2209801.11 | 2209801.11 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 1649 only components scope. Poles location will be reduced, estimated of: 590 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 1649 only components scope. Poles location will be reduced, estimated of: 590 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
735360 | FAASt [Mayaguez Streetlighting - Part 3] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 2967000 | 0 | 934399.04 | 0 | 0 | 0 | 3901399.04 | 3901399.04 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 2580 only components scope. Poles location will be reduced, estimated of: 1427 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 2580 only components scope. Poles location will be reduced, estimated of: 1427 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
737712 | FAAST [San Juan Streetlighting - Part 3] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 7826900 | 0 | 1103286.53 | 0 | 0 | 0 | 8930186.53 | 8930186.53 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 6847 only components scope. Poles location will be reduced, estimated of: 1478 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 6847 only components scope. Poles location will be reduced, estimated of: 1478 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
734853 | FAASt [Arecibo Streetlighting- Part 3] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 2778400 | 0 | 570030.05 | 0 | 0 | 0 | 3348430.05 | 3348430.05 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 2416 only components scope. Poles location will be reduced, estimated of: 1788 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 2416 only components scope. Poles location will be reduced, estimated of: 1788 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
735672 | FAASt [Caguas Streetlighting - Part 3] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 3448850 | 0 | 752635.32 | 0 | 0 | 0 | 4201485.32 | 4201485.32 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 2999 only components scope. Poles location will be reduced, estimated of: 1053 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 2999 only components scope. Poles location will be reduced, estimated of: 1053 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
735496 | FAASt [Carolina Streetlighting - Part 3] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 3936450 | 0 | 684791.58 | 0 | 0 | 0 | 4621241.58 | 4621241.58 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 3423 only components scope. Poles location will be reduced, estimated of: 1143 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 3423 only components scope. Poles location will be reduced, estimated of: 1143 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
734760 | FAASt [Ponce Streetlighting - Part 3] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 3221150 | 0 | 700990.05 | 0 | 0 | 0 | 3922140.05 | 3922140.05 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 2801 only components scope. Poles location will be reduced, estimated of: 1229 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 2801 only components scope. Poles location will be reduced, estimated of: 1229 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
735952 | FAASt [Trujillo Alto Streetlighting - Part 3] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 1597350 | 0 | 369585.51 | 0 | 0 | 0 | 1966935.51 | 1966935.51 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 1388 only components scope. Poles location will be reduced, estimated of: 732 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 1388 only components scope. Poles location will be reduced, estimated of: 732 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
735338 | FAASt [Aguadilla Streetlighting - Part 3] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 1401850 | 0 | 313621.72 | 0 | 0 | 0 | 1715471.72 | 1715471.72 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 1219 only components scope. Poles location will be reduced, estimated of: 915 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 1219 only components scope. Poles location will be reduced, estimated of: 915 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
735472 | FAASt [Bayamon Streetlighting - Part 3] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 4418300 | 0 | 739172.36 | 0 | 0 | 0 | 5157472.36 | 5157472.36 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 3842 only components scope. Poles location will be reduced, estimated of: 1626 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 3842 only components scope. Poles location will be reduced, estimated of: 1626 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
734789 | FAASt [Guayama Streetlighting - Part 3 ] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 1679000 | 0 | 285214.71 | 0 | 0 | 0 | 1964214.71 | 1964214.71 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 1460 only components scope. Poles location will be reduced, estimated of: 362 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 1460 only components scope. Poles location will be reduced, estimated of: 362 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
735487 | FAASt [Humacao Streetlighting - Part 3] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 1498450 | 0 | 282005.08 | 0 | 0 | 0 | 1780455.08 | 1780455.08 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 1303 only components scope. Poles location will be reduced, estimated of: 636 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 1303 only components scope. Poles location will be reduced, estimated of: 636 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
734928 | FAASt [Isabela Streetlighting - Part 3] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 1163800 | 0 | 325113.23 | 0 | 0 | 0 | 1488913.23 | 1488913.23 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 1012 only components scope. Poles location will be reduced, estimated of: 626 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 1012 only components scope. Poles location will be reduced, estimated of: 626 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
737798 | FAASt [Rio Grande Streetlighting - Part 3] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 1212100 | 0 | 239093.65 | 0 | 0 | 0 | 1451193.65 | 1451193.65 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 1054 only components scope. Poles location will be reduced, estimated of: 545 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 1054 only components scope. Poles location will be reduced, estimated of: 545 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
737699 | FAASt [Toa Alta Streetlighting - Part 3] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 1058000 | 0 | 221137.35 | 0 | 0 | 0 | 1279137.35 | 1279137.35 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 920 only components scope. Poles location will be reduced, estimated of: 346 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 920 only components scope. Poles location will be reduced, estimated of: 346 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
734396 | FAASt [Cabo Rojo Streetlighting - Part 3] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 1246600 | 0 | 279407 | 0 | 0 | 0 | 1526007 | 1526007 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 1084 only components scope. Poles location will be reduced, estimated of: 743 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 1084 only components scope. Poles location will be reduced, estimated of: 743 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
735499 | FAASt [Guaynabo Streetlighting - Part 3] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 1838850 | 0 | 375286.43 | 0 | 0 | 0 | 2214136.43 | 2214136.43 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 1599 only components scope. Poles location will be reduced, estimated of: 904 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 1599 only components scope. Poles location will be reduced, estimated of: 904 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
735959 | FAASt [Toa Baja Streetlighting - Part 3] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 1317900 | 0 | 300491.01 | 0 | 0 | 0 | 1618391.01 | 1618391.01 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 1146 only components scope. Poles location will be reduced, estimated of: 571 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 1146 only components scope. Poles location will be reduced, estimated of: 571 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
735483 | FAASt [Vega Baja Streetlighting - Part 3] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 1308700 | 0 | 265069.11 | 0 | 0 | 0 | 1573769.11 | 1573769.11 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 1138 only components scope. Poles location will be reduced, estimated of: 663 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 1138 only components scope. Poles location will be reduced, estimated of: 663 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
812041 | [Feeder Rebuild # 9501-02] (Distribution | No | No | Distribution | Rebuild | No | Inactive | Inactive | 22571513.15 |  | 3314820.98 |  | 3357740.92 |  | 29244075.05 | 29244075.05 | 0 | No | Victor V. DeCastro Carlo | N/A | Project was under FEMA Workflow EHP evaluation before being withdrawn. This feeder has a CMI of 5.96M, Engineering stages are nearing completion for DSOW submission. (Replacement for 6012-02 CMI 4.8M) | Project was under FEMA Workflow EHP evaluation before being withdrawn. This feeder has a CMI of 5.96M, Engineering stages are nearing completion for DSOW submission. (Replacement for 6012-02 CMI 4.8M) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
754350 | Distribution Underground Circuit Feeders - San Juan Group 1 | No | No | Distribution | Underground | No | Inactive | Inactive | 4310111.715 | 9577521.9267 | 362956.776 | 812115.7863 | 1512.3199 | 58980.4761 | 15123199 | 4674580.8109 | 10448618.1891 | No | Victor V. DeCastro Carlo | N/A | Pending Operation Assessment, and design work has not yet been finalized. Further evaluation is required before moving forward. | Pending Operation Assessment, and design work has not yet been finalized. Further evaluation is required before moving forward. | 4310111.715 | 9577521.9267 | 362956.776 | 812115.7863 | 1512.3199 | 58980.4761 | 15123199 | 4674580.8109 | 10448618.1891 | DSOW – Pending Design Package for Development | Q1 FY2028 | Pending Operation Assessment, and design work has not yet been finalized. Further evaluation is required before moving forward. |  |  | 1 | 0 | 0 | 0 | 0
754351 | ​Distribution Underground Circuit Feeders - San Juan Group 2 | No | No | Distribution | Underground | No | Inactive | Inactive | 2013990.405 | 4475298.6789 | 169599.192 | 379478.1921 | 706.6633 | 27559.8687 | 7066633 | 2184296.2603 | 4882336.7397 | No | Victor V. DeCastro Carlo | N/A | Pending Operation Assessment, and design work has not yet been finalized. Further evaluation is required before moving forward. | Pending Operation Assessment, and design work has not yet been finalized. Further evaluation is required before moving forward. | 2013990.405 | 4475298.6789 | 169599.192 | 379478.1921 | 706.6633 | 27559.8687 | 7066633 | 2184296.2603 | 4882336.7397 | DSOW – Pending Design Package for Development | Q1 FY2028 | Pending Operation Assessment, and design work has not yet been finalized. Further evaluation is required before moving forward. |  |  | 1 | 0 | 0 | 0 | 0
718971 | FAASt [Line 50300 (230kV) from Costa Sur Steam Plant to Aguirre Steam Plant] (Transmission) | No | No | Transmission | Line Rebuild | No | Inactive | Inactive | 9936000 | 5400000 | 864000 | 864000 | 1296000 | 3240000 | 21600000 | 12096000 | 9504000 | N | Hector S. / Daniel H. | N/A | Project Not Obligated | No change to last submitted information. | 9936000 | 5400000 | 864000 | 864000 | 1296000 | 3240000 | 21600000 | 12096000 | 9504000 | DSOW – Pending Design Package for Development | Q3 FY2027 | This line is key for hardening by replacing targeted structures as well as insulators and hardware along the entire line length, with a high-level estimate at $30M. Additional future scope proposed for 406 includes adding a 230/115kV new substation at Santa Isabel TC which would significantly reduce the exposure (probability and likelihood that the facility is not available after a storm) as well as facilitate a pathway for new large-scale renewables being added in the South and Southeast regions. |  |  | 1 | 0 | 0 | 0 | 0
730657 | [Line 2200 Dos Bocas HP to Dorado TC ] (Transmission | No | No | Transmission | Line Rebuild | No | Inactive | Inactive | 57872010.7354 | 31452179.7475 | 5032348.7596 | 5032348.7596 | 7548523.1394 | 18871307.8485 | 125808718.99 | 70452882.6344 | 55355836.3556 | N | Hector S. / Daniel H. | N/A | Project Not Obligated | No change to last submitted information. | 57872010.7354 | 31452179.7475 | 5032348.7596 | 5032348.7596 | 7548523.1394 | 18871307.8485 | 125808718.99 | 70452882.6344 | 55355836.3556 | DSOW – Pending Design Package for Development | Q3 FY2027 | The planned scope for this facility is first to rebuild the undersized segment from Manati to Vega Baja to achieve a capacity increase to a minimum of 1160A. The proposed second phase is to restore the out-of-service segment from Dos Bocas to Cambalache. As requested by PMs based on latest value engineering, 3 segments were selected (1, 7 & 8) |  |  | 1 | 0 | 0 | 0 | 0
753785 | TPole 3300 San Gerardo Sect to Venezuela Sect | Yes | Yes | Transmission | Transmission Priority Pole Replacements | No | Inactive | Inactive | 299085.29 | 81090.53 | 55226.85 | 14556.86 | 12296.95 | 1013.73 | 463270.21 | 366609.09 | 96661.12 | N | Carlos Samalot | N/A | Project Not Obligated | Cost Estimate and DSOW have been updated to latest template and are ready for submittal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
753786 (1066980) | TPole 5900 San Juan SP to Crematorio TO | Yes | Yes | Transmission | Transmission Priority Pole Replacements | No | Active | Active | 407830.94 | 1921.02 | 77598.93 | 1382.15 | 40781.7 | 6101.3 | 535616.04 | 526211.57 | 9404.47 | Y | Carlos Samalot | N/A | Project Not Obligated | Cost Estimate and DSOW have been updated to latest template and are ready for submittal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 0 | 0 | Anadir numero nuevo
753787 | TPole 13700 Mora TC to Isabela TO | Yes | Yes | Transmission | Transmission Priority Pole Replacements | No | Inactive | Inactive | 591148.31 | 7196.15 | 103198.13 | 1529 | 35991.1 | 2143.44 | 741206.13 | 730337.54 | 10868.59 | Y | Carlos Samalot | N/A | Project Not Obligated | Cost Estimate and DSOW have been updated to latest template and are ready for submittal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
811923 (1066730) | Transmission Priority Pole Replacement Program Line 16500 Fajardo TC-Dos Marinas | Yes | Yes | Transmission | Transmission Priority Pole Replacements | No | Active | Active | 212650.88 | 381.28 | 48267.18 | 305.98 | 37102.11 | 1220.26 | 299927.69 | 298020.17 | 1907.52 | Y | Carlos Samalot | N/A | Project Not Obligated | Cost Estimate and DSOW have been updated to latest template and are ready for submittal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 0 | 0 | Anadir numero nuevo
1064452 | Transmission Priority Pole Replacement Program Line 800 Comsat Sect –Cidra Sect (Active) | No | No | Transmission | Transmission Priority Pole Replacements | No | Inactive | Inactive | 609182.23 | 2812.61 | 110189.24 | 1928.4 | 52018.89 | 8792.11 | 784923.48 | 771390.36 | 13533.12 | Y | Carlos Samalot | N/A | Project Not Obligated | The project has been activated by FEMA, and the updated LPCE has been submitted as stated by the Asset Lead. This project has been given a new project number; refer to column A information. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
TBD | Tline 8700 / TL1100 | No | No | Transmission | Line Rebuild | No | Inactive | Inactive | [6 empty] | 40000000 | 0 | 0 | N | Daniel H. | N/A | Project Not Obligated | Project cost is based on a budgetary estimate of ($40M). The 406 HM cost allocation is due to the project serving as a mitigation for generation, as requested by PREB. The project is currently undergoing a technical review between LUMA and PREPA to define the optimal scope for moving forward with execution. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
741097 | Region 1 San Juan Substation/Telecom | No | No | Vegetation | Vegetation | No | Inactive | Inactive | 0 | 867756.78 | 0 | 479435.25 | 0 | 0 | 1347192.03 | 0 | 1347192.03 | N | Rene Baptiste | No amendment needed in these set of projects. | No Comment. Will not be revisited. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
741098 | Region 3 Bayamon Substation/Telecom | No | No | Vegetation | Vegetation | No | Inactive | Inactive | 0 | 169300.95 | 0 | 93538.61 | 0 | 0 | 262839.56 | 0 | 262839.56 | N | Rene Baptiste | No amendment needed in these set of projects. | No Comment. Will not be revisited. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
741102 | Region 5 Mayaguez Substation/Telecom | No | No | Vegetation | Vegetation | No | Inactive | Inactive | 0 | 619336 | 0 | 342183 | 0 | 0 | 961519 | 0 | 961519 | N | Rene Baptiste | No amendment needed in these set of projects. | No Comment. Will not be revisited. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
741101 | Region 2 Arecibo Substation/Telecom | No | No | Vegetation | Vegetation | No | Inactive | Inactive | 0 | 69780.78 | 0 | 38554.25 | 0 | 0 | 108335.03 | 0 | 108335.03 | N | Rene Baptiste | No amendment needed in these set of projects. | No Comment. Will not be revisited. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
741104 | Region 6 Ponce Substation/Telecom | No | No | Vegetation | Vegetation | No | Inactive | Inactive | 0 | 977124.29 | 0 | 539861.35 | 0 | 0 | 1516985.64 | 0 | 1516985.64 | N | Rene Baptiste | No amendment needed in these set of projects. | No Comment. Will not be revisited. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
741100 | Region 4 Caguas Substation/Telecom | No | No | Vegetation | Vegetation | No | Inactive | Inactive | 0 | 1283718.51 | 0 | 709255.11 | 0 | 0 | 1992973.62 | 0 | 1992973.62 | N | Rene Baptiste | No amendment needed in these set of projects. | No Comment. Will not be revisited. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Pending FASSt | FAASt [Region 6 Ponce Distribution sensitive areas] (Vegetation) | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 42934620.7125 | 117568634.2875 | - | - | - | - | 160503255 | 42934620.7125 | 117568634.2875 | N | Rene Baptiste | No amendment needed in these set of projects. | No comment. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Pending FASSt | FAASt [Region 5 Mayaguez Distribution sensitive areas] (Vegetation) | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 58330775.8125 | 159728199.1875 | - | - | - | - | 218058975 | 58330775.8125 | 159728199.1875 | N | Rene Baptiste | No amendment needed in these set of projects. | No comment. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Pending FASSt | FAASt [Region 2 Arecibo Distribution sensitive areas] (Vegetation) | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 50485034.25 | 138244065.75 | - | - | - | - | 188729100 | 50485034.25 | 138244065.75 | N | Rene Baptiste | No amendment needed in these set of projects. | No comment. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Pending FASSt | FAASt [Region 4 Caguas Distribution sensitive areas] (Vegetation) | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 44184703.05 | 120991756.95 | - | - | - | - | 165176460 | 44184703.05 | 120991756.95 | N | Rene Baptiste | No amendment needed in these set of projects. | No comment. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Pending FASSt | FAASt [Region 3 Bayamon Distribution sensitive areas] (Vegetation) | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 9021119.175 | 24702690.825 | - | - | - | - | 33723810 | 9021119.175 | 24702690.825 | N | Rene Baptiste | No amendment needed in these set of projects. | No comment. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Pending FASSt | FAASt [Region 1 San Juan Distribution sensitive areas] (Vegetation) | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 36635336.775 | 100319193.225 | - | - | - | - | 136954530 | 36635336.775 | 100319193.225 | N | Rene Baptiste | No amendment needed in these set of projects. | No comment. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
727691 | FAASt [Region 1 San Juan Transmission 38kV sensitive areas] (Vegetation) - Group C | Yes | No | Vegetation | Vegetation-TL | No | Inactive | Inactive | 788376.99 | 8663674.704 | 6629.484 | 72765.402 | 0 | 0 | 9531446.58 | 795006.474 | 8736440.106 | Y | Rene Baptiste | Amendments might apply in future versions. | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. | No updated comment, previous comment remains. | 1313961.65 | 14439457.84 | 11049.14 | 121275.67 | 0 | 0 | 15885744.3 | 1325010.79 | 14560733.51 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | Project is developed and will be ready to submit to FEMA as soon as projects are reactivated in Grants Portal |  |  | 1 | 0 | 0 | 795006.474 | 8736440.106
740406 | FAASt[Region 1 San Juan Transmission 38kV - Non-Sensitive (Vegetation)] - Group B | Yes | Yes | Vegetation | Vegetation-TL | No | Inactive | Inactive | 281264.03 | 3116841.11 | 2365.12 | 25959.59 | 0 | 0 | 3426429.85 | 283629.15 | 3142800.7 | N | Rene Baptiste | Amendments might apply in future versions. | No comments. Projects already submitted to PREPA. | No updated comment, previous comment remains. | 281345.36 | 3091775.16 | 2365.85 | 25967.52 | 0 | 0 | 3401453.89 | 283711.21 | 3117742.68 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | Project is developed and will be ready to submit to FEMA as soon as projects are reactivated in Grants Portal |  |  | 1 | 0 | 0 | 283629.15 | 3142800.7
740410 | FAASt[Region 2 Arecibo Transmission 38kV - Non-Sensitive (Vegetation)]- Group B | Yes | Yes | Vegetation | Vegetation-TL | No | Inactive | Inactive | 21352.15 | 236614.32 | 179.55 | 1970.74 | 0 | 0 | 260116.76 | 21531.7 | 238585.06 | N | Rene Baptiste | Amendments might apply in future versions. | No comments. Projects already submitted to PREPA. | No updated comment, previous comment remains. | 251201.23 | 2760513.52 | 2112.36 | 23185.29 | 0 | 0 | 3037012.4 | 253313.59 | 2783698.81 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | Project is developed and will be ready to submit to FEMA as soon as projects are reactivated in Grants Portal |  |  | 1 | 0 | 0 | 21531.7 | 238585.06
740409 | FAASt[Region 4 Caguas Transmission 38kV - Non-Sensitive (Vegetation)]- Group B | Yes | Yes | Vegetation | Vegetation-TL | No | Inactive | Inactive | 715385.11 | 7927576.7 | 6901584.83 | 66028.4 | 0 | 0 | 15610575.04 | 7616969.94 | 7993605.1 | N | Rene Baptiste | Amendments might apply in future versions. | No comments. Projects already submitted to PREPA. | No updated comment, previous comment remains. | 715385.11 | 7927576.7 | 6015.7 | 66028.4 | 0 | 0 | 8715005.91 | 721400.81 | 7993605.1 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | Project is developed and will be ready to submit to FEMA as soon as projects are reactivated in Grants Portal |  |  | 1 | 0 | 0 | 7616969.94 | 7993605.1
740414 | FAASt [Region 6 Ponce Transmission 38kV - Non-Sensitive (Vegetation)- Group B | Yes | Yes | Vegetation | Vegetation-TL | No | Inactive | Inactive | 141749.28 | 1570801.41 | 1191.98 | 13083.11 | 0 | 0 | 1726825.78 | 142941.26 | 1583884.52 | N | Rene Baptiste | Amendments might apply in future versions. | No comments. Projects already submitted to PREPA. | No updated comment, previous comment remains. | 799358.09 | 8784348.55 | 6721.82 | 73778.93 | 0 | 0 | 9664207.39 | 806079.91 | 8858127.48 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | Project is developed and will be ready to submit to FEMA as soon as projects are reactivated in Grants Portal |  |  | 1 | 0 | 0 | 142941.26 | 1583884.52
727694 | FAASt [Region 4 Caguas Transmission 38kV sensitive areas] (Vegetation) - Group C | Yes | No | Vegetation | Vegetation-TL | No | Inactive | Inactive | 437628.366 | 4809208.998 | 3680.034 | 40392.096 | 0 | 0 | 5290909.494 | 441308.4 | 4849601.094 | Y | Rene Baptiste | Amendments might apply in future versions. | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. | No updated comment, previous comment remains. | 729380.61 | 8015348.33 | 6133.39 | 67320.16 | 0 | 0 | 8818182.49 | 735514 | 8082668.49 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | Project is developed and will be ready to submit to FEMA as soon as projects are reactivated in Grants Portal |  |  | 1 | 0 | 0 | 441308.4 | 4849601.094
740411 | FAASt [Region 5 Mayaguez Transmission 38kV - Non-Sensitive (Vegetation)]- Group B | Yes | Yes | Vegetation | Vegetation-TL | No | Inactive | Inactive | 799358.09 | 8858127.48 | 6721.82 | 73778.93 | 0 | 0 | 9737986.32 | 806079.91 | 8931906.41 | N | Rene Baptiste | Amendments might apply in future versions. | No comments. Projects already submitted to PREPA. | No updated comment, previous comment remains. | 141749.28 | 1557718.3 | 1191.98 | 13083.11 | 0 | 0 | 1713742.67 | 142941.26 | 1570801.41 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | Project is developed and will be ready to submit to FEMA as soon as projects are reactivated in Grants Portal |  |  | 1 | 0 | 0 | 806079.91 | 8931906.41
727562 | FAASt [Region 5 Mayaguez Transmission 38kV sensitive areas] (Vegetation) - Group C | Yes | No | Vegetation | Vegetation-TL | No | Inactive | Inactive | 1232141.82 | 13540319.136 | 10361.1 | 113723.898 | 0 | 0 | 14896545.954 | 1242502.92 | 13654043.034 | Y | Rene Baptiste | Amendments might apply in future versions. | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. | No updated comment, previous comment remains. | 2053569.7 | 22567198.56 | 17268.5 | 189539.83 | 0 | 0 | 24827576.59 | 2070838.2 | 22756738.39 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | Project is developed and will be ready to submit to FEMA as soon as projects are reactivated in Grants Portal |  |  | 1 | 0 | 0 | 1242502.92 | 13654043.034
727530 | FAASt [Region 6 Ponce Transmission 38kV sensitive areas] (Vegetation) - Group C | Yes | No | Vegetation | Vegetation-TL | No | Inactive | Inactive | 1367036.856 | 15022714.938 | 11495.436 | 126174.408 | 0 | 0 | 16527421.638 | 1378532.292 | 15148889.346 | Y | Rene Baptiste | Amendments might apply in future versions. | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. | No updated comment, previous comment remains. | 2278394.76 | 25037858.23 | 19159.06 | 210290.68 | 0 | 0 | 27545702.73 | 2297553.82 | 25248148.91 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | Project is developed and will be ready to submit to FEMA as soon as projects are reactivated in Grants Portal |  |  | 1 | 0 | 0 | 1378532.292 | 15148889.346
727540 | FAASt [Region 2 Arecibo Transmission 38kV sensitive areas] (Vegetation) - Group C | Yes | No | Vegetation | Vegetation-TL | No | Inactive | Inactive | 1105536.432 | 12149020.278 | 9296.478 | 102038.502 | 0 | 0 | 13365891.69 | 1114832.91 | 12251058.78 | Y | Rene Baptiste | Amendments might apply in future versions. | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. | No updated comment, previous comment remains. | 1842560.72 | 20248367.13 | 15494.13 | 170064.17 | 0 | 0 | 22276486.15 | 1858054.85 | 20418431.3 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | Project is developed and will be ready to submit to FEMA as soon as projects are reactivated in Grants Portal |  |  | 1 | 0 | 0 | 1114832.91 | 12251058.78
740408 | FAASt[Region 3 Bayamon Transmission 38kV - Non-Sensitive (Vegetation)]- Group B | Yes | Yes | Vegetation | Vegetation-TL | No | Inactive | Inactive | 622799.54 | 6901584.83 | 5237.14 | 57482.97 | 0 | 0 | 7587104.48 | 628036.68 | 6959067.8 | N | Rene Baptiste | Amendments might apply in future versions. | No comment. | No updated comment, previous comment remains. | 666580.3 | 7325219.95 | 5605.29 | 61523.84 | 0 | 0 | 8058929.38 | 672185.59 | 7386743.79 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | Project is developed and will be ready to submit to FEMA as soon as projects are reactivated in Grants Portal |  |  | 1 | 0 | 0 | 628036.68 | 6959067.8
727558 | FAASt [Region 3 Bayamon Transmission 38kV sensitive areas] (Vegetation) - Group C | Yes | No | Vegetation | Vegetation-TL | No | Inactive | Inactive | 793759.878 | 8722828.56 | 6674.742 | 73262.238 | 0 | 0 | 9596525.418 | 800434.62 | 8796090.798 | Y | Rene Baptiste | Amendments might apply in future versions. | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. | No updated comment, previous comment remains. | 1322933.13 | 14538047.6 | 11124.57 | 122103.73 | 0 | 0 | 15994209.03 | 1334057.7 | 14660151.33 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | Project is developed and will be ready to submit to FEMA as soon as projects are reactivated in Grants Portal |  |  | 1 | 0 | 0 | 800434.62 | 8796090.798
Pending FASSt | 38kV Transmission Line 100 – Entire Line (Vegetation) | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 254933.334 | 2801526.9 | 2143.746 | 23529.756 | - | - | 3082133.736 | 257077.08 | 2825056.656 | Y | Rene Baptiste | Amendments might apply in future versions. | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. | No updated comment, previous comment remains. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Pending FASSt | 38kV Transmission Line 200 – Entire Line (Vegetation) | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 155350.008 | 1707180.444 | 1306.344 | 14338.44 | - | - | 1878175.236 | 156656.352 | 1721518.884 | Y | Rene Baptiste | Amendments might apply in future versions. | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. | No updated comment, previous comment remains. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Pending FASSt | 38kV Transmission Line 800 – Entire Line (Vegetation) | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 161271.174 | 1772249.706 | 1356.138 | 14884.95 | - | - | 1949761.968 | 162627.312 | 1787134.656 | Y | Rene Baptiste | Amendments might apply in future versions. | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. | No updated comment, previous comment remains. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Pending FASSt | 38kV Transmission Line 1200 – Entire Line (Vegetation) | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 275711.268 | 3029860.812 | 2318.466 | 25447.512 | - | - | 3333338.058 | 278029.734 | 3055308.324 | Y | Rene Baptiste | Amendments might apply in future versions. | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. | No updated comment, previous comment remains. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Pending FASSt | 38kV Transmission Line 1600 – Entire Line (Vegetation) | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 305424.768 | 3356390.148 | 2568.324 | 28190.004 | - | - | 3692573.244 | 307993.092 | 3384580.152 | Y | Rene Baptiste | Amendments might apply in future versions. | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. | No updated comment, previous comment remains. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Pending FASSt | 38kV Transmission Line 2000 – Entire Line (Vegetation) | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 303594.6 | 3336277.806 | 2552.934 | 28021.086 | - | - | 3670446.426 | 306147.534 | 3364298.892 | Y | Rene Baptiste | Amendments might apply in future versions. | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. | No updated comment, previous comment remains. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Pending FASSt | 38kV Transmission Line 2100 – Entire Line (Vegetation) | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 304778.826 | 3349291.674 | 2562.894 | 28130.388 | - | - | 3684763.782 | 307341.72 | 3377422.062 | Y | Rene Baptiste | Amendments might apply in future versions. | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. | No updated comment, previous comment remains. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Pending FASSt | 38kV Transmission Line 2200 – Entire Line (Vegetation) | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 805386.906 | 8850600.906 | 6772.518 | 74335.38 | - | - | 9737095.71 | 812159.424 | 8924936.286 | Y | Rene Baptiste | Amendments might apply in future versions. | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. | No updated comment, previous comment remains. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Pending FASSt | 38kV Transmission Line 2500 – Entire Line (Vegetation) | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 243413.964 | 2674937.64 | 2046.876 | 22466.544 | - | - | 2942865.024 | 245460.84 | 2697404.184 | Y | Rene Baptiste | Amendments might apply in future versions. | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. | No updated comment, previous comment remains. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Pending FASSt | 38kV Transmission Line 2700 – Entire Line (Vegetation) | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 409745.04 | 4502791.986 | 3445.554 | 37818.534 | - | - | 4953801.114 | 413190.594 | 4540610.52 | Y | Rene Baptiste | Amendments might apply in future versions. | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. | No updated comment, previous comment remains. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Pending FASSt | 38kV Transmission Line 3000 – Entire Line (Vegetation) | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 491241.876 | 5398381.47 | 4130.862 | 45340.512 | - | - | 5939094.72 | 495372.738 | 5443721.982 | Y | Rene Baptiste | Amendments might apply in future versions. | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. | No updated comment, previous comment remains. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Pending FASSt | 38kV Transmission Line 3100 – Entire Line (Vegetation) | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 650144.58 | 7144603.488 | 5467.08 | 60006.864 | - | - | 7860222.012 | 655611.66 | 7204610.352 | Y | Rene Baptiste | Amendments might apply in future versions. | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. | No updated comment, previous comment remains. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Pending FASSt | 38kV Transmission Line 3700 – Entire Line (Vegetation) | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 470248.632 | 5167681.416 | 3954.33 | 43402.878 | - | - | 5685287.256 | 474202.962 | 5211084.294 | Y | Rene Baptiste | Amendments might apply in future versions. | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. | No updated comment, previous comment remains. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Pending FASSt | 38kV Transmission Line 3800 – Entire Line (Vegetation) | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 253749.102 | 2788513.05 | 2133.786 | 23420.454 | - | - | 3067816.392 | 255882.888 | 2811933.504 | Y | Rene Baptiste | Amendments might apply in future versions. | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. | No updated comment, previous comment remains. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Pending FASSt | 38kV Transmission Line 4000 – Entire Line (Vegetation) | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 113148.21 | 1243414.146 | 951.474 | 10443.306 | - | - | 1367957.136 | 114099.684 | 1253857.452 | Y | Rene Baptiste | Amendments might apply in future versions. | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. | No updated comment, previous comment remains. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Pending FASSt | 38kV Transmission Line 4800 – Entire Line (Vegetation) | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 428262.162 | 4706281.266 | 3601.272 | 39527.616 | - | - | 5177672.316 | 431863.434 | 4745808.882 | Y | Rene Baptiste | Amendments might apply in future versions. | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. | No updated comment, previous comment remains. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Pending FASSt | 38kV Transmission Line 5300 – Entire Line (Vegetation) | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 166008.114 | 1824305.088 | 1395.972 | 15322.164 | - | - | 2007031.338 | 167404.086 | 1839627.252 | Y | Rene Baptiste | Amendments might apply in future versions. | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. | No updated comment, previous comment remains. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Pending FASSt | 38kV Transmission Line 5400 – Entire Line (Vegetation) | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 288199.554 | 3167097.762 | 2423.478 | 26600.154 | - | - | 3484320.948 | 290623.032 | 3193697.916 | Y | Rene Baptiste | Amendments might apply in future versions. | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. | No updated comment, previous comment remains. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Pending FASSt | 38kV Transmission Line 5600 – Entire Line (Vegetation) | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 293582.43 | 3226251.636 | 2468.742 | 27096.984 | - | - | 3549399.792 | 296051.172 | 3253348.62 | Y | Rene Baptiste | Amendments might apply in future versions. | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. | No updated comment, previous comment remains. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Pending FASSt | 38kV Transmission Line 6500 – Entire Line (Vegetation) | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 447640.536 | 4919235.186 | 3764.22 | 41316.198 | - | - | 5411956.14 | 451404.756 | 4960551.384 | Y | Rene Baptiste | Amendments might apply in future versions. | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. | No updated comment, previous comment remains. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
TBD | Telecom Transport Network Group 2 |  |  | Telecommunication | IT/OT | No |  |  | 38974760.61 | 52405461.42 | 3462203.48 | 4635104.34 |  |  | 99477529.85 | 42436964.09 | 57040565.76 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
547344 (1066724)) | Acacias 6801 TC (Relocation) | Yes | Yes | Substations | Substation Rebuilds | No | Active | Active | 65766025.0617 | 31538831.8413 | 2841208.2382 | 785561.5157 | 12378234.9672 | 3124060.0459 | 116433921.67 | 80985468.2671 | 35448453.4029 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 80985468.2671 | 35448453.4029 | Anadir numero nuevo
TBD | Aguadilla Sect 7003 Transformer 38/13.2-4.16, 22 MVA | No | Yes | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 236211.0391 | 65309.6452 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
TBD | ALTURAS DE MAYAGUEZ | No | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 236211.0391 | 65309.6452 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 0 | 0
TBD | ALTURAS DE RIO GRANDE | No | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 236211.0391 | 65309.6452 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 0 | 0
TBD | BARCELONETA PUEBLO | No | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 236211.0391 | 65309.6452 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 0 | 0
TBD | BRENAS | No | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 236211.0391 | 65309.6452 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 0 | 0
547247 | Cambalache TC Rebuild | Yes | Yes | Substations | Substation Rebuilds | No | Inactive | Inactive | 4966986.47 | 62195402.17 | 344907.31 | 9217663.45 | 151612.12 | 13320220.44 | 90196791.96 | 5463505.9 | 84733286.06 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 5463505.9 | 84733286.06
TBD | CAMUY | No | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 236211.0391 | 65309.6452 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 0 | 0
TBD | CERAMICA | No | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 236211.0391 | 65309.6452 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 0 | 0
TBD | CRUCE DAVILA | No | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 236211.0391 | 65309.6452 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 0 | 0
550099 (1066979) | Esc Industrial Miguel Such (Metal-Clad) 1423 | Yes | Yes | Substations | Substation Rebuilds | No | Active | Active | 3301739.68 | 1135704.94 | 1112050.13 | 0 | 6614733.66 | 4603565.8 | 16767794.21 | 11028523.47 | 5739270.74 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 11028523.47 | 5739270.74 | Anadir numero nuevo
752277 | FAASt [Substation Ciales 8701] (Substation) | No | No | Substations | Substation Rebuilds | No | Inactive | Inactive | 9069707.702 | 4349479.6256 | 391827.364 | 108335.7755 | 1706844.8419 | 431056.671 | 16057251.98 | 11168379.9079 | 4888872.0722 | Y | Carlos Baez | New Project | N/A |  | 3553830.9091 | 524335.7079 | 349557.1386 | 116519.0462 | 466076.1848 | 815633.3234 | 5825952.31 | 4369464.2325 | 1456488.0775 | DSOW – Pending Design Package for Development | Q1 FY2028 | New DSOW needs to be developed , Proposed approach focused on replacing critical components: metal-clad, transformers, breakers, communications. |  |  | 1 | 0 | 0 | 0 | 0
551260 (1066729) | Guaynabo Pueblo | Yes | Yes | Substations | Substation Rebuilds | No | Active | Active | 9487047.4 | 4257510.71 | 2263654.35 | 576564.36 | 4962433.97 | 3961056.7649 | 25508267.5549 | 16713135.72 | 8795131.8349 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 16713135.72 | 8795131.8349 | Anadir numero nuevo
TBD | HATO TEJAS | No | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 236211.0391 | 65309.6452 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 0 | 0
TBD | Hogar Crea 1717 Transformer 115/13.2 kV, 44.8 MVA | No | Yes | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 236211.0391 | 65309.6452 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
TBD | ISABELA PUEBLO | No | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 236211.0391 | 65309.6452 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 0 | 0
TBD | Isla Grande TC Bank 2 Transformer 115/40 kV, 112 MVA | No | Yes | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 236211.0391 | 65309.6452 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
TBD | JUNCOS TC | No | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 12436054.1497 | 2868434.0326 | 548875.3957 | 281565.586 | 2039101.99 | 673911.4961 | 18847942.6501 | 15024031.5354 | 3823911.1147 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 0 | 0
TBD | LA RAMBLA SECT | No | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 236211.0391 | 65309.6452 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 0 | 0
TBD | LAS PIEDRAS SECT | No | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 236211.0391 | 65309.6452 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 0 | 0
TBD | MANATI TC | No | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 9069707.702 | 4349479.6256 | 391827.364 | 108335.7755 | 1706844.8419 | 431056.671 | 16057251.98 | 11168379.9079 | 4888872.0722 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 0 | 0
TBD | Mobile Substations | No | No | Substations | Substations | No | Inactive | Inactive |  |  |  |  | 17709050 |  | 17709050 | 17709050 | 0 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
TBD | NAGUABO | No | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 236211.0391 | 65309.6452 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 0 | 0
TBD | PATILLAS | No | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 236211.0391 | 65309.6452 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 0 | 0
TBD | PENUELAS | No | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 236211.0391 | 65309.6452 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 0 | 0
TBD | PUERTO DEL REY | No | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 236211.0391 | 65309.6452 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 0 | 0
TBD | Quebradillas 7402 Transformer 38/13.2-4.16, 22 MVA | No | Yes | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 236211.0391 | 65309.6452 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
TBD | RAMEY FIELD 3 | No | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 236211.0391 | 65309.6452 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 0 | 0
TBD | Rincon 7301 Transformer 38/13.2-4.16, 22 MVA | No | Yes | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 236211.0391 | 65309.6452 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
TBD | SABANA GRANDE | No | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 236211.0391 | 65309.6452 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 0 | 0
TBD | SALINAS RURAL | No | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 236211.0391 | 65309.6452 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 0 | 0
TBD | SALINAS URBANO | No | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 236211.0391 | 65309.6452 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 0 | 0
TBD | Santa Isabel Sect 4401 Transformer 38/13.2-4.16, 22 MVA | No | Yes | Substations | Substation Component Replacements | No | Inactive | Inactive | 9069707.702 | 4349479.6256 | 391827.364 | 108335.7755 | 1706844.8419 | 431056.671 | 16057251.98 | 11168379.9079 | 4888872.0722 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
TBD | Quebrada Negrito | No | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 236211.0391 | 65309.6452 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 0 | 0
TBD | TOA ALTA | No | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 236211.0391 | 65309.6452 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 0 | 0
TBD | Venezuela WC |  |  | Substations | Grid Modernization | No |  |  | 6337873.936 | 472989.928 | 1584468.484 | 118247.482 | 32941132.73 | 2458367.59 | 43913080.15 | 40863475.15 | 3049605 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
TBD | Hato Rey WC |  |  | Substations | Grid Modernization | No |  |  | 1156110.08 |  | 471848.13 |  | 1079499.89 |  | 2707458.1 | 2707458.1 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
TBD | Santa Isabel WC |  |  | Substations | Grid Modernization | No |  |  | 2197333.81 |  | 7383372.13 |  |  |  | 9580705.94 | 9580705.94 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
TBD | Aguada WC |  |  | Substations | Grid Modernization | No |  |  | 535734.82 |  | 197297.35 |  | 615426.45 |  | 1348458.62 | 1348458.62 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
685869 | [Mayagüez TC] (Substation | No | No | Substations | Substation Rebuilds | No | Inactive | Inactive | 22073642.86 | 7779720.93 | 2605555.14 | 53174.57 | 13511059.91 | 183120 | 46206273.41 | 38190257.91 | 8016015.5 | [5 empty] | 22073642.86 | 543426.36 | 2605555.14 | 53174.57 | 13511059.91 | 183120 | 38969978.84 | 38190257.91 | 779720.93 | DSOW – Pending Design Package for Development | Q1 FY2027 | Awaiting cable termination and subcontractor. Received quote, started micropurchase. Breakers have already been maintained and transformer fans were replaced. Estimated Submission to COR3/FEMA 6/30/2026. |  |  | 1 | 0 | 0 | 0 | 0
TBD | VEREDAS SECT | No | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 236211.0391 | 65309.6452 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 0 | 0
TBD | Aguas Buenas | No | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5614147.55 | 2622060.6228 | 482672.57 | 65309.6452 | 1241258.17 | 259726.6402 | 10285175.1982 | 7338078.29 | 2947096.9082 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 0 | 0
N/A | Fiber Optic Replacement Group 1 | No | Yes | Telecommunication | IT/OT | No | Inactive | Inactive | 67811581.03 | 9902187.96 | 6835688.41 | 948496.8 | 108101.8 |  | 85606056 | 74755371.24 | 10850684.76 | N | Axel Andino | N/A | New Project |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
551927 (1066731) | SCADA Remote Access and RTU Replacements Group 3 | Yes | Yes | Telecommunication | IT/OT | No | Active | Active | 18668671.07 | 3375608.8 | 2470554.28 | 425678.76 | 1293008.64 |  | 26233521.55 | 22432233.99 | 3801287.56 | N | Axel Andino | N/A | New Project |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 22432233.99 | 3801287.56 | Anadir numero nuevo
679035 | Telecomm Infrastructure Group A | Yes | Yes | Telecommunication | IT/OT | No | Inactive | Inactive | 6440145.54 | 15927.16 | 1756408.47 | 4175.18 | 2800 |  | 8219456.35 | 8199354.01 | 20102.34 | N | Axel Andino | N/A | New Project |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 8199354.01 | 20102.34
704805 | Telecomm Infrastructure Group D | No | Yes | Telecommunication | IT/OT | No | Inactive | Inactive | 5297451.62 | 18959.16 | 683790.17 | 2498.07 |  |  | 6002699.02 | 5981241.79 | 21457.23 | N | Axel Andino | N/A | New Project |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
748180 | Transmission Advanced Sensors and Wide-Area Monitoring, Protection, and Control (WAMPAC) System | Yes | Yes | Telecommunication | IT/OT | No | Active | Inactive | 0 | 47130973.41 | 0 | 5250645.64 | 0 | 423360 | 52804979.05 | 0 | 52804979.05 | N | Axel Rodriguez | N/A | New Project |  | 33071971.884 | 4086750.8114 | 4724567.412 | 472456.7412 | 3307197.1884 | 1417370.2236 | 47080314.2606 | 41103736.4844 | 5976577.7762 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | 0 |  |  | 1 | 0 | 0 | 0 | 52804979.05

## Attachment B (Updated) (hidden)
[9 empty] | Estimate Project Costs Allocation (Update) | [8 empty] | Confirmation and Comments |  |  |  |  | PREB Response numbers ( Do not update)
Project # | Title | Should we include the project in the (New List) ? | Submitted to PREPA (Yes/No) | Asset | Sub Asset | Obligated (Yes / No) | Activated by PREPA (Active / Inactive) | Activated by FEMA (Active / Inactive) | 428 Estimate (Without the A&E and E&M) | 406 Estimate (Without the A&E and E&M) | 428 A&E Estimate-PW 9510 | 406 A&E Estimate -PW 9510 | 428 E&M Estimate -PW 10710 | 406 E&M Estimate -PW 10710 | Expected Total Project Estimate Cost | Total 428 Estimate Cost | Total 406 Estimate Cost | Estimate/Cost change (Y/N) | Who confirmed the information? | Obligation Amendment Status | New Comment | Updated Comments | 428 Allocation (Without the A&E and E&M) | 406 Allocation (Without the A&E and E&M) | 428 A&E-PW 9510 | 406 A&E-PW 9510 | 428 E&M-PW 10710 | 406 E&M-PW 10710 | Expected Total Project Cost | Total 428 Expected Cost | Total 406 Expected Cost | Project Status | Expected COR3 Submission Date | Comments | Total NEW LIST | PREPA Note: Cost incurred as reported by LUMA. | Project w Prior Cost Estimate | No File Projects | Shifted Projects | 428 | 406 | DAE Comment
9510 | PBUT34 - Islandwide Feeder Assessments | No | No |  | not found | No | Inactive | Inactive | Not Found | Not Found | Not Found | Not Found | Not Found | Not Found | Not Found | Not Found | Not Found | not found | not found | not found | not found | not found | [14 empty] | 0 | 1 | 0 | 0 | 0
9510 | A&E costs reimbursed related to projects without child | not found | No |  | not found | No | Inactive | Inactive | Not Found | Not Found | Not Found | Not Found | Not Found | Not Found | Not Found | Not Found | Not Found | not found | not found | not found | not found | not found | [14 empty] | 0 | 1 | 0 | 0 | 0
10710 | Reclosers - Without child project (Equipment purchased) | Yes, only E&M | No |  | not found | No | Inactive | Inactive | Not Found | Not Found | Not Found | Not Found | Not Found | Not Found | Not Found | Not Found | Not Found | not found | not found | not found | not found | not found | [14 empty] | 0 | 1 | 0 | Not Found | Not Found
TBD35 | Poles- Included in the E&M without child (Poles paid) | not found |  |  | not found | No | Inactive | Inactive | Not Found | Not Found | Not Found | Not Found | Not Found | Not Found | Not Found | Not Found | Not Found | not found | not found | not found | not found | not found | [14 empty] | 0 | 1 | 0 | 0 | 0
750503 | FAASt [25 MW BESS Installation and Integration - San Juan] (Substation) | Yes | No | Substations | Grid Modernization | No | Inactive | Inactive | 0 | 24053536.03 | 0 | 3187811.29 | 0 | 28261718.24 | 55503065.56 | 0 | 55503065.56 | N | Luis Munet |  |  |  | 0 | 24053536.03 | 0 | 3187811.29 | 0 | 28261718.24 | 55503065.56 | 0 | 55503065.56 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | 406 HM Split 100% As it was last submitted to FEMA. Contingent to FEMA Hazard Mitigation Evaluation and approval. |  |  | 1 | 0 | 1 | 0 | 55503065.56
750502 | FAASt [25 MW BESS Installation and Integration - Aguadilla] (Substation) | Yes | No | Substations | Grid Modernization | No | Inactive | Inactive | 0 | 21118171.64 | 0 | 3340630.47 | 0 | 28261718.24 | 52720520.35 | 0 | 52720520.35 | N | Luis Munet |  |  |  | 0 | 21118171.64 | 0 | 3340630.47 | 0 | 28261718.24 | 52720520.35 | 0 | 52720520.35 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | 406 HM Split 100% As it was last submitted to FEMA |  |  | 1 | 0 | 0 | 0 | 52720520.35
752972 | FAASt [4 x 25 MW BESS Interconnections Manati] (Substation) | Yes | No | Substations | Grid Modernization | No | Inactive | Inactive | 0 | 23808829.62 | 0 | 3414922.97 | 0 | 30416253.08 | 57640005.67 | 0 | 57640005.67 | N | Luis Munet |  |  |  | 0 | 23808829.62 | 0 | 3414922.97 | 0 | 30416253.08 | 57640005.67 | 0 | 57640005.67 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | 406 HM Split 100% As it was last submitted to FEMA |  |  | 1 | 0 | 0 | 0 | 57640005.67
738671 | FAASt [25 MW BESS Installation and Integration - Barceloneta] (Substation) | Yes | No | Substations | Grid Modernization | No | Inactive | Inactive | 0 | 20318919.35 | 0 | 5211394.35 | 0 | 30411453.8 | 55941767.5 | 0 | 55941767.5 | N | Luis Munet |  |  |  | 0 | 20318919.35 | 0 | 5211394.35 | 0 | 30411453.8 | 55941767.5 | 0 | 55941767.5 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | 406 HM Split 100% As it was last submitted to FEMA |  |  | 1 | 0 | 0 | 0 | 55941767.5
688623 | FAASt [Automation Program Group 1A-8 Feeders] (Distribution) | No | No | Distribution | Automation | No | Inactive | Inactive | 15682783.16 | 2926805 | 3241962.6 | 516495 | 3708204.4 | 2410310 | 28486560.16 | 22632950.16 | 5853610 | Yes | Victor V. DeCastro Carlo | N/A | Actuals for the "Work Completed" as of March 2026 considered, and Class 5 Estimate for the remaining work. Group 1A with 1B, 1C, and 1D was consolidated into a unique Group 1. The remaining work is based is Class 5 estimated total per project is considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (59) 3PH Reclosers, (266) 1ph reclosers, (165) cFCi. It requires an engineering evaluation once project is reactivated in order to meet current standards. Expenses incurred for partial work, including engineering and studies, which still need to be reconciled. Actuals in Work Completed portion +$11,270,060 as of March 2026 was added to the total project cost. It was split under 428 bucket, "428 Estimate (Without the A&E and E&M)": +$6,385,873.16, "428 A&E Estimate-PW 9510": +$2,381,137.6, "428 E&M Estimate -PW 10710": +$2,503,049.40. | Estimate date for the work to be completed portion only, consolidating Group 1A with 1B, 1C, and 1D into a unique Group 1. This is Class 5 estimated total per project is considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (59) 3PH Reclosers, (266) 1ph reclosers, (165) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions.. Expenses have already been incurred for completed and partial work, including engineering and studies, which still need to be reconciled. The scope requires restructuring and proper formulation to move forward. | 3591270 | 1130585 | 332525 | 199515 | 465535 | 931070 | 6650500 | 4389330 | 2261170 | DSOW – Pending Design Package for Development | Q3 FY2027 | Estimate date for the work to be completed portion only. The estimated total per project is considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (23) 3PH Reclosers, (104) 1ph reclosers, (48) cFCi. |  |  | 1 | 0 | 0 | 0 | 0
740662 | [Automation Program Group 2] (TL/ Distribution | No | No | Distribution | Automation | No | Inactive | Inactive | 36782398.44 | 6876500 | 6277691.02 | 1213500 | 6850965.04 | 5663000 | 63664054.5 | 49911054.5 | 13753000 | No | Victor V. DeCastro Carlo | N/A | Actuals for the "Work Completed" as of March 2026 considered, and Class 5 Estimate for the remaining work. The remaining work is Class 5 estimated total per project is considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (145) 3PH Reclosers, (539) 1ph reclosers, (254) cFCi. It requires an engineering evaluation once project is reactivated in order to meet current standards. Expenses incurred for partial work, including engineering and studies, which still need to be reconciled. Actuals in Work Completed portion is +$23,214,054.50 as of March 2026 was added to the total estimate cost. It was split under 428 bucket, "428 Estimate (Without the A&E and E&M)": +$14,939,398.44, "428 A&E Estimate-PW 9510": + $4,255,191.02, "428 E&M Estimate -PW 10710": +$4,019,465.04. | Estimate date for the work to be completed portion only. This is Class 5 estimated total per project is considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (145) 3PH Reclosers, (539) 1ph reclosers, (254) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions. Expenses have already been incurred for completed and partial work, including engineering and studies, which still need to be reconciled. The scope requires restructuring and proper formulation to move forward. | 21843000 | 6876500 | 2022500 | 1213500 | 2831500 | 5663000 | 40450000 | 26697000 | 13753000 | DSOW – Pending Design Package for Development | Q3 FY2027 | Estimate date for the work to be completed portion only. The estimated total per project is considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (145) 3PH Reclosers, (539) 1ph reclosers, (254) cFCi. |  |  | 1 | 0 | 0 | 0 | 0
741678 | [Automation Program Group 4] (TL/Distribution | No | No | Distribution | Automation | No | Inactive | Inactive | 29500343.61 | 5347180 | 4420325.45 | 943620 | 6946880.68 | 4403560 | 51561909.74 | 40867549.74 | 10694360 | No | Victor V. DeCastro Carlo | N/A | Actuals for the "Work Completed" as of March 2026 considered, and Class 5 Estimate for the remaining work. The remaining work is Class 5 estimated total per project is considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (117) 3PH Reclosers, (247) 1ph reclosers, (182) cFCi. It requires an engineering evaluation once project is reactivated in order to meet current standards. Expenses incurred for partial work, including engineering and studies, which still need to be reconciled. Expenses have already been incurred for completed and partial work, including engineering and studies, which still need to be reconciled. Actuals in Work Completed portion is +$20,107,909.74 as of March 2026 was added to the total estimate cost. It was split under 428 bucket, "428 Estimate (Without the A&E and E&M)": +$12,515,183.61, "428 A&E Estimate-PW 9510": +$2,847,625.45, "428 E&M Estimate -PW 10710": +$4,475,100.68. | Estimate date for the work to be completed portion only. This is Class 5 estimated total per project is considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (117) 3PH Reclosers, (247) 1ph reclosers, (182) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions. Expenses have already been incurred for completed and partial work, including engineering and studies, which still need to be reconciled. The scope requires restructuring and proper formulation to move forward. | 16985160 | 5347180 | 1572700 | 943620 | 2201780 | 4403560 | 31454000 | 20759640 | 10694360 | DSOW – Pending Design Package for Development | Q3 FY2027 | Estimate date for the work to be completed portion only. The estimated total per project is considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (117) 3PH Reclosers, (247) 1ph reclosers, (182) cFCi. |  |  | 1 | 0 | 0 | 0 | 0
705657 | [Automation Program Group 3] (TL/Distribution | No | No | Distribution | Automation | No | Inactive | Inactive | 30089122.78 | 4299385 | 7264119.61 | 758715 | 6881478.06 | 3540670 | 52833490.45 | 44234720.45 | 8598770 | No | Victor V. DeCastro Carlo | N/A | Actuals for the "Work Completed" as of March 2026 considered, and Class 5 Estimate for the remaining work. The remaining work is Class 5 estimated total per project is considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (99) 3PH Reclosers, (316) 1ph reclosers, (212) cFCi.It requires an engineering evaluation once project is reactivated in order to meet current standards. Expenses incurred for partial work, including engineering and studies, which still need to be reconciled. Expenses have already been incurred for completed and partial work, including engineering and studies, which still need to be reconciled. Actuals in Work Completed portion is +$27,542,990.45 as of March 2026 was added to the total estimate cost. It was split under 428 bucket, "428 Estimate (Without the A&E and E&M)": +$16,432,252.78, "428 A&E Estimate-PW 9510": +$5,999,594.61, "428 E&M Estimate -PW 10710": +$5,111,143.06. | Estimate date for the work to be completed portion only. This is Class 5 estimated total per project is considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (99) 3PH Reclosers, (316) 1ph reclosers, (212) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions. Expenses have already been incurred for completed and partial work, including engineering and studies, which still need to be reconciled. The scope requires restructuring and proper formulation to move forward. | 13656870 | 4299385 | 1264525 | 758715 | 1770335 | 3540670 | 25290500 | 16691730 | 8598770 | DSOW – Pending Design Package for Development | Q3 FY2027 | Estimate date for the work to be completed portion only. The estimated total per project is considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (99) 3PH Reclosers, (316) 1ph reclosers, (212) cFCi. |  |  | 1 | 0 | 0 | 0 | 0
800394 | Automation Program Group 39 (Distribution) | Yes | Yes | Distribution | Automation | No | Inactive | Inactive | 1256040 | 395420 | 116300 | 69780 | 162820 | 325640 | 2326000 | 1535160 | 790840 |  | Victor V. DeCastro Carlo | N/A | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (11) 3PH Reclosers, (17) 1ph reclosers, (18) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions. | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (11) 3PH Reclosers, (17) 1ph reclosers, (18) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 1535160 | 790840
800369 | FAASt [Automation Program Group 38 | No | No | Distribution | Automation | No | Inactive | Inactive | 802170 | 252535 | 74275 | 44565 | 103985 | 207970 | 1485500 | 980430 | 505070 |  | Victor V. DeCastro Carlo | N/A | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (4) 3PH Reclosers, (29) 1ph reclosers, (21) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions. | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (4) 3PH Reclosers, (29) 1ph reclosers, (21) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
800399 | FAASt [Automation Program Group 40 | No | No | Distribution | Automation | No | Inactive | Inactive | 1536300 | 483650 | 142250 | 85350 | 199150 | 398300 | 2845000 | 1877700 | 967300 |  | Victor V. DeCastro Carlo | N/A | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (11) 3PH Reclosers, (35) 1ph reclosers, (33) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions. | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (11) 3PH Reclosers, (35) 1ph reclosers, (33) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
401432 | FAASt [Automation Program Group 41 | No | No | Distribution | Automation | No | Inactive | Inactive | 1469610 | 462655 | 136075 | 81645 | 190505 | 381010 | 2721500 | 1796190 | 925310 |  | Victor V. DeCastro Carlo | N/A | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (10) 3PH Reclosers, (39) 1ph reclosers, (18) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions. | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (10) 3PH Reclosers, (39) 1ph reclosers, (18) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
801437 | FAASt [Automation Program Group 42 | No | No | Distribution | Automation | No | Inactive | Inactive | 604800 | 190400 | 56000 | 33600 | 78400 | 156800 | 1120000 | 739200 | 380800 |  | Victor V. DeCastro Carlo | N/A | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (2) 3PH Reclosers, (30) 1ph reclosers, (6) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions. | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (2) 3PH Reclosers, (30) 1ph reclosers, (6) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
801438 | FAASt [Automation Program Group 43 | No | No | Distribution | Automation | No | Inactive | Inactive | 851580 | 268090 | 78850 | 47310 | 110390 | 220780 | 1577000 | 1040820 | 536180 |  | Victor V. DeCastro Carlo | N/A | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (4) 3PH Reclosers, (34) 1ph reclosers, (12) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions. | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (4) 3PH Reclosers, (34) 1ph reclosers, (12) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
801440 | FAASt [Automation Program Group 44 | No | No | Distribution | Automation | No | Inactive | Inactive | 597510 | 188105 | 55325 | 33195 | 77455 | 154910 | 1106500 | 730290 | 376210 |  | Victor V. DeCastro Carlo | N/A | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (5) 3PH Reclosers, (10) 1ph reclosers, (6) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions. | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (5) 3PH Reclosers, (10) 1ph reclosers, (6) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
801441 | FAASt [Automation Program Group 45 | No | No | Distribution | Automation | No | Inactive | Inactive | 1221750 | 384625 | 113125 | 67875 | 158375 | 316750 | 2262500 | 1493250 | 769250 |  | Victor V. DeCastro Carlo | N/A | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (10) 3PH Reclosers, (21) 1ph reclosers, (18) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions. | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (10) 3PH Reclosers, (21) 1ph reclosers, (18) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
745854 | FAASt [Automation Program Group 9 | No | No | Distribution | Automation | No | Inactive | Inactive | 589140 | 185470 | 54550 | 32730 | 76370 | 152740 | 1091000 | 720060 | 370940 |  | Victor V. DeCastro Carlo | N/A | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (4) 3PH Reclosers, (14) 1ph reclosers, (18) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions. | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (4) 3PH Reclosers, (14) 1ph reclosers, (18) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
745871 | FAASt [Automation Program Group 10 | No | No | Distribution | Automation | No | Inactive | Inactive | 713610 | 224655 | 66075 | 39645 | 92505 | 185010 | 1321500 | 872190 | 449310 |  | Victor V. DeCastro Carlo | N/A | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (6) 3PH Reclosers, (11) 1ph reclosers, (12) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions. | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (6) 3PH Reclosers, (11) 1ph reclosers, (12) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
745851 | FAASt [Automation Program Group 11 | No | No | Distribution | Automation | No | Inactive | Inactive | 720630 | 226865 | 66725 | 40035 | 93415 | 186830 | 1334500 | 880770 | 453730 |  | Victor V. DeCastro Carlo | N/A | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (5) 3PH Reclosers, (18) 1ph reclosers, (12) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions. | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (5) 3PH Reclosers, (18) 1ph reclosers, (12) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
745852 | FAASt [Automation Program Group 13 | No | No | Distribution | Automation | No | Inactive | Inactive | 897480 | 282540 | 83100 | 49860 | 116340 | 232680 | 1662000 | 1096920 | 565080 |  | Victor V. DeCastro Carlo | N/A | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (9) 3PH Reclosers, (3) 1ph reclosers, (24) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions. | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (9) 3PH Reclosers, (3) 1ph reclosers, (24) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
790427 | Distribution Pole and Conductor Repair - Caguas Group 5 - Phase 2 | Yes | Yes | Distribution | Distribution Pole and Conductor Repair | No | Active | Active | 7522113.13 | 215009.46 | 668118.89 | 35608.17 | 520612.13 | 213636.87 | 9175098.65 | 8710844.15 | 464254.5 |  | Victor V. DeCastro Carlo | N/A | Class 3 estimate has been submitted to COR3 for validation. WOP design is 100% completed, and the DSOW package has been completed. We are currently pending COR3’s review prior to FEMA submission. | Class 3 estimate has been submitted to COR3 for validation. WOP design is 100% completed, and the DSOW package has been completed. We are currently pending COR3’s review prior to FEMA submission. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 8710844.15 | 464254.5 | Anadir numero nuevo
806935 | Distribution Pole and Conductor Repair - Caguas Group 6 - Phase 2 | Yes | Yes | Distribution | Distribution Pole and Conductor Repair | No | Active | Active | 7262006.01 | 330225.13 | 645539.7 | 44770.71 | 509451.1 | 208755.9 | 9000748.55 | 8416996.81 | 583751.74 |  | Victor V. DeCastro Carlo | N/A | Class 3 estimate has been submitted to COR3 for validation. WOP design is 100% completed, and the DSOW package has been completed. We are currently pending COR3’s review prior to FEMA submission. | Class 3 estimate has been submitted to COR3 for validation. WOP design is 100% completed, and the DSOW package has been completed. We are currently pending COR3’s review prior to FEMA submission. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 8416996.81 | 583751.74 | Anadir numero nuevo
757945 | Distribution Pole and Conductor Repair - Arecibo Group 3 – Phase 2 | Yes | Yes | Distribution | Distribution Pole and Conductor Repair | No | Active | Active | 2039409.93 | 366564.02 | 181779.7 | 35823.76 | 173097.79 | 69460.21 | 2866135.41 | 2394287.42 | 471847.99 |  | Victor V. DeCastro Carlo | N/A | Class 3 estimate has been submitted to COR3 for validation. WOP design is 100% completed, and the DSOW package has been completed. We are currently pending COR3’s review prior to FEMA submission. | Class 3 estimate has been submitted to COR3 for validation. WOP design is 100% completed, and the DSOW package has been completed. We are currently pending COR3’s review prior to FEMA submission. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 2394287.42 | 471847.99 | Anadir numero nuevo
790446 | Distribution Pole and Conductor Repair – Caguas Group 4 – Phase 2 | Yes | Yes | Distribution | Distribution Pole and Conductor Repair | No | Active | Active | 3449507.56 | 434031.63 | 308003.3 | 44842.58 | 258899.2 | 105879.8 | 4601164.07 | 4016410.06 | 584754.01 |  | Victor V. DeCastro Carlo | N/A | Class 3 estimate has been submitted to COR3 for validation. WOP design is 100% completed, and the DSOW package has been completed. We are currently pending COR3’s review prior to FEMA submission. | Class 3 estimate has been submitted to COR3 for validation. WOP design is 100% completed, and the DSOW package has been completed. We are currently pending COR3’s review prior to FEMA submission. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 4016410.06 | 584754.01 | Anadir numero nuevo
817249 | Distribution Pole and Conductor Repair – Caguas Group 7 – Phase 2 | Yes | Yes | Distribution | Distribution Pole and Conductor Repair | No | Active | Active | 4608333 | 284709.51 | 409935.75 | 36039.36 | 381146.2 | 153938.8 | 5874102.62 | 5399414.95 | 474687.67 |  | Victor V. DeCastro Carlo | N/A | Class 3 estimate has been submitted to COR3 for validation. WOP design is 100% completed, and the DSOW package has been completed. We are currently pending COR3’s review prior to FEMA submission. | Class 3 estimate has been submitted to COR3 for validation. WOP design is 100% completed, and the DSOW package has been completed. We are currently pending COR3’s review prior to FEMA submission. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 5399414.95 | 474687.67 | Anadir numero nuevo
764707 | [Feeder Rebuild # 6012-02] (Distribution | No | No | Distribution | Rebuild | No | Inactive | Inactive | 16634520 | 482160 | 5062680 | 241080 | 1446480 | 241080 | 24108000 | 23143680 | 964320 | No | Victor V. DeCastro Carlo | N/A | This feeder has a CMI of 4.8M, and the design is approximately 39% complete. It includes a total of 239 structures. It is recommended to replace for feeders 1204‑05(CMI 14.6M), 2404‑06(CMI 7.2M), and 1303‑0(CMI 5M), due to their higher CMIs and because their engineering stages are nearing completion for DSOW submission. | This feeder has a CMI of 4.8M, and the design is approximately 39% complete. It includes a total of 239 structures. It is recommended to replace for feeders 1204‑05(CMI 14.6M), 2404‑06(CMI 7.2M), and 1303‑0(CMI 5M), due to their higher CMIs and because their engineering stages are nearing completion for DSOW submission. | 16634520 | 482160 | 5062680 | 241080 | 1446480 | 241080 | 24108000 | 23143680 | 964320 | DSOW – Pending Design Package for Development | FY2029 | Design is about 39% complete. This project is currently classified as withdrawn (T1) and covers 5.74 miles with 239 structures. DSOW – Waiting on the design package to be developed. |  |  | 1 | 0 | 0 | 0 | 0
764705 | [Feeder Rebuild # 6014-02] (Distribution | No | No | Distribution | Rebuild | No | Inactive | Inactive | 23763600 | 688800 | 7232400 | 344400 | 2066400 | 344400 | 34440000 | 33062400 | 1377600 | No | Victor V. DeCastro Carlo | N/A | This feeder has a CMI of 16.8M. Engineering stages are nearing completion for DSOW submission. | This feeder has a CMI of 16.8M. Engineering stages are nearing completion for DSOW submission. | 23763600 | 688800 | 7232400 | 344400 | 2066400 | 344400 | 34440000 | 33062400 | 1377600 | DSOW – Pending Design Package for Development | FY2029 | Design is about 52% complete. This project is currently classified as withdrawn (T1) and covers 8.20 miles with 343 structures. DSOW – Waiting on the design package to be developed. |  |  | 1 | 0 | 0 | 0 | 0
767381 | [Feeder Rebuild # 1204-05] (Distribution | No | No | Distribution | Rebuild | No | Inactive | Inactive | 3880428.29 | 112476.18 | 1180999.92 | 56238.09 | 337428.55 | 56238.09 | 5623809.12 | 5398856.76 | 224952.36 | No | Victor V. DeCastro Carlo | N/A | This feeder has a CMI of 14.6M, Engineering stages are nearing completion for DSOW submission. (Replacement for 6012-02 CMI 4.8M) | This feeder has a CMI of 14.6M, Engineering stages are nearing completion for DSOW submission. (Replacement for 6012-02 CMI 4.8M) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
817961 | [Feeder Rebuild # 2404-06] (Distribution | No | No | Distribution | Rebuild | No | Inactive | Inactive | 18825472.43 | 399260.06 | 1826739.4 | 50231.61 | 692201.89 | 82130.27 | 21876035.66 | 21344413.72 | 531621.94 | No | Victor V. DeCastro Carlo | N/A | This feeder has a CMI of 7.2M, Engineering stages are nearing completion for DSOW submission. (Replacement for 6012-02 CMI 4.8M) | This feeder has a CMI of 7.2M, Engineering stages are nearing completion for DSOW submission. (Replacement for 6012-02 CMI 4.8M) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
767387 | [Feeder Rebuild # 1303-01] (Distribution | No | No | Distribution | Rebuild | No | Inactive | Inactive | 5013491.62 | 145318.6 | 1525845.28 | 72659.3 | 435955.79 | 72659.3 | 7265929.89 | 6975292.69 | 290637.2 | No | Victor V. DeCastro Carlo | N/A | This feeder has a CMI of 5M, Engineering stages are nearing completion for DSOW submission. (Replacement for 6012-02 CMI 4.8M) | This feeder has a CMI of 5M, Engineering stages are nearing completion for DSOW submission. (Replacement for 6012-02 CMI 4.8M) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
666894 | FAASt [San Juan Streetlighting] (Distribution) | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 28178017.76 | 2123472.21 | 6380570.04 | 123157.52 |  |  | 36805217.53 | 34558587.8 | 2246629.73 | N | Victor V. DeCastro Carlo | N/A | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered. | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer. | 27201946.76 | 1465463.21 | 6380570.04 | 123157.52 | 976071 | 658009 | 36805217.53 | 34558587.8 | 2246629.73 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. |  |  | 1 | 0 | 0 | 34558587.8 | 2246629.73
671396 | FAASt [Utuado Streetlighting] (Distribution) | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 16760927.205 | 2851675.47 | 3319870.72 | 155072.6 |  |  | 23087545.995 | 20080797.925 | 3006748.07 | N | Victor V. DeCastro Carlo | N/A | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered. | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. | 15515918.205 | 2012364.47 | 3319870.72 | 155072.6 | 1245009 | 839311 | 23087545.995 | 20080797.925 | 3006748.07 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. |  |  | 1 | 0 | 0 | 20080797.925 | 3006748.07
671400 | FAASt [Barceloneta Streetlighting] (Distribution) | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 7422038.0375 | 477869.14 | 1206563.5 | 50306 |  |  | 9156776.6775 | 8628601.5375 | 528175.14 | N | Victor V. DeCastro Carlo | N/A | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered. | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. | 7024652.0375 | 209975.14 | 1206563.5 | 50306 | 397386 | 267894 | 9156776.6775 | 8628601.5375 | 528175.14 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. |  |  | 1 | 0 | 0 | 8628601.5375 | 528175.14
678794 | FAASt [Ponce Streetlighting] (Distribution) | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 10968715.275 | 884181.41 | 1713141.92 | 51717 |  |  | 13617755.605 | 12681857.195 | 935898.41 | N | Victor V. DeCastro Carlo | N/A | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered. | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. | 10629532.275 | 655524.41 | 1713141.92 | 51717 | 339183 | 228657 | 13617755.605 | 12681857.195 | 935898.41 | DSOW – Scope and Cost Update in Progress | Q2 FY2027 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. |  |  | 1 | 0 | 0 | 12681857.195 | 935898.41
678795 | FAASt [Arecibo Streetlighting] (Distribution) | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 11879105.0925 | 800134.36 | 1902215.74 | 59360 |  |  | 14640815.1925 | 13781320.8325 | 859494.36 | N | Victor V. DeCastro Carlo | N/A | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered. | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. | 11412143.0925 | 485336.36 | 1902215.74 | 59360 | 466962 | 314798 | 14640815.1925 | 13781320.8325 | 859494.36 | DSOW – Scope and Cost Update in Progress | Q1 FY2027 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. |  |  | 1 | 0 | 0 | 13781320.8325 | 859494.36
686482 | FAASt [Isabela Streetlighting] (Distribution) | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 6005455.39 | 671912.08 | 1332970.6 | 37797.8 |  |  | 8048135.87 | 7338425.99 | 709709.88 | N | Victor V. DeCastro Carlo | N/A | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered. | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. | 5745883.39 | 496924.08 | 1332970.6 | 37797.8 | 259572 | 174988 | 8048135.87 | 7338425.99 | 709709.88 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. |  |  | 1 | 0 | 0 | 7338425.99 | 709709.88
690480 | FAASt [Humacao Streetlighting] (Distribution) | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 6455271.8825 | 488325.81 | 1006696.36 | 29209 |  |  | 7979503.0525 | 7461968.2425 | 517534.81 | N | Victor V. DeCastro Carlo | N/A | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered. | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. | 6175629.8825 | 299807.81 | 1006696.36 | 29209 | 279642 | 188518 | 7979503.0525 | 7461968.2425 | 517534.81 | DSOW – Scope and Cost Update in Progress | Q1 FY2027 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. |  |  | 1 | 0 | 1 | 7461968.2425 | 517534.81
690483 | FAASt [Cayey Streetlighting] | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 10596790.82 | 1275717.24 | 2435204.39 | 95954.76 |  |  | 14403667.21 | 13031995.21 | 1371672 | N | Victor V. DeCastro Carlo | N/A | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered. | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. | 10093033.82 | 936114.24 | 2435204.39 | 95954.76 | 503757 | 339603 | 14403667.21 | 13031995.21 | 1371672 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. |  |  | 1 | 0 | 1 | 13031995.21 | 1371672
690721 | FAASt [Guayama Streetlighting] (Distribution) | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 4107291.015 | 305442.59 | 1011463.98 | 25642.92 |  |  | 5449840.505 | 5118754.995 | 331085.51 | N | Victor V. DeCastro Carlo | N/A | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered. | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. | 3974160.015 | 215693.59 | 1011463.98 | 25642.92 | 133131 | 89749 | 5449840.505 | 5118754.995 | 331085.51 | DSOW – Scope and Cost Update in Progress | Q1 FY2027 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. |  |  | 1 | 0 | 1 | 5118754.995 | 331085.51
693543 | FAASt [Juncos Streetlighting] (Distribution) | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 10994681.6975 | 685135.01 | 1631297.312 | 26436.06 |  |  | 13337550.0795 | 12625979.0095 | 711571.07 | N | Victor V. DeCastro Carlo | N/A | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered. | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. | 10405292.6975 | 287804.01 | 1631297.312 | 26436.06 | 589389 | 397331 | 13337550.0795 | 12625979.0095 | 711571.07 | DSOW – Scope and Cost Update in Progress | Q1 FY2027 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. |  |  | 1 | 0 | 1 | 12625979.0095 | 711571.07
693615 | [Rio Grande Streetlighting] (Distribution | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 5347407.42 | 397032.05 | 1156399.63 | 21533.62 |  |  | 6922372.72 | 6503807.05 | 418565.67 | N | Victor V. DeCastro Carlo | N/A | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered. | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. | 5156073.42 | 268046.05 | 1156399.63 | 21533.62 | 191334 | 128986 | 6922372.72 | 6503807.05 | 418565.67 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. |  |  | 1 | 0 | 0 | 6503807.05 | 418565.67
693788 | FAASt [Toa Alta Streetlighting] (Distribution) | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 4767387.52 | 197071.81 | 1162797.94 | 17891.57 |  |  | 6145148.84 | 5930185.46 | 214963.38 | N | Victor V. DeCastro Carlo | N/A | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered. | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. | 4596792.52 | 82066.81 | 1162797.94 | 17891.57 | 170595 | 115005 | 6145148.84 | 5930185.46 | 214963.38 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. |  |  | 1 | 0 | 0 | 5930185.46 | 214963.38
697183 | FAASt [Vega Baja Streetlighting] (Distribution) | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 8602549.46 | 1056851.66 | 1621313.74 | 17891.57 |  |  | 11298606.43 | 10223863.2 | 1074743.23 | N | Victor V. DeCastro Carlo | N/A | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered. | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. | 8233261.46 | 807899.66 | 1621313.74 | 17891.57 | 369288 | 248952 | 11298606.43 | 10223863.2 | 1074743.23 | DSOW – Scope and Cost Update in Progress | Q4 FY2027 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. |  |  | 1 | 0 | 0 | 10223863.2 | 1074743.23
698427 | [Maricao Streetlighting] (Distribution | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 4873133.615 | 921314.71 | 926826.7734 | 43337.3166 |  |  | 6764612.415 | 5799960.3884 | 964652.0266 | N | Victor V. DeCastro Carlo | N/A | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered. | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. | 4466381.615 | 647106.71 | 926826.7734 | 43337.3166 | 406752 | 274208 | 6764612.415 | 5799960.3884 | 964652.0266 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. |  |  | 1 | 0 | 0 | 5799960.3884 | 964652.0266
698432 | FAASt [Hormigueros Streetlighting] (Distribution) | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 5999141.915 | 489811.44 | 1362869.66 | 17724.97 |  |  | 7869547.985 | 7362011.575 | 507536.41 | N | Victor V. DeCastro Carlo | N/A | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered. | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. | 5694746.915 | 284606.44 | 1362869.66 | 17724.97 | 304395 | 205205 | 7869547.985 | 7362011.575 | 507536.41 | DSOW – Scope and Cost Update in Progress | Q4 FY2027 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. |  |  | 1 | 0 | 0 | 7362011.575 | 507536.41
698522 | [Vieques Streetlighting] (Distribution | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 3987957.0575 | 454616.91 | 810226.05 | 32120.4 |  |  | 5284920.4175 | 4798183.1075 | 486737.31 | N | Victor V. DeCastro Carlo | N/A | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered. | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. | 3791271.0575 | 322022.91 | 810226.05 | 32120.4 | 196686 | 132594 | 5284920.4175 | 4798183.1075 | 486737.31 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. |  |  | 1 | 0 | 0 | 4798183.1075 | 486737.31
699814 | FAASt [Juana Diaz Streetlighting] (Distribution) | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 14011750.655 | 872747.53 | 2795912.01 | 55146.97 |  |  | 17735557.165 | 16807662.665 | 927894.5 | N | Victor V. DeCastro Carlo | N/A | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered. | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. | 13267153.655 | 370784.53 | 2795912.01 | 55146.97 | 744597 | 501963 | 17735557.165 | 16807662.665 | 927894.5 | DSOW – Scope and Cost Update in Progress | Q1 FY2027 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. |  |  | 1 | 0 | 0 | 16807662.665 | 927894.5
701473 | FAASt [Canovanas Streetlighting] (Distribution) | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 11994894.83 | 1520521.43 | 2377385.56 | 89359.81 |  |  | 15982161.63 | 14372280.39 | 1609881.24 | N | Victor V. DeCastro Carlo | N/A | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered. | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. | 11399484.83 | 1119131.43 | 2377385.56 | 89359.81 | 595410 | 401390 | 15982161.63 | 14372280.39 | 1609881.24 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. |  |  | 1 | 0 | 0 | 14372280.39 | 1609881.24
704744 | [San Sebastian Streetlighting] (Distribution | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 21521273.585 | 1542129.95 | 4057973.95 | 94811.81 |  |  | 27216189.295 | 25579247.535 | 1636941.76 | N | Victor V. DeCastro Carlo | N/A | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered. | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. | 19955144.585 | 486338.95 | 4057973.95 | 94811.81 | 1566129 | 1055791 | 27216189.295 | 25579247.535 | 1636941.76 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. |  |  | 1 | 0 | 0 | 25579247.535 | 1636941.76
704757 | FAASt [Santa Isabel Streetlighting] (Distribution) | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 8526009.33 | 383038.38 | 1562084.58 | 22536.63 |  |  | 10493668.92 | 10088093.91 | 405575.01 | N | Victor V. DeCastro Carlo | N/A | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered. | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. | 8241015.33 | 190912.38 | 1562084.58 | 22536.63 | 284994 | 192126 | 10493668.92 | 10088093.91 | 405575.01 | DSOW – Scope and Cost Update in Progress | Q1 FY2027 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. |  |  | 1 | 0 | 0 | 10088093.91 | 405575.01
704793 | [Yauco Streetlighting] (Distribution | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 13232024.93 | 1588137.76 | 2540431.6 | 79529.34 |  |  | 17440123.63 | 15772456.53 | 1667667.1 | N | Victor V. DeCastro Carlo | N/A | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered. | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. | 12597812.93 | 1160589.76 | 2540431.6 | 79529.34 | 634212 | 427548 | 17440123.63 | 15772456.53 | 1667667.1 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. |  |  | 1 | 0 | 0 | 15772456.53 | 1667667.1
704862 | FAASt [Fajardo Streetlighting] (Distribution) | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 11073921.95 | 1052403.97 | 2150579.88 | 58676.25 |  |  | 14335582.05 | 13224501.83 | 1111080.22 | N | Victor V. DeCastro Carlo | N/A | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered. | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. | 10758153.95 | 839531.97 | 2150579.88 | 58676.25 | 315768 | 212872 | 14335582.05 | 13224501.83 | 1111080.22 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. |  |  | 1 | 0 | 0 | 13224501.83 | 1111080.22
704929 | [San Lorenzo Streetlighting] (Distribution | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 13787578.6125 | 968406.72 | 2944605.83 | 60896.29 |  |  | 17761487.4525 | 16732184.4425 | 1029303.01 | N | Victor V. DeCastro Carlo | N/A | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered. | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. | 12867034.6125 | 347830.72 | 2944605.83 | 60896.29 | 920544 | 620576 | 17761487.4525 | 16732184.4425 | 1029303.01 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. |  |  | 1 | 0 | 0 | 16732184.4425 | 1029303.01
704931 | FAASt [Camuy Streetlighting] (Distribution) | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 14028036.5825 | 867189.9 | 1972441.141 | 107984.699 |  |  | 16975652.3225 | 16000477.7235 | 975174.599 | N | Victor V. DeCastro Carlo | N/A | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered. | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. | 13069359.5825 | 220906.9 | 1972441.141 | 107984.699 | 958677 | 646283 | 16975652.3225 | 16000477.7235 | 975174.599 | DSOW – Scope and Cost Update in Progress | Q1 FY2027 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. |  |  | 1 | 0 | 0 | 16000477.7235 | 975174.599
724603 | FAASt [Cabo Rojo Streetlighting] (Distribution) | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 7308020.08 | 517830.31 | 1689593.17 | 41489.51 |  |  | 9556933.07 | 8997613.25 | 559319.82 | N | Victor V. DeCastro Carlo | N/A | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered. | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. | 6954788.08 | 279702.31 | 1689593.17 | 41489.51 | 353232 | 238128 | 9556933.07 | 8997613.25 | 559319.82 | DSOW – Scope and Cost Update in Progress | Q1 FY2027 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. |  |  | 1 | 0 | 1 | 8997613.25 | 559319.82
724828 | [Loiza Streetlighting] (Distribution | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 6213147.88 | 388351.58 | 1248099.37 | 14137.5 |  |  | 7863736.33 | 7461247.25 | 402489.08 | N | Victor V. DeCastro Carlo | N/A | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered. | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. | 5936181.88 | 201637.58 | 1248099.37 | 14137.5 | 276966 | 186714 | 7863736.33 | 7461247.25 | 402489.08 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. |  |  | 1 | 0 | 1 | 7461247.25 | 402489.08
724941 | [Aguas Buenas Streetlighting] (Distribution | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 12423846.45 | 585725.31 | 1646095.25 | 83021.58 |  |  | 14738688.59 | 14069941.7 | 668746.89 | N | Victor V. DeCastro Carlo | N/A | DSOW package complete.Ready to be sumitted, scope consider all construction phases. | DSOW package complete.Ready to be sumitted, scope consider all construction phases. | 11340397.36 | 201510.89 | 2036460.34 | 0 | 693084 | 467236 | 14738688.59 | 14069941.7 | 668746.89 | DSOW – Scope and Cost development in progress | Q1 FY2027 | DSOW package complete.Ready to be sumitted, scope consider all construction phases. |  |  | 1 | 0 | 1 | 14069941.7 | 668746.89
704741 | [Moca Streetlighting] (Distribution | Yes | Yes | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 19741562.46 | 976458.2 | 2533607.94 | 134366.43 |  |  | 23385995.03 | 22275170.4 | 1110824.63 | N | Victor V. DeCastro Carlo | N/A | DSOW package complete.Ready to be sumitted, scope consider all construction phases. | DSOW package complete.Ready to be sumitted, scope consider all construction phases. | 17932518.84 | 308495.64 | 3152500.55 | 0 | 1190151 | 802329 | 23385995.03 | 22275170.39 | 1110824.64 | DSOW – Scope and Cost development in progress | Q1 FY2027 | DSOW package complete.Ready to be sumitted, scope consider all construction phases. |  |  | 1 | 0 | 0 | 22275170.4 | 1110824.63
724605 | [Guayanilla Streetlighting] (Distribution | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 8485594.47 | 412336.03 | 1106363.96 | 57568.51 |  |  | 10061862.97 | 9591958.43 | 469904.54 | N | Victor V. DeCastro Carlo | N/A | DSOW package complete.Ready to be sumitted, scope consider all construction phases. | DSOW package complete.Ready to be sumitted, scope consider all construction phases. | 7795083.32 | 183970.54 | 1372729.11 | 0 | 424146 | 285934 | 10061862.97 | 9591958.43 | 469904.54 | DSOW – Scope and Cost development in progress | Q1 FY2027 | DSOW package complete.Ready to be sumitted, scope consider all construction phases. |  |  | 1 | 0 | 1 | 9591958.43 | 469904.54
724599 | [Sabana Grande Streetlighting] (Distribution | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 11849851.49 | 636889.83 | 1536485.07 | 88808.54 |  |  | 14112034.93 | 13386336.56 | 725698.37 | N | Victor V. DeCastro Carlo | N/A | DSOW package complete.Ready to be sumitted, scope consider all construction phases. | DSOW package complete.Ready to be sumitted, scope consider all construction phases. | 10754272.51 | 236814.37 | 1906868.06 | 0 | 725196 | 488884 | 14112034.94 | 13386336.57 | 725698.37 | DSOW – Scope and Cost development in progress | Q1 FY2027 | DSOW package complete.Ready to be sumitted, scope consider all construction phases. |  |  | 1 | 0 | 0 | 13386336.56 | 725698.37
724669 | [Ciales Streetlighting] (Distribution | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 13170687.29 | 682982.51 | 1629722.94 | 90151.24 |  |  | 15573543.98 | 14800410.23 | 773133.75 | N | Victor V. DeCastro Carlo | N/A | DSOW package complete.Ready to be sumitted, scope consider all construction phases. | DSOW package complete.Ready to be sumitted, scope consider all construction phases. | 12013750.42 | 272974.74 | 2044738.82 | 0 | 741921 | 500159 | 15573543.98 | 14800410.24 | 773133.74 | DSOW – Scope and Cost development in progress | Q1 FY2027 | DSOW package complete.Ready to be sumitted, scope consider all construction phases. |  |  | 1 | 0 | 1 | 14800410.23 | 773133.75
724716 | [Quebradillas Streetlighting] (Distribution | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 11505789.6 | 550706.35 | 1511148.92 | 77403.68 |  |  | 13645048.55 | 13016938.52 | 628110.03 | N | Victor V. DeCastro Carlo | N/A | DSOW package complete.Ready to be sumitted, scope consider all construction phases. | DSOW package complete.Ready to be sumitted, scope consider all construction phases. | 10502157.5 | 195150.03 | 1872541.02 | 0 | 642240 | 432960 | 13645048.55 | 13016938.52 | 628110.03 | DSOW – Scope and Cost development in progress | Q1 FY2027 | DSOW package complete.Ready to be sumitted, scope consider all construction phases. |  |  | 1 | 0 | 1 | 13016938.52 | 628110.03
713795 | [Lares Streetlighting] (Distribution | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 13027118.33 | 631320.8 | 1563494.51 | 80701.22 |  |  | 15302634.86 | 14590612.84 | 712022.02 | N | Victor V. DeCastro Carlo | N/A | DSOW package complete.Ready to be sumitted, scope consider all construction phases. | DSOW package complete.Ready to be sumitted, scope consider all construction phases. | 11882095.1 | 217275.01 | 1974624.75 | 0 | 733893 | 494747 | 15302634.86 | 14590612.85 | 712022.01 | DSOW – Scope and Cost development in progress | Q1 FY2027 | DSOW package complete.Ready to be sumitted, scope consider all construction phases. |  |  | 1 | 0 | 0 | 14590612.84 | 712022.02
724670 | [Patillas Streetlighting] (Distribution | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 9123256.82 | 358025.92 | 1167539.54 | 48560.66 |  |  | 10697382.94 | 10290796.36 | 406586.58 | N | Victor V. DeCastro Carlo | N/A | DSOW package complete.Ready to be sumitted, scope consider all construction phases. | DSOW package complete.Ready to be sumitted, scope consider all construction phases. | 8408428.82 | 119750.59 | 1456883.53 | 0 | 425484 | 286836 | 10697382.94 | 10290796.35 | 406586.59 | DSOW – Scope and Cost development in progress | Q1 FY2027 | DSOW package complete.Ready to be sumitted, scope consider all construction phases. |  |  | 1 | 0 | 1 | 10290796.36 | 406586.58
724781 | [Penuelas Streetlighting] (Distribution | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 8600953.35 | 357444.72 | 1159987.24 | 51045.69 |  |  | 10169431 | 9760940.59 | 408490.41 | N | Victor V. DeCastro Carlo | N/A | DSOW package complete.Ready to be sumitted, scope consider all construction phases. | DSOW package complete.Ready to be sumitted, scope consider all construction phases. | 7929864.73 | 140145.41 | 1433020.87 | 0 | 398055 | 268345 | 10169431.01 | 9760940.6 | 408490.41 | DSOW – Scope and Cost development in progress | Q1 FY2027 | DSOW package complete.Ready to be sumitted, scope consider all construction phases. |  |  | 1 | 0 | 1 | 9760940.59 | 408490.41
735357 | FAASt [Mayaguez Streetlighting - Part 2] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 2005600 | 0 | 330319.93 | 0 | 0 | 0 | 2335919.93 | 2335919.93 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 1744 only components scope. Poles location will be reduced, estimated of: 516 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 1744 only components scope. Poles location will be reduced, estimated of: 516 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
746108 | FAASt [San Juan Streetlighting - Part 2] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 7814250 | 0 | 825170.91 | 0 | 0 | 0 | 8639420.91 | 8639420.91 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 6795 only components scope. Poles location will be reduced, estimated of: 1231 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 6795 only components scope. Poles location will be reduced, estimated of: 1231 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
735131 | FAASt [Arecibo Streetlighting - Part 2] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 3149850 | 0 | 503094.78 | 0 | 0 | 0 | 3652944.78 | 3652944.78 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 2739 only components scope. Poles location will be reduced, estimated of: 981 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 2739 only components scope. Poles location will be reduced, estimated of: 981 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
746111 | FAASt [Caguas Streetlighting - Part 2] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 3646650 | 0 | 508288.97 | 0 | 0 | 0 | 4154938.97 | 4154938.97 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 3171 only components scope. Poles location will be reduced, estimated of: 595 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 3171 only components scope. Poles location will be reduced, estimated of: 595 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
735665 | FAASt [Carolina Streetlighting - Part 2] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 4328600 | 0 | 795422.75 | 0 | 0 | 0 | 5124022.75 | 5124022.75 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 3764 only components scope. Poles location will be reduced, estimated of: 258 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 3764 only components scope. Poles location will be reduced, estimated of: 258 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
734728 | FAASt [Ponce Streetlighting - Part 2] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 3681150 | 0 | 576959.77 | 0 | 0 | 0 | 4258109.77 | 4258109.77 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 3201 only components scope. Poles location will be reduced, estimated of: 742 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 3201 only components scope. Poles location will be reduced, estimated of: 742 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
735954 | FAASt [Trujillo Alto Streetlighting - Part 2] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 1817000 | 0 | 251430.18 | 0 | 0 | 0 | 2068430.18 | 2068430.18 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 1580 only components scope. Poles location will be reduced, estimated of: 505 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 1580 only components scope. Poles location will be reduced, estimated of: 505 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
734859 | FAASt [Aguadilla Streetlighting - Part 2] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 2010200 | 0 | 299127.03 | 0 | 0 | 0 | 2309327.03 | 2309327.03 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 1748 only components scope. Poles location will be reduced, estimated of: 859 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 1748 only components scope. Poles location will be reduced, estimated of: 859 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
735470 | FAASt [Bayamón Streetlighting - Part 2] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 5318750 | 0 | 704446.74 | 0 | 0 | 0 | 6023196.74 | 6023196.74 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 4625 only components scope. Poles location will be reduced, estimated of: 710 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 4625 only components scope. Poles location will be reduced, estimated of: 710 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
734791 | FAASt [Guayama Streetlighting - Part 2] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 1756050 | 0 | 444662.71 | 0 | 0 | 0 | 2200712.71 | 2200712.71 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 1527 only components scope. Poles location will be reduced, estimated of: 400 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 1527 only components scope. Poles location will be reduced, estimated of: 400 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
735493 | FAASt [Humacao Streetlighting - Part 2] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 1826200 | 0 | 324830.45 | 0 | 0 | 0 | 2151030.45 | 2151030.45 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 1589 only components scope. Poles location will be reduced, estimated of: 548 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 1589 only components scope. Poles location will be reduced, estimated of: 548 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
734927 | FAASt [Isabela Streetlighting - Part 2] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 1552500 | 0 | 306973.5 | 0 | 0 | 0 | 1859473.5 | 1859473.5 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 1350 only components scope. Poles location will be reduced, estimated of: 846 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 1350 only components scope. Poles location will be reduced, estimated of: 846 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
737804 | FAASt [Rio Grande Streetlighting - Part 2 ] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 1788250 | 0 | 279529.57 | 0 | 0 | 0 | 2067779.57 | 2067779.57 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 1555 only components scope. Poles location will be reduced, estimated of: 451 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 1555 only components scope. Poles location will be reduced, estimated of: 451 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
737707 | FAASt [Toa Alta Streetlighting - Part 2] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 2219500 | 0 | 364572.61 | 0 | 0 | 0 | 2584072.61 | 2584072.61 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 1930 only components scope. Poles location will be reduced, estimated of: 565 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 1930 only components scope. Poles location will be reduced, estimated of: 565 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
734393 | FAASt [Cabo Rojo Streetlighting - Part 2] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 2168900 | 0 | 368432.14 | 0 | 0 | 0 | 2537332.14 | 2537332.14 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 1886 only components scope. Poles location will be reduced, estimated of: 633 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 1886 only components scope. Poles location will be reduced, estimated of: 633 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
735677 | FAASt [Guaynabo Streetlighting - Part 2] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 1935450 | 0 | 384791.84 | 0 | 0 | 0 | 2320241.84 | 2320241.84 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 1683 only components scope. Poles location will be reduced, estimated of: 597 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 1683 only components scope. Poles location will be reduced, estimated of: 597 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
735960 | FAASt [Toa Baja Streetlighting - Part 2] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 1461650 | 0 | 311784.53 | 0 | 0 | 0 | 1773434.53 | 1773434.53 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 1271 only components scope. Poles location will be reduced, estimated of: 767 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 1271 only components scope. Poles location will be reduced, estimated of: 767 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
735940 | FAASt [Vega Baja Streetlighting - Part 2] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 1896350 | 0 | 313451.11 | 0 | 0 | 0 | 2209801.11 | 2209801.11 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 1649 only components scope. Poles location will be reduced, estimated of: 590 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 1649 only components scope. Poles location will be reduced, estimated of: 590 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
735360 | FAASt [Mayaguez Streetlighting - Part 3] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 2967000 | 0 | 934399.04 | 0 | 0 | 0 | 3901399.04 | 3901399.04 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 2580 only components scope. Poles location will be reduced, estimated of: 1427 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 2580 only components scope. Poles location will be reduced, estimated of: 1427 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
737712 | FAAST [San Juan Streetlighting - Part 3] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 7826900 | 0 | 1103286.53 | 0 | 0 | 0 | 8930186.53 | 8930186.53 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 6847 only components scope. Poles location will be reduced, estimated of: 1478 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 6847 only components scope. Poles location will be reduced, estimated of: 1478 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
734853 | FAASt [Arecibo Streetlighting- Part 3] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 2778400 | 0 | 570030.05 | 0 | 0 | 0 | 3348430.05 | 3348430.05 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 2416 only components scope. Poles location will be reduced, estimated of: 1788 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 2416 only components scope. Poles location will be reduced, estimated of: 1788 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
735672 | FAASt [Caguas Streetlighting - Part 3] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 3448850 | 0 | 752635.32 | 0 | 0 | 0 | 4201485.32 | 4201485.32 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 2999 only components scope. Poles location will be reduced, estimated of: 1053 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 2999 only components scope. Poles location will be reduced, estimated of: 1053 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
735496 | FAASt [Carolina Streetlighting - Part 3] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 3936450 | 0 | 684791.58 | 0 | 0 | 0 | 4621241.58 | 4621241.58 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 3423 only components scope. Poles location will be reduced, estimated of: 1143 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 3423 only components scope. Poles location will be reduced, estimated of: 1143 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
734760 | FAASt [Ponce Streetlighting - Part 3] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 3221150 | 0 | 700990.05 | 0 | 0 | 0 | 3922140.05 | 3922140.05 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 2801 only components scope. Poles location will be reduced, estimated of: 1229 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 2801 only components scope. Poles location will be reduced, estimated of: 1229 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
735952 | FAASt [Trujillo Alto Streetlighting - Part 3] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 1597350 | 0 | 369585.51 | 0 | 0 | 0 | 1966935.51 | 1966935.51 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 1388 only components scope. Poles location will be reduced, estimated of: 732 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 1388 only components scope. Poles location will be reduced, estimated of: 732 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
735338 | FAASt [Aguadilla Streetlighting - Part 3] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 1401850 | 0 | 313621.72 | 0 | 0 | 0 | 1715471.72 | 1715471.72 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 1219 only components scope. Poles location will be reduced, estimated of: 915 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 1219 only components scope. Poles location will be reduced, estimated of: 915 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
735472 | FAASt [Bayamon Streetlighting - Part 3] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 4418300 | 0 | 739172.36 | 0 | 0 | 0 | 5157472.36 | 5157472.36 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 3842 only components scope. Poles location will be reduced, estimated of: 1626 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 3842 only components scope. Poles location will be reduced, estimated of: 1626 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
734789 | FAASt [Guayama Streetlighting - Part 3 ] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 1679000 | 0 | 285214.71 | 0 | 0 | 0 | 1964214.71 | 1964214.71 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 1460 only components scope. Poles location will be reduced, estimated of: 362 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 1460 only components scope. Poles location will be reduced, estimated of: 362 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
735487 | FAASt [Humacao Streetlighting - Part 3] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 1498450 | 0 | 282005.08 | 0 | 0 | 0 | 1780455.08 | 1780455.08 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 1303 only components scope. Poles location will be reduced, estimated of: 636 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 1303 only components scope. Poles location will be reduced, estimated of: 636 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
734928 | FAASt [Isabela Streetlighting - Part 3] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 1163800 | 0 | 325113.23 | 0 | 0 | 0 | 1488913.23 | 1488913.23 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 1012 only components scope. Poles location will be reduced, estimated of: 626 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 1012 only components scope. Poles location will be reduced, estimated of: 626 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
737798 | FAASt [Rio Grande Streetlighting - Part 3] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 1212100 | 0 | 239093.65 | 0 | 0 | 0 | 1451193.65 | 1451193.65 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 1054 only components scope. Poles location will be reduced, estimated of: 545 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 1054 only components scope. Poles location will be reduced, estimated of: 545 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
737699 | FAASt [Toa Alta Streetlighting - Part 3] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 1058000 | 0 | 221137.35 | 0 | 0 | 0 | 1279137.35 | 1279137.35 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 920 only components scope. Poles location will be reduced, estimated of: 346 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 920 only components scope. Poles location will be reduced, estimated of: 346 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
734396 | FAASt [Cabo Rojo Streetlighting - Part 3] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 1246600 | 0 | 279407 | 0 | 0 | 0 | 1526007 | 1526007 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 1084 only components scope. Poles location will be reduced, estimated of: 743 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 1084 only components scope. Poles location will be reduced, estimated of: 743 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
735499 | FAASt [Guaynabo Streetlighting - Part 3] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 1838850 | 0 | 375286.43 | 0 | 0 | 0 | 2214136.43 | 2214136.43 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 1599 only components scope. Poles location will be reduced, estimated of: 904 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 1599 only components scope. Poles location will be reduced, estimated of: 904 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
735959 | FAASt [Toa Baja Streetlighting - Part 3] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 1317900 | 0 | 300491.01 | 0 | 0 | 0 | 1618391.01 | 1618391.01 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 1146 only components scope. Poles location will be reduced, estimated of: 571 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 1146 only components scope. Poles location will be reduced, estimated of: 571 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
735483 | FAASt [Vega Baja Streetlighting - Part 3] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 1308700 | 0 | 265069.11 | 0 | 0 | 0 | 1573769.11 | 1573769.11 | 0 |  | Victor V. DeCastro Carlo | N/A | This project have an estimate of: 1138 only components scope. Poles location will be reduced, estimated of: 663 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope.Lodging and Perdiem Cost arent considered | This project have an estimate of: 1138 only components scope. Poles location will be reduced, estimated of: 663 locations. Once previous ongoing obligated projects in the program enter in closeout stage, savings will be considered for ammedment to include pole scope. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
812041 | [Feeder Rebuild # 9501-02] (Distribution | No | No | Distribution | Rebuild | No | Inactive | Inactive | 22571513.15 |  | 3314820.98 |  | 3357740.92 |  | 29244075.05 | 29244075.05 | 0 | No | Victor V. DeCastro Carlo | N/A | Project was under FEMA Workflow EHP evaluation before being withdrawn. This feeder has a CMI of 5.96M, Engineering stages are nearing completion for DSOW submission. (Replacement for 6012-02 CMI 4.8M) | Project was under FEMA Workflow EHP evaluation before being withdrawn. This feeder has a CMI of 5.96M, Engineering stages are nearing completion for DSOW submission. (Replacement for 6012-02 CMI 4.8M) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
754350 | Distribution Underground Circuit Feeders - San Juan Group 1 | No | No | Distribution | Underground | No | Inactive | Inactive | 4310111.715 | 9577521.9267 | 362956.776 | 812115.7863 | 1512.3199 | 58980.4761 | 15123199 | 4674580.8109 | 10448618.1891 | No | Victor V. DeCastro Carlo | N/A | Pending Operation Assessment, and design work has not yet been finalized. Further evaluation is required before moving forward. | Pending Operation Assessment, and design work has not yet been finalized. Further evaluation is required before moving forward. | 4310111.715 | 9577521.9267 | 362956.776 | 812115.7863 | 1512.3199 | 58980.4761 | 15123199 | 4674580.8109 | 10448618.1891 | DSOW – Pending Design Package for Development | Q1 FY2028 | Pending Operation Assessment, and design work has not yet been finalized. Further evaluation is required before moving forward. |  |  | 1 | 0 | 0 | 0 | 0
754351 | ​Distribution Underground Circuit Feeders - San Juan Group 2 | No | No | Distribution | Underground | No | Inactive | Inactive | 2013990.405 | 4475298.6789 | 169599.192 | 379478.1921 | 706.6633 | 27559.8687 | 7066633 | 2184296.2603 | 4882336.7397 | No | Victor V. DeCastro Carlo | N/A | Pending Operation Assessment, and design work has not yet been finalized. Further evaluation is required before moving forward. | Pending Operation Assessment, and design work has not yet been finalized. Further evaluation is required before moving forward. | 2013990.405 | 4475298.6789 | 169599.192 | 379478.1921 | 706.6633 | 27559.8687 | 7066633 | 2184296.2603 | 4882336.7397 | DSOW – Pending Design Package for Development | Q1 FY2028 | Pending Operation Assessment, and design work has not yet been finalized. Further evaluation is required before moving forward. |  |  | 1 | 0 | 0 | 0 | 0
718971 | FAASt [Line 50300 (230kV) from Costa Sur Steam Plant to Aguirre Steam Plant] (Transmission) | No | No | Transmission | Line Rebuild | No | Inactive | Inactive | 9936000 | 5400000 | 864000 | 864000 | 1296000 | 3240000 | 21600000 | 12096000 | 9504000 | N | Hector S. / Daniel H. | N/A | Project Not Obligated | No change to last submitted information. | 9936000 | 5400000 | 864000 | 864000 | 1296000 | 3240000 | 21600000 | 12096000 | 9504000 | DSOW – Pending Design Package for Development | Q3 FY2027 | This line is key for hardening by replacing targeted structures as well as insulators and hardware along the entire line length, with a high-level estimate at $30M. Additional future scope proposed for 406 includes adding a 230/115kV new substation at Santa Isabel TC which would significantly reduce the exposure (probability and likelihood that the facility is not available after a storm) as well as facilitate a pathway for new large-scale renewables being added in the South and Southeast regions. |  |  | 1 | 0 | 0 | 0 | 0
730657 | [Line 2200 Dos Bocas HP to Dorado TC ] (Transmission | No | No | Transmission | Line Rebuild | No | Inactive | Inactive | 57872010.7354 | 31452179.7475 | 5032348.7596 | 5032348.7596 | 7548523.1394 | 18871307.8485 | 125808718.99 | 70452882.6344 | 55355836.3556 | N | Hector S. / Daniel H. | N/A | Project Not Obligated | No change to last submitted information. | 57872010.7354 | 31452179.7475 | 5032348.7596 | 5032348.7596 | 7548523.1394 | 18871307.8485 | 125808718.99 | 70452882.6344 | 55355836.3556 | DSOW – Pending Design Package for Development | Q3 FY2027 | The planned scope for this facility is first to rebuild the undersized segment from Manati to Vega Baja to achieve a capacity increase to a minimum of 1160A. The proposed second phase is to restore the out-of-service segment from Dos Bocas to Cambalache. As requested by PMs based on latest value engineering, 3 segments were selected (1, 7 & 8) |  |  | 1 | 0 | 0 | 0 | 0
753785 | TPole 3300 San Gerardo Sect to Venezuela Sect | Yes | Yes | Transmission | Transmission Priority Pole Replacements | No | Inactive | Inactive | 299085.29 | 81090.53 | 55226.85 | 14556.86 | 12296.95 | 1013.73 | 463270.21 | 366609.09 | 96661.12 | N | Carlos Samalot | N/A | Project Not Obligated | Cost Estimate and DSOW have been updated to latest template and are ready for submittal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
753786 | TPole 5900 San Juan SP to Crematorio TO | Yes | Yes | Transmission | Transmission Priority Pole Replacements | No | Active | Active | 407830.94 | 1921.02 | 77598.93 | 1382.15 | 40781.7 | 6101.3 | 535616.04 | 526211.57 | 9404.47 | Y | Carlos Samalot | N/A | Project Not Obligated | Cost Estimate and DSOW have been updated to latest template and are ready for submittal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 0 | 0 | Anadir numero nuevo
753787 | TPole 13700 Mora TC to Isabela TO | Yes | Yes | Transmission | Transmission Priority Pole Replacements | No | Inactive | Inactive | 591148.31 | 7196.15 | 103198.13 | 1529 | 35991.1 | 2143.44 | 741206.13 | 730337.54 | 10868.59 | Y | Carlos Samalot | N/A | Project Not Obligated | Cost Estimate and DSOW have been updated to latest template and are ready for submittal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
811923 | Transmission Priority Pole Replacement Program Line 16500 Fajardo TC-Dos Marinas | Yes | Yes | Transmission | Transmission Priority Pole Replacements | No | Active | Active | 212650.88 | 381.28 | 48267.18 | 305.98 | 37102.11 | 1220.26 | 299927.69 | 298020.17 | 1907.52 | Y | Carlos Samalot | N/A | Project Not Obligated | Cost Estimate and DSOW have been updated to latest template and are ready for submittal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 0 | 0 | Anadir numero nuevo
1064452 | Transmission Priority Pole Replacement Program Line 800 Comsat Sect –Cidra Sect (Active) | No | No | Transmission | Transmission Priority Pole Replacements | No | Inactive | Inactive | 609182.23 | 2812.61 | 110189.24 | 1928.4 | 52018.89 | 8792.11 | 784923.48 | 771390.36 | 13533.12 | Y | Carlos Samalot | N/A | Project Not Obligated | The project has been activated by FEMA, and the updated LPCE has been submitted as stated by the Asset Lead. This project has been given a new project number; refer to column A information. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
TBD | Tline 8700 / TL1100 | No | No | Transmission | Line Rebuild | No | Inactive | Inactive | [6 empty] | 40000000 | 0 | 0 | N | Daniel H. | N/A | Project Not Obligated | Project cost is based on a budgetary estimate of ($40M). The 406 HM cost allocation is due to the project serving as a mitigation for generation, as requested by PREB. The project is currently undergoing a technical review between LUMA and PREPA to define the optimal scope for moving forward with execution. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
741097 | Region 1 San Juan Substation/Telecom | No | No | Vegetation | Vegetation | No | Inactive | Inactive | 0 | 867756.78 | 0 | 479435.25 | 0 | 0 | 1347192.03 | 0 | 1347192.03 | N | Rene Baptiste | No amendment needed in these set of projects. | No Comment. Will not be revisited. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
741098 | Region 3 Bayamon Substation/Telecom | No | No | Vegetation | Vegetation | No | Inactive | Inactive | 0 | 169300.95 | 0 | 93538.61 | 0 | 0 | 262839.56 | 0 | 262839.56 | N | Rene Baptiste | No amendment needed in these set of projects. | No Comment. Will not be revisited. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
741102 | Region 5 Mayaguez Substation/Telecom | No | No | Vegetation | Vegetation | No | Inactive | Inactive | 0 | 619336 | 0 | 342183 | 0 | 0 | 961519 | 0 | 961519 | N | Rene Baptiste | No amendment needed in these set of projects. | No Comment. Will not be revisited. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
741101 | Region 2 Arecibo Substation/Telecom | No | No | Vegetation | Vegetation | No | Inactive | Inactive | 0 | 69780.78 | 0 | 38554.25 | 0 | 0 | 108335.03 | 0 | 108335.03 | N | Rene Baptiste | No amendment needed in these set of projects. | No Comment. Will not be revisited. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
741104 | Region 6 Ponce Substation/Telecom | No | No | Vegetation | Vegetation | No | Inactive | Inactive | 0 | 977124.29 | 0 | 539861.35 | 0 | 0 | 1516985.64 | 0 | 1516985.64 | N | Rene Baptiste | No amendment needed in these set of projects. | No Comment. Will not be revisited. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
741100 | Region 4 Caguas Substation/Telecom | No | No | Vegetation | Vegetation | No | Inactive | Inactive | 0 | 1283718.51 | 0 | 709255.11 | 0 | 0 | 1992973.62 | 0 | 1992973.62 | N | Rene Baptiste | No amendment needed in these set of projects. | No Comment. Will not be revisited. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Pending FASSt | FAASt [Region 6 Ponce Distribution sensitive areas] (Vegetation) | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 42934620.7125 | 117568634.2875 | - | - | - | - | 160503255 | 42934620.7125 | 117568634.2875 | N | Rene Baptiste | No amendment needed in these set of projects. | No comment. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Pending FASSt | FAASt [Region 5 Mayaguez Distribution sensitive areas] (Vegetation) | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 58330775.8125 | 159728199.1875 | - | - | - | - | 218058975 | 58330775.8125 | 159728199.1875 | N | Rene Baptiste | No amendment needed in these set of projects. | No comment. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Pending FASSt | FAASt [Region 2 Arecibo Distribution sensitive areas] (Vegetation) | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 50485034.25 | 138244065.75 | - | - | - | - | 188729100 | 50485034.25 | 138244065.75 | N | Rene Baptiste | No amendment needed in these set of projects. | No comment. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Pending FASSt | FAASt [Region 4 Caguas Distribution sensitive areas] (Vegetation) | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 44184703.05 | 120991756.95 | - | - | - | - | 165176460 | 44184703.05 | 120991756.95 | N | Rene Baptiste | No amendment needed in these set of projects. | No comment. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Pending FASSt | FAASt [Region 3 Bayamon Distribution sensitive areas] (Vegetation) | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 9021119.175 | 24702690.825 | - | - | - | - | 33723810 | 9021119.175 | 24702690.825 | N | Rene Baptiste | No amendment needed in these set of projects. | No comment. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Pending FASSt | FAASt [Region 1 San Juan Distribution sensitive areas] (Vegetation) | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 36635336.775 | 100319193.225 | - | - | - | - | 136954530 | 36635336.775 | 100319193.225 | N | Rene Baptiste | No amendment needed in these set of projects. | No comment. | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
727691 | FAASt [Region 1 San Juan Transmission 38kV sensitive areas] (Vegetation) - Group C | Yes | No | Vegetation | Vegetation-TL | No | Inactive | Inactive | 788376.99 | 8663674.704 | 6629.484 | 72765.402 | 0 | 0 | 9531446.58 | 795006.474 | 8736440.106 | Y | Rene Baptiste | Amendments might apply in future versions. | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. | No updated comment, previous comment remains. | 1313961.65 | 14439457.84 | 11049.14 | 121275.67 | 0 | 0 | 15885744.3 | 1325010.79 | 14560733.51 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | Project is developed and will be ready to submit to FEMA as soon as projects are reactivated in Grants Portal |  |  | 1 | 0 | 0 | 795006.474 | 8736440.106
740406 | FAASt[Region 1 San Juan Transmission 38kV - Non-Sensitive (Vegetation)] - Group B | Yes | Yes | Vegetation | Vegetation-TL | No | Inactive | Inactive | 281264.03 | 3116841.11 | 2365.12 | 25959.59 | 0 | 0 | 3426429.85 | 283629.15 | 3142800.7 | N | Rene Baptiste | Amendments might apply in future versions. | No comments. Projects already submitted to PREPA. | No updated comment, previous comment remains. | 281345.36 | 3091775.16 | 2365.85 | 25967.52 | 0 | 0 | 3401453.89 | 283711.21 | 3117742.68 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | Project is developed and will be ready to submit to FEMA as soon as projects are reactivated in Grants Portal |  |  | 1 | 0 | 0 | 283629.15 | 3142800.7
740410 | FAASt[Region 2 Arecibo Transmission 38kV - Non-Sensitive (Vegetation)]- Group B | Yes | Yes | Vegetation | Vegetation-TL | No | Inactive | Inactive | 21352.15 | 236614.32 | 179.55 | 1970.74 | 0 | 0 | 260116.76 | 21531.7 | 238585.06 | N | Rene Baptiste | Amendments might apply in future versions. | No comments. Projects already submitted to PREPA. | No updated comment, previous comment remains. | 251201.23 | 2760513.52 | 2112.36 | 23185.29 | 0 | 0 | 3037012.4 | 253313.59 | 2783698.81 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | Project is developed and will be ready to submit to FEMA as soon as projects are reactivated in Grants Portal |  |  | 1 | 0 | 0 | 21531.7 | 238585.06
740409 | FAASt[Region 4 Caguas Transmission 38kV - Non-Sensitive (Vegetation)]- Group B | Yes | Yes | Vegetation | Vegetation-TL | No | Inactive | Inactive | 715385.11 | 7927576.7 | 6901584.83 | 66028.4 | 0 | 0 | 15610575.04 | 7616969.94 | 7993605.1 | N | Rene Baptiste | Amendments might apply in future versions. | No comments. Projects already submitted to PREPA. | No updated comment, previous comment remains. | 715385.11 | 7927576.7 | 6015.7 | 66028.4 | 0 | 0 | 8715005.91 | 721400.81 | 7993605.1 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | Project is developed and will be ready to submit to FEMA as soon as projects are reactivated in Grants Portal |  |  | 1 | 0 | 0 | 7616969.94 | 7993605.1
740414 | FAASt [Region 6 Ponce Transmission 38kV - Non-Sensitive (Vegetation)- Group B | Yes | Yes | Vegetation | Vegetation-TL | No | Inactive | Inactive | 141749.28 | 1570801.41 | 1191.98 | 13083.11 | 0 | 0 | 1726825.78 | 142941.26 | 1583884.52 | N | Rene Baptiste | Amendments might apply in future versions. | No comments. Projects already submitted to PREPA. | No updated comment, previous comment remains. | 799358.09 | 8784348.55 | 6721.82 | 73778.93 | 0 | 0 | 9664207.39 | 806079.91 | 8858127.48 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | Project is developed and will be ready to submit to FEMA as soon as projects are reactivated in Grants Portal |  |  | 1 | 0 | 0 | 142941.26 | 1583884.52
727694 | FAASt [Region 4 Caguas Transmission 38kV sensitive areas] (Vegetation) - Group C | Yes | No | Vegetation | Vegetation-TL | No | Inactive | Inactive | 437628.366 | 4809208.998 | 3680.034 | 40392.096 | 0 | 0 | 5290909.494 | 441308.4 | 4849601.094 | Y | Rene Baptiste | Amendments might apply in future versions. | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. | No updated comment, previous comment remains. | 729380.61 | 8015348.33 | 6133.39 | 67320.16 | 0 | 0 | 8818182.49 | 735514 | 8082668.49 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | Project is developed and will be ready to submit to FEMA as soon as projects are reactivated in Grants Portal |  |  | 1 | 0 | 0 | 441308.4 | 4849601.094
740411 | FAASt [Region 5 Mayaguez Transmission 38kV - Non-Sensitive (Vegetation)]- Group B | Yes | Yes | Vegetation | Vegetation-TL | No | Inactive | Inactive | 799358.09 | 8858127.48 | 6721.82 | 73778.93 | 0 | 0 | 9737986.32 | 806079.91 | 8931906.41 | N | Rene Baptiste | Amendments might apply in future versions. | No comments. Projects already submitted to PREPA. | No updated comment, previous comment remains. | 141749.28 | 1557718.3 | 1191.98 | 13083.11 | 0 | 0 | 1713742.67 | 142941.26 | 1570801.41 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | Project is developed and will be ready to submit to FEMA as soon as projects are reactivated in Grants Portal |  |  | 1 | 0 | 0 | 806079.91 | 8931906.41
727562 | FAASt [Region 5 Mayaguez Transmission 38kV sensitive areas] (Vegetation) - Group C | Yes | No | Vegetation | Vegetation-TL | No | Inactive | Inactive | 1232141.82 | 13540319.136 | 10361.1 | 113723.898 | 0 | 0 | 14896545.954 | 1242502.92 | 13654043.034 | Y | Rene Baptiste | Amendments might apply in future versions. | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. | No updated comment, previous comment remains. | 2053569.7 | 22567198.56 | 17268.5 | 189539.83 | 0 | 0 | 24827576.59 | 2070838.2 | 22756738.39 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | Project is developed and will be ready to submit to FEMA as soon as projects are reactivated in Grants Portal |  |  | 1 | 0 | 0 | 1242502.92 | 13654043.034
727530 | FAASt [Region 6 Ponce Transmission 38kV sensitive areas] (Vegetation) - Group C | Yes | No | Vegetation | Vegetation-TL | No | Inactive | Inactive | 1367036.856 | 15022714.938 | 11495.436 | 126174.408 | 0 | 0 | 16527421.638 | 1378532.292 | 15148889.346 | Y | Rene Baptiste | Amendments might apply in future versions. | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. | No updated comment, previous comment remains. | 2278394.76 | 25037858.23 | 19159.06 | 210290.68 | 0 | 0 | 27545702.73 | 2297553.82 | 25248148.91 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | Project is developed and will be ready to submit to FEMA as soon as projects are reactivated in Grants Portal |  |  | 1 | 0 | 0 | 1378532.292 | 15148889.346
727540 | FAASt [Region 2 Arecibo Transmission 38kV sensitive areas] (Vegetation) - Group C | Yes | No | Vegetation | Vegetation-TL | No | Inactive | Inactive | 1105536.432 | 12149020.278 | 9296.478 | 102038.502 | 0 | 0 | 13365891.69 | 1114832.91 | 12251058.78 | Y | Rene Baptiste | Amendments might apply in future versions. | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. | No updated comment, previous comment remains. | 1842560.72 | 20248367.13 | 15494.13 | 170064.17 | 0 | 0 | 22276486.15 | 1858054.85 | 20418431.3 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | Project is developed and will be ready to submit to FEMA as soon as projects are reactivated in Grants Portal |  |  | 1 | 0 | 0 | 1114832.91 | 12251058.78
740408 | FAASt[Region 3 Bayamon Transmission 38kV - Non-Sensitive (Vegetation)]- Group B | Yes | Yes | Vegetation | Vegetation-TL | No | Inactive | Inactive | 622799.54 | 6901584.83 | 5237.14 | 57482.97 | 0 | 0 | 7587104.48 | 628036.68 | 6959067.8 | N | Rene Baptiste | Amendments might apply in future versions. | No comment. | No updated comment, previous comment remains. | 666580.3 | 7325219.95 | 5605.29 | 61523.84 | 0 | 0 | 8058929.38 | 672185.59 | 7386743.79 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | Project is developed and will be ready to submit to FEMA as soon as projects are reactivated in Grants Portal |  |  | 1 | 0 | 0 | 628036.68 | 6959067.8
727558 | FAASt [Region 3 Bayamon Transmission 38kV sensitive areas] (Vegetation) - Group C | Yes | No | Vegetation | Vegetation-TL | No | Inactive | Inactive | 793759.878 | 8722828.56 | 6674.742 | 73262.238 | 0 | 0 | 9596525.418 | 800434.62 | 8796090.798 | Y | Rene Baptiste | Amendments might apply in future versions. | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. | No updated comment, previous comment remains. | 1322933.13 | 14538047.6 | 11124.57 | 122103.73 | 0 | 0 | 15994209.03 | 1334057.7 | 14660151.33 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | Project is developed and will be ready to submit to FEMA as soon as projects are reactivated in Grants Portal |  |  | 1 | 0 | 0 | 800434.62 | 8796090.798
Pending FASSt | 38kV Transmission Line 100 – Entire Line (Vegetation) | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 254933.334 | 2801526.9 | 2143.746 | 23529.756 | - | - | 3082133.736 | 257077.08 | 2825056.656 | Y | Rene Baptiste | Amendments might apply in future versions. | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. | No updated comment, previous comment remains. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Pending FASSt | 38kV Transmission Line 200 – Entire Line (Vegetation) | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 155350.008 | 1707180.444 | 1306.344 | 14338.44 | - | - | 1878175.236 | 156656.352 | 1721518.884 | Y | Rene Baptiste | Amendments might apply in future versions. | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. | No updated comment, previous comment remains. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Pending FASSt | 38kV Transmission Line 800 – Entire Line (Vegetation) | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 161271.174 | 1772249.706 | 1356.138 | 14884.95 | - | - | 1949761.968 | 162627.312 | 1787134.656 | Y | Rene Baptiste | Amendments might apply in future versions. | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. | No updated comment, previous comment remains. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Pending FASSt | 38kV Transmission Line 1200 – Entire Line (Vegetation) | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 275711.268 | 3029860.812 | 2318.466 | 25447.512 | - | - | 3333338.058 | 278029.734 | 3055308.324 | Y | Rene Baptiste | Amendments might apply in future versions. | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. | No updated comment, previous comment remains. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Pending FASSt | 38kV Transmission Line 1600 – Entire Line (Vegetation) | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 305424.768 | 3356390.148 | 2568.324 | 28190.004 | - | - | 3692573.244 | 307993.092 | 3384580.152 | Y | Rene Baptiste | Amendments might apply in future versions. | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. | No updated comment, previous comment remains. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Pending FASSt | 38kV Transmission Line 2000 – Entire Line (Vegetation) | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 303594.6 | 3336277.806 | 2552.934 | 28021.086 | - | - | 3670446.426 | 306147.534 | 3364298.892 | Y | Rene Baptiste | Amendments might apply in future versions. | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. | No updated comment, previous comment remains. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Pending FASSt | 38kV Transmission Line 2100 – Entire Line (Vegetation) | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 304778.826 | 3349291.674 | 2562.894 | 28130.388 | - | - | 3684763.782 | 307341.72 | 3377422.062 | Y | Rene Baptiste | Amendments might apply in future versions. | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. | No updated comment, previous comment remains. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Pending FASSt | 38kV Transmission Line 2200 – Entire Line (Vegetation) | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 805386.906 | 8850600.906 | 6772.518 | 74335.38 | - | - | 9737095.71 | 812159.424 | 8924936.286 | Y | Rene Baptiste | Amendments might apply in future versions. | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. | No updated comment, previous comment remains. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Pending FASSt | 38kV Transmission Line 2500 – Entire Line (Vegetation) | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 243413.964 | 2674937.64 | 2046.876 | 22466.544 | - | - | 2942865.024 | 245460.84 | 2697404.184 | Y | Rene Baptiste | Amendments might apply in future versions. | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. | No updated comment, previous comment remains. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Pending FASSt | 38kV Transmission Line 2700 – Entire Line (Vegetation) | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 409745.04 | 4502791.986 | 3445.554 | 37818.534 | - | - | 4953801.114 | 413190.594 | 4540610.52 | Y | Rene Baptiste | Amendments might apply in future versions. | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. | No updated comment, previous comment remains. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Pending FASSt | 38kV Transmission Line 3000 – Entire Line (Vegetation) | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 491241.876 | 5398381.47 | 4130.862 | 45340.512 | - | - | 5939094.72 | 495372.738 | 5443721.982 | Y | Rene Baptiste | Amendments might apply in future versions. | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. | No updated comment, previous comment remains. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Pending FASSt | 38kV Transmission Line 3100 – Entire Line (Vegetation) | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 650144.58 | 7144603.488 | 5467.08 | 60006.864 | - | - | 7860222.012 | 655611.66 | 7204610.352 | Y | Rene Baptiste | Amendments might apply in future versions. | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. | No updated comment, previous comment remains. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Pending FASSt | 38kV Transmission Line 3700 – Entire Line (Vegetation) | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 470248.632 | 5167681.416 | 3954.33 | 43402.878 | - | - | 5685287.256 | 474202.962 | 5211084.294 | Y | Rene Baptiste | Amendments might apply in future versions. | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. | No updated comment, previous comment remains. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Pending FASSt | 38kV Transmission Line 3800 – Entire Line (Vegetation) | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 253749.102 | 2788513.05 | 2133.786 | 23420.454 | - | - | 3067816.392 | 255882.888 | 2811933.504 | Y | Rene Baptiste | Amendments might apply in future versions. | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. | No updated comment, previous comment remains. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Pending FASSt | 38kV Transmission Line 4000 – Entire Line (Vegetation) | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 113148.21 | 1243414.146 | 951.474 | 10443.306 | - | - | 1367957.136 | 114099.684 | 1253857.452 | Y | Rene Baptiste | Amendments might apply in future versions. | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. | No updated comment, previous comment remains. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Pending FASSt | 38kV Transmission Line 4800 – Entire Line (Vegetation) | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 428262.162 | 4706281.266 | 3601.272 | 39527.616 | - | - | 5177672.316 | 431863.434 | 4745808.882 | Y | Rene Baptiste | Amendments might apply in future versions. | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. | No updated comment, previous comment remains. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Pending FASSt | 38kV Transmission Line 5300 – Entire Line (Vegetation) | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 166008.114 | 1824305.088 | 1395.972 | 15322.164 | - | - | 2007031.338 | 167404.086 | 1839627.252 | Y | Rene Baptiste | Amendments might apply in future versions. | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. | No updated comment, previous comment remains. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Pending FASSt | 38kV Transmission Line 5400 – Entire Line (Vegetation) | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 288199.554 | 3167097.762 | 2423.478 | 26600.154 | - | - | 3484320.948 | 290623.032 | 3193697.916 | Y | Rene Baptiste | Amendments might apply in future versions. | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. | No updated comment, previous comment remains. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Pending FASSt | 38kV Transmission Line 5600 – Entire Line (Vegetation) | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 293582.43 | 3226251.636 | 2468.742 | 27096.984 | - | - | 3549399.792 | 296051.172 | 3253348.62 | Y | Rene Baptiste | Amendments might apply in future versions. | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. | No updated comment, previous comment remains. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
Pending FASSt | 38kV Transmission Line 6500 – Entire Line (Vegetation) | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 447640.536 | 4919235.186 | 3764.22 | 41316.198 | - | - | 5411956.14 | 451404.756 | 4960551.384 | Y | Rene Baptiste | Amendments might apply in future versions. | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. | No updated comment, previous comment remains. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
TBD | Telecom Transport Network Group 2 |  |  | Telecommunication | IT/OT | No |  |  | 38974760.61 | 52405461.42 | 3462203.48 | 4635104.34 |  |  | 99477529.85 | 42436964.09 | 57040565.76 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
547344 | Acacias 6801 TC (Relocation) | Yes | Yes | Substations | Substation Rebuilds | No | Active | Active | 65766025.0617 | 31538831.8413 | 2841208.2382 | 785561.5157 | 12378234.9672 | 3124060.0459 | 116433921.67 | 80985468.2671 | 35448453.4029 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 80985468.2671 | 35448453.4029 | Anadir numero nuevo
TBD | Aguadilla Sect 7003 Transformer 38/13.2-4.16, 22 MVA | Yes | Yes | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 236211.0391 | 65309.6452 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 6732931.9118 | 2947096.9082
TBD | ALTURAS DE MAYAGUEZ | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 236211.0391 | 65309.6452 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 1029095.8984 | 259726.6402
TBD | ALTURAS DE RIO GRANDE | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 236211.0391 | 65309.6452 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 1029095.8984 | 259726.6402
TBD | BARCELONETA PUEBLO | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 236211.0391 | 65309.6452 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 1029095.8984 | 259726.6402
TBD | BRENAS | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 236211.0391 | 65309.6452 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 1029095.8984 | 259726.6402
547247 | Cambalache TC Rebuild | Yes | Yes | Substations | Substation Rebuilds | No | Inactive | Inactive | 4966986.47 | 62195402.17 | 344907.31 | 9217663.45 | 151612.12 | 13320220.44 | 90196791.96 | 5463505.9 | 84733286.06 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 5463505.9 | 84733286.06
TBD | CAMUY | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 236211.0391 | 65309.6452 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 1029095.8984 | 259726.6402
TBD | CERAMICA | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 236211.0391 | 65309.6452 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 1029095.8984 | 259726.6402
TBD | CRUCE DAVILA | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 236211.0391 | 65309.6452 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 1029095.8984 | 259726.6402
550099 | Esc Industrial Miguel Such (Metal-Clad) 1423 | Yes | Yes | Substations | Substation Rebuilds | No | Active | Active | 3301739.68 | 1135704.94 | 1112050.13 | 0 | 6614733.66 | 4603565.8 | 16767794.21 | 11028523.47 | 5739270.74 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 11028523.47 | 5739270.74 | Anadir numero nuevo
752277 | FAASt [Substation Ciales 8701] (Substation) | No | No | Substations | Substation Rebuilds | No | Inactive | Inactive | 9069707.702 | 4349479.6256 | 391827.364 | 108335.7755 | 1706844.8419 | 431056.671 | 16057251.98 | 11168379.9079 | 4888872.0722 | Y | Carlos Baez | New Project | N/A |  | 3553830.9091 | 524335.7079 | 349557.1386 | 116519.0462 | 466076.1848 | 815633.3234 | 5825952.31 | 4369464.2325 | 1456488.0775 | DSOW – Pending Design Package for Development | Q1 FY2028 | New DSOW needs to be developed , Proposed approach focused on replacing critical components: metal-clad, transformers, breakers, communications. |  |  | 1 | 0 | 0 | 0 | 0
551260 | Guaynabo Pueblo | Yes | Yes | Substations | Substation Rebuilds | No | Active | Active | 9487047.4 | 4257510.71 | 2263654.35 | 576564.36 | 4962433.97 | 3961056.7649 | 25508267.5549 | 16713135.72 | 8795131.8349 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 16713135.72 | 8795131.8349 | Anadir numero nuevo
TBD | HATO TEJAS | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 236211.0391 | 65309.6452 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 1029095.8984 | 259726.6402
TBD | Hogar Crea 1717 Transformer 115/13.2 kV, 44.8 MVA | Yes | Yes | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 236211.0391 | 65309.6452 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 6732931.9118 | 2947096.9082
TBD | ISABELA PUEBLO | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 236211.0391 | 65309.6452 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 1029095.8984 | 259726.6402
TBD | Isla Grande TC Bank 2 Transformer 115/40 kV, 112 MVA | Yes | Yes | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 236211.0391 | 65309.6452 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 6732931.9118 | 2947096.9082
TBD | JUNCOS TC | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 12436054.1497 | 2868434.0326 | 548875.3957 | 281565.586 | 2039101.99 | 673911.4961 | 18847942.6501 | 15024031.5354 | 3823911.1147 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 2039101.99 | 673911.4961
TBD | LA RAMBLA SECT | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 236211.0391 | 65309.6452 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 1029095.8984 | 259726.6402
TBD | LAS PIEDRAS SECT | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 236211.0391 | 65309.6452 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 1029095.8984 | 259726.6402
TBD | MANATI TC | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 9069707.702 | 4349479.6256 | 391827.364 | 108335.7755 | 1706844.8419 | 431056.671 | 16057251.98 | 11168379.9079 | 4888872.0722 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 1706844.8419 | 431056.671
TBD | Mobile Substations | Yes, only E&M | No | Substations | Substations | No | Inactive | Inactive |  |  |  |  | 17709050 |  | 17709050 | 17709050 | 0 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 17709050 | 0
TBD | NAGUABO | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 236211.0391 | 65309.6452 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 1029095.8984 | 259726.6402
TBD | PATILLAS | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 236211.0391 | 65309.6452 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 1029095.8984 | 259726.6402
TBD | PENUELAS | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 236211.0391 | 65309.6452 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 1029095.8984 | 259726.6402
TBD | PUERTO DEL REY | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 236211.0391 | 65309.6452 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 1029095.8984 | 259726.6402
TBD | Quebradillas 7402 Transformer 38/13.2-4.16, 22 MVA | Yes | Yes | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 236211.0391 | 65309.6452 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 6732931.9118 | 2947096.9082
TBD | RAMEY FIELD 3 | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 236211.0391 | 65309.6452 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 1029095.8984 | 259726.6402
TBD | Rincon 7301 Transformer 38/13.2-4.16, 22 MVA | Yes | Yes | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 236211.0391 | 65309.6452 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 6732931.9118 | 2947096.9082
TBD | SABANA GRANDE | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 236211.0391 | 65309.6452 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 1029095.8984 | 259726.6402
TBD | SALINAS RURAL | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 236211.0391 | 65309.6452 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 1029095.8984 | 259726.6402
TBD | SALINAS URBANO | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 236211.0391 | 65309.6452 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 1029095.8984 | 259726.6402
TBD | Santa Isabel Sect 4401 Transformer 38/13.2-4.16, 22 MVA | Yes | Yes | Substations | Substation Component Replacements | No | Inactive | Inactive | 9069707.702 | 4349479.6256 | 391827.364 | 108335.7755 | 1706844.8419 | 431056.671 | 16057251.98 | 11168379.9079 | 4888872.0722 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 11168379.9079 | 4888872.0722
TBD | Quebrada Negrito | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 236211.0391 | 65309.6452 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 1029095.8984 | 259726.6402
TBD | TOA ALTA | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 236211.0391 | 65309.6452 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 1029095.8984 | 259726.6402
TBD | Venezuela WC |  |  | Substations | Grid Modernization | No |  |  | 6337873.936 | 472989.928 | 1584468.484 | 118247.482 | 32941132.73 | 2458367.59 | 43913080.15 | 40863475.15 | 3049605 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
TBD | Hato Rey WC |  |  | Substations | Grid Modernization | No |  |  | 1156110.08 |  | 471848.13 |  | 1079499.89 |  | 2707458.1 | 2707458.1 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
TBD | Santa Isabel WC |  |  | Substations | Grid Modernization | No |  |  | 2197333.81 |  | 7383372.13 |  |  |  | 9580705.94 | 9580705.94 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
TBD | Aguada WC |  |  | Substations | Grid Modernization | No |  |  | 535734.82 |  | 197297.35 |  | 615426.45 |  | 1348458.62 | 1348458.62 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
685869 | [Mayagüez TC] (Substation | No | No | Substations | Substation Rebuilds | No | Inactive | Inactive | 22073642.86 | 7779720.93 | 2605555.14 | 53174.57 | 13511059.91 | 183120 | 46206273.41 | 38190257.91 | 8016015.5 | [5 empty] | 22073642.86 | 543426.36 | 2605555.14 | 53174.57 | 13511059.91 | 183120 | 38969978.84 | 38190257.91 | 779720.93 | DSOW – Pending Design Package for Development | Q1 FY2027 | Awaiting cable termination and subcontractor. Received quote, started micropurchase. Breakers have already been maintained and transformer fans were replaced. Estimated Submission to COR3/FEMA 6/30/2026. |  |  | 1 | 0 | 0 | 0 | 0
TBD | VEREDAS SECT | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 236211.0391 | 65309.6452 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | Y | Carlos Baez | New Project | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 1029095.8984 | 259726.6402
TBD | Aguas Buenas | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5614147.55 | 2622060.6228 | 482672.57 | 65309.6452 | 1241258.17 | 259726.6402 | 10285175.1982 | 7338078.29 | 2947096.9082 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 1241258.17 | 259726.6402
N/A | Fiber Optic Replacement Group 1 | No | Yes | Telecommunication | IT/OT | No | Inactive | Inactive | 67811581.03 | 9902187.96 | 6835688.41 | 948496.8 | 108101.8 |  | 85606056 | 74755371.24 | 10850684.76 | N | Axel Andino | N/A | New Project |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
551927 | SCADA Remote Access and RTU Replacements Group 3 | Yes | Yes | Telecommunication | IT/OT | No | Active | Active | 18668671.07 | 3375608.8 | 2470554.28 | 425678.76 | 1293008.64 |  | 26233521.55 | 22432233.99 | 3801287.56 | N | Axel Andino | N/A | New Project |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 22432233.99 | 3801287.56 | Anadir numero nuevo
679035 | Telecomm Infrastructure Group A | Yes | Yes | Telecommunication | IT/OT | No | Inactive | Inactive | 6440145.54 | 15927.16 | 1756408.47 | 4175.18 | 2800 |  | 8219456.35 | 8199354.01 | 20102.34 | N | Axel Andino | N/A | New Project |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 1 | 8199354.01 | 20102.34
704805 | Telecomm Infrastructure Group D | No | Yes | Telecommunication | IT/OT | No | Inactive | Inactive | 5297451.62 | 18959.16 | 683790.17 | 2498.07 |  |  | 6002699.02 | 5981241.79 | 21457.23 | N | Axel Andino | N/A | New Project |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
748180 | Transmission Advanced Sensors and Wide-Area Monitoring, Protection, and Control (WAMPAC) System | Yes | Yes | Telecommunication | IT/OT | No | Active | Inactive | 0 | 47130973.41 | 0 | 5250645.64 | 0 | 423360 | 52804979.05 | 0 | 52804979.05 | N | Axel Rodriguez | N/A | New Project |  | 33071971.884 | 4086750.8114 | 4724567.412 | 472456.7412 | 3307197.1884 | 1417370.2236 | 47080314.2606 | 41103736.4844 | 5976577.7762 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | 0 |  |  | 1 | 0 | 0 | 0 | 52804979.05

## Summary
LUMA Attachment C |  | Amount ($M) | Allocation |  | Amount ($M)
428 Cost Allocation |  |  | 428 Cost Allocation |  |  | 428 Cost Allocation
| 428 Allocation (Without the A&E and E&M) | 500127199.41 |  | 428 Allocation (Without the A&E and E&M) | 4394929374.7295 |  | 428 Allocation (Without the A&E and E&M) | 3894802175.3195
| 428 A&E-PW 9510 | 45800250.62 |  | 428 A&E-PW 9510 | 517315505.9557 |  | 428 A&E-PW 9510 | 471515255.3357
| 428 E&M-PW 10710 | 162120280.4567 |  | 428 E&M-PW 10710 | 704174073.7956 |  | 428 E&M-PW 10710 | 542053793.3389
| 428 Other Incurred Cost | 54270.33 |  | 428 Other Incurred Cost | 54270.33
406 Cost Allocation
406 Cost Allocation |  |  | 406 Cost Allocation |  |  |  | 406 Allocation (Without the A&E and E&M) | 2298728982.6983
| 406 Allocation (Without the A&E and E&M) | 301262959.26 |  | 406 Allocation (Without the A&E and E&M) | 2599991941.9583 |  | 406 A&E-PW 9510 | 191927360.0168
| 406 A&E-PW 9510 | 15217565.11 |  | 406 A&E-PW 9510 | 207144925.1268 |  | 406 E&M-PW 10710 | 430916194.2041
| 406 E&M-PW 10710 | 79304184.2533 |  | 406 E&M-PW 10710 | 510220378.4575
Total 428 Expected Cost |  | 708102000.8167 | Total 428 Expected Cost |  | 5616473224.8108
Total 406 Expected Cost |  | 395784708.6233 | Total 406 Expected Cost |  | 3317357245.5426
Expected Total Project Cost |  | 1103886709.44 | Expected Total Project Cost |  | 8933830470.3534
Summary Expected Project Costs Allocation
Total Project Costs Allocation
Inccluded LUMA Consolidated List, Attachment A, Attachment B and Attachment C

## Attachment C
Estimate Project Costs Allocation (Update)
Project # | Title | Source of Project | Asset | Sub Asset | 428 Estimate (Without the A&E and E&M) | 406 Estimate (Without the A&E and E&M) | 428 A&E Estimate-PW 9510 | 406 A&E Estimate -PW 9510 | 428 E&M Estimate -PW 10710 | 406 E&M Estimate -PW 10710 | 428 Other Incurred Cost | Expected Total Project Estimate Cost | Total 428 Estimate Cost | Total 406 Estimate Cost | Comment
688623 | FAASt [Automation Program Group 1A-8 Feeders] (Distribution) | Inactive Projects List | Distribution | Automation | 15682783.16 | 2926805 | 3241962.6 | 516495 | 3708204.4 | 2410310 | 0 | 28486560.16 | 22632950.16 | 5853610 | Actuals for the "Work Completed" as of March 2026 considered, and Class 5 Estimate for the remaining work. Group 1A with 1B, 1C, and 1D was consolidated into a unique Group 1. The remaining work is based is Class 5 estimated total per project is considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (59) 3PH Reclosers, (266) 1ph reclosers, (165) cFCi. It requires an engineering evaluation once project is reactivated in order to meet current standards. Expenses incurred for partial work, including engineering and studies, which still need to be reconciled.
740662 | [Automation Program Group 2] (TL/ Distribution | Inactive Projects List | Distribution | Automation | 36782398.44 | 6876500 | 6277691.02 | 1213500 | 6850965.04 | 5663000 | 0 | 63664054.5 | 49911054.5 | 13753000 | Actuals for the "Work Completed" as of March 2026 considered, and Class 5 Estimate for the remaining work. The remaining work is Class 5 estimated total per project is considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (145) 3PH Reclosers, (539) 1ph reclosers, (254) cFCi. It requires an engineering evaluation once project is reactivated in order to meet current standards. Expenses incurred for partial work, including engineering and studies, which still need to be reconciled.
741678 | [Automation Program Group 4] (TL/Distribution | Inactive Projects List | Distribution | Automation | 29500343.61 | 5347180 | 4420325.45 | 943620 | 6946880.68 | 4403560 | 0 | 51561909.74 | 40867549.74 | 10694360 | Actuals for the "Work Completed" as of March 2026 considered, and Class 5 Estimate for the remaining work. The remaining work is Class 5 estimated total per project is considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (117) 3PH Reclosers, (247) 1ph reclosers, (182) cFCi. It requires an engineering evaluation once project is reactivated in order to meet current standards. Expenses incurred for partial work, including engineering and studies, which still need to be reconciled. Expenses have already been incurred for completed and partial work, including engineering and studies, which still need to be reconciled.
705657 | [Automation Program Group 3] (TL/Distribution | Inactive Projects List | Distribution | Automation | 30089122.78 | 4299385 | 7264119.61 | 758715 | 6881478.06 | 3540670 | 0 | 52833490.45 | 44234720.45 | 8598770 | Actuals for the "Work Completed" as of March 2026 considered, and Class 5 Estimate for the remaining work. The remaining work is Class 5 estimated total per project is considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (99) 3PH Reclosers, (316) 1ph reclosers, (212) cFCi.It requires an engineering evaluation once project is reactivated in order to meet current standards. Expenses incurred for partial work, including engineering and studies, which still need to be reconciled. Expenses have already been incurred for completed and partial work, including engineering and studies, which still need to be reconciled.
800369 | FAASt [Automation Program Group 38 | Inactive Projects List | Distribution | Automation | 802170 | 252535 | 74275 | 44565 | 103985 | 207970 | 0 | 1485500 | 980430 | 505070 | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (4) 3PH Reclosers, (29) 1ph reclosers, (21) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions.
800399 | FAASt [Automation Program Group 40 | Inactive Projects List | Distribution | Automation | 1536300 | 483650 | 142250 | 85350 | 199150 | 398300 | 0 | 2845000 | 1877700 | 967300 | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (11) 3PH Reclosers, (35) 1ph reclosers, (33) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions.
401432 | FAASt [Automation Program Group 41 | Inactive Projects List | Distribution | Automation | 1469610 | 462655 | 136075 | 81645 | 190505 | 381010 | 0 | 2721500 | 1796190 | 925310 | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (10) 3PH Reclosers, (39) 1ph reclosers, (18) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions.
801437 | FAASt [Automation Program Group 42 | Inactive Projects List | Distribution | Automation | 604800 | 190400 | 56000 | 33600 | 78400 | 156800 | 0 | 1120000 | 739200 | 380800 | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (2) 3PH Reclosers, (30) 1ph reclosers, (6) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions.
801438 | FAASt [Automation Program Group 43 | Inactive Projects List | Distribution | Automation | 851580 | 268090 | 78850 | 47310 | 110390 | 220780 | 0 | 1577000 | 1040820 | 536180 | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (4) 3PH Reclosers, (34) 1ph reclosers, (12) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions.
801440 | FAASt [Automation Program Group 44 | Inactive Projects List | Distribution | Automation | 597510 | 188105 | 55325 | 33195 | 77455 | 154910 | 0 | 1106500 | 730290 | 376210 | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (5) 3PH Reclosers, (10) 1ph reclosers, (6) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions.
801441 | FAASt [Automation Program Group 45 | Inactive Projects List | Distribution | Automation | 1221750 | 384625 | 113125 | 67875 | 158375 | 316750 | 0 | 2262500 | 1493250 | 769250 | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (10) 3PH Reclosers, (21) 1ph reclosers, (18) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions.
745854 | FAASt [Automation Program Group 9 | Inactive Projects List | Distribution | Automation | 589140 | 185470 | 54550 | 32730 | 76370 | 152740 | 0 | 1091000 | 720060 | 370940 | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (4) 3PH Reclosers, (14) 1ph reclosers, (18) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions.
745871 | FAASt [Automation Program Group 10 | Inactive Projects List | Distribution | Automation | 713610 | 224655 | 66075 | 39645 | 92505 | 185010 | 0 | 1321500 | 872190 | 449310 | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (6) 3PH Reclosers, (11) 1ph reclosers, (12) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions.
745851 | FAASt [Automation Program Group 11 | Inactive Projects List | Distribution | Automation | 720630 | 226865 | 66725 | 40035 | 93415 | 186830 | 0 | 1334500 | 880770 | 453730 | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (5) 3PH Reclosers, (18) 1ph reclosers, (12) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions.
745852 | FAASt [Automation Program Group 13 | Inactive Projects List | Distribution | Automation | 897480 | 282540 | 83100 | 49860 | 116340 | 232680 | 0 | 1662000 | 1096920 | 565080 | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (9) 3PH Reclosers, (3) 1ph reclosers, (24) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions.
TBD (Various) | Distribution Automation Program Group (67 of 151) | Urgent Incremental List | Distribution | Automation | 102018342.89 | 68012228.59 | 5106108.85 | 3404072.57 | 14932926.92 | 21347320.18 | 0 | 214821000 | 122057378.66 | 92763621.34 | The Automation Program included here is based on a grouping of projects that LUMA will split to separate groups during the formulation process as DSOWs are submitted to FEMA. This program has Approximately $61 million of cost Incurred to the E&M PW. To be clear, this line does not include "Work Completed" Distribution Automation, as construction has not commenced for the units included herein as we are pending FAASt numbers.
Pending FAASt | Venezuela WC | Urgent Incremental List | Substation | Grid Modernization | 988258.98 | 0 | 541838.04 | 0 | 1083257.99 | 0 | 0 | 2613355.01 | 2613355.01 | 0
Pending FAASt | Hato Rey WC | Urgent Incremental List | Substation | Grid Modernization | 1156110.08 | 0 | 471848.13 | 0 | 1079499.89 | 0 | 0 | 2707458.1 | 2707458.1 | 0
Pending FAASt | Aguada WC | Urgent Incremental List | Substation | Grid Modernization | 535734.82 | 0 | 197297.35 | 0 | 615426.45 | 0 | 0 | 1348458.62 | 1348458.62 | 0
Pending FAASt | Monterrey | Urgent Incremental List | Substation | Grid Modernization | 5467624.97 | 2622060.62 | 236211.04 | 65309.65 | 635052.46 | 259860.22 | 0 | 9286118.96 | 6338888.47 | 2947230.49
Pending FAASt | ALTURAS DE MAYAGUEZ | Urgent Incremental List | Substation | Substation Component Replacements | 5467624.97 | 2622060.62 | 236211.04 | 65309.65 | 1470519.69 | 490173.23 | 0 | 10351899.2 | 7174355.7 | 3177543.5
Pending FAASt | ALTURAS DE RIO GRANDE | Urgent Incremental List | Substation | Substation Component Replacements | 5467624.97 | 2622060.62 | 236211.04 | 65309.65 | 1623084.8 | 405771.2 | 0 | 10420062.28 | 7326920.81 | 3093141.47
Pending FAASt | BARCELONETA PUEBLO | Urgent Incremental List | Substation | Substation Component Replacements | 5467624.97 | 2622060.62 | 236211.04 | 65309.65 | 1736924 | 434231 | 0 | 10562361.28 | 7440760.01 | 3121601.27
Pending FAASt | BRENAS | Urgent Incremental List | Substation | Substation Component Replacements | 5467624.97 | 2622060.62 | 236211.04 | 65309.65 | 1246482.4 | 311620.6 | 0 | 9949309.28 | 6950318.41 | 2998990.87
Pending FAASt | CAMUY | Urgent Incremental List | Substation | Substation Component Replacements | 5467624.97 | 2622060.62 | 236211.04 | 65309.65 | 1736924 | 434231 | 0 | 10562361.28 | 7440760.01 | 3121601.27
Pending FAASt | CERAMICA (aka Vistamar) | Urgent Incremental List | Substation | Substation Component Replacements | 5467624.97 | 2622060.62 | 236211.04 | 65309.65 | 1623084.8 | 405771.2 | 0 | 10420062.28 | 7326920.81 | 3093141.47
Pending FAASt | CRUCE DAVILA | Urgent Incremental List | Substation | Substation Component Replacements | 5467624.97 | 2622060.62 | 236211.04 | 65309.65 | 1029095.9 | 259726.64 | 0 | 9680028.82 | 6732931.91 | 2947096.91
Pending FAASt | HATO TEJAS | Urgent Incremental List | Substation | Substation Component Replacements | 5467624.97 | 2622060.62 | 236211.04 | 65309.65 | 1470519.69 | 490173.23 | 0 | 10351899.2 | 7174355.7 | 3177543.5
Pending FAASt | ISABELA PUEBLO | Urgent Incremental List | Substation | Substation Component Replacements | 5467624.97 | 2622060.62 | 236211.04 | 65309.65 | 1736924 | 434231 | 0 | 10562361.28 | 7440760.01 | 3121601.27
Pending FAASt | JUNCOS TC | Urgent Incremental List | Substation | Substation Component Replacements | 12436054.15 | 2868434.03 | 548875.4 | 281565.59 | 2580317.19 | 860105.73 | 0 | 19575352.08 | 15565246.74 | 4010105.35
Pending FAASt | LA RAMBLA SECT | Urgent Incremental List | Substation | Substation Component Replacements | 5467624.97 | 2622060.62 | 236211.04 | 65309.65 | 1341072.11 | 447024.04 | 0 | 10179302.42 | 7044908.12 | 3134394.3
Pending FAASt | LAS PIEDRAS SECT | Urgent Incremental List | Substation | Substation Component Replacements | 5467624.97 | 2622060.62 | 236211.04 | 65309.65 | 1029095.9 | 259726.64 | 0 | 9680028.82 | 6732931.91 | 2947096.91
Pending FAASt | MANATI TC | Urgent Incremental List | Substation | Substation Component Replacements | 9069707.7 | 4349479.63 | 391827.36 | 108335.78 | 7277943.2 | 1819485.8 | 0 | 23016779.47 | 16739478.27 | 6277301.2
Pending FAASt | NAGUABO | Urgent Incremental List | Substation | Substation Component Replacements | 5467624.97 | 2622060.62 | 236211.04 | 65309.65 | 1246482.4 | 311620.6 | 0 | 9949309.28 | 6950318.41 | 2998990.87
Pending FAASt | PATILLAS | Urgent Incremental List | Substation | Substation Component Replacements | 5467624.97 | 2622060.62 | 236211.04 | 65309.65 | 1736924 | 434231 | 0 | 10562361.28 | 7440760.01 | 3121601.27
Pending FAASt | PENUELAS | Urgent Incremental List | Substation | Substation Component Replacements | 5467624.97 | 2622060.62 | 236211.04 | 65309.65 | 1029095.9 | 259726.64 | 0 | 9680028.82 | 6732931.91 | 2947096.91
Pending FAASt | PUERTO DEL REY | Urgent Incremental List | Substation | Substation Component Replacements | 5467624.97 | 2622060.62 | 236211.04 | 65309.65 | 1341072.11 | 447024.04 | 0 | 10179302.42 | 7044908.12 | 3134394.3
Pending FAASt | RAMEY FIELD 3 | Urgent Incremental List | Substation | Substation Component Replacements | 5467624.97 | 2622060.62 | 236211.04 | 65309.65 | 1029095.9 | 259726.64 | 0 | 9680028.82 | 6732931.91 | 2947096.91
Pending FAASt | SABANA GRANDE | Urgent Incremental List | Substation | Substation Component Replacements | 5467624.97 | 2622060.62 | 236211.04 | 65309.65 | 1029095.9 | 259726.64 | 0 | 9680028.82 | 6732931.91 | 2947096.91
Pending FAASt | SALINAS RURAL | Urgent Incremental List | Substation | Substation Component Replacements | 5467624.97 | 2622060.62 | 236211.04 | 65309.65 | 1029095.9 | 259726.64 | 0 | 9680028.82 | 6732931.91 | 2947096.91
Pending FAASt | SALINAS URBANO | Urgent Incremental List | Substation | Substation Component Replacements | 5467624.97 | 2622060.62 | 236211.04 | 65309.65 | 1029095.9 | 259726.64 | 0 | 9680028.82 | 6732931.91 | 2947096.91
Pending FAASt | QUEBRADA NEGRITO | Urgent Incremental List | Substation | Substation Component Replacements | 5467624.97 | 2622060.62 | 236211.04 | 65309.65 | 1260159.24 | 420053.08 | 0 | 10071418.6 | 6963995.25 | 3107423.35
Pending FAASt | TOA ALTA | Urgent Incremental List | Substation | Substation Component Replacements | 5467624.97 | 2622060.62 | 236211.04 | 65309.65 | 1736924 | 434231 | 0 | 10562361.28 | 7440760.01 | 3121601.27
Pending FAASt | VEREDAS SECT | Urgent Incremental List | Substation | Substation Component Replacements | 5467624.97 | 2622060.62 | 236211.04 | 65309.65 | 1341072.11 | 447024.04 | 0 | 10179302.42 | 7044908.12 | 3134394.3
Pending FAASt | AGUAS BUENAS | Urgent Incremental List | Substation | Substation Component Replacements | 5614147.55 | 2622060.62 | 482672.57 | 65309.65 | 1241258.17 | 259726.64 | 0 | 10285175.2 | 7338078.29 | 2947096.91
Pending FAASt | PALMER | Urgent Incremental List | Substation | Substation Component Replacements | 5467624.97 | 2622060.62 | 236211.04 | 65309.65 | 1470519.69 | 490173.23 | 0 | 10351899.2 | 7174355.7 | 3177543.5
752277 | FAASt [Substation Ciales 8701] (Substation) | Inactive Projects List | Substation | Substation Rebuilds | 9069707.7 | 4349479.63 | 391827.36 | 108335.78 | 1706844.84 | 431056.67 | 0 | 16057251.98 | 11168379.91 | 4888872.07
Pending FAASt | Telecom Transport Network Group 2 | Incremental | Telecommunication | IT/OT | 38974760.61 | 52405461.42 | 3462203.48 | 4635104.34 | 0 | 0 | 0 | 99477529.85 | 42436964.09 | 57040565.76
805517 | 38kV Recloser TL 2100 Hatillo TC to Quebradillas Sect. | Inactive Projects List | Transmission | Automation | 261599.08 | 0 | 110178.42 | 0 | 69170.22 | 0 | 21463.67 | 462411.39 | 462411.39 | 0
805519 | 38kV Recloser TL 1900 Dos Bocas HP to San Sebastian TC | Inactive Projects List | Transmission | Automation | 510778.57 | 0 | 101897.17 | 0 | 77960.25 | 0 | 17772.02 | 708408.01 | 708408.01 | 0
805521 | 38 kv Reclosers TL7800 | Inactive Projects List | Transmission | Automation | 63058.79 | 0 | 142174.45 | 0 | 64775.2 | 0 | 15034.64 | 285043.08 | 285043.08 | 0
TBD (Various) | TL 38kV Reclosers | Urgent Incremental List | Transmission | Automation | 23109489.55 | 0 | 3121828.2 | 0 | 3400000 | 0 | 0 | 29631317.75 | 29631317.75 | 0 | Cost Incurred for 38kV Recloser Program is due to Engineering and Project Management Costs ($3.1M) and Equipment Purchase Cost as the Reclosers for these projects have already been procured under the Equipment & Material PW and are in LUMA's Warehouse ($3.4M). 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review.
Pending FAASt | TL36100 Dos Bocas to Ciales - Transmission Line Rebuild | Incremental | Transmission | Line Rebuild | 36215386.59 | 6160027.9 | 2872795.2 | 429630.09 | 2206882.19 | 286465.11 |  | 48171187.08 | 41295063.98 | 6876123.1 | Was originally part of the 36100 full submittal, but the scope of that project was reduced to just the segment between Bayamon and Monacillos (and that scoped project is already in Exhibit 2). Because of that scope change, this Dos Bocas to Ciales segment does not have any other project, so needs to be added here in Attachment C. The full line 36100 has A&E incurred costs. These incurred costs are being attempted to include all in the Exhibit 2 project for the Bayamon to Monacillos segment, so that is why this project is showing as zero incurred costs for now.
Pending FAASt | 38kV Transmission Line 100 – Entire Line (Vegetation) | Incremental Vegetation Project | Vegetation | Vegetation-DL | 254933.33 | 2801526.9 | 2143.75 | 23529.76 | 0 | 0 | 0 | 3082133.74 | 257077.08 | 2825056.66 | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800.
Pending FAASt | 38kV Transmission Line 200 – Entire Line (Vegetation) | Incremental Vegetation Project | Vegetation | Vegetation-DL | 155350.01 | 1707180.44 | 1306.34 | 14338.44 | 0 | 0 | 0 | 1878175.24 | 156656.35 | 1721518.88 | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800.
Pending FAASt | 38kV Transmission Line 800 – Entire Line (Vegetation) | Incremental Vegetation Project | Vegetation | Vegetation-DL | 161271.17 | 1772249.71 | 1356.14 | 14884.95 | 0 | 0 | 0 | 1949761.97 | 162627.31 | 1787134.66 | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800.
Pending FAASt | 38kV Transmission Line 1200 – Entire Line (Vegetation) | Incremental Vegetation Project | Vegetation | Vegetation-DL | 275711.27 | 3029860.81 | 2318.47 | 25447.51 | 0 | 0 | 0 | 3333338.06 | 278029.73 | 3055308.32 | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800.
Pending FAASt | 38kV Transmission Line 1600 – Entire Line (Vegetation) | Incremental Vegetation Project | Vegetation | Vegetation-DL | 305424.77 | 3356390.15 | 2568.32 | 28190 | 0 | 0 | 0 | 3692573.24 | 307993.09 | 3384580.15 | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800.
Pending FAASt | 38kV Transmission Line 2000 – Entire Line (Vegetation) | Incremental Vegetation Project | Vegetation | Vegetation-DL | 303594.6 | 3336277.81 | 2552.93 | 28021.09 | 0 | 0 | 0 | 3670446.43 | 306147.53 | 3364298.89 | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800.
Pending FAASt | 38kV Transmission Line 2100 – Entire Line (Vegetation) | Incremental Vegetation Project | Vegetation | Vegetation-DL | 304778.83 | 3349291.67 | 2562.89 | 28130.39 | 0 | 0 | 0 | 3684763.78 | 307341.72 | 3377422.06 | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800.
Pending FAASt | 38kV Transmission Line 2200 – Entire Line (Vegetation) | Incremental Vegetation Project | Vegetation | Vegetation-DL | 805386.91 | 8850600.91 | 6772.52 | 74335.38 | 0 | 0 | 0 | 9737095.71 | 812159.42 | 8924936.29 | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800.
Pending FAASt | 38kV Transmission Line 2500 – Entire Line (Vegetation) | Incremental Vegetation Project | Vegetation | Vegetation-DL | 243413.96 | 2674937.64 | 2046.88 | 22466.54 | 0 | 0 | 0 | 2942865.02 | 245460.84 | 2697404.18 | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800.
Pending FAASt | 38kV Transmission Line 2700 – Entire Line (Vegetation) | Incremental Vegetation Project | Vegetation | Vegetation-DL | 409745.04 | 4502791.99 | 3445.55 | 37818.53 | 0 | 0 | 0 | 4953801.11 | 413190.59 | 4540610.52 | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800.
Pending FAASt | 38kV Transmission Line 3000 – Entire Line (Vegetation) | Incremental Vegetation Project | Vegetation | Vegetation-DL | 491241.88 | 5398381.47 | 4130.86 | 45340.51 | 0 | 0 | 0 | 5939094.72 | 495372.74 | 5443721.98 | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800.
Pending FAASt | 38kV Transmission Line 3100 – Entire Line (Vegetation) | Incremental Vegetation Project | Vegetation | Vegetation-DL | 650144.58 | 7144603.49 | 5467.08 | 60006.86 | 0 | 0 | 0 | 7860222.01 | 655611.66 | 7204610.35 | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800.
Pending FAASt | 38kV Transmission Line 3700 – Entire Line (Vegetation) | Incremental Vegetation Project | Vegetation | Vegetation-DL | 470248.63 | 5167681.42 | 3954.33 | 43402.88 | 0 | 0 | 0 | 5685287.26 | 474202.96 | 5211084.29 | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800.
Pending FAASt | 38kV Transmission Line 3800 – Entire Line (Vegetation) | Incremental Vegetation Project | Vegetation | Vegetation-DL | 253749.1 | 2788513.05 | 2133.79 | 23420.45 | 0 | 0 | 0 | 3067816.39 | 255882.89 | 2811933.5 | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800.
Pending FAASt | 38kV Transmission Line 4000 – Entire Line (Vegetation) | Incremental Vegetation Project | Vegetation | Vegetation-DL | 113148.21 | 1243414.15 | 951.47 | 10443.31 | 0 | 0 | 0 | 1367957.14 | 114099.68 | 1253857.45 | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800.
Pending FAASt | 38kV Transmission Line 4800 – Entire Line (Vegetation) | Incremental Vegetation Project | Vegetation | Vegetation-DL | 428262.16 | 4706281.27 | 3601.27 | 39527.62 | 0 | 0 | 0 | 5177672.32 | 431863.43 | 4745808.88 | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800.
Pending FAASt | 38kV Transmission Line 5300 – Entire Line (Vegetation) | Incremental Vegetation Project | Vegetation | Vegetation-DL | 166008.11 | 1824305.09 | 1395.97 | 15322.16 | 0 | 0 | 0 | 2007031.34 | 167404.09 | 1839627.25 | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800.
Pending FAASt | 38kV Transmission Line 5400 – Entire Line (Vegetation) | Incremental Vegetation Project | Vegetation | Vegetation-DL | 288199.55 | 3167097.76 | 2423.48 | 26600.15 | 0 | 0 | 0 | 3484320.95 | 290623.03 | 3193697.92 | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800.
Pending FAASt | 38kV Transmission Line 5600 – Entire Line (Vegetation) | Incremental Vegetation Project | Vegetation | Vegetation-DL | 293582.43 | 3226251.64 | 2468.74 | 27096.98 | 0 | 0 | 0 | 3549399.79 | 296051.17 | 3253348.62 | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800.
Pending FAASt | 38kV Transmission Line 6500 – Entire Line (Vegetation) | Incremental Vegetation Project | Vegetation | Vegetation-DL | 447640.54 | 4919235.19 | 3764.22 | 41316.2 | 0 | 0 | 0 | 5411956.14 | 451404.76 | 4960551.38 | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800.
TBD | Poles Purchased - Included in the E&M without child | N/A | N/A | Pole and Conductors | 0 | 0 | 0 | 0 | 54755600 | 0 | 0 | 54755600 | 54755600 | 0 | This line item is for poles purchased under the global Equipment and Material PW that do not currently have a child project based on current allocations.
TBD | DA Equipment Purchased - Included in the E&M PW Without Child | N/A | N/A | Automation | 0 | 0 | 0 | 0 | 13386586.9667 | 26773173.9333 | 0 | 40159760.9 | 13386586.9667 | 26773173.9333 | This line item is for Reclosers, Bypass Switches (DA Equipment) purchased under the global Equipment and Material PW that do not currently have a child project based on current allocations. Also includes CFCIs ($12M) that are contracted.
[5 empty] | 500127199.41 | 301262959.26 | 45800250.62 | 15217565.11 | 162120280.4567 | 79304184.2533 | 54270.33 | 1103886709.41 | 708102000.8267 | 395784708.5333
LUMA Attachment C

## LUMA Exhibit 2_TEST (hidden)
[6 empty] | Section A: Obligation - Per Grants Portal (If project is not obligated leave in blank) | [8 empty] | Section B: For Obligated Projects include Delta and for Projects not Obligated include full Estimate | [8 empty] | Total (Section A + Section B) Update this section | [8 empty] | Confirmation and Comments | [5 empty] | Information for Reference | [8 empty] | Information Submitted to PREB
Project # | Title | Asset | Sub Asset | Obligated (Yes / No) | Process Step | 428 Allocation (Without the A&E and E&M) | 406 Allocation (Without the A&E and E&M) | 428 A&E-PW 9510 | 406 A&E-PW 9510 | 428 E&M-PW 10710 | 406 E&M-PW 10710 | FORMULA Expected Total Project Cost | FORMULA Total 428 Expected cost | FORMULA Total 406 Expected Cost | 428 Allocation (Without the A&E and E&M) | 406 Allocation (Without the A&E and E&M) | 428 A&E-PW 9510 | 406 A&E-PW 9510 | 428 E&M-PW 10710 | 406 E&M-PW 10710 | FORMULA Expected Total Project Cost | FORMULA Total 428 Expected cost | FORMULA Total 406 Expected Cost | 428 Allocation (Without the A&E and E&M) | 406 Allocation (Without the A&E and E&M) | 428 A&E-PW 9510 | 406 A&E-PW 9510 | 428 E&M-PW 10710 | 406 E&M-PW 10710 | FORMULA Expected Total Project Cost | FORMULA Total 428 Expected cost | FORMULA Total 406 Expected Cost | Estimate/Cost change (Y/N) | Who confirmed the information? | Obligation Amendment Status | New Comment | Comentario revisor | Revisor | Current Versioning Status in Grants Protal | Date of Obligation | Current Status in Grants Protal | Construction % of Completion as of 2/28/2026 | A&E Spend as of 2/28/2026 | Construction Spend as of 2/28/2026 | E&M Spend as of 2/28/2026 | Total Spend as of 2/28/2026 | Compare (Information Submitted to PREB vs Luma) | 428 Allocation (Without the A&E and E&M) | 406 Allocation (Without the A&E and E&M) | 428 A&E-PW 9510 | 406 A&E-PW 9510 | 428 E&M-PW 10710 | 406 E&M-PW 10710 | Expected Total Project Cost | Total 428 Expected cost | Total 406 Expected Cost | Project Reconciliation Status | Expected Reconciliation date | Comments | Variance Flag | 10 Reactivate Flag
682328 | FAASt [Bayamón TC - Rebuild] (Substation) | Substation | Substation | No | Pending Scope & Cost Completion by Applicant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87274829.6388 | 13294600.018 | 8875105.814 | 3024407.7676 | 21340863.5442 | 19963184.0398 | 153772990.8224 | 117490798.997 | 36282191.8254 | 87274829.6388 | 13294600.018 | 8875105.814 | 3024407.7676 | 21340863.5442 | 19963184.0398 | 153772990.8224 | 117490798.997 | 36282191.8254 | Y | Carlos Baez | Project in V0 - No amendment required at this time | LUMA finalizing scope, amendment to be submitted Q2 FY27 Ammendment driven by more developed scope and cost inflation Cost change is driven by more define scope and inflation | Project costs need to be reviewed as per work completed cost of 2M+ and rebuild cost sent to COR3 (8.6M + Components to be added) on 1/16/26 - Incurred cost including E&M identified surpass the $33M ++++++++++++ Is the cost of the temp transformer included? Should be 50 EM (3 transformers) + costs of breakers | Gabriel Torres | Pending Scope & Cost Completion by Applicant |  | Pending Scope & Cost Completion by Applicant | N/A | 3224629.84 | 14871908.58 |  | 18096538.42 | 150867694.7424 | 1770998.9781 | 269776.7861 | 180095.4914 | 61371.9109 | 217955.8349 | 405097.0787 | 2905296.08 | 2169050.3043 | 736245.7757 | Amendment – Submitted to COR3/PREPA | Submitted |  | 1 | #VALUE!
165225 | FAASt - EPC - Vieques 2501 substation repairs & New Vieques 2502 substation (Substation) | Substation | Vieques and Culebra Projects (6) | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 2115845.46 | 61747355.43 | 196682.43 | 74220.68 | 209878.53 | 481486.47 | 64825469 | 2522406.42 | 62303062.58 | Y | Carlos Baez | Amendment - Pending Development | This substation will be part of the micro grid scope Cost change is driven by more define scope and inflation | No Cost changes from the Submitted to the PREB. Significant increase from obligated. Incurred cost is 51% of the total cost with only 2% of construction. A&E incurred cost surpass the total estimated. (406 Duplicity identified) | Gabriel Torres | Pending Scope & Cost Completion by Applicant | 2022-06-10 11:48 | Obligated, Pending Scope & Cost Completion by Applicant | 2% | 2333876.59 | 144321.37 |  | 2478197.96 | 59922698.24 | 1479929.82 | 1291181.43 | 731583.82 | 878415.74 | 16046.1 | 505613.85 | 4902770.76 | 2227559.74 | 2675211.02 | Amendment – Submitted to COR3/PREPA | Submitted | Only existing substation is obligated | #REF! | #VALUE!
165209 | FAASt - EPC - Culebra Substation 3801 and New Culebra Substation 3802 (Substation) | Substation | Vieques and Culebra Projects (6) | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1133466.58 | 58777240.65 | 148303.89 | 84426.9677 | 118838.82 | 298749.59 | 60561026.4977 | 1400609.29 | 59160417.2077 | Y | Carlos Baez | Amendment - Pending Development | This substation will be part of the micro grid scope Cost change is driven by more define scope and inflation | No Cost changes from the Submitted to the PREB. Significant increase from obligated. Incurred cost is61% of the total cost with 44% of construction completed. A&E incurred cost surpass the total estimated. (406 Duplicity identified) | Gabriel Torres | Pending Scope & Cost Completion by Applicant | 2022-06-10 11:48 | Obligated, Pending Scope & Cost Completion by Applicant | 44% | 1886396.25 | 926055.39 |  | 2812451.64 | 55965278.9377 | 1538953.94 | 1267232.34 | 603858.08 | 681493.25 | 16046.1 | 488163.85 | 4595747.56 | 2158858.12 | 2436889.44 | Amendment – Submitted to COR3/PREPA | Submitted | Only existing substation is obligated | #REF! | #VALUE!
169276 | FAASt Substation - Viaducto TC - MC 1100 - Equipment Repair & Replacement (Substation) | Substation | Substation Rebuilds | No | Pending Scope & Cost Completion by Applicant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55931024.5724 | 25736012.7031 | 4317911.5193 | 1570417.2477 | 38843873.86 | 2801096.1 | 129200336.0024 | 99092809.9517 | 30107526.0508 | 55931024.5724 | 25736012.7031 | 4317911.5193 | 1570417.2477 | 38843873.86 | 2801096.1 | 129200336.0024 | 99092809.9517 | 30107526.0508 | N | Carlos Baez | Project in V0 - No amendment required at this time | LUMA working on project scope, revised scope to be submitted Q3 FY27 Cost change is driven by more define scope and inflation | No Cost changes from the Submitted to the PREB. Construction cost incurred with no N/A construction %. Cost incurred does not exceeds the final estimation. (406 Duplication identified) New cost estimate reflects a total cost of $83 M (4M over the provided cost) | Chantee Santana | Pending Scope & Cost Completion by Applicant |  | Pending Scope & Cost Completion by Applicant | N/A | 3665916.7 | 655629.74 |  | 4321546.44 | 48033700.5024 | 44329891.87 | 20397885.95 | 3422296.52 | 1244683.56 | 11765689.6 | 6188 | 81166635.5 | 59517877.99 | 21648757.51 | DSOW – Pending Design Package for Development | FY2027 |  | 1 | #VALUE!
178577 | FAASt [Cachete – MC 1526] (Substations) | Substation | Substation | No | Pending Scope & Cost Completion by Applicant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28780859.5334 | 8197490.385 | 3180011.1696 | 1083666.0036 | 39248524.9358 | 7152945.5114 | 87643497.5388 | 71209395.6388 | 16434101.9 | 28780859.5334 | 8197490.385 | 3180011.1696 | 1083666.0036 | 39248524.9358 | 7152945.5114 | 87643497.5388 | 71209395.6388 | 16434101.9 | Y | Carlos Baez | Project in V0 - No amendment required at this time | LUMA working on scope, revised scope to be submitted Q2 FY27 | No Cost changes from the Submitted to the PREB. Cost incurred does not exceeds the final estimation. | Chantee Santana | Pending Scope & Cost Completion by Applicant |  | Pending Scope & Cost Completion by Applicant | N/A | 2275152.98 | 4322.89 |  | 2279475.87 | 44169037.5388 | 23590868.47 | 6947025.75 | 2694924.72 | 918361.02 | 3261461.81 | 6061818.23 | 43474460 | 29547255 | 13927205 | DSOW – Scope and Cost development in progress | Q2 FY2027 | Currently under Scope revision by Planning | 1 | #VALUE!
169500 | FAASt [Bayamon TC - MC-BKRS-Y1] (Substation) | Substation | Substation Rebuilds | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 7511561.2795 | 1144238.3003 | 763861.7166 | 260304.4243 | 1258128.95 | 36445918.63 | 47384013.3006 | 9533551.9461 | 37850461.3545 | Y | Carlos Baez | Amendment - Pending Development | Luma finalizing scope, amendment to be submitted Q1 FY27 Cost change is driven by more define scope and inflation | Cost will change due to deobligation of componets -Components will be now included in Bayamon Rebuild (682328). Cost need to be deducted from this project and included in the other. (No 406 Duplicity Identified) | Gabriel Torres | Obligated | 2023-06-16 12:55 | Obligated | 44% | 1795011.09 | 6090723.65 |  | 7885734.74 | 36181650.9306 | 6828692.0723 | 1040216.6366 | 694419.7424 | 236640.3857 | 840403.2415 | 1561990.2915 | 11202362.37 | 8363515.0562 | 2838847.3138 | Amendment – Amendment Needed/Pending Development | Q4 FY2026 | estimate under review | #REF! | #VALUE!
723077 | FAASt - EPC - [Sabana Llana TC] (Substation) | Substation | Substation Rebuilds | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 75932414.213 | 8971281.759 | 7744020.4116 | 1085098.707 | 39651716.253 | 10017910.1187 | 143402441.4624 | 123328150.8777 | 20074290.5847 | Y | Carlos Baez | Amendment - Pending Development | LUMA finalizing scope, amendment to be submitted Q1 FY27 Cost change is driven by more define scope and inflation | total cost provided does not aling with amendment in progress. The amendment has a reduction of $10M. Please confirm. (406 duplicity identified) | Gabriel Torres | Obligated | 2023-12-19 12:23 | Obligated | 18% | 4845973.38 | 4170194.21 |  | 9016167.59 | 33778944.8224 | 63916173.58 | 8155710.69 | 5214828.56 | 730706.2 | 24860010.19 | 6746067.42 | 109623496.64 | 93991012.33 | 15632484.31 | Amendment – Pending Design Package for Development | Q4 FY2026 |  | #REF! | #VALUE!
723078 | FAASt - EPC - [San Juan SP TC] (Substation) | Substation | Substation Rebuilds | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 47732082.057 | 7712225.873 | 6479737.176 | 1137410.296 | 54699508.996 | 10188178.968 | 127949143.366 | 108911328.229 | 19037815.137 | Y | Carlos Baez | Amendment - Pending Development | LUMA working on project scope with Genera, amendment to be submitted Q2 FY27 Cost change is driven by more define scope and inflation | Amendment in process with a total cost of $109M. The new cost provided reflects a lower cost ( 406 duplicity identified) | Gabriel Torres | Obligated | 2023-12-19 12:23 | Obligated | 2% | 2728423.27 | 95853.36 |  | 2824276.63 | 31041834.476 | 41692705.96 | 18968379.24 | 4167397.2 | 2030397.52 | 19295213.53 | 10753215.44 | 96907308.89 | 65155316.69 | 31751992.2 | Amendment – Scope and Cost development in progress | Q4 FY2026 |  | #REF! | #VALUE!
743399 | FAASt [High Voltage Equipment Replacement - Group 3] (Substation) | Substation | Substation | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 21038292.91 | 0 | 4509930.04 | 0 | 3457839.23 | 0 | 29006062.18 | 29006062.18 | 0 | Y | Carlos Baez | Amendment - Pending Development | LUMA finalizing scope, amendment to be submitted Q2 FY27 | What is included in E&M? Should be 0 | Luis Sepulveda/ Chantee | Obligated | 2024-08-26 10:08 | Obligated | 10% | 1215959.95 | 1477534.97 |  | 2693494.92 | 23428430.91 | 3917912.12 | 0 | 463572.76 | 0 | 1196146.39 | 0 | 5577631.27 | 5577631.27 | 0 | Amendment – Submitted to COR3/PREPA | Submitted | Scope does not include hazard mitigation. No reconciliation needed. Project is in execution; Amendment due to scope/cost changes submitted. | #REF! | #VALUE!
551914 | FAASt [Caparra 1912 & 1924] (Substation) | Substation | Substation | No | Pending Scope & Cost Completion by Applicant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7611654.41 | 6435512.38 | 708217.1 | 448433.37 | 5350921.67 | 6374855.95 | 26929594.88 | 13670793.18 | 13258801.7 | 7611654.41 | 6435512.38 | 708217.1 | 448433.37 | 5350921.67 | 6374855.95 | 26929594.88 | 13670793.18 | 13258801.7 | Y | Carlos Baez | Project in V0 - No amendment required at this time | Submitted | E&M should be 6 for the GIS (Review GIS costs (actual). + transformert | Gabriel Torres | Pending Scope & Cost Completion by Applicant |  | Pending Scope & Cost Completion by Applicant | N/A | 1713915.25 | 2912.75 |  | 1716828 | 18016849.45 | 5432996.3672 | 827609.9065 | 552489.3929 | 188274.1735 | 668635.7665 | 1242739.8233 | 8912745.43 | 6654121.5267 | 2258623.9033 | DSOW – Submitted to COR3/PREPA | Q1 FY2027 | We resubmit DSOW on January 2026. | 1 | #VALUE!
169266 | FAASt Centro Medico 1327/1359 (Substattion) Rebuilt | Substation | Substation Rebuilds | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 16976611.278 | 6063148.102 | 4484183.594 | 1270820.683 | 11542228.878 | 2457771.126 | 42794763.661 | 33003023.75 | 9791739.911 | Y | Carlos Baez | Amendment - Pending Development | Luma finalizing scope, amendment to be submitted Q1 FY27 Cost change is driven by more define scope and inflation | How was calculated the E&M . Only E&M should be the GIS $12-$14 | Gabriel Torres | Obligated | 2023-11-03 11:30 | Obligated | 5% | 4401854.33 | 1079731.32 |  | 5481585.65 | 13652253.861 | 12202124 | 7130202 | 3317753 | 1306032 | 2593199.4 | 2593199.4 | 29142509.8 | 18113076.4 | 11029433.4 | Amendment – Amendment Needed/Pending Development | Q4 FY2026 |  | #REF! | #VALUE!
684920 | FAASt Substation High Voltage Replacement_Group 1 (Substation) | Substation | Substation Rebuilds | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 12563778.153 | 189367.6032 | 5504338.38 | 0 | 0 | 0 | 18257484.1362 | 18068116.533 | 189367.6032 | Y | Carlos Baez | Amendment - Pending Development | LUMA finalizing scope, amendment to be submitted Q2 FY27 Cost change is driven by more define scope and inflation | What is included in E&M? Should be 0 | Luis Sepulveda | Obligated | 2023-12-29 12:31 | Obligated | 82% | 5632387.78 | 7711675.88 |  | 13344063.66 | 12741014.5562 | 3874950.13 | 0 | 458489.44 | 0 | 1183030.01 | 0 | 5516469.58 | 5516469.58 | 0 | Obligated -No expected changes | N/A | No Amendment Needed | #REF! | #VALUE!
729286 | FAASt HV Equipment Replacement Group 2 (Substation) | Substation | Substation | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 17860595.12 | 0 | 5206874.3 | 0 | 0 | 0 | 23067469.42 | 23067469.42 | 0 | Y | Carlos Baez | Amendment - Pending Development | LUMA finalizing scope, amendment to be submitted Q2 FY27 Cost change is driven by more define scope and inflation | What is included in E&M? Should be 0 . The actuals are higher than original obligation. | Orlando Rodriguez | Obligated | 2024-07-08 11:28 | Obligated | 52% | 1743415.11 | 9109977.67 |  | 10853392.78 | 12645609.04 | 7320658.38 | 0 | 866190.39 | 0 | 2235011.61 | 0 | 10421860.38 | 10421860.38 | 0 | Amendment – Submitted to COR3/PREPA | Submitted | Scope does not include hazard mitigation. No reconciliation needed. Project is in execution; Amendment due to scope/cost changes submitted. | #REF! | #VALUE!
682121 | FAASt - EPC -Aguirre TC-Phase II (Substation) | Substation | Substation Rebuilds | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 83657110.0997 | 3775560.6762 | 8101618.921 | 359601.847 | 36352089.0673 | 1554241.9338 | 133800222.545 | 128110818.088 | 5689404.457 | Y | Carlos Baez | Amendment - Pending Development | LUMA working on scope, amendment to be submitted Q2 FY27 | No Cost changes from the Submitted to the PREB. Cost incurred does not exceeds the final estimation. No mayor flags identified in cost. (No 496 duplication identified) | Gabriel Torres | Obligated | 2024-03-22 10:16 | Obligated | 4% | 4856917.02 | 5613354.26 |  | 10470271.28 | 12163656.595 | 76051918.2725 | 3432327.8875 | 7365108.11 | 326910.77 | 33047353.6975 | 1412947.2125 | 121636565.95 | 116464380.08 | 5172185.87 | Amendment – Scope and Cost development in progress | Q4 FY2026 | scope to be revised | #REF! | #VALUE!
174422 | FAASt - Catano-Rebuild 1801(Substation) | Substation | Substation | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 20620556.5073 | 3141135.3313 | 2096934.7257 | 714581.4152 | 4515587.433 | 8392761.2153 | 39481556.6278 | 27233078.666 | 12248477.9618 | Y | Carlos Baez | Amendment - Pending Development | Scope of amendment finalized, LUMA to submit Q4 FY26. Cost change is driven by more define scope and inflation | E&M should only include the GIS 6.7M | Gabriel Torres | Obligated | 2022-05-18 11:30 | Obligated | 66% | 5510502.25 | 11157823.46 |  | 16668325.71 | 9976933.6178 | 16677900.7662 | 2540549.443 | 3127217.3734 | 1291524.2237 | 2052539.7423 | 3814891.4615 | 29504623.01 | 21857657.8819 | 7646965.1281 | Amendment – Amendment Needed/Pending Development | Q4 FY2026 | Pending IFC package to include all the changes in scope as part of the DSOW ammendment. | #REF! | #VALUE!
682645 | FAASt [Maunabo TC] (Substation) | Substation | Substation Rebuilds | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 64448906.8891 | 9817520.6097 | 6553904.1509 | 2233401.949 | 7931690.2403 | 14741998.2911 | 105727422.13 | 78934501.2803 | 26792920.8497 | Y | Carlos Baez | Amendment - Pending Development | LUMA working on scope, amendment to be submitted Q2 FY27 Cost change is driven by more define scope and inflation | No Cost changes from the Submitted to the PREB. Cost incurred does not exceeds the final estimation. No mayor flags identified in cost. | Chantee Santana | Obligated | 2025-09-17 18:16 | Obligated | 30% | 3152477.52 | 2167332.87 |  | 5319810.39 | 9611583.83 | 58589915.3537 | 8925018.7361 | 5958094.6826 | 2030365.4081 | 7210627.4912 | 13401816.6283 | 96115838.3 | 71758637.5275 | 24357200.7725 | Amendment – Pending Design Package for Development | FY2027 | The Amount Obligated by FEMA was $8.2M | #REF! | #VALUE!
723002 | FAASt - EPC - Jobos TC (Substation) | Substation | Substation | No | Pending Scope & Cost Completion by Applicant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51025274.884 | 7772694.8675 | 5188835.2651 | 1768221.5863 | 6279651.4998 | 11671486.0104 | 83706164.113 | 62493761.6489 | 21212402.4641 | 51025274.884 | 7772694.8675 | 5188835.2651 | 1768221.5863 | 6279651.4998 | 11671486.0104 | 83706164.113 | 62493761.6489 | 21212402.4641 | Y | Carlos Baez | Project in V0 - No amendment required at this time | LUMA working on scope, revised scope to be submitted Q3 FY27 Cost change is driven by more define scope and inflation | No Cost changes from the Submitted to the PREB. Cost incurred does not exceeds the final estimation. Construction cost incurred with no N/A construction % . Mayor reduction expected due to change in scope from relocation to rebuild | Chantee Santana | Pending Scope & Cost Completion by Applicant |  | Pending Scope & Cost Completion by Applicant | N/A | 1942607.63 | 15989.76 |  | 1958597.39 | 7609651.283 | 46386613.5309 | 7066086.2431 | 4717122.9683 | 1607474.1693 | 5708774.0907 | 10610441.8276 | 76096512.83 | 56812510.5899 | 19284002.2401 | DSOW – Pending Design Package for Development | FY2027 | Planning and Engineering is working on the scope for the project. | 1 | #VALUE!
550106 | FAASt [Conquistador CH] (Substation) | Substation | Substation Rebuilds | No | Pending Scope & Cost Completion by Applicant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8360260.4039 | 1994931.4709 | 823453.8066 | 341756.0115 | 4324989.8973 | 4563696.6127 | 20409088.2028 | 13508704.1077 | 6900384.0951 | 8360260.4039 | 1994931.4709 | 823453.8066 | 341756.0115 | 4324989.8973 | 4563696.6127 | 20409088.2028 | 13508704.1077 | 6900384.0951 | N | Carlos Baez | Project in V0 - No amendment required at this time | Submitted | This project has WC,and WTBC the total cost provided is under the current amendment total Also the A&E estimated allocation is$2M lower than the incurred cost. (406 Cost duplication identified) | Gabriel Torres | Pending Scope & Cost Completion by Applicant |  | Pending Scope & Cost Completion by Applicant | N/A | 2933756.62 | 772607.09 |  | 3706363.71 | 7489488.7028 | 6785925.6525 | 1619262.5575 | 668387.83 | 277399.36 | 1675808.9975 | 1892815.1025 | 12919599.5 | 9130122.48 | 3789477.02 | DSOW – Scope and Cost development in progress | Q4 FY2026 | Pending recieve assesment to iclude repairs to the fiber between Monacillos and El Conquistador | 1 | #VALUE!
542758 | FAASt Substation Minor Repairs -Group B (Substation) | Substation | Substation Rebuilds | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 8776075.803 | 1217442.578 | 451066.682 | 80034.625 | 0 | 0 | 10524619.688 | 9227142.485 | 1297477.203 | Y | Carlos Baez | Amendment – Submitted to COR3/PREPA | Submitted | Rhys envió las correcciones el 2 de abril de 2026 | Sandra Valentin | Obligated | 2023-07-07 11:35 | Obligated | 76% | 1096744.1 | 5242365.72 |  | 6339109.82 | 6388728.688 | 2973035 | 302946 | 723315 | 136595 | 0 | 0 | 4135891 | 3696350 | 439541 | Amendment – Submitted to COR3/PREPA | Submitted | E&M allocations not included in original obligation | #REF! | #VALUE!
178258 | FAASt - [Taft - MC 1105] (Substations) | Substation | Substation | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 11140186.6419 | 1696987.8503 | 1132861.9677 | 386050.2181 | 2678011.84 | 3321988.16 | 20356086.6779 | 14951060.4496 | 5405026.2283 | Y | Carlos Baez | Amendment - Pending Development | Luma finalizing scope, amendment to be submitted Q2 FY27 Cost change is driven by more define scope and inflation | How was calculated the E&M . Only E&M should be the GIS $6 | Gabriel Torres | Obligated | 2025-02-06 20:16 | Obligated | 0% | 1737998.31 | 10073.34 |  | 1748071.65 | 5567132.9579 | 9014992.3462 | 1373256.3891 | 916747.8334 | 312404.0802 | 1109469.9702 | 2062083.1008 | 14788953.72 | 11041210.1499 | 3747743.5701 | DSOW – Scope and Cost development in progress | Q1 FY2027 |  | #REF! | #VALUE!
165268 | FAASt Rio Grande Estate Substation CH-2306 (Su | Substation | Substation Rebuilds | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 22290107.58 | 8550353.26 | 1837831.336 | 1216566.725 | 510106.56 | 15489893.44 | 49894858.901 | 24638045.476 | 25256813.425 | Y | Carlos Baez | Amendment – Submitted to COR3/PREPA | Submitted | How was calculated the E&M . Should be 14-16 | Gabriel Torres | Obligated | 2022-12-21 12:37 | Obligated | 93% | 4311264.88 | 7006384.18 |  | 11317649.06 | 4535896.261 | 10575737.82 | 5646415.07 | 1670755.76 | 1105969.75 | 15043028.3 | 11317055.94 | 45358962.64 | 27289521.88 | 18069440.76 | Amendment – Submitted to COR3/PREPA | Q4 FY2026 | Submit to COR3 on 02/27/2026 | #REF! | #VALUE!
169058 | FAASt - Llorens Torres MC 1106 - Equipment Repair & Replacement - (Substations) | Substation | Substation Rebuilds | No | Pending Scope & Cost Completion by Applicant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20962734.639 | 10164051.2316 | 1335184.07 | 721159.747 | 4713846.148 | 3706655.7 | 41603631.5356 | 27011764.857 | 14591866.6786 | 20962734.639 | 10164051.2316 | 1335184.07 | 721159.747 | 4713846.148 | 3706655.7 | 41603631.5356 | 27011764.857 | 14591866.6786 | N | Carlos Baez | Project in V0 - No amendment required at this time | LUMA working on scope, revised scope to be submitted Q3 FY27 | No Cost changes from the Submitted to the PREB. Cost incurred does not exceeds the final estimation. Construction cost incurred with no N/A construction % No mayor flags identified in cost. | Chantee Santana | Pending Scope & Cost Completion by Applicant |  | Pending Scope & Cost Completion by Applicant | N/A | 2099708.01 | 13367.36 |  | 2113075.37 | 3782148.3214 | 19057031.49 | 9240046.5742 | 1213803.7 | 655599.77 | 4285314.68 | 3369687 | 37821483.2142 | 24556149.87 | 13265333.3442 | Amendment – Amendment Needed/Pending Development | Q4 FY2026 |  | 1 | #VALUE!
169896 | FAASt - Costa Sur SP TC  Equipment Repair and | Substation | Substation Rebuilds | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 31075136.224 | 548761.477 | 3742364.835 | 58919.883 | 0 | 0 | 35425182.419 | 34817501.059 | 607681.36 | Y | Carlos Baez | Amendment - Pending Development | Submitted | No Cost changes from the Submitted to the PREB. Cost incurred does not exceeds the final estimation. Incurred cost is <50% with 43% of construction completed. Amendment in COR3 review with minor cost difference of final cost provided . No mayor flags identified in cost. | Gabriel Torres | Obligated | 2022-08-02 11:42 | Obligated | 43% | 3453256.41 | 11157319.2 |  | 14610575.61 | 3220471.129 | 28250123.84 | 498874.07 | 3402149.85 | 53563.53 | 0 | 0 | 32204711.29 | 31652273.69 | 552437.6 | Amendment – Submitted to COR3/PREPA | Submitted |  | #REF! | #VALUE!
825843 | FAASt [Guanica TC] (Substation) | Priority Substation | Substation | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 2552411.356 | 0 | 909679.243 | 0 | 4620795.872 | 0 | 8082886.471 | 8082886.471 | 0 | Y | Carlos Baez | Amendment - Pending Development | Luma finalizing scope, amendment to be submitted Q2 FY27 Cost change is driven by more define scope and inflation | Cost will increase due to additional environmental studies - Gabriel Torres | Gabriel Torres | Obligated | 2025-09-22 16:15 | Obligated | 10% | 26409.69 | 123299.14 |  | 149708.83 | 734807.861 | 2320373.96 | 0 | 826981.13 | 0 | 4200723.52 | 0 | 7348078.61 | 7348078.61 | 0 | Amendment – Amendment Needed/Pending Development | Q4 FY2026 |  | #REF! | #VALUE!
746660 | FAASt [Minor Protection, Automation, and Control [PAC] Replacement] (Substation) | Substation | Substation | No | Pending Scope & Cost Completion by Applicant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12586601.6917 | 4270769.9909 | 1139689.148 | 388376.7455 | 0 | 0 | 18385437.576 | 13726290.8396 | 4659146.7364 | 12586601.6917 | 4270769.9909 | 1139689.148 | 388376.7455 | 0 | 0 | 18385437.576 | 13726290.8396 | 4659146.7364 | N | Carlos Baez | Project in V0 - No amendment required at this time | No changes expected Cost change is driven by more define scope and inflation | E&M should be 0 | Gabriel Torres | Pending Scope & Cost Completion by Applicant |  | Pending Scope & Cost Completion by Applicant | N/A | 2423098.68 | 30058.15 |  | 2453156.83 | 1671403.416 | 10188475.3228 | 1552013.39 | 1036081.0436 | 353069.7686 | 1253889.8514 | 2330504.7835 | 16714034.16 | 12478446.2178 | 4235587.9422 | DSOW – Submitted to COR3/PREPA | Submitted | Submitted to COR3 in Jan. 2026 | 1 | #VALUE!
662238 | FAASt [Microwave Point-to-Point Backbone] (Telecommunications) | Telecommunication | IT/OT | No | Pending CRC Review | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28826526.1978 | 5417440.08 | 2708469.2267 | 509009.2933 | 0 | 0 | 37461444.7978 | 31534995.4245 | 5926449.3733 | 28826526.1978 | 5417440.08 | 2708469.2267 | 509009.2933 | 0 | 0 | 37461444.7978 | 31534995.4245 | 5926449.3733 | Y | Axel Andino | Project in V0 - No amendment required at this time | Project under CRC review; Pending Obligation. | - Rhys envió las correcciones el 2 de abril de 2026 - Axel Rodriguez - Correct amount in Column AE = $37,461,444.79, and column AG = $5,926,449.37. | Sandra Valentin/Axel Rodriguez | Pending FEMA 406 HMP Completion |  | Pending FEMA 406 HMP Completion | N/A | 1334035.28 | 1657.07 |  | 1335692.35 | 0.0077553 | 28822774.33 | 5421191.94 | 2708151.69 | 509326.83 | 0 | 0 | 37461444.79 | 31530926.02 | 5930518.77 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Proyect under CRC review by Feb 16th. Pending Obligation to determine Amendment submission date. | 1 | #VALUE!
678800 | FAASt [Telecom Infrastructure – Group B] (Telecommunication) | Telecommunication | IT/OT | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 13148929.44 | 55895.837 | 2828793.1 | 10487.44 | 0 | 0 | 16044105.817 | 15977722.54 | 66383.277 | Y | Axel Andino | Obligated - No amendment need Identified | Design Package expected Jun 2026 but No change in cost expected. | - Rhys envió las correcciones el 2 de abril de 2026. - Axel Rodriguez - Correct amount in Column AE = $16,033,618.38, and column AG = $55,895.84. | Sandra Valentin/Axel Rodriguez | Obligated | 2025-11-05 16:17 | Obligated | 0% | 2069779.45 | 244332.31 |  | 2314111.76 | 10487.437 | 13148929.44 | 45408.4 | 2828793.1 | 10487.44 | 0 | 0 | 16033618.38 | 15977722.54 | 55895.84 | Amendment – Pending Design Package for Development | Q1 FY2027 | Design Package expected Jun 2026. | #REF! | #VALUE!
551963 | FAASt [Transport Network Group 1] (Telecommunication) | Telecommunication | IT/OT | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 4489030.64 | 3693295.57 | 671253.14 | 539034.63 | 0 | 0 | 9392613.98 | 5160283.78 | 4232330.2 | Y | Axel Andino | Amendment – Submitted to FEMA | Amendment submitted to include the 428/406 split. | -Rhys envió las correcciones el 2 de abril de 2026 - Axel Rodriguez - Correct amount in Column AE = $9,392,613.98, and column AG = $4,232,330.20. | Sandra Valentin/Axel Rodriguez | Pending Scope & Cost Completion by Applicant | 2025-09-17 18:16 | Obligated, Pending Scope & Cost Completion by Applicant | 1% | 12893716.78 | 161091.77 |  | 13054808.55 | 0 | 4489030.64 | 3693295.57 | 671253.14 | 539034.63 | 0 | 0 | 9392613.98 | 5160283.78 | 4232330.2 | Amendment – Submitted to FEMA | Submitted | Amedment submitted to FEMA on Jan 26,2026. Cost estimate revised and splited 428 55% & 406 45% Aprox. | #REF! | #VALUE!
686471 | FAASt [Pole and Conductor Repair - Arecibo Group 5] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 319916.81 | 57115.8 | 49227 | 14392 | 0 | 0 | 440651.61 | 369143.81 | 71507.8 | Y | Yaritza Acevedo Ortiz | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version. | No comment | Luis Sepulveda | Obligated | 2022-12-27 11:53 | Obligated | 97% | 71386.99 | 366264.62 |  | 437651.61 | 45036.61 | 250906 | 54308 | 49227 | 14392 | 0 | 0 | 395615 | 300133 | 68700 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
712968 | FAASt [Pole and Conductor Repair - Arecibo Group 2 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 6147251.54 | 145147 | 503550 | 35903.97 | 0 | 0 | 6831852.51 | 6650801.54 | 181050.97 | Y | Yaritza Acevedo Ortiz | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version. | Se espera que este proyecto tenga costos que sobrepasan la obligación por $520k. | Luis Sepulveda | Obligated | 2024-11-01 15:15 | Obligated | 84% | 623754.39 | 5707876.02 |  | 6331630.41 | 520528.54 | 5629060 | 1482809 | 503551 | 35903.97 | 0 | 0 | 6311323.97 | 6132611 | 1518712.97 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
682180 | FAASt [Pole and Conductor Repair - Mayagüez Group 10] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 120882.62 | 8412 | 8414 | 1308 | 0 | 0 | 139016.62 | 129296.62 | 9720 | Y | Yaritza Acevedo Ortiz | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version. | The project expenses cover 100% of the project's expected cost, and the project is at 51% of construction. | Luis Sepulveda | Obligated | 2023-01-10 13:19 | Obligated | 51% | 46554.55 | 92462.07 |  | 139016.62 | 76200.62 | 43374 | 8718 | 8414 | 2310 | 0 | 0 | 62816 | 51788 | 11028 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
682865 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 7] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 152533.26 | 16132 | 13377 | 2508 | 0 | 0 | 184550.26 | 165910.26 | 18640 | Y | Yaritza Acevedo Ortiz | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version. | No Comment | Luis Sepulveda | Obligated | 2022-12-27 11:53 | Obligated | 82% | 54416.25 | 96220.44 |  | 150636.69 | 79342.26 | 70683 | 16718 | 13377 | 4430 | 0 | 0 | 105208 | 84060 | 21148 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
685477 | FAASt [Pole and Conductor Repair - Arecibo Group 6] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 392742.1 | 47748.1 | 67123 | 6914 | 0 | 0 | 514527.2 | 459865.1 | 54662.1 | Y | Yaritza Acevedo Ortiz | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version. | No Comment | Luis Sepulveda | Obligated | 2023-01-24 13:14 | Obligated | 81% | 114176.28 | 335523.79 |  | 449700.07 | 50429.33 | 355178 | 46090 | 67123 | 12214 | 0 | 0 | 464097.87 | 422301 | 58304 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
679025 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 4] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 402804.8 | 42382 | 46884 | 6588 | 0 | 0 | 498658.8 | 449688.8 | 48970 | Y | Yaritza Acevedo Ortiz | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version. | No comment | Luis Sepulveda | Obligated | 2022-12-27 11:53 | Obligated | 80% | 72104.52 | 383640.71 |  | 455745.23 | 153143.8 | 243073 | 43919 | 46884 | 11639 | 0 | 0 | 345515 | 289957 | 55558 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
682172 | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 8] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 362192.7 | 43995.35 | 40930 | 6838 | 0 | 0 | 453956.05 | 403122.7 | 50833.35 | Y | Yaritza Acevedo Ortiz | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version. | No Comment | Luis Sepulveda | Obligated | 2023-01-24 13:14 | Obligated | 83% | 126286.86 | 321669.19 |  | 447956.05 | 96379.05 | 208400 | 45590 | 40930 | 12081.35 | 0 | 0 | 357577 | 249330 | 57671.35 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
682910 | FAASt [Distribution Pole and Conductor Repair - Bayamón Group 7] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 580036.28 | 82945 | 99229 | 12530 | 0 | 0 | 774740.28 | 679265.28 | 95475 | Y | Yaritza Acevedo Ortiz | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version. | No Comment | Luis Sepulveda | Obligated | 2023-01-31 12:56 | Obligated | 97% | 123441.5 | 642298.78 |  | 765740.28 | 59871.28 | 517156 | 83531 | 99229 | 22135.72 | 0 | 0 | 714869 | 616385 | 105666.72 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
673774 | FAASt [Distribution Pole and Conductor Repair - Mayaguez Group 1] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 3378138.08 | 283336 | 273831 | 75084 | 0 | 0 | 4010389.08 | 3651969.08 | 358420 | Y | Yaritza Acevedo Ortiz | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version. | Este Proyecto se espera que tenga costos que sobrepasan la obligación por $1.9 millón. | Luis Sepulveda | Obligated | 2022-08-02 11:42 | Obligated | 62% | 660694.74 | 2989558.68 |  | 3650253.42 | 1969607.08 | 1408531 | 283336 | 273831 | 75084 | 0 | 0 | 2040782 | 1682362 | 358420 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
745856 | FAASt [Automation Program Group 14] (TL/Distribution) | Grid Automation | Grid Automation | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1410445.2 | 555441.55 | 112272.97 | 65062.72 | 148295.58 | 442571.92 | 2734089.94 | 1671013.75 | 1063076.19 | Y | Angelica Rosario/Oscar Fuentes | Amendment – Submitted to FEMA | 406HM Revision currently Pending to be Award in GP / Estimated date Cfci strategy to be defined. In addition to the amendment version, a revised differential estimate of $61,669.20 for the communications wireless portion was added to the 406 section (without A&E and E&M).Estimate is an Class 3. | Verificar los costos totales presentados en 406, (Columna Z) ya que duplica los costos incluidos en la revisión del estimado preparado para la enmienda | Amaury Pacheco | Pending FEMA 406 HMP Completion | 2025-02-06 20:16 | Obligated, Pending FEMA 406 HMP Completion | 92% | 447795.88 | 1125897.42 |  | 1573693.3 | -445965.44 | 1410445.2 | 1001406.99 | 112272.97 | 65062.72 | 148295.58 | 442571.92 | 3180055.38 | 1671013.75 | 1509041.63 | Amendment – Submitted to FEMA | Submitted | 406HM Revision Pending Award in GP / Estimated date Cfci strategy to be defined | #REF! | #VALUE!
745859 | FAASt [Automation Program Group 18: DAR – SAN JUAN 2001- FY24] (Distribution) | Grid Automation | Grid Automation | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 223935.37 | 120620.22 | 21856.33 | 15504.92 | 33515.73 | 77702.27 | 493134.84 | 279307.43 | 213827.41 | Y | Angelica Rosario/Oscar Fuentes | Amendment – Submitted to FEMA | 406HM Revision Pending Award in GP / Estimated date Cfci strategy to be defined. In addition to the amendment version, a revised differential estimate of $15,417.30 for the communications wireless portion was added to the 406 section (without A&E and E&M).Estimate is an Class 3. | Verificar los costos totales presentados en 406, (Columna Z) ya que duplica los costos incluidos en la revisión del estimado preparado para la enmienda | Amaury Pacheco | Pending Award | 2024-09-18 15:15 | Obligated, Pending Award | 72% | 97307.06 | 257781.06 |  | 355088.12 | -77789.89 | 223935.37 | 198410.11 | 21856.33 | 15504.92 | 33515.73 | 77702.27 | 570924.73 | 279307.43 | 291617.3 | Amendment – Submitted to FEMA | Submitted | 406HM Revision Pending Award in GP / Estimated date Cfci strategy to be defined | #REF! | #VALUE!
745861 | FAASt [Automation Program Group 12] (TL/Distribution) | Grid Automation | Grid Automation | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 2168647.62 | 784104.06 | 196183.24 | 101775.43 | 228547.36 | 557560.64 | 4036818.35 | 2593378.22 | 1443440.13 | Y | Angelica Rosario/Oscar Fuentes | Amendment – Submitted to FEMA | 406HM Revision Pending Award in GP / Estimated date Cfci strategy to be defined.In addition to the amendment version, a revised differential estimate of $84,795.15 for the communications wireless portion was added to the 406 section (without A&E and E&M).Estimate is an Class 3. | Verificar los costos totales presentados en 406, (Columna Z) ya que duplica los costos incluidos en la revisión del estimado preparado para la enmienda | Amaury Pacheco | Pending PDMG Scope & Cost Routing | 2025-02-06 20:16 | Obligated, Pending PDMG Scope & Cost Routing | 76% | 528755.13 | 1584522.77 |  | 2113277.9 | -570328.39 | 2181157.9 | 1341922.17 | 200395.78 | 97562.89 | 228547.36 | 557560.64 | 4607146.74 | 2610101.04 | 1997045.7 | Amendment – Submitted to FEMA | Submitted | 406HM Revision Pending Award in GP / Estimated date Cfci strategy to be defined | #REF! | #VALUE!
746309 | FAASt [Automation Program Group 30] (Distribution) | Grid Automation | Grid Automation | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 327791.49 | 132752.89 | 53695.19 | 28394.95 | 65212.75 | 98251.25 | 706098.52 | 446699.43 | 259399.09 | Y | Angelica Rosario/Oscar Fuentes | DSOW – Submitted to FEMA | No Amendment Needed. In addition to the amendment version, a revised differential estimate of $23,125.95 for the communications wireless portion was added to the 406 section (without A&E and E&M).Estimate is an Class 3. | Verificar los costos totales presentados en 406, (Columna Z) ya que duplica los costos incluidos en la revisión del estimado preparado para la enmienda | Amaury Pacheco | Obligated | 2026-03-01 18:16 | Obligated | N/A | 45237.83 | 4.5475e-13 |  | 45237.83 | -103520.25 | 327791.49 | 236273.14 | 53695.19 | 28394.95 | 65212.75 | 98251.25 | 809618.77 | 446699.43 | 362919.34 | DSOW – Submitted to FEMA | N/A | No Amendment Needed | #REF! | #VALUE!
752808 | FAASt [Automation Program Group 19] (TL/Distribution) | Grid Automation | Grid Automation | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1352947.241 | 389336.94 | 119711.919 | 52375.13 | 134857.23 | 320428.9 | 2369657.36 | 1607516.39 | 762140.97 | Y | Angelica Rosario/Oscar Fuentes | Amendment – Submitted to FEMA | 406HM Revision Pending Award in GP / Estimated date Cfci strategy to be defined. In addition to the amendment version, a revised differential estimate of $38,543.25 for the communications wireless portion was added to the 406 section (without A&E and E&M).Estimate is an Class 3. | Verificar los costos totales presentados en 406, (Columna Z) ya que duplica los costos incluidos en la revisión del estimado preparado para la enmienda | Amaury Pacheco | Pending EHP Review | 2025-02-06 20:16 | Obligated, Pending EHP Review | 85% | 365793.35 | 1238377.93 |  | 1604171.28 | -334260.78 | 1352947.241 | 723597.72 | 119711.919 | 52375.13 | 134857.23 | 320428.9 | 2703918.14 | 1607516.39 | 1096401.75 | Amendment – Submitted to FEMA | Submitted | 406HM Revision on FEMA CRC / Estimated date Cfci strategy to be defined | #REF! | #VALUE!
752810 | FAASt [Automation Program Group 20] (TL/Distribution) | Grid Automation | Grid Automation | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1645985.22 | 492364.67 | 176266.8 | 72284.36 | 202809.71 | 358776.21 | 2948486.97 | 2025061.73 | 923425.24 | Y | Angelica Rosario/Oscar Fuentes | Amendment – Submitted to FEMA | 406HM Revision Pending Award in GP / Estimated date Cfci strategy to be defined. In addition to the amendment version, a revised differential estimate of $53,960.55 for the communications wireless portion was added to the 406 section (without A&E and E&M).Estimate is an Class 3. | Verificar los costos totales presentados en 406, (Columna Z) ya que duplica los costos incluidos en la revisión del estimado preparado para la enmienda | Amaury Pacheco | Pending PDMG Scope & Cost Routing | 2025-02-06 20:16 | Obligated, Pending PDMG Scope & Cost Routing | 77% | 433255.05 | 930843.98 |  | 1364099.03 | -355349.39 | 1645985.22 | 847714.06 | 176266.8 | 72284.36 | 202809.71 | 358776.21 | 3303836.36 | 2025061.73 | 1278774.63 | Amendment – Submitted to FEMA | Submitted | Open Soft RFI to revise soft Cost will be submitted 02/20 / Estimated date Cfci strategy to be defined | #REF! | #VALUE!
755211 | FAASt [Automation Program Group 15] (Distribution) | Grid Automation | Grid Automation | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 276277.7686 | 143276.18 | 29684.97 | 18557.49 | 53139.71 | 103164.29 | 624100.4086 | 359102.4486 | 264997.96 | Y | Angelica Rosario/Oscar Fuentes | Amendment – Submitted to FEMA | 406HM Revision Pending Award in GP / Estimated date Cfci strategy to be defined.In addition to the amendment version, a revised differential estimate of $15,417.30 for the communications wireless portion was added to the 406 section (without A&E and E&M). Estimate is an Class 3. | Verificar los costos totales presentados en 406, (Columna Z) ya que duplica los costos incluidos en la revisión del estimado preparado para la enmienda | Amaury Pacheco | Pending Award | 2025-02-06 20:16 | Obligated, Pending Award | 72% | 164033.11 | 334487.39 |  | 498520.5 | -106304.48 | 276277.7686 | 249580.66 | 29684.97 | 18557.49 | 53139.71 | 103164.29 | 730404.8886 | 359102.4486 | 371302.44 | Amendment – Submitted to FEMA | Submitted | 406HM Revision Pending Award in GP / Estimated date Cfci strategy to be defined | #REF! | #VALUE!
757662 | FAASt [Automation Program Group 21] (Distribution) | Grid Automation | Grid Automation | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1450834.51 | 409419.06 | 316327.09 | 133329.79 | 152199 | 326377 | 2788486.45 | 1919360.6 | 869125.85 | Y | Angelica Rosario/Oscar Fuentes | Amendment – Amendment Needed/Pending Development | 406HM Revision to be submitted May 2026 to GP / Estimated date Cfci strategy to be defined. In addition to the amendment version, a revised differential estimate of $46,251.90 for the communications wireless portion was added to the 406 section (without AEstimate is an Class 3. | Verificar los costos totales presentados en 406, (Columna Z) ya que duplica los costos incluidos en la revisión del estimado preparado para la enmienda | Amaury Pacheco | Obligated | 2025-10-30 20:15 | Obligated | 8% | 228520.47 | 17727.94 |  | 246248.41 | 284625.44 | 1284891.5683 | 425656.3717 | 205400.7597 | 75115.8303 | 162255.9386 | 350540.5414 | 2503861.01 | 1652548.2666 | 851312.7434 | Amendment – Amendment Needed/Pending Development | Q1 FY2027 | 406HM Revision to be submitted June 2026 / Estimated date Cfci strategy to be defined | #REF! | #VALUE!
757687 | FAASt [Automation Program Group 22] (Distribution) | Grid Automation | Grid Automation | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1746764.31 | 530280.7 | 364393.9 | 164099.27 | 176671.17 | 397630.03 | 3379839.38 | 2287829.38 | 1092010 | Y | Angelica Rosario/Oscar Fuentes | Amendment – Amendment Needed/Pending Development | 406HM Revision to be submitted May 2026 to GP / Estimated date Cfci strategy to be defined. In addition to the amendment version, a revised differential estimate of $61,669.20 for the communications wireless portion was added to the 406 section (without AEstimate is an Class 3. | Verificar los costos totales presentados en 406, (Columna Z) ya que duplica los costos incluidos en la revisión del estimado preparado para la enmienda | Amaury Pacheco | Obligated | 2025-10-30 20:15 | Obligated | 11% | 214384.9 | 598636.59 |  | 813021.49 | 152960.2 | 1488484.9 | 1318276.22 | 169367.15 | 153103.22 | 44894.57 | 52753.12 | 3226879.18 | 1702746.62 | 1524132.56 | Amendment – Amendment Needed/Pending Development | Q4 FY2026 | 406HM Revision to be submitted May 2026/ Estimated date Cfci strategy to be defined | #REF! | #VALUE!
757689 | FAASt [Automation Program Group 24] (Distribution) | Grid Automation | Grid Automation | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1594252.07 | 500159.95 | 141012.25 | 68290.29 | 169799.83 | 399788.17 | 2873302.56 | 1905064.15 | 968238.41 | Y | Angelica Rosario/Oscar Fuentes | Amendment – Submitted to FEMA | 406HM Revision Pending Award in GP / Estimated date Cfci strategy to be defined. In addition to the amendment version, a revised differential estimate of $53,960.55 for the communications wireless portion was added to the 406 section (without A&E and E&M).Estimate is an Class 3. | Verificar los costos totales presentados en 406, (Columna Z) ya que duplica los costos incluidos en la revisión del estimado preparado para la enmienda | Amaury Pacheco | Pending Amendment Request Approval | 2025-09-17 19:15 | Obligated, Pending Amendment Request Approval | 40% | 405037.61 | 1273278.52 |  | 1678316.13 | 53960.55 | 1598412.2339 | 442039.2361 | 142037.0968 | 67265.4432 | 168735.76 | 400852.24 | 2819342.01 | 1909185.0907 | 910156.9193 | Amendment – Submitted to FEMA | Submitted | Open Soft RFI to revise soft Cost will be submitted 02/20 / Estimated date Cfci strategy to be defined | #REF! | #VALUE!
757692 | FAASt [Automation Program Group 26] (TL / Distribution) | Grid Automation | Grid Automation | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 807422.25 | 340229.83 | 69331.28 | 43770.32 | 82692.01 | 259575.99 | 1603021.68 | 959445.54 | 643576.14 | Y | Angelica Rosario/Oscar Fuentes | Amendment – Submitted to FEMA | 406HM Revision Pending Award in GP / Estimated date Cfci strategy to be defined. In addition to the amendment version, a revised differential estimate of $38,543.25 for the communications wireless portion was added to the 406 section (without A&E and E&M).Estimate is an Class 3. | Verificar los costos totales presentados en 406, (Columna Z) ya que duplica los costos incluidos en la revisión del estimado preparado para la enmienda | Amaury Pacheco | Pending PDMG Scope & Cost Routing | 2025-09-03 20:15 | Obligated, Pending PDMG Scope & Cost Routing | 50% | 178504.71 | 975235.86 |  | 1153740.57 | -254490.45 | 805588.09 | 597770.7 | 71140.9 | 41960.7 | 89982.74 | 251069 | 1857512.13 | 966711.73 | 890800.4 | Amendment – Submitted to FEMA | Submitted | Open Soft RFI to revise soft Cost will be submitted 02/20 / Estimated date Cfci strategy to be defined | #REF! | #VALUE!
757694 | FAASt [Automation Program Group 27] (Distribution) | Grid Automation | Grid Automation | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1854481.54 | 591389.65 | 381502.7 | 196477.51 | 230481.01 | 495146.19 | 3749478.6 | 2466465.25 | 1283013.35 | Y | Angelica Rosario/Oscar Fuentes | Amendment – Amendment Needed/Pending Development | 406HM Revision to be submitted April 2026 to GP/ Waiting for COR3 feedback/ Estimated date Cfci strategy to be defined. In addition to the amendment version, a revised differential estimate of $53,960.55 for the communications wireless portion was added to the 406 section (without A&E and E&M).Estimate is an Class 3. | Verificar los costos totales presentados en 406, (Columna Z) ya que duplica los costos incluidos en la revisión del estimado preparado para la enmienda | Amaury Pacheco | Obligated | 2025-09-25 16:16 | Obligated | 15% | 245433.59 | 252445.32 |  | 497878.91 | 36885.73 | 1683592.9921 | 631140.7879 | 308544.3439 | 111377.7861 | 458173.9582 | 519763.0018 | 3712592.87 | 2450311.2942 | 1262281.5758 | Amendment – Amendment Needed/Pending Development | Q4 FY2026 | 406 HM Revision to be submitted May 2026 / Estimated date Cfci strategy to be defined | #REF! | #VALUE!
757696 | FAASt [Automation Program Group 31] (Distribution) | Grid Automation | Grid Automation | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 940960.74 | 346598.27 | 87081.37 | 44095.89 | 122168.23 | 240541.77 | 1781446.27 | 1150210.34 | 631235.93 | Y | Angelica Rosario/Oscar Fuentes | Amendment – Submitted to FEMA | 406HM Revision Pending Award in GP / Estimated date Cfci strategy to be defined. In addition to the amendment version, a revised differential estimate of $46,251.90 for the communications wireless portion was added to the 406 section (without A&E and E&M).Estimate is an Class 3. | Verificar los costos totales presentados en 406, (Columna Z) ya que duplica los costos incluidos en la revisión del estimado preparado para la enmienda | Amaury Pacheco | Pending PDMG Scope & Cost Routing | 2025-09-17 19:15 | Obligated, Pending PDMG Scope & Cost Routing | 32% | 236991.52 | 812101 |  | 1049092.52 | -237992.23 | 942101.34 | 583449.9 | 87474.903 | 43702.3571 | 122168.23 | 240541.77 | 2019438.5 | 1151744.473 | 867694.0271 | Amendment – Submitted to FEMA | Submitted | Open Soft RFI to revise soft Cost will be submitted 02/20/ Estimated date Cfci strategy to be defined | #REF! | #VALUE!
757697 | FAASt [Automation Program Group 32] (TL / Distribution) | Grid Automation | Grid Automation | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 2053127.85 | 562049.57 | 317057.24 | 138127.24 | 219381.16 | 471983.84 | 3761726.9 | 2589566.25 | 1172160.65 | Y | Angelica Rosario/Oscar Fuentes | Amendment – Amendment Needed/Pending Development | 406HM Revision to be submitted April 2026 to GP/ Waiting for COR3 feedback/ Estimated date Cfci strategy to be defined.In addition to the amendment version, a revised differential estimate of $53,960.55 for the communications wireless portion was added to the 406 section (without A&E and E&M).Estimate is an Class 3. | Verificar los costos totales presentados en 406, (Columna Z) ya que duplica los costos incluidos en la revisión del estimado preparado para la enmienda | Amaury Pacheco | Obligated | 2025-09-25 17:15 | Obligated | 17% | 228055.46 | 39875.94 |  | 267931.4 | 208272.78 | 2115845.46 | 475340.55 | 196682.43 | 74220.68 | 209878.53 | 481486.47 | 3553454.12 | 2522406.42 | 1031047.7 | Amendment – Amendment Needed/Pending Development | Q4 FY2026 | 406 HM Revision to be submitted April 2026/ Estimated date Cfci strategy to be defined | #REF! | #VALUE!
757698 | FAASt [Automation Program Group 33] (Distribution) | Grid Automation | Grid Automation | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1435455.15 | 570512.93 | 298284.82 | 143185.1 | 185468.25 | 392343.7 | 3025249.95 | 1919208.22 | 1106041.73 | Y | Angelica Rosario/Oscar Fuentes | Amendment – Submitted to FEMA | 406 HM Revision Submitted March 31 2026 to GP/ Estimated date Cfci strategy to be defined. In addition to the amendment version, a revised differential estimate of $69,377.85 for the communications wireless portion was added to the 406 section (without A&E and E&M).Estimate is an Class 3. | Verificar los costos totales presentados en 406, (Columna Z) ya que duplica los costos incluidos en la revisión del estimado preparado para la enmienda | Amaury Pacheco | Obligated | 2025-09-25 17:15 | Obligated | 20% | 146082.21 | 1146114.8 |  | 1292197.01 | 269103.21 | 1124448.32 | 1149434.09 | 141667.93 | 165158.11 | 30777.97 | 144660.32 | 2756146.74 | 1296894.22 | 1459252.52 | Amendment – Amendment Needed/Pending Development | Q4 FY2026 | 406 HM Revision to be submitted April 2026/ Estimated date Cfci strategy to be defined | #REF! | #VALUE!
757699 | FAASt [Automation Program Group 34] (Distribution) | Grid Automation | Grid Automation | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 2072695.44 | 606035.3 | 433846.26 | 195477.43 | 209012.07 | 473571.13 | 3990637.63 | 2715553.77 | 1275083.86 | Y | Angelica Rosario/Oscar Fuentes | Amendment – Amendment Needed/Pending Development | 406HM Revision to be submitted May 2026 to GP / Estimated date Cfci strategy to be defined. In addition to the amendment version, a revised differential estimate of $61,669.20 for the communications wireless portion was added to the 406 section (without A&E and E&M).Estimate is an Class 3. | Verificar los costos totales presentados en 406, (Columna Z) ya que duplica los costos incluidos en la revisión del estimado preparado para la enmienda | Amaury Pacheco | Obligated | 2025-11-05 16:17 | Obligated | 4% | 303189.59 | 19984.26 |  | 323173.85 | -30012.75 | 2600700.95 | 561457.08 | 233404.43 | 74776.72 | 147275.17 | 403036.03 | 4020650.38 | 2981380.55 | 1039269.83 | Amendment – Amendment Needed/Pending Development | Q4 FY2026 | 406HM Revision to be submitted June 2026 / Estimated date Cfci strategy to be defined | #REF! | #VALUE!
757700 | FAASt [Automation Program Group 35] (TL / Distribution) | Grid Automation | Grid Automation | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1130075.79 | 551850.51 | 147185.05 | 85545.81 | 118838.8 | 298749.6 | 2332245.56 | 1396099.64 | 936145.92 | Y | Angelica Rosario/Oscar Fuentes | Amendment – Submitted to FEMA | 406HM Revision currently Pending to be Award in GP / Estimated date Cfci strategy to be defined. In addition to the amendment version, a revised differential estimate of $61,669.20 for the communications wireless portion was added to the 406 section (without A&E and E&M).Estimate is an Class 3. | Verificar los costos totales presentados en 406, (Columna Z) ya que duplica los costos incluidos en la revisión del estimado preparado para la enmienda | Amaury Pacheco | Pending FEMA 406 HMP Completion | 2025-09-17 19:15 | Obligated, Pending FEMA 406 HMP Completion | 10% | 316891.15 | 1136104.46 |  | 1452995.61 | -321507.3577 | 1133466.58 | 869967.07 | 148303.89 | 84426.9677 | 118838.82 | 298749.59 | 2653752.9177 | 1400609.29 | 1253143.6277 | Amendment – Submitted to FEMA | Submitted | Open Soft RFI to revise soft Cost will be submitted 02/20 / Estimated date Cfci strategy to be defined | #REF! | #VALUE!
800286 | FAASt [Automation Program Group 36] (TL / Distribution) | Grid Automation | Grid Automation | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1427638.4262 | 582790.347 | 137043.707 | 78366.543 | 175789.83 | 397237.57 | 2798866.4232 | 1740471.9632 | 1058394.46 | Y | Angelica Rosario/Oscar Fuentes | Amendment – Submitted to FEMA | 406HM Revision currently Pending to be Award in GP / Estimated date Cfci strategy to be defined. In addition to the amendment version, a revised differential estimate of $63,377.85 for the communications wireless portion was added to the 406 section (without A&E and E&M).Estimate is an Class 3. | Verificar los costos totales presentados en 406, (Columna Z) ya que duplica los costos incluidos en la revisión del estimado preparado para la enmienda | Amaury Pacheco | Pending EHP Review | 2025-09-17 19:15 | Obligated, Pending EHP Review | 26% | 268286.3 | 861684.63 |  | 1129970.93 | -412226.263 | 1427638.4262 | 995016.61 | 137043.707 | 78366.543 | 175789.83 | 397237.57 | 3211092.6862 | 1740471.9632 | 1470620.723 | Amendment – Submitted to FEMA | Submitted | 406HM Revision Pending Award in GP / Estimated date Cfci strategy to be defined | #REF! | #VALUE!
800361 | FAASt [Automation Program Group 37] (Distribution) | Grid Automation | Grid Automation | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1514451.93 | 369437.55 | 174540.79 | 68764.66 | 164586.33 | 302167.8 | 2593949.06 | 1853579.05 | 740370.01 | Y | Angelica Rosario/Oscar Fuentes | Amendment – Submitted to FEMA | 406HM Revision Pending Award in GP / Estimated date Cfci strategy to be defined. In addition to the amendment version, a revised differential estimate of $46,251.90 for the communications wireless portion was added to the 406 section (without A&E and E&M).Estimate is an Class 3. | Verificar los costos totales presentados en 406, (Columna Z) ya que duplica los costos incluidos en la revisión del estimado preparado para la enmienda | Amaury Pacheco | Pending Amendment Request Approval | 2025-09-17 19:15 | Obligated, Pending Amendment Request Approval | 40% | 299645.5 | 720209.99 |  | 1019855.49 | 8818.4 | 1539270.03 | 341311.78 | 182365.82 | 60877.03 | 158441.28 | 302864.72 | 2585130.66 | 1880077.13 | 705053.53 | Amendment – Submitted to FEMA | Submitted | Open Soft RFI to revise soft Cost will be submitted 02/20 / Estimated date Cfci strategy to be defined | #REF! | #VALUE!
673844 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 3] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1286113.33 | 252343 | 208800.58 | 66870.9 | 0 | 0 | 1814127.81 | 1494913.91 | 319213.9 | Y | Yaritza Acevedo Ortiz | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version. | Se espera que este proyecto tenga costos que sobrepasan la obligación por $213k. | Luis Sepulveda | Obligated | 2022-08-24 10:30 | Obligated | 87% | 317413.67 | 1302232.74 |  | 1619646.41 | 1526924.84 | 243833.22 | 919.39 | 21435.45 | 574.91 | 14432.64 | 6007.36 | 287202.97 | 279701.31 | 7501.66 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
753782 | FAASt [Transmission Priority Pole Replacement Program Line 3100 Monacillos TC – Sabana Llana TC] (Transmission) | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 221703.17 | 2218.84 | 20500.96 | 291.07 | 5970.66 | 1473.34 | 252158.04 | 248174.79 | 3983.25 | Y | Carlos Samalot | Obligated - Amendment Pending Final Actual Costs | This information reflects the latest LPCE data provided and includes the actuals delta. The final cost will be taken into consideration during the project reconciliation and close-out. | Estimate cost change should be Yes. The new cost differs from the obligated and from the cost submitted to PREB. NEW Cost is over the obligated cost, and less than the submitted to PREB. Cost incurred does not exceeds the final estimation. No mayor flags identified in cost. | Chantee Santana | Obligated | 2025-10-30 20:15 | Obligated | 0% | 153880.76 | 277.28 |  | 154158.04 | -52586716.73 | 32064811.63 | 4437681.65 | 3286608.94 | 1116082.17 | 4091238.32 | 7842452.06 | 52838874.77 | 39442658.89 | 13396215.88 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | No Amendment Needed | #REF! | #VALUE!
550950 | FAASt - EPC - [Monacillo TC] (Substations) | Priority Substation | Substation | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 105263051.6657 | 16405165.3271 | 16410099.5355 | 1849115.9258 | 62121740.86 | 11046468.76 | 213095642.0741 | 183794892.0613 | 29300750.0129 | Y | Carlos Baez | Amendment – Submitted to FEMA | Ammedment include full rebuild scope Cost change is driven by more define scope and inflation | Check estimate: should include 6 transformer, 15kv gis, 38 kv gis, 115 gis, .. Number should be $40-45 for EM | Sandra Valentin | Obligated | 2023-12-19 12:23 | Obligated | 11% | 5935100.26 | 11153695.49 |  | 17088795.75 | 53929814.7842 | 93729896.23 | 13188476.41 | 18252835.9 | 1706525.37 | 28961853.03 | 3326240.35 | 159165827.29 | 140944585.16 | 18221242.13 | Amendment – Submitted to FEMA | Submitted |  | #REF! | #VALUE!
547187 | FAASt [Substation Component Replacement Program] (Substation) | Substation | Substation | No | Pending Scope & Cost Completion by Applicant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8910537.185 | 272764.041 | 2942350.301 | 89054.581 | 2669172.077 | 22183.282 | 14906061.467 | 14522059.563 | 384001.904 | 8910537.185 | 272764.041 | 2942350.301 | 89054.581 | 2669172.077 | 22183.282 | 14906061.467 | 14522059.563 | 384001.904 | N | Carlos Baez | Project in V0 - No amendment required at this time | No expected changes | Cost difference seems to be contingency cost added to 428. Cost incurred does not exceeds the final estimation. Construction cost incurred with no N/A construction %. (406 cost duplicity identified) | Gabriel Torres | Pending Scope & Cost Completion by Applicant |  | Pending Scope & Cost Completion by Applicant | N/A | 1074712.85 | 11499.14 |  | 1086211.99 | 1355096.497 | 8100488.35 | 247967.31 | 2674863.91 | 80958.71 | 2426520.07 | 20166.62 | 13550964.97 | 13201872.33 | 349092.64 | DSOW – Submitted to COR3/PREPA | Submitted | Submitted to COR3 in Feb. 2026 | 1 | #VALUE!
956593 | FAASt [Factor Sect 8014 Transformer Replacement] (Substation) | Substation | Substation | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 4404224.9449 | 1427070.1716 | 402805.69 | 137265.82 | 134857.23 | 320428.9 | 6826652.7565 | 4941887.8649 | 1884764.8916 | N | Carlos Baez | Amendment - Pending Development | No expected changes | No Cost changes from the Submitted to the PREB/Obligated. Construction cost incurred with no N/A construction %. Cost incurred does not exceeds the final estimation. No mayor flags identified in cost | Gabriel Torres | Obligated | 2025-09-22 16:15 | Obligated | 20% | 218717.81 | 372387.71 |  | 591105.52 | 919333.1465 | 3600960.6953 | 548535.3833 | 366186.9904 | 124787.1069 | 443168.1805 | 823681.2536 | 5907319.61 | 4410315.8663 | 1497003.7437 | Obligated -No expected changes | N/A |  | #REF! | #VALUE!
550910 | FAASt Physical Security - Group 1 (Substatio | Substation | Substation Security | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 6627797.242 | 509533.277 | 1406160.756 | 223021.579 | 0 | 0 | 8766512.854 | 8033957.998 | 732554.856 | Y | Carlos Baez | Amendment - Pending Development | Submitted | Final cost provided is same as obligated. However, Incurred cost surpass this total and the submitted to COR3 in 11/14 have a total cost of $14M | Gabriel Torres | Obligated | 2023-05-04 11:30 | Obligated | 81% | 2379891.36 | 8174673.94 |  | 10554565.3 | 796955.714 | 6025270.22 | 463212.07 | 1278327.96 | 202746.89 | 0 | 0 | 7969557.14 | 7303598.18 | 665958.96 | Amendment – Submitted to COR3/PREPA | Submitted | E&M allocations not included in original obligation | #REF! | #VALUE!
546370 | FAASt - Substation Minor Repairs Group A (Subs | Substation | Substation Rebuilds | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 4931269.761 | 367083.277 | 1095995.021 | 169939.561 | 0 | 0 | 6564287.62 | 6027264.782 | 537022.838 | Y | Carlos Baez | Amendment - Pending Development | Luma finalizing scope, amendment to be submitted Q4 FY26 Cost change is driven by more define scope and inflation | Final cost provided is same as obligated. However, Incurred cost is over this total with 30% stip pending in construction. The pending amendment have a total cost of $6.5M | Gabriel Torres | Obligated | 2024-02-13 12:36 | Obligated | 71% | 2841572.68 | 3200923.86 |  | 6042496.54 | 596753.42 | 4482972.51 | 333712.07 | 996359.11 | 154490.51 | 0 | 0 | 5967534.2 | 5479331.62 | 488202.58 | Amendment – Amendment Needed/Pending Development | Q4 FY2026 | E&M allocations not included in original obligation | #REF! | #VALUE!
673843 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 3] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 2253235.45 | 179969 | 175796 | 47692 | 0 | 0 | 2656692.45 | 2429031.45 | 227661 | Y | Yaritza Acevedo Ortiz | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version. | Se espera que este proyecto tenga costos que sobrepasan la obligación por $1.3 millones. | Luis Sepulveda | Obligated | 2022-10-17 11:37 | Obligated | 80% | 365075.68 | 2165876.07 |  | 2530951.75 | 1349041.45 | 904194 | 179969 | 175796 | 47692 | 0 | 0 | 1307651 | 1079990 | 227661 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
165213 | FAASt – Line 5400 – Rio Blanco HP to Daguao TC to Punta Lima TO to Vieques 2501 to Culebra 3801 (Transmission) | Transmission | Vieques and Culebra Projects (6) | No | Pending Scope & Cost Completion by Applicant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90286761.91 | 33780983.5629 | 7450643.73 | 2497575.1807 | 14930827.72 | 1685383.8863 | 150632175.99 | 112668233.36 | 37963942.63 | 90286761.91 | 33780983.5629 | 7450643.73 | 2497575.1807 | 14930827.72 | 1685383.8863 | 150632175.99 | 112668233.36 | 37963942.63 | Y | Jose Santos | Project in V0 - No amendment required at this time | The DSOW revision will be submitted as part of the pending RFI response. The updated scope and design incorporate an additional segment. The revised estimate includes a budgetary allowance for this added transmission overhead line segment, as well as new underground distribution and transmission components that will likely be Hazard Mitigation | The new cost total did not changed from the cost submitted to PREB. However the allocations did. Increased in 406 allocation. Cost incurred does not exceeds the final estimation. Construction cost incurred reflected with no N/A construction % No mayor flags identified in cost. | Chantee Santana | Pending Scope & Cost Completion by Applicant |  | Pending Scope & Cost Completion by Applicant | N/A | 5633450.47 | 27819.85 |  | 5661270.32 | 24000000 | 90286761.91 | 12425361.64 | 7450643.73 | 918661.08 | 14930827.72 | 619919.91 | 126632175.99 | 112668233.36 | 13963942.63 | DSOW – Scope and Cost development in progress | Q1 FY2026 | Issue for Approval was received meeting ongoing to discuss the design and agree in the final scope to be submitted to FEMA. | 1 | #VALUE!
756997 | FAASt [TL 1900 Caguanas to Lares TO] (Transmission) | Transmission | Transmission Line Rebuild | No | Pending Scope & Cost Completion by Applicant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34621568.58 | 7218553.15 | 2584537.17 | 770659.35 | 1066728.72 | 3635223.17 | 49897270.14 | 38272834.47 | 11624435.67 | 34621568.58 | 7218553.15 | 2584537.17 | 770659.35 | 1066728.72 | 3635223.17 | 49897270.14 | 38272834.47 | 11624435.67 | Y | Nelson Torres | Project in V0 - No amendment required at this time | The DSOW revision has been submitted to FEMA | The new cost total increased from the previously submitted to the PREB. And shows a significant difference from the obligated cost. Latest DSOW was submitted to FEMA on 2/4/2026. A&E Cost incurred exceeds the estimated cost.Construction cost incurred with no N/A construction %. Original A&E design was for the whole line (Dos Bocas to San Sebastian) and it was divided in 3 segments. | Chantee Santana | Pending Scope & Cost Completion by Applicant |  | Pending Scope & Cost Completion by Applicant | N/A | 3861197.67 | 279802.22 |  | 4140999.89 | 6549781.02 | 30997111.49 | 4687634.65 | 2356500.58 | 611010.51 | 1066728.72 | 3628503.17 | 43347489.12 | 34420340.79 | 8927148.33 | DSOW – Submitted to COR3/PREPA | Submitted | Already Submitted | 1 | #VALUE!
549725 | FAASt [Substation Minor Repairs - Group E] (Substation) | Substation | Substation | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 4316417.259 | 414743.23 | 900049.964 | 223001.042 | 0 | 0 | 5854211.495 | 5216467.223 | 637744.272 | Y | Carlos Baez | Amendment - Pending Development | LUMA working on project scope with Genera, amendment to be submitted Q1 FY27 Cost change is driven by more define scope and inflation | No Cost changes from the Submitted to the PREB. Construction cost incurred with no N/A construction %. Cost incurred does not exceeds the final estimation. No mayor flags identified in cost. | Gabriel Torres | Obligated | 2024-05-10 10:17 | Obligated | 57% | 456120.13 | 2775409.5 |  | 3231529.63 | 532201.045 | 3924015.69 | 377039.3 | 818227.24 | 202728.22 | 0 | 0 | 5322010.45 | 4742242.93 | 579767.52 | Amendment – Amendment Needed/Pending Development | Q1 FY2027 | E&M allocations not included in original obligation | #REF! | #VALUE!
551861 | FAASt [Physical Security - Group 3] (Substation) | Substation | Substation Security | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 4066652.26 | 333495.019 | 929320.381 | 146526.534 | 0 | 0 | 5475994.194 | 4995972.641 | 480021.553 | Y | Carlos Baez | Amendment - Pending Development | Submitted | Final cost provided is same as obligated. However, Incurred cost is 75% of cost with 48% of construction. The submitted amendment to COR3 in 11/14 have a total cost of $12M | Gabriel Torres | Obligated | 2023-06-16 12:55 | Obligated | 48% | 456389.67 | 3255929.64 |  | 3712319.31 | 497817.654 | 3696956.6 | 303177.29 | 844836.71 | 133205.94 | 0 | 0 | 4978176.54 | 4541793.31 | 436383.23 | Amendment – Submitted to COR3/PREPA | Submitted | E&M allocations not included in original obligation | #REF! | #VALUE!
682834 | FAASt [EPC - Costa Sur TC - Phase II & III ] (Substation) | Priority Substation | Substation Rebuilds | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 53265182.432 | 7858797.408 | 5239198.272 | 1746399.424 | 14525597.69 | 37474402.31 | 120109577.536 | 73029978.394 | 47079599.142 | Y | Carlos Baez | Amendment - Pending Development | Luma finalizing scope, amendment to be submitted Q2 FY27 Cost change is driven by more define scope and inflation | In the EM we have 52M | Gabriel Torres | Obligated | 2024-02-13 12:36 | Obligated | 1% | 4559202.8 | 1760103.26 |  | 6319306.06 | 41246885.686 | 36917509.58 | 0 | 6435349.91 | 0 | 35509832.36 | 0 | 78862691.85 | 78862691.85 | 0 | Amendment – Scope and Cost development in progress | Q4 FY2026 |  | #REF! | #VALUE!
660422 | FAASt [Physical Security - Group 4] (Substation) | Substation | Substation Security | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 3826369.8 | 249315 | 843279.8 | 122789.7 | 0 | 0 | 5041754.3 | 4669649.6 | 372104.7 | Y | Carlos Baez | Amendment - Pending Development | Luma finalizing scope, amendment to be submitted Q2 FY27 Cost change is driven by more define scope and inflation | No Cost changes from the Submitted to the PREB. Cost incurred does not exceeds the final estimation. No mayor flags identified in cost. | Gabriel Torres | Obligated | 2023-12-29 12:31 | Obligated | 43% | 279040.58 | 1035431.54 |  | 1314472.12 | 458341.3 | 3478518 | 226650 | 766618 | 111627 | 0 | 0 | 4583413 | 4245136 | 338277 | Amendment – Amendment Needed/Pending Development | Q1 FY2027 | E&M allocations not included in original obligation | #REF! | #VALUE!
546371 | FAASt- Substation Minor Repairs Group C (Substation) | Substation | Substation Rebuilds | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 2913084.966 | 288261.908 | 711120.476 | 134833.446 | 0 | 0 | 4047300.796 | 3624205.442 | 423095.354 | Y | Carlos Baez | Amendment - Pending Development | LUMA working on scope, amendment to be submitted Q1 FY27 Cost change is driven by more define scope and inflation | No Cost changes from the Submitted to the PREB. Amendment in progress for more than the total cost provided ($6.7) | Gabriel Torres | Obligated | 2023-08-22 11:21 | Obligated | 76% | 2233567.02 | 2261047.96 |  | 4494614.98 | 367936.436 | 2648259.06 | 262056.28 | 646473.16 | 122575.86 | 0 | 0 | 3679364.36 | 3294732.22 | 384632.14 | Amendment – Amendment Needed/Pending Development | Q4 FY2026 | E&M allocations not included in original obligation | #REF! | #VALUE!
549715 | FAASt Substation Minor Repairs - Group D (Substation) | Substation | Substation Rebuilds | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 2841446.894 | 201293.004 | 638207.559 | 115642.934 | 0 | 0 | 3796590.391 | 3479654.453 | 316935.938 | Y | Carlos Baez | Amendment - Pending Development | Luma finalizing scope, amendment to be submitted Q2 FY27 Cost change is driven by more define scope and inflation | Menciona que necesita una enmienda pero los costos son iguales a la obligación. Se debe revisar | Gabriel Torres | Obligated | 2024-04-12 11:19 | Obligated | 33% | 419380.77 | 380949.36 |  | 800330.13 | 345144.581 | 2583133.54 | 182993.64 | 580188.69 | 105129.94 | 0 | 0 | 3451445.81 | 3163322.23 | 288123.58 | Amendment – Amendment Needed/Pending Development | Q1 FY2027 | E&M allocations not included in original obligation | #REF! | #VALUE!
549764 | FAASt Physical Security - Group 2 (Substation) | Substation | Substation Security | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 2374913.541 | 165562.287 | 582748.639 | 81586.461 | 0 | 0 | 3204810.928 | 2957662.18 | 247148.748 | Y | Carlos Baez | Amendment - Pending Development | LUMA finalizing scope, revised scope to be submitted Q4 FY26 Cost change is driven by more define scope and inflation | No Cost changes from the Submitted to the PREB, however Amendment in progress reflects a total cost greater that the total provided ($3.1M) | Gabriel Torres | Obligated | 2023-06-16 12:55 | Obligated | 85% | 282253.1 | 1930999.02 |  | 2213252.12 | 291346.448 | 2159012.31 | 150511.17 | 529771.49 | 74169.51 | 0 | 0 | 2913464.48 | 2688783.8 | 224680.68 | Amendment – Amendment Needed/Pending Development | Q4 FY2026 | E&M allocations not included in original obligation | #REF! | #VALUE!
179558 | FAASt - Manatí TC - BRKS 230 kV - (Substation) | Substation | Substation Rebuilds | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1932688.3493 | 655782.0456 | 175000.6866 | 59635.7325 | 0 | 0 | 2823106.814 | 2107689.036 | 715417.778 | Y | Carlos Baez | Amendment – Submitted to COR3/PREPA | Submitted | E&M should be 0 | Gabriel Torres | Obligated | 2022-05-26 11:24 | Obligated | 100% | 1006502.23 | 329663.3 |  | 1336165.53 | 256646.074 | 1564453.0618 | 238313.587 | 159091.5333 | 54214.3022 | 192536.3467 | 357851.909 | 2566460.74 | 1916080.9418 | 650379.7982 | Amendment – Submitted to COR3/PREPA | Submitted |  | #REF! | #VALUE!
957578 | FAASt [Costa Sur TC Underground Cable Failure Replacement on Transformer Lead Bank #2] (Substation) | Substation | Substation | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1273789.3886 | 432210.5068 | 115338.8324 | 39304.5072 | 0 | 0 | 1860643.235 | 1389128.221 | 471515.014 | Y | Carlos Baez | Amendment - Pending Development | LUMA working on project scope with Genera, amendment to be submitted Q1FY27 Cost change is driven by more define scope and inflation | What is included in E&M? Should be 0 | Gabriel Torres | Obligated | 2025-09-17 19:15 | Obligated | 0% | 4909.66 | 4556.83 |  | 9466.49 | 169149.385 | 1031094.1802 | 157066.8744 | 104853.484 | 35731.3702 | 126896.1731 | 235851.7681 | 1691493.85 | 1262843.8373 | 428650.0127 | Amendment – Amendment Needed/Pending Development | Q4 FY2026 | scope and estimate to be revised | #REF! | #VALUE!
169495 | FAASt [Substations - Tapia GIS Rebuilt Equipment Repair &amp;amp; Replacement] (Substations) | Substation | Substation Rebuilds | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 8253800.1089 | 1962924.3274 | 1167269.299 | 530329.9907 | 3869859.11 | 3130140.89 | 18914323.7259 | 13290928.5179 | 5623395.208 | Y | Carlos Baez | Amendment - Pending Development | LUMA finalizing scope, revised scope to be submitted Q4 FY26 | How was calculated the E&M . Only E&M should be the GIS $7 | Gabriel Torres | Obligated | 2023-08-22 11:21 | Obligated | 8% | 2109213.46 | 30423.56 |  | 2139637.02 | -635840.6866 | 6681615.89 | 1589026.4125 | 944927.79 | 429312.71 | 5815884.59 | 4089397.02 | 19550164.4125 | 13442428.27 | 6107736.1425 | Amendment – Amendment Needed/Pending Development | Q1 FY2027 | Pending IFC to complete Estimate review | #REF! | #VALUE!
178503 | FAASt Aguirre TC - BKRS (Substations) | Substation | Substation Rebuilds | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 5675844.778 | 8568991.2456 | 1494839.9029 | 694125.0394 | 0 | 0 | 16433800.9659 | 7170684.681 | 9263116.285 | Y | Carlos Baez | Amendment – Submitted to COR3/PREPA | Submitted | What is included in E&M? Should be 0 | Orlando Rodriguez/chantee | Obligated | 2022-12-27 11:53 | Obligated | 33% | 4646057.03 | 9868755.21 |  | 14514812.24 | -26837083.3641 | 38926711.43 | 257069.07 | 4062989.94 | 24113.89 | 0 | 0 | 43270884.33 | 42989701.37 | 281182.96 | Amendment – Submitted to COR3/PREPA | Submitted |  | #REF! | #VALUE!
751656 | FAASt [Culebra Microgrid] (Transmission) | Transmission | Vieques and Culebra Projects (6) | No | Pending Scope & Cost Completion by Applicant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 671661.536 | 109183728.0243 | 10795126.3543 | 22484740.5443 | 0 | 25228860.2043 | 168364116.6632 | 11466787.8903 | 156897328.7729 | 671661.536 | 109183728.0243 | 10795126.3543 | 22484740.5443 | 0 | 25228860.2043 | 168364116.6632 | 11466787.8903 | 156897328.7729 | Y | Janice Lopez | Not obligated - Increase in estimate that will be submitted to FEMA. | The expected total reflects the latest information from the discontinued RFP. | This estimate does not include the addition of a new substation to this project | Jose A Cruz | Pending Scope & Cost Completion by Applicant |  | Pending Scope & Cost Completion by Applicant | N/A | 521638.9 | 0 |  | 521638.9 | 42919807.5831 | 520290.54 | 99551019.1 | 27002.9 | 8445174.73 | 0 | 16900821.81 | 125444309.08 | 547293.44 | 124897015.64 | DSOW – Pending Design Package for Development | Q2 FY2027 | The DSOW Revision 2 for the Vieques and Culebra Microgrid was submitted in July 2025. After receiving various Requests for Information (RFIs) from FEMA related to the design, an internal decision was made to re-submit the DSOW once the 30% design is completed, providing more robust information to adequately address the agency’s requests. As of today, the DSOW is estimated to be re-submitted in October 2026 following the completion of the 60% design. | 1 | #VALUE!
176971 | FAASt –38kV Line 8200 - San Juan SP to Catano Sect Line (Transmission) | Priority Transmission | Transmission Line Rebuild | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 18218875.04 | 4631659.7 | 2848814.49 | 568928.1 | 1080651.07 | 23122.43 | 27372050.83 | 22148340.6 | 5223710.23 | Y | Jan Lopez | Amendment - Pending Development | Information represents the latest LPCE information provided. | Additional information requested from A&E regarding foundations and insulators to be added to the scope and estimate. Possible new cost with these changes | Jose A Cruz | Obligated | 2025-11-05 16:17 | Obligated | 0% | 2172259.97 | 63133.09 |  | 2235393.06 | 3382384.46 | 18028195.83 | 3833616.78 | 1664551.02 | 342899.38 | 118276.26 | 2127.1 | 23989666.37 | 19811023.11 | 4178643.26 | Amendment – Scope and Cost development in progress | Q4 FY2026 |  | #REF! | #VALUE!
176913 | FAASt [Palo Seco SP to Catano Sect 38kV Line- 9500] (Transmission) | Priority Transmission | Transmission Line Rebuild | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 17467604.15 | 3864276.13 | 2619374.41 | 2157076.76 | 2071399.22 | 66725.58 | 28246456.25 | 22158377.78 | 6088078.47 | Y | Jan Lopez | Amendment - Pending Development | Information represents the latest LPCE information provided. | The Column AB cost does not align with the 406% assigned to the project. New information requested from A&E, will probable generate additional costs. | Jose A Cruz | Obligated | 2025-11-05 16:17 | Obligated | 0% | 2663813.77 | 73599.62 |  | 2737413.39 | -6467854.19 | 29688455.53 | 656415.25 | 4164273.96 | 93674.84 | 96089.14 | 15401.72 | 34714310.44 | 33948818.63 | 765491.81 | Amendment – Scope and Cost development in progress | Q4 FY2026 | Obligated for $33.5M. The expected total project cost is $40.8M | #REF! | #VALUE!
749072 | FAASt [Transmission Priority Pole Replacement Program Line 2700 Aguadilla Hospital Distrito Sect – Mora TC] (Transmission) | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1002273.48 | 44679.36 | 181551.75 | 2952.97 | 85082.65 | 14236.35 | 1330776.56 | 1268907.88 | 61868.68 | Y | Carlos Samalot | Obligated - Amendment needed | Information represents the latest LPCE information provided. | The project has expenses in A&E that surpass the numbers presented by the PM by $238k | Luis Sepulveda | Obligated | 2025-11-05 16:16 | Obligated | 0% | 317290.12 | 928.59 |  | 318218.71 | 368945.23 | 763811.92 | 51189.5 | 68678.99 | 4322.92 | 69251.52 | 4576.48 | 961831.33 | 901742.43 | 60088.9 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | No Amendment Needed | #REF! | #VALUE!
711670 | FAASt [T-Pole Program Line 100] (Transmission) | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 441327.62 | 18841.36 | 12340.69 | 4531.35 | 0 | 0 | 477041.02 | 453668.31 | 23372.71 | Y | Carlos Samalot | Amendment - Pending Development | This information reflects the latest LPCE data provided and includes the actuals delta. The final cost will be taken into consideration during the project reconciliation and close-out. | Pending additions of the A&E costs of the projects. | Jose A Cruz | Obligated | 2024-06-18 11:28 | Obligated | 93% | 245506.97 | 215837.69 |  | 461344.66 | 341769.17 | 102171.23 | 13243.54 | 16958.53 | 1285.62 | 662.57 | 950.36 | 135271.85 | 119792.33 | 15479.52 | Obligated -No expected changes | N/A | No Amendment Needed | #REF! | #VALUE!
750168 | FAASt [ Transmission Priority Pole Replacement Program Line 4800 Santa Isabel TC – Aibonito TO] (Transmission) | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 431757.15 | 28284.79 | 45787.13 | 3335.39 | 36682.34 | 5852.66 | 551699.46 | 514226.62 | 37472.84 | N | Carlos Samalot | Amendment - Pending Development | Information represents the latest LPCE information provided. | No Comment | Jose A Cruz | Obligated | 2025-11-25 18:15 | Obligated | 0% | 40356.92 | 586.81 |  | 40943.73 | 0 | 428428.21 | 31613.73 | 45787.13 | 3335.39 | 40011.28 | 2523.72 | 551699.46 | 514226.62 | 37472.84 | Obligated -No expected changes | N/A | Already Submitted | #REF! | #VALUE!
750150 | FAASt [Transmission Priority Pole Replacement Program Line 4800 Santa Isabel TC – Toro Negro 1 HP] (Transmission) | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 138347.1 | 5675.78 | 19852.4 | 1075.69 | 5971.66 | 1473.34 | 172395.97 | 164171.16 | 8224.81 | Y | Carlos Samalot | Amendment - Pending Development | This information reflects the latest LPCE data provided and includes the actuals delta. The final cost will be taken into consideration during the project reconciliation and close-out. | No Comment | Jose A Cruz | Obligated | 2025-11-05 16:16 | Obligated | 0% | 70395.96 | 0 |  | 70395.96 | 12423.55 | 125923.56 | 5675.78 | 19852.4 | 1075.68 | 5971.66 | 1473.34 | 159972.42 | 151747.62 | 8224.8 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | No Amendment Needed | #REF! | #VALUE!
749060 | FAASt [Transmission Priority Pole Replacement Program Line 5600 Victoria TC – Añasco TC] (Transmission) | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1077371.11 | 145054.24 | 154904.41 | 21644.91 | 134447.11 | 24366.65 | 1557788.43 | 1366722.63 | 191065.8 | Y | Carlos Samalot | Amendment - Pending Development | Information represents the latest LPCE information provided. | Information confirmed with PM | Jose A Cruz | Obligated | 2026-03-01 18:16 | Obligated | N/A | 308615.22 | 0 |  | 308615.22 | 40887.35 | 425379.95 | 829239.3 | 40970.81 | 86903.02 | 19608.94 | 114799.06 | 1516901.08 | 485959.7 | 1030941.38 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | No Amendment Needed | #REF! | #VALUE!
167446 | FAASt - Line 36100 (115kV) - Bayamon to Monacillos (Transmission) | Priority Transmission | Transmission Line Rebuild | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 16767135.99 | 10441839.67 | 4907530.43 | 3867090.21 | 2133671.71 | 5779812.06 | 43897080.07 | 23808338.13 | 20088741.94 | Y | Ted Hicks | Amendment - Pending Development | Information represents the latest LPCE information provided. | The costs incurred in A&E exceed the costs included in the project's expected cost. | Jose A Cruz | Obligated | 2025-11-05 16:17 | Obligated | 0% | 9633230.75 | 1121278.11 |  | 10754508.86 | 4612314.41 | 18657617.56 | 10503244.02 | 1398471.71 | 1349494.84 | 2069637.1 | 5306300.43 | 39284765.66 | 22125726.37 | 17159039.29 | Amendment – Scope and Cost development in progress | Submitted |  | #REF! | #VALUE!
668592 | FAASt Line 9800 Bayamon TC - Guaraguao Sect | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 524429.75 | 8046.34 | 34734.97 | 698.02 | 0 | 0 | 567909.08 | 559164.72 | 8744.36 | Y | Carlos Samalot | Amendment - Pending Development | This information reflects the latest LPCE data provided and includes the actuals delta. The final cost will be taken into consideration during the project reconciliation and close-out. | Project amendment pending COR3 approval since 3/4/2026 | Jose A Cruz | Pending Amendment Request Approval | 2022-09-16 11:54 | Obligated, Pending Amendment Request Approval | 94% | 174616.04 | 389293.04 |  | 563909.08 | 124992.66 | 359543.38 | 5405.05 | 34734.97 | 698.02 | 39893.71 | 2641.29 | 442916.42 | 434172.06 | 8744.36 | Amendment – Submitted to COR3/PREPA | Submitted |  | #REF! | #VALUE!
334468 | FAASt Line 2200 Dos Bocas HP to Dorado TC (T | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 3049725.4 | 33717.27 | 129281.25 | 2827.08 | 9793.65 | 0 | 3225344.65 | 3188800.3 | 36544.35 | Y | Carlos Samalot | Amendment - Pending Development | This information reflects the latest LPCE data provided and includes the actuals delta. The final cost will be taken into consideration during the project reconciliation and close-out. | Project pending COR 3 amendment approval since 2/18/26 | Jose A Cruz | Pending Amendment Request Approval | 2022-07-13 21:08 | Obligated, Pending Amendment Request Approval | 93% | 1664354.71 | 1556989.94 |  | 3221344.65 | 1520895.5 | 1528829.9 | 33717.27 | 129281.25 | 2827.08 | 9793.65 | 0 | 1704449.15 | 1667904.8 | 36544.35 | Amendment – Submitted to COR3/PREPA | Submitted |  | #REF! | #VALUE!
334470 | FAASt [TL 3100 Monacillos TC to Sabana Llana TC] (Transmission) | Priority Transmission | Transmission Line Rebuild | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 27732104.95 | 8785252.58 | 4550630.02 | 2355507.88 | 5594861.69 | 10425727.74 | 59444084.86 | 37877596.66 | 21566488.2 | Y | Ted Hicks | Amendment - Pending Development | The information reflects the latest LPCE data provided. The cost currently includes the full line rebuild A&E design cost, under 428. This will be corrected through the obligation amendment. | No comment. | Jose A Cruz | Obligated | 2025-11-05 16:17 | Obligated | 0% | 5865198.45 | 22693.38 |  | 5887891.83 | 35068.02 | 35438292.75 | 7238872.38 | 3499216.45 | 1292224.88 | 4097958.32 | 7842452.06 | 59409016.84 | 43035467.52 | 16373549.32 | Amendment – Scope and Cost development in progress | Q4 FY2026 | Obligated for $47.1M, the expected total project cost is $54M | #REF! | #VALUE!
168483 | FAASt - 115kV Line 36400 - Dos Bocas HP to Ponce TC (Transmission) | Transmission | Transmission Line Rebuild | No | Pending Scope & Cost Completion by Applicant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73843869.7985 | 62335950.1897 | 4386536.3259 | 3697488.9625 | 29668.6935 | 0 | 144293513.97 | 78260074.8179 | 66033439.1521 | 73843869.7985 | 62335950.1897 | 4386536.3259 | 3697488.9625 | 29668.6935 | 0 | 144293513.97 | 78260074.8179 | 66033439.1521 | Y | Ted Hicks | Project in V0 - No amendment required at this time | The estimate added in the original (2.28.2026)document only included one of the two segments within the project ($81M) one of the estimates was left out. Adding both segments, totals $144M however, the latest LPCE has not undergone 428/406 split therefore the percentage split used was the same split for the TL36100 project. | Project under new A&E & IFA design. The E&M split should be reviewed as the amounts are too low relative to the total project cost. | Luis Sepulveda | Pending Scope & Cost Completion by Applicant |  | Pending Scope & Cost Completion by Applicant | N/A | 5097248 | 69398.6 |  | 5166646.6 | 62592525.4 | 71272552.67 | 5820746.94 | 4233792.76 | 345260.6 | 28635.6 | 0 | 81700988.57 | 75534981.03 | 6166007.54 | Amendment – Amendment Needed/Pending Development | Q1 FY2027 | / | 1 | #VALUE!
668583 | FAASt Line 13300 GOAB 13301C to Hato Tejas Se | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 909002.34 | 5807.1 | 55062.25 | 2246.48 | 100526.19 | 18046.81 | 1090691.17 | 1064590.78 | 26100.39 | Y | Carlos Samalot | Amendment - Pending Development | This information reflects the latest LPCE data provided and includes the actuals delta. The final cost will be taken into consideration during the project reconciliation and close-out. | Project under PREPA review because of cost overrun | Jose A Cruz | Obligated | 2022-08-02 11:42 | Obligated | 91% | 280376.69 | 806314.48 |  | 1086691.17 | 303572.82 | 665239.4 | 2703.16 | 58708.55 | 918.24 | 51007.18 | 8541.82 | 787118.35 | 774955.13 | 12163.22 | Amendment – Submitted to COR3/PREPA | Submitted |  | #REF! | #VALUE!
751655 | FAASt [Vieques Microgrid] (Transmission) | Transmission | Vieques and Culebra Projects (6) | No | Pending Scope & Cost Completion by Applicant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 406083.4394 | 62593651.6797 | 51303.2161 | 9109976.8943 | 0 | 9746878.2781 | 81907893.5075 | 457386.6555 | 81450506.852 | 406083.4394 | 62593651.6797 | 51303.2161 | 9109976.8943 | 0 | 9746878.2781 | 81907893.5075 | 457386.6555 | 81450506.852 | Y | Janice Lopez | Not obligated - Increase in estimate that will be submitted to FEMA. | The expected total reflects the latest information from the discontinued RFP. | This estimate does not include the addition of a new substation to this project | Jose A Cruz | Pending Scope & Cost Completion by Applicant |  | Pending Scope & Cost Completion by Applicant | N/A | 662740.83 | 0 |  | 662740.83 | 11112821.5475 | 287219.87 | 55806508.56 | 15173.21 | 5897280.98 | 0 | 8788889.34 | 70795071.96 | 302393.08 | 70492678.88 | DSOW – Pending Design Package for Development | Q2 FY2027 | The DSOW Revision 2 for the Vieques and Culebra Microgrid was submitted in July 2025. After receiving various Requests for Information (RFIs) from FEMA related to the design, an internal decision was made to re-submit the DSOW once the 30% design is completed, providing more robust information to adequately address the agency’s requests. As of today, the DSOW is estimated to be re-submitted in October 2026 following the completion of the 60% design. | 1 | #VALUE!
673847 | FAASt [Distribution Pole and Conductor Repair-Carolina Group 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 924289.93 | 39481 | 37242 | 10462 | 0 | 0 | 1011474.93 | 961531.93 | 49943 | Y | Yaritza Acevedo Ortiz | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version. | Se espera que este proyecto tenga costos que sobrepasan la obligación por $733k. | Luis Sepulveda | Obligated | 2022-08-08 11:30 | Obligated | 78% | 192227.38 | 782333.98 |  | 974561.36 | 733719.93 | 190570 | 39481 | 37242 | 10468 | 0 | 0 | 277755 | 227812 | 49949 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
750151 | FAASt [Transmission Priority Pole Replacement Program Line 700 Costa Sur SP – Yauco 2 HP] (Transmission) | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 243268.16 | 9181.75 | 23495.1804 | 1041.06 | 16785.94 | 2341.06 | 296113.1504 | 283549.2804 | 12563.87 | N | Carlos Samalot | Amendment - Pending Development | Information represents the latest LPCE information provided. | No Comment | Jose Cruz | Obligated | 2026-01-16 16:15 | Obligated | 0% | 44406.69 | 309.53 |  | 44716.22 | -1479265.8096 | 1508927.85 | 9181.75 | 131787.84 | 648.92 | 107681.05 | 17151.55 | 1775378.96 | 1748396.74 | 26982.22 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | No Amendment Needed | #REF! | #VALUE!
742026 | FAASt [Pole and Conductor Repair - San Juan Group 2 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1740768.37 | 68617 | 83942.74 | 15418.96 | 0 | 0 | 1908747.07 | 1824711.11 | 84035.96 | Y | Yaritza Acevedo Ortiz | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version. | Se espera que este proyecto tenga costos que sobrepasan la obligación por $707k. | Luis Sepulveda | Obligated | 2024-05-31 11:36 | Obligated | 85% | 307412.33 | 1460594.04 |  | 1768006.37 | 707392.3 | 1033375.81 | 68618 | 83943 | 15418.96 | 0 | 0 | 1201354.77 | 1117318.81 | 84036.96 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
678985 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 4] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 735890.97 | 42939 | 66915 | 11378.84 | 0 | 0 | 857123.81 | 802805.97 | 54317.84 | Y | Yaritza Acevedo Ortiz | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version. | Se espera que este proyecto tenga costos que sobrepasan la obligación por $382k. | Luis Sepulveda | Obligated | 2022-12-27 11:53 | Obligated | 79% | 231240.45 | 582969.79 |  | 814210.24 | 382262.97 | 353628 | 42939 | 66915 | 11378.84 | 0 | 0 | 474860.84 | 420543 | 54317.84 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
711856 | FAASt [Pole and Conductor Repair - Bayamon Group 3 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 11304564.29 | 328412 | 891093.89 | 67251.43 | 0 | 0 | 12591321.61 | 12195658.18 | 395663.43 | Y | Yaritza Acevedo Ortiz | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version. | Se espera que este proyecto tenga costos que sobrepasan la obligación por $364k. | Luis Sepulveda | Obligated | 2024-08-26 10:08 | Obligated | 89% | 1268583.26 | 9051973.61 |  | 10320556.87 | 364243.27 | 10940320.91 | 328412 | 891094 | 67251.43 | 0 | 0 | 12227078.34 | 11831414.91 | 395663.43 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
708579 | FAASt [Pole and Conductor Repair - Ponce Group 16, 17, 18 & 19] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1976883.61 | 307856.04 | 343118.15 | 81581.8 | 0 | 0 | 2709439.6 | 2320001.76 | 389437.84 | Y | Yaritza Acevedo Ortiz | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version. | Se espera que este proyecto tenga costos que sobrepasan la obligación por $212k. | Luis Sepulveda | Obligated | 2023-10-23 11:32 | Obligated | 89% | 306154.73 | 2211544.17 |  | 2517698.9 | 212314.84 | 1764568.92 | 307856 | 343118 | 81581.84 | 0 | 0 | 2497124.76 | 2107686.92 | 389437.84 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
738120 | FAASt [Pole and Conductor Repair-Carolina Group 2- Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 11242486.77 | 234531 | 1159111 | 175368.81 | 0 | 0 | 12811497.58 | 12401597.77 | 409899.81 | Y | Yaritza Acevedo Ortiz | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version. | Se espera que este proyecto tenga costos que sobrepasan la obligación por $201k. | Luis Sepulveda | Obligated | 2024-11-25 16:15 | Obligated | 74% | 951515.73 | 9855303.54 |  | 10806819.27 | 201215.77 | 11041271 | 234531 | 1159111 | 175368.81 | 0 | 0 | 12610281.81 | 12200382 | 409899.81 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
691246 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 10] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 374263.26 | 26654 | 41363.6 | 7063.31 | 0 | 0 | 449344.17 | 415626.86 | 33717.31 | Y | Yaritza Acevedo Ortiz | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and proceed with the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, and any necessary cost adjustments will be incorporated into the final version. | No comment | Luis Sepulveda | Obligated | 2023-02-16 12:51 | Obligated | 88% | 91014.29 | 321416.31 |  | 412430.6 | 162640.1 | 211622.76 | 26654 | 41364 | 7063.31 | 0 | 0 | 286704.07 | 252986.76 | 33717.31 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
679026 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 5] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 784267.71 | 81250 | 93451 | 12630 | 0 | 0 | 971598.71 | 877718.71 | 93880 | Y | Yaritza Acevedo Ortiz | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version. | Se espera que este proyecto tenga costos que sobrepasan la obligación por $287k | Luis Sepulveda | Obligated | 2022-12-27 11:53 | Obligated | 78% | 120986.82 | 832611.89 |  | 953598.71 | 287851.71 | 483786 | 84198 | 93451 | 22312 | 0 | 0 | 683747 | 577237 | 106510 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
701679 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 12] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 168343.89 | 12827 | 12535.35 | 3399.16 | 0 | 0 | 197105.4 | 180879.24 | 16226.16 | Y | Yaritza Acevedo Ortiz | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version. | The 16k available from the number provided by the Capital Programs staff is enough to complete the 33% pending? | Luis Sepulveda | Obligated | 2023-03-02 12:24 | Obligated | 67% | 41673.73 | 155431.67 |  | 197105.4 | 103918.8 | 64425.44 | 12827 | 12535 | 3399.16 | 0 | 0 | 93186.6 | 76960.44 | 16226.16 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
682898 | FAASt [Distribution Pole and Conductor Repair - Bayamón Group 6] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 853881.22 | 82921.49 | 120284.25 | 12889.35 | 0 | 0 | 1069976.31 | 974165.47 | 95810.84 | Y | Yaritza Acevedo Ortiz | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version. | El proyecto tendrá un aumento de alrededor de $200K y no estan considerando una enmienda hasta closeout. Pendiente el split. |  | Obligated | 2023-01-24 13:14 | Obligated | 89% | 140664.37 | 908311.94 |  | 1048976.31 | 256694.03 | 635326.93 | 85929 | 120284 | 22771.19 | 0 | 0 | 813282.28 | 755610.93 | 108700.19 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
673818 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 1] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 674464.58 | 151265 | 121044 | 20349 | 0 | 0 | 967122.58 | 795508.58 | 171614 | Y | Yaritza Acevedo Ortiz | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version. | No Comment | Luis Sepulveda | Obligated | 2022-08-08 11:30 | Obligated | 87% | 165605.97 | 755603.04 |  | 921209.01 | 52660.58 | 621804 | 135633 | 121044 | 35951 | 0 | 0 | 914462 | 742848 | 171584 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
673839 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 69706.66 | 4609 | 10152 | 1221 | 0 | 0 | 85688.66 | 79858.66 | 5830 | Y | Yaritza Acevedo Ortiz | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. The scope was adjusted to address unforeseen site conditions, based on a high‑level assessment. The additional budget of $85,688.66 is to cover both overruns and outstanding activities. Project Class 3 estimate will be revised, any adjustments will be incorporated into the final amendment during closeout. | No Comment | Luis Sepulveda | Obligated | 2022-07-12 11:39 | Obligated | 100% | 47480.18 | 38208.48 |  | 85688.66 | 49237.66 | 20468 | 4609 | 10153 | 1221 | 0 | 0 | 36451 | 30621 | 5830 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
689071 | FAASt [Pole and Conductor Repair - Arecibo Group 11] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 106997.11 | 13827 | 11878.8 | 3664.16 | 0 | 0 | 136367.07 | 118875.91 | 17491.16 | Y | Yaritza Acevedo Ortiz | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version. | No comment | Luis Sepulveda | Obligated | 2023-03-02 12:24 | Obligated | 90% | 46699.71 | 86667.36 |  | 133367.07 | 47451.99 | 59545.08 | 13827 | 11879 | 3664 | 0 | 0 | 88915.08 | 71424.08 | 17491 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
705584 | FAASt [Distribution Pole and Conductor Repair - Ponce Groups 14 &amp;amp; 15] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1511604.39 | 299196 | 284698 | 79287 | 0 | 0 | 2174785.39 | 1796302.39 | 378483 | Y | Yaritza Acevedo Ortiz | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version. | No Comment | Luis Sepulveda | Obligated | 2023-06-16 12:55 | Obligated | 80% | 172615.86 | 1809515.27 |  | 1982131.13 | 47108.39 | 1464496 | 299196 | 284698 | 79287 | 0 | 0 | 2127677 | 1749194 | 378483 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
673838 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 329669.44 | 57917 | 55025 | 15348 | 0 | 0 | 457959.44 | 384694.44 | 73265 | Y | Yaritza Acevedo Ortiz | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version. | No Comment | Luis Sepulveda | Obligated | 2022-07-12 11:39 | Obligated | 85% | 138402.39 | 313557.05 |  | 451959.44 | 45321.44 | 284349 | 57917 | 55024 | 15348 | 0 | 0 | 412638 | 339373 | 73265 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
682870 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 6] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 115082.99 | 13827 | 16716.65 | 3664 | 0 | 0 | 149290.64 | 131799.64 | 17491 | Y | Yaritza Acevedo Ortiz | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version. | No comment | Luis Sepulveda | Obligated | 2022-12-27 11:53 | Obligated | 89% | 36653.1 | 109637.54 |  | 146290.64 | 29160.87 | 85921.77 | 13827 | 16717 | 3664 | 0 | 0 | 120129.77 | 102638.77 | 17491 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
686453 | FAASt [Pole and Conductor Repair - Mayagüez Group 7] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 39233.59 | 3949 | 4059 | 1046 | 0 | 0 | 48287.59 | 43292.59 | 4995 | Y | Yaritza Acevedo Ortiz | Amendment - Pending Development | Project is 100% executed, and QC has been fully completed. This project was obligated under a 428/406 based on a Class 3 estimate. Reconciliation of actual costs is currently in progress in order to initiate close out according to FEMA Guidelines. | No Comment | Luis Sepulveda | Obligated | 2022-12-27 11:53 | Obligated | 100% | 17941.39 | 30346.2 |  | 48287.59 | 18649.59 | 20584 | 3949 | 4059 | 1046 | 0 | 0 | 29638 | 24643 | 4995 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
688630 | FAASt [Pole and Conductor Repair - Mayagüez Group 12] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 59446.36 | 7898 | 8327.05 | 2092.97 | 0 | 0 | 77764.38 | 67773.41 | 9990.97 | Y | Yaritza Acevedo Ortiz | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version. | The project expenses cover 100% of the project's expected cost, and the project is at 50% of construction. | Luis Sepulveda | Obligated | 2023-03-08 12:36 | Obligated | 51% | 48673.98 | 29090.4 |  | 77764.38 | 16718 | 42728.41 | 7898 | 8327 | 2092.97 | 0 | 0 | 61046.38 | 51055.41 | 9990.97 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
710110 | FAASt [Distribution Pole and Conductor Repair - Bayamon Group 2 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 94998.5 | 2000 | 14756.12 | 478.06 | 0 | 0 | 112232.68 | 109754.62 | 2478.06 | Y | Yaritza Acevedo Ortiz | Amendment - Pending Development | Project is 100% executed, and QC has been fully completed. This project was obligated under a 428/406 based on a Class 3 estimate. Reconciliation of actual costs is currently in progress in order to initiate close out according to FEMA Guidelines. | No comment | Luis Sepulveda | Obligated | 2023-10-23 11:32 | Obligated | 100% | 24406.16 | 87826.52 |  | 112232.68 | 9701.88 | 85296.74 | 2000 | 14756 | 478.06 | 0 | 0 | 102530.8 | 100052.74 | 2478.06 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
701495 | FAASt [Pole and Conductor Repair - Mayagüez Group 14] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 20549.54 | 4609 | 3959.6 | 1221.39 | 0 | 0 | 30339.53 | 24509.14 | 5830.39 | Y | Yaritza Acevedo Ortiz | Amendment - Pending Development | Project is 100% executed, and QC has been fully completed. This project was obligated under a 428/406 based on a Class 3 estimate. Reconciliation of actual costs is currently in progress in order to initiate close out according to FEMA Guidelines. | No comment | Luis Sepulveda | Obligated | 2023-03-02 12:24 | Obligated | 100% | 13366.51 | 16973.02 |  | 30339.53 | 701.18 | 19848.36 | 4609 | 3959.6 | 1221.39 | 0 | 0 | 29638.35 | 23807.96 | 5830.39 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
673848 | FAASt [Distribution Pole and Conductor Repair-Carolina Group 3] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 139921 | 4443 | 13281 | 1177 | 0 | 0 | 158822 | 153202 | 5620 | Y | Yaritza Acevedo Ortiz | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version. | The project has only completed 56% of the Scope and has expended $130 K, and the presented cost by LUMA is $158K | Luis Sepulveda | Obligated | 2022-07-12 11:39 | Obligated | 56% | 42133.88 | 88774.55 |  | 130908.43 | -2289579.19 | 2046324.94 | 9000.11 | 182160.96 | 5677.18 | 145915.26 | 59322.74 | 2448401.19 | 2374401.16 | 74000.03 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
673795 | FAASt Distribution Pole and Conductor Repair - Mayaguez Group 4 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1615221.64 | 291663 | 278116 | 77291 | 0 | 0 | 2262291.64 | 1893337.64 | 368954 | Y | Yaritza Acevedo Ortiz | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version. | Se espera que este proyecto tenga costos que sobrepasan la obligación por $190k. | Luis Sepulveda | Obligated | 2022-08-02 11:42 | Obligated | 89% | 488162.33 | 1538561.48 |  | 2026723.81 | -8126669.6 | 8687329.99 | 35434.35 | 773151.6 | 23427.4 | 622940.21 | 246677.69 | 10388961.24 | 10083421.8 | 305539.44 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
674092 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 5] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 939116.74 | 71480 | 82578 | 18942 | 0 | 0 | 1112116.74 | 1021694.74 | 90422 | Y | Yaritza Acevedo Ortiz | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version. | Se espera que este proyecto tenga costos que sobrepasan la obligación por $497k. | Luis Sepulveda | Obligated | 2022-09-16 11:54 | Obligated | 78% | 156813.86 | 934302.88 |  | 1091116.74 | -8127564.81 | 7714746.94 | 2136.3 | 719754.49 | 1369.92 | 787627.58 | 14046.32 | 9239681.55 | 9222129.01 | 17552.54 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
673775 | FAASt [Distribution Pole and Conductor Repair - Mayaguez Group 3] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 5304271.78 | 777623 | 689888.45 | 79570.1 | 0 | 0 | 6851353.33 | 5994160.23 | 857193.1 | Y | Yaritza Acevedo Ortiz | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version. | Se espera que este proyecto tenga costos que sobrepasan la obligación por $1.7 millones. | Luis Sepulveda | Obligated | 2022-12-27 11:53 | Obligated | 89% | 990297.73 | 5471574.2 |  | 6461871.93 | -11660844.13 | 15534571.38 | 65783.22 | 1378411.7 | 41393.16 | 1059507.72 | 432530.28 | 18512197.46 | 17972490.8 | 539706.66 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
334329 | FAASt Distribution Pole and Conductor Repair - Ponce Group 2 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 342249.92 | 50699 | 25530 | 13435 | 0 | 0 | 431913.92 | 367779.92 | 64134 | Y | Yaritza Acevedo Ortiz | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version. | Se debe confirmar si con los aprox 12,000 se puede terminar el 13% que esta pendiente a completar. | Luis Sepulveda | Obligated | 2022-05-20 12:05 | Obligated | 87% | 99612.94 | 320300.98 |  | 419913.92 | -16134219.56 | 13767291.01 | 5248.03 | 1304890.11 | 3414.73 | 1450714.05 | 34575.55 | 16566133.48 | 16522895.17 | 43238.31 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
674088 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 3] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1502387.82 | 228975 | 267370 | 60678 | 0 | 0 | 2059410.82 | 1769757.82 | 289653 | Y | Yaritza Acevedo Ortiz | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version. | Se debe confirmar si con los aprox $9,000 se puede terminar el 12% que esta pendiente a completar. | Luis Sepulveda | Obligated | 2022-10-17 11:37 | Obligated | 88% | 293717.97 | 1756692.85 |  | 2050410.82 | -18629098.24 | 17238816.15 | 68279.82 | 1579773.97 | 43968.92 | 1309700 | 447970.2 | 20688509.06 | 20128290.12 | 560218.94 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
710099 | FAASt [Pole and Conductor Repair - Arecibo Group 1 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 7366388.46 | 153523.07 | 602047.2 | 42926.93 | 0 | 0 | 8164885.66 | 7968435.66 | 196450 | Y | Yaritza Acevedo Ortiz | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version. | Se espera que este proyecto tenga costos que sobrepasan la obligación por $619k |  | Obligated | 2025-01-07 23:15 | Obligated | 93% | 620432.5 | 6843231.06 |  | 7463663.56 | 619040.04 | 6704421.69 | 196450 | 602047 | 42926.93 | 0 | 0 | 7545845.62 | 7306468.69 | 239376.93 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
705527 | FAASt [Distribution Pole and Conductor Repair - San Juan 17-18-19-20-21] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 668853.23 | 98919 | 125147 | 26214 | 0 | 0 | 919133.23 | 794000.23 | 125133 | Y | Yaritza Acevedo Ortiz | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version. | The project has $800k in expenses, but the expected cost presented by the LUMA CP team is $200K | Luis Sepulveda | Obligated | 2023-07-28 11:42 | Obligated | 68% | 189871.91 | 612520.62 |  | 802392.53 | 26132.23 | 642721 | 98919 | 125147 | 26214 | 0 | 0 | 893001 | 767868 | 125133 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
165226 | FAASt [Feeders Vieques & Culebra] (Distribution) | Distribution | Vieques and Culebra Projects (6) | No | Pending PDMG Scope & Cost Routing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53655359.67 | 7910341.47 | 6294597.32 | 1006025.84 | 3171076.36 | 1176186.58 | 73213587.24 | 63121033.35 | 10092553.89 | 53655359.67 | 7910341.47 | 6294597.32 | 1006025.84 | 3171076.36 | 1176186.58 | 73213587.24 | 63121033.35 | 10092553.89 | Y | Jorge Lopez Burgos | Project in V0 - No amendment required at this time | The project estimate was based on a Class 3. Project under FEMA evaluation | Verificar los costos totales presentados en 406, (Columna Z) ya que duplica los costos incluidos en la revisión del estimado preparado para la enmienda | Amaury Pacheco | Pending PDMG Scope & Cost Routing |  | Pending PDMG Scope & Cost Routing | N/A | 4889996.11 | 750935.94 |  | 5640932.05 | -398359.08 | 53571610.15 | 8023162.98 | 6288308.87 | 1016034.08 | 3512487.97 | 1200342.27 | 73611946.32 | 63372406.99 | 10239539.33 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | DSOW was sent 2/16/2026 | 1 | #VALUE!
688109 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 11] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 448719.06 | 90680 | 87443.55 | 24030.2 | 0 | 0 | 650872.81 | 536162.61 | 114710.2 | N | Yaritza Acevedo Ortiz | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase. | No Comment | Luis Sepulveda | Obligated | 2023-03-08 12:36 | Obligated | 89% | 143571.39 | 448624.17 |  | 592195.56 | 108879.36 | 448719.06 | 90680 | 87444 | 24030.2 | 0 | 0 | 541993.45 | 536163.06 | 114710.2 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
686480 | FAASt [Pole and Conductor Repair - Ponce Group 7] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 523404 | 85891 | 101359 | 22761 | 0 | 0 | 733415 | 624763 | 108652 | N | Yaritza Acevedo Ortiz | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase. | No comment | Luis Sepulveda | Obligated | 2023-02-16 12:51 | Obligated | 87% | 111962.35 | 447630.76 |  | 559593.11 | 93666 | 523404 | 85891 | 101359 | 22761 | 0 | 0 | 639749 | 624763 | 108652 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
701552 | FAASt [Pole and Conductor Repair - Ponce Group 12] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 186321 | 40981 | 36670 | 10860 | 0 | 0 | 274832 | 222991 | 51841 | N | Yaritza Acevedo Ortiz | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase. | No comment | Luis Sepulveda | Obligated | 2023-03-08 12:36 | Obligated | 90% | 89899.68 | 162935.82 |  | 252835.5 | 34349.84 | 186321 | 40981 | 36670 | 10860 | 0 | 0 | 240482.16 | 222991 | 51841 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
714641 | FAASt [Rincón Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 10842339.26 | 82026.55 | 1946225.97 | 106422.03 | 750618 | 506022 | 14233653.81 | 13539183.23 | 694470.58 | N | Mariano Perez | Obligated - No amendment need Identified | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at: 0.00%/0 locations completed. | The 406 A&E cost estimate was not included. | Luis Sepulveda | Obligated | 2026-03-01 18:15 | Obligated | N/A | 431237.39 | 307.56 |  | 431544.95 | -575351.95 | 10915553.24 | 588048.55 | 1928249.61 | 106422.03 | 753614 | 0 | 14809005.76 | 13597416.85 | 694470.58 | DSOW – Submitted to FEMA | Q4 FY2027 | Pending Homeland Security for final signature and start construction Grants portal total project cost is $14.2M | #REF! | #VALUE!
682882 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 11] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 545661.24 | 89627 | 104353.35 | 23751.16 | 0 | 0 | 763392.75 | 650014.59 | 113378.16 | N | Yaritza Acevedo Ortiz | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase. | No comment | Luis Sepulveda | Obligated | 2023-01-10 13:19 | Obligated | 85% | 74890.91 | 572134.2 |  | 647025.11 | 0.51 | 545661.24 | 89627 | 104353 | 23751.16 | 0 | 0 | 763392.24 | 650014.24 | 113378.16 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
704849 | FAASt [Naguabo Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 11620676.42 | 1182070.57 | 2380242.99 | 487666.4 | 0 | 0 | 15670656.38 | 14000919.41 | 1669736.97 | N | Mariano Perez | Amendment - Pending Development | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at: 72.69%/2661 locations completed. | El proyecto presenta un aumento de la entrega al PREB de $4 millones, pero es el mismo número de la obligación. | Luis Sepulveda | Obligated | 2024-05-10 10:17 | Obligated | 67% | 929157.85 | 7176923.51 |  | 8106081.36 | 4797962.38 | 7240724 | 1182070.57 | 1925642 | 487666.4 | 0 | 0 | 10872694 | 9166366 | 1669736.97 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
682178 | FAASt [Pole and Conductor Repair - Arecibo Group 7] (Distribution ) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 208544.25 | 42487 | 40949.45 | 11259.06 | 0 | 0 | 303239.76 | 249493.7 | 53746.06 | N | Yaritza Acevedo Ortiz | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase. | No Comment | Luis Sepulveda | Obligated | 2023-01-31 12:56 | Obligated | 80% | 92258.39 | 144000.36 |  | 236258.75 | 0.45 | 208544.25 | 42487 | 40949 | 11259.06 | 0 | 0 | 303239.31 | 249493.25 | 53746.06 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
710094 | FAASt [Pole and Conductor Repair - Bayamon Group 1 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 7096249.5 | 165571 | 614123.07 | 29565.32 | 0 | 0 | 7905508.89 | 7710372.57 | 195136.32 | N | Yaritza Acevedo Ortiz | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase. | No Comment | Luis Sepulveda | Obligated | 2024-11-01 15:15 | Obligated | 71% | 482312.1 | 5390539.06 |  | 5872851.16 | 0.07 | 7096249.5 | 165571 | 614123 | 29565.32 | 0 | 0 | 7905508.82 | 7710372.5 | 195136.32 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
738672 | FAASt [Pole and Conductor Repair - Mayaguez Group 1 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 10313627 | 243129 | 834793 | 63002.37 | 0 | 0 | 11454551.37 | 11148420 | 306131.37 | N | Yaritza Acevedo Ortiz | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase. | Confirm if the $1.8 Million available are enough to complete the 30% of the project that is pending to be completed. | Luis Sepulveda | Obligated | 2024-11-25 16:15 | Obligated | 70% | 871847.36 | 8387939.78 |  | 9259787.14 | 0 | 10313627 | 243128.63 | 834793 | 63002.37 | 0 | 0 | 11454551.37 | 11148420 | 306131 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
550896 | FAASt Line 6700 Martin Peña TC to Villamar Se | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1322875.5755 | 5312.0445 | 86031.6501 | 1203.8499 | 159132.66 | 10982.34 | 1585538.12 | 1568039.8856 | 17498.2344 | Y | Carlos Samalot | Amendment - Pending Development | This information reflects the latest LPCE data provided and includes the actuals delta. The final cost will be taken into consideration during the project reconciliation and close-out. | $4k is enough to complete the 10% pending. | Luis Sepulveda | Pending PDMG Scope & Cost Routing | 2022-08-08 11:30 | Obligated, Pending PDMG Scope & Cost Routing | 90% | 424746.39 | 1156791.73 |  | 1581538.12 | -705318.18 | 1923721.17 | 13772.66 | 166749.56 | 1956.97 | 173673.6 | 10982.34 | 2290856.3 | 2264144.33 | 26711.97 | Amendment – Submitted to FEMA | Submitted |  | #REF! | #VALUE!
704916 | FAASt [Pole and Conductor Repair - Arecibo Group 13-14-15-16] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 273996 | 23695 | 49755 | 6279 | 0 | 0 | 353725 | 323751 | 29974 | N | Yaritza Acevedo Ortiz | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase. | Confirm if the $18K available are enough to complete the 20% of the project that is pending to be completed. | Luis Sepulveda | Obligated | 2023-04-06 11:12 | Obligated | 80% | 117941.21 | 218856.76 |  | 336797.97 | 0 | 273996 | 23695 | 49755 | 6279 | 0 | 0 | 353725 | 323751 | 29974 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
704933 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 13-14-15-16] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1201420 | 177653 | 231255 | 47078 | 0 | 0 | 1657406 | 1432675 | 224731 | N | Yaritza Acevedo Ortiz | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase. | Confirm if the $400K available are enough to complete the 50% of the project that is pending to be completed. | Luis Sepulveda | Obligated | 2023-08-04 19:29 | Obligated | 50% | 240917.35 | 1007597.88 |  | 1248515.23 | 0 | 1201420 | 177653 | 231255 | 47078 | 0 | 0 | 1657406 | 1432675 | 224731 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
674072 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 1] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 872891 | 188302.7 | 171585 | 49900.3 | 0 | 0 | 1282679 | 1044476 | 238203 | N | Yaritza Acevedo Ortiz | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase. | No Comment | Luis Sepulveda | Obligated | 2022-09-16 11:54 | Obligated | 88% | 215800.09 | 1030475.62 |  | 1246275.71 | 0 | 872891 | 188303 | 171585 | 49900.3 | 0 | 0 | 1282679 | 1044476 | 238203.3 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
701545 | FAASt [Pole and Conductor Repair - Ponce Group 11] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 487190 | 102007 | 95198 | 27032 | 0 | 0 | 711427 | 582388 | 129039 | N | Yaritza Acevedo Ortiz | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase. | No Comment | Luis Sepulveda | Obligated | 2023-03-08 12:36 | Obligated | 84% | 149557.2 | 363038.03 |  | 512595.23 | 0 | 487190 | 102007 | 95198 | 27032 | 0 | 0 | 711427 | 582388 | 129039 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
708637 | FAASt T-Pole Program Line 3700] (Transmission) | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1367810.2561 | 38822.55 | 41458.8653 | 5793.0785 | 35983.6407 | 6521.5294 | 1496389.92 | 1445252.7621 | 51137.1579 | Y | Carlos Samalot | Amendment - Pending Development | This information reflects the latest LPCE data provided and includes the actuals delta. The final cost will be taken into consideration during the project reconciliation and close-out. | El proyecto aumentó en $1 millón, pero mencionan que no se necesita enmienda hasta el closeout. | Luis Sepulveda | Obligated | 2024-08-26 10:08 | Obligated | 90% | 662482.32 | 830133.34 |  | 1492615.66 | 1141737.82 | 255862.85 | 38293.66 | 30158.85 | 4783.59 | 20073.47 | 5479.68 | 354652.1 | 306095.17 | 48556.93 | Obligated -No expected changes | N/A | No Amendment Needed | #REF! | #VALUE!
712980 | FAASt [T-Pole Program Line 3000] (Transmission) | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1609934.104 | 43793.7069 | 46767.5976 | 6534.8717 | 40591.2804 | 7356.5994 | 1754978.16 | 1697292.9821 | 57685.1779 | Y | Carlos Samalot | Amendment - Pending Development | This information reflects the latest LPCE data provided and includes the actuals delta. The final cost will be taken into consideration during the project reconciliation and close-out. | El proyecto aumentó en $1 millón, pero mencionan que no se necesita enmienda hasta el closeout. | Luis Sepulveda | Obligated | 2024-11-01 15:15 | Obligated | 77% | 1072412.88 | 701044.83 |  | 1773457.71 | 1426337.86 | 232028.81 | 37424.09 | 28581 | 4483.52 | 23456.66 | 2666.22 | 328640.3 | 284066.47 | 44573.83 | Obligated -No expected changes | N/A | No Amendment Needed | #REF! | #VALUE!
701555 | FAASt [Pole and Conductor Repair - Ponce Group 13] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 547010 | 80962 | 104535 | 21455 | 0 | 0 | 753962 | 651545 | 102417 | N | Yaritza Acevedo Ortiz | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase. | No Comment | Luis Sepulveda | Obligated | 2023-03-08 12:36 | Obligated | 89% | 100054.87 | 383909 |  | 483963.87 | 0 | 547010 | 80962 | 104535 | 21455 | 0 | 0 | 753962 | 651545 | 102417 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
704751 | FAASt Distribution Pole and Conductor Repair - Bayamon Group 11 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 338491 | 76424 | 66168 | 20252 | 0 | 0 | 501335 | 404659 | 96676 | N | Yaritza Acevedo Ortiz | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase. | No Comment | Luis Sepulveda | Obligated | 2023-04-06 11:12 | Obligated | 91% | 174293.41 | 254644.93 |  | 428938.34 | 0 | 338491 | 76424 | 66168 | 20252 | 0 | 0 | 501335 | 404659 | 96676 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
679149 | FAASt Distribution Pole and Conductor Repair - Mayagüez Group 5 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 129744 | 21694 | 25191 | 5749 | 0 | 0 | 182378 | 154935 | 27443 | N | Yaritza Acevedo Ortiz | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase. | No Comment | Luis Sepulveda | Obligated | 2022-12-27 11:53 | Obligated | 88% | 42313.07 | 64876.23 |  | 107189.3 | 0 | 129744 | 21694 | 25191 | 5749 | 0 | 0 | 182378 | 154935 | 27443 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
688627 | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 9] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 303774 | 57066 | 58918 | 15122.49 | 0 | 0 | 434880.49 | 362692 | 72188.49 | N | Yaritza Acevedo Ortiz | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase. | No Comment | Luis Sepulveda | Obligated | 2023-01-31 12:56 | Obligated | 84% | 45814.58 | 163661.74 |  | 209476.32 | 0 | 303774 | 72188.49 | 58918 | 0 | 0 | 0 | 434880.49 | 362692 | 72188.49 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
547251 | FAASt Line 2400 Dos Bocas HP to America Apparel (Transmission) | Transmission | Transmission Line Rebuild | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 41036495.65 | 5812385.04 | 3399766.76 | 535704.77 | 7682133.79 | 343803.19 | 58810289.2 | 52118396.2 | 6691893 | Y | Jan Lopez | Amendment - Pending Development | The information reflects the latest LPCE data provided. The cost currently includes the full line rebuild A&E design cost, under 428. This will be corrected through the obligation amendment. | No comment | Luis Sepulveda | Obligated | 2026-02-20 19:15 | Obligated | 0% | 2648451.06 | 35575.61 |  | 2684026.67 | 8567202.83 | 36790729.34 | 2900981.23 | 3092708.78 | 618690.18 | 1982784.48 | 4857192.36 | 50243086.37 | 41866222.6 | 8376863.77 | Amendment – Amendment Needed/Pending Development | Q4 FY2026 | Pending obligation, latest estimate is $54.5M | #REF! | #VALUE!
704844 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 16-17-18-19-20] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 320740 | 70006 | 62490 | 18552 | 0 | 0 | 471788 | 383230 | 88558 | N | Yaritza Acevedo Ortiz | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase. | No Comment | Luis Sepulveda | Obligated | 2023-05-17 11:31 | Obligated | 86% | 94560.77 | 238358.7 |  | 332919.47 | 0 | 320740 | 70006 | 62490 | 18552 | 0 | 0 | 471788 | 383230 | 88558 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
180052 | FAASt Ponce TC to Salinas Urbano TC- 38kV 100 & 200 (Transmission) | Priority Transmission | Transmission Line Rebuild | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 189214147.25 | 38650198.93 | 18683215.39 | 6899520.54 | 21880052.02 | 41872865.87 | 317200000 | 229777414.66 | 87422585.34 | Y | Jose Santos | Amendment - Pending Development | Currently undergoing redesign with updated scope, latest estimate refelcts $317M. The scope will be reconfigured to go from a double circuit (100 & 200) to a single circuit with a higher capacity | In Monday's meeting Rinly stated that this project's total cost was going to be around $200 mllion. The team included a $300 million estimate. | Luis Sepulveda | Obligated | 2025-11-05 16:17 | Obligated | 0% | 5683411.48 | 71911.84 |  | 5755323.32 | 0 | 189214147.25 | 38650198.93 | 18683215.39 | 6899520.54 | 21880052.02 | 41872865.87 | 317200000 | 229777414.66 | 87422585.34 | Amendment – Scope and Cost development in progress | Q4 FY2026 | Currently undergoing redesign with updated scope | #REF! | #VALUE!
679033 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 9] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 729040 | 142215 | 140628 | 37687 | 0 | 0 | 1049570 | 869668 | 179902 | N | Yaritza Acevedo Ortiz | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase. | No Comment | Luis Sepulveda | Obligated | 2022-12-27 11:53 | Obligated | 89% | 78826.32 | 834139.58 |  | 912965.9 | 0 | 729040 | 142215 | 140628 | 37687 | 0 | 0 | 1049570 | 869668 | 179902 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
679457 | FAASt [Distribution Pole and Conductor Repair - Ponce Group 3] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 589335 | 123232 | 115386 | 33921 | 0 | 0 | 861874 | 704721 | 157153 | N | Yaritza Acevedo Ortiz | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase. | No Comment | Luis Sepulveda | Obligated | 2022-12-27 11:53 | Obligated | 86% | 106213.98 | 540665.14 |  | 646879.12 | 0 | 589335 | 123232 | 115386 | 33921 | 0 | 0 | 861874 | 704721 | 157153 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
688629 | FAASt [Pole and Conductor Repair - Mayagüez Group 13] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 106941.99 | 22045 | 20833.9 | 5841.93 | 0 | 0 | 155662.82 | 127775.89 | 27886.93 | N | Yaritza Acevedo Ortiz | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase. | No Comment | Luis Sepulveda | Obligated | 2023-03-08 12:36 | Obligated | 89% | 46185.11 | 53225.75 |  | 99410.86 | -0.1 | 106941.99 | 22045 | 20834 | 5841.93 | 0 | 0 | 155662.92 | 127775.99 | 27886.93 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
688625 | FAASt [Pole and Conductor Repair - Ponce Group 10] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 710014.69 | 151206 | 139357.85 | 40069.59 | 0 | 0 | 1040648.13 | 849372.54 | 191275.59 | N | Yaritza Acevedo Ortiz | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase. | No Comment | Luis Sepulveda | Obligated | 2023-03-20 11:45 | Obligated | 87% | 130618.07 | 416996.8 |  | 547614.87 | -0.15 | 710014.69 | 151206 | 139358 | 40069.59 | 0 | 0 | 1040648.28 | 849372.69 | 191275.59 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
688198 | FAASt [Pole and Conductor Repair - Arecibo Group 10] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 60838.48 | 12667 | 12052.8 | 3356.76 | 0 | 0 | 88915.04 | 72891.28 | 16023.76 | N | Yaritza Acevedo Ortiz | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase. | The $4k available are enough to complete the 15% that is pending? | Luis Sepulveda | Obligated | 2023-03-20 11:45 | Obligated | 85% | 32133.66 | 52234.74 |  | 84368.4 | -0.2 | 60838.48 | 12667 | 12053 | 3356.76 | 0 | 0 | 88915.24 | 72891.48 | 16023.76 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
742070 | FAASt [Pole and Conductor Repair - San Juan Group 1 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 5461200.05 | 170555 | 491326.68 | 35032.38 | 0 | 0 | 6158114.11 | 5952526.73 | 205587.38 | N | Yaritza Acevedo Ortiz | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase. | No Comment | Luis Sepulveda | Obligated | 2024-06-18 11:28 | Obligated | 85% | 835781.06 | 4520957.11 |  | 5356738.17 | -0.32 | 5461200.05 | 170555 | 491327 | 35032.38 | 0 | 0 | 6158114.43 | 5952527.05 | 205587.38 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
711888 | FAASt [Pole and Conductor Repair - Caguas Group 1 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 5425810.57 | 132877 | 434784.65 | 33026.3 | 0 | 0 | 6026498.52 | 5860595.22 | 165903.3 | N | Yaritza Acevedo Ortiz | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase. | No Comment | Luis Sepulveda | Obligated | 2024-03-22 10:16 | Obligated | 92% | 389419.46 | 4757697.68 |  | 5147117.14 | -0.35 | 5425810.57 | 132877 | 434785 | 33026 | 0 | 0 | 6026498.87 | 5860595.57 | 165903 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
738670 | FAASt [Pole and Conductor Repair - Ponce Group 1 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 4926640 | 116500.11 | 439974.62 | 31370.9 | 0 | 0 | 5514485.63 | 5366614.62 | 147871.01 | N | Yaritza Acevedo Ortiz | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase. | No Comment | Luis Sepulveda | Obligated | 2024-11-25 16:15 | Obligated | 94% | 661280.6 | 3322915 |  | 3984195.6 | -0.38 | 4926640.11 | 116500.1 | 439975 | 31370.9 | 0 | 0 | 5514486.01 | 5366615.11 | 147871 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
688472 | FAASt [Pole and Conductor Repair - Mayaguez Group 11] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 164908.86 | 11846.54 | 29921.55 | 3139.46 | 0 | 0 | 209816.41 | 194830.41 | 14986 | N | Yaritza Acevedo Ortiz | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase. | No Comment | Luis Sepulveda | Obligated | 2023-02-16 12:51 | Obligated | 85% | 40704.72 | 89649.92 |  | 130354.64 | -0.45 | 164908.86 | 11847 | 29922 | 3139.46 | 0 | 0 | 209816.86 | 194830.86 | 14986.46 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
679153 | FAASt Distribution Pole and Conductor Repair - Mayagüez Group 6 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 163846.51 | 40583 | 31068.05 | 10754.5 | 0 | 0 | 246252.06 | 194914.56 | 51337.5 | N | Yaritza Acevedo Ortiz | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase. | No Comment | Luis Sepulveda | Obligated | 2022-12-27 11:53 | Obligated | 88% | 41229.48 | 97985.99 |  | 139215.47 | -105815.45 | 163846.51 | 40583 | 31068 | 10754.5 | 0 | 0 | 352067.51 | 194914.51 | 51337.5 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
334527 | FAASt [Distribution Pole and Conductor Repair – Caguas Group 8 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 108847 | 12431 | 8540 | 2443 | 0 | 0 | 132261 | 117387 | 14874 | N | Yaritza Acevedo Ortiz | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase. | No comment | Luis Sepulveda | Obligated | 2022-06-10 11:48 | Obligated | 97% | 50102.81 | 44077.66 |  | 94180.47 | -2369522.29 | 2083897.82 | 821.8 | 197576.9 | 535.27 | 213549.07 | 5402.43 | 2501783.29 | 2495023.79 | 6759.5 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
679127 | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 3] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 171152.23 | 36372 | 33340.3 | 9638.58 | 0 | 0 | 250503.11 | 204492.53 | 46010.58 | N | Yaritza Acevedo Ortiz | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase. | No comment | Luis Sepulveda | Obligated | 2022-12-27 11:53 | Obligated | 88% | 52521.43 | 125072.43 |  | 177593.86 | -2826160 | 2569486.15 | 1816.46 | 240897.11 | 1170.09 | 251407.95 | 11885.35 | 3076663.11 | 3061791.21 | 14871.9 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
673772 | FAASt [Distribution Pole and Conductor Repair - Mayagüez Group 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 3286536 | 660857 | 636837 | 175127 | 0 | 0 | 4759357 | 3923373 | 835984 | N | Yaritza Acevedo Ortiz | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase. | No comment | Luis Sepulveda | Obligated | 2022-10-24 11:36 | Obligated | 83% | 542710.83 | 3111666.29 |  | 3654377.12 | -4195457.95 | 7474369.54 | 3899.16 | 696566.78 | 2495.46 | 751912.5 | 25571.51 | 8954814.95 | 8922848.82 | 31966.13 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
334488 | FAASt [Distribution Pole and Conductor Repair – Caguas Group 4 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 142917 | 9779 | 11465 | 1047 | 0 | 0 | 165208 | 154382 | 10826 | N | Yaritza Acevedo Ortiz | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase. | No comment | Amaury Pacheco | Obligated | 2022-05-26 11:24 | Obligated | 88% | -65994.48 | 126934.57 |  | 60940.09 | -4485668.32 | 3882564.66 | 6767.3 | 361458.25 | 1409.37 | 388789.38 | 9887.36 | 4650876.32 | 4632812.29 | 18064.03 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
334323 | FAASt Distribution Pole and Conductor Repair - Ponce Group 1 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 323692 | 54648 | 26179 | 14482 | 0 | 0 | 419001 | 349871 | 69130 | N | Yaritza Acevedo Ortiz | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase. | The project has additional funds expended beyond the cost included by the LUMA Capital Programs team. | Luis Sepulveda | Obligated | 2022-05-26 11:24 | Obligated | 91% | 265264.51 | 184969.79 |  | 450234.3 | -5046395 | 4099047 | 437231.68 | 273269.8 | 109307.92 | 273269.8 | 273269.8 | 5465396 | 4645586.6 | 819809.4 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
542762 | FAASt Distribution Pole and Conductor Repair – Arecibo Group 2 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 610448 | 146428 | 50794 | 10992 | 0 | 0 | 818662 | 661242 | 157420 | N | Yaritza Acevedo Ortiz | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase. | No comment | Amaury Pacheco | Obligated | 2022-06-03 11:23 | Obligated | 97% | 140629.4 | 329617.6 |  | 470247 | -5827066 | 4984296 | 531658.24 | 332286.4 | 132914.56 | 332286.4 | 332286.4 | 6645728 | 5648868.8 | 996859.2 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
674098 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 7] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 84433 | 20556 | 16517 | 2766 | 0 | 0 | 124272 | 100950 | 23322 | N | Yaritza Acevedo Ortiz | Obligated - Final Ammendment Version once closeout stage | Project is 100% executed, and QC has been fully completed. This project was obligated under a 428/406 based on a Class 3 estimate. Reconciliation of actual costs is currently in progress in order to initiate close out according to FEMA Guidelines. | No comment | Amaury Pacheco | Obligated | 2022-08-08 11:30 | Obligated | 100% | 20781.84 | 98678.17 |  | 119460.01 | -6633339.3 | 5641956.19 | 3297.53 | 528429.47 | 2122.11 | 560196.28 | 21609.72 | 6757611.3 | 6730581.94 | 27029.36 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
674096 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 6] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1773428 | 252057 | 332705 | 66795 | 0 | 0 | 2424985 | 2106133 | 318852 | N | Yaritza Acevedo Ortiz | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase. | The new cost provided is the same as the obligated cost. This reflects a reduction in what was presented to PREB in the last report. The incurred cost is under the provided cost, with 88% of the construction. The provided cost is allowing 9% of the total cost to perform the pending 12%. | Chantee Santana | Obligated | 2022-10-17 11:37 | Obligated | 88% | 323173.77 | 1878900.17 |  | 2202073.94 | -6649206.29 | 7579644.48 | 2302.03 | 706904.78 | 1475.8 | 768737.4 | 15126.8 | 9074191.29 | 9055286.66 | 18904.63 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
698511 | FAASt [Culebra Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1155804 | 91406 | 476440 | 62197 | 0 | 0 | 1785847 | 1632244 | 153603 | N | Mariano Perez | Amendment - Pending Development | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at: 78.02%/323 locations completed. | The 406 A&E cost estimate was not included. | Luis Sepulveda | Obligated | 2024-04-12 11:19 | Obligated | 83% | 184307.82 | 1050819.19 |  | 1235127.01 | 1 | 1155804 | 91406 | 476439 | 62197 | 0 | 0 | 1785846 | 1632243 | 153603 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
724938 | FAASt [Vega Alta Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 12445015.33 | 1331810.63 | 2459742.66 | 537278.89 | 0 | 0 | 16773847.51 | 14904757.99 | 1869089.52 | N | Mariano Perez | Amendment - Pending Development | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at: 61.03%/2401 locations completed. | The 406 A&E cost estimate was not included. | Luis Sepulveda | Obligated | 2024-05-10 10:17 | Obligated | 59% | 702385.01 | 8047337.5 |  | 8749722.51 | 0.51 | 12445015 | 1331811.11 | 2459743 | 537278.89 | 0 | 0 | 16773847 | 14904758 | 1869090 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
704927 | FAASt [Añasco Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 12087876.17 | 1294052.66 | 2420466.41 | 526309.26 | 0 | 0 | 16328704.5 | 14508342.58 | 1820361.92 | N | Mariano Perez | Amendment - Pending Development | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at: 89.01%/3354 locations completed. | The 406 A&E cost estimate was not included. | Luis Sepulveda | Obligated | 2024-07-08 11:28 | Obligated | 90% | 2051793.69 | 8786988.61 |  | 10838782.3 | 0.41 | 12087876.17 | 1294052.66 | 2420466 | 526309.26 | 0 | 0 | 16328704.09 | 14508342.17 | 1820361.92 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
704921 | FAASt [Barranquitas Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 9430329.22 | 1104151.73 | 2048083.31 | 472894.36 | 0 | 0 | 13055458.62 | 11478412.53 | 1577046.09 | N | Mariano Perez | Amendment - Pending Development | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at: 66.99%/1727 locations completed. | The 406 A&E cost estimate was not included. | Luis Sepulveda | Obligated | 2024-05-31 11:36 | Obligated | 65% | 563958.34 | 6064286.85 |  | 6628245.19 | 0.31 | 9430329.22 | 1104151.73 | 2048083 | 472894.36 | 0 | 0 | 13055458.31 | 11478412.22 | 1577046.09 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
698458 | FAASt [Distribution Streetlighting - Guaynabo] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 9762754.59 | 605024.35 | 1979750.26 | 248032.07 | 0 | 0 | 12595561.27 | 11742504.85 | 853056.42 | N | Mariano Perez | Amendment - Pending Development | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at: 77.27%/2237 locations completed. | The 406 A&E cost estimate was not included. | Luis Sepulveda | Obligated | 2023-11-03 11:30 | Obligated | 77% | 1027559.99 | 5201107.12 |  | 6228667.11 | 0.26 | 9762754.59 | 605024.35 | 1979750 | 248032.07 | 0 | 0 | 12595561.01 | 11742504.59 | 853056.42 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
724703 | FAASt [Arroyo Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 5314332 | 489465.16 | 1504203.15 | 250928.85 | 0 | 0 | 7558929.16 | 6818535.15 | 740394.01 | N | Mariano Perez | Amendment - Pending Development | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at: 76.83%/1502 locations completed. | The 406 A&E cost estimate was not included. | Luis Sepulveda | Obligated | 2024-06-18 11:28 | Obligated | 60% | 444120.48 | 3773474.62 |  | 4217595.1 | 0.15 | 5314332 | 489465.16 | 1504203 | 250928.85 | 0 | 0 | 7558929.01 | 6818535 | 740394.01 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
679780 | FAASt [Distribution Streetlighting - Bayamon] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 20710527 | 871692 | 3212958 | 304684 | 0 | 0 | 25099861 | 23923485 | 1176376 | N | Mariano Perez | Amendment - Pending Development | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at: 76.90%/5076 locations completed. | The 406 A&E cost estimate was not included. | Luis Sepulveda | Obligated | 2023-11-03 11:30 | Obligated | 78% | 1082061.52 | 6687522.88 |  | 7769584.4 | 0 | 20710527 | 1176376 | 3212958 | 0 | 0 | 0 | 25099861 | 23923485 | 1176376 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
698439 | FAASt Streetlight - Las Marías (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 7073217 | 888414 | 1653390 | 399291 | 0 | 0 | 10014312 | 8726607 | 1287705 | N | Mariano Perez | Amendment - Pending Development | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at: 51.97%/898 locations completed. | The 406 A&E cost estimate was not included. | Luis Sepulveda | Obligated | 2023-11-03 11:30 | Obligated | 53% | 1344027.4 | 2142717.62 |  | 3486745.02 | 0 | 7073217 | 1287705 | 1653390 | 0 | 0 | 0 | 10014312 | 8726607 | 1287705 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
678793 | FAASt [Streetlighting - Mayagüez] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 11019180.1 | 954580.45 | 2291581 | 397623.91 | 0 | 0 | 14662965.46 | 13310761.1 | 1352204.36 | N | Mariano Perez | Amendment - Pending Development | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at: 56.86%/1723 locations completed. | The 406 A&E cost estimate was not included. | Luis Sepulveda | Obligated | 2023-11-03 11:30 | Obligated | 55% | 1413781.37 | 3675869.91 |  | 5089651.28 | 0 | 11019180.1 | 1352204.36 | 2291581 | 0 | 0 | 0 | 14662965.46 | 13310761.1 | 1352204.36 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
701472 | FAASt [Comerio Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 6538769.44 | 585944.46 | 1640383 | 276181.29 | 0 | 0 | 9041278.19 | 8179152.44 | 862125.75 | N | Mariano Perez | Amendment - Pending Development | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at: 82.75%/1382 locations completed. | The 406 A&E cost estimate was not included. | Luis Sepulveda | Obligated | 2024-05-10 10:17 | Obligated | 83% | 356061.79 | 4266182.31 |  | 4622244.1 | 0 | 6538769.44 | 862125.75 | 1640383 | 0 | 0 | 0 | 9041278.19 | 8179152.44 | 862125.75 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
659715 | FAASt Distribution Streetlighting - Aibonito | Distribution | Distribution Streetlighting | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 5738710 | 137843.3353 | 1197087 | 52403.6647 | 0 | 0 | 7126044 | 6935797 | 190247 | Y | Mariano Perez | Amendment - Pending Development | This project was among the first to be developed, originally including the underground work as part of the program's initial scope—estimated at: $2M for this portion to be removed. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at: 89.62%/2496 locations completed.Estimate ammedment submission Q1FY27. | The 406 A&E cost estimate was not included. | Luis Sepulveda | Obligated | 2022-12-27 11:53 | Obligated | 91% | 771300.47 | 5466320.32 |  | 6237620.79 | -2008113.9756 | 7074498.4202 | 129540 | 1880872.5823 | 49247 | 0 | 0 | 9134157.9756 | 8955371.0025 | 178787 | Amendment – Amendment Needed/Pending Development | Q2 FY2027 | Amendment pending to remove underground scope | #REF! | #VALUE!
660239 | FAASt Streetlighting - Villalba (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 12489008.47 | 607135.3755 | 1810409 | 85900.6245 | 0 | 0 | 14992453.47 | 14299417.47 | 693036 | Y | Mariano Perez | Amendment - Pending Development | This project is currently over budget because the work assigned, based on vendor rates, exceeded the Class 3 estimate. Based on a high‑level evaluation, the work that can be executed within the remaining budget is estimated to be approximately $2,195,079.47 to cover both overruns and pending work (Added to 428 Child for FFO review). This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at: 90.60%/3065 locations completed. | The project costs incurred are over the costs included by the Capital Programs team. The 406 A&E cost estimate was not included. | Luis Sepulveda | Obligated | 2022-08-24 10:30 | Obligated | 89% | 1435736.35 | 13431081.73 |  | 14866818.08 | 1489333.1511 | 10190536.0518 | 497349.58 | 2630718.608 | 84516.08 | 0 | 0 | 13503120.3189 | 12821254.6598 | 581865.66 | Amendment – Amendment Needed/Pending Development | Q2 FY2027 | Amendment pending to remove underground scope | #REF! | #VALUE!
673771 | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 1] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1894033.53 | 373539 | 370850.25 | 98988 | 0 | 0 | 2737410.78 | 2264883.78 | 472527 | N | Yaritza Acevedo Ortiz | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase. | No Comment | Luis Sepulveda | Obligated | 2022-10-17 11:37 | Obligated | 86% | 646696.55 | 1011911.9 |  | 1658608.45 | 0.25 | 1894033.53 | 373539 | 370850 | 98988 | 0 | 0 | 2737410.53 | 2264883.53 | 472527 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
674083 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1747929 | 286587 | 335722 | 75946 | 0 | 0 | 2446184 | 2083651 | 362533 | N | Yaritza Acevedo Ortiz | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase. | No Comment | Luis Sepulveda | Obligated | 2022-08-08 11:30 | Obligated | 80% | 306580.88 | 1527801.4 |  | 1834382.28 | 0.1 | 1747929 | 286587 | 335721.9 | 75946 | 0 | 0 | 2446183.9 | 2083650.9 | 362533 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
704868 | FAASt [Ceiba Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 5152111.14 | 472131.79 | 1481546.84 | 244786.81 | 0 | 0 | 7350576.58 | 6633657.98 | 716918.6 | N | Mariano Perez | Amendment - Pending Development | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at: 66.77%/1125 locations completed. | The 406 A&E cost estimate was not included. | Luis Sepulveda | Obligated | 2024-07-08 11:28 | Obligated | 68% | 296022.95 | 2586620.8 |  | 2882643.75 | 0 | 5152111.14 | 472131.79 | 1481546.84 | 244786.81 | 0 | 0 | 7350576.58 | 6633657.98 | 716918.6 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
704679 | FAASt Coamo Streetlight (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 14311922.45 | 1481726 | 2687463.9 | 579175.35 | 0 | 0 | 19060287.7 | 16999386.35 | 2060901.35 | N | Mariano Perez | Amendment - Pending Development | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at: 64.97%/3177 locations completed. | The 406 A&E cost estimate was not included. | Luis Sepulveda | Obligated | 2023-11-03 11:30 | Obligated | 69% | 2624114.44 | 11411907.14 |  | 14036021.58 | -0.1 | 14311922.45 | 1481726 | 2687464 | 579175.35 | 0 | 0 | 19060287.8 | 16999386.45 | 2060901.35 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
704755 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 12-13-14] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 725501.08 | 76551.4 | 83450.9 | 18053.92 | 0 | 0 | 903557.3 | 808951.98 | 94605.32 | Y | Yaritza Acevedo Ortiz | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version. | Se espera que este proyecto tenga costos que sobrepasan la obligación por $295k. | Luis Sepulveda | Obligated | 2023-05-17 11:31 | Obligated | 84% | 132475.69 | 682254.48 |  | 814730.17 | 295714.69 | 438209.69 | 68128 | 83451 | 18053.92 | 0 | 0 | 607842.61 | 521660.69 | 86181.92 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
678789 | FAASt [Distribution Streetlighting - Carolina] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 14865613.02 | 845273.47 | 2559492.85 | 313673.09 | 0 | 0 | 18584052.43 | 17425105.87 | 1158946.56 | N | Mariano Perez | Amendment - Pending Development | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at: 69.97%/3032 locations completed. | The 406 A&E cost estimate was not included. | Luis Sepulveda | Obligated | 2023-11-03 11:30 | Obligated | 66% | 1057017.4 | 4871749.65 |  | 5928767.05 | -0.15 | 14865613.02 | 1158946.56 | 2559493 | 0 | 0 | 0 | 18584052.58 | 17425106.02 | 1158946.56 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
704750 | FAASt Distribution Pole and Conductor Repair - Bayamon Group 10 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 486385 | 72920 | 92511 | 19324 | 0 | 0 | 671140 | 578896 | 92244 | N | Yaritza Acevedo Ortiz | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase. | No Comment | Luis Sepulveda | Obligated | 2023-04-06 11:12 | Obligated | 88% | 93090.43 | 492930.91 |  | 586021.34 | 0 | 486385 | 72920 | 92511 | 19324 | 0 | 0 | 671140 | 578896 | 92244 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
724825 | FAASt [Cidra Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 12812478.84 | 1311297.11 | 2516455.74 | 526932.49 | 0 | 0 | 17167164.18 | 15328934.58 | 1838229.6 | N | Mariano Perez | Amendment - Pending Development | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at: 69.99%/2551 locations completed. | The 406 A&E cost estimate was not included. | Luis Sepulveda | Obligated | 2024-05-10 10:17 | Obligated | 66% | 1803326.86 | 7913559 |  | 9716885.86 | -0.26 | 12812478.84 | 1311297.11 | 2516456 | 526932.49 | 0 | 0 | 17167164.44 | 15328934.84 | 1838229.6 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
678988 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 5] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 911136.76 | 163360 | 175440.55 | 43290.4 | 0 | 0 | 1293227.71 | 1086577.31 | 206650.4 | N | Yaritza Acevedo Ortiz | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase. | No Comment | Luis Sepulveda | Obligated | 2022-12-27 11:53 | Obligated | 87% | 116955.71 | 957645.71 |  | 1074601.42 | -0.45 | 911136.76 | 163360 | 175441 | 43290.4 | 0 | 0 | 1293228.16 | 1086577.76 | 206650.4 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
673836 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 1] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 4686914.68 | 841203 | 900014.8 | 222918.8 | 0 | 0 | 6651051.28 | 5586929.48 | 1064121.8 | N | Yaritza Acevedo Ortiz | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase. | No Comment | Luis Sepulveda | Obligated | 2022-12-21 12:37 | Obligated | 86% | 514464.94 | 5304918.59 |  | 5819383.53 | -0.2 | 4686914.68 | 1064121.8 | 900015 | 0 | 0 | 0 | 6651051.48 | 5586929.68 | 1064121.8 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
724698 | FAASt [Adjuntas Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 10742462 | 1338877 | 2199843.63 | 552275 | 0 | 0 | 14833457.63 | 12942305.63 | 1891152 | N | Mariano Perez | Amendment - Pending Development | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at: 81.53%/2423 locations completed. | The 406 A&E cost estimate was not included. | Luis Sepulveda | Obligated | 2024-06-18 11:28 | Obligated | 79% | 1353321.41 | 7889965.76 |  | 9243287.17 | -0.37 | 10742462 | 1338877 | 2199844 | 552275 | 0 | 0 | 14833458 | 12942306 | 1891152 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
688096 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 15] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 21408.25 | 4609 | 4169.45 | 1221.39 | 0 | 0 | 31408.09 | 25577.7 | 5830.39 | N | Yaritza Acevedo Ortiz | Obligated - Final Ammendment Version once closeout stage | Project is 100% executed, and QC has been fully completed. This project was obligated under a 428/406 based on a Class 3 estimate. Reconciliation of actual costs is currently in progress in order to initiate close out according to FEMA Guidelines. | No Comment | Luis Sepulveda | Obligated | 2023-01-31 12:56 | Obligated | 100% | 9130.83 | 33824.25 |  | 42955.08 | 0.84 | 21408.25 | 4609 | 4169 | 1221 | 0 | 0 | 31407.25 | 25577.25 | 5830 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
682373 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 14] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 65944 | 9218 | 12740 | 2443 | 0 | 0 | 90345 | 78684 | 11661 | N | Yaritza Acevedo Ortiz | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase. | No Comment | Luis Sepulveda | Obligated | 2023-01-10 13:19 | Obligated | 90% | 22981.33 | 56953.82 |  | 79935.15 | 0 | 65944 | 9218 | 12740 | 2443 | 0 | 0 | 90345 | 78684 | 11661 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
685370 | FAASt [Pole and Conductor Repair - Mayagüez Group 8] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 68823 | 11847 | 13127 | 3139 | 0 | 0 | 96936 | 81950 | 14986 | N | Yaritza Acevedo Ortiz | Obligated - Final Ammendment Version once closeout stage | Project is 100% executed, and QC has been fully completed. This project was obligated under a 428/406 based on a Class 3 estimate. Reconciliation of actual costs is currently in progress in order to initiate close out according to FEMA Guidelines. | No Comment | Luis Sepulveda | Obligated | 2023-01-10 13:19 | Obligated | 100% | 27864.95 | 50766.55 |  | 78631.5 | 0 | 68823 | 11847 | 13127 | 3139 | 0 | 0 | 96936 | 81950 | 14986 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
701504 | FAASt [Pole and Conductor Repair - Arecibo Group 12] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 150345 | 29943 | 29252 | 7935 | 0 | 0 | 217475 | 179597 | 37878 | N | Yaritza Acevedo Ortiz | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase. | No Comment | Luis Sepulveda | Obligated | 2023-03-08 12:36 | Obligated | 100% | 33295.7 | 99140.02 |  | 132435.72 | -51422.58 | 211260.32 | 1161.51 | 23475.13 | 868.52 | 24568.7 | 7563.4 | 268897.58 | 259304.15 | 9593.43 | Amendment – Submitted to COR3/PREPA | Submitted | Amendment submitted Feb 12, 2026 | #REF! | #VALUE!
698570 | FAASt [Distribution Streetlighting - Corozal] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 13720208.31 | 1608383.29 | 2501126 | 617490.33 | 0 | 0 | 18447207.93 | 16221334.31 | 2225873.62 | N | Mariano Perez | Amendment - Pending Development | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at: 81.41%/3180 locations completed. | The 406 A&E cost estimate was not included. | Luis Sepulveda | Obligated | 2023-12-29 12:31 | Obligated | 84% | 1926441.65 | 9907102.27 |  | 11833543.92 | -87444.07 | 13648195 | 1608383.29 | 2640715 | 617490.33 | 0 | 0 | 18534652 | 16288910 | 2225873.62 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
682210 | FAASt [Pole and Conductor Repair - Mayagüez Group 9] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 198050.74 | 33041 | 38248.35 | 8755.87 | 0 | 0 | 278095.96 | 236299.09 | 41796.87 | N | Yaritza Acevedo Ortiz | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase. | No Comment | Luis Sepulveda | Obligated | 2023-01-24 13:14 | Obligated | 81% | 57250.62 | 172099.07 |  | 229349.69 | 0.35 | 198050.74 | 33041 | 38248 | 8755.87 | 0 | 0 | 278095.61 | 236298.74 | 41796.87 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
671502 | FAASt [Distribution Streetlighting - Yabucoa] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 14918381.07 | 1418283.01 | 2742910.41 | 547325.25 | 0 | 0 | 19626899.74 | 17661291.48 | 1965608.26 | N | Mariano Perez | Amendment - Pending Development | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at: 63.93%/3096 locations completed. | The 406 A&E cost estimate was not included. | Luis Sepulveda | Obligated | 2023-12-29 12:31 | Obligated | 69% | 2622974.69 | 9129753.51 |  | 11752728.2 | -219266.5425 | 14931289.0239 | 1987567.5115 | 2927309.7471 | 0 | 0 | 0 | 19846166.2825 | 17858598.771 | 1987567.5115 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
703535 | FAASt [Toa Baja Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 9529190.37 | 444807.71 | 1814022 | 175326.98 | 0 | 0 | 11963347.06 | 11343212.37 | 620134.69 | N | Mariano Perez | Amendment - Pending Development | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at: 62.61%/1492 locations completed. | The 406 A&E cost estimate was not included. | Luis Sepulveda | Obligated | 2024-06-18 11:28 | Obligated | 55% | 421395.41 | 2844675.01 |  | 3266070.42 | 0 | 9529190.37 | 444807.71 | 1814022 | 175326.98 | 0 | 0 | 11963347.06 | 11343212.37 | 620134.69 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
679134 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 10] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 452956.93 | 87431 | 86724.25 | 23169.22 | 0 | 0 | 650281.4 | 539681.18 | 110600.22 | N | Yaritza Acevedo Ortiz | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase. | No Comment | Luis Sepulveda | Obligated | 2023-01-10 13:19 | Obligated | 94% | 78944.82 | 524069.06 |  | 603013.88 | 0.25 | 452956.93 | 87431 | 86724 | 23169.22 | 0 | 0 | 650281.15 | 539680.93 | 110600.22 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
704938 | FAASt [Distribution Streetlighting - Las Piedras (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 13807923.4 | 1285354.42 | 2760454.04 | 522246.69 | 0 | 0 | 18375978.55 | 16568377.44 | 1807601.11 | N | Mariano Perez | Amendment - Pending Development | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at: 69.50%/3480 locations completed. | The 406 A&E cost estimate was not included. | Luis Sepulveda | Obligated | 2024-04-12 11:19 | Obligated | 70% | 939246.76 | 8823541.05 |  | 9762787.81 | 0.04 | 13807923.4 | 1285354.42 | 2760454 | 522246.69 | 0 | 0 | 18375978.51 | 16568377.4 | 1807601.11 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
685943 | FAASt Distribution Pole and Conductor Repair Ponce Group 5(Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 254972.22 | 50008 | 49774.2 | 13252 | 0 | 0 | 368006.42 | 304746.42 | 63260 | N | Yaritza Acevedo Ortiz | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase. | No Comment | Luis Sepulveda | Obligated | 2023-01-10 13:19 | Obligated | 88% | 72531.62 | 271120.98 |  | 343652.6 | 0.2 | 254972.22 | 50008 | 49774 | 13252 | 0 | 0 | 368006.22 | 304746.22 | 63260 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
724601 | FAASt [Salinas Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 12097203.53 | 1141690.52 | 2463885.54 | 469330.38 | 0 | 0 | 16172109.97 | 14561089.07 | 1611020.9 | N | Mariano Perez | Amendment - Pending Development | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at: 79.89%/3225 locations completed. | The 406 A&E cost estimate was not included. | Luis Sepulveda | Obligated | 2024-07-08 11:28 | Obligated | 79% | 1515998.56 | 8960437.9 |  | 10476436.46 | -0.46 | 12097203.53 | 1141690.52 | 2463886 | 469330.38 | 0 | 0 | 16172110.43 | 14561089.53 | 1611020.9 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
709631 | FAASt [Morovis Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 13486398.85 | 1257031.57 | 2499521.06 | 487450.7 | 0 | 0 | 17730402.18 | 15985919.91 | 1744482.27 | N | Mariano Perez | Amendment - Pending Development | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at: 78.98%/2585 locations completed. | The 406 A&E cost estimate was not included. | Luis Sepulveda | Obligated | 2024-03-22 10:16 | Obligated | 80% | 624831.32 | 12648292.15 |  | 13273123.47 | 0.06 | 13486398.85 | 1257031.57 | 2499521 | 487450.7 | 0 | 0 | 17730402.12 | 15985919.85 | 1744482.27 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
704943 | FAASt [Naranjito Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 11644048.42 | 1501948.72 | 2348209.91 | 613589.66 | 0 | 0 | 16107796.71 | 13992258.33 | 2115538.38 | N | Mariano Perez | Amendment - Pending Development | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at: 67.10%/2144 locations completed. | The 406 A&E cost estimate was not included. | Luis Sepulveda | Obligated | 2024-04-12 11:19 | Obligated | 64% | 1343697.77 | 7491314.11 |  | 8835011.88 | -0.09 | 11644048.42 | 1501948.72 | 2348210 | 613589.66 | 0 | 0 | 16107796.8 | 13992258.42 | 2115538.38 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
724600 | FAASt [Jayuya Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 7277670.2 | 931433.8 | 1704125.72 | 419107.52 | 0 | 0 | 10332337.24 | 8981795.92 | 1350541.32 | N | Mariano Perez | Obligated - Final Ammendment Version once closeout stage | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at: 73.80%/1332 locations completed. | The 406 A&E cost estimate was not included. | Luis Sepulveda | Obligated | 2024-05-31 11:36 | Obligated | 73% | 944820.43 | 5199174.46 |  | 6143994.89 | -0.28 | 7277670.2 | 931433.8 | 1704126 | 419107.52 | 0 | 0 | 10332337.52 | 8981796.2 | 1350541.32 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
679039 | FAASt [Distribution Streetlighting - Caguas] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 22960633 | 1507378.5968 | 4065133 | 452047.4032 | 0 | 0 | 28985192 | 27025766 | 1959426 | Y | Mariano Perez | Amendment - Pending Development | This project was among the first to be developed, originally including the underground work as part of the program's initial scope—estimated at: $55M for this portion to be removed. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at: 38.19%/2394 locations completed.Estimate ammedment submission Q1FY27. | Se presenta una disminución de $53 millones del documento del PREB a este documento. | Luis Sepulveda | Obligated | 2023-07-05 11:36 | Obligated | 48% | 1467080.25 | 3909718.1 |  | 5376798.35 | -52493532 | 71310194 | 1422693 | 8324691 | 426651.06 | 0 | 0 | 81478724 | 79634885 | 1849344.06 | Amendment – Amendment Needed/Pending Development | Q1 FY2028 | Amendment pending to remove underground scope Grants portal total project cost is $84.1M | #REF! | #VALUE!
690545 | FAASt Aguadilla Streetlight (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 10433035 | 1035906.3077 | 2151690 | 358776.6923 | 0 | 0 | 13979408 | 12584725 | 1394683 | Y | Mariano Perez | Amendment - Pending Development | This project was among the first to be developed, originally including the underground work as part of the program's initial scope—estimated at: $10M for this portion to be removed. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at: 46.93%/1148 locations completed.Estimate ammedment submission Q1FY27. | The 406 A&E cost estimate was not included. | Luis Sepulveda | Obligated | 2023-05-17 11:31 | Obligated | 49% | 1403833.3 | 4028370.1 |  | 5432203.4 | -10134418 | 19796809 | 962442 | 3021242 | 333333 | 0 | 0 | 24113826 | 22818051 | 1295775 | Amendment – Amendment Needed/Pending Development | Q1 FY2027 | Amendment pending to remove underground scope | #REF! | #VALUE!
735474 | FAASt [Pole and Conductor Repair -Caguas Group 3 Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 17211915.22 | 71312.91 | 1524520.51 | 44805.65 | 1144636.03 | 468198.97 | 20465389.29 | 19881071.76 | 584317.53 | Y | Yaritza Acevedo Ortiz | Amendment - Pending Development | Project obligated under based on a Class 3 estimate full 428. The 428/406HM Amendment was submitted with the revised Class 3 estimate. | No Comment | Luis Sepulveda | Pending Amendment Processing | 2025-09-17 18:16 | Obligated, Pending Amendment Processing | 47% | 1724027.43 | 10902862.7 |  | 12626890.13 | 0 | 17211915.22 | 71311.91 | 1524520.51 | 44806.65 | 1144636.03 | 468198.97 | 20465389.29 | 19881071.76 | 584317.53 | Amendment – Submitted to FEMA | Submitted | DSOW – Submitted to FEMA -Currently under FEMA evaluation | #REF! | #VALUE!
750692 | FAASt [Pole and Conductor Repair - Mayaguez Group 3 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 15534571.38 | 65783.22 | 1378411.7 | 41393.16 | 1059507.72 | 432530.28 | 18512197.46 | 17972490.8 | 539706.66 | Y | Yaritza Acevedo Ortiz | Amendment - Pending Development | Project obligated under based on a Class 3 estimate full 428. The 428/406HM Amendment was submitted with the revised Class 3 estimate. | Se espera que este proyecto tenga costos que sobrepasan la obligación por $1.2 millones. | Luis Sepulveda | Pending Amendment Processing | 2025-09-25 16:15 | Obligated, Pending Amendment Processing | 27% | 1235245.48 | 4593133.24 |  | 5828378.72 | 0 | 15534571.38 | 65783.22 | 1378411.7 | 41393.16 | 1059507.72 | 432530.28 | 18512197.46 | 17972490.8 | 539706.66 | Amendment – Submitted to FEMA | Submitted | DSOW – Submitted to FEMA -Currently under FEMA evaluation | #REF! | #VALUE!
752540 | FAASt [Pole and Conductor Repair -Mayaguez Group 4 Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 8685452.68 | 37311.66 | 773151.6 | 23427.4 | 624817.52 | 244800.38 | 10388961.24 | 10083421.8 | 305539.44 | Y | Yaritza Acevedo Ortiz | Amendment - Pending Development | Project obligated under based on a Class 3 estimate full 428. The 428/406HM Amendment was submitted with the revised Class 3 estimate. | Se espera que este proyecto tenga costos que sobrepasan la obligación por $910k | Luis Sepulveda | Pending Amendment Processing | 2025-09-25 16:15 | Obligated, Pending Amendment Processing | 0% | 414698.41 | 135811.89 |  | 550510.3 | 0 | 8687329.99 | 35434.35 | 773151.6 | 23427.4 | 622940.21 | 246677.69 | 10388961.24 | 10083421.8 | 305539.44 | Amendment – Submitted to FEMA | Submitted | DSOW – Submitted to FEMA -Currently under FEMA evaluation | #REF! | #VALUE!
790443 | FAASt [Pole and Conductor Repair -San Juan Group 3 Phase 2 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 243833.22 | 919.39 | 21435.45 | 574.91 | 14432.64 | 6007.36 | 287202.97 | 279701.31 | 7501.66 | Y | Yaritza Acevedo Ortiz | Amendment - Pending Development | Project obligated under based on a Class 3 estimate full 428. The 428/406HM Amendment was submitted with the revised Class 3 estimate. | No Comment | Luis Sepulveda | Pending Final FEMA Review | 2025-09-03 20:15 | Obligated, Pending Final FEMA Review | 51% | 42822.13 | 75698.79 |  | 118520.92 | -6526.08 | 244155.63 | 919.99 | 25573.49 | 679.94 | 16392.64 | 6007.36 | 293729.05 | 286121.76 | 7607.29 | Amendment – Submitted to FEMA | Submitted | DSOW – Submitted to FEMA -Currently under FEMA evaluation | #REF! | #VALUE!
679458 | FAASt [Distribution Pole and Conductor Repair - Ponce Group 4] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 498436 | 75480 | 95421 | 20002 | 0 | 0 | 689339 | 593857 | 95482 | N | Yaritza Acevedo Ortiz | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase. | No Comment | Luis Sepulveda | Obligated | 2023-01-10 13:19 | Obligated | 88% | 61634.48 | 469886.88 |  | 531521.36 | 0 | 498436 | 75480 | 95421 | 20002 | 0 | 0 | 689339 | 593857 | 95482 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
682136 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 9] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 469650.95 | 75853 | 90259.5 | 20101.05 | 0 | 0 | 655864.5 | 559910.45 | 95954.05 | N | Yaritza Acevedo Ortiz | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase. | No Comment | Luis Sepulveda | Obligated | 2023-01-31 12:56 | Obligated | 95% | 158107.78 | 467050.89 |  | 625158.67 | -0.5 | 469650.95 | 75853 | 90260 | 20101.05 | 0 | 0 | 655865 | 559910.95 | 95954.05 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
688774 | FAASt Distribution Pole and Conductor Repair - Ponce Group 9 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 443331 | 77853 | 86719 | 20631 | 0 | 0 | 628534 | 530050 | 98484 | N | Yaritza Acevedo Ortiz | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase. | No Comment | Luis Sepulveda | Obligated | 2023-01-31 12:56 | Obligated | 87% | 79105.19 | 236370.68 |  | 315475.87 | 0 | 443331 | 77853 | 86719 | 20631 | 0 | 0 | 628534 | 530050 | 98484 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
682890 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 12] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 510067.96 | 80878 | 98275.6 | 21432.67 | 0 | 0 | 710654.23 | 608343.56 | 102310.67 | N | Yaritza Acevedo Ortiz | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase. | No Comment | Luis Sepulveda | Obligated | 2022-12-27 11:53 | Obligated | 88% | 90359.9 | 549372.52 |  | 639732.42 | -0.4 | 510067.96 | 80878 | 98276 | 21432.67 | 0 | 0 | 710654.63 | 608343.96 | 102310.67 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
682028 | FAASt [Pole and Conductor Repair - San Juan Group 8] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 431381.68 | 83592 | 83822 | 22151.62 | 0 | 0 | 620947.3 | 515203.68 | 105743.62 | N | Yaritza Acevedo Ortiz | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase. | El proyecto no cambia de la obligación |  | Obligated | 2023-01-10 13:19 | Obligated | 75% | 110527.7 | 380899.81 |  | 491427.51 | 94082.62 | 431381.68 | 83591 | 83822 | 22151.62 | 0 | 0 | 526864.68 | 515203.68 | 105742.62 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
691702 | FAASt Distribution Streetlighting - Trujillo Alto (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 9704697 | 860820.467 | 1981105 | 277993.533 | 0 | 0 | 12824616 | 11685802 | 1138814 | Y | Mariano Perez | Amendment - Pending Development | This project was among the first to be developed, originally including the underground work as part of the program's initial scope—estimated at: $16M for this portion to be removed. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at: 36.09%/939 locations completed.Estimate ammedment submission Q1FY27. | The 406 A&E cost estimate was not included. | Luis Sepulveda | Obligated | 2023-05-17 11:31 | Obligated | 45% | 415062.95 | 1727729.45 |  | 2142792.4 | -2000635 | 12199399 | 763112 | 2277871 | 246446 | 0 | 0 | 14825251 | 14477270 | 1009558 | Amendment – Amendment Needed/Pending Development | FY2027 | Amendment pending to remove underground scope Grants portal total project cost is $29.7M | #REF! | #VALUE!
660437 | FAASt Manati Streetlight (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 15401358 | 1286291.785 | 2596783 | 411619.215 | 0 | 0 | 19696052 | 17998141 | 1697911 | Y | Mariano Perez | Amendment - Pending Development | This project was among the first to be developed, originally including the underground work as part of the program's initial scope—estimated at: $14M for this portion to be removed. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at: 63.98%/3704 locations completed.Estimate ammedment submission Q1FY27. | The 406 A&E cost estimate was not included. | Luis Sepulveda | Obligated | 2023-01-24 13:14 | Obligated | 66% | 1460283.71 | 8221672.45 |  | 9681956.16 | -14762412.7468 | 27067865.4688 | 1188605 | 5821635.5034 | 380359 | 0 | 0 | 34458464.7468 | 32889500.9722 | 1568964 | Amendment – Amendment Needed/Pending Development | Q4 FY2027 | Amendment pending to remove underground scope | #REF! | #VALUE!
659625 | FAASt Distribution Streetlighting - Dorado | Distribution | Distribution Streetlighting | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 12068437 | 1385150.1318 | 1911204 | 171057.8682 | 0 | 0 | 15535849 | 13979641 | 1556208 | Y | Mariano Perez | Amendment - Pending Development | This project was among the first to be developed, originally including the underground work as part of the program's initial scope—estimated at: $11M for this portion to be removed. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at: 76.39%/3314 locations completed.Estimate ammedment submission Q1FY27. | The 406 A&E cost estimate was not included. | Luis Sepulveda | Obligated | 2023-01-24 13:14 | Obligated | 79% | 1590751.19 | 4882711.44 |  | 6473462.63 | -13551362.5954 | 22864971.8931 | 1149672 | 4716594.2453 | 355973 | 0 | 0 | 29087211.5954 | 27581566.1384 | 1505645 | Amendment – Amendment Needed/Pending Development | Q2 FY2027 | Amendment pending to remove underground scope | #REF! | #VALUE!
682031 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 9] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 516951 | 85571 | 94044 | 22676 | 0 | 0 | 719242 | 610995 | 108247 | N | Yaritza Acevedo Ortiz | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase. | No Comment | Luis Sepulveda | Obligated | 2023-01-31 12:56 | Obligated | 26% | 146791.32 | 147755.52 |  | 294546.84 | 0 | 516951 | 85571 | 94044 | 22676 | 0 | 0 | 719242 | 610995 | 108247 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
682135 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 8] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 577000.79 | 92316 | 109858.85 | 24463.74 | 0 | 0 | 803639.38 | 686859.64 | 116779.74 | N | Yaritza Acevedo Ortiz | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase. | No Comment | Luis Sepulveda | Obligated | 2023-01-10 13:19 | Obligated | 86% | 102626.17 | 547426.65 |  | 650052.82 | -19402.72 | 577000.79 | 92316 | 109859 | 24463.74 | 0 | 0 | 823042.1 | 686859.79 | 116779.74 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
685263 | FAASt Distribution Pole and Conductor Repair - Ponce Group 6 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 537688 | 106478 | 103281 | 28217 | 0 | 0 | 775664 | 640969 | 134695 | N | Yaritza Acevedo Ortiz | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase. | No Comment | Luis Sepulveda | Obligated | 2022-12-27 11:53 | Obligated | 86% | 69845.95 | 458183.25 |  | 528029.2 | 0 | 537688 | 106478 | 103281 | 28217 | 0 | 0 | 775664 | 640969 | 134695 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
682324 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 13] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 573047.24 | 107654 | 110616.4 | 28528.31 | 0 | 0 | 819845.95 | 683663.64 | 136182.31 | N | Yaritza Acevedo Ortiz | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase. | No Comment | Luis Sepulveda | Obligated | 2023-01-10 13:19 | Obligated | 82% | 85417.83 | 664925.8 |  | 750343.63 | 0 | 573047.24 | 107654 | 110616.4 | 28528.31 | 0 | 0 | 819845.95 | 683663.64 | 136182.31 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
682228 | FAASt [Pole and Conductor Repair - Ponce Group 8] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 775779 | 139828 | 150784 | 37054.42 | 0 | 0 | 1103445.42 | 926563 | 176882.42 | N | Yaritza Acevedo Ortiz | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase. | No Comment | Luis Sepulveda | Obligated | 2023-01-31 12:56 | Obligated | 88% | 223903.89 | 476285.81 |  | 700189.7 | 0 | 775779 | 139828 | 150784 | 37054.42 | 0 | 0 | 1103445.42 | 926563 | 176882.42 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
659623 | FAASt Distribution Streetlighting - Cataño ( | Distribution | Distribution Streetlighting | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 7282778 | 499180.1274 | 1345465 | 156938.8726 | 0 | 0 | 9284362 | 8628243 | 656119 | Y | Mariano Perez | Amendment - Pending Development | This project was among the first to be developed, originally including the underground work as part of the program's initial scope—estimated at: $11M for this portion to be removed. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at: 55.73%/1299 locations completed.Estimate ammedment submission Q1FY27. | The 406 A&E cost estimate was not included. | Luis Sepulveda | Obligated | 2022-12-27 11:53 | Obligated | 77% | 1129471.99 | 2894190.49 |  | 4023662.48 | -11852448.1562 | 16996757.9573 | 516042 | 3574762.8595 | 49247 | 0 | 0 | 21136810.1562 | 20571520.8168 | 565289 | Amendment – Amendment Needed/Pending Development | Q2 FY2027 | Amendment pending to remove underground scope | #REF! | #VALUE!
673504 | FAASt [Distribution Streetlighting - Gurabo] | Distribution | Distribution Streetlighting | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 13326352 | 1163470.3301 | 2498935 | 411543.6699 | 0 | 0 | 17400301 | 15825287 | 1575014 | Y | Mariano Perez | Amendment - Pending Development | This project was among the first to be developed, originally including the underground work as part of the program's initial scope—estimated at: $6M for this portion to be removed. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at: 77.57%/2919 locations completed.Estimate ammedment submission Q1FY27. | The 406 A&E cost estimate was not included. | Luis Sepulveda | Obligated | 2023-05-17 11:31 | Obligated | 69% | 1066631.61 | 10060207.65 |  | 11126839.26 | -6385668.008 | 19208993.6756 | 1132656 | 3043675.3411 | 400644 | 0 | 0 | 23785969.008 | 22252669.0167 | 1533300 | Amendment – Amendment Needed/Pending Development | Q2 FY2028 | Amendment pending to remove underground scope | #REF! | #VALUE!
659968 | FAASt [San Germán Streetlighting] (Distributio | Distribution | Distribution Streetlighting | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 26194807 | 3105148.8829 | 4178149 | 1064155.1171 | 0 | 0 | 34542260 | 30372956 | 4169304 | Y | Mariano Perez | Amendment - Pending Development | This project was among the first to be developed, originally including the underground work as part of the program's initial scope—estimated at: $5M for this portion to be removed. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at: 83.80%/4339 locations completed. Estimate ammedment submission Q1FY27. | The 406 A&E cost estimate was not included. | Luis Sepulveda | Obligated | 2023-05-04 11:30 | Obligated | 72% | 4404198 | 17318241.86 |  | 21722439.86 | -4959873.2497 | 30849348.4835 | 3004065 | 4619206.9342 | 1029513 | 0 | 0 | 39502133.2497 | 35468555.4178 | 4033578 | Amendment – Amendment Needed/Pending Development | Q1 FY2028 | Amendment pending to remove underground scope | #REF! | #VALUE!
542517 | FAASt -Luquillo Distribution Streetlighting | Distribution | Distribution Streetlighting | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 4946319 | 158253.8999 | 989521 | 36758.1001 | 0 | 0 | 6130852 | 5935840 | 195012 | Y | Mariano Perez | Amendment - Pending Development | This project was among the first to be developed, originally including the underground work as part of the program's initial scope—estimated at: $4M for this portion to be removed. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at: 81.19%/1986 locations completed.Estimate ammedment submission Q1FY27. | The 406 A&E cost estimate was not included. | Luis Sepulveda | Obligated | 2022-05-20 12:05 | Obligated | 88% | 972416.24 | 2834354.64 |  | 3806770.88 | -6687939.8371 | 10632900.5227 | 181658.0813 | 2004233.2331 | 0 | 0 | 0 | 12818791.8371 | 12637133.7558 | 181658.0813 | Amendment – Amendment Needed/Pending Development | Q2 FY2027 | Amendment pending to remove underground scope Grants portal total project cost is $2M | #REF! | #VALUE!
660227 | FAASt Hatillo Streetlight (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 16131869 | 1430424.6192 | 2596438 | 487221.3808 | 0 | 0 | 20645953 | 18728307 | 1917646 | Y | Mariano Perez | Amendment - Pending Development | This project was among the first to be developed, originally including the underground work as part of the program's initial scope—estimated at: $4M for this portion to be removed. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at: 82.67%/4375 locations completed. | The 406 A&E cost estimate was not included. | Luis Sepulveda | Obligated | 2023-01-24 13:14 | Obligated | 79% | 2518200.59 | 9798208.1 |  | 12316408.69 | -4006390.3772 | 18570095.2497 | 1316105.06 | 4317860.4264 | 448282.64 | 0 | 0 | 24652343.3772 | 22887955.6761 | 1764387.7 | Amendment – Amendment Needed/Pending Development | Q3 FY2027 | Amendment pending to remove underground scope | #REF! | #VALUE!
542756 | FAASt Streetlighting - Guánica (Distribution | Distribution | Distribution Streetlighting | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 6817015 | 506125.5667 | 1189325 | 116896.4333 | 0 | 0 | 8629362 | 8006340 | 623022 | Y | Mariano Perez | Amendment - Pending Development | This project was among the first to be developed, originally including the underground work as part of the program's initial scope—estimated at: $3M for this portion to be removed. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at: 86.43%/2598 locations completed.Estimate ammedment submission Q1FY27. | The 406 A&E cost estimate was not included. | Luis Sepulveda | Obligated | 2022-05-26 11:24 | Obligated | 89% | 710048.67 | 3682408.62 |  | 4392457.29 | -5903456.386 | 11924623.8365 | 370808.2187 | 2237386.3309 | 0 | 0 | 0 | 14532818.386 | 14162010.1673 | 370808.2187 | Amendment – Amendment Needed/Pending Development | Q2 FY2027 | Amendment pending to remove underground scope Grants portal total project cost is $2.237M | #REF! | #VALUE!
698424 | FAASt Streetlight Florida Distribution | Distribution | Distribution Streetlighting | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 7063699 | 741458.8765 | 1487857 | 285427.1235 | 0 | 0 | 9578442 | 8551556 | 1026886 | Y | Mariano Perez | Amendment - Pending Development | This project was among the first to be developed, originally including the underground work as part of the program's initial scope—estimated at: $2M for this portion to be removed. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at: 85.08%/1454 locations completed.Estimate ammedment submission Q1FY27. | The 406 A&E cost estimate was not included. | Luis Sepulveda | Obligated | 2023-10-23 11:32 | Obligated | 75% | 1512708.84 | 4834340.37 |  | 6347049.21 | -2435685.53 | 9311841.53 | 720017 | 1705096 | 277173 | 0 | 0 | 12014127.53 | 11016937.53 | 997190 | Amendment – Amendment Needed/Pending Development | FY2027 | Amendment pending to remove underground scope | #REF! | #VALUE!
738971 | FAASt [Pole and Conductor Repair - Caguas Group 2 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 13884126 | 310288 | 1643630 | 66835.67 | 0 | 0 | 15904879.67 | 15527756 | 377123.67 | N | Yaritza Acevedo Ortiz | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase. | Confirm if the $2 Million available are enough to complete the 30% of the project that is pending to be completed. | Luis Sepulveda | Obligated | 2025-02-06 20:16 | Obligated | 70% | 1300738.16 | 12798397.58 |  | 14099135.74 | 0 | 13884126 | 310288 | 1643630 | 66835.67 | 0 | 0 | 15904879.67 | 15527756 | 377123.67 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
542688 | FAASt Aguada Streetlighting (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 17056591 | 1425202.197 | 2565976 | 329317.803 | 0 | 0 | 21377087 | 19622567 | 1754520 | Y | Mariano Perez | Amendment - Pending Development | This project was among the first to be developed, originally including the underground work as part of the program's initial scope—estimated at: $1.2M for this portion to be removed. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at: 88.74%/6047 locations completed. | The 406 A&E cost estimate was not included. | Luis Sepulveda | Obligated | 2022-05-05 12:44 | Obligated | 95% | 1020179.15 | 12653210.52 |  | 13673389.67 | -5404200.9037 | 21869280.099 | 807222.0429 | 4104785.7618 | 0 | 0 | 0 | 26781287.9037 | 25974065.8608 | 807222.0429 | Amendment – Amendment Needed/Pending Development | Q2 FY2027 | Amendment pending to remove underground scope Grants portal total project cost is $4.1M | #REF! | #VALUE!
542690 | FAASt Maunabo Streetlighting (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 5640236 | 197986.2881 | 984819 | 48872.7119 | 0 | 0 | 6871914 | 6625055 | 246859 | Y | Mariano Perez | Amendment - Pending Development | This project was among the first to be developed, originally including the underground work as part of the program's initial scope—estimated at: $1M for this portion to be removed. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at: 95.09%/2306 locations completed.Estimate ammedment submission Q1FY27. | The 406 A&E cost estimate was not included. | Luis Sepulveda | Obligated | 2022-05-05 11:20 | Obligated | 95% | 688794.98 | 4580838.2 |  | 5269633.18 | -2632720.3826 | 7730315.5622 | 179642 | 1530438.4909 | 64238 | 0 | 0 | 9504634.3826 | 9260754.0531 | 243880 | Amendment – Amendment Needed/Pending Development | Q4 FY2026 | Amendment pending to remove underground scope Grants portal total project cost is $7.9M | #REF! | #VALUE!
542687 | FAASt Lajas Streetlighting (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 10510560 | 793672.8937 | 1674019 | 194038.1063 | 0 | 0 | 13172290 | 12184579 | 987711 | Y | Mariano Perez | Amendment - Pending Development | This project was among the first to be developed, originally including the underground work as part of the program's initial scope—estimated at: $45K for this portion to be removed. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at: 93.87%/3888 locations completed.Estimate ammedment submission Q1FY27. | The 406 A&E cost estimate was not included. | Luis Sepulveda | Obligated | 2022-05-20 12:05 | Obligated | 93% | 1075763.82 | 5981576.91 |  | 7057340.73 | -2558086.0356 | 12791189.8219 | 426332.4825 | 2512853.7311 | 0 | 0 | 0 | 15730376.0356 | 15304043.553 | 426332.4825 | Amendment – Amendment Needed/Pending Development | Q3 FY2027 | Amendment pending to remove underground scope Grants portal total project cost is $2.5 | #REF! | #VALUE!
698579 | FAASt [Distribution Streetlighting - Orocovis] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 9591989.9 | 925633.77 | 1873982.08 | 414167.51 | 0 | 0 | 12805773.26 | 11465971.98 | 1339801.28 | Y | Mariano Perez | Obligated - Final Ammendment Version once closeout stage | This project is currently over budget because the work assigned, based on vendor rates, exceeded the Class 3 estimate. Based on a high‑level evaluation, the work that can be executed within the remaining budget is estimated to be approximately $1,521,024.94 to cover both overruns and pending work (Added to 428 Child for FFO review). This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at: 72.60%/1627 locations completed. | The 406 A&E cost estimate was not included. | Luis Sepulveda | Obligated | 2024-03-22 10:16 | Obligated | 57% | 532947.21 | 8580713.74 |  | 9113660.95 | 1521025.02 | 8070964.96 | 925633.77 | 1873982 | 414167.51 | 0 | 0 | 11284748.24 | 9944946.96 | 1339801.28 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed. | #REF! | #VALUE!
801166 | FAASt [Feeder Rebuild # 6601-03] (Distribution) | Distribution | Feeders | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 19979701.47 | 0 | 1724565.72 | 0 | 2135838.13 | 0 | 23840105.32 | 23840105.32 | 0 | Y | Jorge Lopez Burgos | Not Submitted | The project was fully obligated under Section 428 using the Class 3 estimate. Versioning was submitted, including the split between 428 and 406, and it is currently under FEMA evaluation. The final DSOW versioning will be submitted, reflecting an additional $152,918 to the approved budget. | No comment | Amaury Pacheco | Obligated | 2026-01-08 16:17 | Obligated | 0% | 1877483.66 | 75764.59 |  | 1953248.25 | 237614.25 | 18342600.15 | 1465349.66 | 1564501.94 | 153975.57 | 1578988.43 | 497075.32 | 23602491.07 | 21486090.52 | 2116400.55 | Amendment – Pending Design Package for Development | Q1 FY2027 | IFA versioning in-progress. Survey aligment of 477 structures, 7.2 miles on rural area. Next step is IFC development and submission to FEMA on Jul 2026 | #REF! | #VALUE!
812569 | FAASt [Feeder Rebuild 3502-02] (Distribution) | Distribution | Feeders | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 10019547.43 | 1071193.26 | 1552343.58 | 168085.95 | 399838.42 | 57779.14 | 13268787.78 | 11971729.43 | 1297058.35 | Y | Jorge Lopez Burgos | Amendment – Submitted to COR3/PREPA | Project was obligated full 428 based on a Class 3 estimate, versioning was submitted including split 428/406, Under FEMA evaluation. | Verificar los costos totales presentados en 406, (Columna Z) ya que duplica los costos incluidos en la revisión del estimado preparado para la enmienda | Amaury Pacheco | Obligated | 2025-09-25 16:15 | Obligated | 0% | 1669007.45 | 28392.26 |  | 1697399.71 | 728085.48 | 9913132.84 | 597420.75 | 1301050.25 | 86144.8 | 547637.41 | 95316.25 | 12540702.3 | 11761820.5 | 778881.8 | Amendment – Amendment Needed/Pending Development | Q4 FY2026 | IEM is working on versioning, to be submitted to FEMA on Mar 2026 | #REF! | #VALUE!
798275 | FAASt [Feeder Rebuild # 1620-02] (Distribution) | Distribution | Feeders | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 6267255.15 | 215006.18 | 1289176.91 | 37409.72 | 531498.7 | 78348.17 | 8418694.83 | 8087930.76 | 330764.07 | Y | Jorge Lopez Burgos | Ammendment submitted to FEMA needs to be adjusted with new estimate cost | Project was obligated full 428 based on a Class 3 estimate, versioning was submitted including split 428/406, Under FEMA evaluation. | Verificar los costos totales presentados en 406, (Columna Z) ya que duplica los costos incluidos en la revisión del estimado preparado para la enmienda | Amaury Pacheco | Pending Amendment Request Approval | 2025-09-17 18:16 | Obligated, Pending Amendment Request Approval | 0% | 1447054.36 | 37429.23 |  | 1484483.59 | 795374.44 | 5339236.4 | 338774.39 | 1228581.96 | 98180.39 | 490913.44 | 127633.81 | 7623320.39 | 7058731.8 | 564588.59 | Amendment – Submitted to COR3/PREPA | Q4 FY2026 |  | #REF! | #VALUE!
746545 | FAASt [Primary Control Center / Secondary Data Center & Control Room] (Telecommunication) | Building | Building | No | Pending PDMG Scope & Cost Routing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93654467.72 | 44072690.69 | 12578331.03 | 5919214.6 | 0 | 0 | 156224704.04 | 106232798.75 | 49991905.29 | 93654467.72 | 44072690.69 | 12578331.03 | 5919214.6 | 0 | 0 | 156224704.04 | 106232798.75 | 49991905.29 | Y | Rhys Dela Cruz | Project in V0 - No amendment required at this time | The PCC Project is in a Tiered Environmental Assessment process that is being led by FEMA and after the TEA process is completed the DSOW review will continue through to funding obligation. The DSOW is still in Version 0 and will not require an amendment until the TEA process is complete. | ¿Quién proveerá la información para este proyecto? SV 9-apr-26 Rhys de la Cruz provided the numbers SV 30-apr-26 - New Comment provided by Oscar Ramos via Teams | Sandra Valentin | Pending PDMG Scope & Cost Routing |  | Pending PDMG Scope & Cost Routing | N/A | 10886342.21 | 477754.91 |  | 11364097.12 | 25055430.04 | 78491693.5616 | 36937267.5584 | 10703412.7584 | 5036900.1216 | 0 | 0 | 131169274 | 89195106.32 | 41974167.68 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Project under NEPA review process. An amendment will be developed after obligation to add 406 split. | 1 | #VALUE!
711819 | FAASt [Transmission Priority Pole Replacement Program Line 13400 San German Sect-La Parguera Sect] (Transmission) | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 2202286.53 | 160980.0333 | 201035.14 | 15575.52 | 147447.87 | 21069.57 | 2748394.6633 | 2550769.54 | 197625.1233 | N | Carlos Samalot | Obligated - No amendment need Identified | Information represents the latest LPCE information provided. | Jonathan envió las correcciones el 2 de abril de 2026 | Sandra Valentin | Obligated | 2026-03-01 18:16 | Obligated | N/A | 623902.84 | 832177.64 | 129931.98 | 1586012.46 | -337144.7667 | 2619583.06 | 20527.74 | 292186.72 | 3160.19 | 140718.36 | 9363.36 | 3085539.43 | 3052488.14 | 33051.29 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | No Amendment Needed | #REF! | #VALUE!
714654 | FAASt [Advanced Metering Infrastructure (AMI)] (Telecommunications) | Telecommunication | AMI Implementation Program | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 332062581 | 517366615 | 1484008 | 26840980 | 0 | 0 | 877754184 | 333546589 | 544207595 | N | Greg Chiszar | Obligated - No amendment need Identified | Confirmed via email between Orlando Rodríguez and Greg Chiszar on April 9, 2026 there are no changes in cost. | Se le puso la cantidad de la obligación en lo que nos proveen los numeros. SV 9-apr-26 Según intercambio de email entre Orlando y Greg Chiszar, la cantidad de dinero es la que ya está obligada. | Sandra Valentin | Obligated | 2023-12-08 11:19 | Obligated | 9% | 58318159.91 | 130591789.45 |  | 188909949.36 | -14966915 | 332062581 | 541786319 | 16450923 | 2421276 | 0 | 0 | 892721099 | 348513504 | 544207595 | Obligated -No expected changes | Submitted | Already Submitted | #REF! | #VALUE!
168226 | FAASt San Juan 115kV Underground Transmission | Transmission | Transmission Line Rebuild | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 14746039.57 | 0 | 2258339.67 | 0 | 0 | 0 | 17004379.24 | 17004379.24 | 0 | N | Jan Lopez | Obligated - No amendment need Identified | Data included was not modified, it represents the obligated amounts. The scope is being revised and may impact the estimate | Confirm that the project does not include 406. | Sandra Valentin/ Jose A Cruz | Obligated | 2022-12-21 12:37 | Obligated | 0% | 1567383.54 | 58077.11 |  | 1625460.65 | 2250000 | 12496039.57 | 0 | 2258339.67 | 0 | 0 | 0 | 14754379.24 | 14754379.24 | 0 | Obligated -No expected changes | N/A | Scope confirmation under discussion to create amendment Insurance deduction of $2,250,000 | #REF! | #VALUE!
750066 | FAASt [Region 4 -Caguas Group A] Low Density (Vegetation) | Vegetation | Vegetation-DT | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 28466485.03 | 77871225.66 | 448177.27 | 1226007.11 | 0 | 0 | 108011895.07 | 28914662.3 | 79097232.77 | n | Rene Baptiste Omar Miranda | Project obligated. No Amendment needed. | Cost aligned to the FEMA Obligation values |  | Rene Baptiste | Obligated | 2026-03-01 17:15 | Obligated | N/A | 253316.92 | 30262.67 |  | 283579.59 | -16201791.39 | 32703357.23 | 90995446.51 | 514882.72 | 2059216.24 | 0 | 0 | 124213686.46 | 33218239.95 | 93054662.75 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Project is pending FEMA obligation | #REF! | #VALUE!
750065 | FAASt [Region 3 -Bayamon Group A] Low Density (Vegetation) | Vegetation | Vegetation-DT | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 18569923.87 | 50798780.76 | 294281.61 | 805019.28 | 0 | 0 | 70468005.52 | 18864205.48 | 51603800.04 | n | Rene Baptiste Omar Miranda | Project obligated. No Amendment needed. | Cost aligned to the FEMA Obligation values |  | Rene Baptiste | Obligated | 2026-03-01 18:15 | Obligated | N/A | 120549.61 | 45858.06 |  | 166407.67 | -10570205.48 | 21333819.52 | 59366309.82 | 338081.66 | 1151514.49 | 0 | 0 | 81038211 | 21671901.18 | 60517824.31 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Project is pending FEMA obligation | #REF! | #VALUE!
750067 | FAASt [Region 2 -Arecibo Group A] Low Density (Vegetation) | Vegetation | Vegetation-DT | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 15030146.18 | 41115575.14 | 238185.98 | 651567.42 | 0 | 0 | 57035474.72 | 15268332.16 | 41767142.56 | n | Rene Baptiste Omar Miranda | Project obligated. No Amendment needed. | Cost aligned to the FEMA Obligation values |  | Rene Baptiste | Obligated | 2026-03-01 18:15 | Obligated | N/A | 193158.39 | 64314.49 |  | 257472.88 | -8555324.97 | 17267191.18 | 48049971.59 | 273636.92 | 931916.64 | 0 | 0 | 65590799.69 | 17540828.1 | 48981888.23 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Project is pending FEMA obligation | #REF! | #VALUE!
750068 | FAASt [Region 5 -Mayaguez Group A] Low Density (Vegetation) | Vegetation | Vegetation-DT | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 13840548.75 | 37861383.08 | 219334.17 | 599997.54 | 0 | 0 | 52521263.54 | 14059882.92 | 38461380.62 | n | Rene Baptiste Omar Miranda | Project obligated. No Amendment needed. | Cost aligned to the FEMA Obligation values |  | Rene Baptiste | Obligated | 2026-03-01 18:15 | Obligated | N/A | 170084.91 | 58772.51 |  | 228857.42 | -7878193 | 15900537.4 | 44246939.88 | 251979.26 | 858465.45 | 0 | 0 | 60399456.54 | 16152516.66 | 45105405.33 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Project is pending FEMA obligation | #REF! | #VALUE!
727572 | FAASt [Region 3 -Bayamon Group A] High Density (Vegetation) | Vegetation | Vegetation-DT | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 11268772.7 | 30826184.94 | 179741.68 | 491691 | 0 | 0 | 42766390.32 | 11448514.38 | 31317875.94 | n | Rene Baptiste Omar Miranda | Project obligated. No Amendment needed. | Cost aligned to the FEMA Obligation values |  | Rene Baptiste | Obligated | 2026-03-01 18:15 | Obligated | N/A | 443277.11 | 364268.12 |  | 807545.23 | -6208467.45 | 12945985.39 | 36028872.38 | 0 | 698724.72 | 0 | 0 | 48974857.77 | 12945985.39 | 36727597.1 | Obligated -No expected changes | N/A | Project is pending FEMA obligation | #REF! | #VALUE!
727692 | FAASt [Region 4 -Caguas Group A] High Density (Vegetation) | Vegetation | Vegetation-DT | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 7414164.75 | 20309782.6 | 119789.88 | 328143.02 | 0 | 0 | 28171880.25 | 7533954.63 | 20637925.62 | n | Rene Baptiste Omar Miranda | Project obligated. No Amendment needed. | Cost aligned to the FEMA Obligation values |  | Rene Baptiste | Obligated | 2025-04-28 19:15 | Obligated | 76% | 1573121.52 | 4639985.9 |  | 6213107.42 | 119789.88 | 7414164.75 | 20637925.62 | 0 | 328143.02 | 0 | 0 | 28052090.37 | 7414164.75 | 20966068.64 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Project is currently in execution | #REF! | #VALUE!
727531 | FAASt [Region 6 -Ponce Group A] High Density (Vegetation) | Vegetation | Vegetation-DT | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 6849050.26 | 15776180 | 110659.38 | 3288703.85 | 0 | 0 | 26024593.49 | 6959709.64 | 19064883.85 | n | Rene Baptiste Omar Miranda | Project obligated. No Amendment needed. | Cost aligned to the FEMA Obligation values |  | Rene Baptiste | Obligated | 2025-04-28 19:15 | Obligated | 58% | 1013304.96 | 5383764.2 |  | 6397069.16 | 110659.38 | 6849050.26 | 19064883.85 | 0 | 369745.52 | 0 | 0 | 25913934.11 | 6849050.26 | 19434629.37 | Obligated -No expected changes | N/A | Project is currently in execution | #REF! | #VALUE!
728827 | FAASt [Region 2 -Arecibo Group A] High Density (Vegetation) | Vegetation | Vegetation-DT | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 4807675.47 | 13169769.88 | 79166.85 | 216863.46 | 0 | 0 | 18273475.66 | 4886842.32 | 13386633.34 | n | Rene Baptiste Omar Miranda | Project obligated. No Amendment needed. | Cost aligned to the FEMA Obligation values |  | Rene Baptiste | Obligated | 2025-04-28 19:15 | Obligated | 86% | 847092.92 | 4070911.08 |  | 4918004 | 79166.85 | 4807675.47 | 13386633.34 | 0 | 259813.59 | 0 | 0 | 18194308.81 | 4807675.47 | 13646446.93 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Project is currently in execution | #REF! | #VALUE!
728832 | FAASt [Region 5 -Mayaguez Group A] High Density (Vegetation) | Vegetation | Vegetation-DT | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 3767690.42 | 8682952.46 | 62820.38 | 1810049.02 | 0 | 0 | 14323512.28 | 3830510.8 | 10493001.48 | n | Rene Baptiste Omar Miranda | Project obligated. No Amendment needed. | Cost aligned to the FEMA Obligation values |  | Rene Baptiste | Obligated | 2025-04-28 19:15 | Obligated | 45% | 770354.12 | 2541535.09 |  | 3311889.21 | 62820.38 | 3767690.42 | 10493001.48 | 0 | 203638.57 | 0 | 0 | 14260691.9 | 3767690.42 | 10696640.05 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Project is currently in execution | #REF! | #VALUE!
741105 | FAASt [All Regions TL - 230kV] (Vegetation) | Vegetation | Vegetation-TL | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 18022659.27 | 75789392.67 | 204576.49 | 702611.58 | 0 | 0 | 94719240.01 | 18227235.76 | 76492004.25 | y | Rene Baptiste Omar Miranda | Obligated - Amendment Pending Final Assessment or Actual Costs | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. Amendment will be needed after work completion and /or assessment completion. |  | Rene Baptiste | Obligated | 2026-03-01 18:15 | Obligated | N/A | 36917.5 | 0 |  | 36917.5 | -64317179.3 | 30099566.86 | 127486673.75 | 279159.4 | 1171019.3 | 0 | 0 | 159036419.31 | 30378726.26 | 128657693.05 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Total submitted estimated project cost is $159,036,419.31, however based on conversations with FEMA, only 38.21/402.54 miles are expected to be obligated. Costs reflect expected obligated cost with these reductions. | #REF! | #VALUE!
750063 | FAASt [Region 6 -Ponce Group A] Low Density (Vegetation) | Vegetation | Vegetation-DT | No | Pending Applicant Project Review | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16058969.33 | 43985784.19 | 481769.0799 | 1319573.5257 | 0 | 0 | 61846096.1256 | 16540738.4099 | 45305357.7157 | 16058969.33 | 43985784.19 | 481769.0799 | 1319573.5257 | 0 | 0 | 61846096.1256 | 16540738.4099 | 45305357.7157 | y | Rene Baptiste Omar Miranda | N/A | Cost were changed to aligned to the pending FEMA Obligation values. |  | Rene Baptiste | Pending Large Project Review |  | Pending Large Project Review | N/A | 191728.3 | 133176.44 |  | 324904.74 | -7494949.6944 | 18254467.11 | 50797296.22 | 289282.49 | 985459.15 | 0 | 0 | 69341045.82 | 18543749.6 | 51782755.37 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Project is pending FEMA obligation | 1 | #VALUE!
727529 | FAASt [Region 6 Ponce TL - 115kV] (Vegetation) | Vegetation | Vegetation-TL | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 7751854.11 | 26340450.42 | 95803.98 | 245287.236 | 0 | 0 | 34433395.746 | 7847658.09 | 26585737.656 | y | Rene Baptiste Omar Miranda | Obligated - Amendment Pending Final Assessment or Actual Costs | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. . Amendment will be needed after work completion and /or assessment completion. |  | Rene Baptiste | Obligated | 2026-03-01 18:15 | Obligated | N/A | 5787.03 | 0 |  | 5787.03 | 25983782.226 | 1894465.49 | 6477731.82 | 17650.9 | 59765.31 | 0 | 0 | 8449613.52 | 1912116.39 | 6537497.13 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Total submitted estimated project cost is $57,838,512.87, however based on conversations with FEMA, only 22.79/156 miles are expected to be obligated. Costs reflect expected obligated cost with these reductions. | #REF! | #VALUE!
723883 | FAASt [Region 1 -San Juan Group A] (Vegetation) | Vegetation | Vegetation-DT | Yes | Obligated, Amendment Pending Large Project Review | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 66761022.13 | 18368702.69 | 879324.5 | 2687.33 | 0 | 0 | 86011736.65 | 67640346.63 | 18371390.02 | y | Luke Samaras Omar Miranda | Obligated - Amendment Pending Final Actual Costs | Project was not listed as obligated in Col F - status has been updated to reflect correct status. Cost revised to aligned with the FEMA Obligation value from Version2 (Amendment 2 - its last amendment). |  | Rene Baptiste | Obligated | 2024-06-05 11:15 | Obligated | 11% | 12212698.92 | 11070770.35 |  | 23283469.27 | 60939644.54 | 6584889.61 | 18404524.67 | 82677.83 | 23074.58 | 0 | 0 | 25072092.11 | 6667567.44 | 18427599.25 | Amendment – Submitted to FEMA | Submitted | Obligated portion of project is currently in execution, project version pending obligation | #REF! | #VALUE!
727606 | FAASt [Region 4 Caguas TL - 115kV] (Vegetation) | Vegetation | Vegetation-TL | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 4217039.02 | 14325508.11 | 50985.56 | 133401.828 | 0 | 0 | 18726934.518 | 4268024.58 | 14458909.938 | y | Rene Baptiste Omar Miranda | Obligated - Amendment Pending Final Assessment or Actual Costs | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. . Amendment will be needed after work completion and /or assessment completion. |  | Rene Baptiste | Obligated | 2026-03-01 18:16 | Obligated | N/A | 97708.51 | 2559.18 |  | 100267.69 | 14052928.388 | 1047946.55 | 3583235.86 | 9763.81 | 33059.91 | 0 | 0 | 4674006.13 | 1057710.36 | 3616295.77 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Total submitted estimated project cost is $32,248,051.77, however based on conversations with FEMA, only 12.63/87.14 miles are expected to be obligated. Costs reflect expected obligated cost with these reductions. | #REF! | #VALUE!
956353 | FAASt [Arecibo Region 2 Line 36100 – Dos Bocas HP to Barrio Pina] (Vegetation) | Vegetation | Vegetation-TL | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 3154458.67 | 11080517.97 | 94633.76 | 332415.54 | 0 | 0 | 14662025.94 | 3249092.43 | 11412933.51 | y | Rene Baptiste Omar Miranda | Obligated - Amendment Pending Final Assessment or Actual Costs | Cost aligned to 80% of the LPCE values for this project. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; project obligations are much lower than submitted mileage, far below forecast needs. LUMA estimates 80% of miles require clearing and seeks gap funding for the mileage not covered/approved by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. . Amendment will be needed after work completion and /or assessment completion. |  | Rene Baptiste | Obligated | 2025-09-17 18:16 | Obligated | 0% | 36905.68 | 16034.81 |  | 52940.49 | 12479348.31 | 493168.61 | 1670722.97 | 4283.23 | 14502.82 | 0 | 0 | 2182677.63 | 497451.84 | 1685225.79 | Amendment – Submitted to FEMA | Submitted | Total submitted estimated project cost is $17,938,929.50, however only 10.54/30.97 miles were obligated by FEMA. Total obligated cost from FEMA reflected. Obligated portion of project is currently in execution. | #REF! | #VALUE!
727608 | FAASt [Region 1 San Juan TL - 115kV] (Vegetation) | Vegetation | Vegetation-TL | No | Pending Large Project Review | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 3698704.16 | 12571501.92 | 46746.2 | 117068.19 | 0 | 0 | 16434020.47 | 3745450.36 | 12688570.11 | y | Luke Samaras Omar Miranda | Obligated - Amendment Pending Final Assessment or Actual Costs | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. . Amendment will be needed after work completion and /or assessment completion. |  | Rene Baptiste | Obligated | 2026-03-01 18:16 | Obligated | N/A | 58830.32 | 35559.27 |  | 94389.59 | 11197183.81 | 1174137.29 | 4014718.94 | 10939.54 | 37040.89 | 0 | 0 | 5236836.66 | 1185076.83 | 4051759.83 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Total submitted estimated project cost is $27,603,651.36, however based on conversations with FEMA, only 14.13/74.48 miles are expected to be obligated. Costs reflect expected obligated cost with these reductions. | #REF! | #VALUE!
727657 | FAASt [Region 5 Mayaguez TL - 115kV] (Vegetation) | Vegetation | Vegetation-TL | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 3096774.74 | 10517290.41 | 36660.8 | 97938.99 | 0 | 0 | 13748664.94 | 3133435.54 | 10615229.4 | y | Rene Baptiste Omar Miranda | Obligated - Amendment Pending Final Assessment or Actual Costs | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. |  | Rene Baptiste | Obligated | 2026-03-01 18:16 | Obligated | N/A | 4379.07 | 0 |  | 4379.07 | 10751083.81 | 672079.74 | 2298037.25 | 6261.82 | 21202.32 | 0 | 0 | 2997581.13 | 678341.56 | 2319239.57 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Total submitted estimated project cost is $23,077,673.93, however based on conversations with FEMA, only 8.1/62.36 miles are expected to be obligated. Costs reflect expected obligated cost with these reductions. | #REF! | #VALUE!
956343 | FAASt [Ponce Region 6 Line 4800 – Toro Negro to Aibonito, Santa Isabel] (Vegetation) | Vegetation | Vegetation-TL | No | Pending Scope & Cost Completion by Applicant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3162797.958 | 8682357.558 | 262734.708 | 720921.912 | 0 | 0 | 12828812.136 | 3425532.666 | 9403279.47 | 3162797.958 | 8682357.558 | 262734.708 | 720921.912 | 0 | 0 | 12828812.136 | 3425532.666 | 9403279.47 | y | Rene Baptiste Omar Miranda | Project in V0 -Amendment Pending Final Assessment or Actual Costs | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. . Amendment will be needed after work completion and /or assessment completion. |  | Rene Baptiste | Pending Large Project Review |  | Pending Large Project Review | N/A | 913.96 | 0 |  | 913.96 | 4958586.926 | 1837079.03 | 5461799.24 | 152606.78 | 418740.16 | 0 | 0 | 7870225.21 | 1989685.81 | 5880539.4 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Total submitted estimated project cost is $22,582,890.08, however based on conversations with FEMA, only 13.86/39.77 miles are expected to be obligated. Costs reflect expected obligated cost with these reductions. | 1 | #VALUE!
956342 | FAASt [Arecibo Region 2 Line 36400 – Ponce TC to Dos Bocas HP] (Vegetation) | Vegetation | Vegetation-TL | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 2786535.15 | 9869424.87 | 83596.05 | 296082.75 | 0 | 0 | 13035638.82 | 2870131.2 | 10165507.62 | y | Rene Baptiste Omar Miranda | Obligated - Amendment Pending Final Assessment or Actual Costs | Cost aligned to 60% of the LPCE values for this project. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; project obligations are much lower than submitted mileage, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the mileage not covered/approved by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. . Amendment will be needed after work completion and /or assessment completion. |  | Rene Baptiste | Obligated | 2025-09-17 18:16 | Obligated | 0% | 11291.92 | 0 |  | 11291.92 | 8819891.69 | 952531.08 | 3226919.92 | 8275.53 | 28020.6 | 0 | 0 | 4215747.13 | 960806.61 | 3254940.52 | Amendment – Submitted to FEMA | Submitted | Total submitted estimated project cost is $21,304,288.88, however only 11.48/36.78 miles were obligated by FEMA. Total obligated cost from FEMA reflected. Obligated portion of project is currently in execution. | #REF! | #VALUE!
956339 | FAASt [Caguas Region 4 - Feeder 3301-01] (Vegetation) | Vegetation | Vegetation-DT | No | Pending Insurance Completion | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2959532.24 | 8798952.37 | 245849.34 | 674589.93 | 0 | 0 | 12678923.88 | 3205381.58 | 9473542.3 | 2959532.24 | 8798952.37 | 245849.34 | 674589.93 | 0 | 0 | 12678923.88 | 3205381.58 | 9473542.3 | y | Rene Baptiste Omar Miranda | Project in V0 -Amendment Pending Final Assessment or Actual Costs | Cost aligned to LUMA LPCE values. Amendment will be needed after project obligation. |  | Rene Baptiste | Pending Large Project Review |  | Pending Large Project Review | N/A | 249.91 | 0 |  | 249.91 | 0 | 2959532.24 | 8798952.37 | 245849.34 | 674589.93 | 0 | 0 | 12678923.88 | 3205381.58 | 9473542.3 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Project is pending FEMA obligation | 1 | #VALUE!
956332 | FAASt [San Juan Region 1 - Feeder 2401-01] (Vegetation) | Vegetation | Vegetation-DT | No | Pending EHP Review | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2787055.9 | 8286164.87 | 231521.7 | 635275.99 | 0 | 0 | 11940018.46 | 3018577.6 | 8921440.86 | 2787055.9 | 8286164.87 | 231521.7 | 635275.99 | 0 | 0 | 11940018.46 | 3018577.6 | 8921440.86 | y | Rene Baptiste Omar Miranda | Project in V0 -Amendment Pending Final Assessment or Actual Costs | Cost aligned to LUMA LPCE values. Amendment will be needed after project obligation. |  | Rene Baptiste | Pending EHP Review |  | Pending EHP Review | N/A | 47.52 | 0 |  | 47.52 | 0 | 2787055.9 | 8286164.87 | 231521.7 | 635275.99 | 0 | 0 | 11940018.46 | 3018577.6 | 8921440.86 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Project is pending FEMA obligation | 1 | #VALUE!
727659 | FAASt [Region 2 Arecibo TL - 115kV] (Vegetation) | Vegetation | Vegetation-TL | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 2669312.23 | 8989281.612 | 80079.3669 | 269678.4484 | 0 | 0 | 12008351.6573 | 2749391.5969 | 9258960.0604 | y | Rene Baptiste Omar Miranda | Obligated - Amendment Pending Final Assessment or Actual Costs | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. . Amendment will be needed after work completion and /or assessment completion. |  | Rene Baptiste | Obligated | 2026-03-01 18:16 | Obligated | N/A | 21507.48 | 102958.5 |  | 124465.98 | 7060492.4373 | 1109346.43 | 3793180 | 10335.88 | 34996.91 | 0 | 0 | 4947859.22 | 1119682.31 | 3828176.91 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Total submitted estimated project cost is $ $19,687,816.76, however based on conversations with FEMA, only 13.37/53.2 miles are expected to be obligated. Costs reflect expected obligated cost with these reductions. | #REF! | #VALUE!
727522 | FAASt [Region 3 Bayamon TL - 115kV] (Vegetation) | Vegetation | Vegetation-TL | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 2653352.966 | 8930252.562 | 79600.589 | 267907.5769 | 0 | 0 | 11931113.6938 | 2732953.555 | 9198160.1389 | y | Rene Baptiste Omar Miranda | Obligated - Amendment Pending Final Assessment or Actual Costs | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. . Amendment will be needed after work completion and /or assessment completion. |  | Rene Baptiste | Obligated | 2026-03-01 18:16 | Obligated | N/A | 28305.6 | 0 |  | 28305.6 | 7886112.7738 | 906918.96 | 3101021.26 | 8449.84 | 28610.86 | 0 | 0 | 4045000.92 | 915368.8 | 3129632.12 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Total submitted estimated project cost is $19,606,400.98 however based on conversations with FEMA, only 10.92/52.93 miles are expected to be obligated. Costs reflect expected obligated cost with these reductions. | #REF! | #VALUE!
956331 | FAASt [Mayaguez Region 5 Feeder 6014-02] (Vegetation) | Vegetation | Vegetation-DT | No | Pending EHP Review | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1977622.66 | 5879647.9 | 164281.79 | 450775.37 | 0 | 0 | 8472327.72 | 2141904.45 | 6330423.27 | 1977622.66 | 5879647.9 | 164281.79 | 450775.37 | 0 | 0 | 8472327.72 | 2141904.45 | 6330423.27 | y | Rene Baptiste Omar Miranda | Project in V0 -Amendment Pending Final Assessment or Actual Costs | Cost aligned to LUMA LPCE values. Amendment will be needed after project obligation. |  | Rene Baptiste | Pending Large Project Review |  | Pending Large Project Review | N/A | 143.61 | 0 |  | 143.61 | 0 | 1977622.66 | 5879647.9 | 164281.79 | 450775.37 | 0 | 0 | 8472327.72 | 2141904.45 | 6330423.27 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Project is pending FEMA obligation | 1 | #VALUE!
956330 | FAASt [Caguas Region 4 - Feeder 3007-03] (Vegetation) | Vegetation | Vegetation-DT | No | Pending QA Review | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1968823.15 | 5853486.17 | 163550.83 | 448769.62 | 0 | 0 | 8434629.77 | 2132373.98 | 6302255.79 | 1968823.15 | 5853486.17 | 163550.83 | 448769.62 | 0 | 0 | 8434629.77 | 2132373.98 | 6302255.79 | y | Rene Baptiste Omar Miranda | Project in V0 -Amendment Pending Final Assessment or Actual Costs | Cost aligned to LUMA LPCE values. Amendment will be needed after project obligation. |  | Rene Baptiste | Pending Large Project Review |  | Pending Large Project Review | N/A | 249.91 | 0 |  | 249.91 | 0 | 1968823.15 | 5853486.17 | 163550.83 | 448769.62 | 0 | 0 | 8434629.77 | 2132373.98 | 6302255.79 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Project is pending FEMA obligation | 1 | #VALUE!
956335 | FAASt [San Juan Region 1 - Feeder 2301-02] (Vegetation) | Vegetation | Vegetation-DT | No | Pending EHP Review | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1849955.27 | 5500081.4 | 153676.43 | 421675.11 | 0 | 0 | 7925388.21 | 2003631.7 | 5921756.51 | 1849955.27 | 5500081.4 | 153676.43 | 421675.11 | 0 | 0 | 7925388.21 | 2003631.7 | 5921756.51 | y | Rene Baptiste Omar Miranda | Project in V0 -Amendment Pending Final Assessment or Actual Costs | Cost aligned to LUMA LPCE values. Amendment will be needed after project obligation. |  | Rene Baptiste | Pending EHP Review |  | Pending EHP Review | N/A | 202.46 | 0 |  | 202.46 | 0 | 1849955.27 | 5500081.4 | 153676.43 | 421675.11 | 0 | 0 | 7925388.21 | 2003631.7 | 5921756.51 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Project is pending FEMA obligation | 1 | #VALUE!
956337 | FAASt [Mayaguez Region 5 Feeder 6012-02] (Vegetation) | Vegetation | Vegetation-DT | No | Pending EHP Review | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800712.05 | 5353676.79 | 149585.76 | 410450.73 | 0 | 0 | 7714425.33 | 1950297.81 | 5764127.52 | 1800712.05 | 5353676.79 | 149585.76 | 410450.73 | 0 | 0 | 7714425.33 | 1950297.81 | 5764127.52 | y | Rene Baptiste Omar Miranda | Project in V0 -Amendment Pending Final Assessment or Actual Costs | Cost aligned to LUMA LPCE values. Amendment will be needed after project obligation. |  | Rene Baptiste | Pending Large Project Review |  | Pending Large Project Review | N/A | 690.25 | 0 |  | 690.25 | -0.18 | 1800712.05 | 5353676.97 | 149585.76 | 410450.73 | 0 | 0 | 7714425.51 | 1950297.81 | 5764127.7 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Project is pending FEMA obligation | 1 | #VALUE!
956357 | FAASt [Mayaguez Region 5 Line 1900 – Dos Bocas HP to San Sebastian TC] (Vegetation) | Vegetation | Vegetation-TL | No | Pending Scope & Cost Completion by Applicant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879460.01 | 5159401.236 | 156127.392 | 428400.39 | 0 | 0 | 7623389.028 | 2035587.402 | 5587801.626 | 1879460.01 | 5159401.236 | 156127.392 | 428400.39 | 0 | 0 | 7623389.028 | 2035587.402 | 5587801.626 | y | Rene Baptiste Omar Miranda | Project in V0 -Amendment Pending Final Assessment or Actual Costs | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. . Amendment will be needed after work completion and /or assessment completion. |  | Rene Baptiste | Pending Final FEMA Review |  | Pending Final FEMA Review | N/A | 1054.59 | 0 |  | 1054.59 | 2093412.848 | 1290814.82 | 3837707.16 | 107228.43 | 294225.77 | 0 | 0 | 5529976.18 | 1398043.25 | 4131932.93 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Total submitted estimated project cost is $13,419,649.03, however based on conversations with FEMA, only 9.21/22.35 miles are expected to be obligated. Costs reflect expected obligated cost with these reductions. | 1 | #VALUE!
956340 | FAASt [Ponce Region 6 Feeder 5602-02] (Vegetation) | Vegetation | Vegetation-DT | No | Pending EHP Review | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1624663.76 | 4830269.73 | 134961.38 | 370322.63 | 0 | 0 | 6960217.5 | 1759625.14 | 5200592.36 | 1624663.76 | 4830269.73 | 134961.38 | 370322.63 | 0 | 0 | 6960217.5 | 1759625.14 | 5200592.36 | y | Rene Baptiste Omar Miranda | Project in V0 -Amendment Pending Final Assessment or Actual Costs | Cost aligned to LUMA LPCE values. Amendment will be needed after project obligation. |  | Rene Baptiste | Pending EHP Review |  | Pending EHP Review | N/A | 199.29 | 0 |  | 199.29 | 0 | 1624663.76 | 4830269.73 | 134961.38 | 370322.63 | 0 | 0 | 6960217.5 | 1759625.14 | 5200592.36 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Project is pending FEMA obligation | 1 | #VALUE!
956349 | FAASt [San Juan Region 1 Transmission Line 36800 – Canovanas TC to Palmer TC] (Vegetation) | Vegetation | Vegetation-TL | Yes | Obligated, Amendment Pending FEMA 406 HMP Completion | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 812052.35 | 2894107.23 | 24361.5705 | 86823.2169 | 0 | 0 | 3817344.3674 | 836413.9205 | 2980930.4469 | y | Rene Baptiste Omar Miranda | Amendment – Submitted to FEMA | Cost aligned to 80% of the LPCE values for this project. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; project obligations are much lower than submitted mileage, far below forecast needs. LUMA estimates 80% of miles require clearing and seeks gap funding for the mileage not covered/approved by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. . Amendment will be needed after work completion and /or assessment completion. |  | Rene Baptiste | Pending EHP Review | 2025-09-17 19:15 | Obligated, Pending EHP Review | 84% | 34607.3 | 158019.37 |  | 192626.67 | 1278236.0374 | 573361.58 | 1942395.21 | 5324.16 | 18027.38 | 0 | 0 | 2539108.33 | 578685.74 | 1960422.59 | Amendment – Submitted to FEMA | Submitted | Total submitted estimated project cost is $4,685,447.53, however only 3.83/11.13 miles were obligated by FEMA. Total obligated cost from FEMA reflected. Obligated portion of project is currently in execution, project version pending obligation. | #REF! | #VALUE!
956345 | FAASt [Arecibo Region 2 Line 2400 – Dos Bocas HP to Coronillas 2] (Vegetation) | Vegetation | Vegetation-TL | No | Pending Scope & Cost Completion by Applicant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1083485.898 | 2974332.24 | 90005.55 | 246967.614 | 0 | 0 | 4394791.302 | 1173491.448 | 3221299.854 | 1083485.898 | 2974332.24 | 90005.55 | 246967.614 | 0 | 0 | 4394791.302 | 1173491.448 | 3221299.854 | y | Rene Baptiste Omar Miranda | Obligated -Amendment Pending Final Assessment or Actual Costs | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. . Amendment will be needed after work completion and /or assessment completion. |  | Rene Baptiste | Pending Award |  | Pending Award | N/A | 938.25 | 0 |  | 938.25 | 1995116.542 | 560135.46 | 1665332.49 | 46530.65 | 127676.16 | 0 | 0 | 2399674.76 | 606666.11 | 1793008.65 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Total submitted estimated project cost is $7,736,264.86, however based on conversations with FEMA, only 4.02/12.96 miles are expected to be obligated. Costs reflect expected obligated cost with these reductions. | 1 | #VALUE!
956356 | FAASt [Ponce Region 6 Transmission Line 39000 – Aguas Buenas Substation to Hacienda San Jose] (Vegetation) | Vegetation | Vegetation-TL | Yes | Obligated, Amendment Pending Award | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 302418.26 | 690456.65 | 9072.54 | 20713.7 | 0 | 0 | 1022661.15 | 311490.8 | 711170.35 | y | Luke Samaras Omar Miranda | Obligated - Amendment Pending Final Actual Costs | Project was not listed as obligated in Col F - status has been updated to reflect correct status. Cost was changed to 60% of total LPCE values. . Amendment will be needed after work completion. |  | Rene Baptiste | Obligated | 2025-09-17 19:15 | Obligated | 95% | 37730.8 | 126497.04 |  | 164227.84 | 559239.84 | 102333.57 | 346668.94 | 3287.5 | 11131.3 | 0 | 0 | 463421.31 | 105621.07 | 357800.24 | Amendment – Submitted to FEMA | Submitted | Total submitted estimated project cost is $474,552.61, however only .913/2.82 miles were obligated by FEMA. Total obligated cost from FEMA reflected. Obligated portion of project is currently in execution, project version pending obligation. | #REF! | #VALUE!
956348 | FAASt [Bayamon Region 3 Line 10000 – Bayamon Pueblo to Magnolia TO] (Vegetation) | Vegetation | Vegetation-TL | No | Pending Scope & Cost Completion by Applicant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176585.496 | 484753.794 | 14669.028 | 40250.52 | 0 | 0 | 716258.838 | 191254.524 | 525004.314 | 176585.496 | 484753.794 | 14669.028 | 40250.52 | 0 | 0 | 716258.838 | 191254.524 | 525004.314 | y | Rene Baptiste Omar Miranda | Obligated -Amendment Pending Final Assessment or Actual Costs | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. . Amendment will be needed after work completion and /or assessment completion. |  | Rene Baptiste | Pending Award |  | Pending Award | N/A | 543.47 | 0 |  | 543.47 | 373806.048 | 79935.82 | 237656.27 | 6640.3 | 18220.4 | 0 | 0 | 342452.79 | 86576.12 | 255876.67 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Total submitted estimated project cost is $1,260,848.93, however based on conversations with FEMA, only 0.66/2.43 miles are expected to be obligated. Costs reflect expected obligated cost with these reductions. | 1 | #VALUE!
551925 | FAASt [SCADA Remote Access and RTU Replacements Group 1] (Telecommunication) | Telecommunication | IT/OT | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 7507076.66 | 1853362.06 | 1043403.42 | 266016.14 | 0 | 0 | 10669858.28 | 8550480.08 | 2119378.2 | Y | PM | Amendment submitted to FEMA April 7, 2026 | Split revised 428/406 , 1 additional site was included + Rooftop repairs costs submitted in the amendment to address actual cost. E&M changed to 0. | EM should be 0 | Sandra Valentin/Axel Rodriguez | Pending Amendment Request Approval | 2024-11-01 15:15 | Obligated, Pending Amendment Request Approval | 94% | 3719832.13 | 4281135.16 |  | 8000967.29 | -80233.3967 | 7266305.24 | 1694442.12 | 1060764.2767 | 273088.36 | 264479.04 | 191012.64 | 10750091.6767 | 8591548.5567 | 2158543.12 | Amendment – Submitted to COR3/PREPA | Submitted | 428/206 split revised, 1 additional site was included in the submitted amendment. | #REF! | #VALUE!
956341 | FAASt [Ponce Region 6 Feeder 5803-02] (Vegetation) | Vegetation | Vegetation-DT | No | Pending EHP Review | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41293.37 | 52055.36 | 3165.6 | 4323.45 | 0 | 0 | 100837.78 | 44458.97 | 56378.81 | 41293.37 | 52055.36 | 3165.6 | 4323.45 | 0 | 0 | 100837.78 | 44458.97 | 56378.81 | y | Rene Baptiste Omar Miranda | Project in V0 -Amendment Pending Final Assessment or Actual Costs | Cost aligned to LUMA LPCE values. Amendment will be needed after project obligation. |  | Rene Baptiste | Pending Award |  | Pending Award | N/A | 249.91 | 0 |  | 249.91 | -2323.1 | 24080 | 71591.83 | 2000.35 | 5488.7 | 0 | 0 | 103160.88 | 26080.35 | 77080.53 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Project is pending FEMA obligation | 1 | #VALUE!
673292 | FAASt Telecom Infrastructure - Cerro Puntas (Telecommunication) | Telecommunication | IT/OT | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 8138862.31 | 39069.68 | 1076416.55 | 3866.5 | 0 | 0 | 9258215.04 | 9215278.86 | 42936.18 | Y | PM | Amendment Expected | Design Package expected Jun 2026. E&M changed to 0. | EM should be 0 | Sandra Valentin/Axel Rodriguez | Obligated | 2025-10-30 20:15 | Obligated | 0% | 865333.82 | 56242.57 |  | 921576.39 | 4293.7712 | 8124106.79 | 44186.4888 | 1075319.59 | 4963.76 | 4917.0688 | 427.5712 | 9253921.2688 | 9204343.4488 | 49577.82 | Amendment – Pending Design Package for Development | Q1 FY2027 | Design Package expected Jun 2026. | #REF! | #VALUE!
551926 | FAASt [SCADA Remote Access and RTU Replacements Group 2] (Telecommunication) | Telecommunication | IT/OT | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 5664186.55 | 939009.1711 | 800287.41 | 134453.44 | 0 | 0 | 7537936.5711 | 6464473.96 | 1073462.6111 | Y | PM | Amendment - In process | Amendment to be submitted to include the 428/406 split and actual cost. | EM should be 0 | Sandra Valentin/Axel Rodriguez | Obligated | 2026-03-01 18:16 | Obligated | N/A | 1382619.44 | 187936.6 |  | 1570556.04 | 0.002146 | 5267467.9889 | 939009.17 | 800287.4104 | 134453.4396 | 396718.56 | 0 | 7537936.5689 | 6464473.9594 | 1073462.6096 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Q1 FY2027 | Pending FEMA Obligation, currently in Phase 5. | #REF! | #VALUE!
657300 | FAASt ENERGY MANAGEMENT SYSTEM (EMS) (Telecom) | Telecommunication | IT/OT | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 36900874.92 | 29069659.63 | 2477105.02 | 1951041.22 | 0 | 0 | 70398680.79 | 39377979.94 | 31020700.85 | Y | PM | Amendment submitted to FEMA March 30, 2026 | Amendment included the revision of the 428/406 split and cost update reflecting the current cost. E&M changed to 0. | EM should be 0 | Sandra Valentin/Axel Rodriguez | Pending Amendment Request Approval | 2022-10-17 11:37 | Obligated, Pending Amendment Request Approval | 95% | 15765664.41 | 9905570.55 |  | 25671234.96 | 0 | 36457328.36 | 28655579.63 | 2477105.02 | 1951041.22 | 443546.56 | 414080 | 70398680.79 | 39377979.94 | 31020700.85 | Amendment – Submitted to COR3/PREPA | Submitted | Amendment submitted Feb 12, 2026 | #REF! | #VALUE!
756999 | FAASt [TL 1900 Lares TO to San Sebastian] (Transmission) | Transmission | Transmission Line Rebuild | No | Pending Scope & Cost Completion by Applicant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29020727.34 | 6217908.83 | 2251104.25 | 556753.47 | 2446381.79 | 1784156.92 | 42277032.6 | 33718213.38 | 8558819.22 | 29020727.34 | 6217908.83 | 2251104.25 | 556753.47 | 2446381.79 | 1784156.92 | 42277032.6 | 33718213.38 | 8558819.22 | Y | Nelson Torres | Project in V0 - No amendment required at this time | The DSOW revision has been submitted to FEMA | Revision needed for the 406 without A&E and E&M column. |  | Pending PDMG Scope & Cost Routing |  | Pending PDMG Scope & Cost Routing | N/A | 324845.85 | 0 |  | 324845.85 | 6180314.37 | 25335445.6 | 4067258.81 | 2040875.23 | 429319.88 | 2446381.79 | 1777436.92 | 36096718.23 | 29822702.62 | 6274015.61 | DSOW – Submitted to COR3/PREPA | Submitted | Already Submitted | 1 | #VALUE!
797148 | FAASt [Feeder Rebuild # 8101-03] (Distribution) | Distribution | Feeders | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 3243578.94 | 76998.98 | 678369.17 | 29445.05 | 424402 | 41009.75 | 4493803.89 | 4346350.11 | 147453.78 | Y | Jorge Lopez Burgos | Ammendment submitted to FEMA needs to be adjusted with new estimate cost | The project obligation was based on a Class 3 estimate. Project will be versioned prior to close out (Final Amendment). Current A/E & Planning costs are higher than the initial estimate ($951.9K). This variance will be mitigated as part of the Final amendment during project versioning prior to closeout. | Los costos presentados en la partida 406 no cuadran con lo presentado en el CE incluido en la enmienda. | Amaury Pacheco | Pending PDMG Scope & Cost Routing | 2025-09-17 18:16 | Obligated, Pending PDMG Scope & Cost Routing | 0% | 1659779.01 | 99204.99 |  | 1758984 | 910634.76 | 2174764.98 | 235072.1 | 641910.96 | 66287.34 | 431054.74 | 34079.01 | 3583169.13 | 3247730.68 | 335438.45 | Amendment – Submitted to FEMA | Submitted | Working on re-versioning (PA-428 & HM-406 already submitted to FEMA), attending soft RFI received from FEMA, to be submitted to FEMA on Mar 2026 | #REF! | #VALUE!
801172 | FAASt [Feeder Rebuild # 1529-15] (Distribution) | Distribution | Feeders | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 2621409.16 | 242729.86 | 538090.23 | 52278.72 | 135020.88 | 39130.64 | 3628659.49 | 3294520.27 | 334139.22 | Y | Jorge Lopez Burgos | Ammendment submitted to FEMA needs to be adjusted with new estimate cost | The project was fully obligated under Section 428 using the Class 3 estimate. Versioning was submitted, including the split between 428 and 406, and it is currently under FEMA evaluation. The final DSOW versioning will be submitted, reflecting an additional $835,029 to the approved budget. | Verificar los costos totales presentados en 406, (Columna Z) ya que duplica los costos incluidos en la revisión del estimado preparado para la enmienda | Amaury Pacheco | Pending Amendment Processing | 2025-09-17 18:16 | Obligated, Pending Amendment Processing | 0% | 1425398.04 | 51437.79 |  | 1476835.83 | 936074.69 | 1862738.37 | 50953.86 | 568090.34 | 22194.71 | 160515.06 | 28092.46 | 2692584.8 | 2591343.77 | 101241.03 | Amendment – Submitted to FEMA | Submitted | Working on re-versioning (PA-428 & HM-406 already submitted to FEMA), to be submitted to FEMA on Feb 2026 | #REF! | #VALUE!
681672 | FAASt Transmission Priority Pole Replacements 2300 | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 835010.89 | 2243 | 0 | 699 | 0 | 0 | 837952.89 | 835010.89 | 2942 | Y | Carlos Samalot | Obligated - Amendment Pending Final Actual Costs | This information reflects the latest LPCE data provided and includes the actuals delta. The final cost will be taken into consideration during the project reconciliation and close-out. | Information confirmed with PM |  | Obligated | 2023-01-31 12:56 | Obligated | 90% | 389270.4 | 443970.12 |  | 833240.52 | 489956.8 | 271850.8 | 4298.39 | 27464.76 | 560.49 | 41708.61 | 2113.04 | 347996.09 | 341024.17 | 6971.92 | Obligated -No expected changes | N/A | No Amendment Needed | #REF! | #VALUE!
817956 | FAASt [Feeder Rebuild # 1303-02] (Distribution) | Distribution | Feeders | Yes | Obligated | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 2783776.04 | 37150.77 | 631442.21 | 8316.85 | 78644.98 | 21278.54 | 3560609.39 | 3493863.23 | 66746.16 | Y | Jorge Lopez Burgos | Ammendment submitted to FEMA needs to be adjusted with new estimate cost | Project was obligated full 428 with Class 3 estimate, versioning was submitted including split 428/406, Under FEMA evaluation. Current A/E & Planning costs are higher than the initial estimate ($681.6K). This variance will be mitigated as part of the Final amendment during project versioning prior to closeout. | Verificar los costos totales presentados en 406, (Columna Z) ya que duplica los costos incluidos en la revisión del estimado preparado para la enmienda | Amaury Pacheco | Pending Amendment Request Approval | 2025-09-25 17:15 | Obligated, Pending Amendment Request Approval | 0% | 1161981.66 | 12376.72 |  | 1174358.38 | 830872.86 | 2102127.04 | 7555.38 | 513368.91 | 6761.68 | 78644.98 | 21278.54 | 2729736.53 | 2694140.93 | 35595.6 | Amendment – Submitted to COR3/PREPA | Q4 FY2026 |  | #REF! | #VALUE!
[6 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 3101276218.1113 | 1922691316.131 | 348523507.4541 | 156084931.0821 | 444008908.4061 | 321809581.6666 | 6294394462.8512 | 3893808633.9716 | 2400585828.8796 | [6 empty] | 0 | 11375904.1514 | 0 | 147.29 | 374101728.56 | 760890947.84 | 129931.98 | 1135122608.38 | 632178637.3524 | 3035704041.1365 | 1701407212.3368 | 349129466.0157 | 90824442.8178 | 293981332.0697 | 200575645.3054 | 5662215825.4988 | 3678814839.2219 | 1992807300.4599
S
Note on AE255: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Based on 100% submitted miles in the project/LPCE costs - update to 60% for each transmission project Add comments to Col AK to indicate changes were made

## Attachment A Withdrawn_TEST (hidden)
[9 empty] | Estimate Project Costs Allocation (Update) | [8 empty] | Confirmation and Comments |  |  |  |  | PREB Response numbers ( Do not update)
Project # | Title | Should we include the project in the (New List) ? | Submitted to PREPA (Yes/No) | Asset | Sub Asset | Obligated (Yes / No) | Activated by PREPA (Active / Inactive) | Activated by FEMA (Active / Inactive) | 428 Estimate (Without the A&E and E&M) | 406 Estimate (Without the A&E and E&M) | 428 A&E Estimate-PW 9510 | 406 A&E Estimate -PW 9510 | 428 E&M Estimate -PW 10710 | 406 E&M Estimate -PW 10710 | Expected Total Project Estimate Cost | Total 428 Estimate Cost | Total 406 Estimate Cost | Estimate/Cost change (Y/N) | Who confirmed the information? | Obligation Amendment Status | New Comment | Updated Comments | 428 Allocation (Without the A&E and E&M) | 406 Allocation (Without the A&E and E&M) | 428 A&E-PW 9510 | 406 A&E-PW 9510 | 428 E&M-PW 10710 | 406 E&M-PW 10710 | Expected Total Project Cost | Total 428 Expected Cost | Total 406 Expected Cost | Project Status | Expected COR3 Submission Date | Comments | Total NEW LIST | PREPA Note: Cost incurred as reported by LUMA. | Projects Added Flag
401432 | FAASt [Automation Program Group 41 | No | No | Distribution | Automation | No | Inactive | Inactive | No | No | Distribution | Automation | No | Inactive | Inactive | 1469610 | 462655 | 190505 | 381010 | 2721500 | 1796190 | 925310 | [14 empty] | 0
688623 | FAASt [Automation Program Group 1A-8 Feeders] (Distribution) | No | No | Distribution | Automation | No | Inactive | Inactive | No | No | Distribution | Automation | No | Inactive | Inactive | 15682783.16 | 2926805 | 3708204.4 | 2410310 | 28486560.16 | 22632950.16 | 5853610 | 3591270 | 1130585 | 332525 | 199515 | 465535 | 931070 | 6650500 | 4389330 | 2261170 | DSOW – Pending Design Package for Development | Q3 FY2027 | Estimate date for the work to be completed portion only. The estimated total per project is considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (23) 3PH Reclosers, (104) 1ph reclosers, (48) cFCi. | 0 | 360903.9102 | 1
705657 | [Automation Program Group 3] (TL/Distribution | No | No | Distribution | Automation | No | Inactive | Inactive | No | No | Distribution | Automation | No | Inactive | Inactive | 30089122.78 | 4299385 | 6881478.06 | 3540670 | 52833490.45 | 44234720.45 | 8598770 | 13656870 | 4299385 | 1264525 | 758715 | 1770335 | 3540670 | 25290500 | 16691730 | 8598770 | DSOW – Pending Design Package for Development | Q3 FY2027 | Estimate date for the work to be completed portion only. The estimated total per project is considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (99) 3PH Reclosers, (316) 1ph reclosers, (212) cFCi. | 0 | 1235166.9496 | 1
800394 | Automation Program Group 39 (Distribution) | Yes | Yes | Distribution | Automation | No | Inactive | Inactive | Yes | Yes | Distribution | Automation | No | Inactive | Inactive | 1256040 | 395420 | 162820 | 325640 | 2326000 | 1535160 | 790840 | [14 empty] | 1
740662 | [Automation Program Group 2] (TL/ Distribution | No | No | Distribution | Automation | No | Inactive | Inactive | No | No | Distribution | Automation | No | Inactive | Inactive | 36782398.44 | 6876500 | 6850965.04 | 5663000 | 63664054.5 | 49911054.5 | 13753000 | 21843000 | 6876500 | 2022500 | 1213500 | 2831500 | 5663000 | 40450000 | 26697000 | 13753000 | DSOW – Pending Design Package for Development | Q3 FY2027 | Estimate date for the work to be completed portion only. The estimated total per project is considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (145) 3PH Reclosers, (539) 1ph reclosers, (254) cFCi. | 0 | 2546994.6399 | 0
741678 | [Automation Program Group 4] (TL/Distribution | No | No | Distribution | Automation | No | Inactive | Inactive | No | No | Distribution | Automation | No | Inactive | Inactive | 29500343.61 | 5347180 | 6946880.68 | 4403560 | 51561909.74 | 40867549.74 | 10694360 | 16985160 | 5347180 | 1572700 | 943620 | 2201780 | 4403560 | 31454000 | 20759640 | 10694360 | DSOW – Pending Design Package for Development | Q3 FY2027 | Estimate date for the work to be completed portion only. The estimated total per project is considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (117) 3PH Reclosers, (247) 1ph reclosers, (182) cFCi. | 0 | 1802599.6427 | 0
745851 | FAASt [Automation Program Group 11 | No | No | Distribution | Automation | No | Inactive | Inactive | No | No | Distribution | Automation | No | Inactive | Inactive | 720630 | 226865 | 93415 | 186830 | 1334500 | 880770 | 453730 | [14 empty] | 0
745852 | FAASt [Automation Program Group 13 | No | No | Distribution | Automation | No | Inactive | Inactive | No | No | Distribution | Automation | No | Inactive | Inactive | 897480 | 282540 | 116340 | 232680 | 1662000 | 1096920 | 565080 | [14 empty] | 1
745854 | FAASt [Automation Program Group 9 | No | No | Distribution | Automation | No | Inactive | Inactive | No | No | Distribution | Automation | No | Inactive | Inactive | 589140 | 185470 | 76370 | 152740 | 1091000 | 720060 | 370940 | [14 empty] | 0
745871 | FAASt [Automation Program Group 10 | No | No | Distribution | Automation | No | Inactive | Inactive | No | No | Distribution | Automation | No | Inactive | Inactive | 713610 | 224655 | 92505 | 185010 | 1321500 | 872190 | 449310 | [14 empty] | 0
800369 | FAASt [Automation Program Group 38 | No | No | Distribution | Automation | No | Inactive | Inactive | No | No | Distribution | Automation | No | Inactive | Inactive | 802170 | 252535 | 103985 | 207970 | 1485500 | 980430 | 505070 | [14 empty] | 1
800399 | FAASt [Automation Program Group 40 | No | No | Distribution | Automation | No | Inactive | Inactive | No | No | Distribution | Automation | No | Inactive | Inactive | 1536300 | 483650 | 199150 | 398300 | 2845000 | 1877700 | 967300 | [14 empty] | 1
801437 | FAASt [Automation Program Group 42 | No | No | Distribution | Automation | No | Inactive | Inactive | No | No | Distribution | Automation | No | Inactive | Inactive | 604800 | 190400 | 78400 | 156800 | 1120000 | 739200 | 380800 | [14 empty] | 0
801438 | FAASt [Automation Program Group 43 | No | No | Distribution | Automation | No | Inactive | Inactive | No | No | Distribution | Automation | No | Inactive | Inactive | 851580 | 268090 | 110390 | 220780 | 1577000 | 1040820 | 536180 | [14 empty] | 0
801440 | FAASt [Automation Program Group 44 | No | No | Distribution | Automation | No | Inactive | Inactive | No | No | Distribution | Automation | No | Inactive | Inactive | 597510 | 188105 | 77455 | 154910 | 1106500 | 730290 | 376210 | [14 empty] | 0
801441 | FAASt [Automation Program Group 45 | No | No | Distribution | Automation | No | Inactive | Inactive | No | No | Distribution | Automation | No | Inactive | Inactive | 1221750 | 384625 | 158375 | 316750 | 2262500 | 1493250 | 769250 | [14 empty] | 0
757945 (1066739) | Distribution Pole and Conductor Repair - Arecibo Group 3 – Phase 2 | Yes | Yes | Distribution | Distribution Pole and Conductor Repair | No | Active | Active | Yes | Yes | Distribution | Distribution Pole and Conductor Repair | No | Active | Active | 2039409.93 | 366564.02 | 173097.79 | 69460.21 | 2866135.41 | 2394287.42 | 471847.99 | [14 empty] | 1
790427 (1066737) | Distribution Pole and Conductor Repair - Caguas Group 5 - Phase 2 | Yes | Yes | Distribution | Distribution Pole and Conductor Repair | No | Active | Active | Yes | Yes | Distribution | Distribution Pole and Conductor Repair | No | Active | Active | 7591896.49 | 32126 | 515199.89 | 211384.11 | 9044328.18 | 8780588.61 | 263739.57 | [14 empty] | 0
790446 (1066740) | Distribution Pole and Conductor Repair – Caguas Group 4 – Phase 2 | Yes | Yes | Distribution | Distribution Pole and Conductor Repair | No | Active | Active | Yes | Yes | Distribution | Distribution Pole and Conductor Repair | No | Active | Active | 3867419.78 | 16119.41 | 258899.2 | 105879.8 | 4601164.07 | 4469032.15 | 132131.92 | [14 empty] | 1
806935 (1066738) | Distribution Pole and Conductor Repair - Caguas Group 6 - Phase 2 | Yes | Yes | Distribution | Distribution Pole and Conductor Repair | No | Active | Active | Yes | Yes | Distribution | Distribution Pole and Conductor Repair | No | Active | Active | 7262006.01 | 330225.13 | 509451.1 | 208755.9 | 9000748.55 | 8416996.81 | 583751.74 | [14 empty] | 1
817249 (1066741) | Distribution Pole and Conductor Repair – Caguas Group 7 – Phase 2 | Yes | Yes | Distribution | Distribution Pole and Conductor Repair | No | Active | Active | Yes | Yes | Distribution | Distribution Pole and Conductor Repair | No | Active | Active | 4608333 | 284709.51 | 381146.2 | 153938.8 | 5874102.62 | 5399414.95 | 474687.67 | [14 empty] | 1
738671 | FAASt [25 MW BESS Installation and Integration - Barceloneta] (Substation) | Yes | No | Substations | Grid Modernization | No | Inactive | Inactive | Yes | No | Substations | Grid Modernization | No | Inactive | Inactive | 0 | 20318919.35 | 0 | 30411453.8 | 55941767.5 | 0 | 55941767.5 |  | 20318919.35 |  | 5211394.35 |  | 30411453.8 | 55941767.5 | 0 | 55941767.5 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | 406 HM Split 100% As it was last submitted to FEMA | Inactive | 437835.2415 | 1
750502 | FAASt [25 MW BESS Installation and Integration - Aguadilla] (Substation) | Yes | No | Substations | Grid Modernization | No | Inactive | Inactive | Yes | No | Substations | Grid Modernization | No | Inactive | Inactive | 0 | 21118171.64 | 0 | 28261718.24 | 52720520.35 | 0 | 52720520.35 |  | 21118171.64 | 0 | 3340630.47 | 0 | 28261718.24 | 52720520.35 | 0 | 52720520.35 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | 406 HM Split 100% As it was last submitted to FEMA | Inactive | 516373.7564 | 0
750503 | FAASt [25 MW BESS Installation and Integration - San Juan] (Substation) | Yes | No | Substations | Grid Modernization | No | Inactive | Inactive | Yes | No | Substations | Grid Modernization | No | Inactive | Inactive | 0 | 24053536.03 | 0 | 28261718.24 | 55503065.56 | 0 | 55503065.56 |  | 24053536.03 | 0 | 3187811.29 | 0 | 28261718.24 | 55503065.56 | 0 | 55503065.56 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | 406 HM Split 100% As it was last submitted to FEMA. Contingent to FEMA Hazard Mitigation Evaluation and approval. | Inactive | 341109.662 | 0
752972 | FAASt [4 x 25 MW BESS Interconnections Manati] (Substation) | Yes | No | Substations | Grid Modernization | No | Inactive | Inactive | Yes | No | Substations | Grid Modernization | No | Inactive | Inactive | 0 | 23808829.62 | 0 | 30416253.08 | 57640005.67 | 0 | 57640005.67 |  | 23808829.62 | 0 | 3414922.97 | 0 | 30416253.08 | 57640005.67 | 0 | 57640005.67 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | 406 HM Split 100% As it was last submitted to FEMA | Inactive | 246353.4254 | 0
679035 | Telecomm Infrastructure Group A | N/A | Yes | Telecommunication | IT/OT | No | Inactive | Inactive | Yes | Yes | Telecommunication | IT/OT | No | Inactive | Inactive | 6440145.54 | 15927.16 | 2800 | 0 | 8219456.35 | 8199354.01 | 20102.34 | [14 empty] | 1
704805 | Telecomm Infrastructure Group D | N/A | Yes | Telecommunication | IT/OT | No | Inactive | Inactive | Yes | Yes | Telecommunication | IT/OT | No | Inactive | Inactive | 5297451.62 | 18959.16 | 0 | 0 | 6002699.02 | 5981241.79 | 21457.23 | [14 empty] | 1
551927 (1066731) | SCADA Remote Access and RTU Replacements Group 3 | N/A | Yes | Telecommunication | IT/OT | No | Active | Active | Yes | Yes | Telecommunication | IT/OT | No | Active | Active | 18668671.07 | 3375608.8 | 1293008.64 | 0 | 26233521.55 | 22432233.99 | 3801287.56 | [14 empty] | 1
N/A | Fiber Optic Replacement Group 1 | N/A | Yes | Telecommunication | IT/OT | No | Inactive | Inactive | Yes | Yes | Telecommunication | IT/OT | No | Inactive | Inactive | 67811581.03 | 9902187.96 | 108101.8 | 0 | 85606056 | 74755371.24 | 10850684.76 | [14 empty] | 1
718971 | FAASt [Line 50300 (230kV) from Costa Sur Steam Plant to Aguirre Steam Plant] (Transmission) | No | No | Transmission | Line Rebuild | No | Inactive | Inactive | No | No | Transmission | Line Rebuild | No | Inactive | Inactive | 9936000 | 5400000 | 1296000 | 3240000 | 21600000 | 12096000 | 9504000 | 9936000 | 5400000 | 864000 | 864000 | 1296000 | 3240000 | 21600000 | 12096000 | 9504000 | DSOW – Pending Design Package for Development | Q3 FY2027 | This line is key for hardening by replacing targeted structures as well as insulators and hardware along the entire line length, with a high-level estimate at $30M. Additional future scope proposed for 406 includes adding a 230/115kV new substation at Santa Isabel TC which would significantly reduce the exposure (probability and likelihood that the facility is not available after a storm) as well as facilitate a pathway for new large-scale renewables being added in the South and Southeast regions. | 0 | 460702.448 | 1
730657 | [Line 2200 Dos Bocas HP to Dorado TC ] (Transmission | No | No | Transmission | Line Rebuild | No | Inactive | Inactive | No | No | Transmission | Line Rebuild | No | Inactive | Inactive | 57872010.7354 | 31452179.7475 | 7548523.1394 | 18871307.8485 | 125808718.99 | 70452882.6344 | 55355836.3556 | 57872010.7354 | 31452179.7475 | 5032348.7596 | 5032348.7596 | 7548523.1394 | 18871307.8485 | 125808718.99 | 70452882.6344 | 55355836.3556 | DSOW – Pending Design Package for Development | Q3 FY2027 | The planned scope for this facility is first to rebuild the undersized segment from Manati to Vega Baja to achieve a capacity increase to a minimum of 1160A. The proposed second phase is to restore the out-of-service segment from Dos Bocas to Cambalache. As requested by PMs based on latest value engineering, 3 segments were selected (1, 7 & 8) | 0 | 8149571.0366 | 1
TBD36 | Tline 8700 / TL1100 | No | No | Transmission | Line Rebuild | No | Inactive | Inactive | No | No | Transmission | Line Rebuild | No | Inactive | 40000000 | 40000000 | 0 | 0 | 0 | 40000000 | 40000000 | 0 | [14 empty] | 1
9510 | PBUT34 - Islandwide Feeder Assessments | No | No |  | not found | No | Inactive | Inactive | Not Found | Not Found | Not Found | Not Found | Not Found | Not Found | Not Found | Not Found | Not Found | not found | not found | not found | not found | not found | [14 empty] | 1
9510 | A&E costs reimbursed related to projects without child | not found | No |  | not found | No | Inactive | Inactive | Not Found | Not Found | Not Found | Not Found | Not Found | Not Found | Not Found | Not Found | Not Found | not found | not found | not found | not found | not found | [14 empty] | 1
10710 | Reclosers - Without child project (Equipment purchased) | Yes, only E&M | No |  | not found | No | Inactive | Inactive | Not Found | Not Found | Not Found | Not Found | Not Found | Not Found | Not Found | Not Found | Not Found | not found | not found | not found | not found | not found | [14 empty] | 0
748180 (TBD) | Transmission Advanced Sensors and Wide-Area Monitoring, Protection, and Control (WAMPAC) System | Yes | Yes | Telecommunication | not found | No | Active | Inactive | Not Found | Not Found | Not Found | Not Found | Not Found | Not Found | Not Found | Not Found | Not Found | not found | not found | not found | not found | not found | 33071971.884 | 4086750.8114 | 4724567.412 | 472456.7412 | 3307197.1884 | 1417370.2236 | 47080314.2606 | 41103736.4844 | 5976577.7762 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 |  | Not Found | #N/A | 1
TBD35 | Poles- Included in the E&M without child (Poles paid) | not found |  |  | not found | No | Inactive | Inactive | Not Found | Not Found | Not Found | Not Found | Not Found | Not Found | Not Found | Not Found | Not Found | not found | not found | not found | not found | not found | [14 empty] | 1
764705 | [Feeder Rebuild # 6014-02] (Distribution | No | No | Distribution | Rebuild | No | Inactive | Inactive | No | No | Distribution | Rebuild | No | Inactive | Inactive | 23763600 | 688800 | 2066400 | 344400 | 34440000 | 33062400 | 1377600 | 23763600 | 688800 | 7232400 | 344400 | 2066400 | 344400 | 34440000 | 33062400 | 1377600 | DSOW – Pending Design Package for Development | FY2029 | Design is about 52% complete. This project is currently classified as withdrawn (T1) and covers 8.20 miles with 343 structures. DSOW – Waiting on the design package to be developed. | 0 | 1973511.253 | 1
764707 | [Feeder Rebuild # 6012-02] (Distribution | No | No | Distribution | Rebuild | No | Inactive | Inactive | No | No | Distribution | Rebuild | No | Inactive | Inactive | 16634520 | 482160 | 1446480 | 241080 | 24108000 | 23143680 | 964320 | 16634520 | 482160 | 5062680 | 241080 | 1446480 | 241080 | 24108000 | 23143680 | 964320 | DSOW – Pending Design Package for Development | FY2029 | Design is about 39% complete. This project is currently classified as withdrawn (T1) and covers 5.74 miles with 239 structures. DSOW – Waiting on the design package to be developed. | 0 | 1046942.5037 | 1
767381 | [Feeder Rebuild # 1204-05] (Distribution | No | No | Distribution | Rebuild | No | Inactive | Inactive | No | No | Distribution | Rebuild | No | Inactive | Inactive | 3880428.29 | 112476.18 | 337428.55 | 56238.09 | 5623809.12 | 5398856.76 | 224952.36 | [14 empty] | 1
767387 | [Feeder Rebuild # 1303-01] (Distribution | No | No | Distribution | Rebuild | No | Inactive | Inactive | No | No | Distribution | Rebuild | No | Inactive | Inactive | 5013491.62 | 145318.6 | 435955.79 | 72659.3 | 7265929.89 | 6975292.69 | 290637.2 | [14 empty] | 1
812041 | [Feeder Rebuild # 9501-02] (Distribution | No | No | Distribution | Rebuild | No | Inactive | Inactive | No | No | Distribution | Rebuild | No | Inactive | Inactive | 22571513.15 | 0 | 3357740.92 | 0 | 29244075.05 | 29244075.05 | 0 | [14 empty] | 1
817961 | [Feeder Rebuild # 2404-06] (Distribution | No | No | Distribution | Rebuild | No | Inactive | Inactive | No | No | Distribution | Rebuild | No | Inactive | Inactive | 18825472.43 | 399260.06 | 692201.89 | 82130.27 | 21876035.66 | 21344413.72 | 531621.94 | [14 empty] | 1
666894 | FAASt [San Juan Streetlighting] (Distribution) | N/A | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 28178017.76 | 2123472.21 | 0 | 0 | 36805217.53 | 34558587.8 | 2246629.73 | 27201946.76 | 1465463.21 | 6380570.04 | 123157.52 | 976071 | 658009 | 36805217.53 | 34558587.8 | 2246629.73 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. | 0 | 1973811.207 | 0
671396 | FAASt [Utuado Streetlighting] (Distribution) | N/A | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 16760927.205 | 2851675.47 | 0 | 0 | 23087545.995 | 20080797.925 | 3006748.07 | 15515918.205 | 2012364.47 | 3319870.72 | 155072.6 | 1245009 | 839311 | 23087545.995 | 20080797.925 | 3006748.07 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. | 0 | 664704.356 | 1
671400 | FAASt [Barceloneta Streetlighting] (Distribution) | N/A | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 7422038.0375 | 477869.14 | 0 | 0 | 9156776.6775 | 8628601.5375 | 528175.14 | 7024652.0375 | 209975.14 | 1206563.5 | 50306 | 397386 | 267894 | 9156776.6775 | 8628601.5375 | 528175.14 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. | 0 | 416323.1767 | 1
678794 | FAASt [Ponce Streetlighting] (Distribution) | N/A | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 10968715.275 | 884181.41 | 0 | 0 | 13617755.605 | 12681857.195 | 935898.41 | 10629532.275 | 655524.41 | 1713141.92 | 51717 | 339183 | 228657 | 13617755.605 | 12681857.195 | 935898.41 | DSOW – Scope and Cost Update in Progress | Q2 FY2027 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. | 0 | 697311.1311 | 0
678795 | FAASt [Arecibo Streetlighting] (Distribution) | N/A | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 11879105.0925 | 800134.36 | 0 | 0 | 14640815.1925 | 13781320.8325 | 859494.36 | 11412143.0925 | 485336.36 | 1902215.74 | 59360 | 466962 | 314798 | 14640815.1925 | 13781320.8325 | 859494.36 | DSOW – Scope and Cost Update in Progress | Q1 FY2027 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. | 0 | 646048.0917 | 1
686482 | FAASt [Isabela Streetlighting] (Distribution) | N/A | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 6005455.39 | 671912.08 | 0 | 0 | 8048135.87 | 7338425.99 | 709709.88 | 5745883.39 | 496924.08 | 1332970.6 | 37797.8 | 259572 | 174988 | 8048135.87 | 7338425.99 | 709709.88 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. | 0 | 248239.9589 | 0
690480 | FAASt [Humacao Streetlighting] (Distribution) | N/A | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 6455271.8825 | 488325.81 | 0 | 0 | 7979503.0525 | 7461968.2425 | 517534.81 | 6175629.8825 | 299807.81 | 1006696.36 | 29209 | 279642 | 188518 | 7979503.0525 | 7461968.2425 | 517534.81 | DSOW – Scope and Cost Update in Progress | Q1 FY2027 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. | 0 | 297152.2294 | 0
690483 | FAASt [Cayey Streetlighting] | N/A | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 10596790.82 | 1275717.24 | 0 | 0 | 14403667.21 | 13031995.21 | 1371672 | 10093033.82 | 936114.24 | 2435204.39 | 95954.76 | 503757 | 339603 | 14403667.21 | 13031995.21 | 1371672 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. | 0 | 643269.5581 | 1
690721 | FAASt [Guayama Streetlighting] (Distribution) | N/A | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 4107291.015 | 305442.59 | 0 | 0 | 5449840.505 | 5118754.995 | 331085.51 | 3974160.015 | 215693.59 | 1011463.98 | 25642.92 | 133131 | 89749 | 5449840.505 | 5118754.995 | 331085.51 | DSOW – Scope and Cost Update in Progress | Q1 FY2027 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. | 0 | 329495.4926 | 1
693543 | FAASt [Juncos Streetlighting] (Distribution) | N/A | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 10994681.6975 | 685135.01 | 0 | 0 | 13337550.0795 | 12625979.0095 | 711571.07 | 10405292.6975 | 287804.01 | 1631297.312 | 26436.06 | 589389 | 397331 | 13337550.0795 | 12625979.0095 | 711571.07 | DSOW – Scope and Cost Update in Progress | Q1 FY2027 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. | 0 | 402911.0913 | 1
693615 | [Rio Grande Streetlighting] (Distribution | N/A | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 5347407.42 | 397032.05 | 0 | 0 | 6922372.72 | 6503807.05 | 418565.67 | 5156073.42 | 268046.05 | 1156399.63 | 21533.62 | 191334 | 128986 | 6922372.72 | 6503807.05 | 418565.67 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. | 0 | 229464.6486 | 1
693788 | FAASt [Toa Alta Streetlighting] (Distribution) | N/A | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 4767387.52 | 197071.81 | 0 | 0 | 6145148.84 | 5930185.46 | 214963.38 | 4596792.52 | 82066.81 | 1162797.94 | 17891.57 | 170595 | 115005 | 6145148.84 | 5930185.46 | 214963.38 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. | 0 | 272844.9723 | 1
697183 | FAASt [Vega Baja Streetlighting] (Distribution) | N/A | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 8602549.46 | 1056851.66 | 0 | 0 | 11298606.43 | 10223863.2 | 1074743.23 | 8233261.46 | 807899.66 | 1621313.74 | 17891.57 | 369288 | 248952 | 11298606.43 | 10223863.2 | 1074743.23 | DSOW – Scope and Cost Update in Progress | Q4 FY2027 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. | 0 | 273173.1946 | 1
698427 | [Maricao Streetlighting] (Distribution | N/A | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 4873133.615 | 921314.71 | 0 | 0 | 6764612.415 | 5799960.3884 | 964652.0266 | 4466381.615 | 647106.71 | 926826.7734 | 43337.3166 | 406752 | 274208 | 6764612.415 | 5799960.3884 | 964652.0266 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. | 0 | 412029.6212 | 0
698432 | FAASt [Hormigueros Streetlighting] (Distribution) | N/A | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 5999141.915 | 489811.44 | 0 | 0 | 7869547.985 | 7362011.575 | 507536.41 | 5694746.915 | 284606.44 | 1362869.66 | 17724.97 | 304395 | 205205 | 7869547.985 | 7362011.575 | 507536.41 | DSOW – Scope and Cost Update in Progress | Q4 FY2027 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. | 0 | 112819.4583 | 1
698522 | [Vieques Streetlighting] (Distribution | N/A | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 3987957.0575 | 454616.91 | 0 | 0 | 5284920.4175 | 4798183.1075 | 486737.31 | 3791271.0575 | 322022.91 | 810226.05 | 32120.4 | 196686 | 132594 | 5284920.4175 | 4798183.1075 | 486737.31 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. | 0 | 135341.7111 | 1
699814 | FAASt [Juana Diaz Streetlighting] (Distribution) | N/A | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 14011750.655 | 872747.53 | 0 | 0 | 17735557.165 | 16807662.665 | 927894.5 | 13267153.655 | 370784.53 | 2795912.01 | 55146.97 | 744597 | 501963 | 17735557.165 | 16807662.665 | 927894.5 | DSOW – Scope and Cost Update in Progress | Q1 FY2027 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. | 0 | 522847.957 | 1
701473 | FAASt [Canovanas Streetlighting] (Distribution) | N/A | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 11994894.83 | 1520521.43 | 0 | 0 | 15982161.63 | 14372280.39 | 1609881.24 | 11399484.83 | 1119131.43 | 2377385.56 | 89359.81 | 595410 | 401390 | 15982161.63 | 14372280.39 | 1609881.24 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. | 0 | 433154.0521 | 1
704741 | [Moca Streetlighting] (Distribution | N/A | Yes | Distribution | Distribution Streetlighting | No | Inactive | Inactive | Yes | Yes | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 19741562.46 | 976458.2 | 0 | 0 | 23385995.03 | 22275170.4 | 1110824.63 | 17932518.84 | 308495.64 | 3152500.55 | 0 | 1190151 | 802329 | 23385995.03 | 22275170.39 | 1110824.64 | DSOW – Scope and Cost development in progress | Q1 FY2027 | DSOW package complete.Ready to be sumitted, scope consider all construction phases. | 0 | 417195.2193 | 1
704744 | [San Sebastian Streetlighting] (Distribution | N/A | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 21521273.585 | 1542129.95 | 0 | 0 | 27216189.295 | 25579247.535 | 1636941.76 | 19955144.585 | 486338.95 | 4057973.95 | 94811.81 | 1566129 | 1055791 | 27216189.295 | 25579247.535 | 1636941.76 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. | 0 | 680660.1749 | 0
704757 | FAASt [Santa Isabel Streetlighting] (Distribution) | N/A | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 8526009.33 | 383038.38 | 0 | 0 | 10493668.92 | 10088093.91 | 405575.01 | 8241015.33 | 190912.38 | 1562084.58 | 22536.63 | 284994 | 192126 | 10493668.92 | 10088093.91 | 405575.01 | DSOW – Scope and Cost Update in Progress | Q1 FY2027 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. | 0 | 306297.5883 | 1
704793 | [Yauco Streetlighting] (Distribution | N/A | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 13232024.93 | 1588137.76 | 0 | 0 | 17440123.63 | 15772456.53 | 1667667.1 | 12597812.93 | 1160589.76 | 2540431.6 | 79529.34 | 634212 | 427548 | 17440123.63 | 15772456.53 | 1667667.1 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. | 0 | 234796.0915 | 0
704862 | FAASt [Fajardo Streetlighting] (Distribution) | N/A | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 11073921.95 | 1052403.97 | 0 | 0 | 14335582.05 | 13224501.83 | 1111080.22 | 10758153.95 | 839531.97 | 2150579.88 | 58676.25 | 315768 | 212872 | 14335582.05 | 13224501.83 | 1111080.22 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. | 0 | 458695.0286 | 1
704929 | [San Lorenzo Streetlighting] (Distribution | N/A | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 13787578.6125 | 968406.72 | 0 | 0 | 17761487.4525 | 16732184.4425 | 1029303.01 | 12867034.6125 | 347830.72 | 2944605.83 | 60896.29 | 920544 | 620576 | 17761487.4525 | 16732184.4425 | 1029303.01 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. | 0 | 615681.5552 | 1
704931 | FAASt [Camuy Streetlighting] (Distribution) | N/A | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 14028036.5825 | 867189.9 | 0 | 0 | 16975652.3225 | 16000477.7235 | 975174.599 | 13069359.5825 | 220906.9 | 1972441.141 | 107984.699 | 958677 | 646283 | 16975652.3225 | 16000477.7235 | 975174.599 | DSOW – Scope and Cost Update in Progress | Q1 FY2027 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. | 0 | 678851.6314 | 1
713795 | [Lares Streetlighting] (Distribution | N/A | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 13027118.33 | 631320.8 | 0 | 0 | 15302634.86 | 14590612.84 | 712022.02 | 11882095.1 | 217275.01 | 1974624.75 | 0 | 733893 | 494747 | 15302634.86 | 14590612.85 | 712022.01 | DSOW – Scope and Cost development in progress | Q1 FY2027 | DSOW package complete.Ready to be sumitted, scope consider all construction phases. | 0 | 259135.6296 | 1
724599 | [Sabana Grande Streetlighting] (Distribution | N/A | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 11849851.49 | 636889.83 | 0 | 0 | 14112034.93 | 13386336.56 | 725698.37 | 10754272.51 | 236814.37 | 1906868.06 | 0 | 725196 | 488884 | 14112034.94 | 13386336.57 | 725698.37 | DSOW – Scope and Cost development in progress | Q1 FY2027 | DSOW package complete.Ready to be sumitted, scope consider all construction phases. | 0 | 441529.1219 | 1
724603 | FAASt [Cabo Rojo Streetlighting] (Distribution) | N/A | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 7308020.08 | 517830.31 | 0 | 0 | 9556933.07 | 8997613.25 | 559319.82 | 6954788.08 | 279702.31 | 1689593.17 | 41489.51 | 353232 | 238128 | 9556933.07 | 8997613.25 | 559319.82 | DSOW – Scope and Cost Update in Progress | Q1 FY2027 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. | 0 | 509029.477 | 1
724605 | [Guayanilla Streetlighting] (Distribution | N/A | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 8485594.47 | 412336.03 | 0 | 0 | 10061862.97 | 9591958.43 | 469904.54 | 7795083.32 | 183970.54 | 1372729.11 | 0 | 424146 | 285934 | 10061862.97 | 9591958.43 | 469904.54 | DSOW – Scope and Cost development in progress | Q1 FY2027 | DSOW package complete.Ready to be sumitted, scope consider all construction phases. | 0 | 506612.2788 | 1
724669 | [Ciales Streetlighting] (Distribution | N/A | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 13170687.29 | 682982.51 | 0 | 0 | 15573543.98 | 14800410.23 | 773133.75 | 12013750.42 | 272974.74 | 2044738.82 | 0 | 741921 | 500159 | 15573543.98 | 14800410.24 | 773133.74 | DSOW – Scope and Cost development in progress | Q1 FY2027 | DSOW package complete.Ready to be sumitted, scope consider all construction phases. | 0 | 400619.9636 | 1
724670 | [Patillas Streetlighting] (Distribution | N/A | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 9123256.82 | 358025.92 | 0 | 0 | 10697382.94 | 10290796.36 | 406586.58 | 8408428.82 | 119750.59 | 1456883.53 | 0 | 425484 | 286836 | 10697382.94 | 10290796.35 | 406586.59 | DSOW – Scope and Cost development in progress | Q1 FY2027 | DSOW package complete.Ready to be sumitted, scope consider all construction phases. | 0 | 58985.215 | 0
724716 | [Quebradillas Streetlighting] (Distribution | N/A | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 11505789.6 | 550706.35 | 0 | 0 | 13645048.55 | 13016938.52 | 628110.03 | 10502157.5 | 195150.03 | 1872541.02 | 0 | 642240 | 432960 | 13645048.55 | 13016938.52 | 628110.03 | DSOW – Scope and Cost development in progress | Q1 FY2027 | DSOW package complete.Ready to be sumitted, scope consider all construction phases. | 0 | 215200.3038 | 1
724781 | [Penuelas Streetlighting] (Distribution | N/A | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 8600953.35 | 357444.72 | 0 | 0 | 10169431 | 9760940.59 | 408490.41 | 7929864.73 | 140145.41 | 1433020.87 | 0 | 398055 | 268345 | 10169431.01 | 9760940.6 | 408490.41 | DSOW – Scope and Cost development in progress | Q1 FY2027 | DSOW package complete.Ready to be sumitted, scope consider all construction phases. | 0 | 88962.1821 | 0
724828 | [Loiza Streetlighting] (Distribution | N/A | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 6213147.88 | 388351.58 | 0 | 0 | 7863736.33 | 7461247.25 | 402489.08 | 5936181.88 | 201637.58 | 1248099.37 | 14137.5 | 276966 | 186714 | 7863736.33 | 7461247.25 | 402489.08 | DSOW – Scope and Cost Update in Progress | Q1 FY2028 | Estimate date to DSOW submission. Considering only the portion to be completed to be fomulated and submit. Estimate its based on latest assumtions. Adding workcompleted portion would take longer. | 0 | 174283.6273 | 1
724941 | [Aguas Buenas Streetlighting] (Distribution | N/A | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | Yes | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 12423846.45 | 585725.31 | 0 | 0 | 14738688.59 | 14069941.7 | 668746.89 | 11340397.36 | 201510.89 | 2036460.34 | 0 | 693084 | 467236 | 14738688.59 | 14069941.7 | 668746.89 | DSOW – Scope and Cost development in progress | Q1 FY2027 | DSOW package complete.Ready to be sumitted, scope consider all construction phases. | 0 | 618088.3347 | 0
734393 | FAASt [Cabo Rojo Streetlighting - Part 2] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 2168900 | 0 | 0 | 0 | 2537332.14 | 2537332.14 | 0 | [14 empty] | 0
734396 | FAASt [Cabo Rojo Streetlighting - Part 3] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 1246600 | 0 | 0 | 0 | 1526007 | 1526007 | 0 | [14 empty] | 0
734728 | FAASt [Ponce Streetlighting - Part 2] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 3681150 | 0 | 0 | 0 | 4258109.77 | 4258109.77 | 0 | [14 empty] | 0
734760 | FAASt [Ponce Streetlighting - Part 3] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 3221150 | 0 | 0 | 0 | 3922140.05 | 3922140.05 | 0 | [14 empty] | 0
734789 | FAASt [Guayama Streetlighting - Part 3 ] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 1679000 | 0 | 0 | 0 | 1964214.71 | 1964214.71 | 0 | [14 empty] | 0
734791 | FAASt [Guayama Streetlighting - Part 2] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 1756050 | 0 | 0 | 0 | 2200712.71 | 2200712.71 | 0 | [14 empty] | 0
734853 | FAASt [Arecibo Streetlighting- Part 3] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 2778400 | 0 | 0 | 0 | 3348430.05 | 3348430.05 | 0 | [14 empty] | 0
734859 | FAASt [Aguadilla Streetlighting - Part 2] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 2010200 | 0 | 0 | 0 | 2309327.03 | 2309327.03 | 0 | [14 empty] | 0
734927 | FAASt [Isabela Streetlighting - Part 2] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 1552500 | 0 | 0 | 0 | 1859473.5 | 1859473.5 | 0 | [14 empty] | 0
734928 | FAASt [Isabela Streetlighting - Part 3] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 1163800 | 0 | 0 | 0 | 1488913.23 | 1488913.23 | 0 | [14 empty] | 0
735131 | FAASt [Arecibo Streetlighting - Part 2] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 3149850 | 0 | 0 | 0 | 3652944.78 | 3652944.78 | 0 | [14 empty] | 1
735338 | FAASt [Aguadilla Streetlighting - Part 3] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 1401850 | 0 | 0 | 0 | 1715471.72 | 1715471.72 | 0 | [14 empty] | 0
735357 | FAASt [Mayaguez Streetlighting - Part 2] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 2005600 | 0 | 0 | 0 | 2335919.93 | 2335919.93 | 0 | [14 empty] | 1
735360 | FAASt [Mayaguez Streetlighting - Part 3] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 2967000 | 0 | 0 | 0 | 3901399.04 | 3901399.04 | 0 | [14 empty] | 0
735470 | FAASt [Bayamón Streetlighting - Part 2] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 5318750 | 0 | 0 | 0 | 6023196.74 | 6023196.74 | 0 | [14 empty] | 0
735472 | FAASt [Bayamon Streetlighting - Part 3] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 4418300 | 0 | 0 | 0 | 5157472.36 | 5157472.36 | 0 | [14 empty] | 0
735483 | FAASt [Vega Baja Streetlighting - Part 3] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 1308700 | 0 | 0 | 0 | 1573769.11 | 1573769.11 | 0 | [14 empty] | 0
735487 | FAASt [Humacao Streetlighting - Part 3] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 1498450 | 0 | 0 | 0 | 1780455.08 | 1780455.08 | 0 | [14 empty] | 0
735493 | FAASt [Humacao Streetlighting - Part 2] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 1826200 | 0 | 0 | 0 | 2151030.45 | 2151030.45 | 0 | [14 empty] | 0
735496 | FAASt [Carolina Streetlighting - Part 3] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 3936450 | 0 | 0 | 0 | 4621241.58 | 4621241.58 | 0 | [14 empty] | 0
735499 | FAASt [Guaynabo Streetlighting - Part 3] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 1838850 | 0 | 0 | 0 | 2214136.43 | 2214136.43 | 0 | [14 empty] | 0
735665 | FAASt [Carolina Streetlighting - Part 2] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 4328600 | 0 | 0 | 0 | 5124022.75 | 5124022.75 | 0 | [14 empty] | 0
735672 | FAASt [Caguas Streetlighting - Part 3] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 3448850 | 0 | 0 | 0 | 4201485.32 | 4201485.32 | 0 | [14 empty] | 0
735677 | FAASt [Guaynabo Streetlighting - Part 2] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 1935450 | 0 | 0 | 0 | 2320241.84 | 2320241.84 | 0 | [14 empty] | 0
735940 | FAASt [Vega Baja Streetlighting - Part 2] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 1896350 | 0 | 0 | 0 | 2209801.11 | 2209801.11 | 0 | [14 empty] | 0
735952 | FAASt [Trujillo Alto Streetlighting - Part 3] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 1597350 | 0 | 0 | 0 | 1966935.51 | 1966935.51 | 0 | [14 empty] | 0
735954 | FAASt [Trujillo Alto Streetlighting - Part 2] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 1817000 | 0 | 0 | 0 | 2068430.18 | 2068430.18 | 0 | [14 empty] | 0
735959 | FAASt [Toa Baja Streetlighting - Part 3] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 1317900 | 0 | 0 | 0 | 1618391.01 | 1618391.01 | 0 | [14 empty] | 0
735960 | FAASt [Toa Baja Streetlighting - Part 2] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 1461650 | 0 | 0 | 0 | 1773434.53 | 1773434.53 | 0 | [14 empty] | 0
737699 | FAASt [Toa Alta Streetlighting - Part 3] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 1058000 | 0 | 0 | 0 | 1279137.35 | 1279137.35 | 0 | [14 empty] | 0
737707 | FAASt [Toa Alta Streetlighting - Part 2] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 2219500 | 0 | 0 | 0 | 2584072.61 | 2584072.61 | 0 | [14 empty] | 0
737712 | FAAST [San Juan Streetlighting - Part 3] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 7826900 | 0 | 0 | 0 | 8930186.53 | 8930186.53 | 0 | [14 empty] | 0
737798 | FAASt [Rio Grande Streetlighting - Part 3] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 1212100 | 0 | 0 | 0 | 1451193.65 | 1451193.65 | 0 | [14 empty] | 0
737804 | FAASt [Rio Grande Streetlighting - Part 2 ] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 1788250 | 0 | 0 | 0 | 2067779.57 | 2067779.57 | 0 | [14 empty] | 0
746108 | FAASt [San Juan Streetlighting - Part 2] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 7814250 | 0 | 0 | 0 | 8639420.91 | 8639420.91 | 0 | [14 empty] | 1
746111 | FAASt [Caguas Streetlighting - Part 2] (Distribution) | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | No | No | Distribution | Distribution Streetlighting | No | Inactive | Inactive | 3646650 | 0 | 0 | 0 | 4154938.97 | 4154938.97 | 0 | [14 empty] | 1
TBD2 | Santa Isabel Sect 4401 Transformer 38/13.2-4.16, 22 MVA | Yes | Yes | Substations | Substation Component Replacements | No | Inactive | Inactive | Yes | Yes | Substations | Substation Component Replacements | No | Inactive | Inactive | 9069707.702 | 4349479.6256 | 1706844.8419 | 431056.671 | 16057251.98 | 11168379.9079 | 4888872.0722 | [14 empty] | 0
TBD3 | Aguadilla Sect 7003 Transformer 38/13.2-4.16, 22 MVA | Yes | Yes | Substations | Substation Component Replacements | No | Inactive | Inactive | Yes | Yes | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | [14 empty] | 1
TBD4 | Hogar Crea 1717 Transformer 115/13.2 kV, 44.8 MVA | Yes | Yes | Substations | Substation Component Replacements | No | Inactive | Inactive | Yes | Yes | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | [14 empty] | 1
TBD5 | Isla Grande TC Bank 2 Transformer 115/40 kV, 112 MVA | Yes | Yes | Substations | Substation Component Replacements | No | Inactive | Inactive | Yes | Yes | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | [14 empty] | 1
TBD6 | Quebradillas 7402 Transformer 38/13.2-4.16, 22 MVA | Yes | Yes | Substations | Substation Component Replacements | No | Inactive | Inactive | Yes | Yes | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | [14 empty] | 1
TBD34 | Rincon 7301 Transformer 38/13.2-4.16, 22 MVA | Yes | Yes | Substations | Substation Component Replacements | No | Inactive | Inactive | Yes | Yes | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | [14 empty] | 1
TBD7 | ALTURAS DE MAYAGUEZ | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | [14 empty] | 0
TBD8 | ALTURAS DE RIO GRANDE | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | [14 empty] | 0
TBD9 | BARCELONETA PUEBLO | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | [14 empty] | 0
TBD10 | BRENAS | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | [14 empty] | 0
TBD11 | CAMUY | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | [14 empty] | 0
TBD12 | CERAMICA | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | [14 empty] | 0
TBD13 | Quebrada Negrito | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | [14 empty] | 1
TBD14 | CRUCE DAVILA | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | [14 empty] | 1
TBD15 | HATO TEJAS | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | [14 empty] | 1
TBD16 | ISABELA PUEBLO | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | [14 empty] | 1
TBD17 | JUNCOS TC | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 12436054.1497 | 2868434.0326 | 2039101.99 | 673911.4961 | 18847942.6501 | 15024031.5354 | 3823911.1147 | [14 empty] | 1
TBD18 | LA RAMBLA SECT | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | [14 empty] | 1
TBD19 | LAS PIEDRAS SECT | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | [14 empty] | 1
TBD20 | MANATI TC | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 9069707.702 | 4349479.6256 | 1706844.8419 | 431056.671 | 16057251.98 | 11168379.9079 | 4888872.0722 | [14 empty] | 1
TBD21 | Aguas Buenas | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5614147.55 | 2622060.6228 | 1241258.17 | 259726.6402 | 10285175.1982 | 7338078.29 | 2947096.9082 | [14 empty] | 1
TBD22 | NAGUABO | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | [14 empty] | 1
TBD23 | PATILLAS | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | [14 empty] | 1
TBD24 | PENUELAS | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | [14 empty] | 1
TBD25 | PUERTO DEL REY | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | [14 empty] | 1
TBD26 | RAMEY FIELD 3 | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | [14 empty] | 1
TBD27 | SABANA GRANDE | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | [14 empty] | 1
TBD28 | SALINAS RURAL | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | [14 empty] | 1
TBD29 | SALINAS URBANO | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | [14 empty] | 0
TBD30 | Berwind TC | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | Not Found | Not Found | Not Found | Not Found | Not Found | Not Found | Not Found | Not Found | Not Found | not found | not found | not found | not found | not found | [14 empty] | 0
TBD31 | Juan Martin | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | Not Found | Not Found | Not Found | Not Found | Not Found | Not Found | Not Found | Not Found | Not Found | not found | not found | not found | not found | not found | [14 empty] | 0
TBD32 | TOA ALTA | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | [14 empty] | 0
TBD33 | VEREDAS SECT | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | Yes, only E&M | No | Substations | Substation Component Replacements | No | Inactive | Inactive | 5467624.9743 | 2622060.6228 | 1029095.8984 | 259726.6402 | 9680028.82 | 6732931.9118 | 2947096.9082 | [14 empty] | 0
685869 | [Mayagüez TC] (Substation | No | No | Substations | Substation Rebuilds | No | Inactive | Inactive | No | No | Substations | Substation Rebuilds | No | Inactive | Inactive | 22073642.86 | 7779720.93 | 13511059.91 | 183120 | 46206273.41 | 38190257.91 | 8016015.5 | 22073642.86 | 543426.36 | 2605555.14 | 53174.57 | 13511059.91 | 183120 | 38969978.84 | 38190257.91 | 779720.93 | DSOW – Pending Design Package for Development | Q1 FY2027 | Awaiting cable termination and subcontractor. Received quote, started micropurchase. Breakers have already been maintained and transformer fans were replaced. Estimated Submission to COR3/FEMA 6/30/2026. | 0 | 391877.4639 | 1
547247 | Cambalache TC Rebuild | Yes | Yes | Substations | Substation Rebuilds | No | Inactive | Inactive | Yes | Yes | Substations | Substation Rebuilds | No | Inactive | Inactive | 4966986.47 | 62195402.17 | 151612.12 | 13320220.44 | 90196791.96 | 5463505.9 | 84733286.06 | [14 empty] | 1
547344 (1066724)) | Acacias 6801 TC (Relocation) | Yes | Yes | Substations | Substation Rebuilds | No | Active | Active | Yes | Yes | Substations | Substation Rebuilds | No | Active | Active | 65766025.0617 | 31538831.8413 | 12378234.9672 | 3124060.0459 | 116433921.67 | 80985468.2671 | 35448453.4029 | [14 empty] | 1
550099 (1066979) | Esc Industrial Miguel Such (Metal-Clad) 1423 | Yes | Yes | Substations | Substation Rebuilds | No | Active | Active | Yes | Yes | Substations | Substation Rebuilds | No | Active | Active | 3301739.68 | 1135704.94 | 6614733.66 | 4603565.8 | 16767794.21 | 11028523.47 | 5739270.74 | [14 empty] | 1
551260 (1066729) | Guaynabo Pueblo | Yes | Yes | Substations | Substation Rebuilds | No | Active | Active | Yes | Yes | Substations | Substation Rebuilds | No | Active | Active | 9487047.4 | 4257510.71 | 4962433.97 | 3961056.7649 | 25508267.5549 | 16713135.72 | 8795131.8349 | [14 empty] | 1
752277 | FAASt [Substation Ciales 8701] (Substation) | No | No | Substations | Substation Rebuilds | No | Inactive | Inactive | No | No | Substations | Substation Rebuilds | No | Inactive | Inactive | 9069707.702 | 4349479.6256 | 1706844.8419 | 431056.671 | 16057251.98 | 11168379.9079 | 4888872.0722 | 3553830.9091 | 524335.7079 | 349557.1386 | 116519.0462 | 466076.1848 | 815633.3234 | 5825952.31 | 4369464.2325 | 1456488.0775 | DSOW – Pending Design Package for Development | Q1 FY2028 | New DSOW needs to be developed , Proposed approach focused on replacing critical components: metal-clad, transformers, breakers, communications. | 0 | 4061.1901 | 1
TBD1 | Mobile Substations | Yes, only E&M | No | Substations | Substations | No | Inactive | Inactive | Yes, only E&M | No | Substations | Substations | No | Inactive | Inactive | 0 | 0 | 17709050 | 0 | 17709050 | 17709050 | 0 | [14 empty] | 1
1064452 | Transmission Priority Pole Replacement Program Line 800 Comsat Sect –Cidra Sect (Active) | No | No | Transmission | Transmission Priority Pole Replacements | No | Inactive | Inactive | No | No | Transmission | Transmission Priority Pole Replacements | No | Inactive | Inactive | 609182.23 | 2812.61 | 52018.89 | 8792.11 | 784923.48 | 771390.36 | 13533.12 | [14 empty] | 1
753785 | TPole 3300 San Gerardo Sect to Venezuela Sect | N/A | Yes | Transmission | Transmission Priority Pole Replacements | No | Inactive | Inactive | Yes | Yes | Transmission | Transmission Priority Pole Replacements | No | Inactive | Inactive | 299085.29 | 81090.53 | 12296.95 | 1013.73 | 463270.21 | 366609.09 | 96661.12 | [14 empty] | 1
753787 | TPole 13700 Mora TC to Isabela TO | N/A | Yes | Transmission | Transmission Priority Pole Replacements | No | Inactive | Inactive | Yes | Yes | Transmission | Transmission Priority Pole Replacements | No | Inactive | Inactive | 591148.31 | 7196.15 | 35991.1 | 2143.44 | 741206.13 | 730337.54 | 10868.59 | [14 empty] | 1
753786 (1066980) | TPole 5900 San Juan SP to Crematorio TO | N/A | Yes | Transmission | Transmission Priority Pole Replacements | No | Active | Active | Yes | Yes | Transmission | Transmission Priority Pole Replacements | No | Active | Active | 407830.94 | 1921.02 | 40781.7 | 6101.3 | 535616.04 | 526211.57 | 9404.47 | [14 empty] | 1
811923 (1066730) | Transmission Priority Pole Replacement Program Line 16500 Fajardo TC-Dos Marinas | N/A | Yes | Transmission | Transmission Priority Pole Replacements | No | Active | Active | Yes | Yes | Transmission | Transmission Priority Pole Replacements | No | Active | Active | 212650.88 | 381.28 | 37102.11 | 1220.26 | 299927.69 | 298020.17 | 1907.52 | [14 empty] | 1
754350 | Distribution Underground Circuit Feeders - San Juan Group 1 | No | No | Distribution | Underground | No | Inactive | Inactive | No | No | Distribution | Underground | No | Inactive | Inactive | 4310111.715 | 9577521.9267 | 1512.3199 | 58980.4761 | 15123199 | 4674580.8109 | 10448618.1891 | 4310111.715 | 9577521.9267 | 362956.776 | 812115.7863 | 1512.3199 | 58980.4761 | 15123199 | 4674580.8109 | 10448618.1891 | DSOW – Pending Design Package for Development | Q1 FY2028 | Pending Operation Assessment, and design work has not yet been finalized. Further evaluation is required before moving forward. | 0 | 54289 | 1
754351 | ​Distribution Underground Circuit Feeders - San Juan Group 2 | No | No | Distribution | Underground | No | Inactive | Inactive | No | No | Distribution | Underground | No | Inactive | Inactive | 2013990.405 | 4475298.6789 | 706.6633 | 27559.8687 | 7066633 | 2184296.2603 | 4882336.7397 | 2013990.405 | 4475298.6789 | 169599.192 | 379478.1921 | 706.6633 | 27559.8687 | 7066633 | 2184296.2603 | 4882336.7397 | DSOW – Pending Design Package for Development | Q1 FY2028 | Pending Operation Assessment, and design work has not yet been finalized. Further evaluation is required before moving forward. | 0 | 41921.5 | 1
741097 | Region 1 San Juan Substation/Telecom | No amendment needed in these set of projects. | No | Vegetation | Vegetation | No | Inactive | Inactive | No | No | Vegetation | Vegetation | No | Inactive | Inactive | 0 | 867756.78 | 0 | 0 | 1347192.03 | 0 | 1347192.03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | DSOW – Pending Design Package for Development | N/A | Vegetation Subs/Telecom projects were withdrawn as substations are under a maintenance cycle and do not require federally funded clearing. These projects will not be reactivated or resubmitted to FEMA. | 0 | 0 | 1
741098 | Region 3 Bayamon Substation/Telecom | No amendment needed in these set of projects. | No | Vegetation | Vegetation | No | Inactive | Inactive | No | No | Vegetation | Vegetation | No | Inactive | Inactive | 0 | 169300.95 | 0 | 0 | 262839.56 | 0 | 262839.56 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | DSOW – Pending Design Package for Development | N/A | Vegetation Subs/Telecom projects were withdrawn as substations are under a maintenance cycle and do not require federally funded clearing. These projects will not be reactivated or resubmitted to FEMA. | 0 | 0 | 1
741100 | Region 4 Caguas Substation/Telecom | No amendment needed in these set of projects. | No | Vegetation | Vegetation | No | Inactive | Inactive | No | No | Vegetation | Vegetation | No | Inactive | Inactive | 0 | 1283718.51 | 0 | 0 | 1992973.62 | 0 | 1992973.62 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | DSOW – Pending Design Package for Development | N/A | Vegetation Subs/Telecom projects were withdrawn as substations are under a maintenance cycle and do not require federally funded clearing. These projects will not be reactivated or resubmitted to FEMA. | 0 | 0 | 1
741101 | Region 2 Arecibo Substation/Telecom | No amendment needed in these set of projects. | No | Vegetation | Vegetation | No | Inactive | Inactive | No | No | Vegetation | Vegetation | No | Inactive | Inactive | 0 | 69780.78 | 0 | 0 | 108335.03 | 0 | 108335.03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | DSOW – Pending Design Package for Development | N/A | Vegetation Subs/Telecom projects were withdrawn as substations are under a maintenance cycle and do not require federally funded clearing. These projects will not be reactivated or resubmitted to FEMA. | 0 | 0 | 1
741102 | Region 5 Mayaguez Substation/Telecom | No amendment needed in these set of projects. | No | Vegetation | Vegetation | No | Inactive | Inactive | No | No | Vegetation | Vegetation | No | Inactive | Inactive | 0 | 619336 | 0 | 0 | 961519 | 0 | 961519 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | DSOW – Pending Design Package for Development | N/A | Vegetation Subs/Telecom projects were withdrawn as substations are under a maintenance cycle and do not require federally funded clearing. These projects will not be reactivated or resubmitted to FEMA. | 0 | 0 | 1
741104 | Region 6 Ponce Substation/Telecom | No amendment needed in these set of projects. | No | Vegetation | Vegetation | No | Inactive | Inactive | No | No | Vegetation | Vegetation | No | Inactive | Inactive | 0 | 977124.29 | 0 | 0 | 1516985.64 | 0 | 1516985.64 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | DSOW – Pending Design Package for Development | N/A | Vegetation Subs/Telecom projects were withdrawn as substations are under a maintenance cycle and do not require federally funded clearing. These projects will not be reactivated or resubmitted to FEMA. | 0 | 0 | 1
Pending FASSt | FAASt [Region 6 Ponce Distribution sensitive areas] (Vegetation) | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 42934620.7125 | 117568634.2875 | - | - | 160503255 | 42934620.7125 | 117568634.2875 | [14 empty] | 1
Pending FASSt | FAASt [Region 5 Mayaguez Distribution sensitive areas] (Vegetation) | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 58330775.8125 | 159728199.1875 | - | - | 218058975 | 58330775.8125 | 159728199.1875 | [14 empty] | 1
Pending FASSt | FAASt [Region 2 Arecibo Distribution sensitive areas] (Vegetation) | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 50485034.25 | 138244065.75 | - | - | 188729100 | 50485034.25 | 138244065.75 | [14 empty] | 1
Pending FASSt | FAASt [Region 4 Caguas Distribution sensitive areas] (Vegetation) | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 44184703.05 | 120991756.95 | - | - | 165176460 | 44184703.05 | 120991756.95 | [14 empty] | 1
Pending FASSt | FAASt [Region 3 Bayamon Distribution sensitive areas] (Vegetation) | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 9021119.175 | 24702690.825 | - | - | 33723810 | 9021119.175 | 24702690.825 | [14 empty] | 1
Pending FASSt | FAASt [Region 1 San Juan Distribution sensitive areas] (Vegetation) | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 36635336.775 | 100319193.225 | - | - | 136954530 | 36635336.775 | 100319193.225 | [14 empty] | 1
727530 | FAASt [Region 6 Ponce Transmission 38kV sensitive areas] (Vegetation) - Group C | Yes | No | Vegetation | Vegetation-TL | No | Inactive | Inactive | Yes | No | Vegetation | Vegetation-TL | No | Inactive | Inactive | 1367036.856 | 15022714.938 | 0 | 0 | 16527421.638 | 1378532.292 | 15148889.346 | 2278394.76 | 25037858.23 | 19159.06 | 210290.68 | 0 | 0 | 27545702.73 | 2297553.82 | 25248148.91 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | Project is developed and will be ready to submit to FEMA as soon as projects are reactivated in Grants Portal | Inactive | 0 | 1
727540 | FAASt [Region 2 Arecibo Transmission 38kV sensitive areas] (Vegetation) - Group C | Yes | No | Vegetation | Vegetation-TL | No | Inactive | Inactive | Yes | No | Vegetation | Vegetation-TL | No | Inactive | Inactive | 1105536.432 | 12149020.278 | 0 | 0 | 13365891.69 | 1114832.91 | 12251058.78 | 1842560.72 | 20248367.13 | 15494.13 | 170064.17 | 0 | 0 | 22276486.15 | 1858054.85 | 20418431.3 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | Project is developed and will be ready to submit to FEMA as soon as projects are reactivated in Grants Portal | Inactive | 0 | 1
727558 | FAASt [Region 3 Bayamon Transmission 38kV sensitive areas] (Vegetation) - Group C | Yes | No | Vegetation | Vegetation-TL | No | Inactive | Inactive | Yes | No | Vegetation | Vegetation-TL | No | Inactive | Inactive | 793759.878 | 8722828.56 | 0 | 0 | 9596525.418 | 800434.62 | 8796090.798 | 1322933.13 | 14538047.6 | 11124.57 | 122103.73 | 0 | 0 | 15994209.03 | 1334057.7 | 14660151.33 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | Project is developed and will be ready to submit to FEMA as soon as projects are reactivated in Grants Portal | Inactive | 0 | 1
727562 | FAASt [Region 5 Mayaguez Transmission 38kV sensitive areas] (Vegetation) - Group C | Yes | No | Vegetation | Vegetation-TL | No | Inactive | Inactive | Yes | No | Vegetation | Vegetation-TL | No | Inactive | Inactive | 1232141.82 | 13540319.136 | 0 | 0 | 14896545.954 | 1242502.92 | 13654043.034 | 2053569.7 | 22567198.56 | 17268.5 | 189539.83 | 0 | 0 | 24827576.59 | 2070838.2 | 22756738.39 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | Project is developed and will be ready to submit to FEMA as soon as projects are reactivated in Grants Portal | Inactive | 0 | 1
727691 | FAASt [Region 1 San Juan Transmission 38kV sensitive areas] (Vegetation) - Group C | Yes | No | Vegetation | Vegetation-TL | No | Inactive | Inactive | Yes | No | Vegetation | Vegetation-TL | No | Inactive | Inactive | 788376.99 | 8663674.704 | 0 | 0 | 9531446.58 | 795006.474 | 8736440.106 | 1313961.65 | 14439457.84 | 11049.14 | 121275.67 | 0 | 0 | 15885744.3 | 1325010.79 | 14560733.51 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | Project is developed and will be ready to submit to FEMA as soon as projects are reactivated in Grants Portal | Inactive | 0 | 1
727694 | FAASt [Region 4 Caguas Transmission 38kV sensitive areas] (Vegetation) - Group C | Yes | No | Vegetation | Vegetation-TL | No | Inactive | Inactive | Yes | No | Vegetation | Vegetation-TL | No | Inactive | Inactive | 437628.366 | 4809208.998 | 0 | 0 | 5290909.494 | 441308.4 | 4849601.094 | 729380.61 | 8015348.33 | 6133.39 | 67320.16 | 0 | 0 | 8818182.49 | 735514 | 8082668.49 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | Project is developed and will be ready to submit to FEMA as soon as projects are reactivated in Grants Portal | Inactive | 0 | 1
Pending FASSt | 38kV Transmission Line 100 – Entire Line (Vegetation) | No | No | Vegetation | Vegetation-TL | No | Inactive | Inactive | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 254933.334 | 2801526.9 | - | - | 3082133.736 | 257077.08 | 2825056.656 | [14 empty] | 1
Pending FASSt | 38kV Transmission Line 200 – Entire Line (Vegetation) | No | No | Vegetation | Vegetation-TL | No | Inactive | Inactive | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 155350.008 | 1707180.444 | - | - | 1878175.236 | 156656.352 | 1721518.884 | [14 empty] | 1
Pending FASSt | 38kV Transmission Line 800 – Entire Line (Vegetation) | No | No | Vegetation | Vegetation-TL | No | Inactive | Inactive | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 161271.174 | 1772249.706 | - | - | 1949761.968 | 162627.312 | 1787134.656 | [14 empty] | 1
Pending FASSt | 38kV Transmission Line 1200 – Entire Line (Vegetation) | No | No | Vegetation | Vegetation-TL | No | Inactive | Inactive | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 275711.268 | 3029860.812 | - | - | 3333338.058 | 278029.734 | 3055308.324 | [14 empty] | 1
Pending FASSt | 38kV Transmission Line 1600 – Entire Line (Vegetation) | No | No | Vegetation | Vegetation-TL | No | Inactive | Inactive | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 305424.768 | 3356390.148 | - | - | 3692573.244 | 307993.092 | 3384580.152 | [14 empty] | 1
Pending FASSt | 38kV Transmission Line 2000 – Entire Line (Vegetation) | No | No | Vegetation | Vegetation-TL | No | Inactive | Inactive | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 303594.6 | 3336277.806 | - | - | 3670446.426 | 306147.534 | 3364298.892 | [14 empty] | 1
Pending FASSt | 38kV Transmission Line 2100 – Entire Line (Vegetation) | No | No | Vegetation | Vegetation-TL | No | Inactive | Inactive | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 304778.826 | 3349291.674 | - | - | 3684763.782 | 307341.72 | 3377422.062 | [14 empty] | 1
Pending FASSt | 38kV Transmission Line 2200 – Entire Line (Vegetation) | No | No | Vegetation | Vegetation-TL | No | Inactive | Inactive | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 805386.906 | 8850600.906 | - | - | 9737095.71 | 812159.424 | 8924936.286 | [14 empty] | 1
Pending FASSt | 38kV Transmission Line 2500 – Entire Line (Vegetation) | No | No | Vegetation | Vegetation-TL | No | Inactive | Inactive | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 243413.964 | 2674937.64 | - | - | 2942865.024 | 245460.84 | 2697404.184 | [14 empty] | 1
Pending FASSt | 38kV Transmission Line 2700 – Entire Line (Vegetation) | No | No | Vegetation | Vegetation-TL | No | Inactive | Inactive | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 409745.04 | 4502791.986 | - | - | 4953801.114 | 413190.594 | 4540610.52 | [14 empty] | 1
Pending FASSt | 38kV Transmission Line 3000 – Entire Line (Vegetation) | No | No | Vegetation | Vegetation-TL | No | Inactive | Inactive | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 491241.876 | 5398381.47 | - | - | 5939094.72 | 495372.738 | 5443721.982 | [14 empty] | 1
Pending FASSt | 38kV Transmission Line 3100 – Entire Line (Vegetation) | No | No | Vegetation | Vegetation-TL | No | Inactive | Inactive | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 650144.58 | 7144603.488 | - | - | 7860222.012 | 655611.66 | 7204610.352 | [14 empty] | 1
Pending FASSt | 38kV Transmission Line 3700 – Entire Line (Vegetation) | No | No | Vegetation | Vegetation-TL | No | Inactive | Inactive | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 470248.632 | 5167681.416 | - | - | 5685287.256 | 474202.962 | 5211084.294 | [14 empty] | 1
Pending FASSt | 38kV Transmission Line 3800 – Entire Line (Vegetation) | No | No | Vegetation | Vegetation-TL | No | Inactive | Inactive | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 253749.102 | 2788513.05 | - | - | 3067816.392 | 255882.888 | 2811933.504 | [14 empty] | 1
Pending FASSt | 38kV Transmission Line 4000 – Entire Line (Vegetation) | No | No | Vegetation | Vegetation-TL | No | Inactive | Inactive | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 113148.21 | 1243414.146 | - | - | 1367957.136 | 114099.684 | 1253857.452 | [14 empty] | 1
Pending FASSt | 38kV Transmission Line 4800 – Entire Line (Vegetation) | No | No | Vegetation | Vegetation-TL | No | Inactive | Inactive | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 428262.162 | 4706281.266 | - | - | 5177672.316 | 431863.434 | 4745808.882 | [14 empty] | 1
Pending FASSt | 38kV Transmission Line 5300 – Entire Line (Vegetation) | No | No | Vegetation | Vegetation-TL | No | Inactive | Inactive | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 166008.114 | 1824305.088 | - | - | 2007031.338 | 167404.086 | 1839627.252 | [14 empty] | 1
Pending FASSt | 38kV Transmission Line 5400 – Entire Line (Vegetation) | No | No | Vegetation | Vegetation-TL | No | Inactive | Inactive | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 288199.554 | 3167097.762 | - | - | 3484320.948 | 290623.032 | 3193697.916 | [14 empty] | 1
Pending FASSt | 38kV Transmission Line 5600 – Entire Line (Vegetation) | No | No | Vegetation | Vegetation-TL | No | Inactive | Inactive | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 293582.43 | 3226251.636 | - | - | 3549399.792 | 296051.172 | 3253348.62 | [14 empty] | 1
Pending FASSt | 38kV Transmission Line 6500 – Entire Line (Vegetation) | No | No | Vegetation | Vegetation-TL | No | Inactive | Inactive | No | No | Vegetation | Vegetation-DL | No | Inactive | Inactive | 447640.536 | 4919235.186 | - | - | 5411956.14 | 451404.756 | 4960551.384 | [14 empty] | 1
740406 | FAASt[Region 1 San Juan Transmission 38kV - Non-Sensitive (Vegetation)] - Group B | Yes | Yes | Vegetation | Vegetation-TL | No | Inactive | Inactive | Yes | Yes | Vegetation | Vegetation-TL | No | Inactive | Inactive | 281264.03 | 3116841.11 | 0 | 0 | 3426429.85 | 283629.15 | 3142800.7 | 281345.36 | 3091775.16 | 2365.85 | 25967.52 | 0 | 0 | 3401453.89 | 283711.21 | 3117742.68 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | Project is developed and will be ready to submit to FEMA as soon as projects are reactivated in Grants Portal | Inactive | 0 | 1
740408 | FAASt[Region 3 Bayamon Transmission 38kV - Non-Sensitive (Vegetation)]- Group B | Yes | Yes | Vegetation | Vegetation-TL | No | Inactive | Inactive | Yes | Yes | Vegetation | Vegetation-TL | No | Inactive | Inactive | 622799.54 | 6901584.83 | 0 | 0 | 7587104.48 | 628036.68 | 6959067.8 | 666580.3 | 7325219.95 | 5605.29 | 61523.84 | 0 | 0 | 8058929.38 | 672185.59 | 7386743.79 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | Project is developed and will be ready to submit to FEMA as soon as projects are reactivated in Grants Portal | Inactive | 0 | 1
740409 | FAASt[Region 4 Caguas Transmission 38kV - Non-Sensitive (Vegetation)]- Group B | Yes | Yes | Vegetation | Vegetation-TL | No | Inactive | Inactive | Yes | Yes | Vegetation | Vegetation-TL | No | Inactive | Inactive | 715385.11 | 7927576.7 | 0 | 0 | 15610575.04 | 7616969.94 | 7993605.1 | 715385.11 | 7927576.7 | 6015.7 | 66028.4 | 0 | 0 | 8715005.91 | 721400.81 | 7993605.1 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | Project is developed and will be ready to submit to FEMA as soon as projects are reactivated in Grants Portal | Inactive | 0 | 1
740410 | FAASt[Region 2 Arecibo Transmission 38kV - Non-Sensitive (Vegetation)]- Group B | Yes | Yes | Vegetation | Vegetation-TL | No | Inactive | Inactive | Yes | Yes | Vegetation | Vegetation-TL | No | Inactive | Inactive | 21352.15 | 236614.32 | 0 | 0 | 260116.76 | 21531.7 | 238585.06 | 251201.23 | 2760513.52 | 2112.36 | 23185.29 | 0 | 0 | 3037012.4 | 253313.59 | 2783698.81 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | Project is developed and will be ready to submit to FEMA as soon as projects are reactivated in Grants Portal | Inactive | 0 | 1
740411 | FAASt [Region 5 Mayaguez Transmission 38kV - Non-Sensitive (Vegetation)]- Group B | Yes | Yes | Vegetation | Vegetation-TL | No | Inactive | Inactive | Yes | Yes | Vegetation | Vegetation-TL | No | Inactive | Inactive | 799358.09 | 8858127.48 | 0 | 0 | 9737986.32 | 806079.91 | 8931906.41 | 141749.28 | 1557718.3 | 1191.98 | 13083.11 | 0 | 0 | 1713742.67 | 142941.26 | 1570801.41 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | Project is developed and will be ready to submit to FEMA as soon as projects are reactivated in Grants Portal | Inactive | 0 | 1
740414 | FAASt [Region 6 Ponce Transmission 38kV - Non-Sensitive (Vegetation)- Group B | Yes | Yes | Vegetation | Vegetation-TL | No | Inactive | Inactive | Yes | Yes | Vegetation | Vegetation-TL | No | Inactive | Inactive | 141749.28 | 1570801.41 | 0 | 0 | 1726825.78 | 142941.26 | 1583884.52 | 799358.09 | 8784348.55 | 6721.82 | 73778.93 | 0 | 0 | 9664207.39 | 806079.91 | 8858127.48 | DSOW- Ready to Submit /Pending Reactivation | Q1 FY2027 | Project is developed and will be ready to submit to FEMA as soon as projects are reactivated in Grants Portal | Inactive | 0 | 1
[15 empty] | 0 | 0 | 428096479.743 | 970600231.6569
[17 empty] | #DIV/0! | #DIV/0!
Note on B38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: New project added to list by Transmission team
Note on P38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Se añadió el estimado del costo total del proyecto debido a que no existe un desglose disponible.
Note on P78: Orlando Rodriguez:
Note on B206: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: non sensitive numbers remain the same, others must be reduced 60% with the same comment as the exhibit 2 tab to indicate reduction

## Analisis (hidden)
project # | 684920
Project title | #REF!
| NEW COST PROVIDED | Submitted to PREB | OBLIGATED | Spend as of 2/28/2026 |  | Estimate/Cost change (Y/N) | #REF!
428 Allocation (Without the A&E and E&M) | #REF! | #REF! | #REF! | #REF! | Construction | Who confirmed the information? | #REF!
406 Allocation (Without the A&E and E&M) | #REF! | #REF! | #REF! |  |  | Obligation Amendment Status | #REF!
428 A&E-PW 9510 | #REF! | #REF! | #REF! | #REF! | A&E | New Comment | #REF!
406 A&E-PW 9510 | #REF! | #REF! | #REF! |  |  | Comentario revisor | #REF!
428 E&M-PW 10710 | #REF! | #REF! | #REF! | #REF! | E&M FINANCE | Current Versioning Status in Grants Protal | #REF!
406 E&M-PW 10710 | #REF! | #REF! | #REF! | $- | E&M GLOBAL | Date of Obligation | #REF!
FORMULA Expected Total Project Cost | #REF! | #REF! | #REF! | #REF! | TOTAL | Current Status in Grants Protal | #REF!
FORMULA Total 428 Expected cost | #REF! | #REF! | #REF! | #REF! | TOTAL WITH E&M | Construction % of Completion as of 2/28/2026 | #REF!
FORMULA Total 406 Expected Cost | #REF! | #REF! | #REF!

## Streetlight (hidden)
Option A | [5 empty] | Option B | Option B
Proyects | Count Projects | Luminarias | Estimate | 428 | 406 |  | Proyects | Count Projects | Luminarias | Estimate | 428 | 406
43 project obligated (only 17 projects have underground budget) | 43 | 172353 | 634798031.6818 | 577647101.8215 | 57150929.8603 |  | 43 project obligated |  | 179439 | 783930883.5318 | 577647101.8215 | 57150929.8603
9 municipalities | 9 | 26424 | 127686622.87 |  |  |  | 9 municipalities |  | 26424 | 127686622.87
26 projects (Attachment A) | 26 | 33898 | 346173133.84 |  |  |  | 26 projects (Attachment A) This includes Part 2 and Part 3 (Do not includes poles) |  | 33898 | 346173133.84
This includes Part 2 and Part 3 (Do not includes poles) | 36 | 82038 | 110978319.25
|  | 314713 | 1219636107.6418 | 182945416.1463 | Posible ahorro |  |  |  | 239761 | 1257790640.2418 |  | 38154532.6
con el discoup de soterrado es posible que se reemplzado algo por proitional overhead (aereo)
Los 346 incluyen $62M of work completed. | [9 empty] | luminarias impactadas
Part 2 y parte 3 no incluyen postes
En estos proyectos es posible que tegan un sobrante entre 100 y 200 millones por multiple srazones como por ejemplo: trabvajos realizados por operaciones, postes que no necesitan reemplazo ya que esta en buena condiciones y solo cambiaron la luminaria,
FEMA aprueba que si en un area requeria soterrado pero ya tenia servicio con probisional aereo se puede dejar soterrado …. si un poste ya tiene povisional aereo se pueda reemplzar y dejarlo provision aereo
So si estamos trabajando areas que se han trabajado provisional aereo
en el campo lo que se esta haciendo se esta haciendo
FEMA requiere que los trabajos cumplan con code and standards … so si habia soterrado no se puuede alimentar por aire ya que se considera provision electrica fuera del standard
6 minicipios tienen aproximadamente 96% completados por lo que el trabajo que falta con fondos fema (43 proyectos ) es minimo …. Eso no significa que no faltan trabajos Aibonito, maunabo, florida, villalba , lajas , aguada
No hay municipios 100% completados
El caso de TPA es algo pendiente a discutir que hay que atenderlo para poder completar el scope del proyecto
En la opcion 2 estariamos dejando de impactar (43,807 parte 2) y $38,291) para trabajar $7,086 en areas impactadas.
No todos los 7,086 requieren cambio de poste
Posible issue de seguridad en 7,086 que no se trabajarian per se atenderia el issue de seguridad en 86 localidades en zonas que no han sido impactadas (Barrios)
el presupuesto no da para atender postes criticos …

## Analisis (LJ) (hidden)
project # | 550106
Project title | #REF!
| NEW COST PROVIDED | previous PREP | OBLIGATED | Spend as of 2/28/2026 |  | Estimate/Cost change (Y/N) | #REF!
428 Allocation (Without the A&E and E&M) | #REF! | #REF! | #REF! | #REF! | Construction | Who confirmed the information? | #REF!
406 Allocation (Without the A&E and E&M) | #REF! | #REF! | #REF! |  |  | Obligation Amendment Status | #REF!
428 A&E-PW 9510 | #REF! | #REF! | #REF! | #REF! | A&E | New Comment | #REF!
406 A&E-PW 9510 | #REF! | #REF! | #REF! |  |  | Comentario revisor | #REF!
428 E&M-PW 10710 | #REF! | #REF! | #REF! | #REF! | E&M FINANCE | Current Versioning Status in Grants Protal | #REF!
406 E&M-PW 10710 | #REF! | #REF! | #REF! | 0 | E&M GLOBAL | Date of Obligation | #REF!
FORMULA Expected Total Project Cost | #REF! | #REF! | #REF! | #REF! | TOTAL | Current Status in Grants Protal | #REF!
FORMULA Total 428 Expected cost | #REF! | #REF! | #REF! | #REF! | TOTAL WITH E&M | Construction % of Completion as of 2/28/2026 | #REF!
FORMULA Total 406 Expected Cost | #REF! | #REF! | #REF!
#REF!
#REF!

## E3-LUMA Consolidated List (hidden)
Grants Portal- Project Costs Allocation
Project # | Title | FEMA Allocation | Asset | Sus Asset | Obligated (Yes / No) | Process Step | Project costs - Submitted to FEMA * | Current PW Version 428 Gross Cost * | 428 Allocation * | 406 Allocation * | A&E-PW 9510 * | E&M-PW 10710 * | A&E Costs Incurred | E&M Cost Incurred | Construction Cost Incurred | Total Estimate Incurred Cost | Project Status | Project Scope | Additional comments
165209 | FAASt - EPC - Culebra Substation 3801 and New Culebra Substation 3802 (Substation) | Priority | Substation | Vieques and Culebra Projects (6) | Yes | Pending Scope & Cost Completion by Applicant | 16241388 | 12765828 | 12765828 | 177391 | 2015951 | 0 | 1616014.42 | 191887.6 | 805798.03 | 2613700.05 |  | Repair and replacement of the control house HVAC, building waterproofing, protection & control features, auxiliary equipment, conduits, control cables, batteries, lights, grounding, finish grades, perimeter fence, and other components to restore functionality. | Project included in list since its already in Pipeline, soon to be Obligated. Project part of LUMA Priority Projects P3A list. Luma stated no duplication with DOE projects
165213 | FAASt – Line 5400 – Rio Blanco HP to Daguao TC to Punta Lima TO to Vieques 2501 to Culebra 3801 (Transmission) | Priority | Transmission | Vieques and Culebra Projects (6) | No | Pending Scope & Cost Completion by Applicant | 122806969.07 | 83734340.49 | 83734340.49 | 33182392.65 | 5890235.93 |  | 4695185.39 | 182727.638 | 27774.97 | 4905687.998 | 7/8/2024 - The Version 0 Boring Plan Evaluation was Completed as of June23, 2023. 6/9/2025 - The 4th HM RFI was submitted to the Applicant for their action. New Deadline is established by the Applicant for 6/26/2025." | Repair/Replace insulators, guy wires; anchors, structure connections, structure foundations or portions of the foundations; ground of the structure and overhead ground conductor; communications associated with the transmission line; conductor spans, bird caged, pitting, burns, kinks, or stretched conductor; and/or drag dampers, armor rods; and other hardware. | Project included in list since its already in Pipeline, soon to be Obligated. Project part of LUMA Priority Projects P3A list. Luma stated no duplication with DOE projects
165225 | FAASt - EPC - Vieques 2501 substation repairs & New Vieques 2502 substation (Substation) | Priority | Substation | Vieques and Culebra Projects (6) | Yes | Pending Scope & Cost Completion by Applicant | 16374033.72 | 13495526.25 | 14704637.25 | 178309 | 1491087.47 | 0 | 2036500.58 | 191887.6 | 141042.85 | 2369431.03 | Still Pending Scope and Cost by LUMA | N/A | Project included in list since its already in Pipeline, soon to be Obligated. Project part of LUMA Priority Projects P3A list. Luma stated no duplication with DOE projects
165226 | FAASt [Feeders Vieques & Culebra] (Distribution) | Priority | Distribution | Vieques and Culebra Projects (6) | No | Pending PDMG Scope & Cost Routing | 86759244 | 86759244 | 86759244 |  |  |  | 3948214 | 3237620.1979 | 760400.65 | 7946234.8479 | Pending 5th HM RFI Responses. On February 14, 2025, the applicant requested an extension until February 28, 2025, to provide responses for the 5th RFI. On February 27, 2025, they requested further time until March 14, 2025, and on March 14, 2025, they sought an additional extension until March 31, 2025.On march 31, 2025 additional extension requested for April 30, 2025. On May 28, 2025 additional extension requested for June 30, 2025. | Reconstruction of feeders across Vieques and Culebra. | Project included in list since its already in Pipeline, soon to be Obligated. Project part of LUMA Priority Projects P3A list. Luma stated no duplication with DOE projects
165268 | FAASt Rio Grande Estate Substation CH-2306 (Su |  | Substation | Substation Rebuilds | Yes | Obligated | 11683614.71 | 7098243.76 | 7098243.76 | 4585370.95 | 1391013 | $- | 3874323.9 | 698996.2 | 6132824.32 | 10706144.42 |  |  | Project included in list since its already in Pipeline, soon to be Obligated. Project part of LUMA Priority Projects P3A list
167446 | FAASt - Line 36100 (115kV) - Bayamon to Monacillos (Transmission) | Priority | Priority Transmission | Transmission | No | Pending Applicant Project Review | 38031104.5 | 34329274.96 | 34329274.96 | 0 | 3616821.54 | 85008 | 8488856.85 | 0 | 1120713.72 | 9609570.57 | "7/8/2024 - The Version 0 Boring Plan Evaluation was not Completed, additional information necessary. - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - - 6/17/2025 - The project is running in the Grant Manager queue. The project is pending CRC Project Development." | Replace structures and reconductor the entire line from Bayamon TC to Monacillos TC. | Project included in list since its already in Pipeline, soon to be Obligated. Project part of LUMA Priority Projects P3A list
168226 | FAASt San Juan 115kV Underground Transmission |  | Transmission | Transmission Line Rebuild | Yes | Obligated | 14746039.57 | 14746039.57 | 14746039.57 | $- | 584325 | $- | 1463723.59 | $- | 57399.86 | 1521123.45 |  |  | Project included in list since its already in Pipeline, soon to be Obligated. Project poart of LUMA Priority Projects P3A list and PREPA Presentation
168483 | FAASt - 115kV Line 36400 - Dos Bocas HP to Ponce TC (Transmission) | Phase 2 | Transmission | Transmission | No | Pending Scope & Cost Completion by Applicant | 0 | [5 empty] | 3565613.95 | 0 | 69711.17 | 3635325.12 | The purpose of this Version is the EHP compliance review of the projects studies that will include geotechnical testing that require vegetation removal, opening of access roads and other impacts that are closer to construction activities | "3/18/2025 - The Version 0 Boring Plan Evaluation start on March 18, 2025. 6/9/2025 - Field EHP: (ESA) Consultation process initiated; drafting ongoing. ECD 7/30/2025. 6/3/2025 - Follow up email sent to the Applicant on May 29, 2025, requesting new forecast for submission of dimensions (list of structures) of concrete foundations and revise FEMA OPGW Resolution. The project is under line priority evaluation forecasted TBD. Forecast was established for April 2025." | Project included in list since its already in Pipeline, soon to be Obligated. Project part of LUMA Priority Projects P3A list and PREPA Presentation
169058 | FAASt - Llorens Torres MC 1106 - Equipment Repair & Replacement - (Substations) | Phase 2 | Substation | Substation | No | Pending Scope & Cost Completion by Applicant | 18737178 | 18279001 | 18279001 | 0 | 458177 | 0 | 1974281.01 | 380001.1 | 13230.12 | 2367512.23 | Pending DSOW submittal by LUMA. Luma forecast pending | Repair and replacement of the metalclad switchgear, feeder cables & conduits and corresponding foundations, grounding, and other related components as necessary. | Project included in list since its already in Pipeline, soon to be Obligated.
169266 | FAASt Centro Medico 1327/1359 Equipment Repair &amp;amp; Replacement (Substation) |  | Substation | Substation Rebuilds | Yes | Obligated | 21332361 | 14795324 | 14795324 | 6537037 | 1810918 | $- | 3169739.18 | 1145298.5 | 1031849.68 | 5346887.36 |  |  | Project included in list since its already in Pipeline, soon to be Obligated.
169276 | FAASt Substation - Viaducto TC - MC 1100 - Equipment Repair & Replacement (Substation) | Phase 2 | Substation | Substation | No | Pending Scope & Cost Completion by Applicant | 20425907 | 20425907 |  |  |  |  | 3388651.17 | 915542.32 | 655231.01 | 4959424.5 | " 2/25/2025 - HM RFI Subs Matrix response send to the applicant on 2/26/2025(concluded that we can move forward with this tool. However, it is important that the subrecipient, when submitting a project, ensure that it contains all necessary information related to the mitigation measure, including a brief description of why it is considered mitigation and cost updates if it necessary 6/17/2025- Applicant update forecast date for DSOW submission to -LUMA forecast: 12/30/2025" | Replacement of the metalclad switchgear, feeder cables, conduits and corresponding foundations, grounding, and other related components as necessary | Project included in list since its already in Pipeline, soon to be Obligated.
169495 | FAASt [Substations - Tapia GIS Rebuilt Equipment Repair &amp;amp; Replacement] (Substations) |  | Substation | Substation Rebuilds | Yes | Obligated | 15339932.33 | 8180049.03 | 8180049.03 | 7159883.3 | 1397860 | 626000.6 | 1827122.61 | 626000.6 | 30331.87 | 2483455.08 |  |  | Project included in list since its already in Pipeline, soon to be Obligated.
169500 | FAASt [Bayamon TC - MC-BKRS-Y1] (Substation) |  | Substation | Substation Rebuilds | Yes | Obligated | 6372063 | 2796182 | 2796182 | 3575881 | 634045 | $- | 1489738.96 | $- | 4489905.15 | 5979644.11 |  |  | Project included in list since its already in Pipeline, soon to be Obligated.
169896 | FAASt - Costa Sur SP TC  Equipment Repair and |  | Substation | Substation Rebuilds | Yes | Obligated | 23251835 | 23251835 | 23251835 | $- | 4734912 | $- | 3085554.87 | $- | 7654798.75 | 10740353.62 |  |  | Project included in list since its already in Pipeline, soon to be Obligated.
174422 | FAASt - Catano-Rebuild 1801(Substation) |  | Substation | Substation | Yes | Obligated | 23255048.94 | 16359899.17 | 16359899.17 | 6895149.77 | 4104786 | $- | 4709154.28 | 1865179.75 | 6903541.44 | 13477875.47 |  |  | Project included in list since its already in Pipeline, soon to be Obligated.
176913 | FAASt [Palo Seco SP to Catano Sect 38kV Line- 9500] (Transmission) | Priority | Priority Transmission | Transmission | No | Pending EHP Review | 46888195.25 | 34395876.55 | 34395876.55 | 7376901 | 4817554.82 | 297862.88 | 1867030.19 | 0 | 73599.38 | 1940629.57 | 6/17/2025 - The project is running in the Grant Manager queue. The project is pending CRC Project Development. | Replace structures and reconductor the entire line from Palo Seco SP to Catano Sect
176971 | FAASt –38kV Line 8200 - San Juan SP to Catano Sect Line (Transmission) | Priority | Priority Transmission | Transmission | No | Pending EHP Review | 26444537.92 | 22273190.89 | 22273190.89 | 4723291 | 3250894.37 | 120403.36 | 1497895.03 | 8101.3782 | 62971.09 | 1568967.4982 | 6/17/2025 - The project is running in the Grant Manager queue. The project is pending CRC Project Development. | Replace structures and reconductor the entireline from SAN JUAN SP to Catano Sect
178258 | FAASt - [Taft - MC 1105] (Substations) |  | Substation | Substation | Yes | Obligated | 9362729.93 | 9362729.93 | 9362729.93 | 4123842.4 | 1302381.39 | $- | 1638735.9 | 459233.9 | 10064.69 | 2108034.49
178503 | FAASt Aguirre TC - BKRS (Substations) |  | Substation | Substation Rebuilds | Yes | Obligated | 39034592 | 39034592 | 39034592 | $- | 5171019 | $- | 4481438.56 | $- | 9459011.4 | 13940449.96
178577 | FAASt [Cachete – MC 1526] (Substations) | Phase 2 | Substation | Substation | No | Pending Scope & Cost Completion by Applicant | [6 empty] | 2119451.09 | 365667.03 | 4322.65 | 2489440.77 | " 2/25/2025 - HM RFI Subs Matrix response send to the applicant on 2/26/2025(concluded that we can move forward with this tool. However, it is important that the subrecipient, when submitting a project, ensure that it contains all necessary information related to the mitigation measure, including a brief description of why it is considered mitigation and cost updates if it necessary 6/10/2025- Follow up email sent on 3/25/2025, 4/14/2025, 4/21/2025, 5/20/2025 and 6/2/2025 requesting an update -LUMA forecast: pending" | Replace this switchgear to PREPA and industry standards, improve system resiliency, and to mitigate safety hazards due to equipment age and environmental concerns. | El proyecto inlcuye remocion de vegetacion. FEMA notifico 6-30-25 que la cuantia de millas solicitada en el scope esta incorrrecta.La mayoria no necesita vegetacion
179558 | FAASt - Manatí TC - BRKS 230 kV - (Substation) |  | Substation | Substation Rebuilds | Yes | Obligated | 1593443 | 1593443 | 1593443 | $- | 688917 | $- | 1006502.47 | $- | 359268.06 | 1365770.53 |  |  | El proyecto inlcuye remocion de vegetacion. FEMA notifico 6-30-25 que la cuantia de millas solicitada en el scope esta incorrrecta.La mayoria no necesita vegetacion
180052 | FAASt Ponce TC to Salinas Urbano TC- 38kV 100 & 200 (Transmission) | Priority | Priority Transmission | Transmission | No | Pending Applicant Project Review | 104967422.32 | 85971750.2 | 85971750.2 | 0 | 9582455.16 | 9413216.96 | 5302957.86 | 178562 | 80311.36 | 5561831.22 | 6/17/2025 - The project is running in the Grant Manager queue. The project is pending CRC Project Development. | Replace structures and reconductor the entire line from Ponce TC to Salinas Urbano TC.
334323 | FAASt Distribution Feeders - Ponce Short Term |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 392822 | 323692 | 323692 | 69130 | 26179 | $- | 259140.6 | $- | 184497.29 | 443637.89
334329 | FAASt Distribution Feeders - Ponce Short Term |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 380253 | 316119 | 316119 | 64134 | 25530 | $- | 86957.37 | $- | 298078.57 | 385035.94 |  |  | No construction Scope- Soil borings and geotechnical testing.The purpose of this Version is the EHP compliance review of the projects studies that will include geotechnical testing.
334468 | FAASt Line 2200 Dos Bocas HP to Dorado TC (T |  | Transmission | Transmission Line Rebuild | Yes | Obligated | 1217429 | 1217429 | 1217429 | $- | 242850 | $- | 1593530.72 | $- | 1568042.54 | 3161573.26
334470 | FAASt [TL 3100 Monacillos TC to Sabana Llana TC] (Transmission) | Priority | Priority Transmission | Transmission | No | Pending Large Project Review | 52098415.55 | 46064675.98 | 46064675.98 | 0 | 5039982.61 | 993756.96 | 4768004.84 | 0 | 21945.02 | 4789949.86 | 6/17/2025 - The project is running in the Grant Manager queue. The project is pending CRC Project Development. | Replace structures and reconductor the entire line from Monacillos TC to Sabana Llana TC.
334488 | FAASt Distribution Feeders - Caguas Short Ter |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 153743 | 142917 | 142917 | 10826 | 19965 | $- | -78080.37 | 4289 | 112634.04 | 38842.67 |  |  | NO DSOW submitted by LUMA- Forecast 12/30/25
334527 | FAASt Distribution Feeders - Caguas Short Term |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 123721 | 108847 | 108847 | 14874 | $- | $- | 39014.16 | $- | 43243.52 | 82257.68 |  |  | NO DSOW submitted by LUMA- Forecast Pending. No construction Scope- Soil borings and geotechnical testing.The purpose of this Version is the EHP compliance review of the projects studies that will include geotechnical testing.
542517 | FAASt -Luquillo Distribution Streetlighting |  | Distribution | Distribution Streetlighting | Yes | Obligated | 8810325.37 | 8628667.29 | 8628667.29 | 181658.08 | 2004233 | $- | 877901.9 | $- | 4324148.44 | 5202050.34
542687 | FAASt Lajas Streetlighting (Distribution) |  | Distribution | Distribution Streetlighting | Yes | Obligated | 10704668.57 | 10278336.09 | 10278336.09 | 426332.48 | 2512854 | $- | 948248.52 | $- | 5908485.78 | 6856734.3
542688 | FAASt Aguada Streetlighting (Distribution) |  | Distribution | Distribution Streetlighting | Yes | Obligated | 18571716.38 | 17764494.34 | 17764494.34 | 807222.04 | 4104786 | $- | 848494.01 | $- | 11069164.76 | 11917658.77
542690 | FAASt Maunabo Streetlighting (Distribution) |  | Distribution | Distribution Streetlighting | Yes | Obligated | 6443757.4 | 6199877.07 | 6199877.07 | 243880.33 | 1530438 | $- | 604704.64 | $- | 4601592.16 | 5206296.8
542756 | FAASt Streetlighting - Guánica (Distribution |  | Distribution | Distribution Streetlighting | Yes | Obligated | 10058046 | 9687238 | 9687238 | 370808 | 2237386 | $- | 588301.64 | $- | 3650893.96 | 4239195.6
542758 | FAASt Substation Minor Repairs -Group B (Substation) |  | Substation | Substation Rebuilds | Yes | Obligated | 3412576 | 2973035 | 2973035 | 439541 | 723314 | $- | 1020689.56 | $- | 5177717.81 | 6198407.37
542762 | FAASt Distribution Feeders - Arecibo Short Te |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 767868 | 610448 | 610448 | 157420 | $- | $- | 132446.21 | $- | 320331.6 | 452777.81
546370 | FAASt - Substation Minor Repairs Group A (Subs |  | Substation | Substation Rebuilds | Yes | Obligated | 4971175.09 | 4482972.51 | 4482972.51 | 488202.58 | 996359 | $- | 2532244.07 | $- | 3188758.43 | 5721002.5
546371 | FAASt- Substation Minor Repairs Group C (Substation) |  | Substation | Substation Rebuilds | Yes | Obligated | 3032891.2 | 2648259.06 | 2648259.06 | 384632.14 | 646473 | $- | 2040817.39 | $- | 2224234.06 | 4265051.45
547187 | FAASt - [Substation Component Replacement Program] (Substation) | Phase 2 | Substation | Substation | No | Pending Scope & Cost Completion by Applicant | 8929767 | 4790316.92 | 4790316.92 |  | 2135844 | 2333225.36 | 939146.21 | 229882.64 | 11496.2 | 1180525.05 | "6/17/2025 - Applicant submit HM RFI response on 6/6/2025. Currently under HM review -HM Forecast: 6/18/2025" | Project will involve designing and constructing a new substation to replace a flooded facility, including various electrical components and site development
547251 | FAASt Line 2400 Dos Bocas HP to America Apparel (Transmission) | Phase 2 | Transmission | Transmission | No | Pending Scope & Cost Completion by Applicant | 54042908.97 | 50289473.68 | 50289473.68 |  | 3753435.29 | 975659.88 | 2230168.28 | 0 | 35575.37 | 2265743.65 | 4/10/2025 - The Version 0 Boring Plan Evaluation was Completed as of April 8, 2025. 7/15/2025 - The project is running in the Grant Manager queue. The project is Pending EHP Review | Repair/Replace structures (including their foundations), framing and insulators, load break switches (manual and automated), conductors, guy wires, anchoring, grounding assemblies, and any other associated components. Most of the construction along this line segment consists of wood monopole guyed structures with some interspersed self-supporting steel and concrete monopoles.
549715 | FAASt Substation Minor Repairs - Group D (Substation) |  | Substation | Substation Rebuilds | Yes | Obligated | 2871257.17 | 2583133.54 | 2583133.54 | 288123.63 | 580189 | $- | 388070.19 | $- | 462002.67 | 850072.86
549725 | FAASt [Substation Minor Repairs - Group E] (Substation) |  | Substation | Substation | Yes | Obligated | 4503783.21 | 3924015.69 | 3924015.69 | 579767.52 | 818227 | $- | 345122.21 | $- | 1224004.58 | 1569126.79
549764 | FAASt Physical Security - Group 2 (Substation) |  | Substation | Substation Security | Yes | Obligated | 2383692.99 | 2159012.31 | 2159012.31 | 224680.68 | 529771 | $- | 177827.09 | $- | 964332.88 | 1142159.97
550106 | FAASt [Conquistador CH] (Substation) | Phase 2 | Substation | Substation | No | Pending Scope & Cost Completion by Applicant | 11639958 | 11639958 |  |  |  |  | 2894958.74 | 0 | 772606.85 | 3667565.59 | " 2/25/2025 - HM RFI Subs Matrix response send to the applicant on 2/26/2025(concluded that we can move forward with this tool. However, it is important that the subrecipient, when submitting a project, ensure that it contains all necessary information related to the mitigation measure, including a brief description of why it is considered mitigation and cost updates if it necessary 6/10/2025- Follow up email sent on 3/25/2025, 4/14/2025, 4/21/2025, and 6/2/25 requesting an update-LUMA forecast: pending" | Replacing the damaged control house and functionally dependent elements.
550896 | FAASt Line 6700 Martin Peña TC to Villamar Se |  | Transmission | Transmission Line Rebuild | Yes | Obligated | 690703 | 690703 | 690703 | $- | 133416 | $- | 414554.26 | $- | 1155649.72 | 1570203.98
550910 | FAASt Physical Security - Group 1 (Substatio |  | Substation | Substation Security | Yes | Obligated | 6691229.18 | 6025270.22 | 6025270.22 | 665958.96 | 1278328 | $- | 2301231.05 | $- | 8053644.37 | 10354875.42
550950 | FAASt - EPC - [Monacillo TC] (Substations) | Priority | Priority Substation | Substation | Yes | Obligated | 103349156.37 | -29901321.56 | 58195134.17 | 0 | 2179830 | 42974192.2 | 4210529.76 | 6199138 | 4908549 | 15318216.76 | Obligated EPC Portion- Version in process $88,096,456 | Monacillos Transformer Replacement - Stabilization phase- Need to clarify - Work identified under the scope and also under DOE Grant funds
551861 | FAASt [Physical Security - Group 3] (Substation) |  | Substation | Substation Security | Yes | Obligated | 4133339.83 | 3696956.6 | 3696956.6 | 436383.23 | 844837 | $- | 368850.58 | $- | 2771311.86 | 3140162.44
551914 | FAASt [Caparra 1912 & 1924] (Substation) | Phase 2 | Substation | Substation | No | Pending Scope & Cost Completion by Applicant | [6 empty] | 1757341.73 | 222662.22 | 3303.67 | 1983307.62 | "4/6/2025- Email was sent to the applicant with the HM RFI response remarks, after evaluating the data submitted by the subrecipient, we still need more information to finalize our evaluation. 6/10/2025- Follow up email was sent to the applicant reuqesting update/forecast regarding the HM RFI #2 -LUMA forecast: pending" | Soil borings and geotechnical testing.The purpose of this Version is the EHP compliance review of the projects studies that will include geotechnical testing.
551925 | FAASt [SCADA Remote Access and RTU Replacements Group 1] (Telecommunication) |  | Telecommunication | IT OT Telecom Systems and Network | Yes | Obligated | 7664336.14 | 5962412.52 | 5962412.52 | 1701923.62 | 1248409.29 | $- | 3035781.94 | $- | 3860099.94 | 6895881.88
551926 | FAASt [SCADA Remote Access and RTU Replacements Group 2] (Telecommunication) | Phase 2 | Telecommunication | Telecomm | No | Pending Large Project Review | 6753699.16 | 5267467.99 | 5267467.99 | 1073462.61 |  |  | 1021302.13 | 0 | 186846.07 | 1208148.2 | Before moving the project forward to the CRC, LUMA must update the “Legend Sites” tab of the Cost Estimate, as it includes the substations that were removed from this new version. | SCADA Remote Access and RTU Replacements
551963 | FAASt [Transport Network Group 1] (Telecommunication) | Pipeline | Telecommunication | Telecom | Yes | Obligated | 7469879.13 | 5490296.88 | 5490296.88 | 0 | 836416.02 | 1143166.23 | 11643381.74 | 0 | 251121.15 | 11894502.89 | Pending Recipient Review- Pending LUMA information regarding A&E COSTS | Project involves assessing sites and designing/installing "Make-Ready" infrastructure and Transport/ITOT network equipment, followed by commissioning and transitioning substation OT services.
657300 | FAASt ENERGY MANAGEMENT SYSTEM (EMS) (Teleco |  | Telecommunications | IT OT Telecom Systems and Network | Yes | Obligated | 48941484 | 48941484 | 48941484 | $- | 2041312 | $- | 12760203.26 | $- | 7242840.54 | 20003043.8
659623 | FAASt Distribution Streetlighting - Cataño ( |  | Distribution | Distribution Streetlighting | Yes | Obligated | 17562047 | 16996758 | 16996758 | 565289 | 3574763 | $- | 1051504.25 | $- | 2703638.95 | 3755143.2
659625 | FAASt Distribution Streetlighting - Dorado |  | Distribution | Distribution Streetlighting | Yes | Obligated | 24370617 | 22864972 | 22864972 | 1505645 | 4716594 | $- | 1323359.29 | $- | 4703608.17 | 6026967.46
659715 | FAASt Distribution Streetlighting - Aibonito |  | Distribution | Distribution Streetlighting | Yes | Obligated | 7253285 | 7074498 | 7074498 | 178787 | 1880873 | $- | 666646.39 | $- | 5340687.39 | 6007333.78
659968 | FAASt [San Germán Streetlighting] (Distributio |  | Distribution | Distribution Streetlighting | Yes | Obligated | 34882926 | 30849348 | 30849348 | 4033578 | 4619207 | $- | 2805481.84 | $- | 16140318.72 | 18945800.56
660227 | FAASt Hatillo Streetlight (Distribution) |  | Distribution | Distribution Streetlighting | Yes | Obligated | 20334482.95 | 18570095.25 | 18570095.25 | 1764387.7 | 4317860 | $- | 1528483.37 | $- | 8201377.28 | 9729860.65
660239 | FAASt Streetlighting - Villalba (Distributio |  | Distribution | Distribution Streetlighting | Yes | Obligated | 10872401.71 | 10190536.05 | 10190536.05 | 681865.66 | 2630719 | $- | 1161252.98 | $- | 13498499.82 | 14659752.8
660422 | FAASt [Physical Security - Group 4] (Substation) |  | Substation | Substation Security | Yes | Obligated | 3816798 | 3478518 | 3478518 | 338280 | 766618 | $- | 207995.2 | $- | 276033.93 | 484029.13
660437 | FAASt Manati Streetlight (Distribution) |  | Distribution | Distribution Streetlighting | Yes | Obligated | 28636829 | 27067865 | 27067865 | 1568964 | 5821636 | $- | 991106.29 | $- | 8006269.21 | 8997375.5
662238 | FAASt [Microwave Point-to-Point Backbone] (Telecommunications) | Phase 2 | Telecommunication |  | No | Pending PDMG Scope & Cost Routing | 34875800.66 | 14142413.06 | 14142413.06 | 3014559.92 | 3576414.62 |  | 967053.02 | 0 | 1656.83 | 968709.85 | DSOW was submitted to FEMA on 7/25
668583 | FAASt Line 13300 GOAB 13301C to Hato Tejas Se |  | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 453597 | 453597 | 453597 | $- | 81996 | $- | 258618.76 | $- | 806252.74 | 1064871.5
668592 | FAASt Line 9800 Bayamon TC - Guaraguao Sect |  | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 420866 | 420866 | 420866 | $- | 43984 | $- | 165754.37 | $- | 389292.9 | 555047.27
671502 | FAASt [Distribution Streetlighting - Yabucoa] (Distribution) |  | Distribution | Distribution Streetlighting | Yes | Obligated | 16883989.33 | 14918381.07 | 14918381.07 | 1965608.26 | 2741367 | $- | 2241258.77 | $- | 8654781.04 | 10896039.81
673292 | FAASt Telecom Infrastructure - Cerro Puntas (Telecommunication) | Pipeline | Telecommunication | Telecomm | No | Pending Award | 9249004.2 | 8124106.79 | 8124106.79 | 49577.82 | 1075319.59 |  | 562200.86 | 0 | 56242.57 | 618443.43 | "Field EHP - Historic: SHPO consultation process initiated; drafting ongoing. Expected Completion Date: 06/27/2025. " | Update the tower facilities and telecommunication building to current codes and standards via repair. This will be achieved by performing the engineering and structural assessments necessary to establish the amount of damage and the necessary repairs or rebuild to update or replace the structure. The engineering assessment shall include the field mapping of structure and appurtenances, geotechnical study, and foundation exploratory. A run rigorous tower structural analysis will be done and with results determined if the tower needs a minor repair or a major repair.
673504 | FAASt [Distribution Streetlighting - Gurabo] |  | Distribution | Distribution Streetlighting | Yes | Obligated | 20742294 | 19208994 | 19208994 | 1533300 | 3043675 | $- | 993893.82 | $- | 6708919.8 | 7702813.62
673771 | FAASt Distribution Pole and Conductor Repair |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 2366560.53 | 1894033.53 | 1894033.53 | 472527 | 370850 | $- | 622290.85 | $- | 1010361.13 | 1632651.98
673772 | FAASt Distribution Pole and Conductor Repair |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 4122520 | 3286536 | 3286536 | 835984 | 636837 | $- | 528906.42 | 21445 | 3092140.64 | 3642492.06
673774 | FAASt Distribution Pole and Conductor Repair |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 1766951 | 1408531 | 1408531 | 358420 | 273831 | $- | 621752.39 | $- | 2673667.99 | 3295420.38
673775 | FAASt Distribution Pole and Conductor Repair |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 4432647.91 | 3575454.81 | 3575454.81 | 857193.1 | 689888 | $- | 963321.48 | 8578 | 5444606.36 | 6416505.84
673795 | FAASt Distribution Pole and Conductor Repair - |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 1794117 | 1425163 | 1425163 | 368954 | 278117 | $- | 430267.01 | $- | 1531177.29 | 1961444.3
673818 | FAASt Distribution Pole and Conductor Repair |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 793418 | 621804 | 621804 | 171614 | 121044 | $- | 154573.07 | $- | 755326.78 | 909899.85
673836 | FAASt Distribution Pole and Conductor Repair- |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 5751036.48 | 4686914.68 | 4686914.68 | 1064121.8 | 900015 | $- | 498382.68 | 25734 | 4899899.59 | 5424016.27
673838 | FAASt Distribution Pole and Conductor Repair |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 357614 | 284349 | 284349 | 73265 | 55024 | $- | 125745.69 | $- | 313557.05 | 439302.74
673839 | FAASt Distribution Pole and Conductor Repair- |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 26298 | 20468 | 20468 | 5830 | 10153 | $- | 47480.18 | $- | 38208.48 | 85688.66
673843 | FAASt Distribution Pole and Conductor Repair- |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 1131855 | 904194 | 904194 | 227661 | 175796 | $- | 337772.79 | $- | 2092281.74 | 2430054.53
673844 | FAASt Distribution Pole and Conductor Repair |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 1392064.88 | 1072850.98 | 1072850.98 | 319213.9 | 208800.6 | $- | 299669.11 | $- | 1296761.89 | 1596431
673847 | FAASt Distribution Pole and Conductor Repair- |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 240513 | 190570 | 190570 | 49943 | 37242 | $- | 168168.04 | $- | 752209.49 | 920377.53
673848 | FAASt Distribution Pole and Conductor Repair- |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 49345 | 43725 | 43725 | 5620 | 13281 | $- | 33613.29 | $- | 88774.55 | 122387.84
674072 | FAASt Distribution Pole and Conductor Repair |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 1111094 | 872891 | 872891 | 238203 | 171585 | $- | 206088.67 | $- | 943635.31 | 1149723.98
674083 | FAASt Distribution Pole and Conductor Repair |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 2110462 | 1747929 | 1747929 | 362533 | 335721.9 | $- | 264695.57 | 4289 | 1389339.82 | 1658324.39
674088 | FAASt Distribution Pole and Conductor Repair |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 1702021 | 1412368 | 1412368 | 289653 | 267370 | $- | 283895.59 | $- | 1690126.27 | 1974021.86
674092 | FAASt Distribution Pole and Conductor Repair |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 531730 | 441308 | 441308 | 90422 | 82578 | $- | 151322.56 | $- | 758832.47 | 910155.03
674096 | FAASt Distribution Pole and Conductor Repair |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 2092280 | 1773428 | 1773428 | 318852 | 332705 | $- | 314835.57 | $- | 1848760.41 | 2163595.98
674098 | FAASt Distribution Pole and Conductor Repair |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 107755 | 84433 | 84433 | 23322 | 16516 | $- | 20781.84 | $- | 98678.17 | 119460.01
678789 | FAASt [Distribution Streetlighting - Carolina] (Distribution) |  | Distribution | Distribution Streetlighting | Yes | Obligated | 16024559.58 | 14865613.02 | 14865613.02 | 1158946.56 | 2559493 | $- | 1014187.47 | $- | 4869954.57 | 5884142.04
678793 | FAASt [Streetlighting - Mayagüez] (Distribution) |  | Distribution | Distribution Streetlighting | Yes | Obligated | 12371384.46 | 11019180.1 | 11019180.1 | 1352204.36 | 2291581 | $- | 1227102.59 | $- | 3337857.63 | 4564960.22
678800 | FAASt [Telecom Infrastructure – Group B] (Telecommunication) | Phase 2 | Telecommunication | Telecomm | No | Pending Large Project Review | 16033618.38 | 13148929.44 | 13148929.44 | 55895.84 | 2828793.1 |  | 1217780.55 | 0 | 244332.31 | 1462112.86 | HM ph2 RFI sent on 7/7/2025 | Atalaya, El Gato, Isabela Plata 1, La Santa, and Manatí TC boring & self-supported tower.
678985 | FAASt Distribution Pole and Conductor Repair- |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 407945.84 | 353628 | 353628 | 54317.84 | 66915 | $- | 224811 | $- | 540687.44 | 765498.44 |  |  | Projects were included in the Consolidated Plan with the condition that as establihsed by FEMA, funding will be through 406 Funds
678988 | FAASt Distribution Pole and Conductor Repair- |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 1117787.16 | 911136.76 | 911136.76 | 206650.4 | 175441 | $- | 89681.86 | 4289 | 920648.32 | 1014619.18 |  |  | Projects were included in the Consolidated Plan with the condition that as establihsed by FEMA, funding will be through 406 Funds
679025 | FAASt Distribution Pole and Conductor Repair |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 298631 | 243073 | 243073 | 55558 | 46884 | $- | 55818.83 | $- | 387677.87 | 443496.7
679026 | FAASt Distribution Pole and |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 590296 | 483786 | 483786 | 106510 | 93451 | $- | 114366.01 | $- | 828324.66 | 942690.67
679033 | FAASt Distribution Pole and Conductor Repair |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 908942 | 729040 | 729040 | 179902 | 140628 | $- | 69214.89 | $- | 774072.08 | 843286.97 |  |  | Repair and replacement of the control house, building waterproofing, protection & control features, auxiliary equipment, 38 kV circuit breaker & steel structure, foundations, conduit, control cables, batteries, lights, grounding, finish grade, perimeter fence and other components to restore functionality.
679039 | FAASt [Distribution Streetlighting - Caguas] (Distribution) |  | Distribution | Distribution Streetlighting | Yes | Obligated | 75586568.64 | 73737224.58 | 73737224.58 | 1849344.06 | 8534897 | $- | 1280396.6 | $- | 3415757.42 | 4696154.02 |  |  | The formulation of this project will depend on the resulution or modification of the actual Environmental & Historic Preservation(EHP) determination. Project formualtion process needs to be revised. If no corrections are executed, Project to be removed from the FAAST Consolidated Plan List
679127 | FAASt Distribution Pole and Conductor Repair |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 217162.81 | 171152.23 | 171152.23 | 46010.58 | 33340 | $- | 39197.46 | $- | 125266.97 | 164464.43 |  |  | Luma agreed to complete request by July 31,2025. If RFI response is not completed or the response doesn't suffice FEMA request, Project to be removed from the FAAST Consolidated Plan List
679134 | FAASt Distribution Pole and Conductor Repair |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 563557.15 | 452956.93 | 452956.93 | 110600.22 | 86724 | $- | 65918.07 | $- | 461596.63 | 527514.7
679149 | FAASt Distribution Pole and Conductor Repair - |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 157187 | 129744 | 129744 | 27443 | 25191 | $- | 29161.03 | $- | 64621.5 | 93782.53
679153 | FAASt Distribution Pole and Conductor Repair |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 215184.01 | 589335 | 163846.51 | 157153 | 31068 | $- | 28410.65 | $- | 92105.95 | 120516.6
679457 | FAASt Distribution Pole and Conductor Repair |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 746488 | 589335 | 589335 | 157153 | 115386 | $- | 97175.13 | $- | 522647.6 | 619822.73
679458 | FAASt Distribution Pole and Conductor Repair |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 593918 | 498436 | 498436 | 95482 | 95421 | $- | 51373.3 | $- | 433201.44 | 484574.74
679780 | FAASt [Distribution Streetlighting - Bayamon] (Distribution) |  | Distribution | Distribution Streetlighting | Yes | Obligated | 21886903 | 20710527 | 20710527 | 1176376 | 3212958 | $- | 1018351.15 | $- | 7358956.92 | 8377308.07
681672 | FAASt Transmission Priority Pole Replacements |  | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 216367 | 214124 | 214124 | 2243 | 26175 | $- | 382983.33 | $- | 485271.97 | 868255.3
682028 | FAASt Distribution Pole and Conductor Repair |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 537125.3 | 65944 | 431381.68 | 11661 | 83822 | $- | 99485.03 | $- | 377347.34 | 476832.37
682031 | FAASt Distribution Pole and Conductor Repair |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 625198 | 516951 | 516951 | 108247 | 94044 | $- | 140556.79 | $- | 147624.06 | 288180.85
682121 | FAASt - EPC -Aguirre TC-Phase II (Substation) |  | Substation | Substation Rebuilds | Yes | Obligated | 82726096.38 | 82726096.38 | 82726096.38 | $- | 11520000 | $- | 4521650.9 | $- | 4685732.23 | 9207383.13
682135 | FAASt Distribution Pole and Conductor Repair |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 693780.53 | 573047.24 | 577000.79 | 136182.31 | 109859 | $- | 80174.1 | $- | 512202.6 | 592376.7
682136 | FAASt Distribution Pole and Conductor Repair- |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 565605 | 469650.95 | 469650.95 | 95954.05 | 90260 | $- | 142509.24 | $- | 488551.24 | 631060.48
682172 | FAASt Distribution Pole and Conductor Repair |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 266071.35 | 516951 | 208400 | 108247 | 40930 | $- | 116501.33 | $- | 297317.73 | 413819.06
682178 | FAASt Distribution Pole and Conductor Repair |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 262290.31 | 208544.25 | 208544.25 | 53746.06 | 40949 | $- | 86535.03 | $- | 142850.31 | 229385.34
682180 | FAASt Distribution Pole and Conductor Repair |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 54402 | 431381.68 | 43374 | 105743.62 | 8414 | $- | 38779.95 | $- | 89758.29 | 128538.24
682210 | FAASt Distribution Pole and Conductor Repair - |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 239847.61 | 198050.74 | 198050.74 | 41796.87 | 38248 | $- | 43558.98 | $- | 172098.59 | 215657.57
682228 | FAASt Distribution Pole and Conductor Repair - |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 952661.42 | 775779 | 775779 | 176882.42 | 150784 | $- | 218822.5 | $- | 475456.94 | 694279.44
682324 | FAASt Distribution Pole and Conductor Repair |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 709229.55 | 573047.24 | 573047.24 | 136182.31 | 110616 | $- | 80482.12 | $- | 664335.2 | 744817.32
682328 | FAASt [Bayamón TC - Rebuild] (Substation) | Phase 2 | Substation | Substation | No | Pending Scope & Cost Completion by Applicant | 2905296.08 | 2637502.74 | 2637502.74 | 0 | 267793.34 | 0 | 2712040.26 | 15305049.39 | 14826874.56 | 32843964.21 | "6/17/2025 -PREB Resolution and Approval received on 4/11/2025. Pending DSOW and CE -LUMA forecast: 7/3/2025" | 230 kV Transformer Transportation & Installation.
682373 | FAASt Distribution Pole and Conductor Repair |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 77605 | 20584 | 65944 | 4995 | 12740 | $- | 22732.55 | $- | 56953.82 | 79686.37
682645 | FAASt [Maunabo TC] (Substation) |  | Substation | Substation | Yes | Obligated | 8292124.95 | 8292124.95 | 8292124.95 | $- | 1605121.68 | 90637.5 | 2435755.36 | 1551782.29 | 113432.08 | 4100969.73
682834 | FAASt [EPC - Costa Sur TC - Phase II & III ] (Substation) | Priority-Pipeline | Priority Substation | Substation | Yes | Obligated | 78862691.85 | -24526745.94 | 36917509.58 | 0 | 6435349.91 | 35509832.36 | 3810069.76 | 2229261.1 | 271586.29 | 6310917.15 | Obligated EPC Portion- Version in process to include transformer costs and remove equipment costs already obligated under PW 10710 and A&E under PW 9510 | Costa Sur Transformer Replacement -Replacement of the existing infrastructure and transmission breakers according to the new proposed 115 kV single line diagram with a gas insulated switchgear (GIS) in breaker-and-a-half configuration. Replace the 230 supply cables for autotransformer Bank #1.Flood mitigation for 115 kV and 38 kV sites due to flood zone location (ABFE Flood Zone A).Construction of new control facilities for 115 kV and 38 kV to include protection, control, and metering equipment. (60 FT x 30 FT) Replace the existing Bank #1: 115/38 kV, 60/80/100/112 MVA transformer with a new one since it has been in service since 1991 and is reaching the end of its useful life. The impedance of this transformer shall be like the existing one. Replace the existing Bank #2: 115/38 kV, 60/80/100/112 MVA transformer with a new one. This bank has 30 years of service and will be kept as an on-site spare in a pad. H.Provide a spare 230/115 kV transformer on a pad on site. Emergency Generator needed at site. (Generator pad size 7FT x 4 FT).
682865 | FAASt Distribution Pole and Conductor Repair |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 91831 | 250906 | 70683 | 68700 | 13377 | $- | 48493.26 | $- | 94910.87 | 143404.13
682870 | FAASt Distribution Pole and Conductor Repair |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 103412.77 | 85921.77 | 85921.77 | 17491 | 16717 | $- | 35944.33 | $- | 109637.54 | 145581.87
682882 | FAASt Distribution Pole and Conductor Repair |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 659039.4 | 70683 | 545661.24 | 21148 | 104353 | $- | 65730.97 | $- | 500085.92 | 565816.89
682890 | FAASt Distribution Pole and Conductor Repair |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 612378.63 | 510067.96 | 510067.96 | 102310.67 | 98276 | $- | 76914.95 | $- | 584279.64 | 661194.59
682898 | FAASt Distribution Pole and Conductor Repair |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 744027.12 | 208400 | 635326.93 | 57671.35 | 120284 | $- | 118177.78 | 4289 | 816959.08 | 939425.86
682910 | FAASt Distribution Pole and Conductor Repair |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 622823 | 443331 | 517156 | 98484 | 99229 | $- | 56103.43 | 4289 | 568820.71 | 629213.14
684920 | FAASt Substation High Voltage Replacement_Group 1 (Substation) |  | Substation | Substation Rebuilds | Yes | Obligated | 6929384 | 6929384 | 6929384 | $- | 958084 | $- | 6846779.79 | $- | 7312139.79 | 14158919.58
685263 | FAASt Distribution Pole and Conductor Repair - |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 672383 | 537688 | 537688 | 134695 | 103281 | $- | 60918.66 | $- | 455288.46 | 516207.12
685370 | FAASt Distribution Pole and Conductor Repair |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 83809 | 577000.79 | 68823 | 116779.74 | 13127 | $- | 27864.95 | $- | 50766.55 | 78631.5
685477 | FAASt Distribution Pole and Conductor Repair - |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 413482 | 198050.74 | 355178 | 41796.87 | 67123 | $- | 105817.1 | $- | 319862.76 | 425679.86
685943 | FAASt Distribution Pole and Conductor Repair P |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 318232.22 | 254972.22 | 254972.22 | 63260 | 49774 | $- | 61593.62 | $- | 259777.72 | 321371.34
686453 | FAASt Distribution Pole and Conductor Repair |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 25579 | 68823 | 20584 | 14986 | 4059 | $- | 17941.39 | $- | 30346.2 | 48287.59
686471 | FAASt Distribution Pole and Conductor Repair |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 319606 | 498436 | 250906 | 95482 | 49227 | $- | 59559.91 | $- | 335642.27 | 395202.18
686480 | FAASt Distribution Pole and Conductor Repair - |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 632056 | 164908.86 | 523404 | 14986 | 101359 | $- | 86732.42 | $- | 446374.77 | 533107.19
688096 | FAASt Distribution Pole and Conductor Repair |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 27238.64 | 517156 | 21408.25 | 105667 | 4169 | $- | 9130.83 | $- | 33824.25 | 42955.08
688109 | FAASt Distribution Pole and Conductor Repair |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 563429.26 | 19848.36 | 448719.06 | 5830.39 | 87444 | $- | 131732.42 | $- | 374639.31 | 506371.73
688198 | FAASt Distribution Pole and Conductor Repair - |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 76862.24 | 60838.48 | 60838.48 | 16023.76 | 12053 | $- | 30569.12 | $- | 52234.74 | 82803.86
688472 | FAASt Distribution Pole and Conductor Repair - |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 179894.86 | 164908.86 | 164908.86 | 14986 | 29922 | $- | 33371.4 | $- | 89606.42 | 122977.82
688625 | FAASt Distribution Pole and Conductor Repair |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 901290.28 | 710014.69 | 710014.69 | 191275.59 | 139358 | $- | 116897.52 | $- | 416779.53 | 533677.05
688627 | FAASt Distribution Pole and Conductor Repair |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 375962.49 | 303774 | 303774 | 72188.49 | 58918 | $- | 35419.14 | $- | 148707.88 | 184127.02
688629 | FAASt Distribution Pole and Conductor Repair |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 134828.92 | 106941.99 | 106941.99 | 27886.93 | 20834 | $- | 39625.81 | $- | 53225.75 | 92851.56
688630 | FAASt Distribution Pole and Conductor |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 52719.38 | 42728.41 | 42728.41 | 9990.97 | 8327 | $- | 43140.83 | $- | 29090.4 | 72231.23
688774 | FAASt Distribution Pole and Conductor Repair |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 541815 | 443331 | 443331 | 98484 | 86719 | $- | 71676.65 | $- | 236156.1 | 307832.75
689071 | FAASt Distribution Pole and Conductor Repair |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 77036.24 | 211622.76 | 59545.08 | 33717.31 | 11879 | $- | 46699.71 | $- | 90234.59 | 136934.3
690545 | FAASt Aguadilla Streetlight (Distribution) |  | Distribution | Distribution Streetlighting | Yes | Obligated | 21092584 | 19796809 | 19796809 | 1295775 | 3021242 | $- | 1059765.51 | $- | 3734213.74 | 4793979.25
691246 | FAASt Distribution Pole and Conductor Repair |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 245340.07 | 211622.76 | 211622.76 | 33717.31 | 41364 | $- | 83544.29 | $- | 275625.55 | 359169.84
691702 | FAASt Distribution Streetlighting - Trujillo Alto (Distribution) |  | Distribution | Distribution Streetlighting | Yes | Obligated | 26286925 | 25277347 | 25277347 | 1009578 | 3389490 | $- | 383816.18 | $- | 1441312.25 | 1825128.43
698424 | FAASt Streetlight Florida Distribution |  | Distribution | Distribution Streetlighting | Yes | Obligated | 10309031.53 | 9311841.53 | 9311841.53 | 997190 | 1705096 | $- | 563905.12 | $- | 2899921.72 | 3463826.84
698439 | FAASt Streetlight - Las Marías (Distribution) |  | Distribution | Distribution Streetlighting | Yes | Obligated | 8360922 | 7073217 | 7073217 | 1287705 | 1653390 | $- | 1319107.47 | $- | 1875384.74 | 3194492.21
698458 | FAASt [Distribution Streetlighting - Guaynabo] (Distribution) |  | Distribution | Distribution Streetlighting | Yes | Obligated | 10615811.01 | 9762754.59 | 9762754.59 | 853056.42 | 1979750 | $- | 654182.33 | $- | 5229160.84 | 5883343.17
698511 | FAASt [Culebra Streetlighting] (Distribution) |  | Distribution | Distribution Streetlighting | Yes | Obligated | 1309407 | 1155804 | 1155804 | 153603 | 476439 | $- | 149025.55 | $- | 1417626.5 | 1566652.05
698570 | FAASt [Distribution Streetlighting - Corozal] (Distribution) |  | Distribution | Distribution Streetlighting | Yes | Obligated | 15946081.93 | 13720208.31 | 13720208.31 | 2225873.62 | 2501126 | $- | 1833309.27 | $- | 8957753.14 | 10791062.41
698579 | FAASt [Distribution Streetlighting - Orocovis] (Distribution) |  | Distribution | Distribution Streetlighting | Yes | Obligated | 9410766.24 | 8070964.96 | 8070964.96 | 1339801.28 | 1873982 | $- | 417640.86 | $- | 3960628.32 | 4378269.18
701472 | FAASt [Comerio Streetlighting] (Distribution) |  | Distribution | Distribution – Pole Replacement | Yes | Obligated | 7400895.19 | 6538769.44 | 6538769.44 | 862125.75 | 1640383 | $- | 275864.56 | $- | 2533032.7 | 2808897.26
701495 | FAASt Distribution Pole and Conductor Repair |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 25678.75 | 186321 | 19848.36 | 51841 | 3960 | $- | 13366.51 | $- | 16973.02 | 30339.53
701504 | FAASt Distribution Pole and Conductor Repair |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 188223 | 64425.44 | 150345 | 16226.16 | 29252 | $- | 26889.93 | $- | 48016.17 | 74906.1
701545 | FAASt Distribution Pole and Conductor Repair |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 616229 | 487190 | 487190 | 129039 | 95198 | $- | 133293.76 | $- | 362477.46 | 495771.22
701552 | FAASt Distribution Pole and Conductor Repair |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 238162 | 59545.08 | 186321 | 17491.16 | 36670 | $- | 78353.75 | $- | 162721.38 | 241075.13
701555 | FAASt Distribution Pole and Conductor Repair |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 649427 | 547010 | 547010 | 102417 | 104535 | $- | 92783.74 | $- | 381000.12 | 473783.86
701679 | FAASt Distribution Pole and Conductor Repair |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 80651.6 | 448719.06 | 64425.44 | 114710.2 | 12535 | $- | 37422.72 | $- | 104027.26 | 141449.98
703535 | FAASt [Toa Baja Streetlighting] (Distribution) |  | Distribution | Distribution Streetlighting | Yes | Obligated | 10149325.06 | 9529190.37 | 9529190.37 | 620134.69 | 1814022 | $- | 389413.93 | $- | 2941234.55 | 3330648.48
704679 | FAASt Coamo Streetlight (Distribution) |  | Distribution | Distribution Streetlighting | Yes | Obligated | 16372823.8 | 14311922.45 | 14311922.45 | 2060901.35 | 2687464 | $- | 1901176.74 | $- | 11452286.8 | 13353463.54
704750 | FAASt Distribution Pole and Conductor Repair - |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 578629 | 486385 | 486385 | 92244 | 92511 | $- | 86614.84 | $- | 450125.21 | 536740.05
704751 | FAASt Distribution Pole and Conductor Repair - |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 435167 | 338491 | 338491 | 96676 | 66168 | $- | 167240.84 | $- | 207250.59 | 374491.43
704755 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 12-13-14] (Distribution) |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 524391.61 | 438209.69 | 438209.69 | 86181.92 | 83451 | $- | 125785.53 | $- | 485612.53 | 611398.06
704844 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 16-17-18-19-20] (Distribution) |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 409298 | 320740 | 320740 | 88558 | 62490 | $- | 88175.68 | $- | 237671.92 | 325847.6
704849 | FAASt [Naguabo Streetlighting] (Distribution) |  | Distribution | Distribution Streetlighting | Yes | Obligated | 13290413.39 | 11620676.42 | 11620676.42 | 1669736.97 | 2380243 | $- | 837167.01 | $- | 5751206.08 | 6588373.09
704868 | FAASt [Ceiba Streetlighting] (Distribution) |  | Distribution | Distribution Streetlighting | Yes | Obligated | 5869029.74 | 5152111.14 | 5152111.14 | 716918.6 | 1481547 | $- | 227332.52 | $- | 2425633.81 | 2652966.33
704916 | FAASt [Distribution Pole and Conductor Repair |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 303970 | 273996 | 273996 | 29974 | 49755 | $- | 109616.53 | $- | 214622.57 | 324239.1
704921 | FAASt [Barranquitas Streetlighting] (Distribution) |  | Distribution | Distribution Streetlighting | Yes | Obligated | 11007375.31 | 9430329.22 | 9430329.22 | 1577046.09 | 2048083 | $- | 504338.39 | $- | 3977175.22 | 4481513.61
704927 | FAASt [Añasco Streetlighting] (Distribution) |  | Distribution | Distribution – Pole Replacement | Yes | Obligated | 13908238.09 | 12087876.17 | 12087876.17 | 1820361.92 | 2420466 | $- | 672255.47 | $- | 5175593.74 | 5847849.21
704933 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 13-14-15-16] (Distribution) |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 1426151 | 1201420 | 1201420 | 224731 | 231255 | $- | 209146.24 | $- | 707034.29 | 916180.53
704938 | FAASt [Distribution Streetlighting - Las Piedras (Distribution) |  | Distribution | Distribution Streetlighting | Yes | Obligated | 15615524.51 | 13807923.4 | 13807923.4 | 1807601.11 | 2760454 | $- | 867824.8 | $- | 5579364.55 | 6447189.35
704943 | FAASt [Naranjito Streetlighting] (Distribution) |  | Distribution | Distribution Streetlighting | Yes | Obligated | 13759586.8 | 11644048.43 | 11644048.42 | 2115538.38 | 2348210 | $- | 561479.02 | $- | 3745401.99 | 4306881.01
705527 | FAASt [Distribution Pole and Conductor Repair - San Juan 17-18-19-20-21] (Distribution) |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 767854 | 642721 | 642721 | 125133 | 125147 | $- | 182210.29 | $- | 475974 | 658184.29
705584 | FAASt [Distribution Pole and Conductor Repair - Ponce Groups 14 &amp;amp; 15] (Distribution) |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 1842979 | 1464496 | 1464496 | 378483 | 284698 | $- | 160901.25 | $- | 1284603.82 | 1445505.07
708579 | FAASt [Distribution Pole and Conductor Repair - Ponce Group 16, 17, 18 &amp;amp; 19] (Distribution) |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 2154006.76 | 1764568.92 | 1764568.92 | 389437.84 | 343118 | $- | 284695.81 | $- | 1829580.44 | 2114276.25
708637 | FAASt T-Pole Program Line 3700] (Transmission) |  | Transmission | Grid Automation | Yes | Obligated | 377354.58 | 303960.92 | 303960.92 | 73393.66 | 39574 | $- | 618160.79 | $- | 817311.81 | 1435472.6
709631 | FAASt [Morovis Streetlighting] (Distribution) |  | Distribution | Distribution Streetlighting | Yes | Obligated | 15230881.12 | 13486398.85 | 13486398.85 | 1744482.27 | 2499521 | $- | 520562.03 | $- | 4676922.1 | 5197484.13
710094 | FAASt [Pole and Conductor Repair - Bayamon Group 1 - Phase 2] (Distribution) |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 7291385.82 | 7096249.5 | 7096249.5 | 195136.32 | 614123 | $- | 288567.74 | $- | 4946400.03 | 5234967.77
710099 | FAASt [Pole and Conductor Repair - Arecibo Group 1 - Phase 2] (Distribution) |  | Distribution | Grid Automation | Yes | Obligated | 6943798.62 | 6704421.69 | 6704421.69 | 239376.93 | 602047 | $- | 158541.5 | $- | 5492233.61 | 5650775.11
710110 | FAASt [Distribution Pole and Conductor Repair - Bayamon Group 2 - Phase 2] (Distribution) |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 87774.8 | 85296.74 | 85296.74 | 2478.06 | 14756 | $- | 23699.65 | $- | 87826.52 | 111526.17
711670 | FAASt [T-Pole Program Line 100] (Transmission) |  | Transmission | Grid Automation | Yes | Obligated | 118160.28 | 94787.57 | 94787.57 | 23372.71 | 12341 | $- | 224618.43 | $- | 215370.16 | 439988.59
711819 | FAASt [Transmission Priority Pole Replacement Program Line 13400 San German Sect-La Parguera Sect] (Transmission) | Phase 2 | Transmission | Poles | No | Pending PDMG Project Review | 2086350 | 1705844 | 1705844 | 158417 | 222089 | 0 | 593102.66 | 0 | 807980.14 | 1401082.8 | 6/17/2025 - The project was reworked, needs additional corrections, including 406/428 E&M, A&E allocation in both document DSOW and LPCE. Project is under applicant QA/QC and the new forecast is set for 6/26/2025. | Replace structures that are critically damaged
711856 | FAASt [Pole and Conductor Repair - Bayamon Group 3 - Phase 2] (Distribution) |  | Distribution | Grid Automation | Yes | Obligated | 11335984.34 | 10940320.91 | 10940320.91 | 395663.43 | 891094 | $- | 974772.99 | $- | 10881521.12 | 11856294.11
711888 | FAASt [Pole and Conductor Repair - Caguas Group 1 - Phase 2] (Distribution) |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 5591713.87 | 5425810.57 | 5425810.57 | 165903.3 | 434785 | $- | 363276.28 | $- | 4646971.03 | 5010247.31
712968 | FAASt [Pole and Conductor Repair - Arecibo Group 2 - Phase 2] (Distribution) |  | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 5807772.97 | 5629060 | 5629060 | 178712.97 | 503551 | $- | 398419.05 | $- | 5817836.63 | 6216255.68
712980 | FAASt [T-Pole Program Line 3000] (Transmission) |  | Transmission | Grid Automation | Yes | Obligated | 631194.26 | 559076.77 | 559076.77 | 72117.49 | 72788 | $- | 1043540.52 | $- | 696530.52 | 1740071.04
714641 | FAASt [Rincón Streetlighting] (Distribution) | Phase 2 | Distribution | Streetlights | No | Pending Large Project Review | 14055391.76 | 10915553.24 | 10915553.24 | 1211588.91 | 1928249.61 | 753614 | 416730.91 | 0 | 307.56 | 417038.47 | Waiting for LUMA to submit DSOW and CE revision as per Vegetation PA 428 Incidental Meeting held 04.22.2025, LUMA forecast 6/19/2025. 6/30/2025 PDMG call with LUMA team to clarify buffer zone for locations duplicated in Vegetation project.Waiting on response from applicant. | Streetlight repairs by replacing lightning components, poles, underground circuits and material disposal.
714654 | FAASt [Advanced Metering Infrastructure (AMI)] (Telecommunications) |  | Telecommunications | AMI Implementation Program | Yes | Obligated | 876270176 | 332062581 | 332062581 | 544207595 | 16450923 | $- | 25740701.54 | $- | 80718949.14 | 106459650.68
723002 | FAASt - EPC - Jobos TC (Substation) | Phase 2 | Substation | Substation | No | Pending Scope & Cost Completion by Applicant |  | 70586386.39 | 70586386.39 |  | 5724710.26 |  | 1739194.78 | 1100210.2 | 15989.76 | 2855394.74 | "7/9/2025 EHP RFI-PRJ-116045 response received on 7/4/2025. Project will continue GM flow. -Process Step: Pending Insurance Completion " | Construction of the facilities, reconfiguration and replacement of disaster-related damaged components and electrical systems into these new facilities, and the addition of new components to restore the facility to the pre-disaster functions with the applicable codes and standards
723077 | FAASt - EPC - [Sabana Llana TC] (Substation) |  | Substation | Substation Rebuilds | Yes | Obligated | 46643078.39 | 46643078.39 | 46643078.39 | $- | 583002.82 | $- | 4152502.12 | 8448675 | 1802520.31 | 14403697.43
723078 | FAASt - EPC - [San Juan SP TC] (Substation) |  | Substation | Substation Rebuilds | Yes | Obligated | 61558468.95 | 61558468.95 | 61558468.95 | $- | 3713097 | $- | 2461842.08 | 587798.4 | 95534.06 | 3145174.54
723883 | FAASt [Region 1 -San Juan Group A] (Vegetation) | Priority-Pipeline | Vegetation | Vegetation | Yes | Pending Large Project Review | 25072092.11 | 6584889.61 | 6584889.61 | 18404524.67 | 82677.83 | 0 | 45864.06 | 0 | 12213046.06 | 12258910.12 | Project Version 1 obligation in process- | This scope of work is for the removal and, when necessary, disposal of vegetative materials that pose an immediate threat to the distribution lines within Region 1 (San Juan).
724600 | FAASt [Jayuya Streetlighting] (Distribution) |  | Distribution | Distribution – Feeder Rebuild | Yes | Obligated | 8628211.52 | 7277670.2 | 7277670.2 | 1350541.32 | 1704126 | $- | 328802.03 | $- | 4552560.71 | 4881362.74
724601 | FAASt [Salinas Streetlighting] (Distribution) |  | Distribution | Grid Automation | Yes | Obligated | 13708224.43 | 12097203.53 | 12097203.53 | 1611020.9 | 2463886 | $- | 550498.92 | $- | 8641914.3 | 9192413.22
724698 | FAASt [Adjuntas Streetlighting] (Distribution) |  | Distribution | Grid Automation | Yes | Obligated | 12633614 | 10742462 | 10742462 | 1891152 | 2199844 | $- | 607261.45 | $- | 4726146.27 | 5333407.72
724703 | FAASt [Arroyo Streetlighting] (Distribution) |  | Distribution | Distribution Streetlighting | Yes | Obligated | 6054726.01 | 5314332 | 5314332 | 740394.01 | 1504203 | $- | 332824.21 | $- | 1549587.46 | 1882411.67
724825 | FAASt [Cidra Streetlighting] (Distribution) |  | Distribution | Distribution – Pole Replacement | Yes | Obligated | 14650708.44 | 12812478.84 | 12812478.84 | 1838229.6 | 2516456 | $- | 600261.79 | $- | 6250494.14 | 6850755.93
724938 | FAASt [Vega Alta Streetlighting] (Distribution) |  | Distribution | Distribution Streetlighting | Yes | Obligated | 14314104.85 | 12445015.33 | 12445015.33 | 1869089.52 | 2459743 | $- | 586372.22 | $- | 4580875.05 | 5167247.27
727522 | FAASt [Region 3 Bayamon TL - 115kV] (Vegetation) | Phase 2 | Vegetation | Vegetation-TL | No | Pending Large Project Review | 73136988.1 | 18031093.89 | 18031093.89 | 53608045.16 | 1497849.05 |  | 14.3 | 0 | 0 | 14.3 | 6/17/2025 - Follow up email sent on 5/16/2025 and 6/10/2025. The applicant currently revising DSOW and they will provide a submittal date schedule. DSOW submitted on 6/27- Cost presented are LUMA estimates | This scope of work is for the removal and, when necessary, disposal of vegetative materials that pose an immediate threat to the 115kV and below power transmission and distribution lines, and identification for corrective actions related to removal of hazardous vegetation (consisting of shrubs, branches, limbs, stumps, bamboo, and trees) within Region 3 (Bayamon) of Puerto Rico.
727529 | FAASt [Region 6 Ponce TL - 115kV] (Vegetation) | Phase 2 | Vegetation | Vegetation-TL | No | Pending Large Project Review | 74301040.39 | 18318077.75 | 18318077.75 | 54661273.75 | 1521688.89 |  | 4.5475e-13 | 0 | 0 | 4.5475e-13 | 6/17/2025 - Follow up email sent on 5/16/2025. The applicant currently revising DSOW and they will provide a submittal date schedule. DSOW submitted on 6/27- Cost presented are LUMA estimates | This scope of work is for the removal and, when necessary, disposal of vegetative materials that pose an immediate threat to the 115kV power transmission lines, and identification for corrective actions related to removal of hazardous vegetation (consisting of shrubs, branches, limbs, stumps, bamboo, and trees) within Region 6 (Ponce) of Puerto Rico.
727531 | FAASt [Region 6 -Ponce Group A] High Density (Vegetation) |  | Vegetation | Distribution – Pole Replacement | Yes | Obligated | 25913934.11 | 6849050.26 | 6849050.26 | 19064883.85 | $- | $- | 707.06 | $- | 1539382.15 | 1540089.21
727572 | FAASt [Region 3 -Bayamon Group A] High Density (Vegetation) | Priority-Pipeline | Vegetation | Vegetation | No | Pending Applicant Project Review | 48974857.77 | 12945985.39 | 12945985.39 | 36028872.38 | 0 | 0 | 0 | 0 | 627738.06 | 627738.06 | 6/17/2025 - The project is under review by Expert review since 4/14/2025. | Vegetation Clearing for Region Bayamon High Density
727606 | FAASt [Region 4 Caguas TL - 115kV] (Vegetation) | Phase 2 | Vegetation | Vegetation-TL | No | Pending Large Project Review | 149456350.77 | 36846766.07 | 36846766.07 | 109548711.44 | 3060873.27 |  | 0 | 0 | 18381.82 | 18381.82 | 6/17/2025 - Follow up email sent on 5/16/2025. The applicant currently revising DSOW and they will provide a submittal date schedule.DSOW submitted on 6/27- Cost presented are LUMA estimates | This scope of work is for the removal and, when necessary, disposal of vegetative materials that pose an immediate threat to the 115kV power transmission lines, and identification for corrective actions related to removal of hazardous vegetation (consisting of shrubs, branches, limbs, stumps, bamboo, and trees) within Region 4 (Caguas) of Puerto Rico.
727608 | FAASt [Region 1 San Juan TL - 115kV] (Vegetation) | Phase 2 | Vegetation | Vegetation-TL | No | Pending Large Project Review | 33286982.49 | 8206527.54 | 8206527.54 | 24398735.91 | 681719.03 |  | 80.96 | 0 | 27533.8 | 27614.76 | 6/17/2025 - Follow up email sent on 5/16/2025. The applicant currently revising DSOW and they will provide a submittal date schedule. DSOW submitted on 6/27- Cost presented are LUMA estimates | This scope of work is for the removal and, when necessary, disposal of vegetative materials that pose an immediate threat to the 115kV and below power transmission and distribution lines, and identification for corrective actions related to removal of hazardous vegetation (consisting of shrubs, branches, limbs, stumps, bamboo, and trees) within Region 1 (SJ) of Puerto Rico.
727657 | FAASt [Region 5 Mayaguez TL - 115kV] (Vegetation) | Phase 2 | Vegetation | Vegetation-TL | No | Pending Large Project Review | 125194568.18 | 30865299.08 | 30865299.08 | 91765278.3 | 2563990.79 |  | -4.5475e-13 | 0 | 94.28 | 94.28 | 6/17/2025 - Follow up email sent on 5/16/2025. The applicant currently revising DSOW and they will provide a submittal date schedule. DSOW submitted on 6/27- Cost presented are LUMA estimates | This scope of work is for the removal and, when necessary, disposal of vegetative materials that pose an immediate threat to the 115kV power transmission lines, and identification for corrective actions related to removal of hazardous vegetation (consisting of shrubs, branches, limbs, stumps, bamboo, and trees) within Region 5 (Mayaguez) of Puerto Rico.
727659 | FAASt [Region 2 Arecibo TL - 115kV] (Vegetation) | Phase 2 | Vegetation | Vegetation-TL | No | Pending Large Project Review | 74088605.9 | 18265704.46 | 18265704.46 | 54305563.22 | 1517338.23 |  | -9.0949e-13 | 0 | -5.6843e-14 | -9.6634e-13 | 6/17/2025 - Follow up email sent on 5/16/2025. The applicant currently revising DSOW and they will provide a submittal date schedule. DSOW submitted on 6/27- Cost presented are LUMA estimates | This scope of work is for the removal and, when necessary, disposal of vegetative materials that pose an immediate threat to the 115kV power transmission lines, and identification for corrective actions related to removal of hazardous vegetation (consisting of shrubs, branches, limbs, stumps, bamboo, and trees) within Region 2 (Arecibo) of Puerto Rico.
727692 | FAASt [Region 4 -Caguas Group A] High Density (Vegetation) |  | Vegetation | Vegetation | Yes | Obligated | 28052090.37 | 7414164.75 | 7414164.75 | 20637925.62 | $- | $- | 0 | $- | 279276.62 | 2010291.71
728827 | FAASt [Region 2 -Arecibo Group A] High Density (Vegetation) |  | Vegetation | Vegetation | Yes | Obligated | 18194308.81 | 4807675.47 | 4807675.47 | 13386633.34 | $- | $- | -1.26 | $- | 0 | 1898839.1
728832 | FAASt [Region 5 -Mayaguez Group A] High Density (Vegetation) |  | Vegetation | Vegetation | Yes | Obligated | 14260691.9 | 3767690.42 | 3767690.42 | 10493001.48 | $- | $- | 0 | $- | 0 | 2205350.06
729286 | FAASt HV Equipment Replacement Group 2 (Substation) |  | Substation | Substation | Yes | Obligated | 15413889.89 | 15413889.89 | 15413889.89 | $- | 2006783 | $- | 1013286.89 | $- | 0 | 7496806.91
735474 | FAASt [Pole and Conductor Repair -Caguas Group 3 Phase 2] (Distribution) | Pipeline | Distribution | Poles | Yes | Obligated | 18747102.15 | 14075641.42 | 14075641.42 | 0 | 1962096.73 | 2709364 | 345648.23 | 1588894.6198 | 0 | 1934542.8498 | Pending EHP review.Waiting for revised DSOW package without brushing to be able to move project forward, | Planned to replace poles in Caguas region
738120 | FAASt [Pole and Conductor Repair-Carolina Group 2- Phase 2] (Distribution) |  | Distribution | Grid Automation | Yes | Obligated | 11451170.81 | 11041271 | 11041271 | 409899.81 | 1159111 | $- | 546986.76 | $- | 0 | 4865354.32
738670 | FAASt [Pole and Conductor Repair - Ponce Group 1 - Phase 2] (Distribution) |  | Distribution | Distribution – Pole Replacement | Yes | Obligated | 5074511.01 | 4926640.11 | 4926640.11 | 147870.9 | 439975 | $- | 272555.79 | $- | 0 | 3437603.83
738672 | FAASt [Pole and Conductor Repair - Mayaguez Group 1 - Phase 2] (Distribution) |  | Distribution | Distribution – Pole Replacement | Yes | Obligated | 10619758.37 | 10313627 | 10313627 | 306131.37 | 834793 | $- | 465746.73 | $- | 0 | 6368574.67
738971 | FAASt [Pole and Conductor Repair - Caguas Group 2 - Phase 2] (Distribution) |  | Distribution | Distribution – Pole Replacement | Yes | Obligated | 14261249.67 | 13884126 | 13884126 | 377123.67 | 1643630 | $- | 477686.79 | $- | 0 | 6216045.77
741105 | FAASt [All Regions TL - 230kV] (Vegetation) | Phase 2 | Vegetation | Vegetation-TL | No | Pending Large Project Review | 157385518.05 | 154791845.18 |  |  | 2593672.87 |  | 0 | 0 | -5.6843e-14 | -5.6843e-14 | 6/17/2025 - Follow up email sent on 5/16/2025. The applicant currently revising DSOW and they will provide a submittal date schedule. Forecast: TBD- Cost presented are LUMA estimates | This scope of work is for the removal and, when necessary, disposal of vegetative materials that pose an immediate threat to the 230kV and below power transmission and distribution lines, and identification for corrective actions related to removal of hazardous vegetation (consisting of shrubs, branches, limbs, stumps, bamboo, and trees) within All Regions Transmission - 230kV of Puerto Rico.
742026 | FAASt [Pole and Conductor Repair - San Juan Group 2 - Phase 2] (Distribution) |  | Distribution | Distribution – Pole Replacement | Yes | Obligated | 1117411.77 | 1033375.81 | 1033375.81 | 84035.96 | 83943 | $- | 285243.13 | $- | 0 | 1675784.98
742070 | FAASt [Pole and Conductor Repair - San Juan Group 1 - Phase 2] (Distribution) |  | Distribution | Distribution – Pole Replacement | Yes | Obligated | 5666787.43 | 5461200.05 | 5461200.05 | 205587.38 | 491327 | $- | 790741.79 | $- | 0 | 5190372.14
743399 | FAASt [High Voltage Equipment Replacement - Group 3] (Substation) |  | Substation | Substation | Yes | Obligated | 17307539.01 | 17307539.01 | 17307539.01 | $- | 2253323.31 | $- | 327884.46 | $- | 0 | 962928.73
745856 | FAASt [Automation Program Group 14] (TL/Distribution) |  | Grid Automation | Grid Automation | Yes | Obligated | 1640186.96 | 1640186.96 | 1640186.96 | $- | 208604.89 | 26370.11 | 251045.91 | 328958.9 | 47.14 | 1670198.69
745859 | FAASt [Automation Program Group 18: DAR – SAN JUAN 2001- FY24] (Distribution) |  | Grid Automation | Grid Automation | Yes | Obligated | 467287.59 | 467287.6 | 467287.59 | $- | 28521.8 | 4395.02 | 65427.99 | 79999.39 | 0 | 401568.87
745861 | FAASt [Automation Program Group 12] (TL/Distribution) |  | Grid Automation | Grid Automation | Yes | Obligated | 3664210.1 | 3664210.1 | 3664210.1 | $- | 477953.55 | $- | 269561.52 | 649196.15 | 47.14 | 2410722.38
746309 | FAASt [Automation Program Group 30] (Distribution) | Phase 2 | Distribution | Automation | No | Pending Award | 668110 | 425975.74 |  |  |  |  | 32095.77 | 127306.1083 | 0 | 159401.8783 | On 7/14/2025 Project moved to FEMA 406 HMP completion. | Deployment of grid automation technologies in feeders.
746545 | FAASt [Primary Control Center / Secondary Data Center & Control Room] (Telecommunication) | Phase 2 | Telecommunication | Telecomm | No | Pending PDMG Scope & Cost Routing | 131169274 | 115638378 | 115638378 | 15530896 |  |  | 9250102.31 | 0 | 0 | 9250102.31 | The formulation of this project will depend on the resulution or modification of the actual Environmental & Historic Preservation(EHP) determination. Project formualtion process needs to be revised. If no corrections are executed, Project to be removed from the FAAST Consolidated Plan List | Relocation of existing Operations teams and equipment, as well as the removal / relocation of electrical infrastructure from the Monacillos campus. The project has three areas of scope. The scope of work description is organized by the area of work. The three areas include (1) the Guaynabo ESC building rehabilitation in Guaynabo, (2) the Durotex Building rehabilitation on the Monacillos campus, (3) and the new PCC building construction / site improvements on the Monacillos campus.
746660 | FAASt [Minor Protection, Automation, and Control [PAC] Replacement] (Substation) | Phase 2 | Substation | Substation | No | Pending Scope & Cost Completion by Applicant | 16713944.15 | 15096658.56 | 15096658.56 | 1617375.6 | N/A | N/A | 2255799.45 | 0 | 0 | 2255799.45 | LUMA submitted DSOW/LPCE on 05.07.2025. Project is under FEMA HM review with an RFI related to 428/406 scope and cost splits. Current deadline for RFI is 08.26.2025. Luma agreed to complete request by July 31,2025. If RFI response is not completed, Project to be removed form FFAST Consolidated List | Increase protection and Control System that protect the electrical components such as Transmission Lines, Transformers, Bus Bar, Breakers, etc
749060 | FAASt [Transmission Priority Pole Replacement Program Line 5600 Victoria TC – Añasco TC] (Transmission) | Phase 2 | Transmission | Poles | No | Pending EHP Review | 953607.59 | 717817.65 | 717817.65 | 142335 | 93454.94 | 0 | 285445.42 | 4395.0182 | 0 | 289840.4382 | 6/17/2025 - Applicant submitted on December 19, 2025, partial response for the EHP-RFI-PRJ-106924. LUMA Forecast 6/20/2025. | Replace structures that are critically damaged
749072 | FAASt [Transmission Priority Pole Replacement Program Line 2700 Aguadilla Hospital Distrito Sect – Mora TC] (Transmission) | Phase 2 | Transmission | Poles | No | Pending Award | 209886.2 | 158495.32 | 158495.32 | 30755.87 | 20635.01 | 0 | 284188.06 | 0 | 0 | 284188.06 | 6/17/2025 - Applicant new forecast for the response for the informal EHP RFI clarification the new deadline for response is 6/26/2025. | Replace structures that are critically damaged
750063 | FAASt [Region 6 -Ponce Group A] Low Density (Vegetation) | Priority | Vegetation | Vegetation-DT | No | Pending Applicant Project Review | 69341045.82 | 18254467.11 | 18254467.11 | 50797296.22 | 289282.49 | 0 | 0 | 0 | 119896.91 | 119896.91 | 7/15/2025 - Field EHP: (ESA) Consultation letter submitted to (USFWS) on 05/29/2025. Waiting for response. (Updated ECD to 08/08/2025). | Removal and, when necessary, disposal of vegetative materials that pose an immediate threat to the distribution lines within Region 6 (Ponce).
750065 | FAASt [Region 3 -Bayamon Group A] Low Density (Vegetation) | Priority | Vegetation | Vegetation-DT | No | Pending Applicant Project Review | 81038211 | 21333819.52 | 21333819.52 | 59366309.82 | 338081.66 | 0 | 0 | 0 | 45858.06 | 45858.06 | 7/15/2025 - Field EHP: ESA Consultation letter submitted to USFWS on 05/29/2025. Waiting for response. ECD 7/28/2025. | Removal and, when necessary, disposal of vegetative materials that pose an immediate threat to the distribution lines within Region 3 (Bayamon).
750066 | FAASt [Region 4 -Caguas Group A] Low Density (Vegetation) | Priority | Vegetation | Vegetation-DT | No | Pending Applicant Project Review | 124213686.46 | 32703357.23 | 32703357.23 | 90995446.51 | 514882.72 | 0 | 0 | 0 | 14236.87 | 14236.87 | 7/15/2025 - Field EHP - Environmental: ESA Consultation letter submitted to USFWS on 06/03/2025. Waiting for response. ECD 08/12/2025. | Removal and, when necessary, disposal of vegetative materials that pose an immediate threat to the distribution lines within Region 4 (Caguas).
750067 | FAASt [Region 2 -Arecibo Group A] Low Density (Vegetation) | Priority | Vegetation | Vegetation-DT | No | Pending Applicant Project Review | 65590799.69 | 17267191.18 | 17267191.18 | 48049971.59 | 273636.92 | 0 | 0 | 0 | 49339.51 | 49339.51 | 7/15/2025 - Field EHP: ESA and CBRA Consultation letter submitted to USFWS on 06/05/2025. Waiting for response. ECD 08/19/2025 | Project is for the removal and, when necessary, disposal of vegetative materials that pose an immediate threat to the distribution lines within Region 2 (Arecibo).
750068 | FAASt [Region 5 -Mayaguez Group A] Low Density (Vegetation) | Priority | Vegetation | Vegetation-DT | No | Pending Applicant Project Review | 60147477.28 | 15900537.4 | 15900537.4 | 44246939.88 | 251979.26 | 0 | 0 | 0 | 47093.44 | 47093.44 | 7/15/2025 -Field EHP: ESA Consultation letter submitted to USFWS on 06/03/2025. Waiting for response. ECD 08/19/2025. | Removal and, when necessary, disposal of vegetative materials that pose an immediate threat to the distribution lines within Region 5 (Mayaguez).
750150 | FAASt [Transmission Priority Pole Replacement Program Line 4800 Santa Isabel TC – Toro Negro 1 HP] (Transmission) | Phase 2 | Transmission | Poles | No | Pending Award | 71874.31 | 58488 | 58488 | 5771.31 | 7615 | 0 | 23704.22 | 0 | 0 | 23704.22 | 6/17/2025 - The 2nd HM RFI has been sent to the applicant on February 26, 2025, for their action. FEMA received communication that Project is under applicant QA/QC and the new forecast is set for 6/26/2025. | Replace structures that are critically damaged
750151 | FAASt [Transmission Priority Pole Replacement Program Line 700 Costa Sur SP – Yauco 2 HP] (Transmission) | Phase 2 | Transmission | Poles | No | Pending Scope & Cost Completion by Applicant | 150223.28 | 123160.67 | 123160.67 | 11027.93 | 16034.68 |  | 18541.41 | 0 | 0 | 18541.41 | 6/9/2025 - The project is under Applicant revision and modification (open ended language EHP request and required corrections). New deadline set by the Applicant 6/19/2025. | Replacement of hardware, several structures, guys anchoring and foundations for TL700.
750168 | FAASt [ Transmission Priority Pole Replacement Program Line 4800 Santa Isabel TC – Aibonito TO] (Transmission) | Phase 2 | Transmission | Poles | No | Pending Scope and Cost Development | 453277.24 | 404349.3 | 375810.42 | 28538.88 | 48927.94 | 0 | 15396.26 | 0 | 0 | 15396.26 | 6/17/2025 - The 3rd HM RFI has been sent to the applicant on May 30, 2025, for their action. The deadline is set 6/27/2025. | Replace structures that are critically damaged
750692 | FAASt [Pole and Conductor Repair - Mayaguez Group 3 - Phase 2] (Distribution) | Pipeline | Distribution | Poles | Yes | Obligated | 17230407 | 12921047 | 12921047 | 0 | 1799743 | 2509617 | 329386.02 | 1479407.0199 | 247.9 | 1809040.9399 | Pending EHP review. Waiting for revised DSOw package without brushing to be able to move project forward. | Planned to replace poles in Mayagüez region
751655 | FAASt [Vieques Microgrid] (Transmission) | Priority | Transmission | Vieques and Culebra Projects (6) | No | Pending Scope & Cost Completion by Applicant | 105481956 | 0 | 0 | 105481956 |  |  | 56150.07 | 383831.1974 | 0 | 439981.2674 | "6/27/2025 - Pending form Applicant to submit the DSOW with all the necessary information. Also, 1st HM RFI was submitted to the applicant on September 13, 2024, for their action. The initial strategy for both projects was submitted on July 19, 2024. Subsequently, the first mitigation RFI was issued on September 13, 2024, with a deadline of September 27, 2024. Since then, FEMA has not received any further information.As noted, the applicant has now proposed a new deadline of April 24, 2025. FOllow up email sent on 4/8/2025. -Applicant forecast date:7/24/2025." | Construct a new microgrid system to provide resiliency, power quality, energy redundancy, stand-alone and black start capabilities to the island of Vieques.
751656 | FAASt [Culebra Microgrid] (Transmission) | Priority | Transmission | Vieques and Culebra Projects (6) | No | Pending Scope & Cost Completion by Applicant | 39954081 | 0 | 0 | 39954081 |  |  | 30728.97 | 137248 | 0 | 167976.97 | "6/27/2025 - Pending form Applicant to submit the DSOW with all the necessary information. Also, 1st HM RFI was submitted to the applicant on September 13, 2024, for their action. The initial strategy for both projects was submitted on July 19, 2024. Subsequently, the first mitigation RFI was issued on September 13, 2024, with a deadline of September 27, 2024. Since then, FEMA has not received any further information.As noted, the applicant has now proposed a new deadline of April 24, 2025. FOllow up email sent on 4/8/2025. -Applicant forecast date:7/24/2025." | Construct a new microgrid system to provide resiliency, power quality, energy redundancy, stand-alone and black start capabilities to the island of Culebra.
752540 | FAASt [Pole and Conductor Repair -Mayaguez Group 4 Phase 2] (Distribution) | Pipeline | Distribution | Poles | Yes | Obligated | 9478854.81 | 7111613.91 | 7111613.91 | 0 | 991211.9 | 1376029 | 243940.67 | 434861.9299 | 682.2 | 679484.7999 | Pending EHP review. Waiting for revised DSOw package without brushing to be able to move project forward. | Replacement of poles and the repair of conductors for specific feeders in Mayagüez region to be performed under the “Proposed 428 Public Assistance Scope of Work”.
752808 | FAASt [Automation Program Group 19] (TL/Distribution) |  | Grid Automation | Grid Automation | Yes | Obligated | 2753627.24 | 2753627.24 | 2753627.24 | $- | 348510.65 | $- | 215742.96 | 354751.53 | 1204703.32 | 1775197.81
752810 | FAASt [Automation Program Group 20] (TL/Distribution) |  | Grid Automation | Grid Automation | Yes | Obligated | 2623262.08 | 2623262.08 | 2623262.08 | $- | 333695.7 | 35160.15 | 197293.36 | 346480.94 | 863054.4 | 1406828.7
753782 | FAASt [Transmission Priority Pole Replacement Program Line 3100 Monacillos TC – Sabana Llana TC] (Transmission) | Phase 2 | Transmission | Transmission | No | Pending Award | 162748.65 | 124593.02 | 124593.02 | 14809.67 | 17120.17 | 6225.79 | 73300.2 | 0 | 0 | 73300.2 | "6/6/2025 - The 1st HM RFI has been sent to the applicant on February 27, 2025, for their action. FEMA received communication that Project is under applicant QA/QC and the new forecast is set for 6/26/2025. " | Transmission Pole Replacement and Critical Repairs 38 KV L 3100 Monacillos TC to Sabana Llana TC, FAAST#: 753782
755211 | FAASt [Automation Program Group 15] (Distribution) | Pipeline | Grid Automation | Automation | Yes | Pending Amendment Request Approval | 643560.85 | 643560.85 | 643560.85 | 0 | 81858.57 | 10690 | 67345.1 | 107145.3691 | 302923.71 | 477414.1791 | Pending Obligation | Installation of smart reclosers with microprocessor-based controllers and the remote monitoring, communications ready and control capabilities in transmission and distribution lines. Installation of cutout type single phase reclosers, with microprocessor-based controllers. Installation of fault current indicators (communications ready).
756997 | FAASt [TL 1900 Caguanas to Lares TO] (Transmission) | Phase 2 | Transmission | Transmission | No | Pending Scope & Cost Completion by Applicant | 43739699.88 | 40557533.61 | 40557533.61 |  |  |  | 3227416.96 | 0 | 279276.62 | 3506693.58 | 7/15/2025 - The project is running in the Grant Manager queue. The project is Pending EHP Review. | Repair/Replace structures (including their foundations), framing and insulators, load break switches (manual and automated), conductors, guy wires, anchoring, grounding assemblies, and any other associated components. Most of the construction along this line segment consists of wood monopole guyed structures with some interspersed self-supporting steel and concrete monopoles. This line primarily traverses forested and urban areas between Dos Bocas HP substation and San Sebastian TC substation.
756999 | FAASt [TL 1900 Lares TO to San Sebastian] (Transmission) | Phase 2 | Transmission | Transmission | No | Pending Scope & Cost Completion by Applicant | 32495692.2 | 29319358.78 | 29319358.78 |  | 2088488.51 | 1087844.91 | 266215.5 | 0 | 0 | 266215.5 | 7/152025 - The project is running in the Grant Manager queue. The project is Pending EHP Review. | Repair/Replace structures (including their foundations), framing and insulators, load break switches (manual and automated), conductors, guy wires, anchoring, grounding assemblies, and any other associated components. Most of the construction along this line segment consists of wood monopole guyed structures with some interspersed self-supporting steel and concrete monopoles. This line primarily traverses forested and urban areas between Dos Bocas HP substation and San Sebastian TC substation.
757662 | FAASt [Automation Program Group 21] (Distribution) | Priority | Grid Automation | Automation | No | Pending Award | 2216560 | 1710547.94 | 1710547.94 | 0 | 280516.59 | 512796.48 | 117212.72 | 393808.7079 | 813.32 | 511834.7479 | On 7/15/2025 Project moived to FEMA Final Review. | Deployment of grid automation technologies in feeders.
757687 | FAASt [Automation Program Group 22] (Distribution) | Priority | Grid Automation | Automation | No | Pending Award | 2792415 | 2356733.87 | 2356733.87 | 0 | 359230.44 | 412012.16 | 85291.07 | 443874.7131 | 559.72 | 529725.5031 | EHP - Environmental: Initial review. Expected Completion Date (ECD) 07/31/2025. System Glitch: Project waiting to be sent back to make corrections to DSOW. | Deployment of grid automation technologies in feeders.
757689 | FAASt [Automation Program Group 24] (Distribution) |  | Grid Automation | Grid Automation | Yes | Obligated | 1774822.4 | 1774822.4 | 1774822.4 | $- | 299299.32 | 562828 | 90144.9 | 458434.34 | 2771.4 | 551350.64
757692 | FAASt [Automation Program Group 26] (TL / Distribution) | Priority-Pipeline | Grid Automation | Automation | Yes | Obligated | 1676936.96 | 938783.63 | 938783.63 | 0 | 175325.33 | 562828 | 38673.52 | 209048.7401 | 2093.03 | 249815.2901 | Pending COR3 review and approval | Deployment of grid automation technologies in feeders.
757694 | FAASt [Automation Program Group 27] (Distribution) | Priority | Grid Automation | Automation | Yes | Obligated | 3271077 | 2314733.78 | 2314733.78 | 0 | 419922.13 | 977936.96 | 103662.78 | 594955.7558 | 641.46 | 699259.9958 | On 7/7/2025 Project moved to Final FEMA Review. | Deployment of grid automation technologies in feeders.
757696 | FAASt [Automation Program Group 31] (Distribution) | Priority | Grid Automation | Automation | Yes | Obligated | 1710177.27 | 1145457.61 | 1145457.61 | 0 | 195175.66 | 369544 | 56017.1 | 262670.8354 | 4033.49 | 322721.4254 | EHP: In review. Expected Completion Date (ECD) 6/23/2025. Project advanced to Pending Recipient Review | Deployment of grid automation technologies in feeders.
757697 | FAASt [Automation Program Group 32] (TL / Distribution) | Priority | Grid Automation | Automation | Yes | Obligated | 2663099 | 1996678.58 | 1996678.58 | 0 | 339647.19 | 666420.83 | 117899.74 | 526409.7143 | 1466.21 | 645775.6643 | EHP - Environmental: In Review. Expected Completion Date (ECD) 08/01/2025. | Deployment of grid automation technologies in feeders.
757698 | FAASt [Automation Program Group 33] (Distribution) | Priority | Grid Automation | Automation | Yes | Obligated | 2250901 | 1888928.21 | 1888928.21 | 0 | 311582.64 | 594117.44 | 52619.47 | 448371.606 | 293.55 | 501284.626 | On 7/7/2025 Project moved to Final FEMA Review. | Deployment of grid automation technologies in feeders.
757699 | FAASt [Automation Program Group 34] (Distribution) | Priority | Grid Automation | Automation | No | Pending PDMG Project Review | 3507467 | 2755938.99 | 2755938.99 | 0 | 462362.68 | 683789.12 | 174934.21 | 514020.5748 | 1835.85 | 690790.6348 | EHP - Initial review. ECD 6/24/2025. 2nd System Glitch: Project waiting to system glitch to make corrections to project facility description. | Deployment of grid automation technologies in feeders.
757700 | FAASt [Automation Program Group 35] (TL / Distribution) | Priority | Grid Automation | Automation | Yes | Obligated | 1988436.16 | 1318515.66 | 1318515.66 | 0 | 245359.86 | 424560.64 | 69865.55 | 54222.255 | 490.28 | 124578.085 | EHP: In review. Expected Completion Date (ECD) 6/23/2025. Project advanced to Pending Recipient Review | Deployment of grid automation technologies in feeders.
790443 | FAASt [Pole and Conductor Repair -San Juan Group 3 Phase 2 (Distribution) | Pipeline | Distribution | Poles | Yes | Obligated | 248306 | 186697 | 186697 | 0 | 25985 | 35624 | 15962.43 | 20132.4 | 273.81 | 36368.64 | Pending Recipient Final Review since 5/22/2025. | Planned to replace poles in San Juan region
797148 | FAASt [Feeder Rebuild # 8101-03] (Distribution) | Pipeline | Distribution | Feeders | Yes | Obligated | 3383166.23 | 2359895.63 | 2359895.63 | 0 | 777847.24 | 245423.36 | 1789592.23 | 126860.4375 | 109948.15 | 2026400.8175 | Project moving through the queues. | Project involves assessing damage and designing a robust Feeder rebuild, replacing damaged components (poles and distribution lines).
798275 | FAASt [Feeder Rebuild # 1620-02] (Distribution) | Pipeline | Distribution | Feeders | Yes | Obligated | 8418694.51 | 6711420.9 | 6711420.9 | 0 | 954420.68 | 752852.93 | 1202388.96 | 199559.0598 | 36188.99 | 1438137.0098 | Project moving through the queues. | Project involves assessing damage and designing a robust Feeder rebuild, replacing damaged components (poles and distribution lines).
800286 | FAASt [Automation Program Group 36] (TL / Distribution) | Priority | Grid Automation | Automation | Yes | Obligated | 2601467.86 | 1703712.83 | 1703712.83 | 0 | 300364.95 | 597390.08 | 63716.05 | 122408.2003 | 0 | 186124.2503 | EHP: In review. Expected Completion Date (ECD) 6/23/2025. Project advanced to Pending Recipient Review | Deployment of grid automation technologies in feeders.
800361 | FAASt [Automation Program Group 37] (Distribution) | Priority-Pipeline | Grid Automation | Automation | Yes | Obligated | 2367851.22 | 1596192.73 | 1596192.73 | 0 | 297988.09 | 473670.4 | 125054.02 | 340308.6176 | 561.91 | 465924.5476 | Project in Final FEMA Review since 6/12/2025. | Deployment of grid automation technologies in feeders.
801166 | FAASt [Feeder Rebuild # 6601-03] (Distribution) | Phase 2 | Distribution | Feeders | No | Pending EHP Review | 24121551.35 | 19191185.67 | 19191185.67 |  | 2734512.13 | 2195853.55 | 1446152.65 | 1466048.5351 | 75764.35 | 2987965.5351 | RFI response received on 6/12/2025.Under FEMA review | Project involves assessing damage and designing a robust Feeder rebuild, replacing damaged components (poles and distribution lines).
801172 | FAASt [Feeder Rebuild # 1529-15] (Distribution) | Pipeline | Distribution | Feeders | Yes | Obligated | 3038024.53 | 2285961.13 | 2285961.13 | 0 | 508777.01 | 243286.39 | 1013367.23 | 104987.1823 | 3698.6 | 1122053.0123 | Project moving through the queues. | Project involves assessing damage and designing a robust Feeder rebuild, replacing damaged components (poles and distribution lines).
812569 | FAASt [Feeder Rebuild 3502-02] (Distribution) | Phase 2 | Distribution | Feeders | Yes | Obligated | 12381703.28 | 10217566.54 |  |  | 1403642.18 | 760494.56 | 1084400.71 | 411859.4948 | 6106.39 | 1502366.5948 | Field EHP: In review. Expected Completion Date (ECD) updated to 7/15/2025. | The project consists of the removal and replacement of 104 poles, the installation of 13 new poles that will be located within the easement, and work on 10 existing poles to comply with codes and standard.
817956 | FAASt [Feeder Rebuild # 1303-02] (Distribution) | Phase 2 | Distribution | Feeders | Yes | Obligated | 3560609.24 | 2054461.78 |  |  | 1376522.26 | 129625.2 | 1010218.88 | 62608.0319 | 10961.27 | 1083788.1819 | Field EHP: In review. Expected Completion Date (ECD) updated to 7/15/2025. | The work to be performed includes but is not limited to; repair/replace poles/structures, damaged crossarms, broken and obsolete hardware, primary and secondary overhead and/or underground distribution lines, and porcelain insulation.
825843 | FAASt [Guanica TC] (Substation) | Priority | Priority Substation | Substation | Yes | Obligated | 7348078.61 | 2320373.96 | 2320373.96 | 0 | 826981.13 | 4200723.52 | 0 | 1305535.44 | 0 | 1305535.44 | 6/17/2025- (Stabilization Projects) EHP is requesting additional information for the subject project. Response Received on 5/8/2025 -Process Step: Field EHP: ESA Consultation process initiated; drafting ongoing. ECD 8/04/2025." | Replace the out-of-service transformer at Guánica. Also, the installation of this transformer will aid and stabilize the transmission and distribution feeders interconnected and related to the function of the substation.
956330 | FAASt [Caguas Region 4 - Feeder 3007-03] (Vegetation) | New Project | Vegetation | Vegetation-DT | No | Pending QA Review | 7985860.15 | 1968823.15 | 1968823.15 | 5853486.17 | 163550.83 |  | 0 | 0 | 0 | 0 | DSOW submitted to FEMA on 6/17/25- Projects under Formulation- Cost presented are LUMA estimates | Scope is for vegetation clearance of 60.23 miles- Entire Line
956331 | FAASt [Mayaguez Region 5 Feeder 6014-02] (Vegetation) | New Project | Vegetation | Vegetation-DT | No | Pending EHP Review | 8021552.35 | 1977622.66 | 1977622.66 | 5879647.9 | 164281.79 |  | 0 | 0 | 0 | 0 | DSOW submitted to FEMA on 6/17/25- Projects under Formulation- Cost presented are LUMA estimates | Scope is for vegetation clearance of 60.5 miles- Entire Line
956332 | FAASt [San Juan Region 1 - Feeder 2401-01] (Vegetation) | New Project | Vegetation | Vegetation-DT | No | Pending EHP Review | 11304742.47 | 2787055.9 | 2787055.9 | 8286164.87 | 231521.7 |  | 0 | 0 | 0 | 0 | DSOW submitted to FEMA on 6/17/25- Projects under Formulation- Cost presented are LUMA estimates | Scope is for vegetation clearance of 85.26 miles- Entire Line
956335 | FAASt [San Juan Region 1 - Feeder 2301-02] (Vegetation) | New Project | Vegetation | Vegetation-DT | No | Pending EHP Review | 7503713.1 | 1849955.27 | 1849955.27 | 5500081.4 | 153676.43 |  | 0 | 0 | 0 | 0 | DSOW submitted to FEMA on 6/17/25- Projects under Formulation- Cost presented are LUMA estimates | Scope is for vegetation clearance of 56.59 miles- Entire Line
956337 | FAASt [Mayaguez Region 5 Feeder 6012-02] (Vegetation) | New Project | Vegetation | Vegetation-DT | No | Pending EHP Review | 7303974.78 | 1800712.05 | 1800712.05 | 5353676.97 | 149585.76 |  | 0 | 0 | 0 | 0 | DSOW submitted to FEMA on 6/17/25- Projects under Formulation- Cost presented are LUMA estimates | Scope is for vegetation clearance of 55.09 miles- Entire Line
956339 | FAASt [Caguas Region 4 - Feeder 3301-01] (Vegetation) | New Project | Vegetation | Vegetation-DT | No | Pending Insurance Completion | 12004333.95 | 2959532.24 | 2959532.24 | 8798952.37 | 245849.34 |  | 0 | 0 | 0 | 0 | DSOW submitted to FEMA on 6/17/25- Projects under Formulation- Cost presented are LUMA estimates | Scope is for vegetation clearance of 90.54 miles- Entire Line
956340 | FAASt [Ponce Region 6 Feeder 5602-02] (Vegetation) | New Project | Vegetation | Vegetation-DT | No | Pending EHP Review | 6589894.87 | 1624663.76 | 1624663.76 | 4830269.73 | 134961.38 |  | 0 | 0 | 0 | 0 | DSOW submitted to FEMA on 6/17/25- Projects under Formulation- Cost presented are LUMA estimates | Scope is for vegetation clearance of 49.7 miles- Entire Line
956341 | FAASt [Ponce Region 6 Feeder 5803-02] (Vegetation) | New Project | Vegetation | Vegetation-DT | No | Pending EHP Review | 97672.18 | 24080 | 24080 | 71591.83 | 2000.35 |  | 0 | 0 | 0 | 0 | DSOW submitted to FEMA on 6/17/25- Projects under Formulation- Cost presented are LUMA estimates | Scope is for vegetation clearance of 0.73 miles- Segment of Line
956342 | FAASt [Arecibo Region 2 Line 36400 – Ponce TC to Dos Bocas HP] (Vegetation) | New Project | Vegetation | Vegetation-TL | Yes | Obligated | 44397505.6 | 10945700.85 | 10945700.85 | 32542541.69 | 909263.06 |  | 0 | 0 | 0 | 0 | DSOW submitted to FEMA on 6/17/25- Projects under Formulation- Transmission HMP Cost analysis still under formualtion. Costs presented are LUMA estimates | Scope is for vegetation clearance of 36.78 miles- Segment of Line- Line included in DOE Emergency Order
956343 | FAASt [Ponce Region 6 Line 4800 – Toro Negro to Aibonito, Santa Isabel] (Vegetation) | New Project | Vegetation | Vegetation-TL | No | Pending Scope & Cost Completion by Applicant | 21381353.56 | 5271329.93 | 5271329.93 | 15672132.45 | 437891.18 |  | 0 | 0 | 0 | 0 | DSOW submitted to FEMA on 6/17/25- Projects under Formulation- Transmission HMP Cost analysis still under formualtion. Costs presented are LUMA estimates | Scope is for vegetation clearance of 39.77 miles- Segment of Line
956345 | FAASt [Arecibo Region 2 Line 2400 – Dos Bocas HP to Coronillas 2] (Vegetation) | New Project | Vegetation | Vegetation-TL | No | Pending Scope & Cost Completion by Applicant | 7324652.17 | 1805809.83 | 1805809.83 | 5368833.09 | 150009.25 |  | 0 | 0 | 0 | 0 | DSOW submitted to FEMA on 6/17/25- Projects under Formulation- Transmission HMP Cost analysis still under formualtion. Costs presented are LUMA estimates | Scope is for vegetation clearance of 12.96 miles- Segment of Line
956348 | FAASt [Bayamon Region 3 Line 10000 – Bayamon Pueblo to Magnolia TO] (Vegetation) | New Project | Vegetation | Vegetation-TL | No | Pending Scope & Cost Completion by Applicant | 1193764.73 | 294309.16 | 294309.16 | 875007.19 | 24448.38 |  | 0 | 0 | 0 | 0 | DSOW submitted to FEMA on 6/17/25- Projects under Formulation- Transmission HMP Cost analysis still under formualtion. Costs presented are LUMA estimates | Scope is for vegetation clearance of 2.43 miles
956349 | FAASt [San Juan Region 1 Transmission Line 36800 – Canovanas TC to Palmer TC] (Vegetation) |  | Vegetation | Vegetation | Yes | Obligated | 1364416.12 | 1364416.12 | 1364416.12 | $- | 283721.94 | $- | 0 | 0 | 0 | 0
956353 | FAASt [Arecibo Region 2 Line 36100 – Dos Bocas HP to Barrio Pina] (Vegetation) | New Project | Vegetation | Vegetation-TL | Yes | Obligated | 37008593.33 | 9124048.44 | 9124048.44 | 27126607.1 | 757937.79 |  | 0 | 0 | 0 | 0 | DSOW submitted to FEMA on 6/17/25- Projects under Formulation- Transmission HMP Cost analysis still under formualtion. Costs presented are LUMA estimates | Scope is for vegetation clearance of 30.97 miles- Segment of the Line-Line included in DOE Emergency Order
956356 | FAASt [Ponce Region 6 Transmission Line 39000 – Aguas Buenas Substation to Hacienda San Jose] (Vegetation) |  | Vegetation | Vegetation | Yes | Obligated | 325421.09 | 325421.09 | 325421.09 | $- | 30566.17 | $- | 0 | 0 | 0 | 0
956357 | FAASt [Mayaguez Region 5 Line 1900 – Dos Bocas HP to San Sebastian TC] (Vegetation) | New Project | Vegetation | Vegetation-TL | No | Pending Scope & Cost Completion by Applicant | 12705648.38 | 3415441.98 | 3132433.35 | 9313002.71 | 260212.32 |  | 0 | 0 | 0 | 0 | DSOW submitted to FEMA on 6/17/25- Projects under Formulation- Transmission HMP Cost analysis still under formualtion. Costs presented are LUMA estimates | Scope is for vegetation clearance of 22.35 miles- Segment of the Line
956593 | FAASt [Factor Sect 8014 Transformer Replacement] (Substation) |  | Substation | Substation | Yes | Obligated | 3751193.63 | 3751193.63 | 3751193.63 | $- | 414861.11 | 414861.11 | 0 | 0 | 0 | 0
957578 | FAASt [Costa Sur TC Underground Cable Failure Replacement on Transformer Lead Bank #2] (Substation) |  | Substation | Substation | Yes | Obligated | 1108989.51 | 1108989.51 | 1108989.51 | $- | 141856.25 | $- | 0 | 0 | 0 | 0

## E3 -LUMA's Inactive Projects (hidden)
Item | Project # | Title | FEMA Allocation | Asset | Project Status | DSOW was submitted to FEMA? | Date DSOW was submitted to FEMA? | Estimated A&E Cost Incurred | Estimated E&M Cost Incurred | Other Cost Incurred | Total Estimate Incurred Cost | Is PW included in the Priority Stabilization Plan? | Additional comments
1 | 727691 | FAASt [Region 1 -San Juan Group C] (Vegetation) |  | Vegetation | Inactive | Yes | #REF! | 73.42 | 0 | 38256.04 | 38329.46 | Yes
50 | 551912 | FAASt [Puerto Nuevo - 1520] (Substation) |  | Substation | Inactive | Yes | #REF! | 874727.96 | 0 | 41567.14 | 916295.1 | Yes
55 | 550986 | FAASt [Condado - 1133] (Substation) |  | Substation | Inactive | Yes | #REF! | 1021451.58 | 0 | 42118.98 | 1063570.56 | Yes
56 | 550980 | FAASt [Parques y Recreos - 1002] (Substation) |  | Substation | Inactive | Yes | #REF! | 894655.2 | 0 | 20004.28 | 914659.48 | Yes
58 | 550894 | FAASt [Baldrich - 1422] (Substation) |  | Substation | Inactive | Yes | #REF! | 934456.18 | 0 | 11439.36 | 945895.54 | Yes
61 | 550099 | FAASt [Esc. Industrial M. Such - 1423] (Substation) |  | Substation | Inactive | Yes | #REF! | 691038.79 | 0 | 43921.94 | 734960.73 | Yes
70 | 547247 | FAASt Cambalache TC Relocation (Substation) |  | Substation | Inactive | Yes | #REF! | 3815420.63 | 604250 | 79715.36 | 4499385.99 | Yes
149 | 738671 | FAASt [25 MW BESS Installation and Integration - Barceloneta] (Substation) |  | Grid Modernization | Inactive | Yes | #REF! | 699102.04 | 0 | 72636.86 | 771738.9 | Yes
150 | 740406 | FAASt [Region 1-San Juan Group B] (Vegetation) |  | Vegetation | Inactive | Yes | #REF! | 92.31 | 0 | 14456.27 | 14548.58 | Yes
151 | 740408 | FAASt [Region 3-Bayamon Group B] (Vegetation) |  | Vegetation | Inactive | Yes | #REF! | 28.58 | 0 | 4197.38 | 4225.96 | Yes
152 | 740409 | FAASt [Region 4-Caguas Group B] (Vegetation) |  | Vegetation | Inactive | Yes | #REF! | 1.819e-12 | 0 | 8084.15 | 8084.15 | Yes
153 | 740410 | FAASt [Region 2-Arecibo Group B] (Vegetation) |  | Vegetation | Inactive | Yes | #REF! | 4.5475e-13 | 0 | 8296.79 | 8296.79 | Yes
154 | 740411 | FAASt [Region 5-Mayaguez Group B] (Vegetation) |  | Vegetation | Inactive | Yes | #REF! | 9.0949e-13 | 0 | 5962.2 | 5962.2 | Yes
155 | 740414 | FAASt [Region 6-Ponce Group B] High Density (Vegetation) |  | Vegetation | Inactive | Yes | #REF! | -216.88 | 0 | 7780.43 | 7563.55 | Yes
157 | 741097 | FAASt [Region 1 San Juan Subs/Telecom] (Vegetation) |  | Vegetation | Inactive | Yes | #REF! | 9.0949e-13 | 0 | 8787.49 | 8787.49 | Yes
163 | 744072 | FAASt [IT OT Technology Systems Reparations] Group 2 (Telecommunication) |  | Telecommunications | Inactive | Yes | #REF! | 0 | 0 | 0 | 0 | Yes
166 | 748180 | FAASt [Advanced Sensors Phasor Measurement Units (PMUs), and Wide-Area Monitoring, Protection, and Control (WAMPAC)] (Telecommunication) |  | Grid Modernization | Inactive | Yes | #REF! | 458759.67 | 0 | 119714.78 | 578474.45 | Yes
167 | 750502 | FAASt [25 MW BESS Installation and Integration - Aguadilla] (Substation) |  | Grid Modernization | Inactive | Yes | #REF! | 727189.77 | 106059.6 | 84267.7 | 917517.07 | Yes
168 | 750503 | FAASt [25 MW BESS Installation and Integration - San Juan] (Substation) |  | Grid Modernization | Inactive | Yes | #REF! | 740551.14 | 79544.7 | 113250.67 | 933346.51 | Yes
177 | 752972 | FAASt [4 x 25 MW BESS Interconnections Manati] (Substation) |  | Grid Modernization | Inactive | Yes | #REF! | 728229.81 | 79544.7 | 69630.44 | 877404.95 | Yes
182 | 753785 | FAASt [Transmission Priority Pole Replacement Program Line 3300 San Gerardo Sect – Venezuela Sect] (Transmission) |  | Transmission | Inactive | Yes | #REF! | 12461.09 | 0 | 14841.31 | 27302.4 | Yes
183 | 753781 | FAASt [Transmission Priority Pole Replacement Program Line 800 Comsat Sect – Cidra Sect] (Transmission) |  | Transmission | Inactive | Yes | #REF! | 331670.13 | 0 | 14773.53 | 346443.66 | Yes
2 | 724941 | FAASt [Aguas Buenas Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 651946.92 | 0 | 4529.61 | 656476.53 | No
3 | 724828 | FAASt [Loiza Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 312602.26 | 0 | 1133540.07 | 1446142.33 | No | Includes Work Completed
4 | 724781 | FAASt [Penuelas Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 279875.5 | 0 | 3359.76 | 283235.26 | No
5 | 724716 | FAASt [Quebradillas Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 369806.37 | 0 | 9160.84 | 378967.21 | No
6 | 724670 | FAASt [Patillas Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 312699.26 | 0 | 4239.71 | 316938.97 | No
7 | 724669 | FAASt [Ciales Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 427398.31 | 0 | 5187.38 | 432585.69 | No
8 | 724605 | FAASt [Guayanilla Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 543528.13 | 0 | 5932.84 | 549460.97 | No
9 | 724603 | FAASt [Cabo Rojo Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 565636.49 | 0 | 1831023.24 | 2396659.73 | No | Includes Work Completed
10 | 724599 | FAASt [Sabana Grande Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 472883.44 | 0 | 3708.63 | 476592.07 | No
11 | 718971 | FAASt [Line 50300 (230kV) from Costa Sur Steam Plant to Aguirre Steam Plant] (Transmission) |  | Transmission | Inactive | Yes | #REF! | 3136106.46 | 0 | 102391.27 | 3238497.73 | No
12 | 718955 | FAASt [Line 50200 (230kv) from Costa Sur SP to Bayamon TC] (Transmission) |  | Transmission | Inactive | Yes | #REF! | 2099429.08 | 0 | 64311.62 | 2163740.7 | No
13 | 718951 | FAASt [Line 51200- Costa Sur Steam Plant to Cambalache Gas Plant (230kV)] (Transmission) |  | Transmission | Inactive | Yes | #REF! | 1322132.33 | 0 | 31755.4 | 1353887.73 | No
14 | 715610 | FAASt [Network Upgrades to Support the Integration of Tranche 1 Utility Scale Renewable Projects] (Transmission) |  | Transmission | Inactive | Yes | #REF! | 0 | 26514.9 | 0 | 26514.9 | No
15 | 713795 | FAASt [Lares Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 320287.03 | 0 | 8878.15 | 329165.18 | No
16 | 705657 | FAASt [Automation Program Group 3] (TL/Distribution) |  | Grid Automation | Inactive | Yes | #REF! | 4787279.92 | 7291.5844 | 14022874.48 | 18817445.9844 | No | Includes Work Completed
17 | 705503 | FAASt [Pole and Conductor Repair Mayaguez Groups 15,16,17,18 & 19] (Distribution) |  | Distribution – Pole Replacement | Inactive | Yes | #REF! | 86247.26 | 0 | 201490.02 | 287737.28 | No
18 | 704931 | FAASt [Camuy Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 704757.7 | 0 | 2127836.67 | 2832594.37 | No | Includes Work Completed
19 | 704929 | FAASt [San Lorenzo Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 684564.35 | 0 | 1045452.1 | 1730016.45 | No | Includes Work Completed
20 | 704862 | FAASt [Fajardo Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 597812.07 | 0 | 2129118.43 | 2726930.5 | No | Includes Work Completed
21 | 704793 | FAASt [Yauco Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 664346.69 | 0 | 2913727.16 | 3578073.85 | No | Includes Work Completed
22 | 704757 | FAASt [Santa Isabel Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 384802.43 | 0 | 2232814.52 | 2617616.95 | No | Includes Work Completed
23 | 704744 | FAASt [San Sebastian Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 754342.03 | 0 | 2721453.75 | 3475795.78 | No | Includes Work Completed
24 | 704741 | FAASt [Moca Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 563643.62 | 0 | 5430.15 | 569073.77 | No
25 | 701473 | FAASt [Canovanas Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 535383.63 | 0 | 1615651.85 | 2151035.48 | No | Includes Work Completed
26 | 699814 | FAASt [Juana Diaz Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 617773.72 | 0 | 2240078.89 | 2857852.61 | No | Includes Work Completed
27 | 698522 | FAASt [Vieques Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 228080.82 | 0 | 1004763.81 | 1232844.63 | No | Includes Work Completed
28 | 698432 | FAASt [Hormigueros Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 366766.64 | 0 | 905135.06 | 1271901.7 | No | Includes Work Completed
29 | 698427 | FAASt [Maricao Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 181912.82 | 0 | 511210.78 | 693123.6 | No | Includes Work Completed
30 | 697183 | FAASt [Vega Baja Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 323918.02 | 0 | 1266013.74 | 1589931.76 | No | Includes Work Completed
31 | 693788 | FAASt [Toa Alta Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 398835.84 | 0 | 1432807.09 | 1831642.93 | No | Includes Work Completed
32 | 693615 | FAASt [Rio Grande Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 327961.04 | 0 | 633015.94 | 960976.98 | No | Includes Work Completed
33 | 693543 | FAASt [Juncos Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 496914.61 | 0 | 1638293.83 | 2135208.44 | No | Includes Work Completed
34 | 690721 | FAASt [Guayama Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 369654.84 | 0 | 1207346.17 | 1577001.01 | No | Includes Work Completed
35 | 690483 | FAASt [Cayey Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 750424.25 | 0 | 2230229.35 | 2980653.6 | No | Includes Work Completed
36 | 690480 | FAASt [Humacao Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 364243.46 | 0 | 839448.25 | 1203691.71 | No | Includes Work Completed
37 | 688623 | FAASt [Automation Program Group 1A-8 Feeders] (Distribution) |  | Grid Automation | Inactive | Yes | #REF! | 1113619.27 | 381308.9303 | 1082773.67 | 2577701.8703 | No | Includes Work Completed
38 | 686482 | FAASt [Isabela Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 335755.45 | 0 | 753235.29 | 1088990.74 | No | Includes Work Completed
39 | 685869 | FAASt [Mayagüez TC] (Substation) |  | Substation | Inactive | No |  | 1498455.38 | 1324498.9 | 94654.81 | 2917609.09 | No
40 | 679006 | FAASt [Test and Technology Laboratory] (Building) |  | Building | Inactive | Yes | #REF! | 747339.67 | 0 | 70121.49 | 817461.16 | No
41 | 678795 | FAASt [Arecibo Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 767004.91 | 0 | 1934700.14 | 2701705.05 | No | Includes Work Completed
42 | 678794 | FAASt [Ponce Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 765473.52 | 0 | 2684972.1 | 3450445.62 | No | Includes Work Completed
43 | 675345 | FAASt [IT OT Technology Systems Reparations] Group 1 (Telecommunication) |  | Telecommunications | Inactive | Yes | #REF! | 0 | 0 | 0 | 0 | No
44 | 671400 | FAASt [Barceloneta Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 524140.74 | 0 | 1356777.25 | 1880917.99 | No | Includes Work Completed
45 | 671396 | FAASt [Utuado Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 772706.37 | 0 | 1827017.56 | 2599723.93 | No | Includes Work Completed
46 | 668665 | FAASt [Cybersecurity Program Implementation] (Telecommunication) |  | Telecommunications | Inactive | Yes | #REF! | 1.53 | 0 | 0.27 | 1.8 | No
47 | 666894 | FAASt [San Juan Streetlighting] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 2499986.19 | 0 | 6779878.71 | 9279864.9 | No | Includes Work Completed
48 | 551927 | FAASt [SCADA Remote Access and RTU Replacements Group 3] (Telecommunication) |  | Substation | Inactive | Yes | #REF! | 1001723.4 | 0 | 171414.24 | 1173137.64 | No
49 | 551918 | FAASt [Crematorio - 1512] (Substation) |  | Substation | Inactive | Yes | #REF! | 929559.92 | 0 | 42289.23 | 971849.15 | No
51 | 551911 | FAASt [Line 9100 (38 kV) - Guaraguao TC to Bayamon Pueblo Sect.] (Transmission) |  | Transmission | Inactive | No |  | 1300502.63 | 26514.9 | 56415.86 | 1383433.39 | No
52 | 551260 | FAASt [Guaynabo Pueblo Substation] (Substation) |  | Substation | Inactive | Yes | #REF! | 1033630.56 | 1022889.52 | 34879.82 | 2091399.9 | No
53 | 551247 | FAASt [Palo Seco South Building Repairs] (Building) |  | Building | Inactive | No |  | 859793.52 | 0 | 35673.15 | 895466.67 | No
54 | 551067 | FAASt [Line 11100 Canovanas Sect. to GOAB 11115] (Transmission) |  | Transmission | Inactive | No |  | 1413859.02 | 1100357.8182 | 26664.26 | 2540881.0982 | No
57 | 550902 | FAASt [Line 9700 Palo Seco SP to Bay View Sect.] (Transmission) |  | Transmission | Inactive | No |  | 1064893.34 | 39772.35 | 20412.45 | 1125078.14 | No
59 | 550498 | FAASt - [Morovis 8801 (Fuse to Breaker)] (Substation) |  | Substation | Inactive | No |  | 126915.84 | 0 | 68529.59 | 195445.43 | No
60 | 550162 | FAASt [Berwind TC - 1336] (Substation) |  | Substation | Inactive | Yes | #REF! | 1447385.34 | 0 | 51252.49 | 1498637.83 | No
62 | 550019 | FAASt [Line 600 Caguas TC to Gautier Benitez Sect.] (Transmission) |  | Transmission | Inactive | Yes | #REF! | 945634.82 | 0 | 39185.68 | 984820.5 | No
63 | 548598 | FAASt [Line 36200 (115 kV) Fajardo to Rio Blanco] (Transmission) |  | Transmission | Inactive | Yes | #REF! | 1082636.93 | 0 | 68164.84 | 1150801.77 | No
64 | 547350 | FAASt [Line 13300 Bayamon TC to Plaza del Sol] (Transmission) |  | Transmission | Inactive | No |  | 1521473.79 | 0 | 8371.81 | 1529845.6 | No
65 | 547344 | FAASt [Acacias 6801 TC Relocation] (Substation) |  | Substation | Inactive | Yes | #REF! | 1625433.19 | 898630 | 60220.95 | 2584284.14 | No
66 | 547343 | FAASt [Victoria TC 7008 Relocation] (Substation) |  | Substation | Inactive | Yes | #REF! | 2508826.39 | 0 | 434647.36 | 2943473.75 | No
67 | 547273 | FAASt Charco Hondo Substation 8008 Relocation (Substation) |  | Substation | Inactive | No |  | 613309.81 | 0 | 23662.68 | 636972.49 | No
68 | 547269 | FAASt Line 2800 (38 kV) Aguadilla Hospital Distrito Sect to T-Bone TO (Transmission) |  | Transmission | Inactive | Yes | #REF! | 1279409.56 | 0 | 89512.15 | 1368921.71 | No
69 | 547259 | FAASt Line 2700 (38kV) Victoria TC to Quebradillas Sect. (Transmission) |  | Transmission | Inactive | Yes | #REF! | 1616166.57 | 0 | 140659.68 | 1756826.25 | No
71 | 547243 | FAASt Egozcue - 1109 (Substation) |  | Substation | Inactive | Yes | #REF! | 1128223.69 | 723116.82 | 23670.42 | 1875010.93 | No
72 | 547241 | FAASt Tallaboa 5402 (Substation) |  | Substation | Inactive | Yes | #REF! | 922655.66 | 198861.75 | 72711.6 | 1194229.01 | No
73 | 547226 | FAASt Barceloneta 11400 TC to Florida TO (Transmission) |  | Transmission | Inactive | No |  | 985966.86 | 0 | 22411.86 | 1008378.72 | No
74 | 547160 | FAASt [Line 1200 Mayaguez GP to Yauco 2 HP] (Transmission) |  | Transmission | Inactive | No |  | 3732057.59 | 0 | 97223.32 | 3829280.91 | No
75 | 546386 | FAASt [Feeders- El Yunque 2305 - Supply] (Distribution) |  | Distribution – Feeder Rebuild | Inactive | Yes | #REF! | 1609417.88 | 0 | 31225.13 | 1640643.01 | No
76 | 546374 | FAASt [Feeders - 1620-02 - San Juan Short Term Group 3] (Distribution) |  | Distribution – Feeder Rebuild | Inactive | Yes | #REF! | 2485192.97 | 0 | 78308.39 | 2563501.36 | No
77 | 436616 | FAASt [Feeders - Arecibo Short Term Group 1] (Distribution) |  | Distribution – Feeder Rebuild | Inactive | Yes | #REF! | 2562116.59 | 296945.8291 | 190901.94 | 3049964.3591 | No
78 | 334518 | FAASt [Feeders - Caguas Short Term Group 7] (Distribution) |  | Distribution – Feeder Rebuild | Inactive | Yes | #REF! | 817708.4 | 191915.5987 | 27139.53 | 1036763.5287 | No
79 | 334497 | FAASt [Feeders - Caguas Short Term Group 6 (Distribution) |  | Distribution – Feeder Rebuild | Inactive | Yes | #REF! | 3284447.24 | 80776.2262 | 332656.49 | 3697879.9562 | No
80 | 334491 | FAASt [Feeders - Caguas Short Term Group 5] (Distribution) |  | Distribution – Feeder Rebuild | Inactive | Yes | #REF! | 749293.91 | 0 | 168615.61 | 917909.52 | No
81 | 334477 | FAASt [Feeders - 2402-02 - Carolina Short Term Group 3] (Distribution) |  | Distribution – Feeder Rebuild | Inactive | Yes | #REF! | 572777.57 | 831634.261 | 14383.79 | 1418795.621 | No
82 | 334476 | FAASt [Feeders - Carolina Short Term Group 2] (Distribution) |  | Distribution – Feeder Rebuild | Inactive | Yes | #REF! | 2094612.85 | 193322.6327 | 62071.2 | 2350006.6827 | No
83 | 334475 | FAASt [Feeders - Bayamon Short Term Group 3] (Distribution) |  | Distribution – Feeder Rebuild | Inactive | Yes | #REF! | 2117849.36 | 471736.6618 | 113559.71 | 2703145.7318 | No
84 | 334474 | FAASt [Feeders - Bayamon Short Term Group 2] (Distribution) |  | Distribution – Feeder Rebuild | Inactive | Yes | #REF! | 420575.65 | 0 | 41060.71 | 461636.36 | No
85 | 334473 | FAASt [Feeders - 1806-02- Bayamon Short Term Group 1] (Distribution) |  | Distribution – Feeder Rebuild | Inactive | Yes | #REF! | 931456.09 | 37063.6 | 90278.79 | 1058798.48 | No
86 | 334472 | FAASt [Feeders - San Juan Short Term Group 2] (Distribution) |  | Distribution – Feeder Rebuild | Inactive | Yes | #REF! | 2815475.62 | 958532.3149 | 83104.83 | 3857112.7649 | No
87 | 334471 | FAASt [Feeders -1303-01- San Juan Short Term Group 1] (Distribution) |  | Distribution – Feeder Rebuild | Inactive | Yes | #REF! | 539799.34 | 127943.7325 | 7576.78 | 675319.8525 | No
88 | 334452 | FAASt [Feeders - Caguas Short Term Group 3] (Distribution) |  | Distribution – Feeder Rebuild | Inactive | Yes | #REF! | 1105038.15 | 351845.2643 | 84910.57 | 1541793.9843 | No
89 | 334443 | FAASt [Feeders - Caguas Short Term Group 2] (Distribution) |  | Distribution – Feeder Rebuild | Inactive | Yes | #REF! | 3918554.07 | 372411.7382 | 153418.7 | 4444384.5082 | No
90 | 334420 | FAASt [Feeders - Caguas Short Term Group 1] (Distribution) |  | Distribution – Feeder Rebuild | Inactive | Yes | #REF! | 2466044.98 | 792484.0911 | 92445.64 | 3350974.7111 | No
91 | 334331 | FAASt Line 1900 Dos Bocas HP to San Sebastian (38kV) TC (Transmission) |  | Transmission | Inactive | Yes | #REF! | 3373474.81 | 0 | 451250.44 | 3824725.25 | No
92 | 334308 | FAASt [Feeders - Mayaguez Short Term Group 1] (Distribution ) |  | Distribution – Feeder Rebuild | Inactive | Yes | #REF! | 1708578.2 | 0 | 94679.16 | 1803257.36 | No
93 | 334293 | FAASt [Feeders - 7805-11- Mayaguez Short Term Group 4] (Distribution ) |  | Distribution – Feeder Rebuild | Inactive | Yes | #REF! | 4868204.67 | 619697.5703 | 274204.5 | 5762106.7403 | No
94 | 334285 | FAASt [Feeders - Mayaguez Short Term Group 2] (Distribution ) |  | Distribution – Feeder Rebuild | Inactive | Yes | #REF! | 3970385.77 | 531797.2057 | 117889.93 | 4620072.9057 | No
95 | 334191 | FAASt [Feeders - Mayaguez Short Term Group 3] (Distribution) |  | Distribution – Feeder Rebuild | Inactive | Yes | #REF! | 5717025.17 | 3863896.9283 | 108889.99 | 9689812.0883 | No
96 | 180326 | FAASt - Line 36800 (115kV) - Sabana Llana TC to Canovanas TC to Palmer-Fajardo TC (Transmission) |  | Transmission | Inactive | Yes | #REF! | 2738961.97 | 0 | 197639.44 | 2936601.41 | No
97 | 177191 | FAASt - 115kV Line 39000 - Aguas Buenas TC to Caguas TC (Transmission) |  | Transmission | Inactive | Yes | #REF! | 1860551.68 | 0 | 486694.87 | 2347246.55 | No
98 | 177134 | FAASt Guaraguao TC to Comerio TC Line-4100 (Transmission) |  | Transmission | Inactive | Yes | #REF! | 2825116.95 | 0 | 155611.14 | 2980728.09 | No
99 | 176954 | FAASt Garzas 1 HP to Garzas 2 HP - 38kV Line 1100 (Transmission) |  | Transmission | Inactive | Yes | #REF! | 803736.24 | 0 | 164175.64 | 967911.88 | No
100 | 167508 | FAASt Transmission - Line 50100 (230KV)- Cambalache GP TC to Manati TC (Transmission) |  | Transmission | Inactive | Yes | #REF! | 1487923.99 | 0 | 27464.43 | 1515388.42 | No
101 | 167443 | FAASt - Line 36200 (115KV)- Monacillos TC to Juncos TC (Transmission) |  | Transmission | Inactive | Yes | #REF! | 1946817.06 | 0 | 107036.18 | 2053853.24 | No
102 | 167168 | FAASt [Transmission 115kV Line 37100 Costa Sur ST - Acacias TC] (Transmission) |  | Transmission | Inactive | Yes | #REF! | 3713271.18 | 0 | 106074.99 | 3819346.17 | No
103 | 166904 | FAASt Transmission 115kV Line 37800 Caguas TC to Monacillos TC (TRANSMISSION) |  | Transmission | Inactive | Yes | #REF! | 1701248.61 | 0 | 174713.68 | 1875962.29 | No
104 | 166860 | FAASt-Line 37800 (115kV) - Jobos TC to Cayey TC & Cayey TC to Caguas TC (Transmission) |  | Transmission | Inactive | Yes | #REF! | 3529391.09 | 0 | 55770.17 | 3585161.26 | No
105 | 166707 | FAASt - Line 51300 (230KV) - Ponce TC to Costa Sur SP TC (Transmission) |  | Transmission | Inactive | Yes | #REF! | 2885457.37 | 0 | 668485.68 | 3553943.05 | No
106 | 730821 | FAASt [Feeders - Arecibo Short Term Group 2] (Distribution) |  | Distribution – Feeder Rebuild | Inactive | Yes | #REF! | 2015105.41 | 167040.7236 | 83429.02 | 2265575.1536 | No
107 | 730824 | FAASt [Feeders - Ponce Short Term Group 2] (Distribution) |  | Distribution – Feeder Rebuild | Inactive | Yes | #REF! | 2432367.96 | 0 | 32196.37 | 2464564.33 | No
108 | 730513 | FAASt [Feeders-Caguas Short Term Group 4] (Distribution) |  | Distribution – Feeder Rebuild | Inactive | Yes | #REF! | 823250.66 | 0 | 4473.25 | 827723.91 | No
109 | 730541 | FAASt [Feeders - Caguas Short Term Group 8] (Distribution) |  | Distribution – Feeder Rebuild | Inactive | Yes | #REF! | 2328548.5 | 216619.9383 | 78239.56 | 2623407.9983 | No
110 | 730586 | FAASt [Feeders - Ponce Short Term Group 1] (Distribution) |  | Distribution – Feeder Rebuild | Inactive | Yes | #REF! | 2385628.07 | 20375.2655 | 94994.92 | 2500998.2555 | No
111 | 730657 | FAASt [Line 2200 Dos Bocas HP to Dorado TC ] (Transmission) |  | Transmission | Inactive | No |  | 9142055.58 | 0 | 110975.62 | 9253031.2 | No
112 | 738667 | FAASt [Pole and Conductor Repair - Ponce Group 2 - Phase 2] (Distribution) |  | Distribution – Pole Replacement | Inactive | Yes | #REF! | 377477.04 | 0 | 9701.73 | 387178.77 | No
113 | 738674 | FAASt [Pole and Conductor Repair - Mayaguez Group 2 - Phase 2] (Distribution) |  | Distribution – Pole Replacement | Inactive | Yes | #REF! | 137975.62 | 11119.08 | 11329.66 | 160424.36 | No
114 | 738692 | FAASt [Pole and Conductor Repair - Carolina Group 1 - Phase 2] (Distribution) |  | Distribution – Pole Replacement | Inactive | No |  | 57166.28 | 0 | 9719.02 | 66885.3 | No
115 | 734393 | FAASt [Cabo Rojo Streetlighting - Part 2] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 364960.59 | 0 | 3471.55 | 368432.14 | No
116 | 734396 | FAASt [Cabo Rojo Streetlighting - Part 3] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 270658.3 | 0 | 8748.7 | 279407 | No
117 | 735483 | FAASt [Vega Baja Streetlighting - Part 3] (Distribution) |  | Distribution – Streetlighting | Inactive | No |  | 253410.27 | 0 | 11658.84 | 265069.11 | No
118 | 734760 | FAASt [Ponce Streetlighting - Part 3] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 691037.11 | 0 | 9952.94 | 700990.05 | No
119 | 735360 | FAASt [Mayaguez Streetlighting - Part 3] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 671635.88 | 0 | 262763.16 | 934399.04 | No
120 | 734728 | FAASt [Ponce Streetlighting - Part 2] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 572254.77 | 0 | 3733 | 575987.77 | No
121 | 735357 | FAASt [Mayaguez Streetlighting - Part 2] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 328248.22 | 0 | 2071.71 | 330319.93 | No
122 | 734928 | FAASt [Isabela Streetlighting - Part 3] (Distribution) |  | Distribution – Streetlighting | Inactive | No |  | 314304.66 | 0 | 10808.57 | 325113.23 | No
123 | 734927 | FAASt [Isabela Streetlighting - Part 2] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 304601.84 | 0 | 2371.66 | 306973.5 | No
124 | 735487 | FAASt [Humacao Streetlighting - Part 3] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 273446.16 | 0 | 8558.92 | 282005.08 | No
125 | 734791 | FAASt [Guayama Streetlighting - Part 2] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 424480.22 | 0 | 7121.24 | 431601.46 | No
126 | 735493 | FAASt [Humacao Streetlighting - Part 2] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 321233.51 | 0 | 3596.94 | 324830.45 | No
127 | 734789 | FAASt [Guayama Streetlighting - Part 3 ] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 277617.77 | 0 | 7596.94 | 285214.71 | No
128 | 735496 | FAASt [Carolina Streetlighting - Part 3] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 668286.36 | 0 | 16505.22 | 684791.58 | No
129 | 735499 | FAASt [Guaynabo Streetlighting - Part 3] (Distribution) |  | Distribution – Streetlighting | Inactive | No |  | 358119.53 | 0 | 17166.9 | 375286.43 | No
130 | 735665 | FAASt [Carolina Streetlighting - Part 2] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 789946.93 | 0 | 5475.82 | 795422.75 | No
131 | 735672 | FAASt [Caguas Streetlighting - Part 3] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 746347.26 | 0 | 6288.06 | 752635.32 | No
132 | 735677 | FAASt [Guaynabo Streetlighting - Part 2] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 348065.75 | 0 | 36726.09 | 384791.84 | No
133 | 735940 | FAASt [Vega Baja Streetlighting - Part 2] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 304376.42 | 0 | 9074.69 | 313451.11 | No
134 | 735952 | FAASt [Trujillo Alto Streetlighting - Part 3] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 357078.1 | 0 | 12507.41 | 369585.51 | No
135 | 735954 | FAASt [Trujillo Alto Streetlighting - Part 2] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 244352.23 | 0 | 6105.95 | 250458.18 | No
136 | 735959 | FAASt [Toa Baja Streetlighting - Part 3] (Distribution) |  | Distribution – Streetlighting | Inactive | No |  | 286913.59 | 0 | 13577.42 | 300491.01 | No
137 | 735960 | FAASt [Toa Baja Streetlighting - Part 2] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 305288.21 | 0 | 6496.32 | 311784.53 | No
138 | 737699 | FAASt [Toa Alta Streetlighting - Part 3] (Distribution) |  | Distribution – Streetlighting | Inactive | No |  | 213368.24 | 0 | 7769.11 | 221137.35 | No
139 | 737707 | FAASt [Toa Alta Streetlighting - Part 2] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 350733.15 | 0 | 13839.46 | 364572.61 | No
140 | 737712 | FAAST [San Juan Streetlighting - Part 3] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 1098114.69 | 0 | 5171.84 | 1103286.53 | No
141 | 737798 | FAASt [Rio Grande Streetlighting - Part 3] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 230006.04 | 0 | 9087.61 | 239093.65 | No
142 | 737804 | FAASt [Rio Grande Streetlighting - Part 2 ] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 274947.63 | 0 | 3609.94 | 278557.57 | No
143 | 735131 | FAASt [Arecibo Streetlighting - Part 2] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 497360.7 | 0 | 5734.08 | 503094.78 | No
144 | 734853 | FAASt [Arecibo Streetlighting- Part 3] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 558092.62 | 0 | 11937.43 | 570030.05 | No
145 | 734859 | FAASt [Aguadilla Streetlighting - Part 2] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 290922.13 | 0 | 7232.9 | 298155.03 | No
146 | 735472 | FAASt [Bayamon Streetlighting - Part 3] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 693761.38 | 0 | 11729.21 | 705490.59 | No
147 | 735470 | FAASt [Bayamón Streetlighting - Part 2] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 692749.72 | 0 | 10725.02 | 703474.74 | No
148 | 735338 | FAASt [Aguadilla Streetlighting - Part 3] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 300143.9 | 0 | 13477.82 | 313621.72 | No
156 | 740662 | FAASt [Automation Program Group 2] (TL/ Distribution) |  | Grid Automation | Inactive | Yes | #REF! | 6969935.9 | 0 | 16219867.09 | 23189802.99 | No | Includes Work Completed
158 | 745854 | FAASt [ Automation Program Group 9] (Distribution) |  | Grid Automation | Inactive | Yes | #REF! | 65312.07 | 118359.1407 | 1215.31 | 184886.5207 | No
159 | 745871 | FAASt [Automation Program Group 10] (Distribution) |  | Grid Automation | Inactive | Yes | #REF! | 0 | 290967.3491 | 0 | 290967.3491 | No
160 | 745851 | FAASt [Automation Program Group 11] (Distribution) |  | Grid Automation | Inactive | Yes | #REF! | 52762.1 | 201844.4227 | 829.93 | 255436.4527 | No
161 | 745852 | FAASt [Automation Program Group 13] (Distribution) |  | Grid Automation | Inactive | Yes | #REF! | 0 | 837283.816 | 0 | 837283.816 | No
162 | 741678 | FAASt [Automation Program Group 4] (TL/Distribution) |  | Grid Automation | Inactive | Yes | #REF! | 5490227.99 | 1765011.9281 | 14921572.96 | 22176812.8781 | No | Includes Work Completed
164 | 746108 | FAASt [San Juan Streetlighting - Part 2] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 820059.08 | 0 | 4139.83 | 824198.91 | No
165 | 746111 | FAASt [Caguas Streetlighting - Part 2] (Distribution) |  | Distribution – Streetlighting | Inactive | Yes | #REF! | 504585.9 | 0 | 3703.07 | 508288.97 | No
169 | 750730 | FAASt [Line 500 Ponce TC to Costa Sur SP] (Transmission) |  | Transmission | Inactive | No |  | 2645964.16 | 0 | 57509.11 | 2703473.27 | No
170 | 752052 | FAASt [Transmission Line 9900 TAP9905A to Rio Blanco HP] (Transmission) |  | Transmission | Inactive | No |  | 815006.65 | 0 | 40075.35 | 855082 | No
171 | 752277 | FAASt [Substation Ciales 8701] (Substation) |  | Substation | Inactive | Yes | #REF! | 419830.42 | 0 | 16607.05 | 436437.47 | No
172 | 752276 | FAASt [Monterrey 9502 & 9503 (Fuse to Breaker)] (Substation) |  | Substation | Inactive | No |  | 699860.15 | 557718.26 | 73612.09 | 1331190.5 | No
173 | 752275 | FAASt [Unibon 9501 (Fuse to Breaker)] (Substation) |  | Substation | Inactive | No |  | 742932.1 | 0 | 63265.84 | 806197.94 | No
174 | 752500 | FAASt [Automation Program Group 1B-6 Feeders] (Distribution) |  | Grid Automation | Inactive | No |  | 744990.84 | 139695.5176 | 1605282.86 | 2489969.2176 | No | Includes Work Completed
175 | 752502 | FAASt [Automation Program Group 1C-7 Feeders] (Distribution) |  | Grid Automation | Inactive | No |  | 1058497.11 | 340359.5987 | 1058114.52 | 2456971.2287 | No | Includes Work Completed
176 | 752503 | FAASt [Automation Program Group 1D-7 Feeders] (Distribution) |  | Grid Automation | Inactive | No |  | 1124553.03 | 50309.8182 | 3443551.68 | 4618414.5282 | No | Includes Work Completed
178 | 753302 | FAASt [Telecom Infrastructure Group G] (Telecommunication) |  | Telecommunications | Inactive | No |  | 19771.47 | 0 | 9534.67 | 29306.14 | No
179 | 753788 | FAASt [Transmission Priority Pole Replacement Program Line 1900 Dos Bocas HP – San Sebastian TC] (Transmission) |  | Transmission | Inactive | Yes | #REF! | 266480.89 | 0 | 11898.74 | 278379.63 | No
180 | 753787 | FAASt [Transmission Priority Pole Replacement Program Line 13700 Mora TC-Isabela TO] (Transmission) |  | Transmission | Inactive | Yes | #REF! | 42672.97 | 0 | 4423.26 | 47096.23 | No
181 | 753786 | FAASt [Transmission Priority Pole Replacement Program Line 5900 San Juan SP - Crematorio TO] (Transmission) |  | Transmission | Inactive | Yes | #REF! | 78163.5 | 0 | 8904.48 | 87067.98 | No
184 | 753777 | FAASt [Line 1500 - Mayaguez GP to GOAB 1515] (Transmission) |  | Transmission | Inactive | No |  | 4211801.41 | 0 | 57120.95 | 4268922.36 | No
185 | 754351 | FAASt [Underground Circuit Feeders - San Juan Group 2] (Distribution) |  | Distribution – Underground | Inactive | Yes | #REF! | 567000.45 | 0 | 155562.85 | 722563.3 | No
186 | 754350 | FAASt [Underground Circuit Feeders - San Juan Group 1] (Distribution) |  | Distribution – Underground | Inactive | Yes | #REF! | 667130.1 | 0 | 163703.39 | 830833.49 | No
187 | 800369 | FAASt [Automation Program Group 38] (Distribution) |  | Grid Automation | Inactive | No |  | 61845.16 | 279038.2036 | 6823.21 | 347706.5736 | No
188 | 800394 | FAASt [Automation Program Group 39] (Distribution) |  | Grid Automation | Inactive | No |  | 89687.2 | 285030.5685 | 9958.04 | 384675.8085 | No
189 | 800399 | FAASt [Automation Program Group 40] (Distribution) |  | Grid Automation | Inactive | No |  | 218712.06 | 590462.1371 | 9950.63 | 819124.8271 | No
190 | 757945 | FAASt [Pole and Conductor Repair - Arecibo Group 3 - Phase 2] (Distribution) |  | Distribution – Pole Replacement | Inactive | Yes | #REF! | 53378.86 | 0 | 6658.57 | 60037.43 | No
191 | 759051 | FAASt Pole and Conductor - Bayamon Group 4 - Phase 2 (Distribution) |  | Distribution | Inactive | No |  | 30058.16 | 0 | 10722.37 | 40780.53 | No
192 | 759004 | FAASt [Pole and Conductor - Arecibo Group 4 - Phase 2] (Distribution) |  | Distribution | Inactive | No |  | 81705.29 | 0 | 56028.17 | 137733.46 | No
193 | 761563 | FAASt [San Jose Relocation] (Substation) |  | Substation | Inactive | No |  | 662865.05 | 0 | 13450.81 | 676315.86 | No
194 | 811923 | FAASt [Transmission Priority Pole Replacement Program Line 16500 Fajardo TC-Dos Marinas] (Transmission) |  | Transmission – Pole Replacement | Inactive | Yes | #REF! | 51079.42 | 0 | 15787.34 | 66866.76 | No
195 | 811913 | FAASt [Transmission Priority Pole Replacement Program Line 9600 Bayamon TC – Catano Sect] (Transmission) |  | Transmission – Pole Replacement | Inactive | Yes | #REF! | 33407.6 | 0 | 8978.4 | 42386 | No
196 | 805521 | FAASt [38kV Recloser TL 7800 Dorado TC to Vega Alta Sect.] (Transmission) |  | Transmission – Pole Replacement | Inactive | Yes | #REF! | 142174.45 | 64775.2 | 15034.64 | 221984.29 | No
197 | 801432 | FAASt [Automation Program Group 41] (Distribution) |  | Grid Automation | Inactive | No |  | 45668.3 | 571816.0095 | 1347.82 | 618832.1295 | No
198 | 801437 | FAASt [Automation Program Group 42] (Distribution) |  | Grid Automation | Inactive | No |  | 19879.2 | 201413.4785 | 3224.35 | 224517.0285 | No
199 | 801438 | FAASt [Automation Program Group 43] (Distribution) |  | Grid Automation | Inactive | No |  | 75315.28 | 329467.884 | 2482.77 | 407265.934 | No
200 | 801440 | FAASt [Automation Program Group 44] (Distribution) |  | Grid Automation | Inactive | No |  | 39944.71 | 228127.4774 | 2752.72 | 270824.9074 | No
201 | 801441 | FAASt [Automation Program Group 45] (Distribution |  | Grid Automation | Inactive | No |  | 38926.6 | 479180.0277 | 1467.61 | 519574.2377 | No
202 | 806935 | FAASt [Pole and Conductor Repair - Caguas Group 6 - Phase 2] (Distribution) |  | Distribution – Pole Replacement | Inactive | No |  | 14869.09 | 0 | 9379.3 | 24248.39 | No
203 | 806936 | FAASt [Pole and Conductor Repair - Carolina Group 3 - Phase 2] (Distribution) |  | Distribution – Pole Replacement | Inactive | No |  | 200585.92 | 0 | 6803.91 | 207389.83 | No
204 | 805519 | FAASt [38kV Recloser TL 1900 Dos Bocas HP to San Sebastian TC] (Transmission) |  | Transmission | Inactive | Yes | #REF! | 101897.17 | 77960.2547 | 17772.02 | 197629.4447 | No
205 | 805517 | FAASt [38kV Recloser TL 2100 Hatillo TC to Quebradillas Sect.] (Transmission) |  | Transmission | Inactive | Yes | #REF! | 110178.42 | 69170.2182 | 21463.67 | 200812.3082 | No
206 | 790427 | FAASt [Pole and Conductor Repair -Caguas Group 5 Phase 2 (Distribution) |  | Distribution | Inactive | Yes | #REF! | 608897.76 | 0 | 8524.87 | 617422.63 | No
207 | 790446 | FAASt [Pole and Conductor Repair -Caguas Group 4 Phase 2 (Distribution) |  | Distribution | Inactive | Yes | #REF! | 112030.52 | 0 | 9397.13 | 121427.65 | No
208 | 812041 | FAASt [Distribution Feeder Rebuild 9501-02] |  | Distribution | Inactive | Yes | #REF! | 1336858.37 | 226284 | 76362.85 | 1639505.22 | No
209 | 814792 | FAASt [Telecom Infrastructure – Group E] |  | Telecommunications | Inactive | No |  | 562641.94 | 0 | 113659.6 | 676301.54 | No
210 | 814793 | FAASt [Telecom Infrastructure – Group F] |  | Telecommunications | Inactive | No |  | 464395.59 | 0 | 87687.56 | 552083.15 | No
211 | 817961 | FAASt [Feeder Rebuild # 2404-06] (Distribution) |  | Distribution – Feeder Rebuild | Inactive | Yes | #REF! | 1213724.13 | 0 | 33726.8 | 1247450.93 | No
212 | 818006 | FAASt [Feeder Rebuild #2402-02] (Distribution) |  | Distribution – Feeder Rebuild | Inactive | No |  | 1497224.17 | 0 | 61748.27 | 1558972.44 | No
213 | 817993 | FAASt [Feeder Rebuild # 1801-03] (Distribution) |  | Distribution – Feeder Rebuild | Inactive | No |  | 1135718.34 | 0 | 64565.73 | 1200284.07 | No
214 | 818056 | FAASt [Feeder Rebuild # 6305-03] (Distribution) |  | Distribution – Feeder Rebuild | Inactive | No |  | 1635991.21 | 667144.8 | 50902.28 | 2354038.29 | No
215 | 818055 | FAASt [Feeder Rebuild # 3006-05] (Distribution) |  | Distribution – Feeder Rebuild | Inactive | No |  | 1702257.95 | 48534.08 | 352833.21 | 2103625.24 | No
216 | 818041 | FAASt [Feeder Rebuild # 3701-03] (Distribution) |  | Distribution – Feeder Rebuild | Inactive | No |  | 1750126.44 | 507812 | 80295.93 | 2338234.37 | No
217 | 817962 | FAASt [Feeder Rebuild # 9403-03] (Distribution) |  | Distribution – Feeder Rebuild | Inactive | No |  | 699973.75 | 30087.9091 | 44787.96 | 774849.6191 | No
218 | 817249 | FAASt [Pole and Conductor Repair -Caguas Group 7 - Phase 2] (Distribution) |  | Distribution – Pole Replacement | Inactive | No |  | 181431.75 | 0 | 8030.24 | 189461.99 | No
219 | 817242 | FAASt [Pole and Conductor Repair -Caguas Group 8 - Phase 2] (Distribution) |  | Distribution – Pole Replacement | Inactive | No |  | 79895.01 | 0 | 6878.01 | 86773.02 | No
220 | 817247 | FAASt [Pole and Conductor Repair -Ponce Group 3 - Phase 2] (Distribution) |  | Distribution – Pole Replacement | Inactive | No |  | 289257.2 | 0 | 31827.44 | 321084.64 | No
221 | 817250 | FAASt [Pole and Conductor Repair -San Juan Group 4 - Phase 2] (Distribution) |  | Distribution – Pole Replacement | Inactive | No |  | 55326.72 | 0 | 57494.46 | 112821.18 | No
222 | 954184 | FAASt [Carolina ESC Building Repairs] (Buildings) |  | Building | Inactive | Yes | #REF! | 0 | 0 | 0 | 0 | No
223 | 956782 | Feeder Rebuild #6802-04 (Distribution) |  | Distribution – Feeder Rebuild | Inactive | Yes | #REF! | 1544468.19 | 51889.04 | 30020.13 | 1626377.36 | No
224 | 958367 | FAASt [Feeder Rebuild #6603-01] (Distribution) |  | Distribution | Inactive | Yes | #REF! | 1663612.58 | 111190.8 | 85949.86 | 1860753.24 | No
[8 empty] | 225708722.5 | 25877249.0742 | 110243281.77 | 361829253.3442

## To Discuss (hidden)
[6 empty] | RFR Team | [18 empty] | Expected Project Costs Allocation
Project # | Title | Asset | Sub Asset | Obligated (Yes / No) | Process Step | 428 Allocation (Without the A&E and E&M) | 406 Allocation (Without the A&E and E&M) | 428 A&E-PW 9510 | 406 A&E-PW 9510 | 428 E&M-PW 10710 | 406 E&M-PW 10710 | Is 406 Allocation $0 and A&E/E&M Balance | FORMULA Expected Total Project Cost | FORMULA Total 428 Expected cost | FORMULA Total 406 Expected Cost | Current Versioning Status in Grants Protal | Date of Obligation | Current Status in Grants Protal | Construction % of Completion as of 2/28/2026 | A&E Spend as of 2/28/2026 | Construction Spend as of 2/28/2026 | E&M Spend as of 2/28/2026 | Total Spend as of 2/28/2026 | Compare | 428 Allocation (Without the A&E and E&M) | 406 Allocation (Without the A&E and E&M) | 428 A&E-PW 9510 | 406 A&E-PW 9510 | 428 E&M-PW 10710 | 406 E&M-PW 10710 | Expected Total Project Cost | Total 428 Expected cost | Total 406 Expected Cost | Project Reconciliation Status | Expected Reconciliation date | Comments
701504 | FAASt [Pole and Conductor Repair - Arecibo Group 12] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 150345 | 33387 | 29252 | 4491 | 0 | 0 | 0 | 217475 | 179597 | 37878 | Obligated | 2023-03-08 12:36 | Obligated | 100% | 33295.7 | 99140.02 |  | 132435.72 | -51422.58 | 211260.32 | 1161.51 | 23475.13 | 868.52 | 24568.7 | 7563.4 | 268897.58 | 259304.15 | 9593.43 | Amendment – Submitted to COR3/PREPA | Submitted | Amendment submitted Feb 12, 2026
334329 | FAASt Distribution Pole and Conductor Repair - Ponce Group 2 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 316119 | 64134 | 25530 | 0 | 0 | 0 | 0 | 405783 | 341649 | 64134 | Obligated | 2022-05-20 12:05 | Obligated | 87% | 99612.94 | 320300.98 |  | 419913.92 | -16160350.48 | 13767291.01 | 5248.03 | 1304890.11 | 3414.73 | 1450714.05 | 34575.55 | 16566133.48 | 16522895.17 | 43238.31 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
169896 | FAASt - Costa Sur SP TC  Equipment Repair and | Substation | Substation Rebuilds | Yes | Obligated | 23251835 | 0 | 4734912 | 0 | 0 | 0 | 0 | 27986747 | 27986747 | 0 | Obligated | 2022-08-02 11:42 | Obligated | 43% | 3453256.41 | 11157319.2 |  | 14610575.61 | -4217964.29 | 28250123.84 | 498874.07 | 3402149.85 | 53563.53 | 0 | 0 | 32204711.29 | 31652273.69 | 552437.6 | Amendment – Submitted to COR3/PREPA | Submitted
165209 | FAASt - EPC - Culebra Substation 3801 and New Culebra Substation 3802 (Substation) | Substation | Vieques and Culebra Projects (6) | Yes | Obligated | 1282218 | 105202 | 522360 | 0 | 0 | 0 | 0 | 1909780 | 1804578 | 105202 | Pending Scope & Cost Completion by Applicant | 2022-06-10 11:48 | Obligated, Pending Scope & Cost Completion by Applicant | 44% | 1886396.25 | 926055.39 |  | 2812451.64 | -2685967.56 | 1538953.94 | 1267232.34 | 603858.08 | 681493.25 | 16046.1 | 488163.85 | 4595747.56 | 2158858.12 | 2436889.44 | Amendment – Submitted to COR3/PREPA | Submitted | Only existing substation is obligated
165225 | FAASt - EPC - Vieques 2501 substation repairs & New Vieques 2502 substation (Substation) | Substation | Vieques and Culebra Projects (6) | Yes | Obligated | 1209111 | 178309 | 531763 | 0 | 0 | 0 | 0 | 1919183 | 1740874 | 178309 | Pending Scope & Cost Completion by Applicant | 2022-06-10 11:48 | Obligated, Pending Scope & Cost Completion by Applicant | 2% | 2333876.59 | 144321.37 |  | 2478197.96 | -2983587.76 | 1479929.82 | 1291181.43 | 731583.82 | 878415.74 | 16046.1 | 505613.85 | 4902770.76 | 2227559.74 | 2675211.02 | Amendment – Submitted to COR3/PREPA | Submitted | Only existing substation is obligated
179558 | FAASt - Manatí TC - BRKS 230 kV - (Substation) | Substation | Substation Rebuilds | Yes | Obligated | 1593443 | 0 | 688917 | 0 | 0 | 0 | 0 | 2282360 | 2282360 | 0 | Obligated | 2022-05-26 11:24 | Obligated | 100% | 1006502.23 | 329663.3 |  | 1336165.53 | -284100.74 | 1564453.0618 | 238313.587 | 159091.5333 | 54214.3022 | 192536.3467 | 357851.909 | 2566460.74 | 1916080.9418 | 650379.7982 | Amendment – Submitted to COR3/PREPA | Submitted
743399 | FAASt [High Voltage Equipment Replacement - Group 3] (Substation) | Substation | Substation | Yes | Obligated | 17307539.01 | 0 | 2253322.97 | 0 | 0 | 0 | 0 | 19560861.98 | 19560861.98 | 0 | Obligated | 2024-08-26 10:08 | Obligated | 10% | 1215959.95 | 1477534.97 |  | 2693494.92 | 13983230.71 | 3917912.12 | 0 | 463572.76 | 0 | 1196146.39 | 0 | 5577631.27 | 5577631.27 | 0 | Amendment – Submitted to COR3/PREPA | Submitted | Scope does not include hazard mitigation. No reconciliation needed. Project is in execution; Amendment due to scope/cost changes submitted.
729286 | FAASt HV Equipment Replacement Group 2 (Substation) | Substation | Substation | Yes | Obligated | 15413889.89 | 0 | 2006783 | 0 | 0 | 0 | 0 | 17420672.89 | 17420672.89 | 0 | Obligated | 2024-07-08 11:28 | Obligated | 52% | 1743415.11 | 9109977.67 |  | 10853392.78 | 6998812.51 | 7320658.38 | 0 | 866190.39 | 0 | 2235011.61 | 0 | 10421860.38 | 10421860.38 | 0 | Amendment – Submitted to COR3/PREPA | Submitted | Scope does not include hazard mitigation. No reconciliation needed. Project is in execution; Amendment due to scope/cost changes submitted.
178503 | FAASt Aguirre TC - BKRS (Substations) | Substation | Substation Rebuilds | Yes | Obligated | 39034592 | 0 | 5171019 | 0 | 0 | 0 | 0 | 44205611 | 44205611 | 0 | Obligated | 2022-12-27 11:53 | Obligated | 33% | 4646057.03 | 9868755.21 |  | 14514812.24 | 934726.67 | 38926711.43 | 257069.07 | 4062989.94 | 24113.89 | 0 | 0 | 43270884.33 | 42989701.37 | 281182.96 | Amendment – Submitted to COR3/PREPA | Submitted
551925 | FAASt [SCADA Remote Access and RTU Replacements Group 1] (Telecommunication) | Telecommunication | IT/OT | Yes | Obligated | 5962412.52 | 1407196.27 | 1248409.19 | 294727.35 | 0 | 0 | 0 | 8912745.33 | 7210821.71 | 1701923.62 | Pending Amendment Request Approval | 2024-11-01 15:15 | Obligated, Pending Amendment Request Approval | 94% | 3719832.13 | 4281135.16 |  | 8000967.29 | -1837346.3467 | 7266305.24 | 1694442.12 | 1060764.2767 | 273088.36 | 264479.04 | 191012.64 | 10750091.6767 | 8591548.5567 | 2158543.12 | Amendment – Submitted to COR3/PREPA | Submitted | 428/206 split revised, 1 additional site was included in the submitted amendment.
657300 | FAASt ENERGY MANAGEMENT SYSTEM (EMS) (Telecom) | Telecommunication | IT/OT | Yes | Obligated | 164579862 | 0 | 2041312 | 0 | 0 | 0 | 0 | 166621174 | 166621174 | 0 | Pending Amendment Request Approval | 2022-10-17 11:37 | Obligated, Pending Amendment Request Approval | 95% | 15765664.41 | 9905570.55 |  | 25671234.96 | 96222493.21 | 36457328.36 | 28655579.63 | 2477105.02 | 1951041.22 | 443546.56 | 414080 | 70398680.79 | 39377979.94 | 31020700.85 | Amendment – Submitted to COR3/PREPA | Submitted | Amendment submitted Feb 12, 2026
668583 | FAASt Line 13300 GOAB 13301C to Hato Tejas Se | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 453597 | 0 | 81996 | 0 | 0 | 0 | 0 | 535593 | 535593 | 0 | Obligated | 2022-08-02 11:42 | Obligated | 91% | 280376.69 | 806314.48 |  | 1086691.17 | -251525.35 | 665239.4 | 2703.16 | 58708.55 | 918.24 | 51007.18 | 8541.82 | 787118.35 | 774955.13 | 12163.22 | Amendment – Submitted to COR3/PREPA | Submitted
334468 | FAASt Line 2200 Dos Bocas HP to Dorado TC (T | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 1217429 | 0 | 242850 | 0 | 0 | 0 | 0 | 1460279 | 1460279 | 0 | Pending Amendment Request Approval | 2022-07-13 21:08 | Obligated, Pending Amendment Request Approval | 93% | 1664354.71 | 1556989.94 |  | 3221344.65 | -244170.15 | 1528829.9 | 33717.27 | 129281.25 | 2827.08 | 9793.65 | 0 | 1704449.15 | 1667904.8 | 36544.35 | Amendment – Submitted to COR3/PREPA | Submitted
668592 | FAASt Line 9800 Bayamon TC - Guaraguao Sect | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 420866 | 0 | 43984 | 0 | 0 | 0 | 0 | 464850 | 464850 | 0 | Pending Amendment Request Approval | 2022-09-16 11:54 | Obligated, Pending Amendment Request Approval | 94% | 174616.04 | 389293.04 |  | 563909.08 | 21933.58 | 359543.38 | 5405.05 | 34734.97 | 698.02 | 39893.71 | 2641.29 | 442916.42 | 434172.06 | 8744.36 | Amendment – Submitted to COR3/PREPA | Submitted
551861 | FAASt [Physical Security - Group 3] (Substation) | Substation | Substation Security | Yes | Obligated | 3696956.6 | 436383.23 | 844836.71 | 0 | 0 | 0 | 0 | 4978176.54 | 4541793.31 | 436383.23 | Obligated | 2023-06-16 12:55 | Obligated | 48% | 456389.67 | 3255929.64 |  | 3712319.31 | 0 | 3696956.6 | 303177.29 | 844836.71 | 133205.94 | 0 | 0 | 4978176.54 | 4541793.31 | 436383.23 | Amendment – Submitted to COR3/PREPA | Submitted | E&M allocations not included in original obligation
550910 | FAASt Physical Security - Group 1 (Substatio | Substation | Substation Security | Yes | Obligated | 6025270.22 | 665958.96 | 1278327.97 | 0 | 0 | 0 | 0 | 7969557.15 | 7303598.19 | 665958.96 | Obligated | 2023-05-04 11:30 | Obligated | 81% | 2379891.36 | 8174673.94 |  | 10554565.3 | 0.01 | 6025270.22 | 463212.07 | 1278327.96 | 202746.89 | 0 | 0 | 7969557.14 | 7303598.18 | 665958.96 | Amendment – Submitted to COR3/PREPA | Submitted | E&M allocations not included in original obligation
542758 | FAASt Substation Minor Repairs -Group B (Substation) | Substation | Substation Rebuilds | Yes | Obligated | 2973035 | 425074 | 152806 | 14467 | 0 | 0 | 0 | 3565382 | 3125841 | 439541 | Obligated | 2023-07-07 11:35 | Obligated | 76% | 1096744.1 | 5242365.72 |  | 6339109.82 | -570509 | 2973035 | 302946 | 723315 | 136595 | 0 | 0 | 4135891 | 3696350 | 439541 | Amendment – Submitted to COR3/PREPA | Submitted | E&M allocations not included in original obligation
167446 | FAASt - Line 36100 (115kV) - Bayamon to Monacillos (Transmission) | Priority Transmission | Transmission Line Rebuild | Yes | Obligated | 33956314.58 | 0 | 3408229.98 | 0 | 85008 | 0 | 0 | 37449552.56 | 37449552.56 | 0 | Obligated | 2025-11-05 16:17 | Obligated | 0% | 9633230.75 | 1121278.11 |  | 10754508.86 | -1835213.1 | 18657617.56 | 10503244.02 | 1398471.71 | 1349494.84 | 2069637.1 | 5306300.43 | 39284765.66 | 22125726.37 | 17159039.29 | Amendment – Scope and Cost development in progress | Submitted
550950 | FAASt - EPC - [Monacillo TC] (Substations) | Priority Substation | Substation | Yes | Obligated | 58195134 | 0 | 6623439.52 | 0 | 42974192.2 | 0 | 0 | 107792765.72 | 107792765.72 | 0 | Obligated | 2023-12-19 12:23 | Obligated | 11% | 5935100.26 | 11153695.49 |  | 17088795.75 | -51373061.57 | 93729896.23 | 13188476.41 | 18252835.9 | 1706525.37 | 28961853.03 | 3326240.35 | 159165827.29 | 140944585.16 | 18221242.13 | Amendment – Submitted to FEMA | Submitted
723077 | FAASt - EPC - [Sabana Llana TC] (Substation) | Substation | Substation Rebuilds | Yes | Obligated | 46643078.39 | 0 | 4850983.03 | 0 | 57324983 | 0 | 0 | 108819044.42 | 108819044.42 | 0 | Obligated | 2023-12-19 12:23 | Obligated | 18% | 4845973.38 | 4170194.21 |  | 9016167.59 | -804452.22 | 63916173.58 | 8155710.69 | 5214828.56 | 730706.2 | 24860010.19 | 6746067.42 | 109623496.64 | 93991012.33 | 15632484.31 | Amendment – Pending Design Package for Development | Q4 FY2026
180052 | FAASt Ponce TC to Salinas Urbano TC- 38kV 100 & 200 (Transmission) | Priority Transmission | Transmission Line Rebuild | Yes | Obligated | 74520098.48 | 0 | 8369786.38 | 0 | 9413216.96 | 0 | 0 | 92303101.82 | 92303101.82 | 0 | Obligated | 2025-11-05 16:17 | Obligated | 0% | 5683411.48 | 71911.84 |  | 5755323.32 | -224896898.18 | 189214147.25 | 38650198.93 | 18683215.39 | 6899520.54 | 21880052.02 | 41872865.87 | 317200000 | 229777414.66 | 87422585.34 | Amendment – Scope and Cost development in progress | Q4 FY2026 | Currently undergoing redesign with updated scope
334470 | FAASt [TL 3100 Monacillos TC to Sabana Llana TC] (Transmission) | Priority Transmission | Transmission Line Rebuild | Yes | Obligated | 47112099.92 | 0 | 2747003.78 | 0 | 965924.9 | 0 | 0 | 50825028.6 | 50825028.6 | 0 | Obligated | 2025-11-05 16:17 | Obligated | 0% | 5865198.45 | 22693.38 |  | 5887891.83 | -8583988.24 | 35438292.75 | 7238872.38 | 3499216.45 | 1292224.88 | 4097958.32 | 7842452.06 | 59409016.84 | 43035467.52 | 16373549.32 | Amendment – Scope and Cost development in progress | Q4 FY2026 | Obligated for $47.1M, the expected total project cost is $54M
176913 | FAASt [Palo Seco SP to Catano Sect 38kV Line- 9500] (Transmission) | Priority Transmission | Transmission Line Rebuild | Yes | Obligated | 33526671.86 | 0 | 4657292.73 | 0 | 297862.88 | 0 | 0 | 38481827.47 | 38481827.47 | 0 | Obligated | 2025-11-05 16:17 | Obligated | 0% | 2663813.77 | 73599.62 |  | 2737413.39 | 3767517.03 | 29688455.53 | 656415.25 | 4164273.96 | 93674.84 | 96089.14 | 15401.72 | 34714310.44 | 33948818.63 | 765491.81 | Amendment – Scope and Cost development in progress | Q4 FY2026 | Obligated for $33.5M. The expected total project cost is $40.8M
176971 | FAASt –38kV Line 8200 - San Juan SP to Catano Sect Line (Transmission) | Priority Transmission | Transmission Line Rebuild | Yes | Obligated | 21670623.78 | 0 | 3124951.32 | 0 | 120403.36 | 0 | 0 | 24915978.46 | 24915978.46 | 0 | Obligated | 2025-11-05 16:17 | Obligated | 0% | 2172259.97 | 63133.09 |  | 2235393.06 | 926312.09 | 18028195.83 | 3833616.78 | 1664551.02 | 342899.38 | 118276.26 | 2127.1 | 23989666.37 | 19811023.11 | 4178643.26 | Amendment – Scope and Cost development in progress | Q4 FY2026
165268 | FAASt Rio Grande Estate Substation CH-2306 (Su | Substation | Substation Rebuilds | Yes | Obligated | 7098243.76 | 4585370.95 | 1391012.61 | 0 | 0 | 0 | 0 | 13074627.32 | 8489256.37 | 4585370.95 | Obligated | 2022-12-21 12:37 | Obligated | 93% | 4311264.88 | 7006384.18 |  | 11317649.06 | -32284335.32 | 10575737.82 | 5646415.07 | 1670755.76 | 1105969.75 | 15043028.3 | 11317055.94 | 45358962.64 | 27289521.88 | 18069440.76 | Amendment – Submitted to COR3/PREPA | Q4 FY2026 | Submit to COR3 on 02/27/2026
542762 | FAASt Distribution Pole and Conductor Repair – Arecibo Group 2 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 610448 | 157420 | 50794 | 0 | 0 | 0 | 0 | 818662 | 661242 | 157420 | Obligated | 2022-06-03 11:23 | Obligated | 97% | 140629.4 | 329617.6 |  | 470247 | -5827066 | 4984296 | 531658.24 | 332286.4 | 132914.56 | 332286.4 | 332286.4 | 6645728 | 5648868.8 | 996859.2 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
723078 | FAASt - EPC - [San Juan SP TC] (Substation) | Substation | Substation Rebuilds | Yes | Obligated | 61558468.95 | 0 | 3713096.54 | 0 | 0 | 0 | 0 | 65271565.49 | 65271565.49 | 0 | Obligated | 2023-12-19 12:23 | Obligated | 2% | 2728423.27 | 95853.36 |  | 2824276.63 | -31635743.4 | 41692705.96 | 18968379.24 | 4167397.2 | 2030397.52 | 19295213.53 | 10753215.44 | 96907308.89 | 65155316.69 | 31751992.2 | Amendment – Scope and Cost development in progress | Q4 FY2026
682121 | FAASt - EPC -Aguirre TC-Phase II (Substation) | Substation | Substation Rebuilds | Yes | Obligated | 82726096.38 | 0 | 7789677 | 0 | 0 | 0 | 0 | 90515773.38 | 90515773.38 | 0 | Obligated | 2024-03-22 10:16 | Obligated | 4% | 4856917.02 | 5613354.26 |  | 10470271.28 | -31120792.57 | 76051918.2725 | 3432327.8875 | 7365108.11 | 326910.77 | 33047353.6975 | 1412947.2125 | 121636565.95 | 116464380.08 | 5172185.87 | Amendment – Scope and Cost development in progress | Q4 FY2026 | scope to be revised
682834 | FAASt [EPC - Costa Sur TC - Phase II & III ] (Substation) | Priority Substation | Substation | Yes | Obligated | 36917510 | 0 | 5090347.22 | 0 | 30357996.36 | 5151836 | 1 | 77517689.58 | 72365853.58 | 5151836 | Obligated | 2024-02-13 12:36 | Obligated | 1% | 4559202.8 | 1760103.26 |  | 6319306.06 | -1345002.27 | 36917509.58 | 0 | 6435349.91 | 0 | 35509832.36 | 0 | 78862691.85 | 78862691.85 | 0 | Amendment – Scope and Cost development in progress | Q4 FY2026
757687 | FAASt [Automation Program Group 22] (Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 2356733.87 | 0 | 359230.44 | 0 | 412012.16 | 0 | 0 | 3127976.47 | 3127976.47 | 0 | Obligated | 2025-10-30 20:15 | Obligated | 11% | 214384.9 | 598636.59 |  | 813021.49 | -98902.71 | 1488484.9 | 1318276.22 | 169367.15 | 153103.22 | 44894.57 | 52753.12 | 3226879.18 | 1702746.62 | 1524132.56 | Amendment – Amendment Needed/Pending Development | Q4 FY2026 | 406HM Revision to be submitted May 2026/ Estimated date Cfci strategy to be defined
800286 | FAASt [Automation Program Group 36] (TL / Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 1703713 | 0 | 300364.95 | 0 | 230628.16 | 342399.24 | 1 | 2577105.35 | 2234706.11 | 342399.24 | Pending EHP Review | 2025-09-17 19:15 | Obligated, Pending EHP Review | 26% | 268286.3 | 861684.63 |  | 1129970.93 | -633987.3362 | 1427638.4262 | 995016.61 | 137043.707 | 78366.543 | 175789.83 | 397237.57 | 3211092.6862 | 1740471.9632 | 1470620.723 | Amendment – Submitted to FEMA | Submitted | 406HM Revision Pending Award in GP / Estimated date Cfci strategy to be defined
745861 | FAASt [Automation Program Group 12] (TL/Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 3664210.1 | 0 | 477953.55 | 0 | 228785.14 | 557322.86 | 1 | 4928271.65 | 4370948.79 | 557322.86 | Pending PDMG Scope & Cost Routing | 2025-02-06 20:16 | Obligated, Pending PDMG Scope & Cost Routing | 76% | 528755.13 | 1584522.77 |  | 2113277.9 | 321124.91 | 2181157.9 | 1341922.17 | 200395.78 | 97562.89 | 228547.36 | 557560.64 | 4607146.74 | 2610101.04 | 1997045.7 | Amendment – Submitted to FEMA | Submitted | 406HM Revision Pending Award in GP / Estimated date Cfci strategy to be defined
745856 | FAASt [Automation Program Group 14] (TL/Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 1640186.96 | 0 | 208604.89 | 0 | 148295.58 | 442571.92 | 1 | 2439659.35 | 1997087.43 | 442571.92 | Pending FEMA 406 HMP Completion | 2025-02-06 20:16 | Obligated, Pending FEMA 406 HMP Completion | 92% | 447795.88 | 1125897.42 |  | 1573693.3 | -740396.03 | 1410445.2 | 1001406.99 | 112272.97 | 65062.72 | 148295.58 | 442571.92 | 3180055.38 | 1671013.75 | 1509041.63 | Amendment – Submitted to FEMA | Submitted | 406HM Revision Pending Award in GP / Estimated date Cfci strategy to be defined
674096 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 6] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 1773428 | 318852 | 332705 | 0 | 0 | 0 | 0 | 2424985 | 2106133 | 318852 | Obligated | 2022-10-17 11:37 | Obligated | 88% | 323173.77 | 1878900.17 |  | 2202073.94 | -6649206.29 | 7579644.48 | 2302.03 | 706904.78 | 1475.8 | 768737.4 | 15126.8 | 9074191.29 | 9055286.66 | 18904.63 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
169500 | FAASt [Bayamon TC - MC-BKRS-Y1] (Substation) | Substation | Substation Rebuilds | Yes | Obligated | 2796182 | 3575881 | 634046 | 0 | 0 | 0 | 0 | 7006109 | 3430228 | 3575881 | Obligated | 2023-06-16 12:55 | Obligated | 44% | 1795011.09 | 6090723.65 |  | 7885734.74 | -4196253.37 | 6828692.0723 | 1040216.6366 | 694419.7424 | 236640.3857 | 840403.2415 | 1561990.2915 | 11202362.37 | 8363515.0562 | 2838847.3138 | Amendment – Amendment Needed/Pending Development | Q4 FY2026 | estimate under review
755211 | FAASt [Automation Program Group 15] (Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 276277.77 | 127858.88 | 110225.14 | 19875.89 | 53139.71 | 103164.29 | 0 | 690541.68 | 439642.62 | 250899.06 | Pending Award | 2025-02-06 20:16 | Obligated, Pending Award | 72% | 164033.11 | 334487.39 |  | 498520.5 | -39863.2086 | 276277.7686 | 249580.66 | 29684.97 | 18557.49 | 53139.71 | 103164.29 | 730404.8886 | 359102.4486 | 371302.44 | Amendment – Submitted to FEMA | Submitted | 406HM Revision Pending Award in GP / Estimated date Cfci strategy to be defined
682136 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 9] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 469650.95 | 84576.1 | 90259.5 | 11377.95 | 0 | 0 | 0 | 655864.5 | 559910.45 | 95954.05 | Obligated | 2023-01-31 12:56 | Obligated | 95% | 158107.78 | 467050.89 |  | 625158.67 | -0.5 | 469650.95 | 75853 | 90260 | 20101.05 | 0 | 0 | 655865 | 559910.95 | 95954.05 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
701552 | FAASt [Pole and Conductor Repair - Ponce Group 12] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 186321 | 51841 | 36670 | 0 | 0 | 0 | 0 | 274832 | 222991 | 51841 | Obligated | 2023-03-08 12:36 | Obligated | 90% | 89899.68 | 162935.82 |  | 252835.5 | 34349.84 | 186321 | 40981 | 36670 | 10860 | 0 | 0 | 240482.16 | 222991 | 51841 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
673795 | FAASt Distribution Pole and Conductor Repair - Mayaguez Group 4 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 1425163 | 368954 | 278116 | 0 | 0 | 0 | 0 | 2072233 | 1703279 | 368954 | Obligated | 2022-08-02 11:42 | Obligated | 89% | 488162.33 | 1538561.48 |  | 2026723.81 | -8316728.24 | 8687329.99 | 35434.35 | 773151.6 | 23427.4 | 622940.21 | 246677.69 | 10388961.24 | 10083421.8 | 305539.44 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
742070 | FAASt [Pole and Conductor Repair - San Juan Group 1 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 5461200.05 | 205587.38 | 491326.68 | 0 | 0 | 0 | 0 | 6158114.11 | 5952526.73 | 205587.38 | Obligated | 2024-06-18 11:28 | Obligated | 85% | 835781.06 | 4520957.11 |  | 5356738.17 | -0.32 | 5461200.05 | 170555 | 491327 | 35032.38 | 0 | 0 | 6158114.43 | 5952527.05 | 205587.38 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
334488 | FAASt [Distribution Pole and Conductor Repair – Caguas Group 4 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 142917 | 10826 | 11465 | 0 | 0 | 0 | 0 | 165208 | 154382 | 10826 | Obligated | 2022-05-26 11:24 | Obligated | 88% | -65994.48 | 126934.57 |  | 60940.09 | -4485668.32 | 3882564.66 | 6767.3 | 361458.25 | 1409.37 | 388789.38 | 9887.36 | 4650876.32 | 4632812.29 | 18064.03 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
685943 | FAASt Distribution Pole and Conductor Repair Ponce Group 5(Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 254972.22 | 55758.8 | 49774.2 | 7501.2 | 0 | 0 | 0 | 368006.42 | 304746.42 | 63260 | Obligated | 2023-01-10 13:19 | Obligated | 88% | 72531.62 | 271120.98 |  | 343652.6 | 0.2 | 254972.22 | 50008 | 49774 | 13252 | 0 | 0 | 368006.22 | 304746.22 | 63260 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
674072 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 1] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 872891 | 238203 | 171585 | 0 | 0 | 0 | 0 | 1282679 | 1044476 | 238203 | Obligated | 2022-09-16 11:54 | Obligated | 88% | 215800.09 | 1030475.62 |  | 1246275.71 | 0 | 872891 | 188303 | 171585 | 49900.3 | 0 | 0 | 1282679 | 1044476 | 238203.3 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
673818 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 1] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 621804 | 171614 | 121044 | 0 | 0 | 0 | 0 | 914462 | 742848 | 171614 | Obligated | 2022-08-08 11:30 | Obligated | 87% | 165605.97 | 755603.04 |  | 921209.01 | 0 | 621804 | 135633 | 121044 | 35951 | 0 | 0 | 914462 | 742848 | 171584 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
711856 | FAASt [Pole and Conductor Repair - Bayamon Group 3 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 10940320.91 | 395663.43 | 891093.89 | 0 | 0 | 0 | 0 | 12227078.23 | 11831414.8 | 395663.43 | Obligated | 2024-08-26 10:08 | Obligated | 89% | 1268583.26 | 9051973.61 |  | 10320556.87 | -0.11 | 10940320.91 | 328412 | 891094 | 67251.43 | 0 | 0 | 12227078.34 | 11831414.91 | 395663.43 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
682890 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 12] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 510067.96 | 90178.97 | 98275.6 | 12131.7 | 0 | 0 | 0 | 710654.23 | 608343.56 | 102310.67 | Obligated | 2022-12-27 11:53 | Obligated | 88% | 90359.9 | 549372.52 |  | 639732.42 | -0.4 | 510067.96 | 80878 | 98276 | 21432.67 | 0 | 0 | 710654.63 | 608343.96 | 102310.67 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
708579 | FAASt [Pole and Conductor Repair - Ponce Group 16, 17, 18 & 19] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 1764568.92 | 389437.84 | 343118.15 | 0 | 0 | 0 | 0 | 2497124.91 | 2107687.07 | 389437.84 | Obligated | 2023-10-23 11:32 | Obligated | 89% | 306154.73 | 2211544.17 |  | 2517698.9 | 0.15 | 1764568.92 | 307856 | 343118 | 81581.84 | 0 | 0 | 2497124.76 | 2107686.92 | 389437.84 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
685370 | FAASt [Pole and Conductor Repair - Mayagüez Group 8] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 68823 | 13209 | 13127 | 1777 | 0 | 0 | 0 | 96936 | 81950 | 14986 | Obligated | 2023-01-10 13:19 | Obligated | 100% | 27864.95 | 50766.55 |  | 78631.5 | 0 | 68823 | 11847 | 13127 | 3139 | 0 | 0 | 96936 | 81950 | 14986 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
178258 | FAASt - [Taft - MC 1105] (Substations) | Substation | Substation | Yes | Obligated | 9362729.93 | 3620255.01 | 1302381.39 | 503587.39 | 0 | 0 | 0 | 14788953.72 | 10665111.32 | 4123842.4 | Obligated | 2025-02-06 20:16 | Obligated | 0% | 1737998.31 | 10073.34 |  | 1748071.65 | 0 | 9014992.3462 | 1373256.3891 | 916747.8334 | 312404.0802 | 1109469.9702 | 2062083.1008 | 14788953.72 | 11041210.1499 | 3747743.5701 | DSOW – Scope and Cost development in progress | Q1 FY2027
169266 | FAASt Centro Medico 1327/1359 (Substattion) Rebuilt | Substation | Substation Rebuilds | Yes | Obligated | 14795324 | 6537037 | 1810918 | 0 | 0 | 0 | 0 | 23143279 | 16606242 | 6537037 | Obligated | 2023-11-03 11:30 | Obligated | 5% | 4401854.33 | 1079731.32 |  | 5481585.65 | -5999230.8 | 12202124 | 7130202 | 3317753 | 1306032 | 2593199.4 | 2593199.4 | 29142509.8 | 18113076.4 | 11029433.4 | Amendment – Amendment Needed/Pending Development | Q4 FY2026
674098 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 7] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 84433 | 23322 | 16517 | 0 | 0 | 0 | 0 | 124272 | 100950 | 23322 | Obligated | 2022-08-08 11:30 | Obligated | 100% | 20781.84 | 98678.17 |  | 119460.01 | -6633339.3 | 5641956.19 | 3297.53 | 528429.47 | 2122.11 | 560196.28 | 21609.72 | 6757611.3 | 6730581.94 | 27029.36 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
546370 | FAASt - Substation Minor Repairs Group A (Subs | Substation | Substation Rebuilds | Yes | Obligated | 4482972.51 | 488202.58 | 996359.11 | 0 | 0 | 0 | 0 | 5967534.2 | 5479331.62 | 488202.58 | Obligated | 2024-02-13 12:36 | Obligated | 71% | 2841572.68 | 3200923.86 |  | 6042496.54 | 0 | 4482972.51 | 333712.07 | 996359.11 | 154490.51 | 0 | 0 | 5967534.2 | 5479331.62 | 488202.58 | Amendment – Amendment Needed/Pending Development | Q4 FY2026 | E&M allocations not included in original obligation
549764 | FAASt Physical Security - Group 2 (Substation) | Substation | Substation Security | Yes | Obligated | 2159012.31 | 224680.68 | 529771.49 | 0 | 0 | 0 | 0 | 2913464.48 | 2688783.8 | 224680.68 | Obligated | 2023-06-16 12:55 | Obligated | 85% | 282253.1 | 1930999.02 |  | 2213252.12 | 0 | 2159012.31 | 150511.17 | 529771.49 | 74169.51 | 0 | 0 | 2913464.48 | 2688783.8 | 224680.68 | Amendment – Amendment Needed/Pending Development | Q4 FY2026 | E&M allocations not included in original obligation
546371 | FAASt- Substation Minor Repairs Group C (Substation) | Substation | Substation Rebuilds | Yes | Obligated | 2648259.06 | 384632.14 | 173985.91 | 0 | 0 | 0 | 0 | 3206877.11 | 2822244.97 | 384632.14 | Obligated | 2023-08-22 11:21 | Obligated | 76% | 2233567.02 | 2261047.96 |  | 4494614.98 | -472487.25 | 2648259.06 | 262056.28 | 646473.16 | 122575.86 | 0 | 0 | 3679364.36 | 3294732.22 | 384632.14 | Amendment – Amendment Needed/Pending Development | Q4 FY2026 | E&M allocations not included in original obligation
738120 | FAASt [Pole and Conductor Repair-Carolina Group 2- Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 11041271 | 409899.81 | 1159111 | 0 | 0 | 0 | 0 | 12610281.81 | 12200382 | 409899.81 | Obligated | 2024-11-25 16:15 | Obligated | 74% | 951515.73 | 9855303.54 |  | 10806819.27 | 0 | 11041271 | 234531 | 1159111 | 175368.81 | 0 | 0 | 12610281.81 | 12200382 | 409899.81 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
673774 | FAASt [Distribution Pole and Conductor Repair - Mayaguez Group 1] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 1408531 | 358420 | 273831 | 0 | 0 | 0 | 0 | 2040782 | 1682362 | 358420 | Obligated | 2022-08-02 11:42 | Obligated | 62% | 660694.74 | 2989558.68 |  | 3650253.42 | 0 | 1408531 | 283336 | 273831 | 75084 | 0 | 0 | 2040782 | 1682362 | 358420 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
691246 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 10] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 211622.76 | 33717.31 | 41363.6 | 0 | 0 | 0 | 0 | 286703.67 | 252986.36 | 33717.31 | Obligated | 2023-02-16 12:51 | Obligated | 88% | 91014.29 | 321416.31 |  | 412430.6 | -0.4 | 211622.76 | 26654 | 41364 | 7063.31 | 0 | 0 | 286704.07 | 252986.76 | 33717.31 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
701679 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 12] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 64425.44 | 16226.16 | 12535.35 | 0 | 0 | 0 | 0 | 93186.95 | 76960.79 | 16226.16 | Obligated | 2023-03-02 12:24 | Obligated | 67% | 41673.73 | 155431.67 |  | 197105.4 | 0.35 | 64425.44 | 12827 | 12535 | 3399.16 | 0 | 0 | 93186.6 | 76960.44 | 16226.16 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
679025 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 4] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 243073 | 48970 | 46884 | 6588 | 0 | 0 | 0 | 345515 | 289957 | 55558 | Obligated | 2022-12-27 11:53 | Obligated | 80% | 72104.52 | 383640.71 |  | 455745.23 | 0 | 243073 | 43919 | 46884 | 11639 | 0 | 0 | 345515 | 289957 | 55558 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
679026 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 5] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 483786 | 93880 | 93451 | 12630 | 0 | 0 | 0 | 683747 | 577237 | 106510 | Obligated | 2022-12-27 11:53 | Obligated | 78% | 120986.82 | 832611.89 |  | 953598.71 | 0 | 483786 | 84198 | 93451 | 22312 | 0 | 0 | 683747 | 577237 | 106510 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
682870 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 6] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 85921.77 | 17491 | 16716.65 | 0 | 0 | 0 | 0 | 120129.42 | 102638.42 | 17491 | Obligated | 2022-12-27 11:53 | Obligated | 89% | 36653.1 | 109637.54 |  | 146290.64 | -0.35 | 85921.77 | 13827 | 16717 | 3664 | 0 | 0 | 120129.77 | 102638.77 | 17491 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
682865 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 7] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 70683 | 18640 | 13377 | 2508 | 0 | 0 | 0 | 105208 | 84060 | 21148 | Obligated | 2022-12-27 11:53 | Obligated | 82% | 54416.25 | 96220.44 |  | 150636.69 | 0 | 70683 | 16718 | 13377 | 4430 | 0 | 0 | 105208 | 84060 | 21148 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
704755 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 12-13-14] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 438209.69 | 86181.92 | 83450.9 | 0 | 0 | 0 | 0 | 607842.51 | 521660.59 | 86181.92 | Obligated | 2023-05-17 11:31 | Obligated | 84% | 132475.69 | 682254.48 |  | 814730.17 | -0.1 | 438209.69 | 68128 | 83451 | 18053.92 | 0 | 0 | 607842.61 | 521660.69 | 86181.92 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
678985 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 4] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 353628 | 54317.84 | 66915 | 0 | 0 | 0 | 0 | 474860.84 | 420543 | 54317.84 | Obligated | 2022-12-27 11:53 | Obligated | 79% | 231240.45 | 582969.79 |  | 814210.24 | 0 | 353628 | 42939 | 66915 | 11378.84 | 0 | 0 | 474860.84 | 420543 | 54317.84 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
689071 | FAASt [Pole and Conductor Repair - Arecibo Group 11] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 59545.08 | 17491.16 | 11878.8 | 0 | 0 | 0 | 0 | 88915.04 | 71423.88 | 17491.16 | Obligated | 2023-03-02 12:24 | Obligated | 90% | 46699.71 | 86667.36 |  | 133367.07 | -0.04 | 59545.08 | 13827 | 11879 | 3664 | 0 | 0 | 88915.08 | 71424.08 | 17491 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
712968 | FAASt [Pole and Conductor Repair - Arecibo Group 2 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 5629060 | 178712.97 | 503550 | 0 | 0 | 0 | 0 | 6311322.97 | 6132610 | 178712.97 | Obligated | 2024-11-01 15:15 | Obligated | 84% | 623754.39 | 5707876.02 |  | 6331630.41 | -1 | 5629060 | 1482809 | 503551 | 35903.97 | 0 | 0 | 6311323.97 | 6132611 | 1518712.97 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
686471 | FAASt [Pole and Conductor Repair - Arecibo Group 5] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 250906 | 68700 | 49227 | 0 | 0 | 0 | 0 | 368833 | 300133 | 68700 | Obligated | 2022-12-27 11:53 | Obligated | 97% | 71386.99 | 366264.62 |  | 437651.61 | -26782 | 250906 | 54308 | 49227 | 14392 | 0 | 0 | 395615 | 300133 | 68700 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
685477 | FAASt [Pole and Conductor Repair - Arecibo Group 6] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 355178 | 51390 | 67123 | 6914 | 0 | 0 | 0 | 480605 | 422301 | 58304 | Obligated | 2023-01-24 13:14 | Obligated | 81% | 114176.28 | 335523.79 |  | 449700.07 | 16507.13 | 355178 | 46090 | 67123 | 12214 | 0 | 0 | 464097.87 | 422301 | 58304 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
682180 | FAASt [Pole and Conductor Repair - Mayagüez Group 10] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 43374 | 9720 | 8414 | 1308 | 0 | 0 | 0 | 62816 | 51788 | 11028 | Obligated | 2023-01-10 13:19 | Obligated | 51% | 46554.55 | 92462.07 |  | 139016.62 | 0 | 43374 | 8718 | 8414 | 2310 | 0 | 0 | 62816 | 51788 | 11028 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
686453 | FAASt [Pole and Conductor Repair - Mayagüez Group 7] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 20584 | 4995 | 4059 | 0 | 0 | 0 | 0 | 29638 | 24643 | 4995 | Obligated | 2022-12-27 11:53 | Obligated | 100% | 17941.39 | 30346.2 |  | 48287.59 | 0 | 20584 | 3949 | 4059 | 1046 | 0 | 0 | 29638 | 24643 | 4995 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
742026 | FAASt [Pole and Conductor Repair - San Juan Group 2 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 1033375.81 | 84035.96 | 83942.74 | 0 | 0 | 0 | 0 | 1201354.51 | 1117318.55 | 84035.96 | Obligated | 2024-05-31 11:36 | Obligated | 85% | 307412.33 | 1460594.04 |  | 1768006.37 | -0.26 | 1033375.81 | 68618 | 83943 | 15418.96 | 0 | 0 | 1201354.77 | 1117318.81 | 84036.96 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
698579 | FAASt [Distribution Streetlighting - Orocovis] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 8070964.96 | 1339801.28 | 1873982.08 | 0 | 0 | 0 | 0 | 11284748.32 | 9944947.04 | 1339801.28 | Obligated | 2024-03-22 10:16 | Obligated | 57% | 532947.21 | 8580713.74 |  | 9113660.95 | 0.08 | 8070964.96 | 925633.77 | 1873982 | 414167.51 | 0 | 0 | 11284748.24 | 9944946.96 | 1339801.28 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
698511 | FAASt [Culebra Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 1155804 | 153603 | 476440 | 0 | 0 | 0 | 0 | 1785847 | 1632244 | 153603 | Obligated | 2024-04-12 11:19 | Obligated | 83% | 184307.82 | 1050819.19 |  | 1235127.01 | 1 | 1155804 | 91406 | 476439 | 62197 | 0 | 0 | 1785846 | 1632243 | 153603 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
660239 | FAASt Streetlighting - Villalba (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 10190536.05 | 681865.66 | 2630718.61 | 0 | 0 | 0 | 0 | 13503120.32 | 12821254.66 | 681865.66 | Obligated | 2022-08-24 10:30 | Obligated | 89% | 1435736.35 | 13431081.73 |  | 14866818.08 | 0.0011475 | 10190536.0518 | 497349.58 | 2630718.608 | 84516.08 | 0 | 0 | 13503120.3189 | 12821254.6598 | 581865.66 | Amendment – Amendment Needed/Pending Development | Q2 FY2027 | Amendment pending to remove underground scope
738971 | FAASt [Pole and Conductor Repair - Caguas Group 2 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 13884126 | 343580.67 | 1643630 | 33543 | 0 | 0 | 0 | 15904879.67 | 15527756 | 377123.67 | Obligated | 2025-02-06 20:16 | Obligated | 70% | 1300738.16 | 12798397.58 |  | 14099135.74 | 0 | 13884126 | 310288 | 1643630 | 66835.67 | 0 | 0 | 15904879.67 | 15527756 | 377123.67 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
674088 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 3] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 1412368 | 289653 | 267370 | 0 | 0 | 0 | 0 | 1969391 | 1679738 | 289653 | Obligated | 2022-10-17 11:37 | Obligated | 88% | 293717.97 | 1756692.85 |  | 2050410.82 | -18719118.06 | 17238816.15 | 68279.82 | 1579773.97 | 43968.92 | 1309700 | 447970.2 | 20688509.06 | 20128290.12 | 560218.94 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
674092 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 5] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 441308 | 90422 | 82578 | 0 | 0 | 0 | 0 | 614308 | 523886 | 90422 | Obligated | 2022-09-16 11:54 | Obligated | 78% | 156813.86 | 934302.88 |  | 1091116.74 | -8625373.55 | 7714746.94 | 2136.3 | 719754.49 | 1369.92 | 787627.58 | 14046.32 | 9239681.55 | 9222129.01 | 17552.54 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
673775 | FAASt [Distribution Pole and Conductor Repair - Mayaguez Group 3] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 3575454.81 | 857193.1 | 689888.45 | 0 | 0 | 0 | 0 | 5122536.36 | 4265343.26 | 857193.1 | Obligated | 2022-12-27 11:53 | Obligated | 89% | 990297.73 | 5471574.2 |  | 6461871.93 | -13389661.1 | 15534571.38 | 65783.22 | 1378411.7 | 41393.16 | 1059507.72 | 432530.28 | 18512197.46 | 17972490.8 | 539706.66 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
673844 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 3] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 1072850.98 | 319213.9 | 208800.58 | 0 | 0 | 0 | 0 | 1600865.46 | 1281651.56 | 319213.9 | Obligated | 2022-08-24 10:30 | Obligated | 87% | 317413.67 | 1302232.74 |  | 1619646.41 | 1313662.49 | 243833.22 | 919.39 | 21435.45 | 574.91 | 14432.64 | 6007.36 | 287202.97 | 279701.31 | 7501.66 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
673843 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 3] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 904194 | 227661 | 175796 | 0 | 0 | 0 | 0 | 1307651 | 1079990 | 227661 | Obligated | 2022-10-17 11:37 | Obligated | 80% | 365075.68 | 2165876.07 |  | 2530951.75 | 0 | 904194 | 179969 | 175796 | 47692 | 0 | 0 | 1307651 | 1079990 | 227661 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
673847 | FAASt [Distribution Pole and Conductor Repair-Carolina Group 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 190570 | 49943 | 37242 | 0 | 0 | 0 | 0 | 277755 | 227812 | 49943 | Obligated | 2022-08-08 11:30 | Obligated | 78% | 192227.38 | 782333.98 |  | 974561.36 | 0 | 190570 | 39481 | 37242 | 10468 | 0 | 0 | 277755 | 227812 | 49949 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
673848 | FAASt [Distribution Pole and Conductor Repair-Carolina Group 3] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 43725 | 5620 | 13281 | 0 | 0 | 0 | 0 | 62626 | 57006 | 5620 | Obligated | 2022-07-12 11:39 | Obligated | 56% | 42133.88 | 88774.55 |  | 130908.43 | -2385775.19 | 2046324.94 | 9000.11 | 182160.96 | 5677.18 | 145915.26 | 59322.74 | 2448401.19 | 2374401.16 | 74000.03 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
710099 | FAASt [Pole and Conductor Repair - Arecibo Group 1 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 6704421.69 | 196450 | 602047.2 | 42926.93 | 0 | 0 | 0 | 7545845.82 | 7306468.89 | 239376.93 | Obligated | 2025-01-07 23:15 | Obligated | 93% | 620432.5 | 6843231.06 |  | 7463663.56 | 0.2 | 6704421.69 | 196450 | 602047 | 42926.93 | 0 | 0 | 7545845.62 | 7306468.69 | 239376.93 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
710094 | FAASt [Pole and Conductor Repair - Bayamon Group 1 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 7096249.5 | 195136.32 | 614123.07 | 0 | 0 | 0 | 0 | 7905508.89 | 7710372.57 | 195136.32 | Obligated | 2024-11-01 15:15 | Obligated | 71% | 482312.1 | 5390539.06 |  | 5872851.16 | 0.07 | 7096249.5 | 165571 | 614123 | 29565.32 | 0 | 0 | 7905508.82 | 7710372.5 | 195136.32 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
682172 | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 8] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 208400 | 50833.35 | 40930 | 6838 | 0 | 0 | 0 | 307001.35 | 249330 | 57671.35 | Obligated | 2023-01-24 13:14 | Obligated | 83% | 126286.86 | 321669.19 |  | 447956.05 | -50575.65 | 208400 | 45590 | 40930 | 12081.35 | 0 | 0 | 357577 | 249330 | 57671.35 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
682898 | FAASt [Distribution Pole and Conductor Repair - Bayamón Group 6] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 635326.93 | 95810.84 | 120284.25 | 12889.35 | 0 | 0 | 0 | 864311.37 | 755611.18 | 108700.19 | Obligated | 2023-01-24 13:14 | Obligated | 89% | 140664.37 | 908311.94 |  | 1048976.31 | 51029.09 | 635326.93 | 85929 | 120284 | 22771.19 | 0 | 0 | 813282.28 | 755610.93 | 108700.19 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
682910 | FAASt [Distribution Pole and Conductor Repair - Bayamón Group 7] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 517156 | 93137 | 99229 | 12530 | 0 | 0 | 0 | 722052 | 616385 | 105667 | Obligated | 2023-01-31 12:56 | Obligated | 97% | 123441.5 | 642298.78 |  | 765740.28 | 7183 | 517156 | 83531 | 99229 | 22135.72 | 0 | 0 | 714869 | 616385 | 105666.72 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
542690 | FAASt Maunabo Streetlighting (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 6199877.07 | 243880.33 | 1530438.49 | 0 | 0 | 0 | 0 | 7974195.89 | 7730315.56 | 243880.33 | Obligated | 2022-05-05 11:20 | Obligated | 95% | 688794.98 | 4580838.2 |  | 5269633.18 | -1530438.4926 | 7730315.5622 | 179642 | 1530438.4909 | 64238 | 0 | 0 | 9504634.3826 | 9260754.0531 | 243880 | Amendment – Amendment Needed/Pending Development | Q4 FY2026 | Amendment pending to remove underground scope Grants portal total project cost is $7.9M
956353 | FAASt [Arecibo Region 2 Line 36100 – Dos Bocas HP to Barrio Pina] (Vegetation) | Vegetation | Vegetation-TL | Yes | Obligated | 3756065 | 0 | 116166.96 | 0 | 0 | 0 | 0 | 3872231.96 | 3872231.96 | 0 | Obligated | 2025-09-17 18:16 | Obligated | 0% | 36905.68 | 16034.81 |  | 52940.49 | 1689554.33 | 493168.61 | 1670722.97 | 4283.23 | 14502.82 | 0 | 0 | 2182677.63 | 497451.84 | 1685225.79 | Amendment – Submitted to FEMA | Submitted | Total submitted estimated project cost is $17,938,929.50, however only 10.54/30.97 miles were obligated by FEMA. Total obligated cost from FEMA reflected. Obligated portion of project is currently in execution.
956342 | FAASt [Arecibo Region 2 Line 36400 – Ponce TC to Dos Bocas HP] (Vegetation) | Vegetation | Vegetation-TL | Yes | Obligated | 4093248 | 0 | 126595.31 | 0 | 0 | 0 | 0 | 4219843.31 | 4219843.31 | 0 | Obligated | 2025-09-17 18:16 | Obligated | 0% | 11291.92 | 0 |  | 11291.92 | 4096.18 | 952531.08 | 3226919.92 | 8275.53 | 28020.6 | 0 | 0 | 4215747.13 | 960806.61 | 3254940.52 | Amendment – Submitted to FEMA | Submitted | Total submitted estimated project cost is $21,304,288.88, however only 11.48/36.78 miles were obligated by FEMA. Total obligated cost from FEMA reflected. Obligated portion of project is currently in execution.
334527 | FAASt [Distribution Pole and Conductor Repair – Caguas Group 8 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 108847 | 14874 | 8540 | 0 | 0 | 0 | 0 | 132261 | 117387 | 14874 | Obligated | 2022-06-10 11:48 | Obligated | 97% | 50102.81 | 44077.66 |  | 94180.47 | -2369522.29 | 2083897.82 | 821.8 | 197576.9 | 535.27 | 213549.07 | 5402.43 | 2501783.29 | 2495023.79 | 6759.5 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
825843 | FAASt [Guanica TC] (Substation) | Priority Substation | Substation | Yes | Obligated | 2320373.96 | 0 | 826981.13 | 0 | 4200723.52 | 0 | 0 | 7348078.61 | 7348078.61 | 0 | Obligated | 2025-09-22 16:15 | Obligated | 10% | 26409.69 | 123299.14 |  | 149708.83 | 0 | 2320373.96 | 0 | 826981.13 | 0 | 4200723.52 | 0 | 7348078.61 | 7348078.61 | 0 | Amendment – Amendment Needed/Pending Development | Q4 FY2026
957578 | FAASt [Costa Sur TC Underground Cable Failure Replacement on Transformer Lead Bank #2] (Substation) | Substation | Substation | Yes | Obligated | 1108990 | 0 | 141856.25 | 0 | 0 | 0 | 0 | 1250846.25 | 1250846.25 | 0 | Obligated | 2025-09-17 19:15 | Obligated | 0% | 4909.66 | 4556.83 |  | 9466.49 | -440647.6 | 1031094.1802 | 157066.8744 | 104853.484 | 35731.3702 | 126896.1731 | 235851.7681 | 1691493.85 | 1262843.8373 | 428650.0127 | Amendment – Amendment Needed/Pending Development | Q4 FY2026 | scope and estimate to be revised
956593 | FAASt [Factor Sect 8014 Transformer Replacement] (Substation) | Substation | Substation | Yes | Obligated | 3751193.63 | 0 | 414861.11 | 0 | 1741264.87 | 0 | 0 | 5907319.61 | 5907319.61 | 0 | Obligated | 2025-09-22 16:15 | Obligated | 20% | 218717.81 | 372387.71 |  | 591105.52 | 0 | 3600960.6953 | 548535.3833 | 366186.9904 | 124787.1069 | 443168.1805 | 823681.2536 | 5907319.61 | 4410315.8663 | 1497003.7437 | Obligated -No expected changes | N/A
682645 | FAASt [Maunabo TC] (Substation) | Substation | Substation | Yes | Obligated | 8292125 | 0 | 1605121.68 | 0 | 4724211.98 | 0 | 0 | 14621458.66 | 14621458.66 | 0 | Obligated | 2025-09-17 18:16 | Obligated | 30% | 3152477.52 | 2167332.87 |  | 5319810.39 | -81494379.64 | 58589915.3537 | 8925018.7361 | 5958094.6826 | 2030365.4081 | 7210627.4912 | 13401816.6283 | 96115838.3 | 71758637.5275 | 24357200.7725 | Amendment – Pending Design Package for Development | FY2027 | The Amount Obligated by FEMA was $8.2M
682328 | FAASt [Bayamón TC - Rebuild] (Substation) | Substation | Substation | No | Pending Scope & Cost Completion by Applicant | 0 | 0 | 0 | 0 | 4748384.44 | 0 | 0 | 4748384.44 | 4748384.44 | 0 | Pending Scope & Cost Completion by Applicant |  | Obligated, Pending Scope & Cost Completion by Applicant | N/A | 3224629.84 | 14871908.58 |  | 18096538.42 | 1843088.36 | 1770998.9781 | 269776.7861 | 180095.4914 | 61371.9109 | 217955.8349 | 405097.0787 | 2905296.08 | 2169050.3043 | 736245.7757 | Amendment – Submitted to COR3/PREPA | Submitted
711819 | FAASt [Transmission Priority Pole Replacement Program Line 13400 San German Sect-La Parguera Sect] (Transmission) | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 2202286.53 | 176555.56 | 201035.14 | 0 | 147447.87 | 21069.57 | 0 | 2748394.67 | 2550769.54 | 197625.13 | Obligated | 2026-03-01 18:16 | Obligated | N/A | 623902.84 | 832177.64 | 129931.98 | 1586012.46 | -337144.76 | 2619583.06 | 20527.74 | 292186.72 | 3160.19 | 140718.36 | 9363.36 | 3085539.43 | 3052488.14 | 33051.29 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | No Amendment Needed
550106 | FAASt [Conquistador CH] (Substation) | Substation | Substation | No | Pending Scope & Cost Completion by Applicant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Pending Scope & Cost Completion by Applicant |  | Obligated, Pending Scope & Cost Completion by Applicant | N/A | 2933756.62 | 772607.09 |  | 3706363.71 | -12919599.5 | 6785925.6525 | 1619262.5575 | 668387.83 | 277399.36 | 1675808.9975 | 1892815.1025 | 12919599.5 | 9130122.48 | 3789477.02 | DSOW – Scope and Cost development in progress | Q4 FY2026 | Pending recieve assesment to iclude repairs to the fiber between Monacillos and El Conquistador
701495 | FAASt [Pole and Conductor Repair - Mayagüez Group 14] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 19848.36 | 5830.39 | 3959.6 | 0 | 0 | 0 | 0 | 29638.35 | 23807.96 | 5830.39 | Obligated | 2023-03-02 12:24 | Obligated | 100% | 13366.51 | 16973.02 |  | 30339.53 | 0 | 19848.36 | 4609 | 3959.6 | 1221.39 | 0 | 0 | 29638.35 | 23807.96 | 5830.39 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
745859 | FAASt [Automation Program Group 18: DAR – SAN JUAN 2001- FY24] (Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 223935.37 | 121965.2 | 21856.33 | 0 | 33515.73 | 76444.91 | 0 | 477717.54 | 279307.43 | 198410.11 | Pending Award | 2024-09-18 15:15 | Obligated, Pending Award | 72% | 97307.06 | 257781.06 |  | 355088.12 | -93207.19 | 223935.37 | 198410.11 | 21856.33 | 15504.92 | 33515.73 | 77702.27 | 570924.73 | 279307.43 | 291617.3 | Amendment – Submitted to FEMA | Submitted | 406HM Revision Pending Award in GP / Estimated date Cfci strategy to be defined
710110 | FAASt [Distribution Pole and Conductor Repair - Bayamon Group 2 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 85296.74 | 2478.06 | 14756.12 | 0 | 0 | 0 | 0 | 102530.92 | 100052.86 | 2478.06 | Obligated | 2023-10-23 11:32 | Obligated | 100% | 24406.16 | 87826.52 |  | 112232.68 | 0.12 | 85296.74 | 2000 | 14756 | 478.06 | 0 | 0 | 102530.8 | 100052.74 | 2478.06 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
673839 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 20468 | 5830 | 10152 | 0 | 0 | 0 | 0 | 36450 | 30620 | 5830 | Obligated | 2022-07-12 11:39 | Obligated | 100% | 47480.18 | 38208.48 |  | 85688.66 | -1 | 20468 | 4609 | 10153 | 1221 | 0 | 0 | 36451 | 30621 | 5830 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
688096 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 15] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 21408.25 | 5139.04 | 4169.45 | 691.35 | 0 | 0 | 0 | 31408.09 | 25577.7 | 5830.39 | Obligated | 2023-01-31 12:56 | Obligated | 100% | 9130.83 | 33824.25 |  | 42955.08 | 0.84 | 21408.25 | 4609 | 4169 | 1221 | 0 | 0 | 31407.25 | 25577.25 | 5830 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
334323 | FAASt Distribution Pole and Conductor Repair - Ponce Group 1 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 323692 | 69130 | 26179 | 0 | 0 | 0 | 0 | 419001 | 349871 | 69130 | Obligated | 2022-05-26 11:24 | Obligated | 91% | 265264.51 | 184969.79 |  | 450234.3 | -5046395 | 4099047 | 437231.68 | 273269.8 | 109307.92 | 273269.8 | 273269.8 | 5465396 | 4645586.6 | 819809.4 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
547251 | FAASt Line 2400 Dos Bocas HP to America Apparel (Transmission) | Transmission | Transmission Line Rebuild | Yes | Obligated | 50289473.68 | 0 | 3753435.29 | 0 | 8180.36 | 0 | 0 | 54051089.33 | 54051089.33 | 0 | Obligated | 2026-02-20 19:15 | Obligated | 0% | 2648451.06 | 35575.61 |  | 2684026.67 | 3808002.96 | 36790729.34 | 2900981.23 | 3092708.78 | 618690.18 | 1982784.48 | 4857192.36 | 50243086.37 | 41866222.6 | 8376863.77 | Amendment – Amendment Needed/Pending Development | Q4 FY2026 | Pending obligation, latest estimate is $54.5M
165226 | FAASt [Feeders Vieques & Culebra] (Distribution) | Distribution | Vieques and Culebra Projects (6) | No | Pending PDMG Scope & Cost Routing | 0 | 0 | 0 | 0 | 3880212.29 | 1009930.36 | 1 | 4890142.65 | 3880212.29 | 1009930.36 | Pending PDMG Scope & Cost Routing |  | Obligated, Pending PDMG Scope & Cost Routing | N/A | 4889996.11 | 750935.94 |  | 5640932.05 | -68721803.67 | 53571610.15 | 8023162.98 | 6288308.87 | 1016034.08 | 3512487.97 | 1200342.27 | 73611946.32 | 63372406.99 | 10239539.33 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | DSOW was sent 2/16/2026
169276 | FAASt Substation - Viaducto TC - MC 1100 - Equipment Repair & Replacement (Substation) | Substation | Substation | No | Pending Scope & Cost Completion by Applicant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Pending Scope & Cost Completion by Applicant |  | Obligated, Pending Scope & Cost Completion by Applicant | N/A | 3665916.7 | 655629.74 |  | 4321546.44 | -81166635.5 | 44329891.87 | 20397885.95 | 3422296.52 | 1244683.56 | 11765689.6 | 6188 | 81166635.5 | 59517877.99 | 21648757.51 | DSOW – Pending Design Package for Development | FY2027
746545 | FAASt [Primary Control Center / Secondary Data Center & Control Room] (Telecommunication) | Building | Building | No | Pending PDMG Scope & Cost Routing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Pending PDMG Scope & Cost Routing |  | Obligated, Pending PDMG Scope & Cost Routing | N/A | 10886342.21 | 477754.91 |  | 11364097.12 | -131169274 | 78491693.5616 | 36937267.5584 | 10703412.7584 | 5036900.1216 | 0 | 0 | 131169274 | 89195106.32 | 41974167.68 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Project under NEPA review process. An amendment will be developed after obligation to add 406 split.
798275 | FAASt [Feeder Rebuild # 1620-02] (Distribution) | Distribution | Feeders | Yes | Obligated | 6711421 | 0 | 954420.68 | 0 | 752852.93 | 0 | 0 | 8418694.61 | 8418694.61 | 0 | Pending Amendment Request Approval | 2025-09-17 18:16 | Obligated, Pending Amendment Request Approval | 0% | 1447054.36 | 37429.23 |  | 1484483.59 | 795374.22 | 5339236.4 | 338774.39 | 1228581.96 | 98180.39 | 490913.44 | 127633.81 | 7623320.39 | 7058731.8 | 564588.59 | Amendment – Submitted to COR3/PREPA | Q4 FY2026
705584 | FAASt [Distribution Pole and Conductor Repair - Ponce Groups 14 &amp;amp; 15] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 1464496 | 378483 | 284698 | 0 | 0 | 0 | 0 | 2127677 | 1749194 | 378483 | Obligated | 2023-06-16 12:55 | Obligated | 80% | 172615.86 | 1809515.27 |  | 1982131.13 | 0 | 1464496 | 299196 | 284698 | 79287 | 0 | 0 | 2127677 | 1749194 | 378483 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
705527 | FAASt [Distribution Pole and Conductor Repair - San Juan 17-18-19-20-21] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 642721 | 125133 | 125147 | 0 | 0 | 0 | 0 | 893001 | 767868 | 125133 | Obligated | 2023-07-28 11:42 | Obligated | 68% | 189871.91 | 612520.62 |  | 802392.53 | 0 | 642721 | 98919 | 125147 | 26214 | 0 | 0 | 893001 | 767868 | 125133 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
688109 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 11] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 448719.06 | 114710.2 | 87443.55 | 0 | 0 | 0 | 0 | 650872.81 | 536162.61 | 114710.2 | Obligated | 2023-03-08 12:36 | Obligated | 89% | 143571.39 | 448624.17 |  | 592195.56 | 108879.36 | 448719.06 | 90680 | 87444 | 24030.2 | 0 | 0 | 541993.45 | 536163.06 | 114710.2 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
704933 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 13-14-15-16] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 1201420 | 224731 | 231255 | 0 | 0 | 0 | 0 | 1657406 | 1432675 | 224731 | Obligated | 2023-08-04 19:29 | Obligated | 50% | 240917.35 | 1007597.88 |  | 1248515.23 | 0 | 1201420 | 177653 | 231255 | 47078 | 0 | 0 | 1657406 | 1432675 | 224731 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
682031 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 9] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 516951 | 95411 | 94044 | 12836 | 0 | 0 | 0 | 719242 | 610995 | 108247 | Obligated | 2023-01-31 12:56 | Obligated | 26% | 146791.32 | 147755.52 |  | 294546.84 | 0 | 516951 | 85571 | 94044 | 22676 | 0 | 0 | 719242 | 610995 | 108247 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
678988 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 5] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 911136.76 | 206650.4 | 175440.55 | 0 | 0 | 0 | 0 | 1293227.71 | 1086577.31 | 206650.4 | Obligated | 2022-12-27 11:53 | Obligated | 87% | 116955.71 | 957645.71 |  | 1074601.42 | -0.45 | 911136.76 | 163360 | 175441 | 43290.4 | 0 | 0 | 1293228.16 | 1086577.76 | 206650.4 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
682135 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 8] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 577000.79 | 102932.34 | 109858.85 | 13847.4 | 0 | 0 | 0 | 803639.38 | 686859.64 | 116779.74 | Obligated | 2023-01-10 13:19 | Obligated | 86% | 102626.17 | 547426.65 |  | 650052.82 | -19402.72 | 577000.79 | 92316 | 109859 | 24463.74 | 0 | 0 | 823042.1 | 686859.79 | 116779.74 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
688198 | FAASt [Pole and Conductor Repair - Arecibo Group 10] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 60838.48 | 16023.76 | 12052.8 | 0 | 0 | 0 | 0 | 88915.04 | 72891.28 | 16023.76 | Obligated | 2023-03-20 11:45 | Obligated | 85% | 32133.66 | 52234.74 |  | 84368.4 | -0.2 | 60838.48 | 12667 | 12053 | 3356.76 | 0 | 0 | 88915.24 | 72891.48 | 16023.76 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
704916 | FAASt [Pole and Conductor Repair - Arecibo Group 13-14-15-16] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 273996 | 29974 | 49755 | 0 | 0 | 0 | 0 | 353725 | 323751 | 29974 | Obligated | 2023-04-06 11:12 | Obligated | 80% | 117941.21 | 218856.76 |  | 336797.97 | 0 | 273996 | 23695 | 49755 | 6279 | 0 | 0 | 353725 | 323751 | 29974 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
682178 | FAASt [Pole and Conductor Repair - Arecibo Group 7] (Distribution ) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 208544.25 | 53746.06 | 40949.45 | 0 | 0 | 0 | 0 | 303239.76 | 249493.7 | 53746.06 | Obligated | 2023-01-31 12:56 | Obligated | 80% | 92258.39 | 144000.36 |  | 236258.75 | 0.45 | 208544.25 | 42487 | 40949 | 11259.06 | 0 | 0 | 303239.31 | 249493.25 | 53746.06 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
711888 | FAASt [Pole and Conductor Repair - Caguas Group 1 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 5425810.57 | 165903.3 | 434784.65 | 0 | 0 | 0 | 0 | 6026498.52 | 5860595.22 | 165903.3 | Obligated | 2024-03-22 10:16 | Obligated | 92% | 389419.46 | 4757697.68 |  | 5147117.14 | -0.35 | 5425810.57 | 132877 | 434785 | 33026 | 0 | 0 | 6026498.87 | 5860595.57 | 165903 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
688472 | FAASt [Pole and Conductor Repair - Mayaguez Group 11] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 164908.86 | 14986 | 29921.55 | 0 | 0 | 0 | 0 | 209816.41 | 194830.41 | 14986 | Obligated | 2023-02-16 12:51 | Obligated | 85% | 40704.72 | 89649.92 |  | 130354.64 | -0.45 | 164908.86 | 11847 | 29922 | 3139.46 | 0 | 0 | 209816.86 | 194830.86 | 14986.46 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
688630 | FAASt [Pole and Conductor Repair - Mayagüez Group 12] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 42728.41 | 9990.97 | 8327.05 | 0 | 0 | 0 | 0 | 61046.43 | 51055.46 | 9990.97 | Obligated | 2023-03-08 12:36 | Obligated | 51% | 48673.98 | 29090.4 |  | 77764.38 | 0.05 | 42728.41 | 7898 | 8327 | 2092.97 | 0 | 0 | 61046.38 | 51055.41 | 9990.97 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
688629 | FAASt [Pole and Conductor Repair - Mayagüez Group 13] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 106941.99 | 27886.93 | 20833.9 | 0 | 0 | 0 | 0 | 155662.82 | 127775.89 | 27886.93 | Obligated | 2023-03-08 12:36 | Obligated | 89% | 46185.11 | 53225.75 |  | 99410.86 | -0.1 | 106941.99 | 22045 | 20834 | 5841.93 | 0 | 0 | 155662.92 | 127775.99 | 27886.93 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
682210 | FAASt [Pole and Conductor Repair - Mayagüez Group 9] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 198050.74 | 36840.72 | 38248.35 | 4956.15 | 0 | 0 | 0 | 278095.96 | 236299.09 | 41796.87 | Obligated | 2023-01-24 13:14 | Obligated | 81% | 57250.62 | 172099.07 |  | 229349.69 | 0.35 | 198050.74 | 33041 | 38248 | 8755.87 | 0 | 0 | 278095.61 | 236298.74 | 41796.87 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
688625 | FAASt [Pole and Conductor Repair - Ponce Group 10] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 710014.69 | 191275.59 | 139357.85 | 0 | 0 | 0 | 0 | 1040648.13 | 849372.54 | 191275.59 | Obligated | 2023-03-20 11:45 | Obligated | 87% | 130618.07 | 416996.8 |  | 547614.87 | -0.15 | 710014.69 | 151206 | 139358 | 40069.59 | 0 | 0 | 1040648.28 | 849372.69 | 191275.59 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
701545 | FAASt [Pole and Conductor Repair - Ponce Group 11] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 487190 | 129039 | 95198 | 0 | 0 | 0 | 0 | 711427 | 582388 | 129039 | Obligated | 2023-03-08 12:36 | Obligated | 84% | 149557.2 | 363038.03 |  | 512595.23 | 0 | 487190 | 102007 | 95198 | 27032 | 0 | 0 | 711427 | 582388 | 129039 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
701555 | FAASt [Pole and Conductor Repair - Ponce Group 13] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 547010 | 102417 | 104535 | 0 | 0 | 0 | 0 | 753962 | 651545 | 102417 | Obligated | 2023-03-08 12:36 | Obligated | 89% | 100054.87 | 383909 |  | 483963.87 | 0 | 547010 | 80962 | 104535 | 21455 | 0 | 0 | 753962 | 651545 | 102417 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
686480 | FAASt [Pole and Conductor Repair - Ponce Group 7] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 523404 | 108652 | 101359 | 0 | 0 | 0 | 0 | 733415 | 624763 | 108652 | Obligated | 2023-02-16 12:51 | Obligated | 87% | 111962.35 | 447630.76 |  | 559593.11 | 93666 | 523404 | 85891 | 101359 | 22761 | 0 | 0 | 639749 | 624763 | 108652 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
682228 | FAASt [Pole and Conductor Repair - Ponce Group 8] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 775779 | 155908.42 | 150784 | 20974 | 0 | 0 | 0 | 1103445.42 | 926563 | 176882.42 | Obligated | 2023-01-31 12:56 | Obligated | 88% | 223903.89 | 476285.81 |  | 700189.7 | 0 | 775779 | 139828 | 150784 | 37054.42 | 0 | 0 | 1103445.42 | 926563 | 176882.42 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
727572 | FAASt [Region 3 -Bayamon Group A] High Density (Vegetation) | Vegetation | Vegetation | Yes | Obligated | 11268772.7 | 30826184.94 | 179741.68 | 491691 | 0 | 0 | 0 | 42766390.32 | 11448514.38 | 31317875.94 | Obligated | 2026-03-01 18:15 | Obligated | N/A | 443277.11 | 364268.12 |  | 807545.23 | -6208467.45 | 12945985.39 | 36028872.38 | 0 | 698724.72 | 0 | 0 | 48974857.77 | 12945985.39 | 36727597.1 | Obligated -No expected changes | N/A | Project is pending FEMA obligation
682028 | FAASt [Pole and Conductor Repair - San Juan Group 8] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 431381.68 | 93204.62 | 83822 | 12539 | 0 | 0 | 0 | 620947.3 | 515203.68 | 105743.62 | Obligated | 2023-01-10 13:19 | Obligated | 75% | 110527.7 | 380899.81 |  | 491427.51 | 94082.62 | 431381.68 | 83591 | 83822 | 22151.62 | 0 | 0 | 526864.68 | 515203.68 | 105742.62 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
817956 | FAASt [Feeder Rebuild # 1303-02] (Distribution) | Distribution | Feeders | Yes | Obligated | 2054461.78 | 0 | 1376522.26 | 0 | 129625.2 | 0 | 0 | 3560609.24 | 3560609.24 | 0 | Pending Amendment Request Approval | 2025-09-25 17:15 | Obligated, Pending Amendment Request Approval | 0% | 1161981.66 | 12376.72 |  | 1174358.38 | 830872.71 | 2102127.04 | 7555.38 | 513368.91 | 6761.68 | 78644.98 | 21278.54 | 2729736.53 | 2694140.93 | 35595.6 | Amendment – Submitted to COR3/PREPA | Q4 FY2026
812569 | FAASt [Feeder Rebuild 3502-02] (Distribution) | Distribution | Feeders | Yes | Obligated | 10217566.54 | 0 | 1403642.18 | 0 | 760494.56 | 0 | 0 | 12381703.28 | 12381703.28 | 0 | Obligated | 2025-09-25 16:15 | Obligated | 0% | 1669007.45 | 28392.26 |  | 1697399.71 | -158999.02 | 9913132.84 | 597420.75 | 1301050.25 | 86144.8 | 547637.41 | 95316.25 | 12540702.3 | 11761820.5 | 778881.8 | Amendment – Amendment Needed/Pending Development | Q4 FY2026 | IEM is working on versioning, to be submitted to FEMA on Mar 2026
801166 | FAASt [Feeder Rebuild # 6601-03] (Distribution) | Distribution | Feeders | Yes | Obligated | 19826783.47 | 0 | 1724565.72 | 0 | 2135838.13 | 0 | 0 | 23687187.32 | 23687187.32 | 0 | Obligated | 2026-01-08 16:17 | Obligated | 0% | 1877483.66 | 75764.59 |  | 1953248.25 | 84696.25 | 18342600.15 | 1465349.66 | 1564501.94 | 153975.57 | 1578988.43 | 497075.32 | 23602491.07 | 21486090.52 | 2116400.55 | Amendment – Pending Design Package for Development | Q1 FY2027 | IFA versioning in-progress. Survey aligment of 477 structures, 7.2 miles on rural area. Next step is IFC development and submission to FEMA on Jul 2026
756997 | FAASt [TL 1900 Caguanas to Lares TO] (Transmission) | Transmission | Transmission Line Rebuild | No | Pending Scope & Cost Completion by Applicant | 0 | 0 | 0 | 0 | 510654.48 | 0 | 0 | 510654.48 | 510654.48 | 0 | Pending Scope & Cost Completion by Applicant |  | Obligated, Pending Scope & Cost Completion by Applicant | N/A | 3861197.67 | 279802.22 |  | 4140999.89 | -42836834.64 | 30997111.49 | 4687634.65 | 2356500.58 | 611010.51 | 1066728.72 | 3628503.17 | 43347489.12 | 34420340.79 | 8927148.33 | DSOW – Submitted to COR3/PREPA | Submitted | Already Submitted
704750 | FAASt Distribution Pole and Conductor Repair - Bayamon Group 10 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 486385 | 92244 | 92511 | 0 | 0 | 0 | 0 | 671140 | 578896 | 92244 | Obligated | 2023-04-06 11:12 | Obligated | 88% | 93090.43 | 492930.91 |  | 586021.34 | 0 | 486385 | 72920 | 92511 | 19324 | 0 | 0 | 671140 | 578896 | 92244 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
704751 | FAASt Distribution Pole and Conductor Repair - Bayamon Group 11 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 338491 | 96676 | 66168 | 0 | 0 | 0 | 0 | 501335 | 404659 | 96676 | Obligated | 2023-04-06 11:12 | Obligated | 91% | 174293.41 | 254644.93 |  | 428938.34 | 0 | 338491 | 76424 | 66168 | 20252 | 0 | 0 | 501335 | 404659 | 96676 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
679149 | FAASt Distribution Pole and Conductor Repair - Mayagüez Group 5 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 129744 | 27443 | 25191 | 0 | 0 | 0 | 0 | 182378 | 154935 | 27443 | Obligated | 2022-12-27 11:53 | Obligated | 88% | 42313.07 | 64876.23 |  | 107189.3 | 0 | 129744 | 21694 | 25191 | 5749 | 0 | 0 | 182378 | 154935 | 27443 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
679153 | FAASt Distribution Pole and Conductor Repair - Mayagüez Group 6 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 163846.51 | 51337.5 | 31068.05 | 0 | 0 | 0 | 0 | 246252.06 | 194914.56 | 51337.5 | Obligated | 2022-12-27 11:53 | Obligated | 88% | 41229.48 | 97985.99 |  | 139215.47 | -105815.45 | 163846.51 | 40583 | 31068 | 10754.5 | 0 | 0 | 352067.51 | 194914.51 | 51337.5 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
685263 | FAASt Distribution Pole and Conductor Repair - Ponce Group 6 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 537688 | 118723 | 103281 | 15972 | 0 | 0 | 0 | 775664 | 640969 | 134695 | Obligated | 2022-12-27 11:53 | Obligated | 86% | 69845.95 | 458183.25 |  | 528029.2 | 0 | 537688 | 106478 | 103281 | 28217 | 0 | 0 | 775664 | 640969 | 134695 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
688774 | FAASt Distribution Pole and Conductor Repair - Ponce Group 9 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 443331 | 86806 | 86719 | 11678 | 0 | 0 | 0 | 628534 | 530050 | 98484 | Obligated | 2023-01-31 12:56 | Obligated | 87% | 79105.19 | 236370.68 |  | 315475.87 | 0 | 443331 | 77853 | 86719 | 20631 | 0 | 0 | 628534 | 530050 | 98484 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
698570 | FAASt [Distribution Streetlighting - Corozal] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 13720208.31 | 2225873.62 | 2501126 | 0 | 0 | 0 | 0 | 18447207.93 | 16221334.31 | 2225873.62 | Obligated | 2023-12-29 12:31 | Obligated | 84% | 1926441.65 | 9907102.27 |  | 11833543.92 | -87444.07 | 13648195 | 1608383.29 | 2640715 | 617490.33 | 0 | 0 | 18534652 | 16288910 | 2225873.62 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
698458 | FAASt [Distribution Streetlighting - Guaynabo] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 9762754.59 | 853056.42 | 1979750.26 | 0 | 0 | 0 | 0 | 12595561.27 | 11742504.85 | 853056.42 | Obligated | 2023-11-03 11:30 | Obligated | 77% | 1027559.99 | 5201107.12 |  | 6228667.11 | 0.26 | 9762754.59 | 605024.35 | 1979750 | 248032.07 | 0 | 0 | 12595561.01 | 11742504.59 | 853056.42 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
704938 | FAASt [Distribution Streetlighting - Las Piedras (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 13807923.4 | 1807601.11 | 2760454.04 | 0 | 0 | 0 | 0 | 18375978.55 | 16568377.44 | 1807601.11 | Obligated | 2024-04-12 11:19 | Obligated | 70% | 939246.76 | 8823541.05 |  | 9762787.81 | 0.04 | 13807923.4 | 1285354.42 | 2760454 | 522246.69 | 0 | 0 | 18375978.51 | 16568377.4 | 1807601.11 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
724600 | FAASt [Jayuya Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 7277670.2 | 1350541.32 | 1704125.72 | 0 | 0 | 0 | 0 | 10332337.24 | 8981795.92 | 1350541.32 | Obligated | 2024-05-31 11:36 | Obligated | 73% | 944820.43 | 5199174.46 |  | 6143994.89 | -0.28 | 7277670.2 | 931433.8 | 1704126 | 419107.52 | 0 | 0 | 10332337.52 | 8981796.2 | 1350541.32 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
709631 | FAASt [Morovis Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 13486398.85 | 1744482.27 | 2499521.06 | 0 | 0 | 0 | 0 | 17730402.18 | 15985919.91 | 1744482.27 | Obligated | 2024-03-22 10:16 | Obligated | 80% | 624831.32 | 12648292.15 |  | 13273123.47 | 0.06 | 13486398.85 | 1257031.57 | 2499521 | 487450.7 | 0 | 0 | 17730402.12 | 15985919.85 | 1744482.27 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
704849 | FAASt [Naguabo Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 11620676.42 | 1669736.97 | 2380242.99 | 0 | 0 | 0 | 0 | 15670656.38 | 14000919.41 | 1669736.97 | Obligated | 2024-05-10 10:17 | Obligated | 67% | 929157.85 | 7176923.51 |  | 8106081.36 | 4797962.38 | 7240724 | 1182070.57 | 1925642 | 487666.4 | 0 | 0 | 10872694 | 9166366 | 1669736.97 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
704943 | FAASt [Naranjito Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 11644048.42 | 1501948.72 | 2348209.91 | 613589.66 | 0 | 0 | 0 | 16107796.71 | 13992258.33 | 2115538.38 | Obligated | 2024-04-12 11:19 | Obligated | 64% | 1343697.77 | 7491314.11 |  | 8835011.88 | -0.09 | 11644048.42 | 1501948.72 | 2348210 | 613589.66 | 0 | 0 | 16107796.8 | 13992258.42 | 2115538.38 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
724601 | FAASt [Salinas Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 12097203.53 | 1611020.9 | 2463885.54 | 0 | 0 | 0 | 0 | 16172109.97 | 14561089.07 | 1611020.9 | Obligated | 2024-07-08 11:28 | Obligated | 79% | 1515998.56 | 8960437.9 |  | 10476436.46 | -0.46 | 12097203.53 | 1141690.52 | 2463886 | 469330.38 | 0 | 0 | 16172110.43 | 14561089.53 | 1611020.9 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
703535 | FAASt [Toa Baja Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 9529190.37 | 620134.69 | 1814022 | 0 | 0 | 0 | 0 | 11963347.06 | 11343212.37 | 620134.69 | Obligated | 2024-06-18 11:28 | Obligated | 55% | 421395.41 | 2844675.01 |  | 3266070.42 | 0 | 9529190.37 | 444807.71 | 1814022 | 175326.98 | 0 | 0 | 11963347.06 | 11343212.37 | 620134.69 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
690545 | FAASt Aguadilla Streetlight (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 19796809 | 1295775 | 3021242 | 0 | 0 | 0 | 0 | 24113826 | 22818051 | 1295775 | Obligated | 2023-05-17 11:31 | Obligated | 49% | 1403833.3 | 4028370.1 |  | 5432203.4 | 0 | 19796809 | 962442 | 3021242 | 333333 | 0 | 0 | 24113826 | 22818051 | 1295775 | Amendment – Amendment Needed/Pending Development | Q1 FY2027 | Amendment pending to remove underground scope
704679 | FAASt Coamo Streetlight (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 14311922.45 | 2060901.35 | 2687463.9 | 0 | 0 | 0 | 0 | 19060287.7 | 16999386.35 | 2060901.35 | Obligated | 2023-11-03 11:30 | Obligated | 69% | 2624114.44 | 11411907.14 |  | 14036021.58 | -0.1 | 14311922.45 | 1481726 | 2687464 | 579175.35 | 0 | 0 | 19060287.8 | 16999386.45 | 2060901.35 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
691702 | FAASt Distribution Streetlighting - Trujillo Alto (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 25277347 | 1009578 | 3389490 | 0 | 0 | 0 | 0 | 29676415 | 28666837 | 1009578 | Obligated | 2023-05-17 11:31 | Obligated | 45% | 415062.95 | 1727729.45 |  | 2142792.4 | 14851164 | 12199399 | 763112 | 2277871 | 246446 | 0 | 0 | 14825251 | 14477270 | 1009558 | Amendment – Amendment Needed/Pending Development | FY2027 | Amendment pending to remove underground scope Grants portal total project cost is $29.7M
724698 | FAASt [Adjuntas Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 10742462 | 1891152 | 2199843.63 | 0 | 0 | 0 | 0 | 14833457.63 | 12942305.63 | 1891152 | Obligated | 2024-06-18 11:28 | Obligated | 79% | 1353321.41 | 7889965.76 |  | 9243287.17 | -0.37 | 10742462 | 1338877 | 2199844 | 552275 | 0 | 0 | 14833458 | 12942306 | 1891152 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
704927 | FAASt [Añasco Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 12087876.17 | 1820361.92 | 2420466.41 | 0 | 0 | 0 | 0 | 16328704.5 | 14508342.58 | 1820361.92 | Obligated | 2024-07-08 11:28 | Obligated | 90% | 2051793.69 | 8786988.61 |  | 10838782.3 | 0.41 | 12087876.17 | 1294052.66 | 2420466 | 526309.26 | 0 | 0 | 16328704.09 | 14508342.17 | 1820361.92 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
724703 | FAASt [Arroyo Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 5314332 | 740394.01 | 1504203.15 | 0 | 0 | 0 | 0 | 7558929.16 | 6818535.15 | 740394.01 | Obligated | 2024-06-18 11:28 | Obligated | 60% | 444120.48 | 3773474.62 |  | 4217595.1 | 0.15 | 5314332 | 489465.16 | 1504203 | 250928.85 | 0 | 0 | 7558929.01 | 6818535 | 740394.01 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
704921 | FAASt [Barranquitas Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 9430329.22 | 1577046.09 | 2048083.31 | 0 | 0 | 0 | 0 | 13055458.62 | 11478412.53 | 1577046.09 | Obligated | 2024-05-31 11:36 | Obligated | 65% | 563958.34 | 6064286.85 |  | 6628245.19 | 0.31 | 9430329.22 | 1104151.73 | 2048083 | 472894.36 | 0 | 0 | 13055458.31 | 11478412.22 | 1577046.09 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
704868 | FAASt [Ceiba Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 5152111.14 | 716918.6 | 1481546.84 | 0 | 0 | 0 | 0 | 7350576.58 | 6633657.98 | 716918.6 | Obligated | 2024-07-08 11:28 | Obligated | 68% | 296022.95 | 2586620.8 |  | 2882643.75 | 0 | 5152111.14 | 472131.79 | 1481546.84 | 244786.81 | 0 | 0 | 7350576.58 | 6633657.98 | 716918.6 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
724825 | FAASt [Cidra Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 12812478.84 | 1838229.6 | 2516455.74 | 0 | 0 | 0 | 0 | 17167164.18 | 15328934.58 | 1838229.6 | Obligated | 2024-05-10 10:17 | Obligated | 66% | 1803326.86 | 7913559 |  | 9716885.86 | -0.26 | 12812478.84 | 1311297.11 | 2516456 | 526932.49 | 0 | 0 | 17167164.44 | 15328934.84 | 1838229.6 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
701472 | FAASt [Comerio Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 6538769.44 | 862125.75 | 1640383 | 0 | 0 | 0 | 0 | 9041278.19 | 8179152.44 | 862125.75 | Obligated | 2024-05-10 10:17 | Obligated | 83% | 356061.79 | 4266182.31 |  | 4622244.1 | 0 | 6538769.44 | 862125.75 | 1640383 | 0 | 0 | 0 | 9041278.19 | 8179152.44 | 862125.75 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
679780 | FAASt [Distribution Streetlighting - Bayamon] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 20710527 | 1176376 | 3212958 | 0 | 0 | 0 | 0 | 25099861 | 23923485 | 1176376 | Obligated | 2023-11-03 11:30 | Obligated | 78% | 1082061.52 | 6687522.88 |  | 7769584.4 | 0 | 20710527 | 1176376 | 3212958 | 0 | 0 | 0 | 25099861 | 23923485 | 1176376 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
679039 | FAASt [Distribution Streetlighting - Caguas] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 73737224.58 | 1849344.06 | 8534896.89 | 0 | 0 | 0 | 0 | 84121465.53 | 82272121.47 | 1849344.06 | Obligated | 2023-07-05 11:36 | Obligated | 48% | 1467080.25 | 3909718.1 |  | 5376798.35 | 2642741.53 | 71310194 | 1422693 | 8324691 | 426651.06 | 0 | 0 | 81478724 | 79634885 | 1849344.06 | Amendment – Amendment Needed/Pending Development | Q1 FY2028 | Amendment pending to remove underground scope Grants portal total project cost is $84.1M
678789 | FAASt [Distribution Streetlighting - Carolina] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 14865613.02 | 1158946.56 | 2559492.85 | 0 | 0 | 0 | 0 | 18584052.43 | 17425105.87 | 1158946.56 | Obligated | 2023-11-03 11:30 | Obligated | 66% | 1057017.4 | 4871749.65 |  | 5928767.05 | -0.15 | 14865613.02 | 1158946.56 | 2559493 | 0 | 0 | 0 | 18584052.58 | 17425106.02 | 1158946.56 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
673504 | FAASt [Distribution Streetlighting - Gurabo] | Distribution | Distribution Streetlighting | Yes | Obligated | 19208994 | 1533300 | 3043676 | 0 | 0 | 0 | 0 | 23785970 | 22252670 | 1533300 | Obligated | 2023-05-17 11:31 | Obligated | 69% | 1066631.61 | 10060207.65 |  | 11126839.26 | 0.99197 | 19208993.6756 | 1132656 | 3043675.3411 | 400644 | 0 | 0 | 23785969.008 | 22252669.0167 | 1533300 | Amendment – Amendment Needed/Pending Development | Q2 FY2028 | Amendment pending to remove underground scope
671502 | FAASt [Distribution Streetlighting - Yabucoa] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 14918381.07 | 1965608.26 | 2742910.41 | 0 | 0 | 0 | 0 | 19626899.74 | 17661291.48 | 1965608.26 | Obligated | 2023-12-29 12:31 | Obligated | 69% | 2622974.69 | 9129753.51 |  | 11752728.2 | -219266.5425 | 14931289.0239 | 1987567.5115 | 2927309.7471 | 0 | 0 | 0 | 19846166.2825 | 17858598.771 | 1987567.5115 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
659968 | FAASt [San Germán Streetlighting] (Distributio | Distribution | Distribution Streetlighting | Yes | Obligated | 30849348 | 4033578 | 4619207 | 0 | 0 | 0 | 0 | 39502133 | 35468555 | 4033578 | Obligated | 2023-05-04 11:30 | Obligated | 72% | 4404198 | 17318241.86 |  | 21722439.86 | -0.24973 | 30849348.4835 | 3004065 | 4619206.9342 | 1029513 | 0 | 0 | 39502133.2497 | 35468555.4178 | 4033578 | Amendment – Amendment Needed/Pending Development | Q1 FY2028 | Amendment pending to remove underground scope
678793 | FAASt [Streetlighting - Mayagüez] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 11019180.1 | 1352204.36 | 2291581 | 0 | 0 | 0 | 0 | 14662965.46 | 13310761.1 | 1352204.36 | Obligated | 2023-11-03 11:30 | Obligated | 55% | 1413781.37 | 3675869.91 |  | 5089651.28 | 0 | 11019180.1 | 1352204.36 | 2291581 | 0 | 0 | 0 | 14662965.46 | 13310761.1 | 1352204.36 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
724938 | FAASt [Vega Alta Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 12445015.33 | 1869089.52 | 2459742.66 | 0 | 0 | 0 | 0 | 16773847.51 | 14904757.99 | 1869089.52 | Obligated | 2024-05-10 10:17 | Obligated | 59% | 702385.01 | 8047337.5 |  | 8749722.51 | 0.51 | 12445015 | 1331811.11 | 2459743 | 537278.89 | 0 | 0 | 16773847 | 14904758 | 1869090 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
542688 | FAASt Aguada Streetlighting (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 17764494.34 | 807222.04 | 4104785.76 | 0 | 0 | 0 | 0 | 22676502.14 | 21869280.1 | 807222.04 | Obligated | 2022-05-05 12:44 | Obligated | 95% | 1020179.15 | 12653210.52 |  | 13673389.67 | -4104785.7637 | 21869280.099 | 807222.0429 | 4104785.7618 | 0 | 0 | 0 | 26781287.9037 | 25974065.8608 | 807222.0429 | Amendment – Amendment Needed/Pending Development | Q2 FY2027 | Amendment pending to remove underground scope Grants portal total project cost is $4.1M
659715 | FAASt Distribution Streetlighting - Aibonito | Distribution | Distribution Streetlighting | Yes | Obligated | 7074498 | 178787 | 1880873 | 0 | 0 | 0 | 0 | 9134158 | 8955371 | 178787 | Obligated | 2022-12-27 11:53 | Obligated | 91% | 771300.47 | 5466320.32 |  | 6237620.79 | 0.024431 | 7074498.4202 | 129540 | 1880872.5823 | 49247 | 0 | 0 | 9134157.9756 | 8955371.0025 | 178787 | Amendment – Amendment Needed/Pending Development | Q2 FY2027 | Amendment pending to remove underground scope
659623 | FAASt Distribution Streetlighting - Cataño ( | Distribution | Distribution Streetlighting | Yes | Obligated | 16996758 | 565289 | 3574763 | 0 | 0 | 0 | 0 | 21136810 | 20571521 | 565289 | Obligated | 2022-12-27 11:53 | Obligated | 77% | 1129471.99 | 2894190.49 |  | 4023662.48 | -0.15624 | 16996757.9573 | 516042 | 3574762.8595 | 49247 | 0 | 0 | 21136810.1562 | 20571520.8168 | 565289 | Amendment – Amendment Needed/Pending Development | Q2 FY2027 | Amendment pending to remove underground scope
659625 | FAASt Distribution Streetlighting - Dorado | Distribution | Distribution Streetlighting | Yes | Obligated | 22864972 | 1340145 | 3031749 | 165500 | 0 | 0 | 0 | 27402366 | 25896721 | 1505645 | Obligated | 2023-01-24 13:14 | Obligated | 79% | 1590751.19 | 4882711.44 |  | 6473462.63 | -1684845.5954 | 22864971.8931 | 1149672 | 4716594.2453 | 355973 | 0 | 0 | 29087211.5954 | 27581566.1384 | 1505645 | Amendment – Amendment Needed/Pending Development | Q2 FY2027 | Amendment pending to remove underground scope
660227 | FAASt Hatillo Streetlight (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 18570095.25 | 1764387.7 | 4317860.43 | 0 | 0 | 0 | 0 | 24652343.38 | 22887955.68 | 1764387.7 | Obligated | 2023-01-24 13:14 | Obligated | 79% | 2518200.59 | 9798208.1 |  | 12316408.69 | 0.0028212 | 18570095.2497 | 1316105.06 | 4317860.4264 | 448282.64 | 0 | 0 | 24652343.3772 | 22887955.6761 | 1764387.7 | Amendment – Amendment Needed/Pending Development | Q3 FY2027 | Amendment pending to remove underground scope
542687 | FAASt Lajas Streetlighting (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 10278336.09 | 426332.48 | 2512853.73 | 0 | 0 | 0 | 0 | 13217522.3 | 12791189.82 | 426332.48 | Obligated | 2022-05-20 12:05 | Obligated | 93% | 1075763.82 | 5981576.91 |  | 7057340.73 | -2512853.7356 | 12791189.8219 | 426332.4825 | 2512853.7311 | 0 | 0 | 0 | 15730376.0356 | 15304043.553 | 426332.4825 | Amendment – Amendment Needed/Pending Development | Q3 FY2027 | Amendment pending to remove underground scope Grants portal total project cost is $2.5
542517 | FAASt -Luquillo Distribution Streetlighting | Distribution | Distribution Streetlighting | Yes | Obligated | 8628667.29 | 181658.08 | 2004233.23 | 0 | 0 | 0 | 0 | 10814558.6 | 10632900.52 | 181658.08 | Obligated | 2022-05-20 12:05 | Obligated | 88% | 972416.24 | 2834354.64 |  | 3806770.88 | -2004233.2371 | 10632900.5227 | 181658.0813 | 2004233.2331 | 0 | 0 | 0 | 12818791.8371 | 12637133.7558 | 181658.0813 | Amendment – Amendment Needed/Pending Development | Q2 FY2027 | Amendment pending to remove underground scope Grants portal total project cost is $2M
660437 | FAASt Manati Streetlight (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 27067865 | 1568964 | 5821635 | 0 | 0 | 0 | 0 | 34458464 | 32889500 | 1568964 | Obligated | 2023-01-24 13:14 | Obligated | 66% | 1460283.71 | 8221672.45 |  | 9681956.16 | -0.74679 | 27067865.4688 | 1188605 | 5821635.5034 | 380359 | 0 | 0 | 34458464.7468 | 32889500.9722 | 1568964 | Amendment – Amendment Needed/Pending Development | Q4 FY2027 | Amendment pending to remove underground scope
698439 | FAASt Streetlight - Las Marías (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 7073217 | 1287705 | 1653390 | 0 | 0 | 0 | 0 | 10014312 | 8726607 | 1287705 | Obligated | 2023-11-03 11:30 | Obligated | 53% | 1344027.4 | 2142717.62 |  | 3486745.02 | 0 | 7073217 | 1287705 | 1653390 | 0 | 0 | 0 | 10014312 | 8726607 | 1287705 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
698424 | FAASt Streetlight Florida Distribution | Distribution | Distribution Streetlighting | Yes | Obligated | 9311841.53 | 997190 | 1705096.48 | 0 | 0 | 0 | 0 | 12014128.01 | 11016938.01 | 997190 | Obligated | 2023-10-23 11:32 | Obligated | 75% | 1512708.84 | 4834340.37 |  | 6347049.21 | 0.48 | 9311841.53 | 720017 | 1705096 | 277173 | 0 | 0 | 12014127.53 | 11016937.53 | 997190 | Amendment – Amendment Needed/Pending Development | FY2027 | Amendment pending to remove underground scope
542756 | FAASt Streetlighting - Guánica (Distribution | Distribution | Distribution Streetlighting | Yes | Obligated | 9687238 | 370808 | 2237386 | 0 | 0 | 0 | 0 | 12295432 | 11924624 | 370808 | Obligated | 2022-05-26 11:24 | Obligated | 89% | 710048.67 | 3682408.62 |  | 4392457.29 | -2237386.386 | 11924623.8365 | 370808.2187 | 2237386.3309 | 0 | 0 | 0 | 14532818.386 | 14162010.1673 | 370808.2187 | Amendment – Amendment Needed/Pending Development | Q2 FY2027 | Amendment pending to remove underground scope Grants portal total project cost is $2.237M
551926 | FAASt [SCADA Remote Access and RTU Replacements Group 2] (Telecommunication) | Telecommunication | IT/OT | Yes | Obligated | 5267467.99 | 939009.17 | 800287.41 | 134453.44 | 0 | 0 | 0 | 7141218.01 | 6067755.4 | 1073462.61 | Obligated | 2026-03-01 18:16 | Obligated | N/A | 1382619.44 | 187936.6 |  | 1570556.04 | -396718.5589 | 5267467.9889 | 939009.17 | 800287.4104 | 134453.4396 | 396718.56 | 0 | 7537936.5689 | 6464473.9594 | 1073462.6096 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Q1 FY2027 | Pending FEMA Obligation, currently in Phase 5.
750063 | FAASt [Region 6 -Ponce Group A] Low Density (Vegetation) | Vegetation | Vegetation-DT | No | Pending Applicant Project Review | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Pending Large Project Review |  | Obligated, Pending Large Project Review | N/A | 191728.3 | 133176.44 |  | 324904.74 | -69341045.82 | 18254467.11 | 50797296.22 | 289282.49 | 985459.15 | 0 | 0 | 69341045.82 | 18543749.6 | 51782755.37 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Project is pending FEMA obligation
727659 | FAASt [Region 2 Arecibo TL - 115kV] (Vegetation) | Vegetation | Vegetation-TL | Yes | Obligated | 953592.14 | 3230664.72 | 8880.74 | 30086.96 | 0 | 0 | 0 | 4223224.56 | 962472.88 | 3260751.68 | Obligated | 2026-03-01 18:16 | Obligated | N/A | 21507.48 | 102958.5 |  | 124465.98 | -724634.66 | 1109346.43 | 3793180 | 10335.88 | 34996.91 | 0 | 0 | 4947859.22 | 1119682.31 | 3828176.91 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Total submitted estimated project cost is $ $19,687,816.76, however based on conversations with FEMA, only 13.37/53.2 miles are expected to be obligated. Costs reflect expected obligated cost with these reductions.
168483 | FAASt - 115kV Line 36400 - Dos Bocas HP to Ponce TC (Transmission) | Transmission | Transmission Line Rebuild | No | Pending Scope & Cost Completion by Applicant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Pending Scope & Cost Completion by Applicant |  | Obligated, Pending Scope & Cost Completion by Applicant | N/A | 5097248 | 69398.6 |  | 5166646.6 | -81700988.57 | 71272552.67 | 5820746.94 | 4233792.76 | 345260.6 | 28635.6 | 0 | 81700988.57 | 75534981.03 | 6166007.54 | Amendment – Amendment Needed/Pending Development | Q1 FY2027 | Project contains multiple segments and distribution scope. The estimates are still under review and the current estimates are over $120M all together.
750067 | FAASt [Region 2 -Arecibo Group A] Low Density (Vegetation) | Vegetation | Vegetation-DT | Yes | Obligated | 15030146.18 | 41767142.56 | 238185.98 | 0 | 0 | 0 | 0 | 57035474.72 | 15268332.16 | 41767142.56 | Obligated | 2026-03-01 18:15 | Obligated | N/A | 193158.39 | 64314.49 |  | 257472.88 | -8555324.97 | 17267191.18 | 48049971.59 | 273636.92 | 931916.64 | 0 | 0 | 65590799.69 | 17540828.1 | 48981888.23 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Project is pending FEMA obligation
750068 | FAASt [Region 5 -Mayaguez Group A] Low Density (Vegetation) | Vegetation | Vegetation-DT | Yes | Obligated | 13840548.75 | 37861383.08 | 219334.17 | 599997.54 | 0 | 0 | 0 | 52521263.54 | 14059882.92 | 38461380.62 | Obligated | 2026-03-01 18:15 | Obligated | N/A | 170084.91 | 58772.51 |  | 228857.42 | -7878193 | 15900537.4 | 44246939.88 | 251979.26 | 858465.45 | 0 | 0 | 60399456.54 | 16152516.66 | 45105405.33 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Project is pending FEMA obligation
750065 | FAASt [Region 3 -Bayamon Group A] Low Density (Vegetation) | Vegetation | Vegetation-DT | Yes | Obligated | 18569923.87 | 51603800.04 | 294281.61 | 0 | 0 | 0 | 0 | 70468005.52 | 18864205.48 | 51603800.04 | Obligated | 2026-03-01 18:15 | Obligated | N/A | 120549.61 | 45858.06 |  | 166407.67 | -10570205.48 | 21333819.52 | 59366309.82 | 338081.66 | 1151514.49 | 0 | 0 | 81038211 | 21671901.18 | 60517824.31 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Project is pending FEMA obligation
727608 | FAASt [Region 1 San Juan TL - 115kV] (Vegetation) | Vegetation | Vegetation-TL | No | Pending Large Project Review | 1007797.83 | 3414307.59 | 9385.55 | 31797.21 | 0 | 0 | 0 | 4463288.18 | 1017183.38 | 3446104.8 | Obligated | 2026-03-01 18:16 | Obligated | N/A | 58830.32 | 35559.27 |  | 94389.59 | -773548.48 | 1174137.29 | 4014718.94 | 10939.54 | 37040.89 | 0 | 0 | 5236836.66 | 1185076.83 | 4051759.83 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Total submitted estimated project cost is $27,603,651.36, however based on conversations with FEMA, only 14.13/74.48 miles are expected to be obligated. Costs reflect expected obligated cost with these reductions.
750066 | FAASt [Region 4 -Caguas Group A] Low Density (Vegetation) | Vegetation | Vegetation-DT | Yes | Obligated | 28466485.03 | 79097232.77 | 448177.27 | 0 | 0 | 0 | 0 | 108011895.07 | 28914662.3 | 79097232.77 | Obligated | 2026-03-01 17:15 | Obligated | N/A | 253316.92 | 30262.67 |  | 283579.59 | -16201791.39 | 32703357.23 | 90995446.51 | 514882.72 | 2059216.24 | 0 | 0 | 124213686.46 | 33218239.95 | 93054662.75 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Project is pending FEMA obligation
746660 | FAASt [Minor Protection, Automation, and Control [PAC] Replacement] (Substation) | Substation | Substation | No | Pending Scope & Cost Completion by Applicant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Pending Scope & Cost Completion by Applicant |  | Obligated, Pending Scope & Cost Completion by Applicant | N/A | 2423098.68 | 30058.15 |  | 2453156.83 | -16714034.16 | 10188475.3228 | 1552013.39 | 1036081.0436 | 353069.7686 | 1253889.8514 | 2330504.7835 | 16714034.16 | 12478446.2178 | 4235587.9422 | DSOW – Submitted to COR3/PREPA | Submitted | Submitted to COR3 in Jan. 2026
165213 | FAASt – Line 5400 – Rio Blanco HP to Daguao TC to Punta Lima TO to Vieques 2501 to Culebra 3801 (Transmission) | Transmission | Vieques and Culebra Projects (6) | No | Pending Scope & Cost Completion by Applicant | 0 | 0 | 0 | 0 | 0 | 12125.03 | 1 | 12125.03 | 0 | 12125.03 | Pending Scope & Cost Completion by Applicant |  | Obligated, Pending Scope & Cost Completion by Applicant | N/A | 5633450.47 | 27819.85 |  | 5661270.32 | -126620050.96 | 90286761.91 | 12425361.64 | 7450643.73 | 918661.08 | 14930827.72 | 619919.91 | 126632175.99 | 112668233.36 | 13963942.63 | DSOW – Scope and Cost development in progress | Q1 FY2026 | Issue for Approval was received meeting ongoing to discuss the design and agree in the final scope to be submitted to FEMA.
723002 | FAASt - EPC - Jobos TC (Substation) | Substation | Substation | No | Pending Scope & Cost Completion by Applicant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Pending Scope & Cost Completion by Applicant |  | Obligated, Pending Scope & Cost Completion by Applicant | N/A | 1942607.63 | 15989.76 |  | 1958597.39 | -76096512.83 | 46386613.5309 | 7066086.2431 | 4717122.9683 | 1607474.1693 | 5708774.0907 | 10610441.8276 | 76096512.83 | 56812510.5899 | 19284002.2401 | DSOW – Pending Design Package for Development | FY2027 | Planning and Engineering is working on the scope for the project.
169058 | FAASt - Llorens Torres MC 1106 - Equipment Repair & Replacement - (Substations) | Substation | Substation | No | Pending Scope & Cost Completion by Applicant | 0 | 0 | 0 | 0 | 4078410.44 | 3369687 | 1 | 7448097.44 | 4078410.44 | 3369687 | Pending Scope & Cost Completion by Applicant |  | Obligated, Pending Scope & Cost Completion by Applicant | N/A | 2099708.01 | 13367.36 |  | 2113075.37 | -30373385.7742 | 19057031.49 | 9240046.5742 | 1213803.7 | 655599.77 | 4285314.68 | 3369687 | 37821483.2142 | 24556149.87 | 13265333.3442 | Amendment – Amendment Needed/Pending Development | Q4 FY2026
547187 | FAASt [Substation Component Replacement Program] (Substation) | Substation | Substation | No | Pending Scope & Cost Completion by Applicant | 0 | 0 | 0 | 0 | 2233992.76 | 99234.74 | 1 | 2333227.5 | 2233992.76 | 99234.74 | Pending Scope & Cost Completion by Applicant |  | Obligated, Pending Scope & Cost Completion by Applicant | N/A | 1074712.85 | 11499.14 |  | 1086211.99 | -11217737.47 | 8100488.35 | 247967.31 | 2674863.91 | 80958.71 | 2426520.07 | 20166.62 | 13550964.97 | 13201872.33 | 349092.64 | DSOW – Submitted to COR3/PREPA | Submitted | Submitted to COR3 in Feb. 2026
178577 | FAASt [Cachete – MC 1526] (Substations) | Substation | Substation | No | Pending Scope & Cost Completion by Applicant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Pending Scope & Cost Completion by Applicant |  | Obligated, Pending Scope & Cost Completion by Applicant | N/A | 2275152.98 | 4322.89 |  | 2279475.87 | -43474460 | 23590868.47 | 6947025.75 | 2694924.72 | 918361.02 | 3261461.81 | 6061818.23 | 43474460 | 29547255 | 13927205 | DSOW – Scope and Cost development in progress | Q2 FY2027 | Currently under Scope revision by Planning
551914 | FAASt [Caparra 1912 & 1924] (Substation) | Substation | Substation | No | Pending Scope & Cost Completion by Applicant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Pending Scope & Cost Completion by Applicant |  | Obligated, Pending Scope & Cost Completion by Applicant | N/A | 1713915.25 | 2912.75 |  | 1716828 | -8912745.43 | 5432996.3672 | 827609.9065 | 552489.3929 | 188274.1735 | 668635.7665 | 1242739.8233 | 8912745.43 | 6654121.5267 | 2258623.9033 | DSOW – Submitted to COR3/PREPA | Q1 FY2027 | We resubmit DSOW on January 2026.
728827 | FAASt [Region 2 -Arecibo Group A] High Density (Vegetation) | Vegetation | Vegetation | Yes | Obligated | 4807675.47 | 13386633.34 | 79166.85 | 0 | 0 | 0 | 0 | 18273475.66 | 4886842.32 | 13386633.34 | Obligated | 2025-04-28 19:15 | Obligated | 86% | 847092.92 | 4070911.08 |  | 4918004 | 79166.85 | 4807675.47 | 13386633.34 | 0 | 259813.59 | 0 | 0 | 18194308.81 | 4807675.47 | 13646446.93 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Project is currently in execution
727606 | FAASt [Region 4 Caguas TL - 115kV] (Vegetation) | Vegetation | Vegetation-TL | Yes | Obligated | 900812.92 | 3080276.26 | 8389.21 | 0 | 0 | 0 | 0 | 3989478.39 | 909202.13 | 3080276.26 | Obligated | 2026-03-01 18:16 | Obligated | N/A | 97708.51 | 2559.18 |  | 100267.69 | -684527.74 | 1047946.55 | 3583235.86 | 9763.81 | 33059.91 | 0 | 0 | 4674006.13 | 1057710.36 | 3616295.77 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Total submitted estimated project cost is $32,248,051.77, however based on conversations with FEMA, only 12.63/87.14 miles are expected to be obligated. Costs reflect expected obligated cost with these reductions.
662238 | FAASt [Microwave Point-to-Point Backbone] (Telecommunications) | Telecommunication | IT/OT | No | Pending CRC Review | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Pending FEMA 406 HMP Completion |  | Obligated, Pending FEMA 406 HMP Completion | N/A | 1334035.28 | 1657.07 |  | 1335692.35 | -37461444.79 | 28822774.33 | 5421191.94 | 2708151.69 | 509326.83 | 0 | 0 | 37461444.79 | 31530926.02 | 5930518.77 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Proyect under CRC review by Feb 16th. Pending Obligation to determine Amendment submission date.
727692 | FAASt [Region 4 -Caguas Group A] High Density (Vegetation) | Vegetation | Vegetation | Yes | Obligated | 7414164.75 | 20637925.62 | 0 | 0 | 0 | 0 | 0 | 28052090.37 | 7414164.75 | 20637925.62 | Obligated | 2025-04-28 19:15 | Obligated | 76% | 1573121.52 | 4639985.9 |  | 6213107.42 | 0 | 7414164.75 | 20637925.62 | 0 | 328143.02 | 0 | 0 | 28052090.37 | 7414164.75 | 20966068.64 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Project is currently in execution
714641 | FAASt [Rincón Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 10842339.26 | 82026.55 | 1946225.97 | 106422.03 | 750618 | 506022 | 0 | 14233653.81 | 13539183.23 | 694470.58 | Obligated | 2026-03-01 18:15 | Obligated | N/A | 431237.39 | 307.56 |  | 431544.95 | -575351.95 | 10915553.24 | 588048.55 | 1928249.61 | 106422.03 | 753614 | 0 | 14809005.76 | 13597416.85 | 694470.58 | DSOW – Submitted to FEMA | Q4 FY2027 | Pending Homeland Security for final signature and start construction Grants portal total project cost is $14.2M
728832 | FAASt [Region 5 -Mayaguez Group A] High Density (Vegetation) | Vegetation | Vegetation | Yes | Obligated | 3767690.42 | 10493001.48 | 62820.38 | 0 | 0 | 0 | 0 | 14323512.28 | 3830510.8 | 10493001.48 | Obligated | 2025-04-28 19:15 | Obligated | 45% | 770354.12 | 2541535.09 |  | 3311889.21 | 62820.38 | 3767690.42 | 10493001.48 | 0 | 203638.57 | 0 | 0 | 14260691.9 | 3767690.42 | 10696640.05 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Project is currently in execution
746309 | FAASt [Automation Program Group 30] (Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 327791.49 | 109626.94 | 53695.19 | 28394.95 | 65212.75 | 98251.25 | 0 | 682972.57 | 446699.43 | 236273.14 | Obligated | 2026-03-01 18:16 | Obligated | N/A | 45237.83 | 4.5475e-13 |  | 45237.83 | -126646.2 | 327791.49 | 236273.14 | 53695.19 | 28394.95 | 65212.75 | 98251.25 | 809618.77 | 446699.43 | 362919.34 | DSOW – Submitted to FEMA | N/A | No Amendment Needed
956357 | FAASt [Mayaguez Region 5 Line 1900 – Dos Bocas HP to San Sebastian TC] (Vegetation) | Vegetation | Vegetation-TL | No | Pending Scope & Cost Completion by Applicant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Pending Final FEMA Review |  | Obligated, Pending Final FEMA Review | N/A | 1054.59 | 0 |  | 1054.59 | -5529976.18 | 1290814.82 | 3837707.16 | 107228.43 | 294225.77 | 0 | 0 | 5529976.18 | 1398043.25 | 4131932.93 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Total submitted estimated project cost is $13,419,649.03, however based on conversations with FEMA, only 9.21/22.35 miles are expected to be obligated. Costs reflect expected obligated cost with these reductions.
956340 | FAASt [Ponce Region 6 Feeder 5602-02] (Vegetation) | Vegetation | Vegetation-DT | No | Pending EHP Review | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Pending EHP Review |  | Obligated, Pending EHP Review | N/A | 199.29 | 0 |  | 199.29 | -6960217.5 | 1624663.76 | 4830269.73 | 134961.38 | 370322.63 | 0 | 0 | 6960217.5 | 1759625.14 | 5200592.36 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Project is pending FEMA obligation
727531 | FAASt [Region 6 -Ponce Group A] High Density (Vegetation) | Vegetation | Vegetation | Yes | Obligated | 6849050.26 | 19064883.85 | 0 | 0 | 0 | 0 | 0 | 25913934.11 | 6849050.26 | 19064883.85 | Obligated | 2025-04-28 19:15 | Obligated | 58% | 1013304.96 | 5383764.2 |  | 6397069.16 | 0 | 6849050.26 | 19064883.85 | 0 | 369745.52 | 0 | 0 | 25913934.11 | 6849050.26 | 19434629.37 | Obligated -No expected changes | N/A | Project is currently in execution
738672 | FAASt [Pole and Conductor Repair - Mayaguez Group 1 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 10313627 | 306131.37 | 834793 | 0 | 0 | 0 | 0 | 11454551.37 | 11148420 | 306131.37 | Obligated | 2024-11-25 16:15 | Obligated | 70% | 871847.36 | 8387939.78 |  | 9259787.14 | 0 | 10313627 | 243128.63 | 834793 | 63002.37 | 0 | 0 | 11454551.37 | 11148420 | 306131 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
738670 | FAASt [Pole and Conductor Repair - Ponce Group 1 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 4926640 | 147871.01 | 439974.62 | 0 | 0 | 0 | 0 | 5514485.63 | 5366614.62 | 147871.01 | Obligated | 2024-11-25 16:15 | Obligated | 94% | 661280.6 | 3322915 |  | 3984195.6 | -0.38 | 4926640.11 | 116500.1 | 439975 | 31370.9 | 0 | 0 | 5514486.01 | 5366615.11 | 147871 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
679127 | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 3] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 171152.23 | 46010.58 | 33340.3 | 0 | 0 | 0 | 0 | 250503.11 | 204492.53 | 46010.58 | Obligated | 2022-12-27 11:53 | Obligated | 88% | 52521.43 | 125072.43 |  | 177593.86 | -2826160 | 2569486.15 | 1816.46 | 240897.11 | 1170.09 | 251407.95 | 11885.35 | 3076663.11 | 3061791.21 | 14871.9 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
674083 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 1747929 | 362533 | 335722 | 0 | 0 | 0 | 0 | 2446184 | 2083651 | 362533 | Obligated | 2022-08-08 11:30 | Obligated | 80% | 306580.88 | 1527801.4 |  | 1834382.28 | 0.1 | 1747929 | 286587 | 335721.9 | 75946 | 0 | 0 | 2446183.9 | 2083650.9 | 362533 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
673772 | FAASt [Distribution Pole and Conductor Repair - Mayagüez Group 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 3286536 | 835984 | 636837 | 0 | 0 | 0 | 0 | 4759357 | 3923373 | 835984 | Obligated | 2022-10-24 11:36 | Obligated | 83% | 542710.83 | 3111666.29 |  | 3654377.12 | -4195457.95 | 7474369.54 | 3899.16 | 696566.78 | 2495.46 | 751912.5 | 25571.51 | 8954814.95 | 8922848.82 | 31966.13 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
673838 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 284349 | 73265 | 55025 | 0 | 0 | 0 | 0 | 412639 | 339374 | 73265 | Obligated | 2022-07-12 11:39 | Obligated | 85% | 138402.39 | 313557.05 |  | 451959.44 | 1 | 284349 | 57917 | 55024 | 15348 | 0 | 0 | 412638 | 339373 | 73265 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
673836 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 1] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 4686914.68 | 1064121.8 | 900014.8 | 0 | 0 | 0 | 0 | 6651051.28 | 5586929.48 | 1064121.8 | Obligated | 2022-12-21 12:37 | Obligated | 86% | 514464.94 | 5304918.59 |  | 5819383.53 | -0.2 | 4686914.68 | 1064121.8 | 900015 | 0 | 0 | 0 | 6651051.48 | 5586929.68 | 1064121.8 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
752808 | FAASt [Automation Program Group 19] (TL/Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 2753627.24 | 0 | 348510.65 | 0 | 143163.5 | 312122.7 | 1 | 3557424.09 | 3245301.39 | 312122.7 | Pending EHP Review | 2025-02-06 20:16 | Obligated, Pending EHP Review | 85% | 365793.35 | 1238377.93 |  | 1604171.28 | 853505.95 | 1352947.241 | 723597.72 | 119711.919 | 52375.13 | 134857.23 | 320428.9 | 2703918.14 | 1607516.39 | 1096401.75 | Amendment – Submitted to FEMA | Submitted | 406HM Revision on FEMA CRC / Estimated date Cfci strategy to be defined
673771 | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 1] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 1894033.53 | 472527 | 370850.25 | 0 | 0 | 0 | 0 | 2737410.78 | 2264883.78 | 472527 | Obligated | 2022-10-17 11:37 | Obligated | 86% | 646696.55 | 1011911.9 |  | 1658608.45 | 0.25 | 1894033.53 | 373539 | 370850 | 98988 | 0 | 0 | 2737410.53 | 2264883.53 | 472527 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
688627 | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 9] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 303774 | 72188.49 | 58918 | 0 | 0 | 0 | 0 | 434880.49 | 362692 | 72188.49 | Obligated | 2023-01-31 12:56 | Obligated | 84% | 45814.58 | 163661.74 |  | 209476.32 | 0 | 303774 | 72188.49 | 58918 | 0 | 0 | 0 | 434880.49 | 362692 | 72188.49 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
679134 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 10] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 452956.93 | 97485.57 | 86724.25 | 13114.65 | 0 | 0 | 0 | 650281.4 | 539681.18 | 110600.22 | Obligated | 2023-01-10 13:19 | Obligated | 94% | 78944.82 | 524069.06 |  | 603013.88 | 0.25 | 452956.93 | 87431 | 86724 | 23169.22 | 0 | 0 | 650281.15 | 539680.93 | 110600.22 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
682882 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 11] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 545661.24 | 113378.16 | 104353.35 | 0 | 0 | 0 | 0 | 763392.75 | 650014.59 | 113378.16 | Obligated | 2023-01-10 13:19 | Obligated | 85% | 74890.91 | 572134.2 |  | 647025.11 | 0.51 | 545661.24 | 89627 | 104353 | 23751.16 | 0 | 0 | 763392.24 | 650014.24 | 113378.16 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
682324 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 13] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 573047.24 | 120034.21 | 110616.4 | 16148.1 | 0 | 0 | 0 | 819845.95 | 683663.64 | 136182.31 | Obligated | 2023-01-10 13:19 | Obligated | 82% | 85417.83 | 664925.8 |  | 750343.63 | 0 | 573047.24 | 107654 | 110616.4 | 28528.31 | 0 | 0 | 819845.95 | 683663.64 | 136182.31 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
682373 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 14] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 65944 | 10278 | 12740 | 1383 | 0 | 0 | 0 | 90345 | 78684 | 11661 | Obligated | 2023-01-10 13:19 | Obligated | 90% | 22981.33 | 56953.82 |  | 79935.15 | 0 | 65944 | 9218 | 12740 | 2443 | 0 | 0 | 90345 | 78684 | 11661 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
704844 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 16-17-18-19-20] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 320740 | 88558 | 62490 | 0 | 0 | 0 | 0 | 471788 | 383230 | 88558 | Obligated | 2023-05-17 11:31 | Obligated | 86% | 94560.77 | 238358.7 |  | 332919.47 | 0 | 320740 | 70006 | 62490 | 18552 | 0 | 0 | 471788 | 383230 | 88558 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
679033 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 9] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 729040 | 179902 | 140628 | 0 | 0 | 0 | 0 | 1049570 | 869668 | 179902 | Obligated | 2022-12-27 11:53 | Obligated | 89% | 78826.32 | 834139.58 |  | 912965.9 | 0 | 729040 | 142215 | 140628 | 37687 | 0 | 0 | 1049570 | 869668 | 179902 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
679457 | FAASt [Distribution Pole and Conductor Repair - Ponce Group 3] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 589335 | 157153 | 115386 | 0 | 0 | 0 | 0 | 861874 | 704721 | 157153 | Obligated | 2022-12-27 11:53 | Obligated | 86% | 106213.98 | 540665.14 |  | 646879.12 | 0 | 589335 | 123232 | 115386 | 33921 | 0 | 0 | 861874 | 704721 | 157153 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
679458 | FAASt [Distribution Pole and Conductor Repair - Ponce Group 4] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 498436 | 84160 | 95421 | 11322 | 0 | 0 | 0 | 689339 | 593857 | 95482 | Obligated | 2023-01-10 13:19 | Obligated | 88% | 61634.48 | 469886.88 |  | 531521.36 | 0 | 498436 | 75480 | 95421 | 20002 | 0 | 0 | 689339 | 593857 | 95482 | Obligated -No expected changes | N/A | Project will be versioned prior to close out if needed.
956341 | FAASt [Ponce Region 6 Feeder 5803-02] (Vegetation) | Vegetation | Vegetation-DT | No | Pending EHP Review | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Pending Award |  | Obligated, Pending Award | N/A | 249.91 | 0 |  | 249.91 | -103160.88 | 24080 | 71591.83 | 2000.35 | 5488.7 | 0 | 0 | 103160.88 | 26080.35 | 77080.53 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Project is pending FEMA obligation
741105 | FAASt [All Regions TL - 230kV] (Vegetation) | Vegetation | Vegetation-TL | Yes | Obligated | 2430054.31 | 10455751.16 | 22529.43 | 0 | 0 | 0 | 0 | 12908334.9 | 2452583.74 | 10455751.16 | Obligated | 2026-03-01 18:15 | Obligated | N/A | 36917.5 | 0 |  | 36917.5 | -146128084.41 | 30099566.86 | 127486673.75 | 279159.4 | 1171019.3 | 0 | 0 | 159036419.31 | 30378726.26 | 128657693.05 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Total submitted estimated project cost is $159,036,419.31, however based on conversations with FEMA, only 38.21/402.54 miles are expected to be obligated. Costs reflect expected obligated cost with these reductions.
956345 | FAASt [Arecibo Region 2 Line 2400 – Dos Bocas HP to Coronillas 2] (Vegetation) | Vegetation | Vegetation-TL | No | Pending Scope & Cost Completion by Applicant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Pending Award |  | Obligated, Pending Award | N/A | 938.25 | 0 |  | 938.25 | -2399674.76 | 560135.46 | 1665332.49 | 46530.65 | 127676.16 | 0 | 0 | 2399674.76 | 606666.11 | 1793008.65 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Total submitted estimated project cost is $7,736,264.86, however based on conversations with FEMA, only 4.02/12.96 miles are expected to be obligated. Costs reflect expected obligated cost with these reductions.
956348 | FAASt [Bayamon Region 3 Line 10000 – Bayamon Pueblo to Magnolia TO] (Vegetation) | Vegetation | Vegetation-TL | No | Pending Scope & Cost Completion by Applicant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Pending Award |  | Obligated, Pending Award | N/A | 543.47 | 0 |  | 543.47 | -342452.79 | 79935.82 | 237656.27 | 6640.3 | 18220.4 | 0 | 0 | 342452.79 | 86576.12 | 255876.67 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Total submitted estimated project cost is $1,260,848.93, however based on conversations with FEMA, only 0.66/2.43 miles are expected to be obligated. Costs reflect expected obligated cost with these reductions.
956330 | FAASt [Caguas Region 4 - Feeder 3007-03] (Vegetation) | Vegetation | Vegetation-DT | No | Pending QA Review | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Pending Large Project Review |  | Obligated, Pending Large Project Review | N/A | 249.91 | 0 |  | 249.91 | -8434629.77 | 1968823.15 | 5853486.17 | 163550.83 | 448769.62 | 0 | 0 | 8434629.77 | 2132373.98 | 6302255.79 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Project is pending FEMA obligation
169495 | FAASt [Substations - Tapia GIS Rebuilt Equipment Repair &amp;amp; Replacement] (Substations) | Substation | Substation Rebuilds | Yes | Obligated | 8180049.03 | 7159883.3 | 1397859.52 | 0 | 0 | 0 | 0 | 16737791.85 | 9577908.55 | 7159883.3 | Obligated | 2023-08-22 11:21 | Obligated | 8% | 2109213.46 | 30423.56 |  | 2139637.02 | -2812372.5625 | 6681615.89 | 1589026.4125 | 944927.79 | 429312.71 | 5815884.59 | 4089397.02 | 19550164.4125 | 13442428.27 | 6107736.1425 | Amendment – Amendment Needed/Pending Development | Q1 FY2027 | Pending IFC to complete Estimate review
174422 | FAASt - Catano-Rebuild 1801(Substation) | Substation | Substation | Yes | Obligated | 16359899.17 | 6895149.77 | 1211174.91 | 0 | 0 | 0 | 0 | 24466223.85 | 17571074.08 | 6895149.77 | Obligated | 2022-05-18 11:30 | Obligated | 66% | 5510502.25 | 11157823.46 |  | 16668325.71 | -5038399.16 | 16677900.7662 | 2540549.443 | 3127217.3734 | 1291524.2237 | 2052539.7423 | 3814891.4615 | 29504623.01 | 21857657.8819 | 7646965.1281 | Amendment – Amendment Needed/Pending Development | Q4 FY2026 | Pending IFC package to include all the changes in scope as part of the DSOW ammendment.
956339 | FAASt [Caguas Region 4 - Feeder 3301-01] (Vegetation) | Vegetation | Vegetation-DT | No | Pending Insurance Completion | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Pending Large Project Review |  | Obligated, Pending Large Project Review | N/A | 249.91 | 0 |  | 249.91 | -12678923.88 | 2959532.24 | 8798952.37 | 245849.34 | 674589.93 | 0 | 0 | 12678923.88 | 3205381.58 | 9473542.3 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Project is pending FEMA obligation
956337 | FAASt [Mayaguez Region 5 Feeder 6012-02] (Vegetation) | Vegetation | Vegetation-DT | No | Pending EHP Review | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Pending Large Project Review |  | Obligated, Pending Large Project Review | N/A | 690.25 | 0 |  | 690.25 | -7714425.51 | 1800712.05 | 5353676.97 | 149585.76 | 410450.73 | 0 | 0 | 7714425.51 | 1950297.81 | 5764127.7 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Project is pending FEMA obligation
660422 | FAASt [Physical Security - Group 4] (Substation) | Substation | Substation Security | Yes | Obligated | 3478518 | 338280 | 460523 | 0 | 0 | 0 | 0 | 4277321 | 3939041 | 338280 | Obligated | 2023-12-29 12:31 | Obligated | 43% | 279040.58 | 1035431.54 |  | 1314472.12 | -306092 | 3478518 | 226650 | 766618 | 111627 | 0 | 0 | 4583413 | 4245136 | 338277 | Amendment – Amendment Needed/Pending Development | Q1 FY2027 | E&M allocations not included in original obligation
549725 | FAASt [Substation Minor Repairs - Group E] (Substation) | Substation | Substation | Yes | Obligated | 3924015.69 | 568439.05 | 98349.5 | 11328.47 | 0 | 0 | 0 | 4602132.71 | 4022365.19 | 579767.52 | Obligated | 2024-05-10 10:17 | Obligated | 57% | 456120.13 | 2775409.5 |  | 3231529.63 | -719877.74 | 3924015.69 | 377039.3 | 818227.24 | 202728.22 | 0 | 0 | 5322010.45 | 4742242.93 | 579767.52 | Amendment – Amendment Needed/Pending Development | Q1 FY2027 | E&M allocations not included in original obligation
956331 | FAASt [Mayaguez Region 5 Feeder 6014-02] (Vegetation) | Vegetation | Vegetation-DT | No | Pending EHP Review | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Pending Large Project Review |  | Obligated, Pending Large Project Review | N/A | 143.61 | 0 |  | 143.61 | -8472327.72 | 1977622.66 | 5879647.9 | 164281.79 | 450775.37 | 0 | 0 | 8472327.72 | 2141904.45 | 6330423.27 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Project is pending FEMA obligation
549715 | FAASt Substation Minor Repairs - Group D (Substation) | Substation | Substation Rebuilds | Yes | Obligated | 2583133.54 | 288123.63 | 580188.69 | 0 | 0 | 0 | 0 | 3451445.86 | 3163322.23 | 288123.63 | Obligated | 2024-04-12 11:19 | Obligated | 33% | 419380.77 | 380949.36 |  | 800330.13 | 0.05 | 2583133.54 | 182993.64 | 580188.69 | 105129.94 | 0 | 0 | 3451445.81 | 3163322.23 | 288123.58 | Amendment – Amendment Needed/Pending Development | Q1 FY2027 | E&M allocations not included in original obligation
956343 | FAASt [Ponce Region 6 Line 4800 – Toro Negro to Aibonito, Santa Isabel] (Vegetation) | Vegetation | Vegetation-TL | No | Pending Scope & Cost Completion by Applicant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Pending Large Project Review |  | Obligated, Pending Large Project Review | N/A | 913.96 | 0 |  | 913.96 | -7870225.21 | 1837079.03 | 5461799.24 | 152606.78 | 418740.16 | 0 | 0 | 7870225.21 | 1989685.81 | 5880539.4 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Total submitted estimated project cost is $22,582,890.08, however based on conversations with FEMA, only 13.86/39.77 miles are expected to be obligated. Costs reflect expected obligated cost with these reductions.
727522 | FAASt [Region 3 Bayamon TL - 115kV] (Vegetation) | Vegetation | Vegetation-TL | Yes | Obligated | 778850.12 | 2663231.73 | 7253.38 | 0 | 0 | 0 | 0 | 3449335.23 | 786103.5 | 2663231.73 | Obligated | 2026-03-01 18:16 | Obligated | N/A | 28305.6 | 0 |  | 28305.6 | -595665.69 | 906918.96 | 3101021.26 | 8449.84 | 28610.86 | 0 | 0 | 4045000.92 | 915368.8 | 3129632.12 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Total submitted estimated project cost is $19,606,400.98 however based on conversations with FEMA, only 10.92/52.93 miles are expected to be obligated. Costs reflect expected obligated cost with these reductions.
678800 | FAASt [Telecom Infrastructure – Group B] (Telecommunication) | Telecommunication | IT/OT | Yes | Obligated | 13148929.44 | 45408.4 | 2828793.1 | 10487.44 | 0 | 0 | 0 | 16033618.38 | 15977722.54 | 55895.84 | Obligated | 2025-11-05 16:17 | Obligated | 0% | 2069779.45 | 244332.31 |  | 2314111.76 | 0 | 13148929.44 | 45408.4 | 2828793.1 | 10487.44 | 0 | 0 | 16033618.38 | 15977722.54 | 55895.84 | Amendment – Pending Design Package for Development | Q1 FY2027 | Design Package expected Jun 2026.
673292 | FAASt Telecom Infrastructure - Cerro Puntas (Telecommunication) | Telecommunication | IT/OT | Yes | Obligated | 8124106.79 | 44186.49 | 1075319.59 | 4963.76 | 4917.07 | 427.57 | 0 | 9253921.27 | 9204343.45 | 49577.82 | Obligated | 2025-10-30 20:15 | Obligated | 0% | 865333.82 | 56242.57 |  | 921576.39 | 0.0012 | 8124106.79 | 44186.4888 | 1075319.59 | 4963.76 | 4917.0688 | 427.5712 | 9253921.2688 | 9204343.4488 | 49577.82 | Amendment – Pending Design Package for Development | Q1 FY2027 | Design Package expected Jun 2026.
714654 | FAASt [Advanced Metering Infrastructure (AMI)] (Telecommunications) | Telecommunication | AMI Implementation Program | Yes | Obligated | 332062581 | 541786319 | 1484008 | 2421276 | 0 | 0 | 0 | 877754184 | 333546589 | 544207595 | Obligated | 2023-12-08 11:19 | Obligated | 9% | 58318159.91 | 130591789.45 |  | 188909949.36 | -14966915 | 332062581 | 541786319 | 16450923 | 2421276 | 0 | 0 | 892721099 | 348513504 | 544207595 | Obligated -No expected changes | Submitted | Already Submitted
727657 | FAASt [Region 5 Mayaguez TL - 115kV] (Vegetation) | Vegetation | Vegetation-TL | Yes | Obligated | 577718.5 | 1975474.09 | 5380.25 | 0 | 0 | 0 | 0 | 2558572.84 | 583098.75 | 1975474.09 | Obligated | 2026-03-01 18:16 | Obligated | N/A | 4379.07 | 0 |  | 4379.07 | -439008.29 | 672079.74 | 2298037.25 | 6261.82 | 21202.32 | 0 | 0 | 2997581.13 | 678341.56 | 2319239.57 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Total submitted estimated project cost is $23,077,673.93, however based on conversations with FEMA, only 8.1/62.36 miles are expected to be obligated. Costs reflect expected obligated cost with these reductions.
750168 | FAASt [ Transmission Priority Pole Replacement Program Line 4800 Santa Isabel TC – Aibonito TO] (Transmission) | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 431757.15 | 28284.79 | 45787.13 | 3335.39 | 36682.34 | 5852.66 | 0 | 551699.46 | 514226.62 | 37472.84 | Obligated | 2025-11-25 18:15 | Obligated | 0% | 40356.92 | 586.81 |  | 40943.73 | 0 | 428428.21 | 31613.73 | 45787.13 | 3335.39 | 40011.28 | 2523.72 | 551699.46 | 514226.62 | 37472.84 | Obligated -No expected changes | N/A | Already Submitted
727529 | FAASt [Region 6 Ponce TL - 115kV] (Vegetation) | Vegetation | Vegetation-TL | Yes | Obligated | 1879368.2 | 6426387.93 | 17502.43 | 0 | 0 | 0 | 0 | 8323258.56 | 1896870.63 | 6426387.93 | Obligated | 2026-03-01 18:15 | Obligated | N/A | 5787.03 | 0 |  | 5787.03 | -126354.96 | 1894465.49 | 6477731.82 | 17650.9 | 59765.31 | 0 | 0 | 8449613.52 | 1912116.39 | 6537497.13 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Total submitted estimated project cost is $57,838,512.87, however based on conversations with FEMA, only 22.79/156 miles are expected to be obligated. Costs reflect expected obligated cost with these reductions.
956335 | FAASt [San Juan Region 1 - Feeder 2301-02] (Vegetation) | Vegetation | Vegetation-DT | No | Pending EHP Review | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Pending EHP Review |  | Obligated, Pending EHP Review | N/A | 202.46 | 0 |  | 202.46 | -7925388.21 | 1849955.27 | 5500081.4 | 153676.43 | 421675.11 | 0 | 0 | 7925388.21 | 2003631.7 | 5921756.51 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Project is pending FEMA obligation
956332 | FAASt [San Juan Region 1 - Feeder 2401-01] (Vegetation) | Vegetation | Vegetation-DT | No | Pending EHP Review | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Pending EHP Review |  | Obligated, Pending EHP Review | N/A | 47.52 | 0 |  | 47.52 | -11940018.46 | 2787055.9 | 8286164.87 | 231521.7 | 635275.99 | 0 | 0 | 11940018.46 | 3018577.6 | 8921440.86 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | Project is pending FEMA obligation
751655 | FAASt [Culebra Microgrid] (Transmission) | Transmission | Vieques and Culebra Projects (6) | No | Pending Scope & Cost Completion by Applicant | 0 | 0 | 0 | 0 | 0 | 14497546.99 | 1 | 14497546.99 | 0 | 14497546.99 | Pending Scope & Cost Completion by Applicant |  | Obligated, Pending Scope & Cost Completion by Applicant | N/A | 662740.83 | 0 |  | 662740.83 | -56297524.97 | 287219.87 | 55806508.56 | 15173.21 | 5897280.98 | 0 | 8788889.34 | 70795071.96 | 302393.08 | 70492678.88 | DSOW – Pending Design Package for Development | Q2 FY2027 | The DSOW Revision 2 for the Vieques and Culebra Microgrid was submitted in July 2025. After receiving various Requests for Information (RFIs) from FEMA related to the design, an internal decision was made to re-submit the DSOW once the 30% design is completed, providing more robust information to adequately address the agency’s requests. As of today, the DSOW is estimated to be re-submitted in October 2026 following the completion of the 60% design.
749072 | FAASt [Transmission Priority Pole Replacement Program Line 2700 Aguadilla Hospital Distrito Sect – Mora TC] (Transmission) | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 767377.79 | 54738.82 | 73616.34 | 4890.99 | 55935.65 | 0 | 0 | 956559.59 | 896929.78 | 59629.81 | Obligated | 2025-11-05 16:16 | Obligated | 0% | 317290.12 | 928.59 |  | 318218.71 | -5271.74 | 763811.92 | 51189.5 | 68678.99 | 4322.92 | 69251.52 | 4576.48 | 961831.33 | 901742.43 | 60088.9 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | No Amendment Needed
753782 | FAASt [Transmission Priority Pole Replacement Program Line 3100 Monacillos TC – Sabana Llana TC] (Transmission) | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 129361.92 | 1927.77 | 20500.96 | 291.07 | 5970.66 | 0 | 0 | 158052.38 | 155833.54 | 2218.84 | Obligated | 2025-10-30 20:15 | Obligated | 0% | 153880.76 | 277.28 |  | 154158.04 | -52680822.39 | 32064811.63 | 4437681.65 | 3286608.94 | 1116082.17 | 4091238.32 | 7842452.06 | 52838874.77 | 39442658.89 | 13396215.88 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | No Amendment Needed
750150 | FAASt [Transmission Priority Pole Replacement Program Line 4800 Santa Isabel TC – Toro Negro 1 HP] (Transmission) | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 125923.56 | 7149.12 | 19852.4 | 1075.68 | 5971.66 | 0 | 0 | 159972.42 | 151747.62 | 8224.8 | Obligated | 2025-11-05 16:16 | Obligated | 0% | 70395.96 | 0 |  | 70395.96 | 0 | 125923.56 | 5675.78 | 19852.4 | 1075.68 | 5971.66 | 1473.34 | 159972.42 | 151747.62 | 8224.8 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | No Amendment Needed
756999 | FAASt [TL 1900 Lares TO to San Sebastian] (Transmission) | Transmission | Transmission Line Rebuild | No | Pending Scope & Cost Completion by Applicant | 0 | 0 | 0 | 0 | 1449761.7 | 0 | 0 | 1449761.7 | 1449761.7 | 0 | Pending PDMG Scope & Cost Routing |  | Obligated, Pending PDMG Scope & Cost Routing | N/A | 324845.85 | 0 |  | 324845.85 | -34646956.53 | 25335445.6 | 4067258.81 | 2040875.23 | 429319.88 | 2446381.79 | 1777436.92 | 36096718.23 | 29822702.62 | 6274015.61 | DSOW – Submitted to COR3/PREPA | Submitted | Already Submitted
750151 | FAASt [Transmission Priority Pole Replacement Program Line 700 Costa Sur SP – Yauco 2 HP] (Transmission) | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 243268.16 | 9181.75 | 23495.18 | 1041.06 | 16785.94 | 2341.06 | 0 | 296113.15 | 283549.28 | 12563.87 | Obligated | 2026-01-16 16:15 | Obligated | 0% | 44406.69 | 309.53 |  | 44716.22 | -1479265.81 | 1508927.85 | 9181.75 | 131787.84 | 648.92 | 107681.05 | 17151.55 | 1775378.96 | 1748396.74 | 26982.22 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | No Amendment Needed
749060 | FAASt [Transmission Priority Pole Replacement Program Line 5600 Victoria TC – Añasco TC] (Transmission) | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 1175435.49 | 111409.61 | 120608.99 | 11800 | 141345.83 | 17467.93 | 0 | 1578067.85 | 1437390.31 | 140677.54 | Obligated | 2026-03-01 18:16 | Obligated | N/A | 308615.22 | 0 |  | 308615.22 | 61166.77 | 425379.95 | 829239.3 | 40970.81 | 86903.02 | 19608.94 | 114799.06 | 1516901.08 | 485959.7 | 1030941.38 | DSOW – Submitted to FEMA -Currently under FEMA evaluation | Submitted | No Amendment Needed
168226 | FAASt San Juan 115kV Underground Transmission | Transmission | Transmission Line Rebuild | Yes | Obligated | 14746039.57 | 0 | 2258339.67 | 0 | 0 | 0 | 0 | 17004379.24 | 17004379.24 | 0 | Obligated | 2022-12-21 12:37 | Obligated | 0% | 1567383.54 | 58077.11 |  | 1625460.65 | 2250000 | 12496039.57 | 0 | 2258339.67 | 0 | 0 | 0 | 14754379.24 | 14754379.24 | 0 | Obligated -No expected changes | N/A | Scope confirmation under discussion to create amendment Insurance deduction of $2,250,000
684920 | FAASt Substation High Voltage Replacement_Group 1 (Substation) | Substation | Substation Rebuilds | Yes | Obligated | 6929384 | 0 | 958084 | 0 | 0 | 0 | 0 | 7887468 | 7887468 | 0 | Obligated | 2023-12-29 12:31 | Obligated | 82% | 5632387.78 | 7711675.88 |  | 13344063.66 | 2370998.42 | 3874950.13 | 0 | 458489.44 | 0 | 1183030.01 | 0 | 5516469.58 | 5516469.58 | 0 | Obligated -No expected changes | N/A | No Amendment Needed
708637 | FAASt T-Pole Program Line 3700] (Transmission) | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 303960.92 | 64939.04 | 39573.63 | 8454.62 | 0 | 0 | 0 | 416928.21 | 343534.55 | 73393.66 | Obligated | 2024-08-26 10:08 | Obligated | 90% | 662482.32 | 830133.34 |  | 1492615.66 | 62276.11 | 255862.85 | 38293.66 | 30158.85 | 4783.59 | 20073.47 | 5479.68 | 354652.1 | 306095.17 | 48556.93 | Obligated -No expected changes | N/A | No Amendment Needed
681672 | FAASt Transmission Priority Pole Replacements | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 214124 | 2243 | 26175 | 0 | 0 | 0 | 0 | 242542 | 240299 | 2243 | Obligated | 2023-01-31 12:56 | Obligated | 90% | 389270.4 | 443970.12 |  | 833240.52 | -105454.09 | 271850.8 | 4298.39 | 27464.76 | 560.49 | 41708.61 | 2113.04 | 347996.09 | 341024.17 | 6971.92 | Obligated -No expected changes | N/A | No Amendment Needed
711670 | FAASt [T-Pole Program Line 100] (Transmission) | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 94787.57 | 23372.71 | 12340.69 | 0 | 0 | 0 | 0 | 130500.97 | 107128.26 | 23372.71 | Obligated | 2024-06-18 11:28 | Obligated | 93% | 245506.97 | 215837.69 |  | 461344.66 | -4770.88 | 102171.23 | 13243.54 | 16958.53 | 1285.62 | 662.57 | 950.36 | 135271.85 | 119792.33 | 15479.52 | Obligated -No expected changes | N/A | No Amendment Needed
712980 | FAASt [T-Pole Program Line 3000] (Transmission) | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 559076.77 | 72117.49 | 72787.96 | 0 | 0 | 0 | 0 | 703982.22 | 631864.73 | 72117.49 | Obligated | 2024-11-01 15:15 | Obligated | 77% | 1072412.88 | 701044.83 |  | 1773457.71 | 375341.92 | 232028.81 | 37424.09 | 28581 | 4483.52 | 23456.66 | 2666.22 | 328640.3 | 284066.47 | 44573.83 | Obligated -No expected changes | N/A | No Amendment Needed
801172 | FAASt [Feeder Rebuild # 1529-15] (Distribution) | Distribution | Feeders | Yes | Obligated | 2285961 | 0 | 508777.01 | 0 | 243286.39 | 0 | 0 | 3038024.4 | 3038024.4 | 0 | Pending Amendment Processing | 2025-09-17 18:16 | Obligated, Pending Amendment Processing | 0% | 1425398.04 | 51437.79 |  | 1476835.83 | 345439.6 | 1862738.37 | 50953.86 | 568090.34 | 22194.71 | 160515.06 | 28092.46 | 2692584.8 | 2591343.77 | 101241.03 | Amendment – Submitted to FEMA | Submitted | Working on re-versioning (PA-428 & HM-406 already submitted to FEMA), to be submitted to FEMA on Feb 2026
735474 | FAASt [Pole and Conductor Repair -Caguas Group 3 Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 14075641 | 0 | 1962096.73 | 0 | 1317347.93 | 295487.07 | 1 | 17650572.73 | 17355085.66 | 295487.07 | Pending Amendment Processing | 2025-09-17 18:16 | Obligated, Pending Amendment Processing | 47% | 1724027.43 | 10902862.7 |  | 12626890.13 | -2814816.56 | 17211915.22 | 71311.91 | 1524520.51 | 44806.65 | 1144636.03 | 468198.97 | 20465389.29 | 19881071.76 | 584317.53 | Amendment – Submitted to FEMA | Submitted | DSOW – Submitted to FEMA -Currently under FEMA evaluation
750692 | FAASt [Pole and Conductor Repair - Mayaguez Group 3 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 12921047 | 0 | 1799743 | 0 | 1096303.06 | 395734.94 | 1 | 16212828 | 15817093.06 | 395734.94 | Pending Amendment Processing | 2025-09-25 16:15 | Obligated, Pending Amendment Processing | 27% | 1235245.48 | 4593133.24 |  | 5828378.72 | -2299369.46 | 15534571.38 | 65783.22 | 1378411.7 | 41393.16 | 1059507.72 | 432530.28 | 18512197.46 | 17972490.8 | 539706.66 | Amendment – Submitted to FEMA | Submitted | DSOW – Submitted to FEMA -Currently under FEMA evaluation
752540 | FAASt [Pole and Conductor Repair -Mayaguez Group 4 Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 7111613.91 | 0 | 991211.9 | 0 | 628196.69 | 241421.21 | 1 | 8972443.71 | 8731022.5 | 241421.21 | Pending Amendment Processing | 2025-09-25 16:15 | Obligated, Pending Amendment Processing | 0% | 414698.41 | 135811.89 |  | 550510.3 | -1416517.53 | 8687329.99 | 35434.35 | 773151.6 | 23427.4 | 622940.21 | 246677.69 | 10388961.24 | 10083421.8 | 305539.44 | Amendment – Submitted to FEMA | Submitted | DSOW – Submitted to FEMA -Currently under FEMA evaluation
752810 | FAASt [Automation Program Group 20] (TL/Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 2623262.08 | 0 | 333695.7 | 0 | 209802.68 | 349543.04 | 1 | 3516303.5 | 3166760.46 | 349543.04 | Pending PDMG Scope & Cost Routing | 2025-02-06 20:16 | Obligated, Pending PDMG Scope & Cost Routing | 77% | 433255.05 | 930843.98 |  | 1364099.03 | 212467.14 | 1645985.22 | 847714.06 | 176266.8 | 72284.36 | 202809.71 | 358776.21 | 3303836.36 | 2025061.73 | 1278774.63 | Amendment – Submitted to FEMA | Submitted | Open Soft RFI to revise soft Cost will be submitted 02/20 / Estimated date Cfci strategy to be defined
757662 | FAASt [Automation Program Group 21] (Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 2356733.87 | 0 | 280516.59 | 0 | 512796.48 | 0 | 0 | 3150046.94 | 3150046.94 | 0 | Obligated | 2025-10-30 20:15 | Obligated | 8% | 228520.47 | 17727.94 |  | 246248.41 | 646185.93 | 1284891.5683 | 425656.3717 | 205400.7597 | 75115.8303 | 162255.9386 | 350540.5414 | 2503861.01 | 1652548.2666 | 851312.7434 | Amendment – Amendment Needed/Pending Development | Q1 FY2027 | 406HM Revision to be submitted June 2026 / Estimated date Cfci strategy to be defined
757689 | FAASt [Automation Program Group 24] (Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 1774822 | 0 | 299299.32 | 0 | 562828 | 0 | 0 | 2636949.32 | 2636949.32 | 0 | Pending Amendment Request Approval | 2025-09-17 19:15 | Obligated, Pending Amendment Request Approval | 40% | 405037.61 | 1273278.52 |  | 1678316.13 | -182392.69 | 1598412.2339 | 442039.2361 | 142037.0968 | 67265.4432 | 168735.76 | 400852.24 | 2819342.01 | 1909185.0907 | 910156.9193 | Amendment – Submitted to FEMA | Submitted | Open Soft RFI to revise soft Cost will be submitted 02/20 / Estimated date Cfci strategy to be defined
757692 | FAASt [Automation Program Group 26] (TL / Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 938783.63 | 0 | 175325.33 | 0 | 169539 | 256947 | 1 | 1540594.96 | 1283647.96 | 256947 | Pending PDMG Scope & Cost Routing | 2025-09-03 20:15 | Obligated, Pending PDMG Scope & Cost Routing | 50% | 178504.71 | 975235.86 |  | 1153740.57 | -316917.17 | 805588.09 | 597770.7 | 71140.9 | 41960.7 | 89982.74 | 251069 | 1857512.13 | 966711.73 | 890800.4 | Amendment – Submitted to FEMA | Submitted | Open Soft RFI to revise soft Cost will be submitted 02/20 / Estimated date Cfci strategy to be defined
956356 | FAASt [Ponce Region 6 Transmission Line 39000 – Aguas Buenas Substation to Hacienda San Jose] (Vegetation) | Vegetation | Vegetation | Yes | Obligated, Amendment Pending Award | 86484.8 | 302418.26 | 9409.44 | 0 | 0 | 0 | 0 | 398312.5 | 95894.24 | 302418.26 | Obligated | 2025-09-17 19:15 | Obligated | 95% | 37730.8 | 126497.04 |  | 164227.84 | -65108.81 | 102333.57 | 346668.94 | 3287.5 | 11131.3 | 0 | 0 | 463421.31 | 105621.07 | 357800.24 | Amendment – Submitted to FEMA | Submitted | Total submitted estimated project cost is $474,552.61, however only .913/2.82 miles were obligated by FEMA. Total obligated cost from FEMA reflected. Obligated portion of project is currently in execution, project version pending obligation.
790443 | FAASt [Pole and Conductor Repair -San Juan Group 3 Phase 2 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 186697 | 0 | 25985 | 0 | 14432.64 | 6007.36 | 1 | 233122 | 227114.64 | 6007.36 | Pending Final FEMA Review | 2025-09-03 20:15 | Obligated, Pending Final FEMA Review | 51% | 42822.13 | 75698.79 |  | 118520.92 | -60607.05 | 244155.63 | 919.99 | 25573.49 | 679.94 | 16392.64 | 6007.36 | 293729.05 | 286121.76 | 7607.29 | Amendment – Submitted to FEMA | Submitted | DSOW – Submitted to FEMA -Currently under FEMA evaluation
757694 | FAASt [Automation Program Group 27] (Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 2314733.78 | 0 | 419922.13 | 0 | 977936.96 | 0 | 0 | 3712592.87 | 3712592.87 | 0 | Obligated | 2025-09-25 16:16 | Obligated | 15% | 245433.59 | 252445.32 |  | 497878.91 | 0 | 1683592.9921 | 631140.7879 | 308544.3439 | 111377.7861 | 458173.9582 | 519763.0018 | 3712592.87 | 2450311.2942 | 1262281.5758 | Amendment – Amendment Needed/Pending Development | Q4 FY2026 | 406 HM Revision to be submitted May 2026 / Estimated date Cfci strategy to be defined
550896 | FAASt Line 6700 Martin Peña TC to Villamar Se | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 1070274.56 | 0 | 133416 | 0 | 0 | 0 | 0 | 1203690.56 | 1203690.56 | 0 | Pending PDMG Scope & Cost Routing | 2022-08-08 11:30 | Obligated, Pending PDMG Scope & Cost Routing | 90% | 424746.39 | 1156791.73 |  | 1581538.12 | -1087165.74 | 1923721.17 | 13772.66 | 166749.56 | 1956.97 | 173673.6 | 10982.34 | 2290856.3 | 2264144.33 | 26711.97 | Amendment – Submitted to FEMA | Submitted
956349 | FAASt [San Juan Region 1 Transmission Line 36800 – Canovanas TC to Palmer TC] (Vegetation) | Vegetation | Vegetation | Yes | Obligated, Amendment Pending FEMA 406 HMP Completion | 1364416 | 0 | 42198.44 | 0 | 0 | 0 | 0 | 1406614.44 | 1406614.44 | 0 | Pending EHP Review | 2025-09-17 19:15 | Obligated, Pending EHP Review | 84% | 34607.3 | 158019.37 |  | 192626.67 | -1132493.89 | 573361.58 | 1942395.21 | 5324.16 | 18027.38 | 0 | 0 | 2539108.33 | 578685.74 | 1960422.59 | Amendment – Submitted to FEMA | Submitted | Total submitted estimated project cost is $4,685,447.53, however only 3.83/11.13 miles were obligated by FEMA. Total obligated cost from FEMA reflected. Obligated portion of project is currently in execution, project version pending obligation.
723883 | FAASt [Region 1 -San Juan Group A] (Vegetation) | Vegetation | Vegetation | Yes | Obligated, Amendment Pending Large Project Review | 6573069.54 | 18368702.69 | 82513.12 | 2687.33 | 0 | 0 | 0 | 25026972.68 | 6655582.66 | 18371390.02 | Obligated | 2024-06-05 11:15 | Obligated | 11% | 12212698.92 | 11070770.35 |  | 23283469.27 | -45119.43 | 6584889.61 | 18404524.67 | 82677.83 | 23074.58 | 0 | 0 | 25072092.11 | 6667567.44 | 18427599.25 | Amendment – Submitted to FEMA | Submitted | Obligated portion of project is currently in execution, project version pending obligation
751656 | FAASt [Vieques Microgrid] (Transmission) | Transmission | Vieques and Culebra Projects (6) | No | Pending Scope & Cost Completion by Applicant | 0 | 0 | 0 | 0 | 0 | 8788889.34 | 1 | 8788889.34 | 0 | 8788889.34 | Pending Scope & Cost Completion by Applicant |  | Obligated, Pending Scope & Cost Completion by Applicant | N/A | 521638.9 | 0 |  | 521638.9 | -116655419.74 | 520290.54 | 99551019.1 | 27002.9 | 8445174.73 | 0 | 16900821.81 | 125444309.08 | 547293.44 | 124897015.64 | DSOW – Pending Design Package for Development | Q2 FY2027 | The DSOW Revision 2 for the Vieques and Culebra Microgrid was submitted in July 2025. After receiving various Requests for Information (RFIs) from FEMA related to the design, an internal decision was made to re-submit the DSOW once the 30% design is completed, providing more robust information to adequately address the agency’s requests. As of today, the DSOW is estimated to be re-submitted in October 2026 following the completion of the 60% design.
757696 | FAASt [Automation Program Group 31] (Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 1145458 | 0 | 195175.66 | 0 | 119259.88 | 241210.12 | 1 | 1701103.66 | 1459893.54 | 241210.12 | Pending PDMG Scope & Cost Routing | 2025-09-17 19:15 | Obligated, Pending PDMG Scope & Cost Routing | 32% | 236991.52 | 812101 |  | 1049092.52 | -318334.84 | 942101.34 | 583449.9 | 87474.903 | 43702.3571 | 122168.23 | 240541.77 | 2019438.5 | 1151744.473 | 867694.0271 | Amendment – Submitted to FEMA | Submitted | Open Soft RFI to revise soft Cost will be submitted 02/20/ Estimated date Cfci strategy to be defined
757697 | FAASt [Automation Program Group 32] (TL / Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 1996678.58 | 0 | 339647.19 | 0 | 666420.83 | 0 | 0 | 3002746.6 | 3002746.6 | 0 | Obligated | 2025-09-25 17:15 | Obligated | 17% | 228055.46 | 39875.94 |  | 267931.4 | -550707.52 | 2115845.46 | 475340.55 | 196682.43 | 74220.68 | 209878.53 | 481486.47 | 3553454.12 | 2522406.42 | 1031047.7 | Amendment – Amendment Needed/Pending Development | Q4 FY2026 | 406 HM Revision to be submitted April 2026/ Estimated date Cfci strategy to be defined
757698 | FAASt [Automation Program Group 33] (Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 1888928.21 | 0 | 311582.64 | 0 | 594117.44 | 0 | 0 | 2794628.29 | 2794628.29 | 0 | Obligated | 2025-09-25 17:15 | Obligated | 20% | 146082.21 | 1146114.8 |  | 1292197.01 | 38481.55 | 1124448.32 | 1149434.09 | 141667.93 | 165158.11 | 30777.97 | 144660.32 | 2756146.74 | 1296894.22 | 1459252.52 | Amendment – Amendment Needed/Pending Development | Q4 FY2026 | 406 HM Revision to be submitted April 2026/ Estimated date Cfci strategy to be defined
797148 | FAASt [Feeder Rebuild # 8101-03] (Distribution) | Distribution | Feeders | Yes | Obligated | 2359896 | 0 | 777847.24 | 0 | 245423.36 | 0 | 0 | 3383166.6 | 3383166.6 | 0 | Pending PDMG Scope & Cost Routing | 2025-09-17 18:16 | Obligated, Pending PDMG Scope & Cost Routing | 0% | 1659779.01 | 99204.99 |  | 1758984 | -200002.53 | 2174764.98 | 235072.1 | 641910.96 | 66287.34 | 431054.74 | 34079.01 | 3583169.13 | 3247730.68 | 335438.45 | Amendment – Submitted to FEMA | Submitted | Working on re-versioning (PA-428 & HM-406 already submitted to FEMA), attending soft RFI received from FEMA, to be submitted to FEMA on Mar 2026
757699 | FAASt [Automation Program Group 34] (Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 2755938.99 | 0 | 462362.68 | 0 | 683789.12 | 0 | 0 | 3902090.79 | 3902090.79 | 0 | Obligated | 2025-11-05 16:17 | Obligated | 4% | 303189.59 | 19984.26 |  | 323173.85 | -118559.59 | 2600700.95 | 561457.08 | 233404.43 | 74776.72 | 147275.17 | 403036.03 | 4020650.38 | 2981380.55 | 1039269.83 | Amendment – Amendment Needed/Pending Development | Q4 FY2026 | 406HM Revision to be submitted June 2026 / Estimated date Cfci strategy to be defined
757700 | FAASt [Automation Program Group 35] (TL / Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 1318516 | 0 | 245359.86 | 0 | 121387.44 | 293400.96 | 1 | 1978664.26 | 1685263.3 | 293400.96 | Pending FEMA 406 HMP Completion | 2025-09-17 19:15 | Obligated, Pending FEMA 406 HMP Completion | 10% | 316891.15 | 1136104.46 |  | 1452995.61 | -675088.6577 | 1133466.58 | 869967.07 | 148303.89 | 84426.9677 | 118838.82 | 298749.59 | 2653752.9177 | 1400609.29 | 1253143.6277 | Amendment – Submitted to FEMA | Submitted | Open Soft RFI to revise soft Cost will be submitted 02/20 / Estimated date Cfci strategy to be defined
800361 | FAASt [Automation Program Group 37] (Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 1596193 | 0 | 297988.09 | 0 | 473670.4 | 0 | 0 | 2367851.49 | 2367851.49 | 0 | Pending Amendment Request Approval | 2025-09-17 19:15 | Obligated, Pending Amendment Request Approval | 40% | 299645.5 | 720209.99 |  | 1019855.49 | -217279.17 | 1539270.03 | 341311.78 | 182365.82 | 60877.03 | 158441.28 | 302864.72 | 2585130.66 | 1880077.13 | 705053.53 | Amendment – Submitted to FEMA | Submitted | Open Soft RFI to revise soft Cost will be submitted 02/20 / Estimated date Cfci strategy to be defined
551963 | FAASt [Transport Network Group 1] (Telecommunication) | Telecommunication | IT/OT | Yes | Obligated | 5490297 | 0 | 836416.02 | 0 | 1143166.33 | 0 | 0 | 7469879.35 | 7469879.35 | 0 | Pending Scope & Cost Completion by Applicant | 2025-09-17 18:16 | Obligated, Pending Scope & Cost Completion by Applicant | 1% | 12893716.78 | 161091.77 |  | 13054808.55 | -1922734.63 | 4489030.64 | 3693295.57 | 671253.14 | 539034.63 | 0 | 0 | 9392613.98 | 5160283.78 | 4232330.2 | Amendment – Submitted to FEMA | Submitted | Amedment submitted to FEMA on Jan 26,2026. Cost estimate revised and splited 428 55% & 406 45% Aprox.
[25 empty] | 3035704041.1365 | 1701407212.3368 | 349129466.0157 | 90824442.8178 | 293981332.0697 | 200575645.3054 | 5662215825.4988 | 3678814839.2219 | 1992807300.4599
Note on G6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: BE Reply: Construction 428 Reply: Approved Obligated Amount - CRC Gross Cost Cal
Note on H6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Construction 406
Note on I6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: BP Reply: 428 A&E Obligated Cost
Note on J6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: BQ Reply: 406 A&E Obligated Cost
Note on K6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: BW Reply: E&M 428
Note on L6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: BX Reply: E&M 406

## Sheet3 (hidden)
AS_TRANS_QTY
1 | 1037090
10 | 414836
9
10 | 1140799
2 | 725000
8 | 415799
5
-8
1
2
4

## Pending (hidden)
Project # | PW | Approved Obligated Amount - CRC Net Cost Cal | Approved Obligated Amount - CRC Gross Cost Cal | 406 A&E Obligated Cost | E&M 406 | Construction (406) | Observation
682834 | 11402 | 36917510 | 36917510 | 0 | 5151836 | -5151836 | PW Sheet states no E&M
800286 | 108077 | 1703713 | 1703713 | 0 | 342399.24 | -342399.24 | Driven by E&M
745861 | 107957 | 3664210.1 | 3664210.1 | 0 | 557322.86 | -557322.86 | Driven by E&M
745856 | 107956 | 1640186.96 | 1640186.96 | 0 | 442571.92 | -442571.92 | Driven by E&M
710099 | 11667 | 6943798.62 | 6704421.69 | 42926.93 | 0 | 196450
752808 | 108000 | 2753627.24 | 2753627.24 | 0 | 312122.7 | -312122.7
735474 | 107918 | 14075641 | 14075641 | 0 | 295487.07 | -295487.07
750692 | 107979 | 12921047 | 12921047 | 0 | 395734.94 | -395734.94
752540 | 107999 | 7111613.91 | 7111613.91 | 0 | 241421.21 | -241421.21
752810 | 108001 | 2623262.08 | 2623262.08 | 0 | 349543.04 | -349543.04
757692 | 108035 | 938783.63 | 938783.63 | 0 | 256947 | -256947
790443 | 108070 | 186697 | 186697 | 0 | 6007.36 | -6007.36
757696 | 108037 | 1145458 | 1145458 | 0 | 241210.12 | -241210.12
757700 | 108041 | 1318516 | 1318516 | 0 | 293400.96 | -293400.96
239376.93

## ISODSOW_Delete (hidden)
FAASt # | P/W # | LUMA Project Name | LUMA ID # | Program Brief | Asset | LUMA Improvement Program | PSP | Restoration / Improved / Alternate | 90 Day Plan | Latest DSOW Submission Date per 90 Day Plan | Current or Past Priority Project | Inactive | Withdrawn Category | Withdrawn Category Status | To Be Reactivated | ISOW Date Submitted to Regulatory | ISOW PREB Cost Estimate | ISOW PREB Submittal Target Date | PREB ISOW Approval Date | Resubmittal Target Date for Withdrawn Projects | ISOW PREB 30 Day Auto Date | Date Revised ISOW Received from CP | Date ISOW Sent Back to CP for Revision | # ISOW Submitted | ISOW - Date submitted to FEMA | Date FAASt Project Created | Initial DSOW Expected Date per 90 Day Plan | Initial DSOW Submission | Latest DSOW Revision | FEMA Internal EHP Deadline Date (ECD) | Date FEMA Internal EHP Deadline Posted | EHP Comments | # DSOW Submitted | ISOW Cost Estimate | FEMA Best Available Cost | 406 Cost Estimate | A&E Cost Estimate | E&M Cost Estimate | 428 Cost Estimate | 406 A&E | 406 CE - 406 A&E | Luma Expected Cost (428+406) | Total LUMA Expected Cost (406+428+A&E) | Earliest Expected Obligation Date | Latest Expected Obligation Date | Initial Date Obligated | Last Date Obligated | Obligated Amount - V0 CRC Net Cost | Obligated Amount - V0 CRC Gross Cost | Obligated Amount - V1 CRC Net Cost | Obligated Amount - V1 CRC Gross Cost | Obligated Amount - V2 CRC Net Cost | E&M Obligated Cost | Obligated Amount - V2 CRC Gross Cost | Approved Obligated Amount - CRC Net Cost Cal | Approved Obligated Amount - CRC Gross Cost Cal | PoP Expiration Date | Document Path | Notes | Modified | Created | Created By | For Jeremy | Modified By | ObligationEstimatingFormulaResult | ObligationEstimatingFormulaResultLookUp | 428 A&E Obligated Cost | 406 A&E Obligated Cost | Scope Change | Scope Change Score | Date Inactivated | RFIFAASt | Title | E&M 428 | E&M 406 | E&M 428 + 406 Total Calc | Multiple Financial Numbers | Item Type | Path | Construction 406
727694 | 107903 | FAASt [Region 4 -Caguas Group C] (Vegetation) | 15F019480000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation | TRUE |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 45138 | 8/4/2023 | 45138 | 45138 | 45271 |  |  |  | 1 |  | 41689596.63 | 76781710.48 |  |  |  |  | 76781710.48 | 76781710.48 | 76781710.48 | 45596 | 45747 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1/38kV%20and%20below%20DSOW%20with%20applicant%20identified%20EHP%20sensitive%20areas%20-%20Region%204_%20Caguas%20(1).pdf?web=1 |  | 46059.6222 | 45152.4647 | Jahdiel Franqui | Island-Wide Vegetation Clearing | Jason Fournier |  |  |  |  | 0.54296 | 3 | 45845 | 727694RFI1 | 727694 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
727692 | 11724 | FAASt [Region 4 -Caguas Group A] High Density (Vegetation) | 15F019870000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation | TRUE |  | FALSE |  | Past | [13 empty] | 45138 | 8/4/2023 | 45138 | 45142 | 45614 | 45746 | 45728 |  |  | 4681848.01 | 4681848.01 | 46038244.43 |  |  |  | 328143.02 | 45710101.41 | 46038244.43 | 46038244.43 | 45565 | 45657 | 45775 |  | 28052090.37 | 7414164.75 | [5 empty] | 28052090.37 | 7414164.75 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/2/38kV%20and%20below%20DSOW-%20Region%204_%20Caguas%20(1)%20(1).pdf?web=1 | 18JULY2024 Project was split into High and Low Density which reduced the total miles in the previous submittal for this project. So if the High and Low Density project values are added together, it will equate to the original submission total.7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List7/25/2025 - Work continues to be performed and completed by field crews | 46059.5496 | 45152.4647 | Jahdiel Franqui | Island-Wide Vegetation Clearing | Jason Fournier |  |  |  |  | 0.10169 | 5 |  | 727692RFI2 | 727692 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 20637925.62
727691 | 107902 | FAASt [Region 1 -San Juan Group C] (Vegetation) | 15F019330000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation | TRUE |  | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 45138 | 8/4/2023 | 45138 | 45138 | 45271 | [5 empty] | 18245048.09 | 44200121.5 |  |  |  |  | 44200121.5 | 44200121.5 | 44200121.5 | 45716 | 45900 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/3/38kV%20and%20below%20DSOW%20with%20applicant%20identified%20EHP%20sensitive%20areas%20-%20Region%201%20San%20Juan%20(1).pdf?web=1 |  | 46059.6219 | 45152.4647 | Jahdiel Franqui | Island-Wide Vegetation Clearing | Jason Fournier |  |  |  |  | 0.41278 | 3 | 45880 | 727691RFI3 | 727691 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
727659 | 107901 | FAASt [Region 2 Arecibo TL - 115kV] (Vegetation) | 15F019560000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation | TRUE |  | FALSE |  | Current | FALSE | Involuntarily Withdrawal Status in Grants Portal | Resubmitted | [10 empty] | 45138 | 8/4/2023 | 45138 | 45138 | 45978 | [5 empty] | 18075945.32 | 3793220.88 | 10330.93 |  | 1098979.51 | 35000.05 | 3758220.83 | 4892200.39 | 4902531.32 | 45596 | 45747 | 46082 |  | 4214343.82 | 953592.14 | [5 empty] | 4214343.82 | 953592.14 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/4/PRJ_Report_727659_20260302.pdf?web=1 | 08/07/2025 04:40 PM AST Project unwithdrawn by System Admin per FEMA Request INC1748838 | 46083.6602 | 45152.4647 | Jahdiel Franqui | Island-Wide Vegetation Clearing | Marlina Crespo |  |  | 8880.74 | 30086.96 | 3.6948 | 1 | 45845 | 727659RFI4 | 727659 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 3230664.72
727657 | 107900 | FAASt [Region 5 Mayaguez TL - 115kV] (Vegetation) | 15F019410000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation | TRUE |  | FALSE |  | Current | FALSE | Involuntarily Withdrawal Status in Grants Portal | Resubmitted | [10 empty] | 45138 | 8/4/2023 | 45138 | 45138 | 45978 | [5 empty] | 16212759.99 | 2298062.02 | 6258.83 |  | 665799.1 | 21204.22 | 2276857.8 | 2963861.12 | 2970119.95 | 45716 | 45900 | 46082 |  | 2553192.59 | 577718.5 | [5 empty] | 2553192.59 | 577718.5 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/5/115kV%20DSOW%20Region%205%20-%20Mayaguez%20(1).pdf?web=1 | 08/07/2025 04:40 PM AST Project unwithdrawn by System Admin per FEMA Request INC1748838 | 46083.6607 | 45152.4647 | Jahdiel Franqui | Island-Wide Vegetation Clearing | Marlina Crespo |  |  | 5380.25 |  | 5.4701 | 1 | 45845 | 727657RFI5 | 727657 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 1975474.09
727608 | 107899 | FAASt [Region 1 San Juan TL - 115kV] (Vegetation) | 15F019310000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation | TRUE |  | FALSE |  | Current | [13 empty] | 45138 | 8/3/2023 | 45138 | 45138 | 45978 | [5 empty] | 18605239.31 | 4008841.52 | 10918.18 |  | 1161449.55 | 36989.58 | 3971851.94 | 5170291.07 | 5181209.25 | 45716 | 45900 | 46082 |  | 4453902.63 | 1007797.83 | [5 empty] | 4453902.63 | 1007797.83 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/6/PRJ_Report_727608_20260302.pdf?web=1 |  | 46083.6636 | 45152.4647 | Jahdiel Franqui | Island-Wide Vegetation Clearing | Marlina Crespo |  |  | 9385.55 | 31797.21 | 3.5985 | 1 |  | 727608RFI6 | 727608 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 3414307.59
727606 | 107898 | FAASt [Region 4 Caguas TL - 115kV] (Vegetation) | 15F019460000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation | TRUE |  | FALSE |  | Current | FALSE | Involuntarily Withdrawal Status in Grants Portal | Resubmitted | [10 empty] | 45138 | 8/3/2023 | 45138 | 45138 | 45978 | 45992 | 45982 | 11/21/2025 - Field EHP - Environmental: In review. ECD 12/01/2025. |  |  | 16306957.02 | 24722341.5 | 67364.86 |  | 7230250.37 | 33062.87 | 24689278.63 | 31952591.87 | 32019956.73 | 45716 | 45900 | 46082 |  | 3981089.18 | 900812.92 | [5 empty] | 3981089.18 | 900812.92 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/7/115kV%20DSOW%20Region%204%20-%20Caguas.docx?web=1 | 08/07/2025 04:40 PM AST Project unwithdrawn by System Admin per FEMA Request INC1748838 | 46083.664 | 45152.4647 | Jahdiel Franqui | Island-Wide Vegetation Clearing | Marlina Crespo |  |  | 8389.21 |  | 0.51035 | 3 | 45845 | 727606RFI7 | 727606 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 3080276.26
727572 | 11720 | FAASt [Region 3 -Bayamon Group A] High Density (Vegetation) | 15F019880000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation | TRUE |  | FALSE |  | Current | [13 empty] | 45138 | 8/3/2023 | 45138 | 45141 | 45951 | 45973 | 45957 | 10/27/2025 - Field EHP: Environmental; under review Expected Completion Date (ECD) 11/12/2025 |  |  | 8173601.57 | 80353343.34 |  |  |  | 698724.72 | 79654618.62 | 80353343.34 | 80353343.34 | 45535 | 45626 | 46082 |  | 42586648.64 | 11268772.7 | [5 empty] | 42586648.64 | 11268772.7 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/8/PRJ_Report_727572_20260302.pdf?web=1 |  | 46083.666 | 45152.4647 | Jahdiel Franqui | Island-Wide Vegetation Clearing | Marlina Crespo |  |  | 179741.68 | 491691 | 0.10172 | 5 |  | 727572RFI8 | 727572 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 30826184.94
727562 | 107897 | FAASt [Region 5 -Mayaguez Group C] (Vegetation) | 15F019430000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation | TRUE |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 45138 | 8/3/2023 | 45138 | 45138 | 45271 | [5 empty] | 34961938.79 | 84411128.06 |  |  |  |  | 84411128.06 | 84411128.06 | 84411128.06 | 45716 | 45900 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/9/38kV%20and%20below%20DSOW%20with%20applicant%20identified%20EHP%20sensitive%20areas%20-%20Region%205_%20Mayaguez%20(1).pdf?web=1 |  | 46059.6218 | 45152.4647 | Jahdiel Franqui | Island-Wide Vegetation Clearing | Jason Fournier |  |  |  |  | 0.41419 | 3 | 45845 | 727562RFI9 | 727562 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
727558 | 107896 | FAASt [Region 3 -Bayamon Group C] (Vegetation) | 15F019530000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation | TRUE |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 45138 | 8/3/2023 | 45138 | 45138 | 45271 | [5 empty] | 16458603.47 | 16374246.76 |  |  |  |  | 16374246.76 | 16374246.76 | 16374246.76 | 45716 | 45900 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/10/115kV%20DSOW%20Region%203%20%20Bayamon%20(1).pdf?web=1 |  | 46059.6216 | 45152.4647 | Jahdiel Franqui | Island-Wide Vegetation Clearing | Jason Fournier |  |  |  |  | 1.0052 | 1 | 45845 | 727558RFI10 | 727558 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
727540 | 107895 | FAASt [Region 2 -Arecibo Group C] (Vegetation) | 15F019580000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation | TRUE |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 45138 | 8/3/2023 | 45138 | 45138 | 45271 | [5 empty] | 42848782.64 | 66510486.76 |  |  |  |  | 66510486.76 | 66510486.76 | 66510486.76 | 45716 | 45900 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/11/38kV%20and%20below%20DSOW%20with%20applicant%20identified%20EHP%20sensitive%20areas%20-%20Region%202_%20Arecibo%20(1).pdf?web=1 |  | 46059.6215 | 45152.4647 | Jahdiel Franqui | Island-Wide Vegetation Clearing | Jason Fournier |  |  |  |  | 0.64424 | 2 | 45845 | 727540RFI11 | 727540 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
727531 | 11715 | FAASt [Region 6 -Ponce Group A] High Density (Vegetation) | 15F019850000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation | TRUE |  | FALSE |  | Past | [13 empty] | 45138 | 8/3/2023 | 45138 | 45141 | 45614 | 45737 | 45730 |  |  |  | 4324993.22 | 42520736.92 |  |  |  | 369745.52 | 42150991.4 | 42520736.92 | 42520736.92 | 45565 | 45657 | 45775 |  | 25913934.11 | 6849050.26 | [5 empty] | 25913934.11 | 6849050.26 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/12/38kV%20and%20below%20DSOW-%20Region%206_%20Ponce%20(1).pdf?web=1 | 7/25/2025 - Work continues to be performed and completed by field crews | 46059.5502 | 45152.4647 | Jahdiel Franqui | Island-Wide Vegetation Clearing | Jason Fournier |  |  | 0 |  | 0.10171 | 5 |  | 727531RFI12 | 727531 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 19064883.85
727530 | 107894 | FAASt [Region 6 -Ponce Group C] (Vegetation) | 15F019380000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation | TRUE |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 45138 | 8/3/2023 | 45138 | 45138 | 45271 | [5 empty] | 32605348.76 | 70421923.26 |  |  |  |  | 70421923.26 | 70421923.26 | 70421923.26 | 45716 | 45900 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/13/38kV%20and%20below%20DSOW%20with%20applicant%20identified%20EHP%20sensitive%20areas%20-%20Region%206_%20Ponce%20(1)%20(1).pdf?web=1 |  | 46059.6214 | 45152.4647 | Jahdiel Franqui | Island-Wide Vegetation Clearing | Jason Fournier |  |  |  |  | 0.463 | 3 | 45845 | 727530RFI13 | 727530 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
727529 | 107893 | FAASt [Region 6 Ponce TL - 115kV] (Vegetation) | 15F019360000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation | TRUE |  | FALSE |  | Current | FALSE | Involuntarily Withdrawal Status in Grants Portal | Resubmitted | [10 empty] | 45138 | 8/3/2023 | 45138 | 45138 | 45978 | 45992 | 45982 | 11/21/2025 - Field EHP: In review, ECD 12/01/2025. |  |  | 20674478.43 | 44340770.67 | 120822.29 |  | 12967819.92 | 68979.15 | 44271791.52 | 57308590.59 | 57429412.88 | 45716 | 45900 | 46082 |  | 8305756.13 | 1879368.2 | [5 empty] | 8305756.13 | 1879368.2 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/14/115kV%20DSOW%20Region%206%20%20Ponce%20(1)%20(1).pdf?web=1 | 08/07/2025 04:40 PM AST Project unwithdrawn by System Admin per FEMA Request INC1748838 | 46083.6669 | 45152.4647 | Jahdiel Franqui | Island-Wide Vegetation Clearing | Marlina Crespo |  |  | 17502.43 |  | 0.36076 | 4 | 45845 | 727529RFI14 | 727529 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 6426387.93
727522 | 107892 | FAASt [Region 3 Bayamon TL - 115kV] (Vegetation) | 15F019510000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation | TRUE |  | FALSE |  | Current | FALSE | Involuntarily Withdrawal Status in Grants Portal | Resubmitted | [10 empty] | 45141 | 8/3/2023 | 45138 | 45138 | 45978 | 45992 | 45985 | 11/24/2025 - Field EHP - Environmental: In Review. Expected Completion Date (ECD) 12/01/2025 |  |  | 102855378 | 3098128.05 | 8437.83 |  | 897595.83 | 28586.43 | 3069541.62 | 3995723.88 | 4004161.71 | 45596 | 45747 | 46082 |  | 3442081.85 | 778850.12 | [5 empty] | 3442081.85 | 778850.12 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/15/PRJ_MultiVersionReport_727522_20260302.pdf?web=1 | 08/07/2025 04:40 PM AST - Project unwithdrawn by System Admin per FEMA Request INC1748838 | 46083.6678 | 45152.4647 | Jahdiel Franqui | Island-Wide Vegetation Clearing | Marlina Crespo |  |  | 7253.38 |  | 25.7414 | 1 | 45845 | 727522RFI15 | 727522 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 2663231.73
724941 | 11733 | FAASt [Aguas Buenas Streetlighting] (Distribution) | 14F018000000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 45141 | 7/7/2023 | 45351 | 45350 | 45391 |  |  |  |  | 8126825 | 11260820.47 | 1686477 | 2317060 |  | 11260820 | 287979 | 1398498 | 12947297 | 15264357 | 45473 | 45626 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/16/724941-DR4339PR-FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Aguas%20Buenas.pdf?web=1 |  | 46077.5788 | 45152.4647 | Jahdiel Franqui | Distribution Streetlighting | Ashleah Dingle |  |  |  |  | 0.86974 | 1 | 45873 | 724941RFI16 | 724941 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
724938 | 11673 | FAASt [Vega Alta Streetlighting] (Distribution) | 14F018120000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE | [15 empty] | 45100 | 7/7/2023 | 45322 | 45313 | [5 empty] | 11756915 | 14314104.85 | 1869090 | 2459743 |  | 12445015 | 537278.89 | 1331811.11 | 14314105 | 16773848 | 45473 | 45504 | 45422 |  | 14314104.85 | 12445015.33 | [5 empty] | 14314104.85 | 12445015.33 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/17/724938-DR4339PR-FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Vega%20Alta%20(1).pdf?web=1 |  | 45856.7687 | 45152.4647 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 2459742.66 |  | 1 | 1 |  | 724938RFI17 | 724938 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 1869089.52
724828 | 11692 | FAASt [Loiza Streetlighting] (Distribution) | 14F018060000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 45108 | 7/6/2023 | 45322 | 45310 | [5 empty] | 5620918 | 6696269.82 | 816844 | 1653580 |  | 6696270 | 161766 | 655078 | 7513114 | 9166694 | 45473 | 45626 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/18/724828-DR4339PR-FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Lo%C3%ADza%20(1).pdf?web=1 |  | 46077.5788 | 45152.4647 | Jahdiel Franqui | Distribution Streetlighting | Ashleah Dingle |  |  |  |  | 0.89128 | 1 | 45873 | 724828RFI18 | 724828 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
724825 | 11725 | FAASt [Cidra Streetlighting] (Distribution) | 14F018030000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE | [15 empty] | 45108 | 7/6/2023 | 45351 | 45350 | 45391 |  |  |  |  | 11213219 | 14650708.44 | 1838230 | 2516456 |  | 12812479 | 526932.49 | 1311297.51 | 14650709 | 17167165 | 45473 | 45535 | 45422 |  | 14650708.44 | 12812478.84 | [5 empty] | 14650708.44 | 12812478.84 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/19/1336051-DR4339PR-FEMA iSOW Distribution Streetlighting - Cidra (1).pdf | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 45856.7687 | 45152.4647 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 2516455.74 |  | 1 | 1 |  | 724825RFI19 | 724825 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 1838229.6
724781 | 11736 | FAASt [Penuelas Streetlighting] (Distribution) | 14F018080000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 45108 | 7/6/2023 | 45351 | 45350 | 45840 |  |  |  |  | 5702676 | 7948618.17 | 408490.41 | 1433020.87 |  | 8327919.73 | 63060.64 | 345429.77 | 8736410.14 | 10169431.01 | 45473 | 45626 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/20/[724781] DR4339PR FAASt Penuelas Streetlighting (Distribution) (1).pdf | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 46077.5788 | 45152.4647 | Jahdiel Franqui | Distribution Streetlighting | Ashleah Dingle |  |  |  |  | 0.90983 | 1 | 45873 | 724781RFI20 | 724781 | 398055 | 268345 | 666400 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
724716 | 11729 | FAASt [Quebradillas Streetlighting] (Distribution) | 14F018090000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 45108 | 7/5/2023 | 45351 | 45350 | 45840 |  |  |  |  | 7787526 | 10455022.32 | 628110.03 | 1872541.02 |  | 11144397.5 | 95914.82 | 532195.21 | 11772507.53 | 13645048.55 | 45473 | 45626 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/21/1335655 DR4339PR FEMA iSOW Distribution Streetlighting - Quebradillas (3) (1) (1).pdf | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 46077.5788 | 45152.4647 | Jahdiel Franqui | Distribution Streetlighting | Ashleah Dingle |  |  |  |  | 0.88809 | 1 | 45873 | 724716RFI21 | 724716 | 642240 | 432960 | 1075200 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
724703 | 11671 | FAASt [Arroyo Streetlighting] (Distribution) | 14F017990000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  | Past | [13 empty] | 45108 | 7/5/2023 | 45291 | 45288 | [5 empty] | 6119646 | 6054726.01 | 740394 | 1504203 |  | 5314332 | 250928.85 | 489465.15 | 6054726 | 7558929 | 45473 | 45535 | 45461 |  | 6054726.01 | 5314332 | [5 empty] | 6054726.01 | 5314332 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/22/724709 DR4339PR iSOW Distribution Streetlighting - Arroyo (1).pdf | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short List | 45856.7687 | 45152.4647 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 1504203.15 |  | 1 | 1 |  | 724703RFI22 | 724703 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 740394.01
724698 | 11734 | FAASt [Adjuntas Streetlighting] (Distribution) | 14F017980000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  | Past | [13 empty] | 45108 | 7/5/2023 | 45351 | 45350 | 45391 |  |  |  |  | 7264269 | 12633614 | 1891152 | 2199844 |  | 10742462 | 552275 | 1338877 | 12633614 | 14833458 | 45473 | 45535 | 45461 |  | 12633614 | 10742462 | [5 empty] | 12633614 | 10742462 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/23/724698 DR4339PR FEMA iSOW Distribution Streetlighting - Adjuntas (1).pdf | QC Review Complete: 2/28/2024 | 45856.7687 | 45152.4647 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 2199843.63 |  | 1 | 1 |  | 724698RFI23 | 724698 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 1891152
724670 | 11731 | FAASt [Patillas Streetlighting] (Distribution) | 14F018070000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 45108 | 7/5/2023 | 45351 | 45350 | 45840 |  |  |  | 5 | 7603568 | 8375887.52 | 406586.59 | 1456883.53 |  | 8833912.82 | 60595.15 | 345991.44 | 9240499.41 | 10697382.94 | 45473 | 45626 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/24/[724670] DR4339PR FAASt Patillas Streetlighting ISOW (Distribution) (1) (1).pdf | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 46077.5788 | 45152.4647 | Jahdiel Franqui | Distribution Streetlighting | Ashleah Dingle |  |  |  |  | 0.90643 | 1 | 45873 | 724670RFI24 | 724670 | 425484 | 286836 | 712320 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
724669 | 11730 | FAASt [Ciales Streetlighting] (Distribution) | 14F018020000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 45108 | 7/5/2023 | 45351 | 45350 | 45840 | 45883 | 45861 |  |  | 7227478 | 10780496.72 | 773133.74 | 2044738.82 |  | 12755671.42 | 113108.63 | 660025.11 | 13528805.16 | 15573543.98 | 45473 | 45626 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/25/1335558-DR4339PR-SOW (1) (1).pdf | <div class="ExternalClassDB9581A60FAA41448D386AD98828A1B2"><div style="font-family&#58;Calibri, Arial, Helvetica, sans-serif;font-size&#58;11pt;color&#58;rgb(0, 0, 0);">7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short List<br></div></div> | 46077.5788 | 45152.4647 | Jahdiel Franqui | Distribution Streetlighting | Ashleah Dingle |  |  |  |  | 0.79686 | 2 | 45873 | 724669RFI25 | 724669 | 741921 | 500159 | 1242080 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
724605 | 11732 | FAASt [Guayanilla Streetlighting] (Distribution) | 14F018040000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 45108 | 7/3/2023 | 45351 | 45350 | 45876 |  |  |  |  | 5831446 | 7949936.1 | 469904.54 | 1372729.11 |  | 8219229.32 | 71428.54 | 398476 | 8689133.86 | 10061862.97 | 45473 | 45626 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/26/1335512-DR4339PR-SOW (4) (1).pdf | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 46077.5787 | 45152.4647 | Jahdiel Franqui | Distribution Streetlighting | Ashleah Dingle |  |  |  |  | 0.91493 | 1 | 45874 | 724605RFI26 | 724605 | 424146 | 285934 | 710080 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
724603 | 11684 | FAASt [Cabo Rojo Streetlighting] (Distribution) | 14F018010000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 45108 | 7/3/2023 | 45322 | 45310 | [5 empty] | 20517371 | 9017148.04 | 1044683 | 2012276 |  | 9017148 | 190599 | 854084 | 10061831 | 12074107 | 45473 | 45626 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/27/1335511-DR4339PR-SOW (2) (1).pdf |  | 46059.6213 | 45152.4647 | Jahdiel Franqui | Distribution Streetlighting | Jason Fournier |  |  |  |  | 0.89617 | 1 | 45874 | 724603RFI27 | 724603 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
724601 | 11739 | FAASt [Salinas Streetlighting] (Distribution) | 14F018110000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  | Past | [13 empty] | 45108 | 7/3/2023 | 45351 | 45350 | 45391 |  |  |  |  | 13130463 | 13708224.43 | 1611021 | 2463886 |  | 12097204 | 469330.38 | 1141690.62 | 13708225 | 16172111 | 45473 | 45535 | 45481 |  | 13708224.43 | 12097203.53 | [5 empty] | 13708224.43 | 12097203.53 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/28/1335509-DR4339PR-SOW (2) (1).pdf | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 45856.7688 | 45152.4647 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 2463885.54 |  | 1 | 1 |  | 724601RFI28 | 724601 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 1611020.9
724600 | 11735 | FAASt [Jayuya Streetlighting] (Distribution) | 14F018050000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  | Past | [13 empty] | 45108 | 7/3/2023 | 45351 | 45350 | 45391 |  |  |  |  | 5077221 | 8628211.52 | 1350541 | 1704126 |  | 7277670 | 419107.52 | 931433.48 | 8628211 | 10332337 | 45473 | 45535 | 45443 |  | 8628211.52 | 7277670.2 | [5 empty] | 8628211.52 | 7277670.2 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/29/1335507-DR4339PR-SOW (2) (1).pdf | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 45856.7688 | 45152.4647 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 1704125.72 |  | 1 | 1 |  | 724600RFI29 | 724600 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 1350541.32
724599 | 11738 | FAASt [Sabana Grande Streetlighting] (Distribution) | 14F018100000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 45108 | 7/3/2023 | 45351 | 45350 | 45840 |  |  |  |  | 7576997 | 10744021.82 | 725698.37 | 1906868.06 |  | 11479468.51 | 110216.6 | 615481.77 | 12205166.88 | 14112034.94 | 45473 | 45626 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/30/1335504-DR4339PR-SOW (2) (1).pdf | 2/28/2024: QC Review Complete7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 46077.5787 | 45152.4647 | Jahdiel Franqui | Distribution Streetlighting | Ashleah Dingle |  |  |  |  | 0.88028 | 1 | 45874 | 724599RFI30 | 724599 | 725196 | 488884 | 1214080 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
723883 | 11696 | FAASt [Region 1 -San Juan Group A] (Vegetation) | 15F019300000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation | TRUE | 406 | FALSE |  | Current | [5 empty] | 1200000000 | 45040 | 45051 |  | 45070 |  |  |  | 45056 | 6/26/2023 | 45107 | 45125 | 45974 | 46001 | 45986 | 11/25/2025 - In review. Expected Completion Date (ECD) 12/10/2025 |  | 1200000000 | 18151116.72 | 145069437.94 |  |  |  | 23074.58 | 145046363.36 | 145069437.94 | 145069437.94 | 45473 | 45535 | 45448 | 3/1/2026 | 18151116.72 | 0 | 18151116.72 | 0 | 24944459.56 |  | 6573069.54 | 24944459.56 | 6573069.54 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/31/38kV%20and%20below%20DSOW-%20Region%201%20San%20Juan%20(1).pdf?web=1 | Project advancing in the project process flow. Refer to Process Status History for more details. | 46083.6694 | 45152.4647 | Jahdiel Franqui | Island-Wide Vegetation Clearing | Marlina Crespo | 0 Months |  | 82513.12 | 2687.33 | 0.12512 | 5 |  | 723883RFI31 | 723883 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 18368702.69
723078 | 11555 | FAASt - EPC - [San Juan SP TC] (Substation) | 14F009040000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | TRUE | Restoration | FALSE | [7 empty] | 89700000 | 44876 | 44905 |  | 44906 |  |  |  | 45093 | 6/16/2023 | 45107 | 45093 | 45230 |  |  |  |  | 89700000 | 61558468.95 |  | 3713097 |  | 61558469 | 0 | 0 | 61558469 | 65271566 |  |  | 45279 |  | 61558468.95 | 61558468.95 | [5 empty] | 61558468.95 | 61558468.95 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/32/723078%20-%20DR-4339PR-%20San%20Juan%20SP%20Transmission%20Center%20-%20FEMA%20Detailed%20Scope%20of%20Work%208.15.23%20rev.pdf |  | 46059.5417 | 45152.4647 | Jahdiel Franqui | San Juan SP TC | Jason Fournier |  |  | 3713096.54 |  | 1 | 1 |  | 723078RFI32 | 723078 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
723077 | 11556 | FAASt - EPC - [Sabana Llana TC] (Substation) | 14F009060000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | TRUE | Restoration | FALSE |  | Past | [5 empty] | 125500000 | 44876 | 44905 |  | 44906 |  |  |  | 45093 | 6/16/2023 | 45107 | 45093 | 45758 | 45727 | 45713 |  |  | 125500000 | 100686731.41 | 0 | 583002.82 |  | 3281329.98 | 0 | 0 | 3281329.98 | 3864332.8 |  |  | 45279 | 04/28/2025 | 100686731.41 | 100686731.41 | 46643078.39 | 46643078.39 |  | 57324983 |  | 46643078.39 | 46643078.39 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/33/723077-%20Sabana%20LLana%20FEMA%20Detailed%20Scope%20of%20Work%209.15.23%20rev.pdf | 4/24/2024: QC Review Complete | 46059.5417 | 45152.4647 | Jahdiel Franqui | Sabana Llana TC | Jason Fournier |  |  | 4850983.03 |  | 30.6847 | 1 |  | 723077RFI33 | 723077 | 57324983 |  | 57324983 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
723002 | 107888 | FAASt - EPC - Jobos TC (Substation) | 14F009050000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | TRUE | Restoration | FALSE |  | Current | [5 empty] | 42900000 | 44876 | 44905 |  | 44906 |  |  |  | 45093 | 6/15/2023 | 45107 | 45092 | 45622 | 45915 | 45908 | 9/8/2025 - Field EHP: SHPO response letter received on 9/5/2025. Under review by EHP Specialist. ECD 9/15/2025. |  | 42900000 | 70090705.72 | 0 | 6191932.29 |  | 69904580.54 | 0 | 0 | 69904580.54 | 76096512.83 | 45716 | 45808 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/34/723002%20-DR-4339PR-%20Jobos%20TC%20-%20FEMA%20Project%20Detailed%20Scope%20of%20Work%20rev%208.17.23%20(2).pdf | 8/12/2025 11:16AM AST - Field EHP: SHPO consultation process initiated; drafting ongoing. Expected Completion Date (ECD) 8/22/2025. | 46059.5417 | 45152.4647 | Jahdiel Franqui | Jobos TC | Jason Fournier | 0 Months |  |  |  | 1.0027 | 1 |  | 723002RFI34 | 723002 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
718971 | 107884 | FAASt [Line 50300 (230kV) from Costa Sur Steam Plant to Aguirre Steam Plant] (Transmission) | 14F015610000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE |  | 173630000 | 45043 | 45051 |  | 45073 |  |  |  | 45055 | 5/11/2023 | 45138 | 45118 | 45145 |  |  |  |  | 917700007 | 917523716 | 901810364 | 176291 |  | 15713352 | 10005336 | 891805028 | 917523716 | 917700007 | 45808 | 45961 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/35/718971-DR4339-PR%20DSOW-0001_Rev1%20-%20T%20Line%2050300%20from%20Costa%20Sur%20SP%20to%20Aguirre%20SP%20-%20signed%20(2).pdf |  | 46059.621 | 45152.4647 | Jahdiel Franqui | Line 50300 from Costa Sur Steam Plant to Aguirre Steam Plant | Jason Fournier |  |  |  |  | 1 | 1 | 45884 | 718971RFI35 | 718971 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
718955 | 107883 | FAASt [Line 50200 (230kv) from Costa Sur SP to Bayamon TC] (Transmission) | 14F015630000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 279240000 | 45043 | 45051 |  | 45073 |  |  |  | 45055 | 5/11/2023 | 45138 | 45118 | 45230 |  |  |  |  | 279240000 | 219184721 | 88423396 | 6123395 |  | 146779642 | 4590570 | 83832826 | 235203038 | 241326433 | 45808 | 45961 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/36/718955-DR4339PR-DSOW-0001_Rev1-%20Line%2050200%20from%20Costa%20Sur%20SP%20to%20Bayamon%20TC%20-%20signed.pdf |  | 45887.6354 | 45152.4647 | Jahdiel Franqui | Line 50200 from Costa Sur SP to Bayamon TC | Ashleah Dingle |  |  |  |  | 0.9319 | 1 | 45887 | 718955RFI36 | 718955 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
718951 | 107882 | FAASt [Line 51200- Costa Sur Steam Plant to Cambalache Gas Plant (230kV)] (Transmission) | 14F015620000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 161130000 | 45043 | 45051 |  | 45073 |  |  |  | 45055 | 5/11/2023 | 45138 | 45118 | 45230 |  |  |  |  | 161140000 | 143758497 | 64652304 | 4748151 |  | 91592573 | 3186387 | 61465917 | 156244877 | 160993028 | 45838 | 45991 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/37/718951-DR4339PR-DSOW-0001_Rev1%20-%20Line%2051200%20from%20Costa%20Sur%20SP%20to%20Cambalache%20GP%207723%20-%20signed%20(1).pdf |  | 45887.6354 | 45152.4647 | Jahdiel Franqui | Line 51200 from Costa Sur Steam Plant to Cambalache Gas Plant | Ashleah Dingle |  |  |  |  | 0.92008 | 1 | 45887 | 718951RFI37 | 718951 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
715610 | 107877 | FAASt [Network Upgrades to Support the Integration of Tranche 1 Utility Scale Renewable Projects] (Transmission) |  | PBUT13 - T Priority Pole Repl | Transmission | PREB Mandate |  | Restoration | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 78300000 | 44956 | 44979 |  | 44986 |  |  |  | 44936 | 4/28/2023 |  | 45251 | [5 empty] | 78300000 | 118409122.46 | 0 | 26336371 |  | 118409122 | 0 | 0 | 118409122 | 144745493 | 45504 | 45596 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/38/[715610] FAASt [Network Upgrades to Support the Integration of Tranche 1 Utility Scale Renewable Projects] (1).pdf |  | 45887.6354 | 45152.4647 | Jahdiel Franqui | PREB Mandate | Ashleah Dingle |  |  |  |  | 1 | 1 | 45887 | 715610RFI38 | 715610 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
714654 | 11583 | FAASt [Advanced Metering Infrastructure (AMI)] (Telecommunications) | 14F000000000 | PBUT36 - AMI Implementation Prog | Telecommunications | AMI Implementation Program |  | Restoration | FALSE | [7 empty] | 780000000 | 45014 | 45021 |  | 45044 |  |  |  | 45034 | 4/20/2023 | 45138 | 45118 | 45275 |  |  |  |  | 780000000 | 876270176 | 544207595 | 16450923 |  | 317095666 | 2421276 | 541786319 | 861303261 | 877754184 |  |  | 45268 | 05/01/2024 | 873848901 | 873848901 | 332062581 | 332062581 | 876270176 |  | 332062581 | 876270176 | 332062581 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/39/714654-DR4339PR-DSOW%20AMI%20V2%20(2).pdf?web=1 |  | 45918.6317 | 45152.4647 | Jahdiel Franqui | Advanced Metering Infrastructure (AMI) | Marlina Crespo |  |  | 1484008 | 2421276 | 1.0174 | 1 |  | 714654RFI39 | 714654 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 541786319
714641 | 11630 | FAASt [Rincón Streetlighting] (Distribution) | 14F017260000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  | Current | [13 empty] | 45035 | 4/20/2023 | 45230 | 45261 | 45826 | 45884 | 45881 | 8/12/2025 - Field EHP: In final review. ECD Updated: 8/15/2025. |  | 6614287 | 10689504.94 | 694470.58 | 1946225.97 |  | 11592957.26 | 106422.03 | 588048.55 | 12287427.84 | 14233653.81 | 45473 | 45626 | 46082 |  | 11536809.84 | 10842339.26 |  |  |  | 750618 |  | 11536809.84 | 10842339.26 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/40/[714641] FAASt [Distribution Streetlighting - Rincón] (Distribution)iSOW (2) (1).pdf | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short List 8/12/2025 - Field EHP: In final review. ECD Updated: 8/15/2025. 8/15/2025 10:03 AM AST - EHP Compliance review was completed, project is in Pending PDMG Project Review. | 46083.6704 | 45152.4647 | Jahdiel Franqui | Distribution Streetlighting | Marlina Crespo | 0 Months |  | 1946225.97 | 106422.03 | 0.86995 | 1 |  | 714641RFI40 | 714641 | 750618 | 506022 | 1256640 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 82026.55
713795 | 11624 | FAASt [Lares Streetlighting] (Distribution) | 14F017010000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 45019 | 4/12/2023 | 45291 | 45261 | 45876 |  |  |  |  | 5994964 | 11909808.29 | 712022.01 | 1974624.75 |  | 12615988.1 | 101922.08 | 610099.93 | 13328010.11 | 15302634.86 | 45473 | 45626 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/41/[713795] DR4339PR- FEMA iSOW Distribution Streetlighting - Lares (Distribution).pdf | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short List | 46077.5787 | 45152.4647 | Jahdiel Franqui | Distribution Streetlighting | Ashleah Dingle |  |  |  |  | 0.89359 | 1 | 45874 | 713795RFI41 | 713795 | 733893 | 494747 | 1228640 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
713592 | 107874 | FAASt [Telecom Infrastructure – Group F] (Telecommunications) | 14F019040000 | PBIT01 - Telecom Sys & Network | Telecommunications | IT OT Telecom Systems and Network | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active | [5 empty] | 45610 |  |  |  |  | 45021 | 4/11/2023 | [7 empty] | 4600000 | 4600000 | [5 empty] | 0 | 4600000 | 4600000 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/42/713592-DR4339PR-Telecom Infrastructure.pdf | 4/4/2024 - Received withdrawal status data/info from Director Timothy Auch. This project is being developed and A&E work needed for submission will be completed to support re-submission date5/29/2024 - Update received for Resubmittal Target Date from Grid Strategy Performance Team, original date was 11/15/2024. | 45877.577 | 45152.4647 | Jahdiel Franqui | Telecom Infrastructure | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 713592RFI42 | 713592 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
713497 | 107873 | FAASt [Substation Minor Repairs - Group C-1] |  | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active | [10 empty] | 45021 | 4/10/2023 | [7 empty] | 2800000 | 2800000 | [5 empty] | 0 | 2800000 | 2800000 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/43/1313998-DR4339PR-FEMA Initial Scope of Work - Substation Minor Repairs - Group C-1 Rev0 (2) (2).pdf | 4/2/2024 - Received withdrawal status data/info from Manager Yadira L. Lugo Cordero. Working with Planning and Engineering to re-organize the group. | 45877.577 | 45152.4647 | Jahdiel Franqui | Substation Minor Repairs | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 713497RFI43 | 713497 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
713496 | 107872 | FAASt [Substation Minor Repairs - Group - H] (Substations) |  | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active | [10 empty] | 45021 | 4/10/2023 | [7 empty] | 3500000 | 3500000 | [5 empty] | 0 | 3500000 | 3500000 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/44/[713496] DR4339PR FAASt [Substation Minor Repairs - Group H] (Substations) Initial SOW CE (2).pdf | 4/2/2024 - Received withdrawal status data/info from Manager Yadira L. Lugo Cordero. Working with Planning and Engineering to re-organize the group. | 45877.577 | 45152.4647 | Jahdiel Franqui | Substation Minor Repairs | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 713496RFI44 | 713496 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
713491 | 107871 | FAASt [Substation Minor Repairs - Group A-1] (Substation) |  | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active | [10 empty] | 45021 | 4/10/2023 | [7 empty] | 3800000 | 3800000 | [5 empty] | 0 | 3800000 | 3800000 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/45/713491-DR4339PR-FEMA Initial Scope of Work - Substation Minor Repairs - Group A-1 Rev0 (1).pdf | 4/2/2024 - Received withdrawal status data/info from Manager Yadira L. Lugo Cordero. Working with Planning and Engineering to re-organize the group. | 45877.577 | 45152.4647 | Jahdiel Franqui | Substation Minor Repairs | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 713491RFI45 | 713491 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
713459 | 107870 | FAASt [Substation Minor Repairs - Group A-2] (Substation) |  | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active | [10 empty] | 45021 | 4/10/2023 | [7 empty] | 3450000 | 3450000 | [5 empty] | 0 | 3450000 | 3450000 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/46/713459-DR4339PR-Substation Minor Repairs - Group A-2 Rev0 (1).pdf | 4/2/2024 - Received withdrawal status data/info from Manager Yadira L. Lugo Cordero. Working with Planning and Engineering to re-organize the group. | 45877.577 | 45152.4647 | Jahdiel Franqui | Substation Minor Repairs | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 713459RFI46 | 713459 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
713181 | 107869 | FAASt [ Substation Minor Repairs - Group E-2] (Substation) |  | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active | [10 empty] | 45021 | 4/5/2023 | [7 empty] | 2600000 | 2600000 | [5 empty] | 0 | 2600000 | 2600000 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/47/713181-FEMA Initial Scope of Work - Substation Minor Repairs - Group E-2 Rev0 (1).pdf | 4/2/2024 - Received withdrawal status data/info from Manager Yadira L. Lugo Cordero. Working with Planning and Engineering to re-organize the group. | 45877.577 | 45152.4647 | Jahdiel Franqui | Substation Minor Repairs | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 713181RFI47 | 713181 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
713179 | 107868 | FAASt [ Minor Repairs - Group D-1] (Substation) |  | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active | [10 empty] | 45021 | 4/5/2023 | [7 empty] | 1800000 | 1800000 | [5 empty] | 0 | 1800000 | 1800000 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/48/FEMA Project Scope of Work - Substation Minor Repairs - Group D-1 Rev0.pdf | 4/2/2024 - Received withdrawal status data/info from Manager Yadira L. Lugo Cordero. Working with Planning and Engineering to re-organize the group. | 45877.577 | 45152.4647 | Jahdiel Franqui | Substation Minor Repairs | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 713179RFI48 | 713179 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
713149 | 107867 | FAASt [Substation Minor Repairs - Group E-1] (Substation) |  | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active | [10 empty] | 45021 | 4/5/2023 | [7 empty] | 2000000 | 2000000 | [5 empty] | 0 | 2000000 | 2000000 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/49/FEMA Initial Scope of Work - Substation Minor Repairs - Group E-1 Rev0 (1).pdf | 4/2/2024 - Received withdrawal status data/info from Manager Yadira L. Lugo Cordero. Working with Planning and Engineering to re-organize the group. | 45877.5771 | 45152.4647 | Jahdiel Franqui | Substation Minor Repairs | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 713149RFI49 | 713149 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
712988 | 107866 | FAASt [Minor Protection, Automation, and Control (PAC) Replacement] (Substation) |  | PBUT07 - Substation Reliability | Substation | Substation Reliability |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Retired FAASt -- New FAASt Created |  |  | 70500000 |  |  | 45397 |  |  |  |  | 44994 | 4/4/2023 | 45382 | [6 empty] | 70500000 | 70500000 | [5 empty] | 0 | 70500000 | 70500000 | [11 empty] | 0 | 0 |  | Automation,, and Control (PAC) Replacement (1).pdf, https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/50/712988-DR4339PR-Minor Protection, Automation, and Control (PAC) Replacement (1).pdf | 4/8/2024 - Email notification received from Kevin Smeltzer for this FAASt #, placed under a new FAASt # 7466604/2/2024 - Received withdrawal status data/info from Manager Yadira L. Lugo Cordero. DSOW for Group 1 we tried to submitted in March 28, but project is withdrawn from GP. DSOW Group 1 is ready to be submitted, as soon the project are active in GP. 3/27/2024: QC Review Complete | 45877.5771 | 45152.4648 | Jahdiel Franqui | Substation Reliability | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 712988RFI50 | 712988 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
712982 | 107865 | FAASt [Distribution Pole and Conductor Repair – Mayaguez Group 23] (Distribution) | 14F017000000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active | [10 empty] | 45014 | 4/4/2023 | [7 empty] | 1250000 | 1250000 | [5 empty] | 0 | 1250000 | 1250000 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/51/FEMA Project Scope of Work Distribution Pole and Conductor Repair -Mayaguez Group 23.pdf | 3/27/2024 - Received withdrawal status data/info from Project Coordinator Yaritza Acevedo Ortiz. | 45877.5771 | 45152.4648 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 712982RFI51 | 712982 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
712981 | 107864 | FAASt [Distribution Pole and Conductor Repair - Ponce Group 24] (Distribution) | 14F016960000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active | [10 empty] | 45014 | 4/4/2023 | [7 empty] | 1250000 | 1250000 | [5 empty] | 0 | 1250000 | 1250000 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/52/FEMA Project Scope of Work Distribution Pole and Conductor Repair - Ponce Group 24.pdf | 3/27/2024 - Received withdrawal status data/info from Project Coordinator Yaritza Acevedo Ortiz. | 45877.5771 | 45152.4648 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 712981RFI52 | 712981 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
712980 | 11754 | FAASt [T-Pole Program Line 3000] (Transmission) | 14F017350000 | PBUT13 - T Priority Pole Repl | Transmission – Pole Replacement | Transmission Priority Pole Replacements |  | Restoration | FALSE |  | Past | [13 empty] | 44994 | 4/4/2023 | 45291 | 45317 | 45358 |  |  |  |  | 616000 | 631194.26 | 72118 | 72788 |  | 559077 | 13981.67 | 58136.33 | 631195 | 703983 | 45535 | 45626 | 45597 |  | 631194.26 | 559076.77 | [5 empty] | 631194.26 | 559076.77 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/53/1312596-DR4339PR-FEMA Scope of Work Line 3000 Caguax Sect - Juncos TC.DOC (1) (1).pdf |  | 45856.7688 | 45152.4648 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Rey Roldan Rodríguez |  |  | 72787.96 |  | 1 | 1 |  | 712980RFI53 | 712980 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 72117.49
712979 | 107863 | FAASt [TL 12600 Humacao TC to Verde Mar] (Transmission) |  |  | Transmission | Transmission Priority Pole Replacements | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 44994 | 4/4/2023 | [7 empty] | 539000 | 539000 | [5 empty] | 0 | 539000 | 539000 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/54/[712979] DR4339 FAASt [TL 12600 Humacao TC to Verde Mar] (Transmission) Initial SOW and Cost Estimate.pdf | 3/28/2024 - Received withdrawal status data/info from Project Manager Claudio R. Jaquez. | 45877.5771 | 45152.4648 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 712979RFI54 | 712979 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
712978 | 107862 | FAASt [Once de Agosto Sect. - San Sebastian TC 38kV Line 2000] (Transmission) | 14F017340000 | PBUT13 - T Priority Pole Repl | Transmission | Transmission – Pole Replacement |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active | [5 empty] | 45392 |  |  |  |  | 44994 | 4/4/2023 | [7 empty] | 1848000 | 1848000 | [5 empty] | 0 | 1848000 | 1848000 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/55/712978-DR4339PR-Scope of Work L2000 Once de Agosto Sect. - San Sebastian TC.DOC.pdf | 3/28/2024 - Received withdrawal status data/info from Project Manager Claudio R. Jaquez. | 46078.5667 | 45152.4648 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 712978RFI55 | 712978 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
712977 | 107861 | FAASt [L3000 Caguas TC - Caguax Sect] (Transmission) | 14F017350000 | PBUT13 - T Priority Pole Repl | Transmission | Transmission Priority Pole Replacements | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 44994 | 4/4/2023 | 45291 | [6 empty] | 154000 | 154000 | [5 empty] | 0 | 154000 | 154000 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/56/[712977] DR4339PR FAASt [L3000 Caguas TC - Caguax Sect] Initial SOW CE.pdf | 9/12/2024 - GP Notes "6/25/2024 The project was withdrawn with the comment "Project is being withdrawn since it was not included in the Applicant’s latest workplan for submittal of a SOW. FEMA may in the future re-create the project at the request of the Applicant and COR3 if a SOW submittal date is provided.". | 45877.5771 | 45152.4648 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 712977RFI56 | 712977 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
712968 | 11666 | FAASt [Pole and Conductor Repair - Arecibo Group 2 - Phase 2] (Distribution) | 14F016510000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE |  | Past | [13 empty] | 45014 | 4/4/2023 | 45230 | 45231 | 45413 |  |  |  |  | 3000000 | 5807772.97 | 178713 | 503551 |  | 5629060 | 35903.97 | 142809.03 | 5807773 | 6311324 | 45473 | 45626 | 45597 |  | 5807772.97 | 5629060 | [5 empty] | 5807772.97 | 5629060 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/57/FEMA%20SOW%20Distribution%20Pole%20and%20Conductor%20Repair%20-%20Arecibo%20Group%202%20-%20Phase%202%20(1).pdf?web=1 |  | 45856.7688 | 45152.4648 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 503550 |  | 1 | 1 |  | 712968RFI57 | 712968 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 178712.97
712963 | 107860 | FAASt [Mayaguez GP - Leon Sect 38kV Line 1600] (Transmission) |  |  | Transmission | Transmission Priority Pole Replacements | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 44994 | 4/4/2023 | [7 empty] | 231000 | 231000 | [5 empty] | 0 | 231000 | 231000 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/58/712963-DR4339PR-Project Scope of Work L1600 Mayaguez GP - Leon Sect.DOC.pdf | 3/28/2024 - Received withdrawal status data/info from Project Manager Claudio R. Jaquez. | 45877.5771 | 45152.4648 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 712963RFI58 | 712963 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
711962 | 107859 | FAASt [Distribution Pole and Conductor Repair -Mayaguez Group 21] (Distribution) | 14F016950000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active | [10 empty] | 45014 | 4/4/2023 | [7 empty] | 1250000 | 1250000 | [5 empty] | 0 | 1250000 | 1250000 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/59/711962-DR4339PR-Project Scope of Work Distribution Pole and Conductor Repair -Mayaguez Group 21.pdf | 3/27/2024 - Received withdrawal status data/info from Project Coordinator Yaritza Acevedo Ortiz. | 45877.5771 | 45152.4648 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 711962RFI59 | 711962 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
711909 | 107858 | FAASt [ TL100 Jobos TC to Guayama TO] (Transmission) | 14F017290000 | PBUT13 - T Priority Pole Repl | Transmission | Transmission Priority Pole Replacements | [5 empty] | TRUE | Voluntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 44994 | 4/3/2023 | 45291 | [6 empty] | 231000 | 231000 | [5 empty] | 0 | 231000 | 231000 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/60/711909-DR4339PR-FEMA Scope of Work TL100 Jobos TC to Guayama TO.DOC.pdf | 3/28/2024 - Received withdrawal status data/info from Project Manager Claudio R. Jaquez. Project merged into another existing FAASt 711670. | 45877.5772 | 45152.4648 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 711909RFI60 | 711909 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
711888 | 11640 | FAASt [Pole and Conductor Repair - Caguas Group 1 - Phase 2] (Distribution) | 14F016970000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 45014 | 4/3/2023 | 45199 | 45204 | 45272 |  |  |  |  | 3000000 | 5591713.87 | 165903 | 434785 |  | 5425810 | 0 | 165903 | 5591713 | 6026498 | 45473 | 45535 | 45373 | 8/30/2024 | 5591713.87 | 5425810.57 | 5591713.87 | 5425810.57 |  |  |  | 5591713.87 | 5425810.57 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/61/711888-DR4339PR-FEMA SOW Distribution Pole and Conductor Repair - Caguas Group 1 - Phase 2.pdf | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 46070.5278 | 45152.4648 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Marlina Crespo |  |  | 434784.65 |  | 1 | 1 |  | 711888RFI61 | 711888 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 165903.3
711862 | 107857 | FAASt [TL100 Ponce TC to Santa Isabel Sect](Transmission) | 14F017300000 | PBUT13 - T Priority Pole Repl | Transmission | Transmission Priority Pole Replacements | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 44994 | 4/3/2023 | [7 empty] | 1232000 | 1232000 | [5 empty] | 0 | 1232000 | 1232000 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/62/711862 DR4339PR- FAASt FEMA Scope of Work TL100 Ponce TC to Santa Isabel Sect.DOC.pdf | 3/28/2024 - Received withdrawal status data/info from Project Manager Claudio R. Jaquez. | 45877.5772 | 45152.4648 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 711862RFI62 | 711862 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
711856 | 11746 | FAASt [Pole and Conductor Repair - Bayamon Group 3 - Phase 2] (Distribution) | 14F016980000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE |  | Past | [13 empty] | 45014 | 4/3/2023 | 45260 | 45261 | 45271 |  |  |  |  | 3000000 | 11335984.34 | 395663 | 891094 |  | 10940321 | 67251.43 | 328411.57 | 11335984 | 12227078 | 45473 | 45626 | 45530 | 12/16/2024 | 11335984.34 | 10940320.91 | 11335984.34 | 10940320.91 |  |  |  | 11335984.34 | 10940320.91 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/63/711856-DR4339PR-FEMA%20SOW%20Distribution%20Pole%20and%20Conductor%20Repair%20-%20Bayamon%20Group%203%20-%20Phase%202.pdf?web=1 |  | 45856.7688 | 45152.4648 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 891093.89 |  | 1 | 1 |  | 711856RFI63 | 711856 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 395663.43
711829 | 107856 | FAASt [Santa Isabel Sect. - Salinas Sect. 38kV Line 100] (Transmission) | 14F017310000 | PBUT13 - T Priority Pole Repl | Transmission | Transmission Priority Pole Replacements | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 44994 | 4/3/2023 | [7 empty] | 1309000 | 1309000 | [5 empty] | 0 | 1309000 | 1309000 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/64/711829-DR4339PR-Project Scope of Work L100 Santa Isabel Sect. - Salinas Sect..DOC.pdf | 3/28/2024 - Received withdrawal status data/info from Project Manager Claudio R. Jaquez. | 45877.5772 | 45152.4648 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 711829RFI64 | 711829 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
711819 | 11840 | FAASt [TL 13400 TC-San German Sect-La Parguera Sect] (Transmission) | 14F017330000 | PBUT13 - T Priority Pole Repl | Transmission – Pole Replacement | Transmission Priority Pole Replacements | TRUE | Restoration | FALSE |  | Current | [13 empty] | 44994 | 4/3/2023 | 45291 | 45281 | 45917 | 45936 | 45930 | 10/3/2025 - Field EHP - Environmental: In Review. Expected Completion Date (ECD) 10/06/2025. |  | 1617000 | 1804189 | 197625.13 | 201035.14 |  | 2349734.4 | 15575.52 | 182049.61 | 2547359.53 | 2748394.67 | 45777 | 45869 | 46082 |  | 2399911.66 | 2202286.53 |  |  |  | 147447.87 |  | 2399911.66 | 2202286.53 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/65/711819 DR4339PR-FAASt TL 13400 TC-San German Sect-La Parguera Sect.DOC.pdf |  | 46083.6722 | 45152.4648 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Marlina Crespo |  |  | 201035.14 |  | 0.70826 | 2 |  | 711819RFI65 | 711819 | 147447.87 | 21069.57 | 168517.44 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 176555.56
711670 | 11719 | FAASt [T-Pole Program Line 100] (Transmission) | 14F017290000 | PBUT13 - T Priority Pole Repl | Transmission – Pole Replacement | Transmission Priority Pole Replacements |  | Restoration | FALSE |  | Past | [13 empty] | 44994 | 3/31/2023 | 45291 | 45278 | 45341 |  |  |  |  | 462000 | 118160.28 | 23372 | 12341 |  | 94787 | 0 | 23372 | 118159 | 130500 | 45473 | 45535 | 45461 | 8/30/2024 | 118160.28 | 94787.57 | 118160.28 | 94787.57 |  |  |  | 118160.28 | 94787.57 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/66/711670-DR4339PR-Project Scope of Work L100 Salinas Sect. - Jobos TC.pdf |  | 46070.5275 | 45152.4648 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Marlina Crespo |  |  | 12340.69 |  | 1 | 1 |  | 711670RFI66 | 711670 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 23372.71
711291 | 107855 | FAASt [Telecom Infrastructure – Group E] (Telecommunication) | 14F008930000 | PBIT01 - Telecom Sys & Network | Telecommunications | IT OT Telecom Systems and Network | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active | [5 empty] | 45691 |  |  |  |  | 44991 | 3/29/2023 | [7 empty] | 5600000 | 5600000 | [5 empty] | 0 | 5600000 | 5600000 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/67/711291-DR4339PR_ISOW_Telecomm Antennas_Moca_Quebradillas_San Sebastian.pdf | 4/4/2024 - Received withdrawal status data/info from Director Timothy Auch. This project is being developed and A&E work needed for submission will be completed to support re-submission date5/29/2024 - Update received for Resubmittal Target Date from Grid Strategy Performance Team, original date was 10/30/2024. | 45877.5772 | 45152.4648 | Jahdiel Franqui | Telecom Infrastructure | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 711291RFI67 | 711291 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
711172 | 107854 | FAASt [L3700 Jobos TC - Maunabo TC] (Transmission) | 14F017400000 | PBUT13 - T Priority Pole Repl | Transmission | Transmission Priority Pole Replacements | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 44946 | 3/28/2023 | [7 empty] | 539739 | 539739 | [5 empty] | 0 | 539739 | 539739 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/68/711172-DR4339PR-ISOW- Line 3700 Jobos TC - Maunabo TC.pdf | 3/28/2024 - Received withdrawal status data/info from Project Manager Claudio R. Jaquez. Project merged into another existing FAASt 708637. | 45877.5772 | 45152.4648 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 711172RFI68 | 711172 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
710498 | 107851 | FAASt [Distribution Pole and Conductor Repair - Bayamon Group 16] (Distribution) | 14F016490000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active | [10 empty] | 45002 | 3/22/2023 | [7 empty] | 1250000 | 1250000 | [5 empty] | 0 | 1250000 | 1250000 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/69/[710498] DR4339 FAASt [Distribution Pole and Conductor Repair - Bayamon Group 16] (Distribution) ISOW CE.pdf | 3/27/2024 - Received withdrawal status data/info from Project Coordinator Yaritza Acevedo Ortiz. | 45877.5772 | 45152.4648 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 710498RFI69 | 710498 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
710363 | 107850 | FAASt [Distribution Pole and Conductor Repair - Bayamon Group 15] (Distribution) | 14F016500000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active | [10 empty] | 45002 | 3/22/2023 | [7 empty] | 1250000 | 1250000 | [5 empty] | 0 | 1250000 | 1250000 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/70/1310158-DR4339PR-FEMA Project Scope of Work Distribution Pole and Conductor Repair - Bayamon Group 15 (1).pdf | 3/27/2024 - Received withdrawal status data/info from Project Coordinator Yaritza Acevedo Ortiz. | 45877.5772 | 45152.4648 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 710363RFI70 | 710363 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
710110 | 11534 | FAASt [Distribution Pole and Conductor Repair - Bayamon Group 2 - Phase 2] (Distribution) | 14F016550000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 45002 | 3/20/2023 | 45169 | 45160 | [5 empty] | 2000000 | 87774.8 | 2478.06 | 14756 |  | 85297 | 478.06 | 2000 | 87775.06 | 102531.06 |  |  | 45222 |  | 87774.8 | 85296.74 | [5 empty] | 87774.8 | 85296.74 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/71/710110-DR4339PR-Detailed%20SOW%20Bayamon%20Group%202%20-%20phase%202%20Rev0%20(2).pdf |  | 45856.7688 | 45152.4648 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 14756.12 |  | 1 | 1 |  | 710110RFI71 | 710110 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 2478.06
710099 | 11667 | FAASt [Pole and Conductor Repair - Arecibo Group 1 - Phase 2] (Distribution) | 14F016530000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE |  | Past | [13 empty] | 45002 | 3/20/2023 | 45199 | 45204 | 45392 | 45604 | 45596 |  |  | 3000000 | 6943798.62 | 239377 | 602047 |  | 6704422 | 42926.93 | 196450.07 | 6943799 | 7545846 | 45473 | 45626 | 45664 |  | 6943798.62 | 6704421.69 | [5 empty] | 6943798.62 | 6704421.69 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/72/710099-DR4339PR-FEMA SOW Distribution Pole and Conductor Repair - Arecibo Group 1 - Phase 2.pdf |  | 45856.7688 | 45152.4648 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 602047.2 | 42926.93 | 1 | 1 |  | 710099RFI72 | 710099 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 196450
710094 | 11639 | FAASt [Pole and Conductor Repair - Bayamon Group 1 - Phase 2] (Distribution) | 14F016990000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE |  | Past | [13 empty] | 45002 | 3/20/2023 | 45169 | 45175 | 45397 |  |  |  |  | 3500000 | 7291385.82 | 195136 | 614123 |  | 7096250 | 29565.32 | 165570.68 | 7291386 | 7905509 | 45473 | 45626 | 45597 |  | 7291385.82 | 7096249.5 | [5 empty] | 7291385.82 | 7096249.5 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/73/710094-DR4339PR-Detailed%20SOW%20Bayamon%20Group%201%20-%20Phase%202%20Rev0.pdf |  | 45856.7688 | 45152.4648 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 614123.07 |  | 1 | 1 |  | 710094RFI73 | 710094 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 195136.32
710045 | 107849 | FAASt [Distribution Pole and Conductor Repair -Mayaguez Group 20] (Distribution) | 14F016540000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active | [10 empty] | 45002 | 3/20/2023 | [7 empty] | 1250000 | 1250000 | [5 empty] | 0 | 1250000 | 1250000 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/74/710045-DR4339PR- FEMA Project Scope of Work Distribution Pole and Conductor Repair - Mayaguez Group 20 (1).pdf | 3/27/2024 - Received withdrawal status data/info from Project Coordinator Yaritza Acevedo Ortiz. | 45877.5772 | 45152.4648 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 710045RFI74 | 710045 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
710026 | 107849 | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 17] (Distribution) | 14F016520000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active | [10 empty] | 45002 | 3/20/2023 | [7 empty] | 1250000 | 1250000 | [5 empty] | 0 | 1250000 | 1250000 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/75/710026-DR4339PR-FEMA Project Scope of Work Distribution Pole and Conductor Repair - Arecibo Group 17.pdf | 3/27/2024 - Received withdrawal status data/info from Project Coordinator Yaritza Acevedo Ortiz. | 45877.5772 | 45152.4648 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 710026RFI75 | 710026 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
709631 | 11627 | FAASt [Morovis Streetlighting] (Distribution) | 14F017270000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE | [15 empty] | 44998 | 3/15/2023 | 45291 | 45261 | [5 empty] | 8987336 | 15230881.12 | 1744482 | 2499521 |  | 13486399 | 487450.7 | 1257031.3 | 15230881 | 17730402 | 45473 | 45535 | 45373 |  | 15230881.12 | 13486398.85 | [5 empty] | 15230881.12 | 13486398.85 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/76/709631-DR4339PR- ISOW - FEMA Project Scope of Work - Morovis.pdf |  | 45856.7688 | 45152.4648 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 2499521.06 |  | 1 | 1 |  | 709631RFI76 | 709631 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 1744482.27
708951 | 107846 | FAASt [L6500 Toro Negro 1 H.P. - Barranquitas T.C.] (Transmission) |  |  | Transmission | Transmission Priority Pole Replacements | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 44946 | 3/8/2023 | [7 empty] | 510000 | 510000 | [5 empty] | 0 | 510000 | 510000 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/77/[708951] DR4339PR FAASt [Line 6500 Toro Negro 1 HP - Barranquitas TC] (Transmission) Initial SOW and CE (2).docx | 3/28/2024 - Received withdrawal status data/info from Project Manager Claudio R. Jaquez. | 45877.5772 | 45152.4648 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 708951RFI77 | 708951 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
708909 | 107845 | FAASt [L3000 Juncos TC - Rio Blanco HP] (Transmission) | 14F017380000 | PBUT33 - T Line Rebuild | Transmission | Transmission Priority Pole Replacements | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 44946 | 3/7/2023 | [7 empty] | 600000 | 600000 | [5 empty] | 0 | 600000 | 600000 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/78/[708909] DR4339PR FAASt [Line 3000 Juncos TC - Rio Blanco HP] (Transimission) ISOW CE.pdf | 3/28/2024 - Received withdrawal status data/info from Project Manager Claudio R. Jaquez. Project merged into another existing FAASt 712980. | 45877.5772 | 45152.4648 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 708909RFI78 | 708909 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
708819 | 107844 | FAASt [L2000 Once de Agosto Sect. - San Sebastian TC ] (Transmission) | 14F017340000 | PBUT13 - T Priority Pole Repl | Transmission | Transmission Priority Pole Replacements |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 44946 | 3/7/2023 | [7 empty] | 761985 | 761985 | [5 empty] | 0 | 761985 | 761985 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/79/708819-DR4339PR-ISOW-EN-SOW-0001_Rev1 - Line 2000 Once de Agosto Sect - San Sebastian TC.docx | 3/28/2024 - Received withdrawal status data/info from Project Manager Claudio R. Jaquez. Duplicate FAASt. Project under 712978. | 45877.5772 | 45152.4648 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 708819RFI79 | 708819 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
708734 | 107843 | FAASt Line 800 Comsat Sect - Cidra Sect. (Transmission) |  |  | Transmission | Transmission Priority Pole Replacements |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active | [5 empty] | 45444 |  |  |  |  | 44946 | 3/6/2023 | [7 empty] | 349243 | 349243 | [5 empty] | 0 | 349243 | 349243 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/80/1305869-DR4339PR- Line 800 Comsat Sect - Cidra Sect (1).pdf | 3/28/2024 - Received withdrawal status data/info from Project Manager Claudio R. Jaquez. | 45877.5772 | 45152.4648 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 708734RFI80 | 708734 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
708637 | 11723 | FAASt [T-Pole Program Line 3700] (Transmission) | 14F017400000 | PBUT13 - T Priority Pole Repl | Transmission – Pole Replacement | Transmission Priority Pole Replacements |  | Restoration | FALSE |  | Past | [13 empty] | 44946 | 3/3/2023 | 45291 | 45303 | 45385 |  |  |  |  | 480000 | 377354.58 | 73394 | 39574 |  | 303960 | 14229.08 | 59164.92 | 377354 | 416928 | 45626 | 45716 | 45530 | 12/16/2024 | 377354.58 | 303960.92 | 377354.58 | 303960.92 |  |  |  | 377354.58 | 303960.92 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/81/708637-DR4339PR-Line 3700 Maunabo TC - Humacao TC.docx |  | 45856.7688 | 45152.4648 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Rey Roldan Rodríguez |  |  | 39573.63 | 8454.62 | 1 | 1 |  | 708637RFI81 | 708637 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 64939.04
708630 | 107842 | FAASt L37400 Dorado TC - Vega Baja TC] (Transmission) |  |  | Transmission | Transmission Priority Pole Replacements | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active | [5 empty] | 45474 |  |  |  |  | 44946 | 3/3/2023 | [7 empty] | 285744 | 285744 | [5 empty] | 0 | 285744 | 285744 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/82/708630-DR4339PR-Line 37400 Dorado TC - Vega Baja TC.docx | 3/28/2024 - Received withdrawal status data/info from Project Manager Claudio R. Jaquez. | 45877.5772 | 45152.4648 | Jahdiel Franqui | 115 kV Transmission Priority Poles and Structures Replacements | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 708630RFI82 | 708630 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
708599 | 107841 | FAASt [L700 Costa Sur SP - Yauco 2 HP] (Transmission) | 14F015420000 | PBUT33 - T Line Rebuild | Transmission | Transmission Priority Pole Replacements | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active | [5 empty] | 45397 |  |  |  |  | 44946 | 3/3/2023 | [7 empty] | 380992 | 380992 | [5 empty] | 0 | 380992 | 380992 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/83/ISOW-EN-SOW-0001_Rev1 - Line 700 Costa Sur SP - Yauco 2 HP.docx | 3/28/2024 - Received withdrawal status data/info from Project Manager Claudio R. Jaquez. | 45877.5772 | 45152.4648 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 708599RFI83 | 708599 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
708579 | 11508 | FAASt [Pole and Conductor Repair - Ponce Group 16, 17, 18 & 19] (Distribution) | 14F014730000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44984 | 3/3/2023 | 45046 | 45105 | 45127 | [5 empty] | 2154006.76 | 389437.84 | 343118 |  | 1764569 | 0 | 389437.84 | 2154006.84 | 2497124.84 |  |  | 45222 | 8/30/2024 | 2154006.76 | 1764568.92 | 2154006.76 | 1764568.92 |  |  |  | 2154006.76 | 1764568.92 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/84/708579-DR4339PR-Detailed%20SOW%20Ponce%20Group%2016-17-18-19%20Rev0%20-%20signed%20(1).pdf?web=1 |  | 46070.5271 | 45152.4648 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Marlina Crespo |  |  | 343118.15 |  | 1 | 1 |  | 708579RFI84 | 708579 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 389437.84
708577 | 107840 | FAASt Transmission Line 4800 (38KV) Santa Isabel TC - Santa Isabel SECT |  |  | Transmission | Transmission Priority Pole Replacements | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active | [5 empty] | 45407 |  |  |  |  | 44946 | 3/3/2023 | [7 empty] | 190496 | 190496 | [5 empty] | 0 | 190496 | 190496 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/85/708577-DR4339PR- ISOW Transmission Line 4800 Santa Isabel TC - Santa Isabel Sect.pdf | 3/28/2024 - Received withdrawal status data/info from Project Manager Claudio R. Jaquez. | 45877.5773 | 45152.4648 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 708577RFI85 | 708577 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
708575 | 107839 | FAASt Transmission Line 37400 (115KV) Cambalache TC - Dos Bocas Hydro Plant |  |  | Transmission | Transmission Priority Pole Replacements | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active |  |  | 318800000 |  |  | 45474 |  |  |  |  | 44946 | 3/3/2023 | [7 empty] | 380992 | 380992 | [5 empty] | 0 | 380992 | 380992 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/86/708575-DR4339PR- ISOW Transmission Line 37400 Cambalache TC - Dos Bocas Hydro Plant.pdf | 3/28/2024 - Received withdrawal status data/info from Project Manager Claudio R. Jaquez. | 45877.5773 | 45152.4648 | Jahdiel Franqui | 115 kV Transmission Priority Poles and Structures Replacements | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 708575RFI86 | 708575 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
706498 | 107832 | FAASt Transmission and Distribution Automation Program Installation of Intelligent Reclosers, Single Phase Reclosers and Fault Current Indicators Group 4 | 14F003280000 | PBUT04 - Distribution Automation | Distribution | Distribution Automation | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Retired FAASt -- New FAASt Created | [10 empty] | 44964 | 2/15/2023 | 45291 | [6 empty] | 5800000 | 5800000 | [5 empty] | 0 | 5800000 | 5800000 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/87/1302760-DR4339PR-Applicant SOW Transmission and Distribution Group 4 Feb072022.pdf | 4/3/2024 - Received withdrawal status data/info from Project Manager Oscar Fuentes Garcia. FEMA Canceled this FAASt because it wasn’t included in 90 Plan, new FAASt was assigned to this group on December 2023 - 740662 (initial DSOW submission - 12/13/2024) | 45877.5773 | 45152.4648 | Jahdiel Franqui | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 706498RFI87 | 706498 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
705657 | 107826 | FAASt [Automation Program Group 3] (TL/Distribution) | 14F004910000, 14F004930000, 14F004950000, 14F004980000, 14F004940000, 14F004900000, 14F004990000, 14F003330000, 14F004920000 | PBUT04 - Distribution Automation | Grid Automation | Distribution Automation |  | Restoration | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 44964 | 2/9/2023 | 45230 | 45230 | 45288 |  |  |  |  | 6300000 | 6300000 | 19657460 | 466338 |  | 4462681 | 1859214 | 17798246 | 24120141 | 24586479 | 45657 | 45838 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/88/705657-DR433PR-FEMA SOW Transmission and Distribution Automation - Group 03.pdf | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short List | 46077.5787 | 45152.4648 | Jahdiel Franqui | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Ashleah Dingle |  |  |  |  | 0.26119 | 4 | 45887 | 705657RFI88 | 705657 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
705584 | 11365 | FAASt [Pole and Conductor Repair - Ponce Groups 14 & 15] (Distribution) | 14F014420000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44963 | 2/9/2023 | 45046 | 45035 | [5 empty] | 1250000 | 1842979 | 378483 | 284698 |  | 1464496 | 0 | 378483 | 1842979 | 2127677 |  |  | 45093 |  | 1842979 | 1464496 | [5 empty] | 1842979 | 1464496 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/89/705584-DR4339PR-Detailed%20SOW%20Ponce%20Group%2014-15%20Rev0.pdf?web=1 |  | 45856.7689 | 45152.4648 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 284698 |  | 1 | 1 |  | 705584RFI89 | 705584 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 378483
705527 | 11449 | FAASt [Distribution Pole and Conductor Repair – San Juan 17-18-19-20-21] (Distribution) | 14F014430000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44963 | 2/8/2023 | 45016 | 45029 | 45041 |  |  |  |  | 1250000 | 767854 | 125133 | 125147 |  | 642721 | 0 | 125133 | 767854 | 893001 |  |  | 45135 |  | 767854 | 642721 | [5 empty] | 767854 | 642721 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/90/705527%20-%20DR4339PR-Detailed%20SOW%20San%20Juan%20Group%2017-18-19-20-21%20Rev1%20-%20signed.pdf?web=1 |  | 45856.7689 | 45152.4648 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 125147 |  | 1 | 1 |  | 705527RFI90 | 705527 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 125133
705503 | 11476 | FAASt [Pole and Conductor Repair Mayaguez Groups 15,16,17,18 & 19] (Distribution) | 14F014410000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 44963 | 2/8/2023 | 45046 | 45098 | [5 empty] | 1250000 | 1176665.69 | 192105 | 221088 |  | 1396854 | 21294 | 170811 | 1588959 | 1810047 | 45688 | 45838 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/91/705503-DR4339PR-Detailed%20SOW%20Mayaguez%20Group%2015-16-17-18-19%20Rev0.pdf?web=1 |  | 45880.3829 | 45152.4648 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Ashleah Dingle |  |  |  |  | 0.74053 | 2 | 45877 | 705503RFI91 | 705503 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
704943 | 11664 | FAASt [Naranjito Streetlighting] (Distribution) | 14F014700000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE | [15 empty] | 44953 | 2/3/2023 | 45291 | 45287 | [5 empty] | 6978114 | 13759586.8 | 2115538 | 2348210 |  | 11644048 | 613589.66 | 1501948.34 | 13759586 | 16107796 | 45473 | 45535 | 45394 |  | 13759586.8 | 11644048.42 | [5 empty] | 13759586.8 | 11644048.42 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/92/1297186-DR4339PR-Applicant SOW 01-31-2023 (1).pdf |  | 46098.4735 | 45152.4648 | Jahdiel Franqui | Distribution Streetlighting | Marlina Crespo |  |  | 2348209.91 | 613589.66 | 1 | 1 |  | 704943RFI92 | 704943 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 1501948.72
704933 | 11465 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 13-14-15-16] (Distribution) | 14F014460000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44953 | 2/3/2023 | 45046 | 45016 | 45041 |  |  |  |  | 1250000 | 1426151 | 224731 | 231255 |  | 1201420 | 47078 | 177653 | 1426151 | 1657406 |  |  | 45142 |  | 1426151 | 1201420 | [5 empty] | 1426151 | 1201420 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/93/704933%20-%20DR4339PR-Detailed%20SOW%20San%20Juan%20Group%2013-14-15-16%20Rev1%20-%20signed%20(1).pdf?web=1 |  | 45856.7689 | 45152.4648 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 231255 |  | 1 | 1 |  | 704933RFI93 | 704933 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 224731
704931 | 11651 | FAASt [Camuy Streetlighting] (Distribution) | 14F014680000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 44953 | 2/3/2023 | 45230 | 45261 | 45286 |  |  |  |  | 11239791 | 15436783.23 | 2269186 | 2828651 |  | 15436783 | 351414 | 1917772 | 17705969 | 20534620 | 45535 | 45688 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/94/704931-DR4339PR-FEMA Project Scope of Work - Distribution Streetlighting - Camuy.pdf |  | 46059.6208 | 45152.4649 | Jahdiel Franqui | Distribution Streetlighting | Jason Fournier |  |  |  |  | 0.87184 | 1 | 45874 | 704931RFI94 | 704931 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
704929 | 11635 | FAASt [San Lorenzo Streetlighting] (Distribution) | 14F014710000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 44953 | 2/3/2023 | 45291 | 45261 | 45876 |  |  |  |  | 11082405 | 14343817.06 | 2284857 | 2780414 |  | 14343817 | 2284857 | 0 | 16628674 | 19409088 | 45596 | 45747 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/95/704929-DR4339PR-FEMA Project Scope of Work - Distribution Streetlighting - San Lorenzo.pdf |  | 46077.5787 | 45152.4649 | Jahdiel Franqui | Distribution Streetlighting | Ashleah Dingle |  |  |  |  | 0.8626 | 1 | 45874 | 704929RFI95 | 704929 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
704938 | 11633 | FAASt [Las Piedras Streetlighting] (Distribution) | 14F014610000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE | [15 empty] | 44953 | 2/3/2023 | 45291 | 45261 | [5 empty] | 11100801 | 15615524.51 | 1807601 | 2760454 |  | 13807923 | 522246.69 | 1285354.31 | 15615524 | 18375978 | 45473 | 45535 | 45394 |  | 15615524.51 | 13807923.4 | [5 empty] | 15615524.51 | 13807923.4 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/96/1297192-DR4339OPR-Applicant SOW 01-31-2023.pdf |  | 45856.7689 | 45152.4649 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 2760454.04 |  | 1 | 1 |  | 704938RFI96 | 704938 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 1807601.11
704927 | 11711 | FAASt [Añasco Streetlighting] (Distribution) | 14F014720000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  | Past | [13 empty] | 44953 | 2/3/2023 | 45322 | 45310 | [5 empty] | 7572909 | 13908238.09 | 1820362 | 2420466 |  | 12087876 | 0 | 1820362 | 13908238 | 16328704 | 45473 | 45535 | 45481 | 8/30/2024 | 13908238.09 | 12087876.17 | 13908238.09 | 12087876.17 |  |  |  | 13908238.09 | 12087876.17 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/97/1297195-DR4339PR-Applicant SOW 01-31-2023.pdf | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short List | 46070.5268 | 45152.4649 | Jahdiel Franqui | Distribution Streetlighting | Marlina Crespo |  |  | 2420466.41 |  | 1 | 1 |  | 704927RFI97 | 704927 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 1820361.92
704921 | 11675 | FAASt [Barranquitas Streetlighting] (Distribution) | 14F014640000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE | [15 empty] | 44953 | 2/3/2023 | 45322 | 45310 | [5 empty] | 5782391 | 11007375.31 | 1577046 | 2048083 |  | 9430329 | 472894.36 | 1104151.64 | 11007375 | 13055458 | 45473 | 45535 | 45443 |  | 11007375.31 | 9430329.22 | [5 empty] | 11007375.31 | 9430329.22 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/98/704921-DR4339PR-FEMA Project Scope of Work - Distribution Streetlighting - Barranquitas.pdf |  | 45856.7689 | 45152.4649 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 2048083.31 |  | 1 | 1 |  | 704921RFI98 | 704921 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 1577046.09
704916 | 11312 | FAASt [Pole and Conductor Repair - Arecibo Group 13-14-15-16] (Distribution) | 14F013920000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44960 | 2/3/2023 | 45016 | 44985 | 44993 |  |  |  |  | 1250000 | 303970 | 29974 | 49755 |  | 273996 | 6279 | 23695 | 303970 | 353725 |  |  | 45022 |  | 303970 | 273996 | [5 empty] | 303970 | 273996 | 46650 | https://aeepr.sharepoint.com/:b:/r/sites/Test4552/Shared%20Documents/General/ISOW%20DSOW%20Information%20(Attachments)/704916-DR4339PR-Detailed%20SOW%20Arecibo%20Group%2013-14-15-16%20Rev1%20-%20signed.pdf?csf=1&web=1&e=aNrEX2 |  | 45856.7689 | 45152.4649 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 49755 |  | 1 | 1 |  | 704916RFI99 | 704916 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 29974
704868 | 11650 | FAASt [Ceiba Streetlighting] (Distribution) | 14F014630000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE | [15 empty] | 44953 | 2/2/2023 | 45291 | 45287 | [5 empty] | 5590258 | 5869029.74 | 716919 | 1481547 |  | 5152111 | 244786.81 | 472132.19 | 5869030 | 7350577 | 45473 | 45535 | 45481 |  | 5869029.74 | 5152111.14 | [5 empty] | 5869029.74 | 5152111.14 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW DSOW Tracker/Attachments/100/[704868] DR4339PR - FAASt [Distribution Streetlighting - Ceiba] (Distribution) SOW CE.pdf |  | 46051.4481 | 45152.4649 | Jahdiel Franqui | Distribution Streetlighting | Ashleah Dingle |  |  | 1481546.84 |  | 1 | 1 |  | 704868RFI100 | 704868 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 716918.6
704862 | 11728 | FAASt [Fajardo Streetlighting] (Distribution) | 14F014600000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 44953 | 2/2/2023 | 45351 | 45350 | 45876 |  |  |  |  | 11724212 | 11333806.13 | 1104923 | 2297199 |  | 11333806 | 1104923 | 0 | 12438729 | 14735928 | 45504 | 45657 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/101/%5B704862%5D%20DR4339PR%20-%20Distribution%20Streetlighting%20-%20Fajardo%20(Distribution)%20SOW%20CE.pdf?web=1 | QC Review Complete: 2/28/2024 | 46059.6202 | 45152.465 | Jahdiel Franqui | Distribution Streetlighting | Jason Fournier |  |  |  |  | 0.91117 | 1 | 45875 | 704862RFI101 | 704862 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
704849 | 11658 | FAASt [Naguabo Streetlighting] (Distribution) | 14F014620000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE | [15 empty] | 44953 | 2/2/2023 | 45291 | 45287 | [5 empty] | 9670022 | 13290413.39 | 1669737 | 2380243 |  | 11620676 | 0 | 1669737 | 13290413 | 15670656 | 45473 | 45535 | 45422 | 8/30/2024 | 13290413.39 | 11620676.42 | 13290413.39 | 11620676.42 |  |  |  | 13290413.39 | 11620676.42 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/102/704849%20-%20DR4339PR%20FAASt%20%5BDistribution%20Streetlightling%20-%20Naguabo%5D%20(Ditribution)%20SOW%20CE.pdf?web=1 |  | 46070.5264 | 45152.465 | Jahdiel Franqui | Distribution Streetlighting | Marlina Crespo |  |  | 2380242.99 |  | 1 | 1 |  | 704849RFI102 | 704849 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 1669736.97
704844 | 11340 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 16-17-18-19-20] (Distribution) | 14F014450000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44956 | 2/2/2023 | 45016 | 45016 | [5 empty] | 1250000 | 409298 | 88558 | 62490 |  | 320740 | 18552 | 70006 | 409298 | 471788 |  |  | 45063 |  | 409298 | 320740 | [5 empty] | 409298 | 320740 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/103/704844-DR4339PR-Detailed%20SOW%20Caguas%20Group%2016-17-18-19-20%20Rev0.pdf |  | 45856.7689 | 45152.465 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 62490 |  | 1 | 1 |  | 704844RFI103 | 704844 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 88558
704805 | 11863 | FAASt [Telecom Infrastructure – Group D] (Telecommunication) | 14F008600000, 14F008620000, 14F008610000, 14F008630000 | PBIT01 - Telecom Sys & Network | Telecommunications | IT OT Telecom Systems and Network | TRUE |  | TRUE | 45869 |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 44959 | 2/2/2023 | [7 empty] | 6905000 | 6905000 | [5 empty] | 0 | 6905000 | 6905000 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/104/704805-DR4339PR-Telecom%20Infrastructure%20%E2%80%93%20Group%20D-Rev.%201.pdf?web=1 | 4/4/2024 - Received withdrawal status data/info from Director Timothy Auch. This project is being developed and A&E work needed for submission will be completed to support re-submission date5/29/2024 - Update received for Resubmittal Target Date from Grid Strategy Performance Team, original date was 9/30/2024.9/12/2024 - "6/25/2024 Project unwithdrawn by System Admin per FEMA Request ServiceNow INC1122383" Grants Portal6/12/2025 - Project withdrawn in Grants Portal | 46059.5594 | 45152.465 | Jahdiel Franqui | Telecom Infrastructure | Jason Fournier |  |  |  |  | 1 | 1 | 45820 | 704805RFI104 | 704805 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
704793 | 11691 | FAASt [Yauco Streetlighting] (Distribution) | 14F014590000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 44953 | 2/2/2023 | 45322 | 45313 | 45876 |  |  |  |  | 13804973 | 14713958.38 | 1639888 | 2718070 |  | 14713958 | 255698 | 1384190 | 16353846 | 19071916 | 45535 | 45688 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/105/704793-DR4339PR-FEMA%20Project%20Scope%20of%20Work%20-%20Distribution%20Streetlighting%20-%20Yauco.pdf?web=1 |  | 46077.5787 | 45152.465 | Jahdiel Franqui | Distribution Streetlighting | Ashleah Dingle |  |  |  |  | 0.89972 | 1 | 45875 | 704793RFI105 | 704793 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
704763 | 107825 | FAASt [Telecom Infrastructure – Group C] (Telecommunication) | 14F004650000 | PBIT01 - Telecom Sys & Network | Telecommunications | IT OT Telecom Systems and Network | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active | [5 empty] | 45975 |  |  |  |  | 44959 | 2/2/2023 | [7 empty] | 2800000 | 2800000 | [5 empty] | 0 | 2800000 | 2800000 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/106/704763-DR4339PR-Telecom%20Infrastructure%20%E2%80%93%20Group%20C-Rev.%201.pdf?web=1 | 4/4/2024 - Received withdrawal status data/info from Director Timothy Auch. This project will need low level support as we work to procure land needed for the project5/29/2024 - Update received for Resubmittal Target Date from Grid Strategy Performance Team, original date was 12/20/2025. | 45877.5773 | 45152.465 | Jahdiel Franqui | Telecom Infrastructure | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 704763RFI106 | 704763 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
704757 | 11638 | FAASt [Santa Isabel Streetlighting] (Distribution) | 14F014660000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 44953 | 2/2/2023 | 45291 | 45261 | [5 empty] | 7826361 | 7956662 | 820333 | 1750406 |  | 7956663 | 147924 | 672409 | 8776996 | 10527402 | 45535 | 45688 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/107/704757-DR4339PR-FEMA%20Project%20Scope%20of%20Work%20-%20Distribution%20Streetlighting%20-%20Santa%20Isabel.pdf?web=1 |  | 46059.62 | 45152.465 | Jahdiel Franqui | Distribution Streetlighting | Jason Fournier |  |  |  |  | 0.90654 | 1 | 45875 | 704757RFI107 | 704757 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
704755 | 11352 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 12-13-14] (Distribution) | 14F014440000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44946 | 2/2/2023 | 45016 | 45016 | [5 empty] | 1250000 | 524391.61 | 86181.92 | 83451 |  | 438210 | 0 | 86181.92 | 524391.92 | 607842.92 |  |  | 45063 |  | 524391.61 | 438209.69 | [5 empty] | 524391.61 | 438209.69 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/108/704755-DR4339PR-Distribution%20Pole%20and%20Conductor%20Repair%20-%20Bayamon%20Group%2012-13-14.pdf?web=1 |  | 45856.7689 | 45152.465 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 83450.9 |  | 1 | 1 |  | 704755RFI108 | 704755 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 86181.92
704751 | 11311 | FAASt Distribution Pole and Conductor Repair - Bayamon Group 11 (Distribution) | 14F013940000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44946 | 2/2/2023 | 45016 | 44986 | [5 empty] | 435167 | 435167 | 96676 | 66168 |  | 338491 | 20252 | 76424 | 435167 | 501335 |  |  | 45022 |  | 435167 | 338491 | [5 empty] | 435167 | 338491 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/109/704751-DR4339PR-Detailed%20SOW%20Bayamon%20Group%2011%20Rev0%20-%20signed.pdf?web=1 |  | 45856.7689 | 45152.465 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 66168 |  | 1 | 1 |  | 704751RFI109 | 704751 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 96676
704750 | 11314 | FAASt Distribution Pole and Conductor Repair - Bayamon Group 10 (Distribution) | 14F013930000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44946 | 2/2/2023 | 45016 | 44985 | 44992 |  |  |  |  | 1250000 | 578629 | 92244 | 92511 |  | 486385 | 19324 | 72920 | 578629 | 671140 |  |  | 45022 |  | 578629 | 486385 | [5 empty] | 578629 | 486385 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/110/704750-DR4339PR-Distribution%20Pole%20and%20Conductor%20Repair%20-%20Bayamon%20Group%2010.pdf?web=1 |  | 45856.7689 | 45152.465 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 92511 |  | 1 | 1 |  | 704750RFI110 | 704750 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 92244
704744 | 11626 | FAASt [San Sebastian Streetlighting] (Distribution) | 14F014690000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 44953 | 2/2/2023 | 45230 | 45261 | [5 empty] | 12472305 | 22246737.73 | 3663221 | 3725225 |  | 22246738 | 525425 | 3137796 | 25909959 | 29635184 | 45535 | 45688 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/111/704744-DR4339PR-%20FEMA%20Project%20Scope%20of%20Work%20-%20Distribution%20Streetlighting%20-%20San%20Sebasti%C3%A1n.pdf?web=1 |  | 46077.5786 | 45152.465 | Jahdiel Franqui | Distribution Streetlighting | Ashleah Dingle |  |  |  |  | 0.85862 | 1 | 45875 | 704744RFI111 | 704744 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
704741 | 11737 | FAASt [Moca Streetlighting] (Distribution) | 14F014650000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 44953 | 2/2/2023 | 45351 | 45350 | 45840 |  |  |  |  | 12034895 | 17686091.97 | 1110824.64 | 3152500.55 |  | 19122669.84 | 167188.56 | 943636.08 | 20233494.48 | 23385995.03 | 45473 | 45626 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/112/704741-DR4339PR-FEMA%20Project%20Scope%20of%20Work%20-%20Distribution%20Streetlighting%20-%20Moca.pdf?web=1 | 2/28/2024: QC Review Complete7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 46077.5786 | 45152.465 | Jahdiel Franqui | Distribution Streetlighting | Ashleah Dingle | 0 Months |  |  |  | 0.8741 | 1 | 45875 | 704741RFI112 | 704741 | 1190151 | 802329 | 1992480 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
704679 | 11524 | FAASt [Coamo Streetlighting] (Distribution) | 14F014670000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE | [15 empty] | 44953 | 2/1/2023 | 45107 | 45107 | 45108 |  |  |  |  | 12196369 | 16372823.8 | 2060901.35 | 2687464 |  | 14311922 | 0 | 2060901.35 | 16372823.35 | 19060287.35 |  |  | 45233 | 8/30/2024 | 16372823.8 | 14311922.45 | 16372823.8 | 14311922.45 |  |  |  | 16372823.8 | 14311922.45 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/113/704679-DR4339PR-Detailed%20SOW%20Coamo%20Rev0%20-%20DSOW%20-%20signed%20(1).pdf?web=1 |  | 46070.5262 | 45152.465 | Jahdiel Franqui | Distribution Streetlighting | Marlina Crespo |  |  | 2687463.9 |  | 1 | 1 |  | 704679RFI113 | 704679 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 2060901.35
703535 | 11636 | FAASt [Toa Baja Streetlighting] (Distribution) | 14F013890000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE | [15 empty] | 44908 | 1/23/2023 | 45230 | 45261 | [5 empty] | 18518368 | 10149325.06 | 620135 | 1814022 |  | 9529190 | 0 | 620135 | 10149325 | 11963347 | 45473 | 45535 | 45461 | 8/30/2024 | 10149325.06 | 9529190.37 | 10149325.06 | 9529190.37 |  |  |  | 10149325.06 | 9529190.37 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/114/703535%20-%20DR4339%20-%20FAASt%20%5BDistribution%20Streetlighting%20-%20Toa%20Baja%5D%20(Distribution)%20CE-ISOW.pdf?web=1 |  | 46070.5258 | 45152.465 | Jahdiel Franqui | Distribution Streetlighting | Marlina Crespo |  |  | 1814022 |  | 1 | 1 |  | 703535RFI114 | 703535 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 620134.69
703222 | 107824 | FAASt [Transmission and Distribution Automation Program Installation of Intelligent Reclosers, Single Phase Reclosers and Fault Current Indicators Group 2] (Transmission and Distribution) | 14F000800000 | PBUT04 - Distribution Automation | Distribution | Distribution Automation | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Retired FAASt -- New FAASt Created |  |  | 230370000 |  |  | 45273 |  |  |  |  | 44902 | 1/19/2023 | 45230 | [6 empty] | 4500000 | 4500000 | [5 empty] | 0 | 4500000 | 4500000 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/115/703222-DR4339PR-T%20ad%20D%20intelligent%20Re0closers,%20Single%20Phase%20Reclosers%20and%20Fault%20Current%20Indicators%20Group%202.pdf | 4/3/2024 - Received withdrawal status data/info from Project Manager Oscar Fuentes Garcia. FEMA Canceled this FAASt because it wasn’t included in 90 Plan, new FAASt was assigned to this group on December 2023 - 740662 (initial DSOW submission - 12/13/2024) | 45877.5775 | 45152.465 | Jahdiel Franqui | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 703222RFI115 | 703222 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
701679 | 11267 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 12] (Distribution) | 14F010320000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44917 | 1/4/2023 | 44926 | 44957 | [5 empty] | 850000 | 80651.6 | 16226.16 | 12535 |  | 64425 | 3399.16 | 12827 | 80651.16 | 93186.16 |  |  | 44987 |  | 80651.6 | 64425.44 | [5 empty] | 80651.6 | 64425.44 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/116/701679-DR4339PR-FEMA%20iSOW%20Distribution%20Pole%20and%20Conductor%20Repair%20-%20San%20Juan%20Group%2012.pdf?web=1 |  | 45856.7689 | 45152.465 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 12535.35 |  | 1 | 1 |  | 701679RFI116 | 701679 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 16226.16
701555 | 11275 | FAASt [Pole and Conductor Repair - Ponce Group 13] (Distribution) | 14F010350000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44917 | 1/3/2023 | 44957 | 44953 | [5 empty] | 1250000 | 649427 | 102417 | 104535 |  | 547010 | 21455 | 80962 | 649427 | 753962 |  |  | 44993 |  | 649427 | 547010 | [5 empty] | 649427 | 547010 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/117/701555-DR4339PR-Detailed%20SOW%20Ponce%20Group%2013%20Rev0%20-%20signed.pdf?web=1 |  | 45856.7689 | 45152.465 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 104535 |  | 1 | 1 |  | 701555RFI117 | 701555 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 102417
701552 | 11257 | FAASt [Pole and Conductor Repair - Ponce Group 12] (Distribution) | 14F010360000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44917 | 1/3/2023 | 44957 | 44946 | [5 empty] | 1250000 | 238162 | 51841 | 36670 |  | 186321 | 10860 | 40981 | 238162 | 274832 |  |  | 44993 |  | 238162 | 186321 | [5 empty] | 238162 | 186321 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/118/701552-DR4339PR-Detailed%20SOW%20Ponce%20Group%2012%20Rev0%20-%20signed.pdf?web=1 |  | 45856.7689 | 45152.465 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 36670 |  | 1 | 1 |  | 701552RFI118 | 701552 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 51841
701545 | 11269 | FAASt [Pole and Conductor Repair - Ponce Group 11] (Distribution) | 14F010370000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44917 | 1/3/2023 | 44926 | 44946 | [5 empty] | 1250000 | 616229 | 129039 | 95198 |  | 487190 | 27032 | 102007 | 616229 | 711427 |  |  | 44993 |  | 616229 | 487190 | [5 empty] | 616229 | 487190 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/119/701545-DR4339PR-Detailed%20SOW%20Ponce%20Group%2011%20Rev0%20-%20signed%20(1).pdf?web=1 |  | 45856.7689 | 45152.465 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 95198 |  | 1 | 1 |  | 701545RFI119 | 701545 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 129039
701504 | 11268 | FAASt [Pole and Conductor Repair - Arecibo Group 12] (Distribution) | 14F010450000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44917 | 1/3/2023 | 44957 | 44953 | [5 empty] | 1250000 | 188223 | 37878 | 29252 |  | 150345 | 7935 | 29943 | 188223 | 217475 |  |  | 44993 |  | 188223 | 150345 | [5 empty] | 188223 | 150345 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/120/701504-DR4339PR-Detailed%20SOW%20Arecibo%20Group%2012%20Rev0%20-%20signed.pdf?web=1 |  | 45856.7689 | 45152.465 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 29252 | 4491 | 1 | 1 |  | 701504RFI120 | 701504 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 33387
701495 | 11263 | FAASt [Pole and Conductor Repair - Mayagüez Group 14] (Distribution) | 14F010400000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44917 | 1/3/2023 | 44957 | 44953 | [5 empty] | 1250000 | 25678.75 | 5830.39 | 3960 |  | 19848 | 1221.39 | 4609 | 25678.39 | 29638.39 |  |  | 44987 |  | 25678.75 | 19848.36 | [5 empty] | 25678.75 | 19848.36 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/121/701495-DR4339PR-Detailed%20SOW%20Mayaguez%20Group%2014%20Rev0%20-%20signed.pdf?web=1 |  | 45856.7689 | 45152.465 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 3959.6 |  | 1 | 1 |  | 701495RFI121 | 701495 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 5830.39
701473 | 11693 | FAASt [Canovanas Streetlighting] (Distribution) | 14F013770000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 44909 | 1/3/2023 | 45199 | 45197 | 45876 |  |  |  |  | 11554562 | 14314798.95 | 1574362 | 14314799 |  | 2681107 | 1574362 | 0 | 4255469 | 18570268 | 45473 | 45626 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/122/701473-DR4339PR-Distribution%20Streetlight%20-%20Can%C3%B3vanas.pdf?web=1 |  | 46059.6197 | 45152.465 | Jahdiel Franqui | Distribution Streetlighting | Jason Fournier |  |  |  |  | 3.3639 | 1 | 45875 | 701473RFI122 | 701473 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
701472 | 11727 | FAASt [Comerio Streetlighting] (Distribution) | 14F013760000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE | [15 empty] | 44909 | 1/3/2023 | 45382 | 45350 | 45391 |  |  |  |  | 4664340 | 7400895.19 | 862126 | 1640383 |  | 6538769 | 0 | 862126 | 7400895 | 9041278 | 45473 | 45535 | 45422 | 8/30/2024 | 7400895.19 | 6538769.44 | 7400895.19 | 6538769.44 |  |  |  | 7400895.19 | 6538769.44 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/123/701472-DR4339PR-Distribution%20Streetlight%20-%20Comer%C3%ADo.pdf?web=1 | 2/28/2024: QC Review Complete7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 46070.5248 | 45152.465 | Jahdiel Franqui | Distribution Streetlighting | Marlina Crespo |  |  | 1640383 |  | 1 | 1 |  | 701472RFI123 | 701472 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 862125.75
699814 | 11576 | FAASt [Juana Diaz Streetlighting] (Distribution) | 14F013900000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 44908 | 12/23/2022 | 45199 | 45197 | 45306 |  |  |  |  | 13124331 | 15781505 | 1909452 | 2898942 |  | 15781505 | 296320 | 1613132 | 17690957 | 20589899 | 45596 | 45747 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/124/699814-DR4339PR-%20ISOW-%20Project%20Scope%20of%20work-Juana%20D%C3%ADaz.pdf?web=1 |  | 46059.6195 | 45152.465 | Jahdiel Franqui | Distribution Streetlighting | Jason Fournier |  |  |  |  | 0.89207 | 1 | 45875 | 699814RFI124 | 699814 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
698579 | 11629 | FAASt [Orocovis Streetlighting] (Distribution) | 14F013800000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE | [15 empty] | 44909 | 12/20/2022 | 45291 | 45261 | [5 empty] | 3973478 | 9410766.24 | 1339801 | 1873982 |  | 8070965 | 414167.51 | 925633.49 | 9410766 | 11284748 | 45473 | 45535 | 45373 |  | 9410766.24 | 8070964.96 | [5 empty] | 9410766.24 | 8070964.96 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/125/698579-DR4339PR-ISOW%20Distribution%20Streetlight%20-%20Orocovis.pdf?web=1 |  | 45856.7689 | 45152.465 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 1873982.08 |  | 1 | 1 |  | 698579RFI125 | 698579 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 1339801.28
698570 | 11560 | FAASt [Corozal Streetlighting] (Distribution) | 14F013750000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE | [15 empty] | 44909 | 12/20/2022 | 45169 | 45161 | 45187 |  |  |  |  | 10808513 | 15946081.93 | 2225874 | 2501126 |  | 13720208 | 0 | 2225874 | 15946082 | 18447208 |  |  | 45289 | 8/30/2024 | 15946081.93 | 13720208.31 | 15946081.93 | 13720208.31 |  |  |  | 15946081.93 | 13720208.31 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/126/698570-DR4339PR-ISOW%20Distribution%20Streetlight%20-%20Corozal.pdf?web=1 |  | 46070.5244 | 45152.465 | Jahdiel Franqui | Distribution Streetlighting | Marlina Crespo |  |  | 2501126 |  | 1 | 1 |  | 698570RFI126 | 698570 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 2225873.62
698522 | 11582 | FAASt [Vieques Streetlighting] (Distribution) | 14F013790000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 44909 | 12/20/2022 | 45199 | 45197 | 45306 |  |  |  |  | 3832444 | 4386770.2 | 519326 | 1374011 |  | 4386770 | 123865 | 395461 | 4906096 | 6280107 | 45473 | 45626 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/127/698522-DR4339PR-Distribution%20Streetlighting%20-%20Vieque.pdf?web=1 |  | 46077.5786 | 45152.465 | Jahdiel Franqui | Distribution Streetlighting | Ashleah Dingle |  |  |  |  | 0.89415 | 1 | 45875 | 698522RFI127 | 698522 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
698511 | 11680 | FAASt [Culebra Streetlighting] (Distribution) | 14F013910000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE | [15 empty] | 44909 | 12/20/2022 | 45291 | 45261 | 45315 |  |  |  |  | 1036293 | 1309407 | 153603 | 476439 |  | 1155804 | 62197 | 91406 | 1309407 | 1785846 | 45473 | 45504 | 45394 |  | 1309407 | 1155804 | [5 empty] | 1309407 | 1155804 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/128/698511-DR4339PR-Distribution%20Streetlighting%20-%20Culebra.pdf?web=1 |  | 45856.7689 | 45152.465 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 476440 |  | 1 | 1 |  | 698511RFI128 | 698511 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 153603
698458 | 11518 | FAASt [Guaynabo Streetlighting] (Distribution) | 14F013840000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE | [15 empty] | 44909 | 12/20/2022 | 45107 | 45108 | 45134 |  |  |  |  | 10334312 | 10615811.01 | 853056.42 | 1979750 |  | 9762755 | 0 | 853056.42 | 10615811.42 | 12595561.42 |  |  | 45233 | 8/30/2024 | 10615811.01 | 9762754.59 | 10615811.01 | 9762754.59 |  |  |  | 10615811.01 | 9762754.59 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/129/698458-DR4339PR-Detailed%20SOW%20Guaynabo%20Phase%201%20High%20Priority%20Rev1%20-%20DSOW%20-%20signed%20(2).pdf |  | 46070.524 | 45152.465 | Jahdiel Franqui | Distribution Streetlighting | Marlina Crespo |  |  | 1979750.26 |  | 1 | 1 |  | 698458RFI129 | 698458 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 853056.42
698439 | 11526 | FAASt [Las Marias Streetlighting] (Distribution) | 14F013820000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE | [15 empty] | 44909 | 12/20/2022 | 45107 | 45107 | 45147 |  |  |  |  | 3525848 | 8360922 | 1287705 | 1653390 |  | 7073217 | 0 | 1287705 | 8360922 | 10014312 |  |  | 45233 | 8/30/2024 | 8360922 | 7073217 | 8360922 | 7073217 |  |  |  | 8360922 | 7073217 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/130/698439-DR4339PR-Detailed%20SOW%20Las%20Mar%C3%ADas%20Rev1%20-%20DSOW%20-%20signed%20(2).pdf?web=1 |  | 46070.5237 | 45152.465 | Jahdiel Franqui | Distribution Streetlighting | Marlina Crespo |  |  | 1653390 |  | 1 | 1 |  | 698439RFI130 | 698439 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 1287705
698432 | 11523 | FAASt [Hormigueros Streetlighting] (Distribution) | 14F013830000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 44909 | 12/20/2022 | 45107 | 45107 | 45287 |  |  |  |  | 5171244 | 6920157.56 | 968057 | 1698467 |  | 6920158 | 190774 | 777283 | 7888215 | 9586682 | 45657 | 45808 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/131/698432-DR4339PR-Detailed%20SOW%20Hormigueros%20Rev1%20-%20DSOW%20-%20signed.pdf?web=1 |  | 46059.6192 | 45152.465 | Jahdiel Franqui | Distribution Streetlighting | Jason Fournier |  |  |  |  | 0.87728 | 1 | 45875 | 698432RFI131 | 698432 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
698427 | 11525 | FAASt [Maricao Streetlighting] (Distribution) | 14F013810000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 44909 | 12/20/2022 | 45107 | 45108 | 45279 |  |  |  |  | 1250000 | 4846034.89 | 1028907 | 1377820 |  | 4846035 | 227776 | 801131 | 5874942 | 7252762 | 45626 | 45777 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/132/698427-DR4339PR-Detailed%20SOW%20Maricao%20Rev0%20-%20DSOW%20-%20signed%20(1).pdf?web=1 |  | 46077.5786 | 45152.465 | Jahdiel Franqui | Distribution Streetlighting | Ashleah Dingle |  |  |  |  | 0.82487 | 1 | 45875 | 698427RFI132 | 698427 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
698424 | 11344 | FAASt [Florida Streetlighting] (Distribution) | 14F013850000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE | [15 empty] | 44909 | 12/20/2022 | 45016 | 45016 | [5 empty] | 4130863 | 10309031.53 | 997190 | 1705096 |  | 9311842 | 277173 | 720017 | 10309032 | 12014128 |  |  | 45222 |  | 10309031.53 | 9311841.53 | [5 empty] | 10309031.53 | 9311841.53 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/133/698424-DR4339PR-Detailed%20SOW%20Florida%20Rev0%20-%20signed%20-%20DSOW%20(1).pdf?web=1 |  | 45856.7689 | 45152.465 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 1705096.48 |  | 1 | 1 |  | 698424RFI133 | 698424 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 997190
697183 | 11668 | FAASt [Vega Baja Streetlighting] (Distribution) | 14F013860000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 44901 | 12/15/2022 | 45291 | 45287 | [5 empty] | 16684927 | 9248657.11 | 1117331 | 1940155 |  | 9248657 | 193746 | 923585 | 10365988 | 12306143 | 45473 | 45626 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/134/1272890-DR4339PR-Applicant%20Scope%20of%20Work%20Vega%20Baja.pdf?web=1 |  | 46059.6189 | 45152.465 | Jahdiel Franqui | Distribution Streetlighting | Jason Fournier |  |  |  |  | 0.89221 | 1 | 45875 | 697183RFI134 | 697183 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
693788 | 11547 | FAASt [Toa Alta Streetlighting] (Distribution) | 14F013870000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 44904 | 12/9/2022 | 45169 | 45161 | 45279 |  |  |  |  | 6721337.37 | 5847563.41 | 481369 | 1617458 |  | 5847563 | 104298 | 377071 | 6328932 | 7946390 | 45626 | 45777 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/135/693788-DR4339PR-Detailed%20SOW%20Toa%20Alta%20Phase%201%20High%20Priority%20Rev0%20-%20DSOW%20-%20signed.pdf?web=1 |  | 46059.6188 | 45152.465 | Jahdiel Franqui | Distribution Streetlighting | Jason Fournier |  |  |  |  | 0.92394 | 1 | 45875 | 693788RFI135 | 693788 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
693615 | 11685 | FAASt [Rio Grande Streetlighting] (Distribution) | 14F013880000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 44903 | 12/8/2022 | 45199 | 45197 | 45309 |  |  |  |  | 14880102 | 6376770.32 | 700108 | 1579242 |  | 6376770 | 138969 | 561139 | 7076878 | 8656120 | 45504 | 45657 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/136/920554-DR4339PR-Distribution%20Streetlighting%20-%20Rio%20Grande.pdf?web=1 |  | 46077.5786 | 45152.465 | Jahdiel Franqui | Distribution Streetlighting | Ashleah Dingle |  |  |  |  | 0.90107 | 1 | 45875 | 693615RFI136 | 693615 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
693543 | 11634 | FAASt [Juncos Streetlighting] (Distribution) | 14F013780000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 44903 | 12/8/2022 | 45230 | 45261 | 45541 |  |  |  |  | 10957723 | 12854140.62 | 1643590 | 1899782 |  | 11568798 | 260418 | 1383172 | 13212388 | 15112170 | 45596 | 45747 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/137/936204-DR4339PR-Distribution%20Streetlighting%20-%20Juncos.pdf?web=1 |  | 46059.6186 | 45152.465 | Jahdiel Franqui | Distribution Streetlighting | Jason Fournier | 0 Months |  |  |  | 0.97289 | 1 | 45875 | 693543RFI137 | 693543 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
691702 | 11326 | FAASt [Trujillo Alto Streetlighting] (Distribution) | 14F012860000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE | [15 empty] | 44895 | 11/30/2022 | 45016 | 44998 | [5 empty] | 16750334 | 26286925 | 1009578 | 3389490 |  | 25277347 | 246446 | 763132 | 26286925 | 29676415 |  |  | 45063 |  | 26286925 | 25277347 | [5 empty] | 26286925 | 25277347 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/138/FEMA%20Detailed%20Scope%20of%20Work%20Trujillo%20Alto%20Phase%201%20High%20Priority%20-%20signed.pdf?web=1 |  | 45856.7689 | 45152.465 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 3389490 |  | 1 | 1 |  | 691702RFI138 | 691702 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 1009578
691246 | 11231 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 10] (Distribution) | 14F010340000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44866 | 11/28/2022 | 44926 | 44916 | 44942 |  |  |  |  | 3000000 | 245340.07 | 33717.31 | 41364 |  | 211623 | 0 | 33717.31 | 245340.31 | 286704.31 |  |  | 44973.5347 | 8/30/2024 | 245340.07 | 211622.76 | 245340.07 | 211622.76 |  |  |  | 245340.07 | 211622.76 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/139/691246%20-%20DR4339PR-Detailed%20SOW%20San%20Juan%20Group%2010%20Rev1.pdf?web=1 |  | 46070.5233 | 45152.465 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Marlina Crespo |  |  | 41363.6 |  | 1 | 1 |  | 691246RFI139 | 691246 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 33717.31
690721 | 11531 | FAASt [Guayama Streetlighting] (Distribution) | 14F012830000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 44887 | 11/22/2022 | 45107 | 45108 | 45279 |  |  |  |  | 16731938 | 5525916.66 | 542958 | 1519802 |  | 5525917 | 117119 | 425839 | 6068875 | 7588677 | 45688 | 45838 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/140/690721-DR4339PR-Detailed%20SOW%20Guayama%20Rev0%20-%20DSOW%20-%20signed%20(1).pdf?web=1 |  | 46059.6182 | 45152.465 | Jahdiel Franqui | Distribution Streetlighting | Jason Fournier |  |  |  |  | 0.91053 | 1 | 45875 | 690721RFI140 | 690721 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
690545 | 11319 | FAASt [Aguadilla Streetlighting] (Distribution) | 14F012780000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE | [15 empty] | 44886 | 11/21/2022 | 45016 | 44998 | [5 empty] | 19301209 | 21092584 | 1295775 | 3021242 |  | 19796808 | 333333 | 962442 | 21092583 | 24113825 |  |  | 45063 | 05/15/2024 | 21092584 | 19796809 | 21092584 | 19796809 |  |  |  | 21092584 | 19796809 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/141/FEMA%20Detailed%20Scope%20of%20Work%20Aguadilla%20Municipality%20Phase%201%20High%20Priority%20-%20Signed.pdf?web=1 |  | 45856.769 | 45152.465 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 3021242 |  | 1 | 1 |  | 690545RFI141 | 690545 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 1295775
690483 | 11552 | FAASt [Cayey Streetlighting] (Distribution) | 14F012820000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 44886 | 11/21/2022 | 45169 | 45161 | 45279 |  |  |  |  | 13498378 | 13343261.38 | 1319139 | 2650718 |  | 13343261 | 218624 | 1100515 | 14662400 | 17313118 | 45626 | 45777 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/142/690483-DR4339PR-Detailed%20SOW%20Cayey%20Rev1%20-%20DSOW%20-%20signed.pdf |  | 46059.618 | 45152.465 | Jahdiel Franqui | Distribution Streetlighting | Jason Fournier |  |  |  |  | 0.91003 | 1 | 45875 | 690483RFI142 | 690483 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
690480 | 11683 | FAASt [Humacao Streetlighting] (Distribution) | 14F012870000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 44886 | 11/21/2022 | 45199 | 45197 | 45306 |  |  |  |  | 17827506 | 7598892 | 922000 | 1719130 |  | 7598892 | 170104 | 751896 | 8520892 | 10240022 | 45565 | 45716 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/143/690480-DR4339PR-ISOW%20-%20FEMA%20Project%20Scope%20of%20Work%20-%20Humacao.pdf?web=1 |  | 46059.6179 | 45152.465 | Jahdiel Franqui | Distribution Streetlighting | Jason Fournier |  |  |  |  | 0.8918 | 1 | 45875 | 690480RFI143 | 690480 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
689071 | 11256 | FAASt [Pole and Conductor Repair - Arecibo Group 11] (Distribution) | 14F010460000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44866 | 11/9/2022 | 44926 | 44953 | 44958 |  |  |  |  | 3500000 | 77036.24 | 17491.16 | 11879 |  | 59545 | 3664.16 | 13827 | 77036.16 | 88915.16 |  |  | 44987.5167 |  | 77036.24 | 59545.08 | [5 empty] | 77036.24 | 59545.08 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/144/689071-DR4339PR-Detailed%20SOW%20Arecibo%20Group%2011%20Rev%201.pdf?web=1 |  | 45856.769 | 45152.465 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 11878.8 |  | 1 | 1 |  | 689071RFI144 | 689071 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 17491.16
688774 | 11207 | FAASt Distribution Pole and Conductor Repair - Ponce Group 9 (Distribution) | 14F010390000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44866 | 11/7/2022 | 44926 | 44916 | [5 empty] | 3000000 | 541815 | 98484 | 86719 |  | 443331 | 20631 | 77853 | 541815 | 628534 |  |  | 44957.5389 |  | 541815 | 443331 | [5 empty] | 541815 | 443331 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/145/688774-DR4339PR-Detailed%20SOW%20Ponce%20Group%209%20Rev0.pdf?web=1 |  | 45856.769 | 45152.465 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 86719 | 11678 | 1 | 1 |  | 688774RFI145 | 688774 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 86806
688630 | 11273 | FAASt [Pole and Conductor Repair - Mayagüez Group 12] (Distribution) | 14F010420000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44866 | 11/7/2022 | 44926 | 44946 | [5 empty] | 3000000 | 52719.38 | 9990.97 | 8327 |  | 42728 | 0 | 9990.97 | 52718.97 | 61045.97 |  |  | 44993.525 | 8/30/2024 | 52719.38 | 42728.41 | 52719.38 | 42728.41 |  |  |  | 52719.38 | 42728.41 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/146/688630-DR4339PR-Detailed%20SOW%20Mayaguez%20Group%2012%20Rev0%20-%20signed.pdf?web=1 |  | 46070.5229 | 45152.4651 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Marlina Crespo |  |  | 8327.05 |  | 1 | 1 |  | 688630RFI146 | 688630 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 9990.97
688629 | 11277 | FAASt [Pole and Conductor Repair - Mayagüez Group 13] (Distribution) | 14F010410000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44866 | 11/7/2022 | 44926 | 44953 | [5 empty] | 3000000 | 134828.92 | 27886.93 | 20834 |  | 106942 | 5841.93 | 22045 | 134828.93 | 155662.93 |  |  | 44993.525 |  | 134828.92 | 106941.99 | [5 empty] | 134828.92 | 106941.99 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/147/688629-DR4339PR-Detailed%20SOW%20Mayaguez%20Group%2013%20Rev0%20-%20signed%20(2).pdf?web=1 |  | 45856.769 | 45152.4651 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 20833.9 |  | 1 | 1 |  | 688629RFI147 | 688629 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 27886.93
688627 | 11193 | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 9] (Distribution) | 14F010480000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44866 | 11/7/2022 | 44926 | 44915 | [5 empty] | 3000000 | 375962.49 | 72188.49 | 58918 |  | 303774 | 0 | 72188.49 | 375962.49 | 434880.49 |  |  | 44957.5389 | 8/30/2024 | 375962.49 | 303774 | 375962.49 | 303774 |  |  |  | 375962.49 | 303774 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/148/688627-DR4339PR-Detailed%20SOW%20Arecibo%20Group%209%20Rev0.pdf?web=1 |  | 46070.5223 | 45152.4651 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Marlina Crespo |  |  | 58918 |  | 1 | 1 |  | 688627RFI148 | 688627 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 72188.49
688625 | 11279 | FAASt [Pole and Conductor Repair - Ponce Group 10] (Distribution) | 14F010380000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44867 | 11/7/2022 | 44926 | 44946 | [5 empty] | 3000000 | 901290.28 | 191275.59 | 139358 |  | 710015 | 0 | 191275.59 | 901290.59 | 1040648.59 |  |  | 45005.4896 | 8/30/2024 | 901290.28 | 710014.69 | 901290.28 | 710014.69 |  |  |  | 901290.28 | 710014.69 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/149/688625-DR4339PR-Detailed%20SOW%20Ponce%20Group%2010%20Rev0%20-%20signed.pdf?web=1 |  | 46070.5219 | 45152.4651 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Marlina Crespo |  |  | 139357.85 |  | 1 | 1 |  | 688625RFI149 | 688625 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 191275.59
688623 | 107781 | FAASt [Automation Program Group 1A-8 Feeders] (Distribution) | 14F005200000, 14F000350000, 14F000160000, 14F003260000 | PBUT04 - Distribution Automation | Grid Automation | Distribution Automation |  | Restoration | TRUE | 45869 | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE |  | 230370000 | 44771 | 44798 |  | 44801 |  |  |  | 44873 | 11/7/2022 | 45077 | 45047 | 45288 |  |  |  |  | 900000 | 5145417.32 | 1877045 | 130382 |  | 874904 | 243445 | 1633600 | 2751949 | 2882331 | 45900 | 46053 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/150/688623-DR4339PR-DSOW%20Automation%20Group%201%2006142023%5B22070%5D%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short List | 46059.6178 | 45152.4651 | Jahdiel Franqui | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Jason Fournier |  |  |  |  | 1.8697 | 1 | 45887 | 688623RFI150 | 688623 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
688472 | 11217 | FAASt [Pole and Conductor Repair - Mayaguez Group 11] (Distribution) | 14F010430000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44869 | 11/4/2022 | 44926 | 44916 | 44930 |  |  |  |  | 3000000 | 179894.86 | 14986 | 29922 |  | 164909 | 0 | 14986 | 179895 | 209817 |  |  | 44973 | 8/30/2024 | 179894.86 | 164908.86 | 179894.86 | 164908.86 |  |  |  | 179894.86 | 164908.86 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/151/688472-DR4339PR-Detailed%20SOW%20Mayaguez%20Group%2011%20Rev0%20(1).pdf |  | 46070.5203 | 45152.4651 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Marlina Crespo |  |  | 29921.55 |  | 1 | 1 |  | 688472RFI151 | 688472 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 14986
688198 | 11276 | FAASt [Pole and Conductor Repair - Arecibo Group 10] (Distribution) | 14F010470000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44868 | 11/3/2022 | 44926 | 44946 | [5 empty] | 2500000 | 76862.24 | 16023.76 | 12053 |  | 60838 | 3356.76 | 12667 | 76861.76 | 88914.76 |  |  | 45005 |  | 76862.24 | 60838.48 | [5 empty] | 76862.24 | 60838.48 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/152/688198-DR4339PR-Detailed%20SOW%20Arecibo%20Group%2010%20Rev0%20-%20signed.pdf?web=1 |  | 45856.769 | 45152.4651 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 12052.8 |  | 1 | 1 |  | 688198RFI152 | 688198 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 16023.76
688109 | 11264 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 11] (Distribution) | 14F010330000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44867 | 11/2/2022 | 44926 | 44946 | [5 empty] | 3000000 | 563429.26 | 114710.2 | 87444 |  | 448719 | 0 | 114710.2 | 563429.2 | 650873.2 |  |  | 44993 | 8/30/2024 | 563429.26 | 448719.06 | 563429.26 | 448719.06 |  |  |  | 563429.26 | 448719.06 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/153/688109%20-%20DR4339PR-Detailed%20SOW%20San%20Juan%20Group%2011%20Rev0%20-%20signed.pdf?web=1 |  | 46070.5201 | 45152.4651 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Marlina Crespo |  |  | 87443.55 |  | 1 | 1 |  | 688109RFI153 | 688109 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 114710.2
688096 | 11214 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 15] (Distribution) | 14F010440000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44867 | 11/2/2022 | 44926 | 44915 | [5 empty] | 3000000 | 27238.64 | 5830.39 | 4169 |  | 21408 | 1221.39 | 4609 | 27238.39 | 31407.39 |  |  | 44957 |  | 27238.64 | 21408.25 | [5 empty] | 27238.64 | 21408.25 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/154/688096-DR4339PR-Detailed%20SOW%20Caguas%20Group%2015%20Rev0.pdf?web=1 |  | 45856.769 | 45152.4651 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 4169.45 | 691.35 | 1 | 1 |  | 688096RFI154 | 688096 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 5139.04
686482 | 11572 | FAASt [Isabela Streetlighting] (Distribution) | 14F012880000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 44812 | 10/20/2022 | 45199 | 45187 | 45306 |  |  |  |  | 16599080 | 7013624.27 | 733835 | 1698664 |  | 7013624 | 143078 | 590757 | 7747459 | 9446123 | 45596 | 45747 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/155/686482%20-DR4339PR%20-ISOW%20-%20FEMA%20Project%20Scope%20of%20Work%20-%20Isabela.pdf?web=1 |  | 46059.6175 | 45152.4651 | Jahdiel Franqui | Distribution Streetlighting | Jason Fournier |  |  |  |  | 0.90528 | 1 | 45875 | 686482RFI155 | 686482 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
686480 | 11229 | FAASt [Pole and Conductor Repair - Ponce Group 7] (Distribution) | 14F008880000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44805 | 10/20/2022 | 44926 | 44902 | 44935 |  |  |  |  | 3000000 | 632056 | 108652 | 101359 |  | 523404 | 22761 | 85891 | 632056 | 733415 |  |  | 44973 |  | 632056 | 523404 | [5 empty] | 632056 | 523404 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/156/686480-DR4339PR-Detailed%20SOW%20Ponce%20Group%207%20Rev1.pdf?web=1 |  | 45856.769 | 45152.4651 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 101359 |  | 1 | 1 |  | 686480RFI156 | 686480 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 108652
686471 | 11116 | FAASt [Pole and Conductor Repair - Arecibo Group 5] (Distribution) | 14F008640000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44840 | 10/20/2022 | 44895 | 44882 | [5 empty] | 3000000 | 319606 | 68700 | 49227 |  | 250906 | 14392 | 54308 | 319606 | 368833 |  |  | 44922 | 4/17/2024 | 319606 | 250906 | 319606 | 250906 |  |  |  | 319606 | 250906 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/157/686471-DR4339PR-Detailed%20SOW%20Arecibo%20Group%205%20Rev0.pdf?web=1 |  | 45856.769 | 45152.4651 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 49227 |  | 1 | 1 |  | 686471RFI157 | 686471 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 68700
686453 | 11152 | FAASt [Pole and Conductor Repair - Mayagüez Group 7] (Distribution) | 14F008700000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44854 | 10/20/2022 | 44895 | 44886 | [5 empty] | 3000000 | 25579 | 4995 | 4059 |  | 20584 | 1046 | 3949 | 25579 | 29638 |  |  | 44922 |  | 25579 | 20584 | [5 empty] | 25579 | 20584 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/158/686453-DR4339PR-Detailed%20SOW%20Mayaguez%20Group%207%20Rev0.pdf?web=1 |  | 45856.769 | 45152.4651 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 4059 |  | 1 | 1 |  | 686453RFI158 | 686453 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 4995
685943 | 11138 | FAASt Distribution Pole and Conductor Repair Ponce Group 5(Distribution) | 14F008720000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44840 | 10/18/2022 | 44895 | 44886 | [6 empty] | 318232.22 | 63260 | 49774 |  | 254972 | 13252 | 50008 | 318232 | 368006 |  |  | 44936 |  | 318232.22 | 254972.22 | [5 empty] | 318232.22 | 254972.22 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/159/685943-DR4339PR-Detailed%20SOW%20Ponce%20Group%205%20Rev0.pdf?web=1 |  | 45856.769 | 45152.4651 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 49774.2 | 7501.2 | 1 | 1 |  | 685943RFI159 | 685943 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 55758.8
685869 | 107780 | FAASt [Mayagüez TC] (Substation) | 14F016580000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds |  |  | TRUE | 45930 |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 44851 | 10/17/2022 | [7 empty] | 3200000 | 14464362 | [5 empty] | 0 | 3200000 | 3200000 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/160/685869-DR4339PR0ISOW-Substation%20Minor%20Repairs%20Group%20G.pdf?web=1 |  | 46077.5786 | 45152.4651 | Jahdiel Franqui | Substation Minor Repairs | Ashleah Dingle |  |  |  |  | 4.5201 | 1 | 45888 | 685869RFI160 | 685869 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
685477 | 11171 | FAASt [Pole and Conductor Repair - Arecibo Group 6] (Distribution) | 14F008650000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44840 | 10/13/2022 | 44895 | 44887 | 44908 |  |  |  |  | 3000000 | 413482 | 58304 | 67123 |  | 355178 | 12214 | 46090 | 413482 | 480605 |  |  | 44950 |  | 413482 | 355178 | [5 empty] | 413482 | 355178 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/161/685477-DR4339PR-Detailed%20SOW%20Arecibo%20Group%206%20Rev1.pdf?web=1 |  | 45856.769 | 45152.4651 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 67123 | 6914 | 1 | 1 |  | 685477RFI161 | 685477 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 51390
685370 | 11150 | FAASt [Pole and Conductor Repair - Mayagüez Group 8] (Distribution) | 14F008710000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44840 | 10/12/2022 | 44895 | 44885 | [5 empty] | 3000000 | 83809 | 14986 | 13127 |  | 68823 | 3139 | 11847 | 83809 | 96936 |  |  | 44936 |  | 83809 | 68823 | [5 empty] | 83809 | 68823 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/162/685370-DR4339PR-Detailed%20SOW%20Mayaguez%20Group%208%20Rev0.pdf?web=1 |  | 45856.769 | 45152.4651 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 13127 | 1777 | 1 | 1 |  | 685370RFI162 | 685370 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 13209
685263 | 11143 | FAASt Distribution Pole and Conductor Repair - Ponce Group 6 (Distribution) | 14F008730000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44846 | 10/11/2022 | 44895 | 44886 | [5 empty] | 3000000 | 672383 | 134695 | 103281 |  | 537688 | 28217 | 106478 | 672383 | 775664 |  |  | 44922 |  | 672383 | 537688 | [5 empty] | 672383 | 537688 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/163/685263-DR4339PR-Detailed%20SOW%20Ponce%20Group%206%20Rev0.pdf?web=1 |  | 45856.769 | 45152.4651 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 103281 | 15972 | 1 | 1 |  | 685263RFI163 | 685263 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 118723
684920 | 11573 | FAASt Substation High Voltage Replacement_Group 1 (Substation) | 14F019940000, 14F019930000, 14F019950000, 14F008410000, 14F019960000 | PBUT07 - Substation Reliability | Substation | Substation Rebuilds |  | Restoration | FALSE | [7 empty] | 75700000 | 44771 | 44798 |  | 44801 |  |  |  | 44840 | 10/6/2022 | 45107 | 45107 | 45244 |  |  |  |  | 9410000 | 6929384 | 0 | 958084 |  | 6929383 | 0 | 0 | 6929383 | 7887467 |  |  | 45289 | 8/30/2024 | 6929384 | 6929384 | 6929384 | 6929384 |  |  |  | 6929384 | 6929384 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/164/684920-DR4339PR-Detail%20SOW%20-%20Sub%20HV%20Replacement_Group%201%20-%20Rev%200%20(1)%20-%20signed%20(1).pdf?web=1 |  | 46070.5197 | 45152.4651 | Jahdiel Franqui | Substation High Voltage Equipment Replacement | Marlina Crespo |  |  | 958084 |  | 1 | 1 |  | 684920RFI164 | 684920 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
682910 | 11212 | FAASt [Distribution Pole and Conductor Repair - Bayamón Group 7] (Distribution) | 14F008670000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44823 | 9/19/2022 | 44895 | 44883 | [5 empty] | 3000000 | 622823 | 105667 | 99229 |  | 517156 | 22135.72 | 83531.28 | 622823 | 722052 |  |  | 44957 |  | 622823 | 517156 | [5 empty] | 622823 | 517156 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/165/682910-DR4339PR-Detailed%20SOW%20Bayamon%20Group%207%20Rev0.pdf?web=1 |  | 45856.769 | 45152.4651 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 99229 | 12530 | 1 | 1 |  | 682910RFI165 | 682910 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 93137
682898 | 11183 | FAASt [Distribution Pole and Conductor Repair - Bayamón Group 6] (Distribution) | 14F008660000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44823 | 9/19/2022 | 44895 | 44882 | 44908 |  |  |  |  | 3000000 | 744027.12 | 108700.19 | 120284 |  | 635327 | 22771.19 | 85929 | 744027.19 | 864311.19 |  |  | 44950 |  | 744027.12 | 635326.93 | [5 empty] | 744027.12 | 635326.93 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/166/682898-DR4339PR-Detailed%20SOW%20Bayamon%20Group%206%20Rev1.pdf?web=1 |  | 45856.769 | 45152.4651 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 120284.25 | 12889.35 | 1 | 1 |  | 682898RFI166 | 682898 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 95810.84
682890 | 11136 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 12] (Distribution) | 14F008690000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44823 | 9/19/2022 | 44895 | 44886 | [5 empty] | 3000000 | 612378.63 | 102310.67 | 98276 |  | 510068 | 21432.67 | 80878 | 612378.67 | 710654.67 |  |  | 44922 |  | 612378.63 | 510067.96 | [5 empty] | 612378.63 | 510067.96 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/167/682890-DR4339PR-Detailed%20SOW%20Caguas%20Group%2012%20Rev0.pdf?web=1 |  | 45856.769 | 45152.4651 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 98275.6 | 12131.7 | 1 | 1 |  | 682890RFI167 | 682890 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 90178.97
682882 | 11130 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 11] (Distribution) | 14F008680000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44823 | 9/19/2022 | 44895 | 44883 | [5 empty] | 3500000 | 659039.4 | 113378.16 | 104353 |  | 545661 | 23751.16 | 89627 | 659039.16 | 763392.16 |  |  | 44936 |  | 659039.4 | 545661.24 | [5 empty] | 659039.4 | 545661.24 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/168/682882-DR4339PR-Detailed%20SOW%20Caguas%20Group%2011%20Rev0.pdf?web=1 |  | 45856.769 | 45152.4651 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 104353.35 |  | 1 | 1 |  | 682882RFI168 | 682882 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 113378.16
682870 | 11137 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 6] (Distribution) | 14F008740000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44823 | 9/19/2022 | 44895 | 44887 | [5 empty] | 3500000 | 103412.77 | 17491 | 16717 |  | 85922 | 0 | 17491 | 103413 | 120130 |  |  | 44922 | 8/30/2024 | 103412.77 | 85921.77 | 103412.77 | 85921.77 |  |  |  | 103412.77 | 85921.77 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/169/682870-DR4339PR-Detailed%20SOW%20San%20Juan%20Group%206%20Rev0.pdf?web=1 |  | 46070.5194 | 45152.4651 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Marlina Crespo |  |  | 16716.65 |  | 1 | 1 |  | 682870RFI169 | 682870 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 17491
682865 | 11123 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 7] (Distribution) | 14F008750000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44823 | 9/19/2022 | 44895 | 44882 | [5 empty] | 3000000 | 91831 | 21148 | 13377 |  | 70683 | 4430 | 16718 | 91831 | 105208 |  |  | 44922 |  | 91831 | 70683 | [5 empty] | 91831 | 70683 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/170/682865-DR4339PR-Detailed%20SOW%20San%20Juan%20Group%207%20Rev0.pdf?web=1 |  | 45856.769 | 45152.4651 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 13377 | 2508 | 1 | 1 |  | 682865RFI170 | 682865 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 18640
682834 | 11402 | FAASt [EPC - Costa Sur TC - Phase II & III ] (Substation) | 14F008420000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | TRUE | Restoration | FALSE |  | Current | [5 empty] | 161980000 | 45288 | 45321 |  | 45318 |  |  |  | 44820 | 9/16/2022 | 45016 | 45016 | 45740 |  |  |  |  | 161980000 | 61444255.52 | 0 | 1345002.69 |  | 10983086.42 | 0 | 0 | 10983086.42 | 12328089.11 |  |  | 45335 | 9/17/2025 | 61444255.52 | 61444255.52 | 36917509.58 | 61444255.52 | 36917510 | 30357996.36 | 36917510 | 36917510 | 36917510 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/171/Estimates%20LPCE%20(Costa%20Sur%20Scope%203)%20With%20Out%20D%20&%20T%201-9-2024%20Rev.1%20(1).xlsx?web=1 |  | 46059.5417 | 45152.4651 | Jahdiel Franqui | Costa Sur TC (Guaypao TC) - Phase II & III | Jason Fournier | 0 Months |  | 5090347.22 | 0 | 5.5944 | 1 |  | 682834RFI171 | 682834 | 30357996.36 | 5151836 | 35509832.36 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
682645 | 107779 | FAASt [Maunabo TC] (Substation) | 14F016570000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | TRUE |  | FALSE |  | Current | [13 empty] | 44819 | 9/15/2022 |  | 45771 |  | 45798 | 45785 |  |  | 2400000 | 96115838 | 0 | 1605121.68 |  | 13016336.93 | 0 | 0 | 13016336.93 | 14621458.61 |  |  | 45917 |  | 8292125 | 8292125 |  |  |  | 4724211.98 |  | 8292125 | 8292125 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/172/682645-DR4339PR-ISOW-Substation%20Minor%20Repairs%20Group%20F.pdf?web=1 |  | 46059.5417 | 45152.4651 | Jahdiel Franqui | Substation Minor Repairs | Jason Fournier |  |  | 1605121.68 | 0 | 7.3842 | 1 |  | 682645RFI172 | 682645 | 4724211.98 |  | 4724211.98 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
682373 | 11165 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 14] (Distribution) | 14F008850000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44818 | 9/12/2022 | 44926 | 44903 | [5 empty] | 3000000 | 77605 | 11661 | 12740 |  | 65944 | 2443 | 9218 | 77605 | 90345 |  |  | 44936 |  | 77605 | 65944 | [5 empty] | 77605 | 65944 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/173/682373-DR4339PR-Detailed%20SOW%20Caguas%20Group%2014%20Rev0.pdf?web=1 |  | 45856.769 | 45152.4651 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 12740 | 1383 | 1 | 1 |  | 682373RFI173 | 682373 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 10278
682331 | 107777 | FAASt [RTU and Telecommunication Replacements Group 1 - Mayaguez Area] (Telecommunication) | 14F004430000 | PBIT01 - Telecom Sys & Network | Telecommunications | IT OT Telecom Systems and Network | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 44816 | 9/12/2022 | [7 empty] | 4360000 | 4360000 | [5 empty] | 0 | 4360000 | 4360000 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/174/1241927-DR4339PR-SOW.pdf?web=1 | 6/12/2025 - Project withdrawn in Grants Portal | 45877.5777 | 45152.4651 | Jahdiel Franqui | SCADA Remote Access and RTU Replacements | Ashleah Dingle |  |  |  |  | 1 | 1 | 45820 | 682331RFI174 | 682331 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
682328 | 11876 | FAASt [Bayamón TC - Rebuild] (Substation) | 14F008430000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | TRUE |  | FALSE |  | Current | [5 empty] | 71000000 | 44771 | 44798 |  | 44801 |  |  |  | 44816 | 9/12/2022 | 45260 | 45257 | 45862 | 45912 | 45897 | 8/28/2025 - Field EHP - Historic: Previous status applies: In review. Expected Completion Date (ECD): 9/12/2025. |  | 71000000 | 2637502.74 | 0 | 1136049.98 |  | 9126057.99 | 0 | 0 | 9126057.99 | 10262107.97 | 45688 | 45777 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/175/682328-DR-4339-PR-DSOW%20Transformer%20Replacement%20115-40kV%20112MVA%20Bayamon%20TC%207.24.2025%20signed.pdf?web=1 |  | 46059.5417 | 45152.4651 | Jahdiel Franqui | Bayamon TC - Phase II | Jason Fournier |  |  |  |  | 0.28901 | 4 |  | 682328RFI175 | 682328 | 4748384.44 | 0 | 4748384.44 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
682324 | 11145 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 13] (Distribution) | 14F008840000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44816 | 9/12/2022 | 44895 | 44893 | [5 empty] | 3000000 | 709229.55 | 136182.31 | 110616 |  | 573047 | 28528.31 | 107654 | 709229.31 | 819845.31 |  |  | 44936 |  | 709229.55 | 573047.24 | [5 empty] | 709229.55 | 573047.24 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/176/%5B682324%5D%20DR4339PR%20-%20FAASt%20%5BDistribution%20Pole%20and%20Conductor%20Repair%20-%20Caguas%20Group%2013%5D%20(Distribution)-%20SOW%20CE.pdf?web=1 |  | 45856.769 | 45152.4651 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 110616.4 | 16148.1 | 1 | 1 |  | 682324RFI176 | 682324 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 120034.21
682228 | 11196 | FAASt [Pole and Conductor Repair - Ponce Group 8] (Distribution) | 14F008890000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44812 | 9/8/2022 | 44926 | 44910 | [5 empty] | 3000000 | 952661.42 | 176882.42 | 150784 |  | 775779 | 37054.42 | 139828 | 952661.42 | 1103445.42 |  |  | 44957 |  | 952661.42 | 775779 | [5 empty] | 952661.42 | 775779 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/177/682228-DR4339PR-Detailed%20SOW%20Ponce%20Group%208%20Rev0.pdf?web=1 |  | 45856.769 | 45152.4651 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 150784 | 20974 | 1 | 1 |  | 682228RFI177 | 682228 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 155908.42
682210 | 11169 | FAASt [Pole and Conductor Repair - Mayagüez Group 9] (Distribution) | 14F008860000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44812 | 9/8/2022 | 44926 | 44902 | [5 empty] | 3000000 | 239847.61 | 41796.87 | 38248 |  | 198051 | 8755.87 | 33041 | 239847.87 | 278095.87 |  |  | 44950 |  | 239847.61 | 198050.74 | [5 empty] | 239847.61 | 198050.74 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/178/682210-DR4339PR-Detailed%20SOW%20Mayaguez%20Group%209%20Rev0.pdf?web=1 |  | 45856.769 | 45152.4651 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 38248.35 | 4956.15 | 1 | 1 |  | 682210RFI178 | 682210 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 36840.72
682180 | 11168 | FAASt [Pole and Conductor Repair - Mayagüez Group 10] (Distribution) | 14F008870000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44812 | 9/8/2022 | 44925 | 44903 | [5 empty] | 3000000 | 54402 | 11028 | 8414 |  | 43374 | 2310 | 8718 | 54402 | 62816 |  |  | 44936 |  | 54402 | 43374 | [5 empty] | 54402 | 43374 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/179/682180-DR4339PR-Detailed%20SOW%20Mayaguez%20Group%2010%20Rev0.pdf?web=1 |  | 45856.769 | 45152.4651 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 8414 | 1308 | 1 | 1 |  | 682180RFI179 | 682180 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 9720
682178 | 11201 | FAASt [Pole and Conductor Repair - Arecibo Group 7] (Distribution ) | 14F008800000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44812 | 9/8/2022 | 44926 | 44902 | [5 empty] | 3000000 | 262290.31 | 53746.06 | 40949 |  | 208544 | 11259.06 | 42487 | 262290.06 | 303239.06 |  |  | 44957 | 4/17/2024 | 262290.31 | 208544.25 | 262290.31 | 208544.25 |  |  |  | 262290.31 | 208544.25 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/180/682178-DR4339PR-Detailed%20SOW%20Arecibo%20Group%207%20Rev0.pdf?web=1 |  | 45856.769 | 45152.4651 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 40949.45 |  | 1 | 1 |  | 682178RFI180 | 682178 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 53746.06
682172 | 11182 | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 8] (Distribution) | 14F008810000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44812 | 9/8/2022 | 44926 | 44910 | [5 empty] | 3500000 | 266071.35 | 57671.35 | 40930 |  | 208400 | 12081.35 | 45590 | 266071.35 | 307001.35 |  |  | 44950 |  | 266071.35 | 208400 | [5 empty] | 266071.35 | 208400 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/181/682172-DR4339PR-Detailed%20SOW%20Arecibo%20Group%208%20Rev0.pdf?web=1 |  | 45856.769 | 45152.4651 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 40930 | 6838 | 1 | 1 |  | 682172RFI181 | 682172 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 50833.35
682136 | 11203 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 9] (Distribution) | 14F008830000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44811 | 9/7/2022 | 44926 | 44910 | 44930 |  |  |  |  | 3500000 | 565605 | 95954.05 | 90260 |  | 469651 | 20101.05 | 75853 | 565605.05 | 655865.05 |  |  | 44957 |  | 565605 | 469650.95 | [5 empty] | 565605 | 469650.95 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/182/682136-DR4339PR-Detailed%20SOW%20Bayamon%20Group%209%20Rev1.pdf?web=1 |  | 45856.769 | 45152.4651 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 90259.5 | 11377.95 | 1 | 1 |  | 682136RFI182 | 682136 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 84576.1
682135 | 11149 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 8] (Distribution) | 14F008820000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44811 | 9/7/2022 | 44895 | 44893 | [5 empty] | 3000000 | 693780.53 | 116779.74 | 109859 |  | 577001 | 24463.74 | 92316 | 693780.74 | 803639.74 |  |  | 44936 |  | 693780.53 | 577000.79 | [5 empty] | 693780.53 | 577000.79 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/183/682135-DR4339PR-Detailed%20SOW%20Bayamon%20Group%208%20Rev0.pdf?web=1 |  | 45856.769 | 45152.4652 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 109858.85 | 13847.4 | 1 | 1 |  | 682135RFI183 | 682135 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 102932.34
682121 | 11652 | FAASt - EPC -Aguirre TC-Phase II (Substation) | 14F008450000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | TRUE | Restoration | FALSE | [7 empty] | 192270000 | 45288 | 45321 |  | 45318 |  |  |  | 44811 | 9/7/2022 | 45107 | 45078 | [5 empty] | 192270000 | 82726096.38 |  | 11520000 |  | 180750000 | 0 | 0 | 180750000 | 192270000 | 45444 | 45900 | 45373 | 8/30/2024 | 82726096.38 | 82726096.38 | 82726096.38 | 82726096.38 |  |  |  | 82726096.38 | 82726096.38 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/184/Aguirre%20(%20El%20coqui%20TC)%20-%20FEMA%20Project%20Detailed%20Scope%20of%20Work%20rev%20-%20signed.pdf?web=1 |  | 46070.519 | 45152.4652 | Jahdiel Franqui | Aguirre TC (El Coqui) - Phase II and Phase III | Marlina Crespo |  |  | 7789677 |  | 0.45768 | 3 |  | 682121RFI184 | 682121 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
682031 | 11181 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 9] (Distribution) | 14F008910000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44810 | 9/6/2022 | 44926 | 44914 | [5 empty] | 3000000 | 625198 | 108247 | 94044 |  | 516951 | 22676 | 85571 | 625198 | 719242 |  |  | 44957 |  | 625198 | 516951 | [5 empty] | 625198 | 516951 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/185/682031-DR4339PR-Detailed%20SOW%20San%20Juan%20Group%209%20Rev0.pdf?web=1 |  | 45856.769 | 45152.4652 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 94044 | 12836 | 1 | 1 |  | 682031RFI185 | 682031 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 95411
682028 | 11166 | FAASt [Pole and Conductor Repair - San Juan Group 8] (Distribution) | 14F008900000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44810 | 9/6/2022 | 44926 | 44902 | [5 empty] | 3000000 | 537125.3 | 105743.62 | 83822 |  | 431382 | 22151.62 | 83592 | 537125.62 | 620947.62 |  |  | 44936 |  | 537125.3 | 431381.68 | [5 empty] | 537125.3 | 431381.68 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/186/682028-DR4339PR-Detailed%20SOW%20San%20Juan%20Group%208%20Rev0.pdf?web=1 |  | 45856.769 | 45152.4652 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 83822 | 12539 | 1 | 1 |  | 682028RFI186 | 682028 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 93204.62
681672 | 11184 | FAASt Transmission Priority Pole Replacements –38kV Line 2300 (Transmission) | 14F008920000 | PBUT13 - T Priority Pole Repl | Transmission – Pole Replacement | Transmission Priority Pole Replacements |  | Restoration | FALSE | [15 empty] | 44804 | 8/31/2022 | 44834 | 44820 | 44917 |  |  |  |  | 330000 | 216367 | 2243 | 26175 |  | 214124 | 699 | 1544 | 216367 | 242542 |  |  | 44957 | 4/18/2024 | 216367 | 214124 | 216367 | 214124 |  |  |  | 216367 | 214124 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/187/681672-DR4339PR-Detailed%20SOW%20-%20Line%202300%20Rev.2.pdf?web=1 |  | 45856.769 | 45152.4652 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Rey Roldan Rodríguez |  |  | 26175 |  | 1 | 1 |  | 681672RFI187 | 681672 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 2243
679780 | 11540 | FAASt [Bayamón Streetlighting] (Distribution) | 14F012800000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE | [15 empty] | 44777 | 8/8/2022 | 45230 | 45146 | 45167 |  |  |  |  | 46886628 | 21886903 | 1176376 | 3212958 |  | 20710527 | 0 | 1176376 | 21886903 | 25099861 |  |  | 45233 | 8/30/2024 | 21886903 | 20710527 | 21886903 | 20710527 |  |  |  | 21886903 | 20710527 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/188/679780-DR4339PR-Detailed%20SOW%20Bayam%c3%b3n%20Phase%201%20High%20Priority%20Rev1%20-%20DSOW%20-%20signed%20(1).pdf |  | 46070.5186 | 45152.4652 | Jahdiel Franqui | Distribution Streetlighting | Marlina Crespo |  |  | 3212958 |  | 1 | 1 |  | 679780RFI188 | 679780 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 1176376
679458 | 11114 | FAASt [Distribution Pole and Conductor Repair - Ponce Group 4] (Distribution) | 14F008580000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44776 | 8/3/2022 | 45138 | 44819 | 44882 |  |  |  |  | 3000000 | 593918 | 95482 | 95421 |  | 498436 | 20002 | 75480 | 593918 | 689339 |  |  | 44936 |  | 593918 | 498436 | [5 empty] | 593918 | 498436 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/189/679458-DR4339PR-Detailed%20SOW%20Ponce%20Group%204%20Rev1%20New%20Template.pdf?web=1 |  | 45856.769 | 45152.4652 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 95421 | 11322 | 1 | 1 |  | 679458RFI189 | 679458 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 84160
679457 | 11105 | FAASt [Distribution Pole and Conductor Repair - Ponce Group 3] (Distribution) | 14F008520000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44776 | 8/3/2022 | 44804 | 44812 | 44883 |  |  |  |  | 3000000 | 746488 | 157153 | 115386 |  | 589335 | 33921 | 123232 | 746488 | 861874 |  |  | 44922 |  | 746488 | 589335 | [5 empty] | 746488 | 589335 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/190/679457-DR4339PR-Detailed%20SOW%20Ponce%20Group%203%20Rev3.pdf |  | 45856.769 | 45152.4652 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 115386 |  | 1 | 1 |  | 679457RFI190 | 679457 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 157153
679153 | 11106 | FAASt Distribution Pole and Conductor Repair - Mayagüez Group 6 (Distribution) | 14F008570000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44770 | 7/28/2022 | 44834 | 44820 | 44882 |  |  |  |  | 3000000 | 215184.01 | 51337.5 | 31068 |  | 163847 | 10754.5 | 40583 | 215184.5 | 246252.5 |  |  | 44922 |  | 215184.01 | 163846.51 | [5 empty] | 215184.01 | 163846.51 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/191/679153-DR4339PR-Detailed%20SOW%20Mayaguez%20Group%206%20Rev1.pdf?web=1 |  | 45856.769 | 45152.4652 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 31068.05 |  | 1 | 1 |  | 679153RFI191 | 679153 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 51337.5
679149 | 11089 | FAASt Distribution Pole and Conductor Repair - Mayagüez Group 5 (Distribution) | 14F008510000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44770 | 7/28/2022 | 44804 | 44812 | 44880 |  |  |  |  | 3000000 | 157187 | 27443 | 25191 |  | 129744 | 5749 | 21694 | 157187 | 182378 |  |  | 44922 |  | 157187 | 129744 | [5 empty] | 157187 | 129744 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/192/679149-DR4339PR-Detailed%20SOW%20Mayaguez%20Group%205%20Rev2%20New%20Template.pdf?web=1 |  | 45856.7691 | 45152.4652 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 25191 |  | 1 | 1 |  | 679149RFI192 | 679149 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 27443
679134 | 11109 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 10] (Distribution) | 14F008560000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44770 | 7/28/2022 | 44834 | 44819 | 44881 |  |  |  |  | 3000000 | 563557.15 | 110600.22 | 86724 |  | 452957 | 23169.22 | 87431 | 563557.22 | 650281.22 |  |  | 44936 |  | 563557.15 | 452956.93 | [5 empty] | 563557.15 | 452956.93 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/193/679134-DR4339PR-Detailed%20SOW%20Caguas%20Group%2010%20Rev1.pdf?web=1 |  | 45856.7691 | 45152.4652 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 86724.25 | 13114.65 | 1 | 1 |  | 679134RFI193 | 679134 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 97485.57
679133 | 11090 | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 4] (Distribution) | 14F008540000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE |  | Current | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 44771 | 7/28/2022 | 44834 | 44818 | 44882 | 45790 | 45786 |  |  | 3000000 | 21362 | 633 | 4078 |  | 20729 | 133 | 500 | 21362 | 25440 |  |  | 44922 | 9/12/2025 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/194/679133-DR4339PR-Detailed%20SOW%20Arecibo%20Group%204%20Rev1.pdf?web=1 | 15SEPTEMBER2025 - Version 2 was created to withdraw funds of Project 679133. In version 01, the funds for work to be completed were de-obligated. The replacement of the pole is no longer feasible because is a private pole and does not belong to PREPA/LUMA. Please refer to document "679133 4339-DR Withdrawal form - Arecibo Group 4 - Phase 1 signed.pdf”. | 46070.5183 | 45152.4652 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Marlina Crespo |  |  | 0 | 0 | 1 | 1 | 45919 | 679133RFI194 | 679133 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
679127 | 11096 | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 3] (Distribution) | 14F008480000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44771 | 7/28/2022 | 44804 | 44804 | 44880 |  |  |  |  | 3000000 | 217162.81 | 46010.58 | 33340 |  | 46010.58 | 9638.58 | 36372 | 92021.16 | 125361.16 |  |  | 44922 |  | 217162.81 | 171152.23 | [5 empty] | 217162.81 | 171152.23 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/195/679127-DR4339PR-Detailed%20SOW%20Arecibo%20Group%203%20Rev2%20New%20Template.pdf?web=1 |  | 45856.7691 | 45152.4652 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 33340.3 |  | 2.3599 | 1 |  | 679127RFI195 | 679127 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 46010.58
679039 | 11351 | FAASt [Caguas Streetlighting] (Distribution) | 14F009270000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE | [15 empty] | 44769 | 7/27/2022 | 45016 | 45016 | [5 empty] | 37416915 | 75586568.64 | 1849344.06 | 8534897 |  | 73737225 | 426651.06 | 1422693 | 75586569.06 | 84121466.06 |  |  | 45112 |  | 75586568.64 | 73737224.58 | [5 empty] | 75586568.64 | 73737224.58 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/196/679039-DR4339PR-Detailed%20SOW%20Caguas%20Phase%201%20High%20Priority%20Rev0%20-%20signed%20-%20DSOW.pdf?web=1 |  | 45856.7691 | 45152.4652 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 8534896.89 |  | 1 | 1 |  | 679039RFI196 | 679039 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 1849344.06
679035 | 11861 | FAASt [Telecom Infrastructure – Group A] (Telecommunication) | 14F004570000, 14F004550000, 14F004560000 | PBIT01 - Telecom Sys & Network | Telecommunications | IT OT Telecom Systems and Network | TRUE |  | TRUE | 45869 |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 44769 | 7/27/2022 | [7 empty] | 5900000 | 5900000 | [5 empty] | 0 | 5900000 | 5900000 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/197/PR679035%20-%20DR4339PR%20-%20Telecom%20Infraestructure%20-%20Group%20A%20SOW.pdf?web=1 | 6/12/2025 - Project withdrawn in Grants Portal | 46059.5595 | 45152.4652 | Jahdiel Franqui | Telecom Infrastructure | Jason Fournier |  |  |  |  | 1 | 1 | 45820 | 679035RFI197 | 679035 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
679033 | 11098 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 9] (Distribution) | 14F008500000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44769 | 7/27/2022 | 44804 | 44812 | 44880 |  |  |  |  | 3000000 | 908942 | 179902 | 140628 |  | 729040 | 37687 | 142215 | 908942 | 1049570 |  |  | 44922 |  | 908942 | 729040 | [5 empty] | 908942 | 729040 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/198/679033-DR4339PR-Detailed%20SOW%20Caguas%20Group%209%20Rev2%20New%20Template.pdf?web=1 |  | 45856.7691 | 45152.4652 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 140628 |  | 1 | 1 |  | 679033RFI198 | 679033 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 179902
679026 | 11107 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 5] (Distribution) | 14F008590000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44769 | 7/27/2022 | 44834 | 44819 | 44882 |  |  |  |  | 3000000 | 590296 | 106510 | 93451 |  | 483786 | 22312 | 84198 | 590296 | 683747 |  |  | 44922 |  | 590296 | 483786 | [5 empty] | 590296 | 483786 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/199/679026-DR4339PR-Detailed%20SOW%20San%20Juan%20Group%205%20Rev1.pdf?web=1 |  | 45856.7691 | 45152.4652 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 93451 | 12630 | 1 | 1 |  | 679026RFI199 | 679026 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 93880
679025 | 11101 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 4] (Distribution) | 14F008530000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44769 | 7/27/2022 | 44804 | 44812 | 44880 |  |  |  |  | 3000000 | 298631 | 55558 | 46884 |  | 243073 | 11639 | 43919 | 298631 | 345515 |  |  | 44922 |  | 298631 | 243073 | [5 empty] | 298631 | 243073 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/200/679025-DR4339PR-Detailed%20SOW%20San%20Juan%20Group%204%20Rev2%20New%20Template.pdf?web=1 |  | 45856.7691 | 45152.4652 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 46884 | 6588 | 1 | 1 |  | 679025RFI200 | 679025 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 48970
679006 | 11862 | FAASt [Test and Technology Laboratory] (Building) | 14F019640000 | PBFM01 - Facilities Dev & Implem | Building | IT OT Telecom Systems and Network |  | Improved | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 11880000 | 44701 | 44753 |  | 44731 |  |  |  | 44769 | 7/26/2022 | 44895 | 44867 | 45432 |  |  |  |  | 11880000 | 25192128 | 8186857 | 386408 |  | 12739422 | 500959 | 7685898 | 20926279 | 21312687 | 45626 | 45808 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/201/10163-FA-SOW-0003-Rev%201%202023.05%2030.pdf |  | 45881.4653 | 45152.4652 | Jahdiel Franqui | Test and Technology Laboratory | Maria Mujica Gonzalez |  |  |  |  | 1.2039 | 1 | 45880 | 679006RFI201 | 679006 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
678988 | 11113 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 5] (Distribution) | 14F008550000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44768 | 7/26/2022 | 44834 | 44819 | 44882 |  |  |  |  | 3000000 | 1117787.16 | 206650.4 | 175441 |  | 911137 | 0 | 206650.4 | 1117787.4 | 1293228.4 |  |  | 44922 | 8/30/2024 | 1117787.16 | 911136.76 | 1117787.16 | 911136.76 |  |  |  | 1117787.16 | 911136.76 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/202/678988-DR4339PR-Detailed%20SOW%20Bayamon%20Group%205%20Rev1.pdf?web=1 |  | 46070.5167 | 45152.4652 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Marlina Crespo |  |  | 175440.55 |  | 1 | 1 |  | 678988RFI202 | 678988 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 206650.4
678985 | 11103 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 4] (Distribution) | 14F008490000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44768 | 7/26/2022 | 44804 | 44802 | 44880 |  |  |  |  | 3000000 | 407945.84 | 54317.84 | 66915 |  | 353628 | 11378.84 | 42939 | 407945.84 | 474860.84 |  |  | 44922 |  | 407945.84 | 353628 | [5 empty] | 407945.84 | 353628 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/203/678985-DR4339PR-Distribution%20Pole%20and%20Conductor%20Repair%20-%20Bayamon%20Group%204.pdf?web=1 |  | 45856.7691 | 45152.4652 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 66915 |  | 1 | 1 |  | 678985RFI203 | 678985 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 54317.84
678800 | 11425 | FAASt [Telecom Infrastructure – Group B] (Telecommunication) | 14F004590000, 14F004580000, 14F004620000, 14F004610000, 14F004600000 | PBIT01 - Telecom Sys & Network | Telecommunications | IT OT Telecom Systems and Network | TRUE | Restoration | FALSE |  | Current | [13 empty] | 44764 | 7/22/2022 |  | 45426 | 45855 | 45952 | 45929 | 9/29/2025 - Field EHP – Historic: Initial review. Expected Completion Date (ECD) 10/22/2025. |  | 10500000 |  | 55895.84 | 2828793.1 |  | 13148929.44 | 10487.44 | 45408.4 | 13204825.28 | 16033618.38 |  |  | 45966 |  | 13204825.28 | 13148929.44 |  |  |  | 0 |  | 13204825.28 | 13148929.44 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/204/1237892-DR4339PR-SOW%20(2).pdf?web=1 | 4/04/2024: QC Review Complete 8/5/2025 - Field EHP – Environmental: Initial review. Expected Completion Date (ECD) 08/27/2025 | 46059.5417 | 45152.4652 | Jahdiel Franqui | Telecom Infrastructure | Jason Fournier | 7-12 months |  | 2828793.1 | 10487.44 | 0 | 5 |  | 678800RFI204 | 678800 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 45408.4
678795 | 11535 | FAASt [Arecibo Streetlighting] (Distribution) | 14F012790000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 44764 | 7/22/2022 | 45107 | 45107 | 45279 |  |  |  |  | 32568618 | 14607500.56 | 1527389 | 2673960 |  | 14601018 | 222962 | 1304427 | 16128407 | 18802367 | 45626 | 45777 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/205/678795-DR4339PR-Detailed%20SOW%20Arecibo%20Phase%201%20High%20Priority%20Rev1%20-%20DSOW%20-%20signed.pdf |  | 46059.6165 | 45152.4652 | Jahdiel Franqui | Distribution Streetlighting | Jason Fournier |  |  |  |  | 0.9057 | 1 | 45874 | 678795RFI205 | 678795 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
678794 | 11527 | FAASt [Ponce Streetlighting] (Distribution) | 14F012850000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 44764 | 7/22/2022 | 45107 | 45107 | 45279 |  |  |  |  | 44090477 | 16043135.52 | 1444528 | 2808935 |  | 16043136 | 215232 | 1229296 | 17487664 | 20296599 | 45657 | 45808 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/206/678794-DR4339PR-Detailed%20SOW%20Ponce%20Phase%201%20High%20Priority%20Rev1%20-%20DSOW%20-%20signed.pdf |  | 46059.6162 | 45152.4652 | Jahdiel Franqui | Distribution Streetlighting | Jason Fournier |  |  |  |  | 0.9174 | 1 | 45874 | 678794RFI206 | 678794 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
678793 | 11532 | FAASt [Mayagüez Streetlighting] (Distribution) | 14F012840000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE | [15 empty] | 44764 | 7/22/2022 | 45107 | 45108 | 45134 |  |  |  |  | 24355947 | 12371384.46 | 1352204.36 | 2291581 |  | 11019180 | 0 | 1352204.36 | 12371384.36 | 14662965.36 |  |  | 45233 | 8/30/2024 | 12371384.46 | 11019180.1 | 12371384.46 | 11019180.1 |  |  |  | 12371384.46 | 11019180.1 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/207/678793-DR4339PR-Detailed%20SOW%20Mayaguez%20Phase%201%20High%20Priority%20Rev1%20-%20DSOW%20-%20signed.pdf |  | 46070.5178 | 45152.4652 | Jahdiel Franqui | Distribution Streetlighting | Marlina Crespo |  |  | 2291581 |  | 1 | 1 |  | 678793RFI207 | 678793 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 1352204.36
678789 | 11533 | FAASt [Carolina Streetlighting] (Distribution) | 14F012810000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE | [15 empty] | 44764 | 7/22/2022 | 45107 | 45108 | 45134 |  |  |  |  | 37245221 | 16024559.58 | 1158946.56 | 2559493 |  | 14865613 | 0 | 1158946.56 | 16024559.56 | 18584052.56 |  |  | 45233 | 8/30/2024 | 16024559.58 | 14865613.02 | 16024559.58 | 14865613.02 |  |  |  | 16024559.58 | 14865613.02 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/208/678789-DR4339PR-Detailed%20SOW%20Carolina%20Phase%201%20High%20Priority%20Rev1%20-%20DSOW%20-%20signed%20(1).pdf |  | 46070.5149 | 45152.4652 | Jahdiel Franqui | Distribution Streetlighting | Marlina Crespo |  |  | 2559492.85 |  | 1 | 1 |  | 678789RFI208 | 678789 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 1158946.56
675406 | 107767 | FAASt [Two-Way Land Mobile Radio Network] (Telecommunication) | 14F003900000 | PBIT01 - Telecom Sys & Network | Telecommunications | IT OT Telecom Systems and Network | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 46200000 | 44438 | 44461 |  | 44468 |  |  |  | 44727 | 6/15/2022 | [7 empty] | 46200000 | 46200000 | [5 empty] | 0 | 46200000 | 46200000 | [11 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/209/675406-DR4339PR-Two-Way%20Land%20Mobile%20Radio%20Network.pdf?web=1 | 6/12/2025 - Project withdrawn in Grants Portal | 45877.5777 | 45152.4652 | Jahdiel Franqui | Two Way Land Mobile Radio Network | Ashleah Dingle |  |  |  |  | 1 | 1 | 45820 | 675406RFI209 | 675406 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
675345 | 107766 | FAASt [IT OT Technology Systems Reparations] Group 1 (Telecommunication) |  | PBIT01 - Telecom Sys & Network | Telecommunications | IT OT Telecom Systems and Network |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 35700000 | 44783 | 44798 |  | 44813 |  |  |  | 44726 | 6/14/2022 | 45046 | 45026 | 45336 |  |  |  |  | 35700000 | 21640536 | 0 | 798980.71 |  | 8378200.51 | 0 | 0 | 8378200.51 | 9177181.22 | 45688 | 45838 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/210/675345-%20IT-OT%20System%20Reparation%20Detailed%20%20Scope%20of%20Work%20-%20signed.pdf?web=1 |  | 45881.4774 | 45152.4652 | Jahdiel Franqui | IT OT Technology Systems Reparations | Maria Mujica Gonzalez |  |  |  |  | 2.583 | 1 | 45880 | 675345RFI210 | 675345 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
674506 | 107765 | FAASt [Field Area Network (FAN)] (Telecommunication) | 14F002090000 | PBIT01 - Telecom Sys & Network | Telecommunications | IT OT Telecom Systems and Network | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active |  |  | 330000000 |  |  | 45695 |  |  |  |  | 44715 | 6/3/2022 | [7 empty] | 330000000 | 330000000 | [5 empty] | 0 | 330000000 | 330000000 | [11 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/211/921840-DR4339PR-SOW%20(1).pdf?web=1 | 4/4/2024 - Received withdrawal status data/info from Director Timothy Auch.This project is being developed and internal strategy needed for submission will be completed to support re-submission date5/29/2024 - Update received for Resubmittal Target Date from Grid Strategy Performance Team, original date was 8/26/2024. | 45877.5777 | 45152.4652 | Jahdiel Franqui | Field Area Network(FAN) | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 674506RFI211 | 674506 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
674098 | 10824 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 7] (Distribution) | 14F004040000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44714 | 5/27/2022 | 44742 | 44739 | [5 empty] | 2500000 | 107755 | 23322 | 16516 |  | 84433 | 0 | 23322 | 107755 | 124271 |  |  | 44781 |  | 107755 | 84433 | [5 empty] | 107755 | 84433 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/212/674098-DR4339PR-Detailed%20SOW%20Caguas%20Group%207%20Rev0.pdf?web=1 |  | 45856.7691 | 45152.4652 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 16517 |  | 1 | 1 |  | 674098RFI212 | 674098 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 23322
674096 | 10935 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 6] (Distribution) | 14F004030000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44714 | 5/27/2022 | 44773 | 44757 | 44796 |  |  |  |  | 3000000 | 2092280 | 318852 | 332705 |  | 1773428 | 66795 | 252057 | 2092280 | 2424985 |  |  | 44851 |  | 2092280 | 1773428 | [5 empty] | 2092280 | 1773428 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/213/674096-DR4339PR-Detailed%20SOW%20Caguas%20Group%206%20Rev1.pdf?web=1 |  | 45856.7691 | 45152.4652 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 332705 |  | 1 | 1 |  | 674096RFI213 | 674096 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 318852
674092 | 10893 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 5] (Distribution) | 14F004020000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44714 | 5/27/2022 | 44742 | 44736 | 44781 |  |  |  |  | 3000000 | 531730 | 90422 | 82578 |  | 441308 | 18942 | 71480 | 531730 | 614308 |  |  | 44820 |  | 531730 | 441308 | [5 empty] | 531730 | 441308 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/214/674092-DR4339PR-Detailed%20SOW%20Caguas%20Group%205%20Rev1.pdf?web=1 |  | 45856.7691 | 45152.4652 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 82578 |  | 1 | 1 |  | 674092RFI214 | 674092 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 90422
674088 | 10933 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 3] (Distribution) | 14F004000000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44714 | 5/27/2022 | 44773 | 44756 | [5 empty] | 3500000 | 1702021 | 289653 | 267370 |  | 1412368 | 60678 | 228975 | 1702021 | 1969391 |  |  | 44851 |  | 1702021 | 1412368 | [5 empty] | 1702021 | 1412368 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/215/674088-DR4339PR-Detailed%20SOW%20Caguas%20Group%203%20Rev0.pdf?web=1 |  | 45856.7691 | 45152.4652 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 267370 |  | 1 | 1 |  | 674088RFI215 | 674088 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 289653
674083 | 10827 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 2] (Distribution) | 14F003990000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44714 | 5/27/2022 | 44773 | 44743 | [5 empty] | 3000000 | 2110462 | 362533 | 335721.9 |  | 1747928.9 | 75946 | 286587 | 2110461.9 | 2446183.8 |  |  | 44781 |  | 2110462 | 1747929 | [5 empty] | 2110462 | 1747929 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/216/674083-DR4339PR-Detailed%20SOW%20Caguas%20Group%202%20Rev0.pdf?web=1 |  | 45856.7691 | 45152.4652 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 335722 |  | 1 | 1 |  | 674083RFI216 | 674083 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 362533
674072 | 10906 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 1] (Distribution) | 14F003980000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44714 | 5/27/2022 | 44773 | 44748 | [5 empty] | 3000000 | 1111094 | 238203 | 171585 |  | 872891 | 49900.3 | 188302.7 | 1111094 | 1282679 |  |  | 44820 |  | 1111094 | 872891 | [5 empty] | 1111094 | 872891 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/217/674072-DR4339PR-Detailed%20SOW%20Caguas%20Group%201%20Rev0.pdf?web=1 |  | 45856.7691 | 45152.4652 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 171585 |  | 1 | 1 |  | 674072RFI217 | 674072 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 238203
673920 | 107764 | FAASt [Isla Grande 1101] (Substation) | 14F001860000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active |  |  | 600000 | [7 empty] | 44733 | 5/25/2022 | [7 empty] | 600000 | 600000 | [5 empty] | 0 | 600000 | 600000 | [11 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/218/673920-DR4339PR-ISOW-Isla%20Grande%201101-Substation.pdf?web=1 | 4/2/2024 - Received withdrawal status data/info from Manager Yadira L. Lugo Cordero. Working with Planning and Engineering to complete assessments to define scope and start the Preliminary Engineering. | 45877.5777 | 45152.4652 | Jahdiel Franqui | Isla Grande 1101 | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 673920RFI218 | 673920 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
673848 | 10751 | FAASt [Distribution Pole and Conductor Repair-Carolina Group 3] (Distribution) | 14F004080000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44706 | 5/25/2022 | 44742 | 44714 | 44736 |  |  |  |  | 2500000 | 49345 | 5620 | 13281 |  | 43725 | 1177 | 4443 | 49345 | 62626 |  |  | 44754 |  | 49345 | 43725 | [5 empty] | 49345 | 43725 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/219/673848-DR4339PR-Detalied%20SOW%20Carolina%20Group%203%20Rev1.pdf?web=1 |  | 45856.7691 | 45152.4652 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 13281 |  | 1 | 1 |  | 673848RFI219 | 673848 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 5620
673847 | 10812 | FAASt [Distribution Pole and Conductor Repair-Carolina Group 2] (Distribution) | 14F004070000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44706 | 5/25/2022 | 44742 | 44734 | 44761 |  |  |  |  | 2500000 | 240513 | 49943 | 37242 |  | 190570 | 10462 | 39481 | 240513 | 277755 |  |  | 44781 |  | 240513 | 190570 | [5 empty] | 240513 | 190570 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/220/673847-DR4339PR-Detalied%20SOW%20Carolina%20Group%202%20Rev2.pdf?web=1 |  | 45856.7691 | 45152.4652 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 37242 |  | 1 | 1 |  | 673847RFI220 | 673847 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 49943
673844 | 10864 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 3] (Distribution) | 14F004170000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44706 | 5/25/2022 | 44773 | 44749 | [5 empty] | 2500000 | 1392064.88 | 319213.9 | 208800.6 |  | 1072851 | 0 | 319213.9 | 1392064.9 | 1600865.5 |  |  | 44797 | 8/30/2024 | 1392064.88 | 1072850.98 | 1392064.88 | 1072850.98 |  |  |  | 1392064.88 | 1072850.98 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/221/673844-DR4339PR-Detailed%20SOW%20San%20Juan%20Group%203%20Rev0.pdf?web=1 |  | 46070.5146 | 45152.4652 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Marlina Crespo |  |  | 208800.58 |  | 1 | 1 |  | 673844RFI221 | 673844 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 319213.9
673843 | 10922 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 3] (Distribution) | 14F003970000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44706 | 5/25/2022 | 44773 | 44753 | [5 empty] | 3000000 | 1131855 | 227661 | 175796 |  | 904194 | 47692 | 179969 | 1131855 | 1307651 |  |  | 44851 |  | 1131855 | 904194 | [5 empty] | 1131855 | 904194 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/222/673843-DR4339PR-Detailed%20SOW%20Bayamon%20Group%203%20Rev0.pdf?web=1 |  | 45856.7691 | 45152.4652 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 175796 |  | 1 | 1 |  | 673843RFI222 | 673843 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 227661
673839 | 10742 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 2] (Distribution) | 14F003960000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44706 | 5/25/2022 | 44712 | 44713 | 44733 |  |  |  |  | 2500000 | 26298 | 5830 | 10153 |  | 20468 | 1221 | 4609 | 26298 | 36451 |  |  | 44754 |  | 26298 | 20468 | [5 empty] | 26298 | 20468 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/223/673839-DR4339PR-Detailed%20SOW%20Bayamon%20Group%202%20Rev1.pdf?web=1 |  | 45856.7691 | 45152.4652 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 10152 |  | 1 | 1 |  | 673839RFI223 | 673839 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 5830
673838 | 10764 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 2] (Distribution) | 14F004160000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44706 | 5/25/2022 | 44742 | 44714 | 44736 |  |  |  |  | 2500000 | 357614 | 73265 | 55024 |  | 284348 | 15348 | 57917 | 357613 | 412637 |  |  | 44754 |  | 357614 | 284349 | [5 empty] | 357614 | 284349 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/224/673838-DR4339PR-Detailed%20SOW%20San%20Juan%20Group%202%20Rev1.pdf?web=1 |  | 45856.7691 | 45152.4652 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 55025 |  | 1 | 1 |  | 673838RFI224 | 673838 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 73265
673836 | 11041 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 1] (Distribution) | 14F003950000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44706 | 5/25/2022 | 44773 | 44743 | 44844 |  |  |  |  | 3500000 | 5751036.48 | 1064121.8 | 900015 |  | 4686915 | 0 | 1064121.8 | 5751036.8 | 6651051.8 |  |  | 44916 | 8/30/2024 | 5751036.48 | 4686914.68 | 5751036.48 | 4686914.68 |  |  |  | 5751036.48 | 4686914.68 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/225/673836-DR4339PR-Detailed%20SOW%20Bayamon%20Group%201%20Rev3.pdf?web=1 |  | 46070.5142 | 45152.4652 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Marlina Crespo |  |  | 900014.8 |  | 1 | 1 |  | 673836RFI225 | 673836 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 1064121.8
673818 | 10821 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 1] (Distribution) | 14F004150000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44706 | 5/25/2022 | 44742 | 44742 | [5 empty] | 3500000 | 793418 | 171614 | 121044 |  | 621804 | 0 | 171614 | 793418 | 914462 |  |  | 44781 |  | 793418 | 621804 | [5 empty] | 793418 | 621804 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/226/673818-DR4339PR-Detailed%20SOW%20San%20Juan%20Group%201%20Rev0.pdf?web=1 |  | 45856.7691 | 45152.4652 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 121044 |  | 1 | 1 |  | 673818RFI226 | 673818 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 171614
673795 | 10777 | FAASt Distribution Pole and Conductor Repair - Mayaguez Group 4 (Distribution) | 14F004120000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44707 | 5/24/2022 | 44742 | 44725 | 44741 |  |  |  |  | 3500000 | 1794117 | 368954 | 278117 |  | 1425163 | 77291 | 291663 | 1794117 | 2072234 |  |  | 44775 |  | 1794117 | 1425163 | [5 empty] | 1794117 | 1425163 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/227/673795-DR4339PR-Detailed%20SOW%20Mayaguez%20Group%204%20Rev1.pdf?web=1 |  | 45856.7691 | 45152.4652 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 278116 |  | 1 | 1 |  | 673795RFI227 | 673795 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 368954
673775 | 10962 | FAASt [Distribution Pole and Conductor Repair - Mayaguez Group 3] (Distribution) | 14F004110000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44705 | 5/24/2022 | 44773 | 44768 | 44866 |  |  |  |  | 4000000 | 4432647.91 | 859175 | 689888 |  | 3575455 | 79570.1 | 779604.9 | 4434630 | 5124518 |  |  | 44922 |  | 4432647.91 | 3575454.81 | [5 empty] | 4432647.91 | 3575454.81 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/228/673775-DR4339PR-Detailed%20SOW%20Mayaguez%20Group%203%20Rev3.pdf?web=1 |  | 45856.7691 | 45152.4652 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 689888.45 |  | 0.99955 | 1 |  | 673775RFI228 | 673775 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 857193.1
673774 | 10773 | FAASt [Distribution Pole and Conductor Repair - Mayaguez Group 1] (Distribution) | 14F004090000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44705 | 5/24/2022 | 44742 | 44725 | 44742 |  |  |  |  | 4000000 | 1766951 | 358420 | 273831 |  | 1408531 | 75084 | 283336 | 1766951 | 2040782 |  |  | 44775 |  | 1766951 | 1408531 | [5 empty] | 1766951 | 1408531 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/229/673774-DR4339PR-Detailed%20SOW%20Mayaguez%20Group%201%20Rev1.pdf?web=1 |  | 45856.7691 | 45152.4652 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 273831 |  | 1 | 1 |  | 673774RFI229 | 673774 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 358420
673772 | 10919 | FAASt [Distribution Pole and Conductor Repair - Mayagüez Group 2] (Distribution) | 14F004100000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44705 | 5/24/2022 | 44773 | 44761 | 44813 |  |  |  |  | 4500000 | 4122520 | 835984 | 636837 |  | 3286536 | 175127 | 660857 | 4122520 | 4759357 |  |  | 44858 |  | 4122520 | 3286536 | [5 empty] | 4122520 | 3286536 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/230/673772-DR4339PR-Detailed%20SOW%20Mayaguez%20Group%202%20Rev1.pdf?web=1 |  | 45856.7691 | 45152.4652 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 636837 |  | 1 | 1 |  | 673772RFI230 | 673772 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 835984
673771 | 10909 | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 1] (Distribution) | 14F003930000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [7 empty] | 600000000 | [7 empty] | 44705 | 5/24/2022 | 44773 | 44753 | [5 empty] | 3000000 | 2366560.53 | 472527 | 370850 |  | 1894034 | 98988 | 373539 | 2366561 | 2737411 |  |  | 44851 |  | 2366560.53 | 1894033.53 | [5 empty] | 2366560.53 | 1894033.53 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/231/673771-DR4339PR-Detailed%20SOW%20Arecibo%20Group%201%20Rev0.pdf?web=1 |  | 45856.7691 | 45152.4652 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 370850.25 |  | 1 | 1 |  | 673771RFI231 | 673771 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 472527
673691 | 10710 | FAASt [Equipment and Materials] | 14F008760000 | PBOP06 - Materials Management | Other | TBD |  | NA | [16 empty] | 44707 | 5/23/2022 | [8 empty] | 3075694700.2 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 44722 | 12/29/2023 | 1506189735.2 |  | 797183125.2 | 797183125.2 | 1733204375 |  | 1733204375 | 1733204375 | 1733204375 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/232/PRJ_Report_673691_20241106.pdf?web=1 |  | 45856.7691 | 45152.4652 | Jahdiel Franqui |  | Rey Roldan Rodríguez |  |  | 0 |  |  |  |  | 673691RFI232 | 673691 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
673504 | 11317 | FAASt [Gurabo Streetlighting] (Distribution) | 14F004630000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE | [15 empty] | 44700 | 5/19/2022 | 44985 | 44985 | [5 empty] | 12840220 | 20742294 | 1533300 | 3043675 |  | 19208994 | 400644 | 1132656 | 20742294 | 23785969 |  |  | 45063 |  | 20742294 | 19208994 | [5 empty] | 20742294 | 19208994 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/233/673504-FEMA%20Detailed%20SOW-Streetlight-%20Gurabo.pdf?web=1 |  | 45856.7691 | 45152.4652 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 3043676 |  | 1 | 1 |  | 673504RFI233 | 673504 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 1533300
673292 | 11452 | FAASt Telecom Infrastructure - Cerro Puntas (Telecommunication) | 14F004510000 | PBIT01 - Telecom Sys & Network | Telecommunications | IT OT Telecom Systems and Network | TRUE | Restoration | FALSE |  | Current | [5 empty] | 96500000 | 44438 | 44461 |  | 44468 |  |  |  | 44698 | 5/17/2022 | 45382 | 45327 | 45750 | 45915 | 45884 | Field EHP: ESA Consultation letter submitted to USFWS on 5/28/2025. Waiting for response. ECD Updated to 9/15/2025 |  | 4800000 | 6767654.15 | 49577.82 | 1075319.59 |  | 8129023.86 | 49577.82 | 0 | 8178601.68 | 9253921.27 | 45838 | 45991 | 45960 |  | 8173684.61 | 8124106.79 |  |  |  | 4917.07 |  | 8173684.61 | 8124106.79 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/234/1230468%20D4339PR-ISOW-Telecom%20Infrastructure-Cerro%20Puntas%20(2).pdf?web=1 | 8/15/2025 - Field EHP: ESA Consultation letter submitted to USFWS on 5/28/2025. Waiting for response. ECD Updated to 9/15/2025 | 46059.5417 | 45152.4652 | Jahdiel Franqui | Telecom Infrastructure | Jason Fournier |  |  | 1075319.59 | 4963.76 | 0.82748 | 1 |  | 673292RFI234 | 673292 | 4917.07 | 427.57 | 5344.64 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 44186.49
671502 | 11522 | FAASt [Yabucoa Streetlighting] (Distribution) | 14F004530000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE | [15 empty] | 44677 | 4/26/2022 | 45107 | 45108 | 45134 |  |  |  |  | 11205044 | 16883989.33 | 1986076 | 2741367 |  | 14918273 | 0 | 1986076 | 16904349 | 19645716 |  |  | 45289 | 8/30/2024 | 16883989.33 | 14918381.07 | 16883989.33 | 14918381.07 |  |  |  | 16883989.33 | 14918381.07 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/235/671502-DR4339PR-Detailed%20SOW%20Yabucoa%20Rev1%20-%20DSOW%20-%20signed.pdf?web=1 |  | 46070.5136 | 45152.4652 | Jahdiel Franqui | Distribution Streetlighting | Marlina Crespo |  |  | 2742910.41 |  | 0.9988 | 1 |  | 671502RFI235 | 671502 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 1965608.26
671400 | 11529 | FAASt [Barceloneta Streetlighting] (Distribution) | 14F004540000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 44676 | 4/25/2022 | 45107 | 45108 | 45279 |  |  |  |  | 6352659 | 8163052.71 | 1109633 | 1890247 |  | 8163053 | 198246 | 911387 | 9272686 | 11162933 | 45626 | 45777 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/236/671400-DR4339PR-Detailed%20SOW%20Barceloneta%20Rev1%20-%20DSOW%20-%20signed.pdf?web=1 |  | 46059.6162 | 45152.4652 | Jahdiel Franqui | Distribution Streetlighting | Jason Fournier |  |  |  |  | 0.88033 | 1 | 45874 | 671400RFI236 | 671400 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
671396 | 11530 | FAASt [Utuado Streetlighting] (Distribution) | 14F004520000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 44676 | 4/25/2022 | 45107 | 45108 | 45307 |  |  |  |  | 10162619 | 17961216.53 | 2911033 | 3174654 |  | 17961217 | 437244 | 2473789 | 20872250 | 24046904 | 45626 | 45777 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/237/671396-DR4339PR-Detailed%20SOW%20Utuado%20Rev1%20-%20DSOW%20-%20signed.pdf?web=1 |  | 46059.6158 | 45152.4652 | Jahdiel Franqui | Distribution Streetlighting | Jason Fournier |  |  |  |  | 0.86053 | 1 | 45873 | 671396RFI237 | 671396 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
668669 | 107754 | FAASt [Line 50500 230kV Mayaguez TC - Mora TC - Cambalache Power Plant] (Transmission) | 14F003670000 | PBUT13 - T Priority Pole Repl | Transmission | Transmission Priority Pole Replacements |  | Restoration |  |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | FALSE |  | 31300000 | [7 empty] | 44650 | 3/30/2022 | 44681 | 44655 | [5 empty] | 110470000 | 307465 | 0 |  |  | 307465 | 0 | 0 | 307465 | 307465 | 45900 | 46053 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/238/668669-DR4339PR-Detailed%20SOW%20-Transmission%20Priority%20Pole%20Replacement-%20Mora%2050500%20Rev0.pdf?web=1 | 9/12/2024 - GP Notes "6/25/2024 The project was withdrawn with the comment "Project is being withdrawn since it was not included in the Applicant’s latest workplan for submittal of a SOW. FEMA may in the future re-create the project at the request of the Applicant and COR3 if a SOW submittal date is provided." | 46077.5799 | 45152.4652 | Jahdiel Franqui | 230 kV Transmission Priority Poles and Structures Replacements | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 668669RFI238 | 668669 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
668665 | 107753 | FAASt [Cybersecurity Program Implementation] (Telecommunication) | 14F002070000 | PBIT02 - Cybersecurity Program | Telecommunications | IT OT Cybersecurity Program |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 24500000 | 44585 | 44635 |  | 44615 |  |  |  | 44650 | 3/30/2022 | 45230 | 45230 | 45862 |  |  |  |  | 24500000 | 24500000 | 0 | 2150367.26 |  | 22436888.87 | 0 | 0 | 22436888.87 | 24587256.13 | 45535 | 45657 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/239/668665-DR4339PR-Cybersecurity%20Program%20Implementation%20(Telecommunication).pdf?web=1 |  | 45981.5354 | 45152.4652 | Jahdiel Franqui | Cybersecurity Implementation Program | Marlina Crespo | 0 Months |  |  |  | 1.092 | 1 | 45880 | 668665RFI239 | 668665 | 0 | 0 | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
668592 | 10891 | FAASt [Transmission Priority Pole Replacement – Line 9800] (Transmission) | 14F004460000 | PBUT13 - T Priority Pole Repl | Transmission – Pole Replacement | Transmission Priority Pole Replacements |  | Restoration | FALSE | [15 empty] | 44649 | 3/29/2022 | 44742 | 44749 | [5 empty] | 2200000 | 420866 | 0 | 43984 |  | 420867 | 0 | 0 | 420867 | 464851 |  |  | 44820 |  | 420866 | 420866 | [5 empty] | 420866 | 420866 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/240/668592-DR4339PR-Detailed%20SOW%20-%20Line%209800%20Rev.0.pdf?web=1 |  | 45856.7691 | 45152.4652 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Rey Roldan Rodríguez |  |  | 43984 |  | 1 | 1 |  | 668592RFI240 | 668592 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
668583 | 10800 | FAASt [Transmission Priority Pole Replacements – Line 13300] (Transmission) | 14F004470000 | PBUT13 - T Priority Pole Repl | Transmission – Pole Replacement | Transmission Priority Pole Replacements |  | Restoration | FALSE | [15 empty] | 44649 | 3/29/2022 | 44742 | 44720 | [5 empty] | 2830000 | 453597 | 0 | 81996 |  | 453597 | 0 | 0 | 453597 | 535593 |  |  | 44775 | 8/30/2024 | 453597 | 453597 | 453597 | 453597 |  |  |  | 453597 | 453597 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/241/668583-DR4339PR-Detailed%20SOW%20-%20Line%2013300%20Rev1.pdf?web=1 |  | 46070.5126 | 45152.4652 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Marlina Crespo |  |  | 81996 |  | 1 | 1 |  | 668583RFI241 | 668583 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
666894 | 11519 | FAASt [San Juan Streetlighting] (Distribution) | 14F008790000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 44636 | 3/16/2022 | 45504 | 45108 | 45279 |  |  |  |  | 73611536 | 30550204.86 | 3532039 | 4738922 |  | 30543791 | 474312 | 3057727 | 34075830 | 38814752 | 45535 | 45626 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/242/666894-DR4339PR-Detailed%20SOW%20San%20Juan%20Phase%201%20High%20Priority%20Rev1%20-%20DSOW%20-%20signed.pdf?web=1 |  | 46059.6156 | 45152.4652 | Jahdiel Franqui | Distribution Streetlighting | Jason Fournier |  |  |  |  | 0.89654 | 1 | 45873 | 666894RFI242 | 666894 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
662238 | 107742 | FAASt [Microwave Point-to-Point Backbone] (Telecommunications) | 14F004500000 | PBIT01 - Telecom Sys & Network | Telecommunications | IT OT Telecom Systems and Network | TRUE | Restoration | FALSE |  | Current | FALSE |  | Resubmitted |  |  | 6000000 | 44438 | 44461 |  | 44468 |  |  |  | 44606 | 2/14/2022 | 45077 | 45069 | 46070 |  |  |  |  | 6000000 | 16046926.54 | 5926449.37 | 2708469.23 | 0 | 28826526.19 | 509009.29 | 5417440.08 | 34752975.56 | 37461444.79 | 45504 | 45657 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/243/662238%20FEMA%20DSOW%20Microwave%20PTP%20Backbone%20Signed%20EP%20ML%20TP%20(1).pdf?web=1 | Originally withdrawn on 12/4/2025. This project was reactivated on 12/10/2025 | 46071.5282 | 45152.4652 | Jahdiel Franqui | Microwave Point-to-Point | Marlina Crespo | 0 Months |  |  |  | 0.46174 | 3 |  | 662238RFI243 | 662238 | 0 | 0 | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
660437 | 11097 | FAASt [Manati Streetlighting] (Distribution) | 14F004190000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE | [15 empty] | 44594 | 1/27/2022 | 44773 | 44771 | 44879 |  |  |  |  | 12758461 | 28636829 | 1568964 | 5821636 |  | 27067865 | 380359 | 1188605 | 28636829 | 34458465 |  |  | 44950 |  | 28636829 | 27067865 | [5 empty] | 28636829 | 27067865 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/244/660437-Streetlight-Manati%20DSOW_Rev1.pdf?web=1 |  | 45859.6414 | 45152.4652 | Jahdiel Franqui | Distribution Streetlighting | Jose J Ramos Figueroa |  |  | 5821635 |  | 1 | 1 |  | 660437RFI244 | 660437 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 1568964
660422 | 11566 | FAASt [Physical Security - Group 4] (Substation) | 14F003870000, 14F003750000 | PBUT18 - Substation Security | Substation | Substation Security |  | Restoration | FALSE | [15 empty] | 44614 | 1/27/2022 | 45107 | 45082 | 45190 |  |  |  |  | 800000 | 3816798 | 338280 | 766618 |  | 3478518 | 0 | 338280 | 3816798 | 4583416 |  |  | 45289 | 8/30/2024 | 3816798 | 3478518 | 3816798 | 3478518 |  |  |  | 3816798 | 3478518 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/245/660422%20DR4339PR%20Physical%20Security%20Group%204%20SOW.pdf?web=1 |  | 46070.5111 | 45152.4652 | Jahdiel Franqui | Physical Security | Marlina Crespo |  |  | 460523 |  | 1 | 1 |  | 660422RFI245 | 660422 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 338280
660239 | 10857 | FAASt [Villalba Streetlighting] (Distribution) | 14F004200000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE | [15 empty] | 44587 | 1/26/2022 | 44773 | 44749 | 44763 |  |  |  |  | 5577994 | 10872401.71 | 681865.66 | 2630719 |  | 10190536 | 84516.08 | 597349.58 | 10872401.66 | 13503120.66 |  |  | 44797 |  | 10872401.71 | 10190536.05 | [5 empty] | 10872401.71 | 10190536.05 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/246/660239-DSOW-Distribution%20Streetlighting%20-%20Villalba_Rev3.pdf?web=1 |  | 45856.7691 | 45152.4652 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 2630718.61 |  | 1 | 1 |  | 660239RFI246 | 660239 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 681865.66
660227 | 11095 | FAASt [Hatillo Streetlighting] (Distribution) | 14F004340000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE | [15 empty] | 44588 | 1/26/2022 | 44804 | 44781 | 44876 |  |  |  |  | 12447777 | 20334482.95 | 1764387.7 | 4317860 |  | 18570180 | 448282.64 | 1316105.06 | 20334567.7 | 24652427.7 |  |  | 44950 |  | 20334482.95 | 18570095.25 | [5 empty] | 20334482.95 | 18570095.25 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/247/660227-DR4339PR-Distribution%20Streetlighting%20-%20DSOW-Aibonito_Rev2.pdf?web=1 |  | 45856.7691 | 45152.4652 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 4317860.43 |  | 1 | 1 |  | 660227RFI247 | 660227 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 1764387.7
659968 | 11318 | FAASt [San Germán Streetlighting] (Distribution) | 14F004330000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE | [15 empty] | 44585 | 1/24/2022 | 45016 | 44999 | [5 empty] | 13034397 | 34882926 | 4033578 | 4619207 |  | 30849348 | 1029513 | 3004065 | 34882926 | 39502133 |  |  | 45050 |  | 34882926 | 30849348 | [5 empty] | 34882926 | 30849348 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/248/FEMA%20Detailed%20Scope%20of%20Work%20San%20Germ%C3%A1n%20-%20signed.pdf?web=1 |  | 45856.7691 | 45152.4652 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 4619207 |  | 1 | 1 |  | 659968RFI248 | 659968 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 4033578
659715 | 10876 | FAASt [Aibonito Streetlighting] (Distribution) | 14F004210000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE | [15 empty] | 44582 | 1/21/2022 | 44773 | 44749 | 44879 |  |  |  |  | 6013360 | 7253285 | 178787 | 1880873 |  | 7074498 | 49247 | 129540 | 7253285 | 9134158 |  |  | 44922 |  | 7253285 | 7074498 | [5 empty] | 7253285 | 7074498 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/249/659715-DR4339PR-Distribution%20Streetlighting%20-%20DSOW-Aibonito_Rev2.pdf?web=1 |  | 45856.7691 | 45152.4652 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 1880873 |  | 1 | 1 |  | 659715RFI249 | 659715 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 178787
659625 | 11099 | FAASt [Dorado Streetlighting] (Distribution) | 14F004350000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE | [15 empty] | 44581 | 1/20/2022 | 44804 | 44812 | 44876 |  |  |  |  | 11389001 | 24370617 | 1505645 | 4716594 |  | 22864972 | 355973 | 1149672 | 24370617 | 29087211 |  |  | 44950 |  | 24370617 | 22864972 | [5 empty] | 24370617 | 22864972 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/250/659625-DR4339PR-SOW-Distribution%20Streetlighting%20-%20Dorado_Rev2.pdf?web=1 |  | 45859.6829 | 45152.4652 | Jahdiel Franqui | Distribution Streetlighting | Jose J Ramos Figueroa |  |  | 3031749 | 165500 | 1 | 1 |  | 659625RFI250 | 659625 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 1340145
659623 | 10884 | FAASt [Cataño Streetlighting] (Distribution) | 14F004180000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE | [15 empty] | 44581 | 1/20/2022 | 44773 | 44749 | 44876 |  |  |  |  | 5191684 | 17562047 | 565289 | 3574763 |  | 16996758 | 49247 | 516042 | 17562047 | 21136810 |  |  | 44922 |  | 17562047 | 16996758 | [5 empty] | 17562047 | 16996758 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/251/659623-DSOW-Distribution%20Streetlighting%20-%20Cata%C3%B1o-Rev0.pdf?web=1 |  | 45987.4827 | 45152.4653 | Jahdiel Franqui | Distribution Streetlighting | Jason Fournier |  |  | 3574763 |  | 1 | 1 |  | 659623RFI251 | 659623 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 565289
657300 | 10957 | FAASt [ENERGY MANAGEMENT SYSTEM (EMS)] (Telecommunication) | 14F000020000 | PBUT22 - Critical Energy Mgmt Sy | Telecommunications | IT OT Telecom Systems and Network |  | Improved | FALSE |  | Past | [5 empty] | 42000000 | 44438 | 44461 |  | 44468 |  |  |  | 44580 | 1/19/2022 | 44742 | 44739 | 45530 |  |  |  |  | 126000000 | 48941484 | 0 | 2041312 |  | 48941484 | 0 | 0 | 48941484 | 50982796 |  |  | 44851 | 10/17/2024 | 48941484 | 48941484 | 164579862 | 164579862 |  |  |  | 164579862 | 164579862 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/252/55110%20-%20FAASt%20657300_Phase%202%20EMS_FEMA%20Project%20Detailed%20Scope%20of%20Work_2023.8.21%20Rev%202%20-%20signed.pdf | 5/16/2024 - Previously, 657300 included the EMS (software / servers) and the PCC / SCC (2 buildings) projects. The PCC / SCC projects have been moved to 746545. This means 657300 includes only the EMS (software / servers) scope. Therefore, 657300 is a Telecommunications project, not a Building project. [Update provided by Andrew Buresh, PM for 746545. Phil Vallejo is the PM for 65730] | 46051.3978 | 45152.4653 | Jahdiel Franqui | Primary Control Center Secondary Data Center & Control Room | Ashleah Dingle | 0 Months |  | 2041312 |  | 1 | 1 |  | 657300RFI252 | 657300 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
551963 | 11859 | FAASt [Transport Network] (Telecommunication) | 14F002140000 | PBIT01 - Telecom Sys & Network | Telecommunications | IT OT Telecom Systems and Network | TRUE | Restoration | FALSE |  | Current | [5 empty] | 185000000 | 44438 | 44461 |  | 44468 |  |  |  | 44593 | 12/22/2021 | 45138 | 45136 | 46045 | 45807 | 45799 |  |  | 185000000 | 84287009 | 4232330.2 | 671253.14 |  | 4489030.64 | 539034.63 | 3693295.57 | 8721360.84 | 9392613.98 | 45626 | 45808 | 45917 |  | 5490297 | 5490297 |  |  |  | 1143166.33 |  | 5490297 | 5490297 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/253/551963%20Transport%20Network%20DSOW%20Rev%203%207-28-23%20(EP%20ML%20JC)%20-%20signed.pdf?web=1 | 3/27/2024: QC Review Complete7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short List | 46059.5417 | 45152.4653 | Jahdiel Franqui | Transport Network | Jason Fournier | 0 Months |  | 836416.02 | 0 | 9.6644 | 1 |  | 551963RFI253 | 551963 | 1143166.33 | 0 | 1143166.33 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
551927 | 107736 | FAASt [SCADA Remote Access and RTU Replacements Group 3] (Telecommunication) | 14F003910000 | PBUT07 - Substation Reliability | Substation | IT OT Telecom Systems and Network |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | FALSE | [9 empty] | 44571 | 12/22/2021 | 45322 | 45412 | 45844 | 45594 | 45580 |  |  | 17000000 | 26178032.7 | 3299617.88 | 2431898.51 |  | 16781290.09 | 409517.03 | 2890100.85 | 20080907.97 | 22512806.48 | 45777 | 45596 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/254/551927-DR4339PR-SCADA%20Remote%20Access%20and%20RTU%20Replacement%20Group%203.pdf?web=1 | 4/17/2024: QC Review Complete | 46077.5737 | 45152.4653 | Jahdiel Franqui | SCADA Remote Access and RTU Replacements | Ashleah Dingle |  |  |  |  | 1.3036 | 1 | 45880 | 551927RFI254 | 551927 | 1825681.47 | 155359.48 | 1981040.95 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
551926 | 107735 | FAASt [SCADA Remote Access and RTU Replacements Group 2] (Telecommunication) | 14F002130000 | PBUT07 - Substation Reliability | Telecommunications | IT OT Telecom Systems and Network | TRUE | Restoration | FALSE |  | Current | [13 empty] | 44571 | 12/22/2021 | 45199 | 45198 | 45813 | 45890 | 45883 | 8/14/2025 - Field EHP: In review. Expected Completion Date (ECD) 08/21/2025. |  | 5600000 | 8456184.1 | 1073462.61 | 800287.41 |  | 5664186.55 | 134453.44 | 939009.17 | 6737649.16 | 7537936.57 | 45626 | 45716 | 46082 |  | 6340930.6 | 5267467.99 |  |  |  | 396718.56 |  | 6340930.6 | 5267467.99 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/255/551926-DR4339PR-SCADA%20Remote%20Access%20and%20RTU%20Replacement%20Group%202.pdf?web=1 | 8/14/2025 - Field EHP: In review. Expected Completion Date (ECD) 08/21/2025. | 46083.6737 | 45152.4653 | Jahdiel Franqui | SCADA Remote Access and RTU Replacements | Marlina Crespo |  |  | 800287.41 | 134453.44 | 1.2551 | 1 |  | 551926RFI255 | 551926 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 939009.17
551925 | 11537 | FAASt [SCADA Remote Access and RTU Replacements Group 1] (Telecommunication) | 14F002120000, 10F007390000, 10F007430000, 10F007400000, 10F007410000, 10F007420000, 10F007440000 | PBUT07 - Substation Reliability | Telecommunications | IT OT Telecom Systems and Network |  | Restoration | FALSE |  | Past | [5 empty] | 30000000 | 44438 | 44461 |  | 44468 |  |  |  | 44571 | 12/22/2021 | 44773 | 44757 | 46076 |  |  |  |  | 7000000 | 7664336.14 | 2119378.2 | 1043403.42 | 0 | 7566499.86 | 266016.14 | 1853362.06 | 9685878.06 | 10729281.48 | 45473 | 45626 | 45597 |  | 7664336.14 | 5962412.52 | [5 empty] | 7664336.14 | 5962412.52 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/256/551925-DR4339PR-Detailed%20Scope%20of%20Work%20SCADA%20Remote%20Access%20and%20RTU%20Replacement%20Group1_Revised%207-25-23%20LPCE%20Adjusted%20to%20HM.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short & Long List | 46078.6831 | 45152.4653 | Jahdiel Franqui | SCADA Remote Access and RTU Replacements | Marlina Crespo |  |  | 1248409.19 | 294727.35 | 0.79129 | 2 |  | 551925RFI256 | 551925 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 1407196.27
551918 | 11409 | FAASt [Crematorio - 1512] (Substation) | 14F001810000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 10600000 | 44473 | 44487 |  | 44503 |  |  |  | 44551 | 12/21/2021 | 45107 | 45107 | [5 empty] | 10600000 | 0 | 6048401 | 1241556 |  | 11476729 | 590443 | 5457958 | 17525130 | 18766686 | 46022 | 45716 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/257/551918-DR4339-PR%20FEMA%20Detailed%20Scope%20of%20Work%20for%20Crematorio%201512%20Substation%20(1).pdf?web=1 |  | 45887.592 | 45152.4653 | Jahdiel Franqui | Crematorio - 1512 | Maria Mujica Gonzalez |  |  |  |  | 0 | 5 | 45884 | 551918RFI257 | 551918 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
551916 | 107734 | FAASt [Dorado TC Relocation] (Substation) | 14F003140000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active |  |  | 40100000 | [7 empty] | 44551 | 12/21/2021 | [7 empty] | 40100000 | 40100000 | [5 empty] | 0 | 40100000 | 40100000 | [11 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/258/551916%20-%20DR4339PR%20-%20Dorado%20TC%20Relocation%20(Substation)%20SOW%20CE.pdf?web=1 | 4/2/2024 - Received withdrawal status data/info from Manager Yadira L. Lugo Cordero. Working with Planning and Engineering to complete assessments to define scope and start the Preliminary Engineering. | 45877.5778 | 45152.4653 | Jahdiel Franqui | Dorado TC Relocation | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 551916RFI258 | 551916 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
551914 | 11470 | FAASt [Caparra 1911 & 1924] (Substation) | 14F001930000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | TRUE | Restoration | FALSE |  | Current | [5 empty] | 6600000 | 44473 | 44487 |  | 44503 |  |  |  | 44592 | 12/21/2021 |  | 45471 | 45726 |  |  |  |  | 6600000 | 0 | 5838512.8 | 1069270.88 |  | 8228185.09 | 671468.81 | 5167043.99 | 14066697.89 | 15135968.77 | [11 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/259/551914-DR4339PR-Caparra%201911%20&%201924.pdf?web=1 |  | 46059.5385 | 45152.4653 | Jahdiel Franqui | Caparra 1911 & 1924 | Jason Fournier |  |  |  |  | 0 | 5 |  | 551914RFI259 | 551914 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
551912 | 107733 | FAASt [Puerto Nuevo - 1520] (Substation) | 14F001780000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | TRUE | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 10600000 | 44473 | 44487 |  | 44503 |  |  |  | 44551 | 12/21/2021 | 45107 | 45107 | 45210 |  |  |  |  | 10600000 | 16844776 | 6035307 | 1382809 |  | 10809469 | 684505 | 5350802 | 16844776 | 18227585 | 45869 | 46022 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/260/551912-DR4339PR%20FEMA%20Detailed%20Scope%20of%20Work%20for%20Puerto%20Nuevo%201520%20(1)%20(1).pdf?web=1 |  | 46059.5595 | 45152.4653 | Jahdiel Franqui | Puerto Nuevo - 1520 | Jason Fournier |  |  |  |  | 1 | 1 | 45884 | 551912RFI260 | 551912 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
551911 | 11434 | FAASt [Line 9100 (38 kV) - Guaraguao TC to Bayamon Pueblo Sect.] (Transmission) | 14F002520000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 5050000 | 44473 | 44487 |  | 44503 |  |  |  | 44551 | 12/21/2021 | 45382 | [6 empty] | 5050000 | 0 | [5 empty] | 0 | 5050000 | 5050000 | [11 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/261/551911%20-%20DR4339PR%20-%20Line%209100%20Guaraguao%20TC%20to%20Bayamon%20Pueblo%20Sect.%20SOW%20-%20CE.pdf?web=1 |  | 45887.6356 | 45152.4653 | Jahdiel Franqui | Line 9100 Guaraguao TC to Bayamon Pueblo Sect. | Ashleah Dingle |  |  |  |  | 0 | 5 | 45887 | 551911RFI261 | 551911 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
551861 | 11372 | FAASt [Physical Security - Group 3] (Substation) | 14F003850000, 14F003740000, 14F003860000 | PBUT18 - Substation Security | Substation | Substation Security |  | Restoration | FALSE | [15 empty] | 44553 | 12/21/2021 | 44926 | 44909 | 45044 |  |  |  |  | 1200000 | 4133339.83 | 436383.23 | 844837 |  | 3696956 | 73108.14 | 363275.09 | 4133339.23 | 4978176.23 |  |  | 45093 |  | 4133339.83 | 3696956.6 | [5 empty] | 4133339.83 | 3696956.6 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/262/551861-DR4339PR-%2000%20FEMA%20Detailed%20Scope%20of%20Work%20for%20Physical%20Security%20-%20Group%203%20(40000-CP-SOW-0009Rev5)(2023-04-27)%20-%20signed.pdf?web=1 |  | 45856.7692 | 45152.4653 | Jahdiel Franqui | Physical Security | Rey Roldan Rodríguez |  |  | 844836.71 |  | 1 | 1 |  | 551861RFI262 | 551861 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 436383.23
551827 | 107732 | FAASt [San Juan Region Repair] (Building) | 14F002030000 | PBFM01 - Facilities Dev & Implem | Building | Facilities Development & Implementation | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 31030000 | [7 empty] | 44666 | 12/21/2021 | [7 empty] | 31028730 | 31028730 | [5 empty] | 0 | 31028730 | 31028730 | [11 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/263/551827-DR4339PR-10038-FA-SOW-0001_Rev0-%20San%20Juan%20Region%20Repairs.pdf?web=1 | 4/3/2024 - Received withdrawal status data/info from Deputy Project Manager Gerardo Medina-Sonera. This project will be included in the new Island Wide ISOW approach. | 45877.5778 | 45152.4653 | Jahdiel Franqui | San Juan Region Repairs | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 551827RFI263 | 551827 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
551260 | 107727 | FAASt [Guaynabo Pueblo Substation] (Substation) | 14F001850000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 17200000 | 44473 | 44487 |  | 44503 |  |  |  | 44546 | 12/16/2021 | 45567 | 45201 | 45813 |  |  |  |  | 17200000 | 22373983 | 10941966.54 | 2334521.27 |  | 20046985.57 | 1141020.24 | 9800946.3 | 30988952.11 | 33323473.38 | 45596 | 45747 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/264/551260-DR43339PR-00%20FEMA%20DSOW%20for%20Guaynabo%20Pueblo%20Rev.%202%2004012024%20-%20signed.pdf?web=1 | 3/27/2024: QC Review Complete | 45981.5363 | 45152.4653 | Jahdiel Franqui | Guaynabo Pueblo Substation | Marlina Crespo |  |  |  |  | 0.722 | 2 | 45884 | 551260RFI264 | 551260 | 10219258.33 | 6990448.48 | 17209706.81 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
551247 | 11570 | FAASt [Palo Seco South Building Repairs] (Building) | 14F002000000 | PBFM01 - Facilities Dev & Implem | Building | Facilities Development & Implementation |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 11170000 | 44438 | 44483 |  | 44468 |  |  |  | 44546 | 12/16/2021 | 45382 | [6 empty] | 11170493 | 0 | [5 empty] | 0 | 11170493 | 11170493 | [11 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/265/551247-DR4339PR-10035-FA-SOW-0001_Rev0-%20Palo%20Seco%20South%20Building%20Repairs.pdf?web=1 |  | 45881.4368 | 45152.4653 | Jahdiel Franqui | Palo Seco South Building Repairs | Maria Mujica Gonzalez |  |  |  |  | 0 | 5 | 45880 | 551247RFI265 | 551247 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
551242 | 107726 | FAASt [Bayamon Region Repairs] (Building) | 14F002010000 | PBFM01 - Facilities Dev & Implem | Building | Facilities Development & Implementation | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 15450000 | [7 empty] | 44546 | 12/16/2021 | [7 empty] | 15451305 | 15451305 | [5 empty] | 0 | 15451305 | 15451305 | [11 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/266/551242-DR4339PR-10036-FA-SOW-0001_Rev0-Bayamon%20Region%20Repairs.pdf?web=1 | 4/3/2024 - Received withdrawal status data/info from Deputy Project Manager Gerardo Medina-Sonera. This project will be included in the new Island Wide ISOW approach. | 45877.5778 | 45152.4653 | Jahdiel Franqui | Bayamon Region Repairs | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 551242RFI266 | 551242 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
551100 | 107725 | FAASt [Bayview Sectionalizer 1802 Relocation] (Substation) | 14F001890000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active |  |  | 16700000 | [7 empty] | 44545 | 12/15/2021 | [7 empty] | 16700000 | 16700000 | [5 empty] | 0 | 16700000 | 16700000 | [11 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/267/551100-DR4339PR-10024-EN-SOW-0001_Rev0%20-%20Bayview%20Sectionalizer%201802%20Relocation.pdf?web=1 | 4/2/2024 - Received withdrawal status data/info from Manager Yadira L. Lugo Cordero. Working with Planning and Engineering to complete assessments to define scope and start the Preliminary Engineering. | 45877.5778 | 45152.4653 | Jahdiel Franqui | Bayview Sectionalizer 1802 Relocation | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 551100RFI267 | 551100 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
551067 | 11687 | FAASt [Line 11100 Canovanas Sect. to GOAB 11115] (Transmission) | 14F002540000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 3790000 | 44473 | 44487 |  | 44503 |  |  |  | 44545 | 12/15/2021 | 45382 |  |  | 45730 | 45726 |  |  | 3790000 | 3790000 | [5 empty] | 0 | 3790000 | 3790000 | [11 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/268/551067-DR4339PR-10093-EN-SOW-0001_Rev0%20-%20Line%2011100%20Canovanas%20Sect.%20to%20GOAB%2011115.pdf?web=1 |  | 45888.5056 | 45152.4653 | Jahdiel Franqui | Line 11100 Canovanas Sect. to GOAB 11115 | Maria Mujica Gonzalez |  |  |  |  | 1 | 1 | 45887 | 551067RFI268 | 551067 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
550998 | 107724 | FAASt [Santurce Planta (Sect) 1116] (Substation) | 14F001870000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active |  | 45618 | 9900000 | 45638 | 45668 |  | 45668 |  |  |  | 44544 | 12/14/2021 | [7 empty] | 9900000 | 9900000 | [5 empty] | 0 | 9900000 | 9900000 | [11 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/269/550998-DR4339PR-10022-EN-SOW-0001_Rev0%20-%20Santurce%20Planta%20(Sect)%201116(1).pdf?web=1 | 4/2/2024 - Received withdrawal status data/info from Manager Yadira L. Lugo Cordero. Working with Planning and Engineering to complete assessments to define scope and start the Preliminary Engineering. | 45877.578 | 45152.4653 | Jahdiel Franqui | Santurce Planta (Sect) 1116 | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 550998RFI269 | 550998 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
550986 | 107723 | FAASt [Condado - 1133] (Substation) | 14F001800000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | TRUE | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | FALSE |  | 10600000 | 44473 | 44487 |  | 44503 |  |  |  | 44544 | 12/14/2021 | 45107 | 45107 | [5 empty] | 10600000 | 14709154 | 5427167 | 1367924 |  | 9281987 | 697091 | 4730076 | 14709154 | 16077078 | 45838 | 45991 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/270/550986-4339%20DR-PR%20-%20FEMA%20Detailed%20Scope%20of%20Work%20for%20Condado%201133-6-30-2023%20signed%20(1).pdf?web=1 |  | 46077.5737 | 45152.4653 | Jahdiel Franqui | Condado - 1133 | Ashleah Dingle |  |  |  |  | 1 | 1 | 45884 | 550986RFI270 | 550986 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
550980 | 107722 | FAASt [Parques y Recreos - 1002] (Substation) | 14F001770000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | TRUE | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 7700000 | 44473 | 44487 |  | 44503 |  |  |  | 44544 | 12/14/2021 | 45107 | 45107 | 45338 |  |  |  |  | 7700000 | 20916860 | 8962734.08 | 1608592.37 |  | 10128904.68 | 1227475.29 | 7735258.79 | 19091638.76 | 20700231.13 | 45626 | 45808 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/271/550980-DR4339PR-FEMA%20Detailed%20Scope%20of%20Work%20for%20ParqueRecreo%201002%20-%20signed%20(1).pdf?web=1 |  | 46059.5595 | 45152.4653 | Jahdiel Franqui | Parques y Recreos - 1002 | Jason Fournier |  |  |  |  | 1.0956 | 1 | 45884 | 550980RFI271 | 550980 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
550972 | 107721 | FAASt [Fonalledas GIS Rebuilt 1401 1421] (Substation) | 14F001840000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active |  |  | 31400000 | [7 empty] | 44544 | 12/14/2021 | [7 empty] | 31400000 | 31400000 | [5 empty] | 0 | 31400000 | 31400000 | [11 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/272/550972-DR4339PR-10019-EN-SOW-0001_Rev0%20-%20Fonalledas%20GIS%20Rebuilt%201401%201421(1).pdf?web=1 | 4/2/2024 - Received withdrawal status data/info from Manager Yadira L. Lugo Cordero. Working with Planning and Engineering to complete assessments to define scope and start the Preliminary Engineering. | 45877.578 | 45152.4653 | Jahdiel Franqui | Fonalledas GIS Rebuilt 1401 1421 | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 550972RFI272 | 550972 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
550950 | 11557 | FAASt - EPC - [Monacillo TC] (Substations) | 14F003150000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | TRUE | Restoration | FALSE |  | Current | [5 empty] | 105230000 | 45281 | 45309 |  | 45311 |  |  |  | 44544 | 12/14/2021 | 45077 | 45077 | 45821 | 45849 | 45838 |  |  | 105230000 | 88096455.73 | 0 | 2179830 |  | 13072870.61 | 0 | 0 | 13072870.61 | 15252700.61 |  |  | 45279 | 9/17/2025 | 88096455.73 | 88096455.73 | 58195134.17 | 88096455.73 | 58195134 | 42974192.2 | 58195134 | 58195134 | 58195134 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/273/550950%20-Monacillo%20TC%20(Substations)-%20FEMA%20Project%20Detailed%20Scope%20of%20Work%209.15.23%20rev.pdf?web=1 |  | 46059.5385 | 45152.4653 | Jahdiel Franqui | Monacillo TC | Jason Fournier |  |  | 6623439.52 | 0 | 6.7389 | 1 |  | 550950RFI273 | 550950 | 42974192.2 |  | 42974192.2 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
550910 | 10841 | FAASt [Physical Security - Group 1] (Substation) | 14F003820000, 14F003810000, 14F003800000, 14F003830000, 14F003720000 | PBUT18 - Substation Security | Substation | Substation Security |  | Restoration | FALSE | [7 empty] | 53800000 | [7 empty] | 44553 | 12/14/2021 | 44681 | 44655 | 44909 |  |  |  |  | 2000000 | 6691229.18 | 665958.96 | 1278328 |  | 6025270 | 0 | 665958.96 | 6691228.96 | 7969556.96 |  |  | 45050 | 8/30/2024 | 6691229.18 | 6025270.22 | 6691229.18 | 6025270.22 |  |  |  | 6691229.18 | 6025270.22 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/274/550910-DR4339PR-%2000%20FEMA%20Detailed%20Scope%20of%20Work%20for%20Physical%20Security%20-%20Group%201%20(2023-03-17)%20-%20signed.pdf?web=1 |  | 46070.5108 | 45152.4653 | Jahdiel Franqui | Physical Security | Marlina Crespo |  |  | 1278327.97 |  | 1 | 1 |  | 550910RFI274 | 550910 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 665958.96
550902 | 11688 | FAASt [Line 9700 Palo Seco SP to Bay View Sect.] (Transmission) | 14F002530000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 2320000 | 44473 | 44487 |  | 44503 |  |  |  | 44544 | 12/14/2021 | 45382 | [6 empty] | 2320000 | 2320000 | [5 empty] | 0 | 2320000 | 2320000 | [11 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/275/550902-DR4339PR-10092-EN-SOW-0001_Rev0%20-%20Line%209700%20Palo%20Seco%20SP%20to%20Bay%20View%20Sect(1).pdf?web=1 |  | 45888.4975 | 45152.4653 | Jahdiel Franqui | Line 9700 Palo Seco SP to Bay View Sect. | Maria Mujica Gonzalez |  |  |  |  | 1 | 1 | 45887 | 550902RFI275 | 550902 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
550896 | 10837 | FAASt [Transmission Priority Pole Replacements – Line 6700] (Transmission) | 14F004450000 | PBUT13 - T Priority Pole Repl | Transmission – Pole Replacement | Transmission Line Rebuild |  | Restoration | FALSE | [15 empty] | 44241 | 12/14/2021 | 44985 | 44736 | 46059 |  |  |  |  | 6010000 | 690703 | 17395.24 | 86095.96 | 93552 | 1163826.56 | 1139.54 | 16255.7 | 1181221.8 | 1267317.76 |  |  | 44781 | 12/18/2025 | 690703 | 690703 | 1070274.56 | 1070274.56 |  |  |  | 1070274.56 | 1070274.56 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/276/550896-DR4339PR-Detailed%20SOW%20-%20Line%206700%20Rev.0%20(1).pdf?web=1 |  | 46070.5104 | 45152.4653 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Marlina Crespo |  |  | 133416 |  | 0.58474 | 3 |  | 550896RFI276 | 550896 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
550894 | 107720 | FAASt [Baldrich - 1422] (Substation) | 14F001790000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | TRUE | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | FALSE |  | 10500000 | 44473 | 44487 |  | 44503 |  |  |  | 44544 | 12/14/2021 | 45199 | 45198 | 45397 |  |  |  |  | 10500000 | 26709229 | 28669863 | 88908 |  | 884190 | 2619452 | 26050411 | 29554053 | 29642961 | 45869 | 46022 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/277/550894%20-%20DR4339PR%20-%20%20FAASt%20Baldrich%20Sectionalizer%201422%20-%20SOW%20CE.pdf?web=1 |  | 46077.5737 | 45152.4653 | Jahdiel Franqui | Baldrich - 1422 | Ashleah Dingle |  |  |  |  | 0.90374 | 1 | 45884 | 550894RFI277 | 550894 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
550771 | 107719 | FAASt [Caguas TC] (Substation) | 14F002930000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active |  |  | 2500000 | [7 empty] | 44589 | 12/13/2021 | [7 empty] | 2500000 | 2500000 | [5 empty] | 0 | 2500000 | 2500000 | [11 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/278/550771%20-%20DR4339%20-%20Caguas%20TC%20(Substation)%20Initial%20SOW.pdf?web=1 | 4/2/2024 - Received withdrawal status data/info from Manager Yadira L. Lugo Cordero. Working with Planning and Engineering to complete assessments to define scope and start the Preliminary Engineering. | 45877.578 | 45152.4653 | Jahdiel Franqui | Caguas TC | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 550771RFI278 | 550771 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
550500 | 107718 | FAASt - Ponce Region Repairs (Building) | 14F002050000 | PBFM01 - Facilities Dev & Implem | Building | Facilities Development & Implementation | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 16300000 | [7 empty] | 44547 | 12/10/2021 | [7 empty] | 20294279 | 20294279 | [5 empty] | 0 | 20294279 | 20294279 | [11 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/279/550500-DR4339PR-10040-FA-SOW-0001_Rev0-Ponce%20Region%20Repairs.pdf?web=1 | 4/3/2024 - Received withdrawal status data/info from Deputy Project Manager Gerardo Medina-Sonera. This project will be included in the new Island Wide ISOW approach. | 45877.578 | 45152.4653 | Jahdiel Franqui | Ponce Region Repairs | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 550500RFI279 | 550500 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
550498 | 107717 | FAASt - [Morovis 8801 (Fuse to Breaker)] (Substation) | 14F001910000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 16300000 | 44473 | 44487 |  | 44503 |  |  |  | 44540 | 12/10/2021 | 45291 | [6 empty] | 16300000 | 5844709 | [5 empty] | 0 | 16300000 | 16300000 | [11 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/280/921048-DR4339PR-10026-EN-SOW-0001_Rev0%20-%20Pampanos%20Sect%20Relocation.pdf?web=1 |  | 45887.5994 | 45152.4653 | Jahdiel Franqui | Pampanos Relocation | Maria Mujica Gonzalez |  |  |  |  | 0.35857 | 4 | 45884 | 550498RFI280 | 550498 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
550162 | 11813 | FAASt [Berwind TC - 1336] (Substation) | 14F002920000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 13400000 | 44473 | 44487 |  | 44503 |  |  |  | 44537 | 12/7/2021 | 45230 | 45201 | 45280 |  |  |  |  | 13400000 | 51763597 | 6718315 | 4182974 |  | 40767573 | 625188 | 6093127 | 47485888 | 51668862 | 45657 | 45747 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/281/550162%20-%20DR4339PR%20-%20%20Berwind%20TC%20-%201336%20(Transmission).pdf?web=1 |  | 45887.6004 | 45152.4653 | Jahdiel Franqui | Berwind TC - 1336 | Maria Mujica Gonzalez |  |  |  |  | 1.0901 | 1 | 45884 | 550162RFI281 | 550162 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
550106 | 107714 | FAASt [Conquistador CH] (Substation) | 14F003170000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | TRUE | Restoration | FALSE |  | Current | [5 empty] | 5100000 | 44473 | 44487 |  | 44503 |  |  |  | 44537 | 12/7/2021 | 45107 | 45107 | 45383 |  |  |  |  | 5100000 | 11639958 | 1101071.22 | 1478605.83 |  | 9827316 | 143115.56 | 957955.66 | 10928387.22 | 12406993.05 | 45626 | 45808 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/282/550106-DR4339PR-%20Detail%20Scope%20of%20Work%20Conquistador%20CH%20-%20signed%20(1).pdf?web=1 |  | 46059.5385 | 45152.4653 | Jahdiel Franqui | Conquistador - CH | Jason Fournier |  |  |  |  | 1.0651 | 1 |  | 550106RFI282 | 550106 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
550099 | 107713 | FAASt [Esc. Industrial M. Such - 1423] (Substation) | 14F001830000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | TRUE | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 10600000 | 44473 | 44487 |  | 44503 |  |  |  | 44537 | 12/7/2021 | 45107 | 45107 | 45377 |  |  |  |  | 10600000 | 14335434 | 6851320.87 | 1112050.13 |  | 8804423.21 | 762291.03 | 6089029.84 | 15655744.08 | 16767794.21 | 45626 | 45808 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/283/550099-DR4339PR%20-%20FEMA%20Detailed%20Scope%20of%20Work%20for%20Esc%20Industrial%20Miguel%20Such%201423%20-%20signed%20(1).pdf?web=1 |  | 46059.5595 | 45152.4653 | Jahdiel Franqui | Esc. Industrial M. Such - 1423 | Jason Fournier |  |  |  |  | 0.91567 | 1 | 45884 | 550099RFI283 | 550099 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
550070 | 107712 | FAASt [Line 4000 Comerio HP to Escuela Francisco Morales] (Transmission) | 14F002510000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active |  |  | 22330000 |  |  | 45491 |  |  |  |  | 44537 | 12/7/2021 | [7 empty] | 22330000 | 22330000 | [5 empty] | 0 | 22330000 | 22330000 | [11 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/284/550070%20-%20DR4339PR%20-%20Line%204000%20Comerio%20HP%20to%20Escuela%20Francisco%20Morales%20Initial%20SOW%20CE.pdf?web=1 | 3/28/2024 - Received withdrawal status data/info from Project Manager Claudio R. Jaquez. DSOW submittal forecast: 7/18/2024. | 45877.578 | 45152.4653 | Jahdiel Franqui | Line 4000 Comerio HP to Escuela Francisco Morales | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 550070RFI284 | 550070 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
550060 | 107711 | FAASt [Caguas Region Repairs] (Building) | 14F002020000 | PBFM01 - Facilities Dev & Implem | Building | Facilities Development & Implementation | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 14470000 | [7 empty] | 44537 | 12/7/2021 | [7 empty] | 14472109 | 14472109 | [5 empty] | 0 | 14472109 | 14472109 | [11 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/285/550060%20-DR4339PR%20-%20Caguas%20Region%20Repairs%20Initial%20SOW%20CE.pdf?web=1 | 4/3/2024 - Received withdrawal status data/info from Deputy Project Manager Gerardo Medina-Sonera. This project will be included in the new Island Wide ISOW approach. | 45877.578 | 45152.4653 | Jahdiel Franqui | Caguas Region Repairs | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 550060RFI285 | 550060 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
550019 | 107710 | FAASt [Line 600 Caguas TC to Gautier Benitez Sect.] (Transmission) | 14F002470000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  | 45568 | 10110000 | 44473 | 44487 |  | 44503 |  |  |  | 44537 | 12/7/2021 | 45199 | 45194 | 45407 |  |  |  |  | 10110000 | 21404169 | 4035264 | 2943392 |  | 19190123 | 488834 | 3546430 | 23225387 | 26168779 | 45838 | 45991 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/286/550019%20-%20DR4339PR%20FAASt%20Line%20600%20Caguas%20TC%20to%20Gautier%20Benitez%20%20Sect%20(Transmission)Applicant%20provided%20SOW%20CE.pdf?web=1 | 3/26/2024 - EHP Phase I, II Analyses data received from Grid Strategy and inserted in tracker for affected TLine 600 | 45888.4922 | 45152.4653 | Jahdiel Franqui | Line 600 Caguas TC to Gautier Benitez Sect. | Maria Mujica Gonzalez |  |  |  |  | 0.92159 | 1 | 45887 | 550019RFI286 | 550019 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
549768 | 107709 | FAASt Physical Security - Group 5 (Substation) | 14F003880000 | PBUT18 - Substation Security | Substation | Substation Security |  | Restoration | TRUE | 45869 |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active | [10 empty] | 44533 | 12/3/2021 | [7 empty] | 1200000 | 1200000 | [5 empty] | 0 | 1200000 | 1200000 | [11 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/287/549768-DR4339PR-Physical%20Security%2040000-EN-SOW-0007_Rev0.pdf?web=1 | 4/2/2024 - Received withdrawal status data/info from Manager Yadira L. Lugo Cordero. Working with Planning and Engineering to re-organize the group. | 45877.578 | 45152.4653 | Jahdiel Franqui | Physical Security | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 549768RFI287 | 549768 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
549764 | 11350 | FAASt [Physical Security - Group 2] (Substation) | 14F003840000, 14F003730000 | PBUT18 - Substation Security | Substation | Substation Security |  | Restoration | FALSE | [7 empty] | 53800000 | 44473 | 44487 |  | 44503 |  |  |  | 44533 | 12/3/2021 | 44926 | 44909 | 45047 |  |  |  |  | 800000 | 2383692.99 | 224680.68 | 529771 |  | 2159012 | 0 | 224680.68 | 2383692.68 | 2913463.68 |  |  | 45093 | 8/30/2024 | 2383692.99 | 2159012.31 | 2383692.99 | 2159012.31 |  |  |  | 2383692.99 | 2159012.31 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/288/549764-DR4339PR-%2000%20FEMA%20Detailed%20Scope%20of%20Work%20Physical%20Security%20Group%202%20(40000-CP-SOW-0012Rev2%20)(2023-03-23)%20-%20signed%20(1).pdf?web=1 |  | 46070.51 | 45152.4653 | Jahdiel Franqui | Physical Security | Marlina Crespo |  |  | 529771.49 |  | 1 | 1 |  | 549764RFI288 | 549764 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 224680.68
549725 | 11707 | FAASt [Substation Minor Repairs - Group E] (Substation) | 14F002910000, 14F002890000, 14F002900000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds |  | Restoration | FALSE | [15 empty] | 44533 | 12/3/2021 | 45107 | 45107 | 45329 |  |  |  |  | 1200000 | 4503783.21 | 579768 | 818227 |  | 3924016 | 22126.13 | 557641.87 | 4503784 | 5322011 | 45473 | 45504 | 45422 |  | 4503783.21 | 3924015.69 | [5 empty] | 4503783.21 | 3924015.69 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/289/549725-DR4339PR-00%20Detailed%20Scope%20of%20Work%20for%20Minor%20Repairs%20-%20Group%20E%20Rev.0%20(2023-06-30)%20(1).pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 45862.6139 | 45152.4653 | Jahdiel Franqui | Substation Minor Repairs | Jose J Ramos Figueroa |  |  | 98349.5 | 11328.47 | 1 | 1 |  | 549725RFI289 | 549725 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 568439.05
549715 | 11682 | FAASt Substation Minor Repairs - Group D (Substation) | 14F003000000, 14F003010000, 14F003020000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds |  | Restoration | FALSE | [15 empty] | 44533 | 12/3/2021 | 45107 | 45107 | 45295 |  |  |  |  | 1200000 | 2871257.17 | 288124 | 580189 |  | 2583134 | 0 | 288124 | 2871258 | 3451447 | 45473 | 45504 | 45394 | 8/30/2024 | 2871257.17 | 2583133.54 | 2871257.17 | 2583133.54 |  |  |  | 2871257.17 | 2583133.54 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/290/549715-DR4339PR-00%20Detailed%20Scope%20of%20Work%20for%20Minor%20Repairs%20-%20Group%20D%20Rev.0%20(2023-06-30)%20(1).pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 46070.5094 | 45152.4653 | Jahdiel Franqui | Substation Minor Repairs | Marlina Crespo |  |  | 580188.69 |  | 1 | 1 |  | 549715RFI290 | 549715 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 288123.63
548598 | 11494 | FAASt [Line 36200 (115 kV) Fajardo to Rio Blanco] (Transmission) | 14F002350000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 44310000 | 44473 | 44487 |  | 44503 |  |  |  | 44531 | 12/1/2021 | 45107 | 45107 | 45420 |  |  |  |  | 44310000 | 0 | 15963429 | 4765220 |  | 37425267 | 1717803 | 14245626 | 53388696 | 58153916 | 45596 | 45657 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/291/548598%20-%20DR4339PR%20-%20Line%2036200%20Fajardo%20to%20Rio%20Blanco%20Applicant%20SOW.pdf?web=1 |  | 45888.4875 | 45152.4653 | Jahdiel Franqui | Line 36200 Fajardo to Rio Blanco | Maria Mujica Gonzalez |  |  |  |  | 0 | 5 | 45887 | 548598RFI291 | 548598 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
548596 | 107708 | FAASt [San German Electrical Service Center] (Building) | 14F001980000 | PBFM01 - Facilities Dev & Implem | Building | Facilities Development & Implementation | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 2480000 | [7 empty] | 44531 | 12/1/2021 | [7 empty] | 2478182 | 2478182 | [5 empty] | 0 | 2478182 | 2478182 | [11 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/292/548596-DR4339PR-10033-FA-SOW-0001_Rev0-San%20German%20ESC.pdf?web=1 | 4/3/2024 - Received withdrawal status data/info from Deputy Project Manager Gerardo Medina-Sonera. This project will be included in the new Island Wide ISOW approach. | 45877.578 | 45152.4653 | Jahdiel Franqui | San German Electrical Service Center | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 548596RFI292 | 548596 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
548440 | 107707 | FAASt [Mayaguez Region Repairs] (Building) | 14F002040000 | PBFM01 - Facilities Dev & Implem | Building | Facilities Development & Implementation | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 13350000 | [7 empty] | 44530 | 11/30/2021 | [7 empty] | 13346360 | 13346360 | [5 empty] | 0 | 13346360 | 13346360 | [11 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/293/548440-DR4339PR--FA-SOW-0001_Rev0-%20Mayaguez%20Region%20Repairs.pdf?web=1 | 4/3/2024 - Received withdrawal status data/info from Deputy Project Manager Gerardo Medina-Sonera. This project will be included in the new Island Wide ISOW approach. | 45877.578 | 45152.4653 | Jahdiel Franqui | Mayaguez Region Repairs | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 548440RFI293 | 548440 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
548393 | 107705 | FAASt Arecibo Region Repairs (Buildings) | 14F001990000 | PBFM01 - Facilities Dev & Implem | Building | Facilities Development & Implementation | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 9230000 | [7 empty] | 44557 | 11/29/2021 | [7 empty] | 9226902 | 9226902 | [5 empty] | 0 | 9226902 | 9226902 | [11 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/294/548393%20DR4339PR%20Arecibo%20Region%20Repairs%20(Building).pdf?web=1 | 4/3/2024 - Received withdrawal status data/info from Deputy Project Manager Gerardo Medina-Sonera. This project will be included in the new Island Wide ISOW approach. | 45877.578 | 45152.4653 | Jahdiel Franqui | Arecibo Region Repairs | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 548393RFI294 | 548393 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
547350 | 11854 | FAASt [Line 13300 Bayamon TC to Plaza del Sol] (Transmission) | 14F002460000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 5390000 | 44438 | 44461 |  | 44468 |  |  |  | 44517 | 11/17/2021 | 45382 |  |  | 45642 | 45628 |  |  | 5390000 | 5390000 | [5 empty] | 0 | 5390000 | 5390000 | [11 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/295/547350%20-%20DR4339PR%20-%20%20FAASt%20-%20Line%2013300%20Bayam%C3%B3n%20TC%20to%20Plaza%20del%20Sol%20(Transmission)%20FEMA%20SOW%20CE.pdf?web=1 |  | 45889.4989 | 45152.4653 | Jahdiel Franqui | Line 13300 Bayamon TC to Plaza del Sol | Marlina Crespo |  |  |  |  | 1 | 1 | 45887 | 547350RFI295 | 547350 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
547344 | 107702 | FAASt [Acacias 6801 TC Relocation] (Substation) | 14F003120000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | FALSE |  | 29100000 | 44473 | 44487 |  | 44503 |  |  |  | 44517 | 11/17/2021 | 45291 | 45359 | [5 empty] | 29100000 | 29100000 | 42895135.02 | 677999.83 |  | 8196442.68 | 3277151.71 | 39617983.31 | 51091577.7 | 51769577.53 | 45961 | 46112 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/296/921982-DR4339PR-10115-EN-SOW-0001_Rev0%20-%20Acacias%206801%20TC%20Relocation.pdf?web=1 | 2/28/2024: QC Review Complete | 46077.5737 | 45152.4653 | Jahdiel Franqui | Acacias 6801 TC Relocation | Ashleah Dingle |  |  |  |  | 0.56957 | 3 | 45884 | 547344RFI296 | 547344 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
547343 | 107701 | FAASt [Victoria TC 7008 Relocation] (Substation) | 14F003160000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | FALSE |  | 5500000 | 44473 | 44487 |  | 44503 |  |  |  | 44517 | 11/17/2021 | 45291 | 45472 | [5 empty] | 5500000 | 5500000 | 54844288.98 | 606808.32 |  | 6239636.58 | 4859932.94 | 49984356.04 | 61083925.56 | 61690733.88 | [11 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/297/921981-DR4339PR-10119-EN-SOW-0001_Rev0%20-%20Victoria%20TC%207008.pdf?web=1 |  | 46077.5736 | 45152.4653 | Jahdiel Franqui | Victoria TC 7008 | Ashleah Dingle |  |  |  |  | 0.09004 | 5 | 45884 | 547343RFI297 | 547343 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
547342 | 107700 | FAASt [Line 1500 Mayaguez GP to GOAB 1515] (Transmission) | 14F002490000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 58610000 | [7 empty] | 44517 | 11/17/2021 | [7 empty] | 58610000 | 58610000 | [5 empty] | 0 | 58610000 | 58610000 | [11 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/298/921980-DR4339PR-10088-EN-SOW-0001_Rev0%20Line%201500%20Mayaguez%20GP%20to%20GOAB%201515.pdf?web=1 | 9/12/2024 - GP Notes "The project was withdrawn with the comment "Project is being withdrawn since it was not included in the Applicant’s latest workplan for submittal of a SOW. FEMA may in the future re-create the project at the request of the Applicant and COR3 if a SOW submittal date is provided." | 45877.578 | 45152.4653 | Jahdiel Franqui | Line 1500 Mayaguez GP to GOAB 1515 | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 547342RFI298 | 547342 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
547273 | 107699 | FAASt Charco Hondo Substation 8008 Relocation (Substation) | 14F001900000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 16300000 | 44473 | 44487 |  | 44503 |  |  |  | 44516 | 11/16/2021 | [7 empty] | 16300000 | 16300000 | [5 empty] | 0 | 16300000 | 16300000 | [11 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/299/547273%20DR4339PR%20Charco%20Hondo%208008%20Relocation%20SOW%20and%20Cost%20Estimate%20(1).pdf?web=1 |  | 45887.6074 | 45152.4653 | Jahdiel Franqui | Charco Hondo 8008 Relocation | Maria Mujica Gonzalez |  |  |  |  | 1 | 1 | 45884 | 547273RFI299 | 547273 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
547271 | 107698 | FAASt San Jose Substation 8104 Relocation (Substation) | 14F001920000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active |  |  | 17000000 |  |  | 45534 |  |  |  |  | 44516 | 11/16/2021 | [7 empty] | 17000000 | 17000000 | [5 empty] | 0 | 17000000 | 17000000 | [11 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/300/921686%20DR4339PR-%20San%20Jose%20Relocation%20SOW%20and%20Cost%20Estimate.pdf?web=1 | 4/2/2024 - Received withdrawal status data/info from Manager Yadira L. Lugo Cordero. Pending Task Order signature to complete Preliminary Engineering. | 45877.578 | 45152.4653 | Jahdiel Franqui | San Jose Relocation | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 547271RFI300 | 547271 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
547269 | 11481 | FAASt Line 2800 (38 kV) Aguadilla Hospital Distrito Sect to T-Bone TO (Transmission) | 14F002430000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 3140000 | 44438 | 44461 |  | 44468 |  |  |  | 44516 | 11/16/2021 | 45107 | 45107 | 45407 |  |  |  |  | 3140000 | 0 | 11466633 | 3954335 |  | 32159582 | 1250116 | 10216517 | 43626215 | 47580550 | 45596 | 45747 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/301/Revised%20FEMA%20SOW%20-%20547269-DR4339PR-TL2800%20DSOW-38kv%20Aguadilla%20Hosp.%20Dist.%20Sect.%20to%20T-Bone%20TO-Rev%200%20-%20signed%20(1).pdf?web=1 | 3/26/2024 - EHP Phase I, II Analyses data received from Grid Strategy and inserted in tracker for affected TLine 2800 | 45889.4989 | 45152.4653 | Jahdiel Franqui | Line 2800 Aguadilla Hospital Distrito Sect to T-Bone TO | Marlina Crespo |  |  |  |  | 0 | 5 | 45887 | 547269RFI301 | 547269 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
547259 | 11480 | FAASt Line 2700 (38kV) Victoria TC to Quebradillas Sect. (Transmission) | 14F002420000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 41270000 | 44438 | 44461 |  | 44468 |  |  |  | 44516 | 11/16/2021 | 45107 | 45107 | 45303 |  |  |  |  | 41270000 | 0 | 55843908 | 6838079 |  | 64136647 | 5366230 | 50477678 | 119980555 | 126818634 | 45596 | 45747 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/302/Revised%20FEMA%20SOW%20-%20547259-DR4339PR-TL2700%20DSOW-38%20kV%20Victoria%20TC%20to%20Quebradillas%20Sect-%20Rev%200.pdf%20-%20signed%20(1).pdf?web=1 | 3/26/2024 - EHP Phase I, II Analyses data received from Grid Strategy and inserted in tracker for affected TLine 2700 | 45888.4844 | 45152.4653 | Jahdiel Franqui | Line 2700 Victoria TC to Quebradillas Sect. | Maria Mujica Gonzalez |  |  |  |  | 0 | 5 | 45887 | 547259RFI302 | 547259 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
547251 | 11807 | FAASt Line 2400 Dos Bocas HP to America Apparel (Transmission) | 14F002480000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild |  |  | TRUE | 45869 | Current |  |  |  |  | 45495 | 54600000 | 45504 | 45526 |  | 45534 |  |  |  | 44516 | 11/16/2021 | 45382 | 45839 |  | 46031 | 46021 | 12/30/2025 - Field EHP: In review. Expected Completion Date (ECD) 1/9/2026 |  | 21470000 | 21470000 |  | 433482.47 |  | 6482242.86 |  | 0 | 6482242.86 | 6915725.33 |  |  | 46073 |  | 50289473.68 | 50289473.68 |  |  |  | 975659.88 |  | 50289473.68 | 50289473.68 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/303/921824-DR4339PR-10087-EN-SOW-0001_Rev0%20-%20Line%202400%20Dos%20Bocas%20HP%20to%20America%20Apparel.pdf?web=1 | 3/26/2024 - EHP Phase I, II Analyses data received from Grid Strategy and inserted in tracker for affected TLine 2400 8/8/2025 - Field EHP: In review. Expected Completion Date (ECD) 8/22/2025. 8/12/2025 8:23 AM AST - The PR Electric Power Authority, as the eligible entity (subrecipient), has submitted a consolidated plan for the use of the remaining budget available in the FEMA Accelerated Awards Strategy Project (136271) Fixed Cost Award. This FAASt sub-project has been identified in the list and it will be processed in the national workflow accordingly. | 46076.4159 | 45152.4653 | Jahdiel Franqui | Line 2400 Dos Bocas HP to America Apparel | Ashleah Dingle | 0 Months |  | 3753435.29 |  | 3.3121 | 1 |  | 547251RFI303 | 547251 | 8180.36 | 0 | 8180.36 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
547248 | 107695 | FAASt Canas TC 5002 5018 (Substation) | 14F002940000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active |  |  | 1700000 | [7 empty] | 44516 | 11/16/2021 | [7 empty] | 1700000 | 1700000 | [5 empty] | 0 | 1700000 | 1700000 | [11 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/304/921822-DR4339PR-10109-EN-SOW-0001_Rev0%20-%20Canas%20TC.pdf?web=1 | 4/2/2024 - Received withdrawal status data/info from Manager Yadira L. Lugo Cordero. Working with Planning and Engineering to complete assessments to define scope and start the Preliminary Engineering. | 45877.5781 | 45152.4653 | Jahdiel Franqui | Canas TC | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 547248RFI304 | 547248 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
547247 | 107694 | FAASt Cambalache TC Relocation (Substation) | 14F003130000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | TRUE |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | FALSE | 45568 | 30700000 | 44473 | 44487 |  | 44503 |  |  |  | 44516 | 11/16/2021 | 45382 | 45504 | [5 empty] | 30700000 | 30700000 | 84733286.06 | 319703.09 |  | 5143802.81 | 2090449.36 | 82642836.7 | 89877088.87 | 90196791.96 | [11 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/305/921812-DR4339PR-10116-EN-SOW-0001_Rev0%20-%20Cambalache%20TC%20Relocation.pdf?web=1 |  | 46077.5736 | 45152.4653 | Jahdiel Franqui | Cambalache TC Relocation | Ashleah Dingle | 0 Months |  |  |  | 0.34158 | 4 | 45884 | 547247RFI305 | 547247 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
547243 | 107693 | FAASt Egozcue - 1109 (Substation) | 14F001820000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | FALSE |  | 10500000 | 44473 | 44487 |  | 44503 |  |  |  | 44516 | 11/16/2021 | 45107 | 45107 | 45331 |  |  |  |  | 10500000 | 21850323 | 6952342.26 | 1400260.82 |  | 12496184.94 | 700164.05 | 6252178.21 | 19448527.2 | 20848788.02 | 45626 | 45808 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/306/547243-DR4339PR%20-%20FEMA%20Detailed%20Scope%20of%20Work%20for%20Egozcue%201109%20-%20signed%20(1).pdf?web=1 |  | 46077.5733 | 45152.4653 | Jahdiel Franqui | Egozcue - 1109 | Ashleah Dingle |  |  |  |  | 1.1235 | 1 | 45884 | 547243RFI306 | 547243 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
547241 | 11448 | FAASt Tallaboa 5402 (Substation) | 14F001940000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | FALSE |  | 6900000 | 44473 | 44487 |  | 44503 |  |  |  | 44516 | 11/16/2021 | 45107 | 45107 | [5 empty] | 6900000 | 0 | 5628609 | 1268607 |  | 9655829 | 653626 | 4974983 | 15284438 | 16553045 | 45657 | 45808 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/307/547241-DR4339PR%20-%20FEMA%20Detailed%20Scope%20of%20Work%20for%20Tallaboa%205402%20Substation%20-%20signed%20(1).pdf?web=1 |  | 46077.5733 | 45152.4653 | Jahdiel Franqui | Tallaboa 5402 | Ashleah Dingle |  |  |  |  | 0 | 5 | 45887 | 547241RFI307 | 547241 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
547226 | 11689 | FAASt Barceloneta 11400 TC to Florida TO (Transmission) | 14F002680000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 13810000 | 44473 | 44487 |  | 44503 |  |  |  | 44516 | 11/16/2021 | 45382 | [6 empty] | 13810000 | 13810000 | [5 empty] | 0 | 13810000 | 13810000 | [11 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/308/547226%20DR4339PR%20Line%2011400%20Barceloneta%20TC%20to%20Florida%20TO.pdf?web=1 |  | 45888.4828 | 45152.4653 | Jahdiel Franqui | Line 11400 Barceloneta TC to Florida TO | Maria Mujica Gonzalez |  |  |  |  | 1 | 1 | 45887 | 547226RFI308 | 547226 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
547221 | 107692 | FAASt [Line 3600 Monacillos TC to Martin Peña TC] (Transmission) | 14F002450000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active |  |  | 39980000 |  |  | 45544 |  |  |  |  | 44516 | 11/16/2021 | [7 empty] | 39980000 | 39980000 | [5 empty] | 0 | 39980000 | 39980000 | [11 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/309/547221%20-%20DR4339PR%20%20Line%203600%20Monacillos%20TC%20to%20Martin%20Pe%C3%B1a%20TC%20(Transmission).pdf?web=1 | 3/28/2024 - Received withdrawal status data/info from Project Manager Claudio R. Jaquez. DSOW submittal forecast: 9/9/2024. | 45877.5781 | 45152.4653 | Jahdiel Franqui | Line 3600 Monacillos TC to Martin Peña TC | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 547221RFI309 | 547221 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
547187 | 107690 | FAASt - [Substation Component Replacement Program] (Substation) | 14F001880000, 14F020180000, 14F020090000, 14F020120000, 14F020130000, 14F020190000 | PBUT07 - Substation Reliability | Substation | Substation Rebuilds | TRUE |  | FALSE |  | Current | [5 empty] | 17100000 | 44473 | 44487 |  | 44503 |  |  |  | 44516 | 11/15/2021 | 45322 | 45726 | [5 empty] | 17100000 | 330300000 | 308929.24 | 2069220.14 |  | 6551618.4 | 66626.67 | 242302.57 | 6860547.64 | 8929767.78 | [11 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/310/547187%20DR4339PR%20Arecibo%20Pueblo%208002%20Relocation%20SOW%20(1).pdf?web=1 |  | 46078.6072 | 45152.4653 | Jahdiel Franqui | Arecibo Pueblo 8002 Relocation | Ashleah Dingle |  |  |  |  | 48.1448 | 1 |  | 547187RFI310 | 547187 | 2233992.76 | 99234.74 | 2333227.5 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
547160 | 107689 | FAASt [Line 1200 Mayaguez GP to Yauco 2 HP] (Transmission) | 14F002370000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 55370000 | 44473 | 44487 |  | 44503 |  |  |  | 44515 | 11/15/2021 | [7 empty] | 55370000 | 55370000 | [5 empty] | 0 | 55370000 | 55370000 | [11 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/311/921046-DR4339PR-10076-EN-SOW-0001_Rev0%20-%20Line%201200%20Mayaguez%20GP%20to%20Yauco%202%20HP.pdf?web=1 |  | 45888.4771 | 45152.4653 | Jahdiel Franqui | Line 1200 Mayaguez GP to Yauco 2 HP | Maria Mujica Gonzalez |  |  |  |  | 1 | 1 | 45887 | 547160RFI311 | 547160 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
546386 | 107558 | FAASt [Feeders- El Yunque 2305 - Supply] (Distribution) | 14F003490000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild | Distribution Line Rebuild |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | FALSE |  | 14600000 | 44438 | 44461 |  | 44468 |  |  |  | 44509 | 11/9/2021 | 45199 | 45201 | [5 empty] | 14600000 | 28991235 | 23252037 | 825193 |  | 5739198 | 2922954 | 20329083 | 28991235 | 29816428 | 45869 | 46022 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/312/546386-DR4339PR-10156-EN-SOW-0001_Rev0%20(El%20Yunque%202305-01%20Supply).pdf?web=1 |  | 46077.5733 | 45152.4653 | Jahdiel Franqui | El Yunque 2305-01 Supply | Ashleah Dingle |  |  |  |  | 1 | 1 | 45884 | 546386RFI312 | 546386 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
546374 | 107556 | FAASt [Feeders - 1620-02 - San Juan Short Term Group 3] (Distribution) | 14F001590000, 14F001580000, 14F001560000, 14F001570000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild | Distribution Line Rebuild |  | Restoration | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | FALSE |  | 27280000 | 44438 | 44461 |  | 44468 |  |  |  | 44509 | 11/9/2021 | 45169 | 45169 | 45260 |  |  |  |  | 27280000 | 38107125 | 12777559 | 2091400 |  | 18966760 | 1260325 | 11517234 | 31744319 | 33835719 | 45808 | 45961 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/313/546374-DR4339PR%20-10143-EN-SOW-0001_Rev0%20(Distribution%20Feeders-San%20Juan%20Short%20Term%20Group%203).pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 46077.5733 | 45152.4653 | Jahdiel Franqui | Distribution Feeders - San Juan Short Term Group 3 | Ashleah Dingle | 0 Months |  |  |  | 1.2004 | 1 | 45884 | 546374RFI313 | 546374 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
546371 | 11478 | FAASt- Substation Minor Repairs Group C (Substation) | 14F003030000, 14F003060000, 14F003050000, 14F003040000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds |  | Restoration | FALSE | [15 empty] | 44509 | 11/9/2021 | 44742 | 44729 | 45104 |  |  |  |  | 1600000 | 3032891.2 | 384632.14 | 646473 |  | 2648259 | 25197.64 | 359434.5 | 3032891.14 | 3679364.14 |  |  | 45160 |  | 3032891.2 | 2648259.06 | [5 empty] | 3032891.2 | 2648259.06 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/314/546371-DR4339PR-00%20FEMA%20DSOW%20for%20Sub.%20Minor%20Repairs%20-Group%20C%20(43001-CP-SOW-0009_Rev7)%20(2023-06-26)%20-%20signed.pdf |  | 45862.616 | 45152.4653 | Jahdiel Franqui | Substation Minor Repairs | Jose J Ramos Figueroa |  |  | 173985.91 |  | 1 | 1 |  | 546371RFI314 | 546371 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 384632.14
546370 | 10858 | FAASt - Substation Minor Repairs Group A (Substation) | 14F002840000, 14F002830000, 14F002870000, 14F002860000, 14F002880000, 14F002850000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds |  | Restoration | FALSE | [7 empty] | 400000000 | [7 empty] | 44509 | 11/9/2021 |  | 44712 | 45216 |  |  |  |  | 2400000 | 4971175.09 | 488203 | 996359 |  | 4482973 | 0 | 488203 | 4971176 | 5967535 |  |  | 45335 | 8/30/2024 | 4971175.09 | 4482972.51 | 4971175.09 | 4482972.51 |  |  |  | 4971175.09 | 4482972.51 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/315/546370~1.PDF?web=1 |  | 46070.5089 | 45152.4653 | Jahdiel Franqui | Substation Minor Repairs | Marlina Crespo |  |  | 996359.11 |  | 1 | 1 |  | 546370RFI315 | 546370 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 488202.58
542762 | 10690 | FAASt Distribution Pole and Conductor Repair – Arecibo Group 2 (Distribution) | 14F003940000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44495 | 10/26/2021 | 44592 | 44589 | 44694 |  |  |  |  | 3000000 | 767868 | 157420 |  |  | 661242 | 0 | 157420 | 818662 | 818662 |  |  | 44715.4743 | 8/30/2024 | 767868 | 610448 | 767868 | 610448 |  |  |  | 767868 | 610448 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/316/Revised%20FEMA%20SOW%20-%20542762-DR4339PR-Detalied%20SOW%20Arecibo%20Group%202%20Rev1.pdf?web=1 |  | 46070.4872 | 45152.4653 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Marlina Crespo |  |  | 50794 |  | 0.93795 | 1 |  | 542762RFI316 | 542762 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 157420
542758 | 11385 | FAASt [Minor Repairs -Group B] (Substation) | 14F002950000, 14F002970000, 14F002980000, 14F002960000, 14F002990000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds |  | Restoration | FALSE | [7 empty] | 400000000 | 44438 | 44461 |  | 44468 |  |  |  | 44495 | 10/26/2021 | 44773 | 44753 | 45050 |  |  |  |  | 2000000 | 3412576 | 439541 | 723314 |  | 2973035 | 27113 | 412428 | 3412576 | 4135890 |  |  | 45114 |  | 3412576 | 2973035 | [5 empty] | 3412576 | 2973035 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/317/Revised%20FEMA%20SOW%20-%20542758-DR4339PR-%200%20FEMA%20DSOW%20Group%20B%20Minor%20Repairs%20(43001-CP-SOW-0012_Rev5)%20(2023-05-03)%20-%20signed.pdf?web=1 |  | 45908.5579 | 45152.4653 | Jahdiel Franqui | Substation Minor Repairs | Ashleah Dingle |  |  | 152806 | 14467 | 1 | 1 |  | 542758RFI317 | 542758 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 425074
542756 | 10538 | FAASt [Guánica Streetlighting] (Distribution) | 14F003710000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE | [15 empty] | 44495 | 10/26/2021 | 44651 | 44628 | 44658 |  |  |  |  | 6757365 | 10058046 | 370808 | 2237386 |  | 9687238 | 0 | 370808 | 10058046 | 12295432 |  |  | 44707 |  | 10058046 | 9687238 | [5 empty] | 10058046 | 9687238 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/318/4.18.22%20%20%20PW%20542756%20%20%20Revised%20FEMA%20SOW.pdf?web=1 |  | 45862.6227 | 45152.4654 | Jahdiel Franqui | Distribution Streetlighting | Jose J Ramos Figueroa |  |  | 2237386 |  | 1 | 1 |  | 542756RFI318 | 542756 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 370808
542690 | 10499 | FAASt [Maunabo Streetlighting] (Distribution) | 14F003680000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE | [15 empty] | 44497 | 10/26/2021 | 44620 | 44596 | 44658 |  |  |  |  | 4821725 | 6443757.4 | 243880.33 | 1530438 |  | 6199878 | 243880.33 | 0 | 6443758.33 | 7974196.33 |  |  | 44686.4715 |  | 6443757.4 | 6199877.07 | [5 empty] | 6443757.4 | 6199877.07 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/319/Revised%20FEMA%20SOW%20-%20542690-DR4339PR-Detailed%20SOW%20Maunabo%20Rev0%20-%20signed%20-%20DSOW.pdf?web=1 |  | 45856.7693 | 45152.4654 | Jahdiel Franqui | Distribution Streetlighting | Rey Roldan Rodríguez |  |  | 1530438.49 |  | 1 | 1 |  | 542690RFI319 | 542690 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 243880.33
542688 | 10539 | FAASt [Aguada Streetlighting] (Distribution) | 14F003630000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE | [15 empty] | 44495 | 10/26/2021 | 44651 | 44628 | 44659 |  |  |  |  | 12580635 | 18571716.38 | 807222 | 4104786 |  | 17764494 | 0 | 807222 | 18571716 | 22676502 |  |  | 44686 | 8/30/2024 | 18571716.38 | 17764494.34 | 18571716.38 | 17764494.34 |  |  |  | 18571716.38 | 17764494.34 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/320/Detailed%20SOW-542688.pdf?web=1 |  | 46070.4829 | 45152.4654 | Jahdiel Franqui | Distribution Streetlighting | Marlina Crespo |  |  | 4104785.76 |  | 1 | 1 |  | 542688RFI320 | 542688 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 807222.04
542687 | 10521 | FAASt [Lajas Streetlighting] (Distribution) | 14F003700000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE | [15 empty] | 44495 | 10/26/2021 | 44651 | 44628 | 44662 |  |  |  |  | 9453361 | 10704668.57 | 426332 | 2512854 |  | 10278336 | 0 | 426332 | 10704668 | 13217522 |  |  | 44701 | 8/30/2024 | 10704668.57 | 10278336.09 | 10704668.57 | 10278336.09 |  |  |  | 10704668.57 | 10278336.09 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/321/Revised%20FEMA%20SOW%20542687.pdf?web=1 |  | 46070.4823 | 45152.4654 | Jahdiel Franqui | Distribution Streetlighting | Marlina Crespo |  |  | 2512853.73 |  | 1 | 1 |  | 542687RFI321 | 542687 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 426332.48
542517 | 10515 | FAASt [Luquillo Streetlighting] (Distribution) | 14F003690000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE | [7 empty] | 1220000000 | 44438 | 44461 |  | 44468 |  |  |  | 44494 | 10/25/2021 | 44651 | 44628 | 44662 |  |  |  |  | 6346527 | 8810325.37 | 181658.08 | 2004233 |  | 8628668 | 0 | 181658.08 | 8810326.08 | 10814559.08 |  |  | 44701 | 8/30/2024 | 8810325.37 | 8628667.29 | 8810325.37 | 8628667.29 |  |  |  | 8810325.37 | 8628667.29 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/322/542517-10515%20Luquillo%20Streetlights%20Detailed%20SOW%20Rev.3.pdf?web=1 |  | 46070.4817 | 45152.4654 | Jahdiel Franqui | Distribution Streetlighting | Marlina Crespo |  |  | 2004233.23 |  | 1 | 1 |  | 542517RFI322 | 542517 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 181658.08
436616 | 107551 | FAASt [Feeders - Arecibo Short Term Group 1] (Distribution) | 14F000040000, 14F000050000, 14F000080000, 14F000060000, 14F000070000, 14F000090000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild | Distribution Line Rebuild |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | FALSE |  | 53580000 | 44385 | 44428 |  | 44415 |  |  |  | 44481 | 10/12/2021 | 45199 | 45170 | 45271 |  |  |  |  | 53580000 | 51555365 | 14494388 | 2468970 |  | 24725318 | 1315945 | 13178443 | 39219706 | 41688676 | 45808 | 45961 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/323/436616-%20DR4339PR-%20DSOW%20-Arecibo%20Short%20Term%20Group%201.pdf?web=1 |  | 46077.5733 | 45152.4654 | Jahdiel Franqui | Distribution Feeders ‐ Arecibo Short Term Group 1 | Ashleah Dingle |  |  |  |  | 1.3145 | 1 | 45884 | 436616RFI323 | 436616 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
435257 | 107545 | FAASt [Line 3000 Monacillos TC - Bairoa TO] (Transmission) | 14F017370000 | PBUT13 - T Priority Pole Repl | Transmission | Transmission Priority Pole Replacements | [5 empty] | TRUE | Voluntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 44468 | 9/29/2021 | 45291 | [6 empty] | 924000 | 924000 | [5 empty] | 0 | 924000 | 924000 | [11 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/324/FEMA%20Scope%20of%20Work%20Line%203000%20Monacillos%20TC%20-%20Bairoa%20TO.DOC%20(1).pdf?web=1 | 9/12/2024 - GP Notes "The project was withdrawn with the comment "8/15/2024 - Applicant requested to withdraw the reference project. Please see document with the naming convention "435257-DR4339PR-Withdrawn Confirmation.msg"". | 45877.5781 | 45152.4654 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 435257RFI324 | 435257 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
335168 | 9510 | FAASt A&E PREPA | 14F001650000 | PBFM03 - Financial Mgmt Functions | Other | TBD | [19 empty] | 9/21/2021 | [8 empty] | 1086406842.43 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 44476.4854 | 06/21/2023 | 1086406842.43 |  | 486406842.43 | 486406842.43 | 1058513052.43 |  | 1058513052.43 | 1058513052.43 | 1058513052.43 | 46650 |  |  | 45919.499 | 45152.4654 | Jahdiel Franqui |  | Gabriel Licha |  |  | 0 |  |  |  |  | 335168RFI325 | 335168 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
334527 | 10701 | FAASt [Distribution Pole and Conductor Repair – Caguas Group 8 (Distribution) | 14F004050000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44449 | 9/10/2021 | 44620 | 44600 | 44705 | [5 empty] | 123721 | 14874 |  |  | 102513 | 0 | 14874 | 117387 | 117387 |  |  | 44722.4917 | 8/30/2024 | 123721 | 108847 | 123721 | 108847 |  |  |  | 123721 | 108847 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/326/Revised%20FEMA%20SOW%20-%20334527-DR4339PR-Detalied%20SOW%20Caguas%20Group%208%20Rev3.pdf?web=1 |  | 46070.4812 | 45152.4654 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Marlina Crespo |  |  | 8540 |  | 1.054 | 1 |  | 334527RFI326 | 334527 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 14874
334518 | 107532 | FAASt [Feeders - Caguas Short Term Group 7] (Distribution) | 14F000580000, 14F000650000, 14F000530000, 14F000770000, 14F000540000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild | Distribution Line Rebuild |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 49180000 | 44385 | 44428 |  | 44415 |  |  |  | 44449 | 9/10/2021 | 45199 | 45170 | 45260 |  |  |  |  | 49180000 | 36582202 | 7784267 | 1942279 |  | 10283602 | 1224114 | 6560153 | 18067869 | 20010148 | 45626 | 45808 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/327/334518%20-%20DR4339PR%20-%20Distribution%20Feeders%20-%20Caguas%20Short%20Term%20Group%207.pdf?web=1 |  | 45887.6345 | 45152.4654 | Jahdiel Franqui | Distribution Feeders ‐ Caguas Short Term Group 7 | Ashleah Dingle |  |  |  |  | 2.0247 | 1 | 45884 | 334518RFI327 | 334518 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
334497 | 107531 | FAASt [Feeders - Caguas Short Term Group 6 (Distribution) | 14F000460000, 14F000660000, 14F000380000, 14F000640000, 14F000450000, 14F000470000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild | Distribution Line Rebuild |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 76650000 | 44385 | 44428 |  | 44415 |  |  |  | 44449 | 9/10/2021 | 45199 | 45170 | [5 empty] | 72650000 | 83151265 | 22180767 | 6980220 |  | 60970498 | 2278513 | 19902254 | 83151265 | 90131485 | 45626 | 45808 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/328/334497-DR4339PR-%20DSWOR-%20Caguas%20Short%20Term%20Group%206-Signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 45887.6343 | 45152.4654 | Jahdiel Franqui | Distribution Feeders ‐ Caguas Short Term Group 6 | Ashleah Dingle |  |  |  |  | 1 | 1 | 45884 | 334497RFI328 | 334497 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
334491 | 107530 | FAASt [Feeders - Caguas Short Term Group 5] (Distribution) | 14F000420000, 14F000390000, 14F000600000, 14F000750000, 14F000730000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild | Distribution Line Rebuild |  | Restoration | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 72350000 | 44385 | 44428 |  | 44415 |  |  |  | 44449 | 9/10/2021 | 45199 | 45170 | 45260 |  |  |  |  | 72350000 | 38058553 | 13582684 | 3119148 |  | 16427785 | 2165073 | 11417611 | 30010469 | 33129617 | 45688 | 45869 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/329/334491-DR4339PR-10149-Caguas%20Short%20Term%20Group%205%20%20DSOW%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 45889.4902 | 45152.4654 | Jahdiel Franqui | Distribution Feeders ‐ Caguas Short Term Group 5 | Maria Mujica Gonzalez | 0 Months |  |  |  | 1.2682 | 1 | 45888 | 334491RFI329 | 334491 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
334488 | 10635 | FAASt [Distribution Pole and Conductor Repair – Caguas Group 4 (Distribution) | 14F004010000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44449 | 9/10/2021 | 44620 | 44596 | 44690 |  |  |  |  | 44710000 | 153743 | 10826 | 19965 |  | 134417 | 0 | 10826 | 145243 | 165208 |  |  | 44707 | 8/30/2024 | 153743 | 142917 | 153743 | 142917 |  |  |  | 153743 | 142917 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/330/10148-EN-SOW-0001_Rev0%20-%20FEMA%20SOW%20Distribution%20Feeders%20-%20Caguas%20Short%20Term%20Group%204%20Signed%20-%20Copy.pdf?web=1 |  | 46070.4806 | 45152.4654 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Marlina Crespo |  |  | 11465 |  | 1.0585 | 1 |  | 334488RFI330 | 334488 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 10826
334482 | 11450 | FAASt [Line 3000 (38 kV) Monacillos TC to Juncos TC] (Transmission) | 14F002440000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 90440000 | [7 empty] | 44453 | 9/10/2021 | [7 empty] | 90440000 | 0 | [5 empty] | 0 | 90440000 | 90440000 | [11 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/331/334482-DR4339PR-10083-EN-SOW-0001_Rev0%20-%20FEMA%20SOW%20Line%203000%20Monacillos%20TC%20to%20Juncos%20TC%20Signed%20-%20Copy.pdf?web=1 | 9/12/2024 - GP notes "6/25/2024 The project was withdrawn with the comment "Project is being withdrawn since it was not included in the Applicant’s latest workplan for submittal of a SOW. FEMA may in the future re-create the project at the request of the Applicant and COR3 if a SOW submittal date is provided." | 45877.5781 | 45152.4654 | Jahdiel Franqui | Line 3000 Monacillos TC to Juncos TC | Ashleah Dingle |  |  |  |  | 0 | 5 |  | 334482RFI331 | 334482 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
334477 | 107529 | FAASt [Feeders - 2402-02 - Carolina Short Term Group 3] (Distribution) | 14F000860000, 14F000890000, 14F000870000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild | Distribution Line Rebuild |  | Restoration | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 60760000 | 44385 | 44428 |  | 44415 |  |  |  | 44453 | 9/10/2021 | 45199 | 45170 | 45260 |  |  |  |  | 60760000 | 39416251 | 23907802 | 2623895 |  | 20298233 | 2736726 | 21171076 | 44206035 | 46829930 | 45869 | 46022 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/332/334477-DR4339PR-10137-Carolina%20Short%20Term%20Group%203%20DSOW%20-%20signed.pdf?web=1 |  | 45889.4866 | 45152.4654 | Jahdiel Franqui | Distribution Feeders ‐ Carolina Short Term Group 3 | Maria Mujica Gonzalez | 0 Months |  |  |  | 0.89165 | 1 | 45888 | 334477RFI332 | 334477 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
334476 | 107528 | FAASt [Feeders - Carolina Short Term Group 2] (Distribution) | 14F000840000, 14F000820000, 14F000830000, 14F000810000, 14F000850000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild | Distribution Line Rebuild |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | FALSE |  | 40500000 | 44385 | 44428 |  | 44415 |  |  |  | 44454 | 9/10/2021 | 45260 | 45260 | [5 empty] | 40500000 | 40500000 | 18767542 | 4031089 |  | 14254294 | 3637670 | 15129872 | 33021836 | 37052925 | 45838 | 45991 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/333/334476-DR4339PR-10010-EN-SOW-0001_Rev0%20-%20FEMA%20SOW%20Distribution%20Feeders%20-%20Carolina%20Short%20Term%20Group%202%20Signed.pdf?web=1 |  | 46077.5733 | 45152.4654 | Jahdiel Franqui | Distribution Feeders ‐ Carolina Short Term Group 2 | Ashleah Dingle |  |  |  |  | 1.2265 | 1 | 45888 | 334476RFI333 | 334476 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
334475 | 107527 | FAASt [Feeders - Bayamon Short Term Group 3] (Distribution) | 14F000250000, 14F000240000, 14F000290000, 14F000280000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild | Distribution Line Rebuild |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 65680000 | 44385 | 44428 |  | 44415 |  |  |  | 44454 | 9/10/2021 | 45199 | 45170 | 45260 |  |  |  |  | 65680000 | 67962252 | 17884283 | 4579075 |  | 45856819 | 1623714 | 16260569 | 63741102 | 68320177 | 45838 | 45991 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/334/334475-DR4339PR-%20DSOW%20Bayamon%20Short%20Term%20Group%203_.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 45889.4741 | 45152.4654 | Jahdiel Franqui | Distribution Feeders ‐ Bayamon Short Term Group 3 | Maria Mujica Gonzalez |  |  |  |  | 1.0662 | 1 | 45888 | 334475RFI334 | 334475 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
334474 | 107526 | FAASt [Feeders - Bayamon Short Term Group 2] (Distribution) | 14F000320000, 14F000330000, 14F000310000, 14F000340000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild | Distribution Line Rebuild |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 10350000 | 44385 | 44428 |  | 44415 |  |  |  | 44454 | 9/10/2021 | 45138 | 45108 | 45260 |  |  |  |  | 40500000 | 4337037 | 659178 | 384975 |  | 804315 | 213377 | 445801 | 1463493 | 1848468 | 45838 | 45991 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/335/Revised%20FEMA%20SOW%20-%20334474-DR4339PR-%20DSOW%2010136-BAYAMONN%20STG2%20-%20signed%20(1).pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 45889.4705 | 45152.4654 | Jahdiel Franqui | Distribution Feeders ‐ Bayamon Short Term Group 2 | Maria Mujica Gonzalez |  |  |  |  | 2.9635 | 1 | 45888 | 334474RFI335 | 334474 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
334473 | 107525 | FAASt [Feeders - 1806-02- Bayamon Short Term Group 1] (Distribution) | 14F000230000, 14F000180000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild | Distribution Line Rebuild |  | Restoration | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 85000000 | 44385 | 44428 |  | 44415 |  |  |  | 44454 | 9/10/2021 | 45199 | 45198 | 45847 |  |  |  |  | 85000000 | 61103928 | 1173247.16 | 1298493.93 |  | 16234566.74 | 135257.91 | 1037989.25 | 17407813.9 | 18706307.83 | 45777 | 45961 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/336/334473-DR4339PR-10008-EN-SOW-0001_Rev0%20-%20FEMA%20SOW%20Distribution%20Feeders%20-%20Bayamon%20Short%20Term%20Group%201%20Signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 45981.543 | 45152.4654 | Jahdiel Franqui | Distribution Feeders ‐ Bayamon Short Term Group 1 | Marlina Crespo |  |  |  |  | 3.5101 | 1 | 45884 | 334473RFI336 | 334473 | 1060714.92 | 202401.99 | 1263116.91 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
334472 | 107524 | FAASt [Feeders - San Juan Short Term Group 2] (Distribution) | 14F001550000, 14F001520000, 14F001510000, 14F001530000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild | Distribution Line Rebuild |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | FALSE |  | 10560000 | 44385 | 44428 |  | 44415 |  |  |  | 44455 | 9/10/2021 | 45199 | 45170 | 45266 |  |  |  |  | 10560000 | 27652844 | 5366655 | 3690321 |  | 15093429 | 1052352 | 4314303 | 20460084 | 24150405 | 45838 | 45991 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/337/334472-DR4339PR-DSOW-%20San%20Juan%20Short%20Term%20Group%202.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 46077.5732 | 45152.4654 | Jahdiel Franqui | Distribution Feeders ‐ San Juan Short Term Group 2 | Ashleah Dingle |  |  |  |  | 1.3516 | 1 | 45884 | 334472RFI337 | 334472 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
334471 | 107523 | FAASt [Feeders -1303-01- San Juan Short Term Group 1] (Distribution) | 14F001450000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild | Distribution Line Rebuild |  | Restoration | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 40690000 | 44385 | 44428 |  | 44415 |  |  |  | 44455 | 9/10/2021 | 45199 | 45198 | [5 empty] | 40690000 | 62894812 | 26997816 | 7053158 |  | 35896996 | 4433509 | 22564307 | 62894812 | 69947970 | 45838 | 45991 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/338/334471-DR4339PR-10013-EN-SOW-0001_Rev0%20-%20FEMA%20SOW%20Distribution%20Feeders%20-%20San%20Juan%20Short%20Term%20Group%201%20Signed.pdf?web=1 |  | 45887.5647 | 45152.4654 | Jahdiel Franqui | Distribution Feeders ‐ San Juan Short Term Group 1 | Maria Mujica Gonzalez |  |  |  |  | 1 | 1 | 45884 | 334471RFI338 | 334471 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
334470 | 11708 | FAASt [TL 3100 Monacillos TC to Sabana Llana TC] (Transmission) | 14F002390000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild |  | Restoration | FALSE |  | Current | [5 empty] | 113330000 | 44385 | 44428 |  | 44415 |  |  |  | 44455 | 9/10/2021 | 45291 | 45565 | 45875 | 45882 | 45876 | 8/7/2025 - RFI response received on 08/06/2025, under EHP specialist revision. The expected completion date (ECD) for the response revision is 08/13/2025. |  | 113330000 | 113330000 |  | 2848650.5 |  | 51867865.42 | 0 | 0 | 51867865.42 | 54716515.92 |  |  | 45966 |  | 47112099.92 | 47112099.92 |  |  |  | 965924.9 |  | 47112099.92 | 47112099.92 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/339/334470-DR4339PR-10078-EN-SOW-0001_Rev0%20-%20FEMA%20SOW%20Line%203100%20Monacillos%20TC%20to%20Daguao%20TC%20Signed%20-%20Copy.pdf?web=1 | 3/26/2024 - EHP Phase I, II Analyses data received from Grid Strategy and inserted in tracker for affected TLine 3100 . 8/7/2025 - RFI response received on 08/06/2025, under EHP specialist revision. The expected completion date (ECD) for the response revision is 08/13/2025. 8/12/2025 8:23 AM AST - The PR Electric Power Authority, as the eligible entity (subrecipient), has submitted a consolidated plan for the use of the remaining budget available in the FEMA Accelerated Awards Strategy Project (136271) Fixed Cost Award. This FAASt sub-project has been identified in the list and it will be processed in the national workflow accordingly. | 45992.689 | 45152.4654 | Jahdiel Franqui | Line 3100 Monacillos TC to Daguao TC | Marlina Crespo | 0 Months |  | 2747003.78 | 0 | 2.185 | 1 |  | 334470RFI339 | 334470 | 965924.9 |  | 965924.9 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
334469 | 107522 | FAASt [Line 8900 Monacillos TC to Adm. Tribunal Apelaciones] (Transmission) | 14F002360000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active |  |  | 11510000 |  |  | 45469 |  |  |  |  | 44455 | 9/10/2021 | [7 empty] | 11510000 | 11510000 | [5 empty] | 0 | 11510000 | 11510000 | [11 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/340/334469-DR4339PR-10075-EN-SOW-0001_Rev0%20-%20FEMA%20SOW%20Line%208900%20Monacillos%20TC%20to%20Adm%20Signed%20-%20Copy.pdf?web=1 | 3/28/2024 - Received withdrawal status data/info from Project Manager Claudio R. Jaquez. DSOW submittal forecast: 6/26/2024. | 45877.5781 | 45152.4654 | Jahdiel Franqui | Line 8900 Monacillos TC to Adm. Tribunal Apelaciones | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 334469RFI340 | 334469 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
334468 | 10679 | FAASt [Transmission Priority Pole Replacements – Line 2200] (Transmission) | 14F004440000 | PBUT13 - T Priority Pole Repl | Transmission – Pole Replacement | Transmission Line Rebuild |  | Restoration | FALSE | [7 empty] | 378800000 | 44438 | 44461 |  | 44468 |  |  |  | 44455 | 9/10/2021 | 44712 | 44683 | 44683 |  |  |  |  | 103800000 | 1217429 | 0 | 242850 |  | 1217429 | 0 | 0 | 1217429 | 1460279 |  |  | 44755 | 8/30/2024 | 1217429 | 1217429 | 1217429 | 1217429 |  |  |  | 1217429 | 1217429 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/341/334468-DR4339PR-DSOW%20-TL%202200-Transmission%20Priority%20Pole%20Replacement-%20V0%20(4).pdf?web=1 | 3/26/2024 - EHP Phase I, II Analyses data received from Grid Strategy and inserted in tracker for affected TLine 2200 | 46051.3867 | 45152.4654 | Jahdiel Franqui | 38 kV Transmission Priority Poles and Structures Replacements | Ashleah Dingle |  |  | 242850 |  | 1 | 1 |  | 334468RFI341 | 334468 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
334452 | 107521 | FAASt [Feeders - Caguas Short Term Group 3] (Distribution) | 14F000550000, 14F000400000, 14F000560000, 14F000360000, 14F000720000, 14F000740000, 14F000760000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild | Distribution Line Rebuild |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 82070000 | 44385 | 44428 |  | 44415 |  |  |  | 44449 | 9/9/2021 | 45199 | 45170 | 45260 |  |  |  |  | 82070000 | 79565087 | 20046792 | 6235944 |  | 39516463 | 2749314 | 17297478 | 59563255 | 65799199 | 45838 | 45991 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/342/334452-DR4339PR-DSOW-%20Caguas%20Short%20Term%20Group%203.pdf?web=1 |  | 45887.5739 | 45152.4654 | Jahdiel Franqui | Distribution Feeders ‐ Caguas Short Term Group 3 | Maria Mujica Gonzalez |  |  |  |  | 1.3358 | 1 | 45884 | 334452RFI342 | 334452 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
334443 | 107520 | FAASt [Feeders - Caguas Short Term Group 2] (Distribution) | 14F000430000, 14F000500000, 14F000610000, 14F000570000, 14F000620000, 14F000410000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild | Distribution Line Rebuild |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 111970000 | 44385 | 44428 |  | 44415 |  |  |  | 44448 | 9/9/2021 | 45199 | 45198 | [5 empty] | 111960000 | 104883530 | 51954249 | 8863340 |  | 52929281 | 7448718 | 44505531 | 104883530 | 113746870 | 45688 | 45869 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/343/334443%20-%20DR4339PR%20%20-%20Distribution%20Feeders%20-%20Caguas%20Short%20Term%20Group%202.pdf?web=1 |  | 45888.5397 | 45152.4654 | Jahdiel Franqui | Distribution Feeders ‐ Caguas Short Term Group 2 | Maria Mujica Gonzalez |  |  |  |  | 1 | 1 | 45887 | 334443RFI343 | 334443 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
334420 | 107519 | FAASt [Feeders - Caguas Short Term Group 1] (Distribution) | 14F000440000, 14F000710000, 14F000680000, 14F000590000, 14F000700000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild | Distribution Line Rebuild |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 59850000 | 44385 | 44428 |  | 44415 |  |  |  | 44448 | 9/9/2021 | 45199 | 45198 | [5 empty] | 59850000 | 70560944 | 25596317 | 8617160 |  | 44964627 | 3805840 | 21790477 | 70560944 | 79178104 | 45716 | 45900 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/344/334420%20-%20DR4339PR%20-%20FEMA%20SOW%20%20Distribution%20Feeders%20-%20Caguas%20Short%20Term%20Group%201.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 45887.5904 | 45152.4654 | Jahdiel Franqui | Distribution Feeders ‐ Caguas Short Term Group 1 | Maria Mujica Gonzalez |  |  |  |  | 1 | 1 | 45884 | 334420RFI344 | 334420 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
334334 | 107518 | FAASt Line 500 Ponce TC to Costa Sur SP (Transmission) | 14F002400000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 36590000 | [7 empty] | 44447 | 9/8/2021 | 45382 | [6 empty] | 36590000 | 36590000 | [5 empty] | 0 | 36590000 | 36590000 | [11 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/345/DI%20661562%20-%20DR%204339%20-10079-EN-SOW-0001_Rev0%20-%20FEMA%20SOW%20Line%20500%20Ponce%20TC%20to%20Costa%20Sur%20SP%20Signed.pdf?web=1 | 9/12/2024 - GP Notes "6/25/2024 The project was withdrawn. The project was withdrawn with the comment "Project is being withdrawn since it was not included in the Applicant’s latest workplan for submittal of a SOW. FEMA may in the future re-create the project at the request of the Applicant and COR3 if a SOW submittal date is provided." | 45877.5781 | 45152.4654 | Jahdiel Franqui | Line 500 Ponce TC to Costa Sur SP | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 334334RFI345 | 334334 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
334331 | 11528 | FAASt Line 1900 Dos Bocas HP to San Sebastian (38kV) TC (Transmission) | 14F002410000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  | 45495 | 117600000 | 45504 | 45526 |  | 45534 |  |  |  | 44446 | 9/8/2021 | 45291 | 45565 | 45839 | 45887 | 45856 | Mitigation information reset because the project was sent back. Insurance information reset because the project was sent back. |  | 51200000 | 0 |  | 2009300.52 |  | 31788090.96 |  | 0 | 31788090.96 | 33797391.48 | [11 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/346/DI%20661466%20-%20DR4339%2010080-EN-SOW-0001_Rev0%20-%20FEMA%20SOW%20Line%201900%20Dos%20Bocas%20HP%20to%20San%20Sebastian%20TC%20Signed.pdf?web=1 | 3/26/2024 - EHP Phase I, II Analyses data received from Grid Strategy and inserted in tracker for affected TLine 1900 | 45980.6621 | 45152.4654 | Jahdiel Franqui | Line 1900 Dos Bocas HP to San Sebastian TC | Marlina Crespo | 0 Months |  |  |  | 0 | 5 | 45887 | 334331RFI346 | 334331 | 681967 | 0 | 681967 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
334329 | 10629 | FAASt Distribution Pole and Conductor Repair - Ponce Group 2 (Distribution) | 14F004140000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [15 empty] | 44446 | 9/8/2021 | 44592 | 44589 | 44685 |  |  |  |  | 42380000 | 380253 | 64134 | 25530 |  | 316119 | 0 | 64134 | 380253 | 405783 |  |  | 44701 | 8/30/2024 | 380253 | 316119 | 380253 | 316119 |  |  |  | 380253 | 316119 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/347/DSOW%205.4.22.pdf?web=1 |  | 46070.4799 | 45152.4654 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Marlina Crespo |  |  | 25530 |  | 1 | 1 |  | 334329RFI347 | 334329 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 64134
334323 | 10630 | FAASt Distribution Pole and Conductor Repair - Ponce Group 1 (Distribution) | 14F004130000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | Distribution Pole and Conductor Repair |  | Restoration | FALSE | [7 empty] | 600000000 | 44438 | 44461 |  | 44468 |  |  |  | 44447 | 9/8/2021 | 44592 | 44589 | 44685 |  |  |  |  | 40600000 | 392822 | 69130 | 26179 |  | 323152 | 0 | 69130 | 392282 | 418461 |  |  | 44707 | 8/30/2024 | 392822 | 323692 | 392822 | 323692 |  |  |  | 392822 | 323692 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/348/334323-DR4339PR-Detailed%20SOW-Distribution%20Pole%20and%20Conductor%20Repair%20%E2%80%93%20Ponce%20Group%201-Rev3%20(3).pdf?web=1 |  | 46070.4793 | 45152.4654 | Jahdiel Franqui | Distribution Pole & Conductor Replacement | Marlina Crespo |  |  | 26179 |  | 1.0014 | 1 |  | 334323RFI348 | 334323 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 69130
334308 | 107517 | FAASt [Feeders - Mayaguez Short Term Group 1] (Distribution ) | 14F001040000, 14F001030000, 14F001010000, 14F000990000, 14F001020000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild | Distribution Line Rebuild |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 74170000 | 44385 | 44428 |  | 44415 |  |  |  | 44447 | 9/8/2021 | 45138 | 45108 | [5 empty] | 74170000 | 72626419 | 32030114 | 7650658 |  | 37671047 | 5407189 | 26622925 | 69701161 | 77351819 | 45838 | 45991 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/349/334308-DR4339PR-Detailed%20SOW%20Mayaguez%20Group%201.pdf?web=1 |  | 45887.6181 | 45152.4654 | Jahdiel Franqui | Distribution Feeders ‐ Mayaguez Short Term Group 1 | Maria Mujica Gonzalez |  |  |  |  | 1.042 | 1 | 45884 | 334308RFI349 | 334308 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
334293 | 107516 | FAASt [Feeders - 7805-11- Mayaguez Short Term Group 4] (Distribution ) | 14F003450000, 14F003440000, 14F003480000, 14F003420000, 14F003460000, 14F003430000, 14F003470000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild | Distribution Line Rebuild |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | FALSE |  | 98490000 | 44385 | 44428 |  | 44415 |  |  |  | 44447 | 9/8/2021 | 45138 | 45107 | 45260 |  |  |  |  | 98500000 | 86877699 | 45582792 | 5930015 |  | 41294907 | 5327428 | 40255364 | 86877699 | 92807714 | 45838 | 45991 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/350/Revised%20FEMA%20SOW%20-%20334293-DR4339PR-DSOW-%20Mayag%C3%BCez%20STG4%20-%20signed%20(1).pdf?web=1 | <div class="ExternalClass87E8A90E10984BD18A0558075A015B3F"><div style="font-family&#58;Calibri, Arial, Helvetica, sans-serif;font-size&#58;11pt;color&#58;rgb(0, 0, 0);">7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List<br></div></div> | 46077.5731 | 45152.4654 | Jahdiel Franqui | Distribution Feeders ‐ Mayaguez Short Term Group 4 | Ashleah Dingle |  |  |  |  | 1 | 1 | 45884 | 334293RFI350 | 334293 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
334285 | 107514 | FAASt [Feeders - Mayaguez Short Term Group 2] (Distribution ) | 14F001100000, 14F001110000, 14F001070000, 14F001130000, 14F001120000, 14F001090000, 14F001060000, 14F001050000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild | Distribution Line Rebuild |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 108840000 | 44385 | 44428 |  | 44415 |  |  |  | 44447 | 9/8/2021 | 45138 | 45107 | 45260 |  |  |  |  | 108850000 | 81195988 | 35887745 | 6284173 |  | 42366398 | 4489868 | 31397877 | 78254143 | 84538316 | 45808 | 45961 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/351/334285-DR4339PR-DSOW%2010139%20-%20Mayag%C3%BCez%20STG2%20-%20signed%20(1)%20(1).pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List 8/13/2024 Removed from Priority Projects, broken down further with pending faast number | 45887.6206 | 45152.4654 | Jahdiel Franqui | Distribution Feeders ‐ Mayaguez Short Term Group 2 | Maria Mujica Gonzalez |  |  |  |  | 1.0376 | 1 | 45884 | 334285RFI351 | 334285 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
334191 | 107513 | FAASt [Feeders - Mayaguez Short Term Group 3] (Distribution) | 14F001200000, 14F001140000, 14F001190000, 14F001210000, 14F001160000, 14F001180000, 14F001170000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild | Distribution Line Rebuild |  | Restoration | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | FALSE |  | 134670000 | 44385 | 44428 |  | 44415 |  |  |  | 44446 | 9/7/2021 | 45138 | 45107 | 45260 |  |  |  |  | 134670000 | 98525716 | 38483744 | 7245123 |  | 37430424 | 6091551 | 32392193 | 75914168 | 83159291 | 45838 | 45991 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/352/334191-DR4339PR-%20DSOW%2010140%20-%20Mayag%C3%BCez%20STG3%20-%20signed%20(1)%20(1).pdf?web=1 |  | 46077.573 | 45152.4654 | Jahdiel Franqui | Distribution Feeders ‐ Mayaguez Short Term Group 3 | Ashleah Dingle |  |  |  |  | 1.2979 | 1 | 45884 | 334191RFI352 | 334191 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
180326 | 11441 | FAASt - Line 36800 (115kV) - Sabana Llana TC to Canovanas TC to Palmer-Fajardo TC (Transmission) | 14F002190000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 56130000 | 44314 | 44355 |  | 44344 |  |  |  | 44302 | 4/16/2021 | 44804 | 44803 | 45303 |  |  |  |  | 70310000 | 0 | 32488767 | 6478150 |  | 60760627 | 3117231 | 29371536 | 93249394 | 99727544 | 45504 | 45596 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/353/180326-DR4339PR-%20Detailed%20SOW%20Line%2036800%20(10054-CP-SOW-0003_Rev.0).pdf?web=1 |  | 45888.4683 | 45152.4654 | Jahdiel Franqui | FAASt Canovanas TC to Sabana Llana TC - 36800 (Transmission) FAASt Canovanas TC to Palmer-Fajardo TC - 36800 (Transmission) | Maria Mujica Gonzalez |  |  |  |  | 0 | 5 | 45887 | 180326RFI353 | 180326 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
180052 | 11453 | FAASt Ponce TC to Jobos TC - 38kV 100 & 200 (Transmission) | 14F002170000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild |  | Restoration | FALSE |  | Current | [5 empty] | 87280000 | 44314 | 44355 |  | 44344 |  |  |  | 44459 | 4/14/2021 | 44804 | 44803 | 45883 | 45912 | 45890 | 8/21/2025 - Field EHP - Historic: In review. Expected Completion Date (ECD) updated to: 9/12/2025 |  | 42900000 | 0 | 0 | 1776747.63 |  | 17796351.55 | 0 | 0 | 17796351.55 | 19573099.18 | 45473 | 45535 | 45966 |  | 74520098.48 | 74520098.48 |  |  |  | 9413216.96 |  | 74520098.48 | 74520098.48 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/354/180052%20-%20DR4339PR-00%20FEMA%20DSOW%20-%20Existing%2038%20kV%20TLines%20100,%20200%20PonceTC-Jobos%20TC%2010052-CP-SOW-0003%20Rev%201.pdf?web=1 | 3/26/2024 - EHP Phase I, II Analyses data received from Grid Strategy and inserted in tracker for affected TLine 100/200 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List 8/4/2025 - EHP RFI-PRJ-121350 has been sent to the applicant on July 22, 2025, for their action. The deadline is set for 8/15/2025. 8/12/2025 8:23 AM AST - The PR Electric Power Authority, as the eligible entity (subrecipient), has submitted a consolidated plan for the use of the remaining budget available in the FEMA Accelerated Awards Strategy Project (136271) Fixed Cost Award. This FAASt sub-project has been identified in the list and it will be processed in the national workflow accordingly. | 45992.689 | 45152.4654 | Jahdiel Franqui | FAASt Ponce TC to Jobos TC - 100 (Transmission) FASSt Ponce TC to Jobos TC - 200 (Transmission) | Marlina Crespo | 0 Months |  | 8369786.38 | 0 | 0 | 5 |  | 180052RFI354 | 180052 | 9413216.96 |  | 9413216.96 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
179988 | 107305 | FAASt [Las Lomas – XFMR 1525] (Substation) | 14F003090000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active | [10 empty] | 44300 | 4/14/2021 | [7 empty] | 2400000 | 2400000 | [5 empty] | 0 | 2400000 | 2400000 | [11 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/355/179988-DR4339PR-Las%20Lomas%20-%20XFMER%201525%20-%20FEMA%20SOW%20CE%201-27-21.pdf?web=1 | 4/2/2024 - Received withdrawal status data/info from Manager Yadira L. Lugo Cordero. Working with Planning and Engineering to complete assessments to define scope and start the Preliminary Engineering. | 45877.5781 | 45152.4654 | Jahdiel Franqui |  | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 179988RFI355 | 179988 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
179558 | 10632 | FAASt - Manatí TC - BRKS 230 kV - (Substation) | 14F002820000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds |  | Restoration | FALSE | [7 empty] | 1800000 | 44314 | 44355 |  | 44344 |  |  |  | 44295 | 4/9/2021 | 44712 | 44683 | [5 empty] | 1800000 | 1593443 | 0 | 688917 |  | 1593443 | 0 | 0 | 1593443 | 2282360 |  |  | 44707 |  | 1593443 | 1593443 | [5 empty] | 1593443 | 1593443 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/356/179558-DR4339PR%20-%20Detailed%20SOW%20-%20Manati%20TC%20-%20BRKS%20230kV%20(10106-CP-SOW-0002%20Rev1)%20(2).pdf?web=1 |  | 45856.7693 | 45152.4654 | Jahdiel Franqui | FAASt Manati TC - BRKS 230 kv (Substation) | Rey Roldan Rodríguez |  |  | 688917 |  | 1 | 1 |  | 179558RFI356 | 179558 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
178577 | 11507 | FAASt [Cachete – MC 1526] (Substations) | 14F002810000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | TRUE | Restoration | FALSE |  | Current | [5 empty] | 4000000 | 44314 | 44355 |  | 44344 |  |  |  | 44287 | 4/1/2021 | 45230 | 45201 | 45338 |  |  |  |  | 4000000 | 0 | 16340158.71 | 3196266.58 |  | 24361713.92 | 1892257.29 | 14447901.42 | 40701872.63 | 43898139.21 | 45716 | 45777 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/357/178577%20-%20DR4339PR%20-%20Cachete%20-%20MC%201526%20-%20FEMA%20SOW%20%20CE%201-27-21%20(1).pdf?web=1 |  | 46059.5386 | 45152.4654 | Jahdiel Franqui | Substations – Cachete – MC 1526 | Jason Fournier |  |  |  |  | 0 | 5 |  | 178577RFI357 | 178577 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
178503 | 11100 | FAASt [Aguirre TC - BKRS] (Substations) | 14F002800000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | TRUE | Restoration | FALSE | [7 empty] | 12200000 | 44314 | 44355 |  | 44344 |  |  |  | 44287 | 4/1/2021 | 44865 | 44865 | 45007 |  |  |  |  | 12000000 | 39034592 | 0 | 5171019 |  | 39034592 | 0 | 0 | 39034592 | 44205611 |  |  | 44922 | 04/14/2023 | 39034592 | 39034592 | 39034592 | 39034592 |  |  |  | 39034592 | 39034592 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/358/178503-DR4339PR-%20Detail%20SOW-Aguirre%20TC%20-%20BKRS%20-%20(10104-CP-SOW-0002_Rev%201)%20(3).pdf?web=1 |  | 46059.5386 | 45152.4654 | Jahdiel Franqui | Substations – Aguirre TC - BRKS | Jason Fournier |  |  | 5171019 |  | 1 | 1 |  | 178503RFI358 | 178503 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
178258 | 11721 | FAASt - [Taft - MC 1105] (Substations) | 14F002790000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds |  | Restoration | FALSE | [7 empty] | 4100000 | 44314 | 44355 |  | 44344 |  |  |  | 44285 | 3/31/2021 | 44712 | 44712 | 45422 | 45632 | 45625 |  |  | 4100000 | 13486572.33 | 4123842.4 | 1302381.39 |  | 9362729.93 | 961993.54 | 3161848.86 | 13486572.33 | 14788953.72 | 45596 | 45688 | 45694 |  | 13486572.33 | 9362729.93 | [5 empty] | 13486572.33 | 9362729.93 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/359/178258-DR43339PR-%2000%20FEMA%20Detailed%20Scope%20Of%20Work%20REV.4%20Taft%20MC%201105%202023-07-06%20-%20signed.PDF?web=1 |  | 46051.3931 | 45152.4654 | Jahdiel Franqui | Substations – Taft – MC 1105 | Ashleah Dingle |  |  | 1302381.39 | 503587.39 | 1 | 1 |  | 178258RFI359 | 178258 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 3620255.01
177191 | 11433 | FAASt - 115kV Line 39000 - Aguas Buenas TC to Caguas TC (Transmission) | 14F002340000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | FALSE |  | 9700000 | 44314 | 44355 |  | 44344 |  |  |  | 44279 | 3/24/2021 | 45107 | 44812 | 45421 |  |  |  |  | 9700000 | 0 | 906873 | 2036324 |  | 17371561 | 93989 | 812884 | 18278434 | 20314758 | 45596 | 45688 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/360/177191%20DR4339PR-Detailed%20SOW%2039000%20Aguas%20Buenas%20TC%20to%20Caguas%20TC_Rev%200%20-%20signed.pdf?web=1 |  | 46077.5793 | 45152.4654 | Jahdiel Franqui | FAASt Aguas Buenas TC to Caguas TC - 39000 (Transmission) | Ashleah Dingle |  |  |  |  | 0 | 5 | 45889 | 177191RFI360 | 177191 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
177134 | 11440 | FAASt Guaraguao TC to Comerio TC Line-4100 (Transmission) | 14F002330000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  | 45568 | 25280000 | 44314 | 44355 |  | 44344 |  |  |  | 44281 | 3/24/2021 | 45107 | 45085 | 45461 |  |  |  | 4 | 25280000 | 0 | 7821691 | 5401272 |  | 54274064 | 471725 | 7349966 | 62095755 | 67497027 | 45626 | 45688 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/361/177134-DR4339PR-10071-CP-SOW-0003_Rev0%20(1).pdf?web=1 |  | 45887.5377 | 45152.4654 | Jahdiel Franqui | FAASt Guaraguao TC to Comerio TCLine-4100 (Transmission) | Maria Mujica Gonzalez |  |  |  |  | 0 | 5 | 45884 | 177134RFI361 | 177134 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
176971 | 11373 | FAASt –38kV Line 8200 - San Juan SP to Catano Sect Line (Transmission) | 14F002320000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild |  | Restoration | FALSE |  | Current | [5 empty] | 8070000 | 44314 | 44355 |  | 44344 |  |  |  | 44278 | 3/23/2021 | 44773 | 44771 | 45821 | 45980 | 45911 | 9/11/2025 - Field EHP: ESA Consultation letter submitted to USFWS on 09/10/2025. Waiting for response. ECD 11/19/2025. | 6 | 8070000 | 15567361 | 0 | 3250894.37 |  | 23193643.55 | 0 | 0 | 23193643.55 | 26444537.92 | 45504 | 45657 | 45966 |  | 21670623.78 | 21670623.78 |  |  |  | 120403.36 |  | 21670623.78 | 21670623.78 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/362/176971-DR4339PR-Detailed%20SOW%20-%20TL8200%20Cata%C3%B1o%20Sect.%20to%20San%20Juan%20SP%20Rev.2.pdf?web=1 | 8/8/2025 - Field EHP: RFI response received on 07/31/2025, under EHP specialist revision. The expected completion date (ECD) for the response revision is 08/15/2025. 8/12/2025 8:23 AM AST - The PR Electric Power Authority, as the eligible entity (subrecipient), has submitted a consolidated plan for the use of the remaining budget available in the FEMA Accelerated Awards Strategy Project (136271) Fixed Cost Award. This FAASt sub-project has been identified in the list and it will be processed in the national workflow accordingly. | 46051.393 | 45152.4654 | Jahdiel Franqui | FAASt San Juan SP to Catano SectLine-8200 (Transmission) | Ashleah Dingle |  |  | 3124951.32 | 0 | 0.67119 | 2 |  | 176971RFI362 | 176971 | 120403.36 |  | 120403.36 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
176954 | 11439 | FAASt Garzas 1 HP to Garzas 2 HP - 38kV Line 1100 (Transmission) | 14F002310000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild |  | Improved | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  | 45611 | 3580000 | 44314 | 44355 |  | 44344 |  |  |  | 44278 | 3/23/2021 | 45107 | 44802 | 45110 |  |  |  |  | 3580000 | 0 | 4127356 | 571113 |  | 2791523 | 700994 | 3426362 | 6918879 | 7489992 | 45504 | 45596 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/363/176954%20Detail%20Scope%20of%20Work%2010069-CP-SOW-0003%20-%20signed.pdf?web=1 |  | 45887.5607 | 45152.4655 | Jahdiel Franqui | FAASt Garzas 1 HP to Garzas 2 HP - Line 1100 (Transmission) | Maria Mujica Gonzalez |  |  |  |  | 0 | 5 | 45884 | 176954RFI363 | 176954 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
176913 | 11432 | FAASt [Palo Seco SP to Catano Sect 38kV Line- 9500] (Transmission) | 14F002300000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild |  | Restoration | FALSE |  | Current | [5 empty] | 6710000 | 44314 | 44355 |  | 44344 |  |  |  | 44278 | 3/23/2021 | 44804 | 44771 | 45821 | 45947 | 45917 | 8/12/2025 8:24 AM AST - The PR Electric Power Authority, as the eligible entity (subrecipient), has submitted a consolidated plan for the use of the remaining budget available in the FEMA Accelerated Awards Strategy Project (136271) Fixed Cost Award. This FAASt sub-project has been identified in the list and it will be processed in the national workflow accordingly. 9/17/2025 - Field EHP - Historic: SHPO consultation process ongoing. Letter submitted on 9/17/2025. Waiting for response. Expected Completion Date (ECD) 10/17/2025. |  | 6710000 | 11649409 | 0 | 297862.88 |  | 40504745.14 | 0 | 0 | 40504745.14 | 40802608.02 | 45869 | 46022 | 45966 |  | 33526671.86 | 33526671.86 |  |  |  | 297862.88 |  | 33526671.86 | 33526671.86 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/364/176913-DR4339-Detailed%20SOW%209500%20Palo%20Seco%20SP%20to%20Catano%20Sect.%20%20Line%209500%20(10068-CP-SOW-0003%20Rev%200)%20-%20signed.pdf?web=1 | 8/12/2025 8:24 AM AST - The PR Electric Power Authority, as the eligible entity (subrecipient), has submitted a consolidated plan for the use of the remaining budget available in the FEMA Accelerated Awards Strategy Project (136271) Fixed Cost Award. This FAASt sub-project has been identified in the list and it will be processed in the national workflow accordingly. | 46051.393 | 45152.4655 | Jahdiel Franqui | FAASt Palo Seco SP to Catano SectLine-9500 (Transmission) | Ashleah Dingle |  |  | 4657292.73 | 0 | 0.28761 | 4 |  | 176913RFI364 | 176913 | 297862.88 | 0 | 297862.88 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
174422 | 10496 | FAASt - Catano-Rebuild 1801(Substation) | 14F002770000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | TRUE | Restoration | FALSE | [7 empty] | 11300000 | 44314 | 44355 |  | 44344 |  |  |  | 44259 | 3/4/2021 | 44500 | 44497 | 44659 |  |  |  |  | 11300000 | 23255048.94 | 807222.04 | 4104786 |  | 18571716 | 0 | 807222.04 | 19378938.04 | 23483724.04 |  |  | 44699 |  | 23255048.94 | 16359899.17 | [5 empty] | 23255048.94 | 16359899.17 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/365/10000-CP-SOW-0001Rev2%20(3).pdf?web=1 |  | 46059.5386 | 45152.4655 | Jahdiel Franqui | Substations - Cataño – Rebuilt 1801 | Jason Fournier |  |  | 1211174.91 |  | 1.2 | 1 |  | 174422RFI365 | 174422 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 6895149.77
169896 | 10788 | FAASt - Costa Sur SP TC – Equipment Repair and Replacement (Substation) | 14F002750000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | TRUE | Restoration | FALSE | [7 empty] | 3600000 | 44314 | 44355 |  | 44344 |  |  |  | 44229 | 2/2/2021 | 44742 | 44719 | [5 empty] | 3600000 | 23251835 | 0 | 4734912 |  | 23251835 | 0 | 0 | 23251835 | 27986747 |  |  | 44775 |  | 23251835 | 23251835 | [5 empty] | 23251835 | 23251835 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/366/169896%20-%20DR-4339-PR%20-%20Detailed%20Scope%20of%20Work%20-%20Costs%20Sur%20230kV%2010101%20(2).pdf?web=1 |  | 46059.5386 | 45152.4655 | Jahdiel Franqui | Substations – Costa Sur SP TC – Equipment Repair and Replacement | Jason Fournier |  |  | 4734912 |  | 1 | 1 |  | 169896RFI366 | 169896 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
169804 | 107227 | FAASt Aguadilla Electric Service Center (Building) | 14F001970000 | PBFM01 - Facilities Dev & Implem | Building | Facilities Development & Implementation | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 3500000 | [7 empty] | 44230 | 2/1/2021 | [7 empty] | 3500000 | 3500000 | [5 empty] | 0 | 3500000 | 3500000 | [11 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/367/%5B169804%5D-DR4339PR-Aguadilla%20Electric%20Service%20Center.pdf?web=1 | 4/3/2024 - Received withdrawal status data/info from Deputy Project Manager Gerardo Medina-Sonera. This project will be included in the new Island Wide ISOW approach. | 45877.5781 | 45152.4655 | Jahdiel Franqui | Buildings - Aguadilla Electric Service Center | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 169804RFI367 | 169804 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
169798 | 107226 | FAASt Arecibo Electric Service Center (Building) | 14F001960000 | PBFM01 - Facilities Dev & Implem | Building | Facilities Development & Implementation | [5 empty] | TRUE | Voluntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 2320000 | 44314 | 44355 |  | 44344 |  |  |  | 44230 | 2/1/2021 | [7 empty] | 2320000 | 2320000 | [5 empty] | 0 | 2320000 | 2320000 | [11 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/368/%5B169798%5D-DR4339PR-Arecibo%20Electric%20Service%20Center.pdf?web=1 | 6/12/2025 - Project withdrawn in Grants Portal | 45877.5782 | 45152.4655 | Jahdiel Franqui | Buildings - Arecibo Electric Service Center | Ashleah Dingle |  |  |  |  | 1 | 1 | 45820 | 169798RFI368 | 169798 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
169576 | 107225 | FAASt Arecibo Regional Office Building (Building) | 14F001950000 | PBFM01 - Facilities Dev & Implem | Building | Facilities Development & Implementation | [5 empty] | TRUE | Voluntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 1800000 | 44314 | 44355 |  | 44344 |  |  |  | 44230 | 1/29/2021 | [7 empty] | 1800000 | 1800000 | [5 empty] | 0 | 1800000 | 1800000 | [11 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/369/%5B169576%5D-DR4339PR-Arecibo%20Regional%20Office%20Building.pdf?web=1 | 6/12/2025 - Project withdrawn in Grants Portal | 45877.5782 | 45152.4655 | Jahdiel Franqui | Buildings - Arecibo Regional Office Building | Ashleah Dingle |  |  |  |  | 1 | 1 | 45820 | 169576RFI369 | 169576 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
169503 | 107224 | FAASt [Ceiba Baja TRF 7012] (Substation) | 14F003080000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active | [10 empty] | 44225 | 1/29/2021 | [7 empty] | 2700000 | 2700000 | [5 empty] | 0 | 2700000 | 2700000 | [11 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/370/DI433943-DR4339PR-Substations%20-%20Ceiba%20Baja%20TRF%207012%20%20Intial%20SOW%20&%20CE%201-11-21%20(1).pdf?web=1 | 4/2/2024 - Received withdrawal status data/info from Manager Yadira L. Lugo Cordero. Working with Planning and Engineering to complete assessments to define scope and start the Preliminary Engineering. | 45877.5782 | 45152.4655 | Jahdiel Franqui |  | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 169503RFI370 | 169503 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
169500 | 11347 | FAASt [Bayamon TC – MC-BKRS-Y1] (Substation) | 14F002740000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | TRUE | Restoration | FALSE | [6 empty] | 45443 | 5700000 | 44314 | 44355 |  | 44344 |  |  |  | 44225 | 1/29/2021 | 44742 | 44767 | 45048 |  |  |  |  | 5700000 | 6372063 | 3575881 | 634045 |  | 2796182 | 1496809 | 2079072 | 6372063 | 7006108 |  |  | 45093 |  | 6372063 | 2796182 | [5 empty] | 6372063 | 2796182 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/371/169500-DR4339PR%20-%20FEMA%20DSOW%20-%20Bayamon%20TC%20(10100-CP-SOW-0002_Rev.4)%202023-04-2700-CP-SOW-0002_Rev.4.pdf |  | 46059.5386 | 45152.4655 | Jahdiel Franqui | Substations – Bayamon TC – MC-BKRS-Y1 | Jason Fournier |  |  | 634046 |  | 1 | 1 |  | 169500RFI371 | 169500 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 3575881
169495 | 11479 | FAASt [Substations - Tapia GIS Rebuilt Equipment Repair & Replacement] (Substations) | 14F001760000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | TRUE | Restoration | FALSE | [7 empty] | 23000000 | 44314 | 44355 |  | 44344 |  |  |  | 44225 | 1/29/2021 | 44712 | 44712 | 45092 |  |  |  |  | 23000000 | 15339932.33 | 7159883.3 | 1397860 |  | 8180049 | 1044957.8 | 6114925.5 | 15339932.3 | 16737792.3 |  |  | 45160 |  | 15339932.33 | 8180049.03 | [5 empty] | 15339932.33 | 8180049.03 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/372/169495-DR4339PR-%2000%20Detailed%20SOW%20Tapia%20Substation%20-%20(10059-CP-SOW-0002Rev6)(rev%202023-06-14)%20-%20signed.pdf?web=1 |  | 46059.5386 | 45152.4655 | Jahdiel Franqui | Substations - Tapia GIS Rebuilt - Equipment Repair and Replacement | Jason Fournier |  |  | 1397859.52 |  | 1 | 1 |  | 169495RFI372 | 169495 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 7159883.3
169276 | 107222 | FAASt Substation - Viaducto TC - MC 1100 - Equipment Repair & Replacement [Substation] | 14F002730000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | TRUE | Restoration | FALSE |  | Current | [5 empty] | 4000000 | 44314 | 44355 |  | 44344 |  |  |  | 44224 | 1/28/2021 | 45016 | 45016 | 45385 |  |  |  |  | 4000000 | 20425907 | 3661876.82 | 5917803.36 |  | 75107786 | 267449.67 | 3394427.15 | 78769662.82 | 84687466.18 | 45716 | 45900 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/373/169276-DR4339PR-10099-CP-SOW-0001_Rev.2%20-%20signed%202023-08-23%2012_08_10-1.pdf?web=1 | 3/27/2024: QC Review Complete | 46059.5386 | 45152.4655 | Jahdiel Franqui | FAASt Viaducto TC - MC 1100 - Equipment Repair & Replacement (Substations) | Jason Fournier |  |  |  |  | 0.25931 | 4 |  | 169276RFI373 | 169276 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
169266 | 11489 | FAASt Centro Medico 1327/1359 Equipment Repair & Replacement (Substation) | 14F002720000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | TRUE | Restoration | FALSE | [7 empty] | 11700000 | 44314 | 44355 |  | 44344 |  |  |  | 44224 | 1/28/2021 | 44712 | 44707 | 45134 |  |  |  |  | 11700000 | 21332361 | 6537037 | 1810918 |  | 14795324 | 0 | 6537037 | 21332361 | 23143279 |  |  | 45233 | 8/30/2024 | 21332361 | 14795324 | 21332361 | 14795324 |  |  |  | 21332361 | 14795324 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/374/169266-DR4439PR-Detailed%20SOW-Centro%20Medico%201327%201359%20Equipment%20Repair%20&%20Replacement%20(Substation).pdf?web=1 |  | 46070.4788 | 45152.4655 | Jahdiel Franqui | Substations - Centro Medico 1327/1359 Equipment Repair and Replacement | Marlina Crespo |  |  | 1810918 |  | 1 | 1 |  | 169266RFI374 | 169266 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 6537037
169058 | 107220 | FAASt - Llorens Torres MC 1106 - Equipment Repair & Replacement - (Substations) | 14F002710000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | TRUE | Improved | FALSE |  | Current | [5 empty] | 4000000 | 44314 | 44355 |  | 44344 |  |  |  | 44223 | 1/27/2021 | 44712 | 44685 | 45782 |  |  |  |  | 4000000 | 18279001 | 13265333.34 | 1213803.7 |  | 23342346.17 | 655599.77 | 12609733.57 | 36607679.51 | 37821483.21 | 45657 | 45838 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/375/169058-DR4339PR-10097-CP-SOW-0002_Rev%204%20-%20signed.pdf?web=1 |  | 46059.5386 | 45152.4655 | Jahdiel Franqui | Substations - Llorens Torres MC 1106 - Equipment Repair & Replacement | Jason Fournier |  |  |  |  | 0.49932 | 3 |  | 169058RFI375 | 169058 | 4078410.44 | 3369687 | 7448097.44 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
168483 | 11241 | FAASt - 115kV Line 36400 - Dos Bocas HP to Ponce TC (Transmission) | 14F002290000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild |  | Restoration | FALSE |  | Current | [5 empty] | 83260000 | 44314 | 44355 |  | 44344 |  |  |  | 44218 | 1/22/2021 | 44804 | 44802 | 45421 | 45875 | 45868 | 7/30/2025 - Field EHP: In final review. ECD 7/6/2025. |  | 87440000 | 0 | 8111071 | 10145828 |  | 96749488 | 339692 | 7771379 | 104860559 | 115006387 | 45473 | 45565 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/376/168483-DR4339PR-Detail%20SOW%20TL36400%20Dos%20Bocas%20HP%20to%20Ponce%20TC%20(10067-CP-SOW-0002_Rev0)%20-%20signed.pdf?web=1 | 3/26/2024 - EHP Phase I, II Analyses data received from Grid Strategy and inserted in tracker for affected TLine 36400 7/30/ | 45880.4132 | 45152.4655 | Jahdiel Franqui | Transmission - Line 36400 - Dos Bocas HP to Ponce TC | Ashleah Dingle |  |  |  |  | 0 | 5 |  | 168483RFI376 | 168483 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
168226 | 10978 | FAASt San Juan 115kV Underground Transmission Loop (Transmission) | 14F002280000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild |  | Restoration | FALSE | [7 empty] | 11600000 | 44314 | 44355 |  | 44344 |  |  |  | 44216 | 1/20/2021 | 44712 | 44683 |  | 45555 | 45551 |  |  | 89700000 | 14746039.57 | 0 | 584325 |  | 16420054 | 0 | 0 | 16420054 | 17004379 |  |  | 44916 | 9/10/2025 | 14746039.57 | 14746039.57 | 14746039.57 | 14746039.57 |  |  |  | 14746039.57 | 14746039.57 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/377/168226%20-Detailed%20SOW-115kV-%20TL%2038000%20%20San%20Juan-Isla%20Grande%20Underground%20Loop.pdf?web=1 |  | 46051.4007 | 45152.4655 | Jahdiel Franqui | Transmission - San Juan 115-kV Underground Transmission Loop | Ashleah Dingle |  |  | 2258339.67 |  | 0.89805 | 1 |  | 168226RFI377 | 168226 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
167508 | 11250 | FAASt Transmission - Line 50100 (230KV)- Cambalache GP TC to Manati TC (Transmission) | 14F002270000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 41390000 | 44314 | 44355 |  | 44344 |  |  |  | 44378 | 1/13/2021 | 44895 | 44893 | 45426 |  |  |  |  | 43470000 |  | 4609955 | 7023284 |  | 71765405 | 200381 | 4409574 | 76375360 | 83398644 | 45504 | 45657 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/378/10065-%20TL-50100-%20Detailed%20SOW%20May%2026%20-%20signed.pdf?web=1 | 3/26/2024 - EHP Phase I, II Analyses data received from Grid Strategy and inserted in tracker for affected TLine 50100 | 45887.5611 | 45152.4655 | Jahdiel Franqui | FAASt Transmission - Line 50100 - Cambalache GP TC to Manati TC (Transmission) | Maria Mujica Gonzalez |  |  |  |  | 0 | 5 | 45884 | 167508RFI378 | 167508 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
167446 | 11307 | FAASt - Line 36100 (115kV) - Dos Bocas HP to Monacillos TC (Transmission) | 14F002260000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild |  | Restoration | FALSE |  | Current |  |  |  |  | 45611 | 109970000 | 44314 | 44355 |  | 44344 |  |  |  | 44209 | 1/13/2021 | 45107 | 45107 | 45877 | 45938 | 45917 | 8/11/2025 -This project is under the DOE Emergency declaration 202C, pending R2 guidance. 9/17/2025 - Field EHP - Environmental: In review. Expected Completion Date (ECD): 10/08/2025. |  | 115490000 |  | 0 | 3371255.12 |  | 32863940.58 | 0 | 0 | 32863940.58 | 36235195.7 | 45626 | 45777 | 45966 |  | 33956314.58 | 33956314.58 |  |  |  | 85008 |  | 33956314.58 | 33956314.58 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/379/167446-DR4339PR-TL36100%20Detailed%20SOW%20-%20Dos%20Bocas%20HP%20to%20Monacillos%20TC%20-29JUNE2023-final%20signed%20(1)%20(1).pdf?web=1 | 8/8/2025 - Field EHP: RFI response received on 08/08/2025, under EHP specialist revision. Expected Completion Date (ECD) 08/22/2025. 8/11/2025 -This project is under the DOE Emergency declaration 202C, pending R2 guidance. 8/12/2025 8:24 AM AST - The PR Electric Power Authority, as the eligible entity (subrecipient), has submitted a consolidated plan for the use of the remaining budget available in the FEMA Accelerated Awards Strategy Project (136271) Fixed Cost Award. This FAASt sub-project has been identified in the list and it will be processed in the national workflow accordingly. | 46051.3929 | 45152.4655 | Jahdiel Franqui | FAASt - Line 36100 - Dos Bocas HP to Monacillos TC (Transmission) | Ashleah Dingle |  |  | 3408229.98 | 0 | 0 | 5 |  | 167446RFI379 | 167446 | 85008 |  | 85008 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
167443 | 11251 | FAASt - Line 36200 (115KV)- Monacillos TC to Juncos TC (Transmission) | 14F002250000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  | 45568 | 40690000 | 44314 | 44355 |  | 44344 |  |  |  | 44209 | 1/13/2021 | 45138 | 44806 | 45310 |  |  |  |  | 42730000 | 0 | 15967020 | 6485111 |  | 62522200 | 1461125 | 14505895 | 78489220 | 84974331 | 45473 | 45626 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/380/167443-DR4339PR-Detailed%20SOW%20-%20TL36200%20Monacillos%20TC%20to%20Juncos%20TC%20rev%201%20-%20signed.pdf?web=1 | 3/26/2024 - EHP Phase I, II Analyses data received from Grid Strategy and inserted in tracker for affected TLine 36200 | 45887.5653 | 45152.4655 | Jahdiel Franqui | FAASt - Line 36200 - Monacillos TC to Juncos TC (Transmission) | Maria Mujica Gonzalez |  |  |  |  | 0 | 5 | 45884 | 167443RFI380 | 167443 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
167168 | 11246 | FAASt [Transmission 115kV Line 37100 Costa Sur ST - Acacias TC] (Transmission) | 14F002240000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 87590000 | 44314 | 44355 |  | 44344 |  |  |  | 44207 | 1/11/2021 | 44834 | 44805 | 45107 |  |  |  |  | 91990000 |  | 24646695 | 10274876 |  | 96370356 | 2374619 | 22272076 | 121017051 | 131291927 | 45900 | 45688 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/381/167168-DR4339PR-%20Detailed%20SOW%20Line%2037100%20(10062-CP-SOW-0002_Rev1)%2028JUNE2023.pdf?web=1 | 13SEPTEMBER2024 DSOW Rev. 2 was removed from GP. It was originally submitted on January 12, 2024 | 45887.6109 | 45152.4655 | Jahdiel Franqui | FAASt_TRANSMISSION-LINE-37100_COSTA SUR-ST_ACACIAS-TC | Maria Mujica Gonzalez |  |  |  |  | 0 | 5 | 45884 | 167168RFI381 | 167168 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
166904 | 11451 | FAASt Transmission 115kV Line 37800 Caguas TC to Monacillos TC (TRANSMISSION) | 14F002230000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 32400000 | 44314 | 44355 |  | 44344 |  |  |  | 44203 | 1/7/2021 | 44804 | 44774 | 45303 |  |  |  |  | 33400000 |  | 9229435 | 4855883 |  | 45544705 | 881999 | 8347436 | 54774140 | 59630023 | 45504 | 45596 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/382/166904-DR4339-Detailed%20SOW%2037800%20Caguas%20TC%20-%20Monacillos%20TC%20(10060-CP-SOW-0003%20Rev%200)%20-%20signed.pdf?web=1 |  | 45887.6118 | 45152.4655 | Jahdiel Franqui | FAASt Transmission Line 37800 Caguas TC to Monacillos TC (TRANSMISSION) | Maria Mujica Gonzalez |  |  |  |  | 0 | 5 | 45884 | 166904RFI382 | 166904 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
166860 | 11255 | FAASt-Line 37800 (115kV) - Jobos TC to Cayey TC & Cayey TC to Caguas TC (Transmission) | 14F002220000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 49510000 | 44314 | 44355 |  | 44344 |  |  |  | 44203 | 1/7/2021 | 44804 | 44803 | 45373 |  |  |  |  | 52000000 | 0 | 19709323 | 7900833 |  | 74111756 | 1889975 | 17819348 | 93821079 | 101721912 | 45565 | 45716 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/383/166860-DSOW-115kV%20Transmission%20Line%2037800%20%E2%80%93%20Jobos%20TC%20to%20Caguas%20TC-Rev0.pdf?web=1 |  | 45887.6131 | 45152.4655 | Jahdiel Franqui | FAASt Transmission - Line 37800 - Jobos TC to Cayey TC Transmission - Line 37800 - Cayey TC to Caguas TC (Transmission) | Maria Mujica Gonzalez |  |  |  |  | 0 | 5 | 45884 | 166860RFI383 | 166860 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
166834 | 107214 | FAASt Transmission - Line 40100 & 40200 - Aguirre SP TC to Jobos TC (Transmission) |  | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 30430000 | [7 empty] | 44203 | 1/7/2021 | [7 empty] | 15980000 | 15980000 | [5 empty] | 0 | 15980000 | 15980000 | [11 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/384/166834-DR4339PR-Transmission%20%20Line%2040100%20&%2040200%20-%20Aguirre%20SP%20TC%20to%20Jobos%20TC%20(1).pdf?web=1 | 9/12/2024 - GP Notes6/18/2024 - The project is not included in the 90-Day Plan submitted in June 2024. Forecast have been requested to the applicant.6/25/2024- The project was withdrawn | 45877.5782 | 45152.4655 | Jahdiel Franqui | FAASt Transmission - Line 40100 & 40200 - Aguirre SP TC to Jobos TC (Transmission) | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 166834RFI384 | 166834 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
166707 | 11431 | FAASt - Line 51300 (230KV) - Ponce TC to Costa Sur SP TC (Transmission) | 14F002210000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 24840000 | 44314 | 44355 |  | 44344 |  |  |  | 44202 | 1/6/2021 | 44895 | 44894 | 45324 |  |  |  |  | 26080000 | 0 | 16781976 | 3528829 |  | 28280524 | 1774233 | 15007743 | 45062500 | 48591329 | 45473 | 45626 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/385/166707-10057-DSOW-TL-51300.pdf?web=1 |  | 45887.6174 | 45152.4655 | Jahdiel Franqui | FAASt Transmission Line 51300 - Ponce TC to Costa Sur SP TC | Maria Mujica Gonzalez |  |  |  |  | 0 | 5 | 45884 | 166707RFI385 | 166707 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
165268 | 11045 | FAASt Rio Grande Estate Substation CH-2306 (Substation) | 14F001750000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | TRUE | Improved | FALSE | [6 empty] | 45618 | 3970000 | 44314 | 44355 |  | 44344 |  |  |  | 44183 | 12/18/2020 | 44712 | 44701 | 44879 |  |  |  |  | 3700000 | 11683614.71 | 4585370.95 | 1391013 |  | 7098243 | 1768433.49 | 2816937.46 | 11683613.95 | 13074626.95 |  |  | 44916 |  | 11683614.71 | 7098243.76 | [5 empty] | 11683614.71 | 7098243.76 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/386/165268-DR4339PR-%2000%20-%20Rio%20Grande%20Estates%20CH%202306%20Detailed%20Scope%20of%20Work%20Rev.%203%20(10055-CP-SOW-0003Rev3)%20signed.pdf?web=1 |  | 46059.5386 | 45152.4655 | Jahdiel Franqui | Rio Grande Estates - CH - 2306 | Jason Fournier |  |  | 1391012.61 |  | 1 | 1 |  | 165268RFI386 | 165268 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 4585370.95
165226 | 107206 | FAASt [Feeders Vieques & Culebra] (Distribution) | 14F000930000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild | Distribution Line Rebuild |  | Restoration | FALSE |  | Current | [5 empty] | 31130000 | 44314 | 44355 |  | 44344 |  |  |  | 44183 | 12/18/2020 | 44926 | 44923 | 45993 |  |  |  |  | 28810000 | 57351920 | 12438987.09 | 5588218.14 |  | 66623350 | 962266.1 | 11476720.99 | 79062337.09 | 84650555.23 | 45869 | 46022 | [9 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/387/165226-DR4339PR%20Detailed%20SOW%20Vieques%20&%20Culebra%20-%20signed%20(2).pdf?web=1 |  | 45995.4934 | 45152.4655 | Jahdiel Franqui | Distribution – Vieques Feeders 2501-01, 2501-02, 2501-03 and Culebra Feeders 3801-01, 3801-02 | Marlina Crespo | 0 Months |  |  |  | 0.7254 | 2 |  | 165226RFI387 | 165226 | 3880212.29 | 1009930.36 | 4890142.65 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
165225 | 10624 | FAASt - EPC - Vieques 2501 substation repairs & New Vieques 2502 substation (Substation) | 14F002700000, 14F008780000, 14F000940000, 14F000910000, 14F000930000, 14F000920000, 14F000950000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds |  | Restoration | FALSE |  | Current | [5 empty] | 37910000 | 45288 | 45321 |  | 45318 |  |  |  | 44187 | 12/18/2020 | 44651 | 45077 | 45687 | 45817 | 45786 |  |  | 37910000 | 14704637.25 | 0 | 1491087 |  | 13495526 | 0 | 0 | 13495526 | 14986613 |  |  | 44722 | 06/10/2022 | 1313648.1 | 1209111 | 1387420 | 1209111 |  |  |  | 1387420 | 1209111 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/388/165225-Detailed%20SOW-Vieques%20NEW%20Substation%20V1%20(2)%20(1).pdf?web=1 |  | 46056.4088 | 45152.4655 | Jahdiel Franqui | Vieques 2501 & New Vieques Substation 2502 | Marlina Crespo |  |  | 531763 |  | 1.0896 | 1 |  | 165225RFI388 | 165225 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 178309
165213 | 11244 | FAASt – Line 5400 – Rio Blanco HP to Daguao TC to Punta Lima TO to Vieques 2501 to Culebra 3801 (Transmission) | 14F002200000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild |  | Restoration | FALSE |  | Current | [5 empty] | 73060000 | 44314 | 44355 |  | 44344 |  |  |  | 44183 | 12/18/2020 | 44895 | 44894 | 45924 |  |  |  |  | 73060000 | 0 | 19118456.86 | 4617946.01 |  | 67974026.1 | 1883144.1 | 17235312.76 | 87092482.96 | 91710428.97 | 45869 | 46022 | [9 empty] | 0 | 0 | 46650 |  | Use this link: https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/389/165213-DR4339PR%20DSOW%20TL%205400%20Rio%20Blanco%20HP%20to%20DaguaoTC%20to%20Vieques%20To%20Culebra%20Vieques%20and%20Culebra%20Microgrid%20Rev-4_Sep.22.2025_signed.pdf?web=1 | 45981.5786 | 45152.4655 | Jahdiel Franqui | Transmission – Line 5400 – Rio Blanco HP to Daguao TC to Punta Lima TO to Vieques 2501 to Culebra 3801 | Marlina Crespo | 0 Months |  |  |  | 0 | 5 |  | 165213RFI389 | 165213 | 0 | 12125.03 | 12125.03 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
165209 | 10626 | FAASt - EPC - Culebra Substation 3801 and New Culebra Substation 3802 (Substation) | 14F002690000, 14F008770000 | PBUT08 - Substation Rebuilds | Substation | Substation Rebuilds | TRUE | Restoration | FALSE |  | Current | [5 empty] | 39100000 | 45288 | 45321 |  | 45318 |  |  |  | 44183 | 12/18/2020 | 44651 | 44655 | 45488 | 45597 | 45587 |  |  | 1200000 | 14048046 | 0 | 1493591 |  | 12765829 | 0 | 0 | 12765829 | 14259420 |  |  | 44722 |  | 1387420 | 1282218 | 1459609 | 1282218 |  |  |  | 1387420 | 1282218 | 46650 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/390/165209-DR-4339PR-Culebra%20Substation%203801%20and%20New%20Culebra%20Substation%203802%20FEMA%20Detailed%20Scope%20of%20Work%20Rev.%208%20(7.12.2024)%20-%20signed.pdf?web=1 | 46059.5386 | 45152.4655 | Jahdiel Franqui | Culebra 3801 & New Culebra Substation 3802 | Jason Fournier |  |  | 522360 |  | 1.1004 | 1 |  | 165209RFI390 | 165209 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 105202
165208 | 107205 | FAASt Transmission Access Roads (Environmental) | 10F000180000 |  | Transmission | To be allocated to appropriate program | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 16970000 | [7 empty] | 44183 | 12/18/2020 | [7 empty] | 15186702.6 | 15186702.6 | [5 empty] | 0 | 15186702.6 | 15186702.6 | [11 empty] | 0 | 0 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/391/165208-DR4339PR-Transmission%20Access%20Roads-11.24.2020.pdf?web=1 | 4/3/2024 - Received withdrawal status data/info from Manager Joanna Dlugopolski. | 45877.5782 | 45152.4655 | Jahdiel Franqui | Transmission Access Roads | Ashleah Dingle |  |  |  |  | 1 | 1 |  | 165208RFI391 | 165208 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
136271 | 6099 | MEPA078 Puerto Rico Electrical Power Authority Island Wide FAASt Project |  |  | Other | TBD |  |  | FALSE | [16 empty] | 4/23/2020 | [8 empty] | 4132895287.7 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 44098 | 9/18/2024 | 6129706543.59 | 6323452979.59 | 5955252831.92 | 6148999267.92 | 4106613749.59 |  | 4300360185.59 | 4106613749.59 | 4300360185.59 | 46650 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/392/PRJ_Report_136271_20241106.pdf?web=1 |  | 46083.3855 | 45152.4655 | Jahdiel Franqui |  | Ashleah Dingle | [7 empty] | 136271RFI392 | 136271 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | -193746436
83182 | 1294 | MEPA181-Others- PREPA Management Costs | 14F003210000 | PBCP04 - PM Software & Tools | Other | TBD | [19 empty] | 3/20/2019 | [8 empty] | 620193956.54 |  |  |  | 620193956.5 | 0 | 0 | 620193956.5 | 620193956.5 |  |  | 43866 | 04/14/2023 | 52465131.5 | 52465131.5 | 620193956.54 | 620193956.54 |  |  |  | 620193956.54 | 620193956.54 | 43544 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/393/PRJ_Report_83182_20240219.pdf?web=1 |  | 45856.7694 | 45152.4655 | Jahdiel Franqui |  | Rey Roldan Rodríguez |  |  | 0 |  | 1 | 1 |  | 83182RFI393 | 83182 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
68753 | 1165 | MEPA149- A&E Services-PW 01165 |  |  | Other | TBD | [5 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [11 empty] | 11/28/2018 | [8 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 43714.7757 |  | 0 | 0 | [5 empty] | 0 | 0 |  |  |  | 46070.5306 | 45152.4655 | Jahdiel Franqui |  | Marlina Crespo | [6 empty] | 45800 | 68753RFI394 | 68753 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
728832 | 11718 | FAASt [Region 5 -Mayaguez Group A] High Density (Vegetation) | 15F019860000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation | TRUE |  | FALSE | [15 empty] | 45138 | 08/17/2023 | 45138 | 45155 | 45614 | 45737 | 45734 |  | 2 |  | 2380535.97 | 23418437.42 |  |  |  | 203638.57 | 23214798.85 | 23418437.42 | 23418437.42 | 45535 | 45626 | 45775 |  | 14260691.9 | 3767690.42 | [5 empty] | 14260691.9 | 3767690.42 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/395/38kV%20and%20below%20DSOW-%20Region%205_%20Mayaguez%20(1).pdf?web=1 | <div class="ExternalClass117FD3EDD6014C58A48DC9570AAC4B93"><div style="font-family&#58;Calibri, Arial, Helvetica, sans-serif;font-size&#58;11pt;color&#58;rgb(0, 0, 0);">7/25/2025 - Thomas Miller - Work continues to be performed and completed by field crews</div></div> | 46059.5502 | 45152.5676 | Marlina Crespo | Island-Wide Vegetation Clearing | Jason Fournier |  |  | 62820.38 |  | 0.10165 | 5 |  | 728832RFI395 | 728832 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 10493001.48
728827 | 11714 | FAASt [Region 2 -Arecibo Group A] High Density (Vegetation) | 15F019890000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation | TRUE |  | FALSE | [15 empty] | 45138 | 08/17/2023 | 45138 | 45155 | 45614 | 45744 | 45733 |  | 2 |  | 3036845.07 | 29878565.39 |  |  |  | 259813.59 | 29618751.8 | 29878565.39 | 29878565.39 | 45565 | 45657 | 45775 |  | 18194308.81 | 4807675.47 | [5 empty] | 18194308.81 | 4807675.47 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/396/38kV%20and%20below%20DSOW-%20Region%202_%20Arecibo%20(1).pdf?web=1 | 7/25/2025 - Work continues to be performed and completed by field crews. | 46059.5502 | 45152.5681 | Marlina Crespo | Island-Wide Vegetation Clearing | Jason Fournier |  |  | 79166.85 |  | 0.10164 | 5 |  | 728827RFI396 | 728827 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 13386633.34
729522 | 107905 | FAASt [Automation Program Group 1A-8 Feeders] (Distribution) | 14F019070000 | PBUT04 - Distribution Automation | Grid Automation | Distribution Automation |  |  |  |  | Past | TRUE | Voluntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45148 | 8/25/2023 | [7 empty] | 700000000 | 700000000 | [5 empty] | 0 | 700000000 | 700000000 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/398/DR4339PR%20-%20ISOW%20T%20and%20D%20Auto.%20Prog.%20Intelligent%20Recls,%20Single%20Ph%20Rec%20and%20Fault%20Current%20Indicators.pdf | 9/12/2024 - GP Notes "9/5/2024 The project was withdrawn with the comment "Applicant requested project withdrawal, for reference see: 729522-DR4339PR-Applicant requested project withdrawal.pdf". | 45856.7694 | 45160.443 | Gabriel Licha | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Rey Roldan Rodríguez | 0 Months |  |  |  | 1 | 1 |  | 729522RFI397 | 729522 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
729286 | 11726 | FAASt HV Equipment Replacement Group 2 (Substation) | 14F019990000, 14F020000000, 14F020100000, 14F019980000, 14F020200000, 14F021120000, 14F021130000, 14F019970000 | PBUT07 - Substation Reliability | Substation | Substation Rebuilds |  | Restoration | FALSE |  | Past | [13 empty] | 45124 | 8/23/2023 | 45199 | 45198 | 45379 |  |  |  | 5 | 25611121 | 15413889.89 | 0 | 2006783 |  | 15413890 | 0 | 0 | 15413890 | 17420673 | 45473 | 45535 | 45481 | 8/30/2024 | 15413889.89 | 15413889.89 | 15413889.89 | 15413889.89 |  |  |  | 15413889.89 | 15413889.89 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/400/729286%20DR4339PR%20FAASt%20HV%20Equipment%20Replacement%20Group%202%20(1).pdf?web=1 |  | 46070.4773 | 45162.3412 | Gabriel Licha | Substation High Voltage Equipment Replacement | Marlina Crespo |  |  | 2006783 |  | 1 | 1 |  | 729286RFI398 | 729286 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
730821 | 107911 | FAASt [Feeders - Arecibo Short Term Group 2] (Distribution) | 14F000140000, 14F000150000, 14F000120000, 14F000110000, 14F000130000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild | Distribution Line Rebuild |  | Restoration | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 73900000 | 44438 | 44428 |  | 44468 |  |  |  | 45169 | 09/11/2023 | 45199 | 45198 |  |  |  |  | 2 | 73910000 | 80513487 | 27363279 | 6380697 |  | 53150208 | 2513389 | 24849890 | 80513487 | 86894184 | 45777 | 45961 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/402/10134-EN-SOW-0001_Rev%20ARECIBO%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 45887.6449 | 45170.6032 | Marlina Crespo | Distribution Feeders - Arecibo Short Term Group 2 | Ashleah Dingle |  |  |  |  | 1 | 1 | 45884 | 730821RFI399 | 730821 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
730824 | 107912 | FAASt [Feeders - Ponce Short Term Group 2] (Distribution) | 14F001400000, 14F001370000, 14F001390000, 14F001380000, 14F001410000, 14F001420000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild | Distribution Line Rebuild |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | FALSE |  | 42380000 | [7 empty] | 45169 | 09/11/2023 | 45260 | 45260 |  |  |  |  | 1 | 42380000 | 42380000 | 2840853 | 1157768 |  | 2957665 | 799199 | 2041654 | 5798518 | 6956286 | 45838 | 45991 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/403/10141-EN-SOW-0001_Rev%20Ponce%202%20-%20signed.pdf?web=1 |  | 46077.5749 | 45170.6045 | Marlina Crespo | Distribution Feeders ‐ Ponce Short Term Group 2 | Ashleah Dingle |  |  |  |  | 7.3088 | 1 | 45884 | 730824RFI400 | 730824 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
730513 | 107907 | FAASt [Feeders-Caguas Short Term Group 4] (Distribution) | 14F000670000, 14F000690000, 14F000780000, 14F000630000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild | Distribution Line Rebuild |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 44710000 | [7 empty] | 45169 | 09/07/2023 | 45199 | 45198 | 45260 |  |  |  | 2 | 44710000 | 38886020 | 10929872 | 3184390 |  | 24634172 | 1251143 | 9678729 | 35564044 | 38748434 | 45626 | 45808 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/404/10148-EN-ISOW-0001_Rev%20Caguas%204%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 45887.6364 | 45170.6058 | Marlina Crespo | Distribution Feeders ‐ Caguas Short Term Group 4 | Ashleah Dingle |  |  |  |  | 1.0934 | 1 | 45884 | 730513RFI401 | 730513 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
730541 | 107908 | FAASt [Feeders - Caguas Short Term Group 8] (Distribution) | 14F000370000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild | Distribution Line Rebuild |  | Restoration | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | FALSE |  | 23640000 | [7 empty] | 45169 | 09/07/2023 | 45199 | 45199 |  |  |  |  | 2 | 23650000 | 31124653 | 18671456 | 2070079 |  | 12453197 | 2618347 | 16053109 | 31124653 | 33194732 | 45596 | 45777 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/405/10152-EN-ISOW-0001_Rev%20Caguas%208%20-%20signed.pdf?web=1 |  | 46077.5747 | 45170.607 | Marlina Crespo | Distribution Feeders ‐ Caguas Short Term Group 8 | Ashleah Dingle |  |  |  |  | 1 | 1 | 45884 | 730541RFI402 | 730541 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
730586 | 107909 | FAASt [Feeders - Ponce Short Term Group 1] (Distribution) | 14F001300000, 14F001310000, 14F001330000, 14F001350000, 14F001320000, 14F001340000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild | Distribution Line Rebuild |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | FALSE |  | 40610000 | [7 empty] | 45169 | 09/08/2023 | 45199 | 45198 |  |  |  |  | 2 | 40600000 | 26972761 | 12719346 | 4716393 |  | 14253415 | 3101803 | 9617543 | 26972761 | 31689154 | 45838 | 45991 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/406/10012-EN-SOW-0001_Rev%20Ponce%201%20-%20signed%20(1).pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 46077.5747 | 45170.6077 | Marlina Crespo | Distribution Feeders ‐ Ponce Short Term Group 1 | Ashleah Dingle |  |  |  |  | 1 | 1 | 45884 | 730586RFI403 | 730586 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
738972 | 107931 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 3 - Phase 2] (Distribution) | 14F018500000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | [6 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active | [10 empty] | 45182 | 11/17/2023 | [7 empty] | 3500000 | 3500000 | [5 empty] | 0 | 3500000 | 3500000 | [11 empty] | 0 | 0 | 43544 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/407/FEMA%20ISOW%20Distribution%20Pole%20and%20Conductor%20Repair%20-%20Caguas%20Group%203%20-%20Phase%202%20(2).pdf?web=1 | 3/27/2024 - Received withdrawal status data/info from Project Coordinator Yaritza Acevedo Ortiz. | 45856.7694 | 45176.6606 | Gabriel Licha | Distribution Streetlighting | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 738972RFI404 | 738972 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
738971 | 11812 | FAASt [Pole and Conductor Repair - Caguas Group 2 - Phase 2] (Distribution) | 14F018490000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement |  |  | Restoration | FALSE |  | Past | [13 empty] | 45176 | 11/17/2023 |  | 45328 | 45425 | 45667 | 45660 |  | 2 | 3000000 | 14261249.67 | 377124 | 1643630 |  | 13884126 | 66835.67 | 310288.33 | 14261250 | 15904880 | 45504 | 45596 | 45694 |  | 14261249.67 | 13884126 | [5 empty] | 14261249.67 | 13884126 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/408/FEMA%20ISOW%20Distribution%20Pole%20and%20Conductor%20Repair%20-%20Caguas%20Group%202%20-%20Phase%202.pdf?web=1 |  | 45856.7694 | 45176.6628 | Gabriel Licha | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 1643630 | 33543 | 1 | 1 |  | 738971RFI405 | 738971 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 343580.67
730657 | 11559 | FAASt [Line 2200 Dos Bocas HP to Dorado TC ] (Transmission) | 14F002380000, 14F002380000, 14F002380000, 14F002380000, 14F002380000, 14F002380000, 14F002380000, 14F002380000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE |  | 103810000 | 44381 | 44428 |  | 44411 |  |  |  | 45177 | 09/08/2023 | 45382 | [6 empty] | 103800000 | 0 | [5 empty] | 0 | 103800000 | 103800000 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/409/334468-DR4339PR-Initial%20SOW%20(2).pdf?web=1 |  | 46077.5788 | 45180.6166 | Marlina Crespo | Line 2200 Dos Bocas HP to Dorado TC | Ashleah Dingle |  |  |  |  | 0 | 5 | 45887 | 730657RFI406 | 730657 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
730784 | 107910 | FAASt [ Line 6700 Martin Peña TC to Villamar Sect.] (Transmission) | 14F002500000 | PBUT33 - T Line Rebuild | Transmission | Transmission Line Rebuild |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active |  |  | 6010000 |  |  | 45436 |  |  |  |  | 45180 | 09/11/2023 | [7 empty] | 6010000 | 6010000 | [5 empty] | 0 | 6010000 | 6010000 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/410/73784-DR4339PR-Line%206700%20Martin%20Pe%C3%B1a%20TC%20to%20Villamar%20Sect.pdf?web=1 | 3/28/2024 - Received withdrawal status data/info from Project Manager Claudio R. Jaquez. DSOW submittal forecast: 5/24/2024. | 45856.7694 | 45181.3629 | Marlina Crespo | Line 6700 Martin Peña TC to Villamar Sect. | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 730784RFI407 | 730784 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
738670 | 11712 | FAASt [Pole and Conductor Repair - Ponce Group 1 - Phase 2] (Distribution) | 14F018990000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement |  |  | Restoration | FALSE |  | Past | [13 empty] | 45205 | 11/15/2023 | 45291 | 45310 | 45338 | 45590 | 45587 |  | 3 | 7140000 | 5074511.01 | 147871 | 439975 |  | 4926640 | 31370.9 | 116500.1 | 5074511 | 5514486 | 45473 | 45626 | 45621 |  | 5074511.01 | 4926640 | [5 empty] | 5074511.01 | 4926640 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/436/FEMA%20ISOW%20Distribution%20Pole%20and%20Conductor%20Repair%20-%20Ponce%20Group%201%20-%20Phase%202.pdf?web=1 |  | 45856.7694 | 45208.3731 | Marlina Crespo | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 439974.62 |  | 1 | 1 |  | 738670RFI408 | 738670 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 147871.01
737825 | 107925 | FAAST[Distribution Pole and Conductor Repair - San Juan Group 1 - Phase 2] (Distribution) | 14F019010000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | [6 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Retired FAASt -- New FAASt Created | [10 empty] | 45205 | 11/07/2023 | 45291 | [6 empty] | 7140000 | 7140000 | [5 empty] | 0 | 7140000 | 7140000 | [11 empty] | 0 | 0 | 43544 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/437/-DR4339PR-Detailed%20SOW%20San%20Juan%20Group%201%20-%20Phase%202%20Rev0%201.pdf?web=1 | Project was resubmitted into Grants Portal under a new FAAst #. Old number was 737825. New number is 742070. Edited on 01/10/2024 by J Fournier. 3/27/2024 - Received withdrawal status data/info from Project Coordinator Yaritza Acevedo Ortiz. | 45856.7694 | 45208.3752 | Marlina Crespo | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 737825RFI409 | 737825 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
738667 | 107927 | FAASt [Pole and Conductor Repair - Ponce Group 2 - Phase 2] (Distribution) | 14F019000000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement |  |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45205 | 11/15/2023 | 45382 | 45488 | 45821 |  |  |  |  | 6120000 | 6120000 | 33268.04 | 1724241.14 |  | 14893960.55 | 17535.19 | 15732.85 | 14927228.59 | 16651469.73 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/438/FEMA%20ISOW%20Distribution%20Pole%20and%20Conductor%20Repair%20-%20Ponce%20Group%202%20-%20Phase%202.pdf?web=1 |  | 45980.6699 | 45208.3765 | Marlina Crespo | Distribution Pole & Conductor Replacement | Marlina Crespo |  |  |  |  | 0.40999 | 3 | 45877 | 738667RFI410 | 738667 | 1436520 | 138772.32 | 1575292.32 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
738143 | Project Not In GP | FAASt [Distribution Pole and Conductor Repair - San Juan Group 2 - Phase 2] (Distribution) | 14F019020000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement | [6 empty] | TRUE | Involuntarily Withdrawal Status in Grants Portal | Retired FAASt -- New FAASt Created | [10 empty] | 45205 | 11/09/2023 | 45291 | [6 empty] | 5100000 | 5100000 | [5 empty] | 0 | 5100000 | 5100000 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/439/FEMA%20ISOW%20Distribution%20Pole%20and%20Conductor%20Repair%20-%20San%20Juan%20Group%202%20-%20Phase%202.pdf?web=1 | 3/27/2024 - Received withdrawal status data/info from Project Coordinator Yaritza Acevedo Ortiz. Project was resubmitted into Grants Portal under a new FAAst #7420269/13/2024 - GP Notes "11/29/2023 The project was deleted" - GP Query pulls as old status "Pending Formulation Completion" ensure to filter out project | 45880.3899 | 45208.3775 | Marlina Crespo | Distribution Pole & Conductor Replacement | Ashleah Dingle |  |  |  |  | 1 | 1 | 45259 | 738143RFI411 | 738143 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
738672 | 11686 | FAASt [Pole and Conductor Repair - Mayaguez Group 1 - Phase 2] (Distribution) | 14F018870000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement |  |  | Restoration | FALSE |  | Past | [13 empty] | 45205 | 11/15/2023 | 45260 | 45264 | 45399 | 45587 | 45580 |  | 2 | 8160000 | 10619758.37 | 306131 | 834793 |  | 10313627 | 63002.37 | 243128.63 | 10619758 | 11454551 | 45473 | 45626 | 45621 |  | 10619758.37 | 10313627 | [5 empty] | 10619758.37 | 10313627 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/440/FEMA%20SOW%20Distribution%20Pole%20and%20Conductor%20Repair%20-%20Mayaguez%20Group%201%20-%20Phase%202.pdf?web=1 |  | 45856.7694 | 45208.3787 | Marlina Crespo | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 834793 |  | 1 | 1 |  | 738672RFI412 | 738672 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 306131.37
738674 | 107928 | FAASt [Pole and Conductor Repair - Mayaguez Group 2 - Phase 2] (Distribution) | 14F018960000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement |  |  | Restoration | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45205 | 11/15/2023 | 45382 | 45476 | 45821 |  |  |  |  | 9180000 | 9180000 | 28130.53 | 922352.8 |  | 8013484.69 | 14786.8 | 13343.73 | 8041615.22 | 8963968.02 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/441/FEMA%20SOW%20Distribution%20Pole%20and%20Conductor%20Repair%20-%20Mayaguez%20Group%202%20-%20Phase%202.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 45980.6711 | 45208.3799 | Marlina Crespo | Distribution Pole & Conductor Replacement | Marlina Crespo | 0 months |  |  |  | 1.1416 | 1 | 45877 | 738674RFI413 | 738674 | 727458.75 | 84241.09 | 811699.84 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
738696 | 107930 | FAASt [Distribution Pole and Conductor Repair - Carolina Group 2 - Phase 2] (Distribution) | 14F018940000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement |  |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Active | [10 empty] | 45205 | 11/15/2023 | [7 empty] | 5100000 | 5100000 | [5 empty] | 0 | 5100000 | 5100000 | [11 empty] | 0 | 0 | 43544 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/442/FEMA%20SOW%20Distribution%20Pole%20and%20Conductor%20Repair%20-%20Carolina%20Group%202%20-%20Phase%202.pdf?web=1 | 3/27/2024 - Received withdrawal status data/info from Project Coordinator Yaritza Acevedo Ortiz. | 45856.7694 | 45208.3809 | Marlina Crespo | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | 738696RFI414 | 738696 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
738692 | 107929 | FAASt [Pole and Conductor Repair - Carolina Group 1 - Phase 2] (Distribution) | 14F018930000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement |  |  |  | TRUE | 45900 |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45205 | 11/15/2023 | [7 empty] | 5100000 | 5100000 | [5 empty] | 0 | 5100000 | 5100000 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/443/FEMA%20SOW%20Distribution%20Pole%20and%20Conductor%20Repair%20-%20Carolina%20Group%201%20-%20Phase%202.pdf?web=1 |  | 45881.4694 | 45208.382 | Marlina Crespo | Distribution Pole & Conductor Replacement | Maria Mujica Gonzalez |  |  |  |  | 1 | 1 | 45880 | 738692RFI415 | 738692 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
734393 | 11805 | FAASt [Cabo Rojo Streetlighting - Part 2] (Distribution) | 14F018570000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45209 | 10/11/23 |  | 45412 |  |  |  |  | 1 | 6205493 | 7838709 | 1016421 | 1851275 |  | 7838709 | 194188 | 822233 | 8855130 | 10706405 | 45473 | 45626 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/444/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Cabo%20Rojo%20Phase%202%20Medium%20Priority%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 45876.628 | 45210.4408 | Marlina Crespo | Distribution Streetlighting | Maria Mujica Gonzalez |  |  |  |  | 0.88522 | 1 | 45875 | 734393RFI416 | 734393 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
735474 | 107918 | FAASt [Pole and Conductor Repair -Caguas Group 3 Phase 2] (Distribution) | 14F018500000 | PBUT05 - Distr Streetlighting | Distribution – Pole Replacement |  |  |  | FALSE |  | Current | FALSE | Involuntarily Withdrawal Status in Grants Portal | Resubmitted | [5 empty] | 45378 |  |  |  |  | 45209 | 10/20/2023 |  | 45688 | 46073 | 45791 | 45779 |  |  | 11758959 | 3500000 | 584317.53 | 1524520.51 | 1144636.03 | 18356551.25 | 44806.65 | 539510.88 | 18940868.78 | 20465389.29 | 46173 | 46295 | 45917 |  | 14075641 | 14075641 |  |  |  | 2709364 |  | 14075641 | 14075641 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/445/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Caguas%20Phase%202%20Medium%20Priority%20-%20signed.pdf?web=1 | 3/28/2024 - Received withdrawal status data/info from Project Manager Mariano Pérez Portocarrero. DSOW was submitted 3.27.2024 on project 136271 for FEMA revision and project formulation.3/25/2024: QC Review Complete11/29 The project was withdrawn.4/11 Project unwithdrawn by System Admin per FEMA Request ServiceNow INC1016831 | 46078.6794 | 45210.4416 | Marlina Crespo | Distribution Streetlighting | Marlina Crespo |  |  | 1962096.73 | 0 | 0.18479 | 5 |  | 735474RFI417 | 735474 | 1317347.93 | 295487.07 | 1612835 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
734396 | 107915 | FAASt [Cabo Rojo Streetlighting - Part 3] (Distribution) | 14F018580000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45209 | 10/11/23 |  | 45485 | [5 empty] | 6205493 | 6205493 | 1169678 | 1692815 |  | 6988631 | 228078 | 941600 | 8158309 | 9851124 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/446/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Cabo%20Rojo%20Phase%203%20Low%20Priority%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 45876.6281 | 45210.4425 | Marlina Crespo | Distribution Streetlighting | Maria Mujica Gonzalez | 0 Months |  |  |  | 0.76063 | 2 | 45875 | 734396RFI418 | 734396 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
735483 | 107919 | FAASt [Vega Baja Streetlighting - Part 3] (Distribution) | 14F018860000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  |  | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [5 empty] | 45471 |  |  |  |  | 45209 | 10/20/2023 | [7 empty] | 5377685 | 5377685 | [5 empty] | 0 | 5377685 | 5377685 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/447/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Vega%20Baja%20Phase%203%20Low%20Priority%20-%20signed.pdf?web=1 | 08/06/2025 - Previously withdrawn and resubmitted. Withdrawn again on 08/05/2025 3/28/2024 - Received withdrawal status data/info from Project Manager Mariano Pérez Portocarrero. 11/29 The project was withdrawn.4/11 Project unwithdrawn by System Admin per FEMA Request ServiceNow INC10168317/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 45875.3876 | 45210.4435 | Marlina Crespo | Distribution Streetlighting | Ashleah Dingle | 0 Months |  |  |  | 1 | 1 | 45874 | 735483RFI419 | 735483 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
734760 | 11830 | FAASt [Ponce Streetlighting - Part 3] (Distribution) | 14F018740000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45209 | 10/13/2023 |  | 45443 | 45448 |  |  |  | 2 | 14475396 | 13799462 | 1946734 | 2696696 |  | 13799462 | 318240 | 1628494 | 15746196 | 18442892 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/448/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Ponce%20Phase%203%20Low%20Priority%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 45980.6845 | 45210.4442 | Marlina Crespo | Distribution Streetlighting | Marlina Crespo |  |  |  |  | 0.87637 | 1 | 45875 | 734760RFI420 | 734760 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
735360 | 11832 | FAASt [Mayaguez Streetlighting - Part 3] (Distribution) | 14F018720000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45209 | 10/19/2023 |  | 45443 | 45448 |  |  |  | 2 | 8010318 | 13951292 | 2189842 | 2675465 |  | 13951292 | 352374 | 1837468 | 16141134 | 18816599 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/449/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Mayaguez%20Phase%203%20Low%20Priority%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 45880.3867 | 45210.4447 | Marlina Crespo | Distribution Streetlighting | Ashleah Dingle | 0 Months |  |  |  | 0.86433 | 1 | 45874 | 735360RFI421 | 735360 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
734728 | 11774 | FAASt [Ponce Streetlighting - Part 2] (Distribution) | 14F018730000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45209 | 10/13/2023 |  | 45378 | 45394 |  |  |  | 2 | 14475396 | 12998720.23 | 1402396 | 2475101 |  | 12998720 | 224318 | 1178078 | 14401116 | 16876217 | 45473 | 45626 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/450/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Ponce%20Phase%202%20Medium%20Priority%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short List | 45876.6281 | 45210.4473 | Marlina Crespo | Distribution Streetlighting | Maria Mujica Gonzalez |  |  |  |  | 0.90262 | 1 | 45875 | 734728RFI422 | 734728 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
735357 | 11777 | FAASt [Mayaguez Streetlighting - Part 2] (Distribution) | 14F018710000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45209 | 10/19/2023 |  | 45378 | 45394 |  |  |  | 2 | 8010318 | 7368131.58 | 1097078 | 1731118 |  | 7368132 | 208717 | 888361 | 8465210 | 10196328 | 45473 | 45626 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/451/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Mayaguez%20Phase%202%20Medium%20Priority%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short List | 45880.386 | 45210.4479 | Marlina Crespo | Distribution Streetlighting | Ashleah Dingle |  |  |  |  | 0.8704 | 1 | 45874 | 735357RFI423 | 735357 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
734928 | 107917 | FAASt [Isabela Streetlighting - Part 3] (Distribution) | 14F018700000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  |  | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45209 | 10/16/2023 | [7 empty] | 5293882 | 5293882 | [5 empty] | 0 | 5293882 | 5293882 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/452/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Isabela%20Phase%203%20Low%20Priority%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 45880.385 | 45210.4485 | Marlina Crespo | Distribution Streetlighting | Ashleah Dingle | 0 Months |  |  |  | 1 | 1 | 45874 | 734928RFI424 | 734928 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
734927 | 11773 | FAASt [Isabela Streetlighting - Part 2] (Distribution) | 14F018690000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45209 | 10/16/2023 |  | 45378 | 45394 |  |  |  | 2 | 5293882 | 8007445.57 | 1301829 | 1834728 |  | 8007445 | 242681 | 1059148 | 9309274 | 11144002 | 45473 | 45626 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/453/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Isabela%20Phase%202%20Medium%20Priority%20-%20signed.pdf?web=1 | 3/25/2024: QC Review Complete7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 45880.3847 | 45210.4502 | Marlina Crespo | Distribution Streetlighting | Ashleah Dingle |  |  |  |  | 0.86016 | 1 | 45874 | 734927RFI425 | 734927 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
735487 | 107920 | FAASt [Humacao Streetlighting - Part 3] (Distribution) | 14F018680000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  |  | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [5 empty] | 45471 |  |  |  |  | 45209 | 10/20/2023 |  | 45526 | [5 empty] | 5817139 | 5817139 | 916292 | 1627090 |  | 7901161 | 188693 | 727599 | 8817453 | 10444543 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/454/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Humacao%20Phase%203%20Low%20Priority%20-%20signed.pdf?web=1 | 08/06/2025 - Previously withdrawn and resubmitted. Withdrawn again on 08/05/2025 3/28/2024 - Received withdrawal status data/info from Project Manager Mariano Pérez Portocarrero. 11/29 The project was withdrawn.4/11 Project unwithdrawn by System Admin per FEMA Request ServiceNow INC10168317/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 45875.3873 | 45210.451 | Marlina Crespo | Distribution Streetlighting | Ashleah Dingle | 0 Months |  |  |  | 0.65973 | 2 | 45874 | 735487RFI426 | 735487 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
734791 | 11808 | FAASt [Guayama Streetlighting - Part 2] (Distribution) | 14F018630000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45209 | 10/13/2023 |  | 45412 |  |  |  |  | 1 | 5424696 | 5650820 | 757008 | 1536868 |  | 5650820 | 161863 | 595145 | 6407828 | 7944696 | 45473 | 45626 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/455/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Guayama%20Phase%202%20Medium%20Priority%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short List | 45876.6281 | 45210.4552 | Marlina Crespo | Distribution Streetlighting | Maria Mujica Gonzalez |  |  |  |  | 0.88186 | 1 | 45875 | 734791RFI427 | 734791 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
735493 | 11799 | FAASt [Humacao Streetlighting - Part 2] (Distribution) | 14F018670000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [5 empty] | 45412 |  |  |  |  | 45209 | 10/20/2023 |  | 45412 |  |  |  |  | 1 | 5817139 | 6274071 | 916292 | 1627090 |  | 6274071 | 188693 | 727599 | 7190363 | 8817453 | 45473 | 45626 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/456/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Humacao%20Phase%202%20Medium%20Priority%20-%20signed.pdf?web=1 | 08/06/2025 - Previously withdrawn and resubmitted. Withdrawn again on 08/05/2025 3/28/2024 - Received withdrawal status data/info from Project Manager Mariano Pérez Portocarrero. 11/29 The project was withdrawn.4/11 Project unwithdrawn by System Admin per FEMA Request ServiceNow INC10168317/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short List | 45875.3882 | 45210.4558 | Marlina Crespo | Distribution Streetlighting | Ashleah Dingle |  |  |  |  | 0.87257 | 1 | 45874 | 735493RFI428 | 735493 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
734789 | 107916 | FAASt [Guayama Streetlighting - Part 3 ] (Distribution) | 14F018640000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  |  | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45209 | 10/13/2023 |  | 45526 | [5 empty] | 5424696 | 5424696 | 635977 | 1444780 |  | 6296106 | 145939 | 490038 | 6932083 | 8376863 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/457/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Guayama%20Phase%203%20Low%20Priority%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 45876.6281 | 45210.4563 | Marlina Crespo | Distribution Streetlighting | Maria Mujica Gonzalez |  |  |  |  | 0.78255 | 2 | 45875 | 734789RFI429 | 734789 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
735496 | 11835 | FAASt [Carolina Streetlighting - Part 3] (Distribution) | 14F018620000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [5 empty] | 45443 |  |  |  |  | 45209 | 10/20/2023 |  | 45443 | 45448 |  |  |  | 2 | 11936785 | 14764763 | 2019124 | 2756137 |  | 14764763 | 317620 | 1701504 | 16783887 | 19540024 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/458/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Carolina%20Phase%203%20Low%20Priority%20-%20signed.pdf?web=1 | 08/06/2025 - Previously withdrawn and resubmitted. Withdrawn again on 08/05/2025 3/28/2024 - Received withdrawal status data/info from Project Manager Mariano Pérez Portocarrero. 11/29 The project was withdrawn.4/11 Project unwithdrawn by System Admin per FEMA Request ServiceNow INC10168317/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 45875.3893 | 45210.4617 | Marlina Crespo | Distribution Streetlighting | Ashleah Dingle | 0 Months |  |  |  | 0.8797 | 1 | 45874 | 735496RFI430 | 735496 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
735499 | 107921 | FAASt [Guaynabo Streetlighting - Part 3] (Distribution) | 14F018660000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  |  | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [5 empty] | 45471 |  |  |  |  | 45209 | 10/20/2023 | [7 empty] | 7033301 | 7033301 | [5 empty] | 0 | 7033301 | 7033301 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/459/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Guaynabo%20Phase%203%20Low%20Priority%20-%20signed.pdf?web=1 | 3/28/2024 - Received withdrawal status data/info from Project Manager Mariano Pérez Portocarrero. 11/29 The project was withdrawn.4/11 Project unwithdrawn by System Admin per FEMA Request ServiceNow INC10168317/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 45876.6282 | 45210.4629 | Marlina Crespo | Distribution Streetlighting | Maria Mujica Gonzalez | 0 Months |  |  |  | 1 | 1 | 45875 | 735499RFI431 | 735499 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
735665 | 11783 | FAASt [Carolina Streetlighting - Part 2] (Distribution) | 14F018610000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45209 | 10/23/2023 |  | 45379 | 45394 |  |  |  | 2 | 11936785 | 12296300.92 | 557536 | 2334972 |  | 12296301 | 88976 | 468560 | 12853837 | 15188809 | 45473 | 45626 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/460/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Carolina%20Phase%202%20Medium%20Priority%20-%20signed.pdf?web=1 | 3/25/2024: QC Review Complete7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short List | 45876.6282 | 45210.4637 | Marlina Crespo | Distribution Streetlighting | Maria Mujica Gonzalez |  |  |  |  | 0.95662 | 1 | 45875 | 735665RFI432 | 735665 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
735672 | 11838 | FAASt [Caguas Streetlighting - Part 3] (Distribution) | 14F018600000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45209 | 10/23/2023 |  | 45443 | 45448 |  |  |  | 2 | 11758959 | 11986815 | 1624355 | 2432645 |  | 11986815 | 274039 | 1350316 | 13611170 | 16043815 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/461/FEMA%20ISOW%20Distribution%20Streetlighting%20-%20Caguas%20Phase%203%20Low%20Priority%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 45876.6282 | 45210.4644 | Marlina Crespo | Distribution Streetlighting | Maria Mujica Gonzalez | 0 Months |  |  |  | 0.88066 | 1 | 45875 | 735672RFI433 | 735672 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
735677 | 11801 | FAASt [Guaynabo Streetlighting - Part 2] (Distribution) | 14F018650000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45209 | 10/23/2023 |  | 45412 |  |  |  |  | 1 | 7033301 | 7566377 | 1014066 | 1759349 |  | 7566377 | 191308 | 822758 | 8580443 | 10339792 | 45473 | 45626 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/462/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Guaynabo%20Phase%202%20Medium%20Priority%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 45876.6282 | 45210.465 | Marlina Crespo | Distribution Streetlighting | Maria Mujica Gonzalez |  |  |  |  | 0.88182 | 1 | 45875 | 735677RFI434 | 735677 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
735940 | 11806 | FAASt [Vega Baja Streetlighting - Part 2] (Distribution) | 14F018850000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45209 | 10/25/2023 |  | 45412 |  |  |  |  | 1 | 5377685 | 7551926.09 | 1067250 | 1758054 |  | 7551927 | 201535 | 865715 | 8619177 | 10377231 | 45473 | 45626 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/463/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Vega%20Baja%20Phase%202%20Medium%20Priority%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 45876.6283 | 45210.4652 | Marlina Crespo | Distribution Streetlighting | Maria Mujica Gonzalez |  |  |  |  | 0.87618 | 1 | 45875 | 735940RFI435 | 735940 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
735952 | 11831 | FAASt [Trujillo Alto Streetlighting - Part 3] (Distribution) | 14F018840000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45209 | 10/25/2023 |  | 45443 | 45448 |  |  |  | 2 | 5588214 | 7111974 | 1149506 | 1726148 |  | 7111974 | 224507 | 924999 | 8261480 | 9987628 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/464/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Trujillo%20Alto%20Phase%203%20Low%20Priority%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 45876.6283 | 45210.4669 | Marlina Crespo | Distribution Streetlighting | Maria Mujica Gonzalez | 0 Months |  |  |  | 0.86086 | 1 | 45875 | 735952RFI436 | 735952 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
735954 | 11772 | FAASt [Trujillo Alto Streetlighting - Part 2] (Distribution) | 14F018830000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45209 | 10/25/2023 |  | 45378 | 45394 |  |  |  | 2 | 5588214 | 6426439.39 | 884864 | 1636132 |  | 6426439 | 179565 | 705299 | 7311303 | 8947435 | 45473 | 45626 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/465/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Trujillo%20Alto%20Phase%202%20Medium%20Priority%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short List | 45876.6283 | 45210.4695 | Marlina Crespo | Distribution Streetlighting | Maria Mujica Gonzalez |  |  |  |  | 0.87897 | 1 | 45875 | 735954RFI437 | 735954 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
735959 | 107922 | FAASt [Toa Baja Streetlighting - Part 3] (Distribution) | 14F018820000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  |  | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45209 | 10/25/2023 | [7 empty] | 5878458 | 5878458 | [5 empty] | 0 | 5878458 | 5878458 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/466/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Toa%20Baja%20Phase%203%20Low%20Priority%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 45876.6283 | 45210.4701 | Marlina Crespo | Distribution Streetlighting | Maria Mujica Gonzalez | 0 Months |  |  |  | 1 | 1 | 45875 | 735959RFI438 | 735959 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
735960 | 11803 | FAASt [Toa Baja Streetlighting - Part 2] (Distribution) | 14F018810000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45209 | 10/25/2023 |  | 45412 |  |  |  |  | 1 | 5878458 | 7964179 | 1238774 | 1818344 |  | 7964179 | 230260 | 1008514 | 9202953 | 11021297 | 45473 | 45626 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/467/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Toa%20Baja%20Phase%202%20Medium%20Priority%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 45876.6201 | 45210.4705 | Marlina Crespo | Distribution Streetlighting | Jason Fournier |  |  |  |  | 0.86539 | 1 | 45875 | 735960RFI439 | 735960 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
737699 | 107923 | FAASt [Toa Alta Streetlighting - Part 3] (Distribution) | 14F018800000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  |  | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [5 empty] | 45471 |  |  |  |  | 45209 | 11/07/2023 | [7 empty] | 5526895 | 5526895 | [5 empty] | 0 | 5526895 | 5526895 | [11 empty] | 0 | 0 | 43544 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/468/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Toa%20Alta%20Phase%203%20Low%20Priority%20-%20signed.pdf?web=1 | 3/28/2024 - Received withdrawal status data/info from Project Manager Mariano Pérez Portocarrero. 11/29 The project was withdrawn.4/11 Project unwithdrawn by System Admin per FEMA Request ServiceNow INC10168317/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 45876.631 | 45210.4711 | Marlina Crespo | Distribution Streetlighting | Jason Fournier | 0 Months |  |  |  | 1 | 1 | 45876 | 737699RFI440 | 737699 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
737707 | 11797 | FAASt [Toa Alta Streetlighting - Part 2] (Distribution) | 14F018790000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [5 empty] | 45412 |  |  |  |  | 45209 | 11/07/2023 |  | 45412 |  |  |  |  | 1 | 5526895 | 7066938 | 979674 | 1741115 |  | 7066938 | 193656 | 786018 | 8046612 | 9787727 | 45473 | 45626 | [9 empty] | 0 | 0 | 43544 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/469/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Toa%20Alta%20Phase%202%20Medium%20Priority%20-%20signed.pdf?web=1 | 3/28/2024 - Received withdrawal status data/info from Project Manager Mariano Pérez Portocarrero. 11/29 The project was withdrawn.4/11 Project unwithdrawn by System Admin per FEMA Request ServiceNow INC10168317/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 45876.6325 | 45210.472 | Marlina Crespo | Distribution Streetlighting | Jason Fournier |  |  |  |  | 0.87825 | 1 | 45876 | 737707RFI441 | 737707 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
737712 | 11836 | FAAST [San Juan Streetlighting - Part 3] (Distribution) | 14F018780000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [5 empty] | 45443 |  |  |  |  | 45209 | 11/07/2023 |  | 45443 | 45448 |  |  |  | 2 | 24022779 | 27223280 | 3250259 | 4358459 |  | 27223280 | 448553 | 2801706 | 30473539 | 34831998 | [11 empty] | 0 | 0 | 43544 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/470/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20San%20Juan%20Phase%203%20Low%20Priority%20-%20signed.pdf?web=1 | 3/28/2024 - Received withdrawal status data/info from Project Manager Mariano Pérez Portocarrero. 11/29 The project was withdrawn.4/11 Project unwithdrawn by System Admin per FEMA Request ServiceNow INC10168317/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 45876.633 | 45210.4744 | Marlina Crespo | Distribution Streetlighting | Jason Fournier | 0 Months |  |  |  | 0.89334 | 1 | 45876 | 737712RFI442 | 737712 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
738120 | 11850 | FAASt [Pole and Conductor Repair-Carolina Group 2- Phase 2] (Distribution) | 14F018940000 | PBUT05 - Distr Streetlighting | Distribution – Pole Replacement | Distribution Streetlighting |  | Restoration | FALSE |  | Past | FALSE | Involuntarily Withdrawal Status in Grants Portal | Resubmitted | [5 empty] | 45378 |  |  |  |  | 45209 | 11/09/2023 |  | 45436 |  | 45601 | 45593 |  | 1 | 24022779 | 11451170.81 | 286036 | 1159111 |  | 11041271 | 175368.81 | 110667.19 | 11327307 | 12486418 | 45473 | 45626 | 45621 |  | 11451170.81 | 11041271 | [5 empty] | 11451170.81 | 11041271 | 43544 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/471/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20San%20Juan%20Phase%202%20Medium%20Priority%20-%20signed.pdf?web=1 | 3/28/2024 - Received withdrawal status data/info from Project Manager Mariano Pérez Portocarrero. DSOW was submitted 3.27.2024 on project 136271 for FEMA revision and project formulation.11/29 The project was withdrawn.4/11 Project unwithdrawn by System Admin per FEMA Request ServiceNow INC10168317/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 45856.7695 | 45210.4752 | Marlina Crespo | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 1159111 |  | 1.0109 | 1 |  | 738120RFI443 | 738120 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 409899.81
737798 | 107924 | FAASt [Rio Grande Streetlighting - Part 3] (Distribution) | 14F018760000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  |  | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [5 empty] | 45471 |  |  |  |  | 45209 | 11/07/2023 |  | 45526 | [5 empty] | 4962759 | 4962759 | 877731 | 1513312 |  | 7059041 | 188168 | 689563 | 7936772 | 9450084 | [11 empty] | 0 | 0 | 43544 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/472/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Rio%20Grande%20Phase%203%20Low%20Priority%20-%20signed.pdf?web=1 | 3/28/2024 - Received withdrawal status data/info from Project Manager Mariano Pérez Portocarrero. 11/29 The project was withdrawn.4/11 Project unwithdrawn by System Admin per FEMA Request ServiceNow INC10168317/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 45876.6338 | 45210.4759 | Marlina Crespo | Distribution Streetlighting | Jason Fournier | 0 Months |  |  |  | 0.62529 | 2 | 45876 | 737798RFI444 | 737798 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
737804 | 11809 | FAASt [Rio Grande Streetlighting - Part 2 ] (Distribution) | 14F018750000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [5 empty] | 45412 |  |  |  |  | 45209 | 11/07/2023 |  | 45412 |  |  |  |  | 1 | 4962759 | 6104606.88 | 838135 | 1588337 |  | 6104607 | 173048 | 665087 | 6942742 | 8531079 | 45473 | 45626 | [9 empty] | 0 | 0 | 43544 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/473/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Rio%20Grande%20Phase%202%20Medium%20Priority%20-%20signed.pdf?web=1 | <div class="ExternalClass8A3DEC4383DF43B983FFB9D352A22D75"><div style="font-family&#58;Calibri, Arial, Helvetica, sans-serif;font-size&#58;11pt;color&#58;rgb(0, 0, 0);"><span style="font-family&#58;Calibri, Arial, Helvetica, sans-serif;background-color&#58;rgb(255, 255, 255);display&#58;inline !important;">3/28/2024 - Received withdrawal status data/info from Project Manager Mariano Pérez Portocarrero.&#160;</span><br></div></div><div style="margin-top&#58;0px;margin-bottom&#58;0px;"><span style="color&#58;rgb(0, 0, 0);font-family&#58;Calibri, Arial, Helvetica, sans-serif;font-size&#58;14.6667px;background-color&#58;rgb(255, 255, 255);display&#58;inline !important;">11/29 The project was withdrawn.</span><br style="color&#58;rgb(0, 0, 0);font-family&#58;Calibri, Arial, Helvetica, sans-serif;font-size&#58;14.6667px;background-color&#58;rgb(255, 255, 255);"><span style="color&#58;rgb(0, 0, 0);font-family&#58;Calibri, Arial, Helvetica, sans-serif;font-size&#58;14.6667px;background-color&#58;rgb(255, 255, 255);display&#58;inline !important;">4/11 Project unwithdrawn by System Admin per FEMA Request ServiceNow INC1016831<p><span style="font-size&#58;14px;color&#58;rgb(50, 49, 48);">7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short List</span><br></p></span></div> | 45877.4898 | 45210.4769 | Marlina Crespo | Distribution Streetlighting | Maria Mujica Gonzalez |  |  |  |  | 0.87928 | 1 | 45876 | 737804RFI445 | 737804 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
735131 | 11775 | FAASt [Arecibo Streetlighting - Part 2] (Distribution) | 14F018530000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45210 | 10/18/2023 |  | 45378 | 45394 |  |  |  | 2 | 10338400 | 11247096.52 | 1546160 | 2337125 |  | 11247096 | 266012 | 1280148 | 12793256 | 15130381 | 45473 | 45626 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/474/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Arecibo%20Phase%202%20Medium%20Priority%20-%20signed.pdf?web=1 | QC Review Complete: Mar 25 20247/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short List | 45880.3853 | 45211.3703 | Marlina Crespo | Distribution Streetlighting | Ashleah Dingle |  |  |  |  | 0.87914 | 1 | 45874 | 735131RFI446 | 735131 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
734853 | 11837 | FAASt [Arecibo Streetlighting- Part 3] (Distribution) | 14F018540000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45210 | 10/16/2023 |  | 45443 | 45448 |  |  |  | 2 | 10338400 | 15679863.58 | 2684586 | 2921897 |  | 15679863 | 421685 | 2262901 | 18364449 | 21286346 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/475/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Arecibo%20Phase%203%20Low%20Priority%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 45876.6283 | 45211.3709 | Marlina Crespo | Distribution Streetlighting | Maria Mujica Gonzalez |  |  |  |  | 0.85382 | 1 | 45875 | 734853RFI447 | 734853 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
734859 | 11780 | FAASt [Aguadilla Streetlighting - Part 2] (Distribution) | 14F018510000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45210 | 10/16/2023 |  | 45378 | 45394 |  |  |  | 2 | 6655166 | 8885681.25 | 1346103 | 1987953 |  | 8885681 | 246099 | 1100004 | 10231784 | 12219737 | 45473 | 45626 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/476/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20iSOW%20Aguadilla%20Phase%202%20Medium%20Priority%20-%20signed.pdf?web=1 | QC Review Complete: 3/25/20247/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short List | 45876.6283 | 45211.3716 | Marlina Crespo | Distribution Streetlighting | Maria Mujica Gonzalez |  |  |  |  | 0.86844 | 1 | 45875 | 734859RFI448 | 734859 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
735472 | 11833 | FAASt [Bayamon Streetlighting - Part 3] (Distribution) | 14F018560000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [5 empty] | 45443 |  |  |  |  | 45210 | 10/20/2023 |  | 45443 | 45448 |  |  |  | 2 | 14963904 | 18291400 | 2632407 | 3249865 |  | 18291400 | 397144 | 2235263 | 20923807 | 24173672 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/477/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Bayam%C3%B3n%20Phase%203%20Low%20Priority%20-%20signed.pdf?web=1 | 08/06/2025 - Previously withdrawn and resubmitted. Withdrawn again on 08/05/2025 3/28/2024 - Received withdrawal status data/info from Project Manager Mariano Pérez Portocarrero.11/29 The project was withdrawn.4/11 Project unwithdrawn by System Admin per FEMA Request ServiceNow INC10168317/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 45875.3898 | 45211.3723 | Marlina Crespo | Distribution Streetlighting | Ashleah Dingle | 0 Months |  |  |  | 0.87419 | 1 | 45874 | 735472RFI449 | 735472 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
735470 | 11804 | FAASt [Bayamón Streetlighting - Part 2] (Distribution) | 14F018550000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  | Restoration | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [5 empty] | 45412 |  |  |  |  | 45210 | 10/20/2023 |  | 45412 |  |  |  |  | 1 | 14963904 | 17963819 | 1727642 | 3031817 |  | 17963819 | 249476 | 1478166 | 19691461 | 22723278 | 45473 | 45626 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/478/FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Bayam%C3%B3n%20Phase%202%20Medium%20Priority%20-%20signed.pdf?web=1 | 08/06/2025 - Previously withdrawn and resubmitted. Withdrawn again on 08/05/2025 3/28/2024 - Received withdrawal status data/info from Project Manager Mariano Pérez Portocarrero.11/29 The project was withdrawn.4/11 Project unwithdrawn by System Admin per FEMA Request ServiceNow INC10168317/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short List | 45875.3902 | 45211.3728 | Marlina Crespo | Distribution Streetlighting | Ashleah Dingle |  |  |  |  | 0.91226 | 1 | 45874 | 735470RFI450 | 735470 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
735338 | 11834 | FAASt [Aguadilla Streetlighting - Part 3] (Distribution) | 14F018520000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting | Distribution Streetlighting |  |  | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45218 | 10/19/2023 |  | 45443 |  |  |  |  | 1 | 6655166 | 8195391 | 1423703 | 1856753 |  | 8195391 | 262975 | 1160728 | 9619094 | 11475847 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/479/735338-DR4339PR-FEMA%20iSOW%20Distribution%20Streetlighting%20-%20Aguadilla%20Phase%203%20Low%20Priority%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 45980.6872 | 45219.5628 | Marlina Crespo | Distribution Streetlighting | Marlina Crespo | 0 Months |  |  |  | 0.85199 | 1 | 45874 | 735338RFI451 | 735338 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
738671 | 11819 | FAASt [25 MW BESS Installation and Integration - Barceloneta] (Substation) | 14F019600000 | PBUT37 - Microgrid Inst & Integ | Grid Modernization |  | TRUE |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE |  | 216580000 | 45163 | 45168 |  | 45193 |  |  |  | 45224 | 11/15/2023 | 45382 | 45772 | [5 empty] | 216800000 | 216800000 | 55941767.5 | 0 |  | 0 | 5211394.35 | 50730373.15 | 55941767.5 | 55941767.5 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/480/FEMA%20ISOW%2025MW%20BESS%20102423%20v1%20-%20signed.pdf?web=1 |  | 46059.6231 | 45224.7081 | Marlina Crespo | 4x25 MW BESS Interconnections at LUMA 38 kV System | Jason Fournier |  |  |  |  | 3.8755 | 1 | 45876 | 738671RFI452 | 738671 | 0 | 30411453.8 | 30411453.8 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
749060 | 11874 | FAASt [Transmission Priority Pole Replacement Program Line 5600 Victoria TC – Añasco TC] (Transmission) | 14F020780000 | PBUT13 - T Priority Pole Repl | Transmission – Pole Replacement |  |  | Restoration | FALSE |  | Current | [13 empty] | 45244 | 06/05/2024 |  | 45448 | 45923 | 45961 | 45954 | 10/24/2025 - Field EHP – Historic: In review. Expected Completion Date (ECD) 10/31/2025. | 2 | 924000 | 717817.65 | 140677.54 | 120608.99 |  | 1316781.32 | 11800 | 128877.54 | 1457458.86 | 1578067.85 | 45535 | 45657 | 46082 |  | 1316113.03 | 1175435.49 |  |  |  | 141345.83 |  | 1316113.03 | 1175435.49 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/481/136271-DR4339PR-TL5600%20Priority%20Pole%20Replacement-Initial%20Scope%20of%20Work.pdf?web=1 |  | 46083.6742 | 45244.3848 | Marlina Crespo | Distribution Pole & Conductor Replacement | Marlina Crespo | 0 Months |  | 120608.99 | 11800 | 0.49251 | 3 |  | 749060RFI453 | 749060 | 141345.83 | 17467.93 | 158813.76 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 111409.61
749072 | 11877 | FAASt [Transmission Priority Pole Replacement Program Line 2700 Aguadilla Hospital Distrito Sect – Mora TC] (Transmission) | 14F020680000 | PBUT13 - T Priority Pole Repl | Transmission – Pole Replacement |  | TRUE | Restoration | TRUE | 45930 | Current | [13 empty] | 45257 | 06/05/2024 |  | 45448 | 45898 | 45930 | 45909 | 9/9/2025 - Field EHP - Environmental: In Review. Expected Completion Date (ECD) 09/30/2025. | 2 | 693000 | 158495.32 | 59629.8 | 73616.34 |  | 823313.44 | 4890.99 | 54738.81 | 882943.24 | 956559.58 | 45535 | 45657 | 45966 |  | 827007.6 | 767377.79 |  |  |  | 55935.65 |  | 827007.6 | 767377.79 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/482/136271-DR4339PR%20TL%202700%20Priority%20Pole%20Replacement%20Initial%20Scope%20of%20Work%20Aguadilla%20Hospital%20Distrito%20Sect%20-%20Mora%20TC%20-%20signed.pdf |  | 46059.5502 | 45257.5226 | Marlina Crespo | Distribution Pole & Conductor Replacement | Jason Fournier | 0 Months |  | 73616.34 | 4890.99 | 0.17951 | 5 |  | 749072RFI454 | 749072 | 55935.65 |  | 55935.65 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 54738.82
740406 | 107933 | FAASt [Region 1-San Juan Group B] (Vegetation) | 15F019320000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation | TRUE |  | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 45268 | 12/08/2023 | 45260 | 45271 | 45723 |  |  |  | 1 |  | 691016.47 | 5894785.29 |  |  |  | 1682447.99 | 4212337.3 | 5894785.29 | 5894785.29 | 45716 | 45900 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/483/Appendix%20C%20_%20Location%20List%20and%20Cost%20Estimates_Group%20B%20San%20Juan.xlsx?web=1 | 10/22/2024 - GRANTS PORTAL 10/17/2024 02:36 PM AST Project Updated Title: FAASt [Region 1-San Juan Group B] High Density (Vegetation) - FAASt [Region 1-San Juan Group B] (Vegetation) FAASt #756472 merged under project | 46059.6234 | 45271.3945 | Marlina Crespo | Island-Wide Vegetation Clearing | Jason Fournier |  |  |  |  | 0.11723 | 5 | 45884 | 740406RFI455 | 740406 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
740408 | 107934 | FAASt [Region 3-Bayamon Group B] (Vegetation) | 15F019520000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation | TRUE |  | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 45268 | 12/08/2023 | 45260 | 45271 | 45723 |  |  |  | 1 |  | 1049080.08 | 11782088.78 | 0 |  | 0 | 1838308.82 | 9943779.96 | 11782088.78 | 11782088.78 | 45716 | 45900 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/484/Appendix%20C%20_%20Location%20List%20and%20Cost%20Estimates_Group%20B%20Bayamon.xlsx?web=1 | 10/22/2024 - Grants Portal 10/17/2024 02:39 PM AST Project UpdatedTitle: FAASt [Region 3-Bayamon Group B] High Density (Vegetation) - FAASt [Region 3-Bayamon Group B] (Vegetation) FAASt #756474 merged under project | 46059.6433 | 45271.3949 | Marlina Crespo | Island-Wide Vegetation Clearing | Jason Fournier |  |  |  |  | 0.08904 | 5 | 45884 | 740408RFI456 | 740408 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
740409 | 107935 | FAASt [Region 4-Caguas Group B] (Vegetation) | 15F019470000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation | TRUE |  | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 45268 | 12/08/2023 | 45291 | 45271 | 45723 | [5 empty] | 3068261.01 | 23846154.02 |  |  |  | 2150317.53 | 21695836.49 | 23846154.02 | 23846154.02 | 45596 | 45747 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/485/Region%204_Caguas%20Group%20B%20-%20PW%20740409%20DSOW%2012_19_25.pdf?web=1 | 10/22/2024 - GRANTS PORTAL 10/17/2024 02:39 PM AST Project UpdatedTitle: FAASt [Region 4-Caguas Group B] High Density (Vegetation) - FAASt [Region 4-Caguas Group B] (Vegetation) FAASt 756476 MERGED UNDER PROJECT | 46059.6434 | 45271.3954 | Marlina Crespo | Island-Wide Vegetation Clearing | Jason Fournier |  |  |  |  | 0.12867 | 5 | 45884 | 740409RFI457 | 740409 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
740410 | 107936 | FAASt [Region 2-Arecibo Group B] (Vegetation) | 15F019570000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation | TRUE |  | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 45268 | 12/08/2023 | 45291 | 45271 | 45723 | [5 empty] | 30966.29 | 5425376.76 | 0 |  | 0 | 1658267.85 | 3767108.91 | 5425376.76 | 5425376.76 | 45596 | 45747 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/486/Appendix%20C%20_%20Location%20List%20and%20Cost%20Estimates_Group%20B%20Arecibo.xlsx?web=1 | 10/22/2024 - GRANTS PORTAL 10/17/2024 02:40 PM AST Project UpdatedTitle: FAASt [Region 2-Arecibo Group B] High Density (Vegetation) - FAASt [Region 2-Arecibo Group B] (Vegetation) FAASt 756475 MERGED UNDER PROJECT | 46059.6435 | 45271.3958 | Marlina Crespo | Island-Wide Vegetation Clearing | Jason Fournier |  |  |  |  | 0.0057077 | 5 | 45884 | 740410RFI458 | 740410 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
740411 | 107937 | FAASt [Region 5-Mayaguez Group B] (Vegetation) | 15F019420000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation | TRUE |  | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 45268 | 12/08/2023 | 45291 | 45271 | 45723 |  |  |  | 1 |  | 720951.73 | 3777166.88 | 0 |  | 0 | 1618073.62 | 2159093.26 | 3777166.88 | 3777166.88 | 45565 | 45716 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/487/Appendix%20C%20_%20Location%20List%20and%20Cost%20Estimates_Group%20B%20Mayaguez.xlsx?web=1 | 10/22/2024 - GRANTS PORTAL 10/17/2024 02:47 PM AST Project UpdatedTitle: FAASt [Region 5-Mayaguez Group B] High Density (Vegetation) - FAASt [Region 5-Mayaguez Group B] (Vegetation) FAASt 756477 MERGED UNDER PROJECT | 46091.5488 | 45271.3962 | Marlina Crespo | Island-Wide Vegetation Clearing | Jason Fournier |  |  |  |  | 0.19087 | 5 | 45884 | 740411RFI459 | 740411 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
740414 | 107938 | FAASt [Region 6-Ponce Group B] High Density (Vegetation) | 15F019370000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation | TRUE |  | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 45268 | 12/08/2023 | 45291 | 45279 | 45723 |  |  |  | 1 |  | 1316423.25 | 13788400.37 | 0 |  | 0 | 1887413.02 | 11900987.35 | 13788400.37 | 13788400.37 | 45716 | 45900 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/488/Region%206_Ponce%20Group%20B%20-%20PW%20740414%20DSOW%202_19_25.pdf?web=1 |  | 46059.6438 | 45271.3966 | Marlina Crespo | Island-Wide Vegetation Clearing | Jason Fournier |  |  |  |  | 0.095473 | 5 | 45884 | 740414RFI460 | 740414 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
740662 | 107939 | FAASt [Automation Program Group 2] (TL/ Distribution) | 14F003310000, 14F003320000, 14F005110000, 14F003590000, 14F001610000, 14F003510000, 14F005180000, 14F004820000, 14F003270000, 14F005090000, 14F003570000, 14F000800000, 14F001430000, 14F004840000, 14F004710000, 14F005080000, 14F003560000 | PBUT04 - Distribution Automation | Grid Automation | Distribution Automation |  |  | TRUE | 45930 | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 45268 | 12/11/2023 | 45230 | 45273 |  |  |  |  | 1 | 4500000 | 4500000 | 7224272 | 314567 |  | 2285726 | 873947 | 6350325 | 9509998 | 9824565 | 45869 | 46022 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/489/703222-DR4339PR-APPENDIX%20B-%20Initial%20SOW%20T&D%20Automation%20-%20Group%2002.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 46077.5788 | 45271.4296 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Ashleah Dingle |  |  |  |  | 0.47319 | 3 | 45887 | 740662RFI461 | 740662 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
741097 | 107940 | FAASt [Region 1 San Juan Subs/Telecom] (Vegetation) | 14F019290000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 45275 | 12/15/2023 |  | 45279 |  |  |  |  | 1 |  | 1267726 | 1347191.63 |  |  |  |  | 1347191.63 | 1347191.63 | 1347191.63 | 45716 | 45900 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/491/Appendix%20C%20_Region%201%20San%20Juan%20Substation%20and%20Telecom%20location.xlsx?web=1 |  | 46059.6439 | 45278.6239 | Marlina Crespo | Island-Wide Vegetation Clearing | Jason Fournier |  |  |  |  | 0.94101 | 1 | 45880 | 741097RFI462 | 741097 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
741098 | 107941 | FAASt [Region 3 Bayamon Subs/Telecom] (Vegetation) | 14F019490000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 45275 | 12/15/2023 |  | 45279 |  |  |  |  | 1 |  | 961519 | 961518.65 |  |  |  |  | 961518.65 | 961518.65 | 961518.65 | 45596 | 45747 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/492/Appendix%20C%20_Region%203%20Bayamon%20Substation%20and%20Telecom%20location.xlsx?web=1 | 07JULY2025 - The project was withdrawn | 46059.6446 | 45278.6249 | Marlina Crespo | Island-Wide Vegetation Clearing | Jason Fournier |  |  |  |  | 1 | 1 | 45845 | 741098RFI463 | 741098 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
741100 | 107942 | FAASt [Region 4 Caguas Subs/Telecom] (Vegetation) | 14F019440000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 45275 | 12/15/2023 |  | 45279 |  |  |  |  | 1 |  | 1428326.03 | 1428325.86 |  |  |  |  | 1428325.86 | 1428325.86 | 1428325.86 | 45596 | 45747 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/493/Appendix%20C%20_Region%204%20Caguas%20Substation%20and%20Telecom%20location.xlsx?web=1 |  | 46059.6453 | 45278.6256 | Marlina Crespo | Island-Wide Vegetation Clearing | Jason Fournier |  |  |  |  | 1 | 1 | 45845 | 741100RFI464 | 741100 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
741101 | 107943 | FAASt [Region 2 Arecibo Subs/Telecom] (Vegetation) | 14F019540000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 45275 | 12/15/2023 |  | 45279 |  |  |  |  | 1 |  | 956850.56 | 1058188.92 |  |  |  |  | 1058188.92 | 1058188.92 | 1058188.92 | 45716 | 45900 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/494/Appendix%20C%20_Region%202%20Arecibo%20Substation%20and%20Telecom%20location.xlsx?web=1 |  | 46059.6453 | 45278.6266 | Marlina Crespo | Island-Wide Vegetation Clearing | Jason Fournier |  |  |  |  | 0.90423 | 1 | 45845 | 741101RFI465 | 741101 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
741102 | 107944 | FAASt [Region 5 Mayaguez Subs/Telecom] (Vegetation) | 14F019390000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 45275 | 12/15/2023 |  | 45279 |  |  |  |  | 1 |  | 956850.56 | 1516985.37 |  |  |  |  | 1516985.37 | 1516985.37 | 1516985.37 | 45716 | 45900 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/495/Appendix%20C%20_Region%205%20Mayaguez%20Substation%20and%20Telecom%20location.xlsx?web=1 |  | 46059.6454 | 45278.6273 | Marlina Crespo | Island-Wide Vegetation Clearing | Jason Fournier |  |  |  |  | 0.63076 | 2 | 45845 | 741102RFI466 | 741102 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
741104 | 107945 | FAASt [Region 6 Ponce Subs/Telecom] (Vegetation) | 14F019340000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 45275 | 12/15/2023 |  | 45278 | 45279 |  |  |  | 1 |  | 1538820 | 1992973.53 |  |  |  |  | 1992973.53 | 1992973.53 | 1992973.53 | 45716 | 45900 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/496/Region%201%20San%20Juan%20Substation%20and%20Telecom%20location%20(1).xlsx?web=1 |  | 46059.6457 | 45278.628 | Marlina Crespo | Island-Wide Vegetation Clearing | Jason Fournier |  |  |  |  | 0.77212 | 2 | 45845 | 741104RFI467 | 741104 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
741105 | 107946 | FAASt [All Regions TL - 230kV] (Vegetation) | 15F019590000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation | Vegetation Management and Capital Clearing Implementation | TRUE |  | FALSE |  | Current | FALSE | [12 empty] | 45275 | 12/15/2023 |  | 45278 | 45979 | 45992 | 45982 | 11/21/2025 - Field EHP - Environmental: In Review. Expected Completion Date (ECD) 12/01/2025. | 1 |  | 27012545.63 | 157385518.05 |  |  |  | 2593672.87 | 154791845.18 | 157385518.05 | 157385518.05 | 45716 | 45900 | 46082 |  | 12885805.47 | 2430054.31 | [5 empty] | 12885805.47 | 2430054.31 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/497/PRJ_Report_741105_20260302.pdf?web=1 |  | 46091.5489 | 45278.6287 | Marlina Crespo | Island-Wide Vegetation Clearing | Jason Fournier |  |  | 22529.43 |  | 0.17163 | 5 |  | 741105RFI468 | 741105 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 10455751.16
FAASt Number Pending 1 |  | Substations HV Equipment Replacement (Group 3) |  |  | Substation | [6 empty] | FALSE | [14 empty] | 45382 | [13 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7695 | 45280.6424 | Marlina Crespo | Substation High Voltage Equipment Replacement | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 1RFI469 | FAASt Number Pending 1 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 4 |  | Vieques & Culebra Microgrid |  |  | Grid Modernization |  |  |  | FALSE |  | Past | FALSE |  |  |  |  | 122250000 | [9 empty] | 45322 | [13 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7695 | 45281.5028 | Marlina Crespo | Vieques and Culebra Microgrid | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 4RFI470 | FAASt Number Pending 4 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 5 |  | Island Wide Vegetation Clearing: Region 6 Ponce Substations & Telecommunications Sites |  |  | Vegetation | [6 empty] | FALSE | [14 empty] | 45291 | [13 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7695 | 45281.5036 | Marlina Crespo | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 5RFI471 | FAASt Number Pending 5 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 6 |  | Island Wide Vegetation Clearing: Region 5 Mayaguez Substations & Telecommunications Sites |  |  | Vegetation | [6 empty] | FALSE | [14 empty] | 45291 | [13 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7695 | 45281.5046 | Marlina Crespo | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 6RFI472 | FAASt Number Pending 6 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 7 |  | Island Wide Vegetation Clearing: Region 4 Caguas Substations & Telecommunications Sites |  |  | Vegetation | [6 empty] | FALSE | [14 empty] | 45291 | [13 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7695 | 45281.5052 | Marlina Crespo | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 7RFI473 | FAASt Number Pending 7 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 8 |  | Island Wide Vegetation Clearing: Region 3 Bayamon Substations & Telecommunications Sites |  |  | Vegetation | [6 empty] | FALSE | [14 empty] | 45291 | [13 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7695 | 45281.5056 | Marlina Crespo | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 8RFI474 | FAASt Number Pending 8 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 9 |  | Island Wide Vegetation Clearing: Region 2 Arecibo Substations & Telecommunications Sites |  |  | Vegetation | [6 empty] | FALSE | [14 empty] | 45291 | [13 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7695 | 45281.5062 | Marlina Crespo | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 9RFI475 | FAASt Number Pending 9 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 10 |  | Island Wide Vegetation Clearing: Region 1 San Juan Substations & Telecommunications Sites |  |  | Vegetation | [6 empty] | FALSE | [14 empty] | 45291 | [13 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7695 | 45281.5066 | Marlina Crespo | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 10RFI476 | FAASt Number Pending 10 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 11 |  | Island Wide Vegetation Clearing: All Regions Transmission - 230 kV |  |  | Vegetation | [6 empty] | FALSE | [14 empty] | 45291 | [13 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7695 | 45281.5069 | Marlina Crespo | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 11RFI477 | FAASt Number Pending 11 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 12 |  | Carolina Group 2 – Phase 2 |  |  | Distribution – Pole Replacement | [6 empty] | FALSE | [14 empty] | 45351 | [13 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7695 | 45281.5078 | Marlina Crespo | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 12RFI478 | FAASt Number Pending 12 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
749124 | 107963 | FAASt [Automation Program Group 7] (Distribution) | 10F001780000, 14F004770000, 10F001790000, 10F001770000, 10F001750000, 14F004780000 | PBUT04 - Distribution Automation | Grid Automation |  |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45322 | 06/05/2024 | 45322 | [7 empty] | 3342857 | [5 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/517/729522-DR4339PR-DSOW%20Automation%20Group%207-%20DAR%20-%20BAYAMON%201709,%201719%20-%20FY24%20-%20signed%20(1).pdf?web=1 |  | 45912.6656 | 45281.5111 | Jason Fournier | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Marlina Crespo | [6 empty] | 45918 | 749124RFI479 | 749124 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 25 |  | DAR - BAYAMON 9401, 9801, 9802 - FY24 |  |  | Grid Automation |  |  | Restoration |  |  |  | FALSE | [14 empty] | 45322 | [8 empty] | 1776856 | 124341 |  | 725740 | 182964 | 1593892 | 2502596 | 2626937 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/522/729522-DR4339PR-%20DSOW-%20Group%208-%20DAR%20-%20BAYAMON%209401%209801%209802%20-%20FY24%20-%20signed.pdf?web=1 | 7AUGUST2024 ISOW / DSOW submitted on 1/31/24 - this project was replaced with another project - MC22JANUARY2025 - Removing the DSOW date - MC | 45856.7695 | 45281.513 | Jason Fournier | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | FAASt Number Pending 25RFI480 | FAASt Number Pending 25 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
745854 | 107955 | FAASt [ Automation Program Group 9] (Distribution) | 10F001850000, 10F001890000, 10F001870000, 10F001900000, 10F001860000, 10F001880000 | PBUT04 - Distribution Automation | Grid Automation |  |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | FALSE | [9 empty] | 45322 | 03/22/2024 | 45322 | 45322 | 45461 |  |  |  | 2 |  | 1711509 | 1164604 | 52795 |  | 494110 | 112423 | 1052181 | 1658714 | 1711509 | 45688 | 45869 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/526/729522-DR4339PR-DSOW-Group%209%20-%20DAR%20-%20BAYAMON%201703,%201704%20-FY24%20-%20signed.pdf?web=1 |  | 46077.5751 | 45281.5149 | Jason Fournier | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Ashleah Dingle |  |  |  |  | 1.0318 | 1 | 45887 | 745854RFI481 | 745854 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
745871 | 107958 | FAASt [Automation Program Group 10] (Distribution) | 10F001920000, 14F004800000, 10F001910000 | PBUT04 - Distribution Automation | Grid Automation |  |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45322 | 03/22/2024 | 45322 | 45322 |  |  |  |  | 1 |  | 861045 | 582637 | 26876 |  | 251532 | 56244 | 526393 | 834169 | 861045 | 45900 | 46053 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/527/729522-DR4339PR-DSOW-%2010%20-%20DAR%20-%20BAYAMON%201717%209503%20-FY24%20-%20signed.pdf?web=1 |  | 45887.6456 | 45281.5158 | Jason Fournier | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Ashleah Dingle |  |  |  |  | 1.0322 | 1 | 45887 | 745871RFI482 | 745871 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
745851 | 107953 | FAASt [Automation Program Group 11] (Distribution) | 10F001940000, 10F001950000, 14F004790000 | PBUT04 - Distribution Automation | Grid Automation |  |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | FALSE | [9 empty] | 45322 | 03/22/2024 | 45322 | 45322 | [6 empty] | 1532152 | 1052298 | 46322 |  | 433532 | 101582 | 950716 | 1485830 | 1532152 | 45504 | 45626 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/528/729522-DR4339PR-DSOW%20Automation%20Group-%20Group%2011%20DAR%20Bayamon%201901,%201907-FY24%20-%20signed.pdf?web=1 |  | 46077.575 | 45281.5165 | Jason Fournier | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Ashleah Dingle |  |  |  |  | 1.0312 | 1 | 45887 | 745851RFI483 | 745851 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
745859 | 11839 | FAASt [Automation Program Group 18] (Distribution) | 10F000550000 | PBUT04 - Distribution Automation | Grid Automation |  |  | Restoration | FALSE |  | Past | FALSE | [12 empty] | 45322 | 03/22/2024 | 45322 | 45322 | 45980 | 46010 | 45996 | 12/5/2025 - Field EHP - Environmental: In Review. Expected Completion Date (ECD) 12/19/2025 | 6 |  | 467287.59 | 197005.11 | 22140.69 |  | 258571.74 | 15220.56 | 181784.55 | 455576.85 | 477717.54 | 45596 | 45688 | 45553 | 10/15/2025 | 467287.59 | 467287.59 | 422345.48 | 223935.37 |  | 33515.73 |  | 422345.48 | 223935.37 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/550/729522-DR4339PR-DSOW%20Automation%20%20Group%2018%20-%20DAR%20-%20SAN%20JUAN%202001%20-%20FY24%20-%20signed%20(1).pdf?web=1 | 4/01/2024: QC Review Complete7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 46070.4754 | 45281.5308 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Marlina Crespo | 0 Months |  | 21856.33 |  | 1.0257 | 1 |  | 745859RFI484 | 745859 | 33515.73 | 76444.91 | 109960.64 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 121965.2
FAASt Number Pending 56 |  | DAR - SAN JUAN 2403,2404 - FY24 |  |  | Grid Automation |  |  | Restoration | FALSE |  |  | FALSE | [14 empty] | 45322 | [8 empty] | 570640 | 41953 |  | 322238 | 65735 | 504905 | 892878 | 934831 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/552/729522-DR4339PR-DSOW%20Group%2017-%20DAR%20-%20SAN%20JUAN%202403,2404%20-%20FY24%20-%20signed.pdf?web=1 | 7AUGUST2024 ISOW / DSOW submitted on 1/31/24 - this project was replaced with another project - MC22JANUARY2025 - Removing the DSOW date - MC | 45856.7696 | 45281.5315 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | FAASt Number Pending 56RFI485 | FAASt Number Pending 56 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
745861 | 107957 | FAASt [Automation Program Group 12] (Distribution) | 10F000610000, 10F000630000, 10F000620000, 10F000640000 | PBUT04 - Distribution Automation | Grid Automation |  |  | Restoration | FALSE |  | Past | FALSE | [12 empty] | 45322 | 03/22/2024 | 45351 | 45463 | 46084 | 45642 | 45629 |  | 2 |  | 2360527 | 1358644.98 | 196183.24 | 228547.36 | 2397194.98 | 101775.43 | 1256869.55 | 3755839.96 | 3952023.2 | 45688 | 45869 | 45694 |  | 3664210.1 | 3664210.1 | [5 empty] | 3664210.1 | 3664210.1 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/553/745861-DR4339PR-DSOW-%20Group%2012-%20DAR%20-%20ARECIBO%207402%207403%207702-%20FY24%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 46085.5892 | 45281.5316 | Jason Fournier | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Marlina Crespo |  |  | 477953.55 |  | 0.6285 | 2 |  | 745861RFI486 | 745861 | 228785.14 | 557322.86 | 786108 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
745852 | 107954 | FAASt [Automation Program Group 13] (Distribution) | 10F001020000, 10F001050000, 10F001040000, 10F001060000, 10F001030000, 14F004690000 | PBUT04 - Distribution Automation | Grid Automation |  |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45322 | 03/22/2024 | 45322 | 45322 | 45376 |  |  |  | 1 |  | 2854430 | 1966004 | 85763 |  | 802663 | 189786 | 1776218 | 2768667 | 2854430 | 45688 | 45869 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/555/729522-DR4339PR-DSOW%20Group%2013%20-%20DAR%20-%20ARECIBO%208010,%208013,%208015%20-%20FY24%20-%20signed.pdf?web=1 |  | 45887.6456 | 45281.5321 | Jason Fournier | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Ashleah Dingle |  |  |  |  | 1.031 | 1 | 45887 | 745852RFI487 | 745852 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
745856 | 107956 | FAASt [Automation Program Group 14] (Distribution) | 10F000570000, 10F000580000 | PBUT04 - Distribution Automation | Grid Automation |  |  | Restoration | FALSE | 45994 | Past | FALSE | [12 empty] | 45322 | 03/22/2024 | 45322 | 45322 | 46066 | 45652 | 45636 |  | 1 |  | 1237309 | 1001406.99 | 112272.97 | 148295.58 | 1558740.78 | 65062.72 | 936344.27 | 2560147.77 | 2672420.74 | 45688 | 45869 | 45694 |  | 1640186.96 | 1640186.96 | [5 empty] | 1640186.96 | 1640186.96 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/557/729522-DR4339PR-DSOW%20Group%2014%20-%20DAR%20-%20ARECIBO%208404%20-%20FY24.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 46071.5217 | 45281.5328 | Jason Fournier | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Marlina Crespo | 0 Months |  | 208604.89 |  | 0.4833 | 3 |  | 745856RFI488 | 745856 | 148295.58 | 442571.92 | 590867.5 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
741678 | 107947 | FAASt [Automation Program Group 4] (TL/Distribution) | 14F005130000, 14F005190000, 14F003290000, 14F004810000, 14F005170000, 14F003350000, 14F005120000, 14F003280000 | PBUT04 - Distribution Automation | Grid Automation | Distribution Automation |  | Restoration | TRUE | 45900 | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 45281 | 12/22/2023 |  | 45282 | [5 empty] | 5800000 | 13712378.94 | 10499139.71 | 360048.57 |  | 2853190.65 | 1176445.32 | 9322694.39 | 13352330.36 | 13712378.93 | 45869 | 46022 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/561/741678%20DR4339PR%20DSOW%20Automation%20Group%204-%20SAN%20JUAN%20BAYAMON%20REGION%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 46077.5789 | 45282.672 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Ashleah Dingle |  |  |  |  | 1.027 | 1 | 45887 | 741678RFI489 | 741678 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Undersea 230kV half loop from Mayaguez to Fajardo – UG to Sabana Llana |  |  |  |  | Transmission | [6 empty] | FALSE |  |  |  | 45323 | [17 empty] | 3000000000 | [6 empty] | 0 | 3000000000 | 3000000000 | [11 empty] | 0 | 0 |  |  | 3/20/2024 LUMA Regulatory notes on ISOW submission to PREB - On hold. Awaiting guidance | 45856.7696 | 45287.4136 | Gabriel Licha |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | Undersea 230kV half loop from Mayaguez to Fajardo – UG to Sabana LlanaRFI490 | Undersea 230kV half loop from Mayaguez to Fajardo – UG to Sabana Llana |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
3700 - Striker to Arroyo |  |  |  |  | Transmission | [6 empty] | FALSE |  |  |  | 45303 |  | 45400 | 45419 |  | 45430 | 45399 | 45373 | [10 empty] | 2083233 | [6 empty] | 0 | 2083233 | 2083233 | [11 empty] | 0 | 0 |  |  | 3/19/2024 LUMA Grid Strategy Notes - Batch 3 Transmission Lines (6 - no PLRC) | 45856.7696 | 45287.4138 | Gabriel Licha |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | 3700 - Striker to ArroyoRFI491 | 3700 - Striker to Arroyo |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
36600 115kV San Sebastian – Dos Bocas (Batch 6) |  |  |  |  | Transmission | [6 empty] | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7696 | 45287.414 | Gabriel Licha |  | Rey Roldan Rodríguez | [7 empty] | 36600 115kV San Sebastian – Dos Bocas (Batch 6)RFI492 | 36600 115kV San Sebastian – Dos Bocas (Batch 6) |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
San Juan UG 115 KV Rebuild |  |  |  |  | Transmission | [6 empty] | FALSE | [21 empty] | 195373742 | [6 empty] | 0 | 195373742 | 195373742 | [11 empty] | 0 | 0 |  |  |  | 45856.7696 | 45287.4142 | Gabriel Licha |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | San Juan UG 115 KV RebuildRFI493 | San Juan UG 115 KV Rebuild |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending |  | Sub Rebuilds - Substation that have Functional Specs/will have functional specs |  | PBUT08 - Substation Rebuilds | Substation | [6 empty] | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7696 | 45287.4153 | Gabriel Licha |  | Rey Roldan Rodríguez | [7 empty] | PendingRFI494 | Pending494 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending |  | Sub Rebuild - Canas TC |  | PBUT08 - Substation Rebuilds | Substation | [6 empty] | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7696 | 45287.416 | Gabriel Licha |  | Rey Roldan Rodríguez | [7 empty] | PendingRFI495 | Pending495 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending |  | Sub Rebuild - Santurce Planta |  | PBUT08 - Substation Rebuilds | Substation | [6 empty] | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7696 | 45287.4161 | Gabriel Licha | Santurce Planta (Sect) 1116 | Rey Roldan Rodríguez | [7 empty] | PendingRFI496 | Pending496 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Sub Rebuild - Fajardo Sect |  |  |  | PBUT08 - Substation Rebuilds | Substation | [6 empty] | FALSE |  |  |  | 45316 | [17 empty] | 101312645.45 | [6 empty] | 0 | 101312645.45 | 101312645.45 | [11 empty] | 0 | 0 |  |  | 3/19/2024 LUMA Regulatory Notes on ISOW to PREB - PREB Submittal Target Date: On Hold, Notes: On hold. Awaiting guidance | 45856.7696 | 45287.4163 | Gabriel Licha |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer1 | Sub Rebuild - Fajardo Sect |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
T&D Model Upgrades and Repair |  |  |  |  | Distribution | [6 empty] | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7696 | 45287.4166 | Gabriel Licha |  | Rey Roldan Rodríguez | [7 empty] | qwer2 | T&D Model Upgrades and Repair |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
742026 | 11716 | FAASt [Pole and Conductor Repair - San Juan Group 2 - Phase 2] (Distribution) | 14F019020000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement |  |  | Restoration | FALSE |  |  | FALSE | [12 empty] | 45295 | 01/04/2024 |  | 45295 | 45342 |  |  |  | 4 |  | 1117411.77 | 84036 | 83943 |  | 1033376 | 0 | 84036 | 1117412 | 1201355 | 45473 | 45535 | 45443 | 8/30/2024 | 1117411.77 | 1033375.81 | 1117411.77 | 1033375.81 |  |  |  | 1117411.77 | 1033375.81 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/584/742026-DR4339PR-Detailed%20SOW%20San%20Juan%20Group%202%20-%20Phase%202%20Rev0.pdf?web=1 | Project created with the following damages initially assigned: 661700.7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 46070.465 | 45295.4804 | Marlina Crespo | Distribution Pole & Conductor Replacement | Marlina Crespo |  |  | 83942.74 |  | 1 | 1 |  | qwer3 | 742026 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 84035.96
742070 | 11753 | FAASt [Pole and Conductor Repair - San Juan Group 1 - Phase 2] (Distribution) | 14F019010000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement |  |  | Restoration | FALSE |  |  | FALSE | [12 empty] | 45296 | 01/05/2024 |  | 45296 | 45355 |  |  |  | 2 | 7140000 | 5666787.43 | 205587 | 491327 |  | 5461200 | 35032.38 | 170554.62 | 5666787 | 6158114 | 45473 | 45535 | 45461 |  | 5666787.43 | 5461200.05 | [5 empty] | 5666787.43 | 5461200.05 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/585/742070-DR4339PR-Detailed%20SOW%20San%20Juan%20Group%201%20-%20Phase%202%20Rev0%201.pdf?web=1 | Project was resubmitted into Grants Portal under a new FAAst #. Old number was 737825. New number is 742070. Edited on 01/10/2024 by J Fournier.7/30/2024 - Updated Priority Projects List from Grid Strategy, removed from Long List | 45856.7696 | 45303.6898 | Jason Fournier | Distribution Pole & Conductor Replacement | Rey Roldan Rodríguez |  |  | 491326.68 |  | 1 | 1 |  | qwer4 | 742070 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 205587.38
TBD L37400 Barceloneta TC - Cambalache TC |  |  |  |  | Transmission | [6 empty] | FALSE | [12 empty] | 45308 | [8 empty] | 927000 | [6 empty] | 0 | 927000 | 927000 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/586/136271-DR4339PR-INITIAL%20SOW-Line%2037400%20Priority%20Pole%20Replacement%20Barceloneta%20TC%20-%20Cambalache%20TC%20-%20signed%5B25319%5D.pdf?web=1 | 02MAY2025 37400 is not a priority, and we dont know when it will be requested as a fasst - MC | 45880.3881 | 45308.6303 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 0 | 5 |  | qwer5 | TBD L37400 Barceloneta TC - Cambalache TC |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
743399 | 11764 | FAASt [High Voltage Equipment Replacement - Group 3] (Substation) | 14F021320000, 14F021330000, 14F021310000 | PBUT07 - Substation Reliability | Substation |  |  | Restoration | FALSE |  |  | FALSE | [12 empty] | 45309 | 01/29/2024 |  | 45379 |  |  |  |  | 1 | 22777596 | 17307539.01 | 0 | 2253323.31 |  | 17307538.97 | 0 | 0 | 17307538.97 | 19560862.28 | 45473 | 45626 | 45530 |  | 17307539.01 | 17307539.01 | [5 empty] | 17307539.01 | 17307539.01 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/587/DR4339PR%20-FEMA%20ISOW%20HV%20Equipment%20Replacement%20Group%203%20Rev%200%20-%20signed.pdf?web=1 |  | 45862.6537 | 45315.7203 | Marlina Crespo | Substation High Voltage Equipment Replacement | Jose J Ramos Figueroa |  |  | 2253322.97 |  | 1 | 1 |  | qwer6 | 743399 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
744072 | 107948 | FAASt [IT OT Technology Systems Reparations] Group 2 (Telecommunication) |  | PBIT01 - Telecom Sys & Network | Telecommunications |  | TRUE |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45331 | 02/09/2024 |  | 45737 | [5 empty] | 42700000 | 42700000 | 490438.07 | 181440.64 |  | 1893141.74 | 42892.47 | 447545.6 | 2383579.81 | 2565020.45 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/588/744072-DR4339PR-FEMA%20Initial%20Scope%20of%20Work%20Network%20%20Communication%20Rev%200_01312024.pdf?web=1 | ISOW was never submitted to the Island Wide FAASt Project | 46059.5596 | 45334.385 | Marlina Crespo | IT OT Technology Systems Reparations | Jason Fournier |  |  |  |  | 17.9142 | 1 | 45880 | qwer7 | 744072 | 225680 | 292320 | 518000 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 65 |  | T-Pole L700 - Costa Sur SP - Yauco 2 HP |  |  | Transmission |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7711 | 45366.5271 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer8 | FAASt Number Pending 65 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 66 |  | T-Pole L6500 -Toro Negro HP-Barranquitas TC |  |  | Transmission |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7711 | 45366.5276 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer9 | FAASt Number Pending 66 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 72 |  | DAR - CAGUAS 2603, 2801, 2803, 2906 - FY24 |  |  | Grid Automation |  |  |  | FALSE |  | Past | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7711 | 45369.4583 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer10 | FAASt number pending 72 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 73 |  | DAR - CAGUAS 3004, 3007, 3009 - FY24 |  |  | Grid Automation |  |  |  | FALSE |  | Past | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7711 | 45369.5119 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer11 | FAASt number pending 73 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 74 |  | DAR - CAGUAS 3014, 3015 - FY24 |  |  | Grid Automation |  |  |  | FALSE |  | Past | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7711 | 45369.5413 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer12 | FAASt number pending 74508 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 74 |  | DAR - CAGUAS 3101, 3103, 3205 - FY24 |  |  | Grid Automation |  |  |  | FALSE |  | Past | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7711 | 45369.5429 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer13 | FAASt number pending 74509 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 75 |  | DAR - CAGUAS 3302, 3401, 3406, 3502 - FY24 |  |  | Grid Automation |  |  |  | FALSE |  | Past | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7711 | 45369.5432 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer14 | FAASt number pending 75 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 76 |  | DAR - CAGUAS 3601, 3602, 3604, 3701 - FY24 |  |  | Grid Automation |  |  |  | FALSE |  | Past | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7711 | 45369.5454 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer15 | FAASt number pending 76 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 77 |  | DAR - CAGUAS 9601, 9605, 8703 - FY24 |  |  | Grid Automation |  |  |  | FALSE |  | Past | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7711 | 45369.5468 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer16 | FAASt number pending 77 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 78 |  | DAF - Fuse Cutout Installation – Group B |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7711 | 45369.5471 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer17 | FAASt number pending 78 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 80 |  | DAR - PONCE 5002, 5004, 5007 - FY24 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7711 | 45369.5768 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer18 | FAASt number pending 80 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 81 |  | DAR - PONCE 5018, 5019 - FY24 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7711 | 45369.5778 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer19 | FAASt number pending 81 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 82 |  | DAR - PONCE 5301, 5302, 5304 - FY24 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7711 | 45369.579 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer20 | FAASt number pending 82 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 83 |  | DAR - PONCE 5501, 5802, 5803, 5817, 5901 - FY24 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7711 | 45369.5794 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer21 | FAASt number pending 83 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 84 |  | DAF - Fuse Cutout Installation – Group D |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7711 | 45369.5803 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer22 | FAASt number pending 84 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 85 |  | DAF - Fuse Cutout Installation – Group C |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7711 | 45369.5808 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer23 | FAASt number pending 85 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 86 |  | DAR - ARECIBO 8404, 8405 - FY24 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7712 | 45369.5814 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer24 | FAASt number pending 86 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 87 |  | DAR - ARECIBO 9004 - FY24 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7712 | 45369.6122 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer25 | FAASt number pending 87 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 88 |  | DAR - SAN JUAN 1204, 1346 - FY24 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7712 | 45369.6126 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer26 | FAASt number pending 88 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 89 |  | DAR - CAGUAS 2601, 2602, 2701, 2702 - FY24 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7712 | 45369.613 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer27 | FAASt number pending 89 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 90 |  | DAR - CAGUAS 2901, 3006 - FY24 |  |  | Grid Automation |  |  |  | FALSE |  | Past | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7712 | 45369.6135 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer28 | FAASt number pending 90 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 91 |  | DAR - CAGUAS 3010, 3013 - FY24 |  |  | Grid Automation |  |  |  | FALSE |  | Past | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7712 | 45369.6139 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer29 | FAASt number pending 91 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 92 |  | DAR - CAGUAS 3102, 3201, 3301 - FY24 |  |  | Grid Automation |  |  |  | FALSE |  | Past | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7712 | 45369.6144 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer30 | FAASt number pending 92 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 93 |  | DAR - CAGUAS 3405, 3501 - FY24 |  |  | Grid Automation |  |  |  | FALSE |  | Past | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7712 | 45369.6148 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer31 | FAASt number pending 93 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 94 |  | DAR - CAGUAS 9901, 9902 - FY24 |  |  | Grid Automation |  |  |  | FALSE |  | Past | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7712 | 45369.6152 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer32 | FAASt number pending 94 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 95 |  | DAR - SAN JUAN 1646 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7712 | 45369.6178 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer33 | FAASt number pending 95 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 96 |  | DAR – BAYAMON 9501, 9502 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7712 | 45369.6181 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer34 | FAASt number pending 96530 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 96 |  | DAR - ARECIBO 9101, 9105, 9201 - FY24 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7712 | 45369.6193 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer35 | FAASt number pending 96531 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 97 |  | DAR - PONCE 4001, 5602, 6601 - FY24 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7712 | 45369.623 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer36 | FAASt number pending 97 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
746309 | 107959 | FAASt [Automation Program Group 30] (TL/Distribution) | 10F000560000 | PBUT04 - Distribution Automation | Grid Automation |  |  | Restoration | FALSE |  | Current | FALSE | [12 empty] | 45383 | 04/02/2024 |  | 45383 | 45856 | 45889 | 45867 | 8/1/2025 - Field EHP - Environmental: Initial review. Expected Completion Date (ECD) 08/20/2025. | 4 | 448084 | 425975.74 | 251311.27 | 51889.2 |  | 379772.1 | 30200.94 | 221110.33 | 631083.37 | 682972.57 | 45626 | 45777 | 46082 |  | 564064.63 | 327791.49 |  |  |  | 65212.75 |  | 564064.63 | 327791.49 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/632/746309-DR4339PR-DSOW-%20Group%2030-%20DAR%20-%20BAYAMON%20%209203%20-%20FY24%20%20Rev1%20-%20signed.pdf?web=1 | 8/1/2025 - Field EHP - Environmental: Initial review. Expected Completion Date (ECD) 08/20/2025. 8/12/2025 7:43 AM AST - The PR Electric Power Authority, as the eligible entity (subrecipient), has submitted a consolidated plan for the use of the remaining budget available in the FEMA Accelerated Awards Strategy Project (136271) Fixed Cost Award. This FAASt sub-project has been identified in the list and it will be processed in the national workflow accordingly. | 46083.6757 | 45369.6233 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Marlina Crespo |  |  | 53695.19 | 28394.95 | 0.67499 | 2 |  | qwer37 | 746309 | 65212.75 | 98251.25 | 163464 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 109626.94
FAASt number pending 99 |  | DAR - BAYAMON 1803, 1806 - FY24 |  |  | Grid Automation |  |  |  | FALSE |  | Past | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7712 | 45369.6237 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer38 | FAASt number pending 99 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 100 |  | DAR - BAYAMON 1716, 1734 - FY24 |  |  | Grid Automation |  |  |  | FALSE |  | Past | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7712 | 45369.6243 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer39 | FAASt number pending 100 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 101 |  | DAR - BAYAMON 1710,1711,1713, 1714 - FY24 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7712 | 45369.6248 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer40 | FAASt number pending 101 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 102 |  | DAR - BAYAMON 1706, 1708 - FY24 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7712 | 45369.6325 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer41 | FAASt number pending 102 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 103 |  | DAR - BAYAMON 1909 - FY24 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7712 | 45369.6328 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer42 | FAASt number pending 103 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 104 |  | DAR - ARECIBO 8005, 8101, 8103 - FY24 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7712 | 45369.6332 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer43 | FAASt number pending 104 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 105 |  | DAR - ARECIBO 8202 - FY24 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7712 | 45369.6335 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer44 | FAASt number pending 105 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 106 |  | DAR - ARECIBO 8701, 9001 - FY24 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7712 | 45369.6339 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer45 | FAASt number pending 106 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 107 |  | DAR - PONCE 4003, 4101 - FY24 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7712 | 45369.6343 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer46 | FAASt number pending 107 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 108 |  | DAR - PONCE 4201, 4301, 4401 - FY24 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7712 | 45369.635 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer47 | FAASt number pending 108 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 109 |  | DAR - PONCE 4601 - FY24 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7712 | 45369.6353 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer48 | FAASt number pending 109 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 110 |  | DAR - ARECIBO 8801 - FY24 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7712 | 45369.6357 | Marlina Crespo |  | Rey Roldan Rodríguez | 0 Months | [6 empty] | qwer49 | FAASt number pending 110 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 111 |  | DAR - SAN JUAN 1336 - FY24 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7712 | 45369.6362 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer50 | FAASt number pending 111 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 112 |  | DAR - SAN JUAN 1424, 1619, 1620, 2001, 2005, 2006 - FY24 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7712 | 45369.6367 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer51 | FAASt number pending 112 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 113 |  | DAR - SAN JUAN 2201, 2302, 2305, 2306 - FY24 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7712 | 45369.6373 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer52 | FAASt number pending 113 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 114 |  | DAR – ARECIBO 8010, 8015, 8101 – FY24 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7712 | 45369.6377 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer53 | FAASt number pending 114 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 115 |  | DAR – ARECIBO 8104, 8202, 8203, 8301 – FY24 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7712 | 45369.6381 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer54 | FAASt number pending 115 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 116 |  | DAR - ARECIBO 7403, 8302, 8501, 8504 - FY24 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7712 | 45369.639 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer55 | FAASt number pending 116 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 117 |  | DAR - ARECIBO 8602, 8801, 9001, 9002 - FY24 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7712 | 45369.6398 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer56 | FAASt number pending 117 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 118 |  | DAR - BAYAMON 1529, 1701, 1704, 1707 - FY24 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7712 | 45369.6406 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer57 | FAASt number pending 118 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 120 |  | DAR – SAN JUAN 1110, 1206, 1416 – FY24 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7712 | 45369.6415 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer58 | FAASt number pending 120 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 121 |  | DAR - SAN JUAN 1343, 1437, 1525 - FY24 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7712 | 45369.6418 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer59 | FAASt number pending 121 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 122 |  | DAR - BAYAMON 1711, 1717, 1718 - FY24 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7712 | 45369.6422 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer60 | FAASt number pending 122 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 123 |  | DAR - BAYAMON 9202, 9203, 9207 - FY24 |  |  | Grid Automation |  |  |  | FALSE |  | Past | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7712 | 45369.6427 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer61 | FAASt number pending 123 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 124 |  | DAR - PONCE 4401, 4602, 4603, - FY24 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7712 | 45369.6439 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer62 | FAASt number pending 124 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 125 |  | DAR - ARECIBO 9002, 9003, 9004, 9101 - FY24 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7712 | 45369.6442 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer63 | FAASt number pending 125 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 126 |  | DAR - SAN JUAN 2403, 2404, 3801, 1118, 1646 – FY25 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7712 | 45369.6446 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer64 | FAASt number pending 126560 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 126 |  | DAR - BAYAMON 9801, 1705 – FY25 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7712 | 45369.645 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer65 | FAASt number pending 126561 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 127 |  | DAR - PONCE 5303, 5401, 4101, 5901 - FY25 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7712 | 45369.6456 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer66 | FAASt number pending 127 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 128 |  | DAR - CAGUAS 2604, 3006, 3010, 3405, 3501, 3202 – FY25 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7712 | 45369.6461 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer67 | FAASt number pending 128 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 129 |  | DAR - BAYAMON 9501, 1529, 1706 – FY25 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7712 | 45369.6467 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer68 | FAASt number pending 129 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 130 |  | DAR - BAYAMON 9502, 9503, 1711, 1901 – FY25 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7712 | 45369.6477 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer69 | FAASt number pending 130 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 131 |  | DAR - SAN JUAN 1114, 1620 - FY25 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7712 | 45369.6481 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer70 | FAASt number pending 131 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 132 |  | DAR - ARECIBO 7402, 7601 - FY25 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7712 | 45369.6485 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer71 | FAASt number pending 132 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 133 |  | DAR - ARECIBO 8007, 8011 - FY25 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7712 | 45369.6489 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer72 | FAASt number pending 133 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 134 |  | DAR - ARECIBO 9103 - FY25 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7712 | 45369.6494 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer73 | FAASt number pending 134 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 135 |  | DAR - PONCE 4502 - FY25 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7712 | 45369.6497 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer74 | FAASt number pending 135 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 136 |  | DAR - PONCE 5304, 5802 - FY25 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7712 | 45369.6501 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer75 | FAASt number pending 136 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 137 |  | DAR - MAYAGUEZ 6001, 7104 - FY25 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7712 | 45369.6504 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer76 | FAASt number pending 137 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 138 |  | DAR -MAYAGUEZ 6008 - FY25 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7712 | 45369.6754 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer77 | FAASt number pending 138 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 139 |  | DAR -MAYAGUEZ 7502, 7802 - FY25 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7712 | 45369.6758 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer78 | FAASt number pending 139 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 140 |  | DAR -CAGUAS 3009, 3101 - FY25 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7712 | 45369.6762 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer79 | FAASt number pending 140 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 141 |  | DAR -CAGUAS 2601, 2604, 3016 – FY25 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7712 | 45369.6766 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer80 | FAASt number pending 141 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 142 |  | DAR -CAGUAS 3402 - FY25 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7712 | 45369.6769 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer81 | FAASt number pending 142 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 143 |  | 38kV Reclosers TLine 4800 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7713 | 45369.6772 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer82 | FAASt number pending 143 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 144 |  | 38kV Reclosers TLine 1500 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7713 | 45369.6777 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer83 | FAASt number pending 144 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 145 |  | 38kV Reclosers TLine 3700 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7713 | 45369.678 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer84 | FAASt number pending 145 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 146 |  | 38kV Reclosers TLine 1900 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7713 | 45369.6785 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer85 | FAASt number pending 146 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 147 |  | 38kV Reclosers TLine 2100 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7713 | 45369.6788 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer86 | FAASt number pending 147 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 148 |  | 38kV Reclosers TLine 7800 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7713 | 45369.6791 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer87 | FAASt number pending 148 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 149 |  | 38kV Reclosers TLine 800 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7713 | 45369.6794 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer88 | FAASt number pending 149 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 150 |  | 38kV Reclosers TLine 13400 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7713 | 45369.6797 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer89 | FAASt number pending 150 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 151 |  | 38kV Reclosers TLine 12600 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7713 | 45369.68 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer90 | FAASt number pending 151 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 152 |  | 38kV Reclosers TLine 100 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7713 | 45369.6803 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer91 | FAASt number pending 152 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 153 |  | 38kV Reclosers TLine 8100 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7713 | 45369.6807 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer92 | FAASt number pending 153 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 154 |  | 38kV Reclosers TLine 1600 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7713 | 45369.681 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer93 | FAASt number pending 154 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 155 |  | 38kV Reclosers TLine 2000 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7713 | 45369.6813 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer94 | FAASt number pending 155 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 156 |  | 38kV Reclosers TLine 2200 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7713 | 45369.6815 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer95 | FAASt number pending 156 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 157 |  | 38kV Reclosers TLine 3100 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7713 | 45369.6818 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer96 | FAASt number pending 157 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 158 |  | 38kV Reclosers TLine 3000 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7713 | 45369.6821 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer97 | FAASt number pending 158 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 159 |  | 38kV Reclosers TLine 3600 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7713 | 45369.6824 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer98 | FAASt number pending 159 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 160 |  | 38kV Reclosers TLine 6500 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7713 | 45369.6827 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer99 | FAASt number pending 160 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 161 |  | 38kV Reclosers TLine 5600 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7713 | 45369.6831 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer100 | FAASt number pending 161 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 162 |  | 38kV Reclosers TLine 8200 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7713 | 45369.6834 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer101 | FAASt number pending 162 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 163 |  | 38kV Reclosers TLine 3200 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7713 | 45369.6837 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer102 | FAASt number pending 163 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 164 |  | Distribution Pole and Conductor Repair – Mayaquez Group 3 – Phase 2 |  |  | Distribution – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7713 | 45370.5323 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer103 | FAASt Number Pending 164 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
738671-1 | 11819 | 4 x 25 MW BESS Interconnections Barceloneta TC |  | PBUT37 - Microgrid Inst & Integ | Grid Modernization |  | TRUE |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 46078.5745 | 45370.6243 | Marlina Crespo | 4x25 MW BESS Interconnections at LUMA 38 kV System | Ashleah Dingle | [7 empty] | qwer104 | 738671-1 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
738671-2 | 11819 | 4 x 25 MW BESS Interconnections Vega Baja TC |  | PBUT37 - Microgrid Inst & Integ | Grid Modernization |  | TRUE |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 46078.5745 | 45370.6251 | Marlina Crespo | 4x25 MW BESS Interconnections at LUMA 38 kV System | Ashleah Dingle | [7 empty] | qwer105 | 738671-2 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
738671-3 | 11819 | 4 x 25 MW BESS Interconnections Aguadilla TC |  | PBUT37 - Microgrid Inst & Integ | Grid Modernization |  | TRUE |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 46078.5745 | 45370.6259 | Marlina Crespo | 4x25 MW BESS Interconnections at LUMA 38 kV System | Ashleah Dingle | [7 empty] | qwer106 | 738671-3 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 165 |  | Advanced Sensors Phasor Measurement Units (PMUs), and Wide-Area Monitoring, Protection, and Control (WAMPAC) |  |  | Grid Modernization |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7713 | 45370.6263 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer107 | FAASt number pending 165 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 166 |  | DAF Fuse Cutout Installation - Group A |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7713 | 45370.7346 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer108 | FAASt Number Pending 166 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 167 |  | DAR - PONCE 5011, 5013, 5016 - FY24 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7713 | 45370.7354 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer109 | FAASt Number Pending 167 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
700 - Costa Sur to Yauco Plaza |  |  |  |  | Transmission |  |  |  | FALSE |  |  | FALSE |  |  |  | 45314 |  | 45400 | 45419 |  | 45430 | 45399 | 45373 | [10 empty] | 24998791 | [6 empty] | 0 | 24998791 | 24998791 | [11 empty] | 0 | 0 |  |  | 3/19/2024 LUMA Grid Strategy Notes - Batch 3 Transmission Lines (18 - PLRC Approval Required) | 45856.7713 | 45371.6705 | Ashleah Dingle |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer110 | 700 - Costa Sur to Yauco Plaza |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
41200 - Sabana Llana to Canóvanas |  |  |  |  | Transmission |  |  |  | FALSE |  |  | FALSE |  |  |  | 45314 | [6 empty] | 45373 | [10 empty] | 48460000 | [6 empty] | 0 | 48460000 | 48460000 | [11 empty] | 0 | 0 |  |  | 3/19/2024 LUMA Grid Strategy Notes - Batch 3 Transmission Lines (18 - PLRC Approval Required)3/19/2024 LUMA Regulatory ISOW to PREB Notes - TBD for PREB Submittal Target Date On Hold. Daniel Haughton is working with PM to update initial SOW. Once they complete that they will send it back to us for submittal. | 45856.7713 | 45371.6778 | Ashleah Dingle |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer111 | 41200 - Sabana Llana to Canóvanas |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Sub Rebuild - Fajardo TC |  |  |  | PBUT08 - Substation Rebuilds | Substation |  |  |  | FALSE |  |  | FALSE |  |  |  | 45317 | [24 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  | 3/19/2024 LUMA Regulatory Notes on ISOW to PREB - PREB Submittal Target Date: TBD, Notes: need the ISOW | 45856.7713 | 45371.7086 | Ashleah Dingle |  | Rey Roldan Rodríguez | [7 empty] | qwer112 | Sub Rebuild - Fajardo TC |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 168 |  | DAR - BAYAMON 1708, 1734, 1801, 1901 - FY24 |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7713 | 45372.6231 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer113 | FAASt Number Pending 168 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Dorado Pueblo 9202-04 |  |  |  |  | Distribution |  |  |  | FALSE |  |  | FALSE |  |  |  | 45322 | 3000000 | 45387 | 45405 |  | 45417 | 45387 | 45379 | [10 empty] | 9800000 | [6 empty] | 0 | 9800000 | 9800000 | [11 empty] | 0 | 0 |  |  |  | 45856.7713 | 45373.5282 | Jeremy Malone | Distribution Feeder Dorado Pueblo 8.32 kV 9202-04 | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer114 | Dorado Pueblo 9202-04 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Hato Tejas TC 1713-05 |  |  |  |  | Distribution |  |  |  | FALSE |  |  | FALSE |  |  |  | 45322 | 12300000 | 45387 | 45405 |  | 45417 | 45387 | 45379 | [10 empty] | 12300000 | [6 empty] | 0 | 12300000 | 12300000 | [11 empty] | 0 | 0 |  |  |  | 45856.7713 | 45373.5289 | Jeremy Malone | Distribution Feeder Hato Tejas 1713-05 | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer115 | Hato Tejas TC 1713-05 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
El Abanico PDS 9605-02 |  |  |  |  | Distribution |  |  |  | FALSE |  |  | FALSE |  |  |  | 45322 | 20400000 | 45387 | 45405 |  | 45417 | 45387 | 45379 | [10 empty] | 20400000 | [6 empty] | 0 | 20400000 | 20400000 | [11 empty] | 0 | 0 |  |  |  | 45856.7713 | 45373.5296 | Jeremy Malone | Distribution Feeder El Abanico PDS 9605-02 | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer116 | El Abanico PDS 9605-02 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Humacao Pueblo 2601-01 |  |  |  |  | Distribution |  |  |  | FALSE |  |  | FALSE |  |  |  | 45322 | 11200000 | 45387 | 45405 |  | 45417 | 45387 | 45379 | [10 empty] | 11200000 | [6 empty] | 0 | 11200000 | 11200000 | [11 empty] | 0 | 0 |  |  |  | 45856.7713 | 45373.5302 | Jeremy Malone | Distribution Feeder Humacao Pueblo 2601-01 | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer117 | Humacao Pueblo 2601-01 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Cachete 13KV 1529-11 |  |  |  |  | Distribution |  |  |  | FALSE |  |  | FALSE |  |  |  | 45322 | 8100000 | 45387 | 45405 |  | 45417 | 45387 | 45379 | [10 empty] | 8100000 | [6 empty] | 0 | 8100000 | 8100000 | [11 empty] | 0 | 0 |  |  |  | 45856.7713 | 45373.5342 | Jeremy Malone | Distribution Feeder Cachete 13 kV 1529-11 | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer118 | Cachete 13KV 1529-11 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Fort Allen 13KV 5803-02 |  |  |  |  | Distribution |  |  |  | FALSE |  |  | FALSE |  |  |  | 45322 | 18000000 | 45387 | 45405 |  | 45417 | 45387 | 45379 | [10 empty] | 18000000 | [6 empty] | 0 | 18000000 | 18000000 | [11 empty] | 0 | 0 |  |  |  | 45856.7713 | 45373.5536 | Jeremy Malone | Distribution Feeder Fort Allen 5803-02 | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer119 | Fort Allen 13KV 5803-02 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Berwind 13KV 1336-07 |  |  |  |  | Distribution |  |  |  | FALSE |  |  | FALSE |  |  |  | 45322 | 11200000 | 45387 | 45405 |  | 45417 | 45387 | 45379 | [10 empty] | 11200000 | [6 empty] | 0 | 11200000 | 11200000 | [11 empty] | 0 | 0 |  |  |  | 45856.7713 | 45373.5579 | Jeremy Malone | Distribution Feeder Berwin 13 kV 1336-07 | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer120 | Berwind 13KV 1336-07 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Encantada 1206-03 |  |  |  |  | Distribution |  |  |  | FALSE |  |  | FALSE |  |  |  | 45322 | 12700000 | 45387 | 45405 |  | 45417 | 45387 | 45379 | [10 empty] | 12700000 | [6 empty] | 0 | 12700000 | 12700000 | [11 empty] | 0 | 0 |  |  |  | 45856.7713 | 45373.5587 | Jeremy Malone | Distribution Feeder Encantada 1206-03 | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer121 | Encantada 1206-03 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Buen Pastor 1908-03 |  |  |  |  | Distribution |  |  |  | FALSE |  |  | FALSE |  |  |  | 45322 | 20700000 | 45387 | 45405 |  | 45417 | 45387 | 45379 | [10 empty] | 20700000 | [6 empty] | 0 | 20700000 | 20700000 | [11 empty] | 0 | 0 |  |  |  | 45856.7713 | 45373.56 | Jeremy Malone | Distribution Feeder Buen Pastor 1908-03 | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer122 | Buen Pastor 1908-03618 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Area Planning Bayamón F |  |  |  |  | Distribution |  |  |  | FALSE |  |  | FALSE |  |  |  | 45323 | 119100000 | 45349 | 45364 |  | 45379 | [12 empty] | 119100000 | [6 empty] | 0 | 119100000 | 119100000 | [11 empty] | 0 | 0 |  |  |  | 45856.7713 | 45373.5713 | Jeremy Malone | Area Planning - Bayamón F | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer123 | Area Planning Bayamón F |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Area Planning Bayamón G |  |  |  |  | Distribution | [6 empty] | FALSE |  |  |  | 45323 | 42400000 | 45349 | 45364 |  | 45379 | [12 empty] | 42200000 | [6 empty] | 0 | 42200000 | 42200000 | [11 empty] | 0 | 0 |  |  |  | 45856.7713 | 45373.5717 | Jeremy Malone | Area Planning - Bayamón G | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer124 | Area Planning Bayamón G |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Area Planning San Juan B |  |  |  |  | Distribution |  |  |  | FALSE |  |  | FALSE |  |  |  | 45323 | 58200000 | 45349 | 45364 |  | 45379 | [12 empty] | 58200000 | [6 empty] | 0 | 58200000 | 58200000 | [11 empty] | 0 | 0 |  |  |  | 45856.7713 | 45373.5794 | Jeremy Malone | Area Planning - San Juan B | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer125 | Area Planning San Juan B |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Area Planning San Juan C |  |  |  |  | Distribution |  |  |  | FALSE |  |  | FALSE |  |  |  | 45323 | 150700000 | 45349 | 45364 |  | 45379 | [12 empty] | 1507000 | [6 empty] | 0 | 1507000 | 1507000 | [11 empty] | 0 | 0 |  |  |  | 45856.7713 | 45373.5797 | Jeremy Malone | Area Planning - San Juan C | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer126 | Area Planning San Juan C |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Area Planning San Juan D |  |  |  |  | Distribution |  |  |  | FALSE |  |  | FALSE |  |  |  | 45323 | 71800000 | 45349 | 45364 |  | 45379 | [12 empty] | 71800000 | [6 empty] | 0 | 71800000 | 71800000 | [11 empty] | 0 | 0 |  |  |  | 45856.7713 | 45373.5799 | Jeremy Malone | Area Planning - San Juan D | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer127 | Area Planning San Juan D |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Area Planning San Juan F |  |  |  |  | Distribution |  |  |  | FALSE |  |  | FALSE |  |  |  | 45323 | 30300000 | 45349 | 45364 |  | 45379 | [12 empty] | 30300000 | [6 empty] | 0 | 30300000 | 30300000 | [11 empty] | 0 | 0 |  |  |  | 45856.7713 | 45373.5802 | Jeremy Malone | Area Planning - San Juan F | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer128 | Area Planning San Juan F |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Area Planning San Juan G |  |  |  |  | Distribution |  |  |  | FALSE |  |  | FALSE |  |  |  | 45323 | 39500000 | 45349 | 45364 |  | 45379 | [12 empty] | 39500000 | [6 empty] | 0 | 39500000 | 39500000 | [11 empty] | 0 | 0 |  |  |  | 45856.7713 | 45373.5805 | Jeremy Malone | Area Planning - San Juan G | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer129 | Area Planning San Juan G |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Area Planning San Juan K |  |  |  |  | Distribution |  |  |  | FALSE |  |  | FALSE |  |  |  | 45323 | 45400000 | 45349 | 45364 |  | 45379 | [12 empty] | 45400000 | [6 empty] | 0 | 45400000 | 45400000 | [11 empty] | 0 | 0 |  |  |  | 45856.7713 | 45373.5807 | Jeremy Malone | Area Planning - San Juan K | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer130 | Area Planning San Juan K |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Area Planning Bayamón A |  |  |  |  | Distribution |  |  |  | FALSE |  |  | FALSE |  |  |  | 45323 | 89400000 | 45349 | 45364 |  | 45379 | [12 empty] | 89400000 | [6 empty] | 0 | 89400000 | 89400000 | [11 empty] | 0 | 0 |  |  |  | 45856.7713 | 45373.5809 | Jeremy Malone | Area Planning ‐ Bayamón A | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer131 | Area Planning Bayamón A |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Area Planning Bayamón C |  |  |  |  | Distribution |  |  |  | FALSE |  |  | FALSE |  |  |  | 45323 | 64800000 | 45349 | 45364 |  | 45379 | [12 empty] | 64800000 | [6 empty] | 0 | 64800000 | 64800000 | [11 empty] | 0 | 0 |  |  |  | 45856.7713 | 45373.5812 | Jeremy Malone | Area Planning ‐ Bayamón C | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer132 | Area Planning Bayamón C |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Substation Component Replacement Program |  |  |  |  | Substation |  |  |  | FALSE |  |  | FALSE |  |  |  | 45318 |  | 45349 | 45364 |  | 45379 | [12 empty] | 330300000 | [6 empty] | 0 | 330300000 | 330300000 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/782/DR4339PR-FEMA%20ISOW%20Substation%20Component%20Replacement%20Program%20Rev%200%20-%20signed.pdf?web=1 | Initial ISOW date submitted to FEMA 3/26/2024 but has since been removed | 45856.7713 | 45377.4921 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer133 | Substation Component Replacement Program |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
746108 | 11779 | FAASt [San Juan Streetlighting - Part 2] (Distribution) | 14F018770000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting |  |  | Restoration | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45378 | 03/27/2024 |  | 45378 | 45394 |  |  |  | 3 | 34002129 | 26445766.74 | 3331645 | 4224718 |  | 26445767 | 458919 | 2872726 | 29777412 | 34002130 | 45473 | 45626 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/783/746108-DR4339PR-Detailed%20SOW%20Streetlight%20San%20Juan%20P2%20Medium%20Priority-DSOW-Work%20To%20Be%20Completed%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short List | 45877.496 | 45379.4222 | Marlina Crespo | Distribution Streetlighting | Maria Mujica Gonzalez |  |  |  |  | 0.88812 | 1 | 45876 | qwer134 | 746108 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
746111 | 11778 | FAASt [Caguas Streetlighting - Part 2] (Distribution) | 14F018590000 | PBUT05 - Distr Streetlighting | Distribution – Streetlighting |  |  | Restoration | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45378 | 03/27/2024 |  | 45378 | 45394 |  |  |  | 3 | 13628925 | 10160311.88 | 1317294 | 2151320 |  | 10160312 | 230183 | 1087111 | 11477606 | 13628926 | 45473 | 45626 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/784/746111-DR4339PR-Detailed%20SOW%20Streetlight%20Caguas%20P2%20Medium%20Priority-DSOW-Work%20To%20Be%20Completed%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Short List | 45877.4922 | 45379.4249 | Marlina Crespo | Distribution Streetlighting | Maria Mujica Gonzalez |  |  |  |  | 0.88523 | 1 | 45876 | qwer135 | 746111 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
TBD UG Feeder Rebuilds - Phase 1 |  |  |  |  | Distribution – Feeder Rebuild |  |  |  | FALSE |  |  | FALSE |  |  |  | 45321 |  | 45349 | 45364 |  | 45379 |  |  |  | 45378 | [8 empty] | 249921003 | [6 empty] | 0 | 249921003 | 249921003 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/785/DR-4339%20ISOW-UG%20Feeder%20Rebuilds%20-%20Phase%201_Rev.0%20-%20signed.pdf?web=1 | 02MAY2025 Taking the funds off the tracker. This is an island wide project and we already have 2 projects under this project umbrella - MC | 45880.388 | 45379.5975 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 0 | 5 |  | qwer136 | TBD UG Feeder Rebuilds - Phase 1 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Maunabo TC Rev 2 |  |  |  |  | Substation |  |  |  | FALSE |  |  | FALSE |  |  |  | 45317 |  | 45357 | 45378 |  | 45387 | [12 empty] | 96115838 | [6 empty] | 0 | 96115838 | 96115838 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/786/DR4339PR%20-%20FEMA%20ISOW%20Maunabo%20TC%20Rev%202%20-%20signed.pdf?web=1 | Initial ISOW date submitted to FEMA 4/1/2024 but has since been removed | 45856.7714 | 45383.3997 | Marlina Crespo | Substation Minor Repairs | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer137 | Maunabo TC Rev 2 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Mayaguez TC Rev 2 |  |  |  |  | Substation |  |  |  | FALSE |  |  | FALSE |  |  |  | 45322 | 14400000 | 45357 | 45378 |  | 45387 | [12 empty] | 14464362 | [6 empty] | 0 | 14464362 | 14464362 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/787/DR4339PR-FEMA%20ISOW%20Mayaguez%20TC%20Rev%202%20-%20signed.pdf?web=1 | Initial ISOW date submitted to FEMA 4/1/2024 but has since been removed | 45856.7714 | 45383.4002 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer138 | Mayaguez TC Rev 2 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
748180 | 107961 | FAASt [Advanced Sensors Phasor Measurement Units (PMUs), and Wide-Area Monitoring, Protection, and Control (WAMPAC)] (Telecommunication) | 14F020010000 | PBUT07 - Substation Reliability | Grid Modernization |  | TRUE | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | 45321 | 49750000 | 45357 | 45378 |  | 45387 |  |  |  | 45383 | 05/09/2024 |  | 45566 | 45741 |  |  |  |  | 49755331 | 49755331 | 52804979.05 | 0 |  | 0 | 5250645.64 | 47554333.41 | 52804979.05 | 52804979.05 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/788/DR4339PR-FEMA%20ISOW%20PAC%20WAMPAC%20Program%20Rev%200%20-%20signed.pdf?web=1 |  | 46059.6463 | 45383.4006 | Marlina Crespo | Deployment of Advanced Sensors, Phasor Measurement Units (PMUs), and Wide-Area Monitoring, Protection, and Control (WAMPAC) | Jason Fournier | 0 Months |  |  |  | 0.94225 | 1 | 45880 | qwer139 | 748180 | 0 | 423360 | 423360 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Adjuntas Pueblo 8.32kV 8202-01 |  |  |  |  | Distribution |  |  |  | FALSE |  |  | FALSE |  |  |  | 45322 | 4500000 | 45387 | 45405 |  | 45417 | 45387 | 45379 | [10 empty] | 4500000 | [6 empty] | 0 | 4500000 | 4500000 | [11 empty] | 0 | 0 |  |  |  | 45856.7714 | 45385.5425 | Jeremy Malone | Distribution Feeder Adjuntas Pueblo 8.32 kV 8202-01 | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer140 | Adjuntas Pueblo 8.32kV 8202-01 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Aguada 7205-01 4.16kV |  |  |  |  | Distribution |  |  |  | FALSE |  |  | FALSE |  |  |  | 45322 | 13500000 | 45387 | 45405 |  | 45417 | 45387 | 45379 | [10 empty] | 13500000 | [6 empty] | 0 | 13500000 | 13500000 | [11 empty] | 0 | 0 |  |  |  | 45856.7714 | 45385.5427 | Jeremy Malone | Distribution Feeder Aguada 7205-01 4.16 kV | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer141 | Aguada 7205-01 4.16kV |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Aguas Buenas 3701-02 |  |  |  |  | Distribution |  |  |  | FALSE |  |  | FALSE |  |  |  | 45322 | 5200000 | 45387 | 45405 |  | 45417 | 45387 | 45379 | [10 empty] | 5200000 | [6 empty] | 0 | 5200000 | 5200000 | [11 empty] | 0 | 0 |  |  |  | 45856.7714 | 45385.5428 | Jeremy Malone | Distribution Feeder Aguas Buenas 3701-02 | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer142 | Aguas Buenas 3701-02 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Añasco 6101-04 |  |  |  |  | Distribution |  |  |  | FALSE |  |  | FALSE |  |  |  | 45322 | 12600000 | 45387 | 45405 |  | 45417 | 45387 | 45379 | [10 empty] | 12600000 | [6 empty] | 0 | 12600000 | 12600000 | [11 empty] | 0 | 0 |  |  |  | 45856.7714 | 45385.543 | Jeremy Malone | Distribution Feeder Añasco 6101-04 | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer143 | Añasco 6101-04 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Añasco 6101-05 |  |  |  |  | Distribution |  |  |  | FALSE |  |  | FALSE |  |  |  | 45322 | 10500000 | 45387 | 45405 |  | 45417 | 45387 | 45379 | [10 empty] | 10500000 | [6 empty] | 0 | 10500000 | 10500000 | [11 empty] | 0 | 0 |  |  |  | 45856.7714 | 45385.5432 | Jeremy Malone | Distribution Feeder Añasco 6101-05 | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer144 | Añasco 6101-05 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Buen Pastor 1908-03 |  |  |  |  | Distribution |  |  |  | FALSE |  |  | FALSE |  |  |  | 45322 | 20700000 | 45387 | 45405 |  | 45417 | 45387 | 45379 | [10 empty] | 20700000 | [6 empty] | 0 | 20700000 | 20700000 | [11 empty] | 0 | 0 |  |  |  | 45856.7714 | 45385.5441 | Jeremy Malone | Distribution Feeder Buen Pastor 1908-03 | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer145 | Buen Pastor 1908-03641 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Cana (Interamericana) 1719-15 |  |  |  |  | Distribution |  |  |  | FALSE |  |  | FALSE |  |  |  | 45322 | 7500000 | 45387 | 45405 |  | 45417 | 45387 | 45379 | [10 empty] | 7500000 | [6 empty] | 0 | 7500000 | 7500000 | [11 empty] | 0 | 0 |  |  |  | 45856.7714 | 45385.5446 | Jeremy Malone | Distribution Feeder Cana (Interamericana) 1719-15 | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer146 | Cana (Interamericana) 1719-15 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Cana (Interamericana) 1719-18 |  |  |  |  | Distribution |  |  |  | FALSE |  |  | FALSE |  |  |  | 45322 | 11200000 | 45387 | 45405 |  | 45417 | 45387 | 45379 | [10 empty] | 11200000 | [6 empty] | 0 | 11200000 | 11200000 | [11 empty] | 0 | 0 |  |  |  | 45856.7714 | 45385.5447 | Jeremy Malone | Distribution Feeder Cana (Interamericana) 1719-18 | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer147 | Cana (Interamericana) 1719-18 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Candelero 2604-01 |  |  |  |  | Distribution |  |  |  | FALSE |  |  | FALSE |  |  |  | 45322 | 12700000 | 45387 | 45405 |  | 45417 | 45387 | 45379 | [10 empty] | 12700000 | [6 empty] | 0 | 12700000 | 12700000 | [11 empty] | 0 | 0 |  |  |  | 45856.7714 | 45385.5449 | Jeremy Malone | Distribution Feeder Candelero 2604-01 | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer148 | Candelero 2604-01 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Coamo PDS 4603-02 |  |  |  |  | Distribution |  |  |  | FALSE |  |  | FALSE |  |  |  | 45322 | 12000000 | 45387 | 45405 |  | 45417 | 45387 | 45379 | [10 empty] | 12000000 | [6 empty] | 0 | 12000000 | 12000000 | [11 empty] | 0 | 0 |  |  |  | 45856.7714 | 45385.5473 | Jeremy Malone | Distribution Feeder Coamo PDS 4603-02 | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer149 | Coamo PDS 4603-02 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Crea 1717-01 |  |  |  |  | Distribution |  |  |  | FALSE |  |  | FALSE |  |  |  | 45322 | 7500000 | 45387 | 45405 |  | 45417 | 45387 | 45379 | [10 empty] | 7500000 | [6 empty] | 0 | 7500000 | 7500000 | [11 empty] | 0 | 0 |  |  |  | 45856.7714 | 45385.5474 | Jeremy Malone | Distribution Feeders Crea 1717-01 | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer150 | Crea 1717-01 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Cuatro Hermanos 6004-02 |  |  |  |  | Distribution |  |  |  | FALSE |  |  | FALSE |  |  |  | 45322 | 13900000 | 45387 | 45405 |  | 45417 | 45387 | 45379 | [10 empty] | 13900000 | [6 empty] | 0 | 13900000 | 13900000 | [11 empty] | 0 | 0 |  |  |  | 45856.7714 | 45385.5476 | Jeremy Malone | Distribution Feeder Cuatro Hermanos 6004-02 | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer151 | Cuatro Hermanos 6004-02 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Grana PDS 1907-05 |  |  |  |  | Distribution |  |  |  | FALSE |  |  | FALSE |  |  |  | 45322 | 3000000 | 45387 | 45405 |  | 45417 | 45387 | 45379 | [10 empty] | 3000000 | [6 empty] | 0 | 3000000 | 3000000 | [11 empty] | 0 | 0 |  |  |  | 45856.7714 | 45385.5477 | Jeremy Malone | Distribution Feeder Grana PDS 1907-05 | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer152 | Grana PDS 1907-05 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Humacao TC 13 kV 2603-09 |  |  |  |  | Distribution |  |  |  | FALSE |  |  | FALSE |  |  |  | 45322 | 17600000 | 45387 | 45405 |  | 45417 | 45387 | 45379 | [10 empty] | 17600000 | [6 empty] | 0 | 17600000 | 17600000 | [11 empty] | 0 | 0 |  |  |  | 45856.7714 | 45385.5498 | Jeremy Malone | Distribution Feeder Humacao TC 13 kV 2603-09 | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer153 | Humacao TC 13 kV 2603-09 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Isabela Planta 3 7504-01 4.16kV |  |  |  |  | Distribution |  |  |  | FALSE |  |  | FALSE |  |  |  | 45322 | 6900000 | 45387 | 45405 |  | 45417 | 45387 | 45379 | [10 empty] | 6900000 | [6 empty] | 0 | 6900000 | 6900000 | [11 empty] | 0 | 0 |  |  |  | 45856.7714 | 45385.5501 | Jeremy Malone | Distribution Feeder Isabela Planta 3 7504-01 4.16 kV | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer154 | Isabela Planta 3 7504-01 4.16kV |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Juncos 3201-02 |  |  |  |  | Distribution |  |  |  | FALSE |  |  | FALSE |  |  |  | 45322 | 15000000 | 45387 | 45405 |  | 45417 | 45387 | 45379 | [10 empty] | 15000000 | [6 empty] | 0 | 15000000 | 15000000 | [11 empty] | 0 | 0 |  |  |  | 45856.7714 | 45385.5542 | Jeremy Malone | Distribution Feeder Juncos 3201-02 | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer155 | Juncos 3201-02 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Llorens Torres 13 kV 1118-08 |  |  |  |  | Distribution |  |  |  | FALSE |  |  | FALSE |  |  |  | 45322 | 4200000 | 45387 | 45405 |  | 45417 | 45387 | 45379 | [10 empty] | 4200000 | [6 empty] | 0 | 4200000 | 4200000 | [11 empty] | 0 | 0 |  |  |  | 45856.7714 | 45385.5544 | Jeremy Malone | Distribution Feeder Llorens Torres 13 kV 1118-08 | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer156 | Llorens Torres 13 kV 1118-08 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Llorens Torres 13 kV 1118-09 |  |  |  |  | Distribution |  |  |  | FALSE |  |  | FALSE |  |  |  | 45322 | 4500000 | 45387 | 45405 |  | 45417 | 45387 | 45379 | [10 empty] | 4500000 | [6 empty] | 0 | 4500000 | 4500000 | [11 empty] | 0 | 0 |  |  |  | 45856.7714 | 45385.5548 | Jeremy Malone | Distribution Feeder Llorens Torres 13 kV 1118-09 | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer157 | Llorens Torres 13 kV 1118-09 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Monacillos 13 kV 1346-03 |  |  |  |  | Distribution |  |  |  | FALSE |  |  | FALSE |  |  |  | 45322 | 8200000 | 45387 | 45405 |  | 45417 | 45387 | 45379 | [10 empty] | 8200000 | [6 empty] | 0 | 8200000 | 8200000 | [11 empty] | 0 | 0 |  |  |  | 45856.7714 | 45385.555 | Jeremy Malone | Distribution Feeder Monacillos 13 kV 1346-03 | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer158 | Monacillos 13 kV 1346-03 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Monterrey PDS 13 kV 9503-06 |  |  |  |  | Distribution |  |  |  | FALSE |  |  | FALSE |  |  |  | 45322 |  | 45387 | 45405 |  | 45417 | 45387 | 45379 | [10 empty] | 11700000 | [6 empty] | 0 | 11700000 | 11700000 | [11 empty] | 0 | 0 |  |  |  | 45856.7714 | 45385.5605 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer159 | Monterrey PDS 13 kV 9503-06 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Peñuelas Pueblo 5401-02 |  |  |  |  | Distribution |  |  |  | FALSE |  |  | FALSE |  |  |  | 45322 |  | 45387 | 45405 |  | 45417 | 45387 | 45379 | [10 empty] | 8300000 | [6 empty] | 0 | 8300000 | 8300000 | [11 empty] | 0 | 0 |  |  |  | 45856.7714 | 45385.5609 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer160 | Peñuelas Pueblo 5401-02 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Rio Bayamon 1709-05 |  |  |  |  | Distribution |  |  |  | FALSE |  |  | FALSE |  |  |  | 45322 |  | 45387 | 45405 |  | 45417 | 45387 | 45379 | [10 empty] | 11100000 | [6 empty] | 0 | 11100000 | 11100000 | [11 empty] | 0 | 0 |  |  |  | 45856.7714 | 45385.5611 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer161 | Rio Bayamon 1709-05 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Rio Bayamon 1709-02 |  |  |  |  | Distribution |  |  |  | FALSE |  |  | FALSE |  |  |  | 45322 |  | 45387 | 45405 |  | 45417 | 45387 | 45379 | [10 empty] | 8200000 | [6 empty] | 0 | 8200000 | 8200000 | [11 empty] | 0 | 0 |  |  |  | 45856.7714 | 45385.5622 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer162 | Rio Bayamon 1709-02 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
San Jose 8104-02 4.16 kV |  |  |  |  | Distribution |  |  |  | FALSE |  |  | FALSE |  |  |  | 45322 |  | 45387 | 45405 |  | 45417 | 45387 | 45379 | [10 empty] | 12000000 | [6 empty] | 0 | 12000000 | 12000000 | [11 empty] | 0 | 0 |  |  |  | 45856.7714 | 45385.5624 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer163 | San Jose 8104-02 4.16 kV |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Unibon 9.32 kV 9501-01 |  |  |  |  | Distribution |  |  |  | FALSE |  |  | FALSE |  |  |  | 45322 |  | 45387 | 45405 |  | 45417 | 45387 | 45379 | [10 empty] | 11300000 | [6 empty] | 0 | 11300000 | 11300000 | [11 empty] | 0 | 0 |  |  |  | 45856.7714 | 45385.5625 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer164 | Unibon 9.32 kV 9501-01 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Vega Baja TC 13 kV 9004-08 |  |  |  |  | Distribution |  |  |  | FALSE |  |  | FALSE |  |  |  | 45322 |  | 45387 | 45405 |  | 45417 | 45387 | 45379 | [10 empty] | 22800000 | [6 empty] | 0 | 22800000 | 22800000 | [11 empty] | 0 | 0 |  |  |  | 45856.7714 | 45385.5658 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer165 | Vega Baja TC 13 kV 9004-08 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Vega Baja TC 13 kV 9004-10 |  |  |  |  | Distribution |  |  |  | FALSE |  |  | FALSE |  |  |  | 45322 |  | 45387 | 45405 |  | 45417 | 45387 | 45379 | [10 empty] | 21400000 | [6 empty] | 0 | 21400000 | 21400000 | [11 empty] | 0 | 0 |  |  |  | 45856.7714 | 45385.5659 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer166 | Vega Baja TC 13 kV 9004-10 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Sabana Grande 4.16 kV 6501-04 |  |  |  |  | Distribution |  |  |  | FALSE |  |  | FALSE |  |  |  | 45322 |  | 45387 | 45405 |  | 45417 | 45387 | 45379 | [10 empty] | 9700000 | [6 empty] | 0 | 9700000 | 9700000 | [11 empty] | 0 | 0 |  |  |  | 45856.7714 | 45385.5663 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer167 | Sabana Grande 4.16 kV 6501-04 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Yabucoa Pueblo 2901-04 |  |  |  |  | Distribution |  |  |  | FALSE |  |  | FALSE |  |  |  | 45322 |  | 45387 | 45405 |  | 45417 | 45387 | 45379 | [10 empty] | 12770000 | [6 empty] | 0 | 12770000 | 12770000 | [11 empty] | 0 | 0 |  |  |  | 45856.7714 | 45385.5783 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer168 | Yabucoa Pueblo 2901-04 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Buildings Island-Wide Program |  |  |  |  | Building |  |  |  | FALSE |  |  | FALSE |  |  |  | 45322 | 97477246.69 | 45492 | 45516 |  | 45522 | 45434 | 45408 | [10 empty] | 97477246.69 | [6 empty] | 0 | 97477246.69 | 97477246.69 | [11 empty] | 0 | 0 |  |  |  | 45856.7714 | 45387.6825 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer169 | Buildings Island-Wide Program |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Cerro las Mesas 6010-02 |  |  |  |  | Distribution |  |  |  | FALSE |  |  | FALSE |  |  |  | 45322 |  | 45387 | 45405 |  | 45417 | 45387 | 45379 | [10 empty] | 15000000 | [6 empty] | 0 | 15000000 | 15000000 | [11 empty] | 0 | 0 |  |  |  | 45856.7714 | 45387.7124 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer170 | Cerro las Mesas 6010-02 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Bayamon TC 4kV 1714-02 |  |  |  |  | Distribution |  |  |  | FALSE |  |  | FALSE |  |  |  | 45322 |  | 45387 | 45405 |  | 45417 | 45387 | 45379 | [10 empty] | 3750000 | [6 empty] | 0 | 3750000 | 3750000 | [11 empty] | 0 | 0 |  |  |  | 45856.7714 | 45387.7124 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer171 | Bayamon TC 4kV 1714-02 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Villa del Carmen 5016-01 |  |  |  |  | Distribution |  |  |  | FALSE |  |  | FALSE |  |  |  | 45322 |  | 45387 | 45405 |  | 45417 | 45387 | 45379 | [10 empty] | 11100000 | [6 empty] | 0 | 11100000 | 11100000 | [11 empty] | 0 | 0 |  |  |  | 45856.7714 | 45387.7125 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer172 | Villa del Carmen 5016-01 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Area Planning San Juan A |  |  |  |  | Distribution |  |  |  | FALSE |  |  | FALSE |  |  |  | 45323 |  | 45349 | 45364 |  | 45379 | [12 empty] | 120100000 | [6 empty] | 0 | 120100000 | 120100000 | [11 empty] | 0 | 0 |  |  |  | 45856.7714 | 45387.7161 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer173 | Area Planning San Juan A |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
746545 | 11824 | FAASt [Primary Control Center / Secondary Data Center & Control Room] (Telecommunication) | 14F000010000 | PBUT24 - Ctrl Ctr Const & Refurb | Building |  |  | Improved | FALSE |  | Current | FALSE |  |  |  | 45384 | 146000000 | 45400 | 45419 |  | 45430 |  |  |  | 45386 | 04/04/2024 |  | 45401 | 45425 | 45670 | 45656 |  | 2 | 146000000 | 115638378 | 0 | 15530896 |  | 115638378 | 0 | 0 | 115638378 | 131169274 | 45596 | 45688 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/830/DR4339PR-FASST-iSOW%20Primary%20Control%20Center%20%20(CC)%20-%2004.01.2024%20-%20signed.pdf?web=1 | 4/17/2024: QC Review Complete | 45856.7714 | 45390.4166 | Marlina Crespo | IT OT Telecom Systems & Network | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | qwer174 | 746545 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Morovis 8801 Rev 2 |  |  |  |  | Substation |  |  |  | FALSE |  |  | FALSE |  |  |  | 45314 | 5840000 | 45357 | 45378 |  | 45387 | [12 empty] | 5844709 | [6 empty] | 0 | 5844709 | 5844709 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/831/DR4339PR-FEMA%20ISOW%20Morovis%208801%20Rev%202%20-%20signed.pdf?web=1 | Initial ISOW date submitted to FEMA 4/8/2024 but has since been removed | 45856.7714 | 45390.4466 | Marlina Crespo | Pampanos Relocation | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer175 | Morovis 8801 Rev 2 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
746660 | 107960 | FAASt [Minor Protection, Automation, and Control [PAC] Replacement] (Substation) | 14F019740000, 14F019710000, 14F019730000, 14F019670000, 14F019700000, 14F019750000, 14F019690000, 14F019660000, 14F019720000, 14F019680000, 14F019660000, 14F019760000, 14F019650000, 14F019810000, 14F019790000, 14F019780000, 14F019800000, 14F019870000 | PBUT07 - Substation Reliability | Substation |  | TRUE | Restoration | FALSE |  | Current | FALSE |  | Resubmitted |  |  | 70500000 | 44438 | 44461 |  | 44468 |  |  |  | 45390 | 04/08/2024 |  | 45393 | 46093 |  |  |  | 1 | 70500000 | 70500000 | 240530.55 | 1843798.14 |  | 13962542.11 | 63677.66 | 176852.89 | 14203072.66 | 16046870.8 | 45777 | 45961 | [9 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/832/746660-DR4339PR-%20DSOW%20Minor%20PAC%20Replacement%20%20Group%201%2004112024.pdf?web=1 | Originally withdrawn on 12/4/2025. This project was reactivated on 12/10/2025 | 46094.6472 | 45391.3709 | Marlina Crespo | Minor PAC Replacement and Hazard Mitigation | Marlina Crespo |  |  |  |  | 4.9637 | 1 |  | qwer176 | 746660 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Transmission Program ISOW |  |  |  |  | Transmission |  |  |  | FALSE |  |  | FALSE |  |  |  | 45322 |  | 45464 | 45475 |  | 45494 |  | 45373 | [10 empty] | 501947756 | [6 empty] | 0 | 501947756 | 501947756 | [11 empty] | 0 | 0 |  |  |  | 45856.7714 | 45401.4479 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer177 | Transmission Program ISOW |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
751656 | 107983 | FAASt [Culebra Microgrid] (Transmission) | 14F021690000 | PBUT37 - Microgrid Inst & Integ | Grid Modernization |  |  | Restoration | FALSE |  | Current | FALSE | [12 empty] | 45013 | 07/18/2024 |  | 45492 | 45883 |  |  |  |  | 125117462.87 | 40846080 | 73445001.67 | 366170.82 |  | 46260.79 | 73445001.67 | 0 | 73491262.46 | 73857433.28 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/836/4339-0280_Phase%201%20Approval_VC%20Microgrids_20230328%20(002).pdf?web=1 |  | 45980.6685 | 45407.6689 | Marlina Crespo | Vieques and Culebra Microgrid | Marlina Crespo |  |  |  |  | 0.5558 | 3 |  | qwer178 | 751656 | 0 | 8788889.34 | 8788889.34 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
TBD Remaining Vegetation Funds |  |  |  |  | Vegetation |  |  |  | FALSE |  |  | FALSE | [12 empty] | 45056 | [8 empty] | -63127338.59 | [6 empty] | 0 | -63127338.59 | -63127338.59 | [11 empty] | 0 | 0 |  |  |  | 45856.7714 | 45407.675 | Marlina Crespo | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer179 | TBD Remaining Vegetation Funds |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Sub Rebuild - Santurce Planta |  |  |  |  | Substation |  |  |  | FALSE |  |  | FALSE | [21 empty] | 40362715 | [6 empty] | 0 | 40362715 | 40362715 | [11 empty] | 0 | 0 |  |  |  | 45856.7714 | 45408.4602 | Jeremy Malone | Santurce Planta (Sect) 1116 | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer180 | Sub Rebuild - Santurce Planta |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Sub - Rebuild Canas TC |  |  |  |  | Substation |  |  |  | FALSE |  |  | FALSE | [21 empty] | 71817966 | [6 empty] | 0 | 71817966 | 71817966 | [11 empty] | 0 | 0 |  |  |  | 45856.7714 | 45408.4603 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer181 | Sub - Rebuild Canas TC |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
T/D Asset Model Verification |  |  |  |  | Transmission |  |  |  | FALSE |  |  | FALSE | [21 empty] | 53716202 | [6 empty] | 0 | 53716202 | 53716202 | [11 empty] | 0 | 0 |  |  |  | 45856.7714 | 45408.4604 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer182 | T/D Asset Model Verification |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
36600 115kV San Sabastian - Dos Bocas (Batch 5) |  |  |  |  | Transmission |  |  |  | FALSE |  |  | FALSE | [21 empty] | 107109345 | [6 empty] | 0 | 107109345 | 107109345 | [11 empty] | 0 | 0 |  |  |  | 45856.7714 | 45408.4613 | Jeremy Malone |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer183 | 36600 115kV San Sabastian - Dos Bocas (Batch 5) |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Asset Management System Implementation |  |  |  |  | Substation |  |  |  | FALSE |  |  | FALSE |  |  |  | 45437 | 9737556 | 45471 | 45497 |  | 45501 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7714 | 45442.6915 | Jeremy Malone |  | Rey Roldan Rodríguez | [7 empty] | qwer184 | Asset Management System Implementation |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
TBD Venezuela Substation Transformer Replacement |  |  |  |  | Substation |  |  |  | FALSE |  |  | FALSE |  |  |  | 45322 | 3150000 | 45386 | 45404 |  | 45416 |  |  |  | 45443 | [8 empty] | 3156254 | [6 empty] | 0 | 3156254 | 3156254 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/844/DR4339PR-FEMA%20ISOW%20Venezuela%20Substation%20Transformer%20Replacement%20Rev.3%20-%20signed.pdf?web=1 |  | 45856.7714 | 45446.5662 | Marlina Crespo |  | Rey Roldan Rodríguez |  |  |  |  | 0 | 5 |  | qwer185 | TBD Venezuela Substation Transformer Replacement |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 171 |  | FAASt - Morovis (Substation) |  |  | Substation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7714 | 45455.6853 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer186 | FAASt number pending 171 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 172 |  | FAASt - Maunabo TC (Substation) |  |  | Substation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7714 | 45455.6857 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer187 | FAASt number pending 172 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 173 |  | FAASt - Mayagüez (Substation) |  |  | Substation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7714 | 45455.686 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer188 | FAASt number pending 173 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 176 |  | Substation Component Replacements |  |  | Substation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7714 | 45455.687 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer189 | FAASt number pending 176 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 178 |  | FAASt [T-Pole Program Line 37400 Dorado TC - Vega Baja TC] (Transmission) |  |  | Transmission |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7714 | 45455.6883 | Marlina Crespo | 115 kV Transmission Priority Poles and Structures Replacements | Rey Roldan Rodríguez | [7 empty] | qwer190 | FAASt number pending 178 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 179 |  | FAASt [T-Pole Program Line 37400 Barceloneta TC - Cambalache TC] (Transmission) |  |  | Transmission |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7714 | 45455.6888 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer191 | FAASt number pending 179 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 180 |  | FAASt [T-Pole Program Line 16500 Fajardo TC - Dos Marinas] (Transmission) |  |  | Transmission |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7714 | 45455.6898 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer192 | FAASt number pending 180 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 181 |  | FAASt [T-Pole Program Line 800 Comsat Sect - Cidra Sect] (Transmission) |  |  | Transmission |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7714 | 45455.6903 | Marlina Crespo |  | Rey Roldan Rodríguez | 0 Months | [6 empty] | qwer193 | FAASt number pending 181 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 184 |  | Group 15 - DAUT |  |  | Grid Automation |  |  |  | FALSE |  | Past | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 45856.7714 | 45456.5139 | Marlina Crespo |  | Rey Roldan Rodríguez | 0 Months | [6 empty] | qwer194 | FAASt number pending 184 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 185 |  | Group 19 - DAUT |  |  | Grid Automation |  |  |  | FALSE |  | Past | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 45856.7714 | 45456.5147 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer195 | FAASt number pending 185 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 186 |  | Group 20 - DAUT |  |  | Grid Automation |  |  |  | FALSE |  | Past | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 45856.7714 | 45456.5152 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer196 | FAASt number pending 186 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 187 |  | Group 21 - DAUT |  |  | Grid Automation |  |  |  | FALSE |  | Past | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 45856.7714 | 45456.5158 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer197 | FAASt number pending 187 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 188 |  | Group 22 - DAUT |  |  | Grid Automation |  |  |  | FALSE |  | Past | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 45856.7714 | 45456.5163 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer198 | FAASt number pending 188 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 189 |  | Group 24 - DAUT |  |  | Grid Automation |  |  |  | FALSE |  | Past | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 45856.7715 | 45456.517 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer199 | FAASt number pending 189 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 190 |  | Group 26 - DAUT |  |  | Grid Automation |  |  |  | FALSE |  | Past | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 45856.7715 | 45456.5174 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer200 | FAASt number pending 190 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 191 |  | Group 27 - DAUT |  |  | Grid Automation |  |  |  | FALSE |  | Past | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 45856.7715 | 45456.5186 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer201 | FAASt number pending 191 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 192 |  | Group 31 - DAUT |  |  | Grid Automation |  |  |  | FALSE |  | Past | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 45856.7715 | 45456.5191 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer202 | FAASt number pending 192 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 193 |  | Group 32 - DAUT |  |  | Grid Automation |  |  |  | FALSE |  | Past | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 45856.7715 | 45456.5197 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer203 | FAASt number pending 193 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 194 |  | Group 33 - DAUT |  |  | Grid Automation |  |  |  | FALSE |  | Past | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 45856.7715 | 45456.5205 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer204 | FAASt number pending 194 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 195 |  | Group 34 - DAUT |  |  | Grid Automation |  |  |  | FALSE |  | Past | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 45856.7715 | 45456.521 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer205 | FAASt number pending 195 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 196 |  | Group 35 - DAUT |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 45856.7715 | 45456.5214 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer206 | FAASt number pending 196 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 197 |  | FAASt [Feeders - San Juan Short Term Group 3] (Distribution) - 1620-02 |  |  | Distribution – Feeder Rebuild |  |  |  | FALSE |  | Past | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 45856.7715 | 45456.5225 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer207 | FAASt number pending 197 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 198 |  | FAASt [Feeders - Carolina Short Term Group 3] (Distribution) - 2402-02 |  |  | Distribution – Feeder Rebuild |  |  |  | FALSE |  | Past | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 45856.7715 | 45456.5229 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer208 | FAASt number pending 198 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 199 |  | FAASt [Feeders - San Juan Short Term Group 1] (Distribution) - 1303-01 |  |  | Distribution – Feeder Rebuild |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7715 | 45456.5234 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer209 | FAASt number pending 199 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 200 |  | FAASt [Feeders - San Juan Short Term Group 1] (Distribution) - 1204-05 |  |  | Distribution – Feeder Rebuild |  |  |  | FALSE |  | Past | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 45856.7715 | 45456.5252 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer210 | FAASt number pending 200 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 201 |  | FAASt [Feeders - San Juan Short Term Group 1] (Distribution) - 1204-04 |  |  | Distribution – Feeder Rebuild |  |  |  | FALSE |  | Past | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 45856.7715 | 45456.5256 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer211 | FAASt number pending 201 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 202 |  | FAASt [Feeders - Mayagüez Short Term Group 4] (Distribution )- 7805-11 |  |  | Distribution – Feeder Rebuild |  |  |  | FALSE |  | Past | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 45856.7715 | 45456.5261 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer212 | FAASt number pending 202 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 203 |  | FAASt [Feeders - Carolina Short Term Group 3] (Distribution) - 2402-02 |  |  | Distribution – Feeder Rebuild |  |  |  | FALSE |  | Past | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 45856.7715 | 45456.5265 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer213 | FAASt number pending 203 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 204 |  | FAASt [Feeders - Bayamón Short Term Group 1] (Distribution)-1806- 02 |  |  | Distribution – Feeder Rebuild |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7715 | 45456.5271 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer214 | FAASt number pending 204 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 205 |  | FAASt [Feeders - Mayagüez Short Term Group 3] (Distribution)-6601- 03 |  |  | Distribution – Feeder Rebuild |  |  |  | FALSE |  | Past | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 45856.7715 | 45456.5276 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer215 | FAASt number pending 205 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 206 |  | FAASt [Feeders - San Juan Short Term Group 1] (Distribution) - 1303-05 |  |  | Distribution – Feeder Rebuild |  |  |  | FALSE |  | Past | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 45856.7715 | 45456.5281 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer216 | FAASt number pending 206 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 207 |  | FAASt [Feeders - Mayagüez Short Term Group 2] (Distribution )- 6305-03 |  |  | Distribution – Feeder Rebuild |  |  |  | FALSE |  | Past | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 45856.7715 | 45456.5285 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer217 | FAASt number pending 207 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 208 |  | FAASt [Feeders - Bayamón Short Term Group 1] (Distribution)-1720- 07 |  |  | Distribution – Feeder Rebuild |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7715 | 45456.5295 | Marlina Crespo | Distribution Feeders ‐ Bayamon Short Term Group 1 | Rey Roldan Rodríguez | [7 empty] | qwer218 | FAASt number pending 208 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 209 |  | FAASt [Feeders - Bayamón Short Term Group 1] (Distribution)-1716- 03 |  |  | Distribution – Feeder Rebuild |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7715 | 45456.5299 | Marlina Crespo | Distribution Feeders ‐ Bayamon Short Term Group 1 | Rey Roldan Rodríguez | [7 empty] | qwer219 | FAASt number pending 209 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 210 |  | FAASt [Feeders - Bayamón Short Term Group 3] (Distribution)-9501- 02 |  |  | Distribution – Feeder Rebuild |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7715 | 45456.5302 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer220 | FAASt number pending 210 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 211 |  | Feeder 1115-02, 1115-03, 1115-04, 1117-07, 1117-08 - Santurce UG Rebuilt |  |  | Distribution – Underground |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7715 | 45456.5309 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer221 | FAASt number pending 211 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 212 |  | Feeder 1424-07, 1424-08 - Hato Rey UG Rebuilt |  |  | Distribution – Underground |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7715 | 45456.5313 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer222 | FAASt number pending 212 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 214 |  | FAASt [Pole and Conductor Repair - Caguas Group 3 - Phase 2] (Distribution) |  |  | Distribution – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7715 | 45456.5327 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer223 | FAASt number pending 214 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 215 |  | FAASt [Pole and Conductor Repair - Mayagüez Group 4 - Phase 2] (Distribution) |  |  | Distribution – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7715 | 45456.5331 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer224 | FAASt number pending 215 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
738671-4 | 11819 | 4 x 25 MW BESS Interconnections Monacillos TC |  | PBUT37 - Microgrid Inst & Integ | Grid Modernization |  | TRUE |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 46078.5745 | 45456.5458 | Marlina Crespo | 4x25 MW BESS Interconnections at LUMA 38 kV System | Ashleah Dingle | [7 empty] | qwer225 | 738671-4 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 216 |  | Vieques & Culebra Microgrid |  |  | Grid Modernization |  |  |  | FALSE |  | Past | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List | 45856.7715 | 45456.5481 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer226 | FAASt number pending 216 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
750068 | 107969 | FAASt [Region 5 -Mayaguez Group A] Low Density (Vegetation) | 15F019400000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation |  | TRUE |  | FALSE |  | Current | FALSE | [12 empty] | 45461 | 6/18/2024 |  | 45617 | 46010 | 45884 | 45877 | 8/12/2025 9:13 AM AST - The PR Electric Power Authority, as the eligible entity (subrecipient), has submitted a consolidated plan for the use of the remaining budget available in the FEMA Accelerated Awards Strategy Project (136271) Fixed Cost Award. This FAASt sub-project has been identified in the list and it will be processed in the national workflow accordingly. |  | 14252476.97 | 7000000 | 98723529.73 |  |  |  | 858465.45 | 97865064.28 | 98723529.73 | 98723529.73 |  |  | 46082 |  | 52301929.37 | 13840548.75 | [5 empty] | 52301929.37 | 13840548.75 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/909/PRJ_Report_750068_20260302.pdf?web=1 | 8/12/2025 9:13 AM AST - The PR Electric Power Authority, as the eligible entity (subrecipient), has submitted a consolidated plan for the use of the remaining budget available in the FEMA Accelerated Awards Strategy Project (136271) Fixed Cost Award. This FAASt sub-project has been identified in the list and it will be processed in the national workflow accordingly. | 46083.6766 | 45463.397 | Marlina Crespo | Island-Wide Vegetation Clearing | Marlina Crespo |  |  | 219334.17 | 599997.54 | 0.070905 | 5 |  | qwer227 | 750068 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 37861383.08
750067 | 107968 | FAASt [Region 2 -Arecibo Group A] Low Density (Vegetation) | 15F019550000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation |  | TRUE |  | FALSE |  | Current | FALSE | [12 empty] | 45461 | 06/18/2024 |  | 45617 | 46013 | 45888 | 45811 | Field EHP: ESA and CBRA Consultation letter submitted to USFWS on 06/05/2025. Waiting for response. ECD 08/19/2025 |  | 18122150.56 | 9000000 | 107170415.13 |  |  |  | 931916.64 | 106238498.49 | 107170415.13 | 107170415.13 |  |  | 46082 |  | 56797288.74 | 15030146.18 | [5 empty] | 56797288.74 | 15030146.18 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/910/PRJ_Report_750067_20260302.pdf?web=1 | 10/2/2024 FEMA comment via GP: 10/01/2024 01:08 PM AST, GARCIA DIAZ, CHRISTIAN D. Commented: "10/1/2024 - LUMA sent the documents on 9/20/2024. FEMA performed a pre-review and email with feedback was sent to LUMA on 10/1/2024 for their action to remove duplicity found between Distribution and Transmission. Deadline stablished is 10/3/2024 for LUMA submit documents corrected."10/2/2024 - DSOWs were submitted to FEMA but now are being revised to remove the Herbicide and Mechanical Mastication language | 46083.6776 | 45463.4021 | Marlina Crespo | Island-Wide Vegetation Clearing | Marlina Crespo |  |  | 238185.98 |  | 0.083978 | 5 |  | qwer228 | 750067 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 41767142.56
750066 | 107967 | FAASt [Region 4 -Caguas Group A] Low Density (Vegetation) | 15F019450000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation |  | TRUE |  | FALSE |  | Current | FALSE | [12 empty] | 45461 | 06/18/2024 |  | 45617 | 46013 | 45881 | 45838 | Field EHP - Environmental: ESA Consultation letter submitted to USFWS on 06/03/2025. Waiting for response. ECD 08/12/2025 |  | 33799537.58 | 16000000 | 3142832.19 |  |  |  | 2059216.24 | 1083615.95 | 3142832.19 | 3142832.19 |  |  | 46082 |  | 107563717.8 | 28466485.03 | [5 empty] | 107563717.8 | 28466485.03 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/911/PRJ_Report_750066_20260302.pdf?web=1 | 10/2/2024 FEMA comment via GP: 10/01/2024 01:04 PM AST, GARCIA DIAZ, CHRISTIAN D. Commented: "10/1/2024 - LUMA sent the documents on 9/20/2024. FEMA performed a pre-review and email with feedback was sent to LUMA on 10/1/2024 for their action to remove duplicity found between Distribution and Transmission. Deadline stablished is 10/3/2024 for LUMA submit documents corrected." 10/2/2024 - DSOWs were submitted to FEMA but now are being revised to remove the Herbicide and Mechanical Mastication language | 46083.6823 | 45463.4026 | Marlina Crespo | Island-Wide Vegetation Clearing | Marlina Crespo |  |  | 448177.27 |  | 5.0909 | 1 |  | qwer229 | 750066 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 79097232.77
750065 | 107966 | FAASt [Region 3 -Bayamon Group A] Low Density (Vegetation) | 15F019500000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation |  | TRUE |  | FALSE |  | Current | FALSE | [12 empty] | 45461 | 06/18/2024 |  | 45617 | 46013 | 45883 | 45876 | 8/7/2025 - EHP final review. ECD 8/14/2025. |  | 29267077.73 | 15000000 | 132424167.91 |  |  |  | 1151514.49 | 131272653.42 | 132424167.91 | 132424167.91 |  |  | 46082 |  | 70173723.91 | 18569923.87 | [5 empty] | 70173723.91 | 18569923.87 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/912/PRJ_Report_750065_20260302.pdf?web=1 | 10/2/2024 FEMA comment via GP: 10/01/2024 11:52 AM AST, GARCIA DIAZ, CHRISTIAN D. - Commented: "10/1/2024 - LUMA provided respond for email of duplicity. Still pending to confirm if LUMA used the rural ROW for their review." 10/2/2024 - DSOWs were submitted to FEMA but now are being revised to remove the Herbicide and Mechanical Mastication language 8/7/2025 - EHP final review. ECD 8/14/2025. | 46083.683 | 45463.4033 | Marlina Crespo | Island-Wide Vegetation Clearing | Marlina Crespo |  |  | 294281.61 |  | 0.11327 | 5 |  | qwer230 | 750065 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 51603800.04
750063 | 107965 | FAASt [Region 6 -Ponce Group A] Low Density (Vegetation) | 15F019350000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation |  | TRUE |  | FALSE |  | Current | FALSE | [12 empty] | 45461 | 06/18/2024 |  | 45617 | 45981 | 45882 | 45876 | 8/12/2025 9:12 AM AST - The PR Electric Power Authority, as the eligible entity (subrecipient), has submitted a consolidated plan for the use of the remaining budget available in the FEMA Accelerated Awards Strategy Project (136271) Fixed Cost Award. This FAASt sub-project has been identified in the list and it will be processed in the national workflow accordingly. |  | 20024132.24 | 11000000 | 113327804.46 |  |  |  | 985459.15 | 112342345.31 | 113327804.46 | 113327804.46 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/913/Region%206%20Ponce%20Group%20A%20Low%20Density%20-%20PW%20750063%20DSOW%2011_4_2024.pdf?web=1 | 8/12/2025 9:12 AM AST - The PR Electric Power Authority, as the eligible entity (subrecipient), has submitted a consolidated plan for the use of the remaining budget available in the FEMA Accelerated Awards Strategy Project (136271) Fixed Cost Award. This FAASt sub-project has been identified in the list and it will be processed in the national workflow accordingly. | 46059.5499 | 45463.4039 | Marlina Crespo | Island-Wide Vegetation Clearing | Jason Fournier |  |  |  |  | 0.097064 | 5 |  | qwer231 | 750063 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
750150 | 107970 | FAASt [Transmission Priority Pole Replacement Program Line 4800 Santa Isabel TC – Toro Negro 1 HP] (Transmission) | 14F020790000 | PBUT13 - T Priority Pole Repl | Transmission – Pole Replacement |  | TRUE | Restoration | FALSE |  | Current | FALSE | [12 empty] | 45463 | 06/20/2024 |  | 45463 | 45898 | 45929 | 45915 | 9/15/2025- Field EHP: Initial review in progress. Expected Completion Date (ECD): 9/29/2025. | 1 | 64660.36 | 58488 | 8224.8 | 19852.4 |  | 131895.22 | 1075.68 | 7149.12 | 140120.02 | 159972.42 |  |  | 45966 |  | 134148.36 | 125923.56 |  |  |  | 5971.66 |  | 134148.36 | 125923.56 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/914/136271-DR4339PR-Detailed%20SOW-T-Pole%20TL4800%20Santa%20Isabel%20TC%20%20Toro%20Negro%201%20HP%20Rev0%20-%20signed.pdf?web=1 |  | 46059.5499 | 45463.5124 | Marlina Crespo | 38 kV Transmission Priority Poles and Structures Replacements | Jason Fournier |  |  | 19852.4 | 1075.68 | 0.41741 | 3 |  | qwer232 | 750150 | 5971.66 |  | 5971.66 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 7149.12
750151 | 107971 | FAASt [Transmission Priority Pole Replacement Program Line 700 Costa Sur SP – Yauco 2 HP] (Transmission) | 14F020640000 | PBUT13 - T Priority Pole Repl | Transmission – Pole Replacement |  | TRUE | Restoration | FALSE |  | Current | FALSE | [12 empty] | 45463 | 06/20/2024 |  | 45463 | 45960 | 45994 | 45987 | 11/26/2025 - Field EHP - Environmental: In Review. Expected Completion Date (ECD) 12/03/2025 | 1 | 136702.29 | 123160.67 | 12563.87 | 23495.18 |  | 260054.1 | 1041.06 | 11522.81 | 272617.97 | 296113.15 |  |  | 46038 |  | 255832.03 | 243268.16 |  |  |  | 19127 |  | 255832.03 | 243268.16 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/915/PRJ_MultiVersionReport_750151_20260116.pdf |  | 46059.55 | 45463.513 | Marlina Crespo | 38 kV Transmission Priority Poles and Structures Replacements | Jason Fournier |  |  | 23495.18 | 1041.06 | 0.45177 | 3 |  | qwer233 | 750151 | 16785.94 | 2341.06 | 19127 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 9181.75
750168 | 107972 | FAASt [ Transmission Priority Pole Replacement Program Line 4800 Santa Isabel TC – Aibonito TO] (Transmission) | 14F020800000 | PBUT13 - T Priority Pole Repl | Transmission – Pole Replacement |  | TRUE | Restoration | FALSE |  | Current | FALSE | [12 empty] | 45463 | 06/20/2024 |  | 45463 | 45933 | 45961 | 45947 | 10/17/2025 - Field EHP - Environmental: In Review. Expected Completion Date (ECD) 10/31/2025. |  |  | 375810.42 | 37472.84 | 45787.13 |  | 468439.49 | 3335.39 | 34137.45 | 505912.33 | 551699.46 |  |  | 45986 |  | 469229.99 | 431757.15 |  |  |  | 36682.34 |  | 469229.99 | 431757.15 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/916/136271-DR4339PR-Detailed%20SOW-T-Pole%20TL4800%20Santa%20Isabel%20TC%20-%20Aibonito%20TO%20Rev0%20-%20signed.pdf?web=1 |  | 46059.5538 | 45464.3929 | Marlina Crespo | 38 kV Transmission Priority Poles and Structures Replacements | Jason Fournier |  |  | 45787.13 | 3335.39 | 0.74284 | 2 |  | qwer234 | 750168 | 36682.34 | 5852.66 | 42535 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 28284.79
750502 | 107977 | FAASt [25 MW BESS Installation and Integration - Aguadilla] (Substation) | 14F019620000 | PBUT37 - Microgrid Inst & Integ | Grid Modernization |  | TRUE |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 45470 | 06/27/2024 |  | 45814 |  | 45716 | 45713 |  |  | 3370000 | 3370000 | 52720520.35 | 0 |  | 0 | 3340630.47 | 49379889.88 | 52720520.35 | 52720520.35 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/918/750502%20-%20DR4339PR-%20FEMA%20DSOW%20for%2025%20MW%20BESS%20Installation%20and%20Integration%20-%20Aguadilla%20(Substation)%20signed.pdf?web=1 | Still pending SOW documentation | 46059.6463 | 45471.4614 | Marlina Crespo | 4x25 MW BESS Interconnections at LUMA 38 kV System | Jason Fournier |  |  |  |  | 0.063922 | 5 | 45876 | qwer235 | 750502 | 0 | 28261718.24 | 28261718.24 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
750503 | 107978 | FAASt [25 MW BESS Installation and Integration - San Juan] (Substation) | 14F019610000 | PBUT37 - Microgrid Inst & Integ | Grid Modernization |  | TRUE |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 45470 | 06/27/2024 |  | 45814 |  | 45636 | 45622 |  |  |  | 0 | 55503065.56 | 0 |  | 0 | 3187811.29 | 52315254.27 | 55503065.56 | 55503065.56 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/919/750503%20-%20DR4339PR%20-%20FEMA%20DSOW%20for%2025%20MW%20BESS%20Installation%20and%20Integration%20-%20San%20Juan%20(6.6.2025)%20signed.pdf?web=1 | Still pending SOW documentation | 46059.6467 | 45471.4621 | Marlina Crespo | 4x25 MW BESS Interconnections at LUMA 38 kV System | Jason Fournier |  |  |  |  | 0 | 5 | 45876 | qwer236 | 750503 | 0 | 28261718.24 | 28261718.24 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
750692 | 107979 | FAASt [Pole and Conductor Repair - Mayaguez Group 3 - Phase 2] (Distribution) | 14F018970000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement |  |  |  | FALSE |  | Current | FALSE | [12 empty] | 45475 | 07/02/2024 |  | 45688 | 46073 | 45877 | 45835 | Field EHP: (ESA/CBRS) Consultation letter submitted to USFWS on 05/29/2025. Waiting for response. ECD 08/08/2025. |  | 8160000 | 8160000 | 539706.65 | 1378411.71 | 1059507.72 | 16594079.1 | 37871.84 | 501834.81 | 17133785.75 | 18512197.46 |  |  | 45925 |  | 12921047 | 12921047 |  |  |  | 2509617 |  | 12921047 | 12921047 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/922/ISOW%20-%20Pole%20and%20Conductor%20-%20%20Mayaguez%20Group%203%20-%20Phase%202.pdf |  | 46078.6781 | 45475.4742 | Marlina Crespo | Distribution Pole & Conductor Replacement | Marlina Crespo | 0 Months |  | 1799743 | 0 | 0.47625 | 3 |  | qwer237 | 750692 | 1096303.06 | 395734.94 | 1492038 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
750729 | 107980 | FAASt [Transmission Line 3700 GOAB 3797 to Arroyo Substation 4101] (Transmission) | 14F015440000 | PBUT33 - T Line Rebuild | Transmission |  |  |  | FALSE |  |  | FALSE |  |  |  |  | 2080000 | 45400 | 45419 |  | 45430 |  |  |  | 45475 | 07/02/2024 | [7 empty] | 2083232.55 | 2083232.55 | [5 empty] | 0 | 2083232.55 | 2083232.55 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/923/750729-DR4339PR-Transmission%20Line%203700%20GOAB%203797%20to%20Arroyo%20Substation%204101.pdf?web=1 | 02JULY2025 Project is being administratively use as a placeholder since it was not included in the Applicant’s latest workplan for submittal of a SOW. FEMA may in the future re-create the project for the 33 DI's included in this project at the request of the Applicant and COR3 if a SOW submittal date is provided. | 46097.447 | 45476.4411 | Marlina Crespo | Transmission Line 3700 GOAB 3797 to Arroyo Substation 4101 | Ashleah Dingle |  |  |  |  | 1 | 1 |  | qwer238 | 750729 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
750730 | 107981 | FAASt [Line 500 Ponce TC to Costa Sur SP] (Transmission) | 14F002400000 | PBUT33 - T Line Rebuild | Transmission |  |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 36590000 | 44385 | 44428 |  | 44415 |  |  |  | 45475 | 07/02/2024 | [7 empty] | 36590000 | 36590000 | [5 empty] | 0 | 36590000 | 36590000 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/924/750730-DR4339PR-Line%20500%20Ponce%20TC%20to%20Costa%20Sur%20SP.pdf?web=1 |  | 45887.6462 | 45476.4436 | Marlina Crespo | Line 500 Ponce TC to Costa Sur SP | Ashleah Dingle |  |  |  |  | 1 | 1 | 45887 | qwer239 | 750730 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
751655 | 107982 | FAASt [Vieques Microgrid] (Transmission) | 14F021650000 | PBUT37 - Microgrid Inst & Integ | Grid Modernization |  |  | Restoration | FALSE |  | Current | FALSE |  |  |  |  | 122250000 | 45324 | 45337 |  | 45354 |  |  |  | 45013 | 07/18/2024 |  | 45492 | 45883 |  |  |  |  | 125117462.87 | 81410371 | 124703389.13 | 63813.14 |  | 605646.11 | 11753427.33 | 112949961.8 | 125309035.24 | 125372848.38 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/927/4339-0280_Phase%201%20Approval_VC%20Microgrids_20230328%20(002)%20(1).pdf?web=1 |  | 45980.6692 | 45492.4253 | Marlina Crespo | Vieques and Culebra Microgrid | Marlina Crespo |  |  |  |  | 0.64968 | 2 |  | qwer240 | 751655 | 0 | 14497546.99 | 14497546.99 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
752039 | 107984 | FAASt [Transmission Line 10000 Sierra Linda TO to Magnolia TO] (Transmission) | 14F015550000 | PBUT33 - T Line Rebuild | Transmission |  |  |  | FALSE |  |  | TRUE | Voluntarily Withdrawal Status in Grants Portal | Discontinued |  | 45303 | 7030000 | 45400 | 45419 |  | 45430 |  |  |  | 45496 | 07/23/2024 | [7 empty] | 7032180.12 | 7032180.12 | [5 empty] | 0 | 7032180.12 | 7032180.12 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/929/752039-DR4339PR-Transmission%20Line%2010000%20Sierra%20Linda%20TO%20to%20Magnolia%20TO.pdf | 6/12/2025 - Project withdrawn in Grants Portal | 45856.7715 | 45497.4432 | Marlina Crespo | Transmission Line 10000 Sierra Linda TO to Magnolia TO | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 | 45820 | qwer241 | 752039 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
752041 | 107985 | FAASt [Transmission Line 1000 Venezuela Sect to Capuchinos Sect] (Transmission) | 14F015560000 | PBUT33 - T Line Rebuild | Transmission |  |  |  | FALSE |  |  | TRUE | Voluntarily Withdrawal Status in Grants Portal | Discontinued |  | 45303 | 4060000 | 45400 | 45419 |  | 45430 |  |  |  | 45496 | 07/23/2024 | [7 empty] | 4060000 | 4060000 | [5 empty] | 0 | 4060000 | 4060000 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/930/752041-DR4339PR-Transmission%20Line%201000%20Venezuela%20Sect%20to%20Capuchinos%20Sect.pdf | 6/12/2025 - Project withdrawn in Grants Portal | 45856.7715 | 45497.4534 | Marlina Crespo | Transmission Line 1000 Venezuela Sect to Capuchinos Sect | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 | 45820 | qwer242 | 752041 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
752047 | 107986 | FAASt [Transmission Line 3300 Chardon Sect to Egozcue Sect] (Transmission) | 14F015460000 | PBUT33 - T Line Rebuild | Transmission |  |  |  | FALSE |  |  | TRUE | Voluntarily Withdrawal Status in Grants Portal | Discontinued |  | 45303 | 6540000 | 45400 | 45419 |  | 45430 |  |  |  | 45496 | 07/23/2024 | [7 empty] | 6540000 | 6540000 | [5 empty] | 0 | 6540000 | 6540000 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/931/752047-DR4339PR-Transmission%20Line%203300%20Chardon%20Sect%20to%20Egozcue%20Sect.pdf?web=1 | 6/12/2025 - Project withdrawn in Grants Portal | 45856.7715 | 45497.455 | Marlina Crespo | Transmission Line 3300 Chardon Sect to Egozcue Sect | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 | 45820 | qwer243 | 752047 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
752048 | 107987 | FAASt [Transmission Line 3500 Las Lomas Sect to Monacillos TC] (Transmission) | 14F015450000 | PBUT33 - T Line Rebuild | Transmission |  |  |  | FALSE |  |  | TRUE | Voluntarily Withdrawal Status in Grants Portal | Discontinued |  | 45303 | 8120000 | 45400 | 45419 |  | 45430 |  |  |  | 45496 | 07/23/2024 | [7 empty] | 8120000 | 8120000 | [5 empty] | 0 | 8120000 | 8120000 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/932/752048-DR4339PR-Transmission%20Line%203500%20Las%20Lomas%20Sect%20to%20Monacillos%20TC.pdf?web=1 | 6/12/2025 - Project withdrawn in Grants Portal | 45856.7715 | 45497.4566 | Marlina Crespo | Transmission Line 3500 Las Lomas Sect to Monacillos TC | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 | 45820 | qwer244 | 752048 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
752049 | 107988 | FAASt [Transmission Line 5600 Hotel Rincon to Rincon Substation7301] (Transmission) | 14F015430000 | PBUT33 - T Line Rebuild | Transmission |  |  |  | FALSE |  |  | TRUE | Voluntarily Withdrawal Status in Grants Portal | Discontinued |  | 45303 | 5200000 | 45400 | 45419 |  | 45430 |  |  |  | 45496 | 07/23/2024 | [7 empty] | 5200000 | 5200000 | [5 empty] | 0 | 5200000 | 5200000 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/933/752049-DR4339PR-Transmission%20Line%205600%20Hotel%20Rincon%20to%20Rincon%20Substation7301.pdf?web=1 | 6/12/2025 - Project withdrawn in Grants Portal | 45856.7715 | 45497.4582 | Marlina Crespo | Transmission Line 5600 Hotel Rincon to Rincon Substation7301 | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 | 45820 | qwer245 | 752049 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
752050 | 107989 | FAASt [Transmission Line 9300 Gautier Benitez Sect to ACB 9323] (Transmission) | 14F015410000 | PBUT33 - T Line Rebuild | Transmission |  |  |  | FALSE |  |  | TRUE | Voluntarily Withdrawal Status in Grants Portal | Discontinued |  | 45303 | 20320000 | 45400 | 45419 |  | 45430 |  |  |  | 45496 | 07/23/2024 | [7 empty] | 20320000 | 20320000 | [5 empty] | 0 | 20320000 | 20320000 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/934/752050-DR4339PR-Transmission%20Line%209300%20Gautier%20Benitez%20Sect%20to%20ACB%209323.pdf?web=1 | 6/12/2025 - Project withdrawn in Grants Portal | 45856.7715 | 45497.4599 | Marlina Crespo | Transmission Line 9300 Gautier Benitez Sect to ACB 9323 | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 | 45820 | qwer246 | 752050 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
752051 | 107990 | FAASt [Transmission Line 9300 Juncos TC to ACB 9301] (Transmission) | 14F015400000 | PBUT33 - T Line Rebuild | Transmission |  |  |  | FALSE |  |  | TRUE | Voluntarily Withdrawal Status in Grants Portal | Discontinued |  | 45303 | 16250000 | 45400 | 45419 |  | 45430 |  |  |  | 45496 | 07/23/2024 | [7 empty] | 16250000 | 16250000 | [5 empty] | 0 | 16250000 | 16250000 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/935/752051-DR4339PR-Transmission%20Line%209300%20Juncos%20TC%20to%20ACB%209301.pdf?web=1 | 6/12/2025 - Project withdrawn in Grants Portal | 45856.7715 | 45497.4613 | Marlina Crespo | Transmission Line 9300 Juncos TC to ACB 9301 | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 | 45820 | qwer247 | 752051 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
752052 | 107991 | FAASt [Transmission Line 9900 TAP9905A to Rio Blanco HP] (Transmission) | 14F015390000 | PBUT33 - T Line Rebuild | Transmission |  |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  | 45303 | 32110000 | 45400 | 45419 |  | 45430 |  |  |  | 45496 | 07/23/2024 |  |  |  | 45727 | 45719 |  |  | 32110000 | 32110000 | [5 empty] | 0 | 32110000 | 32110000 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/936/752052-DR4339PRE-Transmission%20Line%209900%20TAP9905A%20to%20Rio%20Blanco%20HP.pdf?web=1 |  | 45887.6462 | 45497.4646 | Marlina Crespo | Transmission Line 9900 TAP9905A to Rio Blanco HP | Ashleah Dingle |  |  |  |  | 1 | 1 | 45887 | qwer248 | 752052 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
752053 | 107992 | FAASt [Transmission Line 13400 Boqueron TO to Acacias TC] (Transmission) | 14F015540000 | PBUT33 - T Line Rebuild | Transmission |  |  |  | FALSE |  |  | TRUE | Voluntarily Withdrawal Status in Grants Portal | Discontinued |  | 45303 | 33330000 | 45400 | 45419 |  | 45430 |  |  |  | 45496 | 07/23/2024 | [7 empty] | 33330000 | 33330000 | [5 empty] | 0 | 33330000 | 33330000 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/937/752053-DR4339PR-Transmission%20Line%2013400%20Boqueron%20TO%20to%20Acacias%20TC.pdf?web=1 | 6/12/2025 - Project withdrawn in Grants Portal | 45856.7715 | 45497.4659 | Marlina Crespo | Transmission Line 13400 Boqueron TO to Acacias TC | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 | 45820 | qwer249 | 752053 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Victoria TC |  |  |  |  | Substation |  |  |  | FALSE |  |  | FALSE |  |  |  | 45497 |  | 45504 | 45527 |  | 45534 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7715 | 45499.4069 | Jeremy Malone |  | Rey Roldan Rodríguez | [7 empty] | qwer250 | Victoria TC |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Arecibo Sectionalizer |  |  |  |  | Substation |  |  |  | FALSE |  |  | FALSE |  |  |  | 45493 |  | 45504 | 45527 |  | 45534 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7715 | 45499.4302 | Jeremy Malone |  | Rey Roldan Rodríguez | [7 empty] | qwer251 | Arecibo Sectionalizer |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
752277 | 107995 | FAASt [Substation Ciales 8701] (Substation) | 14F016640000 | PBUT08 - Substation Rebuilds | Substation |  |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | 45436 | 5820000 | 45471 | 45497 |  | 45501 |  |  |  | 45499 | 07/29/2024 |  | 45622 | [5 empty] | 5825951 | 5825951 | 4177144.45 | 35108.3 |  | 324066.94 | 554759.8 | 3622384.65 | 4501211.39 | 4536319.69 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/944/DR4339PR%20-%20FEMA%20ISOW%20Ciales%208701%20Rev%207%20-%20signed.pdf?web=1 |  | 46078.5771 | 45502.5379 | Marlina Crespo | Substation Ciales 8701 | Ashleah Dingle |  |  |  |  | 1.2943 | 1 | 45888 | qwer252 | 752277 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
752276 | 107994 | FAASt [Monterrey 9502 & 9503 (Fuse to Breaker)] (Substation) | 14F016660000 | PBUT08 - Substation Rebuilds | Substation |  |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  | 45436 | 39600000 | 45471 | 45497 |  | 45501 |  |  |  | 45499 | 07/29/2024 | [7 empty] | 39664220 | 39664220 | [5 empty] | 0 | 39664220 | 39664220 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/945/DR4339PR-FEMA%20ISOW%20Monterrey%209502-9503%20Rev%205%20-%20signed.pdf?web=1 |  | 46078.5771 | 45502.5386 | Marlina Crespo | Substation Monterey 9502 & 9503 | Ashleah Dingle |  |  |  |  | 1 | 1 | 45888 | qwer253 | 752276 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
752275 | 107993 | FAASt [Unibon 9501 (Fuse to Breaker)] (Substation) | 14F016650000 | PBUT08 - Substation Rebuilds | Substation |  |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  | 45436 | 9100000 | 45471 | 45497 |  | 45501 |  |  |  | 45499 | 07/29/2024 | [7 empty] | 9157533 | 9157533 | [5 empty] | 0 | 9157533 | 9157533 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/946/DR4339PR-FEMA%20ISOW%20Unib%C3%B3n%209501%20Rev%207%20-%20signed.pdf?web=1 |  | 46078.6089 | 45502.5391 | Marlina Crespo | Substation Unibón 9501 | Ashleah Dingle |  |  |  |  | 1 | 1 | 45888 | qwer254 | 752275 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
752500 | 107996 | FAASt [Automation Program Group 1B-6 Feeders] (Distribution) | 14F001290000 | PBUT04 - Distribution Automation | Grid Automation |  |  |  | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45505 | 08/01/2024 | [7 empty] | 1250000 | 1250000 | [5 empty] | 0 | 1250000 | 1250000 | [11 empty] | 0 | 0 |  |  | 01AUGUST2024 - Project was created but no ISOW has been submitted. ISOW funding is bulling from GP BAC - mc | 46078.5782 | 45505.5078 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Ashleah Dingle |  |  |  |  | 1 | 1 | 45887 | qwer255 | 752500 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
752502 | 107997 | FAASt [Automation Program Group 1C-7 Feeders] (Distribution) | 14F003520000, 14F003550000 | PBUT04 - Distribution Automation | Grid Automation |  |  |  | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45505 | 08/01/2024 | [7 empty] | 1250000 | 1250000 | [5 empty] | 0 | 1250000 | 1250000 | [11 empty] | 0 | 0 |  |  | 01AUGUST2024 - Project was created but no ISOW has been submitted. ISOW funding is bulling from GP BAC - mc | 46078.5784 | 45505.5087 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Ashleah Dingle |  |  |  |  | 1 | 1 | 45887 | qwer256 | 752502 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
752503 | 107998 | FAASt [Automation Program Group 1D-7 Feeders] (Distribution) | 14F003340000, 14F003300000 | PBUT04 - Distribution Automation | Grid Automation |  |  |  | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45505 | 08/01/2024 | [7 empty] | 1250000 | 1250000 | [5 empty] | 0 | 1250000 | 1250000 | [11 empty] | 0 | 0 |  |  | 01AUGUST2024 - Project was created but no ISOW has been submitted. ISOW funding is bulling from GP BAC - mc | 46078.5785 | 45505.5095 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Ashleah Dingle |  |  |  |  | 1 | 1 | 45887 | qwer257 | 752503 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
752540 | 107999 | FAASt [Pole and Conductor Repair -Mayaguez Group 4 Phase 2] (Distribution) | 14F018980000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement |  |  |  | FALSE |  | Current | FALSE | [12 empty] | 45505 | 08/01/2024 |  | 45688 | 46073 | 45868 | 45863 | Field EHP - Environmental: In Review. Expected Completion Date (ECD) 07/30/2025. |  | 1250000 | 9107127 | 305539.44 | 773151.6 | 622940.21 | 9310270.2 | 23427.4 | 282112.04 | 9615809.64 | 10388961.24 |  |  | 45925 |  | 7111613.91 | 7111613.91 |  |  |  | 1376029 |  | 7111613.91 | 7111613.91 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/950/752540-DR4339PR-Detailed%20SOW%20Mayaguez%20Group%204%20-%20Phase%202%20Rev0%20.pdf?web=1 | 01AUGUST2024 - Project was created but no ISOW has been submitted. ISOW funding is bulling from GP BAC - mc | 46078.6766 | 45505.5106 | Marlina Crespo | Distribution Pole & Conductor Replacement | Marlina Crespo |  |  | 991211.9 | 0 | 0.9471 | 1 |  | qwer258 | 752540 | 628196.69 | 241421.21 | 869617.9 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
752808 | 108000 | FAASt [Automation Program Group 19] (Distribution) | 10F000670000, 10F000660000, 10F000680000 | PBUT04 - Distribution Automation | Grid Automation |  |  | Restoration | FALSE |  | Past | FALSE | [12 empty] | 45511 | 08/07/2024 |  | 45539 | 46059 | 46093 | 46073 | 2/20/2026 - Field EHP - Environmental. Initial Review. Expected Completion Date (ECD) 03/12/2026. |  | 1250000 | 1482000 | 723597.72 | 119711.919 | 134857.23 | 1487804.471 | 52375.131 | 671222.589 | 2211402.191 | 2331114.11 |  |  | 45694 |  | 2753627.24 | 2753627.24 | [5 empty] | 2753627.24 | 2753627.24 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/952/1310158-DR4339PR-FEMA%20Project%20Scope%20of%20Work%20Distribution%20Pole%20and%20Conductor%20Repair%20-%20Bayamon%20Group%2015%20(2).pdf?web=1 |  | 46078.5796 | 45512.3864 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Ashleah Dingle |  |  | 348510.65 |  | 0.67016 | 2 |  | qwer259 | 752808 | 143163.5 | 312122.7 | 455286.2 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
752810 | 108001 | FAASt [Automation Program Group 20] (Distribution) | 10F001070000, 10F001080000, 10F001120000, 10F001090000 | PBUT04 - Distribution Automation | Grid Automation |  |  | Restoration | FALSE |  | Past | FALSE | [12 empty] | 45511 | 08/07/2024 |  | 45539 | 46078 | 45638 | 45631 |  |  |  | 1740000 | 869464.69 | 176266.8 | 202809.71 | 1848791.93 | 72284.36 | 797180.33 | 2718256.62 | 2894523.42 |  |  | 45694 |  | 2623262.08 | 2623262.08 | [5 empty] | 2623262.08 | 2623262.08 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/953/752810-%20DR4339PR-%20DSOW%20Group%2020-%20DAUT.pdf?web=1 | Pending ISOW documentation 8/8/24 - MC | 46078.6736 | 45512.3887 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Marlina Crespo | 0 Months |  | 333695.7 |  | 0.64012 | 2 |  | qwer260 | 752810 | 209802.68 | 349543.04 | 559345.72 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
752972 | 108002 | FAASt [4 x 25 MW BESS Interconnections Manati] (Substation) | 14F019630000 | PBUT37 - Microgrid Inst & Integ | Grid Modernization |  | TRUE |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE |  | 216580000 | [7 empty] | 45513 | 08/09/2024 |  | 45772 |  | 45740 | 45726 |  |  | 54200000 | 54200000 | 57640005.67 | 0 |  | 0 | 3414922.97 | 54225082.7 | 57640005.67 | 57640005.67 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/954/752972%20-%20FEMA%20DSOW%2025%20MW%20BESS%20Installation%20%26%20Integration%20-%20Manat%C3%AD%20sigend.pdf?web=1 | no ISOW was provided at the moment | 46078.5804 | 45516.4589 | Marlina Crespo | 4x25 MW BESS Interconnections at LUMA 38 kV System | Ashleah Dingle |  |  |  |  | 0.94032 | 1 | 45876 | qwer261 | 752972 | 0 | 30416253.08 | 30416253.08 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 217 |  | FAASt [Feeders - Mayaguez Short Term Group 4] (Distribution ) - 7805-13 |  |  | Distribution |  |  |  | FALSE |  | Past | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  | 8/13/2024 Added from Grid Strategy's Priority Project List 7/30/2024 | 45856.7716 | 45517.3753 | Ashleah Dingle |  | Rey Roldan Rodríguez | [7 empty] | qwer262 | FAASt Number Pending 217 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 218 |  | FAASt [Feeders - San Juan Short Term Group 3] (Distribution) - 1336-08 |  |  | Distribution |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  | 8/13/2024 Added from Grid Strategy's Priority Project List 7/30/2024 | 45856.7716 | 45517.3771 | Ashleah Dingle |  | Rey Roldan Rodríguez | [7 empty] | qwer263 | FAASt Number Pending 218 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 219 |  | Line 100/200 - phase 1 |  |  | Transmission |  |  |  | FALSE |  | Past | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  | 8/13/2024 Added from Grid Strategy's Priority Project List 7/30/2024 | 45856.7716 | 45517.3783 | Ashleah Dingle |  | Rey Roldan Rodríguez | [7 empty] | qwer264 | FAASt Number Pending 219 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 220 |  | Santa Isabel Transformer - Stabilization Project |  |  | Substation |  |  |  | FALSE |  | Past | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  | 8/13/2024 Added from Grid Strategy's Priority Project List 7/30/2024 | 45856.7716 | 45517.3797 | Ashleah Dingle |  | Rey Roldan Rodríguez | [7 empty] | qwer265 | FAASt Number Pending 220 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 221 |  | FAASt [Feeders - Bayamon Short Term Group 2] (Distribution) - 1801-03 |  |  | Distribution |  |  |  | FALSE |  | Past | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  | 8/13/2024 Added from Grid Strategy's Priority Project List 7/30/2024 | 45856.7716 | 45517.3849 | Ashleah Dingle |  | Rey Roldan Rodríguez | [7 empty] | qwer266 | FAASt Number Pending 221 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 223 |  | FAASt [Feeders - Mayaguez Short Term Group 2] (Distribution ) - 6802-04 |  |  | Distribution |  |  |  | FALSE |  | Past | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  | 8/13/2024 Added from Grid Strategy's Priority Project List 7/30/2024 | 45856.7716 | 45517.3955 | Ashleah Dingle |  | Rey Roldan Rodríguez | [7 empty] | qwer267 | FAASt Number Pending 223 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
753302 | 108004 | FAASt [Telecom Infrastructure Group G] (Telecommunication) | 14F020240000, 14F020250000 | PBIT01 - Telecom Sys & Network | Telecommunications |  |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45519 | 08/15/2024 | [7 empty] | 8381000 | 8381000 | [5 empty] | 0 | 8381000 | 8381000 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/963/753302-DR4339PR-ISOW%20Telecom%20Infrastructure%20Group%20G%20signed%208-7-2024.pdf?web=1 |  | 46078.5817 | 45520.6996 | Marlina Crespo | Telecom Infrastructure | Ashleah Dingle |  |  |  |  | 1 | 1 | 45873 | qwer268 | 753302 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
753301 | 108003 | FAASt [Telecom Infrastructure Group H] (Telecommunication) | 14F020210000, 14F020220000, 14F020230000 |  | Telecommunications |  |  |  | FALSE |  |  | TRUE | Voluntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45519 | 08/15/2024 | [7 empty] | 7256000 | 7256000 | [5 empty] | 0 | 7256000 | 7256000 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/964/-DR4339PR-ISOW%20Telecom%20Infrastructure%20Group%20H%20Signed%208-7-2024.pdf?web=1 | 6/12/2025 - Project withdrawn in Grants Portal | 45856.7716 | 45520.702 | Marlina Crespo | Telecom Infrastructure | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 | 45820 | qwer269 | 753301 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Venezuela Sectionalizer |  |  |  |  | Substation |  |  |  | FALSE |  |  | FALSE |  |  |  | 45516 |  | 45526 | 45532 |  | 45556 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7716 | 45526.6402 | Jeremy Malone |  | Rey Roldan Rodríguez | [7 empty] | qwer270 | Venezuela Sectionalizer |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Caparra Sectionalizer |  |  |  |  | Substation |  |  |  | FALSE |  |  | FALSE |  |  |  | 45516 |  | 45526 | 45532 |  | 45556 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7716 | 45526.6705 | Jeremy Malone |  | Rey Roldan Rodríguez | [7 empty] | qwer271 | Caparra Sectionalizer |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
753788 | 108014 | FAASt [Transmission Priority Pole Replacement Program Line 1900 Dos Bocas HP – San Sebastian TC] (Transmission) | 14F020660000 |  | Transmission |  |  | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45527 | 08/23/2024 |  | 45527 | [5 empty] | 840422.28 | 840422.28 | 0 | 217503.32 |  | 840422.28 | 0 | 0 | 840422.28 | 1057925.6 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/968/753788-DR4339PR-Detailed%20SOW-TPole%20TL1900%20Dos%20Bocas%20HP%20-%20San%20Sebastian%20TC.pdf?web=1 |  | 45888.4778 | 45527.4331 | Jason Fournier | 38 kV Transmission Priority Poles and Structures Replacements | Maria Mujica Gonzalez |  |  |  |  | 1 | 1 | 45887 | qwer272 | 753788 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
753787 | 108013 | FAASt [Transmission Priority Pole Replacement Program Line 13700 Mora TC-Isabela TO] (Transmission) | 14F020630000 | PBUT13 - T Priority Pole Repl | Transmission |  | TRUE | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45527 | 08/23/2024 |  | 45527 | [5 empty] | 553203.43 | 553203.43 | 0 | 70371.06 |  | 553203.43 | 0 | 0 | 553203.43 | 623574.49 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/969/753787-DR4339PR-Detailed%20SOW-T-Pole%20TL13700%20Mora%20TC-Isabela%20TO%20(1).pdf?web=1 |  | 46078.5837 | 45527.4433 | Jason Fournier | 38 kV Transmission Priority Poles and Structures Replacements | Ashleah Dingle |  |  |  |  | 1 | 1 | 45887 | qwer273 | 753787 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
753786 | 108012 | FAASt [Transmission Priority Pole Replacement Program Line 5900 San Juan SP - Crematorio TO] (Transmission) | 14F020610000 | PBUT13 - T Priority Pole Repl | Transmission |  | TRUE | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45527 | 08/23/2024 |  | 45527 | 45884 |  |  |  |  | 599861.6 | 599861.6 | 24170.88 | 70136.4 |  | 436928.46 | 5360.23 | 18810.65 | 461099.34 | 531235.74 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/970/753786-DR4339PR-Detailed%20SOW-TPole%205900%20San%20Juan%20SP%20-%20CrematorioTO.pdf?web=1 |  | 46078.5837 | 45527.4482 | Jason Fournier | 38 kV Transmission Priority Poles and Structures Replacements | Ashleah Dingle |  |  |  |  | 1.3009 | 1 | 45887 | qwer274 | 753786 | 36524.75 | 11050.25 | 47575 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
753785 | 108011 | FAASt [Transmission Priority Pole Replacement Program Line 3300 San Gerardo Sect – Venezuela Sect] (Transmission) | 14F020600000 | PBUT13 - T Priority Pole Repl | Transmission |  | TRUE | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45527 | 08/23/2024 |  | 45527 | [5 empty] | 298678.49 | 298678.49 | 0 | 38000.29 |  | 298678.49 | 0 | 0 | 298678.49 | 336678.78 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/971/753785-DR4339PR-Detailed%20SOW-TPole%20TL3300%20San%20Gerardo%20Sect%20-%20Venezuela%20Sect.pdf?web=1 |  | 46078.5836 | 45527.4507 | Jason Fournier | 38 kV Transmission Priority Poles and Structures Replacements | Ashleah Dingle |  |  |  |  | 1 | 1 | 45887 | qwer275 | 753785 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
753782 | 108010 | FAASt [Transmission Priority Pole Replacement Program Line 3100 Monacillos TC – Sabana Llana TC] (Transmission) | 14F020580000 | PBUT13 - T Priority Pole Repl | Transmission |  | TRUE | Restoration | FALSE |  | Current | FALSE | [12 empty] | 45527 | 08/23/2024 |  | 45527 | 45898 | 45930 | 45908 | 9/8/2025 - Field EHP – Historic: Initial review. Expected Completion Date (ECD) 09/30/2025. |  | 199697.38 | 199697.38 | 2218.84 | 20500.96 |  | 135332.58 | 291.07 | 1927.77 | 137551.42 | 158052.38 |  |  | 45960 |  | 131580.76 | 129361.92 |  |  |  | 5970.66 |  | 131580.76 | 129361.92 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/972/753782-DR4339PR-Detailed%20SOW-TPole%20TL3100%20Monacillos%20TC%20-%20Sabana%20Llana%20TC.pdf?web=1 |  | 46078.5835 | 45527.4521 | Jason Fournier | 38 kV Transmission Priority Poles and Structures Replacements | Ashleah Dingle |  |  | 20500.96 | 291.07 | 1.4518 | 1 |  | qwer276 | 753782 | 5970.66 |  | 5970.66 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 1927.77
753781 | 108009 | FAASt [Transmission Priority Pole Replacement Program Line 800 Comsat Sect – Cidra Sect] (Transmission) | 14F020560000 |  | Transmission |  | TRUE | Restoration | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45527 | 08/23/2024 |  | 45527 | 45882 |  |  |  |  | 1569945.94 | 1569945.94 | 33695.78 | 85434.18 |  | 640758.24 | 6440.37 | 27255.41 | 674454.02 | 759888.2 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/973/753781-DR4339PR-Detailed%20SOW-T-Pole%20TL800%20Comsat%20Sect%20-%20Cidra%20Sect.pdf?web=1 | 7/25/2025 - We have received your Request for Information regarding Align DSOW poles to be replaced vs. the Structures List amount, Structures list, DSOW structures alignment, clarify fence removal, installation, restoration, and KMZ alignment. Our team is currently reviewing the details, and we will respond promptly. (Note: This project conatins both Construction and Vegetation scope and cost and is submitted as "428 only" 8/13/2025 – The 4th Hazard mitigation RFI response, revised DSOW and cost estimates were submitted today in the project document section for HM review. | 46059.5598 | 45527.4538 | Jason Fournier | 38 kV Transmission Priority Poles and Structures Replacements | Jason Fournier |  |  |  |  | 2.3277 | 1 | 45887 | qwer277 | 753781 | 44078.65 | 15908.55 | 59987.2 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
753777 | 108008 | FAASt [Line 1500 - Mayaguez GP to GOAB 1515] (Transmission) | 14F002490000 | PBUT33 - T Line Rebuild | Transmission |  |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 58610000 | 44473 | 44487 |  | 44503 |  |  |  | 45527 | 08/23/2024 |  |  |  | 45593 | 45580 |  |  | 58661000 | 0 | [5 empty] | 0 | 58661000 | 58661000 | [11 empty] | 0 | 0 |  |  |  | 46078.5819 | 45527.4561 | Jason Fournier | Transmission Line Rebuild | Ashleah Dingle |  |  |  |  | 0 | 5 | 45887 | qwer278 | 753777 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
754351 | 108016 | FAASt [Underground Circuit Feeders - San Juan Group 2] (Distribution) | 14F020360000, 14F020350000 | PBUT06 - Distr Line Rebuild | Distribution – Underground |  |  | Improved | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 45530 | 08/26/2024 |  | 45587 | [5 empty] | 7066632.8 | 7066632.8 | 7066632.8 | 0 |  | 0 | 931013.36 | 6135619.44 | 7066632.8 | 7066632.8 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/975/75435-DR4339PR-Distribution%20Underground%20Circuit%20Feeders%20-%20San%20Juan%20Group%202_Detailed%20Scope%20of%20Work%20Rev.1v4%20-%20Signed.pdf?web=1 |  | 46078.585 | 45530.3549 | Jason Fournier | Distribution Underground Circuit Rebuilds - Phase 1 | Ashleah Dingle | 0 Months |  |  |  | 1 | 1 | 45884 | qwer279 | 754351 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
754350 | 108015 | FAASt [Underground Circuit Feeders - San Juan Group 1] (Distribution) | 14F020320000, 14F020300000, 14F020310000, 14F020340000, 14F020330000 | PBUT06 - Distr Line Rebuild | Distribution – Underground |  |  | Improved | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE |  | 250000000 | 45350 | 45364 |  | 45380 |  |  |  | 45530 | 08/26/2024 |  | 45581 | [5 empty] | 15123199.33 | 15123199.33 | 15123199.33 | 0 |  | 0 | 1419257.38 | 13703941.95 | 15123199.33 | 15123199.33 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/976/754350-DR4339PR-Underground%20%20Circuit%20Feeders-San%20Juan%20Group%201-Detailed%20Scope%20of%20Work.pdf?web=1 |  | 46078.5849 | 45530.3583 | Jason Fournier | Distribution Underground Circuit Rebuilds - Phase 1 | Ashleah Dingle | 0 Months |  |  |  | 1 | 1 | 45884 | qwer280 | 754350 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
755211 | 108022 | FAASt [Automation Program Group 15] (Distribution) | 10F000650000 | PBUT04 - Distribution Automation | Grid Automation |  |  | Restoration | FALSE |  | Current | FALSE | [12 empty] | 45540 | 09/05/2024 |  | 45541 | 45979 | 46013 | 46003 | 12/12/2025 - Field EHP: Review ongoing, previous status applies. ECD Updated (12/22/2025) |  | 324000 | 324000 | 250899.06 | 28366.57 |  | 329417.48 | 19875.89 | 231023.17 | 580316.54 | 608683.11 |  |  | 45694 | 10/15/2025 | 643560.85 | 643560.85 | 527176.83 | 276277.77 |  | 53139.71 |  | 527176.83 | 276277.77 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/985/755211-%20DR4339PR%20-%20DSOW%20Group%2015%20DAUT.pdf?web=1 | 13MAY2025 Version 1 was created to address fund code correction from FC6E to FC06 for FAASt projects. This administrative amendment does not change the previously approved scope of work or costs, however, to be able to process the correction a version is being submitted for de-obligating the available balance in this PW, and a next version will be submitted to reconcile available funding in the correct code. Per the Financial Management Section, the amount to be de-obligated in this version is -$643,560.85 (100%) / -$579,204.77 (90%). 06SEPTEMBER2024 No ISOW provided in Grants Portal at this time - MC | 46078.5861 | 45541.3847 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Ashleah Dingle |  |  | 110225.14 | 19875.89 | 0.55832 | 3 |  | qwer281 | 755211 | 53139.71 | 103164.29 | 156304 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 127858.88
800361 | 108078 | FAASt [Automation Program Group 37] (Distribution) | 10F005220000, 10F005120000, 10F004760000 | PBUT04 - Distribution Automation | Grid Automation |  |  |  | FALSE |  | Current | FALSE | [12 empty] | 45657 | 12/31/2024 |  | 45775 | 46080 | 45817 | 45807 |  |  | 2148000 | 2148000 | 740370.01 | 174540.79 | 172327.33 | 1679038.26 | 68764.66 | 671605.35 | 2419408.27 | 2593949.06 |  |  | 45917 |  | 1596193 | 1596193 |  |  |  | 473670.4 |  | 1596193 | 1596193 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/993/800361-DR4339PR-%20DSOW%20Group%2037-Rev.%201.pdf?web=1 |  | 46085.5917 | 45546.5663 | Rey Roldan Rodríguez | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Marlina Crespo |  |  | 297988.09 | 0 | 0.88782 | 1 |  | qwer282 | 800361 | 473670.4 |  | 473670.4 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
800369 | 108079 | FAASt [Automation Program Group 38] (Distribution) | 10F000970000, 10F000950000 | PBUT04 - Distribution Automation | Grid Automation |  |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45657 | 12/31/2024 | [7 empty] | 1335000 | 1335000 | [5 empty] | 0 | 1335000 | 1335000 | [11 empty] | 0 | 0 |  |  |  | 46078.5934 | 45546.5663 | Rey Roldan Rodríguez | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Ashleah Dingle |  |  |  |  | 1 | 1 | 45888 | qwer283 | 800369 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
800394 | 108080 | FAASt [Automation Program Group 39] (Distribution) | 10F002180000, 10F002200000, 10F002190000, 10F001350000, 10F002170000 | PBUT04 - Distribution Automation | Grid Automation |  |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45657 | 12/31/2024 | [7 empty] | 3084000 | 3084000 | [5 empty] | 0 | 3084000 | 3084000 | [11 empty] | 0 | 0 |  |  |  | 46078.5934 | 45546.5663 | Rey Roldan Rodríguez | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Ashleah Dingle |  |  |  |  | 1 | 1 | 45888 | qwer284 | 800394 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
800399 | 108081 | FAASt [Automation Program Group 40] (Distribution) | 10F001460000, 10F002280000, 10F001420000, 10F005290000, 10F005530000 | PBUT04 - Distribution Automation | Grid Automation |  |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45657 | 12/31/2024 | [7 empty] | 2577000 | 2577000 | [5 empty] | 0 | 2577000 | 2577000 | [11 empty] | 0 | 0 |  |  |  | 46078.5935 | 45546.5663 | Rey Roldan Rodríguez | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Ashleah Dingle |  |  |  |  | 1 | 1 | 45888 | qwer285 | 800399 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 357 |  | FAASt [Distribution Feeder Rebuild # 1620-02] |  |  | Distribution – Feeder Rebuild |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7716 | 45546.5664 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer286 | FAASt number pending 357 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 358 |  | FAASt [Distribution Feeder Rebuild # 2404-06] |  |  | Distribution – Feeder Rebuild |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7716 | 45546.5664 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer287 | FAASt number pending 358 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 361 |  | FAASt [Distribution Feeder Rebuild # 6406-02] |  |  | Distribution – Feeder Rebuild |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7716 | 45546.5664 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer288 | FAASt number pending 361 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
797148 | 108074 | FAASt [Distribution Feeder Rebuild # 8101-03] (Distribution) | 14F000100000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild |  |  | Restoration | FALSE |  | Current | FALSE | [12 empty] | 45632 | 12/06/2024 |  | 45674 | 46085 | 45810 | 45807 |  |  | 4700455 | 4700455 | 147453.78 | 678369.17 | 431054.74 | 2716080.94 | 29445.05 | 118008.73 | 2863534.72 | 3541903.89 |  |  | 45917 |  | 2359896 | 2359896 |  |  |  | 245423.36 |  | 2359896 | 2359896 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1002/797148-DR4339PR-Feeder%20Rebuild%208101-03-DSOW%20Rev.%200.pdf?web=1 | 09DECEMBER2024 No ISOW in Grants Portal - MC | 46094.6443 | 45546.5664 | Rey Roldan Rodríguez | Distribution Feeders - Arecibo Short Term Group 2 | Marlina Crespo |  |  | 777847.24 | 0 | 1.6415 | 1 |  | qwer289 | 797148 | 245423.36 |  | 245423.36 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 363 |  | FAASt [Distribution Feeder Rebuild # 1801-03] |  |  | Distribution – Feeder Rebuild |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7716 | 45546.5664 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer290 | FAASt number pending 363 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 364 |  | FAASt [Distribution Feeder Rebuild # 3502-02] |  |  | Distribution – Feeder Rebuild |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7716 | 45546.5664 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer291 | FAASt number pending 364 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 365 |  | FAASt [Distribution Feeder Rebuild # 6802-04] |  |  | Distribution – Feeder Rebuild |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7716 | 45546.5664 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer292 | FAASt number pending 365 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 366 |  | FAASt [Distribution Feeder Rebuild # 7805-13] |  |  | Distribution – Feeder Rebuild |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7716 | 45546.5664 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer293 | FAASt number pending 366 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 367 |  | FAASt [Distribution Feeder Rebuild # 1336-08] |  |  | Distribution – Feeder Rebuild |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7716 | 45546.5664 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer294 | FAASt number pending 367 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
767387 | 108068 | FAASt # [Distribution Feeder Rebuild # 1303-01] (Distribution) | 14F001480000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild |  |  |  | TRUE | 45869 |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45618 | 11/22/2024 | [7 empty] | 4798378.99 | 4798378.99 | [5 empty] | 0 | 4798378.99 | 4798378.99 | [11 empty] | 0 | 0 |  |  | 22November2024 No ISOW Docs in Grants Portal - MC 6/12/2025 - Project withdrawn in Grants Portal | 46078.5915 | 45546.5664 | Rey Roldan Rodríguez | Distribution Feeders ‐ San Juan Short Term Group 2 | Ashleah Dingle |  |  |  |  | 1 | 1 | 45820 | qwer295 | 767387 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
767381 | 108067 | FAASt [Distribution Feeder Rebuild # 1204-04] (Distribution) | 14F001460000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild |  |  |  | TRUE | 45930 |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45618 | 11/22/2024 | [7 empty] | 9998489 | 9998489 | [5 empty] | 0 | 9998489 | 9998489 | [11 empty] | 0 | 0 |  |  | 22November2024 No ISOW Docs in Grants Portal - MC 6/12/2025 - Project withdrawn in Grants Portal | 46078.5914 | 45546.5664 | Rey Roldan Rodríguez | Distribution Feeders ‐ San Juan Short Term Group 1 | Ashleah Dingle |  |  |  |  | 1 | 1 | 45820 | qwer296 | 767381 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 371 |  | FAASt [Distribution Feeder Rebuild # 1806-02] |  |  | Distribution – Feeder Rebuild |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7716 | 45546.5664 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer297 | FAASt number pending 371 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 372 |  | FAASt #[Distribution Feeder Rebuild # 6601-03] |  |  | Distribution – Feeder Rebuild |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7716 | 45546.5685 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer298 | FAASt number pending 372 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 373 |  | FAASt [Distribution Feeder Rebuild # 6603-01] |  |  | Distribution – Feeder Rebuild |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7716 | 45546.5685 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer299 | FAASt number pending 373 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
801197 | 108084 | FAASt [Distribution Feeder Rebuild # 1204-02 | 14F001440000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild |  |  |  | TRUE | 45930 |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45665 | 1/8/2025 | [7 empty] | 3863358 | 3863358 | [5 empty] | 0 | 3863358 | 3863358 | [11 empty] | 0 | 0 |  |  | 14JANUARY2025 No ISOW in Grants Portal - MC6/12/2025 - Project withdrawn in Grants Portal | 46078.5945 | 45546.5685 | Rey Roldan Rodríguez |  | Ashleah Dingle |  |  |  |  | 1 | 1 | 45820 | qwer300 | 801197 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
767005 | 108062 | FAASt [Distribution Feeder Rebuild # 1303-05] | 14F001500000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild |  |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45617 | 11/21/2024 | [7 empty] | 12631766 | 12631766 | [5 empty] | 0 | 12631766 | 12631766 | [11 empty] | 0 | 0 |  |  | 22November2024 No ISOW Docs in Grants Portal - MC 6/12/2025 - Project withdrawn in Grants Portal | 46078.5914 | 45546.5685 | Rey Roldan Rodríguez | Distribution Feeders ‐ San Juan Short Term Group 1 | Ashleah Dingle |  |  |  |  | 1 | 1 | 45820 | qwer301 | 767005 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 376 |  | FAASt [Distribution Feeder Rebuild # 7805-11] |  |  | Distribution – Feeder Rebuild |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7716 | 45546.5685 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer302 | FAASt number pending 376 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 377 |  | FAASt [Distribution Feeder Rebuild # 6305-03] |  |  | Distribution – Feeder Rebuild |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7716 | 45546.5685 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer303 | FAASt number pending 377 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 378 |  | FAASt [Distribution Feeder Rebuild # 2402-02] |  |  | Distribution – Feeder Rebuild |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7716 | 45546.5686 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer304 | FAASt number pending 378 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 379 |  | FAASt [Distribution Feeder Rebuild # 9501-02] |  |  | Distribution – Feeder Rebuild |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7716 | 45546.5686 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer305 | FAASt number pending 379 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 384 |  | FAASt [Distribution Feeder Rebuild #- 1303-02 |  |  | Distribution – Feeder Rebuild |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7716 | 45546.5686 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer306 | FAASt number pending 384 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 385 |  | FAASt [Distribution Feeder Rebuild #- 6010-01 |  |  | Distribution – Feeder Rebuild |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7716 | 45546.5686 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer307 | FAASt number pending 385 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 386 |  | FAASt [Distribution Feeder Rebuild #- 6306-02 |  |  | Distribution – Feeder Rebuild |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7716 | 45546.5686 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer308 | FAASt number pending 386 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 389 |  | FAASt [Distribution Feeder Rebuild # - 1529-15 |  |  | Distribution – Feeder Rebuild |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7716 | 45546.5686 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer309 | FAASt number pending 389 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 390 |  | FAASt [Distribution Feeder Rebuild #- 3006-05 |  |  | Distribution – Feeder Rebuild |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7716 | 45546.5686 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer310 | FAASt number pending 390 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 391 |  | FAASt [Distribution Feeder Rebuild #- 3007-03 |  |  | Distribution – Feeder Rebuild |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7716 | 45546.5686 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer311 | FAASt number pending 391 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 392 |  | FAASt [Distribution Feeder Rebuild #- 6704-03 |  |  | Distribution – Feeder Rebuild |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7716 | 45546.5686 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer312 | FAASt number pending 392 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 393 |  | FAASt [Distribution Feeder Rebuild # - 2603-08 |  |  | Distribution – Feeder Rebuild |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7717 | 45546.5686 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer313 | FAASt number pending 393 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 395 |  | FAASt [Pole and Conductor Repair- Caguas Group 4-Phase 2] (Distribution) |  |  | Distribution – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7717 | 45546.5686 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer314 | FAASt number pending 395 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 396 |  | FAASt [Pole and Conductor Repair-San Juan Group 3- Phase 2] (Distribution) |  |  | Distribution – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7717 | 45546.5686 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer315 | FAASt number pending 396 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 397 |  | FAASt [Pole and Conductor Repair- Caguas Group 5-Phase 2] (Distribution) |  |  | Distribution – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7717 | 45546.5692 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer316 | FAASt number pending 397 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 398 |  | FAASt [Pole and Conductor Repair- Arecibo Group 3-Phase 2] (Distribution) |  |  | Distribution – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7717 | 45546.5692 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer317 | FAASt number pending 398 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 250 |  | FAASt Salinas TC to Jobos TC – 38kV 100 & 200 (Transmission) |  |  | Transmission |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7717 | 45546.5822 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer318 | FAASt number pending 250 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 258 |  | FAASt - Line 36100(115kV) - Unibon to Monterrey (Transmission) |  |  | Transmission |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7717 | 45546.5835 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer319 | FAASt number pending 258 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 259 |  | FAASt - Line 36100(115kV) - Monterrey to Pinas (Transmission) |  |  | Transmission |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7717 | 45546.5835 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer320 | FAASt number pending 259 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 260 |  | FAASt - Line 36100(115kV) - Pinas to Cana (Transmission) |  |  | Transmission |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7717 | 45546.5835 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer321 | FAASt number pending 260 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 261 |  | FAASt [T-Pole Program Line 16500 Fajardo TC - Dos Marinas] (Transmission) |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7717 | 45546.5835 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer322 | FAASt number pending 261 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 262 |  | FAASt [T-Pole Program Line 800 Comsat Sect - Cidra Sect] (Transmission) |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7717 | 45546.5835 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer323 | FAASt number pending 262 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 263 |  | TL 2000 - Once De Agosto Sect - San Sebastian TC |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7717 | 45546.5835 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer324 | FAASt number pending 263 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 264 |  | TL 3100 Monacillos TC - Sabana Llana TC |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7717 | 45546.5835 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer325 | FAASt number pending 264 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 265 |  | TL1500 Once De Agosto Sect - Sabana Grande TO |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7717 | 45546.5835 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer326 | FAASt number pending 265 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 266 |  | TL 3300 San Gerardo Sect-Venezuela Sect |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7717 | 45546.5835 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer327 | FAASt number pending 266 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 267 |  | TL 5900 San Juan SP- Crematorio TO |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7717 | 45546.5835 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer328 | FAASt number pending 267 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 268 |  | TL 1200 San German Sect-San German TC- Yauco 2HP |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7717 | 45546.5835 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer329 | FAASt number pending 268 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 269 |  | TL 13700 Mora TC -Isabela TO |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7717 | 45546.5835 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer330 | FAASt number pending 269 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 270 |  | TL 1600 Leon Sect - Acacias TC |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7717 | 45546.5835 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer331 | FAASt number pending 270 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 271 |  | TL 1900 Dos Bocas Hp-San Sebastian TC |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7717 | 45546.5836 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer332 | FAASt number pending 271 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 272 |  | TL 10100 - LASLomas Sect-Reparto Metropolitano TO |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7717 | 45546.5836 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer333 | FAASt number pending 272 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 273 |  | TL 2400 - Dos Bocas Hp-Caonillas 2 Hp |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7717 | 45546.5836 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer334 | FAASt number pending 273 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 274 |  | TL 200 Ponce TC - Santa Isabel Sect |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7717 | 45546.5836 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer335 | FAASt number pending 274 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 275 |  | TL 4800 Santa Isabel TC- Santa Isabel Sect |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7717 | 45546.5836 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer336 | FAASt number pending 275 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 276 |  | TL 9600 Bayamon TC - Cataño Sect |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7717 | 45546.5836 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer337 | FAASt number pending 276 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 277 |  | TL 7800 - Dorado Tc- Vega Alta Sect |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7717 | 45546.5836 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer338 | FAASt number pending 277 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 278 |  | TL6700 - Seboruco To- Tapia TO |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7717 | 45546.5836 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer339 | FAASt number pending 278 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 279 |  | TL 7500 - Tres Monjitas Sect-Puerto Nuevo TO |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7717 | 45546.5837 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer340 | FAASt number pending 279 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 280 |  | TL 10700 - Hato Tejas Tc-Hato Tejas Sect |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7717 | 45546.5837 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer341 | FAASt number pending 280 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 281 |  | TL 6000 - Aguadilla Hospital Distrito To-T- Bone TO |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7717 | 45546.5837 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer342 | FAASt number pending 281 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 282 |  | TL 10500-Chardon Sect- Las Monjas TO |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7717 | 45546.5837 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer343 | FAASt number pending 282 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 283 |  | TL 14100 Barceloneta Tc-Merck |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7717 | 45546.5837 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer344 | FAASt number pending 283 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 284 |  | FAASt [T-Pole Program Line 37400 Dorado TC - Vega Baja TC] (Transmission) |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7717 | 45546.5837 | Jason Fournier | 115 kV Transmission Priority Poles and Structures Replacements | Rey Roldan Rodríguez | [7 empty] | qwer345 | FAASt number pending 284 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 285 |  | FAASt [T-Pole Program Line 37400 Barceloneta TC - Cambalache TC] (Transmission) |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7717 | 45546.5837 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer346 | FAASt number pending 285 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 286 |  | TL 1700 - Guanica Tc- Yauco 2 Hp |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7717 | 45546.5837 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer347 | FAASt number pending 286 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 287 |  | TL 18400 -Barranquitas Tc-El Abanico |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7717 | 45546.5837 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer348 | FAASt number pending 287 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 288 |  | TL 2200 -Barceloneta TC-Manati TC |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7717 | 45546.5838 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer349 | FAASt number pending 288 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 289 |  | TL 2200 - Vega Baja TC-Vega Alta Sect |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7717 | 45546.5838 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer350 | FAASt number pending 289 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 290 |  | TL 6900 -Cambalache Tc-Mirador Azul Sect |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7717 | 45546.5838 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer351 | FAASt number pending 290 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 291 |  | TL 6900 - Mirador Azul Sect-Hatillo TO |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7717 | 45546.5838 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer352 | FAASt number pending 291 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 292 |  | TL 8100 - Yauco 1 Hp- Adjuntas TO |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7717 | 45546.5838 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer353 | FAASt number pending 292 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 293 |  | TL 9200 - Añasco TC- Añasco |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7717 | 45546.5838 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer354 | FAASt number pending 293 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 294 |  | TL 9900 - Rio Blanco Hp-Humacao Sect |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7717 | 45546.5839 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer355 | FAASt number pending 294 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 295 |  | TL 2700 - Aguadilla Hospital Distrito Sect - Mora TC |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7717 | 45546.5839 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer356 | FAASt number pending 295 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 296 |  | TL 5600 Anasco TC- Mayaguez GP |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7717 | 45546.5839 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer357 | FAASt number pending 296 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 297 |  | TL 3500 Cachete Sect- Caparra Sect |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7717 | 45546.5839 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer358 | FAASt number pending 297 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 303 |  | TL 36800 Canovanas TC - Palmer TC |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7717 | 45546.5883 | Rey Roldan Rodríguez | FAASt Canovanas TC to Sabana Llana TC - 36800 (Transmission) FAASt Canovanas TC to Palmer-Fajardo TC - 36800 (Transmission) | Rey Roldan Rodríguez | [7 empty] | qwer359 | FAASt number pending 303 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 304 |  | TL 14400 - Caguax Sect- Veredas Sect |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7717 | 45546.5883 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer360 | FAASt number pending 304 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 305 |  | TL 6100 Mayaguez GP - Radial |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7717 | 45546.5883 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer361 | FAASt number pending 305 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 306 |  | TL 14400 - Veredas Sect- Gautier Benitez Sect |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7717 | 45546.5883 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer362 | FAASt number pending 306 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 307 |  | TL 37400 Cambalache TC- Dos Bocas HP |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7717 | 45546.5883 | Rey Roldan Rodríguez | 115 kV Transmission Priority Poles and Structures Replacements | Rey Roldan Rodríguez | [7 empty] | qwer363 | FAASt number pending 307 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 308 |  | TL 10300 - Canovanas TC- Canovanas Sect |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7717 | 45546.5883 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer364 | FAASt number pending 308 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 309 |  | TL 10700 - Hato Tejas Sect-Bayamon Pueblo Sect |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7717 | 45546.5883 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer365 | FAASt number pending 309 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 310 |  | TL 10900 - Jobos Tc-Pfizer Guayama |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7717 | 45546.5883 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer366 | FAASt number pending 310 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 311 |  | TL 13200 - Dorado Tc-Hato Tejas TC |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7717 | 45546.5883 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer367 | FAASt number pending 311 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 312 |  | TL 13200 - Hato Tejas TC- Hato Tejas Sect |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7717 | 45546.5883 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer368 | FAASt number pending 312 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 313 |  | TL 13600 - Arecibo Sect-Mirador Azul Sect- |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7717 | 45546.5883 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer369 | FAASt number pending 313 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 314 |  | TL 14700 Manati TC - Manati Sect |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7717 | 45546.5883 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer370 | FAASt number pending 314 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 315 |  | TL 14900-Quebradillas Sect-Quebradillas TO- |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7717 | 45546.5883 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer371 | FAASt number pending 315 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 316 |  | TL 15900-Victoria TC- Aguada TO |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7717 | 45546.5883 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer372 | FAASt number pending 316 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 317 |  | TL 1800 - Ponce TC -Villa Del Carmen TO |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7718 | 45546.5883 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer373 | FAASt number pending 317 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 318 |  | TL 200-Santa Isabel Sect-Salinas Sect |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7718 | 45546.5883 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer374 | FAASt number pending 318 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 319 |  | TL 2900 Toro Negro 1 HP -Toro Negro 2 HP |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7718 | 45546.5883 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer375 | FAASt number pending 319 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 320 |  | TL 300 - Juana Diaz Tc- La Rambla Sect |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7718 | 45546.5883 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer376 | FAASt number pending 320 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 321 |  | TL 300 - Toro Negro 1 Hp-Juana Diaz TC |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7718 | 45546.5883 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer377 | FAASt number pending 321 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 322 |  | TL 3200 - Hato Rey Tc- Baldrich Sect |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7718 | 45546.5883 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer378 | FAASt number pending 322 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 323 |  | TL 3400 - Monacillos TC-Guaynabo Sect |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7718 | 45546.5883 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer379 | FAASt number pending 323 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 324 |  | TL 37500-Rio Bayamon Sect-Monacillos TC |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7718 | 45546.5883 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer380 | FAASt number pending 324 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 325 |  | TL 37800 Monacillos TC - Buen Pastor Sect |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7718 | 45546.5883 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer381 | FAASt number pending 325 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 326 |  | TL 37800 Caguas TC - Buen Pastor Sect |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7718 | 45546.5883 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer382 | FAASt number pending 326 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 327 |  | TL 400 Caguas TC - Gautier Benitez Sect |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7718 | 45546.5883 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer383 | FAASt number pending 327 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 328 |  | TL 8700-Costa Sur SP- Garzas 1 Hp |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7718 | 45546.5883 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer384 | FAASt number pending 328 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 329 |  | TL 38900 Martin Peña GIS - Berwind TC |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7718 | 45546.5883 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer385 | FAASt number pending 329 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 330 |  | TL 5400 Rio Blanco HP - Daguao TC |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7718 | 45546.5883 | Rey Roldan Rodríguez | Transmission – Line 5400 – Rio Blanco HP to Daguao TC to Punta Lima TO to Vieques 2501 to Culebra 3801 | Rey Roldan Rodríguez | [7 empty] | qwer386 | FAASt number pending 330 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 331 |  | TL 9500-Palo Seco SP - Cataño Sect |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7718 | 45546.5883 | Rey Roldan Rodríguez | FAASt Palo Seco SP to Catano SectLine-9500 (Transmission) | Rey Roldan Rodríguez | [7 empty] | qwer387 | FAASt number pending 331 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 332 |  | TL 500-Ponce TC-Costa Sur SP-Canas TC |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7718 | 45546.5883 | Rey Roldan Rodríguez | Line 500 Ponce TC to Costa Sur SP | Rey Roldan Rodríguez | [7 empty] | qwer388 | FAASt number pending 332 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 333 |  | TL 2600-San Sebastian TC-Quebradillas Sect |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7718 | 45546.5883 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer389 | FAASt number pending 333 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 334 |  | TL 36200 Monacillos TC- Juncos TC |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7718 | 45546.5883 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer390 | FAASt number pending 334 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 335 |  | TL 37400-Barceloneta TC-Cambalache TC |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7718 | 45546.5883 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer391 | FAASt number pending 335 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 336 |  | TL 37400-Dorado TC-Vega Baja TC |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7718 | 45546.5883 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer392 | FAASt number pending 336 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 337 |  | TL 38200-Palo Seco Power Plant-Monacillos TC |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7718 | 45546.5884 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer393 | FAASt number pending 337 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 338 |  | TL 7200-Baldrich Sect- Escuela Industrial TO |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7718 | 45546.5884 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer394 | FAASt number pending 338 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 339 |  | TL 7300-Baldrich Sect- San Jose TO |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7718 | 45546.5884 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer395 | FAASt number pending 339 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 340 |  | TL 37800-Cayey TC-Jobos TC |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7718 | 45546.5884 | Rey Roldan Rodríguez | FAASt Transmission - Line 37800 - Jobos TC to Cayey TC Transmission - Line 37800 - Cayey TC to Caguas TC (Transmission) | Rey Roldan Rodríguez | [7 empty] | qwer396 | FAASt number pending 340 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 341 |  | TL 37800-Cayey TC-Caguas TC- |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7718 | 45546.5884 | Rey Roldan Rodríguez | FAASt Transmission - Line 37800 - Jobos TC to Cayey TC Transmission - Line 37800 - Cayey TC to Caguas TC (Transmission) | Rey Roldan Rodríguez | [7 empty] | qwer397 | FAASt number pending 341 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 343 |  | Group 22 - DAUT |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7718 | 45546.5884 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer398 | FAASt number pending 343 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 344 |  | Group 24 - DAUT |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7718 | 45546.5884 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer399 | FAASt number pending 344 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 345 |  | Group 26 - DAUT |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7718 | 45546.5884 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer400 | FAASt number pending 345 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 346 |  | Group 27 - DAUT |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7718 | 45546.5884 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer401 | FAASt number pending 346 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 347 |  | Group 31 - DAUT |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7718 | 45546.5884 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer402 | FAASt number pending 347 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 348 |  | Group 32 - DAUT |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7718 | 45546.5884 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer403 | FAASt number pending 348 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 349 |  | Group 33 - DAUT |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7718 | 45546.5884 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer404 | FAASt number pending 349 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 350 |  | Group 34 - DAUT |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7718 | 45546.5884 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer405 | FAASt number pending 350 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 351 |  | Group 35 - DAUT |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7718 | 45546.5884 | Rey Roldan Rodríguez |  | Rey Roldan Rodríguez | [7 empty] | qwer406 | FAASt number pending 351 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
800286 | 108077 | FAASt [Automation Program Group 36] (Distribution) | 10F002670000, 10F004180000, 10F004160000, 10F006580000 | PBUT04 - Distribution Automation | Grid Automation |  |  |  | FALSE |  | Current | FALSE | [12 empty] | 45656 | 12/30/2024 |  | 45775 | 46065 | 45817 | 45807 |  |  | 2175000 | 2175000 | 995016.61 | 137043.71 | 175789.83 | 1603428.25 | 78366.54 | 916650.07 | 2598444.86 | 2735488.57 |  |  | 45917 |  | 1703713 | 1703713 |  |  |  | 597390.08 |  | 1703713 | 1703713 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1142/800286-DR4339PR-%20DSOW%20Group%2036.%20Rev.%201.pdf?web=1 | 30DECEMBER2024 No ISOWs in GP at this time MC | 46078.5933 | 45546.5884 | Rey Roldan Rodríguez | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Ashleah Dingle |  |  | 300364.95 | 0 | 0.83704 | 1 |  | qwer407 | 800286 | 230628.16 | 342399.24 | 573027.4 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 251 |  | FAASt {Region 1- San Juan Group B] Low Density (Vegetation) |  |  | Vegetation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7718 | 45546.609 | Jason Fournier | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez | [7 empty] | qwer408 | FAASt number pending 251 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 252 |  | FAASt {Region 2- Arecibo Group B] Low Density (Vegetation) |  |  | Vegetation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7718 | 45546.6091 | Jason Fournier | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez | [7 empty] | qwer409 | FAASt number pending 252 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 253 |  | FAASt {Region 3 - Bayamon Group B] Low Density (Vegetation) |  |  | Vegetation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7718 | 45546.6091 | Jason Fournier | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez | [7 empty] | qwer410 | FAASt number pending 253 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 254 |  | FAASt {Region 4 - Caguas Group B] Low Density (Vegetation) |  |  | Vegetation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7718 | 45546.6091 | Jason Fournier | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez | [7 empty] | qwer411 | FAASt number pending 254 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 255 |  | FAASt {Region 5 - Mayaguez Group B] Low Density (Vegetation) |  |  | Vegetation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7718 | 45546.6091 | Jason Fournier | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez | [7 empty] | qwer412 | FAASt number pending 255 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 298 |  | TL 1600 - SanGerman Sect-San German Tc |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7718 | 45546.6132 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer413 | FAASt number pending 298 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 299 |  | TL 1600 - San German Tc- Yauco 1 Hp |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7718 | 45546.6133 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer414 | FAASt number pending 299 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 300 |  | TL 2800 - Aguadilla Hospital Distrito Sect-T- Bone TO |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7718 | 45546.6133 | Jason Fournier | Line 2800 Aguadilla Hospital Distrito Sect to T-Bone TO | Rey Roldan Rodríguez | [7 empty] | qwer415 | FAASt number pending 300 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 301 |  | TL 3200 - Viaducto Tc- Martin Peña TC |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7718 | 45546.6134 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer416 | FAASt number pending 301 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 302 |  | TL 3200 Hato Rey - Baldrich Sect |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7718 | 45546.6134 | Jason Fournier |  | Rey Roldan Rodríguez | [7 empty] | qwer417 | FAASt number pending 302 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
756472 | 108024 | FAASt [Region 1-San Juan Group B] Low Density (Vegetation) |  |  | Vegetation |  |  |  | FALSE |  |  | TRUE | Voluntarily Withdrawal Status in Grants Portal | Merged FAASt | [10 empty] | 45554 | 09/19/2024 | [7 empty] | 691016.47 | 691016.47 | [5 empty] | 0 | 691016.47 | 691016.47 | [11 empty] | 0 | 0 |  |  | 20SEPTEMBER2024 - No ISOW uploaded18OCT2024 - GRANTS PORTAL "The project was withdrawn" 17OCT202410/22/2024 - Merged w/ 740406 10/17/2024 02:36 PM AST Project Updated Title: FAASt [Region 1-San Juan Group B] High Density (Vegetation) - FAASt [Region 1-San Juan Group B] (Vegetation) FAASt #756472 added | 45856.7718 | 45555.525 | Marlina Crespo | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | qwer418 | 756472 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
756474 | 108025 | FAASt [Region 3-Bayamon Group B] Low Density (Vegetation) |  |  | Vegetation |  |  |  | FALSE |  |  | TRUE | Voluntarily Withdrawal Status in Grants Portal | Merged FAASt | [10 empty] | 45554 | 09/19/2024 | [7 empty] | 1049080.08 | 1049080.08 | [5 empty] | 0 | 1049080.08 | 1049080.08 | [11 empty] | 0 | 0 |  |  | 20SEPTEMBER2024 - No ISOW uploaded18OCT2024 - GRANTS PORTAL "The project was withdrawn" 17OCT202410/22/2024 - GRANTS PORTAL MERGED W/ 740408 10/17/2024 02:39 PM AST 10/17/2024 02:39 PM AST Project Updated Title: FAASt [Region 3-Bayamon Group B] High Density (Vegetation) - FAASt [Region 3-Bayamon Group B] (Vegetation) | 45856.7718 | 45555.5253 | Marlina Crespo | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | qwer419 | 756474 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
756475 | 108026 | FAASt [Region 2-Arecibo Group B] Low Density (Vegetation) |  |  | Vegetation |  |  |  | FALSE |  |  | TRUE | Voluntarily Withdrawal Status in Grants Portal | Merged FAASt | [10 empty] | 45554 | 09/19/2024 | [7 empty] | 30966.29 | 30966.29 | [5 empty] | 0 | 30966.29 | 30966.29 | [11 empty] | 0 | 0 |  |  | 20SEPTEMBER2024 - No ISOW uploaded18OCT2024 - GRANTS PORTAL "The project was withdrawn" 17OCT202410/22/2024 - GRANTS PORTAL MERGED W/ 740410 10/17/2024 02:40 PM AST Project Updated Title: FAASt [Region 2-Arecibo Group B] High Density (Vegetation) - FAASt [Region 2-Arecibo Group B] (Vegetation) | 45856.7718 | 45555.5257 | Marlina Crespo | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | qwer420 | 756475 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
756476 | 108027 | FAASt [Region 4-Caguas Group B] Low Density (Vegetation) |  |  | Vegetation |  |  |  | FALSE |  |  | TRUE | Voluntarily Withdrawal Status in Grants Portal | Merged FAASt | [10 empty] | 45554 | 09/19/2024 | [7 empty] | 3068261.01 | 3068261.01 | [5 empty] | 0 | 3068261.01 | 3068261.01 | [11 empty] | 0 | 0 |  |  | 20SEPTEMBER2024 - No ISOW uploaded18OCT2024 - GRANTS PORTAL "The project was withdrawn" 17OCT202410/22/2024 - GRANTS PORTAL MERGED W/ 740409 10/17/2024 02:39 PM AST Project Updated Title: FAASt [Region 4-Caguas Group B] High Density (Vegetation) - FAASt [Region 4-Caguas Group B] (Vegetation) | 45856.7718 | 45555.5263 | Marlina Crespo | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | qwer421 | 756476 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
756477 | 108028 | FAASt [Region 5-Mayaguez Group B] Low Density (Vegetation) |  |  | Vegetation |  |  |  | FALSE |  |  | TRUE | Voluntarily Withdrawal Status in Grants Portal | Merged FAASt | [10 empty] | 45554 | 09/19/2024 | [7 empty] | 720951.73 | 720951.73 | [5 empty] | 0 | 720951.73 | 720951.73 | [11 empty] | 0 | 0 |  |  | 20SEPTEMBER2024 - No ISOW uploaded18OCT2024 - GRANTS PORTAL "The project was withdrawn" 17OCT202410/22/2024 - MERGED W/ 740411 10/17/2024 02:47 PM AST Project UpdatedTitle: FAASt [Region 5-Mayaguez Group B] High Density (Vegetation) - FAASt [Region 5-Mayaguez Group B] (Vegetation) | 45856.7718 | 45555.5265 | Marlina Crespo | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | qwer422 | 756477 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
756479 | 108029 | FAASt [Region 6-Ponce Group B] Low Density (Vegetation) |  |  | Vegetation |  |  |  | FALSE |  |  | TRUE | Voluntarily Withdrawal Status in Grants Portal | Active | [10 empty] | 45554 | 09/19/2024 | [7 empty] | 1316423.25 | 1316423.25 | [5 empty] | 0 | 1316423.25 | 1316423.25 | [11 empty] | 0 | 0 |  |  | 20SEPTEMBER2024 - No ISOW uploaded18OCT2024 - GRANTS PORTAL "The project was withdrawn" 17OCT2024 & The project was withdrawn with the comment "LUMA requests the elimination of this project. The information of this project will be part of the one that is kept in the system as group B. For more details, please see attached document DR4339PR-Email confirmation to remove Group B Low Density 10.17.24.". | 45856.7718 | 45555.5268 | Marlina Crespo | Island-Wide Vegetation Clearing | Rey Roldan Rodríguez |  |  |  |  | 1 | 1 |  | qwer423 | 756479 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
756997 | 108030 | FAASt [TL 1900 Caguanas to Lares TO] (Transmission) |  | PBUT33 - T Line Rebuild | Transmission |  |  | Restoration | FALSE |  | Current | FALSE | [12 empty] | 45560 | 09/25/2024 |  | 45565 | 46057 | 45884 | 45870 | 8/1/2025 - Field EHP - Environmental: review ongoing. ECD 8/15/2025. |  | 51200000 | 51200000 | 11624435.67 | 2584537.17 |  | 35688297.3 | 770659.35 | 10853776.32 | 47312732.97 | 49897270.14 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1168/756997-DR4339PR-Detailed%20SOW-TLine%20%20Caguanas%20TC%20to%20Lares%20TO%20(Seg.%202)_Rev0.pdf?web=1 | 25SEPTEMBER2024 No ISOW submitted at this time 8/1/2025 - Environmental: review ongoing. ECD 8/15/2025. | 46078.5866 | 45560.3924 | Marlina Crespo | Line 1900 Dos Bocas HP to San Sebastian TC | Ashleah Dingle |  |  |  |  | 1.0822 | 1 |  | qwer424 | 756997 | 510654.48 | 0 | 510654.48 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
756999 | 108031 | FAASt [TL 1900 Lares TO to San Sebastian] (Transmission) |  | PBUT33 - T Line Rebuild | Transmission |  |  | Restoration | FALSE |  | Current | FALSE | [12 empty] | 45560 | 09/25/2024 |  | 45566 | 46057 | 45884 | 45853 | Field EHP - Historic: Previous status applies: In review. ECD: 8/15/2025. |  | 51200000 | 51200000 | 8558819.19 | 2251104.25 | 2446381.79 | 31467109.13 | 2720179.87 | 5838639.32 | 40025928.32 | 42277032.57 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1169/756999-DR4339PR-Detailed%20SOW-TLine%201900%20Lares%20TO%20-%20San%20Sebastian%20(Sec.%203)_Rev0.pdf?web=1 | 25SEPTEMBER2024 No ISOW submitted at this time | 46078.5867 | 45560.3953 | Marlina Crespo | Line 1900 Dos Bocas HP to San Sebastian TC | Ashleah Dingle |  |  |  |  | 1.2792 | 1 |  | qwer425 | 756999 | 1449761.7 | 0 | 1449761.7 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
757662 | 108032 | FAASt [Automation Program Group 21] (Distribution) | 10F001150000, 10F001160000, 10F001140000, 10F001130000 | PBUT04 - Distribution Automation | Grid Automation |  |  |  | FALSE |  | Current | FALSE | [12 empty] | 45562 | 09/27/2024 |  | 45688 | 45827 | 45869 | 45847 |  |  | 1488000 | 1488000 | 0 | 280516.59 |  | 2223344.42 | 0 | 0 | 2223344.42 | 2503861.01 |  |  | 45960 |  | 2356733.87 | 2356733.87 | 1710547.94 | 1710547.94 |  | 512796.48 |  | 2356733.87 | 2356733.87 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1170/757662-DR4339PR-%20DSOW%20Group%2021%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List27SEPTEMBER2024 No ISOW in GP at this time | 46078.5875 | 45562.4224 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Ashleah Dingle |  |  | 280516.59 | 0 | 0.66926 | 2 |  | qwer426 | 757662 | 512796.48 |  | 512796.48 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
757700 | 108041 | FAASt [Automation Program Group 35] (Distribution) | 10F000920000, 10F000930000, 10F000910000 | PBUT04 - Distribution Automation | Grid Automation |  |  |  | FALSE |  | Current | FALSE | [12 empty] | 45562 | 09/27/2024 |  | 45727 | 46071 | 45845 | 45786 |  |  | 1023000 | 1023000 | 874476.72 | 147185.05 | 118838.8 | 1248914.59 | 85545.81 | 788930.91 | 2123391.31 | 2270576.36 |  |  | 45917 |  | 1318516 | 1318516 |  |  |  | 424560.64 |  | 1318516 | 1318516 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1171/757700-%20DR4339PR-%20DSOW%20Group%2035.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List30SEPTEMBER2024 - No ISOWs in GP | 46078.6686 | 45565.5184 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Marlina Crespo |  |  | 245359.86 | 0 | 0.48178 | 3 |  | qwer427 | 757700 | 121387.44 | 293400.96 | 414788.4 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
757699 | 108040 | FAASt [Automation Program Group 34] (Distribution) | 10F002870000, 10F002830000, 10F002860000, 10F002880000, 10F003870000 | PBUT04 - Distribution Automation | Grid Automation |  |  |  | FALSE |  | Current | FALSE | [12 empty] | 45562 | 09/27/2024 |  | 45727 | 45797 | 45933 | 45912 | 9/12/2025 - Field EHP: (CBRA) Consultation process initiated; drafting ongoing. Updated ECD 10/3/2025. |  | 561000 | 561000 | 0 | 462362.68 |  | 3439728.11 | 0 | 0 | 3439728.11 | 3902090.79 |  |  | 45966 |  | 2755938.99 | 2755938.99 |  |  |  | 683789.12 |  | 2755938.99 | 2755938.99 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1172/757699-%20DR4339PR-%20DSOW%20Group%2034.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List30SEPTEMBER2024 - No ISOWs in GP 8/7/2025 - Field EHP: In initial review. Expected Completion Date (ECD) 8/28/2025. 8/12/2025 7:47 AM AST - The PR Electric Power Authority, as the eligible entity (subrecipient), has submitted a consolidated plan for the use of the remaining budget available in the FEMA Accelerated Awards Strategy Project (136271) Fixed Cost Award. This FAASt sub-project has been identified in the list and it will be processed in the national workflow accordingly. | 46078.5885 | 45565.5193 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Ashleah Dingle |  |  | 462362.68 | 0 | 0.16309 | 5 |  | qwer428 | 757699 | 683789.12 |  | 683789.12 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
757698 | 108039 | FAASt [Automation Program Group 33] (Distribution) | 10F000860000, 10F000850000, 10F000840000 | PBUT04 - Distribution Automation | Grid Automation |  |  |  | FALSE |  | Current | FALSE | [12 empty] | 45562 | 09/27/2024 |  | 45727 | 45826 | 45845 | 45835 |  |  | 2226000 | 2226000 | 0 | 311582.64 |  | 2483045.65 | 0 | 0 | 2483045.65 | 2794628.29 |  |  | 45925 |  | 1888928.21 | 1888928.21 |  |  |  | 594117.44 |  | 1888928.21 | 1888928.21 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1173/757698-%20DR4339PR-%20DSOW%20Group%2033.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List30SEPTEMBER2024 - No ISOWs in GP | 46078.5885 | 45565.5207 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Ashleah Dingle |  |  | 311582.64 | 0 | 0.89648 | 1 |  | qwer429 | 757698 | 594117.44 |  | 594117.44 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
757697 | 108038 | FAASt [Automation Program Group 32] (Distribution) | 10F001290000, 10F001320000, 10F001310000, 10F001300000 | PBUT04 - Distribution Automation | Grid Automation |  |  |  | FALSE |  | Current | FALSE | [12 empty] | 45562 | 09/27/2024 |  | 45688 | 45842 | 45870 | 45849 |  |  | 798000 | 798000 | 0 | 339647.19 |  | 2663099.41 | 0 | 0 | 2663099.41 | 3002746.6 |  |  | 45925 |  | 1996678.58 | 1996678.58 |  |  |  | 666420.83 |  | 1996678.58 | 1996678.58 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1174/757697-DR4339PR-%20DSOW%20Group%2032%20-%20signed.pdf?web=1 | <div class="ExternalClass88C5F8DA8A014162A6AA0901E67F47D7"><div style="font-family&#58;Calibri, Arial, Helvetica, sans-serif;font-size&#58;11pt;color&#58;rgb(0, 0, 0);"><span style="font-family&#58;Calibri, Arial, Helvetica, sans-serif;background-color&#58;rgb(255, 255, 255);display&#58;inline !important;">7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List</span><br><p><br></p>30SEPTEMBER2024 - No ISOWs in GP</div></div> | 46078.5884 | 45565.5214 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Ashleah Dingle |  |  | 339647.19 | 0 | 0.29965 | 4 |  | qwer430 | 757697 | 666420.83 |  | 666420.83 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
757696 | 108037 | FAASt [Automation Program Group 31] (Distribution) | 10F000740000, 10F000770000 | PBUT04 - Distribution Automation | Grid Automation |  |  |  | FALSE |  | Current | FALSE | [12 empty] | 45562 | 09/27/2024 |  | 45688 | 46073 | 45828 | 45807 |  |  | 2085000 | 2085000 | 584984.03 | 87081.37 | 122168.23 | 1063128.97 | 44095.89 | 540888.14 | 1648113 | 1735194.37 |  |  | 45917 |  | 1145458 | 1145458 |  |  |  | 369544 |  | 1145458 | 1145458 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1175/757696-DR4339PR-%20DSOW%20Group%2031%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List30SEPTEMBER2024 - No ISOWs in GP | 46078.6805 | 45565.5221 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Marlina Crespo |  |  | 195175.66 | 0 | 1.2651 | 1 |  | qwer431 | 757696 | 119259.88 | 241210.12 | 360470 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
757694 | 108036 | FAASt [Automation Program Group 27] (Distribution) | 10F001260000, 10F001240000, 10F001250000, 10F001230000 | PBUT04 - Distribution Automation | Grid Automation |  |  |  | FALSE |  | Current | FALSE | [12 empty] | 45562 | 09/27/2024 |  | 45688 | 45797 | 45841 | 45839 |  |  | 2364000 | 2364000 | 0 | 419922.13 |  | 3292670.74 | 0 | 0 | 3292670.74 | 3712592.87 |  |  | 45925 |  | 2314733.78 | 2314733.78 |  |  |  | 977936.96 |  | 2314733.78 | 2314733.78 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1176/757694-%20DR4339-PR-%20DSOW-%20Group%2027%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List30SEPTEMBER2024 - No ISOWs in GP | 46078.5881 | 45565.5226 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Ashleah Dingle |  |  | 419922.13 | 0 | 0.71796 | 2 |  | qwer432 | 757694 | 977936.96 |  | 977936.96 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
757692 | 108035 | FAASt [Automation Program Group 26] (Distribution) | 10F000730000 | PBUT04 - Distribution Automation | Grid Automation |  |  |  | FALSE |  | Current | FALSE | [12 empty] | 45562 | 09/27/2024 |  | 45688 | 46080 | 45800 | 45786 |  |  | 1194000 | 1194000 | 605032.89 | 69331.28 | 82696.01 | 890118.26 | 43770.32 | 561262.57 | 1495151.15 | 1564482.43 |  |  | 45903 |  | 938783.63 | 938783.63 |  |  |  | 430336.48 |  | 938783.63 | 938783.63 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1177/PRJ_MultiVersionReport_757692_20250904.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List30SEPTEMBER2024 - No ISOWs in GP | 46085.5908 | 45565.523 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Marlina Crespo |  |  | 175325.33 | 0 | 0.79858 | 2 |  | qwer433 | 757692 | 169539 | 256947 | 426486 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
757689 | 108034 | FAASt [Automation Program Group 24] (Distribution) | 10F001210000, 10F001220000, 10F001200000 | PBUT04 - Distribution Automation | Grid Automation |  |  |  | FALSE |  | Current | FALSE | [12 empty] | 45562 | 09/27/2024 |  | 45688 | 46072 | 45800 | 45786 |  |  | 1836000 | 1836000 | 914277.86 | 141012.25 | 169799.83 | 1764051.9 | 68290.29 | 845987.57 | 2678329.76 | 2819342.01 |  |  | 45917 |  | 1774822 | 1774822 |  |  |  | 562828 |  | 1774822 | 1774822 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1178/757689-%20DR4339-PR-%20DSOW-%20Group%2024%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List30SEPTEMBER2024 - No ISOWs in GP | 46078.6753 | 45565.524 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Marlina Crespo |  |  | 299299.32 | 0 | 0.6855 | 2 |  | qwer434 | 757689 | 562828 |  | 562828 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
757687 | 108033 | FAASt [Automation Program Group 22] (Distribution) | 10F000700000, 10F000690000, 14F004700000, 10F000710000, 14F004720000 | PBUT04 - Distribution Automation | Grid Automation |  |  |  | FALSE |  | Current | FALSE | [12 empty] | 45562 | 09/27/2024 |  | 45688 | 45831 | 45869 | 45849 |  |  | 1671000 | 1671000 | 0 | 359230.44 |  | 2768746.03 | 0 | 0 | 2768746.03 | 3127976.47 |  |  | 45960 |  | 2356733.87 | 2356733.87 |  |  |  | 412012.16 |  | 2356733.87 | 2356733.87 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1179/FULL%20428%20757687-DR4339PR-%20DSOW%20Group%2022%20-%20signed.pdf?web=1 | 7/30/2024 - Updated Priority Projects List from Grid Strategy, added to Long List30SEPTEMBER2024 - No ISOWs in GP | 46078.5875 | 45565.5244 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Ashleah Dingle |  |  | 359230.44 | 0 | 0.60352 | 2 |  | qwer435 | 757687 | 412012.16 |  | 412012.16 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
757945 | 108042 | FAASt [Pole and Conductor Repair - Arecibo Group 3 - Phase 2] (Distribution) | 14F020460000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement |  |  |  | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | FALSE | [9 empty] | 45565 | 10/01/2024 |  | 45848 | [5 empty] | 8540000 | 8540000 | 15039.03 | 259116.51 |  | 2633472.99 | 1347.18 | 13691.85 | 2648512.02 | 2907628.53 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1180/ISOW%20Pole%20and%20Conductor%20-%20Arecibo%20Group%203%20-%20Phase%202%20..pdf?web=1 |  | 46078.5894 | 45566.3747 | Marlina Crespo | Distribution Pole & Conductor Replacement | Ashleah Dingle |  |  |  |  | 3.2245 | 1 | 45880 | qwer436 | 757945 | 251407.95 | 11885.35 | 263293.3 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
759051 | 108046 | FAASt Pole and Conductor - Bayamon Group 4 - Phase 2 (Distribution) | 14F021410000 | PBUT30 - D Pole & Conductor Repair | Distribution |  |  |  | TRUE | 45900 |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45573 | 10/11/2024 | [7 empty] | 3990000 | 3999999 | [5 empty] | 0 | 3990000 | 3990000 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1181/ISOW%20Pole%20and%20Conductor%20-%20Bayamon%20Group%204%20-%20Phase%202.pdf?web=1 |  | 46078.5894 | 45575.6402 | Marlina Crespo | Distribution Pole & Conductor Replacement | Ashleah Dingle |  |  |  |  | 1.0025 | 1 | 45880 | qwer437 | 759051 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
759004 | 108045 | FAASt [Pole and Conductor - Arecibo Group 4 - Phase 2] (Distribution) | 14F021390000 | PBUT30 - D Pole & Conductor Repair | Distribution |  |  |  | TRUE | 45900 |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45573 | 10/10/2024 | [7 empty] | 9280000 | 9280000 | [5 empty] | 0 | 9280000 | 9280000 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1182/ISOW%20Pole%20and%20Conductor%20-%20Arecibo%20Group%204%20-%20Phase%202.pdf?web=1 |  | 46078.5894 | 45575.6412 | Marlina Crespo | Distribution Pole & Conductor Replacement | Ashleah Dingle |  |  |  |  | 1 | 1 | 45880 | qwer438 | 759004 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
760568 | 108048 | FAASt [Distribution Feeder Rebuild # 1710-01] (Distribution) | 14F000170000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild |  |  |  | TRUE | 45900 |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45589 | 10/24/2024 | [7 empty] | 10467848 | 10467848 | [5 empty] | 0 | 10467848 | 10467848 | [11 empty] | 0 | 0 |  |  | 24October2024 - No ISOWs uploaded in GP at the moment. MC6/12/2025 - Project withdrawn in Grants Portal | 46078.5899 | 45593.5511 | Marlina Crespo | Distribution Feeders ‐ Bayamon Short Term Group 1 | Ashleah Dingle |  |  |  |  | 1 | 1 | 45820 | qwer439 | 760568 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
760571 | 108049 | FAASt [Distribution Feeder Rebuild # 1720-07] (Distribution) | 14F000220000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild |  |  |  | TRUE | 45869 |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45589 | 10/24/2024 | [7 empty] | 18005134 | 18005134 | [5 empty] | 0 | 18005134 | 18005134 | [11 empty] | 0 | 0 |  |  | 24October2024 - No ISOWs uploaded in GP at the moment. MC6/12/2025 - Project withdrawn in Grants Portal | 46078.5899 | 45593.553 | Marlina Crespo | Distribution Feeders ‐ Bayamon Short Term Group 1 | Ashleah Dingle |  |  |  |  | 1 | 1 | 45820 | qwer440 | 760571 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
760575 | 108050 | FAASt [Distribution Feeder Rebuild # 1716-03] (Distribution) | 14F000190000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild |  |  |  | TRUE | 45900 |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45589 | 10/24/2024 | [7 empty] | 18102407 | 18102407 | [5 empty] | 0 | 18102407 | 18102407 | [11 empty] | 0 | 0 |  |  | 24October2024 - No ISOWs uploaded in GP at the moment. MC6/12/2025 - Project withdrawn in Grants Portal | 46078.59 | 45593.5541 | Marlina Crespo | Distribution Feeders ‐ Bayamon Short Term Group 1 | Ashleah Dingle |  |  |  |  | 1 | 1 | 45820 | qwer441 | 760575 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
760577 | 108051 | FAASt [Distribution Feeder Rebuild # 1718-02] (Distribution) | 14F000210000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild |  |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45589 | 10/24/2024 | [7 empty] | 8421396 | 8421396 | [5 empty] | 0 | 8421396 | 8421396 | [11 empty] | 0 | 0 |  |  | 24October2024 - No ISOWs uploaded in GP at the moment. MC6/12/2025 - Project withdrawn in Grants Portal | 46078.5901 | 45593.5551 | Marlina Crespo | Distribution Feeders ‐ Bayamon Short Term Group 1 | Ashleah Dingle |  |  |  |  | 1 | 1 | 45820 | qwer442 | 760577 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
760579 | 108052 | FAASt [Distribution Feeder Rebuild # 1717-03] (Distribution) | 14F000200000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild |  |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45589 | 10/24/2024 | [7 empty] | 14143466 | 14143466 | [5 empty] | 0 | 14143466 | 14143466 | [11 empty] | 0 | 0 |  |  | 24October2024 - No ISOWs uploaded in GP at the moment. MC6/12/2025 - Project withdrawn in Grants Portal | 46078.5901 | 45593.5563 | Marlina Crespo | Distribution Feeders ‐ Bayamon Short Term Group 1 | Ashleah Dingle |  |  |  |  | 1 | 1 | 45820 | qwer443 | 760579 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
764709 | 108060 | FAASt [Distribution Feeder Rebuild # 1204-05] (Distribution) | 14F001470000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild |  |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45600 | 11/04/2024 | [7 empty] | 8740820.93 | 8740820.93 | [5 empty] | 0 | 8740820.93 | 8740820.93 | [11 empty] | 0 | 0 |  |  | 04NOVEMBER2024 No ISOW submitted into GP - MC 6/12/2025 - Project withdrawn in Grants Portal | 46078.5911 | 45600.4252 | Marlina Crespo | Distribution Feeders ‐ San Juan Short Term Group 1 | Ashleah Dingle |  |  |  |  | 1 | 1 | 45820 | qwer444 | 764709 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
764708 | 108059 | FAASt [Distribution Feeder Rebuild # 5602-02] (Distribution) | 14F001360000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild |  |  |  | TRUE | 45930 |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 40610000 | 44385 | 44428 |  | 44415 |  |  |  | 45600 | 11/04/2024 | [7 empty] | 5190387.52 | 5190387.52 | [5 empty] | 0 | 5190387.52 | 5190387.52 | [11 empty] | 0 | 0 |  |  | 04NOVEMBER2024 No ISOW submitted into GP - MC 6/12/2025 - Project withdrawn in Grants Portal | 46078.591 | 45600.426 | Marlina Crespo | Distribution Feeders ‐ Ponce Short Term Group 1 | Ashleah Dingle |  |  |  |  | 1 | 1 | 45820 | qwer445 | 764708 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
764707 | 108058 | FAASt [Distribution Feeder Rebuild # 6012-02] (Distribution) | 14F000970000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild |  |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 45600 | 11/04/2024 | [7 empty] | 5540622.64 | 5540622.64 | [5 empty] | 0 | 5540622.64 | 5540622.64 | [11 empty] | 0 | 0 |  |  | 04NOVEMBER2024 No ISOW submitted into GP - MC 6/12/2025 - Project withdrawn in Grants Portal | 46078.591 | 45600.4264 | Marlina Crespo | Distribution Feeders ‐ Mayaguez Short Term Group 1 | Ashleah Dingle |  |  |  |  | 1 | 1 | 45820 | qwer446 | 764707 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
764706 | 108057 | FAASt [Distribution Feeder Rebuild # 7011-03] (Distribution) | 14F001000000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild |  |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45600 | 11/04/2024 | [7 empty] | 9329781.4 | 9329781.4 | [5 empty] | 0 | 9329781.4 | 9329781.4 | [11 empty] | 0 | 0 |  |  | 04NOVEMBER2024 No ISOW submitted into GP - MC 6/12/2025 - Project withdrawn in Grants Portal | 46078.591 | 45600.4267 | Marlina Crespo | Distribution Feeders ‐ Mayaguez Short Term Group 1 | Ashleah Dingle |  |  |  |  | 1 | 1 | 45820 | qwer447 | 764706 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
764705 | 108056 | FAASt [Distribution Feeder Rebuild # 6014-02] (Distribution) | 14F000980000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild |  |  |  | TRUE | 45900 |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | TRUE | [9 empty] | 45600 | 11/04/2024 | [7 empty] | 13387462.29 | 13387462.29 | [5 empty] | 0 | 13387462.29 | 13387462.29 | [11 empty] | 0 | 0 |  |  | 04NOVEMBER2024 No ISOW submitted into GP - MC 6/12/2025 - Project withdrawn in Grants Portal | 46078.591 | 45600.4271 | Marlina Crespo | Distribution Feeders ‐ Mayaguez Short Term Group 1 | Ashleah Dingle |  |  |  |  | 1 | 1 | 45820 | qwer448 | 764705 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
761563 | 108055 | FAASt [San Jose Relocation] (Substation) | 14F001920000 | PBUT08 - Substation Rebuilds | Substation |  |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued |  |  | 17000000 | 44473 | 44487 |  | 44503 |  |  |  | 45597 | 11/01/2024 | [7 empty] | 17000000 | 17000000 | [5 empty] | 0 | 17000000 | 17000000 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1195/761563-DR4339PR-EN-SOW-0001_Rev0%20-%20San%20Jose%20Relocation.pdf?web=1 |  | 46078.5908 | 45600.4279 | Marlina Crespo | San Jose Relocation | Ashleah Dingle |  |  |  |  | 1 | 1 | 45888 | qwer449 | 761563 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
767139 | 108064 | FAASt [Distribution Feeder Rebuild # 2906-02] (Distribution) | 14F000510000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild |  |  |  | TRUE | 45869 |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45617 | 11/21/2024 | [7 empty] | 3205041 | 3205041 | [5 empty] | 0 | 3205041 | 3205041 | [11 empty] | 0 | 0 |  |  | 22November2024 No ISOW Docs in Grants Portal - MC 6/12/2025 - Project withdrawn in Grants Portal | 46078.5914 | 45618.6276 | Marlina Crespo | Distribution Feeders ‐ Caguas Short Term Group 1 | Ashleah Dingle |  |  |  |  | 1 | 1 | 45820 | qwer450 | 767139 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | Guanica - Phase I |  |  | Substation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7719 | 45637.6238 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer451 | FAASt Number Pending 400947 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | Caguas – Phase I |  |  | Substation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7719 | 45637.6277 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer452 | FAASt Number Pending 400948 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | Hato Rey – Phase I |  |  | Substation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7719 | 45637.6282 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer453 | FAASt Number Pending 400949 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | Mora – Phase I (Substation) |  |  | Substation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7719 | 45637.6286 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer454 | FAASt Number Pending 400950 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | San Jose (Utuado) – Phase I |  |  | Substation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7719 | 45637.629 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer455 | FAASt Number Pending 400951 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | Arecibo – Phase I |  |  | Substation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7719 | 45637.6297 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer456 | FAASt Number Pending 400952 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | Pompanos – Phase I |  |  | Substation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7719 | 45637.6299 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer457 | FAASt Number Pending 400953 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | Canas TC – Phase I |  |  | Substation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7719 | 45637.6302 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer458 | FAASt Number Pending 400954 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | Fonalledas – Phase I |  |  | Substation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7719 | 45637.6304 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer459 | FAASt Number Pending 400955 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | Naguabo – Phase I |  |  | Substation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7719 | 45637.6306 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer460 | FAASt Number Pending 400956 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | Fajardo 2002 – Veve Calzada – Phase |  |  | Substation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7719 | 45637.6307 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer461 | FAASt Number Pending 400957 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | Factor – Phase I |  |  | Substation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7719 | 45637.6312 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer462 | FAASt Number Pending 400958 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | FAASt Salinas TC to Jobos TC – 38kV 100 & 200 (Transmission) |  |  | Transmission |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7719 | 45637.6316 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer463 | FAASt Number Pending 400959 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
811923 | 108100 | FAASt [Transmission Priority Pole Replacement Program Line 16500 Fajardo TC-Dos Marinas] (Transmission) | 14F020570000 | PBUT13 - T Priority Pole Repl | Transmission – Pole Replacement |  | TRUE |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45705 | 02/18/2025 |  | 45705 | 45876 |  |  |  |  | 28863.82 | 28863.82 | 22761.43 | 53616.55 |  | 206622.43 | 4687.63 | 18073.8 | 229383.86 | 283000.41 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1212/811923-DR4339PR-Detailed%20SOW-T-Pole%20TL16500%20Fajardo%20TC-Dos%20Marinas%20Rev1_signed.pdf?web=1 |  | 46078.5972 | 45637.6332 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 0.12583 | 5 | 45887 | qwer464 | 811923960 | 11021.7 | 3868.3 | 14890 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
811913 | 108099 | FAASt [Transmission Priority Pole Replacement Program Line 9600 Bayamon TC – Catano Sect] (Transmission) | 14F020510000 | PBUT13 - T Priority Pole Repl | Transmission – Pole Replacement |  | TRUE |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45705 | 02/18/2025 |  | 45705 | 45876 |  |  |  |  | 335555.06 | 335555.06 | 43773.6 | 64330 |  | 355873.89 | 6697.9 | 37075.7 | 399647.49 | 463977.49 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1213/136271-DR4339PR-Detailed%20SOW-T-Pole%20TL9600%20Bayamon%20TC%20%E2%80%93%20Catano%20Sect_Rev.0_2-17-2025.pdf?web=1 |  | 46078.5972 | 45637.6345 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 0.83963 | 1 | 45887 | qwer465 | 811913961 | 83732.55 | 5802.45 | 89535 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | TL1500 Once De Agosto Sect - Sabana Grande TO |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7719 | 45637.6349 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer466 | FAASt Number Pending 400962 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | TL 1200 San German Sect-San German TC - Yauco 2HP |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7719 | 45637.6367 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer467 | FAASt Number Pending 400963 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | TL 1600 Leon Sect - Acacias TC |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7719 | 45637.6369 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer468 | FAASt Number Pending 400964 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | TL 6900 - Mirador Azul Sect-Hatillo TO |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7719 | 45637.637 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer469 | FAASt Number Pending 400965 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | TL 6700 - Seboruco To-Tapia TO |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7719 | 45637.6373 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer470 | FAASt Number Pending 400966 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | TL 200 Ponce TC -Santa Isabel Sect |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7719 | 45637.6374 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer471 | FAASt Number Pending 400967 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | TL 4800 Santa Isabel TC - Santa Isabel Sect |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7719 | 45637.638 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer472 | FAASt Number Pending 400968 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
805521 | 108093 | FAASt [38kV Recloser TL 7800 Dorado TC to Vega Alta Sect.] (Transmission) | 14F019130000 | PBUT04 - Distribution Automation | Transmission – Pole Replacement |  |  | Improved | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45645 | 01/21/2025 |  | 45695 | 45853 | 45742 | 45733 |  |  | 2980000 | 2980000 | 725071.07 | 32294 |  | 252749.08 | 82142.46 | 642928.61 | 977820.15 | 1010114.15 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1221/805521-%20DR4339-PR-%20DSOW-%2038kV%20Reclosers%20TL%207800%20-%20FY25%20Revision%20000_Signed.pdf?web=1 | 22JANUARY2025 No ISOW in Grants Portal - MC | 46078.5963 | 45637.6383 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 3.0476 | 1 | 45887 | qwer473 | 969 | 9182.3 | 97016.62 | 106198.92 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | TL 7500 - Tres Monjitas Sect-Puerto Nuevo TO |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7719 | 45637.6384 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer474 | FAASt Number Pending 400970 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | TL 10700 - Hato Tejas Tc-Hato Tejas Sect |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7719 | 45637.6385 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer475 | FAASt Number Pending 400971 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | TL 2400 - Dos Bocas Hp-Caonillas 2 Hp |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7719 | 45637.6391 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer476 | FAASt Number Pending 400972 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | TL 10500-Chardon Sect-Las Monjas TO |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7719 | 45637.6392 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer477 | FAASt Number Pending 400973 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | TL 14100 Barceloneta C-Merck |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7719 | 45637.6395 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer478 | FAASt Number Pending 400974 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | TL 6000 - Aguadilla Hospital Distrito To-T-Bone TO |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7719 | 45637.6398 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer479 | FAASt Number Pending 400975 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | TL 18400 - Barranquitas Tc-El Abanico |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7719 | 45637.64 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer480 | FAASt Number Pending 400976 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | TL 2200 -Barceloneta TC-Manati TC |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7719 | 45637.6401 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer481 | FAASt Number Pending 400977 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | TL 2200 - Vega Baja TC-Vega Alta Sec |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.772 | 45637.6402 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer482 | FAASt Number Pending 400978 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | TL 9200 - Añasco TC-Añasco |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.772 | 45637.6407 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer483 | FAASt Number Pending 400979 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | TL 3500 Cachete Sect - Caparra Sect |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.772 | 45637.6407 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer484 | FAASt Number Pending 400980 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | TL 9900 - Rio Blanco Hp-Humacao Sec |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.772 | 45637.6412 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer485 | FAASt Number Pending 400981 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | TL 8100 - Yauco 1 Hp-Adjuntas TO |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.772 | 45637.6414 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer486 | FAASt Number Pending 400982 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | TL 1600 - San German Sect-San German Tc |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.772 | 45637.6418 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer487 | FAASt Number Pending 400983 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | TL 1600 - San German Tc-Yauco 1 Hp |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.772 | 45637.6418 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer488 | FAASt Number Pending 400984 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | TL 2800 - Aguadilla Hospital Distrito Sect-T-Bone TO |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.772 | 45637.6424 | Marlina Crespo | Line 2800 Aguadilla Hospital Distrito Sect to T-Bone TO | Rey Roldan Rodríguez | [7 empty] | qwer489 | FAASt Number Pending 400985 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | TL 300 - Juana Diaz Tc-La Rambla Sect |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.772 | 45637.6424 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer490 | FAASt Number Pending 400986 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | TL 300 - Toro Negro 1 Hp-Juana Diaz TC |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.772 | 45637.6424 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer491 | FAASt Number Pending 400987 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | TL 3200 - Viaducto Tc-Martin Peña TC |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.772 | 45637.643 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer492 | FAASt Number Pending 400988 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | TL 3200 Hato Rey -Baldrich Sect |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.772 | 45637.6432 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer493 | FAASt Number Pending 400989 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | TL 36800 Canovanas TC - Palmer TC |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.772 | 45637.6436 | Marlina Crespo | FAASt Canovanas TC to Sabana Llana TC - 36800 (Transmission) FAASt Canovanas TC to Palmer-Fajardo TC - 36800 (Transmission) | Rey Roldan Rodríguez | [7 empty] | qwer494 | FAASt Number Pending 400990 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | TL 6100 Mayaguez GP - Radial |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.772 | 45637.6446 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer495 | FAASt Number Pending 400991 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | FAASt [Automation Program Group 3B- 8 Feeders] (Distribution) |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.772 | 45637.6739 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer496 | FAASt Number Pending 400992 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | FAASt [Automation Program Group 3C- 7 Feeders] (Distribution) |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.772 | 45637.6739 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer497 | FAASt Number Pending 400993 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | FAASt [Automation Program Group 3D- 6 Feeders] (Distribution) |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.772 | 45637.675 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer498 | FAASt Number Pending 400994 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | FAASt [Automation Program Group 3E- 9 Feeders] (Distribution) |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.772 | 45637.675 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer499 | FAASt Number Pending 400995 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | FAASt [Automation Program Group 2B-8 Feeders] (Distribution) |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.772 | 45637.6755 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer500 | FAASt Number Pending 400996 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | FAASt [Automation Program Group 2C-10 Feeders] (Distribution) |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.772 | 45637.6755 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer501 | FAASt Number Pending 400997 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | FAASt [Automation Program Group 2D-8 Feeders] (Distribution) |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.772 | 45637.6757 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer502 | FAASt Number Pending 400998 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | FAASt [Automation Program Group 2E-9 Feeders] (Distribution) |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.772 | 45637.6758 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | qwer503 | FAASt Number Pending 400999 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | [Automation Program Group 36](Distribution) |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.772 | 45637.6769 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Rey Roldan Rodríguez | [7 empty] | qwer504 | FAASt Number Pending 4001000 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | [Automation Program Group 37](Distribution) |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7744 | 45637.6769 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 400RFI1001 | FAASt Number Pending 4001001 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | [Automation Program Group 38](Distribution) |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7744 | 45637.6769 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 400RFI1002 | FAASt Number Pending 4001002 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | [Automation Program Group 39] (Distribution) |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7744 | 45637.6769 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 400RFI1003 | FAASt Number Pending 4001003 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | [Automation Program Group 40] (Distribution) |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7744 | 45637.6769 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 400RFI1004 | FAASt Number Pending 4001004 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
801432 | 108085 | FAASt [Automation Program Group 41] (Distribution) | 10F002350000, 10F002360000, 10F002330000 | PBUT04 - Distribution Automation | Grid Automation |  |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45667 | 1/10/2025 | [7 empty] | 2391000 | 2391000 | [5 empty] | 0 | 2391000 | 2391000 | [11 empty] | 0 | 0 |  |  | 14JANUARY2025 No ISOW in Grants Portal - MC | 46078.5945 | 45637.678 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Ashleah Dingle |  |  |  |  | 1 | 1 | 45888 | 801432RFI1005 | 801432 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
801437 | 108086 | FAASt [Automation Program Group 42] (Distribution) | 10F002110000, 10F002440000, 10F002370000, 10F002390000 | PBUT04 - Distribution Automation | Grid Automation |  |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45667 | 1/10/2025 | [7 empty] | 2883000 | 2883000 | [5 empty] | 0 | 2883000 | 2883000 | [11 empty] | 0 | 0 |  |  | 14JANUARY2025 No ISOW in Grants Portal - MC | 46078.5947 | 45637.678 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Ashleah Dingle |  |  |  |  | 1 | 1 | 45888 | 801437RFI1006 | 801437 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
801438 | 108087 | FAASt [Automation Program Group 43] (Distribution) | 10F003450000, 10F003110000, 10F003440000 | PBUT04 - Distribution Automation | Grid Automation |  |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45667 | 1/10/2025 | [7 empty] | 2490000 | 2490000 | [5 empty] | 0 | 2490000 | 2490000 | [11 empty] | 0 | 0 |  |  | 14JANUARY2025 No ISOW in Grants Portal - MC | 46078.5947 | 45637.678 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Ashleah Dingle |  |  |  |  | 1 | 1 | 45888 | 801438RFI1007 | 801438 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
801440 | 108088 | FAASt [Automation Program Group 44] (Distribution) | 10F002610000, 10F002630000, 10F002580000, 10F002600000 | PBUT04 - Distribution Automation | Grid Automation |  |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45667 | 1/10/2025 | [7 empty] | 3902000 | 3902000 | [5 empty] | 0 | 3902000 | 3902000 | [11 empty] | 0 | 0 |  |  | 14JANUARY2025 No ISOW in Grants Portal - MC | 46078.5948 | 45637.678 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Ashleah Dingle |  |  |  |  | 1 | 1 | 45888 | 801440RFI1008 | 801440 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
801441 | 108089 | FAASt [Automation Program Group 45] (Distribution | 10F001480000, 10F001490000, 10F001470000 | PBUT04 - Distribution Automation | Grid Automation |  |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45667 | 1/10/2025 | [7 empty] | 2400000 | 2400000 | [5 empty] | 0 | 2400000 | 2400000 | [11 empty] | 0 | 0 |  |  | 14JANUARY2025 No ISOW in Grants Portal - MC | 46078.5948 | 45637.678 | Marlina Crespo | Transmission and Distribution Automation Program Installation of Reclosers, Single Phase Reclosers and Fault Current Indicators | Ashleah Dingle |  |  |  |  | 1 | 1 | 45888 | 801441RFI1009 | 801441 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | 38 kV Reclosers TLine 1900 |  |  | Grid Automation – 38 kV Reclosers |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7744 | 45637.6804 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 400RFI1010 | FAASt Number Pending 4001010 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | 38 kV Reclosers Transmission TLine 2100 |  |  | Grid Automation – 38 kV Reclosers |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7744 | 45637.6804 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 400RFI1011 | FAASt Number Pending 4001011 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | 38 kV Reclosers TLine 3000 |  |  | Grid Automation – 38 kV Reclosers |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7744 | 45637.6804 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 400RFI1012 | FAASt Number Pending 4001012 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | 38 kV Reclosers TLine 7800 |  |  | Grid Automation – 38 kV Reclosers |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7744 | 45637.6804 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 400RFI1013 | FAASt Number Pending 4001013 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | 38 kV Reclosers TLine 1500 |  |  | Grid Automation – 38 kV Reclosers |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7744 | 45637.6812 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 400RFI1014 | FAASt Number Pending 4001014 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | 38 kV Reclosers TLine 5600 |  |  | Grid Automation – 38 kV Reclosers |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7744 | 45637.6816 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 400RFI1015 | FAASt Number Pending 4001015 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | 38 kV Reclosers TLine 6500 |  |  | Grid Automation – 38 kV Reclosers |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7744 | 45637.6816 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 400RFI1016 | FAASt Number Pending 4001016 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | 38 kV Reclosers TLine 8100 |  |  | Grid Automation – 38 kV Reclosers |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7744 | 45637.6816 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 400RFI1017 | FAASt Number Pending 4001017 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | 38 kV Reclosers TLine 800 |  |  | Grid Automation – 38 kV Reclosers |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7744 | 45637.6828 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 400RFI1018 | FAASt Number Pending 4001018 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | 38kV Reclosers TLine 12600 |  |  | Grid Automation – 38 kV Reclosers |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7744 | 45637.6828 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 400RFI1019 | FAASt Number Pending 4001019 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | 38kV Reclosers TLine 13400 |  |  | Grid Automation – 38 kV Reclosers |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7744 | 45637.6828 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 400RFI1020 | FAASt Number Pending 4001020 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | 38kV Reclosers TLine 1600 |  |  | Grid Automation – 38 kV Reclosers |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7744 | 45637.6844 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 400RFI1021 | FAASt Number Pending 4001021 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | 38kV Reclosers TLine 2000 |  |  | Grid Automation – 38 kV Reclosers |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7744 | 45637.6844 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 400RFI1022 | FAASt Number Pending 4001022 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | 38kV Reclosers TLine 3700 |  |  | Grid Automation – 38 kV Reclosers |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7744 | 45637.6844 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 400RFI1023 | FAASt Number Pending 4001023 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | 38kV Reclosers TLine 4800 |  |  | Grid Automation – 38 kV Reclosers |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7744 | 45637.6844 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 400RFI1024 | FAASt Number Pending 4001024 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
798275 | 108075 | FAASt [Distribution Feeder Rebuild # 1620-02] (Distribution) | 14F001600000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild |  |  | Restoration | FALSE |  | Current | FALSE | [12 empty] | 45637 | 12/11/2024 |  | 45672 | 45771 | 45793 | 45782 |  |  | 6925970.19 | 6925970.19 | 0 | 954420.68 |  | 7464273.83 | 0 | 0 | 7464273.83 | 8418694.51 |  |  | 45917 |  | 6711421 | 6711421 |  |  |  | 752852.93 |  | 6711421 | 6711421 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1277/798275-DR4339PR-Feeders%20Rebuild%201620-02-DSOW%20Rev.%200.pdf?web=1 | 12DECEMBER2024 No ISOWs in GP at this time MC | 46078.5926 | 45637.6883 | Marlina Crespo | Distribution Feeders - San Juan Short Term Group 3 | Ashleah Dingle |  |  | 954420.68 | 0 | 0.92788 | 1 |  | 798275RFI1025 | 798275 | 752852.93 |  | 752852.93 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | FAASt [Distribution Feeder Rebuild # 8101-03] (Distribution) |  |  | Distribution – Feeder Rebuild |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7744 | 45637.6883 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 400RFI1026 | FAASt Number Pending 4001026 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
801172 | 108083 | FAASt [Distribution Feeder Rebuild # 1529-15] (Distribution) | 14F001540000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild |  |  |  | FALSE |  | Current | FALSE | [12 empty] | 45665 | 1/8/2025 |  | 45688 | 46071 | 45813 | 45811 |  |  | 7155677 | 7155677 | 101241.03 | 568090.34 | 160515.06 | 2023253.43 | 22194.71 | 79046.32 | 2124494.46 | 2692584.8 |  |  | 45917 |  | 2285961 | 2285961 |  |  |  | 243286.39 |  | 2285961 | 2285961 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1279/801172-DR4339PR-Detailed%20Scope%20of%20Work-Rev.%201.pdf?web=1 | 14JANUARY2025 No ISOW in Grants Portal - MC | 46078.671 | 45637.6897 | Marlina Crespo |  | Marlina Crespo |  |  | 508777.01 | 0 | 3.3682 | 1 |  | 801172RFI1027 | 801172 | 243286.39 |  | 243286.39 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
801166 | 108082 | FAASt [Distribution Feeder Rebuild # 6601-03] (Distribution) | 14F001150000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild |  |  |  | FALSE |  | Current | FALSE | [12 empty] | 45665 | 1/8/2025 |  | 45754 | 45937 | 46008 | 45993 | 12/2/2025 - Field EHP-Historic: SHPO response letter received on 12/02/2025. Under review by EHP Specialist. ECD: 12/17/2025 |  | 9010977 | 9010977 | 0 | 1724565.72 |  | 21962621.6 | 0 | 0 | 21962621.6 | 23687187.32 |  |  | 46030 |  | 19826783.47 | 19826783.47 |  |  |  | 2135838.13 |  | 19826783.47 | 19826783.47 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1280/801166-DR4339PR-Distribution%20Feeder%20Rebuild%206601-03-Detailed%20Scope%20of%20Work%20Rev.0.pdf?web=1 | 14JANUARY2025 No ISOW in Grants Portal - MC 8/13/2025 - Field EHP: EHP Formal Request for Information Initiated on 08/13/2025. EHP is requesting additional information for the subject project. This RFI is needed for Completeness and Compliance. To determine compliance, the following information should be provided no later than 15 days from the date of this request. | 46078.5941 | 45637.6897 | Marlina Crespo |  | Ashleah Dingle |  |  | 1724565.72 | 0 | 0.41029 | 3 |  | 801166RFI1028 | 801166 | 2135838.13 | 0 | 2135838.13 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | FAASt [Distribution Feeder Rebuild #6603-01] |  |  | Distribution – Feeder Rebuild |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7744 | 45637.6903 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 400RFI1029 | FAASt Number Pending 4001029 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
812569 | 108102 | FAASt [Distribution Feeder Rebuild 3502-02] | 14F000490000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild |  |  |  | FALSE |  | Current | FALSE | [12 empty] | 45708 | 02/20/2025 |  | 45735 | 45821 | 45867 | 45860 |  |  | 15430988 | 15430988 | 0 | 1403642.18 |  | 10978061.1 | 0 | 0 | 10978061.1 | 12381703.28 |  |  | 45925 |  | 10217566.54 | 10217566.54 |  |  |  | 760494.56 |  | 10217566.54 | 10217566.54 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1282/812569-DR4339PR-Feeder%20Rebuild%203502-02-Detailed%20Scope%20of%20Work.%20Rev.%200.pdf?web=1 | 21FEBRUARY2025 No ISOWs in GP at this time - MC | 46078.5977 | 45637.6903 | Marlina Crespo |  | Ashleah Dingle |  |  | 1403642.18 | 0 | 1.4056 | 1 |  | 812569RFI1030 | 812569 | 760494.56 |  | 760494.56 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | FAASt [Distribution Feeder Rebuild #1303-02 |  |  | Distribution – Feeder Rebuild |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7744 | 45637.6903 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 400RFI1031 | FAASt Number Pending 4001031 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | FAASt [Distribution Feeder Rebuild #-1718-02 |  |  | Distribution – Feeder Rebuild |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7744 | 45637.6912 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 400RFI1032 | FAASt Number Pending 4001032 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | FAASt [Distribution Feeder Rebuild #1303-05] |  |  | Distribution – Feeder Rebuild |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7744 | 45637.6914 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 400RFI1033 | FAASt Number Pending 4001033 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | FAASt [Distribution Feeder Rebuild # 6406-02] (Distribution) |  |  | Distribution – Feeder Rebuild |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7744 | 45638.6025 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 400RFI1034 | FAASt Number Pending 4001034 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 400 |  | FAASt [Distribution Feeder Rebuild # 6802-04] (Distribution) |  |  | Distribution – Feeder Rebuild |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7744 | 45638.6025 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 400RFI1035 | FAASt Number Pending 4001035 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
806935 | 108097 | FAASt [Pole and Conductor Repair - Caguas Group 6 - Phase 2] (Distribution) | 14F018900000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement |  |  |  | TRUE | 45869 | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45685 | 01/28/2025 | [7 empty] | 6120000 | 6120000 | [5 empty] | 0 | 6120000 | 6120000 | [11 empty] | 0 | 0 |  |  | 28JANUARY2025 No ISOW docs in Grants Portal - MC | 46078.5968 | 45638.6039 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 1 | 1 | 45880 | 806935RFI1036 | 806935 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
806936 | 108098 | FAASt [Pole and Conductor Repair - Carolina Group 3 - Phase 2] (Distribution) | 14F018950000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement |  |  |  | TRUE | 45869 | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45685 | 01/28/2025 | [7 empty] | 5100000 | 5100000 | [5 empty] | 0 | 5100000 | 5100000 | [11 empty] | 0 | 0 |  |  | 28JANUARY2025 No ISOW docs in Grants Portal - MC | 46078.5969 | 45638.6039 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 1 | 1 | 45880 | 806936RFI1037 | 806936 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
805519 | 108092 | FAASt [38kV Recloser TL 1900 Dos Bocas HP to San Sebastian TC] (Transmission) | 14F019110000 | PBUT04 - Distribution Automation | Transmission |  |  |  | TRUE | 45869 |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | FALSE | [9 empty] | 45645 | 01/21/2025 |  | 45720 | 45873 |  |  |  |  | 3180000 | 3180000 | 769393.29 | 69012.67 |  | 639395.34 | 74943.63 | 694449.66 | 1408788.63 | 1477801.3 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1299/805519%20-%20DR4339-PR-%20DSOW-%2038kV%20Reclosers%20TL%201900%20Dos%20Bocas%20HP%20to%20San%20Sebastian%20TC%20Rev0%203.4.2025.pdf?web=1 | 22JANUARY2025 No ISOW in Grants Portal - MC | 46078.5963 | 45679.4875 | Marlina Crespo | Line 1900 Dos Bocas HP to San Sebastian TC | Ashleah Dingle |  |  |  |  | 2.2573 | 1 | 45887 | 805519RFI1038 | 805519 | 31058.62 | 70900.38 | 101959 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
805517 | 108091 | FAASt [38kV Recloser TL 2100 Hatillo TC to Quebradillas Sect.] (Transmission) | 14F019120000 | PBUT04 - Distribution Automation | Transmission |  |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45645 | 01/21/2025 |  | 45720 | 45873 |  |  |  |  | 2990000 | 2990000 | 733123.39 | 47826.67 |  | 414584.72 | 75820.29 | 657303.1 | 1147708.11 | 1195534.78 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1300/805517%20-%20DR4339-PR-%20DSOW-%2038kV%20Reclosers%20TL%202100%20Hatillo%20TC%20to%20Quebradillas%20Sect.%20Rev0%203.4.2025.pdf?web=1 | 22JANUARY2025 No ISOW in Grants Portal - MC | 46078.5961 | 45679.4893 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 2.6052 | 1 | 45887 | 805517RFI1039 | 805517 | 4111.54 | 68433.46 | 72545 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
805513 | 108090 | FAASt [38kV Recloser TL 3000 Monacillos TC to Bairoa TO] (Transmission) | 14F019230000 |  | Transmission |  |  |  | TRUE | 45869 |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45645 | 01/21/2025 | [7 empty] | 3250000 | 3250000 | [5 empty] | 0 | 3250000 | 3250000 | [11 empty] | 0 | 0 |  |  | Deleted from Grants Portal on 23JUN2025 - AND 22JANUARY2025 No ISOW in Grants Portal - MC | 45880.3892 | 45679.4897 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 1 | 1 | 45820 | 805513RFI1040 | 805513 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 401 |  | System Stabilization Plan Monacillos TC, Sabana Llana TC & Costa Sur TC |  |  | Substation |  |  |  | FALSE |  |  | FALSE |  |  |  | 45674 |  | 45680 | 45694 |  | 45710 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7744 | 45680.5713 | Jeremy Malone |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 401RFI1041 | FAASt Number Pending 401 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
790427 | 108069 | FAASt [Pole and Conductor Repair -Caguas Group 5 Phase 2 (Distribution) | 14F018890000 | PBUT30 - D Pole & Conductor Repair | Distribution |  |  |  | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45621 | 11/25/2024 |  | 45848 | [5 empty] | 5100000 | 5100000 | 71738.97 | 1002538.6 |  | 8239298.14 | 7782.12 | 63956.85 | 8311037.11 | 9313575.71 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1305/790427-DR4339PR-Detailed%20SOW%20Caguas%20Group%205%20-%20Phase%202%20Rev0%20428%20&%20406-1.pdf?web=1 |  | 46078.592 | 45693.8593 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 0.61364 | 2 | 45880 | 790427RFI1042 | 790427 | 781861.25 | 57239.39 | 839100.64 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
790443 | 108070 | FAASt [Pole and Conductor Repair -San Juan Group 3 Phase 2 (Distribution) | 14F019030000 | PBUT30 - D Pole & Conductor Repair | Distribution |  |  |  | FALSE |  | Current | FALSE | [12 empty] | 45621 | 4/2/2025 |  | 45744 | 46045 | 46070 | 46059 | 2/3/2026 - Field EHP: In initial review, ECD: 2/17/2026 |  | 5100000 | 5100000 | 7501.66 | 21435.45 | 14432.64 | 258265.86 | 574.91 | 6926.75 | 265767.52 | 287202.97 |  |  | 45903 |  | 186697 | 186697 |  |  |  | 35624 |  | 186697 | 186697 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1306/PRJ_MultiVersionReport_790443_20250904.pdf?web=1 |  | 46078.592 | 45693.861 | Marlina Crespo |  | Ashleah Dingle |  |  | 25985 | 0 | 19.1897 | 1 |  | 790443RFI1043 | 790443 | 14432.64 | 6007.36 | 20440 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
790446 | 108071 | FAASt [Pole and Conductor Repair -Caguas Group 4 Phase 2 (Distribution) | 14F018880000 | PBUT30 - D Pole & Conductor Repair | Distribution |  |  |  | FALSE |  | Past | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | FALSE | [9 empty] | 45621 | 11/25/2024 |  | 45848 | [5 empty] | 5100000 | 5100000 | 28582.12 | 523611.41 |  | 4138909.89 | 3209.84 | 25372.28 | 4167492.01 | 4691103.42 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1307/790446-DR4339PR-DPoles-Caguas%20Group%204%20-%20Phase%202-ISOW.pdf?web=1 |  | 46078.5921 | 45693.8636 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 1.2238 | 1 | 45880 | 790446RFI1044 | 790446 | 382663.75 | 15948.73 | 398612.48 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Pending |  | Substation System Improvement Plan |  |  | Substation |  |  |  | FALSE |  |  | FALSE |  |  |  | 45707 |  | 45709 | 45740 |  | 45739 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7744 | 45709.3927 | Jeremy Malone |  | Rey Roldan Rodríguez | [7 empty] | FAASt PendingRFI1045 | FAASt Pending1045 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
812041 | 108101 | FAASt [Distribution Feeder Rebuild 9501-02] | 14F000270000 | PBUT06 - Distr Line Rebuild | Distribution |  |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45707 | 02/19/2025 |  | 45758 | 45862 |  |  |  |  | 13725835 | 13725835 | 0 | 3314820.98 |  | 25929254.07 | 0 | 0 | 25929254.07 | 29244075.05 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1310/812041-%20DR4339PR-%20Feeder%20Rebuild%209501-02-Detailed%20Scope%20of%20Work.pdf?web=1 | 20FEBRUARY2025 No ISOW in GP at this time - MC 7/30/2025 - As confirmed by PDMG, project sent back to Phase II because project is not included in PREPA Consolidated Plan of 7/7/2025. | 46078.5977 | 45709.5219 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 0.52936 | 3 | 45884 | 812041RFI1046 | 812041 | 3693316.44 | 0 | 3693316.44 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Pending |  | Fiber Optic Repair and Replacement |  |  | Telecommunications |  |  |  | FALSE |  |  | FALSE |  |  |  | 45715 |  | 45730 | 45760 |  | 45760 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7744 | 45723.4725 | Jeremy Malone |  | Rey Roldan Rodríguez | [7 empty] | FAASt PendingRFI1047 | FAASt Pending1047 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
814792 | 108105 | FAASt [Telecom Infrastructure – Group E] | 14F009010000, 14F008930000, 14F009020000 | PBIT01 - Telecom Sys & Network | Telecommunications |  |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45723 | 03/07/2025 | [7 empty] | 5600000 | 5600000 | [5 empty] | 0 | 5600000 | 5600000 | [11 empty] | 0 | 0 |  |  | 07MARCH2025 No ISOW in GP - MC | 46078.5982 | 45723.5093 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 1 | 1 | 45873 | 814792RFI1048 | 814792 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
814793 | 108106 | FAASt [Telecom Infrastructure – Group F] | 14F019040000, 14F019050000, 14F019060000 | PBIT01 - Telecom Sys & Network | Telecommunications |  |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45723 | 03/07/2025 | [7 empty] | 4600000 | 4600000 | [5 empty] | 0 | 4600000 | 4600000 | [11 empty] | 0 | 0 |  |  | 07MARCH2025 No ISOW in GP - MC | 46078.5982 | 45723.5118 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 1 | 1 | 45880 | 814793RFI1049 | 814793 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt [Distribution Feeder Rebuild #6603-01] (Distribution) |  |  | Distribution – Feeder Rebuild |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7744 | 45729.6907 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1050 | FAASt number pending 5001050 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt [Transmission Priority Pole Replacement Program Line San Juan Region Group 1](Transmission) |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7744 | 45729.6922 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1051 | FAASt number pending 5001051 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
817956 | 108119 | FAASt [Feeder Rebuild # 1303-02] (Distribution) | 14F001490000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild |  |  |  | FALSE |  | Current | FALSE | [12 empty] | 45742 | 03/26/2025 |  | 45789 | 45828 | 45898 | 45884 | 8/15/2025 - Field EHP: In review. Expected Completion Date ECD 8/29/2025. |  |  | 6132436 | 0 | 1376522.26 |  | 2184086.98 | 0 | 0 | 2184086.98 | 3560609.24 |  |  | 45925 |  | 2054461.78 | 2054461.78 |  |  |  | 129625.2 |  | 2054461.78 | 2054461.78 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1316/817956-DR4339PR-Feeders%20Rebuild%201303-02-Detailed%20Scope%20of%20Work-Rev.%200.pdf?web=1 | 8/1/2025 - Field EHP: Initial review. Expected Completion Date ECD 8/15/2025. 8/13/2025 1:37 PM AST - The PR Electric Power Authority, as the eligible entity (subrecipient), has submitted a consolidated plan for the use of the remaining budget available in the FEMA Accelerated Awards Strategy Project (136271) Fixed Cost Award. This FAASt sub-project has been identified in the list and it will be processed in the national workflow accordingly. | 46078.5994 | 45729.6925 | Marlina Crespo |  | Ashleah Dingle |  |  | 1376522.26 | 0 | 2.8078 | 1 |  | 817956RFI1052 | 817956 | 129625.2 |  | 129625.2 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt [Transmission Priority Pole Replacement Program Line Mayaguez Region Group1](Transmission) |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7744 | 45729.6927 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1053 | FAASt number pending 5001053 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt [Distribution Feeder Rebuild # 6406-02] (Distribution) |  |  | Distribution – Feeder Rebuild |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7744 | 45729.6929 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1054 | FAASt number pending 5001054 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt [Transmission Priority Pole Replacement Program Line Arecibo Region Group 1 (Transmission) |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7744 | 45729.693 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1055 | FAASt number pending 5001055 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt [Distribution Feeder Rebuild # 6802-04] (Distribution) |  |  | Distribution – Feeder Rebuild |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7744 | 45729.6934 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1056 | FAASt number pending 5001056 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt [Transmission Priority Pole Replacement Program Line 9900 - RIO BLANCO HP-HUMACAO SECT](Transmission) |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7744 | 45729.6934 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1057 | FAASt number pending 5001057 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending |  | FAASt [Transmission Priority Pole Replacement Program Line 4800 Santa Isabel TC - Santa Isabel Sect](Transmission) |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7744 | 45729.6936 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pendingRFI1058 | FAASt number pending |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
817961 | 108120 | FAASt [Feeder Rebuild # 2404-06] (Distribution) | 14F000900000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild |  |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45742 | 03/26/2025 |  | 45846 | [5 empty] | 23882838 | 23882838 | 399260.06 | 1826739.4 |  | 19517674.31 | 50231.61 | 349028.45 | 19916934.37 | 21743673.77 | [11 empty] | 0 | 0 |  |  |  | 46078.5996 | 45729.6938 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 1.1991 | 1 | 45884 | 817961RFI1059 | 817961 | 692201.89 | 82130.27 | 774332.16 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt [Transmission Priority Pole Replacement Program Line 1600 LEON SECT-ACACIAS TC](Transmission) |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7744 | 45729.6941 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1060 | FAASt number pending 5001060 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
818006 | 108123 | FAASt [Feeder Rebuild #2402-02] (Distribution) | 14F000880000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild |  |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45742 | 03/26/2025 | [7 empty] | 34516477 | 34516477 | [5 empty] | 0 | 34516477 | 34516477 | [11 empty] | 0 | 0 |  |  |  | 46078.5999 | 45729.6941 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 1 | 1 | 45884 | 818006RFI1061 | 818006 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt [Transmission Priority Pole Replacement Program Line 1500 ONCE DE AGOSTO SECT - SABANA GRANDE TO](Transmission) |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7744 | 45729.6945 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1062 | FAASt number pending 5001062 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
817993 | 108122 | FAASt [Feeder Rebuild # 1801-03] (Distribution) | 14F000300000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild |  |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45742 | 03/26/2025 | [7 empty] | 6131846 | 6131846 | [5 empty] | 0 | 6131846 | 6131846 | [11 empty] | 0 | 0 |  |  |  | 46078.5997 | 45729.6946 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 1 | 1 | 45884 | 817993RFI1063 | 817993 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt [Transmission Priority Pole Replacement Program Line 2000 ONCE DE AGOSTO SECT - SAN SEBASTIAN TC](Transmission) |  |  | Transmission – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7745 | 45729.6948 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1064 | FAASt number pending 5001064 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
818056 | 108126 | FAASt [Feeder Rebuild # 6305-03] (Distribution) | 14F001080000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild |  |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45742 | 03/26/2025 | [7 empty] | 22352214 | 22352214 | [5 empty] | 0 | 22352214 | 22352214 | [11 empty] | 0 | 0 |  |  |  | 46078.6001 | 45729.695 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 1 | 1 | 45884 | 818056RFI1065 | 818056 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt [Transmission Line 36100 Cana to Bayamon] (Transmission) |  |  | Transmission |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7745 | 45729.6951 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1066 | FAASt number pending 5001066 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
818055 | 108125 | FAASt [Feeder Rebuild # 3006-05] (Distribution) | 14F000480000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild |  |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45742 | 03/26/2025 | [7 empty] | 8829008 | 8829008 | [5 empty] | 0 | 8829008 | 8829008 | [11 empty] | 0 | 0 |  |  |  | 46078.6001 | 45729.6954 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 1 | 1 | 45884 | 818055RFI1067 | 818055 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt [Transmission Line 36100 Dos Bocas to Ciales] (Transmission) |  |  | Transmission |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7745 | 45729.6954 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1068 | FAASt number pending 5001068 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
818041 | 108124 | FAASt [Feeder Rebuild # 3701-03] (Distribution) | 14F000520000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild |  |  |  | TRUE | 45869 |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45742 | 03/26/2025 | [7 empty] | 24349603.89 | 24349603.89 | [5 empty] | 0 | 24349603.89 | 24349603.89 | [11 empty] | 0 | 0 |  |  |  | 46078.6001 | 45729.6957 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 1 | 1 | 45884 | 818041RFI1069 | 818041 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
817962 | 108121 | FAASt [Feeder Rebuild # 9403-03] (Distribution) | 14F000260000 | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild |  |  |  | TRUE | 45900 |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45742 | 03/26/2025 | [7 empty] | 5548949 | 5548949 | [5 empty] | 0 | 5548949 | 5548949 | [11 empty] | 0 | 0 |  |  |  | 46078.5996 | 45729.696 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 1 | 1 | 45884 | 817962RFI1070 | 817962 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | Aguas Buenas - Phase I |  |  | Substation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7745 | 45729.6961 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1071 | FAASt number pending 5001071 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt # [Distribution Feeder Rebuild # 1806-02] (Distribution) |  |  | Distribution – Feeder Rebuild |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7745 | 45729.6962 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1072 | FAASt number pending 5001072 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | Rincon - Phase I |  |  | Substation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7745 | 45729.6963 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1073 | FAASt number pending 5001073 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt # [Distribution Feeder Rebuild # 3007-03] (Distribution) |  |  | Distribution – Feeder Rebuild |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7745 | 45729.6965 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1074 | FAASt number pending 5001074 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | Factor – Phase I |  |  | Substation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7745 | 45729.6967 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1075 | FAASt number pending 5001075 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | Naguabo – Phase I |  |  | Substation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7745 | 45729.6969 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1076 | FAASt number pending 5001076 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt # [Distribution Feeder Rebuild # 1909-09] (Distribution) |  |  | Distribution – Feeder Rebuild |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7745 | 45729.6972 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1077 | FAASt number pending 5001077 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | Fonalledas – Phase I |  |  | Substation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7745 | 45729.6974 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1078 | FAASt number pending 5001078 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt # [Distribution Feeder Rebuild # 2603-08] (Distribution) |  |  | Distribution – Feeder Rebuild |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7745 | 45729.6974 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1079 | FAASt number pending 5001079 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt # [Distribution Feeder Rebuild # 7805-13] (Distribution) |  |  | Distribution – Feeder Rebuild |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7745 | 45729.6976 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1080 | FAASt number pending 5001080 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | Canas TC – Phase I |  |  | Substation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7745 | 45729.6977 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1081 | FAASt number pending 5001081 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | Pompanos – Phase I |  |  | Substation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7745 | 45729.698 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1082 | FAASt number pending 5001082 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt # [Distribution Feeder Rebuild # 1336-08] (Distribution) |  |  | Distribution – Feeder Rebuild |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7745 | 45729.698 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1083 | FAASt number pending 5001083 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | Arecibo – Phase I |  |  | Substation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7745 | 45729.6982 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1084 | FAASt number pending 5001084 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt # [Distribution Feeder Rebuild # 6306-02] (Distribution) |  |  | Distribution – Feeder Rebuild |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7745 | 45729.6983 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1085 | FAASt number pending 5001085 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | Mora – Phase I (Substation) |  |  | Substation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7745 | 45729.6986 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1086 | FAASt number pending 5001086 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt # [Distribution Feeder Rebuild # 6704-03] (Distribution) |  |  | Distribution – Feeder Rebuild |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7745 | 45729.6988 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1087 | FAASt number pending 5001087 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | Hato Rey – Phase I |  |  | Substation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7745 | 45729.6988 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1088 | FAASt number pending 5001088 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt # [Distribution Feeder Rebuild # 6010-01] (Distribution) |  |  | Distribution – Feeder Rebuild |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7745 | 45729.699 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1089 | FAASt number pending 5001089 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | Caguas – Phase I |  |  | Substation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7745 | 45729.6991 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1090 | FAASt number pending 5001090 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
825843 | 108134 | FAAST [Guanica Transformer Replacement] (Substation) |  | PBUT07 - Substation Reliability | Substation |  | TRUE |  | FALSE |  | Current | FALSE | [12 empty] | 45756 | 04/09/2025 |  | 45756 |  | 45884 | 45877 | 8/13/2025 9:48 AM AST - The PR Electric Power Authority, as the eligible entity (subrecipient), has submitted a consolidated plan for the use of the remaining budget available in the FEMA Accelerated Awards Strategy Project (136271) Fixed Cost Award. This FAASt sub-project has been identified in the list and it will be processed in the national workflow accordingly. |  |  |  |  | 826981.13 |  | 6521097.48 | 0 | 0 | 6521097.48 | 7348078.61 |  |  | 45922 |  | 2320373.96 | 2320373.96 |  |  |  | 4200723.52 |  | 2320373.96 | 2320373.96 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1355/DR43339PR-FEMA%20DSOW%20Guanica%20TC%20signed%204.8.2025%20(002).pdf?web=1 | 8/13/2025 9:48 AM AST - The PR Electric Power Authority, as the eligible entity (subrecipient), has submitted a consolidated plan for the use of the remaining budget available in the FEMA Accelerated Awards Strategy Project (136271) Fixed Cost Award. This FAASt sub-project has been identified in the list and it will be processed in the national workflow accordingly. | 46078.6015 | 45729.6993 | Maria Mujica Gonzalez |  | Ashleah Dingle |  |  | 826981.13 | 0 | 0 | 5 |  | 825843RFI1091 | 825843 | 4200723.52 |  | 4200723.52 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt # [Distribution Feeder Rebuild # 7805-11] (Distribution) |  |  | Distribution – Feeder Rebuild |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7745 | 45729.6995 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1092 | FAASt number pending 5001092 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | Fajardo 2002 – Veve Calzada – Phase I |  |  | Substation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7745 | 45729.6996 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1093 | FAASt number pending 5001093 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt [38kV Recloser TL 100 Ponce To Jobos (Transmission) |  |  | Grid Automation – 38 kV Reclosers |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7745 | 45729.7001 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1094 | FAASt number pending 5001094 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
817249 | 108116 | FAASt [Pole and Conductor Repair -Caguas Group 7 - Phase 2] (Distribution) | 14F018910000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement |  |  |  | TRUE | 45869 |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | FALSE | [9 empty] | 45737 | 03/21/2025 | [7 empty] | 5100000 | 5100000 | [5 empty] | 0 | 5100000 | 5100000 | [11 empty] | 0 | 0 |  |  |  | 46078.599 | 45729.7005 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 1 | 1 | 45873 | 817249RFI1095 | 817249 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt [38kV Recloser TL 3600-SABANA LLANA TC-LOS ANGELES SECT-] (Transmission) |  |  | Grid Automation – 38 kV Reclosers |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7745 | 45729.7006 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1096 | FAASt number pending 5001096 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
817242 | 108113 | FAASt [Pole and Conductor Repair -Caguas Group 8 - Phase 2] (Distribution) | 14F018920000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement |  |  |  | TRUE | 45869 |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45737 | 03/21/2025 | [7 empty] | 2040000 | 2040000 | [5 empty] | 0 | 2040000 | 2040000 | [11 empty] | 0 | 0 |  |  |  | 46078.5989 | 45729.7007 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 1 | 1 | 45880 | 817242RFI1097 | 817242 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt [38kV Recloser TL 3200-MONACILLOS TC-VENEZUELA SECT-] (Transmission) |  |  | Grid Automation – 38 kV Reclosers |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7745 | 45729.7008 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1098 | FAASt number pending 5001098 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt [38kV Recloser TL 3100-MONACILLOS TC-SABANA LLANA TC] (Transmission) |  |  | Grid Automation – 38 kV Reclosers |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7745 | 45729.7011 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1099 | FAASt number pending 5001099 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
817247 | 108114 | FAASt [Pole and Conductor Repair -Ponce Group 3 - Phase 2] (Distribution) | 14F021430000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement |  |  |  | TRUE | 45930 |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45737 | 03/21/2025 | [7 empty] | 11650000 | 11650000 | [5 empty] | 0 | 11650000 | 11650000 | [11 empty] | 0 | 0 |  |  |  | 46078.5989 | 45729.7013 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 1 | 1 | 45880 | 817247RFI1100 | 817247 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt [38kV Recloser TL 2200-CAMBALACHE TC-Vega Alta SECT] (Transmission) |  |  | Grid Automation – 38 kV Reclosers |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7745 | 45729.7014 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1101 | FAASt number pending 5001101 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | 38kV Reclosers TLine 4800 SANTA ISABEL TC-AIBONITO TO] (Transmission) |  |  | Grid Automation – 38 kV Reclosers |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7745 | 45729.7017 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1102 | FAASt number pending 5001102 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
817250 | 108117 | FAASt [Pole and Conductor Repair -San Juan Group 4 - Phase 2] (Distribution) | 14F021420000 | PBUT30 - D Pole & Conductor Repair | Distribution – Pole Replacement |  |  |  | TRUE | 45930 |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45737 | 03/21/2025 | [7 empty] | 7610000 | 7610000 | [5 empty] | 0 | 7610000 | 7610000 | [11 empty] | 0 | 0 |  |  |  | 46078.599 | 45729.7019 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 1 | 1 | 45880 | 817250RFI1103 | 817250 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | 38kV Reclosers TLine 3700 JOBOS TC to Humacao TC] (Transmission) |  |  | Grid Automation – 38 kV Reclosers |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7745 | 45729.7019 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1104 | FAASt number pending 5001104 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | 38kV Reclosers TLine 2000 ONCE DE AGOSTO SECT to SAN SEBASTIAN TC] (Transmission) |  |  | Grid Automation – 38 kV Reclosers |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7745 | 45729.7022 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1105 | FAASt number pending 5001105 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt [Pole and Conductor Repair -Mayaguez Group 5 - Phase 2 |  |  | Distribution – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7745 | 45729.7023 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1106 | FAASt number pending 5001106 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | 38kV Reclosers TLine 1600 MAYAGUEZ GP to Acacias TC] (Transmission) |  |  | Grid Automation – 38 kV Reclosers |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7745 | 45729.7024 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1107 | FAASt number pending 5001107 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt [Pole and Conductor Repair -Arecibo Group 18-19-20-21 - Phase 3 |  |  | Distribution – Pole Replacement |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7745 | 45729.7027 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1108 | FAASt number pending 5001108 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | 38kV Reclosers TLine 13400 ACACIAS TC-SAN GERMAN SECT] (Transmission) |  |  | Grid Automation – 38 kV Reclosers |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7745 | 45729.7027 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1109 | FAASt number pending 5001109 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | 38kV Reclosers TLine 12600 HUMACAO TC to VERDE MAR-] (Transmission) |  |  | Grid Automation – 38 kV Reclosers |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7745 | 45729.703 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1110 | FAASt number pending 5001110 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | 38 kV ReclosersTLine 800 CAYEY TC to COMSAT SECT] (Transmission) |  |  | Grid Automation – 38 kV Reclosers |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7745 | 45729.7034 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1111 | FAASt number pending 5001111 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt [Automation Program Group 2B-8 Feeders] (Distribution) |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7745 | 45729.7035 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1112 | FAASt number pending 5001112 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | 38 kV Reclosers TLine 8100 YAUCO 1 HP to Canas TC] (Transmission) |  |  | Grid Automation – 38 kV Reclosers |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7745 | 45729.7037 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1113 | FAASt number pending 5001113 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt [Automation Program Group 2C-10 Feeders] (Distribution) |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7745 | 45729.7038 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1114 | FAASt number pending 5001114 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | 38 kV Reclosers TLine 6500 TORO NEGRO 1 HP to Comerio TC] (Transmission) |  |  | Grid Automation – 38 kV Reclosers |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7745 | 45729.7039 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1115 | FAASt number pending 5001115 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | 38 kV Reclosers TLine 5600 VICTORIA TC to AÑASCO TC] (Transmission) |  |  | Grid Automation – 38 kV Reclosers |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7745 | 45729.7042 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1116 | FAASt number pending 5001116 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt [Automation Program Group 2D-8 Feeders] (Distribution) |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7745 | 45729.7042 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1117 | FAASt number pending 5001117 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | 38 kV Reclosers TLine 1500 FAASt [38kV Recloser TL 1500-Yauco HP to San German TC] (Transmission) |  |  | Grid Automation – 38 kV Reclosers |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7745 | 45729.7044 | Maria Mujica Gonzalez |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1118 | FAASt number pending 5001118 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt [Automation Program Group 2E-9 Feeders] (Distribution) |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7745 | 45729.7046 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1119 | FAASt number pending 5001119 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt [Automation Program Group 4B- 6 Feeders] (Distribution) |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7745 | 45729.706 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1120 | FAASt number pending 5001120 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt [Automation Program Group 4C- 7 Feeders] (Distribution) |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7745 | 45729.7062 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1121 | FAASt number pending 5001121 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt [Automation Program Group 4D- 7Feeders] (Distribution) |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7745 | 45729.7065 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1122 | FAASt number pending 5001122 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt [Automation Program Group 46] (Distribution) |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7745 | 45729.7068 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1123 | FAASt number pending 5001123 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt [Automation Program Group 47] (Distribution) |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7745 | 45729.7069 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1124 | FAASt number pending 5001124 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt [Automation Program Group 48] (Distribution) |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7745 | 45729.707 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1125 | FAASt number pending 5001125 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt [Automation Program Group 49] (Distribution) |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7745 | 45729.7071 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1126 | FAASt number pending 5001126 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt [Automation Program Group 50] (Distribution) |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7745 | 45729.7072 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1127 | FAASt number pending 5001127 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt [Automation Program Group 51] (Distribution) |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7746 | 45729.7074 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1128 | FAASt number pending 5001128 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt [Automation Program Group 52] (Distribution) |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7746 | 45729.7075 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1129 | FAASt number pending 5001129 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt [Automation Program Group 53] (Distribution) |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7746 | 45729.7076 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1130 | FAASt number pending 5001130 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt [Automation Program Group 54] (Distribution) |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7746 | 45729.7077 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1131 | FAASt number pending 5001131 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt [Automation Program Group 55] (Distribution) |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7746 | 45729.7087 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1132 | FAASt number pending 5001132 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt [Automation Program Group 56] (Distribution) |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7746 | 45729.7088 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1133 | FAASt number pending 5001133 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt [Automation Program Group 57] (Distribution) |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7746 | 45729.709 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1134 | FAASt number pending 5001134 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt [Automation Program Group 58] (Distribution) |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7746 | 45729.7091 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1135 | FAASt number pending 5001135 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt [Automation Program Group 59] (Distribution) |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7746 | 45729.7092 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1136 | FAASt number pending 5001136 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt [Automation Program Group 60] (Distribution) |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7746 | 45729.7093 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1137 | FAASt number pending 5001137 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt [Automation Program Group 61] (Distribution) |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7746 | 45729.7094 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1138 | FAASt number pending 5001138 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt [Automation Program Group 62] (Distribution) |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7746 | 45729.7095 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1139 | FAASt number pending 5001139 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt [Automation Program Group 63] (Distribution) |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7746 | 45729.7096 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1140 | FAASt number pending 5001140 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt [Automation Program Group 64] (Distribution) |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7746 | 45729.7097 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1141 | FAASt number pending 5001141 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt [Automation Program Group 65] (Distribution) |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7746 | 45729.7105 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1142 | FAASt number pending 5001142 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt [Automation Program Group 66] (Distribution) |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7746 | 45729.7105 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1143 | FAASt number pending 5001143 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt [Automation Program Group 67] (Distribution) |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7746 | 45729.7107 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1144 | FAASt number pending 5001144 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt [Automation Program Group 68] (Distribution) |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7746 | 45729.7108 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1145 | FAASt number pending 5001145 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt [Automation Program Group 69] (Distribution) |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7746 | 45729.7109 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1146 | FAASt number pending 5001146 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt [Automation Program Group 70] (Distribution) |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7746 | 45729.711 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1147 | FAASt number pending 5001147 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt [Automation Program Group 71] (Distribution) |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7746 | 45729.7111 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1148 | FAASt number pending 5001148 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt [Automation Program Group 72] (Distribution) |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7746 | 45729.7113 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1149 | FAASt number pending 5001149 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt [Automation Program Group 73] (Distribution) |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7746 | 45729.7114 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1150 | FAASt number pending 5001150 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt number pending 500 |  | FAASt [Automation Program Group 74] (Distribution) |  |  | Grid Automation |  |  |  | FALSE |  |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7746 | 45729.7115 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt number pending 500RFI1151 | FAASt number pending 5001151 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
825753 | 108133 | FAASt - EPC - [Guanica TC] (Substation) |  |  | Substation |  |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45756 | 04/09/2025 | [7 empty] | 5750000 | [6 empty] | 0 | 5750000 | 5750000 | [11 empty] | 0 | 0 |  |  | 04/10/2025 02:01 PM AST The project was withdrawn with the comment "Project already created under: 825843 FASSt Guanica TC". 04/10/2025 02:01 PM AST Projected 100% Amount set to $0.00 because Project was made inactive for Public Assistance. Reason: Project already created under: 825843 FASSt Guanica TC | 45870.4724 | 45757.5422 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 0 | 5 |  | 825753RFI1152 | 825753 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | FAASt Caridad – XFMR MC 1714 (Substation) |  |  | Substation | Substation Rebuilds |  |  | FALSE |  |  | FALSE |  | Active |  |  | 5500000 | 44314 | 44355 |  | 44344 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7746 | 45762.5286 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1153 | Pending PREB Approval1153 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Transmission Access Roads |  |  | Transmission | To be allocated to appropriate program |  |  | FALSE |  |  | FALSE |  | Active |  |  | 16965451 | 44314 | 44355 |  | 44344 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7746 | 45762.5321 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1154 | Pending PREB Approval1154 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | FAASt Transmission - Line 40100 & 40200 - Aguirre SP TC to Jobos TC (Transmission) |  |  | Transmission | Transmission Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 30428000 | 44355 | 44355 |  | 44385 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7746 | 45762.5322 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1155 | Pending PREB Approval1155 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Line 3000 Monacillos TC to Juncos TC |  |  | Transmission | Transmission Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 90440000 | 44385 | 44428 |  | 44415 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7746 | 45762.5336 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1156 | Pending PREB Approval1156 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Line 8900 Monacillos TC to Adm. Tribunal Apelaciones |  |  | Transmission | Transmission Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 11510000 | 44385 | 44428 |  | 44415 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7746 | 45762.5356 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1157 | Pending PREB Approval1157 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeders ‐ Caguas Short Term Group 4 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 44710000 | 44385 | 44428 |  | 44415 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7746 | 45762.5357 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1158 | Pending PREB Approval1158 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeders ‐ Caguas Short Term Group 8 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 23640000 | 44385 | 44428 |  | 44415 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7746 | 45762.537 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1159 | Pending PREB Approval1159 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeders ‐ Ponce Short Term Group 2 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 42380000 | 44385 | 44428 |  | 44415 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7746 | 45762.5633 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1160 | Pending PREB Approval1160 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | 115 kV Transmission Priority Poles and Structures Replacements |  |  | Transmission | Transmission Priority Pole Replacements |  |  | FALSE |  |  | FALSE |  | Active |  |  | 318800000 | 44438 | 44461 |  | 44468 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7746 | 45762.5633 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1161 | Pending PREB Approval1161 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | 230 kV Transmission Priority Poles and Structures Replacements |  |  | Transmission | Transmission Priority Pole Replacements |  |  | FALSE |  |  | FALSE |  | Active |  |  | 31300000 | 44438 | 44461 |  | 44468 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7746 | 45762.5662 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1162 | Pending PREB Approval1162 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Fiber Optic Replacement |  |  | IT and Telecommunications | IT OT Telecom Systems & Network |  |  | FALSE |  |  | FALSE |  | Discontinued |  |  | 229500000 | 44438 | 44461 |  | 44468 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7746 | 45762.5668 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1163 | Pending PREB Approval1163 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Line 3600 Monacillos TC to Martin Peña TC |  |  | Transmission | Transmission Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 39980000 | 44438 | 44461 |  | 44468 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7746 | 45762.5671 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1164 | Pending PREB Approval1164 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Primary and Secondary Control Centers |  |  | IT and Telecommunications | IT OT Telecom Systems & Network |  |  | FALSE |  |  | FALSE |  | Discontinued |  |  | 84000000 | 44438 | 44461 |  | 44468 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7746 | 45762.5675 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1165 | Pending PREB Approval1165 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Arecibo Region Repairs |  |  | Building | Facilities Development & Implementation |  |  | FALSE |  |  | FALSE |  | Active |  |  | 9226902 | 44438 | 44483 |  | 44468 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7746 | 45762.5678 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1166 | Pending PREB Approval1166 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Bayamon Region Repairs |  |  | Building | Facilities Development & Implementation |  |  | FALSE |  |  | FALSE |  | Active |  |  | 15451304 | 44438 | 44483 |  | 44468 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7746 | 45762.5682 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1167 | Pending PREB Approval1167 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Caguas Region Repairs |  |  | Building | Facilities Development & Implementation |  |  | FALSE |  |  | FALSE |  | Active |  |  | 14472108 | 44438 | 44483 |  | 44468 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7746 | 45762.5686 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1168 | Pending PREB Approval1168 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Mayaguez Region Repairs |  |  | Building | Facilities Development & Implementation |  |  | FALSE |  |  | FALSE |  | Active |  |  | 13346360 | 44438 | 44483 |  | 44468 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7746 | 45762.5691 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1169 | Pending PREB Approval1169 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Ponce Region Repairs |  |  | Building | Facilities Development & Implementation |  |  | FALSE |  |  | FALSE |  | Active |  |  | 16300000 | 44438 | 44483 |  | 44468 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7746 | 45762.5701 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1170 | Pending PREB Approval1170 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | San German Electrical Service Center |  |  | Building | Facilities Development & Implementation |  |  | FALSE |  |  | FALSE |  | Active |  |  | 2478181 | 44438 | 44483 |  | 44468 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7746 | 45762.5715 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1171 | Pending PREB Approval1171 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | San Juan Region Repairs |  |  | Building | Facilities Development & Implementation |  |  | FALSE |  |  | FALSE |  | Active |  |  | 31028729 | 44438 | 44483 |  | 44468 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7746 | 45762.5719 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1172 | Pending PREB Approval1172 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Line 6700 Martin Peña TC to Villamar Sect. |  |  | Transmission | Transmission Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 6010000 | 44473 | 44487 |  | 44503 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7746 | 45762.5723 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1173 | Pending PREB Approval1173 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Bayview Sectionalizer 1802 Relocation |  |  | Substation | Substation Rebuilds |  |  | FALSE |  |  | FALSE |  | Active |  |  | 16700000 | 44473 | 44487 |  | 44503 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7746 | 45762.5727 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1174 | Pending PREB Approval1174 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Caguas TC |  |  | Substation | Substation Rebuilds |  |  | FALSE |  |  | FALSE |  | Active |  |  | 2500000 | 44473 | 44487 |  | 44503 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7746 | 45762.5731 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1175 | Pending PREB Approval1175 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Canas TC |  |  | Substation | Substation Rebuilds |  |  | FALSE |  |  | FALSE |  | Active |  |  | 1700000 | 44473 | 44487 |  | 44503 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7746 | 45762.5736 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1176 | Pending PREB Approval1176 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Dorado TC Relocation |  |  | Substation | Substation Rebuilds |  |  | FALSE |  |  | FALSE |  | Active |  |  | 40100000 | 44473 | 44487 |  | 44503 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7746 | 45762.574 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1177 | Pending PREB Approval1177 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Fonalledas GIS Rebuilt 1401 1421 |  |  | Substation | Substation Rebuilds |  |  | FALSE |  |  | FALSE |  | Active |  |  | 31400000 | 44473 | 44487 |  | 44503 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7746 | 45762.5744 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1178 | Pending PREB Approval1178 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Line 4000 Comerio HP to Escuela Francisco Morales |  |  | Transmission | Transmission Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 22330000 | 44473 | 44487 |  | 44503 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7746 | 45762.5775 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1179 | Pending PREB Approval1179 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Santurce Planta (Sect) 1116 |  |  | Substation | Substation Rebuilds |  |  | FALSE |  |  | FALSE |  | Discontinued |  |  | 9900000 | 44473 | 44487 |  | 44503 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7746 | 45762.5837 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1180 | Pending PREB Approval1180 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Isla Grande 1101 |  |  | Substation | Substation Rebuilds |  |  | FALSE |  |  | FALSE |  | Discontinued |  |  | 600000 | 44585 | 44635 |  | 44615 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7746 | 45762.5843 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1181 | Pending PREB Approval1181 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Field Area Network(FAN) |  |  | IT and Telecommunications | IT OT Telecom Systems & Network |  |  | FALSE |  |  | FALSE |  | Active |  |  | 330000000 | 44585 | 44635 |  | 44615 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7746 | 45762.5856 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1182 | Pending PREB Approval1182 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeders - Arecibo Short Term Group 10 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 30360000 | 44876 | 44905 |  | 44906 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7746 | 45762.5862 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1183 | Pending PREB Approval1183 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeders - Arecibo Short Term Group 12 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Discontinued |  |  | 29040000 | 44876 | 44905 |  | 44906 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7746 | 45762.5867 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1184 | Pending PREB Approval1184 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeders - Arecibo Short Term Group 11 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 36340000 | 44876 | 44905 |  | 44906 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.5876 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1185 | Pending PREB Approval1185 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeders - Arecibo Short Term Group 3 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 34620000 | 44876 | 44905 |  | 44906 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.5917 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1186 | Pending PREB Approval1186 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeders - Arecibo Short Term Group 4 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 31440000 | 44876 | 44905 |  | 44906 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.592 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1187 | Pending PREB Approval1187 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeders - Arecibo Short Term Group 5 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 23660000 | 44876 | 44905 |  | 44906 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.5941 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1188 | Pending PREB Approval1188 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeders - Arecibo Short Term Group 7 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Discontinued |  |  | 30250000 | 44876 | 44905 |  | 44906 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.5945 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1189 | Pending PREB Approval1189 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeders - Arecibo Short Term Group 8 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Discontinued |  |  | 27570000 | 44876 | 44905 |  | 44906 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.5961 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1190 | Pending PREB Approval1190 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeders - Arecibo Short Term Group 6 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 30240000 | 44876 | 44905 |  | 44906 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.5967 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1191 | Pending PREB Approval1191 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeders - Bayamon Short Term Group 4 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Discontinued |  |  | 26290000 | 44876 | 44905 |  | 44906 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.5975 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1192 | Pending PREB Approval1192 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeders - Bayamon Short Term Group 5 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Discontinued |  |  | 29500000 | 44876 | 44905 |  | 44906 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.5988 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1193 | Pending PREB Approval1193 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeders - Bayamon Short Term Group 6 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Discontinued |  |  | 23230000 | 44876 | 44905 |  | 44906 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.5993 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1194 | Pending PREB Approval1194 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeders - Bayamon Short Term Group 7 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Discontinued |  |  | 30910000 | 44876 | 44905 |  | 44906 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.5998 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1195 | Pending PREB Approval1195 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeders - Arecibo Short Term Group 9 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 35930000 | 44876 | 44905 |  | 44906 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.6014 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1196 | Pending PREB Approval1196 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeders - Bayamon Short Term Group 9 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Discontinued |  |  | 29960000 | 44876 | 44905 |  | 44906 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.6019 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1197 | Pending PREB Approval1197 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeders - Caguas Short Term Group 10 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Discontinued |  |  | 31960000 | 44876 | 44905 |  | 44906 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.6024 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1198 | Pending PREB Approval1198 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeders - Bayamon Short Term Group 8 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 24800000 | 44876 | 44905 |  | 44906 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.6029 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1199 | Pending PREB Approval1199 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeders - Caguas Short Term Group 11 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 32040000 | 44876 | 44905 |  | 44906 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.6032 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1200 | Pending PREB Approval1200 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeders - Caguas Short Term Group 13 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Discontinued |  |  | 23010000 | 44876 | 44905 |  | 44906 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.6039 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1201 | Pending PREB Approval1201 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeders - Caguas Short Term Group 14 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Discontinued |  |  | 34390000 | 44876 | 44905 |  | 44906 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.6044 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1202 | Pending PREB Approval1202 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeders - Caguas Short Term Group 12 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 31220000 | 44876 | 44905 |  | 44906 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.6051 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1203 | Pending PREB Approval1203 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeders - Caguas Short Term Group 9 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Discontinued |  |  | 33890000 | 44876 | 44905 |  | 44906 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.6058 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1204 | Pending PREB Approval1204 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeders - Mayaguez Short Term Group 10 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Discontinued |  |  | 31700000 | 44876 | 44905 |  | 44906 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.6063 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1205 | Pending PREB Approval1205 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeders - Mayaguez Short Term Group 12 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Discontinued |  |  | 19040000 | 44876 | 44905 |  | 44906 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.6068 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1206 | Pending PREB Approval1206 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeders - Caguas Short Term Group 15 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 29620000 | 44876 | 44905 |  | 44906 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.6072 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1207 | Pending PREB Approval1207 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeders - Mayaguez Short Term Group 13 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 25880000 | 44876 | 44905 |  | 44906 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.6077 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1208 | Pending PREB Approval1208 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeders - Mayaguez Short Term Group 5 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Discontinued |  |  | 22760000 | 44876 | 44905 |  | 44906 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.6084 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1209 | Pending PREB Approval1209 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeders - Mayaguez Short Term Group 14 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 25880000 | 44876 | 44905 |  | 44906 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.6092 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1210 | Pending PREB Approval1210 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeders - Mayaguez Short Term Group 6 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 24210000 | 44876 | 44905 |  | 44906 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.6097 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1211 | Pending PREB Approval1211 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeders - Mayaguez Short Term Group 8 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Discontinued |  |  | 34620000 | 44876 | 44905 |  | 44906 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.61 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1212 | Pending PREB Approval1212 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeders - Mayaguez Short Term Group 7 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 25510000 | 44876 | 44905 |  | 44906 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.611 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1213 | Pending PREB Approval1213 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeders - Mayaguez Short Term Group 9 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 26590000 | 44876 | 44905 |  | 44906 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.6114 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1214 | Pending PREB Approval1214 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeders - Ponce Short Term Group 11 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Discontinued |  |  | 24430000 | 44876 | 44905 |  | 44906 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.6119 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1215 | Pending PREB Approval1215 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeders - Ponce Short Term Group 12 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Discontinued |  |  | 30470000 | 44876 | 44905 |  | 44906 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.6132 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1216 | Pending PREB Approval1216 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeders - Ponce Short Term Group 10 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 23670000 | 44876 | 44905 |  | 44906 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.6133 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1217 | Pending PREB Approval1217 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeders - Ponce Short Term Group 3 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Discontinued |  |  | 33540000 | 44876 | 44905 |  | 44906 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.6141 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1218 | Pending PREB Approval1218 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeders - Ponce Short Term Group 13 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 20890000 | 44876 | 44905 |  | 44906 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.6145 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1219 | Pending PREB Approval1219 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeders - Ponce Short Term Group 4 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 22290000 | 44876 | 44905 |  | 44906 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.6154 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1220 | Pending PREB Approval1220 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeders - Ponce Short Term Group 6 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Discontinued |  |  | 31760000 | 44876 | 44905 |  | 44906 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.6158 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1221 | Pending PREB Approval1221 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeders - Ponce Short Term Group 5 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 29270000 | 44876 | 44905 |  | 44906 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.6162 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1222 | Pending PREB Approval1222 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeders - Ponce Short Term Group 8 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Discontinued |  |  | 25640000 | 44876 | 44905 |  | 44906 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.6168 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1223 | Pending PREB Approval1223 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeders - Ponce Short Term Group 7 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 21050000 | 44876 | 44905 |  | 44906 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.6173 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1224 | Pending PREB Approval1224 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeders - San Juan Short Term Group 10 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Discontinued |  |  | 16390000 | 44876 | 44905 |  | 44906 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.6177 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1225 | Pending PREB Approval1225 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeders - San Juan Short Term Group 11 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Discontinued |  |  | 23680000 | 44876 | 44905 |  | 44906 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.6185 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1226 | Pending PREB Approval1226 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeders - San Juan Short Term Group 12 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Discontinued |  |  | 20620000 | 44876 | 44905 |  | 44906 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.6194 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1227 | Pending PREB Approval1227 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeders - Ponce Short Term Group 9 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 24780000 | 44876 | 44905 |  | 44906 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.6204 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1228 | Pending PREB Approval1228 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeders - San Juan Short Term Group 4 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 32960000 | 44876 | 44905 |  | 44906 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.6208 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1229 | Pending PREB Approval1229 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeders - San Juan Short Term Group 5 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 26390000 | 44876 | 44905 |  | 44906 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.6213 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1230 | Pending PREB Approval1230 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeders - San Juan Short Term Group 6 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 32790000 | 44876 | 44905 |  | 44906 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.6234 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1231 | Pending PREB Approval1231 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeders - San Juan Short Term Group 7 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 26370000 | 44876 | 44905 |  | 44906 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.6238 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1232 | Pending PREB Approval1232 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeders - San Juan Short Term Group 9 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Discontinued |  |  | 24340000 | 44876 | 44905 |  | 44906 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.6242 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1233 | Pending PREB Approval1233 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeders - San Juan Short Term Group 8 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 17630000 | 44876 | 44905 |  | 44906 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.6247 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1234 | Pending PREB Approval1234 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeders - Mayaguez Short Term Group 11 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 25770000 | 44876 | 44905 |  | 44906 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.6252 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1235 | Pending PREB Approval1235 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Protection Management Systems |  |  | IT and Telecommunications | IT OT Telecom Systems & Network |  |  | FALSE |  |  | FALSE |  | Active |  |  | 5800000 | 44881 | 44905 |  | 44911 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.6256 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1236 | Pending PREB Approval1236 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Transmission and Distribution Automation Program Installation of Three Phase Reclosers, Single Phase Reclosers and Fault Circuit Indicators and Feeder Headend protection devices. |  |  | Distribution | Distribution Automation |  |  | FALSE |  |  | FALSE |  | Active |  |  | 469630000 | 45237 | 45257 |  | 45267 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.6263 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1237 | Pending PREB Approval1237 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Area Planning ‐ Bayamón A |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 89400000 | 45350 | 45364 |  | 45380 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.629 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1238 | Pending PREB Approval1238 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Area Planning ‐ Bayamón C |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 64800000 | 45350 | 45364 |  | 45380 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.6294 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1239 | Pending PREB Approval1239 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Area Planning - Bayamón G |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 42200000 | 45350 | 45364 |  | 45380 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.6299 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1240 | Pending PREB Approval1240 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Area Planning - Bayamón F |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 119100000 | 45350 | 45364 |  | 45380 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.6315 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1241 | Pending PREB Approval1241 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Area Planning - San Juan A |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 120100000 | 45350 | 45364 |  | 45380 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.6326 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1242 | Pending PREB Approval1242 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Area Planning - San Juan B |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 58200000 | 45350 | 45364 |  | 45380 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.6362 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1243 | Pending PREB Approval1243 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Area Planning - San Juan C |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 150700000 | 45350 | 45364 |  | 45380 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.6367 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1244 | Pending PREB Approval1244 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Area Planning - San Juan D |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 71800000 | 45350 | 45364 |  | 45380 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.6372 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1245 | Pending PREB Approval1245 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Area Planning - San Juan F |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 30300000 | 45350 | 45364 |  | 45380 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.6376 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1246 | Pending PREB Approval1246 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Area Planning - San Juan G |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 39500000 | 45350 | 45364 |  | 45380 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.6377 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1247 | Pending PREB Approval1247 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Area Planning - San Juan K |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 45400000 | 45350 | 45364 |  | 45380 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45762.6385 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1248 | Pending PREB Approval1248 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Substation Component Replacement Program |  |  | Substation | Substation Rebuilds |  |  | FALSE |  |  | FALSE |  | Active |  |  | 330300000 | 45350 | 45364 |  | 45380 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7747 | 45763.3581 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1249 | Pending PREB Approval1249 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Substation Maunabo TC |  |  | Substation | Substation Rebuilds |  |  | FALSE |  |  | FALSE |  | Active |  |  | 96110000 | 45357 | 45378 |  | 45387 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.3591 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1250 | Pending PREB Approval1250 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Substation Mayaguez TC |  |  | Substation | Substation Rebuilds |  |  | FALSE |  |  | FALSE |  | Active |  |  | 14400000 | 45357 | 45378 |  | 45387 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.3601 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1251 | Pending PREB Approval1251 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Substation Morovis 8801 |  |  | Substation | Substation Rebuilds |  |  | FALSE |  |  | FALSE |  | Active |  |  | 5840000 | 45357 | 45378 |  | 45387 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.3717 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1252 | Pending PREB Approval1252 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Venezuela Substation Transformer Replacement |  |  | Substation | Substation Rebuilds |  |  | FALSE |  |  | FALSE |  | Active |  |  | 3150000 | 45386 | 45434 |  | 45416 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.3724 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1253 | Pending PREB Approval1253 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeder Adjuntas Pueblo 8.32 kV 8202-01 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 4500000 | 45387 | 45405 |  | 45417 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.3729 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1254 | Pending PREB Approval1254 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeder Aguada 7205-01 4.16 kV |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 13500000 | 45387 | 45405 |  | 45417 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.3733 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1255 | Pending PREB Approval1255 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeder Aguas Buenas 3701-02 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 5200000 | 45387 | 45405 |  | 45417 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.3736 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1256 | Pending PREB Approval1256 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeder Añasco 6101-04 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 12600000 | 45387 | 45405 |  | 45417 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.374 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1257 | Pending PREB Approval1257 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeder Añasco 6101-05 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 10500000 | 45387 | 45405 |  | 45417 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.3745 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1258 | Pending PREB Approval1258 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeder Bayamon TC 13 kV #1 1711-05 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 6000000 | 45387 | 45405 |  | 45417 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.3749 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1259 | Pending PREB Approval1259 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeder Bayamon TC 4 kV 1714-02 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 3750000 | 45387 | 45405 |  | 45417 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.3753 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1260 | Pending PREB Approval1260 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeder Berwin 13 kV 1336-07 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 11200000 | 45387 | 45405 |  | 45417 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.3758 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1261 | Pending PREB Approval1261 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeder Buen Pastor 1908-03 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 20700000 | 45387 | 45405 |  | 45417 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.3763 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1262 | Pending PREB Approval1262 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeder Cachete 13 kV 1529-11 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 8100000 | 45387 | 45405 |  | 45417 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.3768 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1263 | Pending PREB Approval1263 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeder Cana (Interamericana) 1719-15 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 7500000 | 45387 | 45405 |  | 45417 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.3774 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1264 | Pending PREB Approval1264 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeder Cana (Interamericana) 1719-18 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 11200000 | 45387 | 45405 |  | 45417 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.3778 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1265 | Pending PREB Approval1265 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeder Candelero 2604-01 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 12700000 | 45387 | 45405 |  | 45417 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.3782 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1266 | Pending PREB Approval1266 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeder Cerro las Mesas 6010-02 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 10500000 | 45387 | 45405 |  | 45417 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.3787 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1267 | Pending PREB Approval1267 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeder Coamo PDS 4603-02 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 12000000 | 45387 | 45405 |  | 45417 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.3797 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1268 | Pending PREB Approval1268 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeders Crea 1717-01 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 7500000 | 45387 | 45405 |  | 45417 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.3801 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1269 | Pending PREB Approval1269 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeder Cuatro Hermanos 6004-02 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 13900000 | 45387 | 45405 |  | 45417 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.3804 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1270 | Pending PREB Approval1270 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeder Dorado Pueblo 8.32 kV 9202-04 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 9800000 | 45387 | 45405 |  | 45417 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.3808 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1271 | Pending PREB Approval1271 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeder El Abanico PDS 9605-02 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 20400000 | 45387 | 45405 |  | 45417 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.3812 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1272 | Pending PREB Approval1272 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeder Encantada 1206-03 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 12700000 | 45387 | 45405 |  | 45417 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.3816 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1273 | Pending PREB Approval1273 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeder Fort Allen 5803-02 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 18000000 | 45387 | 45405 |  | 45417 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.382 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1274 | Pending PREB Approval1274 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeder Grana PDS 1907-05 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 3000000 | 45387 | 45405 |  | 45417 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.3825 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1275 | Pending PREB Approval1275 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeder Hato Tejas 1713-05 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 12300000 | 45387 | 45405 |  | 45417 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.3829 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1276 | Pending PREB Approval1276 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeder Humacao Pueblo 2601-01 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 11200000 | 45387 | 45405 |  | 45417 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.3833 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1277 | Pending PREB Approval1277 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeder Humacao TC 13 kV 2603-09 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 17600000 | 45387 | 45405 |  | 45417 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.3838 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1278 | Pending PREB Approval1278 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeder Isabela Planta 3 7504-01 4.16 kV |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 6900000 | 45387 | 45405 |  | 45417 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.3842 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1279 | Pending PREB Approval1279 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeder Juncos 3201-02 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 15000000 | 45387 | 45405 |  | 45417 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.3846 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1280 | Pending PREB Approval1280 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeder Llorens Torres 13 kV 1118-08 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 4200000 | 45387 | 45405 |  | 45417 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.3849 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1281 | Pending PREB Approval1281 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeder Llorens Torres 13 kV 1118-09 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 4500000 | 45387 | 45405 |  | 45417 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.3853 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1282 | Pending PREB Approval1282 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeder Monacillos 13 kV 1346-03 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 8200000 | 45387 | 45405 |  | 45417 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.3856 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1283 | Pending PREB Approval1283 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeder Monterrey PDS 13 kV 9503-06 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 11700000 | 45387 | 45405 |  | 45417 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.386 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1284 | Pending PREB Approval1284 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeder Peñuelas Pueblo 5401-02 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 8300000 | 45387 | 45405 |  | 45417 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.3873 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1285 | Pending PREB Approval1285 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeder Rio Bayamon 1709-05 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 11100000 | 45387 | 45405 |  | 45417 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.3888 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1286 | Pending PREB Approval1286 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeder Rio Bayamon 1709-02 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 8200000 | 45387 | 45405 |  | 45417 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.3899 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1287 | Pending PREB Approval1287 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeder San Jose 8104-02 4.16 kV |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 12000000 | 45387 | 45405 |  | 45417 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.3905 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1288 | Pending PREB Approval1288 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeder Unibon 9.32 kV 9501-01 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 11300000 | 45387 | 45405 |  | 45417 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.3961 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1289 | Pending PREB Approval1289 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeder Vega Baja TC 13 kV 9004-08 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 22800000 | 45387 | 45405 |  | 45417 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.3965 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1290 | Pending PREB Approval1290 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeder Vega Baja TC 13 kV 9004-10 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 21400000 | 45387 | 45405 |  | 45417 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.4023 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1291 | Pending PREB Approval1291 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeder Villa del Carmen 5016-01 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 11100000 | 45387 | 45405 |  | 45417 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.4029 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1292 | Pending PREB Approval1292 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeder Sabana Grande 4.16 kV 6501-04 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 9700000 | 45387 | 45405 |  | 45417 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.4064 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1293 | Pending PREB Approval1293 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Distribution Feeder Yabucoa Pueblo 2901-04 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 12770000 | 45387 | 45405 |  | 45417 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.4072 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1294 | Pending PREB Approval1294 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Transmission Line 0700 Costa Sur SP to Yauco Pueblo 1 |  |  | Distribution | Distribution Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 24990000 | 45400 | 45419 |  | 45430 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.4075 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1295 | Pending PREB Approval1295 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Bayamon TC - Rebuild |  |  | Substation | Substation Rebuilds |  |  | FALSE |  |  | FALSE |  | Active |  |  | 124500000 | 45456 | 45471 |  | 45486 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.4319 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1296 | Pending PREB Approval1296 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | New Transmission Lines for System Resilience |  |  | Transmission | Transmission Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 321790000 | 45464 | 45471 |  | 45494 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.4323 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1297 | Pending PREB Approval1297 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Asset Management System Implementation |  |  | IT and Telecommunications | IT OT Asset Management |  |  | FALSE |  |  | FALSE |  | Active |  |  | 9700000 | 45471 | 45497 |  | 45501 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.4331 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1298 | Pending PREB Approval1298 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Building Island Wide Program |  |  | Building | Facilities Development & Implementation |  |  | FALSE |  |  | FALSE |  | Active |  |  | 97470000 | 45492 | 45512 |  | 45522 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.4334 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1299 | Pending PREB Approval1299 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Victoria TC |  |  | Substation | Substation Rebuilds |  |  | FALSE |  |  | FALSE |  | Active |  |  | 61400000 | 45504 | 45526 |  | 45534 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.4358 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1300 | Pending PREB Approval1300 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Arecibo Sectionalizer |  |  | Substation | Substation Rebuilds |  |  | FALSE |  |  | FALSE |  | Active |  |  | 46200000 | 45504 | 45526 |  | 45534 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.4372 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1301 | Pending PREB Approval1301 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Venezuela Sectionalizer |  |  | Substation | Substation Rebuilds |  |  | FALSE |  |  | FALSE |  | Active |  |  | 43910000 | 45527 | 45532 |  | 45557 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.4375 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1302 | Pending PREB Approval1302 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Caparra Sectionalizer |  |  | Substation | Substation Rebuilds |  |  | FALSE |  |  | FALSE |  | Active |  |  | 14200000 | 45527 | 45532 |  | 45557 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.4394 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1303 | Pending PREB Approval1303 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | TL36200 – Monacillos TC to Juncos TC |  |  | Transmission | Transmission Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 84900000 | 45579 |  |  | 45609 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.4398 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1304 | Pending PREB Approval1304 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Line 4100 Guaraguao TC to Comerío TC |  |  | Transmission | Transmission Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 72400000 | 45579 |  |  | 45609 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.4402 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1305 | Pending PREB Approval1305 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Line 600 Caguas TC to Gautier Benitez Sect |  |  | Transmission | Transmission Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 26200000 | 45579 |  |  | 45609 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.4405 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1306 | Pending PREB Approval1306 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Cambalache TC Relocation (Substation) |  |  | Substation | Substation Rebuilds |  |  | FALSE |  |  | FALSE |  | Active |  |  | 90100000 | 45579 |  |  | 45609 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.4421 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1307 | Pending PREB Approval1307 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Line 36100 Dos Bocas HP to Monacillos TC Sections |  |  | Transmission | Transmission Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 178700000 | 45638 | 45695 |  | 45668 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.4425 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1308 | Pending PREB Approval1308 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Santurce Planta Substations 1116 and 1117 |  |  | Substation | Substation Rebuilds |  |  | FALSE |  |  | FALSE |  | Active |  |  | 37700000 | 45638 | 45695 |  | 45668 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.443 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1309 | Pending PREB Approval1309 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Transmission Line 1100-Garzas 1 HP to Garzas 2 HP |  |  | Transmission | Transmission Line Rebuild |  |  | FALSE |  |  | FALSE |  | Active |  |  | 5200000 | 45638 | 45695 |  | 45668 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.4433 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1310 | Pending PREB Approval1310 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Tranformer Replacements in Moncacillos TC, Costa Sur TC & Sabana LLana TC (System Improvements Plan) |  |  | Substation | Substation Rebuilds |  |  | FALSE |  |  | FALSE |  | Active |  |  | 44200000 | 45678 | 45694 |  | 45708 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.4437 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1311 | Pending PREB Approval1311 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | System Improvement Plan – Replacement of Eight Transformers, Metalclad Switchgear, and GIS Repair |  |  | Substation | Substation Rebuilds |  |  | FALSE |  |  | FALSE |  | Active |  |  | 48400000 | 45713 | 45740 |  | 45743 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.4441 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1312 | Pending PREB Approval1312 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Island-Wide Fiber Optic Repair & Replacement |  |  | Transmission |  |  |  | FALSE |  |  | FALSE |  | Active |  |  | 248000000 | 45730 |  |  | 45760 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.4445 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1313 | Pending PREB Approval1313 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Costa Sur TC Underground Cable Failure Replacement on Transformer Lead Bank #2 | [6 empty] | FALSE |  |  | FALSE |  |  |  |  | 882000 | [23 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7748 | 45763.4448 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1314 | Pending PREB Approval1314 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
Pending PREB Approval |  | Buildings - Aguadilla Electric Service Center |  |  | Building | Facilities Development & Implementation |  |  | FALSE |  |  | FALSE |  | Discontinued |  |  | 3500000 | 44314 | 44355 |  | 44344 | [19 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7749 | 45764.5011 | Bianca P Vega Torres |  | Rey Roldan Rodríguez | [7 empty] | Pending PREB ApprovalRFI1315 | Pending PREB Approval1315 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
950482 | 108138 | FAASt [Feeder Rebuild #1710-03] (Distribution) | 14F000180000 |  | Distribution |  |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45784 | 05/07/2025 | [7 empty] | 4375640 | 4375640 | [5 empty] | 0 | 4375640 | 4375640 | [11 empty] | 0 | 0 |  |  |  | 45912.6653 | 45785.3988 | Marlina Crespo |  | Marlina Crespo |  |  |  |  | 1 | 1 | 45884 | 950482RFI1316 | 950482 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt # [Distribution Feeder Rebuild #6406-02] (Distribution) |  |  | Distribution – Feeder Rebuild |  |  |  | TRUE | 45869 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7749 | 45820.6436 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1317 | FAASt Number Pending 6001317 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt # [Distribution Feeder Rebuild # 3006-05] (Distribution) |  |  | Distribution – Feeder Rebuild |  |  |  | TRUE | 45869 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7749 | 45820.645 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1318 | FAASt Number Pending 6001318 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt # [Distribution Feeder Rebuild # 6305-03] (Distribution) |  |  | Distribution – Feeder Rebuild |  |  |  | TRUE | 45869 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7749 | 45820.6458 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1319 | FAASt Number Pending 6001319 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt [Feeder Rebuild # 1718-02] (Distribution) |  |  | Distribution – Feeder Rebuild |  |  |  | TRUE | 45869 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7749 | 45820.6463 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1320 | FAASt Number Pending 6001320 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt # [Distribution Feeder Rebuild # 1303-05] (Distribution) |  |  | Distribution – Feeder Rebuild |  |  |  | TRUE | 45869 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7749 | 45820.6466 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1321 | FAASt Number Pending 6001321 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt # [Distribution Feeder Rebuild # 1909-09] (Distribution) |  |  | Distribution – Feeder Rebuild |  |  |  | TRUE | 45900 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7749 | 45820.6469 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1322 | FAASt Number Pending 6001322 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt # [Distribution Feeder Rebuild # 3007-03] (Distribution) |  |  | Distribution – Feeder Rebuild |  |  |  | TRUE | 45900 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7749 | 45820.6476 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1323 | FAASt Number Pending 6001323 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt [Distribution Feeder Rebuild #7805-11] (Distribution) |  |  | Distribution – Feeder Rebuild |  |  |  | TRUE | 45930 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7749 | 45820.6479 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1324 | FAASt Number Pending 6001324 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt # [Distribution Feeder Rebuild # 2603-08] (Distribution) |  |  | Distribution – Feeder Rebuild |  |  |  | TRUE | 45930 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7749 | 45820.6484 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1325 | FAASt Number Pending 6001325 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt # [Distribution Feeder Rebuild # 7805-13] (Distribution) |  |  | Distribution – Feeder Rebuild |  |  |  | TRUE | 45930 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7749 | 45820.6487 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1326 | FAASt Number Pending 6001326 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt [Pole and Conductor Repair – Mayagüez Group 5 - Phase 2 |  |  | Distribution – Pole Replacement |  |  |  | TRUE | 45930 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7749 | 45820.6491 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1327 | FAASt Number Pending 6001327 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt [Pole and Conductor Repair -Arecibo Group 18-19-20- 21 - Phase 3 |  |  | Distribution – Pole Replacement |  |  |  | TRUE | 45930 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7749 | 45820.6496 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1328 | FAASt Number Pending 6001328 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt [Automation Program Group 46] (Distribution) |  |  | Grid Automation |  |  |  | TRUE | 45869 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7749 | 45820.6501 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1329 | FAASt Number Pending 6001329 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt [Automation Program Group 47] (Distribution) |  |  | Grid Automation |  |  |  | TRUE | 45869 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7749 | 45820.6502 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1330 | FAASt Number Pending 6001330 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt [Automation Program Group 48] (Distribution) |  |  | Grid Automation |  |  |  | TRUE | 45869 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7749 | 45820.6502 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1331 | FAASt Number Pending 6001331 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt [Automation Program Group 49] (Distribution) |  |  | Grid Automation |  |  |  | TRUE | 45869 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7749 | 45820.6503 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1332 | FAASt Number Pending 6001332 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt [Automation Program Group 50] (Distribution) |  |  | Grid Automation |  |  |  | TRUE | 45869 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7749 | 45820.6507 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1333 | FAASt Number Pending 6001333 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt [Automation Program Group 51] (Distribution) |  |  | Grid Automation |  |  |  | TRUE | 45869 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7749 | 45820.6508 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1334 | FAASt Number Pending 6001334 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt [Automation Program Group 52] (Distribution) |  |  | Grid Automation |  |  |  | TRUE | 45869 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7749 | 45820.651 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1335 | FAASt Number Pending 6001335 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt [Automation Program Group 53] (Distribution) |  |  | Grid Automation |  |  |  | TRUE | 45869 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7749 | 45820.651 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1336 | FAASt Number Pending 6001336 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt [Automation Program Group 1B-6 Feeders] (Distribution) |  |  | Grid Automation |  |  |  | TRUE | 45869 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7749 | 45820.6513 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1337 | FAASt Number Pending 6001337 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt [Automation Program Group 4B- 6 Feeders] (Distribution) |  |  | Grid Automation |  |  |  | TRUE | 45900 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7749 | 45820.6516 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1338 | FAASt Number Pending 6001338 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt [Automation Program Group 54] (Distribution) |  |  | Grid Automation |  |  |  | TRUE | 45900 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7749 | 45820.6529 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1339 | FAASt Number Pending 6001339 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt [Automation Program Group 56] (Distribution) |  |  | Grid Automation |  |  |  | TRUE | 45900 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7749 | 45820.6531 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1340 | FAASt Number Pending 6001340 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt [Automation Program Group 55] (Distribution) |  |  | Grid Automation |  |  |  | TRUE | 45900 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7749 | 45820.6531 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1341 | FAASt Number Pending 6001341 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt [Automation Program Group 57] (Distribution) |  |  | Grid Automation |  |  |  | TRUE | 45900 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7749 | 45820.6534 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1342 | FAASt Number Pending 6001342 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt [Automation Program Group 58] (Distribution) |  |  | Grid Automation |  |  |  | TRUE | 45900 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7749 | 45820.6535 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1343 | FAASt Number Pending 6001343 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt [Automation Program Group 59] (Distribution) |  |  | Grid Automation |  |  |  | TRUE | 45900 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7749 | 45820.6536 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1344 | FAASt Number Pending 6001344 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt [Automation Program Group 60] (Distribution) |  |  | Grid Automation |  |  |  | TRUE | 45900 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7749 | 45820.654 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1345 | FAASt Number Pending 6001345 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt [Automation Program Group 61] (Distribution) |  |  | Grid Automation |  |  |  | TRUE | 45900 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7749 | 45820.6541 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1346 | FAASt Number Pending 6001346 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt [Automation Program Group 62] (Distribution) |  |  | Grid Automation |  |  |  | TRUE | 45900 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7749 | 45820.6542 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1347 | FAASt Number Pending 6001347 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt [Automation Program Group 63] (Distribution) |  |  | Grid Automation |  |  |  | TRUE | 45900 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7749 | 45820.6544 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1348 | FAASt Number Pending 6001348 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt [Automation Program Group 4C- 7 Feeders] (Distribution) |  |  | Grid Automation |  |  |  | TRUE | 45930 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7749 | 45820.6544 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1349 | FAASt Number Pending 6001349 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt [Automation Program Group 4D7Feeders] (Distribution) |  |  | Grid Automation |  |  |  | TRUE | 45930 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7749 | 45820.6551 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1350 | FAASt Number Pending 6001350 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt [Automation Program Group 2A- 9 Feeders] (Distribution) |  |  | Grid Automation |  |  |  | TRUE | 45930 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7749 | 45820.6552 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1351 | FAASt Number Pending 6001351 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt [Automation Program Group 2B-8 Feeders] (Distribution) |  |  | Grid Automation |  |  |  | TRUE | 45930 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7749 | 45820.6553 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1352 | FAASt Number Pending 6001352 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt [Automation Program Group 2E-9 Feeders] (Distribution) |  |  | Grid Automation |  |  |  | TRUE | 45930 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7749 | 45820.6555 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1353 | FAASt Number Pending 6001353 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt [Automation Program Group 65] (Distribution) |  |  | Grid Automation |  |  |  | TRUE | 45930 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7749 | 45820.6556 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1354 | FAASt Number Pending 6001354 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt [Automation Program Group 66] (Distribution) |  |  | Grid Automation |  |  |  | TRUE | 45930 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7749 | 45820.6557 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1355 | FAASt Number Pending 6001355 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt [Automation Program Group 67] (Distribution) |  |  | Grid Automation |  |  |  | TRUE | 45930 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7749 | 45820.6558 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1356 | FAASt Number Pending 6001356 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt [Automation Program Group 68] (Distribution) |  |  | Grid Automation |  |  |  | TRUE | 45930 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7749 | 45820.6559 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1357 | FAASt Number Pending 6001357 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt [Automation Program Group 69] (Distribution) |  |  | Grid Automation |  |  |  | TRUE | 45930 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7749 | 45820.656 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1358 | FAASt Number Pending 6001358 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt [Automation Program Group 70] (Distribution) |  |  | Grid Automation |  |  |  | TRUE | 45930 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7749 | 45820.6561 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1359 | FAASt Number Pending 6001359 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt [Automation Program Group 71] (Distribution) |  |  | Grid Automation |  |  |  | TRUE | 45930 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7749 | 45820.6563 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1360 | FAASt Number Pending 6001360 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt [Automation Program Group 64] (Distribution) |  |  | Grid Automation |  |  |  | TRUE | 45930 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7749 | 45820.6565 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1361 | FAASt Number Pending 6001361 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | 38 kV Reclosers TLine 1500 FAASt [38kV Recloser TL 1500-Yauco HP to San German TC] (Transmission) |  |  | Grid Automation – 38 kV Reclosers |  |  |  | TRUE | 45869 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7749 | 45820.6574 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1362 | FAASt Number Pending 6001362 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | 38 kV Reclosers TLine 5600 VICTORIA TC to AÑASCO TC] (Transmission) |  |  | Grid Automation – 38 kV Reclosers |  |  |  | TRUE | 45869 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7749 | 45820.6575 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1363 | FAASt Number Pending 6001363 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | 38 kV Reclosers TLine 6500 TORO NEGRO 1 HP to Comerio TC] (Transmission) |  |  | Grid Automation – 38 kV Reclosers |  |  |  | TRUE | 45869 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7749 | 45820.6576 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1364 | FAASt Number Pending 6001364 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | 38 kV Reclosers TLine 8100 YAUCO 1 HP to Canas TC] (Transmission) |  |  | Grid Automation – 38 kV Reclosers |  |  |  | TRUE | 45869 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7749 | 45820.6577 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1365 | FAASt Number Pending 6001365 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | 38kV Reclosers TLine 13400 ACACIAS TC- SAN GERMAN SECT] (Transmission) |  |  | Grid Automation – 38 kV Reclosers |  |  |  | TRUE | 45869 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7749 | 45820.6578 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1366 | FAASt Number Pending 6001366 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | 38 kV Reclosers TLine 800 CAYEY TC to COMSAT SECT] (Transmission) |  |  | Grid Automation – 38 kV Reclosers |  |  |  | TRUE | 45900 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7749 | 45820.6588 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1367 | FAASt Number Pending 6001367 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | 38kV Reclosers TLine 12600 HUMACAO TC to VERDE MAR-] (Transmission) |  |  | Grid Automation – 38 kV Reclosers |  |  |  | TRUE | 45900 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7749 | 45820.6591 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1368 | FAASt Number Pending 6001368 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | 38kV Reclosers TLine 2000 ONCE DE AGOSTO SECT to SAN SEBASTIAN TC] (Transmission) |  |  | Grid Automation – 38 kV Reclosers |  |  |  | TRUE | 45900 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.7749 | 45820.6592 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1369 | FAASt Number Pending 6001369 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | 38kV Reclosers TLine 1600 MAYAGUEZ GP to Acacias TC] (Transmission) |  |  | Grid Automation – 38 kV Reclosers |  |  |  | TRUE | 45930 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.775 | 45820.6599 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1370 | FAASt Number Pending 6001370 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | Recloser TL 100 Ponce to Jobos (Transmission) |  |  | Grid Automation – 38 kV Reclosers |  |  |  | TRUE | 45930 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.775 | 45820.6599 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1371 | FAASt Number Pending 6001371 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | 38kV Reclosers TLine 3700 JOBOS TC to Humacao TC] (Transmission) |  |  | Grid Automation – 38 kV Reclosers |  |  |  | TRUE | 45930 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.775 | 45820.6601 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1372 | FAASt Number Pending 6001372 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt [Transport Network - Group 2] (Telecommunication) |  |  | IT and Telecommunications |  |  |  | TRUE | 45930 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45904.5939 | 45820.6607 | Marlina Crespo |  | Ashleah Dingle | [7 empty] | FAASt Number Pending 600RFI1373 | FAASt Number Pending 6001373 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | Hato Rey – Phase I |  |  | Substation |  |  |  | TRUE | 45900 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45904.5943 | 45820.6613 | Marlina Crespo |  | Ashleah Dingle | [7 empty] | FAASt Number Pending 600RFI1374 | FAASt Number Pending 6001374 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | 36100 - Ciales to Morovis |  |  | Transmission |  |  |  | TRUE | 45900 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.775 | 45820.662 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1375 | FAASt Number Pending 6001375 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | 36100 - Morovis to Unibon |  |  | Transmission |  |  |  | TRUE | 45900 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.775 | 45820.6622 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1376 | FAASt Number Pending 6001376 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt [Transmission Line 36100 Dos Bocas to Ciales] (Transmission) |  |  | Transmission |  |  |  | TRUE | 45930 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.775 | 45820.6623 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1377 | FAASt Number Pending 6001377 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt [Transmission Line 36100 Cana to Bayamón] (Transmission) |  |  | Transmission |  |  |  | TRUE | 45930 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.775 | 45820.665 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1378 | FAASt Number Pending 6001378 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | 36100 - Unibon to Monterrey |  |  | Transmission |  |  |  | TRUE | 45930 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.775 | 45820.6652 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1379 | FAASt Number Pending 6001379 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | 36100 - Monterrey to Pina |  |  | Transmission |  |  |  | TRUE | 45930 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.775 | 45820.6653 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1380 | FAASt Number Pending 6001380 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | 2200 - Manatí to Vega Baja |  |  | Transmission |  |  |  | TRUE | 45930 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.775 | 45820.6655 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1381 | FAASt Number Pending 6001381 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | 2200 - Vega Baja to San Demetrio |  |  | Transmission |  |  |  | TRUE | 45930 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.775 | 45820.6656 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1382 | FAASt Number Pending 6001382 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt [Transmission Priority Pole Replacement Program Line 1600 LEON SECTACACIAS TC] (Transmission) |  |  | Transmission – Pole Replacement |  |  |  | TRUE | 45869 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.775 | 45820.6661 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1383 | FAASt Number Pending 6001383 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt [Transmission Priority Pole Replacement Program Line 4800 Santa Isabel TC - Santa Isabel Sect] (Transmission) |  |  | Transmission – Pole Replacement |  |  |  | TRUE | 45869 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.775 | 45820.6663 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1384 | FAASt Number Pending 6001384 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt [Transmission Priority Pole Replacement Program Line 9900 - RIO BLANCO HPHUMACAO SECT] (Transmission) |  |  | Transmission – Pole Replacement |  |  |  | TRUE | 45869 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.775 | 45820.6664 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1385 | FAASt Number Pending 6001385 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt [Transmission Priority Pole Replacement Program Line 2000 - ONCE DE AGOSTO SECT - SAN SEBASTIAN TC] (Transmission) |  |  | Transmission – Pole Replacement |  |  |  | TRUE | 45869 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.775 | 45820.6665 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1386 | FAASt Number Pending 6001386 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt [Transmission Priority Pole Replacement Program Line Arecibo Region Group 1 (Transmission) |  |  | Transmission – Pole Replacement |  |  |  | TRUE | 45869 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.775 | 45820.6666 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1387 | FAASt Number Pending 6001387 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt [Transmission Priority Pole Replacement Program Line San Juan Region Group 1] (Transmission) |  |  | Transmission – Pole Replacement |  |  |  | TRUE | 45900 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.775 | 45820.6689 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1388 | FAASt Number Pending 6001388 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt [Transmission Priority Pole Replacement Program Line Mayagüez Region Group1] (Transmission) |  |  | Transmission – Pole Replacement |  |  |  | TRUE | 45930 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.775 | 45820.6699 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1389 | FAASt Number Pending 6001389 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt [Transmission Priority Pole Replacement Program Line 1200 SAN GERMAN SECT-SAN GERMAN TCYAUCO 2 HP] (Transmission) |  |  | Transmission – Pole Replacement |  |  |  | TRUE | 45930 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.775 | 45820.67 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1390 | FAASt Number Pending 6001390 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt [Transmission Priority Pole Replacement Program Line 200 Ponce TC -Santa Isabel Sect] (Transmission) |  |  | Transmission – Pole Replacement |  |  |  | TRUE | 45930 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.775 | 45820.67 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1391 | FAASt Number Pending 6001391 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt [Transmission Priority Pole Replacement Program Line 4800 Santa Isabel TC - Santa Isabel Sect] (Transmission) |  |  | Transmission – Pole Replacement |  |  |  | TRUE | 45930 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.775 | 45820.67 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1392 | FAASt Number Pending 6001392 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt [Transmission Priority Pole Replacement Program Line 10700 - HATO TEJAS TCHATO TEJAS SECT] (Transmission) |  |  | Transmission – Pole Replacement |  |  |  | TRUE | 45930 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.775 | 45820.67 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1393 | FAASt Number Pending 6001393 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt [Transmission Priority Pole Replacement Program Line 18400 - BARRANQUITAS TC-EL ABANICO] (Transmission) |  |  | Transmission – Pole Replacement |  |  |  | TRUE | 45930 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.775 | 45820.67 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1394 | FAASt Number Pending 6001394 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt [Transmission Priority Pole Replacement Program Line 2200 -BARCELONETA TC-MANATI TC] (Transmission) |  |  | Transmission – Pole Replacement |  |  |  | TRUE | 45930 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.775 | 45820.67 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1395 | FAASt Number Pending 6001395 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt [Transmission Priority Pole Replacement Program Line 2200 - VEGA BAJA TCVEGA ALTA SECT] (Transmission) |  |  | Transmission – Pole Replacement |  |  |  | TRUE | 45930 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.775 | 45820.6708 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1396 | FAASt Number Pending 6001396 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt [Transmission Priority Pole Replacement Program Line 9900 - RIO BLANCO HPHUMACAO SECT] (Transmission) |  |  | Transmission – Pole Replacement |  |  |  | TRUE | 45930 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.775 | 45820.671 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1397 | FAASt Number Pending 6001397 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt [Transmission Priority Pole Replacement Program Line 1600 - SAN GERMAN SECT-SAN GERMAN TC] (Transmission) |  |  | Transmission – Pole Replacement |  |  |  | TRUE | 45930 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.775 | 45820.6713 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1398 | FAASt Number Pending 6001398 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt [Transmission Priority Pole Replacement Program Line 8100 - YAUCO 1 HPADJUNTAS TO] (Transmission) |  |  | Transmission – Pole Replacement |  |  |  | TRUE | 45930 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.775 | 45820.6714 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1399 | FAASt Number Pending 6001399 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt [Transmission Priority Pole Replacement Program Line 15900-VICTORIA TCAGUADA TO] (Transmission) |  |  | Transmission – Pole Replacement |  |  |  | TRUE | 45930 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.775 | 45820.6715 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1400 | FAASt Number Pending 6001400 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
FAASt Number Pending 600 |  | FAASt [Transmission Priority Pole Replacement Program Line 2700 - Aguadilla Hospital Distrito Sect - Mora TC] (Transmission) |  |  | Transmission – Pole Replacement |  |  |  | TRUE | 45930 |  | FALSE | [28 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  |  | 45856.775 | 45820.6716 | Marlina Crespo |  | Rey Roldan Rodríguez | [7 empty] | FAASt Number Pending 600RFI1401 | FAASt Number Pending 6001401 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
956353 | 108158 | FAASt [Arecibo Region 2 Transmission Line 36100 – Dos Bocas HP to Barrio Pina] (Vegetation) | 15F020100000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation |  | TRUE |  | TRUE | 45869 | Current | FALSE | [12 empty] | 45826 | 6/18/2025 |  | 45834 | 45870 | 45888 | 45881 | 8/12/2025 - Field EHP - Historic: Initial Review 08/19/2025. |  | 37008593.33 | 37008593.33 | 27126607.1 | 757937.79 |  | 9124048.44 | 2079717.62 | 25046889.48 | 36250655.54 | 37008593.33 |  |  | 45917 |  | 3756065 | 3756065 | [5 empty] | 3756065 | 3756065 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1672/Signed%20956353%20FAASt%20Arecibo%20Region%202%20Transmission%20Line%2036100%20%E2%80%93%20Dos%20Bocas%20HP%20to%20Barrio%20Pina%20(Vegetation).pdf?web=1 | 07/25/2025 01:08 PM AST - Project submitted as 428/406 on 06.26.2025 for FEMA review. Projects will be amended to "428 only" and resubmitted to FEMA with revised costs factoring in additional miles of assessments from Vendors. 8/22/2025 9:02 AM EDT - Field EHP: This project is identified as part of the Department of Energy Emergency Declaration under Order 202-25-2 pursuant to Section 202(c) of the Federal Power Act (FPA). Due to pending clarification of several details between the DOE and the Advisory Council for Historic Preservation (ACHP), these projects will remain in our queue until they are addressed. Once more information is available on the progress of these discussions. ECD: to be determine. | 46078.604 | 45820.6726 | Marlina Crespo |  | Ashleah Dingle |  |  | 116166.96 | 0 | 1.0209 | 1 |  | 956353RFI1402 | 956353 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
956342 | 108153 | FAASt [Arecibo Region 2 Transmission Line 36400 – Ponce TC to Dos Bocas HP] (Vegetation) | 15F020110000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation |  | TRUE |  | TRUE | 45869 | Current | FALSE | [12 empty] | 45826 | 6/18/2025 |  | 45834 | 45870 | 45891 | 45884 | 8/15/2025 11:02 AM EDT - Field EHP: Previous EHP Status applies. ECD 08/22/2025. |  | 44397505.59 | 44397505.59 | 32542541.69 | 909263.06 |  | 10945700.85 | 2494941.49 | 30047600.2 | 43488242.54 | 44397505.6 |  |  | 45917 |  | 4093248 | 4093248 | [5 empty] | 4093248 | 4093248 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1673/Signed%20956342%20FAASt%20Arecibo%20Region%202%20Transmission%20Line%2036400%20%E2%80%93%20Ponce%20TC%20to%20Dos%20Bocas%20HP%20(Vegetation).pdf?web=1 | 07/25/2025 01:06 PM AST - Project submitted as 428/406 on 06.26.2025 for FEMA review. Projects will be amended to "428 only" and resubmitted to FEMA with revised costs factoring in additional miles of assessments from Vendors. 8/15/2025 9:15 AM- The PR Electric Power Authority, as the eligible entity (subrecipient), has submitted a consolidated plan for the use of the remaining budget available in the FEMA Accelerated Awards Strategy Project (136271) Fixed Cost Award. This FAASt sub-project has been identified in the list and it will be processed in the national workflow accordingly. 8/15/2025 11:02 AM EDT - Field EHP: Previous EHP Status applies. ECD 08/22/2025. 8/22/2025 8:55 AM AST - Field EHP - Historic: This project is identified as part of the Department of Energy Emergency Declaration under Order 202-25-2 pursuant to Section 202(c) of the Federal Power Act (FPA). Due to pending clarification of several details between the DOE and the Advisory Council for Historic Preservation (ACHP), these projects will remain in our queue until they are addressed. EDC To be determined. | 46078.6034 | 45820.6727 | Marlina Crespo |  | Ashleah Dingle |  |  | 126595.31 | 0 | 1.0209 | 1 |  | 956342RFI1403 | 956342 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
956348 | 108156 | FAASt [Bayamon Region 3 Transmission Line 10000 – Bayamon Pueblo to Magnolia TO] (Vegetation) | 15F020090000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation |  | TRUE |  | TRUE | 45869 | Current | FALSE | [12 empty] | 45826 | 6/18/2025 |  | 45834 | 46057 | 46052 | 46014 | 12/23/2025 - Field EHP: In review. Drafting documentation for OFA CATEX approval. ECD 1/30/2026 |  | 1193764.74 | 1193764.74 | 875007.19 | 24448.38 |  | 294309.16 | 67084.2 | 807922.99 | 1169316.35 | 1193764.73 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1674/Signed%20956348%20FAASt%20Bayamon%20Region%203%20Transmission%20Line%2010000%20%E2%80%93%20Bayamon%20Pueblo%20to%20Magnolia%20TO%20(Vegetation).pdf?web=1 |  | 46078.6036 | 45820.6728 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 1.0209 | 1 |  | 956348RFI1404 | 956348 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
956349 | 108157 | FAASt [San Juan Region 1 Transmission Line 36800 – Canovanas TC to Palmer TC] (Vegetation) | 15F020120000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation |  | TRUE |  | TRUE | 45869 | Current | FALSE | [12 empty] | 45826 | 6/18/2025 |  | 45834 | 46071 | 46087 | 46073 | 2/20/2026- Field EHP: In Initial Review. Expected Completion Date (ECD) 3/6/2026 |  | 13853576.49 | 13853576.49 | 10154412.56 | 283721.94 |  | 3415441.98 | 778509.08 | 9375903.48 | 13569854.54 | 13853576.48 |  |  | 45917 |  | 1364416 | 1364416 | [5 empty] | 1364416 | 1364416 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1675/Signed%20956349%20FAASt%20San%20Juan%20Region%201%20Transmission%20Line%2036800%20%E2%80%93%20Canovanas%20TC%20to%20Palmer%20TC%20(Vegetation).pdf?web=1 | 07/25/2025 01:07 PM AST - Project submitted as 428/406 on 06.26.2025 for FEMA review. Projects will be amended to "428 only" and resubmitted to FEMA with revised costs factoring in additional miles of assessments from Vendors. 8/15/2025 11:03 AM EDT - Field EHP: Previous EHP Status applies. ECD 08/22/2025. 8/22/2025 11:33 AM AST -Field EHP - Historic: This project is identified as part of the Department of Energy Emergency Declaration under Order 202-25-2 pursuant to Section 202(c) of the Federal Power Act (FPA). Due to pending clarification of several details between the DOE and the Advisory Council for Historic Preservation (ACHP), these projects will remain in our queue until they are addressed. EDC To be determined. | 46078.6038 | 45820.673 | Marlina Crespo |  | Ashleah Dingle |  |  | 42198.44 | 0 | 1.0209 | 1 |  | 956349RFI1405 | 956349 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
956345 | 108155 | FAASt [Arecibo Region 2 Transmission Line 2400 – Dos Bocas HP to Coronillas 2] (Vegetation) | 15F020000000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation |  | TRUE |  | TRUE | 45869 | Current | FALSE | [12 empty] | 45826 | 6/18/2025 |  | 45834 | 46057 | 46052 | 46014 | 12/23/2025 - Field EHP: In review. Drafting documentation for OFA CATEX approval. ECD 1/30/2026 |  | 7324652.18 | 7324652.18 | 5368833.09 | 150009.25 |  | 1805809.83 | 411612.69 | 4957220.4 | 7174642.92 | 7324652.17 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1676/Signed%2095634%20FAASt%20Arecibo%20Region%202%20Transmission%20Line%202400%20Dos%20Bocas%20HP%20to%20Coronillas%202%20Vegetation.pdf?web=1 |  | 46078.6035 | 45820.6731 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 1.0209 | 1 |  | 956345RFI1406 | 956345 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
956357 | 108160 | FAASt [Mayaguez Region 5 Transmission Line 1900 – Dos Bocas HP to San Sebastian TC] (Vegetation) | 15F019980000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation |  | TRUE |  | TRUE | 45869 | Current | FALSE | [12 empty] | 45826 | 06/18/2025 |  | 45834 | 46057 | 46073 | 46063 | 2/10/2026 - Field EHP environmental: “In Initial Review”. ECD 02/20/2026. |  | 12705648.38 | 12705648.38 | 9313002.71 | 260212.32 |  | 3132433.36 | 714000.65 | 8599002.06 | 12445436.07 | 12705648.39 | [11 empty] | 0 | 0 |  |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1677/956357%20-%20FAASt%20%5BMayaguez%20Region%205%20Line%201900%20(38kV)%20%E2%80%93Dos%20Bocas%20HP%20to%20San%20Sebastian%20TC%5D%20(Vegetation)%20DSOW%20Rev%203.pdf?web=1 | 46078.6042 | 45820.6732 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 1.0209 | 1 |  | 956357RFI1407 | 956357 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
956343 | 108154 | FAASt [Ponce Region 6 Transmission Line 4800 – Toro Negro to Aibonito, Santa Isabel] (Vegetation) | 15F020040000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation |  | TRUE |  | TRUE | 45869 | Current | FALSE | [12 empty] | 45826 | 6/18/2025 |  | 45834 | 46057 | 45966 | 45965 | 11/4/2025 - Field EHP - Environmental: In Review. Expected Completion Date (ECD) 11/05/2025 |  | 21381353.56 | 21381353.56 | 15672132.45 | 437891.18 |  | 5271329.93 | 1201536.52 | 14470595.93 | 20943462.38 | 21381353.56 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1678/956343-FAASt%20[Ponce%20Region%206%20Line%204800%20(38kV)%20%e2%80%93%20Toro%20Negro%20to%20Aibonito,%20Santa%20Isabel]%20(Vegetation)%20Rev3.pdf | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1678/956343%20-FAASt%20%5BPonce%20Region%206%20Line%204800%20(38kV)%20%E2%80%93%20Toro%20Negro%20to%20Aibonito,%20Santa%20Isabel%5D%20(Vegetation)%20DSOW%20REV%202.pdf?web=1 | 46078.6034 | 45820.6734 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 1.0209 | 1 |  | 956343RFI1408 | 956343 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
956356 | 108159 | FAASt [Ponce Region 6 Transmission Line 39000 – Aguas Buenas Substation to Hacienda San Jose] (Vegetation) | 15F020130000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation |  | TRUE |  | TRUE | 45869 | Current | FALSE | [12 empty] | 45826 | 6/18/2025 |  | 45834 | 46010 | 45891 | 45881 | 8/22/2025 - Field EHP - Historic: This project is identified as part of the Department of Energy Emergency Declaration under Order 202-25-2 pursuant to Section 202(c) of the Federal Power Act (FPA). Due to pending clarification of several details between the DOE and the Advisory Council for Historic Preservation (ACHP), these projects will remain in our queue until they are addressed. EDC To be determined |  | 3583135.14 | 3583135.14 | 0 | 30566.17 |  | 988951.38 | 0 | 0 | 988951.38 | 1019517.55 |  |  | 45917 | 3/1/2026 | 325421.1 | 325421.1 | 388903.06 | 86484.8 |  |  |  | 388903.06 | 86484.8 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1679/PW%20108159%20PRJ_MultiVersionReport_956356_20260302.pdf?web=1 | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1679/956356%20FAASt%20%5BPonce%20Region%206%20Line%2039000%20(115kV)%20%E2%80%93%20Aguas%20Buenas%20Substation%20to%20Hacienda%20San%20Jose%5D%20(Vegetation)%20DSOW%20V1%20rev.1.pdf?web=1 07/25/2025 01:09 PM AST - Project submitted as "428 only" on 07.24.2025 as per FEMA guidance for expedited obligation. Project is under FEMA review. 07/25/2025 10:48 AM AST - LUMA uploaded on 07.24.2025 a revised DSOW and LPCE as a "428 only" oriented project in alignment to a request by COR3 and FEMA to do so in support of the DOE directive and a commitment from FEMA to expedite obligations of vegetation related projects. 8/12/2025 9:17 AM - The PR Electric Power Authority, as the eligible entity (subrecipient), has submitted a consolidated plan for the use of the remaining budget available in the FEMA Accelerated Awards Strategy Project (136271) Fixed Cost Award. This FAASt sub-project has been identified in the list and it will be processed in the national workflow accordingly. 8/15/2025 10:47 AM EDT - Field EHP - Historic: Previous Status Applies. This project is identified as part of the Department of Energy Emergency Declaration under Order 202-25-2 pursuant to Section 202(c) of the Federal Power Act (FPA). Due to pending clarification of several details between the DOE and the Advisory Council for Historic Preservation (ACHP), these projects will remain in our queue until they are addressed. Once more information is available on the progress of these discussions, an ECD will be provided. | 46083.6846 | 45820.6735 | Marlina Crespo |  | Marlina Crespo |  |  | 9409.44 |  | 3.6232 | 1 |  | 956356RFI1409 | 956356 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 302418.26
954184 | 108144 | FAASt [Carolina ESC Building Repairs] (Buildings) |  |  | Building |  |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45824 | 06/16/2025 |  | 45824 | 45845 | 45875 | 45861 |  |  | 2747126.23 | 2747126.23 | 0 | 293002.71 |  | 2454123.52 | 0 | 0 | 2454123.52 | 2747126.23 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1681/954184-DR4339PR-Carolina%20Electric%20Service%20Center%20Detailed%20Scope%20of%20Work%20-%20DRAFT.docx?web=1 |  | 45980.5912 | 45826.6289 | Marlina Crespo |  | Marlina Crespo |  |  |  |  | 1.1194 | 1 | 45880 | 954184RFI1410 | 954184 | 0 | 0 | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
956341 | 108152 | FAASt [Ponce Region 6 Feeder 5803-02] (Vegetation) | 15F020060000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation |  | TRUE |  | FALSE |  | Current | FALSE | [12 empty] | 45826 | 06/18/2025 |  | 45835 | 45933 | 46052 | 46014 | 12/23/2025 - Field EHP: In review. Drafting documentation for OFA CATEX approval. ECD 1/30/2026. |  | 97672.18 | 97672.18 | 71591.83 | 2000.35 |  | 24080 | 5488.7 | 66103.13 | 95671.83 | 97672.18 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1682/956341%20FAASt%20Single%20Line%20DSOW%20Feeder%205803-02%20Ponce%20Region%206%206-27-25.pdf?web=1 | 7/25/2025 - Project is under FEMA review and submitted as 428/406 as a single feeder vegetation clearing project for expedited obligation by FEMA. 8/12/2025 9:14 AM AST - The PR Electric Power Authority, as the eligible entity (subrecipient), has submitted a consolidated plan for the use of the remaining budget available in the FEMA Accelerated Awards Strategy Project (136271) Fixed Cost Award. This FAASt sub-project has been identified in the list and it will be processed in the national workflow accordingly. | 46078.6034 | 45826.6682 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 1.0209 | 1 |  | 956341RFI1411 | 956341 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
956340 | 108151 | FAASt [Ponce Region 6 Feeder 5602-02] (Vegetation) | 15F020050000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation |  | TRUE |  | FALSE |  | Current | FALSE | [12 empty] | 45826 | 6/18/2025 |  | 45835 | 45931 | 46142 | 46073 | 2/20/2026- Field EHP: Project may require higher level NEPA review. ECD updated to 4/30/2026. |  | 6589894.87 | 6589894.87 | 4830269.73 | 1624663.76 |  | 134961.38 | 4830269.73 | 0 | 4965231.11 | 6589894.87 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1683/956340%20FAASt%20Single%20Line%20DSOW%20Feeder%205602-02%20Ponce%20Region%206%206-27-25.pdf?web=1 | 7/25/2025 - Project is under FEMA review and submitted as 428/406 as a single feeder vegetation clearing project for expedited obligation by FEMA. 8/12/2025 9:14 AM AST - The PR Electric Power Authority, as the eligible entity (subrecipient), has submitted a consolidated plan for the use of the remaining budget available in the FEMA Accelerated Awards Strategy Project (136271) Fixed Cost Award. This FAASt sub-project has been identified in the list and it will be processed in the national workflow accordingly. | 46090.6921 | 45826.684 | Maria Mujica Gonzalez |  | Maria Mujica Gonzalez |  |  |  |  | 1.3272 | 1 |  | 956340RFI1412 | 956340 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
956339 | 108150 | FAASt [Caguas Region 4 - Feeder 3301-01] (Vegetation) | 15F020030000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation |  | TRUE |  | FALSE |  | Current | FALSE | [12 empty] | 45826 | 6/18/2025 |  | 45835 | 45936 | 46087 | 46022 | 12/31/2025 - Field EHP - Environmental: ESA Consultation letter submitted to USFWS on 12/30/2025. Waiting for response. ECD 03/06/2026. |  | 12004333.95 | 12004333.95 | 8798952.37 | 2959532.24 |  | 245849.34 | 8798952.37 | 0 | 9044801.71 | 12004333.95 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1684/956339%20FAASt%20Single%20Line%20DSOW%20Feeder%203301-01%20Caguas%20Region%204%206-27-25.pdf?web=1 | 7/25/2025 - Project is under FEMA review and submitted as 428/406 as a single feeder vegetation clearing project for expedited obligation by FEMA. 8/12/2025 9:14 AM AST - The PR Electric Power Authority, as the eligible entity (subrecipient), has submitted a consolidated plan for the use of the remaining budget available in the FEMA Accelerated Awards Strategy Project (136271) Fixed Cost Award. This FAASt sub-project has been identified in the list and it will be processed in the national workflow accordingly. | 46078.6032 | 45826.6846 | Maria Mujica Gonzalez |  | Ashleah Dingle |  |  |  |  | 1.3272 | 1 |  | 956339RFI1413 | 956339 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
956337 | 108149 | FAASt [Mayaguez Region 5 Feeder 6012-02] (Vegetation) | 15F020070000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation |  | TRUE |  | FALSE |  | Current | FALSE | [12 empty] | 45826 | 6/18/2025 |  | 45835 | 45936 | 46059 | 46052 | 1/30/2026 - In review, drafting documentation for OFA CATEX approval, ECD 2/6/2026. |  | 7303974.78 | 7303974.78 | 5353676.97 | 149585.76 |  | 1800712.05 | 410450.73 | 4943226.24 | 7154389.02 | 7303974.78 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1685/956337%20FAASt%20Single%20Line%20DSOW%20Feeder%206012-02%20Mayaguez%20Region%205%206-27-25.pdf?web=1 | 7/25/2025 - Project is under FEMA review and submitted as 428/406 as a single feeder vegetation clearing project for expedited obligation by FEMA. 8/12/2025 9:14 AM AST - The PR Electric Power Authority, as the eligible entity (subrecipient), has submitted a consolidated plan for the use of the remaining budget available in the FEMA Accelerated Awards Strategy Project (136271) Fixed Cost Award. This FAASt sub-project has been identified in the list and it will be processed in the national workflow accordingly. | 46078.603 | 45826.6862 | Maria Mujica Gonzalez |  | Ashleah Dingle |  |  |  |  | 1.0209 | 1 |  | 956337RFI1414 | 956337 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
956335 | 108148 | FAASt [San Juan Region 1 - Feeder 2301-02] (Vegetation) | 15F019990000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation |  | TRUE |  | FALSE |  | Current | FALSE | [12 empty] | 45826 | 6/18/2025 |  | 45835 | 45933 | 46142 | 46073 | 2/20/2026- Field EHP: WSR response letter received on 02/10/2025, under review by EHP specialist. ESA Consultation letter submitted to USFWS on 02/06/2026, waiting for response. Project may require higher level NEPA review. ECD 4/30/2026. |  | 7503713.1 | 7503713.1 | 5500081.4 | 153676.43 |  | 1849955.27 | 421675.11 | 5078406.29 | 7350036.67 | 7503713.1 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1686/956335%20FAASt%20Single%20Line%20DSOW%20Feeder%202301-02%20San%20Juan%20Region%201%206-27-25.pdf?web=1 | 7/25/2025- Project is under FEMA review and submitted as 428/406 as a single feeder vegetation clearing project for expedited obligation by FEMA. 8/12/2025 9:14 AM AST - The PR Electric Power Authority, as the eligible entity (subrecipient), has submitted a consolidated plan for the use of the remaining budget available in the FEMA Accelerated Awards Strategy Project (136271) Fixed Cost Award. This FAASt sub-project has been identified in the list and it will be processed in the national workflow accordingly. | 46090.686 | 45826.687 | Maria Mujica Gonzalez |  | Maria Mujica Gonzalez |  |  |  |  | 1.0209 | 1 |  | 956335RFI1415 | 956335 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
956332 | 108147 | FAASt [San Juan Region 1 - Feeder 2401-01] (Vegetation) | 15F020010000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation |  | TRUE |  | FALSE |  | Current | FALSE | [12 empty] | 45826 | 6/18/2025 |  | 45835 |  | 46142 | 46073 | 2/20/2026- Field EHP: WSR response letter received on 02/10/2025, under review by EHP specialist. ESA Consultation letter submitted to USFWS on 02/06/2026, waiting for response. Project may require higher level NEPA review. ECD 4/30/2026. |  | 11073220.77 | 11073220.77 | 8286164.87 | 231521.7 |  | 2787055.9 | 635275.99 | 7650888.88 | 11073220.77 | 11304742.47 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1687/956332%20FAASt%20Single%20Line%20DSOW%20Feeder%202401-01%20San%20Juan%20Region%201%206-27-25.pdf?web=1 | 7/25/2025 - Project is under FEMA review and submitted as 428/406 as a single feeder vegetation clearing project for expedited obligation by FEMA. 8/12/2025 9:14 AM AST - The PR Electric Power Authority, as the eligible entity (subrecipient), has submitted a consolidated plan for the use of the remaining budget available in the FEMA Accelerated Awards Strategy Project (136271) Fixed Cost Award. This FAASt sub-project has been identified in the list and it will be processed in the national workflow accordingly. | 46090.6906 | 45826.6878 | Maria Mujica Gonzalez |  | Maria Mujica Gonzalez |  |  |  |  | 1 | 1 |  | 956332RFI1416 | 956332 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
956331 | 108146 | FAASt [Mayaguez Region 5 Feeder 6014-02] (Vegetation) | 15F020080000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation |  | TRUE |  | FALSE |  | Current | FALSE | [12 empty] | 45826 | 6/18/2025 |  | 45835 | 45931 | 46059 | 46052 | 1/30/2026 - In review, drafting documentation for OFA CATEX approval, ECD 2/6/2026. |  | 8021552.35 | 8021552.35 | 5879647.9 | 1977622.66 |  | 164281.79 | 5879647.9 | 0 | 6043929.69 | 8021552.35 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1688/956331%20FAASt%20Single%20Line%20DSOW%20Feeder%206014-02%20Mayaguez%20Region%205%206-27-25.pdf?web=1 | 7/25/2025- Project is under FEMA review and submitted as 428/406 as a single feeder vegetation clearing project for expedited obligation by FEMA. 8/12/2025 9:14 AM AST - The PR Electric Power Authority, as the eligible entity (subrecipient), has submitted a consolidated plan for the use of the remaining budget available in the FEMA Accelerated Awards Strategy Project (136271) Fixed Cost Award. This FAASt sub-project has been identified in the list and it will be processed in the national workflow accordingly. | 46078.6029 | 45826.6885 | Maria Mujica Gonzalez |  | Ashleah Dingle |  |  |  |  | 1.3272 | 1 |  | 956331RFI1417 | 956331 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
956330 | 108145 | FAASt [Caguas Region 4 - Feeder 3007-03] (Vegetation) | 15F020020000 | PBOP07 - Veg.Mngmt&Cap.Clear.Impl | Vegetation |  | TRUE |  | FALSE |  | Current | FALSE | [12 empty] | 45826 | 6/18/2025 |  | 45835 | 45938 | 46059 | 46052 | 1/30/2026 - Field EHP: In review, drafting documentation for OFA CATEX approval, ECD 2/6/2026 |  | 7985860.15 | 7985860.15 | 5853486.17 | 163550.83 |  | 1968823.15 | 448769.62 | 5404716.55 | 7822309.32 | 7985860.15 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1689/956330%20FAASt%20Single%20Line%20DSOW%20Feeder%203007-03%20Caguas%20Region%204%206-27-25.pdf?web=1 | 7/25/2025- Project is under FEMA review and submitted as 428/406 as a single feeder vegetation clearing project for expedited obligation by FEMA. 8/12/2025 9:13 AM AST - The PR Electric Power Authority, as the eligible entity (subrecipient), has submitted a consolidated plan for the use of the remaining budget available in the FEMA Accelerated Awards Strategy Project (136271) Fixed Cost Award. This FAASt sub-project has been identified in the list and it will be processed in the national workflow accordingly. | 46078.6029 | 45826.6896 | Maria Mujica Gonzalez |  | Ashleah Dingle |  |  |  |  | 1.0209 | 1 |  | 956330RFI1418 | 956330 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
956593 | 108161 | FAASt [Factor Sect 8014 Transformer Replacement] (Substation) |  | PBUT07 - Substation Reliability | Substation |  | TRUE |  | FALSE |  | Current | FALSE | [12 empty] | 45831 | 06/23/2025 |  | 45831 |  | 45875 | 45863 | Field EHP - Environmental: In review. Amended Expected Completion Date (ECD) 08/06/2025. |  | 5907319.61 | 5907319.61 | 0 | 414861.11 |  | 5492458.5 | 0 | 0 | 5492458.5 | 5907319.61 |  |  | 45922 |  | 3751193.63 | 3751193.63 |  |  |  | 1741264.87 |  | 3751193.63 | 3751193.63 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1690/DR4339PR%20-%20Detail%20Scope%20of%20Work%20for%20Factor%20Sectionalizer%20signed%20(6.19.2025)%20(003).pdf?web=1 |  | 46078.6049 | 45832.4071 | Marlina Crespo |  | Ashleah Dingle |  |  | 414861.11 | 0 | 1.0755 | 1 |  | 956593RFI1419 | 956593 | 1741264.87 |  | 1741264.87 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
956782 | 108162 | Feeder Rebuild #6802-04 (Distribution) |  | PBUT06 - Distr Line Rebuild | Distribution – Feeder Rebuild |  |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | [10 empty] | 45833 | 06/25/2025 |  | 45833 | [5 empty] | 21957625.63 | 21957625.63 | 2769954.18 | 2489006.38 |  | 19468619.25 | 313928.68 | 2456025.5 | 22238573.43 | 24727579.81 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1691/956782-DR4339PR-6802-04%20DSOW%20Full%20428-406_06212025%20Rev%200.pdf?web=1 |  | 46078.6055 | 45834.3997 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 0.98737 | 1 | 45884 | 956782RFI1420 | 956782 | 2239396.69 | 615641.23 | 2855037.92 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
957578 | 108163 | FAASt [Costa Sur TC Underground Cable Failure Replacement on Transformer Lead Bank #2] (Substation) |  | PBUT08 - Substation Rebuilds | Substation |  | TRUE |  | FALSE |  | Current | FALSE | [12 empty] | 45845 | 07/07/2025 |  | 45853 |  | 45891 | 45876 | 7/31/2025 - EHP final review. ECD: 8/07/2025. |  | 1250845.17 | 1250845.17 | 0 | 141856.25 |  | 1108989.51 | 0 | 0 | 1108989.51 | 1250845.76 |  |  | 45917 |  | 1108990 | 1108990 | [5 empty] | 1108990 | 1108990 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1692/957578%20-%20Costa%20Sur%20TC%20Underground%20Cable%20Failure%20Replacement%20on%20Transformer%20Lead%20Bank%202%20DSOW%20(7.15.2025)%20signed.pdf?web=1 | 7/31/2025 - EHP final review. ECD: 8/07/2025. 8/13/2025 9:47 AM AST - The PR Electric Power Authority, as the eligible entity (subrecipient), has submitted a consolidated plan for the use of the remaining budget available in the FEMA Accelerated Awards Strategy Project (136271) Fixed Cost Award. This FAASt sub-project has been identified in the list and it will be processed in the national workflow accordingly | 46078.6058 | 45847.3912 | Marlina Crespo |  | Ashleah Dingle |  |  | 141856.25 | 0 | 1.1279 | 1 |  | 957578RFI1421 | 957578 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
958367 | 108164 | FAASt [Feeder Rebuild #6603-01] (Distribution) |  | PBUT06 - Distr Line Rebuild | Distribution |  |  |  | FALSE |  |  | TRUE | Involuntarily Withdrawal Status in Grants Portal | Discontinued | FALSE | [9 empty] | 45853 | 07/15/2025 |  | 45853 | [5 empty] | 14474191.76 | 14474191.76 | 1172038.62 | 2885305.81 |  | 11588885.95 | 233606.49 | 938432.13 | 12760924.57 | 15646230.38 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1694/958367-DR4339PR-6603-01%20Detail%20Scope%20of%20Work%20Full%20428%20-%20406%20Rev_0.pdf?web=1 |  | 46078.6059 | 45854.4046 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 1.1343 | 1 | 45884 | qwer506 | 958367 | 1224980.72 | 253175.12 | 1478155.84 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0
1064452 | 108242 | FAASt [Priority Pole Replacement Program Line 800 Comsat Sect – Cidra Sect] / Former project 753781(Transmission) |  | PBUT13 - T Priority Pole Repl | Transmission |  | TRUE |  | FALSE |  |  | FALSE | [12 empty] | 46048 | 01/26/2026 |  | 46048 | [5 empty] | 1569945.94 | 1569945.94 | 33695.78 | 85434.18 | 44078.65 | 640758.24 | 6440.37 | 27255.41 | 674454.02 | 759888.2 | [11 empty] | 0 | 0 |  | https://aeepr.sharepoint.com/sites/Test4552/Lists/ISOW%20%20DSOW%20Tracker/Attachments/1696/753781-DR4339PR-Detailed%20SOW-TPole%20Line%20800%20Comsat%20Sect%20%e2%80%93%20Cidra%20Sect_8.13.2025.pdf | DSOW submitted to FOMB on 1/26/2026 | 46097.4395 | 46051.6933 | Marlina Crespo |  | Ashleah Dingle |  |  |  |  | 2.3277 | 1 |  |  | 1064452 |  |  | 0 |  | Item | sites/Test4552/Lists/ISOW DSOW Tracker | 0

## FAASt - Obligations Summary (3) (hidden)
10704730227.54
FAASt-Consolidated Plan Summary
| Summary | 10429730227.54 |  |  | *Including new version with Insurance deductions
|  | Reductions (Obligations) as of 1-10-26 | Selected Projects under Formulation * | Estimated FAASt Total
A | A&E - Mat | -4131897437.5 |  | -4209258262.63
B | PREPA | -181993398.7 | -1325441298.81 | -1507434697.51
C | LUMA | -2023455438.1378 | -873428908.2 | -2896884346.3378
D | Genera | -918915560.26 | -356903591.95 | -1275819152.21
| Total Reductions | -7256261834.5978 | -2555773798.96 | -9812035633.5578 |  |  |  | 303332908.92
| Remaining Balance 6099 | 3173468392.9422 | 617694593.9822 | 617694593.9822 | Remaining Estimated Balance |  |  | 921027502.9022
|  | 2856121553.648 | * See each respective tab for project details
| Shared PWs-Obligated |  | 428 | 406 | Total Shared
9510 | PA-02-PR-4339-PW-09510 | FAASt A&E (PREPA/LUMA/Genera) | 1133563562.43 | 0 | 1133563562.43
10710 | PA-02-PR-4339-PW-10710 | FAASt Equipment and Materials | 656101430 | 0 | 656101430
| PA-02-PR-4339-PW-10710 | FAASt Equipment and Materials | 141081695.2 | 0 | 141081695.2
| PA-02-PR-4339-PW-10710 | FAASt Equipment and Materials | 709006610 | 0 | 709006610
| PA-02-PR-4339-PW-10710 | FAASt Equipment and Materials | 33478328 | 0 | 33478328
| PA-02-PR-4339-PW-10710 | FAASt Equipment and Materials | 1536026637 | 0 | 1536026637
| PA-02-PR-4339-PW-10710 | FAASt Equipment and Materials | -77360825.13 |  | -77360825.13
|  |  | 4131897437.5 | 0 | 4209258262.63
A
Child PWs
PW | PREPA - Obligated | Project Name | 428 | 406 | Total Child |  |  | Total Executed by PREPA | Transferred to Genera 7/1/23
9312 | 180692 | FAASt Mobile Generation Units Purchases | 59740469.92 | 0 | 59740469.92 | Generation |  | 59740469.92 | 0
10080 | 334509 | FAASt Palo Seco Demin Water Tank 4 | 2883352.33 | 0 | 2883352.33 | Generation |  | 2883352.33 | 0
10455 | 663385 | FAASt Mayaguez Hydro-Gas Power Plant | 21901105.4 | 0 | 21901105.4 | Generation |  | 21901105.4 | 0
10568 | 669233 | FAASt Aguirre Power Plant 002 Units 1 &2 | 20905908.95 | 0 | 20905908.95 | Generation |  | 19539860.92 | 1366048.03
10571 | 669498 | FAASt Aguirre Power Plant 001 Infrastructure | 3031265.05 | 0 | 3031265.05 | Generation |  | 1381975 | 1649290.05
10606 | 662957 | FAASt Palo Seco Power Plant 001 Units 3 & 4 | 28774422.64 | 0 | 28774422.64 | Generation |  | 6507604.8 | 22266817.84
10607 | 663383 | FAASt Cambalache Power Plant | 2007587.81 | 0 | 2007587.81 | Generation |  | 2007587.81 | 0
10608 | 667744 | FAASt San Juan Power Plant - Auxiliary Infrastructure | 3192936 | 0 | 3192936 | Generation |  | 3142486 | 50450
10609 | 671481 | FAASt Palo Seco 002- Auxiliary Infrastructure | 3482468 | 0 | 3482468 | Generation |  | 1172831.25 | 2309636.75
10615 | 662947 | FAASt San Juan 001  Units 5 &amp;amp; | 73453828.76 | 0 | 73453828.76 | Generation |  | 29654228.77 | 43799599.99
10622 | 669815 | FAASt Aguirre Power Plant 003 Combined Cycle | 6384965.36 | 0 | 6384965.36 | Generation |  | 3819020.68 | 2565944.68
10694 | 673006 | FAASt Costa Sur 002 -Infrastructure projects ( | 1021800 | 0 | 1021800 | Generation |  | 122800 | 899000
10702 | 672950 | FAASt Costa Sur Power Plant Permanent | 42429619.54 | 0 | 42429619.54 | Generation |  | 16105860.71 | 26323758.83
11085 | 687480 | FAASt San Juan Power Plant 002 Units 7 & 8 | 19558770 | 0 | 19558770 | Generation |  | 1189095.58 | 18369674.42
11510 | 725535 | FAASt - IT/0T System Upgrade for all Power Plants | 11423825 | 0 | 11423825 | Generation |  | 11423825 | 0
11860 | 746897 | FAASt – BONUS Nuclear Power Plant Repairs (Dams/Hydro) | 1401294.53 | 178320.9 | 1579615.43 | (Dams/Hydro) |  | 1401294.53 | 0
| TOTAL PREPA |  | 301593619.29 | 178320.9 | 301771940.19 | 0 |  | 181993398.7 | 119600220.59
B
PW | LUMA - Obligated | Project Name | 428 | 406 | Total Child | Asset
10496 | 174422 | FAASt - Catano-Rebuild 1801(Substation) | 16359899.17 | 6895149.77 | 23255048.94 | Substation
10499 | 542690 | FAASt Maunabo Streetlighting (Distribution) | 6199877.07 | 243880.33 | 6443757.4 | Distribution
10515 | 542517 | FAASt -Luquillo Distribution Streetlighting | 8628667.29 | 181658.08 | 8810325.37 | Distribution
10521 | 542687 | FAASt Lajas Streetlighting (Distribution) | 10278336.09 | 426332.48 | 10704668.57 | Distribution
10538 | 542756 | FAASt Streetlighting - Guánica (Distribution | 9687238 | 370808 | 10058046 | Distribution
10539 | 542688 | FAASt Aguada Streetlighting (Distribution) | 17764494.34 | 807222.04 | 18571716.38 | Distribution
10624 | 165225 | FAASt-Substation 2501 Vieques (Substation) | 1209111 | 178309 | 1387420 | Substation
10626 | 165209 | FAASt-Substation 3801 Culebra (Substation) | 1282218 | 177391 | 1459609 | Substation
10629 | 334329 | FAASt Distribution Feeders - Ponce Short Term | 316119 | 64134 | 380253 | Distribution
10630 | 334323 | FAASt Distribution Feeders - Ponce Short Term | 323692 | 69130 | 392822 | Distribution
10632 | 179558 | FAASt - Manatí TC - BRKS 230 kV - (Substation) | 1593443 | 0 | 1593443 | Substation
10635 | 334488 | FAASt Distribution Feeders - Caguas Short Ter | 142917 | 10826 | 153743 | Distribution
10679 | 334468 | FAASt Line 2200 Dos Bocas HP to Dorado TC (T | 1217429 | 0 | 1217429 | Transmission
10690 | 542762 | FAASt Distribution Feeders - Arecibo Short Te | 610448 | 157420 | 767868 | Distribution
10701 | 334527 | FAASt Distribution Feeders - Caguas Short Term | 108847 | 14874 | 123721 | Distribution
10742 | 673839 | FAASt Distribution Pole and Conductor Repair- | 20468 | 5830 | 26298 | Distribution
10751 | 673848 | FAASt Distribution Pole and Conductor Repair- | 43725 | 5620 | 49345 | Distribution
10764 | 673838 | FAASt Distribution Pole and Conductor Repair | 284349 | 73265 | 357614 | Distribution
10773 | 673774 | FAASt Distribution Pole and Conductor Repair | 1408531 | 358420 | 1766951 | Distribution
10777 | 673795 | FAASt Distribution Pole and Conductor Repair - | 1425163 | 368954 | 1794117 | Distribution
10788 | 169896 | FAASt - Costa Sur SP TC  Equipment Repair and | 23251835 | 0 | 23251835 | Substation
10800 | 668583 | FAASt Line 13300 GOAB 13301C to Hato Tejas Se | 453597 | 0 | 453597 | Transmission
10812 | 673847 | FAASt Distribution Pole and Conductor Repair- | 190570 | 49943 | 240513 | Distribution
10821 | 673818 | FAASt Distribution Pole and Conductor Repair | 621804 | 171614 | 793418 | Distribution
10824 | 674098 | FAASt Distribution Pole and Conductor Repair | 84433 | 23322 | 107755 | Distribution
10827 | 674083 | FAASt Distribution Pole and Conductor Repair | 1747929 | 362533 | 2110462 | Distribution
10837 | 550896 | FAASt Line 6700 Martin Peña TC to Villamar Se | 690703 | 0 | 690703 | Transmission
10841 | 550910 | FAASt Physical Security - Group 1 (Substatio | 6025270.22 | 665958.96 | 6691229.18 | Substation
10857 | 660239 | FAASt Streetlighting - Villalba (Distributio | 10190536.05 | 681865.66 | 10872401.71 | Distribution
10858 | 546370 | FAASt - Substation Minor Repairs Group A (Subs | 4482972.51 | 488202.58 | 4971175.09 | Substation
10864 | 673844 | FAASt Distribution Pole and Conductor Repair | 1072850.98 | 319213.9 | 1392064.88 | Distribution
10876 | 659715 | FAASt Distribution Streetlighting - Aibonito | 7074498 | 178787 | 7253285 | Distribution
10884 | 659623 | FAASt Distribution Streetlighting - Cataño ( | 16996758 | 565289 | 17562047 | Distribution
10891 | 668592 | FAASt Line 9800 Bayamon TC - Guaraguao Sect | 420866 | 0 | 420866 | Transmission
10893 | 674092 | FAASt Distribution Pole and Conductor Repair | 441308 | 90422 | 531730 | Distribution
10906 | 674072 | FAASt Distribution Pole and Conductor Repair | 872891 | 238203 | 1111094 | Distribution
10909 | 673771 | FAASt Distribution Pole and Conductor Repair | 1894033.53 | 472527 | 2366560.53 | Distribution
10919 | 673772 | FAASt Distribution Pole and Conductor Repair | 3286536 | 835984 | 4122520 | Distribution
10922 | 673843 | FAASt Distribution Pole and Conductor Repair- | 904194 | 227661 | 1131855 | Distribution
10933 | 674088 | FAASt Distribution Pole and Conductor Repair | 1412368 | 289653 | 1702021 | Distribution
10935 | 674096 | FAASt Distribution Pole and Conductor Repair | 1773428 | 318852 | 2092280 | Distribution
10957 | 657300 | FAASt ENERGY MANAGEMENT SYSTEM (EMS) (Teleco | 48941484 | 0 | 48941484 | Telecommunications
10962 | 673775 | FAASt Distribution Pole and Conductor Repair | 3575454.81 | 857193.1 | 4432647.91 | Distribution
10978 | 168226 | FAASt San Juan 115kV Underground Transmission | 14746039.57 | 0 | 14746039.57 | Transmission
11041 | 673836 | FAASt Distribution Pole and Conductor Repair- | 4686914.68 | 1064121.8 | 5751036.48 | Distribution
11045 | 165268 | FAASt Rio Grande Estate Substation CH-2306 (Su | 7098243.76 | 4585370.95 | 11683614.71 | Substation
11089 | 679149 | FAASt Distribution Pole and Conductor Repair - | 129744 | 27443 | 157187 | Distribution
11095 | 660227 | FAASt Hatillo Streetlight (Distribution) | 18570095.25 | 1764387.7 | 20334482.95 | Distribution
11096 | 679127 | FAASt Distribution Pole and Conductor Repair | 171152.23 | 46010.58 | 217162.81 | Distribution
11097 | 660437 | FAASt Manati Streetlight (Distribution) | 27067865 | 1568964 | 28636829 | Distribution
11098 | 679033 | FAASt Distribution Pole and Conductor Repair | 729040 | 179902 | 908942 | Distribution
11099 | 659625 | FAASt Distribution Streetlighting - Dorado | 22864972 | 1505645 | 24370617 | Distribution
11100 | 178503 | FAASt Aguirre TC - BKRS (Substations) | 39034592 | 0 | 39034592 | Substation
11101 | 679025 | FAASt Distribution Pole and Conductor Repair | 243073 | 55558 | 298631 | Distribution
11103 | 678985 | FAASt Distribution Pole and Conductor Repair- | 353628 | 54317.84 | 407945.84 | Distribution
11105 | 679457 | FAASt Distribution Pole and Conductor Repair | 589335 | 157153 | 746488 | Distribution
11106 | 679153 | FAASt Distribution Pole and Conductor Repair | 163846.51 | 51337.5 | 215184.01 | Distribution
11107 | 679026 | FAASt Distribution Pole and | 483786 | 106510 | 590296 | Distribution
11109 | 679134 | FAASt Distribution Pole and Conductor Repair | 452956.93 | 110600.22 | 563557.15 | Distribution
11113 | 678988 | FAASt Distribution Pole and Conductor Repair- | 911136.76 | 206650.4 | 1117787.16 | Distribution
11114 | 679458 | FAASt Distribution Pole and Conductor Repair | 498436 | 95482 | 593918 | Distribution
11116 | 686471 | FAASt Distribution Pole and Conductor Repair | 250906 | 68700 | 319606 | Distribution
11123 | 682865 | FAASt Distribution Pole and Conductor Repair | 70683 | 21148 | 91831 | Distribution
11130 | 682882 | FAASt Distribution Pole and Conductor Repair | 545661.24 | 113378.16 | 659039.4 | Distribution
11136 | 682890 | FAASt Distribution Pole and Conductor Repair | 510067.96 | 102310.67 | 612378.63 | Distribution
11137 | 682870 | FAASt Distribution Pole and Conductor Repair | 85921.77 | 17491 | 103412.77 | Distribution
11138 | 685943 | FAASt Distribution Pole and Conductor Repair P | 254972.22 | 63260 | 318232.22 | Distribution
11143 | 685263 | FAASt Distribution Pole and Conductor Repair - | 537688 | 134695 | 672383 | Distribution
11145 | 682324 | FAASt Distribution Pole and Conductor Repair | 573047.24 | 136182.31 | 709229.55 | Distribution
11149 | 682135 | FAASt Distribution Pole and Conductor Repair | 577000.79 | 116779.74 | 693780.53 | Distribution
11150 | 685370 | FAASt Distribution Pole and Conductor Repair | 68823 | 14986 | 83809 | Distribution
11152 | 686453 | FAASt Distribution Pole and Conductor Repair | 20584 | 4995 | 25579 | Distribution
11165 | 682373 | FAASt Distribution Pole and Conductor Repair | 65944 | 11661 | 77605 | Distribution
11166 | 682028 | FAASt Distribution Pole and Conductor Repair | 431381.68 | 105743.62 | 537125.3 | Distribution
11168 | 682180 | FAASt Distribution Pole and Conductor Repair | 43374 | 11028 | 54402 | Distribution
11169 | 682210 | FAASt Distribution Pole and Conductor Repair - | 198050.74 | 41796.87 | 239847.61 | Distribution
11171 | 685477 | FAASt Distribution Pole and Conductor Repair - | 355178 | 58304 | 413482 | Distribution
11181 | 682031 | FAASt Distribution Pole and Conductor Repair | 516951 | 108247 | 625198 | Distribution
11182 | 682172 | FAASt Distribution Pole and Conductor Repair | 208400 | 57671.35 | 266071.35 | Distribution
11183 | 682898 | FAASt Distribution Pole and Conductor Repair | 635326.93 | 108700.19 | 744027.12 | Distribution
11184 | 681672 | FAASt Transmission Priority Pole Replacements | 214124 | 2243 | 216367 | Distribution
11193 | 688627 | FAASt Distribution Pole and Conductor Repair | 303774 | 72188.49 | 375962.49 | Distribution
11196 | 682228 | FAASt Distribution Pole and Conductor Repair - | 775779 | 176882.42 | 952661.42 | Distribution
11201 | 682178 | FAASt Distribution Pole and Conductor Repair | 208544.25 | 53746.06 | 262290.31 | Distribution
11203 | 682136 | FAASt Distribution Pole and Conductor Repair- | 469650.95 | 95954.05 | 565605 | Distribution
11207 | 688774 | FAASt Distribution Pole and Conductor Repair | 443331 | 98484 | 541815 | Distribution
11212 | 682910 | FAASt Distribution Pole and Conductor Repair | 517156 | 105667 | 622823 | Distribution
11214 | 688096 | FAASt Distribution Pole and Conductor Repair | 21408.25 | 5830.39 | 27238.64 | Distribution
11217 | 688472 | FAASt Distribution Pole and Conductor Repair - | 164908.86 | 14986 | 179894.86 | Distribution
11229 | 686480 | FAASt Distribution Pole and Conductor Repair - | 523404 | 108652 | 632056 | Distribution
11231 | 691246 | FAASt Distribution Pole and Conductor Repair | 211622.76 | 33717.31 | 245340.07 | Distribution
11256 | 689071 | FAASt Distribution Pole and Conductor Repair | 59545.08 | 17491.16 | 77036.24 | Distribution
11257 | 701552 | FAASt Distribution Pole and Conductor Repair | 186321 | 51841 | 238162 | Distribution
11263 | 701495 | FAASt Distribution Pole and Conductor Repair | 19848.36 | 5830.39 | 25678.75 | Distribution
11264 | 688109 | FAASt Distribution Pole and Conductor Repair | 448719.06 | 114710.2 | 563429.26 | Distribution
11267 | 701679 | FAASt Distribution Pole and Conductor Repair | 64425.44 | 16226.16 | 80651.6 | Distribution
11268 | 701504 | FAASt Distribution Pole and Conductor Repair | 150345 | 37878 | 188223 | Distribution
11269 | 701545 | FAASt Distribution Pole and Conductor Repair | 487190 | 129039 | 616229 | Distribution
11273 | 688630 | FAASt Distribution Pole and Conductor | 42728.41 | 9990.97 | 52719.38 | Distribution
11275 | 701555 | FAASt Distribution Pole and Conductor Repair | 547010 | 102417 | 649427 | Distribution
11276 | 688198 | FAASt Distribution Pole and Conductor Repair - | 60838.48 | 16023.76 | 76862.24 | Distribution
11277 | 688629 | FAASt Distribution Pole and Conductor Repair | 106941.99 | 27886.93 | 134828.92 | Distribution
11279 | 688625 | FAASt Distribution Pole and Conductor Repair | 710014.69 | 191275.59 | 901290.28 | Distribution
11311 | 704751 | FAASt Distribution Pole and Conductor Repair - | 338491 | 96676 | 435167 | Distribution
11312 | 704916 | FAASt [Distribution Pole and Conductor Repair | 273996 | 29974 | 303970 | Distribution
11314 | 704750 | FAASt Distribution Pole and Conductor Repair - | 486385 | 92244 | 578629 | Distribution
11317 | 673504 | FAASt [Distribution Streetlighting - Gurabo] | 19208994 | 1533300 | 20742294 | Distribution
11318 | 659968 | FAASt [San Germán Streetlighting] (Distributio | 30849348 | 4033578 | 34882926 | Distribution
11319 | 690545 | FAASt Aguadilla Streetlight (Distribution) | 19796809 | 1295775 | 21092584 | Distribution
11326 | 691702 | FAASt Distribution Streetlighting - Trujillo Alto (Distribution) | 25277347 | 1009578 | 26286925 | Distribution
11340 | 704844 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 16-17-18-19-20] (Distribution) | 320740 | 88558 | 409298 | Distribution
11344 | 698424 | FAASt Streetlight Florida Distribution | 9311841.53 | 997190 | 10309031.53 | Distribution
11347 | 169500 | FAASt [Bayamon TC - MC-BKRS-Y1] (Substation) | 2796182 | 3575881 | 6372063 | Substation
11350 | 549764 | FAASt Physical Security - Group 2 (Substation) | 2159012.31 | 224680.68 | 2383692.99 | Substation
11351 | 679039 | FAASt [Distribution Streetlighting - Caguas] (Distribution) | 73737224.58 | 1849344.06 | 75586568.64 | Distribution
11352 | 704755 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 12-13-14] (Distribution) | 438209.69 | 86181.92 | 524391.61 | Distribution
11365 | 705584 | FAASt [Distribution Pole and Conductor Repair - Ponce Groups 14 &amp;amp; 15] (Distribution) | 1464496 | 378483 | 1842979 | Distribution
11372 | 551861 | FAASt [Physical Security - Group 3] (Substation) | 3696956.6 | 436383.23 | 4133339.83 | Substation
11385 | 542758 | FAASt Substation Minor Repairs -Group B (Substation) | 2973035 | 439541 | 3412576 | Substation
11402 | 682834 | FAASt [Costa Sur TC - Phase II &amp;amp; III ] (Substation) | 36917509.58 | 0 | 36917509.58 | Substation | PW Version
11449 | 705527 | FAASt [Distribution Pole and Conductor Repair - San Juan 17-18-19-20-21] (Distribution) | 642721 | 125133 | 767854 | Distribution
11465 | 704933 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 13-14-15-16] (Distribution) | 1201420 | 224731 | 1426151 | Distribution
11478 | 546371 | FAASt- Substation Minor Repairs Group C (Substation) | 2648259.06 | 384632.14 | 3032891.2 | Substation
11479 | 169495 | FAASt [Substations - Tapia GIS Rebuilt Equipment Repair &amp;amp; Replacement] (Substations) | 8180049.03 | 7159883.3 | 15339932.33 | Substation
11489 | 169266 | FAASt Centro Medico 1327/1359 Equipment Repair &amp;amp; Replacement (Substation) | 14795324 | 6537037 | 21332361 | Substation
11508 | 708579 | FAASt [Distribution Pole and Conductor Repair - Ponce Group 16, 17, 18 &amp;amp; 19] (Distribution) | 1764568.92 | 389437.84 | 2154006.76 | Distribution
11518 | 698458 | FAASt [Distribution Streetlighting - Guaynabo] (Distribution) | 9762754.59 | 853056.42 | 10615811.01 | Distribution
11522 | 671502 | FAASt [Distribution Streetlighting - Yabucoa] (Distribution) | 14918381.07 | 1965608.26 | 16883989.33 | Distribution
11524 | 704679 | FAASt Coamo Streetlight (Distribution) | 14311922.45 | 2060901.35 | 16372823.8 | Distribution
11526 | 698439 | FAASt Streetlight - Las Marías (Distribution) | 7073217 | 1287705 | 8360922 | Distribution
11532 | 678793 | FAASt [Streetlighting - Mayagüez] (Distribution) | 11019180.1 | 1352204.36 | 12371384.46 | Distribution
11533 | 678789 | FAASt [Distribution Streetlighting - Carolina] (Distribution) | 14865613.02 | 1158946.56 | 16024559.58 | Distribution
11534 | 710110 | FAASt [Distribution Pole and Conductor Repair - Bayamon Group 2 - Phase 2] (Distribution) | 85296.74 | 2478.06 | 87774.8 | Distribution
11537 | 551925 | FAASt [SCADA Remote Access and RTU Replacements Group 1] (Telecommunication) | 5962412.52 | 1701923.62 | 7664336.14 | Telecommunications
11540 | 679780 | FAASt [Distribution Streetlighting - Bayamon] (Distribution) | 20710527 | 1176376 | 21886903 | Distribution
11555 | 723078 | FAASt - EPC - [San Juan SP TC] (Substation) | 61558468.95 | 0 | 61558468.95 | Substation
11556 | 723077 | FAASt - EPC - [Sabana Llana TC] (Substation) | 46643078.39 | 0 | 46643078.39 | Substation
11557 | 550950 | FAASt - EPC - [Monacillo TC] (Substations) | 58195134.18 | 0 | 58195134.18 | Substation | PW Version
11560 | 698570 | FAASt [Distribution Streetlighting - Corozal] (Distribution) | 13720208.31 | 2225873.62 | 15946081.93 | Distribution
11566 | 660422 | FAASt [Physical Security - Group 4] (Substation) | 3478518 | 338280 | 3816798 | Substation
11573 | 684920 | FAASt Substation High Voltage Replacement_Group 1 (Substation) | 6929384 | 0 | 6929384 | Substation
11583 | 714654 | FAASt [Advanced Metering Infrastructure (AMI)] (Telecommunications) | 332062581 | 544207595 | 876270176 | Telecommunications
11627 | 709631 | FAASt [Morovis Streetlighting] (Distribution) | 13486398.85 | 1744482.27 | 15230881.12 | Distribution
11629 | 698579 | FAASt [Distribution Streetlighting - Orocovis] (Distribution) | 8070964.96 | 1339801.28 | 9410766.24 | Distribution
11633 | 704938 | FAASt [Distribution Streetlighting - Las Piedras (Distribution) | 13807923.4 | 1807601.11 | 15615524.51 | Distribution
11636 | 703535 | FAASt [Toa Baja Streetlighting] (Distribution) | 9529190.37 | 620134.69 | 10149325.06 | Distribution
11639 | 710094 | FAASt [Pole and Conductor Repair - Bayamon Group 1 - Phase 2] (Distribution) | 7096249.5 | 195136.32 | 7291385.82 | Distribution
11640 | 711888 | FAASt [Pole and Conductor Repair - Caguas Group 1 - Phase 2] (Distribution) | 5425810.57 | 165903.3 | 5591713.87 | Distribution
11650 | 704868 | FAASt [Ceiba Streetlighting] (Distribution) | 5152111.14 | 716918.6 | 5869029.74 | Distribution
11652 | 682121 | FAASt - EPC -Aguirre TC-Phase II (Substation) | 82726096.38 | 0 | 82726096.38 | Substation
11658 | 704849 | FAASt [Naguabo Streetlighting] (Distribution) | 11620676.42 | 1669736.97 | 13290413.39 | Distribution
11664 | 704943 | FAASt [Naranjito Streetlighting] (Distribution) | 11644048.43 | 2115538.38 | 13759586.81 | Distribution
11666 | 712968 | FAASt [Pole and Conductor Repair - Arecibo Group 2 - Phase 2] (Distribution) | 5629060 | 178712.97 | 5807772.97 | Distribution
11671 | 724703 | FAASt [Arroyo Streetlighting] (Distribution) | 5314332 | 740394.01 | 6054726.01 | Distribution
11673 | 724938 | FAASt [Vega Alta Streetlighting] (Distribution) | 12445015.33 | 1869089.52 | 14314104.85 | Distribution
11675 | 704921 | FAASt [Barranquitas Streetlighting] (Distribution) | 9430329.22 | 1577046.09 | 11007375.31 | Distribution
11680 | 698511 | FAASt [Culebra Streetlighting] (Distribution) | 1155804 | 153603 | 1309407 | Distribution
11682 | 549715 | FAASt Substation Minor Repairs - Group D (Substation) | 2583133.54 | 288123.63 | 2871257.17 | Substation
11686 | 738672 | FAASt [Pole and Conductor Repair - Mayaguez Group 1 - Phase 2] (Distribution) | 10313627 | 306131.37 | 10619758.37 | Distribution
11696 | 723883 | FAASt [Region 1 -San Juan Group A] (Vegetation) | 0 | 18151116.72 | 18151116.72 | Vegetation
11707 | 549725 | FAASt [Substation Minor Repairs - Group E] (Substation) | 3924015.69 | 579767.52 | 4503783.21 | Substation
11711 | 704927 | FAASt [Añasco Streetlighting] (Distribution) | 12087876.17 | 1820361.92 | 13908238.09 | Distribution
11712 | 738670 | FAASt [Pole and Conductor Repair - Ponce Group 1 - Phase 2] (Distribution) | 4926640.11 | 147870.9 | 5074511.01 | Distribution
11714 | 728827 | FAASt [Region 2 -Arecibo Group A] High Density (Vegetation) | 4807675.47 | 13386633.34 | 18194308.81 | Vegetation
11715 | 727531 | FAASt [Region 6 -Ponce Group A] High Density (Vegetation) | 6849050.26 | 19064883.85 | 25913934.11 | Vegetation
11716 | 742026 | FAASt [Pole and Conductor Repair - San Juan Group 2 - Phase 2] (Distribution) | 1033375.81 | 84035.96 | 1117411.77 | Distribution
11718 | 728832 | FAASt [Region 5 -Mayaguez Group A] High Density (Vegetation) | 3767690.42 | 10493001.48 | 14260691.9 | Vegetation
11719 | 711670 | FAASt [T-Pole Program Line 100] (Transmission) | 94787.57 | 23372.71 | 118160.28 | Transmission
11723 | 708637 | FAASt T-Pole Program Line 3700] (Transmission) | 303960.92 | 73393.66 | 377354.58 | Transmission
11724 | 727692 | FAASt [Region 4 -Caguas Group A] High Density (Vegetation) | 7414164.75 | 20637925.62 | 28052090.37 | Vegetation
11725 | 724825 | FAASt [Cidra Streetlighting] (Distribution) | 12812478.84 | 1838229.6 | 14650708.44 | Distribution
11726 | 729286 | FAASt HV Equipment Replacement Group 2 (Substation) | 15413889.89 | 0 | 15413889.89 | Substation
11727 | 701472 | FAASt [Comerio Streetlighting] (Distribution) | 6538769.44 | 862125.75 | 7400895.19 | Distribution
11734 | 724698 | FAASt [Adjuntas Streetlighting] (Distribution) | 10742462 | 1891152 | 12633614 | Distribution
11735 | 724600 | FAASt [Jayuya Streetlighting] (Distribution) | 7277670.2 | 1350541.32 | 8628211.52 | Distribution
11739 | 724601 | FAASt [Salinas Streetlighting] (Distribution) | 12097203.53 | 1611020.9 | 13708224.43 | Distribution
11746 | 711856 | FAASt [Pole and Conductor Repair - Bayamon Group 3 - Phase 2] (Distribution) | 10940320.91 | 395663.43 | 11335984.34 | Distribution
11753 | 742070 | FAASt [Pole and Conductor Repair - San Juan Group 1 - Phase 2] (Distribution) | 5461200.05 | 205587.38 | 5666787.43 | Distribution
11754 | 712980 | FAASt [T-Pole Program Line 3000] (Transmission) | 559076.77 | 72117.49 | 631194.26 | Transmission
11764 | 743399 | FAASt [High Voltage Equipment Replacement - Group 3] (Substation) | 17307539.01 | 0 | 17307539.01 | Substation
11839 | 745859 | FAASt [Automation Program Group 18: DAR – SAN JUAN 2001- FY24] (Distribution) | 467287.6 | 0 | 467287.6 | Distribution
11850 | 738120 | FAASt [Pole and Conductor Repair-Carolina Group 2- Phase 2] (Distribution) | 11041271 | 409899.81 | 11451170.81 | Distribution
11667 | 710099 | FAASt [Pole and Conductor Repair - Arecibo Group 1 - Phase 2] (Distribution) | 6704421.6922 | 239376.93 | 6943798.6222 | Distribution
11812 | 738971 | FAASt [Pole and Conductor Repair - Caguas Group 2 - Phase 2] (Distribution) | 13884126 | 377123.67 | 14261249.67 | Distribution
108001 | 752810 | FAASt [Automation Program Group 20] (TL/Distribution) | 2623262.08 | 0 | 2623262.08 | Distribution
108000 | 752808 | FAASt [Automation Program Group 19] (TL/Distribution) | 2753627.24 | 0 | 2753627.24 | Distribution
108022 | 755211 | FAASt [Automation Program Group 15] (TL/Distribution) | 643560.85 | 0 | 643560.85 | Distribution
107956 | 745856 | FAASt [Automation Program Group 14] (TL/Distribution) | 1640186.96 | 0 | 1640186.96 | Distribution
107957 | 745861 | FAASt [Automation Program Group 12] (TL/Distribution) | 3664210.1 | 0 | 3664210.1 | Distribution
11721 | 178258 | FAASt - [Taft - MC 1105] (Substations) | 9362729.93 | 4123842.4 | 13486572.33 | Substation
108070 | 790443 | FAASt [Pole and Conductor Repair -San Juan Group 3 Phase 2 (Distribution) | 186697 | 0 | 186697 | Distribution
108035 | 757692 | FAASt [Automation Program Group 26] (TL / Distribution) | 938783.6333 | 0 | 938783.6333 | Distribution
11859 | 551963 | FAASt [Transport Network Group 1] (Telecommunication) | 5490296.8889 |  | 5490296.8889 | Telecommunications
108157 | 956349 | FAASt [San Juan Region 1 Line 36800 (115kV) – Canovanas TC to Palmer TC] (Vegetation) | 1364416.1222 |  | 1364416.1222 | Vegetation
108159 | 956356 | FAASt [Ponce Region 6 Line 39000 (115kV) – Aguas Buenas Substation to Hacienda San Jose] (Vegetation) | 325421.1 |  | 325421.1 | Vegetation
107999 | 752540 | FAASt [Pole and Conductor Repair -Mayaguez Group 4 Phase 2] (Distribution) | 7111613.9111 |  | 7111613.9111 | Distribution
107918 | 735474 | FAASt [Pole and Conductor Repair -Caguas Group 3 Phase 2] (Distribution) | 14075641.4222 |  | 14075641.4222 | Distribution
107979 | 750692 | FAASt [Pole and Conductor Repair - Mayaguez Group 3 - Phase 2] (Distribution) | 12921047 |  | 12921047 | Distribution
107779 | 682645 | FAASt [Maunabo TC] (Substation) | 8292124.9556 |  | 8292124.9556 | Substation
108134 | 825843 | FAASt [Guanica TC] (Substation) | 2320373.9667 |  | 2320373.9667 | Substation
108102 | 812569 | FAASt [Feeder Rebuild 3502-02] (Distribution) | 10217566.5444 |  | 10217566.5444 | Distribution
108119 | 817956 | FAASt [Feeder Rebuild # 1303-02] (Distribution) | 2054461.7889 |  | 2054461.7889 | Distribution
108161 | 956593 | FAASt [Factor Sect 8014 Transformer Replacement] (Substation) | 3751193.6333 |  | 3751193.6333 | Substation
108163 | 957578 | FAASt [Costa Sur TC Underground Cable Failure Replacement on Transformer Lead Bank #2] (Substation) | 1108989.5111 |  | 1108989.5111 | Substation
108078 | 800361 | FAASt [Automation Program Group 37] (Distribution) | 1596192.7333 |  | 1596192.7333 | Distribution
108041 | 757700 | FAASt [Automation Program Group 35] (TL / Distribution) | 1318515.6667 |  | 1318515.6667 | Distribution
108039 | 757698 | FAASt [Automation Program Group 33] (Distribution) | 1888928.2111 |  | 1888928.2111 | Distribution
108038 | 757697 | FAASt [Automation Program Group 32] (TL / Distribution) | 1996678.5889 |  | 1996678.5889 | Distribution
108037 | 757696 | FAASt [Automation Program Group 31] (Distribution) | 1145457.6111 |  | 1145457.6111 | Distribution
108036 | 757694 | FAASt [Automation Program Group 27] (Distribution) | 2314733.7889 |  | 2314733.7889 | Distribution
108034 | 757689 | FAASt [Automation Program Group 24] (TL/ Distribution) | 1774822.4 |  | 1774822.4 | Distribution
108153 | 956342 | FAASt [Arecibo Region 2 Line 36400 (115Kv) – Ponce TC to Dos Bocas HP] (Vegetation) | 4093248.3889 |  | 4093248.3889 | Vegetation
108158 | 956353 | FAASt [Arecibo Region 2 Line 36100 (115kV) – Dos Bocas HP to Barrio Pina] (Vegetation) | 3756065.0889 |  | 3756065.0889 | Vegetation
108074 | 797148 | FAASt [Feeder Rebuild # 8101-03] (Distribution) | 2359895.6333 |  | 2359895.6333 | Distribution
108075 | 798275 | FAASt [Feeder Rebuild # 1620-02] (Distribution) | 6711420.9 |  | 6711420.9 | Distribution
108083 | 801172 | FAASt [Feeder Rebuild # 1529-15] (Distribution) | 2285961.1333 |  | 2285961.1333 | Distribution
108077 | 800286 | FAASt [Automation Program Group 36] (TL / Distribution) | 1703712.8333 |  | 1703712.8333 | Distribution
108010 | 753782 | FAASt [Priority Pole Replacement Program (Line 3100 Monacillos TC – Sabana Llana TC)] (Transmission) | 129361.9267 | 2218.84 | 131580.7667 | Transmission
108032 | 757662 | FAASt [Automation Program Group 21] (Distribution) | 1710547.9444 |  | 1710547.9444 | Distribution
108033 | 757687 | FAASt [Automation Program Group 22] (Distribution) | 2356733.8778 |  | 2356733.8778 | Distribution
11452 | 673292 | FAASt Telecom Infrastructure - Cerro Puntas (Telecommunication) | 8124106.79 | 49577.82 | 8173684.61 | Telecommunications
11307 | 167446 | FAASt - Line 36100 (115kV) - Bayamon to Monacillos (Transmission) | 33956314.5889 | 0 | 33956314.5889 | Transmission
11432 | 176913 | FAASt [Palo Seco SP to Catano Sect 38kV Line- 9500] (Transmission) | 33526671.8667 | 0 | 33526671.8667 | Transmission
11373 | 176971 | FAASt –38kV Line 8200 - San Juan SP to Catano Sect Line (Transmission) | 21670623.7889 | 0 | 21670623.7889 | Transmission
11453 | 180052 | FAASt Ponce TC to Salinas Urbano TC- 38kV 100 & 200 (Transmission) | 74520098.4889 | 0 | 74520098.4889 | Transmission
11708 | 334470 | FAASt [TL 3100 Monacillos TC to Sabana Llana TC] (Transmission) | 47112099.9222 | 0 | 47112099.9222 | Transmission
11425 | 678800 | FAASt [Telecom Infrastructure – Group B] (Telecommunication) | 13148929.4489 | 55895.84 | 13204825.2889 | Telecommunications
11877 | 749072 | FAASt [Priority Pole Replacement Program (Line 2700 Aguadilla Hospital Distrito Sect – Mora TC)] (Transmission) | 767377.79 | 59629.81 | 827007.6 | Transmission
107970 | 750150 | FAASt [Priority Pole Replacement Program (Line 4800 Santa Isabel TC – Toro Negro 1 HP)] (Transmission) | 125923.5667 | 8224.8 | 134148.3667 | Transmission
108040 | 757699 | FAASt [Automation Program Group 34] (Distribution) | 2755939 | 0 | 2755939 | Distribution
107972 | 750168 | FAASt [Priority Pole Replacement Program (Line 4800 Santa Isabel TC – Aibonito TO)] (Transmission) | 431757.16 | 37472.84 | 469230 | Transmission
108082 | 801166 | FAASt [Feeder Rebuild # 6601-03] (Distribution) | 19826783.47 | 0 | 19826783.47 | Distribution
107971 | 750151 | FAASt [Priority Pole Replacement Program (Line 700 Costa Sur SP – Yauco 2 HP)] (Transmission) | 243268.16 | 12563.87 | 255832.03 | Transmission
| TOTAL LUMA |  | 2023455438.1378 | 734471528.92 | 2757683698.8978 | 0
C
PW | Genera - Obligated | Project Name | 428 | 406 | Total Child | Asset |  | Obligated by PREPA- Transferred to Genera | Total Obligated by Genera
10568 | PA-02-PR-4339-PW-10568 | FAASt Aguirre Power Plant 002 Units 1 &2 | 1366048.03 | 0 | 1366048.03 | Generation |  | -1366048.03 | 0
10571 | PA-02-PR-4339-PW-10571 | FAASt Aguirre Power Plant 001 Infrastructure | 2020619.28 | 0 | 2020619.28 | Generation |  | -1649290.05 | 371329.23
10606 | PA-02-PR-4339-PW-10606 | FAASt Palo Seco Power Plant 001 Units 3 & 4 | 27958689.06 | 0 | 27958689.06 | Generation |  | -22266817.84 | 5691871.22
10607 | PA-02-PR-4339-PW-10607 | FAASt Cambalache Power Plant Permanent Repair | 0 | 0 | 0 | Generation |  | 0 | 0
10608 | PA-02-PR-4339-PW-10608 | FAASt San Juan Power Plant - Auxiliary Infras | 50450 | 0 | 50450 | Generation |  | -50450 | 0
10609 | PA-02-PR-4339-PW-10609 | FAASt Palo Seco 002- Auxiliary Infrastructure | 4012636.75 | 0 | 4012636.75 | Generation |  | -2309636.75 | 1703000
10615 | PA-02-PR-4339-PW-10615 | FAASt San Juan 001 Units 5 &amp;amp; 6 (Generation | 45439729.74 | 0 | 45439729.74 | Generation |  | -43799599.99 | 1640129.75
10622 | PA-02-PR-4339-PW-10622 | FAASt Aguirre Power Plant 003 Combined Cycle | 2565944.68 | 0 | 2565944.68 | Generation |  | -2565944.68 | 0
10694 | PA-02-PR-4339-PW-10694 | FAASt Costa Sur 002 -Infrastructure projects ( | 899000 | 0 | 899000 | Generation |  | -899000 | 0
10702 | PA-02-PR-4339-PW-10702 | FAASt Costa Sur Power Plant Permanent | 31309575.9 | 0 | 31309575.9 | Generation |  | -26323758.83 | 4985817.07
11085 | PA-02-PR-4339-PW-11085 | FAASt San Juan Power Plant 002 Units 7 & 8 | 18658766.12 | 0 | 18658766.12 | Generation |  | -18369674.42 | 289091.7
11510 | PA-02-PR-4339-PW-11510 | FAASt - IT/0T System Upgrade for all Power Plants | 0 | 0 | 0 | Generation |  | 0 | 0
11855 | PA-02-PR-4339-PW-11855 | FAASt Generation Fleet Project (Generation) | 643475586.6667 | 0 | 643475586.6667 | Generation |  | 0 | 643475586.6667
108066 | PA-02-PR-4339-PW-108066 | FAASt [Auxiliary Equipment] (Generation) | 18912976 | 0 | 18912976 | Generation |  |  | 18912976
108115 | PA-02-PR-4339-PRJ-817248 | FAASt [Power Plant Repairs & System Restoration] (Generation) | 89680589.5889 |  | 89680589.5889 | Priority Generation |  | 0 | 89680589.5889
108108 | PA-02-PR-4339-PRJ-816612 | FAASt [Continuous Emission Monitoring Systems (CEMS)] (Generation) | 5008333.2 |  | 5008333.2 | Generation |  | 0 | 5008333.2
108019 | PA-02-PR-4339-PRJ-754801 | FAASt [Repair Unit 9 San Juan Steam Plant] (Generation) | 27556615.2444 |  | 27556615.2444 | Generation |  | 0 | 27556615.2444
|  |  | 918915560.26 | 0 | 918915560.26 | 0 |  | -119600220.59 | 799315339.67
D
| GRAND TOTAL |  | 3243964617.6878 | 734437462.87 | 3133875173.0722
Selected Projects under Formulation *
PRJ | PREPA -Under Formulation | Project Name | 428 | 406 | Total Child | Asset
178722 | PA-02-PR-4339-PRJ-178722 | FAASt [Caonillas Reservoir - Dredging] (Dams/Hydro) | 81857757 |  | 81857757 | Water/Hydro
180723 | PA-02-PR-4339-PRJ-180723 | FAASt [Rio Blanco Hydroelectric System] (Dams/Hydro) | 22911551 | 26094024.55 | 49005575.55 | Water/Hydro
334769 | PA-02-PR-4339-PRJ-334769 | FAASt [Garzas Reservoir – Dredging] (Dams/Hydro) | 11154286 |  | 11154286 | Water/Hydro
334770 | PA-02-PR-4339-PRJ-334770 | FAASt [Guajataca Dam – Permanent Repairs] (Dams/Hydro) & Dredging | 566085576 | 520884424 | 1086970000 | Water/Hydro
334772 | PA-02-PR-4339-PRJ-334772 | FAASt [Guayabal Reservoir – Dredging] (Dams/Hydro) | 6452231 |  | 6452231 | Water/Hydro
334773 | PA-02-PR-4339-PRJ-334773 | FAASt [Lucchetti Reservoir – Dredging] (Dams/Hydro) | 40020000 |  | 40020000 | Water/Hydro
334798 | PA-02-PR-4339-PRJ-334798 | FAASt [Guerrero Reservoir – Dredging] (Dams/Hydro) | 3918132 |  | 3918132 | Water/Hydro
334803 | PA-02-PR-4339-PRJ-334803 | FAASt [Loco Reservoir Dredging] (Dams/Hydro) | 8080000 |  | 8080000 | Water/Hydro
334811 | PA-02-PR-4339-PRJ-334811 | FAASt [Dos Bocas Reservoir Dredging] (Dams/Hydro) | 117400543.58 |  | 117400543.58 | Water/Hydro
334813 | PA-02-PR-4339-PRJ-334813 | FAASt [Guayo Reservoir Dredging] (Dams/Hydro) | 17260000 |  | 17260000 | Water/Hydro
335206 | PA-02-PR-4339-PRJ-335206 | FAASt [Matrullas Reservoir–Dredging] (Dams/Hydro) | 7752364 |  | 7752364 | Water/Hydro
335207 | PA-02-PR-4339-PRJ-335207 | FAASt Guineo Reservoir – Dredging (Dams/Hydro) | 3143743 |  | 3143743 | Water/Hydro
344771 | PA-02-PR-4339-PRJ-344771 | FAASt [Guajataca Dam Dredging | 43732382 |  | 43732382 | Water/Hydro
435769 | PA-02-PR-4339-PRJ-435769 | FAASt [South Coast Irrigation District - Canals] (Dams/Hydro) | 117758206.89 | 27093224.61 | 144851431.5 | Water/Hydro
436462 | PA-02-PR-4339-PRJ-436462 | FAASt [Lajas Irrigation Canals] (Dams/Hydro) | 37270276.12 | 5302995.4 | 42573271.52 | Water/Hydro
436467 | PA-02-PR-4339-PRJ-436467 | FAASt [Isabela Irrigation District - Canals] (Dams/Hydro) | 15000000 |  | 15000000 | Water/Hydro
436468 | PA-02-PR-4339-PRJ-436468 | FAASt [Toro Negro Hydroelectric System Connection](Dams/Hydro) | 43483764.17 | 13760297.54 | 57244061.71 | Water/Hydro
436621 | PA-02-PR-4339-PRJ-436621 | FAASt [Dams Minor Repairs] (Dams/Hydro) | 15309227 | 9298063.48 | 24607290.48 | Water/Hydro
721184 | PA-02-PR-4339-PRJ-721184 | FAASt Guayabal Dam Repairs and Mitigation (Dams/Hydro) | 163240107.05 | 162914788.74 | 326154895.79 | Water/Hydro
728260 | PA-02-PR-4339-PRJ-728260 | FAASt [Caonillas HydroElectric Power Plant No. 1] (Dams/Hydro) | 3611152 |  | 3611152 | Water/Hydro
|  |  | 1325441298.81 | 765348224.32 | 2090789117.13 | 0
B-2
*Cost presented herein are based on scope of works and/or costs estimates available in Grants Portal. Subject to change after FEMA validation
PRJ | LUMA - Under Formulation | Project Name | 428 | 406 | Total Child | Asset |  | 428 -Submitted by LUMA | 406 submitted by LUMA | Total Project estimate | 428 Difference
165209 | PA-02-PR-4339-PRJ-165209 | FAASt - EPC - Culebra Substation 3801 and New Culebra Substation 3802 (Substation) | 14048046 | 177391 | 14225437 | Vieques and Culebra Projects
165225 | PA-02-PR-4339-PW-10624 | FAASt-Substation 2501 Vieques (Substation) & New 2502 Substation | 14704637.25 | 178309 | 13495526.25 | Vieques and Culebra Projects
165226 | PA-02-PR-4339-PRJ-165226 | FAASt [Feeders Vieques & Culebra] (Distribution) | 72211568.14 | 12438987.09 | 84650555.23 | Vieques and Culebra Projects
169058 | PA-02-PR-4339-PRJ-169058 | FAASt - Llorens Torres MC 1106 - Equipment Repair & Replacement - (Substations) | 18279001 |  | 18279001 | Substation |  |  |  | 0
169276 | PA-02-PR-4339-PRJ-169276 | FAASt Substation - Viaducto TC - MC 1100 - Equipment Repair & Replacement (Substation) | 20425907 |  | 20425907 | Substation |  |  |  | 0
178577 | PA-02-PR-4339-PRJ-178577 | FAASt [Cachete – MC 1526] (Substations) | 27557980.5 | 16340158.71 | 43898139.21 | Substation |  |  |  | 0
547187 | PA-02-PR-4339-PRJ-547187 | FAASt - [Substation Component Replacement Program] (Substation) | 4790316.92 |  | 4790316.92 | Substation |  |  |  | 0
550106 | PA-02-PR-4339-PRJ-550106 | FAASt [Conquistador CH] (Substation) | 11639958 |  | 11639958 | Substation |  |  |  | 0
551914 | PA-02-PR-4339-PRJ-551914 | FAASt [Caparra 1912 & 1924] (Substation) | 9297455.97 | 5838512.8 | 15135968.77 | Substation |  |  |  | 0
682328 | PA-02-PR-4339-PRJ-682328 | FAASt [Bayamón TC - Rebuild] (Substation) | 2637502.74 |  | 2637502.74 | Substation |  |  |  | 0
711819 | PA-02-PR-4339-PRJ-711819 | FAASt [Transmission Priority Pole Replacement Program Line 13400 San German Sect-La Parguera Sect] (Transmission) | 1705844 | 158417 | 1864261 | Transmission |  |  |  | 0
723883 | PA-02-PR-4339-PRJ-723883 | FAASt [Region 1 -San Juan Group A] (Vegetation) | 6573069.54 | 18371390.02 | 24944459.56 | Vegetation |  | 6584889.61 | 18404524.67 | 24989414.28 | -11820.07 | Validated amount by FEMA was lower than LUMA formulation
727522 | PA-02-PR-4339-PRJ-727522 | FAASt [Region 3 Bayamon TL - 115kV] (Vegetation) | 778850.12 | 2663231.73 | 3442081.85 | Vegetation |  | 18031093.89 | 53608045.16 | 71639139.05 | -17252243.77 | Validated amount by FEMA was lower than LUMA formulation
727529 | PA-02-PR-4339-PRJ-727529 | FAASt [Region 6 Ponce TL - 115kV] (Vegetation) | 1879368.2 | 6426387.93 | 8305756.13 | Vegetation |  | 18318077.75 | 54661273.75 | 72979351.5 | -16438709.55 | Validated amount by FEMA was lower than LUMA formulation
727572 | PA-02-PR-4339-PRJ-727572 | FAASt [Region 3 -Bayamon Group A] High Density (Vegetation) | 11268772.7 | 31317875.94 | 42586648.64 | Vegetation |  | 12945985.39 | 36028872.38 | 48974857.77 | -1677212.69 | Validated amount by FEMA was lower than LUMA formulation
727606 | PA-02-PR-4339-PRJ-727606 | FAASt [Region 4 Caguas TL - 115kV] (Vegetation) | 900812.92 | 3080276.26 | 3981089.18 | Vegetation |  | 36846766.07 | 109548711.44 | 146395477.51 | -35945953.15 | Validated amount by FEMA was lower than LUMA formulation
727608 | PA-02-PR-4339-PRJ-727608 | FAASt [Region 1 San Juan TL - 115kV] (Vegetation) | 1007797.83 | 3446104.8 | 4453902.63 | Vegetation |  | 8206527.54 | 24398735.91 | 32605263.45 | -7198729.71 | Validated amount by FEMA was lower than LUMA formulation
727657 | PA-02-PR-4339-PRJ-727657 | FAASt [Region 5 Mayaguez TL - 115kV] (Vegetation) | 577718.5 | 1975474.09 | 2553192.59 | Vegetation |  | 30865299.08 | 91765278.3 | 122630577.38 | -30287580.58 | Validated amount by FEMA was lower than LUMA formulation
727659 | PA-02-PR-4339-PRJ-727659 | FAASt [Region 2 Arecibo TL - 115kV] (Vegetation) | 953592.14 | 3260751.68 | 4214343.82 | Vegetation |  | 18265704.46 | 54305563.22 | 72571267.68 | -17312112.32 | Validated amount by FEMA was lower than LUMA formulation
741105 | PA-02-PR-4339-PRJ-741105 | FAASt [All Regions TL - 230kV] (Vegetation) | 2430054.31 | 10455751.16 | 12885805.47 | Vegetation |  | 154791845.18 |  | 154791845.18 | -152361790.87 | Validated amount by FEMA was lower than LUMA formulation
749060 | PA-02-PR-4339-PRJ-749060 | FAASt [Transmission Priority Pole Replacement Program Line 5600 Victoria TC – Añasco TC] (Transmission) | 1175435.49 | 140677.54 | 1316113.03 | Transmission
956330 | PA-02-PR-4339-PRJ-956330 | FAASt [Caguas Region 4 - Feeder 3007-03] (Vegetation) | 1914845.33 | 5681119.27 | 7595964.6 | Vegetation |  | 1968823.15 | 5853486.17 | 7822309.32 | -53977.82 | Validated amount by FEMA was lower than LUMA formulation
956331 | PA-02-PR-4339-PRJ-956331 | FAASt [Mayaguez Region 5 Feeder 6014-02] (Vegetation) | 1813962.21 | 5381811.02 | 7195773.23 | Vegetation
956332 | PA-02-PR-4339-PRJ-956332 | FAASt [San Juan Region 1 - Feeder 2401-01] (Vegetation) | 2664861.34 | 7906327.92 | 10571189.26 | Vegetation |  | 2787055.9 | 8286164.87 | 11073220.77 | -122194.56 | Validated amount by FEMA was lower than LUMA formulation
956335 | PA-02-PR-4339-PRJ-956335 | FAASt [San Juan Region 1 - Feeder 2301-02] (Vegetation) | 1798813.63 | 5336866.97 | 7135680.6 | Vegetation |  | 1849955.27 | 5500081.4 | 7350036.67 | -51141.64 | Validated amount by FEMA was lower than LUMA formulation
956337 | PA-02-PR-4339-PRJ-956337 | FAASt [Mayaguez Region 5 Feeder 6012-02] (Vegetation) | 1378198.73 | 4088952.37 | 5467151.1 | Vegetation |  | 1800712.05 | 5353676.97 | 7154389.02 | -422513.32 | Validated amount by FEMA was lower than LUMA formulation
956339 | PA-02-PR-4339-PRJ-956339 | FAASt [Caguas Region 4 - Feeder 3301-01] (Vegetation) | 2887255.43 | 8566144.83 | 11453400.26 | Vegetation |  | 2959532.24 | 8798952.37 | 11758484.61 | -72276.81 | Validated amount by FEMA was lower than LUMA formulation
956340 | PA-02-PR-4339-PRJ-956340 | FAASt [Ponce Region 6 Feeder 5602-02] (Vegetation) | 1210919.69 | 3592655.29 | 4803574.98 | Vegetation
956341 | PA-02-PR-4339-PRJ-956341 | FAASt [Ponce Region 6 Feeder 5803-02] (Vegetation) | 23528.65 | 69806.72 | 93335.37 | Vegetation |  | 24080 | 71591.83 | 95671.83 | -551.35 | Validated amount by FEMA was lower than LUMA formulation
956343 | PA-02-PR-4339-PRJ-956343 | FAASt [Ponce Region 6 Line 4800 – Toro Negro to Aibonito, Santa Isabel] (Vegetation) | 183092.65 | 2178489.85 | 2361582.5 | Vegetation |  | 5271329.93 | 15672132.45 | 20943462.38 | -5088237.28 | Validated amount by FEMA was lower than LUMA formulation
956345 | PA-02-PR-4339-PRJ-956345 | FAASt [Arecibo Region 2 Line 2400 – Dos Bocas HP to Coronillas 2] (Vegetation) | 53038.75 | 631070.47 | 684109.22 | Vegetation |  | 1805809.83 | 5368833.09 | 7174642.92 | -1752771.08 | Validated amount by FEMA was lower than LUMA formulation
956348 | PA-02-PR-4339-PRJ-956348 | FAASt [Bayamon Region 3 Line 10000 – Bayamon Pueblo to Magnolia TO] (Vegetation) | 8718.69 | 103737.61 | 112456.3 | Vegetation |  | 294309.16 | 875007.19 | 1169316.35 | -285590.47 | Validated amount by FEMA was lower than LUMA formulation
956357 | PA-02-PR-4339-PRJ-956357 | FAASt [Mayaguez Region 5 Line 1900 – Dos Bocas HP to San Sebastian TC] (Vegetation) | 153906.79 |  | 153906.79 | Vegetation |  | 3415441.98 | 9313002.71 | 12728444.69 | -3261535.19 | Validated amount by FEMA was lower than LUMA formulation
168483 | PA-02-PR-4339-PRJ-168483 | FAASt - 115kV Line 36400 - Dos Bocas HP to Ponce TC (Transmission) | 106895316 | 8111071 | 115006387 | Transmission
714641 | PA-02-PR-4339-PRJ-714641 | FAASt [Rincón Streetlighting] (Distribution) | 10842339.26 | 694470.58 | 11536809.84 | Distribution | PW Version | 10915553.24 | 1211588.91 | 12127142.15 | -73213.98 | Validated amount by FEMA was lower than LUMA formulation
723002 | PA-02-PR-4339-PRJ-723002 | FAASt - EPC - Jobos TC (Substation) | 70586386.39 |  | 70586386.39 | Substation
551926 | PA-02-PR-4339-PRJ-551926 | FAASt [SCADA Remote Access and RTU Replacements Group 2] (Telecommunication) | 5267467.99 | 1073462.61 | 6340930.6 | Telecommunication | PW Version
547251 | PA-02-PR-4339-PRJ-547251 | FAASt Line 2400 Dos Bocas HP to America Apparel (Transmission) | 50289473.68 |  | 50289473.68 | Transmission
756997 | PA-02-PR-4339-PRJ-756997 | FAASt [TL 1900 Caguanas to Lares TO] (Transmission) | 40557533.61 |  | 40557533.61 | Transmission
756999 | PA-02-PR-4339-PRJ-756999 | FAASt [TL 1900 Lares TO to San Sebastian] (Transmission) | 29319358.78 |  | 29319358.78 | Transmission
750063 | PA-02-PR-4339-PRJ-750063 | FAASt [Region 6 -Ponce Group A] Low Density (Vegetation) | 15889515.9 | 44155237.62 | 60044753.52 | Vegetation |  | 18254467.11 | 50797296.22 | 69051763.33 | -2364951.21 | Validated amount by FEMA was lower than LUMA formulation
750065 | PA-02-PR-4339-PRJ-750065 | FAASt [Region 3 -Bayamon Group A] Low Density (Vegetation) | 18569923.87 | 51603800.04 | 70173723.91 | Vegetation |  | 21333819.52 | 59366309.82 | 80700129.34 | -2763895.65 | Validated amount by FEMA was lower than LUMA formulation
750066 | PA-02-PR-4339-PRJ-750066 | FAASt [Region 4 -Caguas Group A] Low Density (Vegetation) | 28466485.03 | 79097232.76 | 107563717.79 | Vegetation |  | 32703357.23 | 90995446.51 | 123698803.74 | -4236872.2 | Validated amount by FEMA was lower than LUMA formulation
750067 | PA-02-PR-4339-PRJ-750067 | FAASt [Region 2 -Arecibo Group A] Low Density (Vegetation) | 15030146.18 | 41767142.56 | 56797288.74 | Vegetation |  | 17267191.18 | 48049971.59 | 65317162.77 | -2237045 | Validated amount by FEMA was lower than LUMA formulation
750068 | PA-02-PR-4339-PRJ-750068 | FAASt [Region 5 -Mayaguez Group A] Low Density (Vegetation) | 13840548.75 | 38461380.62 | 52301929.37 | Vegetation |  | 15900537.4 | 44246939.88 | 60147477.28 | -2059988.65 | Validated amount by FEMA was lower than LUMA formulation
746309 | PA-02-PR-4339-PRJ-746309 | FAASt [Automation Program Group 30] (Distribution) | 327791.49 | 236273.14 | 564064.63 | Distribution
165213 | PA-02-PR-4339-PRJ-165213 | FAASt – Line 5400 – Rio Blanco HP to Daguao TC to Punta Lima TO to Vieques 2501 to Culebra 3801 (Transmission) | 83734340.49 | 33182392.65 | 116916733.14 | Vieques and Culebra Projects
751655 | PA-02-PR-4339-PRJ-751655 | FAASt [Vieques Microgrid] (Transmission) | 0 | 105481956 | 105481956 | Vieques and Culebra Projects |  |  |  | 0
751656 | PA-02-PR-4339-PRJ-751656 | FAASt [Culebra Microgrid] (Transmission) | 0 | 39954081 | 39954081 | Vieques and Culebra Projects |  |  |  | 0
662238 | PA-02-PR-4339-PRJ-662238 | FAASt [Microwave Point-to-Point Backbone] (Telecommunications) | 14142413.06 | 3014559.92 | 17156972.98 | Telecommunication |  |  |  | 0
746545 | PA-02-PR-4339-PRJ-746545 | FAASt [Primary Control Center / Secondary Data Center & Control Room] (Telecommunication) | 115638378 | 15530896 | 131169274 | Telecommunication |  |  |  | 0
746660 | PA-02-PR-4339-PRJ-746660 | FAASt [Minor Protection, Automation, and Control [PAC] Replacement] (Substation) | 15096658.56 | 1617375.6 | 16714034.16 | Substation |  |  |  | 0
0
|  |  | 873428908.2 | 623788011.17 | 1495829499.37 | 0 | 0 | 443408164.16 | 802481486.81 | 1245889650.97 | -303332908.92
C-2
*Cost presented herein are based on scope of works and/or costs estimates available in Grants Portal. Subject to change after FEMA validation
PW | Genera - Under Formulation | Project Name | 428 | 406 | Total Child | Asset
663383 | PA-02-PR-4339-PRJ-663383 | FAASt [Cambalache Power Plant Permanent Repairs] (Generation) | 30000000 | 33059916 | 63059916 | Generation
663385 | PA-02-PR-4339-PRJ-663385 | CLOSEOUT - FAASt [Mayaguez Hydro-Gas Power Plant Permanent Repairs] (Generation) | -337107.18 |  | -337107.18 | Generation
670036 | PA-02-PR-4339-PRJ-670036 | FAASt [Design Fire Pump for Aguirre Power Complex] (Generation) | 25000000 |  | 25000000 | Generation
948766 | PA-02-PR-4339-PRJ-948766 | FAASt [Physical Security] (Generation) | 5750000 |  | 5750000 | Generation
10622 | PA-02-PR-4339-PW-10622 | FAASt Aguirre Power Plant 003 Combined Cycle (Amendment) | 2209512.12 |  | 2209512.12 | Generation
10710 | PA-02-PR-4339-PW-10710 | FAASt Equipment and Materials | 294281187.01
|  |  | 356903591.95 | 33059916 | 95682320.94 | 0 | 0 | 0 | 0 | 1 | 0
D-2
*Cost presented herein are based on scope of works and/or costs estimates available in Grants Portal. Subject to change after FEMA validation
PRJ | LUMA - Projects to Reactivate | Project Name | 428 | 406 | Total Child | Asset
| 547241 | FAASt Tallaboa 5402 (Substation) | 10924436 | 5628609 | 16553045 | Substation
| 547243 | FAASt Egozcue - 1109 (Substation) | 13896445.76 | 6952342.26 | 20848788.02 | Substation
| 547247 | FAASt Cambalache TC Relocation (Substation) | 5463505.9 | 84733286.06 | 90196791.96 | Substation
| 547343 | FAASt [Victoria TC 7008 Relocation] (Substation) | 6846444.9 | 54844288.98 | 61690733.88 | Substation
| 547344 | FAASt [Acacias 6801 TC Relocation] (Substation) | 8874442.51 | 42895135.02 | 51769577.53 | Substation
| 550894 | FAASt [Baldrich - 1422] (Substation) | 973098 | 28669863 | 29642961 | Substation
| 550986 | FAASt [Condado - 1133] (Substation) | 10649911 | 5427167 | 16077078 | Substation
| 551927 | FAASt [SCADA Remote Access and RTU Replacements Group 3] (Telecommunication) | 19213188.6 | 3299617.88 | 22512806.48 | Substation
| 752277 | FAASt [Substation Ciales 8701] (Substation) | 359175.24 | 4177144.45 | 4536319.69 | Substation
| 177191 | FAASt - 115kV Line 39000 - Aguas Buenas TC to Caguas TC (Transmission) | 19407885 | 906873 | 20314758 | Transmission
| 668669 | FAASt [Line 50500 230kV Mayaguez TC - Mora TC - Cambalache Power Plant] (Transmission) | 307465 |  | 307465 | Transmission
| 718971 | FAASt [Line 50300 (230kV) from Costa Sur Steam Plant to Aguirre Steam Plant] (Transmission) | 15889643 | 901810364 | 917700007 | Transmission
| 748180 | FAASt Transm. Advanced Sensors and Wide-Area Monitoring, Protection, and Control (WAMPAC) System (Telecommunication) |  | 52804979.05 | 52804979.05 | Transmission
| 805519 | FAASt [38kV Recloser TL 1900 Dos Bocas HP to San Sebastian TC] (Transmission) | 708408.01 | 769393.29 | 1477801.3 | Transmission
| 334191 | FAASt [Feeders - Mayaguez Short Term Group 3] (Distribution) | 44675547 | 38483744 | 83159291 | Distribution
| 334293 | FAASt [Feeders - 7805-11- Mayaguez Short Term Group 4] (Distribution ) | 47224922 | 45582792 | 92807714 | Distribution
| 334472 | FAASt [Feeders - San Juan Short Term Group 2] (Distribution) | 18783750 | 5366655 | 24150405 | Distribution
| 334476 | FAASt [Feeders - Carolina Short Term Group 2] (Distribution) | 18285383 | 18767542 | 37052925 | Distribution
| 436616 | FAASt [Feeders - Arecibo Short Term Group 1] (Distribution) | 27194288 | 14494388 | 41688676 | Distribution
| 546374 | FAASt [Feeders - 1620-02 San Juan Short Term Group 3] (Distribution) | 21058160 | 12777559 | 33835719 | Distribution
| 546386 | FAASt [Feeders- El Yunque 2305 - Supply] (Distribution) | 6564391 | 23252037 | 29816428 | Distribution
| 688623 | FAASt [Automation Program Group 1A] (Distribution) | 1005286 | 1877045 | 2882331 | Distribution
| 730541 | FAASt [Feeders - Caguas Short Term Group 8] (Distribution) | 14523276 | 18671456 | 33194732 | Distribution
| 730586 | FAASt [Feeders - Ponce Short Term Group 1] (Distribution) | 18969808 | 12719346 | 31689154 | Distribution
| 730824 | FAASt [Feeders - Ponce Short Term Group 2] (Distribution) | 4115433 | 2840853 | 6956286 | Distribution
| 745851 | FAASt [Automation Program Group 11] (Distribution) | 479854 | 1052298 | 1532152 | Distribution
| 745854 | FAASt [ Automation Program Group 9] (Distribution) | 546905 | 1164604 | 1711509 | Distribution
| 754350 | FAASt [Underground Circuit Feeders - San Juan Group 1] (Distribution) |  | 15123199.33 | 15123199.33 | Distribution
| 754351 | FAASt [Underground Circuit Feeders - San Juan Group 2] (Distribution) |  | 7066632.8 | 7066632.8 | Distribution
| 757945 | FAASt [Pole and Conductor Repair - Arecibo Group 3 - Phase 2] (Distribution) | 2892589.5 | 15039.03 | 2907628.53 | Distribution
| 790446 | FAASt [Pole and Conductor Repair -Caguas Group 4 Phase 2 (Distribution) | 4662521.3 | 28582.12 | 4691103.42 | Distribution
| 817249 | FAASt [Pole and Conductor Repair -Caguas Group 7 - Phase 2] (Distribution) | 5100000 |  | 5100000 | Distribution
| 958367 | FAASt [Feeder Rebuild #6603-01] (Distribution) | 14474191.76 | 1172038.62 | 15646230.38 | Distribution
| 666894 | FAASt [San Juan Streetlighting] (Distribution) | 35282713 | 3532039 | 38814752 | Streetlights
| 671396 | FAASt [Utuado Streetlighting] (Distribution) | 21135871 | 2911033 | 24046904 | Streetlights
| 671400 | FAASt [Barceloneta Streetlighting] (Distribution) | 10053300 | 1109633 | 11162933 | Streetlights
| 678794 | FAASt [Ponce Streetlighting] (Distribution) | 18852071 | 1444528 | 20296599 | Streetlights
| 678795 | FAASt [Arecibo Streetlighting] (Distribution) | 17274978 | 1527389 | 18802367 | Streetlights
| 686482 | FAASt [Isabela Streetlighting] (Distribution) | 8712288 | 733835 | 9446123 | Streetlights
| 690480 | FAASt [Humacao Streetlighting] (Distribution) | 9318022 | 922000 | 10240022 | Streetlights
| 690483 | FAASt [Cayey Streetlighting] (Distribution) | 15993979 | 1319139 | 17313118 | Streetlights
| 690721 | FAASt [Guayama Streetlighting] (Distribution) | 7045719 | 542958 | 7588677 | Streetlights
| 693543 | FAASt [Juncos Streetlighting] (Distribution) | 13468580 | 1643590 | 15112170 | Streetlights
| 693788 | FAASt [Toa Alta Streetlighting] (Distribution) | 7465021 | 481369 | 7946390 | Streetlights
| 697183 | FAASt [Vega Baja Streetlighting] (Distribution) | 11188812 | 1117331 | 12306143 | Streetlights
| 698432 | FAASt [Hormigueros Streetlighting] (Distribution) | 8618625 | 968057 | 9586682 | Streetlights
| 699814 | FAASt [Juana Diaz Streetlighting] (Distribution) | 18680447 | 1909452 | 20589899 | Streetlights
| 701473 | FAASt [Canovanas Streetlighting] (Distribution) | 16995906 | 1574362 | 18570268 | Streetlights
| 704757 | FAASt [Santa Isabel Streetlighting] (Distribution) | 9707069 | 820333 | 10527402 | Streetlights
| 704862 | FAASt [Fajardo Streetlighting] (Distribution) | 13631005 | 1104923 | 14735928 | Streetlights
| 704931 | FAASt [Camuy Streetlighting] (Distribution) | 18265434 | 2269186 | 20534620 | Streetlights
| 724603 | FAASt [Cabo Rojo Streetlighting] (Distribution) | 11029424 | 1044683 | 12074107 | Streetlights
| 738671 | FAASt [25 MW BESS Installation and Integration - Barceloneta] (Substation) |  | 55941767.5 | 55941767.5 | Substation
| 750502 | FAASt [25 MW BESS Installation and Integration - Aguadilla] (Substation) |  | 52720520.35 | 52720520.35 | Substation
| 750503 | FAASt [25 MW BESS Installation and Integration - San Juan] (Substation) |  | 55503065.56 | 55503065.56 | Substation
| 752972 | FAASt [4 x 25 MW BESS Interconnections Manati] (Substation) |  | 57640005.67 | 57640005.67 | Substation |  |  |  | 428 | 406
| 727530 | FAASt [Region 6 -Ponce Group C] (Vegetation) |  | 70421923.26 | 70421923.26 | Vegetation-38kv trans |  | 30675994.85 | 6748718.867 | 1147282.2074 | 5601436.6596
| 727540 | FAASt [Region 2 -Arecibo Group C] (Vegetation) |  | 66510486.76 | 66510486.76 | Vegetation-38kv trans |  | 22276486.15 | 6237416.122 | 1060360.7407 | 5177055.3813
| 727558 | FAASt [Region 3 -Bayamon Group C] (Vegetation) |  | 16374246.76 | 16374246.76 | Vegetation-38kv trans |  | 15994209.03 | 4478378.5284 | 761324.3498 | 3717054.1786
| 727562 | FAASt [Region 5 -Mayaguez Group C] (Vegetation) |  | 84411128.06 | 84411128.06 | Vegetation-38kv trans |  | 30350600.65 | 8498168.182 | 1444688.5909 | 7053479.5911
| 727691 | FAASt [Region 1 -San Juan Group C] (Vegetation) |  | 44200121.5 | 44200121.5 | Vegetation-38kv trans |  | 15885744.3 | 4448008.404 | 756161.4287 | 3691846.9753
| 727694 | FAASt [Region 4 -Caguas Group C] (Vegetation) |  | 76781710.48 | 76781710.48 | Vegetation-38kv trans |  | 8818182.5 | 2469091.1 | 419745.487 | 2049345.613
| 740406 | FAASt [Region 1-San Juan Group B] (Vegetation) |  | 5894785.29 | 5894785.29 | Vegetation-38kv trans |  | 3401453.89 | 952407.0892 | 161909.2052 | 790497.884
| 740408 | FAASt [Region 3-Bayamon Group B] (Vegetation) |  | 11782088.78 | 11782088.78 | Vegetation-38kv trans |  | 8058929.38 | 2256500.2264 | 383605.0385 | 1872895.1879
| 740409 | FAASt [Region 4-Caguas Group B] (Vegetation) |  | 23846154.02 | 23846154.02 | Vegetation-38kv trans |  | 8648977.51 | 2421713.7028 | 411691.3295 | 2010022.3733
| 740410 | FAASt [Region 2-Arecibo Group B] (Vegetation) |  | 5425376.76 | 5425376.76 | Vegetation-38kv trans |  | 3037012.4 | 850363.472 | 144561.7902 | 705801.6818
| 740411 | FAASt [Region 5-Mayaguez Group B] (Vegetation) |  | 3777166.88 | 3777166.88 | Vegetation-38kv trans |  | 1713742.68 | 479847.9504 | 81574.1516 | 398273.7988
| 740414 | FAASt [Region 6-Ponce Group B] (Vegetation) |  | 13788400.37 | 13788400.37 | Vegetation-38kv trans |  | 9664207.39 | 2705978.0692 | 460016.2718 | 2245961.7974
| 741097 | FAASt [Region 1 San Juan Subs/Telecom] (Vegetation) |  | 1347191.63 | 1347191.63 | Vegetation- Dist |  | 1347191.63 | 377213.6564 | 64126.3216 | 313087.3348
| 741098 | FAASt [Region 3 Bayamon Subs/Telecom] (Vegetation) |  | 961518.65 | 961518.65 | Vegetation- Dist |  | 961518.65 | 269225.222 | 45768.2877 | 223456.9343
| 741100 | FAASt [Region 4 Caguas Subs/Telecom] (Vegetation) |  | 1428325.86 | 1428325.86 | Vegetation- Dist |  | 1428325.86 | 399931.2408 | 67988.3109 | 331942.9299
| 741101 | FAASt [Region 2 Arecibo Subs/Telecom] (Vegetation) |  | 1058188.92 | 1058188.92 | Vegetation- Dist |  | 1058188.92 | 296292.8976 | 50369.7926 | 245923.105
| 741102 | FAASt [Region 5 Mayaguez Subs/Telecom] (Vegetation) |  | 1516985.37 | 1516985.37 | Vegetation- Dist |  | 1516985.37 | 424755.9036 | 72208.5036 | 352547.4
| 741104 | FAASt [Region 6 Ponce Subs/Telecom] (Vegetation) |  | 1992973.53 | 1992973.53 | Vegetation- Dist |  | 1992973.53 | 558032.5884 | 94865.54 | 463167.0484
|  |  | 636789618.48 | 2093674845.85 | 2730464464.33 |  |  |  |  | 7628247.3478 | 37243795.8744

## Sheet1 (hidden)
| Presented | FAAST Obligated Amount
Teleccom | 685928720.98 | 685928720.98
Substations | 781890093.7 | 781890093.7
Transmission | 2642131654.47 | 2642131654.47
Generation | 108927715.08 | 108927715.08
Buildings | 125088362.54 | 125088362.54
Dams/Hydro | 585926275.87 | 860926275.87
Distribution | 5499837404.9 | 5499837404.9
Total | 10429730227.54 | 10704730227.54
|  | 275000000 | Insurance Proceeds Deduction
10429730227.54

## Additional Projects 7-31 (hidden)
Project # | Title | FEMA Allocation | Asset | SUB ASSET | Previous Process Step | Process Step as of 7-15-25 | Project Estimated Cost | Current Version Cost | 428 | 406 | A&E-PW 9510 | E&M-PW 10710 | A&E Costs Incurred | E&M Cost | Project Status 7/31/25 |  | Project Scope | Project in List
Projects Identified by PREPA in Pipeline 7-17-25
551963 | FAASt [Transport Network Group 1] (Telecommunication) | Pipeline | Telecommunication | Telecomm | Pending Recipient Final Review | Pending Recipient Final Review | 7469879.13 | 5490296.88 | 5490296.88 | 0 | 836416.02 | 1143166.23 | 9420564 | 1143166 | Pending Recipient Review- Pending LUMA information regarding A&E COSTS |  | Project involves assessing sites and designing/installing "Make-Ready" infrastructure and Transport/ITOT network equipment, followed by commissioning and transitioning substation OT services. | Included
755211 | FAASt [Automation Program Group 15] (Distribution) | Pipeline | 428 Distribution Automation | Automation | Applicant Signed Project | Applicant Signed Project | 725419.42 | 643560.85 | 643560.85 | 0 | 81858.57 | 0 | Not available | Not available | Pending Obligation |  | Installation of smart reclosers with microprocessor-based controllers and the remote monitoring, communications ready and control capabilities in transmission and distribution lines. Installation of cutout type single phase reclosers, with microprocessor-based controllers. Installation of fault current indicators (communications ready). | Included
679133 | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 4] (Distribution) | Pipeline | Distribution | Poles | Applicant Signed Project | Applicant Signed Project | 0 | -20729 |  |  |  |  | Not available | Not available | Pending Obligation |  | The applicant intents to replace damage and update structures to current standards of poles and conductors for the feeders within the Arecibo Group 4 (Mirador Azul -8007-01, 8007-03; Dominguito - 8010-02, 8010-03; Factor 1 -8011-01 and San Daniel - 8013-02). | Included
Projects in EHP Identified by FEMA List 7-17-25
168483 | FAASt - 115kV Line 36400 - Dos Bocas HP to Ponce TC (Transmission) | Phase 2 | Transmission | Transmission | Not included on FEMA initial list | Pending EHP Review | 0 | [7 empty] | The purpose of this Version is the EHP compliance review of the projects studies that will include geotechnical testing that require vegetation removal, opening of access roads and other impacts that are closer to construction activities |  | "3/18/2025 - The Version 0 Boring Plan Evaluation start on March 18, 2025. 6/9/2025 - Field EHP: (ESA) Consultation process initiated; drafting ongoing. ECD 7/30/2025. 6/3/2025 - Follow up email sent to the Applicant on May 29, 2025, requesting new forecast for submission of dimensions (list of structures) of concrete foundations and revise FEMA OPGW Resolution. The project is under line priority evaluation forecasted TBD. Forecast was established for April 2025." | Included
757687 | FAASt [Automation Program Group 22] (Distribution) | Priority | 428 Distribution Automation | Automation | Pending EHP Review | Pending EHP Review | 2792415 | 2356733.87 | 2356733.87 | 0 | 359230.44 | 412012.16 | 3246 | 412012 | EHP - Environmental: Initial review. Expected Completion Date (ECD) 07/31/2025. System Glitch: Project waiting to be sent back to make corrections to DSOW. |  | Deployment of grid automation technologies in feeders. | Included
757697 | FAASt [Automation Program Group 32] (TL / Distribution) | Priority | 428 Distribution Automation | Automation | Pending EHP Review | Pending EHP Review | 2663099 | 1996678.58 | 1996678.58 | 0 | 339647.19 | 666420.83 | 28222 | 666420 | EHP - Environmental: In Review. Expected Completion Date (ECD) 08/01/2025. |  | Deployment of grid automation technologies in feeders. | Included
812569 | FAASt [Feeder Rebuild 3502-02] (Distribution) | Phase 2 | Distribution | Feeders | Pending Initial Project Development | Pending EHP Review |  | 15430988 |  |  |  |  | Not available | Not available | Field EHP: In review. Expected Completion Date (ECD) updated to 7/15/2025. |  | The project consists of the removal and replacement of 104 poles, the installation of 13 new poles that will be located within the easement, and work on 10 existing poles to comply with codes and standard. | Included
817956 | FAASt [Feeder Rebuild # 1303-02] (Distribution) | Phase 2 | Distribution | Feeders | Pending Initial Project Development | Pending EHP Review |  | 6132436 |  |  |  |  | Not available | Not available | Field EHP: In review. Expected Completion Date (ECD) updated to 7/15/2025. |  | The work to be performed includes but is not limited to; repair/replace poles/structures, damaged crossarms, broken and obsolete hardware, primary and secondary overhead and/or underground distribution lines, and porcelain insulation. | Included
714641 | FAASt [Rincón Streetlighting] (Distribution) | Phase 2 | Distribution | Streetlights | Pending Scope & Cost Completion by Applicant | Pending EHP Review | 14055391.76 | 10915553.24 | 10915553.24 | 1211588.91 | 1928249.61 | 753614 | Not available | Not available | Waiting for LUMA to submit DSOW and CE revision as per Vegetation PA 428 Incidental Meeting held 04.22.2025, LUMA forecast 6/19/2025. 6/30/2025 PDMG call with LUMA team to clarify buffer zone for locations duplicated in Vegetation project.Waiting on response from applicant. |  | Streetlight repairs by replacing lightning components, poles, underground circuits and material disposal. | Included
723002 | FAASt - EPC - Jobos TC (Substation) | Phase 2 | Substation | Substation | Pending PDMG Scope & Cost Routing | Pending EHP Review |  | 69904580.54 |  |  |  |  | Not available | Not available | "7/9/2025 EHP RFI-PRJ-116045 response received on 7/4/2025. Project will continue GM flow. -Process Step: Pending Insurance Completion " |  | Construction of the facilities, reconfiguration and replacement of disaster-related damaged components and electrical systems into these new facilities, and the addition of new components to restore the facility to the pre-disaster functions with the applicable codes and standards | Included
551926 | FAASt [SCADA Remote Access and RTU Replacements Group 2] (Telecommunication) | Phase 2 | Telecommunication | Telecomm | Pending Scope & Cost Completion by Applicant | Pending EHP Review |  | 6753699.16 | 5267467.99 | 1073462.61 |  |  | Not available | Not available | Before moving the project forward to the CRC, LUMA must update the “Legend Sites” tab of the Cost Estimate, as it includes the substations that were removed from this new version. |  | SCADA Remote Access and RTU Replacements | Included
673292 | FAASt Telecom Infrastructure - Cerro Puntas (Telecommunication) | Pipeline | Telecommunication | Telecomm | Pending EHP Review | Pending EHP Review | 9249004.2 | 8124106.79 | 8124106.79 | 49577.82 | 1075319.59 |  |  |  | "Field EHP - Historic: SHPO consultation process initiated; drafting ongoing. Expected Completion Date: 06/27/2025. " |  | Update the tower facilities and telecommunication building to current codes and standards via repair. This will be achieved by performing the engineering and structural assessments necessary to establish the amount of damage and the necessary repairs or rebuild to update or replace the structure. The engineering assessment shall include the field mapping of structure and appurtenances, geotechnical study, and foundation exploratory. A run rigorous tower structural analysis will be done and with results determined if the tower needs a minor repair or a major repair. | Included
547251 | FAASt Line 2400 Dos Bocas HP to America Apparel (Transmission) | Phase 2 | Transmission | Transmission | Pending Scope & Cost Completion by Applicant | Pending EHP Review | 54042908.97 | 50289473.68 | 50289473.68 |  | 3753435.29 | 975659.88 | Not available |  | 4/10/2025 - The Version 0 Boring Plan Evaluation was Completed as of April 8, 2025. 7/15/2025 - The project is running in the Grant Manager queue. The project is Pending EHP Review |  | Repair/Replace structures (including their foundations), framing and insulators, load break switches (manual and automated), conductors, guy wires, anchoring, grounding assemblies, and any other associated components. Most of the construction along this line segment consists of wood monopole guyed structures with some interspersed self-supporting steel and concrete monopoles. | Included
756997 | FAASt [TL 1900 Caguanas to Lares TO] (Transmission) | Phase 2 | Transmission | Transmission | Pending Scope & Cost Completion by Applicant | Pending EHP Review | 43739699.88 | 40557533.61 | 40557533.61 |  |  |  | Not available | Not available | 7/15/2025 - The project is running in the Grant Manager queue. The project is Pending EHP Review. |  | Repair/Replace structures (including their foundations), framing and insulators, load break switches (manual and automated), conductors, guy wires, anchoring, grounding assemblies, and any other associated components. Most of the construction along this line segment consists of wood monopole guyed structures with some interspersed self-supporting steel and concrete monopoles. This line primarily traverses forested and urban areas between Dos Bocas HP substation and San Sebastian TC substation. | Included
756999 | FAASt [TL 1900 Lares TO to San Sebastian] (Transmission) | Phase 2 | Transmission | Transmission | Pending Scope & Cost Completion by Applicant | Pending EHP Review | 32495692.2 | 29319358.78 | 29319358.78 |  | 2088488.51 | 1087844.91 | Not available | Not available | 7/152025 - The project is running in the Grant Manager queue. The project is Pending EHP Review. |  | Repair/Replace structures (including their foundations), framing and insulators, load break switches (manual and automated), conductors, guy wires, anchoring, grounding assemblies, and any other associated components. Most of the construction along this line segment consists of wood monopole guyed structures with some interspersed self-supporting steel and concrete monopoles. This line primarily traverses forested and urban areas between Dos Bocas HP substation and San Sebastian TC substation. | Included
750063 | FAASt [Region 6 -Ponce Group A] Low Density (Vegetation) | Priority | Vegetation | Vegetation-DT | Pending EHP Review | Pending EHP Review | 69341045.82 | 18254467.11 | 18254467.11 | 50797296.22 | 289282.49 | 0 |  |  | 7/15/2025 - Field EHP: (ESA) Consultation letter submitted to (USFWS) on 05/29/2025. Waiting for response. (Updated ECD to 08/08/2025). |  | Removal and, when necessary, disposal of vegetative materials that pose an immediate threat to the distribution lines within Region 6 (Ponce). | Included
750065 | FAASt [Region 3 -Bayamon Group A] Low Density (Vegetation) | Priority | Vegetation | Vegetation-DT | Pending EHP Review | Pending EHP Review | 81038211 | 21333819.52 | 21333819.52 | 59366309.82 | 338081.66 | 0 |  |  | 7/15/2025 - Field EHP: ESA Consultation letter submitted to USFWS on 05/29/2025. Waiting for response. ECD 7/28/2025. |  | Removal and, when necessary, disposal of vegetative materials that pose an immediate threat to the distribution lines within Region 3 (Bayamon). | Included
750066 | FAASt [Region 4 -Caguas Group A] Low Density (Vegetation) | Priority | Vegetation | Vegetation-DT | Pending EHP Review | Pending EHP Review | 124213686.46 | 32703357.23 | 32703357.23 | 90995446.51 | 514882.72 | 0 |  |  | 7/15/2025 - Field EHP - Environmental: ESA Consultation letter submitted to USFWS on 06/03/2025. Waiting for response. ECD 08/12/2025. |  | Removal and, when necessary, disposal of vegetative materials that pose an immediate threat to the distribution lines within Region 4 (Caguas). | Included
750067 | FAASt [Region 2 -Arecibo Group A] Low Density (Vegetation) | Priority | Vegetation | Vegetation-DT | Pending EHP Review | Pending EHP Review | 65590799.69 | 17267191.18 | 17267191.18 | 48049971.59 | 273636.92 | 0 |  |  | 7/15/2025 - Field EHP: ESA and CBRA Consultation letter submitted to USFWS on 06/05/2025. Waiting for response. ECD 08/19/2025 |  | Project is for the removal and, when necessary, disposal of vegetative materials that pose an immediate threat to the distribution lines within Region 2 (Arecibo). | Included
750068 | FAASt [Region 5 -Mayaguez Group A] Low Density (Vegetation) | Priority | Vegetation | Vegetation-DT | Pending EHP Review | Pending EHP Review | 60147477.28 | 15900537.4 | 15900537.4 | 44246939.88 | 251979.26 | 0 |  |  | 7/15/2025 -Field EHP: ESA Consultation letter submitted to USFWS on 06/03/2025. Waiting for response. ECD 08/19/2025. |  | Removal and, when necessary, disposal of vegetative materials that pose an immediate threat to the distribution lines within Region 5 (Mayaguez). | Included
956593 | FAASt [Factor Sect 8014 Transformer Replacement] (Substation) | Phase 2 | Substation | Substation | Not included on FEMA initial list | Pending EHP Review | 5907319.61 | 3751193.63 | 3751193.63 |  | 1741264.87 | 414861.11 |  |  | Field EHP - Environmental: In review. Amended Expected Completion Date (07/25/2025) | Field EHP - Environmental: In review. Amended Expected Completion Date (07/25/2025) | Factor Sectionalizer has two 38/13.2kV transformers, but one is out of service. The purpose of this project is to stabilize the distribution and transmission grids around the Factor Sectionalizer by replacing the out-of-service transformer. | Included
Projects categorized as Priority Identified by FEMA List 7-17-25
746309 | FAASt [Automation Program Group 30] (Distribution) | Phase 2 | Distribution | Automation | Pending FEMA 406 HMP Completion | Pending FEMA 406 HMP Completion | 668110 | 425975.74 | N/A | N/A | N/A | N/A | 19113 | 163655 | On 7/14/2025 Project moved to FEMA 406 HMP completion. |  | Deployment of grid automation technologies in feeders. | Included
757662 | FAASt [Automation Program Group 21] (Distribution) | Priority | 428 Distribution Automation | Automation | Pending EHP Review | Pending Final FEMA Review | 2216560 | 1710547.94 | 1710547.94 | 0 | 280516.59 | 512796.48 | 2634 | 512796 | On 7/15/2025 Project moived to FEMA Final Review. |  | Deployment of grid automation technologies in feeders. | Included
757694 | FAASt [Automation Program Group 27] (Distribution) | Priority | 428 Distribution Automation | Automation | Pending EHP Review | Pending Final FEMA Review | 3271077 | 2314733.78 | 2314733.78 | 0 | 419922.13 | 977936.96 | 20360 | 977936 | On 7/7/2025 Project moved to Final FEMA Review. |  | Deployment of grid automation technologies in feeders. | Included
757698 | FAASt [Automation Program Group 33] (Distribution) | Priority | 428 Distribution Automation | Automation | Pending EHP Review | Pending Final FEMA Review | 2250901 | 1888928.21 | 1888928.21 | 0 | 311582.64 | 594117.44 | 5530 | 594117 | On 7/7/2025 Project moved to Final FEMA Review. |  | Deployment of grid automation technologies in feeders. | Included
757699 | FAASt [Automation Program Group 34] (Distribution) | Priority | 428 Distribution Automation | Automation | Pending EHP Review | Pending Formulation Completion | 3507467 | 2755938.99 | 2755938.99 | 0 | 462362.68 | 683789.12 | 28757 | 683789 | EHP - Initial review. ECD 6/24/2025. 2nd System Glitch: Project waiting to system glitch to make corrections to project facility description. |  | Deployment of grid automation technologies in feeders. | Included
957578 | FAASt [Costa Sur TC Underground Cable Failure Replacement on Transformer Lead Bank #2] (Substation) | Phase 2 | Substation | Substation | Not included on FEMA initial list | Pending EHP Review | 1250845.76 | 1108989.51 | 1108989.51 |  | 141856.25 |  |  |  | "7/15/2025- (Stabilization Projects) Project created as part of the Stabilization Projects. Applicant upload DSOW with corrections. -Process Step: Pending Insurance Completion | Project costs changed- project moved to EHP Review 7-16-25- Part of LUMA Priority stabilization |  | Included
Projects categorized as Priority Identified on COR3 List 7-17-25
165213 | FAASt – Line 5400 – Rio Blanco HP to Daguao TC to Punta Lima TO to Vieques 2501 to Culebra 3801 (Transmission) | Priority | Vieques and Culebra Projects (6) | Transmission | Pending Scope & Cost Completion by Applicant | Pending Scope & Cost Completion by Applicant | 122806969.07 | 83734340.49 | 83734340.49 | 33182392.65 | 5890235.93 | N/A |  |  | 7/8/2024 - The Version 0 Boring Plan Evaluation was Completed as of June23, 2023. 6/9/2025 - The 4th HM RFI was submitted to the Applicant for their action. New Deadline is established by the Applicant for 6/26/2025." |  | Repair/Replace insulators, guy wires; anchors, structure connections, structure foundations or portions of the foundations; ground of the structure and overhead ground conductor; communications associated with the transmission line; conductor spans, bird caged, pitting, burns, kinks, or stretched conductor; and/or drag dampers, armor rods; and other hardware. | Included
751655 | FAASt [Vieques Microgrid] (Transmission) | Priority | Vieques and Culebra Projects (6) | Microgrid | Pending Scope & Cost Completion by Applicant | Pending Scope & Cost Completion by Applicant | 105481956 |  | N/A | 105481956 | N/A | N/A |  |  | "6/27/2025 - Pending form Applicant to submit the DSOW with all the necessary information. Also, 1st HM RFI was submitted to the applicant on September 13, 2024, for their action. The initial strategy for both projects was submitted on July 19, 2024. Subsequently, the first mitigation RFI was issued on September 13, 2024, with a deadline of September 27, 2024. Since then, FEMA has not received any further information.As noted, the applicant has now proposed a new deadline of April 24, 2025. FOllow up email sent on 4/8/2025. -Applicant forecast date:7/24/2025." |  | Construct a new microgrid system to provide resiliency, power quality, energy redundancy, stand-alone and black start capabilities to the island of Vieques. | Included
751656 | FAASt [Culebra Microgrid] (Transmission) | Priority | Vieques and Culebra Projects (6) | Microgrid | Pending Applicant 406 HMP Completion | Pending Scope & Cost Completion by Applicant | 39954081 |  | N/A | 39954081 | N/A | N/A |  |  | "6/27/2025 - Pending form Applicant to submit the DSOW with all the necessary information. Also, 1st HM RFI was submitted to the applicant on September 13, 2024, for their action. The initial strategy for both projects was submitted on July 19, 2024. Subsequently, the first mitigation RFI was issued on September 13, 2024, with a deadline of September 27, 2024. Since then, FEMA has not received any further information.As noted, the applicant has now proposed a new deadline of April 24, 2025. FOllow up email sent on 4/8/2025. -Applicant forecast date:7/24/2025." |  | Construct a new microgrid system to provide resiliency, power quality, energy redundancy, stand-alone and black start capabilities to the island of Culebra. | Included
165225 | FAASt - EPC - Vieques 2501 substation repairs & New Vieques 2502 substation (Substation) | Priority | Vieques and Culebra Projects (6) | Substation | Pending Scope & Cost Completion by Applicant | Pending Scope & Cost Completion by Applicant | 16374033.72 | 13495526.25 | 14704637.25 | 178309 | 1491087.47 | 0 | TBD | No | Still Pending Scope and Cost by LUMA | N/A | Repair and replacement of the control house, building waterproofing, protection & control features, auxiliary equipment, 38 kV circuit breaker & steel structure, foundations, conduit, control cables, batteries, lights, grounding, finish grade, perimeter fence and other components to restore functionality. | Included
Projects categorized as Priority LUMA
678800 | FAASt [Telecom Infrastructure – Group B] (Telecommunication) | Phase 2 | Telecommunication | Telecomm | Pending Scope & Cost Completion by Applicant | Pending Scope and Cost Development | 16033618.38 | 13148929.44 | 13148929.44 | 55895.84 | 2828793.1 | N/A | Not available | Not available | HM ph2 RFI sent on 7/7/2025 |  | Atalaya, El Gato, Isabela Plata 1, La Santa, and Manatí TC boring & self-supported tower. | Included
662238 | FAASt [Microwave Point-to-Point Backbone] (Telecommunications) | Phase 2 | Telecommunication |  | Pending Scope & Cost Completion by Applicant | Pending Scope & Cost Completion by Applicant | 34875800.66 | 14142413.06 | 14142413.06 | 3014559.92 | 3576414.62 |  | TBD | No | DSOW was submitted to FEMA on 7/25 | Not available |  | Included
746545 | FAASt [Primary Control Center / Secondary Data Center & Control Room] (Telecommunication) | Phase 2 | Telecommunication | Telecomm | Pending PDMG Scope & Cost Routing | Pending PDMG Scope & Cost Routing | 131169274 | 115638378 | 115638378 | 15530896 |  |  | TBD | No | The formulation of this project will depend on the resulution or modification of the actual Environmental & Historic Preservation(EHP) determination. Project formualtion process needs to be revised. If no corrections are executed, Project to be removed from the FAAST Consolidated Plan List | Not available | Relocation of existing Operations teams and equipment, as well as the removal / relocation of electrical infrastructure from the Monacillos campus. The project has three areas of scope. The scope of work description is organized by the area of work. The three areas include (1) the Guaynabo ESC building rehabilitation in Guaynabo, (2) the Durotex Building rehabilitation on the Monacillos campus, (3) and the new PCC building construction / site improvements on the Monacillos campus. | Included-Conditionally
746660 | FAASt [Minor Protection, Automation, and Control [PAC] Replacement] (Substation) | Phase 2 | Substation | Substation | Pending Scope & Cost Completion by Applicant | Pending Scope & Cost Completion by Applicant | 16713944.15 | 15096658.56 | 15096658.56 | 1617375.6 | N/A | N/A | TBD | No | Luma agreed to complete request by July 31,2025. If RFI response is not completed or the response doesn't suffice FEMA request, Project to be removed from the FAAST Consolidated Plan List | Not available | Increase protection and Control System that protect the electrical components such as Transmission Lines, Transformers, Bus Bar, Breakers, etc | Included-Conditionally
616432339.29
Note on I2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Either Current Version Gross Cost or Best Available Cost (Initial Estimate based on DI Creation)

## Amendment Request (hidden)
|  |  |  | Obligated Amount |  |  | Amendment Request
PW | LUMA - Obligated | Project Name | Asset | 428 | 406 | Total Child | 428 | 406 | Total Amendment | Difference
10841 | PA-02-PR-4339-PW-10841 | FAASt Physical Security - Group 1 (Substatio | Substation | 6025270.22 | 665958.96 | 6691229.18
11350 | PA-02-PR-4339-PW-11350 | FAASt Physical Security - Group 2 (Substation) | Substation | 2159012.31 | 224680.68 | 2383692.99
11372 | PA-02-PR-4339-PW-11372 | FAASt [Physical Security - Group 3] (Substation) | Substation | 3696956.6 | 436383.23 | 4133339.83
11566 | PA-02-PR-4339-PW-11566 | FAASt [Physical Security - Group 4] (Substation) | Substation | 3478518 | 338280 | 3816798

## Revisions 7-7 (hidden)
723883 | Project Duplicated on previous list- To be removed
727572 | Project Duplicated on previous list- To be removed
790443 | Project to be Included- Already approved pending Obligation (Applicant Signed Project) To be included in the list because the amount has not yet been debited from the FAASt funds.
165209 | Project to be Included-Project Previously Obligated but PW version is in progress.Project Missing on previous list submitted
757700 | Project to be included- Project in Pipeline Pending Recipient Final Review
800286 | Project to be Included-Project in Pipeline Pending Recipient Final Review (Pending COR3 Approval)
Project # | Title | Asset | SUB ASSET | Process Step | Project costs - Submitted to FEMA * | Current PW Version 428 Gross Cost * | 428 Allocation * | 406 Allocation * | A&E-PW 9510 * | E&M-PW 10710 * | A&E Costs Incurred-Luma Provided * | E&M Cost - Luma Provided * | Project Status | Project Scope | Additional comments
723883 | FAASt [Region 1 -San Juan Group A] (Vegetation) | Vegetation | Vegetation | Pending Applicant Project Review (Pending LUMA Approval- Last step) | 25072092.11 | 6584889.61 | 6584889.61 | 18404524.67 | 82677.83 | 0 |  |  | Project Version 1 obligation in process- | This scope of work is for the removal and, when necessary, disposal of vegetative materials that pose an immediate threat to the distribution lines within Region 1 (San Juan). | Project included in list since its already in Pipeline, soon to be Obligated. Project part of LUMA Priority Projects P3A list
727572 | FAASt [Region 3 -Bayamon Group A] High Density (Vegetation) | Vegetation | Vegetation | Pending Applicant Project Review- On Hold Pending Expert R. | 48974857.77 | 12945985.39 | 12945985.39 | 36028872.38 | 0 | 0 | 5950 | 0 | 6/17/2025 - The project is under review by Expert review since 4/14/2025. | Vegetation Clearing for Region Bayamon High Density | Project included in list since its already in Pipeline, soon to be Obligated. Project part of LUMA Priority Projects P3A list
790443 | FAASt [Pole and Conductor Repair -San Juan Group 3 Phase 2 (Distribution) | Distribution | Poles | Applicant Signed Project( Project Approved- Pending Obligation) | 248306 | 186697 | 186697 | 0 | 25985 | 35624 | 14074 | 35624 | Pending Recipient Final Review since 5/22/2025. | Planned to replace poles in San Juan region | Project included in list since its already in Pipeline, soon to be Obligated.
165209 | FAASt - EPC - Culebra Substation 3801 and New Culebra Substation 3802 (Substation) | Vieques and Culebra Projects (6) | Substation | Pending Scope & Cost Completion by Applicant | 16241388 | 12765828 | 14048046 | 177391 | 2015951 | 0 |  |  |  | Repair and replacement of the control house HVAC, building waterproofing, protection & control features, auxiliary equipment, conduits, control cables, batteries, lights, grounding, finish grades, perimeter fence, and other components to restore functionality.
757700 | FAASt [Automation Program Group 35] (TL / Distribution) | 428 Distribution Automation | Automation | Pending Recipient Final Review (Pending COR3 Approval) | 1988436.16 | 1318515.66 | 1318515.66 | 0 | 245359.86 | 424560.64 | 11070 | 424560.64 | EHP: In review. Expected Completion Date (ECD) 6/23/2025. Project advanced to Pending Recipient Review | Deployment of grid automation technologies in feeders. | Project included in list since its already in Pipeline, soon to be Obligated. Project part of LUMA Priority Projects P3A list. Luma stated no duplication with DOE projects
800286 | FAASt [Automation Program Group 36] (TL / Distribution) | 428 Distribution Automation | Automation | Pending Recipient Final Review (Pending COR3 Approval) | 2601467.86 | 1703712.83 | 1703712.83 | 0 | 300364.95 | 597390.08 | 0 | 597390 | EHP: In review. Expected Completion Date (ECD) 6/23/2025. Project advanced to Pending Recipient Review | Deployment of grid automation technologies in feeders. | Project included in list since its already in Pipeline, soon to be Obligated. Project part of LUMA Priority Projects P3A list. Luma stated no duplication with DOE projects

## Streetlights (hidden)
Streetlights Projects- Obligated PWS |  |  |  | FEMA Approved Cost |  |  |  | Disbursements |  | LUMA Provided Status
PW | GM# | Project Name | Municipality | 428 | 406 | Total Child | Asset | WCA | Reimbursement | Construction % | Construction Start Date | Estimated Completion Date
10499 | 542690 | FAASt Maunabo Streetlighting (Distribution) | Maunabo | 6199877.07 | 243880.33 | 6443757.4 | Distribution | 745644.61 | 4153049.13 | 95% | 2022-06-20 | 2025-12-31
10515 | 542517 | FAASt -Luquillo Distribution Streetlighting | Luquillo | 8628667.29 | 181658.08 | 8810325.37 | Distribution | 1982323.21 | 1330293.84 | 87% | 2022-06-27 | 2026-06-11
10521 | 542687 | FAASt Lajas Streetlighting (Distribution) | Lajas | 10278336.09 | 426332.48 | 10704668.57 | Distribution | 862888.71 | 2893069.03 | 92% | 2022-07-05 | 2026-01-20
10538 | 542756 | FAASt Streetlighting - Guánica (Distribution | Guánica | 9687238 | 370808 | 10058046 | Distribution | 2263060.35 | 2159277.72 | 83% | 2022-08-10 | 2026-02-18
10539 | 542688 | FAASt Aguada Streetlighting (Distribution) | Aguada | 17764494.34 | 807222.04 | 18571716.38 | Distribution | 4178636.19 | 5339770.29 | 87% | 2022-06-15 | 2026-01-27
10857 | 660239 | FAASt Streetlighting - Villalba (Distributio | Villalba | 10190536.05 | 681865.66 | 10872401.71 | Distribution | 3295090.96 | 5232394.58 | 86% | 2022-10-28 | 2026-05-15
10876 | 659715 | FAASt Distribution Streetlighting - Aibonito | Aibonito | 7074498 | 178787 | 7253285 | Distribution | 475221.8 | 2941855.15 | 88% | 2022-11-22 | 2026-01-14
10884 | 659623 | FAASt Distribution Streetlighting - Cataño | Cataño | 16996758 | 565289 | 17562047 | Distribution | 1452497.71 | 652424.89 | 77% | 2022-11-28 | 2026-03-31
11095 | 660227 | FAASt Hatillo Streetlight (Distribution) | Hatillo | 18570095.25 | 1764387.7 | 20334482.95 | Distribution | 2526687.11 | 4092914.73 | 76% | 2022-11-22 | 2026-09-04
11097 | 660437 | FAASt Manati Streetlight (Distribution) | Manati | 27067865 | 1568964 | 28636829 | Distribution | 5778104.62 | 2681869.57 | 65% | 2022-11-04 | 2026-05-16
11099 | 659625 | FAASt Distribution Streetlighting - Dorado | Dorado | 22864972 | 1505645 | 24370617 | Distribution | 1599042.88 | 2266792.46 | 76% | 2022-11-22 | 2026-04-30
11317 | 673504 | FAASt [Distribution Streetlighting - Gurabo] | Gurabo | 19208994 | 1533300 | 20742294 | Distribution | 2765597.72 | 3315723.98 | 61% | 2023-03-06 | 2027-06-13
11318 | 659968 | FAASt [San Germán Streetlighting] (Distributio | San Germán | 30849348 | 4033578 | 34882926 | Distribution | 7626675.36 | 3614773.03 | 68% | 2023-05-08 | 2027-04-12
11319 | 690545 | FAASt Aguadilla Streetlight (Distribution) | Aguadilla | 19796809 | 1295775 | 21092584 | Distribution | 1589507.11 | 1119035.23 | 47% | 2023-05-02 | 2026-06-06
11326 | 691702 | FAASt Distribution Streetlighting - Trujillo Alto (Distribution) | Trujillo Alto | 25277347 | 1009578 | 26286925 | Distribution | 662915.06 | 594100.24 | 40% | 2023-04-25 | 2026-06-04
11344 | 698424 | FAASt Streetlight Florida Distribution | Florida | 9311841.53 | 997190 | 10309031.53 | Distribution | 1724054.7 | 595477.4 | 60% | 2023-04-05 | 2027-12-18
11351 | 679039 | FAASt [Distribution Streetlighting - Caguas] (Distribution) | Caguas | 73737224.58 | 1849344.06 | 75586568.64 | Distribution | 674990.31 | 2031704.88 | 44% | 2023-05-05 | 2026-07-15
11518 | 698458 | FAASt [Distribution Streetlighting - Guaynabo] (Distribution) | Guaynabo | 9762754.59 | 853056.42 | 10615811.01 | Distribution | 2072428.67 | 2630171.1 | 74% | 2023-06-26 | 2026-05-13
11522 | 671502 | FAASt [Distribution Streetlighting - Yabucoa] (Distribution) | Yabucoa | 14918381.07 | 1965608.26 | 16883989.33 | Distribution | 2414051.02 | 1992076.43 | 67% | 2023-07-11 | 2026-03-06
11524 | 704679 | FAASt Coamo Streetlight (Distribution) | Coamo | 14311922.45 | 2060901.35 | 16372823.8 | Distribution | 3487459.86 | 4210750.96 | 68% | 2023-08-29 | 2027-02-07
11526 | 698439 | FAASt Streetlight - Las Marías (Distribution) | Las Marías | 7073217 | 1287705 | 8360922 | Distribution | 1573712.55 | 873730 | 53% | 2023-05-31 | 2028-09-21
11532 | 678793 | FAASt [Streetlighting - Mayagüez] (Distribution) | Mayagüez | 11019180.1 | 1352204.36 | 12371384.46 | Distribution | 2783561.5 | 400761 | 54% | 2023-06-26 | 2026-12-07
11533 | 678789 | FAASt [Distribution Streetlighting - Carolina] (Distribution) | Carolina | 14865613.02 | 1158946.56 | 16024559.58 | Distribution | 3148514.28 | 3236429.8 | 66% | 2023-08-18 | 2026-02-15
11540 | 679780 | FAASt [Distribution Streetlighting - Bayamon] (Distribution) | Bayamon | 20710527 | 1176376 | 21886903 | Distribution | 4426604.8 | 4606881.81 | 77% | 2023-10-16 | 2026-05-15
11560 | 698570 | FAASt [Distribution Streetlighting - Corozal] (Distribution) | Corozal | 13720208.31 | 2225873.62 | 15946081.93 | Distribution | 2095283.48 | 1492584.96 | 75% | 2023-09-13 | 2027-03-20
11627 | 709631 | FAASt [Morovis Streetlighting] (Distribution) | Morovis | 13486398.85 | 1744482.27 | 15230881.12 | Distribution | 3426948.25 | 1694462.41 | 67% | 2024-02-19 | 2027-03-22
11629 | 698579 | FAASt [Distribution Streetlighting - Orocovis] (Distribution) | Orocovis | 8070964.96 | 1339801.28 | 9410766.24 | Distribution | 2117422.41 | 902087.48 | 49% | 2024-04-16 | 2027-02-23
11633 | 704938 | FAASt [Distribution Streetlighting - Las Piedras (Distribution) | Las Piedras | 13807923.4 | 1807601.11 | 15615524.51 | Distribution | 3513493.02 | 1654066.11 | 61% | 2024-02-28 | 2026-10-17
11636 | 703535 | FAASt [Toa Baja Streetlighting] (Distribution) | Toa Baja | 9529190.37 | 620134.69 | 10149325.06 | Distribution | 2283598.14 | 1006829.17 | 53% | 2024-02-05 | 2026-09-19
11650 | 704868 | FAASt [Ceiba Streetlighting] (Distribution) | Ceiba | 5152111.14 | 716918.6 | 5869029.74 | Distribution | 1320531.69 | 1078576.92 | 58% | 2024-02-05 | 2027-04-07
11658 | 704849 | FAASt [Naguabo Streetlighting] (Distribution) | Naguabo | 11620676.42 | 1669736.97 | 13290413.39 | Distribution | 2990343.01 | 2307439.74 | 66% | 2024-06-13 | 2027-05-04
11664 | 704943 | FAASt [Naranjito Streetlighting] (Distribution) | Naranjito | 11644048.43 | 2115538.38 | 13759586.81 | Distribution | 3095907.03 | 726622.23 | 52% | 2024-02-01 | 2027-10-08
11671 | 724703 | FAASt [Arroyo Streetlighting] (Distribution) | Arroyo | 5314332 | 740394.01 | 6054726.01 | Distribution | 1362313.35 | 1227253.58 | 59% | 2024-08-29 | 2027-02-09
11673 | 724938 | FAASt [Vega Alta Streetlighting] (Distribution) | Vega Alta | 12445015.33 | 1869089.52 | 14314104.85 | Distribution | 3220673.59 | 2367330.29 | 55% | 2024-03-01 | 2027-04-25
11675 | 704921 | FAASt [Barranquitas Streetlighting] (Distribution) | Barranquitas | 9430329.22 | 1577046.09 | 11007375.31 | Distribution | 2476659.45 | 993173.69 | 64% | 2024-03-19 | 2027-06-15
11680 | 698511 | FAASt [Culebra Streetlighting] (Distribution) | Culebra | 1155804 | 153603 | 1309407 | Distribution | 294616.58 | 239361.1 | 83% | 2024-06-18 | 2026-02-04
11711 | 704927 | FAASt [Añasco Streetlighting] (Distribution) | Añasco | 12087876.17 | 1820361.92 | 13908238.09 | Distribution | 3129353.57 | 913839.1 | 75% | 2024-12-06 | 2027-02-02
11725 | 724825 | FAASt [Cidra Streetlighting] (Distribution) | Cidra | 12812478.84 | 1838229.6 | 14650708.44 | Distribution | 3296409.4 | 643839.77 | 59% | 2024-12-06 | 2027-03-21
11727 | 701472 | FAASt [Comerio Streetlighting] (Distribution) | Comerio | 6538769.44 | 862125.75 | 7400895.19 | Distribution | 1665201.42 | 731804.4 | 68% | 2024-12-11 | 2026-11-12
11734 | 724698 | FAASt [Adjuntas Streetlighting] (Distribution) | Adjuntas | 10742462 | 1891152 | 12633614 | Distribution | 2842563.15 | 1716676.33 | 67% | 2024-11-20 | 2026-11-19
11735 | 724600 | FAASt [Jayuya Streetlighting] (Distribution) | Jayuya | 7277670.2 | 1350541.32 | 8628211.52 | Distribution | 1941347.59 | 2076296.2 | 71% | 2024-10-31 | 2026-11-09
11739 | 724601 | FAASt [Salinas Streetlighting] (Distribution) | Salinas | 12097203.53 | 1611020.9 | 13708224.43 | Distribution | 3084350.5 | 2463515.58 | 77% | 2024-11-27 | 2027-04-08
Streetlights Projects- Pending Obligation PWS |  |  |  | FEMA Approved Cost |  |  |  | Disbursements |  | Project Status
PW | GM# | Project Name | Municipality | 428 | 406 | Total Child | Asset | WCA | Reimbursement | FEMA Formulation Status
11630 | 714641 | FAASt [Rincón Streetlighting] (Distribution) | Rincón | 10842339.26 | 694470.58 | 11536809.84 | Distribution | N/A | N/A | Project pending obligation- Pending Large Project review
Streetlights Projects- Inactive PWS |  |  |  | LUMA Estimated costs |  |  |  | Disbursements |  | Project Status
PW | GM# | Project Name | Municipality | 428 | 406 | Total Child | Asset | WCA | Reimbursement | FEMA Formulation Status
| 666894 | FAASt [San Juan Streetlighting] (Distribution) | San Juan | 30550204.86 | 3532038.94 | 34082243.8 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 671396 | FAASt [Utuado Streetlighting] (Distribution) | Utuado | 17961216.53 | 2911033.07 | 20872249.6 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 671400 | FAASt [Barceloneta Streetlighting] (Distribution) | Barceloneta | 8163052.71 | 1109632.7 | 9272685.41 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 678794 | FAASt [Ponce Streetlighting] (Distribution) | Ponce | 16043135.52 | 1444528.43 | 17487663.95 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 678795 | FAASt [Arecibo Streetlighting] (Distribution) | Arecibo | 14607500.56 | 1513605.01 | 16121105.57 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 686482 | FAASt [Isabela Streetlighting] (Distribution) | Isabela | 7013624.27 | 733834.85 | 7747459.12 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2025
| 690480 | FAASt [Humacao Streetlighting] (Distribution) | Humacao | 7598892 | 921999.67 | 8520891.67 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 690483 | FAASt [Cayey Streetlighting] (Distribution) | Cayey | 13343261.38 | 1319139.42 | 14662400.8 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 690721 | FAASt [Guayama Streetlighting] (Distribution) | Guayama | 5525916.66 | 542958 | 6068874.66 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 693543 | FAASt [Juncos Streetlighting] (Distribution) | Juncos | 12854140.62 | 1566281.47 | 14420422.09 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 693615 | FAASt [Rio Grande Streetlighting] (Distribution) | Rio Grande | 6376770.32 | 700108 | 7076878.32 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 693788 | FAASt [Toa Alta Streetlighting] (Distribution) | Toa Alta | 5847563.41 | 466823.03 | 6314386.44 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 697183 | FAASt [Vega Baja Streetlighting] (Distribution) | Vega Baja | 9248657.11 | 1117331.19 | 10365988.3 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 698427 | FAASt [Maricao Streetlighting] (Distribution) | Maricao | 4846034.89 | 1028907.4 | 5874942.29 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 698432 | FAASt [Hormigueros Streetlighting] (Distribution) | Hormigueros | 6920157.56 | 968057.12 | 7888214.68 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 698522 | FAASt [Vieques Streetlighting] (Distribution) | Vieques | 4386770.2 | 519326.46 | 4906096.66 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 699814 | FAASt [Juana Diaz Streetlighting] (Distribution) | Juana Diaz | 15781505 | 1909452 | 17690957 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 701473 | FAASt [Canovanas Streetlighting] (Distribution) | Canovanas | 14314798.95 | 1574362.23 | 15889161.18 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 704741 | FAASt [Moca Streetlighting] (Distribution) | Moca | 17686091.97 | 2776061.05 | 20462153.02 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 704744 | FAASt [San Sebastian Streetlighting] (Distribution) | San sebastian | 22246737.73 | 3663221 | 25909958.73 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 704757 | FAASt [Santa Isabel Streetlighting] (Distribution) | Santa Isabel | 7956662 | 820333 | 8776995 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 704793 | FAASt [Yauco Streetlighting] (Distribution) | Yauco | 14713958.38 | 1656014.26 | 16369972.64 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 704862 | FAASt [Fajardo Streetlighting] (Distribution) | Fajardo | 11333806.13 | 1104923.17 | 12438729.3 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 704929 | FAASt [San Lorenzo Streetlighting] (Distribution) | San lorenzo | 14343817.06 | 2284857.13 | 16628674.19 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 704931 | FAASt [Camuy Streetlighting] (Distribution) | Camuy | 15436783.23 | 2269186.04 | 17705969.27 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 713795 | FAASt [Lares Streetlighting] (Distribution) | Lares | 11909808.29 | 1759138.02 | 13668946.31 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 724599 | FAASt [Sabana Grande Streetlighting] (Distribution) | Sabana Grande | 10744021.82 | 1778904.02 | 12522925.84 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 724603 | FAASt [Cabo Rojo Streetlighting] (Distribution) | Cabo Rojo | 9017148.04 | 1044682.84 | 10061830.88 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 724605 | FAASt [Guayanilla Streetlighting] (Distribution) | Guayanilla | 7949936.1 | 1109933.93 | 9059870.03 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 724669 | FAASt [Ciales Streetlighting] (Distribution) | Ciales | 10780496.72 | 1862926.59 | 12643423.31 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 724670 | FAASt [Patillas Streetlighting] (Distribution) | Patillas | 8375887.52 | 1048713.32 | 9424600.84 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 724716 | FAASt [Quebradillas Streetlighting] (Distribution) | Quebradillas | 10455022.32 | 1572475.82 | 12027498.14 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 724781 | FAASt [Penuelas Streetlighting] (Distribution) | Penuelas | 7948618.17 | 1016407.79 | 8965025.96 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 724828 | FAASt [Loiza Streetlighting] (Distribution) | Loiza | 6696269.82 | 816843.77 | 7513113.59 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 724941 | FAASt [Aguas Buenas Streetlighting] (Distribution) | Aguas Buenas | 11260820.47 | 1686477.37 | 12947297.84 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 734393 | FAASt [Cabo Rojo Streetlighting - Part 2] (Distribution) | Cabo Rojo | 7838709 | 1016421 | 8855130 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 734396 | FAASt [Cabo Rojo Streetlighting - Part 3] (Distribution) | Cabo Rojo | 6205493 | 0 | 6205493 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 734728 | FAASt [Ponce Streetlighting - Part 2] (Distribution) | Ponce | 12998720.23 | 1402395.55 | 14401115.78 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 734760 | FAASt [Ponce Streetlighting - Part 3] (Distribution) | Ponce | 13799462 | 1946734 | 15746196 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 734789 | FAASt [Guayama Streetlighting - Part 3 ] (Distribution) | Guayama | 6296106 | 635977 | 6932083 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 734791 | FAASt [Guayama Streetlighting - Part 2] (Distribution) | Guayama | 5650820 | 757008 | 6407828 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 734853 | FAASt [Arecibo Streetlighting- Part 3] (Distribution) | Arecibo | 15679863.58 | 2684586 | 18364449.58 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 734859 | FAASt [Aguadilla Streetlighting - Part 2] (Distribution) | Aguadilla | 8885681.25 | 1346103.32 | 10231784.57 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 734927 | FAASt [Isabela Streetlighting - Part 2] (Distribution) | Isabela | 8007445.57 | 1301828.7 | 9309274.27 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 734928 | FAASt [Isabela Streetlighting - Part 3] (Distribution) | Isabela | 5847213 | 1017123 | 6864336 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 735131 | FAASt [Arecibo Streetlighting - Part 2] (Distribution) | Arecibo | 11247096.52 | 1546159.79 | 12793256.31 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 735338 | FAASt [Aguadilla Streetlighting - Part 3] (Distribution) | Aguadilla | 8195391 | 1423702.65 | 9619093.65 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 735357 | FAASt [Mayaguez Streetlighting - Part 2] (Distribution) | Mayaguez | 7368131.58 | 1097078 | 8465209.58 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 735360 | FAASt [Mayaguez Streetlighting - Part 3] (Distribution) | Mayaguez | 13951292 | 2189841.82 | 16141133.82 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 735470 | FAASt [Bayamón Streetlighting - Part 2] (Distribution) | Bayamon | 17963819 | 1727642 | 19691461 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 735472 | FAASt [Bayamon Streetlighting - Part 3] (Distribution) | Bayamon | 18291400 | 2632407 | 20923807 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 735483 | FAASt [Vega Baja Streetlighting - Part 3] (Distribution) | Vega Baja | 6391732 | 1105916 | 7497648 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 735487 | FAASt [Humacao Streetlighting - Part 3] (Distribution) | Humacao | 7901161 | 916292 | 8817453 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 735493 | FAASt [Humacao Streetlighting - Part 2] (Distribution) | Humacao | 6274071 | 916292 | 7190363 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 735496 | FAASt [Carolina Streetlighting - Part 3] (Distribution) | Carolina | 14764763 | 2019124 | 16783887 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 735499 | FAASt [Guaynabo Streetlighting - Part 3] (Distribution) | Guaynabo | 7033301 | 0 | 7033301 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 735665 | FAASt [Carolina Streetlighting - Part 2] (Distribution) | Carolina | 12296300.92 | 557535.92 | 12853836.84 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 735672 | FAASt [Caguas Streetlighting - Part 3] (Distribution) | Caguas | 11986815 | 1624355 | 13611170 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 735677 | FAASt [Guaynabo Streetlighting - Part 2] (Distribution) | Guaynabo | 7566377 | 1014066 | 8580443 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 735940 | FAASt [Vega Baja Streetlighting - Part 2] (Distribution) | Vega Baja | 7551926 | 1067250 | 8619176 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 735952 | FAASt [Trujillo Alto Streetlighting - Part 3] (Distribution) | Trujillo Alto | 8838122 | 1149506 | 9987628 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 735954 | FAASt [Trujillo Alto Streetlighting - Part 2] (Distribution) | Trujillo Alto | 6426439 | 884864 | 7311303 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 735959 | FAASt [Toa Baja Streetlighting - Part 3] (Distribution) | Toa Baja | 6988631 | 1169678 | 8158309 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 735960 | FAASt [Toa Baja Streetlighting - Part 2] (Distribution) | Toa Baja | 9782523 | 1238774 | 11021297 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 737699 | FAASt [Toa Alta Streetlighting - Part 3] (Distribution) | Toa Alta | 3715400 | 606813 | 4322213 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 737707 | FAASt [Toa Alta Streetlighting - Part 2] (Distribution) | Toa Alta | 8808053 | 979674 | 9787727 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 737712 | FAAST [San Juan Streetlighting - Part 3] (Distribution) | San Juan | 31581739 | 3250259 | 34831998 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 737798 | FAASt [Rio Grande Streetlighting - Part 3] (Distribution) | Rio Grande | 7059041 | 877731 | 7936772 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 737804 | FAASt [Rio Grande Streetlighting - Part 2 ] (Distribution) | Rio Grande | 6104607 | 838135 | 6942742 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 746108 | FAASt [San Juan Streetlighting - Part 2] (Distribution) | San Juan | 26445767 | 3331645 | 29777412 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
| 746111 | FAASt [Caguas Streetlighting - Part 2] (Distribution) | Caguas | 10160312 | 1317294 | 11477606 | Distribution | N/A | N/A | Project Administratively withdrawn by FEMA. Project not part of the FAAST Consolidated plan due to lack of documentation and Pending Detailed Scope of Work since 2024
Centro Medico- Projects |  |  |  | FEMA Approved Cost |  |  |  | Disbursements |  | LUMA Provided Status
PW | GM# | Project Name | Municipality | 428 | 406 | Total Child | Asset | WCA | Reimbursement | Construction % | Construction Start Date | Estimated Completion Date
11489 | 169266 | FAASt Centro Medico 1327/1359 Equipment Repair ; Replacement | San Juan | 14795324 | 6537037 | 21332361 | Substation | 1599324.45 | 1584324.45 | 2% | 2024-09-30 | 2027-02-11

## July-Luma Reconsideration Proj. (hidden)
Project # | Title | FEMA Allocation | Asset | SUB ASSET | Previous Process Step | Process Step as of 7-15-25 | Project Estimated Cost | Current Version Cost | 428 | 406 | A&E-PW 9510 | E&M-PW 10710 | PREPA Priority List | P3A-LUMA Priority List | LUMA reconsideration List | Genera Priority List | A&E Costs Incurred | E&M Cost | Project Status 7/15/25 | Project Scope
551963 | FAASt [Transport Network Group 1] (Telecommunication) | Pipeline | Telecommunication | Telecomm | Pending Recipient Final Review | Pending Recipient Final Review | 7469879.13 | 5490296.88 | 5490296.88 | 0 | 836416.02 | 1143166.23 | TBD | Yes | Yes | N/A | 9420564 | 1143166 | Pending Recipient Review- Pending LUMA information regarding A&E COSTS | Project involves assessing sites and designing/installing "Make-Ready" infrastructure and Transport/ITOT network equipment, followed by commissioning and transitioning substation OT services.
551926 | FAASt [SCADA Remote Access and RTU Replacements Group 2] (Telecommunication) | Phase 2 | Telecommunication | Telecomm | Pending Scope & Cost Completion by Applicant | Pending EHP Review |  | 6753699.16 | 5267467.99 | 1073462.61 |  |  | TBD | No | Yes | N/A | Not available | Not available | Before moving the project forward to the CRC, LUMA must update the “Legend Sites” tab of the Cost Estimate, as it includes the substations that were removed from this new version. | SCADA Remote Access and RTU Replacements
673292 | FAASt Telecom Infrastructure - Cerro Puntas (Telecommunication) | Pipeline | Telecommunication | Telecomm | Pending EHP Review | Pending EHP Review | 9249004.2 | 8124106.79 | 8124106.79 | 49577.82 | 1075319.59 |  | No | No | Yes | N/A |  |  | "Field EHP - Historic: SHPO consultation process initiated; drafting ongoing. Expected Completion Date: 06/27/2025. " | Update the tower facilities and telecommunication building to current codes and standards via repair. This will be achieved by performing the engineering and structural assessments necessary to establish the amount of damage and the necessary repairs or rebuild to update or replace the structure. The engineering assessment shall include the field mapping of structure and appurtenances, geotechnical study, and foundation exploratory. A run rigorous tower structural analysis will be done and with results determined if the tower needs a minor repair or a major repair.
957578 | FAASt [Costa Sur TC Underground Cable Failure Replacement on Transformer Lead Bank #2] (Substation) | Phase 2 | Substation | Substation | Not included on FEMA initial list | Pending EHP Review | 1250845.76 | 1108989.51 | 1108989.51 |  | 141856.25 |  |  |  | Yes |  |  |  | "7/15/2025- (Stabilization Projects) Project created as part of the Stabilization Projects. Applicant upload DSOW with corrections. -Process Step: Pending Insurance Completion |  | To clarify glitch issue- Where in the queus is project located
678800 | FAASt [Telecom Infrastructure – Group B] (Telecommunication) | Phase 2 | Telecommunication | Telecomm | Pending Scope & Cost Completion by Applicant | Pending Scope and Cost Development | 16033618.38 | 13148929.44 | 13148929.44 | 55895.84 | 2828793.1 | N/A | TBD | No | Yes | N/A | Not available | Not available | HM ph2 RFI sent on 7/7/2025 | Atalaya, El Gato, Isabela Plata 1, La Santa, and Manatí TC boring & self-supported tower.
746545 | FAASt [Primary Control Center / Secondary Data Center & Control Room] (Telecommunication) | Phase 2 | Telecommunication | Telecomm | Pending PDMG Scope & Cost Routing | Pending PDMG Scope & Cost Routing |  | 115638378 |  |  |  |  | TBD | No | Yes | N/A | Not available | Not available | Letter from PREPA to FEMA re Monacillos Operation Center under EHP review. | Letter from PREPA to FEMA re Monacillos Operation Center under EHP review. | Relocation of existing Operations teams and equipment, as well as the removal / relocation of electrical infrastructure from the Monacillos campus. The project has three areas of scope. The scope of work description is organized by the area of work. The three areas include (1) the Guaynabo ESC building rehabilitation in Guaynabo, (2) the Durotex Building rehabilitation on the Monacillos campus, (3) and the new PCC building construction / site improvements on the Monacillos campus. | Not in List | Pending EHP- SHPO resolution- DSOW should be reworked and segregated by sites. Project not part of LUMA P3 Priority projects, but presented by LUMA for reconsideration on 7-22. Additional information required to analyze project.
662238 | FAASt [Microwave Point-to-Point Backbone] (Telecommunications) | Phase 2 | Telecommunication |  | Pending Scope & Cost Completion by Applicant | Pending Scope & Cost Completion by Applicant |  | 16046926.54 |  |  |  |  | TBD | No | Yes | N/A | Not available | Not available | Pending DSOW | 2/12/2025- In the Energy weekly meeting, it as discuss with the Applicant the posibility of following up regarding the changes in forcast regarding all projects. Applicant will review the information and get back to FEMA with a realistic forecast submission. |  | Not in List | Project has been Pending LUMA DSOW- Project not part of LUMA P3 Priority projects nor Stabilization Plan projects, but presented by LUMA for reconsideration on 7-22. Additional information required to analyze project.
746660 | FAASt [Minor Protection, Automation, and Control [PAC] Replacement] (Substation) | Phase 2 | Substation | Substation | Pending Scope & Cost Completion by Applicant | Pending Scope & Cost Completion by Applicant | 16713944.15 | 15096658.56 | 15096658.56 | 1617375.6 | N/A | N/A | TBD | No | Yes | N/A | Not available | Not available | " 5/5/2025 - Applicant is currently using the data from the presentation to complement the justification in the DSOW. This will to provide context to the PMU section, therefore, will require additional time in order to complete this RFI #1 response. -LUMA updated Forecast: 5/2/2025 | 7/11/2025- 2nd HM RFI and HMCE evaluation in response to the documents presented by LUMA [DSOW Rev.2 and Cost Estimate]. After evaluating the data submitted by the subrecipient, we found some issues that requires the subrecipient review and changes. Please go to HM evaluation comments columns K to Q to expedite the action from the applicant and further validation. Email sent to the applicant for clarification. | Increase protection and Control System that protect the electrical components such as Transmission Lines, Transformers, Bus Bar, Breakers, etc | Not in List | Provide update on project progress and DSOW presented
551927 | FAASt [SCADA Remote Access and RTU Replacements Group 3] (Telecommunication) | Phase 2 | Telecommunication | Telecomm | Pending Scope & Cost Completion by Applicant | Pending Scope & Cost Completion by Applicant |  | 19755645.91 |  |  |  |  | TBD | No | Yes | N/A | Not available | Not available | Pending DSOW | DSOW will be submitted on 3/20/2025 2/12/2025- In the Energy weekly meeting, it as discuss with the Applicant the posibility of following up regarding the changes in forcast regarding all projects. Applicant will review the information and get back to FEMA with a realistic forecast submission. | SCADA Remote Access and RTU Replacements | Not in List | Project has been Pending LUMA DSOW- Project not part of LUMA P3 Priority projects nor Stabilization Plan projects, but presented by LUMA for reconsideration on 7-22. Additional information required to analyze project.
668665 | FAASt [Cybersecurity Program Implementation] (Telecommunication) | Phase 2 | Telecommunication | Telecomm | Pending Scope & Cost Completion by Applicant | Pending Scope & Cost Completion by Applicant |  | 24500000 |  |  |  |  | TBD | No | Yes | N/A | Not available | Not available | 2/12/2025- In the Energy weekly meeting, it as discuss with the Applicant the posibility of following up regarding the changes in forcast regarding all projects. Applicant will review the information and get back to FEMA with a realistic forecast submission. | 2/12/2025- In the Energy weekly meeting, it as discuss with the Applicant the posibility of following up regarding the changes in forcast regarding all projects. Applicant will review the information and get back to FEMA with a realistic forecast submission. | This program focuses on implementing cybersecurity that protects key organizational assets, including critical infrastructure, people, resources, and technology. The program will identify and mitigate cyber risk, internal and external threats, vulnerabilities, and natural disasters based on risk and readiness factors. Improving cybersecurity is critical to hardening and mitigating hazards to the Transmission and Distribution System (T&D) ensuring Critical Infrastructure continuity. | Not in List | Project has been Pending LUMA DSOW- Project not part of LUMA P3 Priority projects nor Stabilization Plan projects, but presented by LUMA for reconsideration on 7-22. Additional information required to analyze project.
675345 | FAASt [IT OT Technology Systems Reparations] Group 1 (Telecommunication) | Phase 2 | Telecommunication | Telecomm | Pending Scope & Cost Completion by Applicant | Pending Scope & Cost Completion by Applicant |  | 21640536 |  |  |  |  | TBD | No | Yes | N/A | Not available | Not available | DSOW forecasted for July 31, 2025 | 2/12/2025- In the Energy weekly meeting, it as discuss with the Applicant the posibility of following up regarding the changes in forcast regarding all projects. Applicant will review the information and get back to FEMA with a realistic forecast submission. | Software upgrade of the existing OMS software to a minor version. Install Networks Enterprise. Test all existing integrations with SCADA, CC&B, STORMS, GIS. Test map migration process. Test default Mobile work forms the staff will be using in the field on Smart devices and tablets. Change management awareness and training to end users. Obtain Cyber Security clearance for commissioning to Production servers. Proceed to deploy solution to production servers. Training of Operators, Dispatchers, and field staff. | Not in List | Project has been Pending LUMA DSOW- Project not part of LUMA P3 Priority projects nor Stabilization Plan projects, but presented by LUMA for reconsideration on 7-22. Additional information required to analyze project.