## LUMA - Annex A
[14 empty] | Portfolio* | Source** |  | Phase***
[13 empty] | Note: 1 For Non-Federally Funded projects, the “Estimated Cost ($)” column reflects the estimated Total Cost of the Project as part of the Long-Term Investment Plan estimates and for Federally Funded projects, the “Estimated Cost ($)” column reflects the obligated amount approved by FEMA. 2 The “Cost ($)” column reflects either the estimated cost of the Initial Scope of Work approved by the Energy Bureau for Federally-Funded projects, or, for Non-Federally Funded projects, the funding allocated to the project in the current Fiscal Year Budget approved by the Energy Bureau. 3For federally funded projects, completion dates reflect all field activities that must be completed before a project can effectively be closed out and are aligned with the % complete. The energized column does not imply overall project completion. | Control Center & Buildings | FF | Federally Funded | Initiation
NEPR-MI-2024-0001 | [13 empty] | Customer Experience | NFF | Non-Federally Funded | Plan
PREB Approved Investments as of: | [13 empty] | Distribution |  |  | Design
2026-03-31 | [13 empty] | Enabling |  |  | Execution
[14 empty] | Substations |  |  | Close Out
Support Services
|  |  |  | Funding |  | PREB's Approval Date |  | Project Phase | [5 empty] | Transmission
Unique ID (FAASt No. or Project ID) | Project Title | Portfolio* | Improvement Program | Source** | Estimated Cost ($M)1 | Cost ($M)2 | Date | Phase*** | Starting Date | Completion Date3 | Energized3 | % Complete3
PBCS4.01 | Wheeling | Customer Experience | Retail Wheeling | NFC | 0 | 0.11992 | 2025-07-31 | Initiation | On Hold | On Hold | N/A | 0%
PBFM1.01 | FMS Santurce Parking Rehab | Control Center & Buildings | Facilities Development & Implementation | NFC | 0 | 0.4 | 2025-07-31 | Close Out | 2025-03-01 | 2026-02-27 | N/A | 100%
PBIT1.01 | GuayaToJob.Fib.Enh-AguiToJobTC | Transmission | OT Telecom Systems & Network | NFC | 0 | 0.43 | 2025-07-31 | Close Out | 2025-05-01 | 2025-06-20 | N/A | 100%
PBIT1.551925 | FAASt [SCADA Remote Access and RTU Replacements Group 1] (Telecommunication) | Transmission | IT OT Telecom Systems & Network | FF | 7.6 | 30 | 2021-09-22 | Execution | 2021-12-22 | 2025-09-26 17:00 | No | 94%
PBIT1.551926 | FAASt [SCADA Remote Access and RTU Replacements Group 2] (Telecommunication) | Transmission | IT OT Telecom Systems & Network | FF | 6.3 | Program Cost Included in PBIT1.551925 | 2021-09-22 | Design | 2021-12-22 | 2026-06-04 | No | 0%
PBIT1.551963 | FAASt [Transport Network] (Telecommunication) | Transmission | IT OT Telecom Systems & Network | FF | 5.4 | 185 | 2021-09-22 | Execution | 2021-12-22 | 2029-05-04 | No | 1%
PBIT1.662238 | FAASt [Microwave Point-to-Point Backbone] (Telecommunications) | Transmission | IT OT Telecom Systems & Network | FF | Pending Obligation | 6 | 2021-09-22 | Design | 2022-02-14 | Pending Obligation | Pending Obligation | 0%
PBIT1.673292 | FAASt Telecom Infrastructure - Cerro Puntas (Telecommunication) | Transmission | IT OT Telecom Systems & Network | FF | 8.1 | 96.5 | 2021-09-22 | Design | 2022-05-17 | 2027-10-27 | No | 0%
PBIT1.678800 | FAASt [Telecom Infrastructure – Group B] (Telecommunication) | Transmission | IT OT Telecom Systems & Network | FF | 13.2 | Program Cost Included in PBIT1.551925 | 2021-09-22 | Design | 2022-07-22 | 2028-08-31 | No | 0%
PBIT1.746545 | FAASt [Primary Control Center / Secondary Data Center & Control Room] (Telecommunication) | Control Center & Buildings | IT OT Telecom Systems & Network | FF | Pending Obligation | 146 | 2024-05-07 | Design | 2024-04-04 | Pending Obligation | Pending Obligation | 0%
PBOP7.723883 | FAASt [Region 1 -San Juan Group A] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | 18.1 | 1200 | 2023-05-05 | Execution | 2023-06-26 | 2027-06-01 | No | 11%
PBOP7.727522 | FAASt [Region 3 Bayamon TL - 115kV] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | 3.4 | Program Cost Included in PBOP7.723883 | 2023-05-05 | Design | 2023-08-03 | 2026-11-01 | No | 0%
PBOP7.727529 | FAASt [Region 6 Ponce TL - 115kV] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | 8.3 | Program Cost Included in PBOP7.723883 | 2023-05-05 | Design | 2023-08-03 | 2026-11-01 | No | 0%
PBOP7.727531 | FAASt [Region 6 -Ponce Group A] High Density (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | 25.9 | Program Cost Included in PBOP7.723883 | 2023-05-05 | Execution | 2023-08-03 | 2028-05-23 | No | 58%
PBOP7.727572 | FAASt [Region 3 -Bayamon Group A] High Density (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | 42.5 | Program Cost Included in PBOP7.723883 | 2023-05-05 | Design | 2023-08-03 | 2026-05-01 | No | 0%
PBOP7.727606 | FAASt [Region 4 Caguas TL - 115kV] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | 3.9 | Program Cost Included in PBOP7.723883 | 2023-05-05 | Design | 2023-08-03 | 2026-06-01 | No | 0%
PBOP7.727608 | FAASt [Region 1 San Juan TL - 115kV] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | 4.4 | Program Cost Included in PBOP7.723883 | 2023-05-05 | Design | 2023-08-03 | 2026-11-01 | No | 0%
PBOP7.727657 | FAASt [Region 5 Mayaguez TL - 115kV] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | 2.5 | Program Cost Included in PBOP7.723883 | 2023-05-05 | Design | 2023-08-04 | 2026-11-01 | No | 0%
PBOP7.727659 | FAASt [Region 2 Arecibo TL - 115kV] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | 4.2 | Program Cost Included in PBOP7.723883 | 2023-05-05 | Design | 2023-08-04 | 2026-11-01 | No | 0%
PBOP7.727692 | FAASt [Region 4 -Caguas Group A] High Density (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | 28.05 | Program Cost Included in PBOP7.723883 | 2023-05-05 | Execution | 2023-08-04 | 2028-06-06 | No | 79%
PBOP7.728827 | FAASt [Region 2 -Arecibo Group A] High Density (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | 18.1 | Program Cost Included in PBOP7.723883 | 2023-05-05 | Execution | 2023-08-17 | 2028-01-25 | No | 89%
PBOP7.728832 | FAASt [Region 5 -Mayaguez Group A] High Density (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | 14.2 | Program Cost Included in PBOP7.723883 | 2023-05-05 | Execution | 2023-08-17 | 2027-12-06 | No | 53%
PBOP7.741105 | FAASt [All Regions TL - 230kV] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | 12.8 | Program Cost Included in PBOP7.723883 | 2023-05-05 | Design | 2023-12-15 | 2026-11-01 | No | 0%
PBOP7.750063 | FAASt [Region 6 -Ponce Group A] Low Density (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.723883 | 2023-05-05 | Design | 2024-06-18 | Pending Obligation | Pending Obligation | 0%
PBOP7.750065 | FAASt [Region 3 -Bayamon Group A] Low Density (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | 70.1 | Program Cost Included in PBOP7.723883 | 2023-05-05 | Design | 2024-06-18 | 2026-05-01 | No | 0%
PBOP7.750066 | FAASt [Region 4 -Caguas Group A] Low Density (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | 107.5 | Program Cost Included in PBOP7.723883 | 2023-05-05 | Design | 2024-06-18 | 2026-11-01 | No | 0%
PBOP7.750067 | FAASt [Region 2 -Arecibo Group A] Low Density (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | 56.7 | Program Cost Included in PBOP7.723883 | 2023-05-05 | Design | 2024-06-18 | 2026-05-01 | No | 0%
PBOP7.750068 | FAASt [Region 5 -Mayaguez Group A] Low Density (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | 52.3 | Program Cost Included in PBOP7.723883 | 2023-05-05 | Design | 2024-06-18 | 2026-11-01 | No | 0%
PBOP7.956330 | FAASt [Caguas Region 4 - Feeder 3007-03] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.956330 | 2023-05-05 | Design | 2025-06-18 | Pending Obligation | Pending Obligation | 0%
PBOP7.956331 | FAASt [Mayaguez Region 5 Feeder 6014-02] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.956331 | 2023-05-05 | Design | 2025-06-18 | Pending Obligation | Pending Obligation | 0%
PBOP7.956332 | FAASt [San Juan Region 1 - Feeder 2401-01] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.956332 | 2023-05-05 | Design | 2025-06-18 | Pending Obligation | Pending Obligation | 0%
PBOP7.956335 | FAASt [San Juan Region 1 - Feeder 2301-02] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.956335 | 2023-05-05 | Design | 2025-06-18 | Pending Obligation | Pending Obligation | 0%
PBOP7.956337 | FAASt [Mayaguez Region 5 Feeder 6012-02] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.956337 | 2023-05-05 | Design | 2025-06-18 | Pending Obligation | Pending Obligation | 0%
PBOP7.956339 | FAASt [Caguas Region 4 - Feeder 3301-01] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.956339 | 2023-05-05 | Design | 2025-06-18 | Pending Obligation | Pending Obligation | 0%
PBOP7.956340 | FAASt [Ponce Region 6 Feeder 5602-02] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.956340 | 2023-05-05 | Design | 2025-06-18 | Pending Obligation | Pending Obligation | 0%
PBOP7.956341 | FAASt [Ponce Region 6 Feeder 5803-02] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.956341 | 2023-05-05 | Design | 2025-06-18 | Pending Obligation | Pending Obligation | 0%
PBOP7.956342 | FAASt [Arecibo Region 2 Transmission Line 36400 – Ponce TC to Dos Bocas HP] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | 4 | Program Cost Included in PBOP7.956342 | 2023-05-05 | Design | 2025-06-18 | 2028-03-15 | No | 0%
PBOP7.956343 | FAASt [Ponce Region 6 Transmission Line 4800 – Toro Negro to Aibonito, Santa Isabel] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.956343 | 2023-05-05 | Design | 2025-06-18 | Pending Obligation | Pending Obligation | 0%
PBOP7.956345 | FAASt [Arecibo Region 2 Transmission Line 2400 – Dos Bocas HP to Coronillas 2] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.956345 | 2023-05-05 | Design | 2025-06-18 | Pending Obligation | Pending Obligation | 0%
PBOP7.956348 | FAASt [Bayamon Region 3 Transmission Line 10000 – Bayamon Pueblo to Magnolia TO] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.956348 | 2023-05-05 | Design | 2025-06-18 | Pending Obligation | Pending Obligation | 0%
PBOP7.956349 | FAASt [San Juan Region 1 Transmission Line 36800 – Canovanas TC to Palmer TC] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | 1.3 | Program Cost Included in PBOP7.956349 | 2023-05-05 | Execution | 2025-06-18 | 2026-03-25 | No | 94%
PBOP7.956353 | FAASt [Arecibo Region 2 Transmission Line 36100 – Dos Bocas HP to Barrio Pina] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | 3.7 | Program Cost Included in PBOP7.956353 | 2023-05-05 | Execution | 2025-06-18 | 2028-03-29 | No | 20%
PBOP7.956356 | FAASt [Ponce Region 6 Transmission Line 39000 – Aguas Buenas Substation to Hacienda San Jose] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | 0.325 | Program Cost Included in PBOP7.956356 | 2023-05-05 | Execution | 2025-06-18 | 2026-02-27 | No | 95%
PBOP7.956357 | FAASt [Mayaguez Region 5 Transmission Line 1900 – Dos Bocas HP to San Sebastian TC] (Vegetation) | Enabling | Vegetation Management and Capital Clearing Implementation | FF | Pending Obligation | Program Cost Included in PBOP7.956357 | 2023-05-05 | Design | 2025-06-18 | Pending Obligation | Pending Obligation | 0%
PBUT13.01 | 10000-Bayamon Pueblo SECT-Magnolia TO | Transmission | Transmission Priority Pole Replacements | NFC | 0 | 0.1 | 2025-07-31 | Initiation | 2026-06-01 | Removed from Scope | N/A | 0%
PBUT13.02 | 10700-HATO TEJAS SECT-BAYAMON PUEBLO SECT- | Transmission | Transmission Priority Pole Replacements | NFC | 0 | 0.5 | 2025-07-31 | Execution | 2026-01-01 | 2026-06-30 | N/A | 10%
PBUT13.03 | 16500-FAJARDO TC-DOS MARINAS- | Transmission | Transmission Priority Pole Replacements | NFC | 0 | 0.2 | 2025-07-31 | Execution | 2026-01-01 | 2026-06-30 | N/A | 90%
PBUT13.04 | 1700-GUANICA TC-YAUCO 2 HP- | Transmission | Transmission Priority Pole Replacements | NFC | 0 | 1.2 | 2025-07-31 | Execution | 2025-11-09 | 2026-06-30 | N/A | 5%
PBUT13.05 | 2300-Arecibo SECT-Cambalache TC | Transmission | Transmission Priority Pole Replacements | NFC | 0 | 0.22 | 2025-07-31 | Initiation | 2026-06-01 | Removed from Scope | N/A | 0%
PBUT13.06 | 3000-CAGUAS TC-CAGUAX SECT-F | Transmission | Transmission Priority Pole Replacements | NFC | 0 | 0.115 | 2025-07-31 | Execution | 2026-03-01 | 2026-06-30 | N/A | 10%
PBUT13.07 | 3000-CAGUAX SECT-JUNCOS TC-F | Transmission | Transmission Priority Pole Replacements | NFC | 0 | 0.3 | 2025-07-31 | Execution | 2026-04-01 | 2026-06-30 | N/A | 10%
PBUT13.08 | 3000-JUNCOS TC-RIO BLANCO HP-F | Transmission | Transmission Priority Pole Replacements | NFC | 0 | 0.92 | 2025-07-31 | Execution | 2026-02-01 | 2026-06-30 | N/A | 10%
PBUT13.09 | 3100-Canovanas SECT-Rio Grande TO | Transmission | Transmission Priority Pole Replacements | NFC | 0 | 0.7 | 2025-07-31 | Initiation | 2026-05-01 | Removed from Scope | N/A | 0%
PBUT13.10 | 3100-CAROLINA-CANOVANAS TC- | Transmission | Transmission Priority Pole Replacements | NFC | 0 | 0.1 | 2025-07-31 | Execution | 2026-04-01 | 2026-06-30 | N/A | 5%
PBUT13.11 | 3200-Monacillos TC-Venezuela SECT | Transmission | Transmission Priority Pole Replacements | NFC | 0 | 0.1 | 2025-07-31 | Execution | 2026-01-01 | 2026-06-30 | N/A | 15%
PBUT13.12 | 3300-Viaducto TC-Egozcue SECT | Transmission | Transmission Priority Pole Replacements | NFC | 0 | 0.1 | 2025-07-31 | Initiation | 2026-06-01 | Removed from Scope | N/A | 0%
PBUT13.13 | 3600-Llorens Torres SECT-Martin Peña | Transmission | Transmission Priority Pole Replacements | NFC | 0 | 0.1 | 2025-07-31 | Execution | 2026-01-01 | 2026-06-30 | N/A | 5%
PBUT13.14 | 3600-Monacillos TC-Sabana Llana TC | Transmission | Transmission Priority Pole Replacements | NFC | 0 | 0.3 | 2025-07-31 | Execution | 2026-01-01 | 2026-06-30 | N/A | 10%
PBUT13.15 | 3600-Sabana Llana TC-Los Ángeles SECT | Transmission | Transmission Priority Pole Replacements | NFC | 0 | 0.1 | 2025-07-31 | Execution | 2026-01-01 | 2026-06-30 | N/A | 10%
PBUT13.16 | 4500-CANAS TC - LA RAMBLA SECT | Transmission | Transmission Priority Pole Replacements | NFC | 0 | 1.4 | 2025-07-31 | Close Out | 2026-01-01 | 2026-02-28 | N/A | 100%
PBUT13.17 | 700-COSTA SUR SP-YAUCO 2 HP- | Transmission | Transmission Priority Pole Replacements | NFC | 0 | 0.145 | 2025-07-31 | Execution | 2026-03-01 | 2026-06-30 | N/A | 5%
PBUT13.18 | 7400-Hato Rey TC-Tres Monjitas SECT | Transmission | Transmission Priority Pole Replacements | NFC | 0 | 0.1 | 2025-07-31 | Initiation | 2026-06-01 | Removed from Scope | N/A | 0%
PBUT13.19 | 800-COMSAT SECT - CIDRA SECT | Transmission | Transmission Priority Pole Replacements | NFC | 0 | 0.7 | 2025-07-31 | Execution | 2025-12-01 | 2026-06-30 | N/A | 10%
PBUT13.20 | 9400-Dorado TC-Toa Alta | Transmission | Transmission Priority Pole Replacements | NFC | 0 | 0.1 | 2025-07-31 | Initiation | 2026-06-01 | Removed from Scope | N/A | 0%
PBUT13.334468 | FAASt [Transmission Priority Pole Replacements – Line 2200] (Transmission) | Transmission | Transmission Line Rebuild | FF | 1.22 | Program Cost Included in PBUT13.681672 | 2021-08-20 | Execution | 2021-09-10 | 2026-07-06 | No | 93%
PBUT13.550896 | FAASt [Transmission Priority Pole Replacements – Line 6700] (Transmission) | Transmission | Transmission Line Rebuild | FF | 0.69 | Program Cost Included in PBUT13.681672 | 2021-10-18 | Execution | 2021-12-14 | 2026-07-06 | Yes | 90%
PBUT13.668583 | FAASt [Transmission Priority Pole Replacements – Line 13300] (Transmission) | Transmission | Transmission Priority Pole Replacements | FF | 0.45 | Program Cost Included in PBUT13.681672 | 2021-09-22 | Execution | 2022-03-29 | 2026-06-30 | Yes | 91%
PBUT13.668592 | FAASt [Transmission Priority Pole Replacement – Line 9800] (Transmission) | Transmission | Transmission Priority Pole Replacements | FF | 0.42 | Program Cost Included in PBUT13.681672 | 2021-09-22 | Execution | 2022-03-29 | 2026-07-15 | Yes | 94%
PBUT13.681672 | FAASt Transmission Priority Pole Replacements –38kV Line 2300 (Transmission) | Transmission | Transmission Priority Pole Replacements | FF | 0.22 | 378.8 | 2021-09-22 | Execution | 2022-08-31 | 2026-06-05 | Yes | 90%
PBUT13.708637 | FAASt [T-Pole Program Line 3700] (Transmission) | Transmission | Transmission Priority Pole Replacements | FF | 0.37 | Program Cost Included in PBUT13.681672 | 2021-09-22 | Execution | 2023-03-03 | 2027-02-12 | No | 90%
PBUT13.711670 | FAASt [T-Pole Program Line 100] (Transmission) | Transmission | Transmission Priority Pole Replacements | FF | 0.12 | Program Cost Included in PBUT13.681672 | 2021-09-22 | Execution | 2023-03-31 | 2026-09-17 | No | 93%
PBUT13.711819 | FAASt [TL 13400 TC-San German Sect-La Parguera Sect] (Transmission) | Transmission | Transmission Priority Pole Replacements | FF | 2.3 | Program Cost Included in PBUT13.681672 | 2021-09-22 | Execution | 2023-04-03 | 2026-11-09 | No | 0%
PBUT13.712980 | FAASt [T-Pole Program Line 3000] (Transmission) | Transmission | Transmission Priority Pole Replacements | FF | 0.631 | Program Cost Included in PBUT13.681672 | 2021-09-22 | Execution | 2023-04-04 | 2026-12-02 | No | 77%
PBUT13.750150 | FAASt [Transmission Priority Pole Replacement Program Line 4800 Santa Isabel TC – Toro Negro 1 HP] (Transmission) | Transmission | Transmission Priority Pole Replacements | FF | 0.134 | Program Cost Included in PBUT13.681672 | 2021-09-22 | Execution | 2024-06-20 | 2026-08-07 | No | 0%
PBUT13.750151 | FAASt [Transmission Priority Pole Replacement Program Line 700 Costa Sur SP – Yauco 2 HP] (Transmission) | Transmission | Transmission Priority Pole Replacements | FF | 0.255 | Program Cost Included in PBUT13.681672 | 2021-09-22 | Execution | 2024-06-20 | 2026-09-25 | No | 0%
PBUT13.750168 | FAASt [ Transmission Priority Pole Replacement Program Line 4800 Santa Isabel TC – Aibonito TO] (Transmission) | Transmission | Transmission Priority Pole Replacements | FF | 0.469 | Program Cost Included in PBUT13.681672 | 2021-09-22 | Execution | 2024-06-20 | 2026-08-07 | No | 0%
PBUT13.753782 | FAASt [Transmission Priority Pole Replacement Program Line 3100 Monacillos TC – Sabana Llana TC] (Transmission) | Transmission | Transmission Priority Pole Replacements | FF | 0.131 | Program Cost Included in PBUT13.681672 | 2021-09-22 | Execution | 2024-08-23 | 2026-06-26 | No | 0%
PBUT18.549764 | FAASt [Physical Security - Group 2] (Substation) | Substation | Substation Security | FF | 2.38 | 53.8 | 2021-10-18 | Execution | 2021-12-03 | 2025-12-05 | No | 86%
PBUT18.550910 | FAASt [Physical Security - Group 1] (Substation) | Substation | Substation Security | FF | 6.69 | Program Cost Included in PBUT18.549764 | 2021-10-18 | Execution | 2021-12-14 | 2025-11-05 | No | 81%
PBUT18.551861 | FAASt [Physical Security - Group 3] (Substation) | Substation | Substation Security | FF | 4.13 | Program Cost Included in PBUT18.549764 | 2021-10-18 | Execution | 2021-12-21 | 2026-05-30 | No | 48%
PBUT18.660422 | FAASt [Physical Security - Group 4] (Substation) | Substation | Substation Security | FF | 3.82 | Program Cost Included in PBUT18.549764 | 2021-10-18 | Execution | 2022-01-27 | 2026-07-24 | No | 43%
PBUT19.01 | CCTV&accessReg&Tech Facility | Substation | Regional Operationas Physical Security | NFC | 0 | 0.040027 | 2025-07-31 | Execution | 2022-07-01 | 2027-06-30 | N/A | 36%
PBUT19.02 | CCTV&accessCustomerExpFacility | Substation | Regional Operationas Physical Security | NFC | 0 | 0.021752 | 2025-07-31 | Execution | 2022-07-01 | 2027-06-30 | N/A | 47%
PBUT19.03 | CCTV&accessPaloSeco | Substation | Regional Operationas Physical Security | NFC | 0 | 0.1637 | 2025-07-31 | Close Out | 2022-07-01 | 2026-03-31 | N/A | 100%
PBUT19.04 | CCTV SatelliteWarehouses | Substation | Regional Operationas Physical Security | NFC | 0 | 0.19199 | 2025-07-31 | Execution | 2022-07-01 | 2027-06-30 | N/A | 21%
PBUT19.05 | CCTV&accessRegionalWarehouses | Substation | Regional Operationas Physical Security | NFC | 0 | 0.15 | 2025-07-31 | Execution | 2022-07-01 | 2027-06-30 | N/A | 50%
PBUT22.657300 | FAASt [ENERGY MANAGEMENT SYSTEM (EMS)] (Telecommunication) | Enabling | Critical Energy Management System Upgrades | FF | 48.94 | 126 | 2021-09-22 | Execution | 2022-01-19 | 2026-03-24 09:36 | No | 95%
PBUT30.334323 | FAASt Distribution Pole and Conductor Repair - Ponce Group 1 (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.39 | 600 | 2021-08-20 | Execution | 2021-09-08 | 2026-03-31 | Yes | 91%
PBUT30.334329 | FAASt Distribution Pole and Conductor Repair - Ponce Group 2 (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.38 | Program Cost Included in PBUT30.334323 | 2021-08-20 | Execution | 2021-09-08 | 2026-03-31 | Yes | 87%
PBUT30.334527 | FAASt [Distribution Pole and Conductor Repair – Caguas Group 8 (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.12 | Program Cost Included in PBUT30.334323 | 2021-08-20 | Execution | 2021-09-10 | 2025-10-31 | Yes | 97%
PBUT30.542762 | FAASt Distribution Pole and Conductor Repair – Arecibo Group 2 (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.77 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2021-10-26 | 2026-03-31 | Yes | 97%
PBUT30.673771 | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 1] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 2.37 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-05-24 | 2026-03-31 | No | 86%
PBUT30.673772 | FAASt [Distribution Pole and Conductor Repair - Mayagüez Group 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 4.12 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-05-24 | 2026-03-31 | No | 83%
PBUT30.673774 | FAASt [Distribution Pole and Conductor Repair - Mayaguez Group 1] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 1.77 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-05-24 | 2026-04-30 | No | 62%
PBUT30.673775 | FAASt [Distribution Pole and Conductor Repair - Mayaguez Group 3] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 4.43 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-05-24 | 2026-03-31 | No | 89%
PBUT30.673795 | FAASt Distribution Pole and Conductor Repair - Mayaguez Group 4 (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 1.79 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-05-24 | 2026-03-31 | No | 89%
PBUT30.673818 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 1] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.79 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-05-25 | 2026-03-31 | No | 87%
PBUT30.673836 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 1] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 5.75 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-05-25 | 2026-03-31 | No | 86%
PBUT30.673838 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.36 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-05-25 | 2026-03-31 | Yes | 85%
PBUT30.673839 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.03 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Close Out | 2022-05-25 | 2023-09-05 | Yes | 100%
PBUT30.673843 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 3] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 1.13 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-05-25 | 2026-03-31 | No | 80%
PBUT30.673844 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 3] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 1.39 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-05-25 | 2026-03-31 | No | 87%
PBUT30.673847 | FAASt [Distribution Pole and Conductor Repair-Carolina Group 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.24 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-05-25 | 2026-02-27 | No | 78%
PBUT30.673848 | FAASt [Distribution Pole and Conductor Repair-Carolina Group 3] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.05 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-05-25 | 2026-03-16 | No | 56%
PBUT30.674072 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 1] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 1.11 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-05-27 | 2026-03-31 | No | 88%
PBUT30.674083 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 2.11 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-05-27 | 2026-03-31 | No | 80%
PBUT30.674088 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 3] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 1.7 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-05-27 | 2026-03-31 | No | 88%
PBUT30.674092 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 5] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.53 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-05-27 | 2026-03-31 | No | 78%
PBUT30.674096 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 6] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 2.09 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-05-27 | 2026-03-31 | No | 88%
PBUT30.674098 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 7] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.11 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Close Out | 2022-05-27 | 2023-05-04 | Yes | 100%
PBUT30.678985 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 4] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.41 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-07-26 | 2026-03-31 | No | 89%
PBUT30.678988 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 5] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 1.12 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-07-26 | 2026-03-31 | No | 87%
PBUT30.679025 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 4] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.3 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-07-27 | 2026-03-31 | No | 80%
PBUT30.679026 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 5] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.59 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-07-27 | 2026-03-31 | No | 78%
PBUT30.679033 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 9] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.91 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-07-27 | 2026-03-31 | Yes | 89%
PBUT30.679127 | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 3] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.22 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-07-28 | 2026-03-31 | Yes | 88%
PBUT30.679134 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 10] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.56 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-07-28 | 2026-02-27 | Yes | 94%
PBUT30.679149 | FAASt Distribution Pole and Conductor Repair - Mayagüez Group 5 (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.16 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-07-28 | 2026-03-31 | Yes | 88%
PBUT30.679153 | FAASt Distribution Pole and Conductor Repair - Mayagüez Group 6 (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.22 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-07-28 | 2026-03-31 | Yes | 88%
PBUT30.679457 | FAASt [Distribution Pole and Conductor Repair - Ponce Group 3] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.75 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-08-03 | 2026-03-31 | No | 86%
PBUT30.679458 | FAASt [Distribution Pole and Conductor Repair - Ponce Group 4] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.59 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-08-03 | 2026-03-31 | Yes | 88%
PBUT30.682028 | FAASt [Pole and Conductor Repair - San Juan Group 8] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.54 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-09-06 | 2025-11-30 | No | 75%
PBUT30.682031 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 9] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.63 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-09-06 | 2026-02-27 | No | 26%
PBUT30.682135 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 8] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.69 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-09-07 | 2026-03-31 | No | 86%
PBUT30.682136 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 9] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.57 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-09-07 | 2026-03-31 | No | 95%
PBUT30.682172 | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 8] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.27 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-09-08 | 2026-03-31 | Yes | 88%
PBUT30.682178 | FAASt [Pole and Conductor Repair - Arecibo Group 7] (Distribution ) | Distribution | Distribution Pole and Conductor Repair | FF | 0.26 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-09-08 | 2026-03-31 | No | 80%
PBUT30.682180 | FAASt [Pole and Conductor Repair - Mayagüez Group 10] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.05 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-09-08 | 2026-03-16 | No | 51%
PBUT30.682210 | FAASt [Pole and Conductor Repair - Mayagüez Group 9] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.24 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-09-08 | 2026-03-31 | Yes | 81%
PBUT30.682228 | FAASt [Pole and Conductor Repair - Ponce Group 8] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.95 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-09-08 | 2026-03-31 | No | 88%
PBUT30.682324 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 13] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.71 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-09-12 | 2026-03-31 | No | 82%
PBUT30.682373 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 14] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.08 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-09-12 | 2026-03-31 | Yes | 90%
PBUT30.682865 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 7] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.09 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-09-19 | 2026-03-16 | No | 82%
PBUT30.682870 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 6] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.1 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-09-19 | 2026-03-31 | No | 89%
PBUT30.682882 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 11] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.66 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-09-19 | 2026-03-31 | No | 85%
PBUT30.682890 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 12] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.61 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-09-19 | 2026-03-31 | Yes | 88%
PBUT30.682898 | FAASt [Distribution Pole and Conductor Repair - Bayamón Group 6] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.74 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-09-19 | 2026-03-31 | No | 89%
PBUT30.682910 | FAASt [Distribution Pole and Conductor Repair - Bayamón Group 7] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.62 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-09-19 | 2026-03-31 | Yes | 97%
PBUT30.685263 | FAASt Distribution Pole and Conductor Repair - Ponce Group 6 (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.67 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-10-11 | 2026-03-31 | Yes | 86%
PBUT30.685370 | FAASt [Pole and Conductor Repair - Mayagüez Group 8] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.08 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Close Out | 2022-10-12 | 2023-08-17 | Yes | 100%
PBUT30.685477 | FAASt [Pole and Conductor Repair - Arecibo Group 6] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.41 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-10-13 | 2026-03-31 | No | 81%
PBUT30.685943 | FAASt Distribution Pole and Conductor Repair Ponce Group 5(Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.32 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-10-18 | 2026-03-31 | Yes | 88%
PBUT30.686453 | FAASt [Pole and Conductor Repair - Mayagüez Group 7] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.03 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Close Out | 2022-10-20 | 2023-07-18 | Yes | 100%
PBUT30.686471 | FAASt [Pole and Conductor Repair - Arecibo Group 5] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.32 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-10-20 | 2026-03-31 | Yes | 97%
PBUT30.686480 | FAASt [Pole and Conductor Repair - Ponce Group 7] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.63 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-10-20 | 2026-03-31 | No | 87%
PBUT30.688096 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 15] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.03 | Program Cost Included in PBUT30.334323 | 2022-12-10 | Close Out | 2022-11-02 | 2023-10-27 | Yes | 100%
PBUT30.688109 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 11] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.56 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-11-02 | 2026-03-31 | Yes | 89%
PBUT30.688198 | FAASt [Pole and Conductor Repair - Arecibo Group 10] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.08 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-11-03 | 2026-03-31 | Yes | 85%
PBUT30.688472 | FAASt [Pole and Conductor Repair - Mayaguez Group 11] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.18 | Program Cost Included in PBUT30.334323 | 2022-12-10 | Execution | 2022-11-04 | 2026-03-31 | No | 85%
PBUT30.688625 | FAASt [Pole and Conductor Repair - Ponce Group 10] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.9 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-11-07 | 2026-03-31 | Yes | 87%
PBUT30.688627 | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 9] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.38 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-11-07 | 2026-03-31 | No | 84%
PBUT30.688629 | FAASt [Pole and Conductor Repair - Mayagüez Group 13] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.13 | Program Cost Included in PBUT30.334323 | 2022-12-10 | Execution | 2022-11-07 | 2026-03-31 | No | 89%
PBUT30.688630 | FAASt [Pole and Conductor Repair - Mayagüez Group 12] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.05 | Program Cost Included in PBUT30.334323 | 2022-12-10 | Execution | 2022-11-07 | 2026-03-31 | No | 51%
PBUT30.688774 | FAASt Distribution Pole and Conductor Repair - Ponce Group 9 (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.54 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-11-07 | 2026-03-31 | No | 87%
PBUT30.689071 | FAASt [Pole and Conductor Repair - Arecibo Group 11] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.08 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-11-09 | 2026-03-31 | Yes | 90%
PBUT30.691246 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 10] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.25 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2022-11-28 | 2026-03-31 | No | 88%
PBUT30.701495 | FAASt [Pole and Conductor Repair - Mayagüez Group 14] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.03 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Close Out | 2023-01-03 | 2023-10-31 | Yes | 100%
PBUT30.701504 | FAASt [Pole and Conductor Repair - Arecibo Group 12] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.19 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Close Out | 2023-01-03 | 2023-10-25 | Yes | 100%
PBUT30.701545 | FAASt [Pole and Conductor Repair - Ponce Group 11] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.62 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2023-01-03 | 2026-03-31 | Yes | 84%
PBUT30.701552 | FAASt [Pole and Conductor Repair - Ponce Group 12] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.24 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2023-01-03 | 2026-03-31 | Yes | 90%
PBUT30.701555 | FAASt [Pole and Conductor Repair - Ponce Group 13] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.65 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2023-01-03 | 2026-03-31 | No | 89%
PBUT30.701679 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 12] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.08 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2023-01-04 | 2026-03-31 | No | 67%
PBUT30.704750 | FAASt Distribution Pole and Conductor Repair - Bayamon Group 10 (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.58 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2023-02-02 | 2026-03-31 | No | 88%
PBUT30.704751 | FAASt Distribution Pole and Conductor Repair - Bayamon Group 11 (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.44 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2023-02-02 | 2026-03-31 | No | 91%
PBUT30.704755 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 12-13-14] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.52 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2023-02-02 | 2026-03-31 | No | 84%
PBUT30.704844 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 16-17-18-19-20] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.41 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2023-02-02 | 2026-03-31 | No | 86%
PBUT30.704916 | FAASt [Pole and Conductor Repair - Arecibo Group 13-14-15-16] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.3 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2023-02-03 | 2026-03-31 | Yes | 80%
PBUT30.704933 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 13-14-15-16] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 1.43 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2023-02-03 | 2026-03-16 | No | 50%
PBUT30.705527 | FAASt [Distribution Pole and Conductor Repair – San Juan 17-18-19-20-21] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.77 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2023-02-08 | 2026-03-31 | No | 68%
PBUT30.705584 | FAASt [Pole and Conductor Repair - Ponce Groups 14 & 15] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 1.84 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2023-02-09 | 2026-03-31 | No | 80%
PBUT30.708579 | FAASt [Pole and Conductor Repair - Ponce Group 16, 17, 18 & 19] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 2.15 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2023-03-03 | 2026-03-31 | No | 89%
PBUT30.710094 | FAASt [Pole and Conductor Repair - Bayamon Group 1 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 7.2 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2023-03-20 | 2026-03-31 | No | 71%
PBUT30.710099 | FAASt [Pole and Conductor Repair - Arecibo Group 1 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 6.9 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2023-03-20 | 2026-03-31 | No | 93%
PBUT30.710110 | FAASt [Distribution Pole and Conductor Repair - Bayamon Group 2 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.09 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Close Out | 2023-03-20 | 2024-11-25 | Yes | 100%
PBUT30.711856 | FAASt [Pole and Conductor Repair - Bayamon Group 3 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 11.3 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2023-04-03 | 2026-01-30 | No | 89%
PBUT30.711888 | FAASt [Pole and Conductor Repair - Caguas Group 1 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 5.5 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2023-04-03 | 2026-03-31 | No | 92%
PBUT30.712968 | FAASt [Pole and Conductor Repair - Arecibo Group 2 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 5.8 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2023-04-04 | 2025-10-31 | No | 84%
PBUT30.738670 | FAASt [Pole and Conductor Repair - Ponce Group 1 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 5.1 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2023-11-15 | 2025-12-31 | No | 94%
PBUT30.738672 | FAASt [Pole and Conductor Repair - Mayaguez Group 1 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 10.6 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2023-11-15 | 2025-12-31 | No | 79%
PBUT30.738971 | FAASt [Pole and Conductor Repair - Caguas Group 2 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 14.2 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2023-11-17 | 2025-12-31 | No | 77%
PBUT30.742026 | FAASt [Pole and Conductor Repair - San Juan Group 2 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 1.1 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2024-01-04 | 2026-01-30 | No | 85%
PBUT30.742070 | FAASt [Pole and Conductor Repair - San Juan Group 1 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 5.6 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2024-01-05 | 2026-03-31 | No | 85%
PBUT30.749060 | FAASt [Transmission Priority Pole Replacement Program Line 5600 Victoria TC – Añasco TC] (Transmission) | Transmission | Transmission Priority Pole Replacements | FF | 1.3 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Design | 2024-06-05 | 2026-08-06 | No | 0%
PBUT30.749072 | FAASt [Transmission Priority Pole Replacement Program Line 2700 Aguadilla Hospital Distrito Sect – Mora TC] (Transmission) | Transmission | Transmission Priority Pole Replacements | FF | 0.827 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Design | 2024-06-05 | 2026-05-05 | No | 0%
PBUT30.750692 | FAASt [Pole and Conductor Repair - Mayaguez Group 3 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 12.9 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2024-07-02 | 2026-07-29 | No | 38%
PBUT30.752540 | FAASt [Pole and Conductor Repair -Mayaguez Group 3 Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 7.1 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Design | 2024-08-01 | 2026-06-30 | No | 0%
PBUT30.790443 | FAASt [Pole and Conductor Repair -San Juan Group 3 Phase 2 (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.186 | Program Cost Included in PBUT30.334323 | 2021-09-22 | Execution | 2025-04-02 | 2026-07-29 | No | 71%
PBUT33.01 | Line40600 Baymn-Monac(UG Loop) | Transmission | Transmission Line Rebuild | NFC | 0 | 0.1625 | 2025-07-31 | Plan | 2022-07-01 | 2027-06-30 | N/A | 0%
PBUT33.02 | 36100 Fast Track-NFC Structure | Transmission | Transmission Line Rebuild | NFC | 0 | 0.4 | 2025-07-31 | Plan | 2023-07-01 | 2027-06-30 | N/A | 0%
PBUT33.03 | Restorat.of UG TL Segment 2200 | Transmission | Transmission Line Rebuild | NFC | 0 | 2.1848 | 2025-07-31 | Plan | 2026-03-01 | 2026-06-30 | N/A | 0%
PBUT33.04 | Restorat.of UG TL Segment16800 | Transmission | Transmission Line Rebuild | NFC | 0 | 0.18476 | 2025-07-31 | Plan | 2026-03-01 | 2026-06-30 | N/A | 0%
PBUT33.05 | DOE TL 2100 | Transmission | Transmission Line Rebuild | NFC | 0 | 2 | 2025-07-31 | Close Out | 2025-07-01 | 11/31/2025 | N/A | 100%
PBUT33.06 | DOE TL 9100 | Transmission | Transmission Line Rebuild | NFC | 0 | 1.5 | 2025-07-31 | Close Out | 2025-07-01 | 11/31/2025 | N/A | 100%
PBUT33.07 | Line 100/200 out of service segment | Transmission | Transmission Line Rebuild | NFC | 0 | 0.25 | 2025-07-31 | Design | N/A | Under Assessment | N/A | 0%
PBUT33.08 | Line 16800 | Transmission | Transmission Line Rebuild | NFC | 0 | 4 | 2025-07-31 | Initiation | N/A | 2026-06-30 | N/A | 0%
PBUT33.165213 | FAASt – Line 5400 – Rio Blanco HP to Daguao TC to Punta Lima TO to Vieques 2501 to Culebra 3801 (Transmission) | Transmission | Transmission Line Rebuild | FF | Pending Obligation | 73.06 | 2021-06-08 | Design | 2020-12-18 | Pending Obligation | Pending Obligation | 0%
PBUT33.167446 | FAASt - Line 36100 (115kV) - Dos Bocas HP to Monacillos TC (Transmission) | Transmission | Transmission Line Rebuild | FF | 33.9 | 109.97 | 2021-06-08 | Design | 2021-01-13 | 2027-04-22 | No | 0%
PBUT33.168226 | FAASt San Juan 115kV Underground Transmission Loop (Transmission) | Transmission | Transmission Line Rebuild | FF | 14.75 | 11.6 | 2021-06-08 | Design | 2021-01-20 | 2030-08-27 17:00 | No | 0%
PBUT33.168483 | FAASt - 115kV Line 36400 - Dos Bocas HP to Ponce TC (Transmission) | Transmission | Transmission Line Rebuild | FF | Pending Obligation | 83.26 | 2021-06-08 | Design | 2021-01-22 | Pending Obligation | Pending Obligation | 0%
PBUT33.176913 | FAASt [Palo Seco SP to Catano Sect 38kV Line- 9500] (Transmission) | Transmission | Transmission Line Rebuild | FF | 33.5 | 6.71 | 2021-06-08 | Design | 2021-03-23 | 2028-08-02 | No | 0%
PBUT33.176971 | FAASt –38kV Line 8200 - San Juan SP to Catano Sect Line (Transmission) | Transmission | Transmission Line Rebuild | FF | 21.6 | 8.07 | 2021-06-08 | Design | 2021-03-23 | 2027-06-28 | No | 0%
PBUT33.180052 | FAASt Ponce TC to Jobos TC - 38kV 100 & 200 (Transmission) | Transmission | Transmission Line Rebuild | FF | 74.5 | 87.28 | 2021-06-08 | Design | 2021-04-14 | 2029-08-24 | No | 0%
PBUT33.334470 | FAASt [Line 3100 Monacillos TC to Daguao TC] (Transmission) | Transmission | Transmission Line Rebuild | FF | 47.1 | 113.33 | 2021-08-20 | Design | 2021-09-10 | 2028-08-04 | no | 0%
PBUT33.547251 | FAASt Line 2400 Dos Bocas HP to America Apparel (Transmission) | Transmission | Transmission Line Rebuild | FF | 50.2 | 21.47 | 2021-10-18 | Design | 2021-11-16 | 2027-01-22 | No | 0%
PBUT33.756997 | FAASt [TL 1900 Caguanas to Lares TO] (Transmission) | Transmission | Transmission Line Rebuild | FF | Pending Obligation | 40.1 | 2024-08-22 | Design | 2024-09-25 | Pending Obligation | Pending Obligation | 0%
PBUT33.756999 | FAASt [TL 1900 Lares TO to San Sebastian] (Transmission) | Transmission | Transmission Line Rebuild | FF | Pending Obligation | 36.5 | 2024-08-22 | Design | 2024-09-25 | Pending Obligation | Pending Obligation | 0%
PBUT36.714654 | FAASt [Advanced Metering Infrastructure (AMI)] (Telecommunications) | Customer Experience | AMI Implementation Program | FF | 873.85 | 780 | 2023-04-05 | Execution | 2023-04-20 | 2028-12-31 | No | 10%
PBUT37.01 | BESS Land Purchase | Enabling | Microgrid, Phasor Measurement Units (PMU), and Battery Energy Storage Installations and Integration | NFC | 0 | 4 | 2025-07-31 | Initiation | N/A | Under Assessment | N/A | 0%
PBUT37.751655 | FAASt [Vieques Microgrid] (Transmission) | Distribution | Microgrid Installation and Integration | FF | Pending Obligation | Program Cost Included in PUBT37.750503 | 2024-02-15 | Design | 2024-07-18 | Pending Obligation | Pending Obligation | 0%
PBUT37.751656 | FAASt [Culebra Microgrid] (Transmission) | Distribution | Microgrid Installation and Integration | FF | Pending Obligation | Program Cost Included in PUBT37.750503 | 2024-02-15 | Design | 2024-07-18 | Pending Obligation | Pending Obligation | 0%
PBUT38.02 | 17-1-243 WR6351877MCasasFulReh | Customer Experience | New Business Connections | NFC | 0 | 1.6207 | 2025-08-02 | Close Out | 2024-11-22 | 2025-09-22 | Yes | 100%
PBUT38.03 | 15-5-0293 Los Tubos Beach | Customer Experience | New Business Connections | NFC | 0 | 0.050243 | 2025-08-03 | Close Out | 2025-04-30 | 2025-09-19 | Yes | 100%
PBUT38.04 | WR6325133-6385841 Terrumo LLC | Customer Experience | New Business Connections | NFC | 0 | 0.00057705 | 2025-08-04 | Close Out | 2025-02-01 | 2025-10-20 | Yes | 100%
PBUT38.05 | ANTENA LIBERTY CRAN 09-165 NPC | Customer Experience | New Business Connections | NFC | 0 | 0.016974 | 2025-08-05 | Close Out | 2025-03-01 | 2025-10-29 | Yes | 100%
PBUT38.06 | Hacienda Peñonales 20-5-0076 | Customer Experience | New Business Connections | NFC | 0 | 0.028884 | 2025-08-06 | Close Out | 2025-09-30 | 2025-10-29 | Yes | 100%
PBUT38.07 | HYDROPHONIC LLC | Customer Experience | New Business Connections | NFC | 0 | 0.017 | 2025-08-07 | Close Out | 2025-03-13 | 9/26/205 | Yes | 100%
PBUT38.08 | La Maquina SG 22-4-0558 | Customer Experience | New Business Connections | NFC | 0 | 0.006528 | 2025-08-08 | Close Out | 2025-09-30 | 2025-10-29 | Yes | 100%
PBUT38.09 | UG Repairs Sanchez Osorio Ave | Customer Experience | New Business Connections | NFC | 0 | 0.31208 | 2025-08-09 | Close Out | 2025-06-30 | 2025-09-19 | Yes | 100%
PBUT38.10 | Virgen M. Ayala 25-4-0007-EE | Customer Experience | New Business Connections | NFC | 0 | 0.012776 | 2025-08-10 | Close Out | 2025-09-30 | 2025-10-29 | Yes | 100%
PBUT4.745856 | FAASt [Automation Program Group 14 DAR ARECIBO 8404- FY24] (Distribution) | Distribution | Distribution Automation | FF | 1.6 | Program Cost Included in PBUT4.688623 | 2022-08-25 | Execution | 2024-03-22 | 2025-09-30 | No | 92%
PBUT4.745859 | FAASt [Automation Program Group 18: DAR – SAN JUAN 2001- FY24] (Distribution) | Distribution | Distribution Automation | FF | 0.46 | Program Cost Included in PBUT4.688623 | 2022-08-25 | Execution | 2024-03-22 | 2025-09-30 | No | 72%
PBUT4.745861 | FAASt [Automation Program Group 12: DAR – ARECIBO 7402, 7403, 7702 FY24] (Distribution) | Distribution | Distribution Automation | FF | 3.6 | Program Cost Included in PBUT4.688623 | 2022-08-25 | Execution | 2024-03-22 | 2025-09-30 | No | 76%
PBUT4.746309 | FAASt [Automation Program Group 30- DAR – Bayamon 9203 - FY24] (TL/Distribution) | Distribution | Distribution Automation | FF | 0.564 | Program Cost Included in PBUT4.688623 | 2022-08-25 | Execution | 2024-04-02 | 2026-03-31 | No | 7%
PBUT4.752808 | FAASt [Automation Program Group 19: Arecibo] (Distribution) | Distribution | Distribution Automation | FF | 2.7 | Program Cost Included in PBUT4.688623 | 2022-08-25 | Execution | 2024-08-07 | 2025-09-30 | No | 85%
PBUT4.752810 | FAASt [Automation Program Group 20: Caguas] (Distribution) | Distribution | Distribution Automation | FF | 2.6 | Program Cost Included in PBUT4.688623 | 2022-08-25 | Execution | 2024-08-07 | 2025-09-30 | No | 77%
PBUT4.755211 | FAASt [Automation Program Group 15] (Distribution) | Distribution | Distribution Automation | FF | 0.643 | Program Cost Included in PBUT4.688623 | 2022-08-25 | Execution | 2024-09-05 | 2025-09-30 | No | 72%
PBUT4.757662 | FAASt [Automation Program Group 21] (Distribution) | Distribution | Distribution Automation | FF | 1.7 | Program Cost Included in PBUT4.688623 | 2022-08-25 | Execution | 2024-09-27 | 2026-06-30 | No | 20%
PBUT4.757687 | FAASt [Automation Program Group 22] (Distribution) | Distribution | Distribution Automation | FF | 2.3 | Program Cost Included in PBUT4.688623 | 2022-08-25 | Execution | 2024-09-27 | 2026-06-30 | No | 30%
PBUT4.757689 | FAASt [Automation Program Group 24] (Distribution) | Distribution | Distribution Automation | FF | 1.7 | Program Cost Included in PBUT4.688623 | 2022-08-25 | Execution | 2024-09-27 | 2026-06-30 | No | 70%
PBUT4.757692 | FAASt [Automation Program Group 26] (Distribution) | Distribution | Distribution Automation | FF | 0.938 | Program Cost Included in PBUT4.688623 | 2022-08-25 | Execution | 2024-09-27 | 2026-03-31 | No | 83%
PBUT4.757694 | FAASt [Automation Program Group 27] (Distribution) | Distribution | Distribution Automation | FF | 2.3 | Program Cost Included in PBUT4.688623 | 2022-08-25 | Execution | 2024-09-27 | 2026-06-30 | No | 20%
PBUT4.757696 | FAASt [Automation Program Group 31] (Distribution) | Distribution | Distribution Automation | FF | 1.1 | Program Cost Included in PBUT4.688623 | 2022-08-25 | Execution | 2024-09-27 | 2026-06-30 | No | 54%
PBUT4.757697 | FAASt [Automation Program Group 32] (Distribution) | Distribution | Distribution Automation | FF | 1.9 | Program Cost Included in PBUT4.688623 | 2022-08-25 | Execution | 2024-09-27 | 2026-06-30 | No | 18%
PBUT4.757698 | FAASt [Automation Program Group 33] (Distribution) | Distribution | Distribution Automation | FF | 1.8 | Program Cost Included in PBUT4.688623 | 2022-08-25 | Execution | 2024-09-27 | 2026-06-09 | No | 32%
PBUT4.757699 | FAASt [Automation Program Group 34] (Distribution) | Distribution | Distribution Automation | FF | 2.7 | Program Cost Included in PBUT4.688623 | 2022-08-25 | Execution | 2024-09-27 | 2026-03-04 | No | 7%
PBUT4.757700 | FAASt [Automation Program Group 35] (Distribution) | Distribution | Distribution Automation | FF | 1.3 | Program Cost Included in PBUT4.688623 | 2022-08-25 | Execution | 2024-09-27 | 2026-06-30 | No | 20%
PBUT4.800286 | FAASt [Automation Program Group 36] (Distribution) | Distribution | Distribution Automation | FF | 1.7 | Program Cost Included in PBUT4.688623 | 2022-08-25 | Execution | 2024-12-30 | 2026-06-30 | No | 45%
PBUT4.800361 | FAASt [Automation Program Group 37] (Distribution) | Distribution | Distribution Automation | FF | 1.5 | Program Cost Included in PBUT4.688623 | 2022-08-25 | Execution | 2024-12-31 | 2026-06-30 | No | 44%
PBUT5.542517 | FAASt [Luquillo Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 8.81 | 1220 | 2021-09-22 | Execution | 2021-10-25 | 2026-06-11 | No | 89%
PBUT5.542687 | FAASt [Lajas Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 10.7 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2021-10-26 | 2026-01-20 | No | 93%
PBUT5.542688 | FAASt [Aguada Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 18.57 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2021-10-26 | 2026-01-27 | No | 95%
PBUT5.542690 | FAASt [Maunabo Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 6.44 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2021-10-26 | 2025-10-28 | No | 95%
PBUT5.542756 | FAASt [Guánica Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 10.06 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2021-10-26 | 2026-02-13 | No | 89%
PBUT5.659623 | FAASt [Cataño Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 17.56 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-01-20 | 2025-11-07 | No | 77%
PBUT5.659625 | FAASt [Dorado Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 24.37 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-01-20 | 2026-02-26 | No | 80%
PBUT5.659715 | FAASt [Aibonito Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 7.25 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-01-21 | 2026-01-14 | No | 93%
PBUT5.659968 | FAASt [San Germán Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 34.88 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-01-24 | 2027-09-08 | No | 74%
PBUT5.660227 | FAASt [Hatillo Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 20.33 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-01-26 | 2026-09-04 | No | 83%
PBUT5.660239 | FAASt [Villalba Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 10.87 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-01-26 | 2026-05-15 | No | 89%
PBUT5.660437 | FAASt [Manati Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 28.64 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-01-27 | 2026-05-16 | No | 77%
PBUT5.671502 | FAASt [Yabucoa Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 16.88 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-04-26 | 2026-03-06 | No | 71%
PBUT5.673504 | FAASt [Gurabo Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 20.74 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-05-19 | 2027-07-27 | No | 71%
PBUT5.678789 | FAASt [Carolina Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 16.02 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-07-22 | 2025-09-08 | No | 69%
PBUT5.678793 | FAASt [Mayagüez Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 12.37 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-07-22 | 2025-10-31 | No | 57%
PBUT5.679039 | FAASt [Caguas Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 75.59 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-07-27 | 2026-01-31 | No | 50%
PBUT5.679780 | FAASt [Bayamón Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 21.89 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-08-08 | 2026-05-15 | No | 78%
PBUT5.690545 | FAASt [Aguadilla Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 21.09 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-11-21 | 2026-02-06 | No | 52%
PBUT5.691702 | FAASt [Trujillo Alto Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 26.29 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-11-30 | 2026-02-04 | No | 47%
PBUT5.698424 | FAASt [Florida Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 10.31 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-12-20 | 2028-01-17 | No | 75%
PBUT5.698439 | FAASt [Las Marias Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 8.36 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-12-20 | 2028-10-26 | No | 53%
PBUT5.698458 | FAASt [Guaynabo Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 10.62 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-12-20 | 2026-05-13 | No | 79%
PBUT5.698511 | FAASt [Culebra Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 1.3 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-12-20 | 2026-01-30 | No | 83%
PBUT5.698570 | FAASt [Corozal Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 15.95 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-12-20 | 2027-08-25 | No | 86%
PBUT5.698579 | FAASt [Orocovis Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 9.4 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2022-12-20 | 2027-06-15 | No | 58%
PBUT5.701472 | FAASt [Comerio Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 7.4 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2023-01-03 | 2026-11-01 | No | 83%
PBUT5.703535 | FAASt [Toa Baja Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 10.1 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2023-01-23 | 2026-02-13 | No | 55%
PBUT5.704679 | FAASt [Coamo Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 16.37 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2023-02-01 | 2027-02-07 | No | 71%
PBUT5.704849 | FAASt [Naguabo Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 13.2 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2023-02-02 | 2027-10-12 | No | 79%
PBUT5.704868 | FAASt [Ceiba Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 5.8 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2023-02-02 | 2027-04-07 | No | 69%
PBUT5.704921 | FAASt [Barranquitas Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 11 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2023-02-03 | 2027-07-01 | No | 67%
PBUT5.704927 | FAASt [Añasco Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 13.9 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2023-02-03 | 2027-04-07 | No | 91%
PBUT5.704938 | FAASt [Las Piedras Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 15.6 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2023-02-03 | 2027-07-16 | No | 70%
PBUT5.704943 | FAASt [Naranjito Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 13.7 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2023-02-03 | 2028-06-08 | No | 66%
PBUT5.709631 | FAASt [Morovis Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 15.2 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2023-03-15 | 2027-05-20 | No | 81%
PBUT5.714641 | FAASt [Rincón Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 11.5 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Design | 2023-04-20 | 2026-04-20 | No | 0%
PBUT5.724600 | FAASt [Jayuya Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 8.6 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2023-07-03 | 2026-12-12 | No | 75%
PBUT5.724601 | FAASt [Salinas Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 13.7 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2023-07-03 | 2027-05-28 | No | 79%
PBUT5.724698 | FAASt [Adjuntas Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 12.6 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2023-07-05 | 2027-06-18 | No | 80%
PBUT5.724703 | FAASt [Arroyo Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 6 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2023-07-05 | 2026-08-16 | No | 62%
PBUT5.724825 | FAASt [Cidra Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 14.6 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2023-07-06 | 2027-07-19 | No | 67%
PBUT5.724938 | FAASt [Vega Alta Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | FF | 15.6 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2023-07-07 | 2027-10-07 | No | 59%
PBUT5.735474 | FAASt [Pole and Conductor Repair -Caguas Group 3 Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 14 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2023-10-20 | 2026-06-30 | No | 74%
PBUT5.738120 | FAASt [Pole and Conductor Repair-Carolina Group 2- Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 11.4 | Program Cost Included in PBUT5.542517 | 2021-09-22 | Execution | 2023-11-09 | 2025-12-31 | No | 74%
PBUT6.01 | Feeder 1657-01 UG Repair | Distribution | Distribution Line Rebuild | NFC | 0 | 0.00015778 | 2025-07-31 | Initiation | 2023-07-01 | 2027-06-30 | N/A | 0%
PBUT6.02 | Feeder 1658-13 UG Repair | Distribution | Distribution Line Rebuild | NFC | 0 | 0.00015778 | 2025-07-31 | Initiation | 2023-07-01 | 2027-06-30 | N/A | 0%
PBUT6.03 | Martin Peña GIS - 1111-01 UG | Distribution | Distribution Line Rebuild | NFC | 0 | 0.0019341 | 2025-07-31 | Plan | 2023-07-01 | 2027-06-30 | N/A | 0%
PBUT6.04 | Grana - 1907-05 UG | Distribution | Distribution Line Rebuild | NFC | 0 | 0.0010485 | 2025-07-31 | Plan | 2023-07-01 | 2027-06-30 | N/A | 0%
PBUT6.05 | Canovanas TC - 2404-06 UG | Distribution | Distribution Line Rebuild | NFC | 0 | 0.00010512 | 2025-07-31 | Plan | 2023-07-01 | 2027-06-30 | N/A | 0%
PBUT6.06 | Candelero - 2604-01 UG | Distribution | Distribution Line Rebuild | NFC | 0 | 0.00015778 | 2025-07-31 | Plan | 2023-07-01 | 2027-06-30 | N/A | 0%
PBUT6.07 | Villa del Carmen - 5016-01 UG | Distribution | Distribution Line Rebuild | NFC | 0 | 0.0010196 | 2025-07-31 | Plan | 2023-07-01 | 2027-06-30 | N/A | 0%
PBUT6.08 | System Improv. for Subst. 7301 | Distribution | Distribution Line Rebuild | NFC | 0 | 0.49734 | 2025-07-31 | Execution | 2025-05-01 | 2026-06-30 | N/A | 80%
PBUT6.165226 | FAASt [Feeders Vieques & Culebra] (Distribution) | Distribution | Distribution Line Rebuild | FF | Pending Obligation | 31.13 | 2021-06-08 | Design | 2020-12-18 | Pending Obligation | Pending Obligation | 0%
PBUT6.334488 | FAASt [Distribution Pole and Conductor Repair – Caguas Group 4 (Distribution) | Distribution | Distribution Pole and Conductor Repair | FF | 0.15 | Program Cost Included in PBUT30.334323 | 2021-08-20 | Execution | 2021-09-10 | 2026-03-31 | Yes | 88%
PBUT6.797148 | FAASt [Distribution Feeder Rebuild # 8101-03] (Distribution) | Distribution | Distribution Line Rebuild | FF | 2.3 | Program Cost Included in PBUT6.797148 | 2021-08-20 | Design | 2024-12-06 | 2026-09-07 | No | 0%
PBUT6.798275 | FAASt [Distribution Feeder Rebuild # 1620-02] (Distribution) | Distribution | Distribution Line Rebuild | FF | 6.7 | Program Cost Included in PBUT6.798275 | 2021-09-22 | Design | 2024-12-11 | 2027-01-12 | No | 0%
PBUT6.801166 | FAASt [Distribution Feeder Rebuild # 6601-03] (Distribution) | Distribution | Distribution Line Rebuild | FF | 19.8 | Program Cost Included in PBUT6.801166 | 2021-09-22 | Design | 2025-01-08 | Pending Obligation | Pending Obligation | 0%
PBUT6.801172 | FAASt [Distribution Feeder Rebuild # 1529-15] (Distribution) | Distribution | Distribution Line Rebuild | FF | 2.2 | Program Cost Included in PBUT6.801172 | 2021-09-22 | Design | 2025-01-08 | 2026-08-07 | No | 0%
PBUT6.812569 | FAASt [Distribution Feeder Rebuild 3502-02] | Distribution | Distribution Line Rebuild | FF | 10.2 | Program Cost Included in PBUT6.812569 | 2021-09-22 | Design | 2025-02-20 | 2026-11-11 | No | 0%
PBUT6.817956 | FAASt [Feeder Rebuild # 1303-02] (Distribution) | Distribution | Distribution Line Rebuild | FF | 2 | Program Cost Included in PBUT6.817956 | 2021-09-22 | Design | 2025-03-26 | 2027-01-20 | No | 0%
PBUT7.01 | GuanicaTC H.Vol.Eq.Repl.MinRep | Substation | Substation Reliability | NFC | 0 | 5.4594 | 2025-07-31 | Execution | 2021-09-01 | Under Assessment | N/A | 40%
PBUT7.02 | Maunabo TC | Substation | Substation Reliability | NFC | 0 | 0.96742 | 2025-07-31 | Execution | 2021-10-01 | 2026-09-08 | N/A | 50%
PBUT7.03 | Monacillo TCBreak&TransforRep | Substation | Substation Reliability | NFC | 0 | 4.325 | 2025-07-31 | Close Out | 2022-07-01 | 2025-09-25 | N/A | 100%
PBUT7.04 | Reliability AltRioGrande | Substation | Substation Reliability | NFC | 0 | 0.00039424 | 2025-07-31 | Initiation | N/A | Removed from Scope | N/A | 0%
PBUT7.05 | Reliability AreciboHospDist | Substation | Substation Reliability | NFC | 0 | 0.00036653 | 2025-07-31 | Initiation | N/A | Removed from Scope | N/A | 0%
PBUT7.06 | Reliability HatoReyTC | Substation | Substation Reliability | NFC | 0 | 0.00029568 | 2025-07-31 | Initiation | N/A | Removed from Scope | N/A | 0%
PBUT7.07 | Reliability CeibaBaja | Substation | Substation Reliability | NFC | 0 | 0.00014784 | 2025-07-31 | Initiation | N/A | Removed from Scope | N/A | 0%
PBUT7.08 | Reliability CharcoHondo | Substation | Substation Reliability | NFC | 0 | 0.00014784 | 2025-07-31 | Initiation | N/A | Removed from Scope | N/A | 0%
PBUT7.09 | Reliability Ciales | Substation | Substation Reliability | NFC | 0 | 9.856e-05 | 2025-07-31 | Initiation | N/A | Removed from Scope | N/A | 0%
PBUT7.10 | Reliability FortAllen | Substation | Substation Reliability | NFC | 0 | 4.928e-05 | 2025-07-31 | Initiation | N/A | Removed from Scope | N/A | 0%
PBUT7.11 | Reliability HumacaoTC | Substation | Substation Reliability | NFC | 0 | 0.14912 | 2025-07-31 | Close Out | 2023-07-01 | 2025-06-15 | N/A | 100%
PBUT7.12 | Reliability ManatiTC | Substation | Substation Reliability | NFC | 0 | 0.15116 | 2025-07-31 | Close Out | 2023-07-01 | 2025-06-06 | N/A | 100%
PBUT7.13 | Reliability VegaAlta9105 | Substation | Substation Reliability | NFC | 0 | 0.02698 | 2025-07-31 | Close Out | 2023-07-01 | 2025-02-14 | N/A | 100%
PBUT7.14 | Reliability Verdemar | Substation | Substation Reliability | NFC | 0 | 0.0079105 | 2025-07-31 | Close Out | 2023-07-01 | 2025-01-28 | N/A | 100%
PBUT7.15 | Reliability YaucoPueb1 | Substation | Substation Reliability | NFC | 0 | 0.01699 | 2025-07-31 | Close Out | 2023-07-01 | 2025-01-29 | N/A | 100%
PBUT7.16 | L 51100 prot EcoElec to C Sur | Substation | Substation Reliability | NFC | 0 | 0.025734 | 2025-07-31 | Close Out | 2023-07-01 | 2025-11-17 | N/A | 100%
PBUT7.17 | Reliability CanovanasTC | Substation | Substation Reliability | NFC | 0 | 0.075931 | 2025-07-31 | Design | 2023-07-01 | Removed from Scope | N/A | 0%
PBUT7.18 | Reliability BerwindTC | Substation | Substation Reliability | NFC | 0 | 0.191 | 2025-07-31 | Execution | 2023-07-01 | 2026-06-30 | N/A | 90%
PBUT7.19 | Reliability Aguada | Substation | Substation Reliability | NFC | 0 | 0.34473 | 2025-07-31 | Close Out | 2023-07-01 | 2025-03-06 | N/A | 100%
PBUT7.20 | Emer.MonacTC115/38kVTransfRepl | Substation | Substation Reliability | NFC | 0 | 0.0066875 | 2025-07-31 | Close Out | 2023-07-01 | 2025-11-24 | N/A | 100%
PBUT7.21 | Maunabo Pueblo 4301-02 CB | Substation | Substation Reliability | NFC | 0 | 0.070902 | 2025-07-31 | Close Out | 2024-08-01 | 2025-12-14 | N/A | 100%
PBUT7.22 | Arecibo Rural 8003 Transf.Repl | Substation | Substation Reliability | NFC | 0 | 0.12781 | 2025-07-31 | Design | 2024-07-01 | Removed from Scope | N/A | 0%
PBUT7.23 | Monacillos CB 37810 | Substation | Substation Reliability | NFC | 0 | 0.32484 | 2025-07-31 | Close Out | 2024-07-01 | 2026-03-06 | N/A | 100%
PBUT7.24 | Yabucoa TC RTU Replacement | Substation | Substation Reliability | NFC | 0 | 0.14576 | 2025-07-31 | Close Out | 2024-07-01 | 2025-11-30 | N/A | 100%
PBUT7.25 | San Juan SP RTU Replacement | Substation | Substation Reliability | NFC | 0 | 0.2346 | 2025-07-31 | Design | 2024-07-01 | Under Assessment | N/A | 0%
PBUT7.26 | Lloren Torres 1118-08 DA Relay | Substation | Substation Reliability | NFC | 0 | 0.022 | 2025-07-31 | Close Out | 2024-07-01 | 2025-12-31 | N/A | 100%
PBUT7.27 | Minillas 1114 DA Relay Repl | Substation | Substation Reliability | NFC | 0 | 0.022 | 2025-07-31 | Close Out | 2024-07-01 | 2026-02-26 | N/A | 100%
PBUT7.28 | BTC-Bayamon 1716-02 DA Relay | Substation | Substation Reliability | NFC | 0 | 0.022 | 2025-07-31 | Close Out | 2024-07-01 | 2024-11-12 | N/A | 100%
PBUT7.29 | Naguabo 2701-03 DA Relay Repl | Substation | Substation Reliability | NFC | 0 | 0.022 | 2025-07-31 | Close Out | 2024-07-01 | 2024-11-13 | N/A | 100%
PBUT7.30 | Once De Agosto 6014-01 CB | Substation | Substation Reliability | NFC | 0 | 0.022 | 2025-07-31 | Design | 2024-07-01 | Removed from Scope | N/A | 0%
PBUT7.31 | Verde Mar 2605-02 DA RelayRepl | Substation | Substation Reliability | NFC | 0 | 0.022 | 2025-07-31 | Close Out | 2024-07-01 | 2024-11-06 | N/A | 100%
PBUT7.32 | PlantaSanturce1117-11 DA Relay | Substation | Substation Reliability | NFC | 0 | 0.022 | 2025-07-31 | Close Out | 2024-07-01 | 2024-10-31 | N/A | 100%
PBUT7.33 | Villamar 1657 - 02 DA Relay | Substation | Substation Reliability | NFC | 0 | 0.022 | 2025-07-31 | Close Out | 2024-07-01 | 2024-11-21 | N/A | 100%
PBUT7.34 | Monacillo Bank#1 & #3 Trf.Repl | Substation | Substation Reliability | NFC | 0 | 5.143 | 2025-07-31 | Close Out | 2024-07-01 | 2025-12-18 | N/A | 100%
PBUT7.35 | Yabucoa 230Kv CB Replcmnt-0040 | Substation | Substation Reliability | NFC | 0 | 0.85 | 2025-07-31 | Close Out | 2024-07-01 | 2024-11-24 | N/A | 100%
PBUT7.36 | 11190 Canóvanas Sect. 38kV | Substation | Substation Reliability | NFC | 0 | 0.4 | 2025-07-31 | Close Out | 2024-07-01 | 2024-10-12 | N/A | 100%
PBUT7.37 | AguadillaHosp.Distr.7003-02 CB | Substation | Substation Reliability | NFC | 0 | 0.157 | 2025-07-31 | Close Out | 2024-07-01 | 2024-11-18 | N/A | 100%
PBUT7.38 | Dos Bocas 8005-2 CB | Substation | Substation Reliability | NFC | 0 | 0.157 | 2025-07-31 | Close Out | 2024-07-01 | 2024-12-23 | N/A | 100%
PBUT7.39 | Manatí 8401-02 CB | Substation | Substation Reliability | NFC | 0 | 0.157 | 2025-07-31 | Close Out | 2024-07-01 | 2024-10-18 | N/A | 100%
PBUT7.40 | Ojo de Agua 7002-2 CB | Substation | Substation Reliability | NFC | 0 | 0.157 | 2025-07-31 | Close Out | 2024-07-01 | 2024-10-24 | N/A | 100%
PBUT7.41 | Ojo de Agua 7002-3 CB | Substation | Substation Reliability | NFC | 0 | 0.192 | 2025-07-31 | Close Out | 2024-07-01 | 2024-10-23 | N/A | 100%
PBUT7.42 | Pajuil 7702-03 CB | Substation | Substation Reliability | NFC | 0 | 0.157 | 2025-07-31 | Close Out | 2024-07-01 | 2024-11-04 | N/A | 100%
PBUT7.43 | Peñuelas 5401-01 CB | Substation | Substation Reliability | NFC | 0 | 0.157 | 2025-07-31 | Close Out | 2024-07-01 | 2024-10-29 | N/A | 100%
PBUT7.44 | Dorado 9207 TC - CB 7810 | Substation | Substation Reliability | NFC | 0 | 0.3 | 2025-07-31 | Close Out | 2024-07-01 | 2024-12-23 | N/A | 100%
PBUT7.45 | AES 50270 230kV-CB Replacement | Substation | Substation Reliability | NFC | 0 | 0.5 | 2025-07-31 | Close Out | 2024-07-01 | 2025-11-15 | N/A | 100%
PBUT7.46 | Substation Relay Aeropuerto | Substation | Substation Reliability | NFC | 0 | 0.2 | 2025-07-31 | Close Out | 2024-07-01 | 2025-01-27 | N/A | 100%
PBUT7.47 | A.BuenasTranRelayRplcFeed39014 | Substation | Substation Reliability | NFC | 0 | 0.05 | 2025-07-31 | Close Out | 2024-07-01 | 2024-12-06 | N/A | 100%
PBUT7.48 | Cana-InterTranRelayRplFeed0020 | Substation | Substation Reliability | NFC | 0 | 0.05 | 2025-07-31 | Close Out | 2024-07-01 | 2024-11-14 | N/A | 100%
PBUT7.49 | HatilloTCTranRelayRplcFeed2120 | Substation | Substation Reliability | NFC | 0 | 0.035 | 2025-07-31 | Close Out | 2024-07-01 | 2025-06-26 | N/A | 100%
PBUT7.50 | IslaGrandeTranRelFeeder 0010 | Substation | Substation Reliability | NFC | 0 | 0.05 | 2025-07-31 | Design | 2024-07-01 | Removed from Scope | N/A | 0%
PBUT7.51 | JobosTCTranRelFeeder 3750 | Substation | Substation Reliability | NFC | 0 | 0.075 | 2025-07-31 | Design | 2024-07-01 | Removed from Scope | N/A | 0%
PBUT7.52 | LosAngelesTranRelFeeder 3642 | Substation | Substation Reliability | NFC | 0 | 0.05 | 2025-07-31 | Close Out | 2024-07-01 | 2024-11-27 | N/A | 100%
PBUT7.53 | PaloSecoTranRelFeeder 9520 | Substation | Substation Reliability | NFC | 0 | 0.05 | 2025-07-31 | Close Out | 2024-07-01 | 2025-04-01 | N/A | 100%
PBUT7.54 | Fajardo 6T01 Replacement | Substation | Substation Reliability | NFC | 0 | 1.0243 | 2025-07-31 | Close Out | 2024-07-01 | 2026-03-26 | N/A | 100%
PBUT7.55 | Bayamon TC - Phase 1 Trnsformr | Substation | Substation Reliability | NFC | 0 | 2.4243 | 2025-07-31 | Close Out | 2024-07-01 | 2026-04-06 | N/A | 100%
PBUT7.56 | Caguas TC - Phase 1 Transfrmer | Substation | Substation Reliability | NFC | 0 | 1.8767 | 2025-07-31 | Close Out | 2024-07-01 | 2025-10-06 | N/A | 100%
PBUT7.57 | Centro Medico - Phase 1 Trnsfo | Substation | Substation Reliability | NFC | 0 | 0.0094297 | 2025-07-31 | Design | 2024-07-01 | Removed from Scope | N/A | 0%
PBUT7.58 | Costa Sur - Phase 1 Transfrmer | Substation | Substation Reliability | NFC | 0 | 1.4835 | 2025-07-31 | Execution | 2024-07-01 | Under Assessment | N/A | 25%
PBUT7.59 | Factor - Phase 1 Transformer | Substation | Substation Reliability | NFC | 0 | 0.46547 | 2025-07-31 | Execution | 2024-07-01 | 2026-09-01 | N/A | 75%
PBUT7.60 | Mora - Phase 1 Transformer | Substation | Substation Reliability | NFC | 0 | 0.90795 | 2025-07-31 | Execution | 2024-07-01 | 2026-05-23 | N/A | 75%
PBUT7.61 | DOE LlorensT13kVMetalcladReplc | Substation | Substation Reliability | NFC | 0 | 5.7 | 2025-07-31 | Design | 2025-08-01 | 2026-10-23 | N/A | 0%
PBUT7.62 | DOE Mayaguez TC 115kv cable | Substation | Substation Reliability | NFC | 0 | 0.5 | 2025-07-31 | Design | 2025-08-01 | 2026-06-30 | N/A | 0%
PBUT7.63 | DOE-OOS Relays | Substation | Substation Reliability | NFC | 0 | 0.429 | 2025-07-31 | Close Out | 2025-08-01 | 2026-03-31 | N/A | 100%
PBUT7.64 | Monacillo 1346 | Substation | Substation Reliability | NFC | 0 | 0.5 | 2025-07-31 | Close Out |  | 2025-09-25 | N/A | 100%
PBUT7.65 | Sabana Llana – 544MVA | Substation | Substation Reliability | NFC | 0 | 9.1 | 2025-07-31 | Execution | 2024-07-01 | 2026-05-05 | N/A | 75%
PBUT7.746660 | FAASt [Minor Protection, Automation, and Control [PAC] Replacement] (Substation) | Substation | Substation Reliability | FF | Pending Obligation | Program Cost Included in PBUT7.746660 | 2021-09-22 | Design | 2024-04-08 | Pending Obligation | Pending Obligation | 0%
PBUT8.01 | 12444 Anasco 115/13.2 kV (L) | Substation | Substation Rebuilds | NFC | 0 | 0.072107 | 2025-07-31 | Close Out | 2021-07-01 | 2025-03-01 | Yes | 100%
PBUT8.02 | HatoReyTC-Transf1420 Emer.Repl | Substation | Substation Rebuilds | NFC | 0 | 3.7695 | 2025-07-31 | Close Out | 2024-07-01 | 2024-11-01 | Yes | 100%
PBUT8.165209 | FAASt - EPC - Culebra Substation 3801 and New Culebra Substation 3802 (Substation) | Substation | Substation Rebuilds | FF | 1.46 | 39.1 | 2021-06-08 | Execution | 2020-12-18 | 2029-01-01 | No | 45%
PBUT8.165225 | FAASt - EPC - Vieques 2501 substation repairs & New Vieques 2502 substation (Substation) | Substation | Substation Rebuilds | FF | 1.39 | 37.91 | 2021-06-08 | Execution | 2020-12-18 | 2029-01-01 | No | 2%
PBUT8.165268 | FAASt Rio Grande Estate Substation CH-2306 (Substation) | Substation | Substation Rebuilds | FF | 11.68 | 3.97 | 2021-06-08 | Execution | 2020-12-18 | 2025-08-30 | No | 93%
PBUT8.169058 | FAASt - Llorens Torres MC 1106 - Equipment Repair & Replacement - (Substations) | Substation | Substation Rebuilds | FF | Pending Obligation | 4 | 2021-06-08 | Design | 2021-01-27 | Pending Obligation | Pending Obligation | 0%
PBUT8.169266 | FAASt Centro Medico 1327/1359 Equipment Repair & Replacement (Substation) | Substation | Substation Rebuilds | FF | 21.33 | 11.7 | 2021-06-08 | Execution | 2021-01-28 | 2027-01-14 | No | 10%
PBUT8.169276 | FAASt Substation - Viaducto TC - MC 1100 - Equipment Repair & Replacement [Substation] | Substation | Substation Rebuilds | FF | Pending Obligation | 4 | 2021-06-08 | Design | 2021-01-28 | Pending Obligation | Pending Obligation | 0%
PBUT8.169495 | FAASt [Substations - Tapia GIS Rebuilt Equipment Repair & Replacement] (Substations) | Substation | Substation Rebuilds | FF | 15.34 | 23 | 2021-06-08 | Execution | 2021-01-29 | 2027-09-30 | No | 8%
PBUT8.169500 | FAASt [Bayamon TC – MC-BKRS-Y1] (Substation) | Substation | Substation Rebuilds | FF | 6.37 | 5.7 | 2021-06-08 | Execution | 2021-01-29 | 2027-05-13 | No | 45%
PBUT8.169896 | FAASt - Costa Sur SP TC – Equipment Repair and Replacement (Substation) | Substation | Substation Rebuilds | FF | 23.25 | 3.6 | 2021-06-08 | Execution | 2021-02-02 | 2026-09-25 | No | 44%
PBUT8.174422 | FAASt - Catano-Rebuild 1801(Substation) | Substation | Substation Rebuilds | FF | 23.26 | 11.3 | 2021-06-08 | Execution | 2021-03-04 | 2026-08-27 | No | 69%
PBUT8.178258 | FAASt - [Taft - MC 1105] (Substations) | Substation | Substation Rebuilds | FF | 13.4 | 4.1 | 2021-06-08 | Design | 2021-03-31 | 2028-03-03 | No | 0%
PBUT8.178503 | FAASt [Aguirre TC - BKRS] (Substations) | Substation | Substation Rebuilds | FF | 39.03 | 12.2 | 2021-06-08 | Execution | 2021-04-01 | 2029-07-03 | No | 33%
PBUT8.178577 | FAASt [Cachete – MC 1526] (Substations) | Substation | Substation Rebuilds | FF | Pending Obligation | 4 | 2021-06-08 | Design | 2021-04-01 | Pending Obligation | Pending Obligation | 0%
PBUT8.179558 | FAASt - Manatí TC - BRKS 230 kV - (Substation) | Substation | Substation Rebuilds | FF | 1.59 | 1.8 | 2021-06-08 | Close Out | 2021-04-09 | 2022-12-12 | Yes | 100%
PBUT8.542758 | FAASt [Minor Repairs -Group B] (Substation) | Substation | Substation Rebuilds | FF | 3.41 | 400 | 2021-09-22 | Execution | 2021-10-26 | 2026-12-30 | No | 76%
PBUT8.546370 | FAASt - Substation Minor Repairs Group A (Substation) | Substation | Substation Rebuilds | FF | 4.9 | Program Cost Included in PBUT8.542758 | 2021-09-22 | Execution | 2021-11-09 | 2026-09-13 | No | 71%
PBUT8.546371 | FAASt- Substation Minor Repairs Group C (Substation) | Substation | Substation Rebuilds | FF | 3.03 | Program Cost Included in PBUT8.542758 | 2021-09-22 | Execution | 2021-11-09 | 2025-12-14 | No | 76%
PBUT8.547187 | FAASt - [Substation Component Replacement Program] (Substation) | Substation | Substation Rebuilds | FF | Pending Obligation | 17.1 | 2021-10-18 | Design | 2021-11-15 | Pending Obligation | Pending Obligation | 0%
PBUT8.549715 | FAASt Substation Minor Repairs - Group D (Substation) | Substation | Substation Rebuilds | FF | 2.8 | Program Cost Included in PBUT8.542758 | 2021-09-22 | Execution | 2021-12-03 | 2026-05-08 | No | 33%
PBUT8.549725 | FAASt [Substation Minor Repairs - Group E] (Substation) | Substation | Substation Rebuilds | FF | 4.5 | Program Cost Included in PBUT8.542758 | 2021-09-22 | Execution | 2021-12-03 | 2026-07-10 | No | 64%
PBUT8.550106 | FAASt [Conquistador CH] (Substation) | Substation | Substation Rebuilds | FF | Pending Obligation | 5.1 | 2021-10-18 | Design | 2021-12-07 | Pending Obligation | Pending Obligation | 0%
PBUT8.550950 | FAASt - EPC - [Monacillo TC] (Substations) | Substation | Substation Rebuilds | FF | 88.1 | 105.23 | 2024-01-18 | Execution | 2021-12-14 | 2028-09-13 | No | 11%
PBUT8.551914 | FAASt [Caparra 1911 & 1924] (Substation) | Substation | Substation Rebuilds | FF | Pending Obligation | 6.6 | 2021-10-18 | Design | 2021-12-21 | Pending Obligation | Pending Obligation | 0%
PBUT8.682121 | FAASt - EPC -Aguirre TC-Phase II (Substation) | Substation | Substation Rebuilds | FF | 90.5 | 192.27 | 2022-08-25 | Execution | 2022-09-07 | 2029-05-04 | No | 5%
PBUT8.682328 | FAASt [Bayamón TC - Rebuild] (Substation) | Substation | Substation Rebuilds | FF | Pending Obligation | 124.5 | 2024-06-28 | Design | 2022-09-12 | Pending Obligation | Pending Obligation | 0%
PBUT8.682645 | FAASt [Maunabo TC] (Substation) | Substation | Substation Rebuilds | FF | 8.2 | Program Cost Included in PBUT8.542758 | 2021-09-22 | Execution | 2022-09-15 | 2028-08-23 | No | 31%
PBUT8.682834 | FAASt [EPC - Costa Sur TC - Phase II & III ] (Substation) | Substation | Substation Rebuilds | FF | 61.4 | 161.98 | 2022-08-25 | Execution | 2022-09-16 | 2029-12-30 | No | 1%
PBUT8.684920 | FAASt Substation High Voltage Replacement_Group 1 (Substation) | Substation | Substation Rebuilds | FF | 6.93 | 75.7 | 2022-08-25 | Execution | 2022-10-06 | 2026-02-07 | Yes | 82%
PBUT8.723002 | FAASt - EPC - Jobos TC (Substation) | Substation | Substation Rebuilds | FF | Pending Obligation | 42.9 | 2022-12-10 | Design | 2023-06-15 | Pending Obligation | Pending Obligation | 0%
PBUT8.723077 | FAASt - EPC - [Sabana Llana TC] (Substation) | Substation | Substation Rebuilds | FF | 100.69 | 125.5 | 2022-12-10 | Execution | 2023-06-16 | 2028-11-22 | No | 19%
PBUT8.723078 | FAASt - EPC - [San Juan SP TC] (Substation) | Substation | Substation Rebuilds | FF | 61.56 | 89.7 | 2022-12-10 | Execution | 2023-06-16 | 2028-09-13 | No | 2%
PBUT8.729286 | FAASt HV Equipment Replacement Group 2 (Substation) | Substation | Substation Rebuilds | FF | 15.4 | Program Cost Included in PBUT8.542758 | 2022-08-25 | Execution | 2023-08-23 | 2028-05-14 | No | 53%
PBUT8.743399 | FAASt [High Voltage Equipment Replacement - Group 3] (Substation) | Substation | Substation Rebuilds | FF | 17.3 | Program Cost Included in PBUT8.542758 | 2022-08-25 | Execution | 2024-01-29 | 2028-04-23 | No | 10%
PBUT8.825843 | FAAST [Guanica Transformer Replacement] (Substation) | Substation | Substation Rebuilds | FF | 2.3 | Program Cost Included in PBUT8.825843 | 2025-03-24 | Execution | 2025-04-09 | 2026-02-23 | No | 12%
PBUT8.956593 | FAASt [Factor Sect 8014 Transformer Replacement] (Substation) | Substation | Substation Rebuilds | FF | 3.7 | Program Cost Included in PBUT8.956593 | 2025-03-24 | Execution | 2025-06-23 | 2026-05-30 | No | 24%
PBUT8.957578 | FAASt [Costa Sur TC Underground Cable Failure Replacement on Transformer Lead Bank #2] (Substation) | Substation | Substation Rebuilds | FF | 1.1 | Program Cost Included in PBUT8.957578 | 2025-02-06 | Design | 2025-07-07 | 2026-06-30 | No | 0%
Annex A