## Attachment A (February 05 2026) (hidden)
Project Number | Project Title | Asset | Sub Asset | DSOW Submitted? | Total Estimate Incurred Cost | 428 Cost | 406 Cost | Total Estimated Cost
334191 | FAASt [Feeders - Mayaguez Short Term Group 3] (Distribution) | Distribution | Line Rebuild | Yes | 9689812.09 | 44675547 | 38483744 | 83159291
666894 | FAASt [San Juan Streetlighting] (Distribution) | Distribution | Streetlighting | Yes | 9279864.9 | 35282713 | 3532039 | 38814752
334293 | FAASt [Feeders - 7805-11- Mayaguez Short Term Group 4] (Distribution ) | Distribution | Line Rebuild | Yes | 5762106.74 | 47224922 | 45582792 | 92807714
547247 | Cambalache TC | Substation | Rebuild | Yes | 4499385.99 | 5463505.9 | 84733286.06 | 90196791.96
334472 | FAASt [Feeders - San Juan Short Term Group 2] (Distribution) | Distribution | Line Rebuild | Yes | 3857112.76 | 18783750 | 5366655 | 24150405
678794 | FAASt [Ponce Streetlighting] (Distribution) | Distribution | Streetlighting | Yes | 3450445.62 | 18852071 | 1444528 | 20296599
718971 | FAASt [Line 50300 (230kV) from Costa Sur Steam Plant to Aguirre Steam Plant] (Transmission) | Transmission | Line Rebuild | Yes | 3238497.73 | 15889643 | 901810364 | 917700007
436616 | FAASt [Feeders - Arecibo Short Term Group 1] (Distribution) | Distribution | Line Rebuild | Yes | 3049964.36 | 27194288 | 14494388 | 41688676
690483 | FAASt [Cayey Streetlighting] | Distribution | Streetlighting | Yes | 2980653.6 | 15993979 | 1319139 | 17313118
547343 | FAASt [Victoria TC 7008 Relocation] (Substation) | Substation | Rebuild | Yes | 2943473.75 | 6846444.9 | 54844288.98 | 61690733.88
699814 | FAASt [Juana Diaz Streetlighting] (Distribution) | Distribution | Streetlighting | Yes | 2857852.61 | 18680447 | 1909452 | 20589899
704931 | FAASt [Camuy Streetlighting] (Distribution) | Distribution | Streetlighting | Yes | 2832594.37 | 18265434 | 2269186 | 20534620
704862 | FAASt [Fajardo Streetlighting] (Distribution) | Distribution | Streetlighting | Yes | 2726930.5 | 13631005 | 1104923 | 14735928
678795 | FAASt [Arecibo Streetlighting] (Distribution) | Distribution | Streetlighting | Yes | 2701705.05 | 17274978 | 1527389 | 18802367
730541 | FAASt [Feeders - Caguas Short Term Group 8] (Distribution) | Distribution | Line Rebuild | Yes | 2623408 | 14523276 | 18671456 | 33194732
704757 | FAASt [Santa Isabel Streetlighting] (Distribution) | Distribution | Streetlighting | Yes | 2617616.95 | 9707069 | 820333 | 10527402
671396 | FAASt [Utuado Streetlighting] (Distribution) | Distribution | Streetlighting | Yes | 2599723.93 | 21135871 | 2911033 | 24046904
547344 | FAASt [Acacias 6801 TC Relocation] (Substation) | Substation | Rebuild | Yes | 2584284.14 | 8874442.51 | 42895135.02 | 51769577.53
688623 | FAASt [Automation Program Group 1A-8 Feeders] (Distribution) | Distribution | Automation | Yes | 2577701.87 | 1005286 | 1877045 | 2882331
546374 | FAASt [Feeders - 1620-02 - San Juan Short Term Group 3] (Distribution) | Distribution | Line Rebuild | Yes | 2563501.36 | 21058160 | 12777559 | 33835719
730586 | FAASt [Feeders - Ponce Short Term Group 1] (Distribution) | Distribution | Line Rebuild | Yes | 2500998.26 | 18969808 | 12719346 | 31689154
730824 | FAASt [Feeders - Ponce Short Term Group 2] (Distribution) | Distribution | Line Rebuild | Yes | 2464564.33 | 4115433 | 2840853 | 6956286
724603 | FAASt [Cabo Rojo Streetlighting] (Distribution) | Distribution | Streetlighting | Yes | 2396659.73 | 11029424 | 1044683 | 12074107
334476 | FAASt [Feeders - Carolina Short Term Group 2] (Distribution) | Distribution | Line Rebuild | Yes | 2350006.68 | 18285383 | 18767542 | 37052925
177191 | FAASt - 115kV Line 39000 - Aguas Buenas TC to Caguas TC (Transmission) | Transmission | Line Rebuild | Yes | 2347246.55 | 19407885 | 906873 | 20314758
701473 | FAASt [Canovanas Streetlighting] (Distribution) | Distribution | Streetlighting | Yes | 2151035.48 | 16995906 | 1574362 | 18570268
693543 | FAASt [Juncos Streetlighting] (Distribution) | Distribution | Streetlighting | Yes | 2135208.44 | 13468580 | 1643590 | 15112170
671400 | FAASt [Barceloneta Streetlighting] (Distribution) | Distribution | Streetlighting | Yes | 1880917.99 | 10053300 | 1109633 | 11162933
547243 | FAASt Egozcue - 1109 (Substation) | Substation | Rebuild | Yes | 1875010.93 | 13896445.76 | 6952342.26 | 20848788.02
958367 | FAASt [Distribution Feeder Rebuild #6603-01] (Distribution) | Distribution | Line Rebuild | Yes | 1860753.24 | 14474191.76 | 1172038.62 | 15646230.38
693788 | FAASt [Toa Alta Streetlighting] (Distribution) | Distribution | Streetlighting | Yes | 1831642.93 | 7465021 | 481369 | 7946390
546386 | FAASt [Feeders- El Yunque 2305 - Supply] (Distribution) | Distribution | Line Rebuild | Yes | 1640643.01 | 6564391 | 23252037 | 29816428
697183 | FAASt [Vega Baja Streetlighting] (Distribution) | Distribution | Streetlighting | Yes | 1589931.76 | 11188812 | 1117331 | 12306143
690721 | FAASt [Guayama Streetlighting] (Distribution) | Distribution | Streetlighting | Yes | 1577001.01 | 7045719 | 542958 | 7588677
698432 | FAASt [Hormigueros Streetlighting] (Distribution) | Distribution | Streetlighting | Yes | 1271901.7 | 8618625 | 968057 | 9586682
690480 | FAASt [Humacao Streetlighting] (Distribution) | Distribution | Streetlighting | Yes | 1203691.71 | 9318022 | 922000 | 10240022
547241 | FAASt Tallaboa 5402 | Substation | Rebuild | Yes | 1194229.01 | 10924436 | 5628609 | 16553045
551927 | 551927 SCADA Remote Access and RTU Replacements Group 3 | IT/OT | N/A | Yes | 1173137.64 | 19213188.6 | 3299617.88 | 22512806.48
686482 | FAASt [Isabela Streetlighting] (Distribution) | Distribution | Streetlighting | Yes | 1088990.74 | 8712288 | 733835 | 9446123
550986 | FAASt Condado - 1133 | Substation | Rebuild | Yes | 1063570.56 | 10649911 | 5427167 | 16077078
550894 | FAASt [Baldrich - 1422] (Substation) | Substation | Rebuild | Yes | 945895.54 | 973098 | 28669863 | 29642961
750503 | FAASt [25 MW BESS Installation and Integration - San Juan] (Substation) | Substation | Grid Modernization | Yes | 933346.51 | $ - | 55503065.56 | 55503065.56
750502 | FAASt [25 MW BESS Installation and Integration - Aguadilla] (Substation) | Substation | Grid Modernization | Yes | 917517.07 | $ - | 52720520.35 | 52720520.35
752972 | FAASt [4 x 25 MW BESS Interconnections Manati] (Substation) | Substation | Grid Modernization | Yes | 877404.95 | $ - | 57640005.67 | 57640005.67
754350 | Distribution Underground Circuit Feeders - San Juan Group 1 | Distribution | Underground | Yes | 830833.49 | $ - | 15123199.33 | 15123199.33
738671 | FAASt [25 MW BESS Installation and Integration - Barceloneta] (Substation) | Substation | Grid Modernization | Yes | 771738.9 | $ - | 55941767.5 | 55941767.5
754351 | ​Distribution Underground Circuit Feeders - San Juan Group 2 | Distribution | Underground | Yes | 722563.3 | $ - | 7066632.8 | 7066632.8
748180 | Transmission Advanced Sensors and Wide-Area Monitoring, Protection, and Control (WAMPAC) System | IT/OT | N/A | Yes | 578474.45 | $ - | 52804979.05 | 52804979.05
752277 | FAASt [Substation Ciales 8701] (Substation) | Substation | Rebuild | Yes | 436437.47 | 359175.24 | 4177144.45 | 4536319.69
745851 | FAASt [Automation Program Group 11] (Distribution) | Distribution | Automation | Yes | 255436.45 | 479854 | 1052298 | 1532152
805519 | 38kV Recloser TL 1900 Dos Bocas HP to San Sebastian TC | Transmission | Automation | Yes | 197629.44 | 708408.01 | 769393.29 | 1477801.3
817249 | FAASt [Pole and Conductor Repair -Caguas Group 7 - Phase 2 | Distribution | Pole and Conductors | No | 189461.99 | 5100000 | TBD | 5100000
745854 | Automation Program Group 9 | Distribution | Automation | Yes | 184886.52 | 546905 | 1164604 | 1711509
790446 | FAASt [Pole and Conductor Repair -Caguas Group 4 Phase 2 (Distribution) | Distribution | Pole and Conductors | Yes | 121427.65 | 4662521.3 | 28582.12 | 4691103.42
668669 | FAASt [Line 50500 230kV Mayaguez TC - Mora TC - Cambalache Power Plant] (Transmission) | Transmission | Line Rebuild | Yes | 73993.29 | 307465 | -1 | 307465
757945 | FAASt [Pole and Conductor Repair - Arecibo Group 3 - Phase 2] (Distribution) | Distribution | Pole and Conductors | Yes | 60037.43 | 2892589.5 | 15039.03 | 2907628.53
727691 | FAASt [Region 1 San Juan Transmission 38kV sensitive areas] (Vegetation) | Vegetation | N/A | Yes | 38329.46 | $ - | 44200121.5 | 44200121.5
740406 | FAASt[Region 1 San Juan Transmission 38kV - Non-Sensitive (Vegetation)] | Vegetation | N/A | Yes | 14548.58 | $ - | 5894785.29 | 5894785.29
741097 | Region 1 San Juan Substation/Telecom | Vegetation | N/A | Yes | 8787.49 | $ - | 1347191.63 | 1347191.63
741098 | Region 3 Bayamon Substation/Telecom | Vegetation | N/A | Yes | 8365.17 | $ - | 961518.65 | 961518.65
740410 | FAASt[Region 2 Arecibo Transmission 38kV - Non-Sensitive (Vegetation)] | Vegetation | N/A | Yes | 8296.79 | $ - | 5425376.76 | 5425376.76
740409 | FAASt[Region 4 Caguas Transmission 38kV - Non-Sensitive (Vegetation)] | Vegetation | N/A | Yes | 8084.15 | $ - | 23846154.02 | 23846154.02
740414 | FAASt [Region 6 Ponce Transmission 38kV - Non-Sensitive (Vegetation) | Vegetation | N/A | Yes | 7563.55 | $ - | 13788400.37 | 13788400.37
741102 | Region 5 Mayaguez Substation/Telecom | Vegetation | N/A | Yes | 7244.12 | $ - | 1516985.37 | 1516985.37
727694 | FAASt [Region 4 Caguas Transmission 38kV sensitive areas] (Vegetation) | Vegetation | N/A | Yes | 6393.72 | $ - | 76781710.48 | 76781710.48
741101 | Region 2 Arecibo Substation/Telecom | Vegetation | N/A | Yes | 6352.17 | $ - | 1058188.92 | 1058188.92
740411 | FAASt [Region 5 Mayaguez Transmission 38kV - Non-Sensitive (Vegetation)] | Vegetation | N/A | Yes | 5962.2 | $ - | 3777166.88 | 3777166.88
727562 | FAASt [Region 5 Mayaguez Transmission 38kV sensitive areas] (Vegetation) | Vegetation | N/A | Yes | 5599.08 | $ - | 84411128.06 | 84411128.06
727530 | FAASt [Region 6 Ponce Transmission 38kV sensitive areas] (Vegetation) | Vegetation | N/A | Yes | 5115.75 | $ - | 70421923.26 | 70421923.26
727540 | FAASt [Region 2 Arecibo Transmission 38kV sensitive areas] (Vegetation) | Vegetation | N/A | Yes | 4692.54 | $ - | 66510486.76 | 66510486.76
741104 | Region 6 Ponce Substation/Telecom | Vegetation | N/A | Yes | 4492.45 | $ - | 1992973.53 | 1992973.53
740408 | FAASt[Region 3 Bayamon Transmission 38kV - Non-Sensitive (Vegetation)] | Vegetation | N/A | Yes | 4225.96 | $ - | 11782088.78 | 11782088.78
741100 | Region 4 Caguas Substation/Telecom | Vegetation | N/A | Yes | 3733.86 | $ - | 1428325.86 | 1428325.86
727558 | FAASt [Region 3 Bayamon Transmission 38kV sensitive areas] (Vegetation) | Vegetation | N/A | Yes | 3251.49 | $ - | 16374246.76 | 16374246.76
|  |  |  | Total | 119281901.01 | 636789618.48 | 2093674845.85 | 2730464464.33

## Summary
Base Activities | FY25 Total Work
Insulation | 0
Hardware Replacement | 235
Pole Replacement | 11
Hot Spot Repairs | 36
Switch Repairs | 33
Inspections | 0
Other | 50
Total Work Completed | 365
Incremental Activities | March 2026 | April 2026 | FY26 Accumulated Work
Insulation | 0 | 0 | 0
Insulation & Hardware Replacement | 9 | 37 | 266
Pole Replacement | 0 | 0 | 12
Hot Spot Repairs | 0 | 0 | 25
Switch Repairs/Replacement | 0 | 0 | 1
Switch Repairs | 0 | 0 | 22
Inspections | 0 | 0 | 0
Other | 1 | 9 | 73
Total Work Completed | 10 | 46 | 399
Summary of Activities

## Incremental Activities (2) (hidden)
Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9 | Column10 | Column11 | Column12 | Column13 | Column14 | Column15
Incremental Activities | January 2026 | February 2026 | March 2026 | April 2026 | May 2026 | June 2026 | July 2026 | August 2026 | September 2026 | October 2026 | November 2026 | December 2026 | January 2027 | FY26 Accumulated Work
Insulation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Insulation & Hardware Replacement | 47 | 20 | 9 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 266
Pole Replacement | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12
Hot Spot Repairs | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25
Switch Repairs/Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
Switch Repairs | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22
Inspections | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other | 8 | 12 | 1 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73
Total Work Completed | 68 | 37 | 10 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 399

## Base Activities (2) (hidden)
Column1 | Column2
Base Activities | FY25 Total Work
Insulation | 0
Hardware Replacement | 235
Pole Replacement | 11
Hot Spot Repairs | 36
Switch Repairs | 33
Inspections | 0
Other | 50
Total Work Completed | 365

## Base Activities
Rank | Segment | Line | Activity | FY 2025 Total Work
1 | 1900-Dos Bocas HP-San Sebastian TC | 1900 | Insulation | -
|  |  | Hardware Replacement | -
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | 1
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 1
2 | 37500-Rio Bayamon Sect-Monacillos TC | 37500 | Insulation | -
|  |  | Hardware Replacement | -
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | 1
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 1
3 | 500-Ponce TC-Costa Sur SP-Canas TC | 500 | Insulation | -
|  |  | Hardware Replacement | 3
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | 4
|  |  | Total Work Completed |  | 7
4 | 13700-Mora TC-Isabela TO | 13700 | Insulation | -
|  |  | Hardware Replacement | 2
|  |  | Pole Replacement | 1
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | 2
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 5
5 | 3200-Monacillos TC-Venezuela SECT | 3200 | Insulation | -
|  |  | Hardware Replacement | -
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | 1
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 1
6 | 2200-Factor SECT-Barceloneta TC | 2200 | Insulation | -
|  |  | Hardware Replacement | 3
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | 1
|  |  | Inspections | -
|  |  | Other | 4
|  |  | Total Work Completed |  | 8
7 | 37400-Cambalache TC-Dos Bocas Hydro Plant | 37400 | Insulation | -
|  |  | Hardware Replacement | 3
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | 2
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | 1
|  |  | Total Work Completed |  | 6
8 | 3000-Monacillos TC-Barioa TO | 3000 | Insulation | -
|  |  | Hardware Replacement | 4
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | 1
|  |  | Switch Repairs | 1
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 6
9 | 7800-Dorado TC-Vega Alta SECT | 7800 | Insulation | -
|  |  | Hardware Replacement | 2
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | 2
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | 3
|  |  | Total Work Completed |  | 7
10 | 2700-Aguadilla Hospital Distrito SECT-Mora TC | 2700 | Insulation | -
|  |  | Hardware Replacement | -
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 0
11 | 300-Toro Negro 1 HP-Juana Diaz TC | 300 | Insulation | -
|  |  | Hardware Replacement | 1
|  |  | Pole Replacement | 1
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | 1
|  |  | Inspections | -
|  |  | Other | 1
|  |  | Total Work Completed |  | 4
12 | 7200-Baldrich SECT-Escuela Industrial TO | 7200 | Insulation | -
|  |  | Hardware Replacement | -
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 0
13 | 2300-Dos Bocas HP-Arecibo SECT | 2300 | Insulation | -
|  |  | Hardware Replacement | -
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 0
14 | 7900-Juana Diaz TC-La Rambla SECT | 7900 | Insulation | -
|  |  | Hardware Replacement | -
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 0
15 | 13500-Acacias TC-Cabo Rojo TO | 13500 | Insulation | -
|  |  | Hardware Replacement | 1
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | 1
|  |  | Inspections | -
|  |  | Other | 1
|  |  | Total Work Completed |  | 3
16 | 600-Caguas TC-Gautier Benitez SECT | 600 | Insulation | -
|  |  | Hardware Replacement | -
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 0
17 | 100-Jobos TC-Guayama TO | 100 | Insulation | -
|  |  | Hardware Replacement | -
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | 1
|  |  | Inspections | -
|  |  | Other | 2
|  |  | Total Work Completed |  | 3
18 | 10300-Canovanas TC-Canovanas SECT | 10300 | Insulation | -
|  |  | Hardware Replacement | -
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | 1
|  |  | Total Work Completed |  | 1
19 | 2300-Arecibo SECT-Cambalache TC | 2300 | Insulation | -
|  |  | Hardware Replacement | -
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 0
20 | 7100-Viaducto TC-Egozcue SECT | 7100 | Insulation | -
|  |  | Hardware Replacement | 39
|  |  | Pole Replacement | 2
|  |  | Hot Spot Repairs | 1
|  |  | Switch Repairs | 4
|  |  | Inspections | -
|  |  | Other | 10
|  |  | Total Work Completed |  | 56
21 | 11400-Barceloneta TC-Florida TO | 11400 | Insulation | -
|  |  | Hardware Replacement | 1
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | 1
|  |  | Switch Repairs | 1
|  |  | Inspections | -
|  |  | Other | 1
|  |  | Total Work Completed |  | 4
22 | 2000-Once de Agosto SECT-San Sebastian TC | 2000 | Insulation | -
|  |  | Hardware Replacement | 1
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | 2
|  |  | Switch Repairs | 3
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 6
23 | 5900-San Juan SP-Crematorio TO | 5900 | Insulation | -
|  |  | Hardware Replacement | -
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 0
24 | 3600-Llorens Torres SECT-Martin Peña TC | 3600 | Insulation | -
|  |  | Hardware Replacement | -
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 0
25 | 1000-San Anton TO-Villa Prades SECT | 1000 | Insulation | -
|  |  | Hardware Replacement | 1
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | 3
|  |  | Total Work Completed |  | 4
26 | 1200-San German SECT-San German TC | 1200 | Insulation | -
|  |  | Hardware Replacement | 1
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | 1
|  |  | Inspections | -
|  |  | Other | 2
|  |  | Total Work Completed |  | 4
27 | 2200-Vega Alta SECT-Dorado TC | 2200 | Insulation | -
|  |  | Hardware Replacement | -
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 0
28 | 7400-Hato Rey TC-Tres Monjitas SECT | 7400 | Insulation | -
|  |  | Hardware Replacement | -
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 0
29 | 5400-Rio Blanco HP-Daguao TC | 5400 | Insulation | -
|  |  | Hardware Replacement | -
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 0
30 | 2600-San Sebastian TC-Quebradillas SECT | 2600 | Insulation | -
|  |  | Hardware Replacement | -
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 0
31 | 3500-Monacillos TC-Las Lomas SECT | 3500 | Insulation | -
|  |  | Hardware Replacement | -
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 0
32 | 3300-Viaducto TC-Egozcue SECT | 3300 | Insulation | -
|  |  | Hardware Replacement | -
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 0
33 | 1000-Villa Prades SECT-Capuchinos SECT | 1000 | Insulation | -
|  |  | Hardware Replacement | 1
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 1
34 | 8900-Monacillos TC-Centro Médico SECT | 8900 | Insulation | -
|  |  | Hardware Replacement | 1
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | 1
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 2
35 | 13400-Acacias TC-San German SECT-LA PARGUERA SEC | 13400 | Insulation | -
|  |  | Hardware Replacement | 77
|  |  | Pole Replacement | 1
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | 1
|  |  | Total Work Completed |  | 79
36 | 36200-Monacillos TC-Juncos TC- | 36200 | Insulation | -
|  |  | Hardware Replacement | -
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | 2
|  |  | Total Work Completed |  | 2
37 | 3100-Monacillos TC-Sabana Llana TC | 3100 | Insulation | -
|  |  | Hardware Replacement | 2
|  |  | Pole Replacement | 2
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | 1
|  |  | Inspections | -
|  |  | Other | 2
|  |  | Total Work Completed |  | 7
38 | 1600-Leon SECT-Acacias TC | 1600 | Insulation | -
|  |  | Hardware Replacement | -
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | 1
|  |  | Inspections | -
|  |  | Other | 1
|  |  | Total Work Completed |  | 2
39 | 6500-Toro Negro 1 HP-Barranquitas TC | 6500 | Insulation | -
|  |  | Hardware Replacement | -
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 0
40 | 3000-Juncos TC-Rio Blanco HP | 3000 | Insulation | -
|  |  | Hardware Replacement | 42
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | 5
|  |  | Switch Repairs | 2
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 49
41 | 2200-Barceloneta TC-Manati TC | 2200 | Insulation | -
|  |  | Hardware Replacement | 20
|  |  | Pole Replacement | 1
|  |  | Hot Spot Repairs | 1
|  |  | Switch Repairs | 3
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 25
42 | 6500-Comerio TC-Aguas Buenas SECT | 6500 | Insulation | -
|  |  | Hardware Replacement | -
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | 1
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 1
43 | 5600-Añasco TC-Mayaguez GP | 5600 | Insulation | -
|  |  | Hardware Replacement | 2
|  |  | Pole Replacement | 1
|  |  | Hot Spot Repairs | 2
|  |  | Switch Repairs | 3
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 8
44 | 3600-Sabana Llana TC-Los Ángeles SECT | 3600 | Insulation | -
|  |  | Hardware Replacement | -
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 0
45 | 10000-Bayamon Pueblo SECT-Magnolia TO | 10000 | Insulation | -
|  |  | Hardware Replacement | 16
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | 2
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 18
46 | 4700-Canas TC-Adjuntas TO | 4700 | Insulation | -
|  |  | Hardware Replacement | -
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | 1
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | 3
|  |  | Total Work Completed |  | 4
47 | 3100-Canovanas SECT-Rio Grande TO | 3100 | Insulation | -
|  |  | Hardware Replacement | -
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 0
48 | 3700-Maunabo TC-Humacao TC | 3700 | Insulation | -
|  |  | Hardware Replacement | -
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 0
49 | 3600-Monacillos TC-Sabana Llana TC | 3600 | Insulation | -
|  |  | Hardware Replacement | 6
|  |  | Pole Replacement | 2
|  |  | Hot Spot Repairs | 7
|  |  | Switch Repairs | 2
|  |  | Inspections | -
|  |  | Other | 6
|  |  | Total Work Completed |  | 23
50 | 9400-Dorado TC-Toa Alta | 9400 | Insulation | -
|  |  | Hardware Replacement | 5
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | 6
|  |  | Switch Repairs | 3
Inspections
|  |  | Other | 2
|  |  | Total Work Completed |  | 16
51 | 700-Costa Sur SP-Yauco 2 HP | 700 | Insulation | -
|  |  | Hardware Replacement | 1
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | -
Inspections
|  |  | Other | -
|  |  | Total Work Completed |  | 1
|  |  | Total Work Completed | 365

## Incremental Activities
Hidden Columns
Rank | Segment | Line | Activity | FY 2026 Submitted Accumulated Work | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | FY 2026 Accumulated Work - Confirmation
1 | 1900-Dos Bocas HP-San Sebastian TC | 1900 | Insulation | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Insulation & Hardware Replacement | 7 | 2026-01-01: 0; 2026-02-01: 2; 2026-03-01: -; 2026-04-01: - | 9
|  |  | Pole Replacement | 1 | [13 empty] | 2 | bar: 2026-01-01 to 2026-04-01
|  |  | Hot Spot Repairs | 11 | [13 empty] | 11 | bar: 2026-01-01 to 2026-04-01
|  |  | Switch Repairs/Replacement | 1 | [13 empty] | 1 | bar: 2026-01-01 to 2026-04-01
|  |  | Inspections | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Other | 8 | 2026-01-01: -; 2026-02-01: 2; 2026-03-01: -; 2026-04-01: - | 10
|  |  | Total Work Completed | 28 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33
2 | 37500-Rio Bayamon Sect-Monacillos TC | 37500 | Insulation | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Insulation & Hardware Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Pole Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Hot Spot Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Switch Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Inspections | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Other | - | 2026-01-01: -; 2026-02-01: -; 2026-03-01: -; 2026-04-01: 2 | 2
|  |  | Total Work Completed | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
3 | 500-Ponce TC-Costa Sur SP-Canas TC | 500 | Insulation | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Insulation & Hardware Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Pole Replacement | 1 | [13 empty] | 1 | bar: 2026-01-01 to 2026-04-01
|  |  | Hot Spot Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Switch Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Inspections | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Other | 2 | [13 empty] | 2 | bar: 2026-01-01 to 2026-04-01
|  |  | Total Work Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
4 | 13700-Mora TC-Isabela TO | 13700 | Insulation | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Insulation & Hardware Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Pole Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Hot Spot Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Switch Repairs | 1 | [13 empty] | 1 | bar: 2026-01-01 to 2026-04-01
|  |  | Inspections | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Other | 2 | [13 empty] | 2 | bar: 2026-01-01 to 2026-04-01
|  |  | Total Work Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
5 | 3200-Monacillos TC-Venezuela SECT | 3200 | Insulation | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Insulation & Hardware Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Pole Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Hot Spot Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Switch Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Inspections | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Other | - | 2026-01-01: -; 2026-02-01: 5; 2026-03-01: -; 2026-04-01: - | 5
|  |  | Total Work Completed | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
6 | 2200-Factor SECT-Barceloneta TC | 2200 | Insulation | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Insulation & Hardware Replacement | 12 | 2026-01-01: 36; 2026-02-01: 9; 2026-03-01: 8; 2026-04-01: 35 | 100
|  |  | Pole Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Hot Spot Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Switch Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Inspections | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Other | - | 2026-01-01: -; 2026-02-01: 1; 2026-03-01: -; 2026-04-01: 2 | 3
|  |  | Total Work Completed | 12 | 36 | 10 | 8 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103
7 | 37400-Cambalache TC-Dos Bocas Hydro Plant | 37400 | Insulation | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Insulation & Hardware Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Pole Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Hot Spot Repairs | - | 2026-01-01: -; 2026-02-01: 2; 2026-03-01: -; 2026-04-01: - | 2
|  |  | Switch Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Inspections | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Other | 1 | [13 empty] | 1 | bar: 2026-01-01 to 2026-04-01
|  |  | Total Work Completed | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
8 | 3000-Monacillos TC-Barioa TO | 3000 | Insulation | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Insulation & Hardware Replacement | 6 | [13 empty] | 6 | bar: 2026-01-01 to 2026-04-01
|  |  | Pole Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Hot Spot Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Switch Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Inspections | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Other | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Total Work Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
9 | 7800-Dorado TC-Vega Alta SECT | 7800 | Insulation | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Insulation & Hardware Replacement | 6 | [13 empty] | 6 | bar: 2026-01-01 to 2026-04-01
|  |  | Pole Replacement | 1 | [13 empty] | 1 | bar: 2026-01-01 to 2026-04-01
|  |  | Hot Spot Repairs | 3 | [13 empty] | 3 | bar: 2026-01-01 to 2026-04-01
|  |  | Switch Repairs | [14 empty] | 1 | bar: 2026-01-01 to 2026-04-01
|  |  | Inspections | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Other | - | [13 empty] | 1 | bar: 2026-01-01 to 2026-04-01
|  |  | Total Work Completed | 10 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12
10 | 2700-Aguadilla Hospital Distrito SECT-Mora TC | 2700 | Insulation | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Insulation & Hardware Replacement | 2 | 2026-01-01: 5; 2026-02-01: -; 2026-03-01: -; 2026-04-01: - | 7
|  |  | Pole Replacement | 1 | 2026-01-01: 3; 2026-02-01: -; 2026-03-01: -; 2026-04-01: - | 4
|  |  | Hot Spot Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Switch Repairs | 4 | [13 empty] | 5 | bar: 2026-01-01 to 2026-04-01
|  |  | Inspections | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Other | 1 | 2026-01-01: 5; 2026-02-01: 1; 2026-03-01: 1; 2026-04-01: - | 8
|  |  | Total Work Completed | 8 | 14 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24
11 | 300-Toro Negro 1 HP-Juana Diaz TC | 300 | Insulation | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Insulation & Hardware Replacement | - | [13 empty] | 1 | bar: 2026-01-01 to 2026-04-01
|  |  | Pole Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Hot Spot Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Switch Repairs | - | [13 empty] | 1 | bar: 2026-01-01 to 2026-04-01
|  |  | Inspections | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Other | 1 | [13 empty] | 2 | bar: 2026-01-01 to 2026-04-01
|  |  | Total Work Completed | 1 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
12 | 7200-Baldrich SECT-Escuela Industrial TO | 7200 | Insulation | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Insulation & Hardware Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Pole Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Hot Spot Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Switch Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Inspections | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Other | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Total Work Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | 2300-Dos Bocas HP-Arecibo SECT | 2300 | Insulation | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Insulation & Hardware Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Pole Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Hot Spot Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Switch Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Inspections | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Other | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Total Work Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | 7900-Juana Diaz TC-La Rambla SECT | 7900 | Insulation | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Insulation & Hardware Replacement | 1 | [13 empty] | 1 | bar: 2026-01-01 to 2026-04-01
|  |  | Pole Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Hot Spot Repairs | 2 | [13 empty] | 2 | bar: 2026-01-01 to 2026-04-01
|  |  | Switch Repairs | 1 | [13 empty] | 1 | bar: 2026-01-01 to 2026-04-01
|  |  | Inspections | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Other | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Total Work Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
15 | 13500-Acacias TC-Cabo Rojo TO | 13500 | Insulation | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Insulation & Hardware Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Pole Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Hot Spot Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Switch Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Inspections | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Other | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Total Work Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | 600-Caguas TC-Gautier Benitez SECT | 600 | Insulation | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Insulation & Hardware Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Pole Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Hot Spot Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Switch Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Inspections | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Other | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Total Work Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | 100-Jobos TC-Guayama TO | 100 | Insulation | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Insulation & Hardware Replacement | 1 | [13 empty] | 1 | bar: 2026-01-01 to 2026-04-01
|  |  | Pole Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Hot Spot Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Switch Repairs | 1 | 2026-01-01: 2; 2026-02-01: -; 2026-03-01: -; 2026-04-01: - | 3
|  |  | Inspections | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Other | 2 | [13 empty] | 2 | bar: 2026-01-01 to 2026-04-01
|  |  | Total Work Completed | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
18 | 10300-Canovanas TC-Canovanas SECT | 10300 | Insulation | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Insulation & Hardware Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Pole Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Hot Spot Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Switch Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Inspections | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Other | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Total Work Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | 2300-Arecibo SECT-Cambalache TC | 2300 | Insulation | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Insulation & Hardware Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Pole Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Hot Spot Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Switch Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Inspections | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Other | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Total Work Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | 7100-Viaducto TC-Egozcue SECT | 7100 | Insulation | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Insulation & Hardware Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Pole Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Hot Spot Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Switch Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Inspections | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Other | - | [13 empty] | 1 | bar: 2026-01-01 to 2026-04-01
|  |  | Total Work Completed | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
21 | 11400-Barceloneta TC-Florida TO | 11400 | Insulation | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Insulation & Hardware Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Pole Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Hot Spot Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Switch Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Inspections | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Other | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Total Work Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | 2000-Once de Agosto SECT-San Sebastian TC | 2000 | Insulation | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Insulation & Hardware Replacement | 3 | [13 empty] | 5 | bar: 2026-01-01 to 2026-04-01
|  |  | Pole Replacement | 1 | [13 empty] | 1 | bar: 2026-01-01 to 2026-04-01
|  |  | Hot Spot Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Switch Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Inspections | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Other | 2 | [13 empty] | 3 | bar: 2026-01-01 to 2026-04-01
|  |  | Total Work Completed | 6 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
23 | 5900-San Juan SP-Crematorio TO | 5900 | Insulation | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Insulation & Hardware Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Pole Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Hot Spot Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Switch Repairs | 1 | [13 empty] | 1 | bar: 2026-01-01 to 2026-04-01
|  |  | Inspections | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Other | 2 | [13 empty] | 2 | bar: 2026-01-01 to 2026-04-01
|  |  | Total Work Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
24 | 3600-Llorens Torres SECT-Martin Peña TC | 3600 | Insulation | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Insulation & Hardware Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Pole Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Hot Spot Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Switch Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Inspections | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Other | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Total Work Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | 1000-San Anton TO-Villa Prades SECT | 1000 | Insulation | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Insulation & Hardware Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Pole Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Hot Spot Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Switch Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Inspections | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Other | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Total Work Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | 1200-San German SECT-San German TC | 1200 | Insulation | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Insulation & Hardware Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Pole Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Hot Spot Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Switch Repairs | [14 empty] | 1 | bar: 2026-01-01 to 2026-04-01
|  |  | Inspections | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Other | 1 | [13 empty] | 1 | bar: 2026-01-01 to 2026-04-01
|  |  | Total Work Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
27 | 2200-Vega Alta SECT-Dorado TC | 2200 | Insulation | 0 | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Insulation & Hardware Replacement | 2 | [13 empty] | 2 | bar: 2026-01-01 to 2026-04-01
|  |  | Pole Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Hot Spot Repairs | 1 | [13 empty] | 1 | bar: 2026-01-01 to 2026-04-01
|  |  | Switch Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Inspections | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Other | 2 | [13 empty] | 3 | bar: 2026-01-01 to 2026-04-01
|  |  | Total Work Completed | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
28 | 7400-Hato Rey TC-Tres Monjitas SECT | 7400 | Insulation | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Insulation & Hardware Replacement | 3 | [13 empty] | 3 | bar: 2026-01-01 to 2026-04-01
|  |  | Pole Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Hot Spot Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Switch Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Inspections | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Other | 1 | [13 empty] | 1 | bar: 2026-01-01 to 2026-04-01
|  |  | Total Work Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
29 | 5400-Rio Blanco HP-Daguao TC | 5400 | Insulation | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Insulation & Hardware Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Pole Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Hot Spot Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Switch Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Inspections | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Other | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Total Work Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | 2600-San Sebastian TC-Quebradillas SECT | 2600 | Insulation | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Insulation & Hardware Replacement | 3 | [13 empty] | 3 | bar: 2026-01-01 to 2026-04-01
|  |  | Pole Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Hot Spot Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Switch Repairs | 2 | [13 empty] | 2 | bar: 2026-01-01 to 2026-04-01
|  |  | Inspections | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Other | 3 | [13 empty] | 3 | bar: 2026-01-01 to 2026-04-01
|  |  | Total Work Completed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
31 | 3500-Monacillos TC-Las Lomas SECT | 3500 | Insulation | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Insulation & Hardware Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Pole Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Hot Spot Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Switch Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Inspections | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Other | - | [13 empty] | 1 | bar: 2026-01-01 to 2026-04-01
|  |  | Total Work Completed | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
32 | 3300-Viaducto TC-Egozcue SECT | 3300 | Insulation | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Insulation & Hardware Replacement | 15 | [13 empty] | 15 | bar: 2026-01-01 to 2026-04-01
|  |  | Pole Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Hot Spot Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Switch Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Inspections | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Other | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Total Work Completed | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15
33 | 1000-Villa Prades SECT-Capuchinos SECT | 1000 | Insulation | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Insulation & Hardware Replacement | 12 | [13 empty] | 12 | bar: 2026-01-01 to 2026-04-01
|  |  | Pole Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Hot Spot Repairs | 2 | [13 empty] | 2 | bar: 2026-01-01 to 2026-04-01
|  |  | Switch Repairs | 3 | [13 empty] | 3 | bar: 2026-01-01 to 2026-04-01
|  |  | Inspections | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Other | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Total Work Completed | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17
34 | 8900-Monacillos TC-Centro Médico SECT | 8900 | Insulation | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Insulation & Hardware Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Pole Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Hot Spot Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Switch Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Inspections | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Other | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Total Work Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | 13400-Acacias TC-San German SECT-LA PARGUERA SEC | 13400 | Insulation | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Insulation & Hardware Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Pole Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Hot Spot Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Switch Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Inspections | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Other | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Total Work Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | 36200-Monacillos TC-Juncos TC- | 36200 | Insulation | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Insulation & Hardware Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Pole Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Hot Spot Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Switch Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Inspections | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Other | 2 | [13 empty] | 2 | bar: 2026-01-01 to 2026-04-01
|  |  | Total Work Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
37 | 3100-Monacillos TC-Sabana Llana TC | 3100 | Insulation | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Insulation & Hardware Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Pole Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Hot Spot Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Switch Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Inspections | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Other | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Total Work Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | 1600-Leon SECT-Acacias TC | 1600 | Insulation | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Insulation & Hardware Replacement | 80 | 2026-01-01: 4; 2026-02-01: -; 2026-03-01: -; 2026-04-01: - | 84
|  |  | Pole Replacement | 1 | [13 empty] | 2 | bar: 2026-01-01 to 2026-04-01
|  |  | Hot Spot Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Switch Repairs | 1 | [13 empty] | 2 | bar: 2026-01-01 to 2026-04-01
|  |  | Inspections | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Other | 2 | [13 empty] | 2 | bar: 2026-01-01 to 2026-04-01
|  |  | Total Work Completed | 84 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90
39 | 6500-Toro Negro 1 HP-Barranquitas TC | 6500 | Insulation | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Insulation & Hardware Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Pole Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Hot Spot Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Switch Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Inspections | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Other | 5 | [13 empty] | 6 | bar: 2026-01-01 to 2026-04-01
|  |  | Total Work Completed | 5 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
40 | 3000-Juncos TC-Rio Blanco HP | 3000 | Insulation | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Insulation & Hardware Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Pole Replacement | - | [13 empty] | 1 | bar: 2026-01-01 to 2026-04-01
|  |  | Hot Spot Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Switch Repairs | - | [13 empty] | 1 | bar: 2026-01-01 to 2026-04-01
|  |  | Inspections | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Other | [14 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Total Work Completed |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
41 | 2200-Barceloneta TC-Manati TC | 2200 | Insulation | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Insulation & Hardware Replacement | - | [13 empty] | 1 | bar: 2026-01-01 to 2026-04-01
|  |  | Pole Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Hot Spot Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Switch Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Inspections | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Other | - | [13 empty] | 1 | bar: 2026-01-01 to 2026-04-01
|  |  | Total Work Completed |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
42 | 6500-Comerio TC-Aguas Buenas SECT | 6500 | Insulation | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Insulation & Hardware Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Pole Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Hot Spot Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Switch Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Inspections | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Other | 1 | [13 empty] | 2 | bar: 2026-01-01 to 2026-04-01
|  |  | Total Work Completed | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
43 | 5600-Añasco TC-Mayaguez GP | 5600 | Insulation | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Insulation & Hardware Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Pole Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Hot Spot Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Switch Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Inspections | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Other | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Total Work Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | 3600-Sabana Llana TC-Los Ángeles SECT | 3600 | Insulation | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Insulation & Hardware Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Pole Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Hot Spot Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Switch Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Inspections | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Other | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Total Work Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | 10000-Bayamon Pueblo SECT-Magnolia TO | 10000 | Insulation | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Insulation & Hardware Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Pole Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Hot Spot Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Switch Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Inspections | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Other | 1 | [13 empty] | 1 | bar: 2026-01-01 to 2026-04-01
|  |  | Total Work Completed | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
46 | 4700-Canas TC-Adjuntas TO | 4700 | Insulation | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Insulation & Hardware Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Pole Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Hot Spot Repairs | 2 | [13 empty] | 2 | bar: 2026-01-01 to 2026-04-01
|  |  | Switch Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Inspections | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Other | 1 | [13 empty] | 1 | bar: 2026-01-01 to 2026-04-01
|  |  | Total Work Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
47 | 3100-Canovanas SECT-Rio Grande TO | 3100 | Insulation | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Insulation & Hardware Replacement | - | 2026-01-01: -; 2026-02-01: 9; 2026-03-01: -; 2026-04-01: 1 | 10
|  |  | Pole Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Hot Spot Repairs | - | 2026-01-01: -; 2026-02-01: 2; 2026-03-01: -; 2026-04-01: - | 2
|  |  | Switch Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Inspections | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Other | 2 | [13 empty] | 3 | bar: 2026-01-01 to 2026-04-01
|  |  | Total Work Completed | 2 | 0 | 11 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15
48 | 3700-Maunabo TC-Humacao TC | 3700 | Insulation | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Insulation & Hardware Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Pole Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Hot Spot Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Switch Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Inspections | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Other | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Total Work Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | 3600-Monacillos TC-Sabana Llana TC | 3600 | Insulation | - | [13 empty] | 0 | 399 | bar: 2026-01-01 to 2026-04-01
|  |  | Insulation & Hardware Replacement | - | [13 empty] | 0 | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Pole Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Hot Spot Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Switch Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Inspections | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Other | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Total Work Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | 9400-Dorado TC-Toa Alta | 9400 | Insulation | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Insulation & Hardware Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Pole Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Hot Spot Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Switch Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Inspections | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Other | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Total Work Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
51 | 700-Costa Sur SP-Yauco 2 HP | 700 | Insulation | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Insulation & Hardware Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Pole Replacement | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Hot Spot Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Switch Repairs | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Inspections | - | [13 empty] | 0 | bar: 2026-01-01 to 2026-04-01
|  |  | Other | 1 | [13 empty] | 2 | bar: 2026-01-01 to 2026-04-01
|  |  | Total Work Completed | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
|  |  |  | 296 | [13 empty] | 399

## Sheet1 (hidden)
FY 2026 Accumulated Work
-
9
2
11
1
2
25
50
-
-
-
-
-
-
-
0
-
-
1
-
-
-
2
3
-
-
-
-
1
-
2
3
-
-
-
-
-
-
5
5
-
57
-
-
-
-
1
58
-
-
-
2
-
-
1
3
-
6
-
-
-
-
-
6
-
6
1
3
1
-
-
11
-
7
4
-
6
-
1
18
-
1
-
-
1
-
1
3
-
-
-
-
-
-
-
0
-
-
-
-
-
-
-
0
-
1
-
1
1
-
-
3
-
-
-
-
-
-
-
0
-
-
-
-
-
-
-
0
-
1
-
-
3
-
2
6
-
-
-
-
-
-
-
0
-
-
-
-
-
-
-
0
-
-
-
-
-
-
1
1
-
-
-
-
-
-
-
0
-
3
1
-
-
-
2
6
-
-
-
-
1
-
2
3
-
-
-
-
-
-
-
0
-
-
-
-
-
-
-
0
-
-
-
-
1
-
1
2
#REF!
2
-
1
-
-
3
#REF!
-
3
-
-
-
-
1
4
-
-
-
-
-
-
-
0
-
3
-
-
1
-
3
7
-
-
-
-
-
-
1
1
-
15
-
-
-
-
-
15
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
-
-
-
-
-
-
-
0
-
-
-
-
-
-
-
0
-
-
-
-
-
-
2
2
-
-
-
-
-
-
-
0
-
84
2
-
1
-
2
89
-
-
-
-
-
-
5
5
-
1
1
-
-
-
-
2
-
1
-
-
-
-
1
2
-
-
-
-
-
-
2
2
-
-
-
-
-
-
-
0
-
-
-
-
-
-
-
0
-
-
-
-
-
-
1
1
-
-
-
2
-
-
1
3
-
9
-
2
-
-
1
12
-
-
-
-
-
-
-
0
-
-
-
-
-
-
-
0
-
-
-
-
-
-
-
0
-
-
-
-
-
-
1
1
#REF!