## Attachment A
# | Current Project Status | Project # | Endorsed by PREPA (Y/N) | Activated by FEMA (Y/N) | Title | Asset | Sub Asset | Date Submitted to PREPA | Date Endorsed by PREPA | Date Project Activated by FEMA | Obligated (Yes / No) | 428 Estimate (Without the A&E and E&M) | 406 Estimate (Without the A&E and E&M) | 428 A&E Estimate-PW 9510 | 406 A&E Estimate -PW 9510 | 428 E&M Estimate -PW 10710 | 406 E&M Estimate -PW 10710 | Expected Total Project Cost | Total 428 Estimate Cost | Total 406 Estimate Cost | Comment
1 | Active | 1068053 | Yes | Yes | Line 8700 – Costa Sur Power Plant to Garzas 2 HP / Garzas 1 HP | Transmission | Line Rebuild | 2026-05-19 | 2026-05-19 | 2026-05-20 | No | 31681262.15 | 0 | 4873900 | 0 | 0 | 0 | 36555162.15 | 36555162.15 | 0 | As part of recent coordination efforts PREPA requested T-line 1100 be taken into consideration by LUMA for reactivation. After internal discussion and evaluation LUMA presented the repair of T-Line 8700 instead of T-Line 1100 and PREPA concurred. The solution for T-Line 8700 will be submitted to FEMA HM for consideration as Hazard Mitigation to the system for a Black Start inclusion of the hidroelectric plants
2 | Active | 1068056 | Yes | Yes | Aguadilla Sect 7003 Transformer 38/13.2-4.16, 22 MVA | Substation | Substation Component Replacements | 2026-03-20 | 2026-05-19 | 2026-05-20 | No | 5579634.34 | 311868.76 | 629419.11 | 31110.94 | 1938416.48 | 60347.84 | 8550797.47 | 8147469.93 | 403327.54 | New Project
3 | Active | 1068051 | Yes | Yes | Hogar Crea 1717 Transformer 115/13.2 kV, 44.8 MVA | Substation | Substation Component Replacements | 2026-03-27 | 2026-05-19 | 2026-05-20 | No | 6398013.45 | 188830.71 | 904549.27 | 23961.87 | 2064663.44 | 34482 | 9614500.74 | 9367226.16 | 247274.58 | New Project
4 | Active | 1068243 | Yes | Yes | Isla Grande TC Bank 2 Transformer 115/40 kV, 112 MVA | Substation | Substation Component Replacements | 2026-03-27 | 2026-05-19 | 2026-05-27 | No | 5001240.02 | 43376.06 | 862846.03 | 5789.88 | 2955632.71 | 9814.28 | 8878698.98 | 8819718.76 | 58980.22 | New Project
5 | Active | 1068057 | Yes | Yes | Quebradillas 7402 Transformer 38/13.2-4.16, 22 MVA | Substation | Substation Component Replacements | 2026-03-20 | 2026-05-19 | 2026-05-20 | No | 4522746.03 | 111790.07 | 559970.38 | 11194.81 | 1878676.91 | 16521.12 | 7100899.32 | 6961393.32 | 139506 | New Project
6 | Active | 1068052 | Yes | Yes | Rincon 7301 Transformer 38/13.2-4.16, 22 MVA | Substation | Substation Component Replacements | 2026-03-20 | 2026-05-19 | 2026-05-20 | No | 5756093.73 | 330484.121 | 658093.86 | 30072.85 | 2034277.28 | 25621.12 | 8834642.961 | 8448464.87 | 386178.091 | New Project
7 | Active | 1068054 | Yes | Yes | Santa Isabel Sect 4401 Transformer 38/13.2-4.16, 22 MVA | Substation | Substation Component Replacements | 2026-03-20 | 2026-05-19 | 2026-05-20 | No | 7837106.38 | 431467.46 | 774387.34 | 38617.71 | 2241468.32 | 71267.84 | 11394315.05 | 10852962.04 | 541353.01 | New Project
8 | Pending Activation/Reactivation | Pending FAASt | Yes | No | Mobile Substations | Substation | TBD | Endorsed without submittal | 2026-07-03 | Pending Activation | No | 0 | 0 | 0 | 0 | 17709050 | 0 | 17709050 | 17709050 | 0 | New Project
9 | Pending Activation/Reactivation | Pending FAASt | Yes | No | TAShelix Mobile Platform Implementation | TBD | TBD | Endorsed without submittal | 2026-07-03 | Pending Activation | No | 0 | 1957950 | 0 | 0 | 0 | 0 | 1957950 | 0 | 1957950 | New Project
10 | Active | 1068050 | Yes | Yes | Fiber Optic Replacement Group 1 | Telecommunication | IT/OT | 2026-03-20 | 2026-05-19 | 2026-05-20 | No | 67811581.03 | 9902187.96 | 6835688.41 | 948496.8 | 108101.8 | 0 | 85606056 | 74755371.24 | 10850684.76 | Cost actualization due to new Estimate Template Revision: 1 (Ver. 21) update.
11 | Active | 666894 | Yes | Yes | FAASt [San Juan Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | 2026-06-12 | 2026-07-03 | 2026-07-15 | No | 28178017.76 | 2123472.21 | 6380570.04 | 123157.52 | 0 | 0 | 36805217.53 | 34558587.8 | 2246629.73 | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered.
12 | Active | 547247 | Yes | Yes | Cambalache TC Rebuild | Substation | Substation Rebuilds | 2026-03-27 | 2026-07-03 | 2026-07-15 | No | 4966986.47 | 62195402.17 | 344907.31 | 9217663.45 | 151612.12 | 13320220.44 | 90196791.96 | 5463505.9 | 84733286.06
13 | Active | 704793 | Yes | Yes | [Yauco Streetlighting] (Distribution | Distribution | Distribution Streetlighting | 2026-06-12 | 2026-07-03 | 2026-07-15 | No | 13232024.93 | 1588137.76 | 2540431.6 | 79529.34 | 0 | 0 | 17440123.63 | 15772456.53 | 1667667.1 | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered.
14 | Active | 704744 | Yes | Yes | [San Sebastian Streetlighting] (Distribution | Distribution | Distribution Streetlighting | 2026-06-12 | 2026-07-03 | 2026-07-15 | No | 21521273.585 | 1542129.95 | 4057973.95 | 94811.81 | 0 | 0 | 27216189.295 | 25579247.535 | 1636941.76 | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered.
15 | Active | 678794 | Yes | Yes | FAASt [Ponce Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | 2026-06-12 | 2026-07-03 | 2026-07-15 | No | 10968715.275 | 884181.41 | 1713141.92 | 51717 | 0 | 0 | 13617755.605 | 12681857.195 | 935898.41 | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered.
16 | Active | 690483 | Yes | Yes | FAASt [Cayey Streetlighting] | Distribution | Distribution Streetlighting | 2026-06-12 | 2026-07-03 | 2026-07-15 | No | 10596790.82 | 1275717.24 | 2435204.39 | 95954.76 | 0 | 0 | 14403667.21 | 13031995.21 | 1371672 | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered.
17 | Active | 699814 | Yes | Yes | FAASt [Juana Diaz Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | 2026-06-12 | 2026-07-03 | 2026-07-15 | No | 14011750.655 | 872747.53 | 2795912.01 | 55146.97 | 0 | 0 | 17735557.165 | 16807662.665 | 927894.5 | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered.
18 | Pending Activation/Reactivation | 704931 | Yes | No | FAASt [Camuy Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | 2026-06-12 | 2026-07-03 | Pending Activation | No | 14028036.5825 | 867189.9 | 1972441.141 | 107984.699 | 0 | 0 | 16975652.3225 | 16000477.7235 | 975174.599 | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered.
19 | Active | 678795 | Yes | Yes | FAASt [Arecibo Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | 2026-06-12 | 2026-07-03 | 2026-07-15 | No | 11879105.0925 | 800134.36 | 1902215.74 | 59360 | 0 | 0 | 14640815.1925 | 13781320.8325 | 859494.36 | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered.
20 | Active | 671396 | Yes | Yes | FAASt [Utuado Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | 2026-06-12 | 2026-07-03 | 2026-07-15 | No | 16760927.205 | 2851675.47 | 3319870.72 | 155072.6 | 0 | 0 | 23087545.995 | 20080797.925 | 3006748.07 | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered.
21 | Active | 1066734 | Yes | Yes | Acacias 6801 TC (Relocation) | Substation | Substation Rebuilds | 2026-01-22 | 2026-03-18 | 2026-04-21 | No | 65766025.0617 | 31538831.8413 | 2841208.2382 | 785561.5157 | 12378234.9672 | 3124060.0459 | 116433921.67 | 80985468.2671 | 35448453.4029
22 | Pending Activation/Reactivation | 724603 | Yes | No | FAASt [Cabo Rojo Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | 2026-06-12 | 2026-07-03 | Pending Activation | No | 7308020.08 | 517830.31 | 1689593.17 | 41489.51 | 0 | 0 | 9556933.07 | 8997613.25 | 559319.82 | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered.
23 | Active | 701473 | Yes | Yes | FAASt [Canovanas Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | 2026-06-12 | 2026-07-03 | 2026-07-15 | No | 11994894.83 | 1520521.43 | 2377385.56 | 89359.81 | 0 | 0 | 15982161.63 | 14372280.39 | 1609881.24 | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered.
24 | Active | 693543 | Yes | Yes | FAASt [Juncos Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | 2026-06-12 | 2026-07-03 | 2026-07-15 | No | 10994681.6975 | 685135.01 | 1631297.312 | 26436.06 | 0 | 0 | 13337550.0795 | 12625979.0095 | 711571.07 | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered.
25 | Active | 1066729 | Yes | Yes | Guaynabo Pueblo | Substation | Substation Rebuilds | 2026-01-16 | 2026-03-18 | 2026-04-21 | No | 9487047.4 | 4257510.71 | 2263654.35 | 576564.36 | 4962433.97 | 3961056.7649 | 25508267.5549 | 16713135.72 | 8795131.8349 | Project scope is being revised, cost is being assessed and will be informed once estimated
26 | Active | 671400 | Yes | Yes | FAASt [Barceloneta Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | 2026-06-12 | 2026-07-03 | 2026-07-15 | No | 7422038.0375 | 477869.14 | 1206563.5 | 50306 | 0 | 0 | 9156776.6775 | 8628601.5375 | 528175.14 | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered.
27 | Active | 693788 | Yes | Yes | FAASt [Toa Alta Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | 2026-06-12 | 2026-07-03 | 2026-07-15 | No | 4767387.52 | 197071.81 | 1162797.94 | 17891.57 | 0 | 0 | 6145148.84 | 5930185.46 | 214963.38 | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered.
28 | Pending Activation/Reactivation | 704929 | Yes | No | [San Lorenzo Streetlighting] (Distribution | Distribution | Distribution Streetlighting | 2026-06-12 | 2026-07-03 | Pending Activation | No | 13787578.6125 | 968406.72 | 2944605.83 | 60896.29 | 0 | 0 | 17761487.4525 | 16732184.4425 | 1029303.01 | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered.
29 | Active | 697183 | Yes | Yes | FAASt [Vega Baja Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | 2026-06-12 | 2026-07-03 | 2026-07-15 | No | 8602549.46 | 1056851.66 | 1621313.74 | 17891.57 | 0 | 0 | 11298606.43 | 10223863.2 | 1074743.23 | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered.
30 | Active | 690721 | Yes | Yes | FAASt [Guayama Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | 2026-06-12 | 2026-07-03 | 2026-07-15 | No | 4107291.015 | 305442.59 | 1011463.98 | 25642.92 | 0 | 0 | 5449840.505 | 5118754.995 | 331085.51 | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered.
31 | Pending Activation/Reactivation | 724828 | Yes | No | [Loiza Streetlighting] (Distribution | Distribution | Distribution Streetlighting | 2026-06-12 | 2026-07-03 | Pending Activation | No | 6213147.88 | 388351.58 | 1248099.37 | 14137.5 | 0 | 0 | 7863736.33 | 7461247.25 | 402489.08 | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered.
32 | Active | 698522 | Yes | Yes | [Vieques Streetlighting] (Distribution | Distribution | Distribution Streetlighting | 2026-06-12 | 2026-07-03 | 2026-07-15 | No | 3987957.0575 | 454616.91 | 810226.05 | 32120.4 | 0 | 0 | 5284920.4175 | 4798183.1075 | 486737.31 | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered.
33 | Active | 690480 | Yes | Yes | FAASt [Humacao Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | 2026-06-12 | 2026-07-03 | 2026-07-15 | No | 6455271.8825 | 488325.81 | 1006696.36 | 29209 | 0 | 0 | 7979503.0525 | 7461968.2425 | 517534.81 | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered.
34 | Active | 1066731 | Yes | Yes | SCADA Remote Access and RTU Replacements Group 3 | Telecommunication | IT/OT | 2026-01-22 | 2026-03-18 | 2026-04-21 | No | 18668671.07 | 3375608.8 | 2470554.28 | 425678.76 | 1293008.64 | 0 | 26233521.55 | 22432233.99 | 3801287.56
35 | Active | 686482 | Yes | Yes | FAASt [Isabela Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | 2026-06-12 | 2026-07-03 | 2026-07-15 | No | 6005455.39 | 671912.08 | 1332970.6 | 37797.8 | 0 | 0 | 8048135.87 | 7338425.99 | 709709.88 | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered.
36 | Active | 693615 | Yes | Yes | [Rio Grande Streetlighting] (Distribution | Distribution | Distribution Streetlighting | 2026-06-12 | 2026-07-03 | 2026-07-15 | No | 5347407.42 | 397032.05 | 1156399.63 | 21533.62 | 0 | 0 | 6922372.72 | 6503807.05 | 418565.67 | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered.
37 | Active | 750503 | Yes | Yes | FAASt [25 MW BESS Installation and Integration - San Juan] (Substation) | Substation | Grid Modernization | Endorsed without submittal | 2026-07-03 | 2026-07-15 | No | 0 | 24053536.03 | 0 | 3187811.29 | 0 | 28261718.24 | 55503065.56 | 0 | 55503065.56
38 | Active | 750502 | Yes | Yes | FAASt [25 MW BESS Installation and Integration - Aguadilla] (Substation) | Substation | Grid Modernization | Endorsed without submittal | 2026-07-03 | 2026-07-15 | No | 0 | 21118171.64 | 0 | 3340630.47 | 0 | 28261718.24 | 52720520.35 | 0 | 52720520.35
39 | Active | 752972 | Yes | Yes | FAASt [4 x 25 MW BESS Interconnections Manati] (Substation) | Substation | Grid Modernization | Endorsed without submittal | 2026-07-03 | 2026-07-15 | No | 0 | 23808829.62 | 0 | 3414922.97 | 0 | 30416253.08 | 57640005.67 | 0 | 57640005.67
40 | Pending Activation/Reactivation | 754350 | Yes | No | Distribution Underground Circuit Feeders - San Juan Group 1 | Distribution | Underground | Endorsed without submittal | 2026-07-03 | Pending Activation | No | 4310111.715 | 9577521.9267 | 362956.776 | 812115.7863 | 1512.3199 | 58980.4761 | 15123199 | 4674580.8109 | 10448618.1891 | Pending Operation Assessment, and design work has not yet been finalized. Further evaluation is required before finalizing the DSOW to be submitted for obligation and move the project forward.
41 | Active | 738671 | Yes | Yes | FAASt [25 MW BESS Installation and Integration - Barceloneta] (Substation) | Substation | Grid Modernization | Endorsed without submittal | 2026-07-03 | 2026-07-15 | No | 0 | 20318919.35 | 0 | 5211394.35 | 0 | 30411453.8 | 55941767.5 | 0 | 55941767.5
42 | Active | 1066979 | Yes | Yes | Esc Industrial Miguel Such (Metal-Clad) 1423 | Substation | Substation Rebuilds | 2026-03-20 | 2026-04-23 | 2026-04-28 | No | 3301739.68 | 1135704.94 | 1112050.13 | 0 | 6614733.66 | 4603565.8 | 16767794.21 | 11028523.47 | 5739270.74
43 | Active | 1068662 | Yes | Yes | [Aguas Buenas Streetlighting] (Distribution | Distribution | Distribution Streetlighting | 2026-05-01 | 2026-06-01 | 2026-06-04 | No | 11613361.45 | 585725.31 | 1646095.25 | 83021.58 | 0 | 0 | 13928203.59 | 13259456.7 | 668746.89 | Costs updated based on the latest DSOW submission
44 | Active | 679035 | Yes | Yes | Telecomm Infrastructure Group A | Telecommunication | IT/OT | 2026-03-27 | 2026-07-03 | 2026-07-15 | No | 6440145.54 | 15927.16 | 1756408.47 | 4175.18 | 2800 | 0 | 8219456.35 | 8199354.01 | 20102.34
45 | Active | 1066737 | Yes | Yes | Distribution Pole and Conductor Repair - Caguas Group 5 - Phase 2 | Distribution | Distribution Pole and Conductor Repair | 2026-01-16 | 2026-03-18 | 2026-04-21 | Yes | 7591896.49 | 32126 | 673492.23 | 20229.46 | 515199.89 | 211384.11 | 9044328.18 | 8780588.61 | 263739.57 | Design is 100% completed, and the DSOW package has been completed. Costs updated based on the latest DSOW submission. Project obligated by FEMA on 7/8/2026.
46 | Pending Activation/Reactivation | 748180 | Yes | No | Transmission Advanced Sensors and Wide-Area Monitoring, Protection, and Control (WAMPAC) System | Telecommunication | IT/OT | 2026-03-20 | 2026-04-23 | Pending Activation | No | 0 | 47130973.41 | 0 | 5250645.64 | 0 | 423360 | 52804979.05 | 0 | 52804979.05
47 | Active | 1068667 | Yes | Yes | [Moca Streetlighting] (Distribution | Distribution | Distribution Streetlighting | 2026-03-20 | 2026-06-01 | 2026-06-04 | No | 18412055.33 | 976458.2 | 2533607.94 | 134366.43 | 0 | 0 | 22056487.9 | 20945663.27 | 1110824.63 | Costs updated based on the latest DSOW submission
48 | Active | 1068665 | Yes | Yes | [Guayanilla Streetlighting] (Distribution | Distribution | Distribution Streetlighting | 2026-05-01 | 2026-06-01 | 2026-06-04 | No | 7924363.09 | 412336.03 | 1106363.96 | 57568.51 | 0 | 0 | 9500631.59 | 9030727.05 | 469904.54 | Costs updated based on the latest DSOW submission
49 | Active | 704805 | Yes | Yes | Telecomm Infrastructure Group D | Telecommunication | IT/OT | 2026-03-27 | 2026-07-03 | 2026-07-15 | No | 5297451.62 | 18959.16 | 683790.17 | 2498.07 | 0 | 0 | 6002699.02 | 5981241.79 | 21457.23
50 | Active | 1068673 | Yes | Yes | [Sabana Grande Streetlighting] (Distribution | Distribution | Distribution Streetlighting | 2026-05-01 | 2026-06-01 | 2026-06-04 | No | 11018893.74 | 636889.83 | 1536485.07 | 88808.54 | 0 | 0 | 13281077.18 | 12555378.81 | 725698.37 | Costs updated based on the latest DSOW submission
51 | Active | 1068664 | Yes | Yes | [Ciales Streetlighting] (Distribution | Distribution | Distribution Streetlighting | 2026-05-01 | 2026-06-01 | 2026-06-04 | No | 11225480.68 | 682982.51 | 1532416.66 | 93235.54 | 0 | 0 | 13534115.39 | 12757897.34 | 776218.05 | Costs updated based on the latest DSOW submission
52 | Active | 800394 | Yes | Yes | Automation Program Group 39 (Distribution) | Distribution | Automation | 2026-03-20 | 2026-07-03 | 2026-07-15 | No | 1256040 | 395420 | 116300 | 69780 | 162820 | 325640 | 2326000 | 1535160 | 790840 | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (11) 3PH Reclosers, (17) 1ph reclosers, (18) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions.
53 | Active | 1068671 | Yes | Yes | [Quebradillas Streetlighting] (Distribution | Distribution | Distribution Streetlighting | 2026-05-01 | 2026-06-01 | 2026-06-04 | No | 10751415.1 | 550706.35 | 1511148.92 | 77403.68 | 0 | 0 | 12890674.05 | 12262564.02 | 628110.03 | Costs updated based on the latest DSOW submission
54 | Active | 1064452 | Yes | Yes | Transmission Priority Pole Replacement Program Line 800 Comsat Sect –Cidra Sect (Active) | Transmission | Transmission Priority Pole Replacements | 2026-01-16 | 2026-01-26 | 2026-01-26 | Yes | 609182.23 | 2812.61 | 110189.24 | 1928.4 | 52018.89 | 8792.11 | 784923.48 | 771390.36 | 13533.12
55 | Active | 1068666 | Yes | Yes | [Lares Streetlighting] (Distribution | Distribution | Distribution Streetlighting | 2026-05-01 | 2026-06-01 | 2026-06-04 | No | 12231124.33 | 631320.8 | 1563494.51 | 80701.22 | 0 | 0 | 14506640.86 | 13794618.84 | 712022.02 | Costs updated based on the latest DSOW submission
56 | Active | 1068669 | Yes | Yes | [Patillas Streetlighting] (Distribution | Distribution | Distribution Streetlighting | 2026-05-01 | 2026-06-01 | 2026-06-04 | No | 8607983.82 | 358025.92 | 1167539.54 | 48560.66 | 0 | 0 | 10182109.94 | 9775523.36 | 406586.58 | Costs updated based on the latest DSOW submission
57 | Active | 1068670 | Yes | Yes | [Penuelas Streetlighting] (Distribution | Distribution | Distribution Streetlighting | 2026-05-01 | 2026-06-01 | 2026-06-04 | No | 8122750.35 | 357444.72 | 1159987.24 | 51045.69 | 0 | 0 | 9691228 | 9282737.59 | 408490.41 | Costs updated based on the latest DSOW submission
58 | Active | 1066741 | Yes | Yes | Distribution Pole and Conductor Repair – Caguas Group 7 – Phase 2 | Distribution | Distribution Pole and Conductor Repair | 2026-01-16 | 2026-03-18 | 2026-04-21 | Yes | 5614901.87 | 23477.61 | 498530.84 | 14731.95 | 388892.2 | 153938.8 | 6694473.27 | 6502324.91 | 192148.36 | Design is 100% completed, and the DSOW package has been completed. Costs updated based on the latest DSOW submission. Project obligated by FEMA on 7/8/2026.
59 | Active | 1066740 | Yes | Yes | Distribution Pole and Conductor Repair – Caguas Group 4 – Phase 2 | Distribution | Distribution Pole and Conductor Repair | 2026-01-16 | 2026-03-18 | 2026-04-21 | Yes | 3867419.78 | 16119.41 | 342713.17 | 10132.71 | 258899.2 | 105879.8 | 4601164.07 | 4469032.15 | 132131.92 | Design is 100% completed, and the DSOW package has been completed. Costs updated based on the latest DSOW submission. Project obligated by FEMA on 7/8/2026.
60 | Active | 1066980 | Yes | Yes | TPole 5900 San Juan SP to Crematorio TO | Transmission | Transmission Priority Pole Replacements | 2026-03-20 | 2026-03-18 | 2026-04-28 | No | 407830.94 | 1921.02 | 77598.93 | 1382.15 | 40781.7 | 6101.3 | 535616.04 | 526211.57 | 9404.47
61 | Active | 1066730 | Yes | Yes | Transmission Priority Pole Replacement Program Line 16500 Fajardo TC-Dos Marinas | Transmission | Transmission Priority Pole Replacements | 2026-01-16 | 2026-03-18 | 2026-04-21 | No | 212650.88 | 381.28 | 48267.18 | 305.98 | 37102.11 | 1220.26 | 299927.69 | 298020.17 | 1907.52
62 | Active | 1066739 | Yes | Yes | Distribution Pole and Conductor Repair - Arecibo Group 3 – Phase 2 | Distribution | Distribution Pole and Conductor Repair | 2026-01-16 | 2026-03-18 | 2026-04-21 | No | 2557027.99 | 10609.31 | 226654.03 | 6647.33 | 173097.79 | 69460.21 | 3043496.66 | 2956779.81 | 86716.85 | Design is 100% completed, and the DSOW package has been completed. Costs updated based on the latest DSOW submission. Pending FEMA obligation.
63 | Active | 753787 | Yes | Yes | TPole 13700 Mora TC to Isabela TO | Transmission | Transmission Priority Pole Replacements | 2026-03-27 | 2026-07-03 | 2026-07-15 | No | 591148.31 | 7196.15 | 103198.13 | 1529 | 35991.1 | 2143.44 | 741206.13 | 730337.54 | 10868.59 | Project Not Obligated
64 | Pending Activation/Reactivation | 727691 | Yes | No | FAASt [Region 1 San Juan Transmission 38kV sensitive areas] (Vegetation) - Group C | Vegetation | Vegetation-TL | 2026-06-26 | 2026-07-03 | Pending Activation | No | 788376.99 | 8663674.704 | 6629.484 | 72765.402 | 0 | 0 | 9531446.58 | 795006.474 | 8736440.106 | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800.
65 | Active | 753785 | Yes | Yes | TPole 3300 San Gerardo Sect to Venezuela Sect | Transmission | Transmission Priority Pole Replacements | 2026-03-27 | 2026-07-03 | 2026-07-15 | No | 299085.29 | 81090.53 | 55226.85 | 14556.86 | 12296.95 | 1013.73 | 463270.21 | 366609.09 | 96661.12 | Project Not Obligated
66 | Active | 1066738 | Yes | Yes | Distribution Pole and Conductor Repair - Caguas Group 6 - Phase 2 | Distribution | Distribution Pole and Conductor Repair | 2026-01-16 | 2026-03-18 | 2026-04-21 | No | 7539064.69 | 31745.7 | 668572.54 | 19977.94 | 509451.1 | 208755.9 | 8977567.87 | 8717088.33 | 260479.54 | Design is 100% completed, and the DSOW package has been completed. Costs updated based on the latest DSOW submission. Pending FEMA obligation.
67 | Active | 1068640 | Yes | Yes | FAASt[Region 1 San Juan Transmission 38kV - Non-Sensitive (Vegetation)] - Group B | Vegetation | Vegetation-TL | 2026-04-02 | 2026-06-01 | 2026-06-04 | No | 281264.03 | 3116841.11 | 2365.12 | 25959.59 | 0 | 0 | 3426429.85 | 283629.15 | 3142800.7
68 | Active | 1068647 | Yes | Yes | FAASt[Region 2 Arecibo Transmission 38kV - Non-Sensitive (Vegetation)]- Group B | Vegetation | Vegetation-TL | 2026-04-02 | 2026-06-01 | 2026-06-04 | No | 21352.15 | 236614.32 | 179.55 | 1970.74 | 0 | 0 | 260116.76 | 21531.7 | 238585.06
69 | Active | 1068646 | Yes | Yes | FAASt[Region 4 Caguas Transmission 38kV - Non-Sensitive (Vegetation)]- Group B | Vegetation | Vegetation-TL | 2026-04-02 | 2026-06-01 | 2026-06-04 | No | 715385.11 | 7927576.7 | 6901584.83 | 66028.4 | 0 | 0 | 15610575.04 | 7616969.94 | 7993605.1
70 | Active | 1068649 | Yes | Yes | FAASt [Region 6 Ponce Transmission 38kV - Non-Sensitive (Vegetation)- Group B | Vegetation | Vegetation-TL | 2026-04-02 | 2026-06-01 | 2026-06-04 | No | 141749.28 | 1570801.41 | 1191.98 | 13083.11 | 0 | 0 | 1726825.78 | 142941.26 | 1583884.52
71 | Pending Activation/Reactivation | 727694 | Yes | No | FAASt [Region 4 Caguas Transmission 38kV sensitive areas] (Vegetation) - Group C | Vegetation | Vegetation-TL | 2026-06-26 | 2026-07-03 | Pending Activation | No | 437628.366 | 4809208.998 | 3680.034 | 40392.096 | 0 | 0 | 5290909.494 | 441308.4 | 4849601.094 | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800.
72 | Active | 1068648 | Yes | Yes | FAASt [Region 5 Mayaguez Transmission 38kV - Non-Sensitive (Vegetation)]- Group B | Vegetation | Vegetation-TL | 2026-04-02 | 2026-06-01 | 2026-06-04 | No | 799358.09 | 8858127.48 | 6721.82 | 73778.93 | 0 | 0 | 9737986.32 | 806079.91 | 8931906.41 | No comments. Projects already submitted to PREPA.
73 | Pending Activation/Reactivation | 727562 | Yes | No | FAASt [Region 5 Mayaguez Transmission 38kV sensitive areas] (Vegetation) - Group C | Vegetation | Vegetation-TL | 2026-06-26 | 2026-07-03 | Pending Activation | No | 1232141.82 | 13540319.136 | 10361.1 | 113723.898 | 0 | 0 | 14896545.954 | 1242502.92 | 13654043.034 | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800.
74 | Pending Activation/Reactivation | 727530 | Yes | No | FAASt [Region 6 Ponce Transmission 38kV sensitive areas] (Vegetation) - Group C | Vegetation | Vegetation-TL | 2026-06-26 | 2026-07-03 | Pending Activation | No | 1367036.856 | 15022714.938 | 11495.436 | 126174.408 | 0 | 0 | 16527421.638 | 1378532.292 | 15148889.346 | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800.
75 | Pending Activation/Reactivation | 727540 | Yes | No | FAASt [Region 2 Arecibo Transmission 38kV sensitive areas] (Vegetation) - Group C | Vegetation | Vegetation-TL | 2026-06-26 | 2026-07-03 | Pending Activation | No | 1105536.432 | 12149020.278 | 9296.478 | 102038.502 | 0 | 0 | 13365891.69 | 1114832.91 | 12251058.78 | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800.
76 | Active | 1068642 | Yes | Yes | FAASt[Region 3 Bayamon Transmission 38kV - Non-Sensitive (Vegetation)]- Group B | Vegetation | Vegetation-TL | 2026-04-02 | 2026-06-01 | 2026-06-04 | No | 622799.54 | 6901584.83 | 5237.14 | 57482.97 | 0 | 0 | 7587104.48 | 628036.68 | 6959067.8
77 | Pending Activation/Reactivation | 727558 | Yes | No | FAASt [Region 3 Bayamon Transmission 38kV sensitive areas] (Vegetation) - Group C | Vegetation | Vegetation-TL | 2026-06-26 | 2026-07-03 | Pending Activation | No | 793759.878 | 8722828.56 | 6674.742 | 73262.238 | 0 | 0 | 9596525.418 | 800434.62 | 8796090.798 | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800.
78 | Pending Activation/Reactivation | 698427 | Yes | No | [Maricao Streetlighting] (Distribution | Distribution | Distribution Streetlighting | 2026-06-12 | 2026-07-03 | Pending Activation | No | 4873133.615 | 921314.71 | 926826.7734 | 43337.3166 | 0 | 0 | 6764612.415 | 5799960.3884 | 964652.0266
79 | Pending Activation/Reactivation | 698432 | Yes | No | FAASt [Hormigueros Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | 2026-06-12 | 2026-07-03 | Pending Activation | No | 5999141.915 | 489811.44 | 1362869.66 | 17724.97 | 0 | 0 | 7869547.985 | 7362011.575 | 507536.41
80 | Pending Activation/Reactivation | 704757 | Yes | No | FAASt [Santa Isabel Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | 2026-06-12 | 2026-07-03 | Pending Activation | No | 8526009.33 | 383038.38 | 1562084.58 | 22536.63 | 0 | 0 | 10493668.92 | 10088093.91 | 405575.01
81 | Pending Activation/Reactivation | 704862 | Yes | No | FAASt [Fajardo Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | 2026-06-12 | 2026-07-03 | Pending Activation | No | 11073921.95 | 1052403.97 | 2150579.88 | 58676.25 | 0 | 0 | 14335582.05 | 13224501.83 | 1111080.22
82 | Pending Activation/Reactivation | Pending FAASt | Yes | No | 38kV Transmission Line 100 – Entire Line (Vegetation) | Vegetation | Vegetation-DL | Endorsed without submittal | 2026-07-03 | Pending Activation | No | 254933.33 | 2801526.9 | 2143.75 | 23529.76 | 0 | 0 | 3082133.74 | 257077.08 | 2825056.66
83 | Pending Activation/Reactivation | Pending FAASt | Yes | No | 38kV Transmission Line 200 – Entire Line (Vegetation) | Vegetation | Vegetation-DL | Endorsed without submittal | 2026-07-03 | Pending Activation | No | 155350.01 | 1707180.44 | 1306.34 | 14338.44 | 0 | 0 | 1878175.23 | 156656.35 | 1721518.88
84 | Pending Activation/Reactivation | Pending FAASt | Yes | No | 38kV Transmission Line 800 – Entire Line (Vegetation) | Vegetation | Vegetation-DL | Endorsed without submittal | 2026-07-03 | Pending Activation | No | 161271.17 | 1772249.71 | 1356.14 | 14884.95 | 0 | 0 | 1949761.97 | 162627.31 | 1787134.66
85 | Pending Activation/Reactivation | Pending FAASt | Yes | No | 38kV Transmission Line 1200 – Entire Line (Vegetation) | Vegetation | Vegetation-DL | Endorsed without submittal | 2026-07-03 | Pending Activation | No | 275711.27 | 3029860.81 | 2318.47 | 25447.51 | 0 | 0 | 3333338.06 | 278029.74 | 3055308.32
86 | Pending Activation/Reactivation | Pending FAASt | Yes | No | 38kV Transmission Line 1600 – Entire Line (Vegetation) | Vegetation | Vegetation-DL | Endorsed without submittal | 2026-07-03 | Pending Activation | No | 305424.77 | 3356390.15 | 2568.32 | 28190 | 0 | 0 | 3692573.24 | 307993.09 | 3384580.15
87 | Pending Activation/Reactivation | Pending FAASt | Yes | No | 38kV Transmission Line 2000 – Entire Line (Vegetation) | Vegetation | Vegetation-DL | Endorsed without submittal | 2026-07-03 | Pending Activation | No | 303594.6 | 3336277.81 | 2552.93 | 28021.09 | 0 | 0 | 3670446.43 | 306147.53 | 3364298.9
88 | Pending Activation/Reactivation | Pending FAASt | Yes | No | 38kV Transmission Line 2100 – Entire Line (Vegetation) | Vegetation | Vegetation-DL | Endorsed without submittal | 2026-07-03 | Pending Activation | No | 304778.83 | 3349291.67 | 2562.89 | 28130.39 | 0 | 0 | 3684763.78 | 307341.72 | 3377422.06
89 | Pending Activation/Reactivation | Pending FAASt | Yes | No | 38kV Transmission Line 2200 – Entire Line (Vegetation) | Vegetation | Vegetation-DL | Endorsed without submittal | 2026-07-03 | Pending Activation | No | 805386.91 | 8850600.91 | 6772.52 | 74335.38 | 0 | 0 | 9737095.72 | 812159.43 | 8924936.29
90 | Pending Activation/Reactivation | Pending FAASt | Yes | No | 38kV Transmission Line 2500 – Entire Line (Vegetation) | Vegetation | Vegetation-DL | Endorsed without submittal | 2026-07-03 | Pending Activation | No | 243413.96 | 2674937.64 | 2046.88 | 22466.54 | 0 | 0 | 2942865.02 | 245460.84 | 2697404.18
91 | Pending Activation/Reactivation | Pending FAASt | Yes | No | 38kV Transmission Line 2700 – Entire Line (Vegetation) | Vegetation | Vegetation-DL | Endorsed without submittal | 2026-07-03 | Pending Activation | No | 409745.04 | 4502791.99 | 3445.55 | 37818.53 | 0 | 0 | 4953801.11 | 413190.59 | 4540610.52
92 | Pending Activation/Reactivation | Pending FAASt | Yes | No | 38kV Transmission Line 3000 – Entire Line (Vegetation) | Vegetation | Vegetation-DL | Endorsed without submittal | 2026-07-03 | Pending Activation | No | 491241.88 | 5398381.47 | 4130.86 | 45340.51 | 0 | 0 | 5939094.72 | 495372.74 | 5443721.98
93 | Pending Activation/Reactivation | Pending FAASt | Yes | No | 38kV Transmission Line 3100 – Entire Line (Vegetation) | Vegetation | Vegetation-DL | Endorsed without submittal | 2026-07-03 | Pending Activation | No | 650144.58 | 7144603.49 | 5467.08 | 60006.86 | 0 | 0 | 7860222.01 | 655611.66 | 7204610.35
94 | Pending Activation/Reactivation | Pending FAASt | Yes | No | 38kV Transmission Line 3700 – Entire Line (Vegetation) | Vegetation | Vegetation-DL | Endorsed without submittal | 2026-07-03 | Pending Activation | No | 470248.63 | 5167681.42 | 3954.33 | 43402.88 | 0 | 0 | 5685287.26 | 474202.96 | 5211084.3
95 | Pending Activation/Reactivation | Pending FAASt | Yes | No | 38kV Transmission Line 3800 – Entire Line (Vegetation) | Vegetation | Vegetation-DL | Endorsed without submittal | 2026-07-03 | Pending Activation | No | 253749.1 | 2788513.05 | 2133.79 | 23420.45 | 0 | 0 | 3067816.39 | 255882.89 | 2811933.5
96 | Pending Activation/Reactivation | Pending FAASt | Yes | No | 38kV Transmission Line 4000 – Entire Line (Vegetation) | Vegetation | Vegetation-DL | Endorsed without submittal | 2026-07-03 | Pending Activation | No | 113148.21 | 1243414.15 | 951.47 | 10443.31 | 0 | 0 | 1367957.14 | 114099.68 | 1253857.46
97 | Pending Activation/Reactivation | Pending FAASt | Yes | No | 38kV Transmission Line 4800 – Entire Line (Vegetation) | Vegetation | Vegetation-DL | Endorsed without submittal | 2026-07-03 | Pending Activation | No | 428262.16 | 4706281.27 | 3601.27 | 39527.62 | 0 | 0 | 5177672.32 | 431863.43 | 4745808.89
98 | Pending Activation/Reactivation | Pending FAASt | Yes | No | 38kV Transmission Line 5300 – Entire Line (Vegetation) | Vegetation | Vegetation-DL | Endorsed without submittal | 2026-07-03 | Pending Activation | No | 166008.11 | 1824305.09 | 1395.97 | 15322.16 | 0 | 0 | 2007031.33 | 167404.08 | 1839627.25
99 | Pending Activation/Reactivation | Pending FAASt | Yes | No | 38kV Transmission Line 5400 – Entire Line (Vegetation) | Vegetation | Vegetation-DL | Endorsed without submittal | 2026-07-03 | Pending Activation | No | 288199.55 | 3167097.76 | 2423.48 | 26600.15 | 0 | 0 | 3484320.94 | 290623.03 | 3193697.91
100 | Pending Activation/Reactivation | Pending FAASt | Yes | No | 38kV Transmission Line 5600 – Entire Line (Vegetation) | Vegetation | Vegetation-DL | Endorsed without submittal | 2026-07-03 | Pending Activation | No | 293582.43 | 3226251.64 | 2468.74 | 27096.98 | 0 | 0 | 3549399.79 | 296051.17 | 3253348.62
101 | Pending Activation/Reactivation | Pending FAASt | Yes | No | 38kV Transmission Line 6500 – Entire Line (Vegetation) | Vegetation | Vegetation-DL | Endorsed without submittal | 2026-07-03 | Pending Activation | No | 447640.54 | 4919235.19 | 3764.22 | 41316.2 | 0 | 0 | 5411956.15 | 451404.76 | 4960551.39
[12 empty] | 667050285.2662 | 457886147.643 | 103954584.5145 | 37020842.2417 | 58521173.5471 | 144154770.7469 | 1468587803.9594 | 829526043.3278 | 639061760.6316
Attachment A