## Distribution Streetlighting
# | FAASt Number | Project Name | Expected Submission Date | Initial Obligation | Expected Final Cost | Expected Versioning Savings | Pending Action
1 | 679039 | Caguas Streetlighting (Distribution) | Submitted to COR3 on 6/19 | 73737224.58 | 21548249.75 | 52188974.83 | Comments from COR3 were received. The team is addressing the comments to move the projects to FEMA.
2 | 691702 | Trujillo Alto Streetlighting] (Distribution) | Submitted to COR3 on 6/19 | 25277347 | 9372449.51 | 15904897.49 | Comments from COR3 were received. The team is addressing the comments to move the projects to FEMA.
3 | 660437 | Manatí Streetlighting (Distribution) | Submitted to COR3 on 6/19 | 27067865 | 15060546 | 12007319 | Comments from COR3 were received. The team is addressing the comments to move the projects to FEMA.
4 | 659625 | Dorado Streetlighting (Distribution) | Submitted to COR3 on 6/19 | 22864972 | 11750650.44 | 11114321.56 | Comments from COR3 were received. The team is addressing the comments to move the projects to FEMA.
5 | 659623 | Cataño Streetlighting (Distribution) | Submitted to COR3 on 6/19 | 16996758 | 7249576.94 | 9747181.06 | Comments from COR3 were received. The team is addressing the comments to move the projects to FEMA.
6 | 690545 | Aguadilla Streetlighting (Distribution) | Submitted to COR3 on 6/19 | 19796809 | 9980273.49 | 9816535.51 | Comments from COR3 were received. The team is addressing the comments to move the projects to FEMA.
7 | 673504 | Gurabo Streetlighting (Distribution) | Jul-26 | 19208994 | 13326352 | 5882642 | The project is in the Engineering, Planning & Project Team Review step, pending review of the project and the addition/removal of items (primary poles). The cost included is from the latest submittal, changes in cost may ocurre when the review is completed.
8 | 659968 | San Germán Streetlighting (Distribution) | Jul-26 | 30849348 | 26194807 | 4654541 | The project is in the Engineering, Planning & Project Team Review step, pending review of the project and the addition/removal of items (primary poles). The cost included is from the latest submittal, changes in cost may ocurre when the review is completed.
9 | 542517 | Luquillo Streetlighting (Distribution) | Jul-26 | 8628667.29 | 4946319 | 3682348.29 | The project is in the Engineering, Planning & Project Team Review step, pending review of the project and the addition/removal of items (primary poles). The cost included is from the latest submittal, changes in cost may ocurre when the review is completed.
10 | 660227 | Hatillo Streetlighting (Distribution) | Jul-26 | 18570095.25 | 16131869 | 2438226.25 | The project is in the Engineering, Planning & Project Team Review step, pending review of the project and the addition/removal of items (primary poles). The cost included is from the latest submittal, changes in cost may ocurre when the review is completed.
11 | 542756 | Guánica Streetlighting (Distribution) | Aug-26 | 9687238 | 6817015 | 2870223 | The project is in the Engineering, Planning & Project Team Review step, pending review of the project and the addition/removal of items (primary poles). The cost included is from the latest submittal, changes in cost may ocurre when the review is completed.
12 | 698424 | Florida Streetlighting (Distribution) | Jul-26 | 9311841.53 | 7063699 | 2248142.53 | The project is in the Engineering, Planning & Project Team Review step, pending review of the project and the addition/removal of items (primary poles). The cost included is from the latest submittal, changes in cost may ocurre when the review is completed.
13 | 659715 | Aibonito Streetlighting (Distribution) | Aug-26 | 7074498 | 5738710 | 1335788 | The project is in the Engineering, Planning & Project Team Review step, pending review of the project and the addition/removal of items (primary poles). The cost included is from the latest submittal, changes in cost may ocurre when the review is completed.
14 | 542687 | Lajas Streetlighting (Distribution) | Aug-26 | 10278336.09 | 10510560 | -232223.91 | The project is in the Engineering, Planning & Project Team Review step, pending review of the project and the addition/removal of items (primary poles). The cost included is from the latest submittal, changes in cost may ocurre when the review is completed.
15 | 542690 | Maunabo Streetlighting (Distribution) | Aug-26 | 6199877.07 | 5640236 | 559641.07 | The project is in the Engineering, Planning & Project Team Review step, pending review of the project and the addition/removal of items (primary poles). The cost included is from the latest submittal, changes in cost may ocurre when the review is completed.
16 | 542688 | Aguada Streetlighting (Distribution) | Aug-26 | 17764494.34 | 17056591 | 707903.34 | The project is in the Engineering, Planning & Project Team Review step, pending review of the project and the addition/removal of items (primary poles). The cost included is from the latest submittal, changes in cost may ocurre when the review is completed.
17 | 660239 | Villalba Streetlighting (Distribution) | Aug-26 | 10190536.05 | 12489008.47 | -2298472.42 | The project is in the Engineering, Planning & Project Team Review step, pending review of the project and the addition/removal of items (primary poles). The cost included is from the latest submittal, changes in cost may ocurre when the review is completed.
Distribution Streetlighting

## Work Plan
WBS | Task Name | % Complete | Duration | Start | Finish
0 | Streetlight DSOW Submission | 19% | 151 days | Fri 5/1/26 | Fri 11/27/26
1 | 17 Underground Amendment Projects | 29% | 122 days | Fri 5/1/26 | Mon 10/19/26
1.1 | Distribution Streetlighting - Cataño | 77% | 65 days | Fri 5/1/26 | Thu 7/30/26
1.1.1 | Engineering FieldMaps Data | 100% | 12 days | Fri 5/1/26 | Mon 5/18/26
1.1.2 | EHP Review Data | 100% | 5 days | Tue 5/19/26 | Mon 5/25/26
1.1.3 | Reconciliation DSOW file | 100% | 12 days | Tue 5/26/26 | Wed 6/10/26
1.1.4 | Submitted to FFO/Appian | 100% | 6 days | Thu 6/11/26 | Thu 6/18/26
1.1.5 | COR3 Evaluation | 50% | 30 days | Fri 6/19/26 | Thu 7/30/26
1.2 | Distribution Streetlighting - Dorado | 77% | 65 days | Fri 5/1/26 | Thu 7/30/26
1.2.1 | Engineering FieldMaps Data | 100% | 12 days | Fri 5/1/26 | Mon 5/18/26
1.2.2 | EHP Review Data | 100% | 5 days | Tue 5/19/26 | Mon 5/25/26
1.2.3 | Reconciliation DSOW file | 100% | 12 days | Tue 5/26/26 | Wed 6/10/26
1.2.4 | Submitted to FFO/Appian | 100% | 6 days | Thu 6/11/26 | Thu 6/18/26
1.2.5 | COR3 Evaluation | 50% | 30 days | Fri 6/19/26 | Thu 7/30/26
1.3 | Distribution Streetlighting - Manati | 77% | 65 days | Fri 5/1/26 | Thu 7/30/26
1.3.1 | Engineering FieldMaps Data | 100% | 12 days | Fri 5/1/26 | Mon 5/18/26
1.3.2 | EHP Review Data | 100% | 5 days | Tue 5/19/26 | Mon 5/25/26
1.3.3 | Reconciliation DSOW file | 100% | 12 days | Tue 5/26/26 | Wed 6/10/26
1.3.4 | Submitted to FFO/Appian | 100% | 6 days | Thu 6/11/26 | Thu 6/18/26
1.3.5 | COR3 Evaluation | 50% | 30 days | Fri 6/19/26 | Thu 7/30/26
1.4 | Distribution Streetlighting - Caguas | 77% | 65 days | Fri 5/1/26 | Thu 7/30/26
1.4.1 | Engineering FieldMaps Data | 100% | 12 days | Fri 5/1/26 | Mon 5/18/26
1.4.2 | EHP Review Data | 100% | 5 days | Tue 5/19/26 | Mon 5/25/26
1.4.3 | Reconciliation DSOW file | 100% | 12 days | Tue 5/26/26 | Wed 6/10/26
1.4.4 | Submitted to FFO/Appian | 100% | 6 days | Thu 6/11/26 | Thu 6/18/26
1.4.5 | COR3 Evaluation | 50% | 30 days | Fri 6/19/26 | Thu 7/30/26
1.5 | Distribution Streetlighting - Aguadilla | 77% | 65 days | Fri 5/1/26 | Thu 7/30/26
1.5.1 | Engineering FieldMaps Data | 100% | 12 days | Fri 5/1/26 | Mon 5/18/26
1.5.2 | EHP Review Data | 100% | 5 days | Tue 5/19/26 | Mon 5/25/26
1.5.3 | Reconciliation DSOW file | 100% | 12 days | Tue 5/26/26 | Wed 6/10/26
1.5.4 | Submitted to FFO/Appian | 100% | 6 days | Thu 6/11/26 | Thu 6/18/26
1.5.5 | COR3 Evaluation | 50% | 30 days | Fri 6/19/26 | Thu 7/30/26
1.6 | Distribution Streetlighting - Trujillo Alto | 77% | 65 days | Fri 5/1/26 | Thu 7/30/26
1.6.1 | Engineering FieldMaps Data | 100% | 12 days | Fri 5/1/26 | Mon 5/18/26
1.6.2 | EHP Review Data | 100% | 5 days | Tue 5/19/26 | Mon 5/25/26
1.6.3 | Reconciliation DSOW file | 100% | 12 days | Tue 5/26/26 | Wed 6/10/26
1.6.4 | Submitted to FFO/Appian | 100% | 6 days | Thu 6/11/26 | Thu 6/18/26
1.6.5 | COR3 Evaluation | 50% | 30 days | Fri 6/19/26 | Thu 7/30/26
1.7 | Distribution Streetlighting - Gurabo | 0% | 65 days | Fri 6/19/26 | Thu 9/17/26
1.7.1 | Engineering FieldMaps Data | 0% | 12 days | Fri 6/19/26 | Mon 7/6/26
1.7.2 | EHP Review Data | 0% | 5 days | Tue 7/7/26 | Mon 7/13/26
1.7.3 | Reconciliation DSOW file | 0% | 12 days | Tue 7/14/26 | Wed 7/29/26
1.7.4 | Submitted to FFO/Appian | 0% | 6 days | Thu 7/30/26 | Thu 8/6/26
1.7.5 | COR3 Evaluation | 0% | 30 days | Fri 8/7/26 | Thu 9/17/26
1.8 | Distribution Streetlighting - San Germán | 0% | 65 days | Fri 6/19/26 | Thu 9/17/26
1.8.1 | Engineering FieldMaps Data | 0% | 12 days | Fri 6/19/26 | Mon 7/6/26
1.8.2 | EHP Review Data | 0% | 5 days | Tue 7/7/26 | Mon 7/13/26
1.8.3 | Reconciliation DSOW file | 0% | 12 days | Tue 7/14/26 | Wed 7/29/26
1.8.4 | Submitted to FFO/Appian | 0% | 6 days | Thu 7/30/26 | Thu 8/6/26
1.8.5 | COR3 Evaluation | 0% | 30 days | Fri 8/7/26 | Thu 9/17/26
1.9 | Distribution Streetlighting - Luquillo | 0% | 65 days | Fri 6/19/26 | Thu 9/17/26
1.9.1 | Engineering FieldMaps Data | 0% | 12 days | Fri 6/19/26 | Mon 7/6/26
1.9.2 | EHP Review Data | 0% | 5 days | Tue 7/7/26 | Mon 7/13/26
1.9.3 | Reconciliation DSOW file | 0% | 12 days | Tue 7/14/26 | Wed 7/29/26
1.9.4 | Submitted to FFO/Appian | 0% | 6 days | Thu 7/30/26 | Thu 8/6/26
1.9.5 | COR3 Evaluation | 0% | 30 days | Fri 8/7/26 | Thu 9/17/26
1.1 | Distribution Streetlighting - Hatillo | 0% | 53 days | Tue 7/7/26 | Thu 9/17/26
1.10.1 | Engineering FieldMaps Data | 0% | 5 days | Tue 7/7/26 | Mon 7/13/26
1.10.2 | EHP Review Data | 0% | 5 days | Tue 7/14/26 | Mon 7/20/26
1.10.3 | Reconciliation DSOW file | 0% | 7 days | Tue 7/21/26 | Wed 7/29/26
1.10.4 | Submitted to FFO/Appian | 0% | 6 days | Thu 7/30/26 | Thu 8/6/26
1.10.5 | COR3 Evaluation | 0% | 30 days | Fri 8/7/26 | Thu 9/17/26
1.11 | Distribution Streetlighting - Guánica | 0% | 53 days | Tue 7/7/26 | Thu 9/17/26
1.11.1 | Engineering FieldMaps Data | 0% | 5 days | Tue 7/7/26 | Mon 7/13/26
1.11.2 | EHP Review Data | 0% | 5 days | Tue 7/14/26 | Mon 7/20/26
1.11.3 | Reconciliation DSOW file | 0% | 7 days | Tue 7/21/26 | Wed 7/29/26
1.11.4 | Submitted to FFO/Appian | 0% | 6 days | Thu 7/30/26 | Thu 8/6/26
1.11.5 | COR3 Evaluation | 0% | 30 days | Fri 8/7/26 | Thu 9/17/26
1.12 | Distribution Streetlighting - Florida | 0% | 58 days | Thu 7/30/26 | Mon 10/19/26
1.12.1 | Engineering FieldMaps Data | 0% | 5 days | Thu 7/30/26 | Wed 8/5/26
1.12.2 | EHP Review Data | 0% | 5 days | Thu 8/6/26 | Wed 8/12/26
1.12.3 | Reconciliation DSOW file | 0% | 12 days | Thu 8/13/26 | Fri 8/28/26
1.12.4 | Submitted to FFO/Appian | 0% | 6 days | Mon 8/31/26 | Mon 9/7/26
1.12.5 | COR3 Evaluation | 0% | 30 days | Tue 9/8/26 | Mon 10/19/26
1.13 | Distribution Streetlighting - Aibonito | 0% | 58 days | Thu 7/30/26 | Mon 10/19/26
1.13.1 | Engineering FieldMaps Data | 0% | 5 days | Thu 7/30/26 | Wed 8/5/26
1.13.2 | EHP Review Data | 0% | 5 days | Thu 8/6/26 | Wed 8/12/26
1.13.3 | Reconciliation DSOW file | 0% | 12 days | Thu 8/13/26 | Fri 8/28/26
1.13.4 | Submitted to FFO/Appian | 0% | 6 days | Mon 8/31/26 | Mon 9/7/26
1.13.5 | COR3 Evaluation | 0% | 30 days | Tue 9/8/26 | Mon 10/19/26
1.14 | Distribution Streetlighting - Aguada | 0% | 58 days | Thu 7/30/26 | Mon 10/19/26
1.14.1 | Engineering FieldMaps Data | 0% | 5 days | Thu 7/30/26 | Wed 8/5/26
1.14.2 | EHP Review Data | 0% | 5 days | Thu 8/6/26 | Wed 8/12/26
1.14.3 | Reconciliation DSOW file | 0% | 12 days | Thu 8/13/26 | Fri 8/28/26
1.14.4 | Submitted to FFO/Appian | 0% | 6 days | Mon 8/31/26 | Mon 9/7/26
1.14.5 | COR3 Evaluation | 0% | 30 days | Tue 9/8/26 | Mon 10/19/26
1.15 | Distribution Streetlighting - Maunabo | 0% | 58 days | Thu 7/30/26 | Mon 10/19/26
1.15.1 | Engineering FieldMaps Data | 0% | 5 days | Thu 7/30/26 | Wed 8/5/26
1.15.2 | EHP Review Data | 0% | 5 days | Thu 8/6/26 | Wed 8/12/26
1.15.3 | Reconciliation DSOW file | 0% | 12 days | Thu 8/13/26 | Fri 8/28/26
1.15.4 | Submitted to FFO/Appian | 0% | 6 days | Mon 8/31/26 | Mon 9/7/26
1.15.5 | COR3 Evaluation | 0% | 30 days | Tue 9/8/26 | Mon 10/19/26
1.16 | Distribution Streetlighting - Lajas | 0% | 58 days | Thu 7/30/26 | Mon 10/19/26
1.16.1 | Engineering FieldMaps Data | 0% | 5 days | Thu 7/30/26 | Wed 8/5/26
1.16.2 | EHP Review Data | 0% | 5 days | Thu 8/6/26 | Wed 8/12/26
1.16.3 | Reconciliation DSOW file | 0% | 12 days | Thu 8/13/26 | Fri 8/28/26
1.16.4 | Submitted to FFO/Appian | 0% | 6 days | Mon 8/31/26 | Mon 9/7/26
1.16.5 | COR3 Evaluation | 0% | 30 days | Tue 9/8/26 | Mon 10/19/26
1.17 | Distribution Streetlighting - Villalba | 0% | 58 days | Thu 7/30/26 | Mon 10/19/26
1.17.1 | Engineering FieldMaps Data | 0% | 5 days | Thu 7/30/26 | Wed 8/5/26
1.17.2 | EHP Review Data | 0% | 5 days | Thu 8/6/26 | Wed 8/12/26
1.17.3 | Reconciliation DSOW file | 0% | 12 days | Thu 8/13/26 | Fri 8/28/26
1.17.4 | Submitted to FFO/Appian | 0% | 6 days | Mon 8/31/26 | Mon 9/7/26
1.17.5 | COR3 Evaluation | 0% | 30 days | Tue 9/8/26 | Mon 10/19/26
Work Plan