## Summary
Summary for June 2026 Report:
| Project Status |  |  |  | Miles |  |  |  |  | Cost
Voltage | Total Projects | Projects Submitted to FEMA | Projects Pending Submission to FEMA | Projects Obligated | Total Miles Submitted to FEMA | Miles Pending Submission to FEMA | Total Miles Obligated | Miles Submitted, Denied by FEMA | Percentage of Submitted Miles Obligated (Average) | Total Funds Obligated
Distribution | 25 | 19 | 6 | 15 | 5181.86 | 7325.04 | 4440.76 | 33.83 | 99% | 472594417.76
38kV | 36 | 10 | 26 | 3 | 220.44 | 1165.42 | 13.89 | 51.02 | 34% | 2552959.58
115kV | 10 | 10 | 0 | 9* | 567.81 | 0 | 115.35 | 452.46 | 20.31% | 37265824.02
230kV | 1 | 1 | 0 | 1 | 402.54 | 0 | 38.21 | 364.33 | 9.492% | 12885805.47
Total | 72 | 40 | 32 | 19 | 6372.65 | 8490.46 | 4608.21 | 901.64 |  | 525299006.83
*One 115kV project is pending obligation of Version 1 by FEMA. FEMA obligated Version 0 in September 2025. Additional miles were submitted by LUMA; these additional miles are under review by FEMA
| June Miles |  |  | Program Restart to Date Miles (5/1/2025 - 6/30/2026)*
Voltage | Federally Funded Clearing** | OpEx Maintenance | Total Miles | Federally Funded Clearing** | OpEx Maintenance*** | Total Miles
Distribution | 94.73 | 56.13 | 150.86 | 700.17 | 94.67 | 794.84
38 kV | 1.2 | 38.77 | 39.97 | 1.4 | 52.57 | 53.97
115 kV | 0.71 | 19.12 | 19.83 | 14.98 | 53.59 | 68.57
230 kV | 0 | 10.28 | 10.28 | 0 | 23.16 | 23.16
Total | 96.64 | 124.3 | 220.94 | 716.55 | 223.99 | 940.54
Note: Figures may not add up due to rounding. *Program restart is May 1, 2025 - the restart was triggered by the obligation of four high density projects on 4/25/25. Prior to this date, 288.14 miles were impacted (cleared and/or assessed as clear spans), for a total of 1,007.54 miles cleared using federal funding as of 5/31/26. **For federally funded miles, the reported figures include both completed work and, in certain circuits, miles assessed as clear spans. All circuits reported have undergone physical vegetation clearing activities. ***Historical data for OpEx/rate payer-funded will be tracked from May 2026 onward; historical data is not provided.

## Transmission Lines
Primary Transmission Lines
FAASt | Line Voltage (kV) | Transmission Lines ID # | Terminal 1 | Terminal 2 | Date | Circuit Miles Maintained / Cleared | Region | Right of Way (ROWs) Width | ROW Acres Maintained / Cleared | Name of Contractor | Clearing Status | Type of Response | VM Activity Point of Contact (POC) | Funding Source | Month | Quarter | Fiscal Year
N/A | 38 | 9300 | Juncos | Gautier | 2026-05-01 | 0.05 | East | 100 | 0.55 | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 9300 | Juncos | Gautier | 2026-05-01 | 0.1 | East | 100 | 1.16 | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 9300 | Juncos | Gautier | 2026-05-01 | 0.11 | East | 100 | 1.35 | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 13100 |  |  | 2026-05-01 | 0.05 | South | 100 | 0.63 | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 13100 |  |  | 2026-05-01 | 0.05 | South | 100 | 0.64 | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36100 | Monacillos | Ciales | 2026-05-01 | 0.15 | Metro | 150 | 2.77 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36200 | Rio Blanco TC | Juncos TC | 2026-05-01 | 0.06 | Metro | 150 | 1.13 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36300 | Jobos | Juan Martin | 2026-05-01 | 0.16 | East | 150 | 2.85 | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36300 | Jobos | Juan Martin | 2026-05-01 | 0.36 | East | 150 | 6.61 | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36400 | Dos Bocas | Jayuya | 2026-05-01 | 0.07 | South | 150 | 1.35 | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36800 | Sabana Llana | Fajardo | 2026-05-01 | 0.31 | Metro | 150 | 5.67 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36800 | Sabana Llana | Fajardo | 2026-05-01 | 0.17 | Metro | 150 | 3.14 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
956349 | 115 | 36800 | Canovanas TC | Palmer TC | 2026-05-01 | 0.05 | San Juan | 150 | 0.91 | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
N/A | 115 | 37400 | Vega Alta | Arecibo | 2026-05-01 | 0.09 | West | 150 | 1.7 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37400 | Vega Alta | Arecibo | 2026-05-01 | 0.09 | West | 150 | 1.7 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37400 | Vega Alta | Arecibo | 2026-05-01 | 0.09 | West | 150 | 1.55 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37800 | Monacillos | Caguas | 2026-05-01 | 0.39 | Metro | 150 | 7.07 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37800 | Monacillos | Caguas | 2026-05-01 | 0.14 | Metro | 150 | 2.61 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37900 | Monacillos | Sabana Llana | 2026-05-01 | 0.23 | Metro | 150 | 4.24 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 51000 | Aguas Buenas | Sabana Llana | 2026-05-01 | 0.2 | Metro | 150 | 3.6 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 51200 | Costa Sur | Cambalache | 2026-05-01 | 0.21 | West | 150 | 3.8 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 51300 | Manati TC | Cambalache TC | 2026-05-01 | 0.04 | South | 150 | 0.75 | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 9300 | Juncos | Gautier | 2026-05-02 | 0.06 | East | 100 | 0.67 | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 9300 | Juncos | Gautier | 2026-05-02 | 0.09 | East | 100 | 1.08 | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 13100 |  |  | 2026-05-02 | 0.05 | South | 100 | 0.64 | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36100 | Morovis | Dos Bocas | 2026-05-02 | 0.08 | Metro | 150 | 1.45 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36100 | Morovis | Dos Bocas | 2026-05-02 | 0.11 | Metro | 150 | 1.99 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36100 | Barrio Pina GIS | Cana Sect | 2026-05-02 | 0.11 | Metro | 150 | 1.99 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36100 | Morovis | Dos Bocas | 2026-05-02 | 0.15 | Metro | 150 | 2.76 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36100 | Morovis | Dos Bocas | 2026-05-02 | 0.12 | Metro | 150 | 2.11 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36100 | Morovis | Dos Bocas | 2026-05-02 | 0.12 | Metro | 150 | 2.17 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36100 | Morovis | Dos Bocas | 2026-05-02 | 0.06 | Metro | 150 | 1.02 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36300 | Jobos | Juan Martin | 2026-05-02 | 0.43 | East | 150 | 7.78 | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36400 | Dos Bocas | Jayuya | 2026-05-02 | 0.05 | South | 150 | 0.84 | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36900 | Costa Sur | Ponce Hostos | 2026-05-02 | 0.16 | South | 150 | 2.97 | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37400 | Vega Alta | Arecibo | 2026-05-02 | 0.09 | West | 150 | 1.67 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37400 | Vega Alta | Arecibo | 2026-05-02 | 0.16 | West | 150 | 2.93 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 38400 | SJSP | Viaducto | 2026-05-02 | 0.06 | Metro | 150 | 1.13 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 50500 | Cambalache | Mayaguez TC | 2026-05-02 | 0.07 | West | 150 | 1.3 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 51200 | Costa Sur | Cambalache | 2026-05-02 | 0.21 | West | 150 | 3.77 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 51200 | Costa Sur | Cambalache | 2026-05-02 | 0.23 | West | 150 | 4.22 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 51200 | Costa Sur | Cambalache | 2026-05-02 | 0.21 | West | 150 | 3.81 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 51200 | Costa Sur | Cambalache | 2026-05-02 | 0.22 | West | 150 | 3.99 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 51200 | Costa Sur | Cambalache | 2026-05-03 | 0.3 | West | 150 | 5.42 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 51200 | Costa Sur | Cambalache | 2026-05-03 | 0.3 | West | 150 | 5.42 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 51200 | Costa Sur | Cambalache | 2026-05-03 | 0.12 | West | 150 | 2.14 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 51200 | Costa Sur | Cambalache | 2026-05-03 | 0.14 | West | 150 | 2.48 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 1400 | Yauco 1 | Yauco 2 | 2026-05-04 | 0.35 | South | 100 | 4.29 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 6900 | Cambalache TC | Mirador Azul Sect | 2026-05-04 | 0.04 | WEST | 100 | 0.46 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36100 | Morovis | Dos Bocas | 2026-05-04 | 0.12 | Metro | 150 | 2.22 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
956353 | 115 | 36100 | Dos Bocas HP | Barrio Pina | 2026-05-04 | 0.07 | Arecibo | 150 | 1.27 | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
N/A | 115 | 36200 | Rio Blanco TC | Juncos TC | 2026-05-04 | 0.18 | Metro | 150 | 3.25 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
956349 | 115 | 36800 | Canovanas TC | Palmer TC | 2026-05-04 | 0.09 | San Juan | 150 | 1.64 | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
N/A | 115 | 38300 | SJSP | Monacillos | 2026-05-04 | 0.06 | Metro | 150 | 1.05 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 39000 | Ponce Hostos | Barranquitas | 2026-05-04 | 0.31 | Metro | 150 | 5.71 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 51200 | Costa Sur | Cambalache | 2026-05-04 | 0.18 | West | 150 | 3.3 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 51200 | Costa Sur | Cambalache | 2026-05-04 | 0.08 | West | 150 | 1.54 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 51200 | Costa Sur | Cambalache | 2026-05-04 | 0.08 | West | 150 | 1.5 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 51200 | Costa Sur | Cambalache | 2026-05-04 | 0.44 | West | 150 | 8 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 1700 | Guanica TC | Yauco 2 HP | 2026-05-05 | 0.04 | South | 100 | 0.49 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 1700 | Guanica TC | Yauco 2 HP | 2026-05-05 | 0.05 | South | 100 | 0.6 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 1700 | Guanica TC | Yauco 2 HP | 2026-05-05 | 0.05 | South | 100 | 0.59 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 1700 | Guanica TC | Yauco 2 HP | 2026-05-05 | 0.01 | South | 100 | 0.17 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 1700 | Guanica TC | Yauco 2 HP | 2026-05-05 | 0.01 | South | 100 | 0.17 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2500 | San Sebastian TC | Victoria TC | 2026-05-05 | 0.03 | West | 100 | 0.33 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 3100 | Saint Just | Sabana Llana | 2026-05-05 | 0.02 | Metro | 100 | 0.26 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 3100 | Monacillos | Sabana Llana | 2026-05-05 | 0.11 | Metro | 100 | 1.27 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 3200 | San Juan |  | 2026-05-05 | 0.03 | Metro | 100 | 0.39 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 3600 | Saint Just | Sabana Llana | 2026-05-05 | 0.08 | Metro | 100 | 0.96 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 7700 | Comerio | Media Luna | 2026-05-05 | 0.04 | East | 100 | 0.51 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36100 | Morovis | Dos Bocas | 2026-05-05 | 0.12 | Metro | 150 | 2.15 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36100 | Morovis | Dos Bocas | 2026-05-05 | 0.24 | Metro | 150 | 4.43 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36100 | Morovis | Dos Bocas | 2026-05-05 | 0.12 | Metro | 150 | 2.15 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
956353 | 115 | 36100 | Dos Bocas HP | Barrio Pina | 2026-05-05 | 0.06 | Arecibo | 150 | 1.09 | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
N/A | 115 | 37400 | Vega Alta | Arecibo | 2026-05-05 | 0.13 | West | 150 | 2.42 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37400 | Vega Alta | Arecibo | 2026-05-05 | 0.15 | West | 150 | 2.66 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37400 | Vega Alta | Arecibo | 2026-05-05 | 0.15 | West | 150 | 2.66 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37400 | Vega Alta | Arecibo | 2026-05-05 | 0.07 | West | 150 | 1.19 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37400 | Vega Alta | Arecibo | 2026-05-05 | 0.15 | West | 150 | 2.64 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37800 | Monacillos | Caguas | 2026-05-05 | 0.09 | Metro | 150 | 1.59 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 38200 | PSSP | Monacillos | 2026-05-05 | 0.03 | Metro | 150 | 0.61 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 51200 | Costa Sur | Cambalache | 2026-05-05 | 0.08 | West | 150 | 1.4 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 51200 | Costa Sur | Cambalache | 2026-05-05 | 0.13 | West | 150 | 2.3 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 51200 | Costa Sur | Cambalache | 2026-05-05 | 0.24 | West | 150 | 4.44 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 51200 | Costa Sur | Cambalache | 2026-05-05 | 0.25 | West | 150 | 4.47 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 1700 | Guanica TC | Yauco 2 HP | 2026-05-06 | 0.05 | South | 100 | 0.61 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 1700 | Guanica TC | Yauco 2 HP | 2026-05-06 | 0.02 | South | 100 | 0.24 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 1700 | Guanica TC | Yauco 2 HP | 2026-05-06 | 0.07 | South | 100 | 0.87 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 1700 | Guanica TC | Yauco 2 HP | 2026-05-06 | 0.11 | South | 100 | 1.37 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 3000 | Bairoa | Rio Blanco | 2026-05-06 | 0.03 | Metro | 100 | 0.32 | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 3100 | Monacillos | Sabana Llana | 2026-05-06 | 0.08 | Metro | 100 | 1.03 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36100 | Morovis | Dos Bocas | 2026-05-06 | 0.11 | Metro | 150 | 2.06 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36800 | Sabana Llana | Fajardo | 2026-05-06 | 0.23 | Metro | 150 | 4.2 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
956349 | 115 | 36800 | Canovanas TC | Palmer TC | 2026-05-06 | 0.05 | San Juan | 150 | 0.91 | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
N/A | 115 | 37400 | Vega Alta | Arecibo | 2026-05-06 | 0.2 | West | 150 | 3.66 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37400 | Vega Alta | Arecibo | 2026-05-06 | 0.09 | West | 150 | 1.59 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37400 | Vega Alta | Arecibo | 2026-05-06 | 0.15 | West | 150 | 2.68 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37400 | Vega Alta | Arecibo | 2026-05-06 | 0.07 | West | 150 | 1.36 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37400 | Vega Alta | Arecibo | 2026-05-06 | 0.15 | West | 150 | 2.64 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37400 | Vega Alta | Arecibo | 2026-05-06 | 0.11 | West | 150 | 1.97 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37500 | BTC | Monacillos | 2026-05-06 | 0.08 | Metro | 150 | 1.4 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37500 | BTC | Monacillos | 2026-05-06 | 0.04 | Metro | 150 | 0.76 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37500 | BTC | Monacillos | 2026-05-06 | 0.04 | Metro | 150 | 0.68 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37800 | Monacillos | Caguas | 2026-05-06 | 0.16 | Metro | 150 | 2.82 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 38200 | PSSP | Monacillos | 2026-05-06 | 0.04 | Metro | 150 | 0.79 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 38200 | PSSP | Monacillos | 2026-05-06 | 0.02 | Metro | 150 | 0.33 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 50200 | Manati TC | Bayamon TC | 2026-05-06 | 0.16 | Metro | 150 | 2.86 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 51200 | Costa Sur | Cambalache | 2026-05-06 | 0.22 | West | 150 | 3.99 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 700 | Yauco | Guayanilla | 2026-05-07 | 0.05 | South | 100 | 0.66 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 700 | Yauco | Guayanilla | 2026-05-07 | 0.05 | South | 100 | 0.63 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 700 | Yauco | Guayanilla | 2026-05-07 | 0.02 | South | 100 | 0.25 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 3100 | Monacillos | Sabana Llana | 2026-05-07 | 0.04 | Metro | 100 | 0.53 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 3100 | Monacillos | Sabana Llana | 2026-05-07 | 0.16 | Metro | 100 | 1.91 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 3100 | Monacillos | Sabana Llana | 2026-05-07 | 0.03 | Metro | 100 | 0.32 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 3100 | Monacillos | Sabana Llana | 2026-05-07 | 0.03 | Metro | 100 | 0.32 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 3600 | Monacillos | Sabana Llana | 2026-05-07 | 0.07 | Metro | 100 | 0.83 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 3600 | Monacillos | Sabana Llana | 2026-05-07 | 0.02 | Metro | 100 | 0.28 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36100 | Morovis | Dos Bocas | 2026-05-07 | 0.07 | Metro | 150 | 1.3 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36100 | Morovis | Dos Bocas | 2026-05-07 | 0.12 | Metro | 150 | 2.09 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36100 | Morovis | Dos Bocas | 2026-05-07 | 0.17 | Metro | 150 | 3.1 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36100 | Morovis | Dos Bocas | 2026-05-07 | 0.17 | Metro | 150 | 3.1 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36100 | Morovis | Dos Bocas | 2026-05-07 | 0.11 | Metro | 150 | 1.96 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36100 | Morovis | Dos Bocas | 2026-05-07 | 0.12 | Metro | 150 | 2.1 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36200 | Rio Blanco TC | Juncos TC | 2026-05-07 | 0.13 | Metro | 150 | 2.45 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36200 | Rio Blanco TC | Juncos TC | 2026-05-07 | 0.04 | Metro | 150 | 0.72 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36200 | Rio Blanco TC | Juncos TC | 2026-05-07 | 0.12 | Metro | 150 | 2.16 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
956349 | 115 | 36800 | Canovanas TC | Palmer TC | 2026-05-07 | 0.13 | San Juan | 150 | 2.36 | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
N/A | 115 | 37400 | Vega Alta | Arecibo | 2026-05-07 | 0.07 | West | 150 | 1.19 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37400 | Vega Alta | Arecibo | 2026-05-07 | 0.08 | West | 150 | 1.38 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37400 | Vega Alta | Arecibo | 2026-05-07 | 0.12 | West | 150 | 2.17 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37400 | Vega Alta | Arecibo | 2026-05-07 | 0.15 | West | 150 | 2.68 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37400 | Vega Alta | Arecibo | 2026-05-07 | 0.13 | West | 150 | 2.44 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37400 | Vega Alta | Arecibo | 2026-05-07 | 0.05 | West | 150 | 0.97 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37400 | Vega Alta | Arecibo | 2026-05-07 | 0.15 | West | 150 | 2.65 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37400 | Vega Alta | Arecibo | 2026-05-07 | 0.08 | West | 150 | 1.52 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37400 | Vega Alta | Arecibo | 2026-05-07 | 0.04 | West | 150 | 0.77 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37500 | Bayamon TC | Monacillos TC | 2026-05-07 | 0.13 | Metro | 150 | 2.29 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37800 | Monacillos | Caguas | 2026-05-07 | 0.2 | Metro | 150 | 3.62 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37800 | Monacillos | Caguas | 2026-05-07 | 0.09 | Metro | 150 | 1.65 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 38300 | SJSP | Monacillos | 2026-05-07 | 0.07 | Metro | 150 | 1.29 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 1700 | Guanica TC | Yauco 2 HP | 2026-05-08 | 0.11 | South | 100 | 1.37 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 1700 | Guanica TC | Yauco 2 HP | 2026-05-08 | 0.17 | South | 100 | 2.06 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 3300 | San Juan |  | 2026-05-08 | 0.04 | Metro | 100 | 0.49 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36100 | Morovis | Dos Bocas | 2026-05-08 | 0.12 | Metro | 150 | 2.21 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
956353 | 115 | 36100 | Dos Bocas HP | Barrio Pina | 2026-05-08 | 0.06 | Arecibo | 150 | 1.09 | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
956349 | 115 | 36800 | Canovanas TC | Palmer TC | 2026-05-08 | 0.03 | San Juan | 150 | 0.55 | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
N/A | 115 | 37400 | Vega Alta | Arecibo | 2026-05-08 | 0.14 | West | 150 | 2.49 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37400 | Vega Alta | Arecibo | 2026-05-08 | 0.22 | West | 150 | 4.04 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37400 | Vega Alta | Arecibo | 2026-05-08 | 0.08 | West | 150 | 1.5 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37400 | Vega Alta | Arecibo | 2026-05-08 | 0.09 | West | 150 | 1.72 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37800 | Monacillos | Caguas | 2026-05-08 | 0.05 | Metro | 150 | 0.92 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37800 | Monacillos | Caguas | 2026-05-08 | 0.14 | Metro | 150 | 2.55 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 40800 | Manati TC | Upjohn | 2026-05-08 | 0.03 | West | 150 | 0.6 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 51200 | Costa Sur | Cambalache | 2026-05-08 | 0.05 | West | 150 | 0.87 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36100 | Morovis | Dos Bocas | 2026-05-09 | 0.12 | Metro | 150 | 2.1 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36100 | Morovis | Dos Bocas | 2026-05-09 | 0.07 | Metro | 150 | 1.35 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36100 | Morovis | Dos Bocas | 2026-05-09 | 0.17 | Metro | 150 | 3.1 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36100 | Morovis | Dos Bocas | 2026-05-09 | 0.15 | Metro | 150 | 2.68 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36100 | Morovis | Dos Bocas | 2026-05-09 | 0.07 | Metro | 150 | 1.29 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37400 | Vega Alta | Arecibo | 2026-05-09 | 0.2 | West | 150 | 3.58 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37400 | Vega Alta | Arecibo | 2026-05-09 | 0.06 | West | 150 | 1.15 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37400 | Vega Alta | Arecibo | 2026-05-09 | 0.14 | West | 150 | 2.49 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37400 | Vega Alta | Arecibo | 2026-05-09 | 0.1 | West | 150 | 1.89 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 40800 | Manati TC | Upjohn | 2026-05-09 | 0.04 | West | 150 | 0.67 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 40800 | Manati TC | Upjohn | 2026-05-09 | 0.04 | West | 150 | 0.65 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 41400 | Juncos | Humacao | 2026-05-09 | 0.05 | East | 150 | 0.98 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 51200 | Costa Sur | Cambalache | 2026-05-09 | 0.31 | West | 150 | 5.61 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 40800 | Manati TC | Upjohn | 2026-05-10 | 0.03 | West | 150 | 0.57 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 3100 | Monacillos | Sabana Llana | 2026-05-11 | 0.28 | Metro | 100 | 3.45 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 3100 | Monacillos | Sabana Llana | 2026-05-11 | 0.06 | Metro | 100 | 0.68 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 3100 | Saint Just | Sabana Llana | 2026-05-11 | 0.03 | Metro | 100 | 0.39 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36100 | Morovis | Dos Bocas | 2026-05-11 | 0.04 | Metro | 150 | 0.74 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36100 | Morovis | Dos Bocas | 2026-05-11 | 0.09 | Metro | 150 | 1.69 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36100 | Morovis | Dos Bocas | 2026-05-11 | 0.07 | Metro | 150 | 1.35 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
956349 | 115 | 36800 | Canovanas TC | Palmer TC | 2026-05-11 | 0.02 | San Juan | 150 | 0.36 | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
N/A | 115 | 39000 | Ponce Hostos | Barranquitas | 2026-05-11 | 0.22 | Metro | 150 | 4.03 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 39000 | Ponce Hostos | Barranquitas | 2026-05-11 | 0.39 | Metro | 150 | 7.11 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 40800 | Manati TC | Dupont and Bristol Myers | 2026-05-11 | 0.04 | West | 150 | 0.66 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 40800 | Manati TC | Dupont and Bristol Myers | 2026-05-11 | 0.02 | West | 150 | 0.4 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 40800 | Manati TC | Dupont and Bristol Myers | 2026-05-11 | 0.02 | West | 150 | 0.44 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 40800 | Manati TC | Dupont and Bristol Myers | 2026-05-11 | 0.03 | West | 150 | 0.6 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 40800 | Manati TC | Upjohn | 2026-05-11 | 0.05 | West | 150 | 0.86 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 40800 | Manati TC | Upjohn | 2026-05-11 | 0.04 | West | 150 | 0.66 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 40800 | Manati TC | Upjohn | 2026-05-11 | 0.03 | West | 150 | 0.63 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 40800 | Manati TC | Upjohn | 2026-05-11 | 0.03 | West | 150 | 0.61 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 40800 | Manati TC | Upjohn | 2026-05-11 | 0.04 | West | 150 | 0.66 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 41400 | Juncos | Humacao | 2026-05-11 | 0.2 | East | 150 | 3.71 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 1300 | Yauco 1 | Yauco 2 | 2026-05-12 | 0.19 | South | 100 | 2.32 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 1300 | Yauco 1 | Yauco 2 | 2026-05-12 | 0.05 | South | 100 | 0.58 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 1300 | Yauco 1 | Yauco 2 | 2026-05-12 | 0.06 | South | 100 | 0.79 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 1300 | Yauco 1 | Yauco 2 | 2026-05-12 | 0.06 | South | 100 | 0.79 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 1400 | Yauco 1 | Yauco 2 | 2026-05-12 | 0.28 | South | 100 | 3.36 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36100 | Morovis | Dos Bocas | 2026-05-12 | 0.22 | Metro | 150 | 3.96 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36200 | Rio Blanco TC | Juncos TC | 2026-05-12 | 0.26 | Metro | 150 | 4.8 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
956349 | 115 | 36800 | Canovanas TC | Palmer TC | 2026-05-12 | 0.03 | San Juan | 150 | 0.55 | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
N/A | 115 | 37200 | Mayaguez GP | Victoria TC | 2026-05-12 | 0.11 | West | 150 | 1.94 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37200 | Mayaguez GP | Victoria TC | 2026-05-12 | 0.08 | West | 150 | 1.47 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37200 | Mayaguez GP | Victoria TC | 2026-05-12 | 0.02 | West | 150 | 0.32 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37400 | Vega Alta | Arecibo | 2026-05-12 | 0.19 | West | 150 | 3.46 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37800 | Monacillos TC | Buen Pastor Sect | 2026-05-12 | 0.22 | Metro | 150 | 4.06 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37800 | Monacillos TC | Buen Pastor Sect | 2026-05-12 | 0.06 | Metro | 150 | 1.06 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37800 | Monacillos TC | Buen Pastor Sect | 2026-05-12 | 0.06 | Metro | 150 | 1.03 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 39000 | Ponce Hostos | Barranquitas | 2026-05-12 | 0.17 | Metro | 150 | 3.07 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 39000 | Ponce Hostos | Barranquitas | 2026-05-12 | 0.14 | Metro | 150 | 2.52 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 40800 | Manati TC | Dupont and Bristol Myers | 2026-05-12 | 0.04 | West | 150 | 0.69 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 40800 | Manati TC | Dupont and Bristol Myers | 2026-05-12 | 0.02 | West | 150 | 0.37 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 40800 | Manati TC | Dupont and Bristol Myers | 2026-05-12 | 0.04 | West | 150 | 0.67 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 40800 | Manati TC | Upjohn | 2026-05-12 | 0.04 | West | 150 | 0.67 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 40800 | Manati TC | Upjohn | 2026-05-12 | 0.02 | West | 150 | 0.37 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 40800 | Manati TC | Upjohn | 2026-05-12 | 0.04 | West | 150 | 0.69 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 40800 | Manati TC | Upjohn | 2026-05-12 | 0.03 | West | 150 | 0.55 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 40800 | Manati TC | Upjohn | 2026-05-12 | 0.04 | West | 150 | 0.65 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 41400 | Juncos | Humacao | 2026-05-12 | 0.06 | East | 150 | 1.01 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 50200 | Manati TC | Costa Sur | 2026-05-12 | 0.24 | Metro | 150 | 4.45 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 50500 | Cambalache | Mayaguez TC | 2026-05-12 | 0.19 | West | 150 | 3.5 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 50500 | Cambalache | Mayaguez TC | 2026-05-12 | 0.08 | West | 150 | 1.52 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 51200 | Costa Sur | Cambalache | 2026-05-12 | 0.14 | West | 150 | 2.48 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 1300 | Yauco 1 | Yauco 2 | 2026-05-13 | 0.05 | South | 100 | 0.58 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 1700 | Guanica TC | Yauco 2 HP | 2026-05-13 | 0.05 | South | 100 | 0.62 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2600 | Quebradillas Sect | San Sebastian TC | 2026-05-13 | 0.11 | WEST | 100 | 1.33 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2600 | Quebradillas Sect | San Sebastian TC | 2026-05-13 | 0.17 | WEST | 100 | 2.05 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2600 | Quebradillas Sect | San Sebastian TC | 2026-05-13 | 0.13 | WEST | 100 | 1.62 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2600 | Quebradillas Sect | San Sebastian TC | 2026-05-13 | 0.28 | WEST | 100 | 3.43 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2600 | Quebradillas Sect | San Sebastian TC | 2026-05-13 | 0.25 | WEST | 100 | 2.98 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 3100 | Monacillos | Sabana Llana | 2026-05-13 | 0.04 | Metro | 100 | 0.53 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36100 | Monacillos | Ciales | 2026-05-13 | 0.21 | Metro | 150 | 3.87 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36200 | Rio Blanco TC | Juncos TC | 2026-05-13 | 0.13 | Metro | 150 | 2.32 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36200 | Rio Blanco TC | Juncos TC | 2026-05-13 | 0.11 | Metro | 150 | 2.09 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36400 | Ponce Hostos | Villalba | 2026-05-13 | 0.09 | South | 150 | 1.55 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36400 | Dos Bocas | Jayuya | 2026-05-13 | 0.07 | South | 150 | 1.3 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36400 | Dos Bocas | Jayuya | 2026-05-13 | 0.11 | South | 150 | 2.01 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36400 | Dos Bocas | Jayuya | 2026-05-13 | 0.07 | South | 150 | 1.25 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
956349 | 115 | 36800 | Canovanas TC | Palmer TC | 2026-05-13 | 0.02 | San Juan | 150 | 0.36 | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
N/A | 115 | 37200 | Mayaguez GP | Victoria TC | 2026-05-13 | 0.06 | West | 150 | 1.01 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37200 | Mayaguez GP | Victoria TC | 2026-05-13 | 0.06 | West | 150 | 1.01 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37200 | Mayaguez GP | Victoria TC | 2026-05-13 | 0.11 | West | 150 | 1.99 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37400 | Vega Alta | Arecibo | 2026-05-13 | 0.07 | West | 150 | 1.31 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37400 | Vega Alta | Arecibo | 2026-05-13 | 0.11 | West | 150 | 1.91 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37800 | Monacillos TC | Buen Pastor Sect | 2026-05-13 | 0.09 | Metro | 150 | 1.67 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37800 | Monacillos TC | Buen Pastor Sect | 2026-05-13 | 0.27 | Metro | 150 | 4.91 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 38700 | PSSP | SJSP | 2026-05-13 | 0.22 | Metro | 150 | 4.03 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 41400 | Juncos | Humacao | 2026-05-13 | 0.06 | East | 150 | 1.13 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 51200 | Costa Sur | Cambalache | 2026-05-13 | 0.24 | West | 150 | 4.39 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2600 | Quebradillas Sect | San Sebastian TC | 2026-05-14 | 0.25 | WEST | 100 | 2.98 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2600 | Quebradillas Sect | San Sebastian TC | 2026-05-14 | 0.21 | WEST | 100 | 2.51 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2600 | Quebradillas Sect | San Sebastian TC | 2026-05-14 | 0.05 | WEST | 100 | 0.6 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 3000 | Bairoa | Rio Blanco | 2026-05-14 | 0.02 | Metro | 100 | 0.29 | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 3000 | Bairoa | Rio Blanco | 2026-05-14 | 0.05 | Metro | 100 | 0.6 | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 3100 | Monacillos | Sabana Llana | 2026-05-14 | 0.04 | Metro | 100 | 0.46 | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 3100 | Monacillos | Sabana Llana | 2026-05-14 | 0.14 | Metro | 100 | 1.64 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 3600 | Monacillos | Sabana Llana | 2026-05-14 | 0.03 | Metro | 100 | 0.36 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36400 | Dos Bocas | Jayuya | 2026-05-14 | 0.07 | South | 150 | 1.3 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36400 | Ponce Hostos | Villalba | 2026-05-14 | 0.16 | South | 150 | 2.83 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36400 | Ponce Hostos | Villalba | 2026-05-14 | 0.07 | South | 150 | 1.28 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36400 | Dos Bocas | Jayuya | 2026-05-14 | 0.08 | South | 150 | 1.52 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36400 | Dos Bocas | Jayuya | 2026-05-14 | 0.04 | South | 150 | 0.65 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36400 | Ponce Hostos | Villalba | 2026-05-14 | 0.11 | South | 150 | 1.95 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
956349 | 115 | 36800 | Canovanas TC | Palmer TC | 2026-05-14 | 0.01 | San Juan | 150 | 0.18 | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
N/A | 115 | 37700 | SJSP | Bayamon | 2026-05-14 | 0.11 | Metro | 150 | 1.92 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37800 | Monacillos TC | Buen Pastor Sect | 2026-05-14 | 0.29 | Metro | 150 | 5.26 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37900 | Monacillos | Sabana Llana | 2026-05-14 | 0.07 | Metro | 150 | 1.28 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 38200 | Palo Seco SP | Monacillos TC | 2026-05-14 | 0.16 | Metro | 150 | 2.85 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 41000 | Humacao |  | 2026-05-14 | 0.15 | East | 150 | 2.8 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2600 | Quebradillas Sect | San Sebastian TC | 2026-05-15 | 0.15 | WEST | 100 | 1.76 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2600 | Quebradillas Sect | San Sebastian TC | 2026-05-15 | 0.26 | WEST | 100 | 3.19 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2600 | Quebradillas Sect | San Sebastian TC | 2026-05-15 | 0.12 | WEST | 100 | 1.43 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2600 | Quebradillas Sect | San Sebastian TC | 2026-05-15 | 0.16 | WEST | 100 | 1.9 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2600 | Quebradillas Sect | San Sebastian TC | 2026-05-15 | 0.16 | WEST | 100 | 1.9 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2600 | Quebradillas Sect | San Sebastian TC | 2026-05-15 | 0.14 | WEST | 100 | 1.65 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36400 | Dos Bocas | Jayuya | 2026-05-15 | 0.25 | South | 150 | 4.62 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36400 | Ponce Hostos | Villalba | 2026-05-15 | 0.29 | South | 150 | 5.18 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36400 | Dos Bocas | Jayuya | 2026-05-15 | 0.04 | South | 150 | 0.65 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36400 | Dos Bocas | Jayuya | 2026-05-15 | 0.25 | South | 150 | 4.62 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36400 | Dos Bocas | Jayuya | 2026-05-15 | 0.25 | South | 150 | 4.62 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37500 | Bayamon TC | Monacillos TC | 2026-05-15 | 0.19 | Metro | 150 | 3.53 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 38200 | Palo Seco SP | Monacillos TC | 2026-05-15 | 0.08 | Metro | 150 | 1.51 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 39000 | Ponce Hostos | Barranquitas | 2026-05-15 | 0.23 | Metro | 150 | 4.23 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 39000 | Ponce Hostos | Barranquitas | 2026-05-15 | 0.23 | Metro | 150 | 4.21 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 41000 | Humacao |  | 2026-05-15 | 0.24 | East | 150 | 4.38 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 50200 | Manati TC | Costa Sur | 2026-05-15 | 0.22 | Metro | 150 | 4.06 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Dorado | Vega Alta | 2026-05-16 | 0.02 | Metro | 100 | 0.22 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2600 | Quebradillas Sect | San Sebastian TC | 2026-05-16 | 0.08 | WEST | 100 | 0.94 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2600 | Quebradillas Sect | San Sebastian TC | 2026-05-16 | 0.23 | WEST | 100 | 2.78 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2600 | Quebradillas Sect | San Sebastian TC | 2026-05-16 | 0.11 | WEST | 100 | 1.38 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 7800 | Dorado TC | Vega Baja | 2026-05-16 | 0.06 | Metro | 100 | 0.73 | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36400 | Ponce Hostos | Villalba | 2026-05-16 | 0.31 | South | 150 | 5.55 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36400 | Dos Bocas | Jayuya | 2026-05-16 | 0.25 | South | 150 | 4.62 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36400 | Dos Bocas | Jayuya | 2026-05-16 | 0.03 | South | 150 | 0.63 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36400 | Dos Bocas | Jayuya | 2026-05-16 | 0.08 | South | 150 | 1.38 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36400 | Ponce Hostos | Villalba | 2026-05-16 | 0.31 | South | 150 | 5.55 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37400 | Vega Alta | Arecibo | 2026-05-16 | 0.08 | West | 150 | 1.44 | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 39000 | Ponce Hostos | Barranquitas | 2026-05-16 | 0.3 | Metro | 150 | 5.43 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 50200 | Manati TC | Costa Sur | 2026-05-16 | 0.21 | Metro | 150 | 3.81 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2600 | Quebradillas Sect | San Sebastian TC | 2026-05-18 | 0.26 | WEST | 100 | 3.19 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 3100 | Monacillos | Sabana Llana | 2026-05-18 | 0.12 | Metro | 100 | 1.41 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 3600 | Monacillos | Sabana Llana | 2026-05-18 | 0.05 | Metro | 100 | 0.64 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 4100 | Comerio | Bayamon | 2026-05-18 | 0.07 | Metro | 100 | 0.84 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36400 | Ponce Hostos | Villalba | 2026-05-18 | 0.09 | South | 150 | 1.73 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36400 | Dos Bocas | Jayuya | 2026-05-18 | 0.05 | South | 150 | 0.84 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36400 | Dos Bocas | Jayuya | 2026-05-18 | 0.05 | South | 150 | 0.84 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36400 | Ponce Hostos | Villalba | 2026-05-18 | 0.07 | South | 150 | 1.19 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36400 | Ponce Hostos | Villalba | 2026-05-18 | 0.24 | South | 150 | 4.28 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37100 | Costa Sur | Acacias TC | 2026-05-18 | 0.09 | South | 150 | 1.68 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37400 | Cambalache TC | Dos Bocas HP | 2026-05-18 | 0.08 | West | 150 | 1.37 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 38200 | Palo Seco SP | Monacillos TC | 2026-05-18 | 0.13 | Metro | 150 | 2.35 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 39000 | Ponce Hostos | Barranquitas | 2026-05-18 | 0.09 | Metro | 150 | 1.62 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 39800 | Mayaguez GP | Acacias TC | 2026-05-18 | 0.14 | South | 150 | 2.48 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 39800 | Mayaguez GP | Acacias TC | 2026-05-18 | 0.26 | South | 150 | 4.76 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 50100 | Cambalache TC | Manati TC | 2026-05-18 | 0.27 | West | 150 | 4.96 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 50100 | Cambalache TC | Manati TC | 2026-05-18 | 0.22 | West | 150 | 3.96 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 50100 | Cambalache TC | Manati TC | 2026-05-18 | 0.16 | West | 150 | 2.95 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 50100 | Cambalache TC | Manati TC | 2026-05-18 | 0.22 | West | 150 | 3.99 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 50200 | Manati TC | Bayamon TC | 2026-05-18 | 0.38 | Metro | 150 | 6.94 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 1700 | Guanica TC | Yauco 2 HP | 2026-05-19 | 0.05 | South | 100 | 0.56 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2000 | San Sebastian TC | Las Marias | 2026-05-19 | 0.1 | WEST | 100 | 1.27 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 3500 | Las Lomas | Monacillos | 2026-05-19 | 0.05 | Metro | 100 | 0.64 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 3800 | Comerio | Cidra | 2026-05-19 | 0.09 | East | 100 | 1.15 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 3800 | Comerio | Cidra | 2026-05-19 | 0.05 | East | 100 | 0.56 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 3800 | Comerio | Cidra | 2026-05-19 | 0.05 | East | 100 | 0.64 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 3800 | Comerio | Cidra | 2026-05-19 | 0.06 | East | 100 | 0.71 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 4100 | Comerio | Bayamon | 2026-05-19 | 0.09 | Metro | 100 | 1.04 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36400 | Ponce Hostos | Villalba | 2026-05-19 | 0.13 | South | 150 | 2.37 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36400 | Dos Bocas | Jayuya | 2026-05-19 | 0.13 | South | 150 | 2.3 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37100 | Costa Sur | Acacias TC | 2026-05-19 | 0.2 | South | 150 | 3.67 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37100 | Costa Sur | Acacias TC | 2026-05-19 | 0.1 | South | 150 | 1.86 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37400 | Cambalache TC | Dos Bocas HP | 2026-05-19 | 0.05 | West | 150 | 0.99 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 38300 | SJSP | Monacillos | 2026-05-19 | 0.09 | Metro | 150 | 1.64 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 50100 | Cambalache TC | Manati TC | 2026-05-19 | 0.19 | West | 150 | 3.45 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 50100 | Cambalache TC | Manati TC | 2026-05-19 | 0.15 | West | 150 | 2.73 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 50100 | Cambalache TC | Manati TC | 2026-05-19 | 0.2 | West | 150 | 3.67 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 50100 | Cambalache TC | Manati TC | 2026-05-19 | 0.24 | West | 150 | 4.33 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 51200 | Costa Sur | Cambalache | 2026-05-19 | 0.1 | West | 150 | 1.73 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
956345 | 38 | 2400 | Dos Bocas HP | Caonillas 2 | 2026-05-20 | 0.07 | Arecibo | 100 | 0.85 | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
N/A | 38 | 3800 | Comerio | Cidra | 2026-05-20 | 0.07 | East | 100 | 0.84 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 3800 | Comerio | Cidra | 2026-05-20 | 0.14 | East | 100 | 1.74 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 3800 | Comerio | Cidra | 2026-05-20 | 0.14 | East | 100 | 1.74 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36400 | Ponce Hostos | Villalba | 2026-05-20 | 0.13 | South | 150 | 2.37 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36400 | Ponce Hostos | Villalba | 2026-05-20 | 0.14 | South | 150 | 2.58 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36400 | Ponce Hostos | Villalba | 2026-05-20 | 0.08 | South | 150 | 1.51 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36400 | Dos Bocas | Jayuya | 2026-05-20 | 0.09 | South | 150 | 1.58 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36400 | Dos Bocas | Jayuya | 2026-05-20 | 0.13 | South | 150 | 2.3 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
956349 | 115 | 36800 | Canovanas TC | Palmer TC | 2026-05-20 | 0.1 | San Juan | 150 | 1.82 | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
N/A | 115 | 37100 | Costa Sur | Acacias TC | 2026-05-20 | 0.13 | South | 150 | 2.4 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37100 | Costa Sur | Acacias TC | 2026-05-20 | 0.1 | South | 150 | 1.76 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37100 | Costa Sur | Acacias TC | 2026-05-20 | 0.13 | South | 150 | 2.44 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37100 | Costa Sur | Acacias TC | 2026-05-20 | 0.09 | South | 150 | 1.69 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37100 | Costa Sur | Acacias TC | 2026-05-20 | 0.09 | South | 150 | 1.69 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37100 | Costa Sur | Acacias TC | 2026-05-20 | 0.09 | South | 150 | 1.69 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37400 | Cambalache TC | Dos Bocas HP | 2026-05-20 | 0.18 | West | 150 | 3.36 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37400 | Dorado | Vega Baja | 2026-05-20 | 0.16 | West | 150 | 2.88 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37900 | Monacillos | Sabana Llana | 2026-05-20 | 0.18 | Metro | 150 | 3.33 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 39800 | Mayaguez GP | Acacias TC | 2026-05-20 | 0.22 | South | 150 | 3.94 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 39800 | Mayaguez GP | Acacias TC | 2026-05-20 | 0.17 | South | 150 | 3.06 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 50100 | Cambalache TC | Manati TC | 2026-05-20 | 0.2 | West | 150 | 3.56 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 50100 | Cambalache TC | Manati TC | 2026-05-20 | 0.16 | West | 150 | 2.92 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 51200 | Costa Sur | Cambalache | 2026-05-20 | 0.08 | West | 150 | 1.54 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Dorado | Vega Alta | 2026-05-21 | 0.05 | Metro | 100 | 0.57 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Dorado | Vega Alta | 2026-05-21 | 0.05 | Metro | 100 | 0.55 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Dorado | Vega Alta | 2026-05-21 | 0.04 | Metro | 100 | 0.45 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Dorado | Vega Alta | 2026-05-21 | 0.05 | Metro | 100 | 0.57 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Dorado | Vega Alta | 2026-05-21 | 0.05 | Metro | 100 | 0.57 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-21 | 0.03 | Metro | 100 | 0.34 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-21 | 0.05 | Metro | 100 | 0.56 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-21 | 0.05 | Metro | 100 | 0.56 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Dorado | Vega Alta | 2026-05-21 | 0.04 | Metro | 100 | 0.45 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 3100 | Monacillos | Sabana Llana | 2026-05-21 | 0.06 | Metro | 100 | 0.77 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 3500 | Las Lomas | Monacillos | 2026-05-21 | 0.07 | Metro | 100 | 0.86 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 3800 | Comerio | Cidra | 2026-05-21 | 0.08 | East | 100 | 0.97 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36400 | Ponce Hostos | Villalba | 2026-05-21 | 0.09 | South | 150 | 1.66 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36400 | Ponce Hostos | Villalba | 2026-05-21 | 0.09 | South | 150 | 1.68 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36400 | Dos Bocas | Jayuya | 2026-05-21 | 0.08 | South | 150 | 1.44 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36800 | Sabana Llana TC | Canovanas TC | 2026-05-21 | 0.21 | Metro | 150 | 3.9 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36800 | Sabana Llana TC | Canovanas TC | 2026-05-21 | 0.09 | Metro | 150 | 1.64 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
956349 | 115 | 36800 | Canovanas TC | Palmer TC | 2026-05-21 | 0.32 | San Juan | 150 | 5.82 | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
N/A | 115 | 37100 | Costa Sur | Acacias TC | 2026-05-21 | 0.26 | South | 150 | 4.7 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37100 | Costa Sur | Acacias TC | 2026-05-21 | 0.21 | South | 150 | 3.76 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37100 | Costa Sur | Acacias TC | 2026-05-21 | 0.2 | South | 150 | 3.55 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37400 | Cambalache TC | Dos Bocas HP | 2026-05-21 | 0.13 | West | 150 | 2.4 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 39800 | Mayaguez GP | Acacias TC | 2026-05-21 | 0.11 | South | 150 | 2.03 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 50100 | Cambalache TC | Manati TC | 2026-05-21 | 0.18 | West | 150 | 3.23 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 50100 | Cambalache TC | Manati TC | 2026-05-21 | 0.22 | West | 150 | 3.91 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 51200 | Costa Sur | Cambalache | 2026-05-21 | 0.18 | West | 150 | 3.3 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-22 | 0.03 | Metro | 100 | 0.35 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-22 | 0.03 | Metro | 100 | 0.36 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-22 | 0.03 | Metro | 100 | 0.37 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Dorado | Vega Alta | 2026-05-22 | 0.04 | Metro | 100 | 0.48 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Dorado | Vega Alta | 2026-05-22 | 0.03 | Metro | 100 | 0.33 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-22 | 0.03 | Metro | 100 | 0.31 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-22 | 0.03 | Metro | 100 | 0.31 | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-22 | 0.03 | Metro | 100 | 0.31 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-22 | 0.04 | Metro | 100 | 0.46 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 3800 | Comerio | Cidra | 2026-05-22 | 0.07 | East | 100 | 0.88 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 3800 | Comerio | Cidra | 2026-05-22 | 0.07 | East | 100 | 0.85 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 6900 | Cambalache TC | Mirador Azul Sect | 2026-05-22 | 0.03 | WEST | 100 | 0.34 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 6900 | Cambalache TC | Mirador Azul Sect | 2026-05-22 | 0.03 | WEST | 100 | 0.34 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 6900 | Cambalache TC | Mirador Azul Sect | 2026-05-22 | 0.04 | WEST | 100 | 0.44 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 6900 | Cambalache TC | Mirador Azul Sect | 2026-05-22 | 0.05 | WEST | 100 | 0.6 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 8200 | Guaynabo |  | 2026-05-22 | 0.05 | Metro | 100 | 0.6 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36400 | Ponce Hostos | Villalba | 2026-05-22 | 0.14 | South | 150 | 2.56 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36800 | Sabana Llana TC | Canovanas TC | 2026-05-22 | 0.16 | Metro | 150 | 2.96 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
956349 | 115 | 36800 | Canovanas TC | Palmer TC | 2026-05-22 | 0.16 | San Juan | 150 | 2.91 | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
N/A | 230 | 50100 | Manati TC | Cambalache TC | 2026-05-22 | 0.08 | West | 150 | 1.4 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 50200 | Manati TC | Bayamon TC | 2026-05-22 | 0.17 | Metro | 150 | 3.16 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 50200 | Manati TC | Bayamon TC | 2026-05-22 | 0.05 | Metro | 150 | 0.93 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Dorado | Vega Alta | 2026-05-23 | 0.03 | Metro | 100 | 0.32 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Dorado | Vega Alta | 2026-05-23 | 0.03 | Metro | 100 | 0.39 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Dorado | Vega Alta | 2026-05-23 | 0.03 | Metro | 100 | 0.34 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Dorado | Vega Alta | 2026-05-23 | 0.09 | Metro | 100 | 1.04 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Dorado | Vega Alta | 2026-05-23 | 0.04 | Metro | 100 | 0.44 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Dorado | Vega Alta | 2026-05-23 | 0.03 | Metro | 100 | 0.32 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Dorado | Vega Alta | 2026-05-23 | 0.02 | Metro | 100 | 0.23 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Dorado | Vega Alta | 2026-05-23 | 0.02 | Metro | 100 | 0.24 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-23 | 0.05 | Metro | 100 | 0.56 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-23 | 0.02 | Metro | 100 | 0.22 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-23 | 0.07 | Metro | 100 | 0.81 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 3800 | Comerio | Cidra | 2026-05-23 | 0.04 | East | 100 | 0.53 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 9400 | Dorado TC | Toa Alta | 2026-05-23 | 0.04 | Metro | 100 | 0.44 | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36400 | Dos Bocas | Jayuya | 2026-05-23 | 0.09 | South | 150 | 1.66 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36400 | Dos Bocas | Jayuya | 2026-05-23 | 0.14 | South | 150 | 2.51 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36400 | Dos Bocas | Jayuya | 2026-05-23 | 0.14 | South | 150 | 2.51 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36400 | Dos Bocas | Jayuya | 2026-05-23 | 0.09 | South | 150 | 1.66 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36400 | Dos Bocas | Jayuya | 2026-05-23 | 0.15 | South | 150 | 2.68 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37000 | Costa Sur | Ponce Hostos | 2026-05-23 | 0.07 | South | 150 | 1.2 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37000 | Costa Sur | Ponce Hostos | 2026-05-23 | 0.11 | South | 150 | 2.02 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37000 | Costa Sur | Ponce Hostos | 2026-05-23 | 0.09 | South | 150 | 1.68 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37100 | Costa Sur | Acacias TC | 2026-05-23 | 0.06 | South | 150 | 1.15 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37100 | Costa Sur | Acacias TC | 2026-05-23 | 0.22 | South | 150 | 4.09 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37100 | Costa Sur | Acacias TC | 2026-05-23 | 0.13 | South | 150 | 2.39 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37100 | Costa Sur | Acacias TC | 2026-05-23 | 0.09 | South | 150 | 1.68 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 50100 | Manati TC | Cambalache TC | 2026-05-23 | 0.15 | West | 150 | 2.65 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 50100 | Cambalache TC | Manati TC | 2026-05-23 | 0.16 | West | 150 | 2.88 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 50100 | Cambalache TC | Manati TC | 2026-05-23 | 0.26 | West | 150 | 4.8 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 50100 | Cambalache TC | Manati TC | 2026-05-23 | 0.19 | West | 150 | 3.42 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 50100 | Cambalache TC | Manati TC | 2026-05-23 | 0.15 | West | 150 | 2.65 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 50100 | Cambalache TC | Manati TC | 2026-05-23 | 0.15 | West | 150 | 2.69 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 51200 | Costa Sur | Cambalache | 2026-05-23 | 0.12 | West | 150 | 2.16 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 51200 | Costa Sur | Cambalache | 2026-05-23 | 0.12 | West | 150 | 2.16 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 51200 | Costa Sur | Cambalache | 2026-05-23 | 0.11 | West | 150 | 2.04 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 3100 | Monacillos | Saint Just | 2026-05-25 | 0.08 | Metro | 100 | 1.03 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 3800 | Comerio | Cidra | 2026-05-25 | 0.06 | East | 100 | 0.71 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-26 | 0.02 | Metro | 100 | 0.3 | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-26 | 0.04 | Metro | 100 | 0.45 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-26 | 0.04 | Metro | 100 | 0.5 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-26 | 0.03 | Metro | 100 | 0.34 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 3100 | Monacillos | Saint Just | 2026-05-26 | 0.05 | Metro | 100 | 0.55 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 3100 | Monacillos | Saint Just | 2026-05-26 | 0.04 | Metro | 100 | 0.54 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 6900 | Cambalache TC | Mirador Azul Sect | 2026-05-26 | 0.03 | WEST | 100 | 0.36 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 6900 | Cambalache TC | Mirador Azul Sect | 2026-05-26 | 0.04 | WEST | 100 | 0.48 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 6900 | Cambalache TC | Mirador Azul Sect | 2026-05-26 | 0.03 | WEST | 100 | 0.4 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36400 | Dos Bocas | Jayuya | 2026-05-26 | 0.15 | South | 150 | 2.68 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36400 | Dos Bocas | Jayuya | 2026-05-26 | 0.15 | South | 150 | 2.68 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36800 | Sabana Llana TC | Canovanas TC | 2026-05-26 | 0.15 | Metro | 150 | 2.67 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37100 | Costa Sur | Acacias TC | 2026-05-26 | 0.19 | South | 150 | 3.43 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37100 | Costa Sur | Acacias TC | 2026-05-26 | 0.19 | South | 150 | 3.43 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37100 | Costa Sur | Acacias TC | 2026-05-26 | 0.26 | South | 150 | 4.7 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37100 | Costa Sur | Acacias TC | 2026-05-26 | 0.16 | South | 150 | 2.89 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37400 | Dorado | Vega Baja | 2026-05-26 | 0.17 | West | 150 | 3.11 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 39000 | Ponce Hostos | Barranquitas | 2026-05-26 | 0.12 | Metro | 150 | 2.22 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 39800 | Mayaguez GP | Acacias TC | 2026-05-26 | 0.33 | South | 150 | 5.95 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 50100 | Cambalache TC | Manati TC | 2026-05-26 | 0.08 | West | 150 | 1.4 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 50100 | Cambalache TC | Manati TC | 2026-05-26 | 0.17 | West | 150 | 3.05 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 50100 | Cambalache TC | Manati TC | 2026-05-26 | 0.29 | West | 150 | 5.2 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-27 | 0.06 | Metro | 100 | 0.75 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-27 | 0.05 | Metro | 100 | 0.66 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-27 | 0.03 | Metro | 100 | 0.36 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-27 | 0.03 | Metro | 100 | 0.36 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-27 | 0.03 | Metro | 100 | 0.37 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-27 | 0.03 | Metro | 100 | 0.32 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
956345 | 38 | 2400 | Dos Bocas HP | Caonillas 2 | 2026-05-27 | 0.05 | Arecibo | 100 | 0.61 | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
N/A | 38 | 3100 | Sabana Llana | Carolina | 2026-05-27 | 0.09 | Metro | 100 | 1.11 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 3100 | Sabana Llana | Carolina | 2026-05-27 | 0.05 | Metro | 100 | 0.66 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 3100 | Sabana Llana | Carolina | 2026-05-27 | 0.15 | Metro | 100 | 1.82 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 3800 | Comerio | Cidra | 2026-05-27 | 0.08 | East | 100 | 0.92 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 3800 | Comerio | Cidra | 2026-05-27 | 0.18 | East | 100 | 2.16 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 6900 | Cambalache TC | Mirador Azul Sect | 2026-05-27 | 0.03 | WEST | 100 | 0.39 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 6900 | Cambalache TC | Mirador Azul Sect | 2026-05-27 | 0.05 | WEST | 100 | 0.66 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36400 | Dos Bocas | Jayuya | 2026-05-27 | 0.07 | South | 150 | 1.23 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36400 | Dos Bocas | Jayuya | 2026-05-27 | 0.07 | South | 150 | 1.23 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36800 | Sabana Llana TC | Canovanas TC | 2026-05-27 | 0.21 | Metro | 150 | 3.9 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37000 | Costa Sur | Ponce Hostos | 2026-05-27 | 0.08 | South | 150 | 1.46 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37100 | Costa Sur | Acacias TC | 2026-05-27 | 0.11 | South | 150 | 1.95 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37100 | Costa Sur | Acacias TC | 2026-05-27 | 0.15 | South | 150 | 2.72 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37100 | Costa Sur | Acacias TC | 2026-05-27 | 0.12 | South | 150 | 2.11 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 50100 | Cambalache TC | Manati TC | 2026-05-27 | 0.14 | West | 150 | 2.47 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 50100 | Cambalache TC | Manati TC | 2026-05-27 | 0.18 | West | 150 | 3.19 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 51200 | Costa Sur | Cambalache | 2026-05-27 | 0.15 | West | 150 | 2.69 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-28 | 0.05 | Metro | 100 | 0.56 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-28 | 0.03 | Metro | 100 | 0.4 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-28 | 0.04 | Metro | 100 | 0.48 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-28 | 0.03 | Metro | 100 | 0.36 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-28 | 0.04 | Metro | 100 | 0.46 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-28 | 0.03 | Metro | 100 | 0.42 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-28 | 0.03 | Metro | 100 | 0.37 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-28 | 0.03 | Metro | 100 | 0.33 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-28 | 0.03 | Metro | 100 | 0.39 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-28 | 0.03 | Metro | 100 | 0.35 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-28 | 0.03 | Metro | 100 | 0.35 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-28 | 0.03 | Metro | 100 | 0.34 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-28 | 0.03 | Metro | 100 | 0.36 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-28 | 0.03 | Metro | 100 | 0.33 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-28 | 0.03 | Metro | 100 | 0.36 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-28 | 0.03 | Metro | 100 | 0.36 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-28 | 0.03 | Metro | 100 | 0.35 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-28 | 0.03 | Metro | 100 | 0.39 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-28 | 0.03 | Metro | 100 | 0.32 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-28 | 0.04 | Metro | 100 | 0.5 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-28 | 0.02 | Metro | 100 | 0.25 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-28 | 0.03 | Metro | 100 | 0.36 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-28 | 0.03 | Metro | 100 | 0.33 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-28 | 0.01 | Metro | 100 | 0.08 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-28 | 0.03 | Metro | 100 | 0.37 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-28 | 0.04 | Metro | 100 | 0.43 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-28 | 0.03 | Metro | 100 | 0.37 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-28 | 0.03 | Metro | 100 | 0.36 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
956345 | 38 | 2400 | Dos Bocas HP | Caonillas 2 | 2026-05-28 | 0.04 | Arecibo | 100 | 0.48 | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
N/A | 38 | 3100 | Sabana Llana | Carolina | 2026-05-28 | 0.01 | Metro | 100 | 0.16 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 3100 | Sabana Llana | Carolina | 2026-05-28 | 0.08 | Metro | 100 | 1.02 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 3800 | Comerio | Cidra | 2026-05-28 | 0.07 | East | 100 | 0.85 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 3800 | Comerio | Cidra | 2026-05-28 | 0.04 | East | 100 | 0.48 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 6900 | Cambalache TC | Mirador Azul Sect | 2026-05-28 | 0.05 | WEST | 100 | 0.57 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 6900 | Cambalache TC | Mirador Azul Sect | 2026-05-28 | 0.01 | WEST | 100 | 0.09 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 6900 | Cambalache TC | Mirador Azul Sect | 2026-05-28 | 0.06 | WEST | 100 | 0.7 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 6900 | Cambalache TC | Mirador Azul Sect | 2026-05-28 | 0.04 | WEST | 100 | 0.46 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36200 | Monacillos | Villa Betina | 2026-05-28 | 0.13 | Metro | 150 | 2.37 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
956349 | 115 | 36800 | Canovanas TC | Palmer TC | 2026-05-28 | 0.09 | San Juan | 150 | 1.64 | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
N/A | 115 | 37000 | Costa Sur | Ponce Hostos | 2026-05-28 | 0.1 | South | 150 | 1.84 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37100 | Costa Sur | Acacias TC | 2026-05-28 | 0.15 | South | 150 | 2.72 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37100 | Costa Sur | Acacias TC | 2026-05-28 | 0.12 | South | 150 | 2.11 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37400 | Vega Alta | Arecibo | 2026-05-28 | 0.16 | West | 150 | 2.95 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37400 | Vega Alta | Arecibo | 2026-05-28 | 0.1 | West | 150 | 1.81 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37900 | Monacillos | Sabana Llana | 2026-05-28 | 0.28 | Metro | 150 | 5.07 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37900 | Monacillos | Sabana Llana | 2026-05-28 | 0.08 | Metro | 150 | 1.53 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 39000 | Ponce Hostos | Barranquitas | 2026-05-28 | 0.23 | Metro | 150 | 4.15 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 39000 | Ponce Hostos | Barranquitas | 2026-05-28 | 0.11 | Metro | 150 | 2.03 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 39000 | Ponce Hostos | Barranquitas | 2026-05-28 | 0.13 | Metro | 150 | 2.31 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 39000 | Ponce Hostos | Barranquitas | 2026-05-28 | 0.19 | Metro | 150 | 3.43 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 50100 | Cambalache TC | Manati TC | 2026-05-28 | 0.17 | West | 150 | 3.07 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 50200 | Manati TC | Bayamon TC | 2026-05-28 | 0.13 | Metro | 150 | 2.31 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 51200 | Costa Sur | Cambalache | 2026-05-28 | 0.12 | West | 150 | 2.16 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-29 | 0.03 | Metro | 100 | 0.36 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-29 | 0.04 | Metro | 100 | 0.48 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-29 | 0.03 | Metro | 100 | 0.37 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-29 | 0.03 | Metro | 100 | 0.4 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-29 | 0.05 | Metro | 100 | 0.57 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-29 | 0.04 | Metro | 100 | 0.46 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-29 | 0.04 | Metro | 100 | 0.46 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-29 | 0.01 | Metro | 100 | 0.16 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-29 | 0.06 | Metro | 100 | 0.68 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-29 | 0.05 | Metro | 100 | 0.57 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-29 | 0.02 | Metro | 100 | 0.27 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-29 | 0.04 | Metro | 100 | 0.53 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
956345 | 38 | 2400 | Dos Bocas HP | Caonillas 2 | 2026-05-29 | 0.04 | Arecibo | 100 | 0.48 | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
N/A | 38 | 3800 | Comerio | Cidra | 2026-05-29 | 0.05 | East | 100 | 0.63 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 6900 | Cambalache TC | Mirador Azul Sect | 2026-05-29 | 0.07 | WEST | 100 | 0.84 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 11400 | Barceloneta TC | Florida | 2026-05-29 | 0.07 | WEST | 100 | 0.79 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 14400 | Acacias TC | Cabo Rojo | 2026-05-29 | 0.06 | East | 100 | 0.74 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 14400 | Caguas | San Lorenzo | 2026-05-29 | 0.02 | East | 100 | 0.28 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36400 | Dos Bocas | Jayuya | 2026-05-29 | 0.21 | South | 150 | 3.77 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 36400 | Dos Bocas | Jayuya | 2026-05-29 | 0.21 | South | 150 | 3.77 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37100 | Costa Sur | Acacias TC | 2026-05-29 | 0.14 | South | 150 | 2.54 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37400 | Vega Alta | Arecibo | 2026-05-29 | 0.2 | West | 150 | 3.55 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 50100 | Cambalache TC | Manati TC | 2026-05-29 | 0.19 | West | 150 | 3.44 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 50100 | Cambalache TC | Manati TC | 2026-05-29 | 0.21 | West | 150 | 3.8 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 50200 | Manati TC | Bayamon TC | 2026-05-29 | 0.13 | Metro | 150 | 2.31 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-30 | 0.02 | Metro | 100 | 0.28 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-30 | 0.02 | Metro | 100 | 0.27 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-30 | 0.02 | Metro | 100 | 0.28 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-30 | 0.04 | Metro | 100 | 0.52 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-30 | 0.03 | Metro | 100 | 0.39 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-30 | 0.04 | Metro | 100 | 0.5 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-30 | 0.05 | Metro | 100 | 0.59 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-30 | 0.02 | Metro | 100 | 0.26 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-30 | 0.03 | Metro | 100 | 0.41 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 2200 | Vega Alta | Cambalache | 2026-05-30 | 0.03 | Metro | 100 | 0.35 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 14400 | Caguas | San Lorenzo | 2026-05-30 | 0.05 | East | 100 | 0.66 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37100 | Costa Sur | Acacias TC | 2026-05-30 | 0.05 | South | 150 | 0.85 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 37100 | Costa Sur | Acacias TC | 2026-05-30 | 0.05 | South | 150 | 0.85 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 39100 | Victoria TC | Cambalache TC | 2026-05-30 | 0.12 | West | 150 | 2.16 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 115 | 39100 | Victoria TC | Cambalache TC | 2026-05-30 | 0.11 | West | 150 | 2.04 | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 50100 | Manati TC | Cambalache TC | 2026-05-30 | 0.15 | West | 150 | 2.76 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 230 | 50100 | Cambalache TC | Manati TC | 2026-05-30 | 0.12 | West | 150 | 2.2 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 13400 | Acacias TC | Cabo Rojo | 2026-05-31 | 0.04 | West | 100 | 0.45 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 13500 | Acacias TC | Cabo Rojo | 2026-05-31 | 0.03 | WEST | 100 | 0.31 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 13500 | Acacias TC | Cabo Rojo | 2026-05-31 | 0.03 | WEST | 100 | 0.31 | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 38 | 600 | Caguas Tc | Gautier Benitez Sect | 2026-06-03 | 0.03 | Caguas | 100 | 0.42 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 1500 | Comsat Sect | Cidra Sect | 2026-06-27 | 0.19 | Mayaguez | 100 | 2.29 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 1900 | Dos Bocas Hp | San Sebastian Tc | 2026-06-20 | 0.21 | Arecibo | 100 | 2.54 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 1900 | Dos Bocas Hp | San Sebastian Tc | 2026-06-14 | 0.21 | Arecibo | 100 | 2.54 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 1900 | Dos Bocas Hp | San Sebastian Tc | 2026-06-13 | 0.06 | Mayaguez | 100 | 0.77 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 1900 | Dos Bocas Hp | San Sebastian Tc | 2026-06-14 | 0.12 | Arecibo | 100 | 1.41 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 1900 | Dos Bocas Hp | San Sebastian Tc | 2026-06-15 | 0.12 | Arecibo | 100 | 1.41 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 1900 | Dos Bocas Hp | San Sebastian Tc | 2026-06-16 | 0.07 | Arecibo | 100 | 0.82 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 1900 | Dos Bocas Hp | San Sebastian Tc | 2026-06-19 | 0.13 | Arecibo | 100 | 1.59 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 1900 | Dos Bocas Hp | San Sebastian Tc | 2026-06-23 | 0.15 | Mayaguez | 100 | 1.78 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 1900 | Dos Bocas Hp | San Sebastian Tc | 2026-06-25 | 0.18 | Arecibo | 100 | 2.23 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 1900 | Dos Bocas Hp | San Sebastian Tc | 2026-06-27 | 0.16 | Mayaguez | 100 | 1.88 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2000 | Mayaguez Gp | Colegio Sect | 2026-06-20 | 0.18 | Mayaguez | 100 | 2.21 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2000 | Mayaguez Gp | Colegio Sect | 2026-06-20 | 0.06 | Mayaguez | 100 | 0.72 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2000 | Mayaguez Gp | Colegio Sect | 2026-06-23 | 0.08 | Mayaguez | 100 | 0.92 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2000 | Mayaguez Gp | Colegio Sect | 2026-06-23 | 0.07 | Mayaguez | 100 | 0.83 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2000 | Mayaguez Gp | Colegio Sect | 2026-06-25 | 0.08 | Mayaguez | 100 | 0.98 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2000 | Mayaguez Gp | Colegio Sect | 2026-06-30 | 0.12 | Mayaguez | 100 | 1.41 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2100 | Dos Bocas Hp | Hatillo Tc | 2026-06-23 | 0.09 | Arecibo | 100 | 1.05 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2100 | Dos Bocas Hp | Hatillo Tc | 2026-06-23 | 0.03 | Arecibo | 100 | 0.34 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2100 | Dos Bocas Hp | Hatillo Tc | 2026-06-23 | 0.09 | Arecibo | 100 | 1.05 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-17 | 0.03 | Arecibo | 100 | 0.38 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-24 | 0.03 | Arecibo | 100 | 0.38 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-23 | 0.03 | Arecibo | 100 | 0.38 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-29 | 0.01 | Bayamon | 100 | 0.11 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-10 | 0.04 | Bayamon | 100 | 0.49 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-12 | 0.04 | Bayamon | 100 | 0.46 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-12 | 0.03 | Bayamon | 100 | 0.42 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-24 | 0.03 | Arecibo | 100 | 0.34 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-24 | 0.04 | Arecibo | 100 | 0.48 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-24 | 0.02 | Arecibo | 100 | 0.28 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-01 | 0.05 | Arecibo | 100 | 0.6 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-04 | 0.03 | Arecibo | 100 | 0.37 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-03 | 0.03 | Arecibo | 100 | 0.35 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-09 | 0.05 | Arecibo | 100 | 0.57 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-16 | 0.02 | Arecibo | 100 | 0.3 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-05 | 0.03 | Bayamon | 100 | 0.31 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-03 | 0.03 | Bayamon | 100 | 0.3 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-01 | 0.02 | Bayamon | 100 | 0.26 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-01 | 0.02 | Bayamon | 100 | 0.26 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-01 | 0.02 | Bayamon | 100 | 0.26 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-01 | 0.02 | Bayamon | 100 | 0.27 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-01 | 0.02 | Bayamon | 100 | 0.27 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-01 | 0.02 | Bayamon | 100 | 0.26 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-12 | 0.04 | Bayamon | 100 | 0.52 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-12 | 0.04 | Bayamon | 100 | 0.45 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-12 | 0.04 | Bayamon | 100 | 0.45 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-12 | 0.04 | Bayamon | 100 | 0.44 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-10 | 0.04 | Bayamon | 100 | 0.45 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-09 | 0.04 | Bayamon | 100 | 0.48 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-10 | 0.04 | Bayamon | 100 | 0.49 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-18 | 0.08 | Bayamon | 100 | 0.94 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-16 | 0.04 | Bayamon | 100 | 0.5 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-16 | 0.04 | Bayamon | 100 | 0.47 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-15 | 0.04 | Bayamon | 100 | 0.44 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-01 | 0.04 | Arecibo | 100 | 0.47 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-15 | 0.04 | Bayamon | 100 | 0.46 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-18 | 0.06 | Bayamon | 100 | 0.75 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-22 | 0.06 | Bayamon | 100 | 0.75 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-22 | 0.09 | Bayamon | 100 | 1.04 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-22 | 0.02 | Bayamon | 100 | 0.28 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-22 | 0.02 | Bayamon | 100 | 0.2 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-22 | 0.02 | Bayamon | 100 | 0.22 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-01 | 0.02 | Arecibo | 100 | 0.29 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-23 | 0.03 | Bayamon | 100 | 0.32 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-01 | 0.02 | Arecibo | 100 | 0.22 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-02 | 0.04 | Arecibo | 100 | 0.47 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-27 | 0.03 | Bayamon | 100 | 0.31 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-27 | 0.03 | Bayamon | 100 | 0.32 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-27 | 0.04 | Bayamon | 100 | 0.53 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-24 | 0.03 | Bayamon | 100 | 0.34 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-03 | 0.03 | Arecibo | 100 | 0.39 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-27 | 0.04 | Bayamon | 100 | 0.48 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-27 | 0.05 | Bayamon | 100 | 0.58 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-27 | 0.05 | Bayamon | 100 | 0.55 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-27 | 0.05 | Bayamon | 100 | 0.63 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-30 | 0.05 | Bayamon | 100 | 0.6 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.03 | Arecibo | 100 | 0.4 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.03 | Arecibo | 100 | 0.31 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.03 | Arecibo | 100 | 0.39 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.03 | Arecibo | 100 | 0.31 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.03 | Arecibo | 100 | 0.37 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.03 | Arecibo | 100 | 0.42 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.03 | Arecibo | 100 | 0.31 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.03 | Arecibo | 100 | 0.3 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.02 | Arecibo | 100 | 0.24 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-27 | 0.03 | Arecibo | 100 | 0.33 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.03 | Arecibo | 100 | 0.34 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.03 | Arecibo | 100 | 0.34 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.03 | Bayamon | 100 | 0.32 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.02 | Bayamon | 100 | 0.28 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.03 | Bayamon | 100 | 0.32 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.04 | Bayamon | 100 | 0.45 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.03 | Bayamon | 100 | 0.31 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.02 | Bayamon | 100 | 0.26 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.03 | Bayamon | 100 | 0.32 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.03 | Bayamon | 100 | 0.34 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.03 | Bayamon | 100 | 0.3 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.03 | Bayamon | 100 | 0.35 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.02 | Bayamon | 100 | 0.3 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.01 | Bayamon | 100 | 0.15 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.02 | Bayamon | 100 | 0.25 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.02 | Bayamon | 100 | 0.21 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.02 | Bayamon | 100 | 0.29 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.04 | Bayamon | 100 | 0.45 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.02 | Bayamon | 100 | 0.28 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.03 | Bayamon | 100 | 0.33 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.03 | Bayamon | 100 | 0.35 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-27 | 0.02 | Bayamon | 100 | 0.3 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.02 | Bayamon | 100 | 0.3 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.03 | Bayamon | 100 | 0.36 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.03 | Bayamon | 100 | 0.34 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.02 | Bayamon | 100 | 0.25 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.05 | Bayamon | 100 | 0.64 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-27 | 0.02 | Bayamon | 100 | 0.29 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-27 | 0.02 | Bayamon | 100 | 0.26 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.04 | Bayamon | 100 | 0.45 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-27 | 0.05 | Bayamon | 100 | 0.55 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-27 | 0.05 | Bayamon | 100 | 0.6 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.04 | Bayamon | 100 | 0.53 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.04 | Bayamon | 100 | 0.47 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.05 | Bayamon | 100 | 0.57 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.05 | Bayamon | 100 | 0.57 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.04 | Bayamon | 100 | 0.52 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.02 | Bayamon | 100 | 0.2 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.03 | Bayamon | 100 | 0.42 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.02 | Bayamon | 100 | 0.27 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.03 | Bayamon | 100 | 0.42 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.04 | Bayamon | 100 | 0.44 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.04 | Bayamon | 100 | 0.5 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.02 | Bayamon | 100 | 0.24 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-29 | 0.02 | Bayamon | 100 | 0.29 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.02 | Bayamon | 100 | 0.27 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-27 | 0.03 | Bayamon | 100 | 0.34 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-27 | 0.03 | Bayamon | 100 | 0.36 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-27 | 0.01 | Bayamon | 100 | 0.15 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.01 | Bayamon | 100 | 0.14 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-22 | 0.03 | Bayamon | 100 | 0.37 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-27 | 0.01 | Bayamon | 100 | 0.15 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-22 | 0.03 | Bayamon | 100 | 0.35 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-22 | 0.02 | Bayamon | 100 | 0.26 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-22 | 0.03 | Bayamon | 100 | 0.35 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-22 | 0.01 | Bayamon | 100 | 0.15 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-22 | 0.03 | Bayamon | 100 | 0.36 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-22 | 0.02 | Bayamon | 100 | 0.29 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-22 | 0.02 | Bayamon | 100 | 0.24 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-22 | 0.02 | Bayamon | 100 | 0.29 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-22 | 0.02 | Bayamon | 100 | 0.28 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-22 | 0.02 | Bayamon | 100 | 0.2 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-22 | 0.03 | Bayamon | 100 | 0.37 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-22 | 0.03 | Bayamon | 100 | 0.32 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-22 | 0.04 | Bayamon | 100 | 0.44 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-01 | 0.05 | Arecibo | 100 | 0.56 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-01 | 0.02 | Arecibo | 100 | 0.22 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-02 | 0.05 | Arecibo | 100 | 0.59 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-03 | 0.04 | Arecibo | 100 | 0.51 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-02 | 0.05 | Arecibo | 100 | 0.57 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-01 | 0.03 | Arecibo | 100 | 0.33 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-01 | 0.05 | Arecibo | 100 | 0.56 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-09 | 0.02 | Bayamon | 100 | 0.21 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-09 | 0.02 | Bayamon | 100 | 0.19 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-05 | 0.02 | Bayamon | 100 | 0.24 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-05 | 0.03 | Bayamon | 100 | 0.31 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-09 | 0.01 | Bayamon | 100 | 0.16 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-01 | 0.02 | Bayamon | 100 | 0.26 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-01 | 0.02 | Bayamon | 100 | 0.27 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-01 | 0.05 | Arecibo | 100 | 0.59 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-08 | 0.03 | Bayamon | 100 | 0.31 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-08 | 0.02 | Bayamon | 100 | 0.25 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-08 | 0.02 | Bayamon | 100 | 0.25 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-05 | 0.05 | Arecibo | 100 | 0.56 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-05 | 0.03 | Bayamon | 100 | 0.38 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-05 | 0.03 | Bayamon | 100 | 0.42 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-04 | 0.04 | Arecibo | 100 | 0.43 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-02 | 0.02 | Arecibo | 100 | 0.28 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-05 | 0.02 | Bayamon | 100 | 0.26 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-08 | 0.03 | Bayamon | 100 | 0.33 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-09 | 0.02 | Bayamon | 100 | 0.23 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-03 | 0.05 | Arecibo | 100 | 0.6 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-09 | 0.02 | Bayamon | 100 | 0.19 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-10 | 0.04 | Bayamon | 100 | 0.46 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-05 | 0.05 | Arecibo | 100 | 0.59 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-11 | 0.03 | Bayamon | 100 | 0.42 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-12 | 0.04 | Bayamon | 100 | 0.49 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-15 | 0.04 | Bayamon | 100 | 0.53 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-16 | 0.06 | Bayamon | 100 | 0.74 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-09 | 0.003 | Arecibo | 100 | 0.03 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-09 | 0.03 | Arecibo | 100 | 0.41 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-11 | 0.04 | Arecibo | 100 | 0.47 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-11 | 0.04 | Arecibo | 100 | 0.43 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-11 | 0.03 | Arecibo | 100 | 0.37 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-12 | 0.02 | Arecibo | 100 | 0.29 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-01 | 0.04 | Arecibo | 100 | 0.47 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-12 | 0.03 | Arecibo | 100 | 0.31 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-15 | 0.03 | Arecibo | 100 | 0.31 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-12 | 0.02 | Arecibo | 100 | 0.24 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-13 | 0.03 | Arecibo | 100 | 0.38 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-13 | 0.03 | Arecibo | 100 | 0.35 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-15 | 0.04 | Arecibo | 100 | 0.46 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-03 | 0.03 | Arecibo | 100 | 0.31 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-03 | 0.03 | Arecibo | 100 | 0.34 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-03 | 0.03 | Arecibo | 100 | 0.41 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-04 | 0.03 | Arecibo | 100 | 0.32 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-01 | 0.01 | Arecibo | 100 | 0.11 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-01 | 0.02 | Arecibo | 100 | 0.26 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-01 | 0.02 | Arecibo | 100 | 0.27 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-01 | 0.02 | Arecibo | 100 | 0.23 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-01 | 0.01 | Arecibo | 100 | 0.17 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-01 | 0.03 | Arecibo | 100 | 0.35 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-01 | 0.02 | Arecibo | 100 | 0.25 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-01 | 0.03 | Arecibo | 100 | 0.37 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-01 | 0.02 | Arecibo | 100 | 0.3 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-01 | 0.04 | Arecibo | 100 | 0.46 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-01 | 0.04 | Arecibo | 100 | 0.44 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-08 | 0.02 | Arecibo | 100 | 0.22 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-06 | 0.02 | Arecibo | 100 | 0.21 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-05 | 0.03 | Arecibo | 100 | 0.32 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-07 | 0.02 | Arecibo | 100 | 0.23 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-08 | 0.01 | Arecibo | 100 | 0.13 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-05 | 0.03 | Arecibo | 100 | 0.32 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-08 | 0.03 | Arecibo | 100 | 0.32 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-08 | 0.03 | Arecibo | 100 | 0.32 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-08 | 0.03 | Arecibo | 100 | 0.32 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-08 | 0.03 | Arecibo | 100 | 0.32 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-02 | 0.05 | Arecibo | 100 | 0.58 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-05 | 0.05 | Arecibo | 100 | 0.56 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-03 | 0.02 | Arecibo | 100 | 0.26 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-15 | 0.03 | Arecibo | 100 | 0.33 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-11 | 0.02 | Arecibo | 100 | 0.29 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-09 | 0.03 | Arecibo | 100 | 0.32 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-11 | 0.03 | Arecibo | 100 | 0.32 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-11 | 0.03 | Arecibo | 100 | 0.32 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-12 | 0.02 | Arecibo | 100 | 0.24 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-11 | 0.02 | Arecibo | 100 | 0.26 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-10 | 0.003 | Arecibo | 100 | 0.03 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-02 | 0.04 | Arecibo | 100 | 0.5 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-02 | 0.05 | Arecibo | 100 | 0.55 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-02 | 0.04 | Arecibo | 100 | 0.54 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-02 | 0.05 | Arecibo | 100 | 0.6 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-02 | 0.04 | Arecibo | 100 | 0.51 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-03 | 0.17 | Arecibo | 100 | 2.08 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-04 | 0.01 | Arecibo | 100 | 0.08 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-03 | 0.02 | Arecibo | 100 | 0.22 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-03 | 0.03 | Arecibo | 100 | 0.32 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-03 | 0.03 | Arecibo | 100 | 0.34 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-03 | 0.04 | Arecibo | 100 | 0.48 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-03 | 0.03 | Arecibo | 100 | 0.36 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-03 | 0.02 | Arecibo | 100 | 0.3 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-03 | 0.03 | Arecibo | 100 | 0.41 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-03 | 0.03 | Arecibo | 100 | 0.4 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-03 | 0.02 | Arecibo | 100 | 0.29 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-03 | 0.03 | Arecibo | 100 | 0.34 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-03 | 0.03 | Arecibo | 100 | 0.33 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-03 | 0.03 | Arecibo | 100 | 0.36 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-03 | 0.03 | Arecibo | 100 | 0.36 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-03 | 0.03 | Arecibo | 100 | 0.36 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-03 | 0.03 | Arecibo | 100 | 0.32 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-03 | 0.02 | Arecibo | 100 | 0.3 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-03 | 0.02 | Arecibo | 100 | 0.26 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-03 | 0.02 | Arecibo | 100 | 0.22 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-03 | 0.02 | Arecibo | 100 | 0.25 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-03 | 0.03 | Arecibo | 100 | 0.35 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-03 | 0.03 | Arecibo | 100 | 0.39 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-03 | 0.03 | Arecibo | 100 | 0.41 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-03 | 0.02 | Arecibo | 100 | 0.3 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-03 | 0.03 | Arecibo | 100 | 0.38 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-04 | 0.02 | Arecibo | 100 | 0.28 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-03 | 0.02 | Arecibo | 100 | 0.25 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-03 | 0.03 | Arecibo | 100 | 0.36 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-03 | 0.02 | Arecibo | 100 | 0.29 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-03 | 0.03 | Arecibo | 100 | 0.4 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-03 | 0.03 | Arecibo | 100 | 0.38 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-03 | 0.05 | Arecibo | 100 | 0.6 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-03 | 0.03 | Arecibo | 100 | 0.38 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-03 | 0.03 | Arecibo | 100 | 0.31 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-03 | 0.03 | Arecibo | 100 | 0.3 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-04 | 0.03 | Arecibo | 100 | 0.35 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-04 | 0.03 | Arecibo | 100 | 0.35 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-04 | 0.03 | Arecibo | 100 | 0.34 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-04 | 0.03 | Arecibo | 100 | 0.35 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-04 | 0.03 | Arecibo | 100 | 0.35 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-04 | 0.03 | Arecibo | 100 | 0.34 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-04 | 0.03 | Arecibo | 100 | 0.39 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-04 | 0.05 | Arecibo | 100 | 0.56 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-04 | 0.05 | Arecibo | 100 | 0.56 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-08 | 0.03 | Arecibo | 100 | 0.32 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-08 | 0.03 | Arecibo | 100 | 0.33 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-06 | 0.03 | Arecibo | 100 | 0.32 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-06 | 0.03 | Arecibo | 100 | 0.32 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-06 | 0.02 | Arecibo | 100 | 0.29 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-11 | 0.01 | Arecibo | 100 | 0.16 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-16 | 0.01 | Arecibo | 100 | 0.1 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-16 | 0.02 | Arecibo | 100 | 0.26 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-16 | 0.05 | Arecibo | 100 | 0.55 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-16 | 0.05 | Arecibo | 100 | 0.55 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-16 | 0.03 | Arecibo | 100 | 0.31 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-16 | 0.03 | Arecibo | 100 | 0.39 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-16 | 0.03 | Arecibo | 100 | 0.39 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-16 | 0.02 | Arecibo | 100 | 0.21 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-16 | 0.02 | Arecibo | 100 | 0.27 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-16 | 0.02 | Arecibo | 100 | 0.28 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-16 | 0.02 | Arecibo | 100 | 0.3 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-16 | 0.003 | Arecibo | 100 | 0.04 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-16 | 0.01 | Arecibo | 100 | 0.17 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-16 | 0.002 | Arecibo | 100 | 0.02 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-16 | 0.01 | Arecibo | 100 | 0.18 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-16 | 0.02 | Arecibo | 100 | 0.21 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-16 | 0.02 | Arecibo | 100 | 0.26 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-16 | 0.002 | Arecibo | 100 | 0.02 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-16 | 0.01 | Arecibo | 100 | 0.14 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-16 | 0.02 | Arecibo | 100 | 0.24 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-16 | 0.03 | Arecibo | 100 | 0.4 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-16 | 0.04 | Arecibo | 100 | 0.5 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-16 | 0.03 | Arecibo | 100 | 0.36 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-16 | 0.04 | Arecibo | 100 | 0.47 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-16 | 0.01 | Arecibo | 100 | 0.17 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-16 | 0.003 | Arecibo | 100 | 0.03 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-16 | 0.01 | Arecibo | 100 | 0.17 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-16 | 0.03 | Arecibo | 100 | 0.31 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-16 | 0.002 | Arecibo | 100 | 0.03 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-08 | 0.03 | Arecibo | 100 | 0.32 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-08 | 0.03 | Arecibo | 100 | 0.33 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-08 | 0.03 | Arecibo | 100 | 0.32 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-08 | 0.03 | Arecibo | 100 | 0.32 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-08 | 0.03 | Arecibo | 100 | 0.32 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-09 | 0.03 | Arecibo | 100 | 0.32 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-09 | 0.03 | Arecibo | 100 | 0.31 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-09 | 0.03 | Arecibo | 100 | 0.32 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-09 | 0.03 | Arecibo | 100 | 0.32 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-09 | 0.03 | Arecibo | 100 | 0.32 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-08 | 0.05 | Arecibo | 100 | 0.56 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-09 | 0.03 | Arecibo | 100 | 0.32 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-10 | 0.03 | Arecibo | 100 | 0.33 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-08 | 0.04 | Arecibo | 100 | 0.48 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-08 | 0.03 | Arecibo | 100 | 0.41 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-12 | 0.02 | Arecibo | 100 | 0.2 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-12 | 0.03 | Arecibo | 100 | 0.34 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-12 | 0.02 | Arecibo | 100 | 0.19 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-12 | 0.02 | Arecibo | 100 | 0.23 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-27 | 0.02 | Arecibo | 100 | 0.23 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-12 | 0.02 | Arecibo | 100 | 0.23 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-15 | 0.02 | Arecibo | 100 | 0.26 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-16 | 0.01 | Arecibo | 100 | 0.11 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-08 | 0.04 | Arecibo | 100 | 0.45 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-09 | 0.05 | Arecibo | 100 | 0.56 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-12 | 0.05 | Arecibo | 100 | 0.56 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-12 | 0.04 | Arecibo | 100 | 0.48 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-12 | 0.03 | Arecibo | 100 | 0.42 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-10 | 0.05 | Arecibo | 100 | 0.61 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.03 | Arecibo | 100 | 0.32 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-12 | 0.03 | Arecibo | 100 | 0.35 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-13 | 0.03 | Arecibo | 100 | 0.36 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-22 | 0.02 | Arecibo | 100 | 0.18 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-24 | 0.03 | Arecibo | 100 | 0.36 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-20 | 0.03 | Arecibo | 100 | 0.31 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-20 | 0.03 | Arecibo | 100 | 0.36 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-15 | 0.03 | Arecibo | 100 | 0.33 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-17 | 0.03 | Arecibo | 100 | 0.38 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-19 | 0.03 | Arecibo | 100 | 0.38 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-19 | 0.03 | Arecibo | 100 | 0.38 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-24 | 0.03 | Arecibo | 100 | 0.37 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-11 | 0.03 | Arecibo | 100 | 0.4 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-11 | 0.02 | Arecibo | 100 | 0.28 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-11 | 0.01 | Arecibo | 100 | 0.07 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-11 | 0.02 | Arecibo | 100 | 0.27 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-11 | 0.02 | Arecibo | 100 | 0.26 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-11 | 0.03 | Arecibo | 100 | 0.35 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-11 | 0.03 | Arecibo | 100 | 0.35 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-11 | 0.04 | Arecibo | 100 | 0.46 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-11 | 0.04 | Arecibo | 100 | 0.44 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-11 | 0.05 | Arecibo | 100 | 0.63 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-15 | 0.02 | Arecibo | 100 | 0.29 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-11 | 0.03 | Arecibo | 100 | 0.32 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-25 | 0.03 | Arecibo | 100 | 0.33 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.03 | Arecibo | 100 | 0.37 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-17 | 0.03 | Arecibo | 100 | 0.35 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-25 | 0.03 | Arecibo | 100 | 0.35 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-12 | 0.04 | Arecibo | 100 | 0.43 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-12 | 0.04 | Arecibo | 100 | 0.5 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-12 | 0.03 | Arecibo | 100 | 0.36 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-15 | 0.03 | Arecibo | 100 | 0.39 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-12 | 0.03 | Arecibo | 100 | 0.32 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-15 | 0.05 | Arecibo | 100 | 0.61 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-13 | 0.03 | Arecibo | 100 | 0.39 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-07 | 0.04 | Arecibo | 100 | 0.53 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-06 | 0.03 | Arecibo | 100 | 0.34 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-07 | 0.03 | Arecibo | 100 | 0.35 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-06 | 0.05 | Arecibo | 100 | 0.59 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-24 | 0.04 | Arecibo | 100 | 0.46 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-24 | 0.03 | Arecibo | 100 | 0.42 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-24 | 0.04 | Arecibo | 100 | 0.48 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-24 | 0.04 | Arecibo | 100 | 0.44 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-24 | 0.04 | Arecibo | 100 | 0.45 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-24 | 0.04 | Arecibo | 100 | 0.46 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-24 | 0.04 | Arecibo | 100 | 0.46 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-24 | 0.04 | Arecibo | 100 | 0.45 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-24 | 0.03 | Arecibo | 100 | 0.4 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-24 | 0.04 | Arecibo | 100 | 0.45 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-24 | 0.04 | Arecibo | 100 | 0.46 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-24 | 0.04 | Arecibo | 100 | 0.47 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-25 | 0.04 | Arecibo | 100 | 0.44 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-25 | 0.04 | Arecibo | 100 | 0.44 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-25 | 0.03 | Arecibo | 100 | 0.36 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.03 | Arecibo | 100 | 0.33 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-15 | 0.03 | Arecibo | 100 | 0.39 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-15 | 0.03 | Arecibo | 100 | 0.36 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-15 | 0.02 | Arecibo | 100 | 0.22 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-15 | 0.02 | Arecibo | 100 | 0.25 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-18 | 0.03 | Arecibo | 100 | 0.35 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-15 | 0.02 | Arecibo | 100 | 0.28 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-15 | 0.03 | Arecibo | 100 | 0.31 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-15 | 0.04 | Arecibo | 100 | 0.43 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-15 | 0.03 | Arecibo | 100 | 0.42 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-15 | 0.03 | Arecibo | 100 | 0.39 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-15 | 0.03 | Arecibo | 100 | 0.4 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-15 | 0.03 | Arecibo | 100 | 0.36 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-15 | 0.04 | Arecibo | 100 | 0.43 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-15 | 0.03 | Arecibo | 100 | 0.32 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-15 | 0.03 | Arecibo | 100 | 0.42 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-15 | 0.03 | Arecibo | 100 | 0.34 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-15 | 0.04 | Arecibo | 100 | 0.43 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-15 | 0.02 | Arecibo | 100 | 0.23 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-15 | 0.02 | Arecibo | 100 | 0.2 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-15 | 0.02 | Arecibo | 100 | 0.26 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-15 | 0.02 | Arecibo | 100 | 0.25 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-15 | 0.04 | Arecibo | 100 | 0.47 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-15 | 0.03 | Arecibo | 100 | 0.36 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-15 | 0.04 | Arecibo | 100 | 0.43 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-15 | 0.04 | Arecibo | 100 | 0.49 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-15 | 0.04 | Arecibo | 100 | 0.44 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-15 | 0.03 | Arecibo | 100 | 0.4 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-15 | 0.04 | Arecibo | 100 | 0.46 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-15 | 0.02 | Arecibo | 100 | 0.24 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-15 | 0.03 | Arecibo | 100 | 0.32 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-15 | 0.03 | Arecibo | 100 | 0.38 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-15 | 0.04 | Arecibo | 100 | 0.43 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-15 | 0.04 | Arecibo | 100 | 0.49 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-16 | 0.03 | Arecibo | 100 | 0.4 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-15 | 0.03 | Arecibo | 100 | 0.38 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-15 | 0.03 | Arecibo | 100 | 0.31 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-15 | 0.03 | Arecibo | 100 | 0.34 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-15 | 0.03 | Arecibo | 100 | 0.38 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-15 | 0.02 | Arecibo | 100 | 0.23 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-15 | 0.01 | Arecibo | 100 | 0.16 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-15 | 0.03 | Arecibo | 100 | 0.37 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-19 | 0.02 | Arecibo | 100 | 0.29 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-22 | 0.02 | Arecibo | 100 | 0.29 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-15 | 0.01 | Arecibo | 100 | 0.16 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-15 | 0.01 | Arecibo | 100 | 0.14 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-16 | 0.03 | Arecibo | 100 | 0.34 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-16 | 0.03 | Arecibo | 100 | 0.35 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-16 | 0.03 | Arecibo | 100 | 0.34 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-16 | 0.03 | Arecibo | 100 | 0.36 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-16 | 0.03 | Arecibo | 100 | 0.34 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-16 | 0.03 | Arecibo | 100 | 0.35 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-16 | 0.03 | Arecibo | 100 | 0.34 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-16 | 0.03 | Arecibo | 100 | 0.35 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-16 | 0.03 | Arecibo | 100 | 0.34 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-15 | 0.02 | Arecibo | 100 | 0.2 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-18 | 0.02 | Arecibo | 100 | 0.29 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-15 | 0.03 | Arecibo | 100 | 0.36 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-15 | 0.03 | Arecibo | 100 | 0.35 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-15 | 0.03 | Arecibo | 100 | 0.37 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-17 | 0.02 | Arecibo | 100 | 0.29 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-17 | 0.03 | Arecibo | 100 | 0.31 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-18 | 0.03 | Arecibo | 100 | 0.34 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-22 | 0.03 | Arecibo | 100 | 0.35 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-25 | 0.03 | Arecibo | 100 | 0.36 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-25 | 0.03 | Arecibo | 100 | 0.33 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-25 | 0.03 | Arecibo | 100 | 0.37 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-25 | 0.04 | Arecibo | 100 | 0.48 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-25 | 0.03 | Arecibo | 100 | 0.39 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-25 | 0.03 | Arecibo | 100 | 0.38 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-20 | 0.03 | Arecibo | 100 | 0.39 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-24 | 0.03 | Arecibo | 100 | 0.35 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.04 | Arecibo | 100 | 0.45 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.04 | Arecibo | 100 | 0.45 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.03 | Arecibo | 100 | 0.35 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-25 | 0.05 | Arecibo | 100 | 0.55 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-25 | 0.03 | Arecibo | 100 | 0.36 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-17 | 0.02 | Arecibo | 100 | 0.27 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-17 | 0.03 | Arecibo | 100 | 0.33 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-17 | 0.03 | Arecibo | 100 | 0.36 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-17 | 0.03 | Arecibo | 100 | 0.32 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-17 | 0.03 | Arecibo | 100 | 0.38 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-17 | 0.03 | Arecibo | 100 | 0.42 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-17 | 0.03 | Arecibo | 100 | 0.35 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-17 | 0.02 | Arecibo | 100 | 0.24 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-17 | 0.02 | Arecibo | 100 | 0.21 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-17 | 0.02 | Arecibo | 100 | 0.19 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-17 | 0.02 | Arecibo | 100 | 0.19 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-17 | 0.03 | Arecibo | 100 | 0.37 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-17 | 0.02 | Arecibo | 100 | 0.2 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-18 | 0.03 | Arecibo | 100 | 0.35 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-27 | 0.03 | Arecibo | 100 | 0.41 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-29 | 0.03 | Arecibo | 100 | 0.4 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-30 | 0.02 | Arecibo | 100 | 0.23 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-18 | 0.03 | Arecibo | 100 | 0.35 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-18 | 0.03 | Arecibo | 100 | 0.35 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-18 | 0.03 | Arecibo | 100 | 0.34 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-18 | 0.03 | Arecibo | 100 | 0.32 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-18 | 0.03 | Arecibo | 100 | 0.36 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-18 | 0.03 | Arecibo | 100 | 0.35 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-18 | 0.02 | Arecibo | 100 | 0.2 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-18 | 0.03 | Arecibo | 100 | 0.35 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-18 | 0.03 | Arecibo | 100 | 0.34 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-18 | 0.03 | Arecibo | 100 | 0.31 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-18 | 0.03 | Arecibo | 100 | 0.31 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-22 | 0.04 | Arecibo | 100 | 0.43 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-18 | 0.02 | Arecibo | 100 | 0.23 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-19 | 0.02 | Arecibo | 100 | 0.29 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-19 | 0.01 | Arecibo | 100 | 0.18 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-19 | 0.02 | Arecibo | 100 | 0.19 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-19 | 0.03 | Arecibo | 100 | 0.34 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-20 | 0.01 | Arecibo | 100 | 0.17 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-20 | 0.03 | Arecibo | 100 | 0.31 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-22 | 0.03 | Arecibo | 100 | 0.35 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-22 | 0.03 | Arecibo | 100 | 0.34 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-22 | 0.03 | Arecibo | 100 | 0.34 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-29 | 0.03 | Arecibo | 100 | 0.35 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-29 | 0.04 | Arecibo | 100 | 0.48 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-29 | 0.03 | Arecibo | 100 | 0.35 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-29 | 0.03 | Arecibo | 100 | 0.36 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-22 | 0.03 | Arecibo | 100 | 0.34 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-22 | 0.03 | Arecibo | 100 | 0.35 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-20 | 0.02 | Arecibo | 100 | 0.23 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-20 | 0.02 | Arecibo | 100 | 0.18 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-20 | 0.02 | Arecibo | 100 | 0.2 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-27 | 0.01 | Arecibo | 100 | 0.18 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-27 | 0.03 | Arecibo | 100 | 0.4 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-27 | 0.03 | Arecibo | 100 | 0.32 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-29 | 0.03 | Arecibo | 100 | 0.37 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-29 | 0.03 | Arecibo | 100 | 0.36 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-30 | 0.02 | Arecibo | 100 | 0.28 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-23 | 0.01 | Arecibo | 100 | 0.12 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-23 | 0.02 | Arecibo | 100 | 0.29 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-23 | 0.02 | Arecibo | 100 | 0.3 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-23 | 0.02 | Arecibo | 100 | 0.26 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-23 | 0.02 | Arecibo | 100 | 0.27 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-23 | 0.02 | Arecibo | 100 | 0.29 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-23 | 0.02 | Arecibo | 100 | 0.24 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-23 | 0.02 | Arecibo | 100 | 0.27 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-25 | 0.02 | Arecibo | 100 | 0.25 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-25 | 0.03 | Arecibo | 100 | 0.39 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-25 | 0.02 | Arecibo | 100 | 0.22 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-25 | 0.03 | Arecibo | 100 | 0.36 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-25 | 0.03 | Arecibo | 100 | 0.33 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.03 | Arecibo | 100 | 0.35 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.03 | Arecibo | 100 | 0.34 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.03 | Arecibo | 100 | 0.33 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.03 | Arecibo | 100 | 0.34 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.03 | Arecibo | 100 | 0.33 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.03 | Arecibo | 100 | 0.32 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-24 | 0.03 | Arecibo | 100 | 0.37 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-24 | 0.03 | Arecibo | 100 | 0.33 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-24 | 0.03 | Arecibo | 100 | 0.37 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-25 | 0.03 | Arecibo | 100 | 0.38 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-25 | 0.02 | Arecibo | 100 | 0.23 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.02 | Arecibo | 100 | 0.28 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-25 | 0.02 | Arecibo | 100 | 0.24 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.03 | Arecibo | 100 | 0.32 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-25 | 0.02 | Arecibo | 100 | 0.29 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.02 | Arecibo | 100 | 0.28 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-25 | 0.03 | Arecibo | 100 | 0.31 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.02 | Arecibo | 100 | 0.23 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.02 | Arecibo | 100 | 0.23 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-25 | 0.02 | Arecibo | 100 | 0.3 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.03 | Arecibo | 100 | 0.31 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-25 | 0.02 | Arecibo | 100 | 0.27 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.02 | Arecibo | 100 | 0.19 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-25 | 0.01 | Arecibo | 100 | 0.11 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-25 | 0.03 | Arecibo | 100 | 0.32 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.04 | Arecibo | 100 | 0.43 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-25 | 0.03 | Arecibo | 100 | 0.32 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.02 | Arecibo | 100 | 0.3 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-25 | 0.03 | Arecibo | 100 | 0.3 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-25 | 0.03 | Arecibo | 100 | 0.38 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-26 | 0.03 | Arecibo | 100 | 0.34 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-25 | 0.03 | Arecibo | 100 | 0.34 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-25 | 0.03 | Arecibo | 100 | 0.34 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-25 | 0.03 | Arecibo | 100 | 0.31 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-27 | 0.05 | Bayamon | 100 | 0.65 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-27 | 0.02 | Bayamon | 100 | 0.2 |  | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2200 | Cambalache Tc | Vega Baja Tc | 2026-06-27 | 0.05 | Bayamon | 100 | 0.61 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2300 | Dos Bocas Hp | Arecibo Sect | 2026-06-10 | 0.05 | Arecibo | 100 | 0.57 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2300 | Dos Bocas Hp | Arecibo Sect | 2026-06-15 | 0.04 | Arecibo | 100 | 0.46 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2300 | Dos Bocas Hp | Arecibo Sect | 2026-06-17 | 0.04 | Arecibo | 100 | 0.46 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2300 | Dos Bocas Hp | Arecibo Sect | 2026-06-18 | 0.04 | Arecibo | 100 | 0.53 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2300 | Dos Bocas Hp | Arecibo Sect | 2026-06-18 | 0.04 | Arecibo | 100 | 0.48 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2300 | Dos Bocas Hp | Arecibo Sect | 2026-06-18 | 0.03 | Arecibo | 100 | 0.32 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2300 | Dos Bocas Hp | Arecibo Sect | 2026-06-18 | 0.04 | Arecibo | 100 | 0.49 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2300 | Dos Bocas Hp | Arecibo Sect | 2026-06-18 | 0.04 | Arecibo | 100 | 0.53 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2300 | Dos Bocas Hp | Arecibo Sect | 2026-06-18 | 0.04 | Arecibo | 100 | 0.53 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2300 | Dos Bocas Hp | Arecibo Sect | 2026-06-18 | 0.05 | Arecibo | 100 | 0.56 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2300 | Dos Bocas Hp | Arecibo Sect | 2026-06-18 | 0.05 | Arecibo | 100 | 0.56 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2300 | Dos Bocas Hp | Arecibo Sect | 2026-06-18 | 0.03 | Arecibo | 100 | 0.32 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2300 | Dos Bocas Hp | Arecibo Sect | 2026-06-18 | 0.04 | Arecibo | 100 | 0.47 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2300 | Dos Bocas Hp | Arecibo Sect | 2026-06-19 | 0.04 | Arecibo | 100 | 0.47 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2300 | Dos Bocas Hp | Arecibo Sect | 2026-06-19 | 0.03 | Arecibo | 100 | 0.42 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2300 | Dos Bocas Hp | Arecibo Sect | 2026-06-19 | 0.03 | Arecibo | 100 | 0.42 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2300 | Dos Bocas Hp | Arecibo Sect | 2026-06-19 | 0.04 | Arecibo | 100 | 0.45 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2300 | Dos Bocas Hp | Arecibo Sect | 2026-06-19 | 0.04 | Arecibo | 100 | 0.43 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2300 | Dos Bocas Hp | Arecibo Sect | 2026-06-19 | 0.04 | Arecibo | 100 | 0.44 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2300 | Dos Bocas Hp | Arecibo Sect | 2026-06-19 | 0.04 | Arecibo | 100 | 0.52 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2300 | Dos Bocas Hp | Arecibo Sect | 2026-06-19 | 0.04 | Arecibo | 100 | 0.46 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2300 | Dos Bocas Hp | Arecibo Sect | 2026-06-19 | 0.04 | Arecibo | 100 | 0.43 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2300 | Dos Bocas Hp | Arecibo Sect | 2026-06-19 | 0.04 | Arecibo | 100 | 0.43 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2300 | Dos Bocas Hp | Arecibo Sect | 2026-06-22 | 0.04 | Arecibo | 100 | 0.46 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2300 | Dos Bocas Hp | Arecibo Sect | 2026-06-22 | 0.03 | Arecibo | 100 | 0.37 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2300 | Dos Bocas Hp | Arecibo Sect | 2026-06-22 | 0.02 | Arecibo | 100 | 0.25 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2300 | Dos Bocas Hp | Arecibo Sect | 2026-06-22 | 0.04 | Arecibo | 100 | 0.47 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2300 | Dos Bocas Hp | Arecibo Sect | 2026-06-22 | 0.02 | Arecibo | 100 | 0.25 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2300 | Dos Bocas Hp | Arecibo Sect | 2026-06-22 | 0.02 | Arecibo | 100 | 0.25 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2300 | Dos Bocas Hp | Arecibo Sect | 2026-06-22 | 0.04 | Arecibo | 100 | 0.46 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2300 | Dos Bocas Hp | Arecibo Sect | 2026-06-22 | 0.04 | Arecibo | 100 | 0.46 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2300 | Dos Bocas Hp | Arecibo Sect | 2026-06-22 | 0.04 | Arecibo | 100 | 0.46 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2300 | Dos Bocas Hp | Arecibo Sect | 2026-06-22 | 0.04 | Arecibo | 100 | 0.46 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2300 | Dos Bocas Hp | Arecibo Sect | 2026-06-22 | 0.04 | Arecibo | 100 | 0.45 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2300 | Dos Bocas Hp | Arecibo Sect | 2026-06-22 | 0.03 | Arecibo | 100 | 0.37 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2300 | Dos Bocas Hp | Arecibo Sect | 2026-06-22 | 0.03 | Arecibo | 100 | 0.37 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2300 | Dos Bocas Hp | Arecibo Sect | 2026-06-22 | 0.04 | Arecibo | 100 | 0.45 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2300 | Dos Bocas Hp | Arecibo Sect | 2026-06-23 | 0.04 | Arecibo | 100 | 0.49 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2300 | Dos Bocas Hp | Arecibo Sect | 2026-06-23 | 0.04 | Arecibo | 100 | 0.49 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2300 | Dos Bocas Hp | Arecibo Sect | 2026-06-23 | 0.08 | Arecibo | 100 | 1.02 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2300 | Dos Bocas Hp | Arecibo Sect | 2026-06-23 | 0.08 | Arecibo | 100 | 0.92 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 2300 | Dos Bocas Hp | Arecibo Sect | 2026-06-24 | 0.08 | Arecibo | 100 | 1.02 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 3100 | Sabana Llana Tc | Carolina | 2026-06-13 | 0.08 | San Juan | 100 | 0.99 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 3100 | Sabana Llana Tc | Carolina | 2026-06-10 | 0.04 | San Juan | 100 | 0.5 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 3100 | Sabana Llana Tc | Carolina | 2026-06-11 | 0.08 | San Juan | 100 | 0.92 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 3100 | Sabana Llana Tc | Carolina | 2026-06-11 | 0.03 | San Juan | 100 | 0.37 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 3100 | Sabana Llana Tc | Carolina | 2026-06-12 | 0.04 | San Juan | 100 | 0.48 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 3100 | Sabana Llana Tc | Carolina | 2026-06-12 | 0.04 | San Juan | 100 | 0.43 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 3100 | Sabana Llana Tc | Carolina | 2026-06-12 | 0.03 | San Juan | 100 | 0.36 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 3100 | Sabana Llana Tc | Carolina | 2026-06-12 | 0.05 | San Juan | 100 | 0.63 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 3100 | Sabana Llana Tc | Carolina | 2026-06-15 | 0.06 | San Juan | 100 | 0.73 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 3100 | Sabana Llana Tc | Carolina | 2026-06-15 | 0.03 | San Juan | 100 | 0.38 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 3100 | Sabana Llana Tc | Carolina | 2026-06-18 | 0.03 | San Juan | 100 | 0.34 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 3100 | Sabana Llana Tc | Carolina | 2026-06-16 | 0.04 | San Juan | 100 | 0.5 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 3100 | Sabana Llana Tc | Carolina | 2026-06-19 | 0.03 | San Juan | 100 | 0.34 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 3100 | Sabana Llana Tc | Carolina | 2026-06-18 | 0.1 | San Juan | 100 | 1.17 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 3100 | Sabana Llana Tc | Carolina | 2026-06-18 | 0.1 | San Juan | 100 | 1.17 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 3100 | Sabana Llana Tc | Carolina | 2026-06-16 | 0.04 | San Juan | 100 | 0.5 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 3400 | Monacillos Tc | Guaynabo Sect | 2026-06-03 | 0.05 | San Juan | 100 | 0.58 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 3800 | Cayey Rural | Jajome | 2026-06-18 | 0.04 | Caguas | 100 | 0.46 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 3800 | Cayey Rural | Jajome | 2026-06-18 | 0.05 | Caguas | 100 | 0.59 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 3800 | Cayey Rural | Jajome | 2026-06-18 | 0.05 | Caguas | 100 | 0.62 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 4300 | Bayamon Tc | Juan Domingo Sect | 2026-06-15 | 0.02 | Bayamon | 100 | 0.25 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 4700 | Canas Tc | Adjuntas To | 2026-06-18 | 0.35 | Ponce | 100 | 4.23 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 4700 | Canas Tc | Adjuntas To | 2026-06-22 | 0.09 | Arecibo | 100 | 1.07 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 5200 | Caguas Tc | Aguas Buenas Sect | 2026-06-05 | 0.12 | Caguas | 100 | 1.42 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 5400 | Rio Blanco Hp | Daguao Tc | 2026-06-04 | 0.04 | Caguas | 100 | 0.53 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 5400 | Rio Blanco Hp | Daguao Tc | 2026-06-04 | 0.04 | Caguas | 100 | 0.53 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 5400 | Rio Blanco Hp | Daguao Tc | 2026-06-07 | 0.03 | San Juan | 100 | 0.32 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 5400 | Rio Blanco Hp | Daguao Tc | 2026-06-07 | 0.03 | San Juan | 100 | 0.35 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 5400 | Rio Blanco Hp | Daguao Tc | 2026-06-07 | 0.03 | San Juan | 100 | 0.36 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 5400 | Rio Blanco Hp | Daguao Tc | 2026-06-07 | 0.05 | San Juan | 100 | 0.57 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 5400 | Rio Blanco Hp | Daguao Tc | 2026-06-07 | 0.09 | San Juan | 100 | 1.12 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 5400 | Rio Blanco Hp | Daguao Tc | 2026-06-08 | 0.1 | San Juan | 100 | 1.24 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 5400 | Rio Blanco Hp | Daguao Tc | 2026-06-08 | 0.03 | San Juan | 100 | 0.35 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 5400 | Rio Blanco Hp | Daguao Tc | 2026-06-09 | 0.03 | San Juan | 100 | 0.35 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 5400 | Rio Blanco Hp | Daguao Tc | 2026-06-07 | 0.08 | San Juan | 100 | 0.99 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 5400 | Rio Blanco Hp | Daguao Tc | 2026-06-07 | 0.06 | San Juan | 100 | 0.77 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 5400 | Rio Blanco Hp | Daguao Tc | 2026-06-08 | 0.13 | San Juan | 100 | 1.58 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 5400 | Rio Blanco Hp | Daguao Tc | 2026-06-26 | 0.04 | Caguas | 100 | 0.54 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 5400 | Rio Blanco Hp | Daguao Tc | 2026-06-24 | 0.03 | Caguas | 100 | 0.41 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 5400 | Rio Blanco Hp | Daguao Tc | 2026-06-26 | 0.03 | Caguas | 100 | 0.38 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 5400 | Rio Blanco Hp | Daguao Tc | 2026-06-23 | 0.02 | Caguas | 100 | 0.29 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 5400 | Rio Blanco Hp | Daguao Tc | 2026-06-26 | 0.1 | Caguas | 100 | 1.18 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 5400 | Rio Blanco Hp | Daguao Tc | 2026-06-25 | 0.04 | Caguas | 100 | 0.48 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 5400 | Rio Blanco Hp | Daguao Tc | 2026-06-24 | 0.05 | Caguas | 100 | 0.59 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 5400 | Rio Blanco Hp | Daguao Tc | 2026-06-24 | 0.03 | Caguas | 100 | 0.41 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 5400 | Rio Blanco Hp | Daguao Tc | 2026-06-25 | 0.03 | Caguas | 100 | 0.41 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 5400 | Rio Blanco Hp | Daguao Tc | 2026-06-26 | 0.05 | Caguas | 100 | 0.56 |  | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 5400 | Rio Blanco Hp | Daguao Tc | 2026-06-26 | 0.05 | Caguas | 100 | 0.56 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 5600 | Victoria Tc | Añasco Tc | 2026-06-28 | 0.03 | Mayaguez | 100 | 0.37 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 5600 | Victoria Tc | Añasco Tc | 2026-06-30 | 0.09 | Mayaguez | 100 | 1.09 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6400 | Bay View Sect | Amelia Sect | 2026-06-05 | 0.03 | Bayamon | 100 | 0.37 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6500 | Barranquitas Tc | Comerio Tc | 2026-06-03 | 0.12 | Ponce | 100 | 1.45 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6500 | Barranquitas Tc | Comerio Tc | 2026-06-03 | 0.11 | Ponce | 100 | 1.35 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6500 | Barranquitas Tc | Comerio Tc | 2026-06-01 | 0.28 | Ponce | 100 | 3.35 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6500 | Barranquitas Tc | Comerio Tc | 2026-06-24 | 0.37 | Caguas | 100 | 4.43 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6500 | Barranquitas Tc | Comerio Tc | 2026-06-24 | 0.22 | Caguas | 100 | 2.69 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6500 | Barranquitas Tc | Comerio Tc | 2026-06-24 | 0.1 | Ponce | 100 | 1.22 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6500 | Barranquitas Tc | Comerio Tc | 2026-06-24 | 0.04 | Ponce | 100 | 0.47 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6500 | Barranquitas Tc | Comerio Tc | 2026-06-25 | 0.04 | Ponce | 100 | 0.53 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6500 | Barranquitas Tc | Comerio Tc | 2026-06-25 | 0.1 | Ponce | 100 | 1.22 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6500 | Barranquitas Tc | Comerio Tc | 2026-06-25 | 0.1 | Ponce | 100 | 1.22 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6500 | Barranquitas Tc | Comerio Tc | 2026-06-24 | 0.28 | Ponce | 100 | 3.35 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6500 | Barranquitas Tc | Comerio Tc | 2026-06-26 | 0.28 | Ponce | 100 | 3.35 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6500 | Barranquitas Tc | Comerio Tc | 2026-06-26 | 0.04 | Ponce | 100 | 0.44 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6500 | Barranquitas Tc | Comerio Tc | 2026-06-27 | 0.1 | Ponce | 100 | 1.16 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6500 | Barranquitas Tc | Comerio Tc | 2026-06-29 | 0.2 | Ponce | 100 | 2.44 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6500 | Barranquitas Tc | Comerio Tc | 2026-06-25 | 0.27 | Caguas | 100 | 3.31 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6500 | Barranquitas Tc | Comerio Tc | 2026-06-30 | 0.11 | Ponce | 100 | 1.32 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6500 | Barranquitas Tc | Comerio Tc | 2026-06-29 | 0.18 | Ponce | 100 | 2.14 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6500 | Barranquitas Tc | Comerio Tc | 2026-06-27 | 0.38 | Caguas | 100 | 4.6 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-18 | 0.04 | Arecibo | 100 | 0.44 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-15 | 0.05 | Arecibo | 100 | 0.55 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-06 | 0.02 | Arecibo | 100 | 0.29 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-17 | 0.04 | Arecibo | 100 | 0.45 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-17 | 0.03 | Arecibo | 100 | 0.35 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-17 | 0.004 | Arecibo | 100 | 0.05 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-23 | 0.04 | Arecibo | 100 | 0.47 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-17 | 0.03 | Arecibo | 100 | 0.32 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-17 | 0.03 | Arecibo | 100 | 0.31 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-17 | 0.03 | Arecibo | 100 | 0.38 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-17 | 0.03 | Arecibo | 100 | 0.32 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-17 | 0.03 | Arecibo | 100 | 0.41 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-23 | 0.03 | Arecibo | 100 | 0.36 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-17 | 0.03 | Arecibo | 100 | 0.33 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-23 | 0.04 | Arecibo | 100 | 0.43 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-23 | 0.03 | Arecibo | 100 | 0.33 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-23 | 0.04 | Arecibo | 100 | 0.48 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-17 | 0.04 | Arecibo | 100 | 0.44 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-17 | 0.03 | Arecibo | 100 | 0.35 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-17 | 0.03 | Arecibo | 100 | 0.32 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-17 | 0.04 | Arecibo | 100 | 0.44 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-11 | 0.04 | Arecibo | 100 | 0.53 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-04 | 0.03 | Arecibo | 100 | 0.42 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-15 | 0.05 | Arecibo | 100 | 0.66 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-04 | 0.03 | Arecibo | 100 | 0.33 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-06 | 0.02 | Arecibo | 100 | 0.26 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-06 | 0.01 | Arecibo | 100 | 0.15 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-05 | 0.04 | Arecibo | 100 | 0.46 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-01 | 0.04 | Arecibo | 100 | 0.48 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-23 | 0.03 | Arecibo | 100 | 0.33 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-23 | 0.04 | Arecibo | 100 | 0.49 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-17 | 0.05 | Arecibo | 100 | 0.62 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-23 | 0.03 | Arecibo | 100 | 0.31 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-04 | 0.02 | Arecibo | 100 | 0.29 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-04 | 0.03 | Arecibo | 100 | 0.32 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-04 | 0.05 | Arecibo | 100 | 0.57 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-04 | 0.02 | Arecibo | 100 | 0.26 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-04 | 0.03 | Arecibo | 100 | 0.35 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-22 | 0.03 | Arecibo | 100 | 0.35 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-04 | 0.04 | Arecibo | 100 | 0.45 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-04 | 0.03 | Arecibo | 100 | 0.37 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-04 | 0.02 | Arecibo | 100 | 0.19 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-04 | 0.01 | Arecibo | 100 | 0.07 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-04 | 0.03 | Arecibo | 100 | 0.41 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-04 | 0.03 | Arecibo | 100 | 0.42 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-05 | 0.05 | Arecibo | 100 | 0.65 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-11 | 0.03 | Arecibo | 100 | 0.35 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-11 | 0.03 | Arecibo | 100 | 0.4 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-11 | 0.04 | Arecibo | 100 | 0.46 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-11 | 0.04 | Arecibo | 100 | 0.44 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-11 | 0.04 | Arecibo | 100 | 0.44 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-11 | 0.03 | Arecibo | 100 | 0.41 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-11 | 0.03 | Arecibo | 100 | 0.39 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-11 | 0.04 | Arecibo | 100 | 0.43 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-25 | 0.04 | Arecibo | 100 | 0.43 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-11 | 0.02 | Arecibo | 100 | 0.28 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-11 | 0.02 | Arecibo | 100 | 0.27 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-11 | 0.02 | Arecibo | 100 | 0.29 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-28 | 0.02 | Arecibo | 100 | 0.21 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-28 | 0.01 | Arecibo | 100 | 0.14 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-11 | 0.02 | Arecibo | 100 | 0.29 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-10 | 0.04 | Arecibo | 100 | 0.46 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-08 | 0.04 | Arecibo | 100 | 0.45 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-29 | 0.03 | Arecibo | 100 | 0.39 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-30 | 0.04 | Arecibo | 100 | 0.47 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-10 | 0.03 | Arecibo | 100 | 0.41 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-10 | 0.04 | Arecibo | 100 | 0.5 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-10 | 0.04 | Arecibo | 100 | 0.5 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-10 | 0.04 | Arecibo | 100 | 0.49 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-10 | 0.04 | Arecibo | 100 | 0.5 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-10 | 0.03 | Arecibo | 100 | 0.42 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-10 | 0.04 | Arecibo | 100 | 0.5 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-10 | 0.04 | Arecibo | 100 | 0.52 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-10 | 0.03 | Arecibo | 100 | 0.35 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-09 | 0.03 | Arecibo | 100 | 0.38 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-10 | 0.02 | Arecibo | 100 | 0.29 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-10 | 0.03 | Arecibo | 100 | 0.39 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-10 | 0.03 | Arecibo | 100 | 0.37 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-10 | 0.04 | Arecibo | 100 | 0.47 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-10 | 0.04 | Arecibo | 100 | 0.46 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-09 | 0.04 | Arecibo | 100 | 0.5 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-10 | 0.05 | Arecibo | 100 | 0.57 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-10 | 0.04 | Arecibo | 100 | 0.46 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-10 | 0.05 | Arecibo | 100 | 0.6 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-10 | 0.04 | Arecibo | 100 | 0.48 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-10 | 0.05 | Arecibo | 100 | 0.57 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-10 | 0.05 | Arecibo | 100 | 0.57 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-11 | 0.04 | Arecibo | 100 | 0.49 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-11 | 0.04 | Arecibo | 100 | 0.49 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-11 | 0.03 | Arecibo | 100 | 0.39 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-12 | 0.04 | Arecibo | 100 | 0.46 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-12 | 0.04 | Arecibo | 100 | 0.46 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-12 | 0.03 | Arecibo | 100 | 0.39 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-12 | 0.05 | Arecibo | 100 | 0.64 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-12 | 0.05 | Arecibo | 100 | 0.64 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-12 | 0.03 | Arecibo | 100 | 0.38 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-12 | 0.03 | Arecibo | 100 | 0.38 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-15 | 0.04 | Arecibo | 100 | 0.45 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-15 | 0.04 | Arecibo | 100 | 0.45 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-15 | 0.03 | Arecibo | 100 | 0.4 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-15 | 0.05 | Arecibo | 100 | 0.57 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-15 | 0.05 | Arecibo | 100 | 0.57 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-15 | 0.05 | Arecibo | 100 | 0.57 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-15 | 0.05 | Arecibo | 100 | 0.57 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-15 | 0.04 | Arecibo | 100 | 0.48 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-17 | 0.03 | Arecibo | 100 | 0.4 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-17 | 0.07 | Arecibo | 100 | 0.85 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-17 | 0.04 | Arecibo | 100 | 0.49 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-17 | 0.04 | Arecibo | 100 | 0.44 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-17 | 0.05 | Arecibo | 100 | 0.6 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-24 | 0.06 | Arecibo | 100 | 0.69 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-17 | 0.05 | Arecibo | 100 | 0.55 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-17 | 0.04 | Arecibo | 100 | 0.49 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-29 | 0.04 | Arecibo | 100 | 0.51 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-17 | 0.01 | Arecibo | 100 | 0.14 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-17 | 0.03 | Arecibo | 100 | 0.36 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-17 | 0.03 | Arecibo | 100 | 0.42 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-17 | 0.04 | Arecibo | 100 | 0.43 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-17 | 0.04 | Arecibo | 100 | 0.52 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-17 | 0.04 | Arecibo | 100 | 0.48 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-17 | 0.03 | Arecibo | 100 | 0.37 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-17 | 0.05 | Arecibo | 100 | 0.59 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-23 | 0.04 | Arecibo | 100 | 0.54 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-23 | 0.03 | Arecibo | 100 | 0.35 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-23 | 0.03 | Arecibo | 100 | 0.35 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-24 | 0.04 | Arecibo | 100 | 0.43 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-24 | 0.04 | Arecibo | 100 | 0.48 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-24 | 0.07 | Arecibo | 100 | 0.8 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-17 | 0.03 | Arecibo | 100 | 0.35 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-17 | 0.03 | Arecibo | 100 | 0.38 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-17 | 0.03 | Arecibo | 100 | 0.33 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-17 | 0.04 | Arecibo | 100 | 0.5 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-17 | 0.04 | Arecibo | 100 | 0.49 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-17 | 0.04 | Arecibo | 100 | 0.48 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-17 | 0.04 | Arecibo | 100 | 0.47 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-17 | 0.03 | Arecibo | 100 | 0.42 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-17 | 0.03 | Arecibo | 100 | 0.33 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-17 | 0.04 | Arecibo | 100 | 0.44 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-24 | 0.02 | Arecibo | 100 | 0.27 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-24 | 0.04 | Arecibo | 100 | 0.51 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-24 | 0.04 | Arecibo | 100 | 0.45 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-24 | 0.06 | Arecibo | 100 | 0.74 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-24 | 0.03 | Arecibo | 100 | 0.35 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-24 | 0.03 | Arecibo | 100 | 0.37 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-24 | 0.02 | Arecibo | 100 | 0.3 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-17 | 0.04 | Arecibo | 100 | 0.46 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-17 | 0.04 | Arecibo | 100 | 0.53 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-17 | 0.04 | Arecibo | 100 | 0.46 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-17 | 0.03 | Arecibo | 100 | 0.34 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-17 | 0.03 | Arecibo | 100 | 0.4 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-17 | 0.05 | Arecibo | 100 | 0.6 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-17 | 0.04 | Arecibo | 100 | 0.46 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-17 | 0.04 | Arecibo | 100 | 0.44 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-17 | 0.04 | Arecibo | 100 | 0.45 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-17 | 0.04 | Arecibo | 100 | 0.43 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-04 | 0.07 | Arecibo | 100 | 0.84 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-17 | 0.05 | Arecibo | 100 | 0.6 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-17 | 0.04 | Arecibo | 100 | 0.43 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-17 | 0.04 | Arecibo | 100 | 0.5 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-17 | 0.04 | Arecibo | 100 | 0.51 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-17 | 0.04 | Arecibo | 100 | 0.51 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-17 | 0.03 | Arecibo | 100 | 0.4 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-17 | 0.03 | Arecibo | 100 | 0.4 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-17 | 0.04 | Arecibo | 100 | 0.47 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-17 | 0.04 | Arecibo | 100 | 0.5 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-17 | 0.04 | Arecibo | 100 | 0.48 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-17 | 0.03 | Arecibo | 100 | 0.36 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-17 | 0.03 | Arecibo | 100 | 0.4 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-23 | 0.04 | Arecibo | 100 | 0.47 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-23 | 0.04 | Arecibo | 100 | 0.5 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-23 | 0.04 | Arecibo | 100 | 0.43 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-29 | 0.02 | Arecibo | 100 | 0.29 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-30 | 0.02 | Arecibo | 100 | 0.24 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-30 | 0.02 | Arecibo | 100 | 0.26 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-24 | 0.02 | Arecibo | 100 | 0.28 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-24 | 0.02 | Arecibo | 100 | 0.26 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-18 | 0.04 | Arecibo | 100 | 0.49 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-24 | 0.03 | Arecibo | 100 | 0.34 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-25 | 0.03 | Arecibo | 100 | 0.36 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-25 | 0.03 | Arecibo | 100 | 0.35 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-26 | 0.04 | Arecibo | 100 | 0.43 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-30 | 0.03 | Arecibo | 100 | 0.4 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-26 | 0.03 | Arecibo | 100 | 0.37 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-26 | 0.03 | Arecibo | 100 | 0.35 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-30 | 0.03 | Arecibo | 100 | 0.35 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-23 | 0.04 | Arecibo | 100 | 0.47 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-30 | 0.02 | Arecibo | 100 | 0.3 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-30 | 0.03 | Arecibo | 100 | 0.33 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-29 | 0.02 | Arecibo | 100 | 0.24 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-29 | 0.03 | Arecibo | 100 | 0.4 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-30 | 0.04 | Arecibo | 100 | 0.47 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-26 | 0.03 | Arecibo | 100 | 0.38 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-26 | 0.03 | Arecibo | 100 | 0.4 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 6900 | Cambalache Tc | Hatillo To | 2026-06-26 | 0.03 | Arecibo | 100 | 0.41 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 7800 | Dorado Tc | Vega Alta Sect | 2026-06-03 | 0.03 | Arecibo | 100 | 0.32 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 7800 | Dorado Tc | Vega Alta Sect | 2026-06-03 | 0.04 | Bayamon | 100 | 0.44 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 8100 | Yauco 1 Hp | Adjuntas To | 2026-06-03 | 0.2 | Arecibo | 100 | 2.47 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 8100 | Yauco 1 Hp | Adjuntas To | 2026-06-22 | 0.07 | Ponce | 100 | 0.81 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 8100 | Yauco 1 Hp | Adjuntas To | 2026-06-22 | 0.07 | Ponce | 100 | 0.81 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 8100 | Yauco 1 Hp | Adjuntas To | 2026-06-30 | 0.12 | Ponce | 100 | 1.48 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 8100 | Yauco 1 Hp | Adjuntas To | 2026-06-23 | 0.13 | Arecibo | 100 | 1.56 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 8100 | Yauco 1 Hp | Adjuntas To | 2026-06-24 | 0.13 | Arecibo | 100 | 1.56 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 8100 | Yauco 1 Hp | Adjuntas To | 2026-06-25 | 0.06 | Arecibo | 100 | 0.78 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 8100 | Yauco 1 Hp | Adjuntas To | 2026-06-29 | 0.39 | Arecibo | 100 | 4.7 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 8100 | Yauco 1 Hp | Adjuntas To | 2026-06-26 | 0.45 | Arecibo | 100 | 5.44 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 8100 | Yauco 1 Hp | Adjuntas To | 2026-06-30 | 0.06 | Mayaguez | 100 | 0.74 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 8900 | Fonalledas To | Venezuela Sect | 2026-06-04 | 0.01 | San Juan | 100 | 0.11 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 8900 | Fonalledas To | Venezuela Sect | 2026-06-10 | 0.05 | San Juan | 100 | 0.63 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 8900 | Fonalledas To | Venezuela Sect | 2026-06-10 | 0.05 | San Juan | 100 | 0.63 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 9300 | Juncos Tc | Gautier Benitez Sect | 2026-06-16 | 0.04 | Caguas | 100 | 0.46 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 9300 | Juncos Tc | Gautier Benitez Sect | 2026-06-16 | 0.03 | Caguas | 100 | 0.42 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 9400 | Dorado Tc | Toa Alta | 2026-06-05 | 0.05 | Bayamon | 100 | 0.65 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 9400 | Dorado Tc | Toa Alta | 2026-06-15 | 0.05 | Bayamon | 100 | 0.65 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 9400 | Dorado Tc | Toa Alta | 2026-06-15 | 0.03 | Bayamon | 100 | 0.38 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 9400 | Dorado Tc | Toa Alta | 2026-06-15 | 0.04 | Bayamon | 100 | 0.44 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 10000 | Magnolia To | Sierra Linda To | 2026-06-19 | 0.04 | Bayamon | 100 | 0.47 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 10000 | Magnolia To | Sierra Linda To | 2026-06-19 | 0.02 | Bayamon | 100 | 0.23 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 10000 | Magnolia To | Sierra Linda To | 2026-06-19 | 0.02 | Bayamon | 100 | 0.23 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 10000 | Magnolia To | Sierra Linda To | 2026-06-22 | 0.02 | Bayamon | 100 | 0.2 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 10000 | Magnolia To | Sierra Linda To | 2026-06-25 | 0.04 | Bayamon | 100 | 0.47 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 10300 | Canovanas Tc | Canovanas Sect | 2026-06-15 | 0.03 | San Juan | 100 | 0.4 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 10300 | Canovanas Tc | Canovanas Sect | 2026-06-15 | 0.02 | San Juan | 100 | 0.3 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 10300 | Canovanas Tc | Canovanas Sect | 2026-06-16 | 0.03 | San Juan | 100 | 0.31 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 10300 | Canovanas Tc | Canovanas Sect | 2026-06-16 | 0.01 | San Juan | 100 | 0.14 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 10300 | Canovanas Tc | Canovanas Sect | 2026-06-16 | 0.01 | San Juan | 100 | 0.14 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 10300 | Canovanas Tc | Canovanas Sect | 2026-06-16 | 0.02 | San Juan | 100 | 0.23 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 10700 | Hato Tejas Tc | Hato Tejas Sect | 2026-06-17 | 0.02 | Bayamon | 100 | 0.27 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 11100 | Canovanas Sect | San Fermin Sf | 2026-06-19 | 0.02 | San Juan | 100 | 0.3 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 11100 | Canovanas Sect | San Fermin Sf | 2026-06-22 | 0.03 | San Juan | 100 | 0.36 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 11100 | Canovanas Sect | San Fermin Sf | 2026-06-24 | 0.02 | San Juan | 100 | 0.29 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 11100 | Canovanas Sect | San Fermin Sf | 2026-06-30 | 0.02 | San Juan | 100 | 0.29 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 11100 | Canovanas Sect | San Fermin Sf | 2026-06-30 | 0.03 | San Juan | 100 | 0.31 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 11100 | Canovanas Sect | San Fermin Sf | 2026-06-27 | 0.03 | San Juan | 100 | 0.32 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 11100 | Canovanas Sect | San Fermin Sf | 2026-06-30 | 0.03 | San Juan | 100 | 0.3 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 11100 | Canovanas Sect | San Fermin Sf | 2026-06-30 | 0.03 | San Juan | 100 | 0.33 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 11400 | Barceloneta Tc | Florida To | 2026-06-26 | 0.17 | Arecibo | 100 | 2.09 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 11400 | Barceloneta Tc | Florida To | 2026-06-01 | 0.23 | Arecibo | 100 | 2.78 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 11400 | Barceloneta Tc | Florida To | 2026-06-02 | 0.07 | Arecibo | 100 | 0.83 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 11400 | Barceloneta Tc | Florida To | 2026-06-04 | 0.07 | Arecibo | 100 | 0.83 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 11400 | Barceloneta Tc | Florida To | 2026-06-06 | 0.27 | Arecibo | 100 | 3.24 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 11400 | Barceloneta Tc | Florida To | 2026-06-11 | 0.15 | Arecibo | 100 | 1.84 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 12300 | Berwind Tc | Villa Prades Sect | 2026-06-10 | 0.03 | San Juan | 100 | 0.41 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 12600 | Humacao Tc | Verde Mar | 2026-06-17 | 0.04 | Caguas | 100 | 0.52 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 12600 | Humacao Tc | Verde Mar | 2026-06-16 | 0.02 | Caguas | 100 | 0.28 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 12600 | Humacao Tc | Verde Mar | 2026-06-16 | 0.03 | Caguas | 100 | 0.39 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 12600 | Humacao Tc | Verde Mar | 2026-06-17 | 0.02 | Caguas | 100 | 0.26 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 12600 | Humacao Tc | Verde Mar | 2026-06-17 | 0.04 | Caguas | 100 | 0.48 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 12600 | Humacao Tc | Verde Mar | 2026-06-29 | 0.02 | Caguas | 100 | 0.28 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 12600 | Humacao Tc | Verde Mar | 2026-06-26 | 0.03 | Caguas | 100 | 0.39 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 12600 | Humacao Tc | Verde Mar | 2026-06-29 | 0.03 | Caguas | 100 | 0.37 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 12600 | Humacao Tc | Verde Mar | 2026-06-29 | 0.05 | Caguas | 100 | 0.55 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 13100 | Costa Sur Sp | Air Products | 2026-06-16 | 0.12 | Ponce | 100 | 1.46 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 13100 | Costa Sur Sp | Air Products | 2026-06-11 | 0.05 | Ponce | 100 | 0.63 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 13400 | Acacias Tc | San German Sect | 2026-06-07 | 0.03 | Mayaguez | 100 | 0.31 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 13400 | Acacias Tc | San German Sect | 2026-06-05 | 0.02 | Mayaguez | 100 | 0.29 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 13500 | Acacias Tc | Cabo Rojo To | 2026-06-01 | 0.03 | Mayaguez | 100 | 0.4 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 13500 | Acacias Tc | Cabo Rojo To | 2026-06-01 | 0.03 | Mayaguez | 100 | 0.4 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 13500 | Acacias Tc | Cabo Rojo To | 2026-06-02 | 0.05 | Mayaguez | 100 | 0.61 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 13500 | Acacias Tc | Cabo Rojo To | 2026-06-03 | 0.1 | Mayaguez | 100 | 1.27 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 13500 | Acacias Tc | Cabo Rojo To | 2026-06-04 | 0.04 | Mayaguez | 100 | 0.44 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 13700 | Isabela To | Isabela Pueblo | 2026-06-17 | 0.03 | Mayaguez | 100 | 0.39 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 13800 | Daguao Tc | India | 2026-06-30 | 0.02 | San Juan | 100 | 0.23 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 13800 | Daguao Tc | India | 2026-06-30 | 0.02 | San Juan | 100 | 0.27 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 14400 | Caguax Sect | Veredas Sect | 2026-06-01 | 0.06 | Caguas | 100 | 0.75 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 14400 | Caguax Sect | Veredas Sect | 2026-06-02 | 0.03 | Caguas | 100 | 0.34 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 14400 | Caguax Sect | Veredas Sect | 2026-06-02 | 0.03 | Caguas | 100 | 0.35 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 14400 | Caguax Sect | Veredas Sect | 2026-06-02 | 0.03 | Caguas | 100 | 0.31 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 14400 | Caguax Sect | Veredas Sect | 2026-06-04 | 0.03 | Caguas | 100 | 0.33 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 14400 | Caguax Sect | Veredas Sect | 2026-06-06 | 0.02 | Caguas | 100 | 0.29 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 14400 | Caguax Sect | Veredas Sect | 2026-06-26 | 0.02 | Caguas | 100 | 0.29 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 15500 | Monacillos Tc | Centro Medico Sect | 2026-06-04 | 0.05 | San Juan | 100 | 0.64 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 17400 | San Juan Mall Sect | San Jose To | 2026-06-16 | 0.02 | San Juan | 100 | 0.19 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 17900 | Juana Diaz Tc | Pastillo | 2026-06-09 | 0.03 | Ponce | 100 | 0.35 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 17900 | Juana Diaz Tc | Pastillo | 2026-06-12 | 0.03 | Ponce | 100 | 0.35 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 17900 | Juana Diaz Tc | Pastillo | 2026-06-13 | 0.04 | Ponce | 100 | 0.43 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 17900 | Juana Diaz Tc | Pastillo | 2026-06-19 | 0.04 | Ponce | 100 | 0.52 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 17900 | Juana Diaz Tc | Pastillo | 2026-06-22 | 0.03 | Ponce | 100 | 0.38 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 17900 | Juana Diaz Tc | Pastillo | 2026-06-22 | 0.02 | Ponce | 100 | 0.3 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 38 | 22000 | Juana Diaz Tc | Coto Laurel Sf | 2026-06-13 | 0.04 | Arecibo | 100 | 0.45 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 36100 | Dos Bocas Hydro Plant | Barrio Piña GIS | 2026-06-26 | 0.11 | Arecibo | 150 | 2.08 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 36100 | Dos Bocas Hydro Plant | Barrio Piña GIS | 2026-06-16 | 0.12 | Arecibo | 150 | 2.17 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 36100 | Dos Bocas Hydro Plant | Barrio Piña GIS | 2026-06-16 | 0.12 | Arecibo | 150 | 2.17 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 36100 | Dos Bocas Hydro Plant | Barrio Piña GIS | 2026-06-26 | 0.1 | Arecibo | 150 | 1.87 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 36300 | Yabucoa TC | Rio Blanco TC | 2026-06-23 | 0.65 | Ponce | 150 | 11.77 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 36300 | Yabucoa TC | Rio Blanco TC | 2026-06-04 | 0.26 | Caguas | 150 | 4.8 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 36300 | Yabucoa TC | Rio Blanco TC | 2026-06-11 | 0.08 | Ponce | 150 | 1.53 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 36300 | Yabucoa TC | Rio Blanco TC | 2026-06-11 | 0.26 | Ponce | 150 | 4.66 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 36300 | Yabucoa TC | Rio Blanco TC | 2026-06-10 | 0.21 | Caguas | 150 | 3.75 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 36300 | Yabucoa TC | Rio Blanco TC | 2026-06-11 | 0.3 | Ponce | 150 | 5.42 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 36300 | Yabucoa TC | Rio Blanco TC | 2026-06-12 | 0.14 | Ponce | 150 | 2.58 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 36300 | Yabucoa TC | Rio Blanco TC | 2026-06-11 | 0.24 | Caguas | 150 | 4.4 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 36300 | Yabucoa TC | Rio Blanco TC | 2026-06-11 | 0.14 | Caguas | 150 | 2.54 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 36300 | Yabucoa TC | Rio Blanco TC | 2026-06-11 | 0.36 | Caguas | 150 | 6.47 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 36300 | Yabucoa TC | Rio Blanco TC | 2026-06-15 | 0.13 | Caguas | 150 | 2.4 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 36300 | Yabucoa TC | Rio Blanco TC | 2026-06-12 | 0.2 | Caguas | 150 | 3.67 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 36300 | Yabucoa TC | Rio Blanco TC | 2026-06-16 | 0.07 | Caguas | 150 | 1.33 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 36300 | Yabucoa TC | Rio Blanco TC | 2026-06-23 | 0.26 | Caguas | 150 | 4.8 |  | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 36300 | Yabucoa TC | Rio Blanco TC | 2026-06-26 | 0.29 | Caguas | 150 | 5.35 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 36300 | Yabucoa TC | Rio Blanco TC | 2026-06-23 | 0.26 | Caguas | 150 | 4.8 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 36300 | Yabucoa TC | Rio Blanco TC | 2026-06-29 | 0.02 | Caguas | 150 | 0.29 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 36400 | Ponce TC | Dos Bocas Hydro Plant | 2026-06-08 | 0.08 | Ponce | 150 | 1.43 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 36400 | Ponce TC | Dos Bocas Hydro Plant | 2026-06-08 | 0.07 | Ponce | 150 | 1.19 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 36400 | Ponce TC | Dos Bocas Hydro Plant | 2026-06-01 | 0.09 | Arecibo | 150 | 1.72 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 36400 | Ponce TC | Dos Bocas Hydro Plant | 2026-06-01 | 0.09 | Arecibo | 150 | 1.72 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 36400 | Ponce TC | Dos Bocas Hydro Plant | 2026-06-03 | 0.1 | Arecibo | 150 | 1.91 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 36400 | Ponce TC | Dos Bocas Hydro Plant | 2026-06-03 | 0.13 | Arecibo | 150 | 2.41 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 36400 | Ponce TC | Dos Bocas Hydro Plant | 2026-06-05 | 0.07 | Arecibo | 150 | 1.28 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 36400 | Ponce TC | Dos Bocas Hydro Plant | 2026-06-05 | 0.07 | Arecibo | 150 | 1.28 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 36400 | Ponce TC | Dos Bocas Hydro Plant | 2026-06-08 | 0.05 | Arecibo | 150 | 0.98 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 36400 | Ponce TC | Dos Bocas Hydro Plant | 2026-06-06 | 0.33 | Arecibo | 150 | 6.04 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 36400 | Ponce TC | Dos Bocas Hydro Plant | 2026-06-06 | 0.06 | Arecibo | 150 | 1.16 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 36400 | Ponce TC | Dos Bocas Hydro Plant | 2026-06-08 | 0.05 | Arecibo | 150 | 0.98 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 36400 | Ponce TC | Dos Bocas Hydro Plant | 2026-06-08 | 0.14 | Arecibo | 150 | 2.6 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 36400 | Ponce TC | Dos Bocas Hydro Plant | 2026-06-09 | 0.23 | Arecibo | 150 | 4.23 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 36400 | Ponce TC | Dos Bocas Hydro Plant | 2026-06-09 | 0.23 | Arecibo | 150 | 4.23 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 36400 | Ponce TC | Dos Bocas Hydro Plant | 2026-06-12 | 0.08 | Arecibo | 150 | 1.4 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 36400 | Ponce TC | Dos Bocas Hydro Plant | 2026-06-12 | 0.13 | Arecibo | 150 | 2.33 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 36400 | Ponce TC | Dos Bocas Hydro Plant | 2026-06-13 | 0.2 | Arecibo | 150 | 3.56 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 36400 | Ponce TC | Dos Bocas Hydro Plant | 2026-06-12 | 0.12 | Arecibo | 150 | 2.25 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 36400 | Ponce TC | Dos Bocas Hydro Plant | 2026-06-13 | 0.12 | Arecibo | 150 | 2.09 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 36400 | Ponce TC | Dos Bocas Hydro Plant | 2026-06-15 | 0.1 | Arecibo | 150 | 1.75 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 36400 | Ponce TC | Dos Bocas Hydro Plant | 2026-06-16 | 0.08 | Arecibo | 150 | 1.44 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 36400 | Ponce TC | Dos Bocas Hydro Plant | 2026-06-17 | 0.23 | Arecibo | 150 | 4.16 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 36400 | Ponce TC | Dos Bocas Hydro Plant | 2026-06-18 | 0.18 | Arecibo | 150 | 3.23 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 36400 | Ponce TC | Dos Bocas Hydro Plant | 2026-06-18 | 0.18 | Arecibo | 150 | 3.23 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 36400 | Ponce TC | Dos Bocas Hydro Plant | 2026-06-18 | 0.23 | Arecibo | 150 | 4.16 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 36400 | Ponce TC | Dos Bocas Hydro Plant | 2026-06-19 | 0.1 | Arecibo | 150 | 1.85 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 36400 | Ponce TC | Dos Bocas Hydro Plant | 2026-06-20 | 0.07 | Arecibo | 150 | 1.25 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 36400 | Ponce TC | Dos Bocas Hydro Plant | 2026-06-20 | 0.24 | Arecibo | 150 | 4.41 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 36400 | Ponce TC | Dos Bocas Hydro Plant | 2026-06-23 | 0.13 | Arecibo | 150 | 2.42 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 36800 | Fajardo TC | Sabana Llana TC | 2026-06-23 | 0.11 | San Juan | 150 | 1.96 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37000 | Costa Sur Power Plant | Ponce TC | 2026-06-05 | 0.1 | Ponce | 150 | 1.82 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37100 | Guanica TC | Costa Sur Power Plant | 2026-06-04 | 0.09 | Ponce | 150 | 1.71 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37100 | Guanica TC | Costa Sur Power Plant | 2026-06-08 | 0.3 | Mayaguez | 150 | 5.54 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37100 | Guanica TC | Costa Sur Power Plant | 2026-06-11 | 0.07 | Mayaguez | 150 | 1.31 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37100 | Guanica TC | Costa Sur Power Plant | 2026-06-16 | 0.06 | Ponce | 150 | 1.11 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37200 | Mayaguez Power Plant | Mayaguez TC | 2026-06-06 | 0.19 | Mayaguez | 150 | 3.37 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37200 | Mayaguez Power Plant | Mayaguez TC | 2026-06-06 | 0.1 | Mayaguez | 150 | 1.84 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37200 | Mayaguez Power Plant | Mayaguez TC | 2026-06-12 | 0.08 | Mayaguez | 150 | 1.54 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37400 | Cambalache TC | Manati TC | 2026-06-09 | 0.15 | Arecibo | 150 | 2.68 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37400 | Cambalache TC | Manati TC | 2026-06-05 | 0.11 | Arecibo | 150 | 2.02 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37400 | Cambalache TC | Manati TC | 2026-06-25 | 0.14 | Arecibo | 150 | 2.52 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37400 | Cambalache TC | Manati TC | 2026-06-20 | 0.1 | Arecibo | 150 | 1.79 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37400 | Cambalache TC | Manati TC | 2026-06-01 | 0.13 | Arecibo | 150 | 2.4 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37400 | Cambalache TC | Manati TC | 2026-06-01 | 0.15 | Arecibo | 150 | 2.74 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37400 | Cambalache TC | Manati TC | 2026-06-05 | 0.11 | Arecibo | 150 | 2.01 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37400 | Cambalache TC | Manati TC | 2026-06-06 | 0.13 | Arecibo | 150 | 2.3 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37400 | Cambalache TC | Manati TC | 2026-06-06 | 0.04 | Arecibo | 150 | 0.78 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37400 | Cambalache TC | Manati TC | 2026-06-11 | 0.14 | Arecibo | 150 | 2.5 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37400 | Cambalache TC | Manati TC | 2026-06-13 | 0.15 | Arecibo | 150 | 2.72 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37400 | Cambalache TC | Manati TC | 2026-06-09 | 0.15 | Arecibo | 150 | 2.68 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37400 | Cambalache TC | Manati TC | 2026-06-13 | 0.04 | Arecibo | 150 | 0.78 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37400 | Cambalache TC | Manati TC | 2026-06-11 | 0.04 | Arecibo | 150 | 0.64 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37400 | Cambalache TC | Manati TC | 2026-06-18 | 0.22 | Arecibo | 150 | 4.04 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37400 | Cambalache TC | Manati TC | 2026-06-16 | 0.15 | Arecibo | 150 | 2.8 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37400 | Cambalache TC | Manati TC | 2026-06-19 | 0.13 | Arecibo | 150 | 2.45 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37400 | Cambalache TC | Manati TC | 2026-06-22 | 0.07 | Arecibo | 150 | 1.28 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37400 | Cambalache TC | Manati TC | 2026-06-21 | 0.11 | Arecibo | 150 | 2.05 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37400 | Cambalache TC | Manati TC | 2026-06-20 | 0.1 | Arecibo | 150 | 1.79 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37400 | Cambalache TC | Manati TC | 2026-06-19 | 0.12 | Arecibo | 150 | 2.24 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37400 | Cambalache TC | Manati TC | 2026-06-19 | 0.12 | Arecibo | 150 | 2.24 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37400 | Cambalache TC | Manati TC | 2026-06-23 | 0.25 | Arecibo | 150 | 4.6 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37400 | Cambalache TC | Manati TC | 2026-06-22 | 0.12 | Arecibo | 150 | 2.2 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37400 | Cambalache TC | Manati TC | 2026-06-22 | 0.12 | Arecibo | 150 | 2.2 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37400 | Cambalache TC | Manati TC | 2026-06-23 | 0.2 | Arecibo | 150 | 3.58 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37400 | Cambalache TC | Manati TC | 2026-06-23 | 0.12 | Arecibo | 150 | 2.21 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37400 | Cambalache TC | Manati TC | 2026-06-25 | 0.12 | Arecibo | 150 | 2.21 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37400 | Cambalache TC | Manati TC | 2026-06-24 | 0.12 | Arecibo | 150 | 2.16 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37400 | Cambalache TC | Manati TC | 2026-06-27 | 0.18 | Arecibo | 150 | 3.23 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37400 | Cambalache TC | Manati TC | 2026-06-27 | 0.15 | Arecibo | 150 | 2.81 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37400 | Cambalache TC | Manati TC | 2026-06-26 | 0.05 | Arecibo | 150 | 0.9 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37400 | Cambalache TC | Manati TC | 2026-06-30 | 0.11 | Arecibo | 150 | 2.07 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37400 | Cambalache TC | Manati TC | 2026-06-29 | 0.08 | Arecibo | 150 | 1.52 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37400 | Cambalache TC | Manati TC | 2026-06-29 | 0.08 | Arecibo | 150 | 1.52 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37400 | Cambalache TC | Manati TC | 2026-06-23 | 0.21 | Arecibo | 150 | 3.81 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37400 | Cambalache TC | Manati TC | 2026-06-23 | 0.18 | Arecibo | 150 | 3.27 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37400 | Cambalache TC | Manati TC | 2026-06-24 | 0.17 | Arecibo | 150 | 3.16 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37400 | Cambalache TC | Manati TC | 2026-06-23 | 0.18 | Arecibo | 150 | 3.2 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37400 | Cambalache TC | Manati TC | 2026-06-22 | 0.17 | Arecibo | 150 | 3.05 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37400 | Cambalache TC | Manati TC | 2026-06-30 | 0.22 | Arecibo | 150 | 4.04 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37400 | Cambalache TC | Manati TC | 2026-06-30 | 0.18 | Arecibo | 150 | 3.19 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37800 | Caguas TC | Jobos TC | 2026-06-06 | 0.07 | San Juan | 150 | 1.32 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37800 | Caguas TC | Jobos TC | 2026-06-10 | 0.07 | San Juan | 150 | 1.32 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37800 | Caguas TC | Jobos TC | 2026-06-10 | 0.13 | San Juan | 150 | 2.3 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37800 | Caguas TC | Jobos TC | 2026-06-10 | 0.13 | SAN JUAN | 150 | 2.3 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37800 | Caguas TC | Jobos TC | 2026-06-16 | 0.29 | Caguas | 150 | 5.26 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37800 | Caguas TC | Jobos TC | 2026-06-17 | 0.13 | San Juan | 150 | 2.4 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37800 | Caguas TC | Jobos TC | 2026-06-18 | 0.13 | San Juan | 150 | 2.38 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37800 | Caguas TC | Jobos TC | 2026-06-18 | 0.08 | Caguas | 150 | 1.53 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37800 | Caguas TC | Jobos TC | 2026-06-18 | 0.06 | San Juan | 150 | 1.03 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37800 | Caguas TC | Jobos TC | 2026-06-19 | 0.14 | San Juan | 150 | 2.62 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37800 | Caguas TC | Jobos TC | 2026-06-20 | 0.07 | San Juan | 150 | 1.36 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 37900 | Monacillos TC | Sabana Llana TC | 2026-06-16 | 0.19 | San Juan | 150 | 3.39 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 39000 | Comerio TC | Aguas Buenas GIS | 2026-06-06 | 0.31 | Caguas | 150 | 5.71 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 39000 | Comerio TC | Aguas Buenas GIS | 2026-06-01 | 0.05 | Ponce | 150 | 0.86 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 39000 | Comerio TC | Aguas Buenas GIS | 2026-06-05 | 0.09 | Ponce | 150 | 1.63 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 39000 | Comerio TC | Aguas Buenas GIS | 2026-06-09 | 0.26 | Ponce | 150 | 4.72 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 39000 | Comerio TC | Aguas Buenas GIS | 2026-06-09 | 0.35 | Ponce | 150 | 6.42 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 39000 | Comerio TC | Aguas Buenas GIS | 2026-06-10 | 0.06 | Ponce | 150 | 1.12 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 39100 | Victoria TC | Mora TC | 2026-06-05 | 0.07 | Arecibo | 150 | 1.35 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 39100 | Victoria TC | Mora TC | 2026-06-11 | 0.06 | Arecibo | 150 | 1.1 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 39100 | Victoria TC | Mora TC | 2026-06-05 | 0.09 | Arecibo | 150 | 1.59 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 39100 | Victoria TC | Mora TC | 2026-06-19 | 0.08 | Mayaguez | 150 | 1.44 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 39100 | Victoria TC | Mora TC | 2026-06-24 | 0.11 | Mayaguez | 150 | 1.92 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 39100 | Victoria TC | Mora TC | 2026-06-24 | 0.13 | Mayaguez | 150 | 2.38 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 39100 | Victoria TC | Mora TC | 2026-06-25 | 0.14 | Mayaguez | 150 | 2.54 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 39100 | Victoria TC | Mora TC | 2026-06-25 | 0.08 | Mayaguez | 150 | 1.44 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 40300 | Santa Isabel TC | Aguirre Power Plant | 2026-06-23 | 0.17 | Ponce | 150 | 3.08 | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 41200 | Sabana Llana TC | Canovanas TC | 2026-06-22 | 0.1 | San Juan | 150 | 1.85 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 41200 | Sabana Llana TC | Canovanas TC | 2026-06-23 | 0.11 | San Juan | 150 | 2.06 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 41200 | Sabana Llana TC | Canovanas TC | 2026-06-23 | 0.1 | San Juan | 150 | 1.85 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 41200 | Sabana Llana TC | Canovanas TC | 2026-06-23 | 0.08 | San Juan | 150 | 1.53 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 41300 | Cambalache TC | Cambalache Power Plant | 2026-06-24 | 0.06 | Arecibo | 150 | 1.13 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 115 | 41300 | Cambalache TC | Cambalache Power Plant | 2026-06-24 | 0.12 | Arecibo | 150 | 2.26 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 50100 | Cambalache Power Plant | Manati TC | 2026-06-20 | 0.19 | Arecibo | 150 | 3.37 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 50100 | Cambalache Power Plant | Manati TC | 2026-06-03 | 0.17 | Arecibo | 150 | 3.05 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 50100 | Cambalache Power Plant | Manati TC | 2026-06-01 | 0.15 | Arecibo | 150 | 2.76 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 50100 | Cambalache Power Plant | Manati TC | 2026-06-02 | 0.18 | Arecibo | 150 | 3.24 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 50100 | Cambalache Power Plant | Manati TC | 2026-06-02 | 0.15 | Arecibo | 150 | 2.77 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 50100 | Cambalache Power Plant | Manati TC | 2026-06-24 | 0.08 | Arecibo | 150 | 1.41 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 50100 | Cambalache Power Plant | Manati TC | 2026-06-11 | 0.18 | Arecibo | 150 | 3.35 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 50100 | Cambalache Power Plant | Manati TC | 2026-06-23 | 0.17 | Arecibo | 150 | 3.03 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 50100 | Cambalache Power Plant | Manati TC | 2026-06-22 | 0.18 | Arecibo | 150 | 3.23 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 50100 | Cambalache Power Plant | Manati TC | 2026-06-22 | 0.1 | Arecibo | 150 | 1.75 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 50100 | Cambalache Power Plant | Manati TC | 2026-06-24 | 0.07 | Arecibo | 150 | 1.27 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 50100 | Cambalache Power Plant | Manati TC | 2026-06-20 | 0.19 | Arecibo | 150 | 3.37 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 50100 | Cambalache Power Plant | Manati TC | 2026-06-21 | 0.12 | Arecibo | 150 | 2.17 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 50100 | Cambalache Power Plant | Manati TC | 2026-06-01 | 0.16 | Arecibo | 150 | 2.97 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 50100 | Cambalache Power Plant | Manati TC | 2026-06-01 | 0.15 | Arecibo | 150 | 2.76 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 50100 | Cambalache Power Plant | Manati TC | 2026-06-02 | 0.09 | Arecibo | 150 | 1.66 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 50100 | Cambalache Power Plant | Manati TC | 2026-06-02 | 0.18 | Arecibo | 150 | 3.24 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 50100 | Cambalache Power Plant | Manati TC | 2026-06-02 | 0.24 | Arecibo | 150 | 4.3 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 50100 | Cambalache Power Plant | Manati TC | 2026-06-02 | 0.05 | Arecibo | 150 | 0.97 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 50100 | Cambalache Power Plant | Manati TC | 2026-06-02 | 0.15 | Arecibo | 150 | 2.77 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 50100 | Cambalache Power Plant | Manati TC | 2026-06-03 | 0.14 | Arecibo | 150 | 2.62 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 50100 | Cambalache Power Plant | Manati TC | 2026-06-18 | 0.17 | Arecibo | 150 | 3.05 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 50100 | Cambalache Power Plant | Manati TC | 2026-06-05 | 0.15 | Arecibo | 150 | 2.79 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 50100 | Cambalache Power Plant | Manati TC | 2026-06-03 | 0.15 | Arecibo | 150 | 2.71 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 50100 | Cambalache Power Plant | Manati TC | 2026-06-06 | 0.06 | Arecibo | 150 | 1.17 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 50100 | Cambalache Power Plant | Manati TC | 2026-06-11 | 0.06 | Arecibo | 150 | 1.13 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 50100 | Cambalache Power Plant | Manati TC | 2026-06-10 | 0.18 | Arecibo | 150 | 3.35 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 50100 | Cambalache Power Plant | Manati TC | 2026-06-09 | 0.16 | Arecibo | 150 | 2.88 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 50100 | Cambalache Power Plant | Manati TC | 2026-06-09 | 0.16 | Arecibo | 150 | 2.88 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 50100 | Cambalache Power Plant | Manati TC | 2026-06-11 | 0.14 | Arecibo | 150 | 2.53 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 50100 | Cambalache Power Plant | Manati TC | 2026-06-13 | 0.15 | Arecibo | 150 | 2.74 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 50100 | Cambalache Power Plant | Manati TC | 2026-06-10 | 0.13 | Arecibo | 150 | 2.44 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 50100 | Cambalache Power Plant | Manati TC | 2026-06-12 | 0.19 | Arecibo | 150 | 3.38 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 50100 | Cambalache Power Plant | Manati TC | 2026-06-11 | 0.16 | Arecibo | 150 | 2.83 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 50100 | Cambalache Power Plant | Manati TC | 2026-06-13 | 0.04 | Arecibo | 150 | 0.79 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 50100 | Cambalache Power Plant | Manati TC | 2026-06-18 | 0.22 | Arecibo | 150 | 4.05 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 50100 | Cambalache Power Plant | Manati TC | 2026-06-16 | 0.15 | Arecibo | 150 | 2.82 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 50100 | Cambalache Power Plant | Manati TC | 2026-06-19 | 0.14 | Arecibo | 150 | 2.47 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 50100 | Cambalache Power Plant | Manati TC | 2026-06-22 | 0.07 | Arecibo | 150 | 1.35 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 50100 | Cambalache Power Plant | Manati TC | 2026-06-21 | 0.11 | Arecibo | 150 | 2.05 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 50100 | Cambalache Power Plant | Manati TC | 2026-06-19 | 0.12 | Arecibo | 150 | 2.22 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 50100 | Cambalache Power Plant | Manati TC | 2026-06-22 | 0.12 | Arecibo | 150 | 2.1 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 50200 | Manati TC | Bayamon TC | 2026-06-03 | 0.17 | Bayamon | 150 | 3.11 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 50200 | Manati TC | Bayamon TC | 2026-06-11 | 0.09 | Bayamon | 150 | 1.55 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 50200 | Manati TC | Bayamon TC | 2026-06-03 | 0.24 | Bayamon | 150 | 4.28 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 50200 | Manati TC | Bayamon TC | 2026-06-02 | 0.17 | Bayamon | 150 | 3.11 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 50200 | Manati TC | Bayamon TC | 2026-06-09 | 0.17 | Bayamon | 150 | 3.11 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 50200 | Manati TC | Bayamon TC | 2026-06-11 | 0.14 | Bayamon | 150 | 2.54 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 50200 | Manati TC | Bayamon TC | 2026-06-11 | 0.2 | Bayamon | 150 | 3.64 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 50200 | Manati TC | Bayamon TC | 2026-06-11 | 0.16 | Bayamon | 150 | 2.85 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 50200 | Manati TC | Bayamon TC | 2026-06-01 | 0.18 | Bayamon | 150 | 3.3 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 50200 | Manati TC | Bayamon TC | 2026-06-09 | 0.15 | Bayamon | 150 | 2.77 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 50200 | Manati TC | Bayamon TC | 2026-06-15 | 0.48 | Ponce | 150 | 8.77 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 50200 | Manati TC | Bayamon TC | 2026-06-16 | 0.48 | Ponce | 150 | 8.77 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 50500 | Mora TC | Cambalache Power Plant | 2026-06-24 | 0.06 | Arecibo | 150 | 1.18 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 50500 | Mora TC | Cambalache Power Plant | 2026-06-24 | 0.13 | Arecibo | 150 | 2.41 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 50500 | Mora TC | Cambalache Power Plant | 2026-06-25 | 0.06 | Arecibo | 150 | 1.15 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 51000 | Aguirre Power Plant | Aguas Buenas GIS | 2026-06-02 | 0.49 | Ponce | 150 | 8.83 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 51000 | Aguirre Power Plant | Aguas Buenas GIS | 2026-06-04 | 0.19 | Ponce | 150 | 3.39 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 51000 | Aguirre Power Plant | Aguas Buenas GIS | 2026-06-04 | 0.49 | Ponce | 150 | 8.83 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 51200 | Costa Sur Power Plant | Cambalache Power Plant | 2026-06-24 | 0.05 | Arecibo | 150 | 0.91 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 51200 | Costa Sur Power Plant | Cambalache Power Plant | 2026-06-24 | 0.14 | Arecibo | 150 | 2.57 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 51200 | Costa Sur Power Plant | Cambalache Power Plant | 2026-06-25 | 0.06 | Arecibo | 150 | 1.13 | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 230 | 51300 |  |  | 2026-06-12 | 0.06 | Ponce | 150 | 1.14 | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
956345 | 38 | 2400 | Dos Bocas HP | Caonillas 2 | 2026-06-01 | 0.02 | Arecibo | 100 | 0.24 | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
956349 | 115 | 36800 | Canovanas TC | Palmer TC | 2026-06-01 | 0.07 | San Juan | 150 | 1.27 | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
956349 | 115 | 36800 | Canovanas TC | Palmer TC | 2026-06-02 | 0.04 | San Juan | 150 | 0.73 | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
956345 | 38 | 2400 | Dos Bocas HP | Caonillas 2 | 2026-06-02 | 0.05 | Arecibo | 100 | 0.61 | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
956345 | 38 | 2400 | Dos Bocas HP | Caonillas 2 | 2026-06-04 | 0.05 | Arecibo | 100 | 0.61 | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
956349 | 115 | 36800 | Canovanas TC | Palmer TC | 2026-06-04 | 0.32 | San Juan | 150 | 5.82 | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
956345 | 38 | 2400 | Dos Bocas HP | Caonillas 2 | 2026-06-05 | 0.01 | Arecibo | 100 | 0.12 | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
956349 | 115 | 36800 | Canovanas TC | Palmer TC | 2026-06-05 | 0.02 | San Juan | 150 | 0.36 | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
956345 | 38 | 2400 | Dos Bocas HP | Caonillas 2 | 2026-06-09 | 0.17 | Arecibo | 100 | 2.06 | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
956349 | 115 | 36800 | Canovanas TC | Palmer TC | 2026-06-08 | 0.01 | San Juan | 150 | 0.18 | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
956349 | 115 | 36800 | Canovanas TC | Palmer TC | 2026-06-09 | 0.08 | San Juan | 150 | 1.45 | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
956345 | 38 | 2400 | Dos Bocas HP | Caonillas 2 | 2026-06-10 | 0.06 | Arecibo | 100 | 0.73 | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
956345 | 38 | 2400 | Dos Bocas HP | Caonillas 2 | 2026-06-11 | 0.08 | Arecibo | 100 | 0.97 | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
956345 | 38 | 2400 | Dos Bocas HP | Caonillas 2 | 2026-06-12 | 0.03 | Arecibo | 100 | 0.36 | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
956345 | 38 | 2400 | Dos Bocas HP | Caonillas 2 | 2026-06-15 | 0.07 | Arecibo | 100 | 0.85 | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
956345 | 38 | 2400 | Dos Bocas HP | Caonillas 2 | 2026-06-16 | 0.11 | Arecibo | 100 | 1.33 | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
956345 | 38 | 2400 | Dos Bocas HP | Caonillas 2 | 2026-06-17 | 0.13 | Arecibo | 100 | 1.58 | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
956345 | 38 | 2400 | Dos Bocas HP | Caonillas 2 | 2026-06-18 | 0.03 | Arecibo | 100 | 0.36 | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
956342 | 115 | 36400 | Ponce TC | Dos Bocas Hydro Plant | 2026-06-18 | 0.01 | Arecibo | 150 | 0.18 | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
956345 | 38 | 2400 | Dos Bocas HP | Caonillas 2 | 2026-06-19 | 0.04 | Arecibo | 100 | 0.48 | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
956342 | 115 | 36400 | Ponce TC | Dos Bocas Hydro Plant | 2026-06-19 | 0.05 | Arecibo | 150 | 0.91 | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
956345 | 38 | 2400 | Dos Bocas HP | Caonillas 2 | 2026-06-22 | 0.04 | Arecibo | 100 | 0.48 | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
956342 | 115 | 36400 | Ponce TC | Dos Bocas Hydro Plant | 2026-06-22 | 0.05 | Arecibo | 150 | 0.91 | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
956345 | 38 | 2400 | Dos Bocas HP | Caonillas 2 | 2026-06-23 | 0.01 | Arecibo | 100 | 0.12 | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
956345 | 38 | 2400 | Dos Bocas HP | Caonillas 2 | 2026-06-25 | 0.07 | Arecibo | 100 | 0.85 | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
956349 | 115 | 36800 | Canovanas TC | Palmer TC | 2026-06-26 | 0.06 | San Juan | 150 | 1.09 | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
956345 | 38 | 2400 | Dos Bocas HP | Caonillas 2 | 2026-06-29 | 0.09 | Arecibo | 100 | 1.09 | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
956345 | 38 | 2400 | Dos Bocas HP | Caonillas 2 | 2026-06-30 | 0.14 | Arecibo | 100 | 1.7 | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026

## Distribution Feeders
Primary Distribution Feeders
FAASt | Line Voltage (kV) | Primary Distribution Line ID # | Clearing Date | Circuit Miles Maintained / Cleared | Right of Way (Rows) Width | ROW Acres Maintained / Cleared | Municipalities Impacted | Name of Contractor | Clearing Status | Type of Response | VM Activity Point of Contact (POC) | Funding Source | Month | Quarter | Fiscal Year
727572 | 2.40/4.16 | 1705-02 | 2026-05-01 | 0.12 | 10 | 0.15 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750065 | 7.62/13.20 | 1710-05 | 2026-05-01 | 0.59 | 10 | 0.71 | Toa Alta | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
727572 | 2.40/4.16 | 1715-02 | 2026-05-01 | 0.06 | 10 | 0.07 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
727572 | 7.62/13.20 | 1719-16 | 2026-05-01 | 0.03 | 10 | 0.04 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
727692 | 2.40/4.16 | 3014-01 | 2026-05-01 | 0.07 | 10 | 0.07 | Caguas | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750067 | 2.40/4.16 | 8602-01 | 2026-05-01 | 0.53 | 10 | 0.64 | Florida | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
727572 | 2.40/4.16 | 1715-02 | 2026-05-01 | 0.06 | 10 | 0.07 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
727572 | 7.62/13.20 | 1719-16 | 2026-05-01 | 0.03 | 10 | 0.04 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
N/A | 4.80/8.32 | 3701-03 | 2026-05-01 | 0.02 | 10 | 0.03 | Aguas Buenas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-05-01 | 0.04 | 10 | 0.05 | San Sebastian | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3701-03 | 2026-05-01 | 0.06 | 10 | 0.07 | Aguas Buenas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 1526-05 | 2026-05-01 | 0.04 | 10 | 0.05 | Guaynabo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3701-03 | 2026-05-01 | 0.05 | 10 | 0.06 | Aguas Buenas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3701-03 | 2026-05-01 | 0.04 | 10 | 0.05 | Aguas Buenas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3701-03 | 2026-05-01 | 0.06 | 10 | 0.07 | Aguas Buenas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6501-04 | 2026-05-01 | 0.15 | 10 | 0.18 | Sabana Grande | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3701-03 | 2026-05-01 | 0.04 | 10 | 0.05 | Aguas Buenas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3701-03 | 2026-05-01 | 0.04 | 10 | 0.05 | Aguas Buenas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 1526-05 | 2026-05-01 | 0.02 | 10 | 0.02 | Guaynabo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-05-01 | 0.07 | 10 | 0.09 | San Sebastian | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6801-02 | 2026-05-01 | 0.04 | 10 | 0.05 | Hormigueros | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7003-05 | 2026-05-02 | 0.04 | 10 | 0.05 | Aguadilla | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 9703-01 | 2026-05-02 | 0.04 | 10 | 0.05 | Comerio | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 9703-01 | 2026-05-02 | 0.12 | 10 | 0.15 | Comerio | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 6406-02 | 2026-05-02 | 0.03 | 10 | 0.04 | San German | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 6406-02 | 2026-05-02 | 0.02 | 10 | 0.02 | San German | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 6406-02 | 2026-05-02 | 0.02 | 10 | 0.02 | San German | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 3201-02 | 2026-05-02 | 0.02 | 10 | 0.02 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8101-03 | 2026-05-02 | 0.04 | 10 | 0.05 | Utuado | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3701-03 | 2026-05-02 | 0.05 | 10 | 0.06 | Aguas Buenas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 1401-08 | 2026-05-02 | 0.03 | 10 | 0.04 | San Juan | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8101-03 | 2026-05-02 | 0.04 | 10 | 0.05 | Utuado | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8101-03 | 2026-05-02 | 0.05 | 10 | 0.06 | Utuado | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 9703-01 | 2026-05-02 | 0.04 | 10 | 0.05 | Comerio | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8101-03 | 2026-05-02 | 0.03 | 10 | 0.04 | Utuado | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3701-03 | 2026-05-02 | 0.04 | 10 | 0.05 | Aguas Buenas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8002-05 | 2026-05-02 | 0.03 | 10 | 0.04 | Arecibo | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 9703-01 | 2026-05-02 | 0.06 | 10 | 0.08 | Comerio | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 9703-01 | 2026-05-02 | 0.07 | 10 | 0.08 | Comerio | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8101-03 | 2026-05-02 | 0.05 | 10 | 0.06 | Utuado | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 9703-01 | 2026-05-02 | 0.04 | 10 | 0.05 | Comerio | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 9703-01 | 2026-05-02 | 0.06 | 10 | 0.08 | Comerio | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 1401-08 | 2026-05-02 | 0.03 | 10 | 0.04 | San Juan | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 9703-01 | 2026-05-02 | 0.02 | 10 | 0.03 | Comerio | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 1401-08 | 2026-05-02 | 0.03 | 10 | 0.03 | San Juan | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 1401-08 | 2026-05-02 | 0.03 | 10 | 0.03 | San Juan | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
750065 | 2.40/4.16 | 1707-05 | 2026-05-04 | 0.004 | 10 | 0.01 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
727572 | 2.40/4.16 | 1714-02 | 2026-05-04 | 0.003 | 10 | 0.004 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750065 | 2.40/4.16 | 1734-01 | 2026-05-04 | 0.14 | 10 | 0.17 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750065 | 2.40/4.16 | 1734-02 | 2026-05-04 | 0.12 | 10 | 0.14 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
727572 | 7.62/13.20 | 1806-01 | 2026-05-04 | 1.12 | 10 | 1.36 | Toa Baja | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
727692 | 2.40/4.16 | 3014-01 | 2026-05-04 | 0.03 | 10 | 0.04 | Caguas | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750066 | 4.80/8.32 | 3601-01 | 2026-05-04 | 0.11 | 10 | 0.14 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750066 | 4.80/8.32 | 3601-03 | 2026-05-04 | 0.88 | 10 | 1.06 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750067 | 2.40/4.16 | 8602-01 | 2026-05-04 | 1.3 | 10 | 1.57 | Florida | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750067 | 4.80/8.32 | 9103-04 | 2026-05-04 | 0.05 | 10 | 0.06 | Vega Alta | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
N/A | 2.40/4.16 | 6501-02 | 2026-05-04 | 0.02 | 10 | 0.02 | Sabana Grande | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 8013-01 | 2026-05-04 | 0.03 | 10 | 0.03 | Hatillo | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 1343-03 | 2026-05-04 | 0.02 | 10 | 0.03 | Guaynabo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 1343-03 | 2026-05-04 | 0.02 | 10 | 0.02 | Guaynabo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 1343-03 | 2026-05-04 | 0.03 | 10 | 0.03 | Guaynabo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 1343-03 | 2026-05-04 | 0.02 | 10 | 0.03 | Guaynabo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 1343-03 | 2026-05-04 | 0.02 | 10 | 0.03 | Guaynabo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 1343-03 | 2026-05-04 | 0.02 | 10 | 0.03 | Guaynabo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 1343-03 | 2026-05-04 | 0.03 | 10 | 0.04 | Guaynabo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 1343-03 | 2026-05-04 | 0.03 | 10 | 0.03 | Guaynabo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7701-04 | 2026-05-04 | 0.03 | 10 | 0.04 | Hatillo | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7701-04 | 2026-05-04 | 0.04 | 10 | 0.04 | Hatillo | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-05-04 | 0.02 | 10 | 0.03 | San Sebastian | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-05-04 | 0.03 | 10 | 0.04 | San Sebastian | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-05-04 | 0.03 | 10 | 0.04 | San Sebastian | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-05-04 | 0.04 | 10 | 0.05 | San Sebastian | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-05-04 | 0.08 | 10 | 0.1 | San Sebastian | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-05-04 | 0.1 | 10 | 0.12 | San Sebastian | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7701-04 | 2026-05-04 | 0.03 | 10 | 0.03 | Hatillo | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7701-04 | 2026-05-04 | 0.03 | 10 | 0.04 | Hatillo | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-05-04 | 0.04 | 10 | 0.04 | San Sebastian | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-05-04 | 0.04 | 10 | 0.05 | San Sebastian | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7701-04 | 2026-05-04 | 0.03 | 10 | 0.03 | Hatillo | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7701-04 | 2026-05-04 | 0.03 | 10 | 0.04 | Hatillo | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 2002-01 | 2026-05-04 | 0.03 | 10 | 0.04 | Fajardo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 2002-01 | 2026-05-04 | 0.04 | 10 | 0.04 | Fajardo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-05-04 | 0.05 | 10 | 0.06 | San Sebastian | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-05-04 | 0.05 | 10 | 0.07 | San Sebastian | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-05-04 | 0.02 | 10 | 0.02 | San Sebastian | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-05-04 | 0.02 | 10 | 0.03 | San Sebastian | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3005-03 | 2026-05-04 | 0.03 | 10 | 0.03 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3005-03 | 2026-05-04 | 0.03 | 10 | 0.04 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6501-02 | 2026-05-04 | 0.04 | 10 | 0.04 | Sabana Grande | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6501-02 | 2026-05-04 | 0.04 | 10 | 0.05 | Sabana Grande | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-05-04 | 0.03 | 10 | 0.04 | San Sebastian | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-05-04 | 0.04 | 10 | 0.04 | San Sebastian | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7701-04 | 2026-05-04 | 0.03 | 10 | 0.03 | Hatillo | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7701-04 | 2026-05-04 | 0.03 | 10 | 0.04 | Hatillo | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-05-04 | 0.03 | 10 | 0.04 | San Sebastian | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-05-04 | 0.04 | 10 | 0.04 | San Sebastian | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-05-04 | 0.03 | 10 | 0.03 | San Sebastian | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-05-04 | 0.03 | 10 | 0.04 | San Sebastian | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-05-04 | 0.04 | 10 | 0.05 | San Sebastian | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-05-04 | 0.05 | 10 | 0.06 | San Sebastian | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7103-04 | 2026-05-04 | 0.06 | 10 | 0.07 | Moca | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7103-04 | 2026-05-04 | 0.07 | 10 | 0.08 | Moca | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 8404-03 | 2026-05-04 | 0.03 | 10 | 0.03 | Manati | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 8404-03 | 2026-05-04 | 0.03 | 10 | 0.04 | Manati | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 2002-01 | 2026-05-04 | 0.03 | 10 | 0.03 | Fajardo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 2002-01 | 2026-05-04 | 0.03 | 10 | 0.04 | Fajardo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-05-04 | 0.11 | 10 | 0.14 | San Sebastian | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-05-04 | 0.14 | 10 | 0.16 | San Sebastian | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 6406-02 | 2026-05-04 | 0.02 | 10 | 0.03 | San German | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 6406-02 | 2026-05-04 | 0.03 | 10 | 0.03 | San German | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 6406-02 | 2026-05-04 | 0.02 | 10 | 0.03 | San German | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 6406-02 | 2026-05-04 | 0.03 | 10 | 0.03 | San German | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 6406-02 | 2026-05-04 | 0.02 | 10 | 0.03 | San German | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 6406-02 | 2026-05-04 | 0.03 | 10 | 0.03 | San German | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 6406-02 | 2026-05-04 | 0.02 | 10 | 0.03 | San German | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 6406-02 | 2026-05-04 | 0.03 | 10 | 0.03 | San German | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-05-04 | 0.03 | 10 | 0.04 | San Sebastian | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-05-04 | 0.04 | 10 | 0.04 | San Sebastian | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-05-04 | 0.02 | 10 | 0.03 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-05-04 | 0.03 | 10 | 0.03 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.3 | 3004-01 | 2026-05-04 | 0.02 | 10 | 0.03 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.3 | 3004-01 | 2026-05-04 | 0.03 | 10 | 0.03 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6801-02 | 2026-05-04 | 0.04 | 10 | 0.05 | Hormigueros | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6801-02 | 2026-05-04 | 0.05 | 10 | 0.06 | Hormigueros | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6801-02 | 2026-05-04 | 0.03 | 10 | 0.03 | Hormigueros | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6801-02 | 2026-05-04 | 0.03 | 10 | 0.04 | Hormigueros | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6801-02 | 2026-05-04 | 0.03 | 10 | 0.03 | Hormigueros | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6801-02 | 2026-05-04 | 0.03 | 10 | 0.04 | Hormigueros | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5005-02 | 2026-05-04 | 0.03 | 10 | 0.04 | Ponce | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4301-03 | 2026-05-04 | 0.03 | 10 | 0.04 | Maunabo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5005-02 | 2026-05-04 | 0.04 | 10 | 0.04 | Ponce | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4301-03 | 2026-05-04 | 0.04 | 10 | 0.04 | Maunabo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4301-03 | 2026-05-04 | 0.05 | 10 | 0.06 | Maunabo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4301-03 | 2026-05-04 | 0.06 | 10 | 0.08 | Maunabo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4301-03 | 2026-05-04 | 0.03 | 10 | 0.03 | Maunabo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4301-03 | 2026-05-04 | 0.03 | 10 | 0.04 | Maunabo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
727572 | 2.40/4.16 | 1705-02 | 2026-05-05 | 0.14 | 10 | 0.17 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750065 | 7.62/13.20 | 1710-05 | 2026-05-05 | 0.53 | 10 | 0.65 | Toa Alta | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750065 | 2.40/4.16 | 1734-02 | 2026-05-05 | 0.16 | 10 | 0.19 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
727572 | 7.62/13.20 | 1806-01 | 2026-05-05 | 0.49 | 10 | 0.6 | Toa Baja | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
727692 | 4.80/8.32 | 3009-04 | 2026-05-05 | 0.02 | 10 | 0.02 | Caguas | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
727692 | 2.40/4.16 | 3014-01 | 2026-05-05 | 0.03 | 10 | 0.04 | Caguas | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750066 | 4.80/8.32 | 3601-01 | 2026-05-05 | 1.06 | 10 | 1.28 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750066 | 4.80/8.32 | 3601-03 | 2026-05-05 | 0.06 | 10 | 0.07 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750067 | 2.40/4.16 | 8011-01 | 2026-05-05 | 0.58 | 10 | 0.7 | Arecibo | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750067 | 2.40/4.16 | 8602-01 | 2026-05-05 | 1.06 | 10 | 1.28 | Florida | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750067 | 4.80/8.32 | 8701-03 | 2026-05-05 | 0.02 | 10 | 0.02 | Ciales | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750067 | 4.80/8.32 | 9103-04 | 2026-05-05 | 0.13 | 10 | 0.16 | Vega Alta | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
N/A | 4.80/8.32 | 8203-01 | 2026-05-05 | 0.04 | 10 | 0.05 | Adjuntas | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-05-05 | 0.03 | 10 | 0.03 | San Sebastian | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-05-05 | 0.03 | 10 | 0.03 | San Sebastian | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7601-01 | 2026-05-05 | 0.02 | 10 | 0.03 | Camuy | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5901-01 | 2026-05-05 | 0.02 | 10 | 0.02 | Villalba | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5901-01 | 2026-05-05 | 0.03 | 10 | 0.03 | Villalba | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-05-05 | 0.02 | 10 | 0.03 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-05-05 | 0.02 | 10 | 0.02 | San Sebastian | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-05-05 | 0.02 | 10 | 0.03 | San Sebastian | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-05-05 | 0.02 | 10 | 0.03 | San Sebastian | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-05 | 0.03 | 10 | 0.04 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 4003-01 | 2026-05-05 | 0.06 | 10 | 0.07 | Guayama | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-05-05 | 0.02 | 10 | 0.02 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 3205-08 | 2026-05-05 | 0.03 | 10 | 0.03 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5501-04 | 2026-05-05 | 0.06 | 10 | 0.08 | Guayanilla | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 3201-04 | 2026-05-05 | 0.02 | 10 | 0.03 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-05 | 0.04 | 10 | 0.05 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5901-01 | 2026-05-05 | 0.05 | 10 | 0.06 | Villalba | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5501-04 | 2026-05-05 | 0.06 | 10 | 0.08 | Guayanilla | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3302-02 | 2026-05-05 | 0.02 | 10 | 0.02 | San Lorenzo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 4003-01 | 2026-05-05 | 0.06 | 10 | 0.07 | Guayama | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7601-01 | 2026-05-05 | 0.02 | 10 | 0.03 | Camuy | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-05-05 | 0.03 | 10 | 0.04 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-05 | 0.03 | 10 | 0.03 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-05-05 | 0.03 | 10 | 0.03 | San Sebastian | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-05-05 | 0.02 | 10 | 0.02 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 3205-08 | 2026-05-05 | 0.03 | 10 | 0.04 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-05-05 | 0.03 | 10 | 0.03 | San Sebastian | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-05-05 | 0.02 | 10 | 0.03 | San Sebastian | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-05-05 | 0.03 | 10 | 0.03 | San Sebastian | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5901-01 | 2026-05-05 | 0.05 | 10 | 0.06 | Villalba | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8101-03 | 2026-05-05 | 0.02 | 10 | 0.02 | Utuado | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5501-04 | 2026-05-05 | 0.06 | 10 | 0.08 | Guayanilla | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-05 | 0.02 | 10 | 0.02 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5501-04 | 2026-05-05 | 0.03 | 10 | 0.04 | Guayanilla | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-05-05 | 0.03 | 10 | 0.03 | San Sebastian | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 9902-02 | 2026-05-05 | 0.03 | 10 | 0.03 | Orocovis | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-05-05 | 0.03 | 10 | 0.03 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-05-05 | 0.02 | 10 | 0.02 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5901-01 | 2026-05-05 | 0.03 | 10 | 0.04 | Villalba | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5901-01 | 2026-05-05 | 0.02 | 10 | 0.02 | Villalba | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5901-01 | 2026-05-05 | 0.04 | 10 | 0.04 | Villalba | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-05 | 0.03 | 10 | 0.03 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7601-01 | 2026-05-05 | 0.03 | 10 | 0.03 | Camuy | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7502-02 | 2026-05-05 | 0.05 | 10 | 0.06 | Isabela | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-05-05 | 0.03 | 10 | 0.04 | San Sebastian | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 3201-04 | 2026-05-05 | 0.02 | 10 | 0.03 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5501-04 | 2026-05-05 | 0.04 | 10 | 0.05 | Guayanilla | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5501-04 | 2026-05-05 | 0.03 | 10 | 0.03 | Guayanilla | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 3205-08 | 2026-05-05 | 0.03 | 10 | 0.03 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6802-01 | 2026-05-05 | 0.04 | 10 | 0.05 | San German | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-05 | 0.03 | 10 | 0.04 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-05 | 0.04 | 10 | 0.04 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5501-04 | 2026-05-05 | 0.04 | 10 | 0.05 | Guayanilla | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7701-04 | 2026-05-05 | 0.03 | 10 | 0.03 | Hatillo | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 8404-01 | 2026-05-05 | 0.06 | 10 | 0.07 | Manati | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5501-04 | 2026-05-05 | 0.07 | 10 | 0.08 | Guayanilla | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-05 | 0.03 | 10 | 0.03 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
727572 | 2.40/4.16 | 1705-02 | 2026-05-06 | 0.07 | 10 | 0.07 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750065 | 2.40/4.16 | 1734-01 | 2026-05-06 | 0.08 | 10 | 0.09 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750065 | 2.40/4.16 | 1734-02 | 2026-05-06 | 0.2 | 10 | 0.25 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
727572 | 7.62/13.20 | 1806-01 | 2026-05-06 | 1.19 | 10 | 1.44 | Toa Baja | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750066 | 4.80/8.32 | 3601-01 | 2026-05-06 | 0.55 | 10 | 0.67 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750066 | 4.80/8.32 | 3603-02 | 2026-05-06 | 0.2 | 10 | 0.24 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750067 | 2.40/4.16 | 8011-01 | 2026-05-06 | 0.56 | 10 | 0.68 | Arecibo | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750067 | 2.40/4.16 | 8602-01 | 2026-05-06 | 0.69 | 10 | 0.83 | Florida | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750067 | 4.80/8.32 | 8701-03 | 2026-05-06 | 0.03 | 10 | 0.04 | Ciales | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750067 | 4.80/8.32 | 9103-04 | 2026-05-06 | 0.27 | 10 | 0.33 | Vega Alta | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
N/A | 7.62/13.20 | 2302-03 | 2026-05-06 | 0.04 | 10 | 0.05 | Rio Grande | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 2302-03 | 2026-05-06 | 0.04 | 10 | 0.05 | Rio Grande | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 3205-08 | 2026-05-06 | 0.02 | 10 | 0.03 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-01 | 2026-05-06 | 0.01 | 10 | 0.02 | San Sebastian | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-05-06 | 0.02 | 10 | 0.03 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-06 | 0.03 | 10 | 0.03 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7601-01 | 2026-05-06 | 0.03 | 10 | 0.04 | Camuy | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 3205-08 | 2026-05-06 | 0.03 | 10 | 0.03 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 9902-02 | 2026-05-06 | 0.04 | 10 | 0.05 | Orocovis | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3701-03 | 2026-05-06 | 0.04 | 10 | 0.04 | Aguas Buenas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 4003-01 | 2026-05-06 | 0.04 | 10 | 0.04 | Guayama | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-05-06 | 0.02 | 10 | 0.02 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6306-02 | 2026-05-06 | 0.02 | 10 | 0.02 | Mayagüez | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3701-03 | 2026-05-06 | 0.03 | 10 | 0.03 | Aguas Buenas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6306-02 | 2026-05-06 | 0.03 | 10 | 0.03 | Mayagüez | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3701-03 | 2026-05-06 | 0.02 | 10 | 0.03 | Aguas Buenas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6306-02 | 2026-05-06 | 0.03 | 10 | 0.03 | Mayagüez | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6306-02 | 2026-05-06 | 0.03 | 10 | 0.03 | Mayagüez | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-05-06 | 0.02 | 10 | 0.03 | San Sebastian | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6306-02 | 2026-05-06 | 0.02 | 10 | 0.02 | Mayagüez | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-01 | 2026-05-06 | 0.02 | 10 | 0.02 | San Sebastian | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-06 | 0.02 | 10 | 0.03 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-01 | 2026-05-06 | 0.03 | 10 | 0.03 | San Sebastian | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3701-03 | 2026-05-06 | 0.03 | 10 | 0.04 | Aguas Buenas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-05-06 | 0.06 | 10 | 0.07 | San Sebastian | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6306-02 | 2026-05-06 | 0.03 | 10 | 0.03 | Mayagüez | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-05-06 | 0.03 | 10 | 0.03 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3701-03 | 2026-05-06 | 0.06 | 10 | 0.07 | Aguas Buenas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3701-03 | 2026-05-06 | 0.04 | 10 | 0.05 | Aguas Buenas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3701-03 | 2026-05-06 | 0.04 | 10 | 0.05 | Aguas Buenas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3701-03 | 2026-05-06 | 0.07 | 10 | 0.08 | Aguas Buenas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 9902-02 | 2026-05-06 | 0.03 | 10 | 0.03 | Orocovis | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3701-03 | 2026-05-06 | 0.03 | 10 | 0.04 | Aguas Buenas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 1342-03 | 2026-05-06 | 0.05 | 10 | 0.06 | San Juan | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3701-03 | 2026-05-06 | 0.04 | 10 | 0.05 | Aguas Buenas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-05-06 | 0.04 | 10 | 0.05 | Cabo Rojo | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 9902-02 | 2026-05-06 | 0.03 | 10 | 0.04 | Orocovis | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 1720-07 | 2026-05-06 | 0.07 | 10 | 0.09 | Bayamon | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-05-06 | 0.03 | 10 | 0.04 | San Sebastian | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 1342-03 | 2026-05-06 | 0.02 | 10 | 0.03 | San Juan | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 1720-07 | 2026-05-06 | 0.07 | 10 | 0.09 | Bayamon | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-05-06 | 0.04 | 10 | 0.05 | Cabo Rojo | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-06 | 0.03 | 10 | 0.03 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 3205-08 | 2026-05-06 | 0.03 | 10 | 0.03 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-06 | 0.03 | 10 | 0.03 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
727572 | 2.40/4.16 | 1705-02 | 2026-05-07 | 0.13 | 10 | 0.16 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750065 | 7.62/13.20 | 1710-05 | 2026-05-07 | 0.11 | 10 | 0.13 | Toa Alta | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
727572 | 2.40/4.16 | 1715-02 | 2026-05-07 | 0.03 | 10 | 0.04 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750065 | 2.40/4.16 | 1734-01 | 2026-05-07 | 0.15 | 10 | 0.18 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750065 | 2.40/4.16 | 1734-02 | 2026-05-07 | 0.15 | 10 | 0.19 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
727572 | 7.62/13.20 | 1806-01 | 2026-05-07 | 1.19 | 10 | 1.44 | Toa Baja | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750066 | 4.80/8.32 | 3601-01 | 2026-05-07 | 0.12 | 10 | 0.14 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750066 | 4.80/8.32 | 3603-02 | 2026-05-07 | 0.15 | 10 | 0.18 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750067 | 2.40/4.16 | 8011-01 | 2026-05-07 | 1.11 | 10 | 1.34 | Arecibo | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750067 | 2.40/4.16 | 8602-01 | 2026-05-07 | 0.59 | 10 | 0.72 | Florida | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750067 | 4.80/8.32 | 9103-04 | 2026-05-07 | 0.18 | 10 | 0.22 | Vega Alta | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
N/A | 2.40/4.16 | 1343-03 | 2026-05-07 | 0.02 | 10 | 0.02 | Guaynabo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6306-02 | 2026-05-07 | 0.03 | 10 | 0.04 | Mayagüez | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 3201-04 | 2026-05-07 | 0.02 | 10 | 0.03 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6306-02 | 2026-05-07 | 0.03 | 10 | 0.04 | Mayagüez | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-05-07 | 0.01 | 10 | 0.02 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-05-07 | 0.06 | 10 | 0.07 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 8405-01 | 2026-05-07 | 0.02 | 10 | 0.02 | Manati | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 9902-02 | 2026-05-07 | 0.03 | 10 | 0.04 | Orocovis | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 8405-01 | 2026-05-07 | 0.02 | 10 | 0.03 | Manati | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6306-02 | 2026-05-07 | 0.03 | 10 | 0.03 | Mayagüez | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6306-02 | 2026-05-07 | 0.03 | 10 | 0.04 | Mayagüez | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 2002-01 | 2026-05-07 | 0.03 | 10 | 0.03 | Fajardo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8103-02 | 2026-05-07 | 0.07 | 10 | 0.09 | Utuado | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 3006-05 | 2026-05-07 | 0.03 | 10 | 0.03 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-07 | 0.03 | 10 | 0.03 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 3201-04 | 2026-05-07 | 0.04 | 10 | 0.05 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 2002-01 | 2026-05-07 | 0.03 | 10 | 0.03 | Fajardo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-07 | 0.01 | 10 | 0.02 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 4003-01 | 2026-05-07 | 0.03 | 10 | 0.04 | Guayama | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 3006-05 | 2026-05-07 | 0.02 | 10 | 0.03 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 5018-03 | 2026-05-07 | 0.02 | 10 | 0.03 | Ponce | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8103-02 | 2026-05-07 | 0.1 | 10 | 0.13 | Utuado | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 3201-04 | 2026-05-07 | 0.03 | 10 | 0.03 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6306-02 | 2026-05-07 | 0.03 | 10 | 0.03 | Mayagüez | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 6406-02 | 2026-05-07 | 0.03 | 10 | 0.04 | San German | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 6406-02 | 2026-05-07 | 0.03 | 10 | 0.04 | San German | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 8405-01 | 2026-05-07 | 0.02 | 10 | 0.02 | Manati | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7201-03 | 2026-05-07 | 0.04 | 10 | 0.04 | Aguada | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8103-02 | 2026-05-07 | 0.08 | 10 | 0.1 | Utuado | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-05-07 | 0.02 | 10 | 0.03 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-05-07 | 0.04 | 10 | 0.05 | Cabo Rojo | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-05-07 | 0.04 | 10 | 0.05 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.16/7.20 | 6601-03 | 2026-05-07 | 0.05 | 10 | 0.06 | Lajas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.16/7.20 | 6601-03 | 2026-05-07 | 0.05 | 10 | 0.07 | Lajas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-07 | 0.03 | 10 | 0.04 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-07 | 0.04 | 10 | 0.05 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 6012-02 | 2026-05-07 | 0.01 | 10 | 0.01 | Anasco | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
727572 | 2.40/4.16 | 1705-02 | 2026-05-08 | 0.1 | 10 | 0.12 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750065 | 7.62/13.20 | 1710-05 | 2026-05-08 | 0.37 | 10 | 0.45 | Toa Alta | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750065 | 2.40/4.16 | 1734-01 | 2026-05-08 | 0.08 | 10 | 0.1 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750066 | 4.80/8.32 | 3601-01 | 2026-05-08 | 0.35 | 10 | 0.42 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750066 | 4.80/8.32 | 3602-02 | 2026-05-08 | 0.95 | 10 | 1.16 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750066 | 4.80/8.32 | 3603-02 | 2026-05-08 | 0.13 | 10 | 0.16 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
N/A | 4.80/8.32 | 2002-01 | 2026-05-08 | 0.02 | 10 | 0.03 | Fajardo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 2002-01 | 2026-05-08 | 0.03 | 10 | 0.03 | Fajardo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 1303-05 | 2026-05-08 | 0.03 | 10 | 0.03 | San Juan | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 3201-04 | 2026-05-08 | 0.03 | 10 | 0.04 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-05-08 | 0.06 | 10 | 0.07 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 8404-03 | 2026-05-08 | 0.02 | 10 | 0.03 | Manati | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 3201-04 | 2026-05-08 | 0.01 | 10 | 0.02 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 3006-05 | 2026-05-08 | 0.03 | 10 | 0.03 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 3006-05 | 2026-05-08 | 0.03 | 10 | 0.03 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-08 | 0.03 | 10 | 0.03 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 3006-05 | 2026-05-08 | 0.03 | 10 | 0.03 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 1204-02 | 2026-05-08 | 0.03 | 10 | 0.03 | Trujillo Alto | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8005-01 | 2026-05-08 | 0.03 | 10 | 0.03 | Utuado | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8005-01 | 2026-05-08 | 0.04 | 10 | 0.05 | Utuado | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 4003-01 | 2026-05-08 | 0.03 | 10 | 0.04 | Guayama | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-01 | 2026-05-08 | 0.03 | 10 | 0.03 | San Sebastian | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 8405-04 | 2026-05-08 | 0.01 | 10 | 0.02 | Manati | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-01 | 2026-05-08 | 0.03 | 10 | 0.03 | San Sebastian | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-01 | 2026-05-08 | 0.02 | 10 | 0.03 | San Sebastian | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-01 | 2026-05-08 | 0.02 | 10 | 0.03 | San Sebastian | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-05-08 | 0.05 | 10 | 0.06 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 3006-05 | 2026-05-08 | 0.03 | 10 | 0.03 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6401-04 | 2026-05-08 | 0.03 | 10 | 0.04 | San German | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 9902-02 | 2026-05-08 | 0.03 | 10 | 0.03 | Orocovis | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 7805-13 | 2026-05-08 | 0.03 | 10 | 0.03 | San Sebastian | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6004-03 | 2026-05-08 | 0.01 | 10 | 0.02 | Mayagüez | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 7805-13 | 2026-05-08 | 0.03 | 10 | 0.03 | San Sebastian | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-05-08 | 0.02 | 10 | 0.02 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 9203-02 | 2026-05-08 | 0.03 | 10 | 0.04 | Toa Baja | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 9203-02 | 2026-05-08 | 0.04 | 10 | 0.04 | Toa Baja | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 9203-02 | 2026-05-08 | 0.03 | 10 | 0.03 | Toa Baja | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 3201-04 | 2026-05-08 | 0.02 | 10 | 0.02 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-08 | 0.03 | 10 | 0.04 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 3006-05 | 2026-05-08 | 0.02 | 10 | 0.03 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 1303-05 | 2026-05-08 | 0.03 | 10 | 0.03 | San Juan | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 9203-02 | 2026-05-08 | 0.02 | 10 | 0.03 | Toa Baja | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6501-01 | 2026-05-08 | 0.09 | 10 | 0.11 | Sabana Grande | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5005-02 | 2026-05-08 | 0.03 | 10 | 0.03 | Ponce | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5005-02 | 2026-05-08 | 0.03 | 10 | 0.03 | Ponce | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-08 | 0.03 | 10 | 0.04 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
750066 | 4.80/8.32 | 3603-02 | 2026-05-09 | 0.03 | 10 | 0.04 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
N/A | 7.62/13.20 | 2302-03 | 2026-05-09 | 0.01 | 10 | 0.02 | Rio Grande | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 1703-04 | 2026-05-09 | 0.03 | 10 | 0.03 | Bayamon | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 1703-04 | 2026-05-09 | 0.03 | 10 | 0.03 | Bayamon | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7201-03 | 2026-05-09 | 0.02 | 10 | 0.02 | Aguada | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 1303-05 | 2026-05-09 | 0.03 | 10 | 0.03 | San Juan | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 2001-02 | 2026-05-09 | 0.03 | 10 | 0.04 | Fajardo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 1336-08 | 2026-05-09 | 0.02 | 10 | 0.03 | San Juan | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 7805-13 | 2026-05-09 | 0.03 | 10 | 0.03 | San Sebastian | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 3006-05 | 2026-05-09 | 0.02 | 10 | 0.02 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7201-03 | 2026-05-09 | 0.05 | 10 | 0.06 | Aguada | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 3201-04 | 2026-05-09 | 0.05 | 10 | 0.06 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 2001-02 | 2026-05-09 | 0.03 | 10 | 0.04 | Fajardo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-09 | 0.02 | 10 | 0.03 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6201-01 | 2026-05-09 | 0.11 | 10 | 0.13 | Las Marias | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 3006-05 | 2026-05-09 | 0.02 | 10 | 0.03 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6101-05 | 2026-05-09 | 0.08 | 10 | 0.1 | Anasco | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6201-01 | 2026-05-09 | 0.11 | 10 | 0.13 | Las Marias | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 9004-08 | 2026-05-09 | 0.02 | 10 | 0.03 | Vega Baja | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 1703-04 | 2026-05-09 | 0.03 | 10 | 0.03 | Bayamon | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 1703-04 | 2026-05-09 | 0.03 | 10 | 0.04 | Bayamon | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 1703-04 | 2026-05-09 | 0.04 | 10 | 0.05 | Bayamon | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 1703-04 | 2026-05-09 | 0.01 | 10 | 0.02 | Bayamon | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 3201-04 | 2026-05-09 | 0.02 | 10 | 0.03 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 1703-04 | 2026-05-09 | 0.03 | 10 | 0.03 | Bayamon | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 1303-05 | 2026-05-09 | 0.03 | 10 | 0.03 | San Juan | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-09 | 0.03 | 10 | 0.04 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 3201-04 | 2026-05-09 | 0.04 | 10 | 0.04 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 3201-04 | 2026-05-09 | 0.02 | 10 | 0.03 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6406-02 | 2026-05-10 | 0.15 | 10 | 0.18 | San German | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
727572 | 2.40/4.16 | 1705-02 | 2026-05-11 | 0.1 | 10 | 0.12 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750065 | 2.40/4.16 | 1734-01 | 2026-05-11 | 0.64 | 10 | 0.78 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750065 | 2.40/4.16 | 1734-02 | 2026-05-11 | 0.23 | 10 | 0.27 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
727572 | 7.62/13.20 | 1806-01 | 2026-05-11 | 0.97 | 10 | 1.17 | Toa Baja | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750066 | 4.80/8.32 | 3602-02 | 2026-05-11 | 1.18 | 10 | 1.42 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750067 | 2.40/4.16 | 8011-01 | 2026-05-11 | 0.27 | 10 | 0.33 | Arecibo | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750067 | 2.40/4.16 | 8602-01 | 2026-05-11 | 0.56 | 10 | 0.68 | Florida | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
N/A | 2.40/4.16 | 6101-01 | 2026-05-11 | 0.02 | 10 | 0.03 | Anasco | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
750066 | 4.80/8.32 | 3603-02 | 2026-05-11 | 0.06 | 10 | 0.07 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750067 | 4.80/8.32 | 9103-04 | 2026-05-11 | 0.11 | 10 | 0.13 | Vega Alta | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
N/A | 2.40/4.16 | 7601-01 | 2026-05-11 | 0.02 | 10 | 0.03 | Camuy | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6306-02 | 2026-05-11 | 0.02 | 10 | 0.03 | Mayagüez | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 8405-01 | 2026-05-11 | 0.03 | 10 | 0.03 | Manati | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 6802-05 | 2026-05-11 | 0.07 | 10 | 0.08 | Cabo Rojo | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6306-02 | 2026-05-11 | 0.03 | 10 | 0.04 | Mayagüez | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 3405-03 | 2026-05-11 | 0.11 | 10 | 0.14 | Cayey | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6306-02 | 2026-05-11 | 0.03 | 10 | 0.04 | Mayagüez | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 8405-01 | 2026-05-11 | 0.02 | 10 | 0.02 | Manati | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6501-04 | 2026-05-11 | 0.03 | 10 | 0.04 | Sabana Grande | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7201-03 | 2026-05-11 | 0.05 | 10 | 0.06 | Aguada | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 4003-01 | 2026-05-11 | 0.03 | 10 | 0.03 | Guayama | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7601-01 | 2026-05-11 | 0.02 | 10 | 0.03 | Camuy | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7601-01 | 2026-05-11 | 0.02 | 10 | 0.03 | Camuy | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7601-01 | 2026-05-11 | 0.03 | 10 | 0.04 | Camuy | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6306-02 | 2026-05-11 | 0.03 | 10 | 0.04 | Mayagüez | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 1303-05 | 2026-05-11 | 0.03 | 10 | 0.04 | San Juan | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6306-02 | 2026-05-11 | 0.02 | 10 | 0.03 | Mayagüez | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6101-01 | 2026-05-11 | 0.02 | 10 | 0.03 | Anasco | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 7805-13 | 2026-05-11 | 0.02 | 10 | 0.03 | San Sebastian | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6101-01 | 2026-05-11 | 0.03 | 10 | 0.03 | Anasco | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3302-03 | 2026-05-11 | 0.04 | 10 | 0.05 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 4003-01 | 2026-05-11 | 0.03 | 10 | 0.03 | Guayama | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 6406-02 | 2026-05-11 | 0.03 | 10 | 0.03 | San German | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6306-02 | 2026-05-11 | 0.03 | 10 | 0.04 | Mayagüez | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6101-01 | 2026-05-11 | 0.04 | 10 | 0.04 | Anasco | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6101-01 | 2026-05-11 | 0.03 | 10 | 0.03 | Anasco | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-05-11 | 0.02 | 10 | 0.02 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 3205-08 | 2026-05-11 | 0.02 | 10 | 0.03 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5005-02 | 2026-05-11 | 0.03 | 10 | 0.04 | Ponce | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6501-04 | 2026-05-11 | 0.06 | 10 | 0.07 | Sabana Grande | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3302-03 | 2026-05-11 | 0.04 | 10 | 0.05 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3302-03 | 2026-05-11 | 0.06 | 10 | 0.07 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 2302-03 | 2026-05-11 | 0.03 | 10 | 0.04 | Rio Grande | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 2302-03 | 2026-05-11 | 0.02 | 10 | 0.03 | Rio Grande | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 2302-03 | 2026-05-11 | 0.02 | 10 | 0.03 | Rio Grande | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 2201-04 | 2026-05-11 | 0.04 | 10 | 0.04 | Luquillo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6501-04 | 2026-05-11 | 0.04 | 10 | 0.05 | Sabana Grande | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6501-04 | 2026-05-11 | 0.03 | 10 | 0.04 | Sabana Grande | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-11 | 0.03 | 10 | 0.03 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6501-04 | 2026-05-11 | 0.05 | 10 | 0.06 | Sabana Grande | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6501-04 | 2026-05-11 | 0.04 | 10 | 0.05 | Sabana Grande | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
727572 | 2.40/4.16 | 1705-02 | 2026-05-12 | 0.15 | 10 | 0.18 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750066 | 4.80/8.32 | 3602-02 | 2026-05-12 | 1.82 | 10 | 2.2 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750066 | 4.80/8.32 | 3603-02 | 2026-05-12 | 0.15 | 10 | 0.18 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750067 | 2.40/4.16 | 8602-01 | 2026-05-12 | 0.28 | 10 | 0.34 | Florida | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750067 | 4.80/8.32 | 9103-04 | 2026-05-12 | 0.25 | 10 | 0.3 | Vega Alta | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
N/A | 2.40/4.16 | 8104-02 | 2026-05-12 | 0.07 | 10 | 0.08 | Utuado | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 6015-02 | 2026-05-12 | 0.01 | 10 | 0.02 | Mayagüez | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 3201-04 | 2026-05-12 | 0.02 | 10 | 0.03 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7805-13 | 2026-05-12 | 0.07 | 10 | 0.09 | San Sebastian | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6501-04 | 2026-05-12 | 0.04 | 10 | 0.05 | Sabana Grande | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 9902-02 | 2026-05-12 | 0.02 | 10 | 0.03 | Orocovis | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6501-04 | 2026-05-12 | 0.03 | 10 | 0.04 | Sabana Grande | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 4003-01 | 2026-05-12 | 0.01 | 10 | 0.02 | Guayama | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-12 | 0.04 | 10 | 0.05 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6406-02 | 2026-05-12 | 0.04 | 10 | 0.05 | San German | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-05-12 | 0.02 | 10 | 0.02 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6406-02 | 2026-05-12 | 0.07 | 10 | 0.08 | San German | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6406-02 | 2026-05-12 | 0.03 | 10 | 0.03 | San German | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 3201-04 | 2026-05-12 | 0.02 | 10 | 0.02 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 6015-01 | 2026-05-12 | 0.03 | 10 | 0.03 | Mayagüez | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 6015-01 | 2026-05-12 | 0.03 | 10 | 0.03 | Mayagüez | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5005-02 | 2026-05-12 | 0.03 | 10 | 0.04 | Ponce | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-05-12 | 0.03 | 10 | 0.03 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 8405-01 | 2026-05-12 | 0.02 | 10 | 0.03 | Manati | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3401-02 | 2026-05-12 | 0.01 | 10 | 0.02 | Cayey | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-12 | 0.02 | 10 | 0.03 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6501-02 | 2026-05-12 | 0.03 | 10 | 0.04 | Sabana Grande | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5005-02 | 2026-05-12 | 0.01 | 10 | 0.02 | Ponce | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-12 | 0.02 | 10 | 0.02 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5005-02 | 2026-05-12 | 0.02 | 10 | 0.03 | Ponce | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
727572 | 2.40/4.16 | 1705-02 | 2026-05-13 | 0.14 | 10 | 0.17 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750065 | 7.62/13.20 | 1710-05 | 2026-05-13 | 0.26 | 10 | 0.31 | Toa Alta | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750065 | 2.40/4.16 | 1734-01 | 2026-05-13 | 0.2 | 10 | 0.24 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750065 | 2.40/4.16 | 1734-02 | 2026-05-13 | 0.03 | 10 | 0.04 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
727572 | 7.62/13.20 | 1806-01 | 2026-05-13 | 0.73 | 10 | 0.89 | Toa Baja | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750066 | 4.80/8.32 | 3602-02 | 2026-05-13 | 1.52 | 10 | 1.84 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750066 | 4.80/8.32 | 3603-02 | 2026-05-13 | 0.2 | 10 | 0.24 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
727531 | 2.40/4.16 | 5802-03 | 2026-05-13 | 0.03 | 10 | 0.04 | Juana Diaz | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750067 | 2.40/4.16 | 8602-01 | 2026-05-13 | 0.16 | 10 | 0.19 | Florida | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750067 | 4.80/8.32 | 9103-04 | 2026-05-13 | 0.19 | 10 | 0.23 | Vega Alta | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
N/A | 2.40/4.16 | 7004-06 | 2026-05-13 | 0.03 | 10 | 0.03 | Aguadilla | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 8405-01 | 2026-05-13 | 0.02 | 10 | 0.02 | Manati | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 8405-01 | 2026-05-13 | 0.01 | 10 | 0.01 | Manati | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8004-02 | 2026-05-13 | 0.04 | 10 | 0.04 | Arecibo | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 3014-02 | 2026-05-13 | 0.03 | 10 | 0.03 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 9902-02 | 2026-05-13 | 0.03 | 10 | 0.04 | Orocovis | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 3014-02 | 2026-05-13 | 0.03 | 10 | 0.03 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-05-13 | 0.05 | 10 | 0.07 | San Sebastian | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 3014-02 | 2026-05-13 | 0.02 | 10 | 0.03 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-05-13 | 0.06 | 10 | 0.07 | San Sebastian | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-05-13 | 0.06 | 10 | 0.08 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-05-13 | 0.05 | 10 | 0.06 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 3014-02 | 2026-05-13 | 0.03 | 10 | 0.03 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 3014-02 | 2026-05-13 | 0.05 | 10 | 0.06 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 6406-02 | 2026-05-13 | 0.03 | 10 | 0.04 | San German | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7805-13 | 2026-05-13 | 0.04 | 10 | 0.05 | San Sebastian | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3501-01 | 2026-05-13 | 0.01 | 10 | 0.02 | Aibonito | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6401-04 | 2026-05-13 | 0.03 | 10 | 0.04 | San German | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6401-04 | 2026-05-13 | 0.03 | 10 | 0.04 | San German | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 3015-06 | 2026-05-13 | 0.02 | 10 | 0.02 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 4003-01 | 2026-05-13 | 0.01 | 10 | 0.02 | Guayama | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-05-13 | 0.04 | 10 | 0.05 | San Sebastian | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6401-04 | 2026-05-13 | 0.04 | 10 | 0.04 | San German | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 1416-01 | 2026-05-13 | 0.02 | 10 | 0.03 | San Juan | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-05-13 | 0.06 | 10 | 0.08 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 3015-06 | 2026-05-13 | 0.02 | 10 | 0.03 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 3014-02 | 2026-05-13 | 0.05 | 10 | 0.06 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 8405-01 | 2026-05-13 | 0.03 | 10 | 0.04 | Manati | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6501-04 | 2026-05-13 | 0.02 | 10 | 0.03 | Sabana Grande | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-05-13 | 0.02 | 10 | 0.02 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-13 | 0.03 | 10 | 0.03 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 1416-01 | 2026-05-13 | 0.03 | 10 | 0.03 | San Juan | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 4003-01 | 2026-05-13 | 0.03 | 10 | 0.04 | Guayama | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5005-02 | 2026-05-13 | 0.02 | 10 | 0.03 | Ponce | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 3205-08 | 2026-05-13 | 0.02 | 10 | 0.03 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 3205-08 | 2026-05-13 | 0.02 | 10 | 0.03 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 3205-08 | 2026-05-13 | 0.03 | 10 | 0.04 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 3014-01 | 2026-05-13 | 0.02 | 10 | 0.03 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 5004-06 | 2026-05-13 | 0.02 | 10 | 0.03 | Ponce | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
727572 | 2.40/4.16 | 1705-02 | 2026-05-14 | 0.08 | 10 | 0.1 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750065 | 7.62/13.20 | 1710-05 | 2026-05-14 | 1.04 | 10 | 1.26 | Toa Alta | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750065 | 2.40/4.16 | 1734-01 | 2026-05-14 | 0.21 | 10 | 0.25 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750065 | 2.40/4.16 | 1734-02 | 2026-05-14 | 0.22 | 10 | 0.26 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
727572 | 7.62/13.20 | 1806-01 | 2026-05-14 | 0.21 | 10 | 0.26 | Toa Baja | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750066 | 4.80/8.32 | 3601-04 | 2026-05-14 | 0.86 | 10 | 1.04 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750066 | 4.80/8.32 | 3602-02 | 2026-05-14 | 0.56 | 10 | 0.67 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750066 | 4.80/8.32 | 3603-02 | 2026-05-14 | 0.15 | 10 | 0.18 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750067 | 2.40/4.16 | 8602-01 | 2026-05-14 | 0.41 | 10 | 0.49 | Florida | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750067 | 4.80/8.32 | 9103-04 | 2026-05-14 | 0.45 | 10 | 0.55 | Vega Alta | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
N/A | 4.80/8.32 | 9902-02 | 2026-05-14 | 0.01 | 10 | 0.02 | Orocovis | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-14 | 0.18 | 10 | 0.22 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 3014-01 | 2026-05-14 | 0.02 | 10 | 0.02 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 2101-01 | 2026-05-14 | 0.03 | 10 | 0.04 | Ceiba | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 2101-01 | 2026-05-14 | 0.04 | 10 | 0.05 | Ceiba | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6101-01 | 2026-05-14 | 0.02 | 10 | 0.02 | Anasco | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6101-01 | 2026-05-14 | 0.05 | 10 | 0.06 | Anasco | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 1303-05 | 2026-05-14 | 0.03 | 10 | 0.03 | San Juan | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8004-02 | 2026-05-14 | 0.03 | 10 | 0.03 | Arecibo | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8004-02 | 2026-05-14 | 0.02 | 10 | 0.03 | Arecibo | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8004-02 | 2026-05-14 | 0.02 | 10 | 0.03 | Arecibo | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6306-02 | 2026-05-14 | 0.03 | 10 | 0.04 | Mayagüez | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 9902-02 | 2026-05-14 | 0.05 | 10 | 0.06 | Orocovis | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6306-02 | 2026-05-14 | 0.03 | 10 | 0.04 | Mayagüez | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-14 | 0.02 | 10 | 0.03 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6306-02 | 2026-05-14 | 0.03 | 10 | 0.03 | Mayagüez | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4603-02 | 2026-05-14 | 0.02 | 10 | 0.02 | Coamo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4603-02 | 2026-05-14 | 0.03 | 10 | 0.03 | Coamo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6501-04 | 2026-05-14 | 0.03 | 10 | 0.04 | Sabana Grande | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6306-02 | 2026-05-14 | 0.03 | 10 | 0.04 | Mayagüez | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6306-02 | 2026-05-14 | 0.03 | 10 | 0.03 | Mayagüez | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6306-02 | 2026-05-14 | 0.02 | 10 | 0.03 | Mayagüez | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-05-14 | 0.04 | 10 | 0.05 | San Sebastian | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 9902-02 | 2026-05-14 | 0.02 | 10 | 0.03 | Orocovis | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6501-04 | 2026-05-14 | 0.04 | 10 | 0.04 | Sabana Grande | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 1303-05 | 2026-05-14 | 0.01 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 8405-01 | 2026-05-14 | 0.02 | 10 | 0.02 | Manati | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4603-02 | 2026-05-14 | 0.04 | 10 | 0.05 | Coamo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8004-02 | 2026-05-14 | 0.02 | 10 | 0.03 | Arecibo | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5007-02 | 2026-05-14 | 0.02 | 10 | 0.02 | Ponce | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 2101-01 | 2026-05-14 | 0.03 | 10 | 0.04 | Ceiba | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 2101-01 | 2026-05-14 | 0.03 | 10 | 0.04 | Ceiba | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 9203-02 | 2026-05-14 | 0.03 | 10 | 0.03 | Toa Baja | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8004-02 | 2026-05-14 | 0.02 | 10 | 0.02 | Arecibo | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4603-02 | 2026-05-14 | 0.03 | 10 | 0.03 | Coamo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 9203-02 | 2026-05-14 | 0.01 | 10 | 0.02 | Toa Baja | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 3014-01 | 2026-05-14 | 0.04 | 10 | 0.05 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 8405-01 | 2026-05-14 | 0.03 | 10 | 0.04 | Manati | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 8405-01 | 2026-05-14 | 0.03 | 10 | 0.03 | Manati | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 9203-02 | 2026-05-14 | 0.01 | 10 | 0.02 | Toa Baja | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6501-04 | 2026-05-14 | 0.03 | 10 | 0.04 | Sabana Grande | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 1303-05 | 2026-05-14 | 0.02 | 10 | 0.02 | San Juan | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 3014-01 | 2026-05-14 | 0.02 | 10 | 0.03 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-05-14 | 0.05 | 10 | 0.06 | Cabo Rojo | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7006-03 | 2026-05-14 | 0.06 | 10 | 0.07 | Aguadilla | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7006-03 | 2026-05-14 | 0.04 | 10 | 0.05 | Aguadilla | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4603-02 | 2026-05-14 | 0.01 | 10 | 0.01 | Coamo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 2404-05 | 2026-05-14 | 0.02 | 10 | 0.03 | Canovanas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-14 | 0.05 | 10 | 0.06 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-14 | 0.02 | 10 | 0.03 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 2404-05 | 2026-05-14 | 0.03 | 10 | 0.03 | Canovanas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5005-02 | 2026-05-14 | 0.02 | 10 | 0.02 | Ponce | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 6406-02 | 2026-05-14 | 0.03 | 10 | 0.04 | San German | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
750065 | 2.40/4.16 | 1734-02 | 2026-05-15 | 0.1 | 10 | 0.12 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
727572 | 7.62/13.20 | 1806-01 | 2026-05-15 | 0.01 | 10 | 0.01 | Toa Baja | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
727692 | 2.40/4.16 | 3014-01 | 2026-05-15 | 0.01 | 10 | 0.01 | Caguas | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750066 | 4.80/8.32 | 3601-04 | 2026-05-15 | 1.32 | 10 | 1.6 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750066 | 4.80/8.32 | 3602-02 | 2026-05-15 | 0.13 | 10 | 0.15 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750066 | 4.80/8.32 | 3603-02 | 2026-05-15 | 0.19 | 10 | 0.23 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
N/A | 2.40/4.16 | 7303-01 | 2026-05-15 | 0.04 | 10 | 0.04 | Aguada | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
727572 | 2.40/4.16 | 1705-02 | 2026-05-15 | 0.11 | 10 | 0.13 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
N/A | 2.40/4.16 | 3201-04 | 2026-05-15 | 0.06 | 10 | 0.08 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5501-02 | 2026-05-15 | 0.1 | 10 | 0.12 | Guayanilla | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8004-02 | 2026-05-15 | 0.02 | 10 | 0.02 | Arecibo | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 5011-03 | 2026-05-15 | 0.04 | 10 | 0.05 | Ponce | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8004-02 | 2026-05-15 | 0.03 | 10 | 0.04 | Arecibo | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7006-03 | 2026-05-15 | 0.03 | 10 | 0.03 | Aguadilla | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 3201-04 | 2026-05-15 | 0.03 | 10 | 0.03 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7006-03 | 2026-05-15 | 0.04 | 10 | 0.05 | Aguadilla | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 9004-10 | 2026-05-15 | 0.02 | 10 | 0.03 | Vega Alta | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-15 | 0.01 | 10 | 0.01 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7006-03 | 2026-05-15 | 0.04 | 10 | 0.05 | Aguadilla | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-15 | 0.03 | 10 | 0.04 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5501-02 | 2026-05-15 | 0.04 | 10 | 0.04 | Guayanilla | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 4003-01 | 2026-05-15 | 0.03 | 10 | 0.03 | Guayama | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3401-02 | 2026-05-15 | 0.07 | 10 | 0.09 | Cayey | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7006-03 | 2026-05-15 | 0.02 | 10 | 0.02 | Aguadilla | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5501-02 | 2026-05-15 | 0.1 | 10 | 0.12 | Guayanilla | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7006-03 | 2026-05-15 | 0.02 | 10 | 0.03 | Aguadilla | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 4003-01 | 2026-05-15 | 0.03 | 10 | 0.04 | Guayama | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-01 | 2026-05-15 | 0.04 | 10 | 0.05 | San Sebastian | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 1717-02 | 2026-05-15 | 0.04 | 10 | 0.04 | Bayamon | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 9004-10 | 2026-05-15 | 0.02 | 10 | 0.03 | Vega Alta | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5501-02 | 2026-05-15 | 0.02 | 10 | 0.02 | Guayanilla | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-05-15 | 0.02 | 10 | 0.03 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-05-15 | 0.04 | 10 | 0.05 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-15 | 0.04 | 10 | 0.05 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 1329-03 | 2026-05-15 | 0.01 | 10 | 0.02 | San Juan | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-05-15 | 0.02 | 10 | 0.03 | San Sebastian | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 3205-08 | 2026-05-15 | 0.02 | 10 | 0.03 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 3205-08 | 2026-05-15 | 0.03 | 10 | 0.03 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 9902-02 | 2026-05-16 | 0.02 | 10 | 0.03 | Orocovis | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6501-04 | 2026-05-16 | 0.03 | 10 | 0.04 | Sabana Grande | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 3201-04 | 2026-05-16 | 0.06 | 10 | 0.08 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 8701-02 | 2026-05-16 | 0.04 | 10 | 0.04 | Ciales | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 1343-03 | 2026-05-16 | 0.03 | 10 | 0.03 | Guaynabo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 1343-03 | 2026-05-16 | 0.02 | 10 | 0.03 | Guaynabo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 1343-03 | 2026-05-16 | 0.02 | 10 | 0.03 | Guaynabo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 1343-03 | 2026-05-16 | 0.03 | 10 | 0.03 | Guaynabo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 1343-03 | 2026-05-16 | 0.03 | 10 | 0.04 | Guaynabo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 1343-03 | 2026-05-16 | 0.02 | 10 | 0.02 | Guaynabo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 1343-03 | 2026-05-16 | 0.02 | 10 | 0.03 | Guaynabo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 1343-03 | 2026-05-16 | 0.01 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 1343-03 | 2026-05-16 | 0.02 | 10 | 0.02 | Guaynabo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6004-03 | 2026-05-16 | 0.02 | 10 | 0.03 | Mayagüez | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 9703-01 | 2026-05-16 | 0.02 | 10 | 0.03 | Comerio | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6501-04 | 2026-05-16 | 0.03 | 10 | 0.03 | Sabana Grande | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-05-16 | 0.03 | 10 | 0.04 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 8701-02 | 2026-05-16 | 0.14 | 10 | 0.17 | Ciales | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 9203-02 | 2026-05-16 | 0.02 | 10 | 0.03 | Toa Baja | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7006-03 | 2026-05-16 | 0.02 | 10 | 0.03 | Aguadilla | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7801-04 | 2026-05-16 | 0.02 | 10 | 0.03 | San Sebastian | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 1310-05 | 2026-05-16 | 0.03 | 10 | 0.04 | San Juan | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 3205-08 | 2026-05-16 | 0.02 | 10 | 0.03 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 9203-02 | 2026-05-16 | 0.04 | 10 | 0.05 | Toa Baja | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 3201-04 | 2026-05-16 | 0.02 | 10 | 0.02 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-05-16 | 0.08 | 10 | 0.09 | San Sebastian | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-16 | 0.05 | 10 | 0.07 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 9203-03 | 2026-05-16 | 0.04 | 10 | 0.04 | Toa Baja | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7006-03 | 2026-05-16 | 0.04 | 10 | 0.05 | Aguadilla | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6501-04 | 2026-05-16 | 0.04 | 10 | 0.05 | Sabana Grande | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-05-16 | 0.03 | 10 | 0.04 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-05-16 | 0.03 | 10 | 0.04 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-16 | 0.16 | 10 | 0.2 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 3201-04 | 2026-05-16 | 0.02 | 10 | 0.02 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 4003-02 | 2026-05-16 | 0.02 | 10 | 0.03 | Guayama | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 9703-01 | 2026-05-16 | 0.16 | 10 | 0.2 | Comerio | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-05-16 | 0.02 | 10 | 0.03 | San Sebastian | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 4003-02 | 2026-05-16 | 0.03 | 10 | 0.04 | Guayama | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 9203-03 | 2026-05-16 | 0.04 | 10 | 0.04 | Toa Baja | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6404-02 | 2026-05-16 | 0.02 | 10 | 0.03 | San German | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6404-02 | 2026-05-16 | 0.03 | 10 | 0.04 | San German | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7006-03 | 2026-05-16 | 0.05 | 10 | 0.06 | Aguadilla | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
727572 | 2.40/4.16 | 1705-02 | 2026-05-18 | 0.04 | 10 | 0.05 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750066 | 4.80/8.32 | 3603-02 | 2026-05-18 | 0.07 | 10 | 0.08 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750067 | 4.80/8.32 | 9103-04 | 2026-05-18 | 0.1 | 10 | 0.12 | Vega Alta | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750065 | 2.40/4.16 | 1734-01 | 2026-05-18 | 0.08 | 10 | 0.09 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750065 | 2.40/4.16 | 1734-02 | 2026-05-18 | 0.13 | 10 | 0.15 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
727572 | 7.62/13.20 | 1806-01 | 2026-05-18 | 0.07 | 10 | 0.09 | Toa Baja | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750066 | 4.80/8.32 | 3601-04 | 2026-05-18 | 1.05 | 10 | 1.27 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750067 | 2.40/4.16 | 8602-01 | 2026-05-18 | 0.04 | 10 | 0.05 | Florida | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
N/A | 2.40/4.16 | 5804-01 | 2026-05-18 | 0.1 | 10 | 0.12 | Juana Diaz | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8004-02 | 2026-05-18 | 0.04 | 10 | 0.05 | Arecibo | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8004-02 | 2026-05-18 | 0.04 | 10 | 0.05 | Arecibo | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8004-02 | 2026-05-18 | 0.03 | 10 | 0.04 | Arecibo | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8004-02 | 2026-05-18 | 0.05 | 10 | 0.06 | Arecibo | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7006-03 | 2026-05-18 | 0.03 | 10 | 0.04 | Aguadilla | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 8701-02 | 2026-05-18 | 0.04 | 10 | 0.05 | Ciales | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7006-03 | 2026-05-18 | 0.04 | 10 | 0.05 | Aguadilla | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 1718-03 | 2026-05-18 | 0.03 | 10 | 0.04 | Toa Alta | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6501-02 | 2026-05-18 | 0.03 | 10 | 0.04 | Sabana Grande | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6501-02 | 2026-05-18 | 0.11 | 10 | 0.13 | Sabana Grande | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-05-18 | 0.03 | 10 | 0.03 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7006-03 | 2026-05-18 | 0.04 | 10 | 0.05 | Aguadilla | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 2404-05 | 2026-05-18 | 0.03 | 10 | 0.04 | Canovanas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 2404-05 | 2026-05-18 | 0.03 | 10 | 0.04 | Canovanas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 8701-02 | 2026-05-18 | 0.03 | 10 | 0.04 | Ciales | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7006-03 | 2026-05-18 | 0.03 | 10 | 0.04 | Aguadilla | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 1718-03 | 2026-05-18 | 0.03 | 10 | 0.04 | Toa Alta | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7006-03 | 2026-05-18 | 0.02 | 10 | 0.03 | Aguadilla | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 8701-02 | 2026-05-18 | 0.04 | 10 | 0.04 | Ciales | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6501-02 | 2026-05-18 | 0.04 | 10 | 0.05 | Sabana Grande | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 1718-03 | 2026-05-18 | 0.03 | 10 | 0.04 | Toa Alta | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7006-03 | 2026-05-18 | 0.05 | 10 | 0.06 | Aguadilla | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-05-18 | 0.02 | 10 | 0.03 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 3201-04 | 2026-05-18 | 0.03 | 10 | 0.03 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 1718-03 | 2026-05-18 | 0.03 | 10 | 0.04 | Toa Alta | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 2404-05 | 2026-05-18 | 0.04 | 10 | 0.05 | Canovanas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 4003-01 | 2026-05-18 | 0.06 | 10 | 0.07 | Guayama | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 3201-04 | 2026-05-18 | 0.03 | 10 | 0.04 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-05-18 | 0.03 | 10 | 0.04 | Cabo Rojo | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-05-18 | 0.04 | 10 | 0.05 | Cabo Rojo | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7006-03 | 2026-05-18 | 0.02 | 10 | 0.03 | Aguadilla | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 9902-02 | 2026-05-18 | 0.03 | 10 | 0.03 | Orocovis | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6501-02 | 2026-05-18 | 0.02 | 10 | 0.03 | Sabana Grande | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7006-03 | 2026-05-18 | 0.02 | 10 | 0.03 | Aguadilla | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7006-03 | 2026-05-18 | 0.01 | 10 | 0.01 | Aguadilla | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 8701-02 | 2026-05-18 | 0.04 | 10 | 0.05 | Ciales | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 3205-08 | 2026-05-18 | 0.03 | 10 | 0.03 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 3205-08 | 2026-05-18 | 0.03 | 10 | 0.03 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-18 | 0.03 | 10 | 0.04 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5901-03 | 2026-05-18 | 0.07 | 10 | 0.08 | Villalba | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 3205-08 | 2026-05-18 | 0.03 | 10 | 0.03 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7006-03 | 2026-05-18 | 0.02 | 10 | 0.03 | Aguadilla | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-05-18 | 0.04 | 10 | 0.05 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-18 | 0.03 | 10 | 0.04 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5005-02 | 2026-05-18 | 0.03 | 10 | 0.03 | Ponce | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7006-03 | 2026-05-18 | 0.02 | 10 | 0.02 | Aguadilla | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6101-05 | 2026-05-18 | 0.05 | 10 | 0.06 | Anasco | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6101-05 | 2026-05-18 | 0.05 | 10 | 0.06 | Anasco | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
727572 | 2.40/4.16 | 1705-02 | 2026-05-19 | 0.01 | 10 | 0.01 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750066 | 4.80/8.32 | 3603-02 | 2026-05-19 | 0.16 | 10 | 0.19 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750067 | 4.80/8.32 | 9103-04 | 2026-05-19 | 0.03 | 10 | 0.04 | Vega Alta | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750065 | 2.40/4.16 | 1734-01 | 2026-05-19 | 0.17 | 10 | 0.21 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750065 | 2.40/4.16 | 1734-02 | 2026-05-19 | 0.13 | 10 | 0.16 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750066 | 4.80/8.32 | 3601-04 | 2026-05-19 | 1.63 | 10 | 1.98 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750067 | 2.40/4.16 | 8602-01 | 2026-05-19 | 0.05 | 10 | 0.06 | Florida | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
N/A | 2.40/4.16 | 5005-02 | 2026-05-19 | 0.03 | 10 | 0.04 | Ponce | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 8701-02 | 2026-05-19 | 0.03 | 10 | 0.04 | Ciales | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8004-02 | 2026-05-19 | 0.04 | 10 | 0.04 | Arecibo | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-19 | 0.04 | 10 | 0.05 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 6406-02 | 2026-05-19 | 0.04 | 10 | 0.05 | San German | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 4003-01 | 2026-05-19 | 0.02 | 10 | 0.03 | Guayama | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 1718-03 | 2026-05-19 | 0.03 | 10 | 0.03 | Toa Alta | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 5011-03 | 2026-05-19 | 0.05 | 10 | 0.06 | Ponce | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 5011-03 | 2026-05-19 | 0.03 | 10 | 0.03 | Ponce | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-05-19 | 0.03 | 10 | 0.04 | Cabo Rojo | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-05-19 | 0.05 | 10 | 0.07 | Cabo Rojo | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 1718-03 | 2026-05-19 | 0.03 | 10 | 0.04 | Toa Alta | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6501-02 | 2026-05-19 | 0.03 | 10 | 0.04 | Sabana Grande | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-19 | 0.06 | 10 | 0.07 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6401-04 | 2026-05-19 | 0.04 | 10 | 0.05 | San German | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6406-02 | 2026-05-19 | 0.1 | 10 | 0.12 | San German | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 9902-02 | 2026-05-19 | 0.02 | 10 | 0.02 | Orocovis | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 4003-01 | 2026-05-19 | 0.04 | 10 | 0.05 | Guayama | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 8010-01 | 2026-05-19 | 0.05 | 10 | 0.06 | Hatillo | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7502-02 | 2026-05-19 | 0.05 | 10 | 0.06 | Isabela | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 2201-01 | 2026-05-19 | 0.05 | 10 | 0.06 | Luquillo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6501-02 | 2026-05-19 | 0.01 | 10 | 0.02 | Sabana Grande | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 1710-05 | 2026-05-19 | 0.03 | 10 | 0.03 | Toa Alta | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-19 | 0.12 | 10 | 0.15 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5005-02 | 2026-05-19 | 0.04 | 10 | 0.04 | Ponce | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-19 | 0.04 | 10 | 0.05 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 3205-08 | 2026-05-19 | 0.03 | 10 | 0.03 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5005-02 | 2026-05-19 | 0.03 | 10 | 0.04 | Ponce | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-05-19 | 0.03 | 10 | 0.04 | San Sebastian | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-05-19 | 0.03 | 10 | 0.04 | San Sebastian | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-05-19 | 0.07 | 10 | 0.09 | San Sebastian | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-05-19 | 0.05 | 10 | 0.06 | San Sebastian | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
727692 | 2.40/4.16 | 3014-01 | 2026-05-20 | 0.08 | 10 | 0.1 | Caguas | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
727572 | 2.40/4.16 | 1705-02 | 2026-05-20 | 0.06 | 10 | 0.07 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750066 | 4.80/8.32 | 3603-02 | 2026-05-20 | 0.42 | 10 | 0.51 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750067 | 4.80/8.32 | 9103-04 | 2026-05-20 | 0.18 | 10 | 0.22 | Vega Alta | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750065 | 2.40/4.16 | 1734-01 | 2026-05-20 | 0.23 | 10 | 0.27 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750065 | 2.40/4.16 | 1734-02 | 2026-05-20 | 0.24 | 10 | 0.29 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750066 | 4.80/8.32 | 3601-04 | 2026-05-20 | 0.42 | 10 | 0.51 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750067 | 2.40/4.16 | 8602-01 | 2026-05-20 | 0.84 | 10 | 1.02 | Florida | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
N/A | 2.40/4.16 | 6501-02 | 2026-05-20 | 0.12 | 10 | 0.15 | Sabana Grande | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-05-20 | 0.04 | 10 | 0.05 | Aguas Buenas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3502-02 | 2026-05-20 | 0.01 | 10 | 0.02 | Aibonito | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 7011-03 | 2026-05-20 | 0.05 | 10 | 0.05 | Aguadilla | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 7011-03 | 2026-05-20 | 0.03 | 10 | 0.04 | Aguadilla | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7011-03 | 2026-05-20 | 0.03 | 10 | 0.04 | Aguadilla | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 6406-02 | 2026-05-20 | 0.04 | 10 | 0.05 | San German | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 7011-03 | 2026-05-20 | 0.03 | 10 | 0.04 | Aguadilla | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-05-20 | 0.04 | 10 | 0.05 | Cabo Rojo | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-05-20 | 0.05 | 10 | 0.06 | Cabo Rojo | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 1718-03 | 2026-05-20 | 0.02 | 10 | 0.02 | Toa Alta | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 6406-02 | 2026-05-20 | 0.04 | 10 | 0.05 | San German | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 6406-02 | 2026-05-20 | 0.03 | 10 | 0.04 | San German | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 9902-02 | 2026-05-20 | 0.05 | 10 | 0.06 | Orocovis | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5012-02 | 2026-05-20 | 0.02 | 10 | 0.03 | Ponce | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 9902-02 | 2026-05-20 | 0.03 | 10 | 0.04 | Orocovis | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8301-03 | 2026-05-20 | 0.1 | 10 | 0.12 | Jayuya | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-20 | 0.03 | 10 | 0.04 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 1525-05 | 2026-05-20 | 0.02 | 10 | 0.02 | San Juan | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-05-20 | 0.04 | 10 | 0.04 | San Sebastian | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5012-02 | 2026-05-20 | 0.03 | 10 | 0.03 | Ponce | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5012-02 | 2026-05-20 | 0.02 | 10 | 0.03 | Ponce | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 7011-03 | 2026-05-20 | 0.06 | 10 | 0.07 | Aguadilla | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-20 | 0.05 | 10 | 0.06 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6501-02 | 2026-05-20 | 0.01 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 9902-02 | 2026-05-20 | 0.02 | 10 | 0.03 | Orocovis | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 7011-03 | 2026-05-20 | 0.04 | 10 | 0.05 | Aguadilla | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-20 | 0.06 | 10 | 0.07 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-05-20 | 0.03 | 10 | 0.04 | San Sebastian | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7005-03 | 2026-05-20 | 0.02 | 10 | 0.02 | Aguadilla | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5012-02 | 2026-05-20 | 0.03 | 10 | 0.03 | Ponce | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 6406-02 | 2026-05-20 | 0.04 | 10 | 0.04 | San German | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-05-20 | 0.04 | 10 | 0.05 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-20 | 0.03 | 10 | 0.03 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6501-02 | 2026-05-20 | 0.04 | 10 | 0.05 | Sabana Grande | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
727572 | 2.40/4.16 | 1705-02 | 2026-05-21 | 0.07 | 10 | 0.08 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750066 | 4.80/8.32 | 3603-02 | 2026-05-21 | 0.19 | 10 | 0.23 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750067 | 4.80/8.32 | 9103-04 | 2026-05-21 | 0.06 | 10 | 0.07 | Vega Alta | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750065 | 2.40/4.16 | 1734-01 | 2026-05-21 | 0.11 | 10 | 0.14 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750065 | 2.40/4.16 | 1734-02 | 2026-05-21 | 0.09 | 10 | 0.1 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750066 | 4.80/8.32 | 3601-04 | 2026-05-21 | 1.28 | 10 | 1.55 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750067 | 2.40/4.16 | 8011-01 | 2026-05-21 | 1.3 | 10 | 1.58 | Arecibo | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750067 | 2.40/4.16 | 8602-01 | 2026-05-21 | 0.001 | 10 | 0.001 | Florida | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
N/A | 2.40/4.16 | 7502-02 | 2026-05-21 | 0.04 | 10 | 0.05 | Isabela | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7301-02 | 2026-05-21 | 0.02 | 10 | 0.02 | Rincon | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-05-21 | 0.03 | 10 | 0.04 | Aguas Buenas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-05-21 | 0.03 | 10 | 0.04 | Arecibo | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-05-21 | 0.03 | 10 | 0.04 | Aguas Buenas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 9501-02 | 2026-05-21 | 0.12 | 10 | 0.14 | Corozal | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 9501-02 | 2026-05-21 | 0.12 | 10 | 0.14 | Corozal | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7301-02 | 2026-05-21 | 0.02 | 10 | 0.03 | Rincon | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 6406-02 | 2026-05-21 | 0.04 | 10 | 0.04 | San German | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-05-21 | 0.04 | 10 | 0.05 | Aguas Buenas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-21 | 0.04 | 10 | 0.04 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7502-02 | 2026-05-21 | 0.04 | 10 | 0.05 | Isabela | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-05-21 | 0.03 | 10 | 0.04 | Aguas Buenas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5012-04 | 2026-05-21 | 0.02 | 10 | 0.03 | Ponce | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 6406-02 | 2026-05-21 | 0.04 | 10 | 0.05 | San German | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-05-21 | 0.04 | 10 | 0.05 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 9902-02 | 2026-05-21 | 0.04 | 10 | 0.05 | Orocovis | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-05-21 | 0.05 | 10 | 0.06 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7005-03 | 2026-05-21 | 0.02 | 10 | 0.02 | Aguadilla | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7301-02 | 2026-05-21 | 0.04 | 10 | 0.05 | Rincon | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6501-02 | 2026-05-21 | 0.04 | 10 | 0.05 | Sabana Grande | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-05-21 | 0.01 | 10 | 0.01 | Arecibo | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 4003-01 | 2026-05-21 | 0.02 | 10 | 0.03 | Guayama | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 4003-01 | 2026-05-21 | 0.03 | 10 | 0.03 | Guayama | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 4003-01 | 2026-05-21 | 0.03 | 10 | 0.04 | Guayama | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5005-02 | 2026-05-21 | 0.03 | 10 | 0.04 | Ponce | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-21 | 0.03 | 10 | 0.04 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5501-04 | 2026-05-21 | 0.1 | 10 | 0.12 | Guayanilla | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
727572 | 2.40/4.16 | 1705-02 | 2026-05-22 | 0.02 | 10 | 0.02 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750066 | 4.80/8.32 | 3603-02 | 2026-05-22 | 0.13 | 10 | 0.16 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750065 | 2.40/4.16 | 1734-02 | 2026-05-22 | 0.18 | 10 | 0.22 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750066 | 4.80/8.32 | 3601-04 | 2026-05-22 | 0.95 | 10 | 1.15 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-05-22 | 0.04 | 10 | 0.05 | Aguas Buenas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8004-02 | 2026-05-22 | 0.03 | 10 | 0.04 | Arecibo | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 6406-02 | 2026-05-22 | 0.04 | 10 | 0.05 | San German | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-05-22 | 0.03 | 10 | 0.03 | Aguas Buenas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-05-22 | 0.02 | 10 | 0.03 | Aguas Buenas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-04 | 2026-05-22 | 0.11 | 10 | 0.13 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-04 | 2026-05-22 | 0.05 | 10 | 0.07 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-04 | 2026-05-22 | 0.1 | 10 | 0.12 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-22 | 0.03 | 10 | 0.03 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-04 | 2026-05-22 | 0.06 | 10 | 0.07 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-05-22 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-05-22 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5005-02 | 2026-05-22 | 0.03 | 10 | 0.04 | Ponce | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5005-02 | 2026-05-22 | 0.03 | 10 | 0.04 | Ponce | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-04 | 2026-05-22 | 0.1 | 10 | 0.12 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7502-02 | 2026-05-22 | 0.04 | 10 | 0.05 | Isabela | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7502-02 | 2026-05-22 | 0.05 | 10 | 0.06 | Isabela | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-04 | 2026-05-22 | 0.08 | 10 | 0.1 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7502-02 | 2026-05-22 | 0.05 | 10 | 0.07 | Isabela | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 9501-02 | 2026-05-22 | 0.07 | 10 | 0.09 | Corozal | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-04 | 2026-05-22 | 0.04 | 10 | 0.05 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 8701-02 | 2026-05-22 | 0.02 | 10 | 0.03 | Ciales | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 8701-02 | 2026-05-22 | 0.02 | 10 | 0.03 | Ciales | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 9902-02 | 2026-05-22 | 0.04 | 10 | 0.05 | Orocovis | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-05-22 | 0.04 | 10 | 0.05 | Cabo Rojo | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-05-22 | 0.05 | 10 | 0.06 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-05-22 | 0.04 | 10 | 0.05 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5005-02 | 2026-05-22 | 0.03 | 10 | 0.04 | Ponce | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6501-02 | 2026-05-22 | 0.02 | 10 | 0.03 | Sabana Grande | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-22 | 0.07 | 10 | 0.09 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 3205-08 | 2026-05-22 | 0.05 | 10 | 0.06 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 3205-08 | 2026-05-22 | 0.04 | 10 | 0.05 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 3205-08 | 2026-05-22 | 0.05 | 10 | 0.06 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 3205-08 | 2026-05-22 | 0.05 | 10 | 0.06 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 3205-08 | 2026-05-22 | 0.06 | 10 | 0.07 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3013-01 | 2026-05-22 | 0.08 | 10 | 0.09 | Gurabo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3013-01 | 2026-05-22 | 0.05 | 10 | 0.06 | Gurabo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3013-01 | 2026-05-22 | 0.08 | 10 | 0.09 | Gurabo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
727692 | 4.80/8.32 | 3009-01 | 2026-05-23 | 0.02 | 10 | 0.02 | Caguas | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
727572 | 2.40/4.16 | 1705-02 | 2026-05-23 | 0.03 | 10 | 0.04 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-23 | 0.03 | 10 | 0.04 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-05-23 | 0.03 | 10 | 0.03 | Cabo Rojo | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-05-23 | 0.04 | 10 | 0.05 | Cabo Rojo | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5005-02 | 2026-05-23 | 0.02 | 10 | 0.02 | Ponce | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 3201-04 | 2026-05-23 | 0.03 | 10 | 0.04 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 3205-08 | 2026-05-23 | 0.03 | 10 | 0.04 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 6406-02 | 2026-05-23 | 0.04 | 10 | 0.04 | San German | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 9207-08 | 2026-05-23 | 0.05 | 10 | 0.06 | Toa Baja | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 9101-04 | 2026-05-23 | 0.04 | 10 | 0.04 | Vega Alta | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-23 | 0.03 | 10 | 0.04 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-05-23 | 0.03 | 10 | 0.04 | San Sebastian | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 4003-02 | 2026-05-23 | 0.03 | 10 | 0.04 | Guayama | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 2604-03 | 2026-05-23 | 0.04 | 10 | 0.05 | Yabucoa | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 2604-03 | 2026-05-23 | 0.04 | 10 | 0.05 | Yabucoa | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 4003-02 | 2026-05-23 | 0.03 | 10 | 0.04 | Guayama | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5005-02 | 2026-05-23 | 0.04 | 10 | 0.05 | Ponce | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-05-23 | 0.05 | 10 | 0.06 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6501-02 | 2026-05-23 | 0.02 | 10 | 0.02 | Sabana Grande | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-05-23 | 0.05 | 10 | 0.06 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7103-04 | 2026-05-23 | 0.14 | 10 | 0.18 | Moca | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-23 | 0.02 | 10 | 0.02 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 6406-02 | 2026-05-23 | 0.04 | 10 | 0.05 | San German | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 3205-08 | 2026-05-23 | 0.03 | 10 | 0.03 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.16/7.20 | 8010-01 | 2026-05-23 | 0.08 | 10 | 0.1 | Hatillo | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6801-02 | 2026-05-24 | 0.13 | 10 | 0.16 | Hormigueros | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8104-02 | 2026-05-24 | 0.31 | 10 | 0.37 | Utuado | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 3201-04 | 2026-05-25 | 0.04 | 10 | 0.05 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-05-25 | 0.02 | 10 | 0.03 | San Sebastian | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5012-02 | 2026-05-25 | 0.03 | 10 | 0.03 | Ponce | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5012-02 | 2026-05-25 | 0.03 | 10 | 0.03 | Ponce | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-05-25 | 0.04 | 10 | 0.05 | San Sebastian | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 3201-04 | 2026-05-25 | 0.11 | 10 | 0.13 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5012-02 | 2026-05-25 | 0.01 | 10 | 0.01 | Ponce | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4501-04 | 2026-05-25 | 0.03 | 10 | 0.04 | Salinas | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 3201-04 | 2026-05-25 | 0.04 | 10 | 0.05 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
727572 | 2.40/4.16 | 1705-02 | 2026-05-26 | 0.02 | 10 | 0.02 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750066 | 4.80/8.32 | 3603-02 | 2026-05-26 | 0.13 | 10 | 0.16 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750067 | 4.80/8.32 | 9103-04 | 2026-05-26 | 0.19 | 10 | 0.23 | Vega Alta | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750065 | 2.40/4.16 | 1734-01 | 2026-05-26 | 0.04 | 10 | 0.05 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750065 | 2.40/4.16 | 1734-02 | 2026-05-26 | 0.05 | 10 | 0.06 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750066 | 4.80/8.32 | 3601-04 | 2026-05-26 | 1.13 | 10 | 1.37 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750067 | 2.40/4.16 | 8011-01 | 2026-05-26 | 1.11 | 10 | 1.34 | Arecibo | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
N/A | 4.80/8.32 | 9003-06 | 2026-05-26 | 0.03 | 10 | 0.04 | Vega Baja | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5005-02 | 2026-05-26 | 0.03 | 10 | 0.04 | Ponce | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7502-02 | 2026-05-26 | 0.04 | 10 | 0.05 | Isabela | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 9902-02 | 2026-05-26 | 0.04 | 10 | 0.05 | Orocovis | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 7008-07 | 2026-05-26 | 0.04 | 10 | 0.05 | Aguadilla | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-05-26 | 0.03 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-26 | 0.04 | 10 | 0.05 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 9003-06 | 2026-05-26 | 0.04 | 10 | 0.05 | Vega Baja | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-05-26 | 0.02 | 10 | 0.02 | Aguas Buenas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5005-02 | 2026-05-26 | 0.03 | 10 | 0.03 | Ponce | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5005-02 | 2026-05-26 | 0.03 | 10 | 0.03 | Ponce | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-26 | 0.03 | 10 | 0.04 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6501-02 | 2026-05-26 | 0.03 | 10 | 0.04 | Sabana Grande | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 9501-02 | 2026-05-26 | 0.07 | 10 | 0.09 | Corozal | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 7008-07 | 2026-05-26 | 0.01 | 10 | 0.01 | Aguadilla | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-05-26 | 0.06 | 10 | 0.07 | Cabo Rojo | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4101-03 | 2026-05-26 | 0.03 | 10 | 0.04 | Arroyo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7502-02 | 2026-05-26 | 0.03 | 10 | 0.04 | Isabela | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 9501-02 | 2026-05-26 | 0.1 | 10 | 0.12 | Corozal | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6501-02 | 2026-05-26 | 0.07 | 10 | 0.08 | Sabana Grande | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7502-02 | 2026-05-26 | 0.04 | 10 | 0.04 | Isabela | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7502-02 | 2026-05-26 | 0.06 | 10 | 0.07 | Isabela | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 9902-02 | 2026-05-26 | 0.06 | 10 | 0.08 | Orocovis | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7502-02 | 2026-05-26 | 0.04 | 10 | 0.05 | Isabela | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7502-02 | 2026-05-26 | 0.03 | 10 | 0.04 | Isabela | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 9003-06 | 2026-05-26 | 0.04 | 10 | 0.04 | Vega Baja | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-05-26 | 0.02 | 10 | 0.02 | Aguas Buenas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 3201-04 | 2026-05-26 | 0.06 | 10 | 0.07 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6201-03 | 2026-05-26 | 0.06 | 10 | 0.07 | Las Marias | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5005-02 | 2026-05-26 | 0.02 | 10 | 0.03 | Ponce | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4101-03 | 2026-05-26 | 0.03 | 10 | 0.03 | Arroyo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6201-03 | 2026-05-26 | 0.17 | 10 | 0.21 | Las Marias | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-05-26 | 0.18 | 10 | 0.22 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-05-26 | 0.18 | 10 | 0.22 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 3201-04 | 2026-05-26 | 0.04 | 10 | 0.05 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4002-03 | 2026-05-26 | 0.02 | 10 | 0.03 | Guayama | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6404-02 | 2026-05-26 | 0.09 | 10 | 0.1 | San German | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
727692 | 4.80/8.32 | 3009-04 | 2026-05-27 | 0.07 | 10 | 0.08 | Caguas | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750066 | 4.80/8.32 | 3603-02 | 2026-05-27 | 0.18 | 10 | 0.22 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
727572 | 2.40/4.16 | 1705-02 | 2026-05-27 | 0.16 | 10 | 0.19 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750067 | 7.62/13.20 | 8014-06 | 2026-05-27 | 0.1 | 10 | 0.12 | Arecibo | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750067 | 4.80/8.32 | 9103-04 | 2026-05-27 | 0.24 | 10 | 0.29 | Vega Alta | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750065 | 2.40/4.16 | 1734-01 | 2026-05-27 | 0.05 | 10 | 0.07 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750066 | 4.80/8.32 | 3601-04 | 2026-05-27 | 1.32 | 10 | 1.6 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750067 | 2.40/4.16 | 8011-01 | 2026-05-27 | 1.16 | 10 | 1.4 | Arecibo | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-05-27 | 0.18 | 10 | 0.22 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5012-03 | 2026-05-27 | 0.17 | 10 | 0.21 | Ponce | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 7008-07 | 2026-05-27 | 0.02 | 10 | 0.03 | Aguadilla | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 6406-02 | 2026-05-27 | 0.04 | 10 | 0.04 | San German | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 9003-06 | 2026-05-27 | 0.04 | 10 | 0.05 | Vega Baja | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 3201-04 | 2026-05-27 | 0.05 | 10 | 0.06 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-01 | 2026-05-27 | 0.11 | 10 | 0.14 | San Sebastian | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7301-01 | 2026-05-27 | 0.02 | 10 | 0.03 | Rincon | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 6406-02 | 2026-05-27 | 0.04 | 10 | 0.04 | San German | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-27 | 0.03 | 10 | 0.04 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-05-27 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7104-05 | 2026-05-27 | 0.12 | 10 | 0.15 | Moca | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-05-27 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4504-03 | 2026-05-27 | 0.03 | 10 | 0.03 | Salinas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 6802-02 | 2026-05-27 | 0.04 | 10 | 0.05 | Hormigueros | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5012-03 | 2026-05-27 | 0.17 | 10 | 0.21 | Ponce | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 7008-07 | 2026-05-27 | 0.02 | 10 | 0.02 | Aguadilla | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 9003-06 | 2026-05-27 | 0.04 | 10 | 0.05 | Vega Baja | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4504-03 | 2026-05-27 | 0.02 | 10 | 0.03 | Salinas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6305-03 | 2026-05-27 | 0.15 | 10 | 0.18 | Maricao | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 1903-05 | 2026-05-27 | 0.03 | 10 | 0.03 | Guaynabo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-05-27 | 0.04 | 10 | 0.04 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 6802-02 | 2026-05-27 | 0.04 | 10 | 0.05 | Hormigueros | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5501-04 | 2026-05-27 | 0.03 | 10 | 0.04 | Guayanilla | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 6802-02 | 2026-05-27 | 0.04 | 10 | 0.05 | Hormigueros | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-05-27 | 0.03 | 10 | 0.04 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8005-01 | 2026-05-27 | 0.06 | 10 | 0.08 | Utuado | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 9902-02 | 2026-05-27 | 0.03 | 10 | 0.03 | Orocovis | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-05-27 | 0.03 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7502-02 | 2026-05-27 | 0.02 | 10 | 0.03 | Isabela | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7502-02 | 2026-05-27 | 0.04 | 10 | 0.05 | Isabela | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 9902-02 | 2026-05-27 | 0.03 | 10 | 0.04 | Orocovis | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 9902-02 | 2026-05-27 | 0.02 | 10 | 0.03 | Orocovis | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4504-03 | 2026-05-27 | 0.05 | 10 | 0.06 | Salinas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-27 | 0.03 | 10 | 0.03 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-05-27 | 0.03 | 10 | 0.04 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4504-03 | 2026-05-27 | 0.05 | 10 | 0.06 | Salinas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-05-27 | 0.18 | 10 | 0.22 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-27 | 0.21 | 10 | 0.26 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-27 | 0.15 | 10 | 0.18 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7403-03 | 2026-05-27 | 0.07 | 10 | 0.09 | Isabela | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 3205-08 | 2026-05-27 | 0.03 | 10 | 0.03 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
750066 | 4.80/8.32 | 3601-01 | 2026-05-28 | 0.11 | 10 | 0.13 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750066 | 4.80/8.32 | 3601-03 | 2026-05-28 | 0.06 | 10 | 0.07 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750067 | 7.62/13.20 | 8014-06 | 2026-05-28 | 0.14 | 10 | 0.17 | Arecibo | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750067 | 4.80/8.32 | 9103-04 | 2026-05-28 | 0.34 | 10 | 0.41 | Vega Alta | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750065 | 2.40/4.16 | 1734-01 | 2026-05-28 | 0.1 | 10 | 0.12 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750065 | 2.40/4.16 | 1734-02 | 2026-05-28 | 0.05 | 10 | 0.06 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750066 | 4.80/8.32 | 3601-04 | 2026-05-28 | 0.14 | 10 | 0.17 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750066 | 4.80/8.32 | 3602-01 | 2026-05-28 | 1.3 | 10 | 1.57 | Cayey | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750066 | 4.80/8.32 | 3603-01 | 2026-05-28 | 0.29 | 10 | 0.35 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750067 | 2.40/4.16 | 8011-01 | 2026-05-28 | 0.34 | 10 | 0.41 | Arecibo | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-05-28 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 9003-06 | 2026-05-28 | 0.02 | 10 | 0.03 | Vega Baja | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-05-28 | 0.03 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-05-28 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5005-02 | 2026-05-28 | 0.03 | 10 | 0.03 | Ponce | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-05-28 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 1707-04 | 2026-05-28 | 0.03 | 10 | 0.04 | Bayamon | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-04 | 2026-05-28 | 0.06 | 10 | 0.07 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7502-02 | 2026-05-28 | 0.05 | 10 | 0.06 | Isabela | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4001-03 | 2026-05-28 | 0.03 | 10 | 0.04 | Guayama | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 1346-04 | 2026-05-28 | 0.02 | 10 | 0.03 | San Juan | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-05-28 | 0.03 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6501-02 | 2026-05-28 | 0.02 | 10 | 0.03 | Sabana Grande | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-05-28 | 0.03 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-05-28 | 0.03 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-05-28 | 0.04 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-05-28 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-05-28 | 0.04 | 10 | 0.05 | Arecibo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-05-28 | 0.04 | 10 | 0.05 | Arecibo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-05-28 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-05-28 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-05-28 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-05-28 | 0.06 | 10 | 0.07 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-05-28 | 0.03 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 9003-06 | 2026-05-28 | 0.03 | 10 | 0.03 | Vega Baja | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8005-01 | 2026-05-28 | 0.03 | 10 | 0.04 | Utuado | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-05-28 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-05-28 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7301-01 | 2026-05-28 | 0.03 | 10 | 0.04 | Rincon | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 1704-01 | 2026-05-28 | 0.02 | 10 | 0.02 | Bayamon | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 1707-04 | 2026-05-28 | 0.03 | 10 | 0.04 | Bayamon | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-05-28 | 0.03 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 3201-04 | 2026-05-28 | 0.06 | 10 | 0.07 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 1707-04 | 2026-05-28 | 0.03 | 10 | 0.04 | Bayamon | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-04 | 2026-05-28 | 0.05 | 10 | 0.06 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8004-01 | 2026-05-28 | 0.04 | 10 | 0.05 | Arecibo | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-05-28 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7701-01 | 2026-05-28 | 0.03 | 10 | 0.04 | Hatillo | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-05-28 | 0.03 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-05-28 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-05-28 | 0.03 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-05-28 | 0.04 | 10 | 0.05 | Arecibo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 6802-02 | 2026-05-28 | 0.04 | 10 | 0.05 | Hormigueros | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 6802-02 | 2026-05-28 | 0.05 | 10 | 0.06 | Hormigueros | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-05-28 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7005-03 | 2026-05-28 | 0.02 | 10 | 0.02 | Aguadilla | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7005-03 | 2026-05-28 | 0.02 | 10 | 0.02 | Aguadilla | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7502-02 | 2026-05-28 | 0.05 | 10 | 0.06 | Isabela | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 1204-02 | 2026-05-28 | 0.03 | 10 | 0.03 | Trujillo Alto | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 1204-02 | 2026-05-28 | 0.01 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 3201-04 | 2026-05-28 | 0.03 | 10 | 0.04 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5005-02 | 2026-05-28 | 0.02 | 10 | 0.02 | Ponce | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 3201-04 | 2026-05-28 | 0.07 | 10 | 0.08 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5005-02 | 2026-05-28 | 0.02 | 10 | 0.03 | Ponce | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 3201-04 | 2026-05-28 | 0.03 | 10 | 0.04 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5005-02 | 2026-05-28 | 0.02 | 10 | 0.03 | Ponce | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-05-28 | 0.06 | 10 | 0.07 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-28 | 0.04 | 10 | 0.04 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6501-02 | 2026-05-28 | 0.03 | 10 | 0.04 | Sabana Grande | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-05-28 | 0.18 | 10 | 0.22 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 3201-04 | 2026-05-28 | 0.03 | 10 | 0.03 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
750066 | 4.80/8.32 | 3601-01 | 2026-05-29 | 0.02 | 10 | 0.02 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750066 | 4.80/8.32 | 3601-03 | 2026-05-29 | 0.01 | 10 | 0.01 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750066 | 4.80/8.32 | 3603-02 | 2026-05-29 | 0.09 | 10 | 0.11 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750067 | 7.62/13.20 | 8014-06 | 2026-05-29 | 0.36 | 10 | 0.44 | Arecibo | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
727572 | 2.40/4.16 | 1705-02 | 2026-05-29 | 0.07 | 10 | 0.08 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750067 | 4.80/8.32 | 9103-04 | 2026-05-29 | 0.21 | 10 | 0.25 | Vega Alta | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750065 | 2.40/4.16 | 1734-01 | 2026-05-29 | 0.09 | 10 | 0.11 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750066 | 4.80/8.32 | 3602-01 | 2026-05-29 | 0.26 | 10 | 0.31 | Cayey | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750066 | 4.80/8.32 | 3701-01 | 2026-05-29 | 0.43 | 10 | 0.52 | Aguas Buenas | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
750067 | 2.40/4.16 | 8011-01 | 2026-05-29 | 0.1 | 10 | 0.12 | Arecibo | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | May | Q4 | FY2026
N/A | 7.62/13.20 | 1204-04 | 2026-05-29 | 0.03 | 10 | 0.04 | San Juan | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7502-02 | 2026-05-29 | 0.05 | 10 | 0.06 | Isabela | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 6406-02 | 2026-05-29 | 0.04 | 10 | 0.04 | San German | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-05-29 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-05-29 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6501-02 | 2026-05-29 | 0.03 | 10 | 0.04 | Sabana Grande | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5005-02 | 2026-05-29 | 0.03 | 10 | 0.04 | Ponce | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5005-02 | 2026-05-29 | 0.03 | 10 | 0.03 | Ponce | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7805-13 | 2026-05-29 | 0.04 | 10 | 0.05 | San Sebastian | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 1204-04 | 2026-05-29 | 0.02 | 10 | 0.02 | San Juan | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 1204-04 | 2026-05-29 | 0.04 | 10 | 0.05 | San Juan | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 1204-04 | 2026-05-29 | 0.02 | 10 | 0.03 | San Juan | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-05-29 | 0.03 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7301-01 | 2026-05-29 | 0.03 | 10 | 0.04 | Rincon | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-05-29 | 0.05 | 10 | 0.06 | Arecibo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7301-01 | 2026-05-29 | 0.03 | 10 | 0.04 | Rincon | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7301-01 | 2026-05-29 | 0.03 | 10 | 0.04 | Rincon | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7502-02 | 2026-05-29 | 0.04 | 10 | 0.05 | Isabela | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-29 | 0.03 | 10 | 0.04 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-05-29 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-05-29 | 0.05 | 10 | 0.06 | Arecibo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 6802-02 | 2026-05-29 | 0.04 | 10 | 0.05 | Hormigueros | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-05-29 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 6802-02 | 2026-05-29 | 0.04 | 10 | 0.05 | Hormigueros | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5005-02 | 2026-05-29 | 0.03 | 10 | 0.04 | Ponce | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4002-03 | 2026-05-29 | 0.02 | 10 | 0.02 | Guayama | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6501-02 | 2026-05-29 | 0.05 | 10 | 0.06 | Sabana Grande | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-29 | 0.08 | 10 | 0.09 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7502-02 | 2026-05-29 | 0.04 | 10 | 0.05 | Isabela | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 3201-04 | 2026-05-29 | 0.06 | 10 | 0.07 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 3201-04 | 2026-05-29 | 0.03 | 10 | 0.04 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 3201-04 | 2026-05-29 | 0.03 | 10 | 0.04 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4002-03 | 2026-05-29 | 0.03 | 10 | 0.03 | Guayama | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6501-02 | 2026-05-29 | 0.04 | 10 | 0.05 | Sabana Grande | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 3201-04 | 2026-05-29 | 0.05 | 10 | 0.06 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7301-01 | 2026-05-29 | 0.03 | 10 | 0.03 | Rincon | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-29 | 0.08 | 10 | 0.1 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7301-01 | 2026-05-29 | 0.03 | 10 | 0.04 | Rincon | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5005-02 | 2026-05-29 | 0.02 | 10 | 0.03 | Ponce | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7301-01 | 2026-05-29 | 0.03 | 10 | 0.04 | Rincon | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-29 | 0.1 | 10 | 0.12 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-05-29 | 0.05 | 10 | 0.06 | San Sebastian | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 2601-01 | 2026-05-29 | 0.03 | 10 | 0.04 | Humacao | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 7008-07 | 2026-05-30 | 0.01 | 10 | 0.01 | Aguadilla | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 7008-07 | 2026-05-30 | 0.04 | 10 | 0.05 | Aguadilla | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 7008-07 | 2026-05-30 | 0.04 | 10 | 0.05 | Aguadilla | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5001-02 | 2026-05-30 | 0.03 | 10 | 0.04 | Ponce | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 8014-07 | 2026-05-30 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 1343-03 | 2026-05-30 | 0.03 | 10 | 0.03 | Guaynabo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 9001-02 | 2026-05-30 | 0.03 | 10 | 0.03 | Vega Baja | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-05-30 | 0.03 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-05-30 | 0.05 | 10 | 0.06 | Arecibo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4603-02 | 2026-05-30 | 0.05 | 10 | 0.06 | Coamo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7702-03 | 2026-05-30 | 0.04 | 10 | 0.04 | Hatillo | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 3205-08 | 2026-05-30 | 0.06 | 10 | 0.08 | Juncos | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 1342-04 | 2026-05-30 | 0.02 | 10 | 0.02 | San Juan | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 6406-02 | 2026-05-30 | 0.04 | 10 | 0.05 | San German | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 1204-04 | 2026-05-30 | 0.03 | 10 | 0.03 | San Juan | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 1343-03 | 2026-05-30 | 0.03 | 10 | 0.04 | Guaynabo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 5001-02 | 2026-05-30 | 0.03 | 10 | 0.03 | Ponce | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 6406-02 | 2026-05-30 | 0.04 | 10 | 0.04 | San German | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-30 | 0.03 | 10 | 0.04 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-05-30 | 0.06 | 10 | 0.07 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-05-30 | 0.06 | 10 | 0.07 | Caguas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 6501-02 | 2026-05-30 | 0.06 | 10 | 0.08 | Sabana Grande | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4602-01 | 2026-05-30 | 0.06 | 10 | 0.08 | Coamo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4602-01 | 2026-05-30 | 0.06 | 10 | 0.08 | Coamo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-05-30 | 0.03 | 10 | 0.03 | Patillas | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 9207-08 | 2026-05-30 | 0.02 | 10 | 0.03 | Toa Baja | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-05-30 | 0.04 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-05-30 | 0.02 | 10 | 0.02 | Arecibo | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 4003-02 | 2026-05-30 | 0.02 | 10 | 0.03 | Guayama | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-05-30 | 0.04 | 10 | 0.05 | San Sebastian | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 6406-02 | 2026-05-30 | 0.04 | 10 | 0.05 | San German | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 7008-07 | 2026-05-30 | 0.01 | 10 | 0.02 | Aguadilla | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 1204-02 | 2026-05-30 | 0.03 | 10 | 0.03 | Trujillo Alto | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 9501-02 | 2026-05-30 | 0.08 | 10 | 0.09 | Corozal | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 4.80/8.32 | 9501-02 | 2026-05-30 | 0.09 | 10 | 0.1 | Corozal | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 7008-07 | 2026-05-31 | 0.04 | 10 | 0.05 | Aguadilla | Xperts | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 7.62/13.20 | 1204-02 | 2026-05-31 | 0.09 | 10 | 0.11 | Trujillo Alto | Wright Tree Services | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 8302-05 | 2026-05-31 | 0.13 | 10 | 0.16 | Jayuya | PIS (Perfect Integrated Solutions) | In Progress | Corrective / Reactive | Ian Kreher | O&M / Rate Payer | May | Q4 | FY2026
N/A | 2.40/4.16 | 1002-02 | 2026-06-27 | 0.04 | 10 | 0.048485 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1002-02 | 2026-06-27 | 0.03 | 10 | 0.036364 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1002-02 | 2026-06-27 | 0.03 | 10 | 0.036364 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1002-02 | 2026-06-27 | 0.01 | 10 | 0.012121 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1002-02 | 2026-06-27 | 0.01 | 10 | 0.012121 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1002-02 | 2026-06-27 | 0.01 | 10 | 0.012121 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1002-02 | 2026-06-27 | 0.03 | 10 | 0.036364 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1002-02 | 2026-06-27 | 0.03 | 10 | 0.036364 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1002-02 | 2026-06-27 | 0.03 | 10 | 0.036364 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1002-02 | 2026-06-27 | 0.02 | 10 | 0.024242 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1002-02 | 2026-06-27 | 0.02 | 10 | 0.024242 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1002-02 | 2026-06-27 | 0.02 | 10 | 0.024242 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1002-02 | 2026-06-27 | 0.01 | 10 | 0.012121 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1002-02 | 2026-06-29 | 0.03 | 10 | 0.036364 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1002-02 | 2026-06-27 | 0.03 | 10 | 0.036364 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1002-02 | 2026-06-27 | 0.03 | 10 | 0.036364 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1002-02 | 2026-06-29 | 0.03 | 10 | 0.036364 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1002-02 | 2026-06-29 | 0.04 | 10 | 0.048485 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1002-02 | 2026-06-29 | 0.02 | 10 | 0.024242 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1002-02 | 2026-06-27 | 0.02 | 10 | 0.024242 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1109-05 | 2026-06-24 | 0.02 | 10 | 0.024242 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1109-05 | 2026-06-24 | 0.01 | 10 | 0.012121 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1109-05 | 2026-06-24 | 0.02 | 10 | 0.024242 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1109-05 | 2026-06-24 | 0.02 | 10 | 0.024242 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1109-05 | 2026-06-24 | 0.02 | 10 | 0.024242 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1109-05 | 2026-06-24 | 0.02 | 10 | 0.024242 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1109-05 | 2026-06-24 | 0.005 | 10 | 0.0060606 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1109-05 | 2026-06-24 | 0.02 | 10 | 0.024242 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1109-05 | 2026-06-24 | 0.01 | 10 | 0.012121 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1109-05 | 2026-06-24 | 0.02 | 10 | 0.024242 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1109-05 | 2026-06-24 | 0.02 | 10 | 0.024242 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1109-05 | 2026-06-24 | 0.01 | 10 | 0.012121 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1109-05 | 2026-06-24 | 0.02 | 10 | 0.024242 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1109-05 | 2026-06-24 | 0.01 | 10 | 0.012121 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1109-05 | 2026-06-24 | 0.02 | 10 | 0.024242 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1109-05 | 2026-06-24 | 0.01 | 10 | 0.012121 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1109-05 | 2026-06-24 | 0.02 | 10 | 0.024242 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1109-05 | 2026-06-24 | 0.01 | 10 | 0.012121 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1109-05 | 2026-06-24 | 0.02 | 10 | 0.024242 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1109-05 | 2026-06-24 | 0.02 | 10 | 0.024242 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1109-05 | 2026-06-24 | 0.02 | 10 | 0.024242 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1109-05 | 2026-06-24 | 0.03 | 10 | 0.036364 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1109-05 | 2026-06-24 | 0.02 | 10 | 0.024242 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1109-05 | 2026-06-24 | 0.02 | 10 | 0.024242 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1109-05 | 2026-06-24 | 0.01 | 10 | 0.012121 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1109-05 | 2026-06-25 | 0.02 | 10 | 0.024242 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1109-05 | 2026-06-25 | 0.02 | 10 | 0.024242 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1109-05 | 2026-06-25 | 0.03 | 10 | 0.036364 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1109-05 | 2026-06-25 | 0.04 | 10 | 0.048485 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1109-05 | 2026-06-25 | 0.01 | 10 | 0.012121 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1109-05 | 2026-06-25 | 0.01 | 10 | 0.012121 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1109-05 | 2026-06-25 | 0.03 | 10 | 0.036364 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1109-05 | 2026-06-25 | 0.02 | 10 | 0.024242 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1109-05 | 2026-06-25 | 0.01 | 10 | 0.012121 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1109-05 | 2026-06-25 | 0.01 | 10 | 0.012121 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1109-05 | 2026-06-25 | 0.01 | 10 | 0.012121 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1109-05 | 2026-06-25 | 0.03 | 10 | 0.036364 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1109-05 | 2026-06-25 | 0.02 | 10 | 0.024242 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1109-05 | 2026-06-25 | 0.02 | 10 | 0.024242 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1109-05 | 2026-06-25 | 0.02 | 10 | 0.024242 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1109-05 | 2026-06-25 | 0.03 | 10 | 0.036364 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1109-05 | 2026-06-25 | 0.02 | 10 | 0.024242 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1118-09 | 2026-06-13 | 0.02 | 10 | 0.024242 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1203-01 | 2026-06-16 | 0.05 | 10 | 0.060606 | Trujillo Alto | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1203-01 | 2026-06-16 | 0.04 | 10 | 0.048485 | Trujillo Alto | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1204-02 | 2026-06-02 | 0.02 | 10 | 0.024242 | Trujillo Alto | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1204-02 | 2026-06-01 | 0.03 | 10 | 0.036364 | Trujillo Alto | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1204-02 | 2026-06-02 | 0.03 | 10 | 0.036364 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1204-02 | 2026-06-03 | 0.03 | 10 | 0.036364 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1204-02 | 2026-06-16 | 0.02 | 10 | 0.024242 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1204-02 | 2026-06-16 | 0.02 | 10 | 0.024242 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1204-02 | 2026-06-16 | 0.02 | 10 | 0.024242 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1204-02 | 2026-06-16 | 0.02 | 10 | 0.024242 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1204-02 | 2026-06-20 | 0.03 | 10 | 0.036364 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1204-04 | 2026-06-04 | 0.02 | 10 | 0.024242 | Trujillo Alto | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1204-04 | 2026-06-04 | 0.02 | 10 | 0.024242 | Trujillo Alto | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1204-04 | 2026-06-04 | 0.03 | 10 | 0.036364 | Trujillo Alto | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1205-03 | 2026-06-24 | 0.03 | 10 | 0.036364 | Trujillo Alto | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1206-03 | 2026-06-19 | 0.03 | 10 | 0.036364 | Trujillo Alto | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1206-03 | 2026-06-17 | 0.03 | 10 | 0.036364 | Trujillo Alto | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1206-03 | 2026-06-17 | 0.01 | 10 | 0.012121 | Trujillo Alto | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1206-03 | 2026-06-17 | 0.03 | 10 | 0.036364 | Trujillo Alto | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1206-03 | 2026-06-19 | 0.02 | 10 | 0.024242 | Trujillo Alto | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1206-03 | 2026-06-22 | 0.01 | 10 | 0.012121 | Trujillo Alto | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1206-03 | 2026-06-19 | 0.02 | 10 | 0.024242 | Trujillo Alto | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1206-03 | 2026-06-20 | 0.02 | 10 | 0.024242 | Trujillo Alto | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1206-03 | 2026-06-20 | 0.02 | 10 | 0.024242 | Trujillo Alto | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1206-03 | 2026-06-20 | 0.01 | 10 | 0.012121 | Trujillo Alto | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1206-03 | 2026-06-27 | 0.01 | 10 | 0.012121 | Trujillo Alto | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1206-03 | 2026-06-25 | 0.05 | 10 | 0.060606 | Trujillo Alto | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1206-03 | 2026-06-25 | 0.04 | 10 | 0.048485 | Trujillo Alto | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1206-03 | 2026-06-25 | 0.04 | 10 | 0.048485 | Trujillo Alto | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1206-03 | 2026-06-25 | 0.03 | 10 | 0.036364 | Trujillo Alto | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1206-03 | 2026-06-25 | 0.05 | 10 | 0.060606 | Trujillo Alto | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1206-03 | 2026-06-24 | 0.05 | 10 | 0.060606 | Trujillo Alto | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1206-03 | 2026-06-23 | 0.03 | 10 | 0.036364 | Trujillo Alto | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1303-02 | 2026-06-12 | 0.03 | 10 | 0.036364 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1303-02 | 2026-06-12 | 0.03 | 10 | 0.036364 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1330-04 | 2026-06-18 | 0.02 | 10 | 0.024242 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1336-08 | 2026-06-17 | 0.02 | 10 | 0.024242 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1342-04 | 2026-06-05 | 0.02 | 10 | 0.024242 | Trujillo Alto | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1343-03 | 2026-06-05 | 0.02 | 10 | 0.024242 | Guaynabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1343-03 | 2026-06-02 | 0.03 | 10 | 0.036364 | Guaynabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1343-03 | 2026-06-02 | 0.03 | 10 | 0.036364 | Guaynabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1343-03 | 2026-06-02 | 0.03 | 10 | 0.036364 | Guaynabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1414-02 | 2026-06-16 | 0.01 | 10 | 0.012121 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1423-03 | 2026-06-09 | 0.02 | 10 | 0.024242 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1525-01 | 2026-06-17 | 0.02 | 10 | 0.024242 | San Juan | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1602-05 | 2026-06-30 | 0.03 | 10 | 0.036364 | Carolina | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1607-03 | 2026-06-09 | 0.03 | 10 | 0.036364 | Carolina | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1646-01 | 2026-06-22 | 0.03 | 10 | 0.036364 | Carolina | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1646-01 | 2026-06-22 | 0.03 | 10 | 0.036364 | Carolina | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1646-01 | 2026-06-22 | 0.03 | 10 | 0.036364 | Carolina | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1646-01 | 2026-06-22 | 0.03 | 10 | 0.036364 | Carolina | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1646-01 | 2026-06-23 | 0.02 | 10 | 0.024242 | Carolina | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1646-01 | 2026-06-26 | 0.03 | 10 | 0.036364 | Carolina | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1646-02 | 2026-06-23 | 0.03 | 10 | 0.036364 | Carolina | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1704-02 | 2026-06-18 | 0.01 | 10 | 0.012121 | Bayamón | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1704-02 | 2026-06-18 | 0.03 | 10 | 0.036364 | Bayamón | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1704-05 | 2026-06-08 | 0.02 | 10 | 0.024242 | Bayamón | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1708-04 | 2026-06-08 | 0.03 | 10 | 0.036364 | Bayamón | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1708-04 | 2026-06-08 | 0.03 | 10 | 0.036364 | Bayamón | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1709-02 | 2026-06-13 | 0.02 | 10 | 0.024242 | Guaynabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1709-02 | 2026-06-10 | 0.02 | 10 | 0.024242 | Guaynabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1709-02 | 2026-06-10 | 0.001 | 10 | 0.0012121 | Guaynabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1709-02 | 2026-06-12 | 0.03 | 10 | 0.036364 | Bayamón | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1709-02 | 2026-06-12 | 0.03 | 10 | 0.036364 | Bayamón | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1709-02 | 2026-06-12 | 0.03 | 10 | 0.036364 | Bayamón | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1710-03 | 2026-06-27 | 0.04 | 10 | 0.048485 | Bayamón | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1710-03 | 2026-06-27 | 0.03 | 10 | 0.036364 | Bayamón | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1710-03 | 2026-06-24 | 0.04 | 10 | 0.048485 | Bayamón | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1710-03 | 2026-06-23 | 0.02 | 10 | 0.024242 | Bayamón | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1710-05 | 2026-06-13 | 0.02 | 10 | 0.024242 | Toa Baja | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1710-05 | 2026-06-13 | 0.04 | 10 | 0.048485 | Toa Alta | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1710-05 | 2026-06-13 | 0.04 | 10 | 0.048485 | Toa Alta | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1710-05 | 2026-06-24 | 0.04 | 10 | 0.048485 | Toa Alta | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1710-05 | 2026-06-27 | 0.03 | 10 | 0.036364 | Toa Alta | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1710-05 | 2026-06-27 | 0.03 | 10 | 0.036364 | Toa Alta | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1710-05 | 2026-06-27 | 0.02 | 10 | 0.024242 | Toa Alta | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1710-05 | 2026-06-27 | 0.03 | 10 | 0.036364 | Toa Alta | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1718-02 | 2026-06-09 | 0.01 | 10 | 0.012121 | Toa Baja | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1719-19 | 2026-06-06 | 0.01 | 10 | 0.012121 | Bayamón | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1719-19 | 2026-06-06 | 0.03 | 10 | 0.036364 | Bayamón | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1719-19 | 2026-06-06 | 0.02 | 10 | 0.024242 | Bayamón | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1720-07 | 2026-06-23 | 0.04 | 10 | 0.048485 | Bayamón | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1720-07 | 2026-06-25 | 0.03 | 10 | 0.036364 | Guaynabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1720-07 | 2026-06-25 | 0.04 | 10 | 0.048485 | Guaynabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1720-07 | 2026-06-25 | 0.04 | 10 | 0.048485 | Guaynabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1720-07 | 2026-06-25 | 0.06 | 10 | 0.072727 | Guaynabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1720-07 | 2026-06-25 | 0.05 | 10 | 0.060606 | Bayamón | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1720-07 | 2026-06-25 | 0.04 | 10 | 0.048485 | Bayamón | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1720-07 | 2026-06-25 | 0.03 | 10 | 0.036364 | Bayamón | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1720-07 | 2026-06-25 | 0.04 | 10 | 0.048485 | Bayamón | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1720-07 | 2026-06-25 | 0.04 | 10 | 0.048485 | Bayamón | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 1901-02 | 2026-06-04 | 0.02 | 10 | 0.024242 | Guaynabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1907-04 | 2026-06-12 | 0.02 | 10 | 0.024242 | Guaynabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1909-09 | 2026-06-09 | 0.03 | 10 | 0.036364 | Guaynabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1909-09 | 2026-06-10 | 0.03 | 10 | 0.036364 | Guaynabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1909-09 | 2026-06-09 | 0.03 | 10 | 0.036364 | Guaynabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1909-09 | 2026-06-09 | 0.04 | 10 | 0.048485 | Guaynabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1909-09 | 2026-06-09 | 0.02 | 10 | 0.024242 | Guaynabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1909-09 | 2026-06-10 | 0.04 | 10 | 0.048485 | Guaynabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1909-09 | 2026-06-12 | 0.04 | 10 | 0.048485 | Guaynabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 1909-09 | 2026-06-12 | 0.02 | 10 | 0.02 | Guaynabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2001-02 | 2026-06-10 | 0.03 | 10 | 0.04 | Fajardo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 2005-10 | 2026-06-10 | 0.03 | 10 | 0.04 | Fajardo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2101-02 | 2026-06-26 | 0.1 | 10 | 0.12 | Naguabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2101-02 | 2026-06-26 | 0.05 | 10 | 0.06 | Naguabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2201-01 | 2026-06-11 | 0.03 | 10 | 0.04 | Luquillo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2301-02 | 2026-06-10 | 0.05 | 10 | 0.06 | Río Grande | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 2302-03 | 2026-06-27 | 0.05 | 10 | 0.06 | Río Grande | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 2302-03 | 2026-06-26 | 0.04 | 10 | 0.05 | Río Grande | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 2302-03 | 2026-06-26 | 0.04 | 10 | 0.05 | Río Grande | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 2302-03 | 2026-06-26 | 0.06 | 10 | 0.07 | Río Grande | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 2302-03 | 2026-06-26 | 0.04 | 10 | 0.05 | Río Grande | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 2302-03 | 2026-06-26 | 0.04 | 10 | 0.05 | Río Grande | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 2302-03 | 2026-06-27 | 0.05 | 10 | 0.06 | Río Grande | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 2302-03 | 2026-06-27 | 0.03 | 10 | 0.04 | Río Grande | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 2302-03 | 2026-06-27 | 0.02 | 10 | 0.03 | Río Grande | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 2302-03 | 2026-06-27 | 0.03 | 10 | 0.04 | Río Grande | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 2302-03 | 2026-06-27 | 0.05 | 10 | 0.06 | Río Grande | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 2302-03 | 2026-06-27 | 0.05 | 10 | 0.06 | Río Grande | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 2302-03 | 2026-06-27 | 0.02 | 10 | 0.02 | Río Grande | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 2302-03 | 2026-06-27 | 0.03 | 10 | 0.04 | Río Grande | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 2302-03 | 2026-06-26 | 0.04 | 10 | 0.05 | Río Grande | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 2302-03 | 2026-06-27 | 0.03 | 10 | 0.04 | Río Grande | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 2302-03 | 2026-06-27 | 0.03 | 10 | 0.03 | Río Grande | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 2302-03 | 2026-06-27 | 0.06 | 10 | 0.07 | Río Grande | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 2302-03 | 2026-06-30 | 0.04 | 10 | 0.05 | Río Grande | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 2302-03 | 2026-06-26 | 0.03 | 10 | 0.04 | Río Grande | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 2302-03 | 2026-06-26 | 0.03 | 10 | 0.04 | Río Grande | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 2302-03 | 2026-06-27 | 0.04 | 10 | 0.05 | Río Grande | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 2302-03 | 2026-06-27 | 0.03 | 10 | 0.04 | Río Grande | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 2302-03 | 2026-06-27 | 0.03 | 10 | 0.04 | Río Grande | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 2302-03 | 2026-06-25 | 0.03 | 10 | 0.04 | Río Grande | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 2302-03 | 2026-06-30 | 0.02 | 10 | 0.03 | Río Grande | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 2302-03 | 2026-06-30 | 0.04 | 10 | 0.05 | Río Grande | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 2305-02 | 2026-06-11 | 0.03 | 10 | 0.04 | Luquillo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2401-03 | 2026-06-15 | 0.02 | 10 | 0.03 | Canóvanas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2401-03 | 2026-06-15 | 0.03 | 10 | 0.04 | Canóvanas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2401-03 | 2026-06-15 | 0.03 | 10 | 0.03 | Canóvanas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2401-03 | 2026-06-03 | 0.02 | 10 | 0.03 | Canóvanas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2401-03 | 2026-06-17 | 0.06 | 10 | 0.07 | Canóvanas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2401-03 | 2026-06-18 | 0.03 | 10 | 0.03 | Canóvanas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 2402-02 | 2026-06-17 | 0.04 | 10 | 0.05 | Canóvanas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 2402-02 | 2026-06-19 | 0.01 | 10 | 0.01 | Canóvanas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 2402-02 | 2026-06-19 | 0.03 | 10 | 0.03 | Canóvanas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 2402-02 | 2026-06-19 | 0.02 | 10 | 0.02 | Canóvanas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 2402-03 | 2026-06-09 | 0.02 | 10 | 0.03 | Canóvanas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 2404-05 | 2026-06-10 | 0.04 | 10 | 0.05 | Canóvanas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 2404-05 | 2026-06-12 | 0.03 | 10 | 0.03 | Canóvanas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 2404-05 | 2026-06-22 | 0.03 | 10 | 0.03 | Canóvanas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 2404-05 | 2026-06-22 | 0.03 | 10 | 0.03 | Canóvanas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 2404-05 | 2026-06-22 | 0.03 | 10 | 0.04 | Canóvanas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 2404-05 | 2026-06-22 | 0.04 | 10 | 0.05 | Canóvanas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 2404-06 | 2026-06-12 | 0.03 | 10 | 0.04 | Carolina | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 2404-08 | 2026-06-12 | 0.06 | 10 | 0.08 | Canóvanas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2601-03 | 2026-06-24 | 0.02 | 10 | 0.03 | Humacao | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 2603-09 | 2026-06-29 | 0.05 | 10 | 0.05 | Humacao | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2701-01 | 2026-06-23 | 0.02 | 10 | 0.03 | Naguabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2701-01 | 2026-06-23 | 0.02 | 10 | 0.03 | Naguabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2701-02 | 2026-06-24 | 0.03 | 10 | 0.04 | Naguabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2701-02 | 2026-06-23 | 0.03 | 10 | 0.04 | Naguabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2702-01 | 2026-06-25 | 0.04 | 10 | 0.05 | Naguabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2702-01 | 2026-06-24 | 0.05 | 10 | 0.06 | Naguabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2702-01 | 2026-06-24 | 0.03 | 10 | 0.04 | Naguabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2702-01 | 2026-06-25 | 0.03 | 10 | 0.04 | Naguabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2801-03 | 2026-06-27 | 0.15 | 10 | 0.18 | Humacao | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2803-02 | 2026-06-01 | 0.04 | 10 | 0.05 | Naguabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2803-02 | 2026-06-05 | 0.04 | 10 | 0.04 | Naguabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2803-02 | 2026-06-01 | 0.04 | 10 | 0.05 | Naguabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2803-02 | 2026-06-04 | 0.03 | 10 | 0.04 | Naguabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2803-02 | 2026-06-04 | 0.05 | 10 | 0.06 | Naguabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2803-02 | 2026-06-05 | 0.02 | 10 | 0.03 | Naguabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2803-02 | 2026-06-08 | 0.03 | 10 | 0.04 | Naguabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2803-02 | 2026-06-05 | 0.04 | 10 | 0.05 | Naguabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2803-02 | 2026-06-06 | 0.02 | 10 | 0.03 | Naguabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2803-02 | 2026-06-05 | 0.03 | 10 | 0.04 | Naguabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2803-02 | 2026-06-08 | 0.04 | 10 | 0.05 | Naguabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2803-02 | 2026-06-06 | 0.04 | 10 | 0.05 | Naguabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2803-02 | 2026-06-05 | 0.02 | 10 | 0.03 | Naguabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2803-02 | 2026-06-05 | 0.04 | 10 | 0.04 | Naguabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-25 | 0.04 | 10 | 0.05 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-13 | 0.03 | 10 | 0.04 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-26 | 0.05 | 10 | 0.06 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-11 | 0.03 | 10 | 0.04 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-15 | 0.05 | 10 | 0.06 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-10 | 0.03 | 10 | 0.03 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-09 | 0.03 | 10 | 0.03 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-11 | 0.03 | 10 | 0.04 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-16 | 0.04 | 10 | 0.05 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-17 | 0.02 | 10 | 0.03 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-18 | 0.04 | 10 | 0.05 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-12 | 0.03 | 10 | 0.04 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-13 | 0.02 | 10 | 0.03 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-26 | 0.04 | 10 | 0.05 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-26 | 0.03 | 10 | 0.03 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-11 | 0.04 | 10 | 0.04 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-11 | 0.11 | 10 | 0.14 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-26 | 0.05 | 10 | 0.06 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-12 | 0.03 | 10 | 0.04 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-12 | 0.02 | 10 | 0.02 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-26 | 0.05 | 10 | 0.06 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-27 | 0.05 | 10 | 0.06 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-12 | 0.03 | 10 | 0.04 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-12 | 0.03 | 10 | 0.03 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-16 | 0.03 | 10 | 0.03 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-10 | 0.02 | 10 | 0.03 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-13 | 0.03 | 10 | 0.03 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-15 | 0.04 | 10 | 0.04 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-15 | 0.03 | 10 | 0.03 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-15 | 0.02 | 10 | 0.03 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-17 | 0.03 | 10 | 0.03 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-17 | 0.03 | 10 | 0.04 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-18 | 0.02 | 10 | 0.03 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-18 | 0.1 | 10 | 0.12 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-18 | 0.1 | 10 | 0.12 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-18 | 0.04 | 10 | 0.05 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-19 | 0.02 | 10 | 0.03 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-19 | 0.02 | 10 | 0.03 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-19 | 0.03 | 10 | 0.03 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-20 | 0.04 | 10 | 0.04 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-20 | 0.03 | 10 | 0.04 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-22 | 0.03 | 10 | 0.03 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-22 | 0.03 | 10 | 0.04 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-22 | 0.02 | 10 | 0.03 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-23 | 0.02 | 10 | 0.03 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-23 | 0.01 | 10 | 0.01 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-23 | 0.04 | 10 | 0.05 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-23 | 0.03 | 10 | 0.04 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-23 | 0.04 | 10 | 0.05 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-25 | 0.05 | 10 | 0.05 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-25 | 0.04 | 10 | 0.05 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-23 | 0.07 | 10 | 0.08 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-23 | 0.02 | 10 | 0.03 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-23 | 0.03 | 10 | 0.04 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-23 | 0.02 | 10 | 0.03 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-23 | 0.05 | 10 | 0.06 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-24 | 0.03 | 10 | 0.03 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-24 | 0.04 | 10 | 0.05 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-30 | 0.04 | 10 | 0.04 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-25 | 0.03 | 10 | 0.03 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-25 | 0.03 | 10 | 0.04 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-24 | 0.03 | 10 | 0.04 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-24 | 0.03 | 10 | 0.03 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-26 | 0.07 | 10 | 0.08 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-27 | 0.04 | 10 | 0.05 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-01 | 2026-06-27 | 0.03 | 10 | 0.03 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-04 | 2026-06-08 | 0.04 | 10 | 0.04 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-04 | 2026-06-08 | 0.03 | 10 | 0.04 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-04 | 2026-06-01 | 0.03 | 10 | 0.03 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-04 | 2026-06-01 | 0.02 | 10 | 0.03 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-04 | 2026-06-02 | 0.03 | 10 | 0.04 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-04 | 2026-06-02 | 0.03 | 10 | 0.04 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-04 | 2026-06-02 | 0.03 | 10 | 0.04 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-04 | 2026-06-02 | 0.03 | 10 | 0.04 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-04 | 2026-06-15 | 0.04 | 10 | 0.05 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-04 | 2026-06-01 | 0.03 | 10 | 0.04 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-04 | 2026-06-02 | 0.03 | 10 | 0.04 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-04 | 2026-06-02 | 0.04 | 10 | 0.04 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-04 | 2026-06-02 | 0.03 | 10 | 0.03 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-04 | 2026-06-15 | 0.03 | 10 | 0.04 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-04 | 2026-06-02 | 0.03 | 10 | 0.04 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-04 | 2026-06-03 | 0.03 | 10 | 0.04 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-04 | 2026-06-03 | 0.03 | 10 | 0.04 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-04 | 2026-06-03 | 0.03 | 10 | 0.04 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-04 | 2026-06-15 | 0.03 | 10 | 0.03 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-04 | 2026-06-06 | 0.03 | 10 | 0.03 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-04 | 2026-06-03 | 0.03 | 10 | 0.04 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-04 | 2026-06-03 | 0.04 | 10 | 0.04 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-04 | 2026-06-15 | 0.04 | 10 | 0.05 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-04 | 2026-06-03 | 0.06 | 10 | 0.08 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-04 | 2026-06-06 | 0.08 | 10 | 0.1 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-04 | 2026-06-06 | 0.03 | 10 | 0.04 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-04 | 2026-06-15 | 0.03 | 10 | 0.04 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-04 | 2026-06-04 | 0.03 | 10 | 0.03 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-04 | 2026-06-06 | 0.03 | 10 | 0.04 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-04 | 2026-06-06 | 0.03 | 10 | 0.04 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-04 | 2026-06-15 | 0.04 | 10 | 0.04 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-04 | 2026-06-15 | 0.01 | 10 | 0.02 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-04 | 2026-06-02 | 0.03 | 10 | 0.04 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-04 | 2026-06-05 | 0.03 | 10 | 0.03 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-04 | 2026-06-10 | 0.07 | 10 | 0.09 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-04 | 2026-06-09 | 0.03 | 10 | 0.04 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-04 | 2026-06-12 | 0.03 | 10 | 0.03 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-04 | 2026-06-12 | 0.03 | 10 | 0.04 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-04 | 2026-06-18 | 0.02 | 10 | 0.02 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-04 | 2026-06-18 | 0.03 | 10 | 0.04 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-04 | 2026-06-18 | 0.04 | 10 | 0.05 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-04 | 2026-06-20 | 0.04 | 10 | 0.05 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-04 | 2026-06-03 | 0.04 | 10 | 0.05 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-04 | 2026-06-10 | 0.02 | 10 | 0.03 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-04 | 2026-06-23 | 0.11 | 10 | 0.13 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-04 | 2026-06-04 | 0.02 | 10 | 0.03 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-04 | 2026-06-20 | 0.1 | 10 | 0.12 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-04 | 2026-06-15 | 0.01 | 10 | 0.02 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-04 | 2026-06-15 | 0.05 | 10 | 0.06 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-04 | 2026-06-10 | 0.03 | 10 | 0.04 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-04 | 2026-06-20 | 0.04 | 10 | 0.05 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 2901-04 | 2026-06-15 | 0.05 | 10 | 0.06 | Yabucoa | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-06-05 | 0.11 | 10 | 0.13 | Caguas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-06-01 | 0.01 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-06-04 | 0.01 | 10 | 0.02 | Caguas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-06-04 | 0.02 | 10 | 0.02 | Caguas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-06-01 | 0.02 | 10 | 0.02 | Caguas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-06-01 | 0.06 | 10 | 0.07 | Caguas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-06-02 | 0.1 | 10 | 0.12 | Caguas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-06-02 | 0.1 | 10 | 0.12 | Caguas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-06-02 | 0.03 | 10 | 0.04 | Caguas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-06-04 | 0.01 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-06-09 | 0.07 | 10 | 0.09 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-06-06 | 0.07 | 10 | 0.09 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-06-09 | 0.03 | 10 | 0.03 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-06-05 | 0.07 | 10 | 0.09 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3004-01 | 2026-06-05 | 0.1 | 10 | 0.12 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3007-03 | 2026-06-10 | 0.02 | 10 | 0.03 | Caguas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3007-03 | 2026-06-10 | 0.03 | 10 | 0.03 | Caguas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3007-03 | 2026-06-15 | 0.02 | 10 | 0.03 | Caguas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3007-03 | 2026-06-15 | 0.03 | 10 | 0.04 | Caguas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3007-03 | 2026-06-11 | 0.04 | 10 | 0.05 | Caguas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3007-03 | 2026-06-11 | 0.03 | 10 | 0.04 | Caguas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3007-03 | 2026-06-10 | 0.03 | 10 | 0.04 | Caguas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3007-03 | 2026-06-10 | 0.01 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3007-03 | 2026-06-17 | 0.02 | 10 | 0.02 | Caguas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3007-03 | 2026-06-12 | 0.03 | 10 | 0.04 | Caguas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3007-03 | 2026-06-12 | 0.03 | 10 | 0.04 | Caguas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3007-03 | 2026-06-12 | 0.07 | 10 | 0.09 | Caguas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3007-03 | 2026-06-12 | 0.01 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3007-03 | 2026-06-03 | 0.02 | 10 | 0.02 | Caguas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3007-03 | 2026-06-15 | 0.03 | 10 | 0.04 | Caguas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3007-03 | 2026-06-13 | 0.03 | 10 | 0.04 | Caguas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3007-03 | 2026-06-13 | 0.05 | 10 | 0.06 | Caguas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3007-03 | 2026-06-17 | 0.04 | 10 | 0.05 | Caguas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3007-03 | 2026-06-13 | 0.03 | 10 | 0.04 | Caguas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3007-03 | 2026-06-12 | 0.03 | 10 | 0.04 | Caguas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3007-03 | 2026-06-12 | 0.07 | 10 | 0.09 | Caguas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3009-02 | 2026-06-08 | 0.01 | 10 | 0.02 | Caguas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3010-04 | 2026-06-16 | 0.1 | 10 | 0.12 | Caguas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3010-04 | 2026-06-16 | 0.1 | 10 | 0.12 | Caguas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 3016-03 | 2026-06-30 | 0.03 | 10 | 0.03 | Caguas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 3016-03 | 2026-06-30 | 0.03 | 10 | 0.04 | Caguas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 3016-03 | 2026-06-30 | 0.02 | 10 | 0.03 | Caguas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 3101-02 | 2026-06-22 | 0.05 | 10 | 0.06 | Gurabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 3101-02 | 2026-06-22 | 0.04 | 10 | 0.05 | Gurabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 3101-02 | 2026-06-22 | 0.03 | 10 | 0.03 | Gurabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 3101-02 | 2026-06-23 | 0.05 | 10 | 0.06 | Gurabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 3101-02 | 2026-06-24 | 0.05 | 10 | 0.06 | Gurabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 3101-02 | 2026-06-23 | 0.04 | 10 | 0.05 | Gurabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 3101-02 | 2026-06-23 | 0.03 | 10 | 0.03 | Gurabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 3101-02 | 2026-06-25 | 0.03 | 10 | 0.03 | Gurabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 3101-02 | 2026-06-25 | 0.03 | 10 | 0.03 | Gurabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 3101-02 | 2026-06-25 | 0.03 | 10 | 0.04 | Gurabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 3101-02 | 2026-06-26 | 0.04 | 10 | 0.04 | Gurabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 3101-02 | 2026-06-26 | 0.03 | 10 | 0.04 | Gurabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 3101-02 | 2026-06-26 | 0.04 | 10 | 0.04 | Gurabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 3101-02 | 2026-06-26 | 0.03 | 10 | 0.04 | Gurabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 3101-02 | 2026-06-29 | 0.03 | 10 | 0.04 | Gurabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 3101-02 | 2026-06-26 | 0.04 | 10 | 0.04 | Gurabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 3101-02 | 2026-06-30 | 0.04 | 10 | 0.05 | Gurabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 3103-03 | 2026-06-02 | 0.03 | 10 | 0.04 | Gurabo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 3201-03 | 2026-06-17 | 0.005 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 3201-04 | 2026-06-18 | 0.04 | 10 | 0.05 | Juncos | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 3201-04 | 2026-06-18 | 0.05 | 10 | 0.06 | Juncos | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 3201-04 | 2026-06-18 | 0.04 | 10 | 0.05 | Juncos | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 3201-04 | 2026-06-18 | 0.02 | 10 | 0.03 | Juncos | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 3201-04 | 2026-06-18 | 0.02 | 10 | 0.03 | Juncos | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 3202-01 | 2026-06-18 | 0.04 | 10 | 0.05 | Juncos | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 3202-01 | 2026-06-18 | 0.03 | 10 | 0.04 | Juncos | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 3205-07 | 2026-06-11 | 0.02 | 10 | 0.03 | Juncos | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 3205-07 | 2026-06-13 | 0.02 | 10 | 0.03 | Juncos | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 3205-08 | 2026-06-27 | 0.04 | 10 | 0.05 | Juncos | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 3205-08 | 2026-06-30 | 0.03 | 10 | 0.04 | Juncos | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 3205-08 | 2026-06-26 | 0.03 | 10 | 0.03 | Juncos | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 3205-08 | 2026-06-23 | 0.03 | 10 | 0.04 | Juncos | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 3205-08 | 2026-06-25 | 0.03 | 10 | 0.03 | Juncos | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 3205-08 | 2026-06-25 | 0.03 | 10 | 0.03 | Juncos | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 3205-08 | 2026-06-25 | 0.03 | 10 | 0.03 | Juncos | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 3205-08 | 2026-06-27 | 0.04 | 10 | 0.05 | Juncos | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 3205-08 | 2026-06-19 | 0.03 | 10 | 0.03 | Juncos | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 3205-08 | 2026-06-23 | 0.02 | 10 | 0.03 | Juncos | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 3205-08 | 2026-06-18 | 0.02 | 10 | 0.02 | Juncos | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 3205-08 | 2026-06-27 | 0.03 | 10 | 0.04 | Juncos | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 3205-08 | 2026-06-27 | 0.02 | 10 | 0.02 | Juncos | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 3205-08 | 2026-06-26 | 0.03 | 10 | 0.04 | Juncos | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 3205-08 | 2026-06-20 | 0.04 | 10 | 0.05 | Juncos | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 3205-08 | 2026-06-20 | 0.04 | 10 | 0.05 | Juncos | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 3205-08 | 2026-06-20 | 0.02 | 10 | 0.02 | Juncos | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 3205-08 | 2026-06-17 | 0.04 | 10 | 0.05 | Juncos | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 3205-08 | 2026-06-17 | 0.04 | 10 | 0.04 | Juncos | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 3205-08 | 2026-06-19 | 0.03 | 10 | 0.04 | Juncos | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 3205-08 | 2026-06-19 | 0.03 | 10 | 0.04 | Juncos | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 3205-08 | 2026-06-19 | 0.03 | 10 | 0.04 | Juncos | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 3205-08 | 2026-06-19 | 0.03 | 10 | 0.04 | Juncos | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 3205-08 | 2026-06-22 | 0.03 | 10 | 0.04 | Juncos | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 3205-08 | 2026-06-22 | 0.03 | 10 | 0.03 | Juncos | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 3205-08 | 2026-06-27 | 0.02 | 10 | 0.02 | Juncos | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3401-03 | 2026-06-20 | 0.02 | 10 | 0.03 | Cayey | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3402-05 | 2026-06-20 | 0.04 | 10 | 0.04 | Cayey | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3402-05 | 2026-06-30 | 0.04 | 10 | 0.04 | Cayey | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3402-05 | 2026-06-30 | 0.03 | 10 | 0.04 | Cayey | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3402-05 | 2026-06-23 | 0.03 | 10 | 0.04 | Cayey | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3402-05 | 2026-06-30 | 0.02 | 10 | 0.03 | Cayey | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3402-05 | 2026-06-30 | 0.02 | 10 | 0.03 | Cayey | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3501-01 | 2026-06-26 | 0.09 | 10 | 0.11 | Aibonito | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3501-03 | 2026-06-29 | 0.02 | 10 | 0.02 | Aibonito | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3602-01 | 2026-06-26 | 0.02 | 10 | 0.03 | Cayey | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3602-01 | 2026-06-27 | 0.01 | 10 | 0.02 | Cayey | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3604-06 | 2026-06-30 | 0.03 | 10 | 0.04 | Caguas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3604-06 | 2026-06-30 | 0.03 | 10 | 0.04 | Caguas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3604-06 | 2026-06-30 | 0.04 | 10 | 0.04 | Caguas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3604-06 | 2026-06-30 | 0.03 | 10 | 0.04 | Caguas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-02 | 0.02 | 10 | 0.03 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-17 | 0.03 | 10 | 0.03 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-17 | 0.03 | 10 | 0.04 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-17 | 0.03 | 10 | 0.03 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-17 | 0.03 | 10 | 0.04 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-17 | 0.03 | 10 | 0.03 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-17 | 0.04 | 10 | 0.05 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-17 | 0.03 | 10 | 0.04 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-17 | 0.04 | 10 | 0.04 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-17 | 0.05 | 10 | 0.06 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-17 | 0.04 | 10 | 0.05 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-17 | 0.04 | 10 | 0.05 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-17 | 0.02 | 10 | 0.03 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-17 | 0.05 | 10 | 0.05 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-17 | 0.03 | 10 | 0.03 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-17 | 0.04 | 10 | 0.05 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-17 | 0.04 | 10 | 0.05 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-17 | 0.02 | 10 | 0.03 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-22 | 0.03 | 10 | 0.03 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-27 | 0.04 | 10 | 0.05 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-18 | 0.04 | 10 | 0.04 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-22 | 0.03 | 10 | 0.03 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-22 | 0.05 | 10 | 0.06 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-22 | 0.03 | 10 | 0.04 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-23 | 0.03 | 10 | 0.04 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-30 | 0.04 | 10 | 0.04 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-22 | 0.04 | 10 | 0.04 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-22 | 0.02 | 10 | 0.03 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-22 | 0.04 | 10 | 0.05 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-22 | 0.03 | 10 | 0.04 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-22 | 0.03 | 10 | 0.04 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-22 | 0.04 | 10 | 0.05 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-22 | 0.04 | 10 | 0.04 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-22 | 0.06 | 10 | 0.07 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-22 | 0.07 | 10 | 0.08 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-22 | 0.07 | 10 | 0.08 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-25 | 0.03 | 10 | 0.04 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-22 | 0.04 | 10 | 0.04 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-22 | 0.04 | 10 | 0.04 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-25 | 0.02 | 10 | 0.03 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-25 | 0.03 | 10 | 0.03 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-25 | 0.03 | 10 | 0.03 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-02 | 0.03 | 10 | 0.03 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-25 | 0.02 | 10 | 0.03 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-18 | 0.03 | 10 | 0.04 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-16 | 0.08 | 10 | 0.1 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-17 | 0.03 | 10 | 0.04 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-22 | 0.08 | 10 | 0.1 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-22 | 0.09 | 10 | 0.1 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-22 | 0.05 | 10 | 0.07 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-26 | 0.04 | 10 | 0.05 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-26 | 0.14 | 10 | 0.17 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-27 | 0.13 | 10 | 0.16 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-22 | 0.04 | 10 | 0.05 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-22 | 0.04 | 10 | 0.05 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-17 | 0.02 | 10 | 0.02 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-25 | 0.04 | 10 | 0.05 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-16 | 0.04 | 10 | 0.05 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-16 | 0.05 | 10 | 0.06 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-17 | 0.05 | 10 | 0.06 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-17 | 0.14 | 10 | 0.17 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-17 | 0.1 | 10 | 0.12 | Caguas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-22 | 0.04 | 10 | 0.05 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-21 | 0.15 | 10 | 0.19 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-18 | 0.01 | 10 | 0.01 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-19 | 0.04 | 10 | 0.05 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-22 | 0.05 | 10 | 0.05 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-22 | 0.04 | 10 | 0.05 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-23 | 0.07 | 10 | 0.08 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-23 | 0.02 | 10 | 0.02 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-23 | 0.16 | 10 | 0.19 | Caguas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-23 | 0.13 | 10 | 0.16 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02 | 2026-06-19 | 0.04 | 10 | 0.04 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 3701-02o | 2026-06-17 | 0.04 | 10 | 0.05 | Aguas Buenas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 4001-03 | 2026-06-02 | 0.05 | 10 | 0.06 | Guayama | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 4001-03 | 2026-06-11 | 0.03 | 10 | 0.04 | Guayama | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 4001-03 | 2026-06-11 | 0.03 | 10 | 0.04 | Guayama | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 4001-03 | 2026-06-11 | 0.05 | 10 | 0.06 | Guayama | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 4001-03 | 2026-06-11 | 0.03 | 10 | 0.04 | Guayama | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 4001-03 | 2026-06-11 | 0.03 | 10 | 0.04 | Guayama | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 4001-03 | 2026-06-11 | 0.03 | 10 | 0.03 | Guayama | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 4001-03 | 2026-06-11 | 0.03 | 10 | 0.04 | Guayama | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 4003-01 | 2026-06-22 | 0.07 | 10 | 0.09 | Guayama | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 4003-01 | 2026-06-24 | 0.03 | 10 | 0.04 | Guayama | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 4003-01 | 2026-06-18 | 0.03 | 10 | 0.04 | Guayama | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 4003-01 | 2026-06-20 | 0.04 | 10 | 0.04 | Guayama | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 4003-01 | 2026-06-15 | 0.05 | 10 | 0.06 | Guayama | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 4003-01 | 2026-06-15 | 0.04 | 10 | 0.05 | Guayama | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 4003-01 | 2026-06-01 | 0.05 | 10 | 0.06 | Guayama | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 4003-01 | 2026-06-01 | 0.04 | 10 | 0.05 | Guayama | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 4003-01 | 2026-06-13 | 0.03 | 10 | 0.04 | Guayama | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 4003-01 | 2026-06-08 | 0.02 | 10 | 0.03 | Guayama | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 4003-01 | 2026-06-08 | 0.03 | 10 | 0.03 | Guayama | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 4003-01 | 2026-06-08 | 0.04 | 10 | 0.05 | Guayama | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 4003-01 | 2026-06-25 | 0.03 | 10 | 0.04 | Guayama | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 4003-01 | 2026-06-25 | 0.04 | 10 | 0.05 | Guayama | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 4003-01 | 2026-06-26 | 0.05 | 10 | 0.06 | Guayama | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 4003-01 | 2026-06-26 | 0.07 | 10 | 0.09 | Guayama | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 4003-01 | 2026-06-27 | 0.07 | 10 | 0.09 | Guayama | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 4003-01 | 2026-06-29 | 0.07 | 10 | 0.08 | Guayama | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 4003-01 | 2026-06-24 | 0.03 | 10 | 0.04 | Guayama | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 4003-01 | 2026-06-24 | 0.04 | 10 | 0.05 | Guayama | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 4003-01 | 2026-06-24 | 0.03 | 10 | 0.04 | Guayama | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 4003-01 | 2026-06-22 | 0.07 | 10 | 0.09 | Guayama | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 4003-01 | 2026-06-22 | 0.07 | 10 | 0.09 | Guayama | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 4003-02 | 2026-06-06 | 0.02 | 10 | 0.03 | Guayama | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 4003-02 | 2026-06-05 | 0.05 | 10 | 0.06 | Guayama | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 4003-02 | 2026-06-05 | 0.05 | 10 | 0.06 | Guayama | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 4003-02 | 2026-06-05 | 0.05 | 10 | 0.06 | Guayama | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 4003-02 | 2026-06-05 | 0.05 | 10 | 0.06 | Guayama | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 4003-02 | 2026-06-05 | 0.05 | 10 | 0.05 | Guayama | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 4101-04 | 2026-06-13 | 0.05 | 10 | 0.07 | Arroyo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 4201-01 | 2026-06-10 | 0.03 | 10 | 0.03 | Patillas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 4201-01 | 2026-06-10 | 0.04 | 10 | 0.04 | Patillas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 4201-01 | 2026-06-10 | 0.03 | 10 | 0.04 | Patillas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 4201-01 | 2026-06-12 | 0.01 | 10 | 0.01 | Patillas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 4201-01 | 2026-06-12 | 0.05 | 10 | 0.06 | Patillas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 4201-01 | 2026-06-12 | 0.02 | 10 | 0.03 | Patillas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-06-01 | 0.03 | 10 | 0.03 | Patillas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-06-01 | 0.02 | 10 | 0.02 | Guayama | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-06-01 | 0.04 | 10 | 0.05 | Guayama | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-06-01 | 0.03 | 10 | 0.04 | Guayama | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-06-01 | 0.03 | 10 | 0.04 | Guayama | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 4201-03 | 2026-06-01 | 0.03 | 10 | 0.04 | Patillas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 4201-04 | 2026-06-02 | 0.06 | 10 | 0.08 | Patillas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 4201-04 | 2026-06-02 | 0.03 | 10 | 0.04 | Patillas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 4201-04 | 2026-06-04 | 0.09 | 10 | 0.11 | Patillas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 4201-04 | 2026-06-23 | 0.03 | 10 | 0.04 | Patillas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 4201-04 | 2026-06-23 | 0.1 | 10 | 0.12 | Patillas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 4201-04 | 2026-06-23 | 0.05 | 10 | 0.06 | Patillas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 4301-02 | 2026-06-17 | 0.02 | 10 | 0.03 | Maunabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 4301-02 | 2026-06-17 | 0.02 | 10 | 0.03 | Maunabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 4301-02 | 2026-06-17 | 0.03 | 10 | 0.04 | Maunabo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 4401-03 | 2026-06-02 | 0.01 | 10 | 0.02 | Santa Isabel | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 4402-02 | 2026-06-19 | 0.03 | 10 | 0.04 | Coamo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 4402-02 | 2026-06-19 | 0.04 | 10 | 0.05 | Coamo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 4402-02 | 2026-06-19 | 0.05 | 10 | 0.06 | Coamo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 4402-02 | 2026-06-19 | 0.02 | 10 | 0.02 | Coamo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 4402-02 | 2026-06-19 | 0.01 | 10 | 0.01 | Coamo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 4501-05 | 2026-06-03 | 0.04 | 10 | 0.05 | Salinas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 4501-05 | 2026-06-03 | 0.04 | 10 | 0.05 | Salinas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 4602-01 | 2026-06-16 | 0.05 | 10 | 0.06 | Coamo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 4603-01 | 2026-06-09 | 0.03 | 10 | 0.04 | Coamo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 4603-01 | 2026-06-09 | 0.06 | 10 | 0.07 | Coamo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 4603-01 | 2026-06-09 | 0.11 | 10 | 0.14 | Coamo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 4603-01 | 2026-06-09 | 0.07 | 10 | 0.08 | Coamo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 4603-01 | 2026-06-09 | 0.08 | 10 | 0.1 | Coamo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5001-02 | 2026-06-02 | 0.03 | 10 | 0.03 | Ponce | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5001-02 | 2026-06-02 | 0.03 | 10 | 0.03 | Ponce | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5001-02 | 2026-06-04 | 0.03 | 10 | 0.03 | Ponce | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5001-02 | 2026-06-09 | 0.03 | 10 | 0.04 | Ponce | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5001-02 | 2026-06-11 | 0.02 | 10 | 0.03 | Ponce | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5001-02 | 2026-06-08 | 0.03 | 10 | 0.03 | Ponce | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5001-05 | 2026-06-01 | 0.02 | 10 | 0.02 | Ponce | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5001-05 | 2026-06-01 | 0.01 | 10 | 0.02 | Ponce | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5003-02 | 2026-06-09 | 0.03 | 10 | 0.04 | Ponce | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5005-02 | 2026-06-04 | 0.03 | 10 | 0.04 | Ponce | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5005-02 | 2026-06-03 | 0.03 | 10 | 0.04 | Ponce | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5005-02 | 2026-06-04 | 0.02 | 10 | 0.03 | Ponce | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5007-02 | 2026-06-19 | 0.02 | 10 | 0.02 | Ponce | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5007-02 | 2026-06-19 | 0.02 | 10 | 0.02 | Ponce | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5012-03 | 2026-06-06 | 0.02 | 10 | 0.03 | Ponce | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5012-03 | 2026-06-05 | 0.11 | 10 | 0.13 | Ponce | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5012-03 | 2026-06-08 | 0.11 | 10 | 0.13 | Ponce | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5012-03 | 2026-06-05 | 0.05 | 10 | 0.06 | Ponce | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5012-03 | 2026-06-06 | 0.04 | 10 | 0.05 | Ponce | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5013-02 | 2026-06-20 | 0.09 | 10 | 0.1 | Ponce | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5019-02 | 2026-06-04 | 0.04 | 10 | 0.05 | Ponce | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5302-01 | 2026-06-12 | 0.03 | 10 | 0.04 | Yauco | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5302-01 | 2026-06-12 | 0.04 | 10 | 0.05 | Yauco | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5302-01 | 2026-06-12 | 0.04 | 10 | 0.05 | Yauco | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5302-01 | 2026-06-12 | 0.05 | 10 | 0.06 | Yauco | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5302-01 | 2026-06-12 | 0.05 | 10 | 0.06 | Yauco | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5302-01 | 2026-06-13 | 0.05 | 10 | 0.06 | Yauco | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5302-01 | 2026-06-12 | 0.05 | 10 | 0.06 | Yauco | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5302-04 | 2026-06-09 | 0.04 | 10 | 0.05 | Yauco | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5302-04 | 2026-06-11 | 0.03 | 10 | 0.04 | Yauco | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5302-04 | 2026-06-16 | 0.03 | 10 | 0.04 | Yauco | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5303-01 | 2026-06-16 | 0.02 | 10 | 0.03 | Yauco | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5303-01 | 2026-06-18 | 0.02 | 10 | 0.02 | Yauco | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5303-01 | 2026-06-19 | 0.02 | 10 | 0.02 | Yauco | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5303-01 | 2026-06-15 | 0.1 | 10 | 0.12 | Yauco | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5303-01 | 2026-06-19 | 0.02 | 10 | 0.02 | Yauco | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5401-01 | 2026-06-03 | 0.02 | 10 | 0.03 | Peñuelas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5402-02 | 2026-06-22 | 0.05 | 10 | 0.06 | Peñuelas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5402-02 | 2026-06-22 | 0.05 | 10 | 0.06 | Peñuelas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5402-02 | 2026-06-22 | 0.05 | 10 | 0.06 | Peñuelas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5501-02 | 2026-06-17 | 0.06 | 10 | 0.07 | Guayanilla | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5501-02 | 2026-06-17 | 0.06 | 10 | 0.07 | Guayanilla | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5501-02 | 2026-06-17 | 0.04 | 10 | 0.05 | Guayanilla | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5501-02 | 2026-06-17 | 0.03 | 10 | 0.04 | Guayanilla | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5501-02 | 2026-06-25 | 0.04 | 10 | 0.05 | Guayanilla | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5501-02 | 2026-06-25 | 0.08 | 10 | 0.1 | Guayanilla | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5501-02 | 2026-06-25 | 0.06 | 10 | 0.07 | Guayanilla | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5501-02 | 2026-06-26 | 0.09 | 10 | 0.1 | Guayanilla | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5501-02 | 2026-06-25 | 0.07 | 10 | 0.08 | Ponce | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5501-02 | 2026-06-26 | 0.1 | 10 | 0.12 | Guayanilla | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5501-02 | 2026-06-25 | 0.2 | 10 | 0.24 | Guayanilla | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5501-02 | 2026-06-25 | 0.2 | 10 | 0.24 | Ponce | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5501-02 | 2026-06-26 | 0.12 | 10 | 0.15 | Guayanilla | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5501-02 | 2026-06-26 | 0.08 | 10 | 0.1 | Guayanilla | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5501-02 | 2026-06-26 | 0.1 | 10 | 0.12 | Guayama | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5602-02 | 2026-06-04 | 0.04 | 10 | 0.05 | Guánica | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5802-01 | 2026-06-29 | 0.02 | 10 | 0.02 | Juana Díaz | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5802-01 | 2026-06-29 | 0.03 | 10 | 0.04 | Juana Díaz | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5802-01 | 2026-06-29 | 0.02 | 10 | 0.02 | Juana Díaz | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 5803-01 | 2026-06-12 | 0.03 | 10 | 0.04 | Juana Díaz | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5817-01 | 2026-06-10 | 0.05 | 10 | 0.06 | Ponce | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5817-01 | 2026-06-10 | 0.06 | 10 | 0.07 | Ponce | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5817-01 | 2026-06-10 | 0.05 | 10 | 0.05 | Ponce | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5817-01 | 2026-06-17 | 0.03 | 10 | 0.03 | Ponce | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5817-01 | 2026-06-17 | 0.02 | 10 | 0.02 | Ponce | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5817-01 | 2026-06-17 | 0.05 | 10 | 0.06 | Ponce | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5817-01 | 2026-06-17 | 0.04 | 10 | 0.05 | Ponce | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5817-01 | 2026-06-24 | 0.02 | 10 | 0.03 | Ponce | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5817-01 | 2026-06-24 | 0.04 | 10 | 0.05 | Ponce | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5901-01 | 2026-06-15 | 0.03 | 10 | 0.04 | Villalba | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5901-01 | 2026-06-15 | 0.03 | 10 | 0.04 | Villalba | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5901-01 | 2026-06-15 | 0.03 | 10 | 0.04 | Villalba | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5901-01 | 2026-06-26 | 0.03 | 10 | 0.03 | Villalba | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5901-02 | 2026-06-15 | 0.01 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5902-02 | 2026-06-26 | 0.02 | 10 | 0.02 | Villalba | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5902-02 | 2026-06-18 | 0.03 | 10 | 0.04 | Villalba | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5902-02 | 2026-06-18 | 0.03 | 10 | 0.03 | Villalba | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5902-02 | 2026-06-18 | 0.04 | 10 | 0.05 | Villalba | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5902-02 | 2026-06-30 | 0.04 | 10 | 0.05 | Villalba | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5902-02 | 2026-06-30 | 0.04 | 10 | 0.05 | Villalba | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 5902-02 | 2026-06-30 | 0.09 | 10 | 0.11 | Villalba | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6014-01 | 2026-06-18 | 0.05 | 10 | 0.07 | Mayaguez | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6014-01 | 2026-06-18 | 0.03 | 10 | 0.04 | Mayaguez | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6014-01 | 2026-06-23 | 0.02 | 10 | 0.02 | Mayaguez | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6101-01 | 2026-06-01 | 0.04 | 10 | 0.05 | Anasco | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6201-01 | 2026-06-25 | 0.04 | 10 | 0.05 | Las Marías | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6201-01 | 2026-06-25 | 0.01 | 10 | 0.02 | Las Marías | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6201-01 | 2026-06-25 | 0.04 | 10 | 0.05 | Las Marías | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6201-01 | 2026-06-25 | 0.1 | 10 | 0.12 | Las Marías | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6201-03 | 2026-06-06 | 0.06 | 10 | 0.07 | Las Marías | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6301-01 | 2026-06-11 | 0.05 | 10 | 0.06 | Maricao | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6303-01 | 2026-06-30 | 0.11 | 10 | 0.14 | San Germán | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6401-02 | 2026-06-12 | 0.03 | 10 | 0.04 | San Germán | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6401-02 | 2026-06-16 | 0.05 | 10 | 0.06 | San Germán | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6401-02 | 2026-06-15 | 0.03 | 10 | 0.04 | San Germán | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6401-02 | 2026-06-23 | 0.03 | 10 | 0.03 | San Germán | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6401-02 | 2026-06-25 | 0.04 | 10 | 0.05 | San Germán | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6401-02 | 2026-06-23 | 0.04 | 10 | 0.05 | San Germán | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6401-02 | 2026-06-19 | 0.01 | 10 | 0.02 | San Germán | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6401-04 | 2026-06-17 | 0.04 | 10 | 0.05 | San Germán | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6404-03 | 2026-06-18 | 0.14 | 10 | 0.17 | San Germán | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6404-03 | 2026-06-25 | 0.22 | 10 | 0.26 | San Germán | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6404-03 | 2026-06-25 | 0.05 | 10 | 0.06 | San Germán | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 6406-02 | 2026-06-19 | 0.03 | 10 | 0.04 | San Germán | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 6406-02 | 2026-06-01 | 0.04 | 10 | 0.04 | San Germán | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 6406-02 | 2026-06-04 | 0.04 | 10 | 0.04 | San Germán | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 6406-02 | 2026-06-04 | 0.04 | 10 | 0.05 | San Germán | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 6406-02 | 2026-06-04 | 0.02 | 10 | 0.03 | San Germán | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 6406-02 | 2026-06-04 | 0.02 | 10 | 0.02 | San Germán | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 6406-02 | 2026-06-04 | 0.01 | 10 | 0.01 | San Germán | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6406-02 | 2026-06-10 | 0.03 | 10 | 0.04 | San Germán | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6406-02 | 2026-06-06 | 0.04 | 10 | 0.04 | San Germán | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6406-02 | 2026-06-10 | 0.03 | 10 | 0.04 | San Germán | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6406-02 | 2026-06-10 | 0.03 | 10 | 0.04 | San Germán | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6406-02 | 2026-06-15 | 0.03 | 10 | 0.03 | San Germán | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6406-02 | 2026-06-15 | 0.04 | 10 | 0.04 | San Germán | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6406-02 | 2026-06-15 | 0.03 | 10 | 0.03 | San Germán | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6406-02 | 2026-06-15 | 0.03 | 10 | 0.03 | San Germán | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6406-02 | 2026-06-15 | 0.03 | 10 | 0.03 | San Germán | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6406-02 | 2026-06-18 | 0.03 | 10 | 0.04 | San Germán | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6406-02 | 2026-06-19 | 0.03 | 10 | 0.04 | San Germán | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6406-02 | 2026-06-22 | 0.03 | 10 | 0.03 | San Germán | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6406-02 | 2026-06-23 | 0.03 | 10 | 0.03 | San Germán | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6406-02 | 2026-06-23 | 0.03 | 10 | 0.04 | San Germán | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6406-02 | 2026-06-22 | 0.03 | 10 | 0.03 | San Germán | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 6406-02 | 2026-06-05 | 0.03 | 10 | 0.04 | San Germán | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 6406-02 | 2026-06-05 | 0.03 | 10 | 0.04 | San Germán | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 6406-02 | 2026-06-05 | 0.02 | 10 | 0.02 | San Germán | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6406-02 | 2026-06-11 | 0.07 | 10 | 0.08 | San Germán | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6406-02 | 2026-06-23 | 0.05 | 10 | 0.07 | San German | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6406-02 | 2026-06-16 | 0.1 | 10 | 0.12 | San German | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6406-02 | 2026-06-19 | 0.1 | 10 | 0.12 | San Germán | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6406-02 | 2026-06-23 | 0.05 | 10 | 0.07 | San Germán | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6406-02 | 2026-06-30 | 0.02 | 10 | 0.03 | San Germán | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6501-02 | 2026-06-03 | 0.01 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6501-02 | 2026-06-03 | 0.02 | 10 | 0.02 | Sabana Grande | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6501-02 | 2026-06-04 | 0.04 | 10 | 0.05 | Sabana Grande | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6501-02 | 2026-06-03 | 0.04 | 10 | 0.05 | Sabana Grande | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6501-02 | 2026-06-03 | 0.03 | 10 | 0.04 | Sabana Grande | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6501-02 | 2026-06-01 | 0.03 | 10 | 0.04 | Sabana Grande | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6501-02 | 2026-06-05 | 0.02 | 10 | 0.03 | Sabana Grande | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6501-02 | 2026-06-08 | 0.04 | 10 | 0.05 | Sabana Grande | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6501-02 | 2026-06-09 | 0.05 | 10 | 0.07 | Sabana Grande | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6501-02 | 2026-06-10 | 0.04 | 10 | 0.05 | Sabana Grande | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6501-02 | 2026-06-10 | 0.04 | 10 | 0.05 | Sabana Grande | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6501-02 | 2026-06-15 | 0.03 | 10 | 0.03 | Sabana Grande | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6501-02 | 2026-06-16 | 0.04 | 10 | 0.04 | Sabana Grande | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6501-02 | 2026-06-18 | 0.03 | 10 | 0.04 | Sabana Grande | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6501-02 | 2026-06-19 | 0.03 | 10 | 0.04 | Sabana Grande | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6501-02 | 2026-06-20 | 0.02 | 10 | 0.03 | Sabana Grande | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6501-02 | 2026-06-23 | 0.02 | 10 | 0.03 | Sabana Grande | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6501-02 | 2026-06-27 | 0.03 | 10 | 0.03 | Sabana Grande | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6501-02 | 2026-06-24 | 0.02 | 10 | 0.03 | Sabana Grande | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6501-02 | 2026-06-30 | 0.04 | 10 | 0.05 | Sabana Grande | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6501-02 | 2026-06-04 | 0.08 | 10 | 0.1 | Sabana Grande | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6501-02 | 2026-06-21 | 0.02 | 10 | 0.03 | Ponce | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6501-02 | 2026-06-22 | 0.28 | 10 | 0.34 | Sabana Grande | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6601-01 | 2026-06-05 | 0.06 | 10 | 0.07 | Ponce | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6601-01 | 2026-06-05 | 0.03 | 10 | 0.04 | Lajas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6601-01 | 2026-06-05 | 0.04 | 10 | 0.05 | Lajas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6601-03 | 2026-06-12 | 0.18 | 10 | 0.22 | Lajas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6601-04 | 2026-06-04 | 0.05 | 10 | 0.06 | San German | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-16 | 0.03 | 10 | 0.04 | Cabo Rojo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-25 | 0.03 | 10 | 0.04 | Cabo Rojo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-16 | 0.03 | 10 | 0.04 | Cabo Rojo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-16 | 0.04 | 10 | 0.04 | Cabo Rojo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-16 | 0.04 | 10 | 0.05 | Cabo Rojo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-16 | 0.03 | 10 | 0.04 | Cabo Rojo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-16 | 0.04 | 10 | 0.05 | Cabo Rojo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-16 | 0.04 | 10 | 0.05 | Cabo Rojo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-15 | 0.03 | 10 | 0.03 | Cabo Rojo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-15 | 0.02 | 10 | 0.03 | Cabo Rojo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-25 | 0.03 | 10 | 0.04 | Cabo Rojo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-27 | 0.06 | 10 | 0.07 | Cabo Rojo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-02 | 0.06 | 10 | 0.07 | Cabo Rojo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-24 | 0.04 | 10 | 0.04 | Cabo Rojo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-25 | 0.03 | 10 | 0.04 | Cabo Rojo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-15 | 0.05 | 10 | 0.06 | Cabo Rojo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-10 | 0.03 | 10 | 0.03 | Cabo Rojo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-09 | 0.07 | 10 | 0.08 | Cabo Rojo | Site Resources | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-09 | 0.06 | 10 | 0.07 | Cabo Rojo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-03 | 0.05 | 10 | 0.06 | Cabo Rojo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-27 | 0.06 | 10 | 0.07 | Cabo Rojo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-27 | 0.13 | 10 | 0.15 | Cabo Rojo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-27 | 0.06 | 10 | 0.08 | Cabo Rojo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-17 | 0.05 | 10 | 0.06 | Cabo Rojo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-17 | 0.05 | 10 | 0.06 | Cabo Rojo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-17 | 0.08 | 10 | 0.09 | Cabo Rojo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-17 | 0.01 | 10 | 0.01 | Cabo Rojo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-03 | 0.05 | 10 | 0.06 | Cabo Rojo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-02 | 0.03 | 10 | 0.03 | Lajas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-03 | 0.05 | 10 | 0.07 | Lajas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-12 | 0.03 | 10 | 0.04 | Lajas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-04 | 0.03 | 10 | 0.04 | Cabo Rojo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-04 | 0.04 | 10 | 0.05 | Cabo Rojo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-05 | 0.03 | 10 | 0.04 | Cabo Rojo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-08 | 0.03 | 10 | 0.04 | Cabo Rojo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-09 | 0.03 | 10 | 0.04 | Cabo Rojo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-09 | 0.03 | 10 | 0.04 | Lajas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-10 | 0.03 | 10 | 0.04 | Lajas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-09 | 0.02 | 10 | 0.03 | Lajas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-10 | 0.04 | 10 | 0.05 | Lajas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-11 | 0.04 | 10 | 0.05 | Lajas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-17 | 0.04 | 10 | 0.05 | Lajas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-11 | 0.04 | 10 | 0.05 | Lajas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-11 | 0.04 | 10 | 0.05 | Lajas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-11 | 0.03 | 10 | 0.04 | Lajas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-10 | 0.02 | 10 | 0.03 | Lajas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-11 | 0.04 | 10 | 0.05 | Lajas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-12 | 0.04 | 10 | 0.05 | Lajas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-13 | 0.03 | 10 | 0.04 | Lajas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-13 | 0.04 | 10 | 0.04 | Lajas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-15 | 0.03 | 10 | 0.04 | Lajas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-18 | 0.03 | 10 | 0.04 | Lajas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-13 | 0.03 | 10 | 0.04 | Lajas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-13 | 0.04 | 10 | 0.04 | Lajas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-19 | 0.04 | 10 | 0.04 | Lajas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-19 | 0.04 | 10 | 0.04 | Lajas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-18 | 0.04 | 10 | 0.04 | Lajas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-19 | 0.04 | 10 | 0.04 | Lajas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-19 | 0.04 | 10 | 0.04 | Lajas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-18 | 0.04 | 10 | 0.04 | Lajas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-19 | 0.04 | 10 | 0.04 | Lajas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-19 | 0.04 | 10 | 0.05 | Lajas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-19 | 0.03 | 10 | 0.04 | Lajas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-19 | 0.04 | 10 | 0.04 | Lajas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-22 | 0.03 | 10 | 0.03 | Lajas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-20 | 0.04 | 10 | 0.04 | Lajas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-20 | 0.04 | 10 | 0.05 | Lajas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-22 | 0.03 | 10 | 0.04 | Lajas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-22 | 0.03 | 10 | 0.04 | Lajas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-23 | 0.03 | 10 | 0.04 | Lajas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-23 | 0.04 | 10 | 0.05 | Lajas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-24 | 0.03 | 10 | 0.04 | Lajas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-23 | 0.02 | 10 | 0.02 | Lajas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-24 | 0.04 | 10 | 0.05 | Lajas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-24 | 0.03 | 10 | 0.03 | Lajas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-16 | 0.04 | 10 | 0.04 | Lajas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-16 | 0.04 | 10 | 0.05 | Lajas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-16 | 0.04 | 10 | 0.04 | Lajas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-16 | 0.04 | 10 | 0.05 | Lajas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-26 | 0.07 | 10 | 0.08 | Cabo Rojo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-24 | 0.04 | 10 | 0.04 | Cabo Rojo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-29 | 0.04 | 10 | 0.05 | Cabo Rojo | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-24 | 0.03 | 10 | 0.04 | Lajas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-24 | 0.02 | 10 | 0.02 | Lajas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-24 | 0.04 | 10 | 0.04 | Lajas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-27 | 0.04 | 10 | 0.04 | Lajas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-30 | 0.004 | 10 | 0.01 | Cabo Rojo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6702-02 | 2026-06-30 | 0.01 | 10 | 0.02 | Cabo Rojo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6703-03 | 2026-06-15 | 0.02 | 10 | 0.02 | Cabo Rojo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6703-03 | 2026-06-06 | 0.04 | 10 | 0.05 | Cabo Rojo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6704-03 | 2026-06-16 | 0.08 | 10 | 0.1 | Cabo Rojo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6704-03 | 2026-06-16 | 0.08 | 10 | 0.1 | Cabo Rojo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6704-03 | 2026-06-17 | 0.03 | 10 | 0.04 | Lajas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 6704-03 | 2026-06-16 | 0.08 | 10 | 0.1 | Cabo Rojo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6801-02 | 2026-06-06 | 0.04 | 10 | 0.04 | Hormigueros | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6801-02 | 2026-06-03 | 0.003 | 10 | 0.004 | San Germán | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6801-02 | 2026-06-03 | 0.04 | 10 | 0.05 | Hormigueros | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6801-02 | 2026-06-08 | 0.06 | 10 | 0.08 | Hormigueros | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6801-02 | 2026-06-09 | 0.03 | 10 | 0.04 | Hormigueros | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6801-02 | 2026-06-06 | 0.02 | 10 | 0.03 | Hormigueros | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6801-03 | 2026-06-02 | 0.01 | 10 | 0.01 | Cabo Rojo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6802-02 | 2026-06-05 | 0.03 | 10 | 0.04 | Hormigueros | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6802-02 | 2026-06-08 | 0.05 | 10 | 0.06 | Hormigueros | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6802-02 | 2026-06-08 | 0.02 | 10 | 0.02 | Hormigueros | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 6802-02 | 2026-06-05 | 0.02 | 10 | 0.03 | Hormigueros | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7003-03 | 2026-06-17 | 0.03 | 10 | 0.04 | Aguadilla | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7005-03 | 2026-06-05 | 0.03 | 10 | 0.04 | Aguadilla | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7008-04 | 2026-06-09 | 0.22 | 10 | 0.27 | Aguada | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7008-04 | 2026-06-18 | 0.04 | 10 | 0.05 | Aguada | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7008-04 | 2026-06-22 | 0.03 | 10 | 0.04 | Aguada | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7008-04 | 2026-06-22 | 0.01 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7008-04 | 2026-06-29 | 0.04 | 10 | 0.05 | Aguada | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7008-04 | 2026-06-27 | 0.02 | 10 | 0.03 | Aguada | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7008-04 | 2026-06-27 | 0.03 | 10 | 0.04 | Aguada | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7008-04 | 2026-06-27 | 0.03 | 10 | 0.04 | Aguada | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7008-07 | 2026-06-09 | 0.02 | 10 | 0.03 | Aguadilla | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7008-07 | 2026-06-16 | 0.02 | 10 | 0.03 | Aguadilla | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7008-07 | 2026-06-16 | 0.02 | 10 | 0.02 | Aguadilla | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7008-07 | 2026-06-16 | 0.02 | 10 | 0.03 | Aguadilla | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7008-07 | 2026-06-10 | 0.02 | 10 | 0.02 | Aguadilla | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7008-07 | 2026-06-11 | 0.02 | 10 | 0.03 | Aguadilla | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7008-07 | 2026-06-10 | 0.02 | 10 | 0.03 | Aguadilla | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7008-07 | 2026-06-10 | 0.02 | 10 | 0.03 | Aguadilla | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7008-07 | 2026-06-11 | 0.02 | 10 | 0.02 | Aguadilla | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7008-07 | 2026-06-16 | 0.02 | 10 | 0.02 | Aguadilla | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7008-07 | 2026-06-16 | 0.02 | 10 | 0.02 | Aguadilla | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7008-07 | 2026-06-18 | 0.02 | 10 | 0.02 | Aguadilla | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7008-07 | 2026-06-18 | 0.02 | 10 | 0.02 | Aguadilla | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7008-07 | 2026-06-08 | 0.02 | 10 | 0.03 | Aguadilla | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7008-07 | 2026-06-08 | 0.02 | 10 | 0.02 | Aguadilla | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7008-07 | 2026-06-08 | 0.02 | 10 | 0.02 | Aguadilla | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7008-07 | 2026-06-09 | 0.02 | 10 | 0.02 | Aguadilla | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7008-07 | 2026-06-05 | 0.02 | 10 | 0.02 | Aguadilla | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7008-07 | 2026-06-01 | 0.04 | 10 | 0.05 | Aguadilla | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7008-07 | 2026-06-02 | 0.04 | 10 | 0.05 | Aguadilla | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7008-07 | 2026-06-02 | 0.04 | 10 | 0.05 | Aguadilla | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7008-07 | 2026-06-02 | 0.04 | 10 | 0.05 | Aguadilla | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7008-07 | 2026-06-02 | 0.04 | 10 | 0.05 | Aguadilla | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7008-07 | 2026-06-02 | 0.04 | 10 | 0.05 | Aguadilla | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7008-07 | 2026-06-02 | 0.04 | 10 | 0.05 | Aguadilla | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7008-07 | 2026-06-02 | 0.04 | 10 | 0.05 | Aguadilla | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7008-07 | 2026-06-02 | 0.04 | 10 | 0.05 | Aguadilla | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7008-07 | 2026-06-08 | 0.04 | 10 | 0.05 | Aguadilla | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7008-07 | 2026-06-05 | 0.03 | 10 | 0.04 | Aguadilla | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7008-07 | 2026-06-01 | 0.04 | 10 | 0.05 | Aguadilla | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7008-07 | 2026-06-01 | 0.04 | 10 | 0.05 | Aguadilla | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7008-07 | 2026-06-02 | 0.04 | 10 | 0.05 | Aguadilla | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7008-07 | 2026-06-05 | 0.01 | 10 | 0.01 | Aguadilla | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7008-07 | 2026-06-05 | 0.02 | 10 | 0.02 | Aguadilla | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7008-07 | 2026-06-05 | 0.02 | 10 | 0.03 | Aguadilla | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7008-07 | 2026-06-05 | 0.02 | 10 | 0.03 | Aguadilla | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7008-07 | 2026-06-08 | 0.02 | 10 | 0.02 | Aguadilla | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7008-07 | 2026-06-08 | 0.02 | 10 | 0.03 | Aguadilla | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7008-07 | 2026-06-08 | 0.02 | 10 | 0.03 | Aguadilla | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7008-07 | 2026-06-08 | 0.02 | 10 | 0.03 | Aguadilla | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7008-07 | 2026-06-09 | 0.02 | 10 | 0.02 | Aguadilla | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7008-07 | 2026-06-09 | 0.02 | 10 | 0.02 | Aguadilla | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7008-07 | 2026-06-10 | 0.02 | 10 | 0.02 | Aguadilla | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7008-07 | 2026-06-09 | 0.02 | 10 | 0.02 | Aguadilla | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7008-07 | 2026-06-11 | 0.02 | 10 | 0.03 | Aguadilla | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7008-07 | 2026-06-16 | 0.02 | 10 | 0.03 | Aguadilla | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7008-08 | 2026-06-18 | 0.05 | 10 | 0.06 | Aguadilla | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7008-08 | 2026-06-19 | 0.03 | 10 | 0.04 | Aguadilla | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7008-08 | 2026-06-19 | 0.03 | 10 | 0.04 | Aguadilla | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7008-08 | 2026-06-19 | 0.06 | 10 | 0.07 | Aguadilla | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7008-08 | 2026-06-18 | 0.04 | 10 | 0.05 | Aguadilla | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7008-08 | 2026-06-17 | 0.06 | 10 | 0.07 | Aguadilla | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7011-01 | 2026-06-16 | 0.02 | 10 | 0.02 | Aguadilla | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7101-03 | 2026-06-05 | 0.07 | 10 | 0.09 | Aguada | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7101-03 | 2026-06-30 | 0.03 | 10 | 0.03 | Aguada | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7101-03 | 2026-06-11 | 0.07 | 10 | 0.09 | Aguada | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7101-03 | 2026-06-30 | 0.07 | 10 | 0.09 | Aguada | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7101-03 | 2026-06-11 | 0.02 | 10 | 0.02 | Aguada | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7104-05 | 2026-06-04 | 0.08 | 10 | 0.09 | Moca | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7201-01 | 2026-06-16 | 0.12 | 10 | 0.15 | Aguada | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7201-01 | 2026-06-17 | 0.06 | 10 | 0.07 | Aguada | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7201-05 | 2026-06-04 | 0.02 | 10 | 0.03 | Aguada | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7201-05 | 2026-06-03 | 0.03 | 10 | 0.04 | Aguada | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7201-05 | 2026-06-03 | 0.02 | 10 | 0.03 | Aguada | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7303-01 | 2026-06-23 | 0.04 | 10 | 0.05 | Aguada | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7303-01 | 2026-06-12 | 0.11 | 10 | 0.13 | Aguada | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7303-01 | 2026-06-23 | 0.02 | 10 | 0.03 | Aguada | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7303-01 | 2026-06-23 | 0.15 | 10 | 0.18 | Aguada | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7403-03 | 2026-06-27 | 0.05 | 10 | 0.06 | San Sebastian | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7403-03 | 2026-06-25 | 0.02 | 10 | 0.02 | San Sebastián | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7403-03 | 2026-06-27 | 0.09 | 10 | 0.1 | San Sebastián | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7403-03 | 2026-06-12 | 0.1 | 10 | 0.12 | San Sebastián | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7403-03 | 2026-06-24 | 0.05 | 10 | 0.06 | Isabela | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7403-03 | 2026-06-24 | 0.03 | 10 | 0.04 | Isabela | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7403-03 | 2026-06-30 | 0.03 | 10 | 0.04 | San Sebastián | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7403-03 | 2026-06-26 | 0.05 | 10 | 0.06 | San Sebastián | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7403-03 | 2026-06-12 | 0.05 | 10 | 0.06 | Isabela | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7403-03 | 2026-06-19 | 0.04 | 10 | 0.05 | San Sebastián | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7403-03 | 2026-06-19 | 0.06 | 10 | 0.07 | San Sebastián | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7403-03 | 2026-06-15 | 0.23 | 10 | 0.27 | Isabela | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7502-02 | 2026-06-01 | 0.04 | 10 | 0.05 | Isabela | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7502-02 | 2026-06-01 | 0.04 | 10 | 0.05 | Isabela | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7502-02 | 2026-06-03 | 0.04 | 10 | 0.05 | Isabela | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7502-02 | 2026-06-03 | 0.03 | 10 | 0.04 | Isabela | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7502-02 | 2026-06-03 | 0.04 | 10 | 0.04 | Isabela | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7502-02 | 2026-06-15 | 0.16 | 10 | 0.19 | Isabela | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7502-02 | 2026-06-18 | 0.1 | 10 | 0.12 | Isabela | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7502-02 | 2026-06-04 | 0.03 | 10 | 0.04 | Isabela | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7502-02 | 2026-06-03 | 0.03 | 10 | 0.03 | Isabela | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7502-02 | 2026-06-02 | 0.04 | 10 | 0.05 | Isabela | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7502-02 | 2026-06-03 | 0.03 | 10 | 0.03 | Isabela | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7502-02 | 2026-06-02 | 0.03 | 10 | 0.04 | Isabela | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7502-03 | 2026-06-26 | 0.05 | 10 | 0.06 | Isabela | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7601-01 | 2026-06-09 | 0.03 | 10 | 0.04 | Camuy | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7601-03 | 2026-06-03 | 0.07 | 10 | 0.08 | Camuy | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7601-03 | 2026-06-03 | 0.05 | 10 | 0.06 | Camuy | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7601-03 | 2026-06-23 | 0.09 | 10 | 0.1 | Camuy | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7601-03 | 2026-06-23 | 0.05 | 10 | 0.06 | Camuy | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7601-03 | 2026-06-03 | 0.07 | 10 | 0.08 | Camuy | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7601-03 | 2026-06-03 | 0.04 | 10 | 0.05 | Camuy | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7601-03 | 2026-06-22 | 0.05 | 10 | 0.06 | Camuy | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7601-03 | 2026-06-23 | 0.08 | 10 | 0.09 | Camuy | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7701-01 | 2026-06-01 | 0.03 | 10 | 0.03 | Hatillo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7701-01 | 2026-06-12 | 0.03 | 10 | 0.03 | Hatillo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7701-01 | 2026-06-12 | 0.03 | 10 | 0.04 | Hatillo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7701-01 | 2026-06-12 | 0.04 | 10 | 0.05 | Hatillo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-06-08 | 0.04 | 10 | 0.05 | San Sebastián | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-06-11 | 0.07 | 10 | 0.09 | San Sebastián | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-06-08 | 0.04 | 10 | 0.04 | San Sebastián | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-06-01 | 0.09 | 10 | 0.11 | San Sebastián | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-06-01 | 0.03 | 10 | 0.04 | San Sebastián | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-06-05 | 0.08 | 10 | 0.09 | San Sebastián | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-06-02 | 0.09 | 10 | 0.11 | San Sebastián | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-06-02 | 0.1 | 10 | 0.13 | San Sebastián | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7802-03 | 2026-06-05 | 0.11 | 10 | 0.14 | San Sebastián | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7802-04 | 2026-06-18 | 0.05 | 10 | 0.05 | San Sebastián | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7802-04 | 2026-06-26 | 0.05 | 10 | 0.06 | San Sebastián | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7802-04 | 2026-06-16 | 0.05 | 10 | 0.06 | San Sebastián | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7802-04 | 2026-06-15 | 0.03 | 10 | 0.04 | San Sebastián | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7802-04 | 2026-06-12 | 0.06 | 10 | 0.07 | San Sebastián | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7802-04 | 2026-06-25 | 0.03 | 10 | 0.04 | San Sebastián | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7802-04 | 2026-06-22 | 0.05 | 10 | 0.06 | San Sebastián | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7805-13 | 2026-06-05 | 0.17 | 10 | 0.2 | San Sebastián | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 7901-04 | 2026-06-07 | 0.11 | 10 | 0.14 | Lares | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7903-06 | 2026-06-13 | 0.03 | 10 | 0.04 | Lares | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7903-06 | 2026-06-15 | 0.02 | 10 | 0.02 | Lares | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7903-06 | 2026-06-16 | 0.03 | 10 | 0.04 | Lares | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7903-06 | 2026-06-18 | 0.03 | 10 | 0.03 | Lares | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7903-06 | 2026-06-19 | 0.04 | 10 | 0.05 | Lares | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7903-06 | 2026-06-23 | 0.03 | 10 | 0.04 | Lares | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7903-06 | 2026-06-25 | 0.03 | 10 | 0.03 | San Sebastián | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7903-06 | 2026-06-25 | 0.02 | 10 | 0.02 | Aguada | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 7903-06 | 2026-06-25 | 0.02 | 10 | 0.03 | San Sebastián | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8001-03 | 2026-06-10 | 0.02 | 10 | 0.03 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8001-03 | 2026-06-10 | 0.02 | 10 | 0.02 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8002-03 | 2026-06-25 | 0.03 | 10 | 0.03 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8002-03 | 2026-06-11 | 0.02 | 10 | 0.03 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8002-03 | 2026-06-11 | 0.02 | 10 | 0.03 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8002-03 | 2026-06-28 | 0.03 | 10 | 0.04 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8002-03 | 2026-06-11 | 0.03 | 10 | 0.04 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8002-03 | 2026-06-10 | 0.04 | 10 | 0.05 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8002-05 | 2026-06-19 | 0.03 | 10 | 0.03 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8002-05 | 2026-06-04 | 0.02 | 10 | 0.03 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8002-05 | 2026-06-04 | 0.03 | 10 | 0.03 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8002-05 | 2026-06-04 | 0.02 | 10 | 0.03 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8002-05 | 2026-06-04 | 0.02 | 10 | 0.03 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8002-05 | 2026-06-04 | 0.04 | 10 | 0.05 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8002-05 | 2026-06-22 | 0.03 | 10 | 0.03 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8002-05 | 2026-06-04 | 0.01 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8002-05 | 2026-06-04 | 0.02 | 10 | 0.03 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8002-05 | 2026-06-04 | 0.01 | 10 | 0.02 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8002-05 | 2026-06-04 | 0.03 | 10 | 0.03 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8002-05 | 2026-06-11 | 0.02 | 10 | 0.02 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8002-05 | 2026-06-11 | 0.01 | 10 | 0.02 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8002-05 | 2026-06-11 | 0.04 | 10 | 0.05 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8002-05 | 2026-06-11 | 0.02 | 10 | 0.03 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8002-05 | 2026-06-11 | 0.04 | 10 | 0.05 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8002-05 | 2026-06-11 | 0.02 | 10 | 0.02 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8002-05 | 2026-06-11 | 0.03 | 10 | 0.04 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8002-05 | 2026-06-11 | 0.03 | 10 | 0.04 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-02 | 2026-06-17 | 0.03 | 10 | 0.04 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-02 | 2026-06-17 | 0.03 | 10 | 0.04 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-02 | 2026-06-17 | 0.004 | 10 | 0.005 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-02 | 2026-06-17 | 0.03 | 10 | 0.03 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-02 | 2026-06-17 | 0.03 | 10 | 0.03 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-02 | 2026-06-17 | 0.03 | 10 | 0.04 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-02 | 2026-06-17 | 0.03 | 10 | 0.04 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-02 | 2026-06-23 | 0.03 | 10 | 0.04 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-02 | 2026-06-23 | 0.03 | 10 | 0.03 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-02 | 2026-06-23 | 0.04 | 10 | 0.04 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-02 | 2026-06-23 | 0.04 | 10 | 0.05 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-02 | 2026-06-17 | 0.04 | 10 | 0.04 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-02 | 2026-06-17 | 0.03 | 10 | 0.04 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-02 | 2026-06-17 | 0.04 | 10 | 0.04 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-02 | 2026-06-11 | 0.04 | 10 | 0.05 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-02 | 2026-06-18 | 0.03 | 10 | 0.03 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-02 | 2026-06-15 | 0.05 | 10 | 0.07 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-02 | 2026-06-15 | 0.04 | 10 | 0.05 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-02 | 2026-06-06 | 0.01 | 10 | 0.02 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-02 | 2026-06-06 | 0.03 | 10 | 0.04 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-02 | 2026-06-05 | 0.03 | 10 | 0.04 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-02 | 2026-06-23 | 0.03 | 10 | 0.03 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-02 | 2026-06-23 | 0.04 | 10 | 0.05 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-02 | 2026-06-17 | 0.06 | 10 | 0.07 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-03 | 2026-06-15 | 0.02 | 10 | 0.02 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-03 | 2026-06-01 | 0.02 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-03 | 2026-06-01 | 0.02 | 10 | 0.02 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-03 | 2026-06-08 | 0.02 | 10 | 0.03 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-03 | 2026-06-01 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-03 | 2026-06-01 | 0.02 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-03 | 2026-06-01 | 0.04 | 10 | 0.05 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-03 | 2026-06-01 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-03 | 2026-06-08 | 0.02 | 10 | 0.02 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-03 | 2026-06-05 | 0.03 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-03 | 2026-06-06 | 0.02 | 10 | 0.02 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-03 | 2026-06-11 | 0.01 | 10 | 0.01 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-03 | 2026-06-05 | 0.03 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-03 | 2026-06-11 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-03 | 2026-06-11 | 0.01 | 10 | 0.01 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-03 | 2026-06-11 | 0.02 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-03 | 2026-06-11 | 0.02 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-03 | 2026-06-11 | 0.02 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-03 | 2026-06-11 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-03 | 2026-06-11 | 0.03 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-01 | 0.04 | 10 | 0.05 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-02 | 0.04 | 10 | 0.05 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-11 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-09 | 0.02 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-12 | 0.02 | 10 | 0.02 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-15 | 0.03 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-15 | 0.04 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-03 | 0.02 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-06 | 0.02 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-03 | 0.03 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-03 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-03 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-01 | 0.03 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-04 | 0.03 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-03 | 0.02 | 10 | 0.02 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-03 | 0.03 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-03 | 0.03 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-03 | 0.04 | 10 | 0.05 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-03 | 0.02 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-03 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-03 | 0.02 | 10 | 0.02 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-03 | 0.02 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-03 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-03 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-03 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-03 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-03 | 0.02 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-03 | 0.02 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-03 | 0.03 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-03 | 0.02 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-03 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-03 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-04 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-04 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-04 | 0.03 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-04 | 0.03 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-04 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-04 | 0.03 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-04 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-16 | 0.01 | 10 | 0.02 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-16 | 0.004 | 10 | 0.01 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-16 | 0.01 | 10 | 0.01 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-15 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-15 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-15 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-15 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-15 | 0.03 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-15 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-15 | 0.03 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-15 | 0.04 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-15 | 0.02 | 10 | 0.02 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-15 | 0.02 | 10 | 0.02 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-15 | 0.02 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-15 | 0.02 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-15 | 0.04 | 10 | 0.05 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-15 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-15 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-15 | 0.04 | 10 | 0.05 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-15 | 0.04 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-15 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-15 | 0.03 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-15 | 0.02 | 10 | 0.02 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-15 | 0.04 | 10 | 0.05 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-15 | 0.03 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-15 | 0.03 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8004-04 | 2026-06-15 | 0.05 | 10 | 0.06 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8005-01 | 2026-06-21 | 0.12 | 10 | 0.14 | Ciales | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 8007-03 | 2026-06-10 | 0.04 | 10 | 0.05 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 8007-03 | 2026-06-10 | 0.03 | 10 | 0.04 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 8007-03 | 2026-06-10 | 0.04 | 10 | 0.05 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 8007-03 | 2026-06-10 | 0.07 | 10 | 0.09 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 8007-03 | 2026-06-10 | 0.07 | 10 | 0.09 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 8007-03 | 2026-06-10 | 0.03 | 10 | 0.04 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 8007-03 | 2026-06-10 | 0.03 | 10 | 0.04 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 8007-03 | 2026-06-10 | 0.04 | 10 | 0.05 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 8007-03 | 2026-06-10 | 0.04 | 10 | 0.05 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 8007-03 | 2026-06-17 | 0.04 | 10 | 0.05 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 8007-03 | 2026-06-17 | 0.04 | 10 | 0.05 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 8007-03 | 2026-06-17 | 0.02 | 10 | 0.02 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 8007-03 | 2026-06-17 | 0.05 | 10 | 0.06 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 8007-03 | 2026-06-24 | 0.04 | 10 | 0.04 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 8007-03 | 2026-06-17 | 0.05 | 10 | 0.05 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 8007-03 | 2026-06-17 | 0.04 | 10 | 0.05 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 8007-03 | 2026-06-29 | 0.02 | 10 | 0.03 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 8007-03 | 2026-06-17 | 0.03 | 10 | 0.03 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 8007-03 | 2026-06-17 | 0.04 | 10 | 0.04 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 8007-03 | 2026-06-17 | 0.03 | 10 | 0.04 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 8007-03 | 2026-06-17 | 0.02 | 10 | 0.03 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 8007-03 | 2026-06-17 | 0.04 | 10 | 0.05 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 8007-03 | 2026-06-17 | 0.02 | 10 | 0.02 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 8007-03 | 2026-06-17 | 0.05 | 10 | 0.06 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 8007-03 | 2026-06-23 | 0.04 | 10 | 0.05 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 8007-03 | 2026-06-24 | 0.04 | 10 | 0.04 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 8007-03 | 2026-06-24 | 0.02 | 10 | 0.03 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 8007-03 | 2026-06-24 | 0.05 | 10 | 0.06 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 8007-03 | 2026-06-17 | 0.03 | 10 | 0.04 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 8007-03 | 2026-06-17 | 0.03 | 10 | 0.04 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 8007-03 | 2026-06-17 | 0.03 | 10 | 0.03 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 8007-03 | 2026-06-17 | 0.04 | 10 | 0.05 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 8007-03 | 2026-06-17 | 0.04 | 10 | 0.05 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 8007-03 | 2026-06-17 | 0.04 | 10 | 0.05 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 8007-03 | 2026-06-17 | 0.04 | 10 | 0.05 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 8007-03 | 2026-06-17 | 0.03 | 10 | 0.04 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 8007-03 | 2026-06-17 | 0.03 | 10 | 0.03 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 8007-03 | 2026-06-17 | 0.03 | 10 | 0.04 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 8007-03 | 2026-06-30 | 0.02 | 10 | 0.02 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 8007-03 | 2026-06-30 | 0.01 | 10 | 0.02 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 8007-03 | 2026-06-23 | 0.03 | 10 | 0.04 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 8007-03 | 2026-06-24 | 0.03 | 10 | 0.04 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 8007-03 | 2026-06-24 | 0.01 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 8007-03 | 2026-06-23 | 0.04 | 10 | 0.05 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 8007-04 | 2026-06-24 | 0.02 | 10 | 0.02 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 8007-04 | 2026-06-24 | 0.06 | 10 | 0.07 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 8007-04 | 2026-06-24 | 0.03 | 10 | 0.03 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 8007-04 | 2026-06-24 | 0.03 | 10 | 0.03 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 8007-04 | 2026-06-23 | 0.04 | 10 | 0.05 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 8007-04 | 2026-06-23 | 0.04 | 10 | 0.05 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 8007-04 | 2026-06-23 | 0.04 | 10 | 0.05 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 8007-04 | 2026-06-24 | 0.03 | 10 | 0.03 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8008-01 | 2026-06-30 | 0.02 | 10 | 0.03 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8008-01 | 2026-06-30 | 0.02 | 10 | 0.02 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8008-01 | 2026-06-30 | 0.03 | 10 | 0.04 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8008-01 | 2026-06-30 | 0.03 | 10 | 0.04 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 8010-02 | 2026-06-26 | 0.07 | 10 | 0.09 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 8010-02 | 2026-06-26 | 0.05 | 10 | 0.06 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 8010-02 | 2026-06-29 | 0.04 | 10 | 0.04 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 8010-02 | 2026-06-29 | 0.06 | 10 | 0.07 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 8010-03 | 2026-06-02 | 0.04 | 10 | 0.05 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.16/7.20 | 8010-03 | 2026-06-02 | 0.04 | 10 | 0.05 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8011-01 | 2026-06-12 | 0.02 | 10 | 0.02 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8011-01 | 2026-06-12 | 0.03 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8011-01 | 2026-06-12 | 0.02 | 10 | 0.02 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8011-01 | 2026-06-11 | 0.02 | 10 | 0.02 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8011-01 | 2026-06-12 | 0.02 | 10 | 0.02 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8011-01 | 2026-06-27 | 0.02 | 10 | 0.02 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8011-01 | 2026-06-12 | 0.02 | 10 | 0.02 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8011-01 | 2026-06-15 | 0.02 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8011-01 | 2026-06-17 | 0.03 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8011-01 | 2026-06-17 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8011-01 | 2026-06-17 | 0.02 | 10 | 0.02 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8011-01 | 2026-06-17 | 0.02 | 10 | 0.02 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8011-01 | 2026-06-17 | 0.02 | 10 | 0.02 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8011-01 | 2026-06-17 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8011-01 | 2026-06-17 | 0.02 | 10 | 0.02 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8011-01 | 2026-06-25 | 0.02 | 10 | 0.02 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8011-01 | 2026-06-26 | 0.04 | 10 | 0.05 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8011-04 | 2026-06-16 | 0.01 | 10 | 0.01 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8011-04 | 2026-06-26 | 0.03 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8011-04 | 2026-06-25 | 0.02 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8011-04 | 2026-06-25 | 0.02 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8011-04 | 2026-06-26 | 0.02 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8011-04 | 2026-06-25 | 0.02 | 10 | 0.02 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8011-04 | 2026-06-26 | 0.02 | 10 | 0.02 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8011-04 | 2026-06-25 | 0.02 | 10 | 0.02 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8013-01 | 2026-06-22 | 0.04 | 10 | 0.04 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8013-01 | 2026-06-22 | 0.02 | 10 | 0.03 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8013-01 | 2026-06-22 | 0.03 | 10 | 0.03 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8013-01 | 2026-06-22 | 0.01 | 10 | 0.02 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8013-01 | 2026-06-22 | 0.03 | 10 | 0.04 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8013-01 | 2026-06-22 | 0.02 | 10 | 0.03 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8013-01 | 2026-06-22 | 0.03 | 10 | 0.03 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8013-01 | 2026-06-22 | 0.03 | 10 | 0.04 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8013-01 | 2026-06-22 | 0.03 | 10 | 0.04 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8013-01 | 2026-06-23 | 0.05 | 10 | 0.06 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8013-01 | 2026-06-23 | 0.04 | 10 | 0.05 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8013-01 | 2026-06-23 | 0.04 | 10 | 0.05 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8013-02 | 2026-06-25 | 0.03 | 10 | 0.04 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8013-02 | 2026-06-25 | 0.03 | 10 | 0.04 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8013-02 | 2026-06-26 | 0.04 | 10 | 0.04 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8013-02 | 2026-06-30 | 0.03 | 10 | 0.04 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8013-02 | 2026-06-26 | 0.03 | 10 | 0.04 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8013-02 | 2026-06-26 | 0.03 | 10 | 0.03 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8013-02 | 2026-06-30 | 0.03 | 10 | 0.03 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8013-02 | 2026-06-29 | 0.02 | 10 | 0.02 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8013-02 | 2026-06-29 | 0.03 | 10 | 0.04 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8013-02 | 2026-06-30 | 0.04 | 10 | 0.05 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8013-02 | 2026-06-26 | 0.03 | 10 | 0.04 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8013-02 | 2026-06-26 | 0.03 | 10 | 0.04 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8013-02 | 2026-06-26 | 0.01 | 10 | 0.02 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8013-03 | 2026-06-30 | 0.03 | 10 | 0.03 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8013-04 | 2026-06-29 | 0.05 | 10 | 0.06 | Hatillo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8014-07 | 2026-06-15 | 0.03 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8014-07 | 2026-06-15 | 0.02 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8014-07 | 2026-06-15 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8014-07 | 2026-06-15 | 0.03 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8014-07 | 2026-06-15 | 0.02 | 10 | 0.02 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8014-07 | 2026-06-15 | 0.02 | 10 | 0.02 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8014-07 | 2026-06-18 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8014-07 | 2026-06-15 | 0.02 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8014-07 | 2026-06-15 | 0.03 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8014-07 | 2026-06-15 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8014-07 | 2026-06-15 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8014-07 | 2026-06-17 | 0.02 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8014-07 | 2026-06-17 | 0.03 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8014-07 | 2026-06-17 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8014-07 | 2026-06-17 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8014-07 | 2026-06-25 | 0.02 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-06-05 | 0.04 | 10 | 0.04 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-06-10 | 0.05 | 10 | 0.07 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-06-05 | 0.02 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-06-01 | 0.05 | 10 | 0.06 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-06-01 | 0.04 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-06-01 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-06-05 | 0.04 | 10 | 0.05 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-06-02 | 0.04 | 10 | 0.05 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-06-02 | 0.04 | 10 | 0.05 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-06-02 | 0.04 | 10 | 0.05 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-06-02 | 0.05 | 10 | 0.06 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-06-02 | 0.04 | 10 | 0.05 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-06-04 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-06-04 | 0.02 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-06-05 | 0.03 | 10 | 0.04 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-06-05 | 0.04 | 10 | 0.05 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-06-05 | 0.04 | 10 | 0.05 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-06-05 | 0.02 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-06-05 | 0.04 | 10 | 0.05 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-06-05 | 0.05 | 10 | 0.06 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-06-08 | 0.02 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-06-05 | 0.04 | 10 | 0.05 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-06-05 | 0.05 | 10 | 0.06 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-06-10 | 0.05 | 10 | 0.06 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8014-08 | 2026-06-26 | 0.03 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8014-08 | 2026-06-12 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8014-08 | 2026-06-26 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-06-22 | 0.01 | 10 | 0.02 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-06-24 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-06-24 | 0.03 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-06-24 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-06-24 | 0.03 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-06-24 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-06-19 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-06-19 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-06-25 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-06-23 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-06-11 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-06-25 | 0.03 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-06-26 | 0.05 | 10 | 0.06 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-06-20 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-06-25 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-06-19 | 0.02 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-06-22 | 0.02 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-06-22 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-06-25 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-06-25 | 0.03 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-06-25 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-06-24 | 0.02 | 10 | 0.02 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-06-25 | 0.04 | 10 | 0.05 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-06-25 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-06-24 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-06-26 | 0.03 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-06-27 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-06-29 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-06-29 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-06-29 | 0.03 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-06-29 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-06-24 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-06-24 | 0.03 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-06-24 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8014-08 | 2026-06-25 | 0.02 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8014-08 | 2026-06-26 | 0.01 | 10 | 0.02 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8014-08 | 2026-06-25 | 0.03 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8014-08 | 2026-06-26 | 0.04 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8014-08 | 2026-06-25 | 0.03 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8014-08 | 2026-06-25 | 0.02 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8014-08 | 2026-06-26 | 0.02 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8014-08 | 2026-06-25 | 0.03 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8014-08 | 2026-06-25 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8014-08 | 2026-06-26 | 0.03 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8014-08 | 2026-06-25 | 0.03 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8014-08 | 2026-06-25 | 0.03 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8015-08 | 2026-06-25 | 0.03 | 10 | 0.03 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8015-08 | 2026-06-11 | 0.02 | 10 | 0.03 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8015-08 | 2026-06-11 | 0.02 | 10 | 0.03 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8015-08 | 2026-06-11 | 0.02 | 10 | 0.03 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8015-08 | 2026-06-10 | 0.04 | 10 | 0.05 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8015-08 | 2026-06-29 | 0.03 | 10 | 0.04 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8015-08 | 2026-06-29 | 0.04 | 10 | 0.05 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8015-08 | 2026-06-10 | 0.03 | 10 | 0.04 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8015-08 | 2026-06-10 | 0.02 | 10 | 0.02 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8015-09 | 2026-06-22 | 0.02 | 10 | 0.03 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8015-09 | 2026-06-22 | 0.03 | 10 | 0.03 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8015-09 | 2026-06-22 | 0.02 | 10 | 0.02 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8015-09 | 2026-06-22 | 0.01 | 10 | 0.02 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8015-09 | 2026-06-22 | 0.02 | 10 | 0.03 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8015-09 | 2026-06-22 | 0.03 | 10 | 0.04 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8015-09 | 2026-06-22 | 0.03 | 10 | 0.04 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 8015-09 | 2026-06-22 | 0.04 | 10 | 0.04 | Arecibo | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8103-01 | 2026-06-28 | 0.03 | 10 | 0.04 | Utuado | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8104-01 | 2026-06-23 | 0.08 | 10 | 0.09 | Utuado | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8104-01 | 2026-06-23 | 0.07 | 10 | 0.08 | Utuado | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8104-01 | 2026-06-23 | 0.05 | 10 | 0.06 | Utuado | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8104-01 | 2026-06-23 | 0.06 | 10 | 0.07 | Utuado | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8104-02 | 2026-06-03 | 0.08 | 10 | 0.09 | Utuado | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8104-02 | 2026-06-04 | 0.05 | 10 | 0.06 | Utuado | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8104-02 | 2026-06-04 | 0.03 | 10 | 0.04 | Utuado | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8104-02 | 2026-06-25 | 0.1 | 10 | 0.12 | Utuado | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8104-02 | 2026-06-25 | 0.04 | 10 | 0.05 | Utuado | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8104-02 | 2026-06-29 | 0.05 | 10 | 0.05 | Adjuntas | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8104-02 | 2026-06-29 | 0.07 | 10 | 0.09 | Adjuntas | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8501-02 | 2026-06-25 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8501-02 | 2026-06-25 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8501-02 | 2026-06-26 | 0.04 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8501-02 | 2026-06-25 | 0.05 | 10 | 0.06 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8501-02 | 2026-06-25 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8501-02 | 2026-06-27 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8501-02 | 2026-06-29 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8501-02 | 2026-06-27 | 0.01 | 10 | 0.02 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8501-02 | 2026-06-27 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8501-02 | 2026-06-27 | 0.03 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8501-02 | 2026-06-29 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8501-02 | 2026-06-29 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8501-02 | 2026-06-30 | 0.02 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8504-03 | 2026-06-17 | 0.03 | 10 | 0.04 | Barceloneta | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8602-03 | 2026-06-08 | 0.04 | 10 | 0.05 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8602-03 | 2026-06-08 | 0.03 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8602-03 | 2026-06-08 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8602-03 | 2026-06-09 | 0.05 | 10 | 0.06 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8602-03 | 2026-06-09 | 0.05 | 10 | 0.06 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8602-03 | 2026-06-12 | 0.05 | 10 | 0.06 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8602-03 | 2026-06-12 | 0.04 | 10 | 0.05 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8602-03 | 2026-06-12 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8602-03 | 2026-06-12 | 0.04 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8602-03 | 2026-06-12 | 0.04 | 10 | 0.05 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8602-03 | 2026-06-12 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8602-03 | 2026-06-15 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8602-03 | 2026-06-12 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8602-03 | 2026-06-15 | 0.05 | 10 | 0.06 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8602-03 | 2026-06-13 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8602-03 | 2026-06-13 | 0.04 | 10 | 0.05 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8602-03 | 2026-06-20 | 0.03 | 10 | 0.04 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8602-03 | 2026-06-18 | 0.03 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8602-03 | 2026-06-18 | 0.03 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8602-03 | 2026-06-18 | 0.02 | 10 | 0.02 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8602-03 | 2026-06-19 | 0.02 | 10 | 0.03 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8602-03 | 2026-06-19 | 0.01 | 10 | 0.02 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 8602-03 | 2026-06-19 | 0.02 | 10 | 0.02 | Arecibo | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 8701-03 | 2026-06-30 | 0.03 | 10 | 0.04 | Ciales | PIS (Perfect Integrated Solutions) | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 8801-03 | 2026-06-17 | 0.03 | 10 | 0.03 | Morovis | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9001-02 | 2026-06-22 | 0.04 | 10 | 0.05 | Vega Alta | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9002-03 | 2026-06-23 | 0.03 | 10 | 0.04 | Vega Baja | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9002-03 | 2026-06-24 | 0.02 | 10 | 0.03 | Vega Baja | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9002-03 | 2026-06-15 | 0.05 | 10 | 0.06 | Vega Baja | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9002-03 | 2026-06-15 | 0.05 | 10 | 0.06 | Vega Baja | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9002-03 | 2026-06-15 | 0.05 | 10 | 0.06 | Vega Baja | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9002-03 | 2026-06-20 | 0.02 | 10 | 0.03 | Vega Baja | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9002-03 | 2026-06-24 | 0.03 | 10 | 0.04 | Vega Baja | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9002-03 | 2026-06-24 | 0.03 | 10 | 0.03 | Vega Baja | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9002-03 | 2026-06-18 | 0.04 | 10 | 0.05 | Vega Baja | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9002-03 | 2026-06-18 | 0.04 | 10 | 0.05 | Vega Baja | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9002-03 | 2026-06-19 | 0.02 | 10 | 0.03 | Vega Baja | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9002-03 | 2026-06-20 | 0.04 | 10 | 0.04 | Vega Baja | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9002-03 | 2026-06-16 | 0.03 | 10 | 0.04 | Vega Baja | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9002-03 | 2026-06-24 | 0.03 | 10 | 0.04 | Vega Baja | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9002-03 | 2026-06-26 | 0.03 | 10 | 0.03 | Vega Baja | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9002-03 | 2026-06-24 | 0.02 | 10 | 0.03 | Vega Baja | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9002-03 | 2026-06-24 | 0.02 | 10 | 0.03 | Vega Baja | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9002-03 | 2026-06-20 | 0.03 | 10 | 0.03 | Vega Baja | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9003-06 | 2026-06-11 | 0.03 | 10 | 0.04 | Vega Baja | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9003-06 | 2026-06-09 | 0.03 | 10 | 0.04 | Vega Baja | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9003-06 | 2026-06-09 | 0.03 | 10 | 0.03 | Vega Baja | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9003-06 | 2026-06-09 | 0.03 | 10 | 0.04 | Vega Baja | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9003-06 | 2026-06-09 | 0.02 | 10 | 0.03 | Vega Baja | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9003-06 | 2026-06-12 | 0.03 | 10 | 0.03 | Vega Baja | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9003-06 | 2026-06-13 | 0.03 | 10 | 0.04 | Vega Baja | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9003-06 | 2026-06-11 | 0.04 | 10 | 0.05 | Vega Baja | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 9004-08 | 2026-06-05 | 0.03 | 10 | 0.04 | Vega Baja | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9101-04 | 2026-06-03 | 0.04 | 10 | 0.05 | Vega Alta | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9101-04 | 2026-06-03 | 0.04 | 10 | 0.05 | Vega Alta | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9101-04 | 2026-06-03 | 0.05 | 10 | 0.06 | Vega Alta | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
750065 | 4.80/8.32 | 9103-01 | 2026-06-10 | 0.37 | 10 | 0.44 | Dorado | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
N/A | 7.62/13.20 | 9105-06 | 2026-06-26 | 0.03 | 10 | 0.04 | Dorado | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9201-02 | 2026-06-29 | 0.06 | 10 | 0.07 | Vega Alta | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9201-02 | 2026-06-29 | 0.01 | 10 | 0.01 | Vega Alta | Xperts | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9203-02 | 2026-06-02 | 0.04 | 10 | 0.05 | Toa Baja | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9203-02 | 2026-06-02 | 0.06 | 10 | 0.08 | Toa Baja | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9203-02 | 2026-06-02 | 0.04 | 10 | 0.05 | Toa Baja | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9203-02 | 2026-06-02 | 0.04 | 10 | 0.05 | Toa Baja | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9203-02 | 2026-06-03 | 0.05 | 10 | 0.06 | Toa Baja | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9203-02 | 2026-06-03 | 0.05 | 10 | 0.06 | Toa Baja | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9203-02 | 2026-06-03 | 0.05 | 10 | 0.06 | Toa Baja | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9203-02 | 2026-06-09 | 0.05 | 10 | 0.06 | Toa Baja | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9203-02 | 2026-06-09 | 0.05 | 10 | 0.06 | Toa Baja | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9203-02 | 2026-06-09 | 0.05 | 10 | 0.06 | Toa Baja | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9203-02 | 2026-06-09 | 0.05 | 10 | 0.06 | Toa Baja | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9203-04 | 2026-06-10 | 0.03 | 10 | 0.03 | Dorado | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 9207-08 | 2026-06-11 | 0.01 | 10 | 0.02 | Toa Alta | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 9207-08 | 2026-06-11 | 0.03 | 10 | 0.04 | Toa Alta | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 9207-08 | 2026-06-12 | 0.03 | 10 | 0.04 | Toa Alta | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 9207-08 | 2026-06-12 | 0.03 | 10 | 0.04 | Toa Alta | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 9207-08 | 2026-06-12 | 0.03 | 10 | 0.04 | Toa Baja | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 9207-08 | 2026-06-18 | 0.03 | 10 | 0.04 | Toa Baja | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 9207-08 | 2026-06-23 | 0.03 | 10 | 0.04 | Toa Baja | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 9403-01 | 2026-06-11 | 0.13 | 10 | 0.15 | Toa Alta | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 9403-01 | 2026-06-11 | 0.08 | 10 | 0.09 | Toa Alta | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 2.40/4.16 | 9403-02 | 2026-06-24 | 0.03 | 10 | 0.04 | Toa Alta | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 9405-05 | 2026-06-20 | 0.03 | 10 | 0.04 | Toa Alta | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 9405-05 | 2026-06-29 | 0.02 | 10 | 0.03 | Toa Alta | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 9405-05 | 2026-06-26 | 0.03 | 10 | 0.03 | Toa Alta | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 9405-05 | 2026-06-27 | 0.03 | 10 | 0.03 | Toa Alta | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 7.62/13.20 | 9405-05 | 2026-06-24 | 0.03 | 10 | 0.03 | Toa Alta | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9501-01 | 2026-06-05 | 0.03 | 10 | 0.04 | Corozal | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9501-01 | 2026-06-05 | 0.03 | 10 | 0.04 | Corozal | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9501-01 | 2026-06-05 | 0.02 | 10 | 0.03 | Corozal | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9501-01 | 2026-06-05 | 0.03 | 10 | 0.03 | Corozal | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9501-01 | 2026-06-05 | 0.04 | 10 | 0.05 | Corozal | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9501-01 | 2026-06-08 | 0.04 | 10 | 0.05 | Corozal | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9501-02 | 2026-06-01 | 0.05 | 10 | 0.06 | Corozal | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9501-02 | 2026-06-01 | 0.04 | 10 | 0.05 | Corozal | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9602-04 | 2026-06-02 | 0.04 | 10 | 0.04 | Barranquitas | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9902-01 | 2026-06-25 | 0.05 | 10 | 0.05 | Orocovis | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9902-01 | 2026-06-25 | 0.03 | 10 | 0.04 | Orocovis | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9902-02 | 2026-06-03 | 0.06 | 10 | 0.08 | Orocovis | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9902-02 | 2026-06-05 | 0.04 | 10 | 0.05 | Orocovis | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9902-02 | 2026-06-05 | 0.03 | 10 | 0.03 | Orocovis | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9902-02 | 2026-06-05 | 0.04 | 10 | 0.05 | Orocovis | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9902-02 | 2026-06-05 | 0.03 | 10 | 0.04 | Orocovis | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9902-02 | 2026-06-05 | 0.05 | 10 | 0.06 | Orocovis | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9902-02 | 2026-06-17 | 0.06 | 10 | 0.07 | Orocovis | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9902-02 | 2026-06-09 | 0.03 | 10 | 0.04 | Orocovis | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9902-02 | 2026-06-09 | 0.02 | 10 | 0.03 | Orocovis | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9902-02 | 2026-06-12 | 0.05 | 10 | 0.06 | Orocovis | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9902-02 | 2026-06-12 | 0.03 | 10 | 0.04 | Orocovis | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9902-02 | 2026-06-11 | 0.01 | 10 | 0.01 | Orocovis | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9902-02 | 2026-06-09 | 0.02 | 10 | 0.02 | Orocovis | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9902-02 | 2026-06-09 | 0.03 | 10 | 0.03 | Orocovis | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9902-02 | 2026-06-09 | 0.01 | 10 | 0.01 | Orocovis | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9902-02 | 2026-06-16 | 0.02 | 10 | 0.03 | Orocovis | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9902-02 | 2026-06-16 | 0.03 | 10 | 0.03 | Orocovis | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9902-02 | 2026-06-16 | 0.02 | 10 | 0.02 | Orocovis | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9902-02 | 2026-06-17 | 0.02 | 10 | 0.03 | Orocovis | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9902-02 | 2026-06-27 | 0.05 | 10 | 0.06 | Orocovis | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
N/A | 4.80/8.32 | 9902-02 | 2026-06-30 | 0.1 | 10 | 0.13 | Orocovis | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
727692 | 4.80/8.32 | 3009-04 | 2026-06-01 | 0.06 | 10 | 0.07 | Caguas | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3601-01 | 2026-06-01 | 0.06 | 10 | 0.07 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750067 | 7.62/13.20 | 8014-06 | 2026-06-01 | 0.33 | 10 | 0.4 | Arecibo | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750067 | 4.80/8.32 | 9103-04 | 2026-06-01 | 0.18 | 10 | 0.22 | Vega Alta | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
727572 | 2.40/4.16 | 1705-02 | 2026-06-02 | 0.02 | 10 | 0.02 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
727692 | 4.80/8.32 | 3009-04 | 2026-06-02 | 0.07 | 10 | 0.08 | Caguas | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3601-03 | 2026-06-02 | 0.07 | 10 | 0.08 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3603-02 | 2026-06-02 | 0.06 | 10 | 0.07 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750067 | 7.62/13.20 | 8014-06 | 2026-06-02 | 0.11 | 10 | 0.13 | Arecibo | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750067 | 4.80/8.32 | 9103-04 | 2026-06-02 | 0.17 | 10 | 0.21 | Vega Alta | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
727572 | 2.40/4.16 | 1705-02 | 2026-06-03 | 0.02 | 10 | 0.02 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
727692 | 4.80/8.32 | 3009-04 | 2026-06-03 | 0.01 | 10 | 0.01 | Caguas | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3601-01 | 2026-06-03 | 0.03 | 10 | 0.04 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3603-02 | 2026-06-03 | 0.03 | 10 | 0.04 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750067 | 7.62/13.20 | 8014-06 | 2026-06-03 | 0.18 | 10 | 0.22 | Arecibo | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750067 | 4.80/8.32 | 9103-04 | 2026-06-03 | 0.05 | 10 | 0.06 | Vega Alta | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3603-02 | 2026-06-04 | 0.04 | 10 | 0.05 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750067 | 7.62/13.20 | 8014-06 | 2026-06-04 | 0.15 | 10 | 0.18 | Arecibo | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750067 | 4.80/8.32 | 9103-04 | 2026-06-04 | 0.23 | 10 | 0.28 | Vega Alta | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
727572 | 2.40/4.16 | 1705-02 | 2026-06-05 | 0.15 | 10 | 0.18 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3603-02 | 2026-06-05 | 0.04 | 10 | 0.05 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
727572 | 2.40/4.16 | 1705-02 | 2026-06-08 | 0.02 | 10 | 0.02 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3603-02 | 2026-06-08 | 0.07 | 10 | 0.08 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750067 | 7.62/13.20 | 8014-06 | 2026-06-08 | 0.05 | 10 | 0.06 | Arecibo | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750067 | 4.80/8.32 | 9103-04 | 2026-06-08 | 0.1 | 10 | 0.12 | Vega Alta | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3601-03 | 2026-06-09 | 0.05 | 10 | 0.06 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3603-02 | 2026-06-09 | 0.02 | 10 | 0.02 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750067 | 4.80/8.32 | 9103-04 | 2026-06-09 | 0.06 | 10 | 0.07 | Vega Alta | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3601-01 | 2026-06-10 | 0.03 | 10 | 0.04 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3601-03 | 2026-06-10 | 0.1 | 10 | 0.12 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750067 | 4.80/8.32 | 9103-04 | 2026-06-10 | 0.28 | 10 | 0.34 | Vega Alta | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3601-03 | 2026-06-11 | 0.12 | 10 | 0.15 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750067 | 4.80/8.32 | 9103-04 | 2026-06-11 | 0.23 | 10 | 0.28 | Vega Alta | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 2.40/4.16 | 9405-09 | 2026-06-11 | 0.04 | 10 | 0.05 | Toa Alta | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3601-03 | 2026-06-12 | 0.23 | 10 | 0.28 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750067 | 4.80/8.32 | 9103-04 | 2026-06-12 | 0.04 | 10 | 0.05 | Vega Alta | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 2.40/4.16 | 9405-09 | 2026-06-13 | 0.16 | 10 | 0.19 | Toa Alta | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3601-01 | 2026-06-15 | 0.1 | 10 | 0.12 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3601-03 | 2026-06-15 | 0.12 | 10 | 0.15 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750067 | 2.40/4.16 | 8602-01 | 2026-06-15 | 0.08 | 10 | 0.1 | Florida | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3601-01 | 2026-06-16 | 0.03 | 10 | 0.04 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3601-03 | 2026-06-16 | 0.14 | 10 | 0.17 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3603-01 | 2026-06-16 | 0.03 | 10 | 0.04 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750067 | 2.40/4.16 | 8602-01 | 2026-06-16 | 0.18 | 10 | 0.22 | Florida | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750067 | 4.80/8.32 | 9103-04 | 2026-06-16 | 0.01 | 10 | 0.01 | Vega Alta | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 2.40/4.16 | 9405-09 | 2026-06-16 | 0.15 | 10 | 0.18 | Toa Alta | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
727572 | 4.80/8.32 | 3601-01 | 2026-06-17 | 0.06 | 10 | 0.07 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
727692 | 4.80/8.32 | 3601-03 | 2026-06-17 | 0.02 | 10 | 0.02 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3603-01 | 2026-06-17 | 0.03 | 10 | 0.04 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 2.40/4.16 | 8602-01 | 2026-06-17 | 0.04 | 10 | 0.05 | Florida | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750068 | 4.80/8.32 | 9103-04 | 2026-06-17 | 0.04 | 10 | 0.05 | Vega Alta | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750067 | 2.40/4.16 | 9405-09 | 2026-06-17 | 0.04 | 10 | 0.05 | Toa Alta | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3601-01 | 2026-06-18 | 0.03 | 10 | 0.04 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3602-01 | 2026-06-18 | 0.08 | 10 | 0.1 | Cayey | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3603-01 | 2026-06-18 | 0.07 | 10 | 0.08 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3701-01 | 2026-06-18 | 0.03 | 10 | 0.04 | Aguas Buenas | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750067 | 2.40/4.16 | 8602-01 | 2026-06-18 | 0.21 | 10 | 0.25 | Florida | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 2.40/4.16 | 9405-09 | 2026-06-18 | 0.23 | 10 | 0.28 | Toa Alta | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3601-01 | 2026-06-19 | 0.06 | 10 | 0.07 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3601-03 | 2026-06-19 | 0.05 | 10 | 0.06 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3602-01 | 2026-06-19 | 0.08 | 10 | 0.1 | Cayey | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3603-01 | 2026-06-19 | 0.04 | 10 | 0.05 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3701-01 | 2026-06-19 | 0.04 | 10 | 0.05 | Aguas Buenas | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
727572 | 7.62/13.20 | 1801-01 | 2026-06-22 | 0.13 | 10 | 0.16 | Catano | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3601-01 | 2026-06-22 | 0.02 | 10 | 0.02 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3601-03 | 2026-06-22 | 0.29 | 10 | 0.35 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3602-01 | 2026-06-22 | 0.05 | 10 | 0.06 | Cayey | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3701-01 | 2026-06-22 | 0.02 | 10 | 0.02 | Aguas Buenas | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 2.40/4.16 | 9405-09 | 2026-06-22 | 0.11 | 10 | 0.13 | Toa Alta | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
727572 | 2.40/4.16 | 1708-05 | 2026-06-23 | 0.08 | 10 | 0.1 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
727572 | 7.62/13.20 | 1801-01 | 2026-06-23 | 0.05 | 10 | 0.06 | Catano | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3601-01 | 2026-06-23 | 0.06 | 10 | 0.07 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3602-01 | 2026-06-23 | 0.03 | 10 | 0.04 | Cayey | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3603-01 | 2026-06-23 | 0.04 | 10 | 0.05 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3603-02 | 2026-06-23 | 0.02 | 10 | 0.02 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750067 | 2.40/4.16 | 8011-01 | 2026-06-23 | 0.03 | 10 | 0.04 | Arecibo | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750067 | 2.40/4.16 | 8602-01 | 2026-06-23 | 0.06 | 10 | 0.07 | Florida | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 2.40/4.16 | 9405-09 | 2026-06-23 | 0.13 | 10 | 0.16 | Toa Alta | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
727572 | 2.40/4.16 | 1708-05 | 2026-06-24 | 0.03 | 10 | 0.04 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
727572 | 7.62/13.20 | 1801-01 | 2026-06-24 | 0.08 | 10 | 0.1 | Catano | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3601-03 | 2026-06-24 | 0.01 | 10 | 0.01 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3603-01 | 2026-06-24 | 0.06 | 10 | 0.07 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750067 | 2.40/4.16 | 8011-01 | 2026-06-24 | 0.13 | 10 | 0.16 | Arecibo | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750067 | 2.40/4.16 | 8602-01 | 2026-06-24 | 0.14 | 10 | 0.17 | Florida | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 2.40/4.16 | 9405-09 | 2026-06-24 | 0.02 | 10 | 0.02 | Toa Alta | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
723883 | 2.40/4.16 | 1602-05 | 2026-06-25 | 0.03 | 10 | 0.04 | Carolina | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
727572 | 7.62/13.20 | 1801-01 | 2026-06-25 | 0.07 | 10 | 0.08 | Catano | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3601-01 | 2026-06-25 | 0.14 | 10 | 0.17 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3602-01 | 2026-06-25 | 0.12 | 10 | 0.15 | Cayey | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3701-01 | 2026-06-25 | 0.04 | 10 | 0.05 | Aguas Buenas | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750067 | 2.40/4.16 | 8011-01 | 2026-06-25 | 0.03 | 10 | 0.04 | Arecibo | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750067 | 2.40/4.16 | 8602-01 | 2026-06-25 | 0.16 | 10 | 0.19 | Florida | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 2.40/4.16 | 9405-09 | 2026-06-25 | 0.15 | 10 | 0.18 | Toa Alta | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3601-01 | 2026-06-26 | 0.03 | 10 | 0.04 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3602-01 | 2026-06-26 | 0.03 | 10 | 0.04 | Cayey | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750067 | 2.40/4.16 | 8011-01 | 2026-06-26 | 0.12 | 10 | 0.15 | Arecibo | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750067 | 2.40/4.16 | 8602-01 | 2026-06-26 | 0.19 | 10 | 0.23 | Florida | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 2.40/4.16 | 9405-09 | 2026-06-26 | 0.12 | 10 | 0.15 | Toa Alta | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
727572 | 2.40/4.16 | 1708-05 | 2026-06-29 | 0.05 | 10 | 0.06 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
727572 | 7.62/13.20 | 1801-01 | 2026-06-29 | 0.03 | 10 | 0.04 | Catano | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3601-01 | 2026-06-29 | 0.11 | 10 | 0.13 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3601-03 | 2026-06-29 | 0.08 | 10 | 0.1 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3603-01 | 2026-06-29 | 0.03 | 10 | 0.04 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750067 | 2.40/4.16 | 8602-01 | 2026-06-29 | 0.16 | 10 | 0.19 | Florida | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
727572 | 2.40/4.16 | 1708-04 | 2026-06-30 | 0.02 | 10 | 0.02 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
727692 | 4.80/8.32 | 3009-04 | 2026-06-30 | 0.06 | 10 | 0.07 | Caguas | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3601-01 | 2026-06-30 | 0.43 | 10 | 0.52 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3601-03 | 2026-06-30 | 0.02 | 10 | 0.02 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750068 | 2.40/4.16 | 7503-02 | 2026-06-30 | 0.06 | 10 | 0.07 | Isabela | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750067 | 2.40/4.16 | 8602-01 | 2026-06-30 | 0.19 | 10 | 0.23 | Florida | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 2.40/4.16 | 9405-09 | 2026-06-30 | 0.12 | 10 | 0.15 | Toa Alta | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 2.40/4.16 | 1734-01 | 2026-06-01 | 0.54 | 10 | 0.65 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 2.40/4.16 | 1734-02 | 2026-06-01 | 0.1 | 10 | 0.12 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3602-01 | 2026-06-01 | 0.22 | 10 | 0.27 | Cayey | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3701-01 | 2026-06-01 | 1.82 | 10 | 2.21 | Aguas Buenas | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3701-02 | 2026-06-01 | 0.26 | 10 | 0.32 | Aguas Buenas | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750067 | 2.40/4.16 | 8011-01 | 2026-06-01 | 0.33 | 10 | 0.4 | Arecibo | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 2.40/4.16 | 1734-01 | 2026-06-02 | 0.28 | 10 | 0.33 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 2.40/4.16 | 1734-02 | 2026-06-02 | 0.4 | 10 | 0.49 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3701-03 | 2026-06-02 | 2.32 | 10 | 2.82 | Aguas Buenas | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750067 | 2.40/4.16 | 8011-01 | 2026-06-02 | 0.7 | 10 | 0.85 | Arecibo | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 2.40/4.16 | 1734-02 | 2026-06-03 | 0.19 | 10 | 0.24 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3701-03 | 2026-06-03 | 2.31 | 10 | 2.8 | Aguas Buenas | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750067 | 4.80/8.32 | 8701-01 | 2026-06-03 | 1.01 | 10 | 1.22 | Ciales | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 2.40/4.16 | 1734-01 | 2026-06-04 | 0.09 | 10 | 0.11 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 2.40/4.16 | 1734-02 | 2026-06-04 | 0.06 | 10 | 0.07 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3701-03 | 2026-06-04 | 0.03 | 10 | 0.03 | Aguas Buenas | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750067 | 4.80/8.32 | 8701-01 | 2026-06-04 | 1.72 | 10 | 2.09 | Ciales | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 2.40/4.16 | 1734-02 | 2026-06-05 | 0.04 | 10 | 0.04 | Bayamon | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3701-03 | 2026-06-05 | 1.3 | 10 | 1.57 | Aguas Buenas | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
727572 | 7.62/13.20 | 1806-01 | 2026-06-08 | 0.003 | 10 | 0.003 | Toa Baja | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3601-04 | 2026-06-08 | 0.04 | 10 | 0.05 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3701-03 | 2026-06-08 | 0.82 | 10 | 1 | Aguas Buenas | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750067 | 4.80/8.32 | 8701-01 | 2026-06-08 | 2.53 | 10 | 3.07 | Ciales | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3601-04 | 2026-06-09 | 0.08 | 10 | 0.1 | Cidra | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3701-03 | 2026-06-09 | 1.24 | 10 | 1.51 | Aguas Buenas | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750067 | 4.80/8.32 | 8701-01 | 2026-06-09 | 1.55 | 10 | 1.87 | Ciales | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3701-03 | 2026-06-10 | 0.71 | 10 | 0.85 | Aguas Buenas | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750067 | 4.80/8.32 | 8701-01 | 2026-06-10 | 0.43 | 10 | 0.52 | Ciales | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9103-01 | 2026-06-11 | 0.9 | 10 | 1.09 | Dorado | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9202-01 | 2026-06-10 | 0.08 | 10 | 0.1 | Dorado | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9203-04 | 2026-06-10 | 1.27 | 10 | 1.54 | Dorado | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 2.40/4.16 | 9401-03 | 2026-06-10 | 0.03 | 10 | 0.03 | Toa Alta | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 2.40/4.16 | 9403-01 | 2026-06-10 | 0.14 | 10 | 0.18 | Toa Alta | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 2.40/4.16 | 9404-01 | 2026-06-10 | 0.1 | 10 | 0.12 | Dorado | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9501-03 | 2026-06-10 | 0.46 | 10 | 0.55 | Morovis | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9502-01 | 2026-06-10 | 0.55 | 10 | 0.67 | Corozal | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9502-03 | 2026-06-10 | 0.31 | 10 | 0.38 | Corozal | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3701-03 | 2026-06-11 | 2.35 | 10 | 2.85 | Aguas Buenas | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750067 | 4.80/8.32 | 8701-01 | 2026-06-11 | 0.32 | 10 | 0.39 | Ciales | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9103-01 | 2026-06-15 | 0.58 | 10 | 0.71 | Dorado | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9202-01 | 2026-06-11 | 0.16 | 10 | 0.19 | Dorado | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9203-04 | 2026-06-11 | 1.12 | 10 | 1.36 | Dorado | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 2.40/4.16 | 9403-01 | 2026-06-11 | 0.48 | 10 | 0.58 | Toa Alta | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 2.40/4.16 | 9404-01 | 2026-06-11 | 0.29 | 10 | 0.35 | Dorado | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9501-03 | 2026-06-11 | 0.88 | 10 | 1.07 | Morovis | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9502-01 | 2026-06-11 | 0.72 | 10 | 0.87 | Corozal | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9502-03 | 2026-06-11 | 0.3 | 10 | 0.36 | Corozal | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3701-03 | 2026-06-12 | 2.79 | 10 | 3.38 | Aguas Buenas | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9202-01 | 2026-06-12 | 0.28 | 10 | 0.34 | Dorado | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 2.40/4.16 | 9401-01 | 2026-06-12 | 0.13 | 10 | 0.16 | Toa Alta | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 2.40/4.16 | 9404-01 | 2026-06-12 | 0.14 | 10 | 0.17 | Dorado | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9501-03 | 2026-06-12 | 0.53 | 10 | 0.64 | Morovis | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9502-03 | 2026-06-12 | 0.41 | 10 | 0.49 | Corozal | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3701-03 | 2026-06-15 | 1.13 | 10 | 1.37 | Aguas Buenas | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750067 | 4.80/8.32 | 8701-01 | 2026-06-15 | 0.09 | 10 | 0.1 | Ciales | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
727572 | 4.80/8.32 | 9103-01 | 2026-06-16 | 0.14 | 10 | 0.17 | Dorado | LUMA | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9203-04 | 2026-06-15 | 1.61 | 10 | 1.96 | Dorado | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 2.40/4.16 | 9403-01 | 2026-06-15 | 0.41 | 10 | 0.5 | Toa Alta | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9501-01 | 2026-06-15 | 0.53 | 10 | 0.64 | Corozal | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9502-01 | 2026-06-15 | 0.41 | 10 | 0.49 | Corozal | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
727572 | 2.40/4.16 | 1707-05 | 2026-06-16 | 0.1 | 10 | 0.12 | Bayamon | LUMA | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
727572 | 7.62/13.20 | 1717-04 | 2026-06-16 | 0.08 | 10 | 0.1 | Bayamon | LUMA | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3701-03 | 2026-06-16 | 1.6 | 10 | 1.94 | Aguas Buenas | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750067 | 4.80/8.32 | 8701-01 | 2026-06-16 | 1.07 | 10 | 1.3 | Ciales | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9103-01 | 2026-06-16 | 0.46 | 10 | 0.56 | Dorado | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9103-01 | 2026-06-17 | 0.94 | 10 | 1.14 | Dorado | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9203-04 | 2026-06-16 | 0.3 | 10 | 0.36 | Dorado | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 2.40/4.16 | 9401-01 | 2026-06-16 | 0.21 | 10 | 0.25 | Toa Alta | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 2.40/4.16 | 9403-01 | 2026-06-16 | 0.53 | 10 | 0.64 | Toa Alta | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 2.40/4.16 | 9404-01 | 2026-06-16 | 0.1 | 10 | 0.12 | Dorado | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9501-01 | 2026-06-16 | 1.4 | 10 | 1.7 | Corozal | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9501-03 | 2026-06-16 | 0.39 | 10 | 0.47 | Morovis | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9502-01 | 2026-06-16 | 0.33 | 10 | 0.4 | Corozal | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9502-03 | 2026-06-16 | 0.55 | 10 | 0.66 | Corozal | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3701-03 | 2026-06-17 | 1.08 | 10 | 1.31 | Aguas Buenas | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750068 | 2.40/4.16 | 6001-03 | 2026-06-17 | 0.04 | 10 | 0.05 | Mayagüez | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750068 | 2.40/4.16 | 6101-03 | 2026-06-17 | 0.41 | 10 | 0.5 | Anasco | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750067 | 4.80/8.32 | 8701-01 | 2026-06-17 | 0.61 | 10 | 0.74 | Ciales | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9103-01 | 2026-06-18 | 0.73 | 10 | 0.89 | Dorado | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
727572 | 4.80/8.32 | 9202-01 | 2026-06-17 | 0.02 | 10 | 0.03 | Dorado | LUMA | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
727572 | 4.80/8.32 | 9203-04 | 2026-06-17 | 0.06 | 10 | 0.07 | Dorado | LUMA | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9203-04 | 2026-06-17 | 0.34 | 10 | 0.41 | Dorado | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 2.40/4.16 | 9401-01 | 2026-06-17 | 0.13 | 10 | 0.15 | Toa Alta | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 2.40/4.16 | 9403-01 | 2026-06-17 | 0.29 | 10 | 0.35 | Toa Alta | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9501-01 | 2026-06-17 | 0.83 | 10 | 1.01 | Corozal | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9501-03 | 2026-06-17 | 0.6 | 10 | 0.73 | Morovis | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9502-01 | 2026-06-17 | 0.47 | 10 | 0.57 | Corozal | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9502-03 | 2026-06-17 | 0.18 | 10 | 0.22 | Corozal | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3502-02 | 2026-06-18 | 0.46 | 10 | 0.55 | Aibonito | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750068 | 2.40/4.16 | 6001-03 | 2026-06-18 | 0.15 | 10 | 0.18 | Mayagüez | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750067 | 4.80/8.32 | 8701-01 | 2026-06-18 | 0.04 | 10 | 0.04 | Ciales | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9103-01 | 2026-06-22 | 0.51 | 10 | 0.62 | Dorado | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9203-04 | 2026-06-18 | 0.14 | 10 | 0.16 | Dorado | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 2.40/4.16 | 9401-01 | 2026-06-18 | 0.41 | 10 | 0.5 | Toa Alta | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 2.40/4.16 | 9403-01 | 2026-06-18 | 0.09 | 10 | 0.11 | Toa Alta | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9501-01 | 2026-06-18 | 0.24 | 10 | 0.29 | Corozal | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9501-03 | 2026-06-18 | 0.93 | 10 | 1.13 | Morovis | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9502-03 | 2026-06-18 | 0.33 | 10 | 0.41 | Corozal | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3502-02 | 2026-06-19 | 0.86 | 10 | 1.04 | Aibonito | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750068 | 2.40/4.16 | 6001-03 | 2026-06-19 | 0.19 | 10 | 0.23 | Mayagüez | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 2.40/4.16 | 9401-01 | 2026-06-19 | 1.05 | 10 | 1.27 | Toa Alta | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9501-01 | 2026-06-19 | 0.36 | 10 | 0.44 | Corozal | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9501-03 | 2026-06-19 | 0.73 | 10 | 0.88 | Morovis | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9502-03 | 2026-06-19 | 0.12 | 10 | 0.14 | Corozal | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3502-02 | 2026-06-22 | 1.14 | 10 | 1.39 | Aibonito | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750068 | 2.40/4.16 | 6001-03 | 2026-06-22 | 0.32 | 10 | 0.38 | Mayagüez | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9103-01 | 2026-06-23 | 1.36 | 10 | 1.64 | Dorado | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9501-01 | 2026-06-22 | 0.39 | 10 | 0.47 | Corozal | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9501-02 | 2026-06-22 | 0.54 | 10 | 0.66 | Corozal | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9502-01 | 2026-06-22 | 0.16 | 10 | 0.2 | Corozal | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3502-02 | 2026-06-23 | 1.16 | 10 | 1.41 | Aibonito | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750068 | 2.40/4.16 | 6001-03 | 2026-06-23 | 0.14 | 10 | 0.17 | Mayagüez | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750067 | 4.80/8.32 | 8701-01 | 2026-06-23 | 0.63 | 10 | 0.76 | Ciales | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
N/A | 4.80/8.32 | 9103-01 | 2026-06-24 | 0.03 | 10 | 0.03 | Dorado | Wright Tree Services | In Progress | Veg Request | Ian Kreher | O&M / Rate Payer | June | Q4 | FY2026
750065 | 2.40/4.16 | 9401-01 | 2026-06-23 | 0.6 | 10 | 0.72 | Toa Alta | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9501-01 | 2026-06-23 | 0.3 | 10 | 0.36 | Corozal | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9501-02 | 2026-06-23 | 0.56 | 10 | 0.68 | Corozal | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9501-03 | 2026-06-23 | 1.03 | 10 | 1.25 | Morovis | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9502-01 | 2026-06-23 | 0.11 | 10 | 0.13 | Corozal | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9502-03 | 2026-06-23 | 0.19 | 10 | 0.23 | Corozal | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3502-02 | 2026-06-24 | 1.48 | 10 | 1.8 | Aibonito | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750068 | 2.40/4.16 | 6201-01 | 2026-06-24 | 0.01 | 10 | 0.02 | Las Marias | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750067 | 4.80/8.32 | 8701-01 | 2026-06-24 | 0.24 | 10 | 0.29 | Ciales | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9103-01 | 2026-06-24 | 0.84 | 10 | 1.02 | Dorado | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 2.40/4.16 | 9401-01 | 2026-06-24 | 0.35 | 10 | 0.42 | Toa Alta | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9501-01 | 2026-06-24 | 0.68 | 10 | 0.83 | Corozal | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9501-02 | 2026-06-24 | 0.28 | 10 | 0.34 | Corozal | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9501-03 | 2026-06-24 | 0.29 | 10 | 0.35 | Morovis | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9502-01 | 2026-06-24 | 0.27 | 10 | 0.33 | Corozal | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9502-03 | 2026-06-24 | 0.08 | 10 | 0.1 | Corozal | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
727572 | 2.40/4.16 | 1703-04 | 2026-06-25 | 0.002 | 10 | 0.002 | Bayamon | LUMA | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
727572 | 7.62/13.20 | 1713-05 | 2026-06-25 | 0.003 | 10 | 0.004 | Bayamon | LUMA | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3502-02 | 2026-06-25 | 0.37 | 10 | 0.45 | Aibonito | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750068 | 2.40/4.16 | 6201-01 | 2026-06-25 | 0.68 | 10 | 0.83 | Las Marias | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750067 | 4.80/8.32 | 8701-01 | 2026-06-25 | 0.2 | 10 | 0.24 | Ciales | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9103-01 | 2026-06-25 | 0.06 | 10 | 0.07 | Dorado | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9203-04 | 2026-06-25 | 0.06 | 10 | 0.07 | Dorado | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 2.40/4.16 | 9403-01 | 2026-06-25 | 0.02 | 10 | 0.03 | Toa Alta | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 2.40/4.16 | 9404-01 | 2026-06-25 | 0.04 | 10 | 0.05 | Dorado | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9501-01 | 2026-06-25 | 0.66 | 10 | 0.8 | Corozal | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9501-02 | 2026-06-25 | 0.14 | 10 | 0.16 | Corozal | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9501-03 | 2026-06-25 | 0.13 | 10 | 0.15 | Morovis | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9502-01 | 2026-06-25 | 0.05 | 10 | 0.05 | Corozal | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9502-03 | 2026-06-25 | 0.05 | 10 | 0.06 | Corozal | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3502-02 | 2026-06-26 | 0.22 | 10 | 0.27 | Aibonito | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750068 | 2.40/4.16 | 6201-01 | 2026-06-26 | 0.18 | 10 | 0.22 | Las Marias | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750067 | 4.80/8.32 | 8701-01 | 2026-06-26 | 0.55 | 10 | 0.67 | Ciales | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 2.40/4.16 | 9401-01 | 2026-06-26 | 0.63 | 10 | 0.77 | Toa Alta | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9501-01 | 2026-06-26 | 0.15 | 10 | 0.18 | Corozal | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9501-03 | 2026-06-26 | 0.22 | 10 | 0.27 | Morovis | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9502-03 | 2026-06-26 | 0.22 | 10 | 0.27 | Corozal | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3502-02 | 2026-06-29 | 0.21 | 10 | 0.25 | Aibonito | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750068 | 2.40/4.16 | 6201-01 | 2026-06-29 | 0.02 | 10 | 0.02 | Las Marias | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750067 | 4.80/8.32 | 8701-01 | 2026-06-29 | 0.11 | 10 | 0.13 | Ciales | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9103-01 | 2026-06-29 | 0.53 | 10 | 0.65 | Dorado | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9501-01 | 2026-06-29 | 0.14 | 10 | 0.17 | Corozal | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9501-02 | 2026-06-29 | 0.52 | 10 | 0.63 | Corozal | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9502-01 | 2026-06-29 | 0.23 | 10 | 0.28 | Corozal | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9802-04 | 2026-06-29 | 0.05 | 10 | 0.06 | Naranjito | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
727572 | 2.40/4.16 | 1704-02 | 2026-06-30 | 0.003 | 10 | 0.004 | Bayamon | LUMA | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
727572 | 7.62/13.20 | 1710-03 | 2026-06-30 | 0.01 | 10 | 0.02 | Bayamon | LUMA | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
727572 | 7.62/13.20 | 1710-05 | 2026-06-30 | 0.03 | 10 | 0.04 | Toa Alta | LUMA | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
727572 | 7.62/13.20 | 1717-04 | 2026-06-30 | 0.01 | 10 | 0.01 | Bayamon | LUMA | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750066 | 4.80/8.32 | 3502-02 | 2026-06-30 | 1.04 | 10 | 1.26 | Aibonito | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750068 | 2.40/4.16 | 6201-01 | 2026-06-30 | 0.11 | 10 | 0.13 | Las Marias | Ceres | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750067 | 4.80/8.32 | 8701-01 | 2026-06-30 | 0.32 | 10 | 0.39 | Ciales | Asplundh Tree Experts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9103-01 | 2026-06-30 | 0.25 | 10 | 0.3 | Dorado | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 2.40/4.16 | 9401-01 | 2026-06-30 | 0.33 | 10 | 0.39 | Toa Alta | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9501-01 | 2026-06-30 | 0.34 | 10 | 0.41 | Corozal | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9501-02 | 2026-06-30 | 0.21 | 10 | 0.25 | Corozal | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9501-03 | 2026-06-30 | 0.57 | 10 | 0.69 | Morovis | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9502-03 | 2026-06-30 | 0.19 | 10 | 0.23 | Corozal | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026
750065 | 4.80/8.32 | 9802-04 | 2026-06-30 | 0.3 | 10 | 0.37 | Naranjito | Xperts | In Progress | Federally Funded Clearing | Ian Kreher | Federal Funds | June | Q4 | FY2026

## FEMA Vegetation Projects
FEMA Vegetation Projects
As of June 30, 2026
Project FAASt # | FEMA EMMIE P/W # | kV Level | Project Title | FEMA Review as of 7/7/26 | Phase at FEMA as of 7/7/26 | Date Project Submitted to FEMA | Last Date Obligated | LUMA Miles Submitted | FEMA Miles Approved and Obligated/to be Obligated | FEMA Percentage Approved | LUMA Submitted Cost & additional cost if Amended | FEMA Net Cost for all Project Versions | Percentage of Costs Obligated | FEMA Federal Share (amount LUMA will get from the FEMA Net Cost) | Non-Federal Share | Amount Spent (as of 5/13/2026 Finance report) | Amount Submitted for Reimbursement | Amount Reimbursed | Miles Assessed | Percentage of Miles Assessed | Assessment Vendor Assigned | Miles Cleared | Percentage of Miles Cleared | Vendors Assigned to Miles Cleared | If the vendor is not active, explain why (e.g., insurance, procurement, contracts or other similar issues)
956349 | 108157 | 115 kV | FAASt [San Juan Region 1 Line 36800 (115kV) – Canovanas TC to Palmer TC] (Vegetation) - Version 0/1 | IN FEMA review - Amendment | Pending EHP Review | 2025-12-12 | 2025-09-17 | 11.13 | 6.59 | 59.21% | 4685447.53 | 2077241.3 | 44.33% | 1869517.17 | 207724.13 | 554673.7 |  |  | 6.59 | 100% | Ceres | 5.22 | 68.59% | Ceres
727608 | 107899 | 115 kV | FAASt [Region 1 San Juan TL - 115kV] (Vegetation) | Obligated | Obligated | 2024-11-27 | 2026-03-01 | 74.48 | 14.13 | 18.97% | 27445152.25 | 4453902.63 | 16.23% | 4008512.37 | 445390.26 | 92943.52 |  |  | 0 | 0% |  | 0 | 0%
727659 | 107901 | 115 kV | FAASt [Region 2 Arecibo TL - 115kV] (Vegetation) | Obligated | Obligated | 2024-11-27 | 2026-03-01 | 53.2 | 13.37 | 25.13% | 19581632.93 | 4214343.82 | 21.52% | 3792909.44 | 421434.38 | 124595.89 |  |  | 0 | 0% |  | 0 | 0%
727522 | 107892 | 115 kV | FAASt [Region 3 Bayamon TL - 115kV] (Vegetation) | Obligated | Obligated | 2024-11-27 | 2026-03-01 | 52.93 | 10.92 | 20.63% | 19467722.13 | 3442081.85 | 17.68% | 3097873.67 | 344208.18 | 32232.81 |  |  | 0 | 0% |  | 0 | 0%
727606 | 107898 | 115 kV | FAASt [Region 4 Caguas TL - 115kV] (Vegetation) | Obligated | Obligated | 2024-11-27 | 2026-03-01 | 87.14 | 12.63 | 14.49% | 32019956.72 | 3981089.18 | 12.43% | 3582980.27 | 398108.91 | 69569.41 |  |  | 0 | 0% |  | 0 | 0%
727657 | 107900 | 115 kV | FAASt [Region 5 Mayaguez TL - 115kV] (Vegetation) | Obligated | Obligated | 2024-11-27 | 2026-03-01 | 62.36 | 8.1 | 12.99% | 22914442.28 | 2553192.59 | 11.14% | 2297873.34 | 255319.25 | 4867.73 |  |  | 0 | 0% |  | 0 | 0%
956357 | 108160 | 38 kV | FAASt [Mayaguez Region 5 Line 1900 (38kV) – Dos Bocas HP to San Sebastian TC] (Vegetation) | Obligated | Obligated | 2025-06-26 | 2026-06-12 | 22.35 | 9.21 | 41% | 12705648.38 | 1692783.13 | 13.32% | 1523504.82 | 169278.31 | 1630.89 |  |  | 0 | 0% |  | 0 | 0%
727529 | 107893 | 115 kV | FAASt [Region 6 Ponce TL - 115kV] (Vegetation) | Obligated | Obligated | 2024-11-27 | 2026-03-01 | 156 | 26.35 | 16.93% | 57429412.88 | 8305756.13 | 14.46% | 7475180.52 | 830575.61 | 19458.35 |  |  | 0 | 0% |  | 0 | 0%
956356 | 108159 | 115 kV | FAASt [Ponce Region 6 Line 39000 (115kV) – Aguas Buenas Substation to Hacienda San Jose] (Vegetation) - Version 0/1 | Obligated | Obligated | 2025-12-05 | 2026-03-01 | 2.82 | 1.24 | 100% | 1019517.55 | 388903.06 | 38.15% | 350012.76 | 38890.3 | 188287.35 |  |  | 1.24 | 100% | Ceres | 1.24 | 100% | Ceres
956343 | 108154 | 38 kV | FAASt [Ponce Region 6 Line 4800 (38kV) – Toro Negro to Aibonito, Santa Isabel] (Vegetation) | Obligated | Obligated | 2025-06-26 | 2026-06-30 | 39.77 | 12.6 | 31.68% | 21381353.56 | 2361582.5 | 11.05% | 2125424.25 | 236158.25 | 1168.25 |  |  | 0 | 0% |  | 0 | 0%
956342 | 108153 | 115 kV | FAASt [Arecibo Region 2 Line 36400 (115Kv) – Ponce TC to Dos Bocas HP] (Vegetation) | Obligated | Obligated | 2025-08-01 | 2025-09-17 | 36.78 | 11.48 | 31.22% | 44397505.59 | 4093248.38 | 9.22% | 3683923.55 | 409324.83 | 7841.89 |  |  | 0.31 | 2.7% |  | 0.06 | 0% |  | All work stopped and will be transitioned to USACE
956353 | 108158 | 115 kV | FAASt [Arecibo Region 2 Line 36100 (115kV) – Dos Bocas HP to Barrio Pina] (Vegetation) | Obligated | Obligated | 2025-08-01 | 2025-09-17 | 30.97 | 10.54 | 34.03% | 37008593.33 | 3756065.08 | 10.15% | 3380458.58 | 375606.5 | 121642.74 |  |  | 19.01 | 100% | Ceres | 1.88 | 17.65% | Ceres
956345 | 108155 | 38 kV | FAASt [Arecibo Region 2 Line 2400 (38kV) – Dos Bocas HP to Caonillas 2] (Vegetation) | Obligated | Obligated | 2025-06-26 | 2026-04-24 | 12.96 | 4.02 | 31.02% | 7324652.18 | 738869.51 | 10.09% | 664982.56 | 73886.95 | 1488.31 |  |  | 3.23 | 10.95% | Ceres | 1.37 | 4.975% | Ceres
956348 | 108156 | 38 kV | FAASt [Bayamon Region 3 Line 10000 (38kV) – Bayamon Pueblo to Magnolia TO] (Vegetation) | Obligated | Obligated | 2025-06-26 | 2026-04-24 | 2.43 | 0.66 | 27.16% | 1019517.55 | 121306.94 | 11.9% | 109176.25 | 12130.69 | 875.71 |  |  | 0 | 0% |  | 0 | 0%
741105 | 107946 | 230 kV | FAASt [All Regions TL - 230kV] (Vegetation) | Obligated | Obligated | 2024-12-13 | 2026-03-01 | 402.54 | 38.21 | 9.49% | 157865400 | 12885805.47 | 8.163% | 11597224.93 | 1288580.54 | 38811.61 |  |  | 0 | 0% |  | 0 | 0%
956330 | 108145 | Distribution | FAASt [Caguas Region 4 - Feeder 3007-03] (Vegetation) | Obligated | Obligated | 2025-06-27 | 2026-06-12 | 60.23 | 59.41 | 98.64% | 7985860.15 | 7595964.6 | 95.12% | 6836368.14 | 759596.46 | 348.82 |  |  | 0 | 0% |  | 0 | 0%
956339 | 108150 | Distribution | FAASt [Caguas Region 4 - Feeder 3301-01] (Vegetation) | Obligated | Obligated | 2025-06-27 | 2026-06-12 | 90.54 | 89.58 | 98.94% | 12004333.95 | 11453400.26 | 95.41% | 10308060.24 | 1145340.02 | 348.82 |  |  | 0 | 0% |  | 0 | 0%
956337 | 108149 | Distribution | FAASt [Mayaguez Region 5 Feeder 6012-02] (Vegetation) | Obligated | Obligated | 2025-06-27 | 2026-06-12 | 55.09 | 42.76 | 77.62% | 7303974.78 | 5467151.1 | 74.85% | 4920435.99 | 546715.11 | 886.83 |  |  | 0 | 0% |  | 0 | 0%
956331 | 108146 | Distribution | FAASt [Mayaguez Region 5 Feeder 6014-02] (Vegetation) | Obligated | Obligated | 2025-06-27 | 2026-06-12 | 60.5 | 56.28 | 93.02% | 8021552.35 | 7195773.23 | 89.71% | 6476195.91 | 719577.32 | 243.23 |  |  | 0 | 0% |  | 0 | 0%
956340 | 108151 | Distribution | FAASt [Ponce Region 6 Feeder 5602-02] (Vegetation) | IN FEMA review | Pending Large Project Review | 2025-06-27 |  | 191.55 | 37.57 | 19.61% | 6589894.87 | 4803574.98 | 72.89% | 4323217.49 | 480357.49 | 298.54 |  |  | 0 | 0% |  | 0 | 0%
956341 | 108152 | Distribution | FAASt [Ponce Region 6 Feeder 5803-02] (Vegetation) | Obligated | Obligated | 2025-06-27 | 2026-05-13 | 0.7366 | 0.73 | 99.1% | 97672.18 | 93335.37 | 95.56% | 84001.84 | 9333.53 | 348.82 |  |  | 0 | 0% |  | 0 | 0%
956335 | 108148 | Distribution | FAASt [San Juan Region 1 - Feeder 2301-02] (Vegetation) | IN FEMA review | Pending Final FEMA Review | 2025-06-27 |  | 56.59 | 55.81 | 98.62% | 7503713.1 | 7135680.6 | 95.1% | 6422112.54 | 713568.06 | 301.68 |  |  | 0 | 0% |  | 0 | 0%
956332 | 108147 | Distribution | FAASt [San Juan Region 1 - Feeder 2401-01] (Vegetation) | IN FEMA review | Pending Large Project Review | 2025-06-27 |  | 85.26 | 82.68 | 96.97% | 11304742.47 | 10571189.26 | 93.51% | 9514070.34 | 1057118.92 | 47.21 |  |  | 0 | 0% |  | 0 | 0%
750063 | 107965 | Distribution | FAASt [Region 6 -Ponce Group A] Low Density (Vegetation) | Obligated | Obligated | 2024-11-22 | 2026-06-30 | 531.21 | 531.21 | 100% | 60044753.52 | 60044753.52 | 100% | 54040278.17 | 6004475.35 | 306361.08 |  |  | 15.06 | 2.835% | Asplundh, Ceres, Xperts | 0 | 0%
750067 | 107968 | Distribution | FAASt [Region 2 -Arecibo Group A] Low Density (Vegetation) | Obligated | Obligated | 2024-11-22 | 2026-03-01 | 502.48 | 502.48 | 100% | 56797288.74 | 56797288.74 | 100% | 51117559.87 | 5679728.87 | 255298.12 |  |  | 105.65 | 21.03% | Asplundh, Ceres | 40.9 | 8.14% | Asplundh
727572 | 11720 | Distribution | FAASt [Region 3 -Bayamon Group A] High Density (Vegetation) | Obligated | Obligated | 2024-11-15 | 2026-03-01 | 376.77 | 376.77 | 100% | 80353343.34 | 42586648.64 | 53% | 38327983.78 | 4258664.86 | 860584.04 |  |  | 170.04 | 45.13% | Xperts | 100 | 26.54% | Xperts
750065 | 107966 | Distribution | FAASt [Region 3 -Bayamon Group A] Low Density (Vegetation) | Obligated | Obligated | 2024-11-22 | 2026-03-01 | 620.82 | 620.82 | 100% | 70173723.91 | 70173723.91 | 100% | 63156351.52 | 7017372.39 | 166440.83 |  |  | 191.39 | 30.83% | Xperts | 59.96 | 9.658% | Xperts
750066 | 107967 | Distribution | FAASt [Region 4 -Caguas Group A] Low Density (Vegetation) | Obligated | Obligated | 2024-11-22 | 2026-03-01 | 951.58 | 951.58 | 100% | 107563717.79 | 107563717.79 | 100% | 96807346.02 | 10756371.77 | 251525.3 |  |  | 155.66 | 16.36% | Ceres | 55.73 | 5.857% | Ceres
750068 | 107969 | Distribution | FAASt [Region 5 -Mayaguez Group A] Low Density (Vegetation) | Obligated | Obligated | 2024-11-22 | 2026-03-01 | 462.71 | 462.71 | 100% | 52301929.37 | 52301929.37 | 100% | 47071736.44 | 5230192.93 | 217179.31 |  |  | 24.29 | 5.25% | Asplundh, Ceres, Xperts | 7.06 | 1.526% | Ceres
723883 | 11696 | Distribution | FAASt [Region 1 -San Juan Group A] (Vegetation) - Version 0 - 2 | Obligated | Obligated | 2025-06-11 | 2026-03-01 | 612.73 | 612.73 | 100% | 24944459.56 | 24944459.56 | 100% | 22450013.61 | 2494445.95 | 20897470.4 | 4371112.5 | 3934001.25 | 508.6 | 83.01% | Asplundh, Ceres, Wright, Xpert | 247.12 | 40.33% | Asplundh, Ceres, Wright, Xperts | Wright withdrew from Federally Funded work in 2025
727531 | 11715 | Distribution | FAASt [Region 6 -Ponce Group A] High Density (Vegetation) | Obligated | Obligated | 2024-11-15 | 2025-04-28 | 199.37 | 199.37 | 100% | 25913934.11 | 25913934.11 | 100% | 23322540.7 | 2591393.41 | 6229319.74 | 1243513.59 |  | 200.5 | 100.6% | Asplundh, Ceres, Xperts | 165.63 | 83.08% | Asplundh, Ceres, Xperts
728832 | 11718 | Distribution | FAASt [Region 5 -Mayaguez Group A] High Density (Vegetation) | Obligated | Obligated | 2024-11-15 | 2025-04-28 | 109.73 | 109.73 | 100% | 14260691.9 | 14260691.9 | 100% | 12834622.71 | 1426069.19 | 3106232.89 | 2006897.66 |  | 106.47 | 97.03% | Ceres | 91.81 | 83.67% | Ceres
727692 | 11724 | Distribution | FAASt [Region 4 -Caguas Group A] High Density (Vegetation) | Obligated | Obligated | 2024-11-15 | 2025-04-28 | 215.82 | 215.82 | 100% | 28052090.37 | 28052090.37 | 100% | 25246881.34 | 2805209.03 | 6908788.7 | 1065863.76 |  | 216.77 | 100.4% | Asplundh, Xperts | 190.97 | 88.49% | Xperts
728827 | 11714 | Distribution | FAASt [Region 2 -Arecibo Group A] High Density (Vegetation) | Obligated | Obligated | 2024-11-15 | 2025-04-28 | 139.99 | 139.99 | 100% | 18194308.81 | 18194308.81 | 100% | 16374877.93 | 1819430.88 | 4037225.54 | 1583575.01 |  | 138.47 | 98.91% | Asplundh, Wright, Ceres | 134.66 | 96.19% | Asplundh, Wright, Ceres | Wright withdrew from Federally Funded work in 2025
1068649 |  | 38 kV | FAASt [Region 6 Ponce 38Kv – Non-Sensitive]/ Former project 740414 (vegetation) | IN FEMA review | Pending Scope & Cost Completion by Applicant | 2026-06-08 |  | 44.55 |  |  | 9664446.2585 | [7 empty] | 0 | 0% |  | 0 | 0%
1068648 |  | 38 kV | FAASt [Region 5 Mayaguez 38Kv – Non-Sensitive]/ Former project 740411 (vegetation) | IN FEMA review | Pending Scope & Cost Completion by Applicant | 2026-06-08 |  | 7.9 |  |  | 1714050.2957 | [7 empty] | 0 | 0% |  | 0 | 0%
1068646 |  | 38 kV | FAASt [Region 4 Caguas 38Kv – Non-Sensitive]/ Former project 740409 (vegetation) | IN FEMA review | Pending Scope & Cost Completion by Applicant | 2026-06-08 |  | 38.87 |  |  | 8650053.2735 | [7 empty] | 0 | 0% |  | 0 | 0%
1068642 |  | 38 kV | FAASt [Region 3 Bayamon 38Kv – Non-Sensitive]/ Former project 740408 (vegetation) | IN FEMA review | Pending Scope & Cost Completion by Applicant | 2026-06-08 |  | 34.74 |  |  | 7529621.5566 | [7 empty] | 0 | 0% |  | 0 | 0%
1068647 |  | 38 kV | FAASt [Region 2 Arecibo 38Kv – Non-Sensitive]/ Former project 740410 (vegetation) | IN FEMA review | Pending Scope & Cost Completion by Applicant | 2026-06-08 |  | 1.19 |  |  | 258146.0574 | [7 empty] | 0 | 0% |  | 0 | 0%
1068640 |  | 38 kV | FAASt [Region 1 San Juan 38Kv – Non-Sensitive]/ Former project 740406 (vegetation) | IN FEMA review | Pending Scope & Cost Completion by Applicant | 2026-06-08 |  | 15.68 |  |  | 3400369.2855 | [7 empty] | 0 | 0% |  | 0 | 0%
Pending FAASt# |  | 38 kV | FAASt [Region 6 Ponce Transmission 38kV sensitive areas] (Vegetation) | Pending Activation |  |  |  | 126.98 |  |  | 27545702.8308 | [7 empty] | 0 | 0% |  | 0 | 0%
Pending FAASt# |  | 38 kV | FAASt [Region 2 Arecibo Transmission 38kV sensitive areas] (Vegetation) | Pending Activation |  |  |  | 102.6917 |  |  | 22276845.8514 | [7 empty] | 0 | 0% |  | 0 | 0%
Pending FAASt# |  | 38 kV | FAASt [Region 3 Bayamon Transmission 38kV sensitive areas] (Vegetation) | Pending Activation |  |  |  | 73.731 |  |  | 15994415.6287 | [7 empty] | 0 | 0% |  | 0 | 0%
Pending FAASt# |  | 38 kV | FAASt [Region 5 Mayaguez Transmission 38kV sensitive areas] (Vegetation) | Pending Activation |  |  |  | 114.45 |  |  | 24827576.697 | [7 empty] | 0 | 0% |  | 0 | 0%
Pending FAASt# |  | 38 kV | FAASt [Region 1 San Juan Transmission 38kV sensitive areas] (Vegetation) | Pending Activation |  |  |  | 73.2374 |  |  | 15887347.061 | [7 empty] | 0 | 0% |  | 0 | 0%
Pending FAASt# |  | 38 kV | FAASt [Region 4 Caguas Transmission 38kV sensitive areas] (Vegetation) | Pending Activation |  |  |  | 40.6529 |  |  | 8818815.3648 | [7 empty] | 0 | 0% |  | 0 | 0%
Pending FAASt# |  | Distribution | FAASt [Group C_Region 6 Ponce Distribution sensitive areas] (Vegetation) | Pending Activation |  |  |  | 1271.29 |  |  | 165946767.16 | [7 empty] | 0 | 0% |  | 0 | 0%
Pending FAASt# |  | Distribution | FAASt [Group C_Region 5 Mayaguez Distribution sensitive areas] (Vegetation) | Pending Activation |  |  |  | 1774.91 |  |  | 231686378.8 | [7 empty] | 0 | 0% |  | 0 | 0%
Pending FAASt# |  | Distribution | FAASt [Group C_Region 2 Arecibo Distribution sensitive areas] (Vegetation) | Pending Activation |  |  |  | 1446.2 |  |  | 188778496.39 | [7 empty] | 0 | 0% |  | 0 | 0%
Pending FAASt# |  | Distribution | FAASt [Group C_Region 4 Caguas Distribution sensitive areas] (Vegetation) | Pending Activation |  |  |  | 1390.14 |  |  | 181460751.58 | [7 empty] | 0 | 0% |  | 0 | 0%
Pending FAASt# |  | Distribution | FAASt [Group C_Region 3 Bayamon Distribution sensitive areas] (Vegetation) | Pending Activation |  |  |  | 258.42 |  |  | 33732636.55 | [7 empty] | 0 | 0% |  | 0 | 0%
Pending FAASt# |  | Distribution | FAASt [Group C_Region 1 San Juan Distribution sensitive areas] (Vegetation) | Pending Activation |  |  |  | 1184.08 |  |  | 154562883.41 | [7 empty] | 0 | 0% |  | 0 | 0%
Pending FAASt# |  | 38 kV | 38kV Transmission Line 100 – Entire Line (Vegetation) | Pending Activation |  |  |  | 23.6779 |  |  | 5136430.3905 | [7 empty] | 0 | 0% |  | 0 | 0%
Pending FAASt# |  | 38 kV | 38kV Transmission Line 200 – Entire Line (Vegetation) | Pending Activation |  |  |  | 14.4286 |  |  | 3129993.9404 | [7 empty] | 0 | 0% |  | 0 | 0%
Pending FAASt# |  | 38 kV | 38kV Transmission Line 800 – Entire Line (Vegetation) | Pending Activation |  |  |  | 14.9828 |  |  | 3250209.6568 | [7 empty] | 0 | 0% |  | 0 | 0%
Pending FAASt# |  | 38 kV | 38kV Transmission Line 1200 – Entire Line (Vegetation) | Pending Activation |  |  |  | 25.6172 |  |  | 5557124.9115 | [7 empty] | 0 | 0% |  | 0 | 0%
Pending FAASt# |  | 38 kV | 38kV Transmission Line 1600 – Entire Line (Vegetation) | Pending Activation |  |  |  | 28.3726 |  |  | 6154852.5799 | [7 empty] | 0 | 0% |  | 0 | 0%
Pending FAASt# |  | 38 kV | 38kV Transmission Line 2000 – Entire Line (Vegetation) | Pending Activation |  |  |  | 28.2012 |  |  | 6117678.6539 | [7 empty] | 0 | 0% |  | 0 | 0%
Pending FAASt# |  | 38 kV | 38kV Transmission Line 2100 – Entire Line (Vegetation) | Pending Activation |  |  |  | 28.3149 |  |  | 6142341.798 | [7 empty] | 0 | 0% |  | 0 | 0%
Pending FAASt# |  | 38 kV | 38kV Transmission Line 2200 – Entire Line (Vegetation) | Pending Activation |  |  |  | 74.8136 |  |  | 16229267.3278 | [7 empty] | 0 | 0% |  | 0 | 0%
Pending FAASt# |  | 38 kV | 38kV Transmission Line 2500 – Entire Line (Vegetation) | Pending Activation |  |  |  | 22.6162 |  |  | 4906124.9971 | [7 empty] | 0 | 0% |  | 0 | 0%
Pending FAASt# |  | 38 kV | 38kV Transmission Line 2700 – Entire Line (Vegetation) | Pending Activation |  |  |  | 38.0604 |  |  | 8256417.9238 | [7 empty] | 0 | 0% |  | 0 | 0%
Pending FAASt# |  | 38 kV | 38kV Transmission Line 3000 – Entire Line (Vegetation) | Pending Activation |  |  |  | 45.6283 |  |  | 9898126.289 | [7 empty] | 0 | 0% |  | 0 | 0%
Pending FAASt# |  | 38 kV | 38kV Transmission Line 3100 – Entire Line (Vegetation) | Pending Activation |  |  |  | 60.3888 |  |  | 13100107.2316 | [7 empty] | 0 | 0% |  | 0 | 0%
Pending FAASt# |  | 38 kV | 38kV Transmission Line 3700 – Entire Line (Vegetation) | Pending Activation |  |  |  | 43.6816 |  |  | 9475835.7268 | [7 empty] | 0 | 0% |  | 0 | 0%
Pending FAASt# |  | 38 kV | 38kV Transmission Line 3800 – Entire Line (Vegetation) | Pending Activation |  |  |  | 23.5742 |  |  | 5113936.7644 | [7 empty] | 0 | 0% |  | 0 | 0%
Pending FAASt# |  | 38 kV | 38kV Transmission Line 4000 – Entire Line (Vegetation) | Pending Activation |  |  |  | 10.5063 |  |  | 2279116.6663 | [7 empty] | 0 | 0% |  | 0 | 0%
Pending FAASt# |  | 38 kV | 38kV Transmission Line 4800 – Entire Line (Vegetation) | Pending Activation |  |  |  | 39.7751 |  |  | 8628382.5758 | [7 empty] | 0 | 0% |  | 0 | 0%
Pending FAASt# |  | 38 kV | 38kV Transmission Line 5300 – Entire Line (Vegetation) | Pending Activation |  |  |  | 15.42 |  |  | 3345060.6836 | [7 empty] | 0 | 0% |  | 0 | 0%
Pending FAASt# |  | 38 kV | 38kV Transmission Line 5400 – Entire Line (Vegetation) | Pending Activation |  |  |  | 26.7657 |  |  | 5806269.7912 | [7 empty] | 0 | 0% |  | 0 | 0%
Pending FAASt# |  | 38 kV | 38kV Transmission Line 5600 – Entire Line (Vegetation) | Pending Activation |  |  |  | 27.2747 |  |  | 5916684.1812 | [7 empty] | 0 | 0% |  | 0 | 0%
Pending FAASt# |  | 38 kV | 38kV Transmission Line 6500 – Entire Line (Vegetation) | Pending Activation |  |  |  | 41.58 |  |  | 9019926.9468 | [7 empty] | 0 | 0% |  | 0 | 0%