## Prioritization Definitions
DEFINITION OF PRIORITY GROUPS
Priority Group | Definition | Description | Priority Driver
1 | High Impact Grid Improvement | Necessary projects in Transmission Lines, Substation and Distribution System which have high impact on Grid Improvement | Critical for Stabilization, Contingency and Reliability
2 | Vegetation Managament | Vegetation Clearing Projects that are necessary to get to a stage of normal maintenance | Critical for Stabilization and Reliability
3 | Grid Improvement | Projects that are less developed in scope and definition of benefits, however many of these could later fall into priority group 1 | Important for Stabilization, Contingency and Reliability
4 | Grid Support | Projects that support the grid and will increase efficency and reliablity of system, IT, Telecom etc. | Supports system reliability
5 | Streetlights Infrastructure | Continued rebuild of unsafe and poor conditioned streetlight system | Public Safety
6 | Buildings and Facilities | Projects that are necessary for improved efficiancy in operation of system, eg. control room buildings and substation security | Supports operational efficiencey
7 | Future Phase System Improvements | Projects across all assets that support modernization, optimization, and continuous improvement. Although beneficial, they do not require immediate activation and can be deferred until primary stabilization, reliability, safety, and operational projects have been executed. | Optimizes long‑term modernization and customer experience, executed only if funding is available after all higher‑priority needs are met.
Cat F | NFC Defined Projects (Pending Federal Formulation/Eligibility) | Projects originally developed for Non-Federal Capital (NFC) that require additional work to be formulated for federal funding. These projects currently lack sufficient information regarding scope, eligibility, compliance pathway, and execution strategy to assign an appropriate prioritization group. | Pending eligibility and scope development; prioritization will be assigned once federal compliance and execution requirements are established
0 | Obligated | Projects that have not started but are obligated

## Complete Prioritization List
# | Prioritization Code | Incurred Costs (Y/N) | Source | Project # | Title | Asset | Sub Asset | Estimated Total Incurred Costs | 428 Allocation (Without the A&E and E&M) | 406 Allocation (Without the A&E and E&M) | 428 A&E-PW 9510 | 406 A&E-PW 9510 | 428 E&M-PW 10710 | 406 E&M-PW 10710 | Expected Total Project Cost | Total 428 Expected cost | Total 406 Expected Cost | Comments
1 | 1 | Y | Attachment C | 688623 - A / 752500 - B / 752502 - C / 752503 - D | FAASt [Automation Program Group 1A-8 Feeders] (Distribution) *Group 1A with 1B, 1C, and 1D was consolidated into a unique Group 1 | Distribution | Automation | 11271718.95 | 15682783.16 | 2926805 | 3241962.6 | 516495 | 3708204.4 | 2410310 | 28486560.16 | 22632950.16 | 5853610 | Actuals for the "Work Completed" as of July 2026 considered, and Class 5 Estimate for the remaining work. Group 1A with 1B, 1C, and 1D was consolidated into a unique Group 1. The remaining work is based is Class 5 estimated total per project is considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (59) 3PH Reclosers, (266) 1ph reclosers, (165) cFCi. It requires an engineering evaluation once project is reactivated in order to meet current standards. Expenses incurred for partial work, including engineering and studies, which still need to be reconciled.
2 | 1 | Y | Attachment C | 740662 | [Automation Program Group 2] (TL/ Distribution | Distribution | Automation | 23203754 | 36782398.44 | 6876500 | 6277691.02 | 1213500 | 6850965.04 | 5663000 | 63664054.5 | 49911054.5 | 13753000 | Actuals for the "Work Completed" as of March 2026 considered, and Class 5 Estimate for the remaining work. The remaining work is Class 5 estimated total per project is considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (145) 3PH Reclosers, (539) 1ph reclosers, (254) cFCi. It requires an engineering evaluation once project is reactivated in order to meet current standards. Expenses incurred for partial work, including engineering and studies, which still need to be reconciled.
3 | 1 | Y | Attachment C | 741678 | [Automation Program Group 4] (TL/Distribution | Distribution | Automation | 20182619.36 | 29500343.61 | 5347180 | 4420325.45 | 943620 | 6946880.68 | 4403560 | 51561909.74 | 40867549.74 | 10694360 | Actuals for the "Work Completed" as of March 2026 considered, and Class 5 Estimate for the remaining work. The remaining work is Class 5 estimated total per project is considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (117) 3PH Reclosers, (247) 1ph reclosers, (182) cFCi. It requires an engineering evaluation once project is reactivated in order to meet current standards. Expenses incurred for partial work, including engineering and studies, which still need to be reconciled. Expenses have already been incurred for completed and partial work, including engineering and studies, which still need to be reconciled.
4 | 1 | Y | Attachment C | 705657 | [Automation Program Group 3] (TL/Distribution | Distribution | Automation | 27659865.35 | 30089122.78 | 4299385 | 7264119.61 | 758715 | 6881478.06 | 3540670 | 52833490.45 | 44234720.45 | 8598770 | Actuals for the "Work Completed" as of March 2026 considered, and Class 5 Estimate for the remaining work. The remaining work is Class 5 estimated total per project is considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (99) 3PH Reclosers, (316) 1ph reclosers, (212) cFCi.It requires an engineering evaluation once project is reactivated in order to meet current standards. Expenses incurred for partial work, including engineering and studies, which still need to be reconciled. Expenses have already been incurred for completed and partial work, including engineering and studies, which still need to be reconciled.
5 | 1 | Y | Attachment C | 800369 | FAASt [Automation Program Group 38 | Distribution | Automation | 347706.57 | 802170 | 252535 | 74275 | 44565 | 103985 | 207970 | 1485500 | 980430 | 505070 | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (4) 3PH Reclosers, (29) 1ph reclosers, (21) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions.
6 | 1 | Y | Attachment C | 800399 | FAASt [Automation Program Group 40 | Distribution | Automation | 819124.83 | 1536300 | 483650 | 142250 | 85350 | 199150 | 398300 | 2845000 | 1877700 | 967300 | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (11) 3PH Reclosers, (35) 1ph reclosers, (33) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions.
7 | 1 | Y | Attachment C | 801432 | FAASt [Automation Program Group 41 | Distribution | Automation | 618832.13 | 1469610 | 462655 | 136075 | 81645 | 190505 | 381010 | 2721500 | 1796190 | 925310 | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (10) 3PH Reclosers, (39) 1ph reclosers, (18) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions.
8 | 1 | Y | Attachment C | 801437 | FAASt [Automation Program Group 42 | Distribution | Automation | 224517.03 | 604800 | 190400 | 56000 | 33600 | 78400 | 156800 | 1120000 | 739200 | 380800 | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (2) 3PH Reclosers, (30) 1ph reclosers, (6) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions.
9 | 1 | Y | Attachment C | 801438 | FAASt [Automation Program Group 43 | Distribution | Automation | 407265.93 | 851580 | 268090 | 78850 | 47310 | 110390 | 220780 | 1577000 | 1040820 | 536180 | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (4) 3PH Reclosers, (34) 1ph reclosers, (12) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions.
10 | 1 | Y | Attachment C | 801440 | FAASt [Automation Program Group 44 | Distribution | Automation | 270824.91 | 597510 | 188105 | 55325 | 33195 | 77455 | 154910 | 1106500 | 730290 | 376210 | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (5) 3PH Reclosers, (10) 1ph reclosers, (6) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions.
11 | 1 | Y | Attachment C | 801441 | FAASt [Automation Program Group 45 | Distribution | Automation | 517574.24 | 1221750 | 384625 | 113125 | 67875 | 158375 | 316750 | 2262500 | 1493250 | 769250 | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (10) 3PH Reclosers, (21) 1ph reclosers, (18) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions.
12 | 1 | Y | Attachment C / Urgent Incremental Projects / Incremental Projects | Pending FAASt Number | FAASt [Automation Program Group 7 | Distribution | Automation | 108018.49 | 1696759.65 | 1131173.1 | 95539.6665 | 63693.111 | 407300.6835 | 271533.789 | 3666000 | 2199600 | 1466400 | FAASt # was withdrwan by FEMA at the end of 2024 because it was not on the latest LUMA 90 day Plan. The engineering is well‑developed, with key elements sufficiently progressed to support FEMA formulation. This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (16) 3PH Reclosers, (30) 1ph reclosers, (24) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions.
13 | 1 | Y | Attachment C / Urgent Incremental Projects / Incremental Projects | Pending FAASt Number | FAASt [Automation Program Group 23 | Distribution | Automation | 79860.4 | 976907.454 | 651271.636 | 55440.5837 | 36960.3892 | 236351.9623 | 157567.9748 | 2114500 | 1268700 | 845800 | The engineering is well‑developed, with key elements sufficiently progressed to support FEMA formulation. This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (9) 3PH Reclosers, (21) 1ph reclosers, (15) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions.
14 | 1 | Y | Attachment C / Urgent Incremental Projects / Incremental Projects | Pending FAASt Number | FAASt [Automation Program Group 25 | Distribution | Automation | 67320.12 | 657473.538 | 438315.692 | 38556.0278 | 25704.0185 | 164370.4342 | 109580.2895 | 1434000 | 860400 | 573600 | The engineering is well‑developed, with key elements sufficiently progressed to support FEMA formulation. This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (4) 3PH Reclosers, (22) 1ph reclosers, (12) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions.
15 | 1 | Y | Attachment C / Urgent Incremental Projects / Incremental Projects | Pending FAASt Number | FAASt [Automation Program Group 28 | Distribution | Automation | 86319.98 | 1435808.424 | 957205.616 | 74326.3994 | 49550.933 | 316865.1766 | 211243.451 | 3045000 | 1827000 | 1218000 | The engineering is well‑developed, with key elements sufficiently progressed to support FEMA formulation. This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (10) 3PH Reclosers, (50) 1ph reclosers, (30) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions.
16 | 1 | Y | Attachment C / Urgent Incremental Projects / Incremental Projects | Pending FAASt Number | FAASt [Automation Program Group 29 | Distribution | Automation | 70752.68 | 1046093.202 | 697395.468 | 55519.2916 | 37012.8611 | 236687.5064 | 157791.6709 | 2230500 | 1338300 | 892200 | The engineering is well‑developed, with key elements sufficiently progressed to support FEMA formulation. This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (8) 3PH Reclosers, (31) 1ph reclosers, (24) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions.
17 | 1 | Y | Attachment C | 745854 | FAASt [Automation Program Group 9 | Distribution | Automation | 184886.52 | 589140 | 185470 | 54550 | 32730 | 76370 | 152740 | 1091000 | 720060 | 370940 | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (4) 3PH Reclosers, (14) 1ph reclosers, (18) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions.
18 | 1 | Y | Attachment C | 745871 | FAASt [Automation Program Group 10 | Distribution | Automation | 290967.35 | 713610 | 224655 | 66075 | 39645 | 92505 | 185010 | 1321500 | 872190 | 449310 | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (6) 3PH Reclosers, (11) 1ph reclosers, (12) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions.
19 | 1 | Y | Attachment C | 745851 | FAASt [Automation Program Group 11 | Distribution | Automation | 255436.45 | 720630 | 226865 | 66725 | 40035 | 93415 | 186830 | 1334500 | 880770 | 453730 | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (5) 3PH Reclosers, (18) 1ph reclosers, (12) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions.
20 | 1 | Y | Attachment C | 745852 | FAASt [Automation Program Group 13 | Distribution | Automation | 837283.82 | 897480 | 282540 | 83100 | 49860 | 116340 | 232680 | 1662000 | 1096920 | 565080 | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (9) 3PH Reclosers, (3) 1ph reclosers, (24) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions.
21 | 1 | Y | Remain Inactive | 334497 | FAASt [Feeders - Caguas Short Term Group 6 (Distribution) | Distribution | Line Rebuild | 3697879.9562 | 64252838.0438 | 0 | 0 | 0 | 0 | 0 | 90131485 | 67950718 | 22180767 | A new strategy has been developed to submit Distribution Line Rebuild Projects by individual feeder instead of groups. Given the limited federal funds, the D-Line Rebuilds will be prioritizing tier 1 feeders that were based on CMI greater than 3.5M. Any other feeders in this project will be lower priority. Therefore, this project scope will only include feeder(s) 3007-03, which currently has an incurred cost of approximately $1,627,885.99 and an estimated project cost of $36,826,885.94
22 | 1 | Y | Remain Inactive | 334293 | FAASt [Feeders - 7805-11- Mayaguez Short Term Group 4] (Distribution ) | Distribution | Line Rebuild | 5762106.7403 | 41462815.2597 | 0 | 0 | 0 | 0 | 0 | 92807714 | 47224922 | 45582792 | A new strategy has been developed to submit Distribution Line Rebuild Projects by individual feeder instead of groups. Given the limited federal funds, the D-Line Rebuilds will be prioritizing tier 1 feeders that were based on CMI greater than 3.5M. Any other feeders in this project will be lower priority. Therefore, this project scope will only include feeder 7805-13 which currently has an incurred cost of approximately $1,021,893.38 and an estimated project cost of $3,201,829.27, final cost will be evaluate during the completion of the engineering.
23 | 1 | Y | Remain Inactive | 818041 | FAASt # [Distribution Feeder Rebuild # 3701-03] (Distribution) | Distribution | Line Rebuild | 2338234.37 | 22011369.52 | 0 | 0 | 0 | 0 | 0 | 24349603.89 | 24349603.89 | Unknown at this time* | Given the limited availability of federal funding, the D‑Line Rebuild program will prioritize Tier 1 feeders identified with a CMI greater than 3.5 million. This project represents a critical rebuild of a major distribution backbone designed to significantly strengthen system resilience and improve customer reliability. The upgraded feeder is engineered to withstand wind speeds up to 160 mph, ensuring long‑term durability and performance under extreme weather conditions. Additionally, this project was selected due to its advanced level of detailed engineering development, allowing a Detailed Scope of Work (DSOW) to be submitted to FEMA within a short timeframe, no more than four months.
24 | 1 | Y | Remain Inactive | 767005 | FAASt [Feeder Rebuild # 1303-05] (Distribution) | Distribution | Line Rebuild | 1784400.44 | 10847365.56 | 0 | 0 | 0 | 0 | 0 | 12631766 | 12631766 | Unknown at this time* | Given the limited availability of federal funding, the D‑Line Rebuild program will prioritize Tier 1 feeders identified with a CMI greater than 3.5 million. This project represents a critical rebuild of a major distribution backbone designed to significantly strengthen system resilience and improve customer reliability. The upgraded feeder is engineered to withstand wind speeds up to 160 mph, ensuring long‑term durability and performance under extreme weather conditions. Additionally, this project was selected due to its advanced level of detailed engineering development, allowing a Detailed Scope of Work (DSOW) to be submitted to FEMA within a short timeframe, no more than four months.
25 | 1 | Y | Remain Inactive | 818055 | FAASt # [Distribution Feeder Rebuild # 3006-05] (Distribution) | Distribution | Line Rebuild | 2103625.24 | 6725382.76 | 0 | 0 | 0 | 0 | 0 | 8829008 | 8829008 | Unknown at this time* | Given the limited availability of federal funding, the D‑Line Rebuild program will prioritize Tier 1 feeders identified with a CMI greater than 3.5 million. This project represents a critical rebuild of a major distribution backbone designed to significantly strengthen system resilience and improve customer reliability. The upgraded feeder is engineered to withstand wind speeds up to 160 mph, ensuring long‑term durability and performance under extreme weather conditions. Additionally, this project was selected due to its advanced level of detailed engineering development, allowing a Detailed Scope of Work (DSOW) to be submitted to FEMA within a short timeframe, no more than four months.
26 | 1 | Y | Remain Inactive | 764709 | FAASt [Feeder Rebuild # 1204-05] (Distribution) | Distribution | Line Rebuild | 1521264.18 | 7219556.75 | 0 | 0 | 0 | 0 | 0 | 8740820.93 | 8740820.93 | Unknown at this time* | Given the limited availability of federal funding, the D‑Line Rebuild program will prioritize Tier 1 feeders identified with a CMI greater than 3.5 million. This project represents a critical rebuild of a major distribution backbone designed to significantly strengthen system resilience and improve customer reliability. The upgraded feeder is engineered to withstand wind speeds up to 160 mph, ensuring long‑term durability and performance under extreme weather conditions. Additionally, this project was selected due to its advanced level of detailed engineering development, allowing a Detailed Scope of Work (DSOW) to be submitted to FEMA within a short timeframe, no more than four months.
27 | 1 | Y | Remain Inactive | 760577 | FAASt [Feeder Rebuild # 1718-02] (Distribution) | Distribution | Line Rebuild | 1454045.39 | 6967350.61 | 0 | 0 | 0 | 0 | 0 | 8421396 | 8421396 | Unknown at this time* | Given the limited availability of federal funding, the D‑Line Rebuild program will prioritize Tier 1 feeders identified with a CMI greater than 3.5 million. This project represents a critical rebuild of a major distribution backbone designed to significantly strengthen system resilience and improve customer reliability. The upgraded feeder is engineered to withstand wind speeds up to 160 mph, ensuring long‑term durability and performance under extreme weather conditions. Additionally, this project was selected due to its advanced level of detailed engineering development, allowing a Detailed Scope of Work (DSOW) to be submitted to FEMA within a short timeframe, no more than four months.
28 | 1 | Y | Remain Inactive | 817993 | FAASt # [Distribution Feeder Rebuild # 1801-03] (Distribution) | Distribution | Line Rebuild | 1200284.07 | 4931561.93 | 0 | 0 | 0 | 0 | 0 | 6131846 | 6131846 | Unknown at this time* | Given the limited availability of federal funding, the D‑Line Rebuild program will prioritize Tier 1 feeders identified with a CMI greater than 3.5 million. This project represents a critical rebuild of a major distribution backbone designed to significantly strengthen system resilience and improve customer reliability. The upgraded feeder is engineered to withstand wind speeds up to 160 mph, ensuring long‑term durability and performance under extreme weather conditions. Additionally, this project was selected due to its advanced level of detailed engineering development, allowing a Detailed Scope of Work (DSOW) to be submitted to FEMA within a short timeframe, no more than four months.
29 | 1 | Y | Remain Inactive | 767387 | FAASt [Feeder Rebuild # 1303-01] (Distribution) | Distribution | Line Rebuild | 1208210.54 | 12179251.75 | 0 | 0 | 0 | 0 | 0 | 13387462.29 | 13387462.29 | Unknown at this time* | Given the limited availability of federal funding, the D‑Line Rebuild program will prioritize Tier 1 feeders identified with a CMI greater than 3.5 million. This project represents a critical rebuild of a major distribution backbone designed to significantly strengthen system resilience and improve customer reliability. The upgraded feeder is engineered to withstand wind speeds up to 160 mph, ensuring long‑term durability and performance under extreme weather conditions. Additionally, this project was selected due to its advanced level of detailed engineering development, allowing a Detailed Scope of Work (DSOW) to be submitted to FEMA within a short timeframe, no more than four months.
30 | 1 | Y | Remain Inactive | 767381 | FAASt [Feeder Rebuild # 1204-04] (Distribution) | Distribution | Line Rebuild | 1348100.48 | 4192522.16 | 0 | 0 | 0 | 0 | 0 | 5540622.64 | 5540622.64 | Unknown at this time* | This is an individual Feeder Project.
31 | 1 | Y | Remain Inactive | 817961 | FAASt [Feeder Rebuild # 2404-06] (Distribution) | Distribution | Line Rebuild | 1247450.93 | -888275.69 | 0 | 0 | 0 | 0 | 0 | 4536319.69 | 359175.24 | 4177144.45 | Given the limited availability of federal funding, the D‑Line Rebuild program will prioritize Tier 1 feeders identified with a CMI greater than 3.5 million. This project represents a critical rebuild of a major distribution backbone designed to significantly strengthen system resilience and improve customer reliability. The upgraded feeder is engineered to withstand wind speeds up to 160 mph, ensuring long‑term durability and performance under extreme weather conditions. Additionally, this project was selected due to its advanced level of detailed engineering development, allowing a Detailed Scope of Work (DSOW) to be submitted to FEMA within a short timeframe, no more than four months.
32 | 1 | Y | Remain Inactive | 754351 | FAASt [Underground Circuit Feeders - San Juan Group 2] (Distribution) | Distribution – Underground | Underground | 722563.3 | 2160436.7 | 0 | 0 | 0 | 0 | 0 | 2883000 | 2883000 | Unknown at this time* | Given limited federal funding, the D Line Rebuild program will prioritize Tier 1 feeders with a CMI above 3.5 million. This project is a critical rebuilding of a major distribution backbone that will strengthen system resilience and improve reliability. The San Juan Baldrich Substation feeders 1424‑07 and 1424‑08 share extensive underground infrastructure, creating shared points of failure. By adding essential redundancy, switching units, and other underground components, the project will reduce the risk of prolonged outages and protect key facilities including hospitals, fire and police command centers, emergency management sites, PRASA pump stations, and educational institutions that serve as storm shelters. Approval is vital to safeguarding public safety and ensuring continuity of critical services during future emergencies. The project will also benefit 10,505 customers through improved load‑transfer capability across these and adjacent feeders.
33 | 1 | N | Apendix F / Attachment A | Pending FAASt Number | Fleet acquisition | E&M | E&M | 0 | 0 | 0 | 0 | 0 | 40000000 | 0 | 40000000 | 40000000 | 0 | New Project
34 | 1 | Y | Remain Inactive | 668665 | Cybersecurity Program Implementation | IT/OT | N/A | 1.8 | 24587254.33 | 0 | 0 | 0 | 0 | 0 | 24587256.13 | 24587256.13 | 0
35 | 1 | Y | Remain Inactive | 675345 | IT OT Technology Systems Reparations Group 1 | IT/OT | N/A | 0 | 9177181.22 | 0 | 0 | 0 | 0 | 0 | 9177181.22 | 9177181.22 | 0
36 | 1 | Y | Attachment C / Incremental Project List | Pending FAASt Number | Transport Network Group 2, 57 sites | IT/OT | N/A | 7678157 | 0 | 0 | 0 | 0 | 0 | 0 | $70,021,267.04 | $38,511,696.87 | $31,509,570.17 | 30% design for make ready and telecom equipment have been completed by internal Telecom Engineering. 428 PA and 406 HM split are based on percentages from Group 1 Ver 1, submitted to FEMA. Project re-defined/re-designed: site count increased from 57 to 83 within the same budget (expected total project cost remains the same).
37 | 1 | Y | Incremental Project List | Pending FAASt Number | Transport Network Group 3, 60 sites | IT/OT | N/A | 4641396 | 0 | 0 | 0 | 0 | 0 | 0 | $73,706,596.88 | $40,538,628.28 | $33,167,968.60 | 30% design not finish, not approved yet. Cost etsimate is based on cost per site and split calculations from Group 2 estimate.
38 | 1 | Y | Attachment C | Pending FAASt Number | Venezuela WC | Substation | Grid Modernization | 1037090 | 988258.98 | 0 | 541838.04 | 0 | 1083257.99 | 0 | 2613355.01 | 2613355.01 | 0 | The incurred cost includes the milestone payments 1-4 for the transformer.
39 | 1 | Y | Attachment C | Pending FAASt Number | Hato Rey WC | Substation | Grid Modernization | 968203 | 1156110.08 | 0 | 471848.13 | 0 | 1079499.89 | 0 | 2707458.1 | 2707458.1 | 0 | The incurred cost includes the milestone 1 payment for the transformer.
40 | 1 | Y | Attachment C | Pending FAASt Number | Aguada WC | Substation | Grid Modernization | 0 | 535734.82 | 0 | 197297.35 | 0 | 615426.45 | 0 | 1348458.62 | 1348458.62 | 0
41 | 1 | Y | Attachment C | Pending FAASt Number | Monterrey | Substation | Grid Modernization | 334955.25 | 5467624.97 | 2622060.62 | 236211.04 | 65309.65 | 635052.46 | 259860.22 | 9286118.96 | 6338888.47 | 2947230.49 | The incurred cost includes the milestone 1 payment for the transformer.
42 | 1 | Y | Attachment C | Pending FAASt Number | ALTURAS DE MAYAGUEZ | Substation | Substation Component Replacements | 334955.25 | 5467624.97 | 2622060.62 | 236211.04 | 65309.65 | 1470519.69 | 490173.23 | 10351899.2 | 7174355.7 | 3177543.5 | The incurred cost includes the milestone 1 payment for the transformer.
43 | 1 | Y | Attachment C | Pending FAASt Number | ALTURAS DE RIO GRANDE | Substation | Substation Component Replacements | 182885.6 | 5467624.97 | 2622060.62 | 236211.04 | 65309.65 | 1623084.8 | 405771.2 | 10420062.28 | 7326920.81 | 3093141.47 | The incurred cost includes the milestone 1 payment for the transformer.
44 | 1 | Y | Attachment C | Pending FAASt Number | BARCELONETA PUEBLO | Substation | Substation Component Replacements | 197115.5 | 5467624.97 | 2622060.62 | 236211.04 | 65309.65 | 1736924 | 434231 | 10562361.28 | 7440760.01 | 3121601.27 | The incurred cost includes the milestone 1 payment for the transformer.
45 | 1 | Y | Attachment C | Pending FAASt Number | BRENAS | Substation | Substation Component Replacements | 135810.3 | 5467624.97 | 2622060.62 | 236211.04 | 65309.65 | 1246482.4 | 311620.6 | 9949309.28 | 6950318.41 | 2998990.87 | The incurred cost includes the milestone 1 payment for the transformer.
46 | 1 | Y | Attachment C | Pending FAASt Number | CAMUY | Substation | Substation Component Replacements | 197115.5 | 5467624.97 | 2622060.62 | 236211.04 | 65309.65 | 1736924 | 434231 | 10562361.28 | 7440760.01 | 3121601.27 | The incurred cost includes the milestone 1 payment for the transformer.
47 | 1 | Y | Attachment C | Pending FAASt Number | CERAMICA (aka Vistamar) | Substation | Substation Component Replacements | 182885.6 | 5467624.97 | 2622060.62 | 236211.04 | 65309.65 | 1623084.8 | 405771.2 | 10420062.28 | 7326920.81 | 3093141.47 | The incurred cost includes the milestone 1 payment for the transformer.
48 | 1 | Y | Attachment C | Pending FAASt Number | CRUCE DAVILA | Substation | Substation Component Replacements | 222662.22 | 5467624.97 | 2622060.62 | 236211.04 | 65309.65 | 1029095.9 | 259726.64 | 9680028.82 | 6732931.91 | 2947096.91 | The incurred cost includes the milestone 1 payment for the transformer.
49 | 1 | Y | Attachment C | Pending FAASt Number | HATO TEJAS | Substation | Substation Component Replacements | 334955.25 | 5467624.97 | 2622060.62 | 236211.04 | 65309.65 | 1470519.69 | 490173.23 | 10351899.2 | 7174355.7 | 3177543.5 | The incurred cost includes the milestone 1 payment for the transformer.
50 | 1 | Y | Attachment C | Pending FAASt Number | ISABELA PUEBLO | Substation | Substation Component Replacements | 197115.5 | 5467624.97 | 2622060.62 | 236211.04 | 65309.65 | 1736924 | 434231 | 10562361.28 | 7440760.01 | 3121601.27 | The incurred cost includes the milestone 1 payment for the transformer.
51 | 1 | Y | Attachment C | Pending FAASt Number | JUNCOS TC | Substation | Substation Component Replacements | 579751.25 | 12436054.15 | 2868434.03 | 548875.4 | 281565.59 | 2580317.19 | 860105.73 | 19575352.08 | 15565246.74 | 4010105.35 | The incurred cost includes the milestone 1 payment for the transformer.
52 | 1 | Y | Attachment C | Pending FAASt Number | LA RAMBLA SECT | Substation | Substation Component Replacements | 314285.89 | 5467624.97 | 2622060.62 | 236211.04 | 65309.65 | 1341072.11 | 447024.04 | 10179302.42 | 7044908.12 | 3134394.3 | The incurred cost includes the milestone 1 payment for the transformer.
53 | 1 | Y | Attachment C | Pending FAASt Number | LAS PIEDRAS SECT | Substation | Substation Component Replacements | 261047.79 | 5467624.97 | 2622060.62 | 236211.04 | 65309.65 | 1029095.9 | 259726.64 | 9680028.82 | 6732931.91 | 2947096.91 | The incurred cost includes the milestone 1 payment for the transformer.
54 | 1 | Y | Attachment C | Pending FAASt Number | MANATI TC | Substation | Substation Component Replacements | 779742.9 | 9069707.7 | 4349479.63 | 391827.36 | 108335.78 | 7277943.2 | 1819485.8 | 23016779.47 | 16739478.27 | 6277301.2 | The incurred cost includes the milestone 1 payment for the transformer.
55 | 1 | Y | Attachment C | Pending FAASt Number | NAGUABO | Substation | Substation Component Replacements | 135810.3 | 5467624.97 | 2622060.62 | 236211.04 | 65309.65 | 1246482.4 | 311620.6 | 9949309.28 | 6950318.41 | 2998990.87 | The incurred cost includes the milestone 1 payment for the transformer.
56 | 1 | Y | Attachment C | Pending FAASt Number | PATILLAS | Substation | Substation Component Replacements | 197115.5 | 5467624.97 | 2622060.62 | 236211.04 | 65309.65 | 1736924 | 434231 | 10562361.28 | 7440760.01 | 3121601.27 | The incurred cost includes the milestone 1 payment for the transformer.
57 | 1 | Y | Attachment C | Pending FAASt Number | PENUELAS | Substation | Substation Component Replacements | 222662.22 | 5467624.97 | 2622060.62 | 236211.04 | 65309.65 | 1029095.9 | 259726.64 | 9680028.82 | 6732931.91 | 2947096.91 | The incurred cost includes the milestone 1 payment for the transformer.
58 | 1 | Y | Attachment C | Pending FAASt Number | PUERTO DEL REY | Substation | Substation Component Replacements | 314285.89 | 5467624.97 | 2622060.62 | 236211.04 | 65309.65 | 1341072.11 | 447024.04 | 10179302.42 | 7044908.12 | 3134394.3 | The incurred cost includes the milestone 1 payment for the transformer.
59 | 1 | Y | Attachment C | Pending FAASt Number | RAMEY FIELD 3 | Substation | Substation Component Replacements | 222662.22 | 5467624.97 | 2622060.62 | 236211.04 | 65309.65 | 1029095.9 | 259726.64 | 9680028.82 | 6732931.91 | 2947096.91 | The incurred cost includes the milestone 1 payment for the transformer.
60 | 1 | Y | Attachment C | Pending FAASt Number | SABANA GRANDE | Substation | Substation Component Replacements | 222662.22 | 5467624.97 | 2622060.62 | 236211.04 | 65309.65 | 1029095.9 | 259726.64 | 9680028.82 | 6732931.91 | 2947096.91 | The incurred cost includes the milestone 1 payment for the transformer.
61 | 1 | Y | Attachment C | Pending FAASt Number | SALINAS RURAL | Substation | Substation Component Replacements | 222662.22 | 5467624.97 | 2622060.62 | 236211.04 | 65309.65 | 1029095.9 | 259726.64 | 9680028.82 | 6732931.91 | 2947096.91 | The incurred cost includes the milestone 1 payment for the transformer.
62 | 1 | Y | Attachment C | Pending FAASt Number | SALINAS URBANO | Substation | Substation Component Replacements | 222662.22 | 5467624.97 | 2622060.62 | 236211.04 | 65309.65 | 1029095.9 | 259726.64 | 9680028.82 | 6732931.91 | 2947096.91 | The incurred cost includes the milestone 1 payment for the transformer.
63 | 1 | Y | Attachment C | Pending FAASt Number | QUEBRADA NEGRITO | Substation | Substation Component Replacements | 278859.13 | 5467624.97 | 2622060.62 | 236211.04 | 65309.65 | 1260159.24 | 420053.08 | 10071418.6 | 6963995.25 | 3107423.35 | The incurred cost includes the milestone 1 payment for the transformer.
64 | 1 | Y | Attachment C | Pending FAASt Number | TOA ALTA | Substation | Substation Component Replacements | 197115.5 | 5467624.97 | 2622060.62 | 236211.04 | 65309.65 | 1736924 | 434231 | 10562361.28 | 7440760.01 | 3121601.27 | The incurred cost includes the milestone 1 payment for the transformer.
65 | 1 | Y | Attachment C | Pending FAASt Number | VEREDAS SECT | Substation | Substation Component Replacements | 314285.89 | 5467624.97 | 2622060.62 | 236211.04 | 65309.65 | 1341072.11 | 447024.04 | 10179302.42 | 7044908.12 | 3134394.3 | The incurred cost includes the milestone 1 payment for the transformer.
66 | 1 | Y | Attachment C | Pending FAASt Number | AGUAS BUENAS | Substation | Substation Component Replacements | 261047.79 | 5614147.55 | 2622060.62 | 482672.57 | 65309.65 | 1241258.17 | 259726.64 | 10285175.2 | 7338078.29 | 2947096.91 | The incurred cost includes the milestone 1 payment for the transformer.
67 | 1 | Y | Attachment C | Pending FAASt Number | PALMER | Substation | Substation Component Replacements | 135810.3 | 5467624.97 | 2622060.62 | 236211.04 | 65309.65 | 1470519.69 | 490173.23 | 10351899.2 | 7174355.7 | 3177543.5 | Due to major challenges to replace the 13.2kV Transformer, it is recommeded to combine this scope with the Palmer Substation Rebuild. The incurred cost includes the milestone 1 payment for the transformer.
68 | 1 | Y | Attachment C | 752277 | FAASt [Substation Ciales 8701] (Substation) | Substation | Substation Rebuild | 436437.47 | 9069707.7 | 4349479.63 | 391827.36 | 108335.78 | 1706844.84 | 431056.67 | 16057251.98 | 11168379.91 | 4888872.07
69 | 1 | Y | Remain Inactive | 547273 | FAASt Charco Hondo Substation 8008 Relocation (Substation) | Substation | Substation Rebuild | 636972.49 | 15663027.51 | 0 | 0 | 0 | 0 | 0 | 16300000 | 16300000 | Unknown at this time*
70 | 1 | Y | Remain Inactive | 551916 | FAASt [Dorado TC Relocation] (Substation) | Substation | Substation Rebuild | 128603.03 | 39971396.97 | 0 | 0 | 0 | 0 | 0 | 40100000 | 40100000 | Unknown at this time*
71 | 1 | Y | Remain Inactive | 673920 | FAASt [Isla Grande 1101] (Substation) | Substation | Substation Rebuild | 40252.17 | 559747.83 | 0 | 0 | 0 | 0 | 0 | 600000 | 600000 | Unknown at this time*
72 | 1 | Y | Remain Inactive | 685869 | FAASt [Mayagüez TC] (Substation) | Substation | Automation | 2917609.09 | -317316.09 | 0 | 0 | 0 | 0 | 0 | 9824565 | 2600293 | 7224272
73 | 1 | Y | Urgent Incremental Projects / Incremental Projects | Pending FAASt Number | Hato Rey TC Transformer Replacement | Substation | Component Replacement | 3763775.37 | 0 | 0 | 0 | 0 | 0 | 0 | 3763775.37 | 3763775.37 | 0 | Transformer purchased and reimbursed to E&M PW ($892,425).
74 | 1 | Y | Urgent Incremental Projects / Incremental Projects | Pending FAASt Number | Venezuela TC | Substation | Component Replacement | 2613825.35 | 0 | 0 | 0 | 0 | 0 | 0 | 2613825.35 | 2613825.35 | 0 | Transformer purchased and reimbursed to E&M PW ($1,037,090).
75 | 1 | Y | Urgent Incremental Projects / Incremental Projects | Pending FAASt Number | Substation Component Group 0 | Substation | Component Replacement | 14145405.55 | 0 | 0 | 0 | 0 | 0 | 0 | 14145405.55 | 14145405.55 | 0 | Project is a priority to get FEMA obligation. The equipment was purchased under the federal E&M. LUMA is requesting a FAASt number to be reconciled for the Equipment purchased under E&M PW. All of this equipment cost would put rate payers at risk if it is not reconciled to child PWs. Equipment included in this cost Incurred are the following: 16 Gas Circuit Breakers ($1,036,579), 5 Transformers - Sabana Llana 1646 ($968,203), Mora TC 112 MVA ($2,926,189.87), Caguas 112 MVA ($4,416,882), Isla Grande 112MVA ($2,926,189.87), Hogar Crea 112 MVA ($1,871,361.81)
76 | 1 | N | Urgent Incremental Projects / Incremental Projects | Pending FAASt Number | Arecibo Sect. Substation Rebuild | Substation | Substation Rebuild | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71435277.14 | 7143527.714 | 64291749.426 | Cost Incurred to date is based on project planning exercises and therefore not tied directly to execution of project. High-Level project scope: Rebuild of priority sectionalizing substation including colocated 8015 Arecibo Hospital Distrito and 8003 Arecibo Rural distribution substations and relocation to site of distribution substation 8002 Arecibo Pueblo substation (due to Historical Flooding).
77 | 1 | N | Urgent Incremental Projects / Incremental Projects | Pending FAASt Number | Chardon Sect. Substation Rebuild | Substation | Substation Rebuild | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000000 | 15000000 | 10000000 | Cost Incurred to date is based on project planning exercises and therfore not tied directly to execution of project. Rebuild of priority sectionalizing substation; will include in scope the rebuild of distribution substations 1403 Chardon I and 1404 Chardón 2
78 | 1 | N | Incremental Project List | Pending FAASt Number | Palmer TC Substation Rebuild | Substation | Substation Rebuild | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000000 | 15000000 | 10000000 | Rebuild of priority Transmission Center; will include in scope the rebuild of distribution substation 2305 Palmer.
79 | 1 | N | Incremental Project List | Pending FAASt Number | Falu 1334 Substation Rebuild | Substation | Substation Rebuild | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000000 | 6000000 | 4000000 | Rebuild of Falú 1334 Distribution Substation.
80 | 1 | N | Appendix F | Pending FAASt Number | Transformers "On-site" Preparation Costs | Substation | Component Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64745000 | 0 | 0 | This total request is for the whole list of transformers coming to the island within the next three years. NFC will be requested to handle FY27.
81 | 1 | Y | Attachment C | 805517 | 38kV Recloser TL 2100 Hatillo TC to Quebradillas Sect. | Transmission | Automation | 200812.31 | 261599.08 | 0 | 110178.42 | 0 | 69170.22 | 0 | 462411.39 | 462411.39 | 0
82 | 1 | Y | Attachment C | 805519 | 38kV Recloser TL 1900 Dos Bocas HP to San Sebastian TC | Transmission | Automation | 197629.44 | 510778.57 | 0 | 101897.17 | 0 | 77960.25 | 0 | 708408.01 | 708408.01 | 0
83 | 1 | Y | Attachment C | 805521 | 38 kv Reclosers TL7800 | Transmission | Automation | 221984.29 | 63058.79 | 0 | 142174.45 | 0 | 64775.2 | 0 | 285043.08 | 285043.08 | 0
84 | 1 | Y | Attachment C | Pending FAASt Number | TL36100 Dos Bocas to Ciales - Transmission Line Rebuild | Transmission | Line Rebuild | 0 | 36215386.59 | 6160027.9 | 2872795.2 | 429630.09 | 2206882.19 | 286465.11 | 48171187.08 | 41295063.98 | 6876123.1 | Was originally part of the 36100 full submittal, but the scope of that project was reduced to just the segment between Bayamon and Monacillos (and that scoped project is already in Exhibit 2). Because of that scope change, this Dos Bocas to Ciales segment does not have any other project, so needs to be added here in Attachment C. The full line 36100 has A&E incurred costs. These incurred costs are under consideration to be included in the Exhibit 2 project for the Bayamon to Monacillos segment, so that is why this project is showing as zero incurred costs for now.
85 | 1 | Y | Remain Inactive | 167443 | FAASt - Line 36200 (115KV)- Monacillos TC to Juncos TC (Transmission) | Transmission | Line Rebuild | 2053853.24 | 66953457.76 | 0 | 0 | 0 | 0 | 0 | 84974331 | 69007311 | 15967020
86 | 1 | Y | Remain Inactive | 177134 | FAASt Guaraguao TC to Comerio TC Line-4100 (Transmission) | Transmission | Line Rebuild | 2980728.09 | 56694607.91 | 0 | 0 | 0 | 0 | 0 | 67497027 | 59675336 | 7821691
87 | 1 | Y | Remain Inactive | 753777 | FAASt [Line 1500 - Mayaguez GP to GOAB 1515] (Transmission) | Transmission | Line Rebuild | 4268922.36 | 54392077.64 | 0 | 0 | 0 | 0 | 0 | 58661000 | 58661000 | Unknown at this time*
88 | 1 | Y | Remain Inactive | 753788 | Transmission Priority Pole Replacement Program Line 1900 Dos Bocas HP – San Sebastián TC | Transmission | Pole Replacement | 278379.63 | 779545.97 | 0 | 0 | 0 | 0 | 0 | 1057925.6 | 1057925.6 | 0
89 | 1 | Y | Remain Inactive | 811913 | Transmission Priority Pole Replacement Program Line 9600 Bayamon TC–Catano Sect | Transmission | Pole Replacement | 42386 | 377817.89 | 0 | 0 | 0 | 0 | 0 | 463977.49 | 420203.89 | 43773.6
90 | 1 | N | Incremental Project List | Pending FAASt Number | 4100-COMERIO TC-GUARAGUAO SECT- | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 93450 | 11550 | Pole Replacements: 0 Critical Repairs: 7
91 | 1 | N | Incremental Project List | Pending FAASt Number | 37400-BARCELONETA TC-CAMBALACHE TC- | Transmission | Line Rebuild | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23175154.506 | 19003626.6949 | 4171527.8111 | Critical line for the 115 kV system.
92 | 1 | N | Incremental Project List | Pending FAASt Number | 37400-CAMBALACHE TC-DOS BOCAS HP- | Transmission | Line Rebuild | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21516401.116 | 17643448.9151 | 3872952.2009 | Critical line for the 115 kV system.
93 | 1 | N | Incremental Project List | Pending FAASt Number | 37400-DORADO TC-HATO TEJAS TC- | Transmission | Line Rebuild | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11611273.73 | 9521244.4586 | 2090029.2714 | Critical line for the 115 kV system.
94 | 1 | N | Incremental Project List | Pending FAASt Number | 37400-DORADO TC-VEGA BAJA TC- | Transmission | Line Rebuild | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21326829.3 | 17488000.026 | 3838829.274 | Critical line for the 115 kV system.
95 | 1 | N | Incremental Project List | Pending FAASt Number | 37400-HATO TEJAS TC-BAYAMON TC- | Transmission | Line Rebuild | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9123143.645 | 7480977.7889 | 1642165.8561 | Critical line for the 115 kV system.
96 | 1 | N | Incremental Project List | Pending FAASt Number | 37400-MANATI TC-BARCELONETA TC- | Transmission | Line Rebuild | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20805506.806 | 17060515.5809 | 3744991.2251 | Critical line for the 115 kV system.
97 | 1 | N | Incremental Project List | Pending FAASt Number | 37400-VEGA BAJA TC-MANATI TC- | Transmission | Line Rebuild | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10971468.851 | 8996604.4578 | 1974864.3932 | Critical line for the 115 kV system.
98 | 1 | Y | Attachment C / Urgent Incremental Projects / Incremental Projects | TBD (Various) | TL 38kV Reclosers | Transmission | Automation | 6521828.2 | 23109489.55 | 0 | 3121828.2 | 0 | 3400000 | 0 | 46523875.17 | 29631317.75 | 16892557.42 | Cost Incurred for 38 kV Recloser Program is due to Engineering and Project Management Costs ($3.1M) and Equipment Purchase Cost as the Reclosers for these projects have already been procured under the Equipment & Material PW and are in LUMA's Warehouse ($3.4M). 406 split is estimated based on Distribution Automation current 406 amendments as the mitigation strategy should follow similarly, but is subject to review.
99 | 1 | Y | Remain Inactive | 715610 | FAASt [Network Upgrades to Support the Integration of Tranche 1 Utility Scale Renewable Projects] (Transmission) | Transmission | N/A | 26514.9 | 144718978.1 | 0 | 0 | 0 | 0 | 0 | 144745493 | 144745493 | 0
100 | 1 | Y | Remain Inactive | 334331 | FAASt Line 1900 Dos Bocas HP to San Sebastian (38kV) TC (Transmission) | Transmission | Line Rebuild | 3824725.25 | 29972666.23 | 0 | 0 | 0 | 0 | 0 | 33797391.48 | 33797391.48 | 0
101 | 2 | N | Vegetation Incremental Projects | Pending FAASt Number | FAASt [Region 1 San Juan Distribution sensitive areas] (Vegetation) | Vegetation | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136954530 | 36628489.0485 | 100284954.5925 | 428/406 Splits based on what was agreed to by LUMA and FEMA (Distribution = 26.745% 428, 73.225% 406).
102 | 2 | N | Vegetation Incremental Projects | Pending FAASt Number | FAASt [Region 2 Arecibo Distribution sensitive areas] (Vegetation) | Vegetation | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 188729100 | 50475597.795 | 138196883.475 | 428/406 Splits based on what was agreed to by LUMA and FEMA (Distribution = 26.745% 428, 73.225% 406).
103 | 2 | N | Vegetation Incremental Projects | Pending FAASt Number | FAASt [Region 3 Bayamon Distribution sensitive areas] (Vegetation) | Vegetation | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33723810 | 9019432.9845 | 24694259.8725 | 428/406 Splits based on what was agreed to by LUMA and FEMA (Distribution = 26.745% 428, 73.225% 406).
104 | 2 | N | Vegetation Incremental Projects | Pending FAASt Number | FAASt [Region 4 Caguas Distribution sensitive areas] (Vegetation) | Vegetation | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165176460 | 44176444.227 | 120950462.835 | 428/406 Splits based on what was agreed to by LUMA and FEMA (Distribution = 26.745% 428, 73.225% 406).
105 | 2 | N | Vegetation Incremental Projects | Pending FAASt Number | FAASt [Region 5 Mayaguez Distribution sensitive areas] (Vegetation) | Vegetation | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 218058975 | 58319872.8638 | 159673684.4437 | 428/406 Splits based on what was agreed to by LUMA and FEMA (Distribution = 26.745% 428, 73.225% 406).
106 | 2 | N | Vegetation Incremental Projects | Pending FAASt Number | FAASt [Region 6 Ponce Distribution sensitive areas] (Vegetation) | Vegetation | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160503255 | 42926595.5498 | 117528508.4737 | 428/406 Splits based on what was agreed to by LUMA and FEMA (Distribution = 26.745% 428, 73.225% 406).
107 | 3 | Y | Attachment C / Urgent Incremental Projects / Incremental Projects | TBD (Various) | Distribution Automation Program 57 Groups (Group #46 to Group #102) *Former Bucket 63 of 151 | Distribution | Automation | 44378156.85 | 87993084.18 | 58662056.1 | 4470551.04 | 2980367.34 | 19058664.85 | 12705776.55 | 185870500 | 111522300 | 74348200 | Updated Comment: Within these originally 63 groups, Group 7, 23, 25, 28, 29 are more ready to be executed and pushed through obligation process (~$6M of 428 w/o A&E and E&M) will be moved out from the bucket. Group 17 would need to be descoped as it has been included in different project (~47,000 of 428 w/o A&E and E&M). Will be reduced to 57 projects. The Automation Program included here is based on a grouping of projects that LUMA will split to separate groups during the formulation process as DSOWs are submitted to FEMA. These 67 groups have approximately $45M of cost incurred to the E&M PW ($61M for all 151). To be clear, this line does not include "Work Completed" Distribution Automation, as construction has not commenced for the units included herein as we are pending FAASt numbers.
108 | 3 | Y | Attachment C | TBD | Poles Purchased - Included in the E&M without child | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 54755600 | 0 | 54755600 | 54755600 | 0 | This line item is for poles purchased under the global Equipment and Material PW that do not currently have a child project based on current allocations.
109 | 3 | Y | Attachment C | TBD | DA Equipment Purchased - Included in the E&M PW Without Child | Distribution | Automation | 0 | 0 | 0 | 0 | 0 | 13386586.9667 | 26773173.9333 | 40159760.9 | 13386586.9667 | 26773173.9333 | This line item is for Reclosers, Bypass Switches (DA Equipment) purchased under the global Equipment and Material PW that do not currently have a child project based on current allocations. Also includes CFCIs ($12M) that are contracted.
110 | 3 | Y | Remain Inactive | 334285 | FAASt [Feeders - Mayaguez Short Term Group 2] (Distribution ) | Distribution | Line Rebuild | 4620072.9057 | 44030498.0943 | 0 | 0 | 0 | 0 | 0 | 84538316 | 48650571 | 35887745 | A new strategy has been developed to submit Distribution Line Rebuild Projects by individual feeder instead of groups and given the limited federal funds, the D-Line Rebuilds will be prioritizing tier 1 feeders that were based on CMI greater than 3.5M. The following feeder(s) from this project have aleady been given an individual FAAST number: 6802-04 ,6305-03. Therefore, this project scope will only include feeder(s) 6010-01 ,6306-02, which currently has an incurred cost of approximately $2,769,998.26 and an estimate project cost of $36,777,000.00
111 | 3 | Y | Remain Inactive | 334191 | FAASt [Feeders - Mayaguez Short Term Group 3] (Distribution) | Distribution | Line Rebuild | 9689812.0883 | 34985734.9117 | 0 | 0 | 0 | 0 | 0 | 83159291 | 44675547 | 38483744 | A new strategy has been developed to submit Distribution Line Rebuild Projects by individual feeder instead of groups. Given the limited federal funds, the D-Line Rebuilds will be prioritizing tier 1 feeders that were based on CMI greater than 3.5M. Any other feeders in this project will be lower priority. Therefore, this project scope will only include feeder(s) 6406-02, 6704-03, 6603-01, which currently has an incurred cost of approximately $6,789,077.47 and an estimated project cost of $60,267,537.38
112 | 3 | Y | Remain Inactive | 818006 | FAASt [Feeder Rebuild #2402-02] (Distribution) | Distribution | Line Rebuild | 1558972.44 | 32957504.56 | 0 | 0 | 0 | 0 | 0 | 34516477 | 34516477 | Unknown at this time* | This is an individual Feeder Project.
113 | 3 | Y | Remain Inactive | 818056 | FAASt # [Distribution Feeder Rebuild # 6305-03] (Distribution) | Distribution | Line Rebuild | 2354038.29 | 19998175.71 | 0 | 0 | 0 | 0 | 0 | 22352214 | 22352214 | Unknown at this time* | This is an individual Feeder Project.
114 | 3 | Y | Remain Inactive | 956782 | FAASt [Distribution Feeder Rebuild # 6802-04] (Distribution) | Distribution | Line Rebuild | 1626377.36 | 20331248.27 | 0 | 0 | 0 | 0 | 0 | 24727579.81 | 21957625.63 | 2769954.18 | This is an individual Feeder Project.
115 | 3 | Y | Remain Inactive | 546374 | FAASt [Feeders - 1620-02 - San Juan Short Term Group 3] (Distribution) | Distribution | Line Rebuild | 2563501.36 | 18494658.64 | 0 | 0 | 0 | 0 | 0 | 33835719 | 21058160 | 12777559 | A new strategy has been developed to submit Distribution Line Rebuild Projects by individual feeder instead of groups. Given the limited federal funds, the D-Line Rebuilds will be prioritizing tier 1 feeders that were based on CMI greater than 3.5M. Any other feeders in this project will be lower priority. Therefore, this project scope will only include feeder(s) 1336-08, which currently has an incurred cost of approximately $1,145,511.47 and an estimated project cost of $26,379,729.00
116 | 3 | Y | Remain Inactive | 334472 | FAASt [Feeders - San Juan Short Term Group 2] (Distribution) | Distribution | Line Rebuild | 3857112.7649 | 14926637.2351 | 0 | 0 | 0 | 0 | 0 | 24150405 | 18783750 | 5366655 | A new strategy has been developed to submit Distribution Line Rebuild Projects by individual feeder instead of groups. Given the limited federal funds, the D-Line Rebuilds will be prioritizing tier 1 feeders that were based on CMI greater than 3.5M. Any other feeders in this project will be lower priority. Therefore, this project scope will only include feeder(s) 1909-09, which currently has an incurred cost of approximately $1,207,238.84 and an estimated project cost of $5,499,761.00
117 | 3 | Y | Remain Inactive | 760575 | FAASt [Distribution Feeder Rebuild # 1716-03] (Distribution) | Distribution | Line Rebuild | 1777925.45 | 16324481.55 | 0 | 0 | 0 | 0 | 0 | 18102407 | 18102407 | Unknown at this time* | This is an individual Feeder Project.
118 | 3 | Y | Remain Inactive | 760571 | FAASt [Feeder Rebuild # 1720-07] (Distribution) | Distribution | Line Rebuild | 2261284.58 | 15743849.42 | 0 | 0 | 0 | 0 | 0 | 18005134 | 18005134 | Unknown at this time* | This is an individual Feeder Project.
119 | 3 | Y | Remain Inactive | 334473 | FAASt [Feeders - 1806-02- Bayamon Short Term Group 1] (Distribution) | Distribution | Line Rebuild | 1058798.48 | 16474262.19 | 0 | 0 | 0 | 0 | 0 | 18706307.83 | 17533060.67 | 1173247.16 | A new strategy has been developed to submit Distribution Line Rebuild Projects by individual feeder instead of groups and given the limited federal funds, the D-Line Rebuilds will be prioritizing tier 1 feeders that were based on CMI greater than 3.5M. Any other feeders in this project will be lower priority. The following feeder(s) from this project have aleady been given an individual FAAST number: 1718-02 ,1710-01 ,1717-03 ,1716-03 ,1720-07. Therefore, this project scope will only include feeder(s) 1806-02, which currently has an incurred cost of approximately $1,023,703.63 and an estimate project cost of $18,706,307.83.
120 | 3 | Y | Remain Inactive | 738667 | FAASt [Pole and Conductor Repair - Ponce Group 2 - Phase 2] (Distribution) | Distribution | Pole and Conductors | 387178.77 | 16231022.92 | 0 | 0 | 0 | 0 | 0 | 16651469.73 | 16618201.69 | 33268.04 | The Engineering is 100% completed. This project involves the replacement of approximately 510 Distribution Poles.
121 | 3 | Y | Remain Inactive | 730541 | FAASt [Feeders - Caguas Short Term Group 8] (Distribution) | Distribution | Line Rebuild | 2623407.9983 | 11899868.0017 | 0 | 0 | 0 | 0 | 0 | 33194732 | 14523276 | 18671456 | A new strategy has been developed to submit Distribution Line Rebuild Projects by individual feeder instead of groups and given the limited federal funds, the D-Line Rebuilds will be prioritizing tier 1 feeders that were based on CMI greater than 3.5M. Any other feeders in this project will be lower priority. The following feeder(s) from this project have aleady been given an individual FAAST number: 3701-03. Therefore, this project scope will only include feeder(s) 2603-08, which currently has an incurred cost of approximately $2,577,874.42 and an estimate project cost of $34,973,000.00.
122 | 3 | Y | Remain Inactive | 760579 | FAASt [Distribution Feeder Rebuild # 1717-03] (Distribution) | Distribution | Line Rebuild | 1524869 | 12618597 | 0 | 0 | 0 | 0 | 0 | 14143466 | 14143466 | Unknown at this time* | This is an individual Feeder Project.
123 | 3 | Y | Remain Inactive | 817247 | FAASt [Pole and Conductor Repair -Ponce Group 3 - Phase 2 | Distribution | Pole and Conductors | 321084.64 | 11328915.36 | 0 | 0 | 0 | 0 | 0 | 11650000 | 11650000 | Unknown at this time* | The Engineering is 100% completed. This project involves the replacement of approximately 266 Distribution Poles.
124 | 3 | Y | Remain Inactive | 760568 | FAASt [Distribution Feeder Rebuild # 1710-01] (Distribution) | Distribution | Line Rebuild | 1441005.22 | 9026842.78 | 0 | 0 | 0 | 0 | 0 | 10467848 | 10467848 | Unknown at this time* | This is an individual Feeder Project.
125 | 3 | Y | Remain Inactive | 764706 | FAASt [Feeder Rebuild # 7011-03] (Distribution) | Distribution | Line Rebuild | 1313746.05 | 8016035.35 | 0 | 0 | 0 | 0 | 0 | 9329781.4 | 9329781.4 | Unknown at this time* | This is an individual Feeder Project.
126 | 3 | Y | Remain Inactive | 759004 | FAASt [Pole and Conductor - Arecibo Group 4 - Phase 2] (Distribution) | Distribution | Pole and Conductors | 137733.46 | 9142266.54 | 0 | 0 | 0 | 0 | 0 | 9280000 | 9280000 | Unknown at this time* | The Engineering is 100% completed. The DSOW is 80% finalized for submission to FEMA. This project involves the replacement of approximately 214 Distribution Poles.
127 | 3 | Y | Remain Inactive | 738674 | FAASt [Pole and Conductor Repair - Mayaguez Group 2 - Phase 2] (Distribution) | Distribution | Pole and Conductors | 160424.36 | 8775413.13 | 0 | 0 | 0 | 0 | 0 | 8963968.02 | 8935837.49 | 28130.53 | The Engineering is 100% completed. This project involves the replacement of approximately 260 Distribution Poles.
128 | 3 | Y | Remain Inactive | 817250 | FAASt [Pole and Conductor Repair -San Juan Group 4 - Phase 2 | Distribution | Pole and Conductors | 112821.18 | 7497178.82 | 0 | 0 | 0 | 0 | 0 | 7610000 | 7610000 | Unknown at this time* | The Engineering is 100% completed. This project involves the replacement of approximately 118 Distribution Poles.
129 | 3 | Y | Remain Inactive | 546386 | FAASt [Feeders- El Yunque 2305 - Supply] (Distribution) | Distribution | Line Rebuild | 1640643.01 | 4923747.99 | 0 | 0 | 0 | 0 | 0 | 29816428 | 6564391 | 23252037 | A new strategy has been developed to submit Distribution Line Rebuild Projects by individual feeder instead of groups. Given the limited federal funds, the D-Line Rebuilds will be prioritizing tier 1 feeders that were based on CMI greater than 3.5M. Any other feeders in this project will be lower priority.
130 | 3 | Y | Remain Inactive | 817962 | FAASt # [Distribution Feeder Rebuild # 9403-03] (Distribution) | Distribution | Line Rebuild | 774849.6191 | 4774099.3809 | 0 | 0 | 0 | 0 | 0 | 5548949 | 5548949 | Unknown at this time* | This is an individual Feeder Project.
131 | 3 | Y | Remain Inactive | 764708 | FAASt [Feeder Rebuild # 5602-02] (Distribution) | Distribution | Line Rebuild | 1629697.74 | 3560689.78 | 0 | 0 | 0 | 0 | 0 | 5190387.52 | 5190387.52 | Unknown at this time* | This is an individual Feeder Project.
132 | 3 | Y | Remain Inactive | 806936 | FAASt [Pole and Conductor Repair - Carolina Group 3 - Phase 2] (Distribution) | Distribution | Pole and Conductors | 207389.83 | 4892610.17 | 0 | 0 | 0 | 0 | 0 | 5100000 | 5100000 | Unknown at this time* | The Engineering is 100% completed. The DSOW is 80% finalized for submission to FEMA. This project involves the replacement of approximately 76 Distribution Poles.
133 | 3 | Y | Remain Inactive | 738692 | FAASt [Pole and Conductor Repair - Carolina Group 1 - Phase 2] (Distribution) | Distribution | Pole and Conductors | 66885.3 | 5033114.7 | 0 | 0 | 0 | 0 | 0 | 5100000 | 5100000 | Unknown at this time* | The Engineering is 100% completed. This project involves the replacement of approximately 33 Distribution Poles.
134 | 3 | Y | Remain Inactive | 759051 | FAASt [Pole and Conductor Repair - Bayamon Group 4 - Phase 2] (Distribution) | Distribution | Pole and Conductors | 40780.53 | 3949219.47 | 0 | 0 | 0 | 0 | 0 | 3990000 | 3990000 | Unknown at this time* | The Engineering is 100% completed. The DSOW is 80% finalized for submission to FEMA. This project involves the replacement of approximately 70 Distribution Poles.
135 | 3 | Y | Remain Inactive | 801197 | FAASt [Feeder Rebuild # 1204-02] (Distribution) | Distribution | Line Rebuild | 2255341.27 | 1608016.73 | 0 | 0 | 0 | 0 | 0 | 3863358 | 3863358 | Unknown at this time* | This is an individual Feeder Project.
136 | 3 | Y | Remain Inactive | 767139 | FAASt [Feeder Rebuild # 2906-02] (Distribution) | Distribution | Line Rebuild | 1206587.62 | 1998453.38 | 0 | 0 | 0 | 0 | 0 | 3205041 | 3205041 | Unknown at this time* | This is an individual Feeder Project.
137 | 3 | Y | Remain Inactive | 817242 | FAASt [Pole and Conductor Repair -Caguas Group 8 - Phase 2 | Distribution | Pole and Conductors | 86773.02 | 1953226.98 | 0 | 0 | 0 | 0 | 0 | 2040000 | 2040000 | Unknown at this time* | The Engineering is 100% completed. The DSOW is 80% finalized for submission to FEMA. This project involves the replacement of approximately 75 Distribution Poles.
138 | 3 | Y | Remain Inactive | 705503 | FAASt [Pole and Conductor Repair Mayaguez Groups 15,16,17,18 & 19] (Distribution) | Distribution | Pole and Conductors | 287737.28 | 1330204.72 | 0 | 0 | 0 | 0 | 0 | 1810047 | 1617942 | 192105 | The Engineering is 100% completed. This project involves the replacement of approximately 48 Distribution Poles.
139 | 3 | Y | Remain Inactive | 710026 | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 17] (Distribution) | Distribution | Pole and Conductors | 5384.54 | 1244615.46 | 0 | 0 | 0 | 0 | 0 | 1250000 | 1250000 | Unknown at this time* | The project scope has been defined based on the HLAs. The final confirmed scope will be established upon completion of the engineering phase.
140 | 3 | Y | Remain Inactive | 710498 | FAASt [Distribution Pole and Conductor Repair - Bayamon Group 16] (Distribution) | Distribution | Pole and Conductors | 5098.91 | 1244901.09 | 0 | 0 | 0 | 0 | 0 | 1250000 | 1250000 | Unknown at this time* | The project scope has been defined based on the HLAs. The final confirmed scope will be established upon completion of the engineering phase.
141 | 3 | Y | Remain Inactive | 710363 | FAASt [Distribution Pole and Conductor Repair - Bayamon Group 15] (Distribution) | Distribution | Pole and Conductors | 4993.66 | 1245006.34 | 0 | 0 | 0 | 0 | 0 | 1250000 | 1250000 | Unknown at this time* | The project scope has been defined based on the HLAs. The final confirmed scope will be established upon completion of the engineering phase.
142 | 3 | Y | Remain Inactive | 712981 | FAASt [Distribution Pole and Conductor Repair - Ponce Group 24] (Distribution) | Distribution | Pole and Conductors | 3672.43 | 1246327.57 | 0 | 0 | 0 | 0 | 0 | 1250000 | 1250000 | Unknown at this time* | The project scope has been defined based on the HLAs. The final confirmed scope will be established upon completion of the engineering phase.
143 | 3 | Y | Remain Inactive | 710045 | FAASt [Distribution Pole and Conductor Repair -Mayaguez Group 20] (Distribution) | Distribution | Pole and Conductors | 2939.26 | 1247060.74 | 0 | 0 | 0 | 0 | 0 | 1250000 | 1250000 | Unknown at this time* | The project scope has been defined based on the HLAs. The final confirmed scope will be established upon completion of the engineering phase.
144 | 3 | Y | Remain Inactive | 711962 | FAASt [Distribution Pole and Conductor Repair -Mayaguez Group 21] (Distribution) | Distribution | Pole and Conductors | 1411.39 | 1248588.61 | 0 | 0 | 0 | 0 | 0 | 1250000 | 1250000 | Unknown at this time* | The project scope has been defined based on the HLAs. The final confirmed scope will be established upon completion of the engineering phase.
145 | 3 | Y | Remain Inactive | 712982 | FAASt [Distribution Pole and Conductor Repair “ Mayaguez Group 23] (Distribution) | Distribution | Pole and Conductors | 976.3 | 1249023.7 | 0 | 0 | 0 | 0 | 0 | 1250000 | 1250000 | Unknown at this time* | The project scope has been defined based on the HLAs. The final confirmed scope will be established upon completion of the engineering phase.
146 | 3 | Y | Remain Inactive | 764707 | FAASt [Feeder Rebuild # 6012-02] (Distribution) | Distribution | Line Rebuild | 2862242.58 | 7136246.42 | 0 | 0 | 0 | 0 | 0 | 9998489 | 9998489 | Unknown at this time* | This is an individual Feeder Project.
147 | 3 | Y | Remain Inactive | 764705 | FAASt [Feeder Rebuild # 6014-02] (Distribution) | Distribution | Line Rebuild | 2798780.93 | 1999598.06 | 0 | 0 | 0 | 0 | 0 | 4798378.99 | 4798378.99 | Unknown at this time* | This is an individual Feeder Project.
148 | 3 | Y | Urgent Incremental Projects / Incremental Projects | Pending FAASt Number | Distribution Automation Program remaining 88 Groups (Group #103 to Group #190) *Former Bucket 84 | Distribution | Automation | 13366709.19 | 41089074.486 | 27392716.324 | 1523804.8477 | 1015869.8984 | 6496220.6663 | 4330813.7776 | 81848500 | 49109100 | 32739400 | The Automation Program included here is based on a grouping of projects that LUMA will split to separate groups during the formulation process as DSOWs are submitted to FEMA. This program has Approximately $61 million of cost Incurred to the E&M PW. To be clear, this line does not include "Work Completed" Distribution Automation, as construction has not commenced for the units included herein as we are pending FASST numbers.
149 | 3 | Y | Remain Inactive | 812041 | FAASt [Distribution Feeder Rebuild 9501-02] | Distribution | Line Rebuild | 1639505.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1347191.63 | This is an individual Feeder Project.
150 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair - Arecibo Group 05 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7642400 | 7260280 | 382120 | Project scope is 233 poles to be replaced form HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies based on scope of work by location.
151 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair - Arecibo Group 06 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15350400 | 14582880 | 767520 | Project scope is 468 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed . 428/406 split varies from pole to pole.
152 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair - Arecibo Group 07 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10463200 | 9940040 | 523160 | Project scope is 319 poles from HLAs performed final scope will be confirmed when engineering is completed . 428/406 split varies from pole to pole.
153 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair - Arecibo Group 08 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10266400 | 9753080 | 513320 | Project scope is 313 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed . 428/406 split varies from pole to pole.
154 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair - Arecibo Group 09 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12792000 | 12152400 | 639600 | Project scope is 390 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed . 428/406 split varies from pole to pole.
155 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Arecibo Group 10 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4723200 | 4487040 | 236160 | Project scope is 144 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed . 428/406 split varies from pole to pole.
156 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Arecibo Group 11 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10430400 | 9908880 | 521520 | Project scope is 318 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed . 428/406 split varies from pole to pole.
157 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Arecibo Group 12 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5936800 | 5639960 | 296840 | Project scope is 181 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed . 428/406 split varies from pole to pole.
158 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Arecibo Group 13 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1148000 | 1090600 | 57400 | Project scope is 35 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed . 428/406 split varies from pole to pole.
159 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Arecibo Group 14 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5346400 | 5079080 | 267320 | Project scope is 163 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed . 428/406 split varies from pole to pole.
160 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Arecibo Group 15 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4428000 | 4206600 | 221400 | Project scope is 135 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed . 428/406 split varies from pole to pole.
161 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Arecibo Group 16 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4788800 | 4549360 | 239440 | Project scope is 146 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed . 428/406 split varies from pole to pole.
162 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Arecibo Group 17 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1344800 | 1277560 | 67240 | Project scope is 41 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed . 428/406 split varies from pole to pole.
163 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Arecibo Group 18 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 656000 | 623200 | 32800 | Project scope is 20 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed . 428/406 split varies from pole to pole.
164 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Bayamon Group 05 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2591200 | 2461640 | 129560 | Project scope is 79 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed . 428/406 split varies from pole to pole.
165 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Bayamon Group 06 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1869600 | 1776120 | 93480 | Project scope is 57 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed . 428/406 split varies from pole to pole.
166 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Bayamon Group 07 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18991200 | 18041640 | 949560 | Project scope is 579 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed . 428/406 split varies from pole to pole.
167 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Bayamon Group 08 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8593600 | 8163920 | 429680 | Project scope is 262 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed . 428/406 split varies from pole to pole.
168 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Bayamon Group 09 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12496800 | 11871960 | 624840 | Project scope is 381 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed . 428/406 split varies from pole to pole.
169 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Bayamon Group 10 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8560800 | 8132760 | 428040 | Project scope is 261 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed . 428/406 split varies from pole to pole.
170 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Bayamon Group 11 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7216000 | 6855200 | 360800 | Project scope is 220 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed . 428/406 split varies from pole to pole.
171 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Bayamon Group 12 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3378400 | 3209480 | 168920 | Project scope is 103 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed . 428/406 split varies from pole to pole.
172 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Bayamon Group 13 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3181600 | 3022520 | 159080 | Project scope is 97 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed . 428/406 split varies from pole to pole.
173 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Bayamon Group 14 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8659200 | 8226240 | 432960 | Project scope is 264 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed . 428/406 split varies from pole to pole.
174 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Bayamon Group 15 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1968000 | 1869600 | 98400 | Project scope is 60 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed . 428/406 split varies from pole to pole.
175 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Bayamon Group 16 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1344800 | 1277560 | 67240 | Project scope is 41 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed . 428/406 split varies from pole to pole.
176 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Bayamon Group 18 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1541600 | 1464520 | 77080 | Project scope is 47 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed . 428/406 split varies from pole to pole.
177 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Caguas Group 09 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13972800 | 13274160 | 698640 | Project scope is 426 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed . 428/406 split varies from pole to pole.
178 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Caguas Group 10 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7150400 | 6792880 | 357520 | Project scope is 218 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed . 428/406 split varies from pole to pole.
179 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Caguas Group 11 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12070400 | 11466880 | 603520 | Project scope is 368 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed . 428/406 split varies from pole to pole.
180 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Caguas Group 12 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8495200 | 8070440 | 424760 | Project scope is 259 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed . 428/406 split varies from pole to pole.
181 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Caguas Group 13 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9610400 | 9129880 | 480520 | Project scope is 293 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
182 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Caguas Group 14 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7642400 | 7260280 | 382120 | Project scope is 233 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
183 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Caguas Group 15 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9249600 | 8787120 | 462480 | Project scope is 282 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
184 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Caguas Group 16 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 820000 | 779000 | 41000 | Project scope is 25 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
185 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Caguas Group 17 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2656800 | 2523960 | 132840 | Project scope is 81 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
186 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Caguas Group 18 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2755200 | 2617440 | 137760 | Project scope is 84 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
187 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Caguas Group 19 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1902400 | 1807280 | 95120 | Project scope is 58 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
188 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Caguas Group 20 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1344800 | 1277560 | 67240 | Project scope is 41 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
189 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Mayaguez Group 06 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10922400 | 10376280 | 546120 | Project scope is 333 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
190 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Mayaguez Group 07 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6560000 | 6232000 | 328000 | Project scope is 200 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
191 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Mayaguez Group 08 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7544000 | 7166800 | 377200 | Project scope is 230 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
192 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Mayaguez Group 09 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7248800 | 6886360 | 362440 | Project scope is 221 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
193 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Mayaguez Group 10 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23976800 | 22777960 | 1198840 | Project scope is 731 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
194 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Mayaguez Group 11 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1574400 | 1495680 | 78720 | Project scope is 48 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
195 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Mayaguez Group 12 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000800 | 1900760 | 100040 | Project scope is 61 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
196 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Mayaguez Group 13 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3411200 | 3240640 | 170560 | Project scope is 104 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
197 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Mayaguez Group 14 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2492800 | 2368160 | 124640 | Project scope is 76 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
198 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Mayaguez Group 15 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1738400 | 1651480 | 86920 | Project scope is 53 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
199 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Mayaguez Group 16 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5051200 | 4798640 | 252560 | Project scope is 154 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
200 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Mayaguez Group 17 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4559200 | 4331240 | 227960 | Project scope is 139 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
201 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Mayaguez Group 18 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3509600 | 3334120 | 175480 | Project scope is 107 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
202 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Mayaguez Group 19 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2230400 | 2118880 | 111520 | Project scope is 68 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
203 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Mayaguez Group 20 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 590400 | 560880 | 29520 | Project scope is 18 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
204 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Mayaguez Group 21 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 524800 | 498560 | 26240 | Project scope is 16 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
205 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Mayaguez Group 22 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 557600 | 529720 | 27880 | Project scope is 17 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
206 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Mayaguez Group 23 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 328000 | 311600 | 16400 | Project scope is 10 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
207 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Ponce Group 04 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8429600 | 8008120 | 421480 | Project scope is 257 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
208 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Ponce Group 05 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5248000 | 4985600 | 262400 | Project scope is 160 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
209 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Ponce Group 06 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4034400 | 3832680 | 201720 | Project scope is 123 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
210 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Ponce Group 07 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 984000 | 934800 | 49200 | Project scope is 30 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
211 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Ponce Group 08 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3509600 | 3334120 | 175480 | Project scope is 107 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
212 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Ponce Group 09 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13743200 | 13056040 | 687160 | Project scope is 419 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
213 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Ponce Group 10 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5313600 | 5047920 | 265680 | Project costs based on assumption of $32,800.00 per pole. 162 poles submitted from HLAs. 428/406 split varies from pole to pole.
214 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Ponce Group 11 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6494400 | 6169680 | 324720 | Project scope is 198 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
215 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Ponce Group 12 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4526400 | 4300080 | 226320 | Project scope is 138 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
216 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Ponce Group 13 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2919200 | 2773240 | 145960 | Project scope is 89 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
217 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Ponce Group 14 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1377600 | 1308720 | 68880 | Project scope is 42 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
218 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Ponce Group 15 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3903200 | 3708040 | 195160 | Project scope is 119 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
219 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Ponce Group 16 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2164800 | 2056560 | 108240 | Project scope is 66 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
220 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Ponce Group 17 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1148000 | 1090600 | 57400 | Project scope is 35 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
221 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Ponce Group 18 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1312000 | 1246400 | 65600 | Project scope is 40 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
222 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Ponce Group 19 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 918400 | 872480 | 45920 | Project scope is 28 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
223 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Ponce Group 21 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2361600 | 2243520 | 118080 | Project scope is 72 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
224 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Ponce Group 22 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 328000 | 311600 | 16400 | Project scope is 10 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
225 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Ponce Group 23 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 295200 | 280440 | 14760 | Project scope is 9 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
226 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-Ponce Group 24 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1476000 | 1402200 | 73800 | Project scope is 45 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
227 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-San Juan Group 05 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4100000 | 3895000 | 205000 | Project scope is 125 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
228 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-San Juan Group 06 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15416000 | 14645200 | 770800 | Project scope is 470 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
229 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-San Juan Group 07 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7183200 | 6824040 | 359160 | Project scope is 219 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
230 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-San Juan Group 07/San Juan Group 55 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 295200 | 280440 | 14760 | Project scope is 9 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
231 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-San Juan Group 08 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3870400 | 3676880 | 193520 | Project scope is 118 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
232 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-San Juan Group 09 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4231200 | 4019640 | 211560 | Project scope is 129 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
233 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-San Juan Group 10 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2033600 | 1931920 | 101680 | Project scope is 62 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
234 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-San Juan Group 11 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5018400 | 4767480 | 250920 | Project scope is 153 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
235 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-San Juan Group 11/San Juan Group 55 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 623200 | 592040 | 31160 | Project scope is 19 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
236 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-San Juan Group 12 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3870400 | 3676880 | 193520 | Project scope is 118 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
237 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-San Juan Group 13 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 262400 | 249280 | 13120 | Project scope is 8 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
238 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-San Juan Group 14 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5149600 | 4892120 | 257480 | Project scope is 157 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
239 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-San Juan Group 15 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1115200 | 1059440 | 55760 | Project scope is 34 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
240 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-San Juan Group 16 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 852800 | 810160 | 42640 | Project scope is 26 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
241 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-San Juan Group 17 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1738400 | 1651480 | 86920 | Project scope is 53 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
242 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-San Juan Group 18 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6658400 | 6325480 | 332920 | Project scope is 203 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
243 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-San Juan Group 19 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The project scope has been defined based on the HLAs. The final confirmed scope will be established upon completion of the engineering phase.
244 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-San Juan Group 20 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2853600 | 2710920 | 142680 | Project scope is 87 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
245 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Pole and Conductor Repair-San Juan Group 21 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3017600 | 2866720 | 150880 | Project scope is 87 poles to be replaced from HLAs performed final scope will be confirmed when engineering is completed. 428/406 split varies from pole to pole.
246 | 3 | Y | Incremental Project List | Pending FAASt Number | Distribution Feeder Rebuild # 1118-08 | Distribution | Line Rebuild | 5736.83 | 0 | 0 | 0 | 0 | 0 | 0 | 4205003.39 | 3868603.1188 | 336400.2712 | Distribution Line Rebuild - 1.4 miles.
247 | 3 | Y | Incremental Project List | Pending FAASt Number | Distribution Feeder Rebuild # 1118-09 | Distribution | Line Rebuild | 2651.77 | 0 | 0 | 0 | 0 | 0 | 0 | 4505360.77 | 4144931.9084 | 360428.8616 | Distribution Line Rebuild - 1.5 miles.
248 | 3 | Y | Incremental Project List | Pending FAASt Number | Distribution Feeder Rebuild # 1206-03 | Distribution | Line Rebuild | 1106.28 | 0 | 0 | 0 | 0 | 0 | 0 | 12765188.86 | 11743973.7512 | 1021215.1088 | Distribution Line Rebuild - 4.25 miles.
249 | 3 | Y | Incremental Project List | Pending FAASt Number | Distribution Feeder Rebuild # 1336-07 | Distribution | Line Rebuild | 6263.82 | 0 | 0 | 0 | 0 | 0 | 0 | 11203330.46 | 10307064.0232 | 896266.4368 | Distribution Line Rebuild - 3.73 miles.
250 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Feeder Rebuild # 1346-03 | Distribution | Line Rebuild | -445.4 | 0 | 0 | 0 | 0 | 0 | 0 | 8259828.09 | 7599041.8428 | 660786.2472 | Distribution Line Rebuild - 2.75 miles.
251 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Feeder Rebuild # 1529-11 | Distribution | Line Rebuild | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8109649.39 | 7460877.4388 | 648771.9512 | Distribution Line Rebuild - 2.7 miles.
252 | 3 | Y | Incremental Project List | Pending FAASt Number | Distribution Feeder Rebuild # 1709-02 | Distribution | Line Rebuild | 3227.53 | 0 | 0 | 0 | 0 | 0 | 0 | 8259828.09 | 7599041.8428 | 660786.2472 | Distribution Line Rebuild - 2.75 miles.
253 | 3 | Y | Incremental Project List | Pending FAASt Number | Distribution Feeder Rebuild # 1709-05 | Distribution | Line Rebuild | 4728.14 | 0 | 0 | 0 | 0 | 0 | 0 | 11075781 | 10189718.52 | 886062.48 | Distribution Line Rebuild - 2.5 miles.
254 | 3 | Y | Incremental Project List | Pending FAASt Number | Distribution Feeder Rebuild # 1711-05 | Distribution | Line Rebuild | 2665.69 | 0 | 0 | 0 | 0 | 0 | 0 | 6007147.7 | 5526575.884 | 480571.816 | Distribution Line Rebuild - 2 miles.
255 | 3 | Y | Incremental Project List | Pending FAASt Number | Distribution Feeder Rebuild # 1713-05 | Distribution | Line Rebuild | 6189.43 | 0 | 0 | 0 | 0 | 0 | 0 | 12314652.78 | 11329480.5576 | 985172.2224 | Distribution Line Rebuild - 4.1 miles.
256 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Feeder Rebuild # 1714-02 | Distribution | Line Rebuild | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3754467.31 | 3454109.9252 | 300357.3848 | Distribution Line Rebuild - 1.25 miles.
257 | 3 | Y | Incremental Project List | Pending FAASt Number | Distribution Feeder Rebuild # 1717-01 | Distribution | Line Rebuild | 2841.76 | 0 | 0 | 0 | 0 | 0 | 0 | 7508934.63 | 6908219.8596 | 600714.7704 | Distribution Line Rebuild - 2.5 miles.
258 | 3 | Y | Incremental Project List | Pending FAASt Number | Distribution Feeder Rebuild # 1719-15 | Distribution | Line Rebuild | 8753.24 | 0 | 0 | 0 | 0 | 0 | 0 | 7508934.63 | 6908219.8596 | 600714.7704 | Distribution Line Rebuild - 2.5 miles.
259 | 3 | Y | Incremental Project List | Pending FAASt Number | Distribution Feeder Rebuild # 1719-18 | Distribution | Line Rebuild | 1700.06 | 0 | 0 | 0 | 0 | 0 | 0 | 11263401.93 | 10362329.7756 | 901072.1544 | Distribution Line Rebuild - 3.75 miles.
260 | 3 | Y | Incremental Project List | Pending FAASt Number | Distribution Feeder Rebuild # 1907-05 | Distribution | Line Rebuild | 291.25 | 0 | 0 | 0 | 0 | 0 | 0 | 3003573.85 | 2763287.942 | 240285.908 | Distribution Line Rebuild - 1 miles.
261 | 3 | Y | Incremental Project List | Pending FAASt Number | Distribution Feeder Rebuild # 1908-03 | Distribution | Line Rebuild | 54.36 | 0 | 0 | 0 | 0 | 0 | 0 | 20694623.82 | 19039053.9144 | 1655569.9056 | Distribution Line Rebuild - 6.89 miles.
262 | 3 | Y | Incremental Project List | Pending FAASt Number | Distribution Feeder Rebuild # 2601-01 | Distribution | Line Rebuild | 11873.35 | 0 | 0 | 0 | 0 | 0 | 0 | 11263401.93 | 10362329.7756 | 901072.1544 | Distribution Line Rebuild - 3.75 miles.
263 | 3 | Y | Incremental Project List | Pending FAASt Number | Distribution Feeder Rebuild # 2603-09 | Distribution | Line Rebuild | 410.97 | 0 | 0 | 0 | 0 | 0 | 0 | 17661915.49 | 16248962.2508 | 1412953.2392 | Distribution Line Rebuild - 4.75 miles.
264 | 3 | Y | Incremental Project List | Pending FAASt Number | Distribution Feeder Rebuild # 2604-01 | Distribution | Line Rebuild | 3101.36 | 0 | 0 | 0 | 0 | 0 | 0 | 12765188.86 | 11743973.7512 | 1021215.1088 | Distribution Line Rebuild - 4.25 miles.
265 | 3 | N | Incremental Project List | Pending FAASt Number | Distribution Feeder Rebuild # 2901-04 | Distribution | Line Rebuild | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12765188.86 | 11743973.7512 | 1021215.1088 | Distribution Line Rebuild - 4.25 miles.
266 | 3 | Y | Incremental Project List | Pending FAASt Number | Distribution Feeder Rebuild # 3201-02 | Distribution | Line Rebuild | 567.35 | 0 | 0 | 0 | 0 | 0 | 0 | 15017869.25 | 13816439.71 | 1201429.54 | Distribution Line Rebuild - 5 miles.
267 | 3 | Y | Incremental Project List | Pending FAASt Number | Distribution Feeder Rebuild # 3701-02 | Distribution | Line Rebuild | 7659.65 | 0 | 0 | 0 | 0 | 0 | 0 | 5256254.23 | 4835753.8916 | 420500.3384 | Distribution Line Rebuild - 1.75 miles.
268 | 3 | Y | Incremental Project List | Pending FAASt Number | Distribution Feeder Rebuild # 4603-02 | Distribution | Line Rebuild | 5265.94 | 0 | 0 | 0 | 0 | 0 | 0 | 12014295.4 | 11053151.768 | 961143.632 | Distribution Line Rebuild - 4 miles.
269 | 3 | Y | Incremental Project List | Pending FAASt Number | Distribution Feeder Rebuild # 5016-01 | Distribution | Line Rebuild | 2015.38 | 0 | 0 | 0 | 0 | 0 | 0 | 11113223.25 | 10224165.39 | 889057.86 | Distribution Line Rebuild - 3.7 miles.
270 | 3 | Y | Incremental Project List | Pending FAASt Number | Distribution Feeder Rebuild # 5401-02 | Distribution | Line Rebuild | 454.35 | 0 | 0 | 0 | 0 | 0 | 0 | 8259828.09 | 7599041.8428 | 660786.2472 | Distribution Line Rebuild - 2.75 miles.
271 | 3 | Y | Incremental Project List | Pending FAASt Number | Distribution Feeder Rebuild # 5803-02 | Distribution | Line Rebuild | 1494.79 | 0 | 0 | 0 | 0 | 0 | 0 | 18021443.09 | 16579727.6428 | 1441715.4472 | Distribution Line Rebuild - 6 miles.
272 | 3 | Y | Incremental Project List | Pending FAASt Number | Distribution Feeder Rebuild # 6004-02 | Distribution | Line Rebuild | 1807.96 | 0 | 0 | 0 | 0 | 0 | 0 | 13816439.71 | 12711124.5332 | 1105315.1768 | Distribution Line Rebuild - 4.6 miles.
273 | 3 | Y | Incremental Project List | Pending FAASt Number | Distribution Feeder Rebuild # 6010-02 | Distribution | Line Rebuild | 285.76 | 0 | 0 | 0 | 0 | 0 | 0 | 15017869.25 | 13816439.71 | 1201429.54 | Distribution Line Rebuild - 5 miles.
274 | 3 | Y | Incremental Project List | Pending FAASt Number | Distribution Feeder Rebuild # 6101-04 | Distribution | Line Rebuild | 8022.88 | 0 | 0 | 0 | 0 | 0 | 0 | 12615010.17 | 11605809.3564 | 1009200.8136 | Distribution Line Rebuild - 4.2 miles.
275 | 3 | Y | Incremental Project List | Pending FAASt Number | Distribution Feeder Rebuild # 6101-05 | Distribution | Line Rebuild | 805.54 | 0 | 0 | 0 | 0 | 0 | 0 | 10512508.47 | 9671507.7924 | 841000.6776 | Distribution Line Rebuild - 3.5 miles.
276 | 3 | Y | Incremental Project List | Pending FAASt Number | Distribution Feeder Rebuild # 6501-04 | Distribution | Line Rebuild | 8026.2 | 0 | 0 | 0 | 0 | 0 | 0 | 9761615.02 | 8980685.8184 | 780929.2016 | Distribution Line Rebuild - 3.25 miles.
277 | 3 | Y | Incremental Project List | Pending FAASt Number | Distribution Feeder Rebuild # 7201-05 | Distribution | Line Rebuild | 13405.44 | 0 | 0 | 0 | 0 | 0 | 0 | 13516082.32 | 12434795.7344 | 1081286.5856 | Distribution Line Rebuild - 4.5 miles.
278 | 3 | Y | Incremental Project List | Pending FAASt Number | Distribution Feeder Rebuild # 7504-01 | Distribution | Line Rebuild | 731.18 | 0 | 0 | 0 | 0 | 0 | 0 | 6908219.86 | 6355562.2712 | 552657.5888 | Distribution Line Rebuild - 2.3 miles.
279 | 3 | Y | Incremental Project List | Pending FAASt Number | Distribution Feeder Rebuild # 8104-02 | Distribution | Line Rebuild | 8736.35 | 0 | 0 | 0 | 0 | 0 | 0 | 12014295.4 | 11053151.768 | 961143.632 | Distribution Line Rebuild - 4 miles.
280 | 3 | Y | Incremental Project List | Pending FAASt Number | Distribution Feeder Rebuild # 8202-01 | Distribution | Line Rebuild | 5594.11 | 0 | 0 | 0 | 0 | 0 | 0 | 4505360.77 | 4144931.9084 | 360428.8616 | Distribution Line Rebuild - 1.5 miles.
281 | 3 | Y | Incremental Project List | Pending FAASt Number | Distribution Feeder Rebuild # 9004-08 | Distribution | Line Rebuild | 1297.28 | 0 | 0 | 0 | 0 | 0 | 0 | 22827161.26 | 21000988.3592 | 1826172.9008 | Distribution Line Rebuild - 7.6 miles.
282 | 3 | Y | Incremental Project List | Pending FAASt Number | Distribution Feeder Rebuild # 9004-10 | Distribution | Line Rebuild | 4771.77 | 0 | 0 | 0 | 0 | 0 | 0 | 21325374.33 | 19619344.3836 | 1706029.9464 | Distribution Line Rebuild - 7.1 miles.
283 | 3 | Y | Incremental Project List | Pending FAASt Number | Distribution Feeder Rebuild # 9202-04 | Distribution | Line Rebuild | 10730.73 | 0 | 0 | 0 | 0 | 0 | 0 | 9761615.02 | 8980685.8184 | 780929.2016 | Distribution Line Rebuild - 3.25 miles.
284 | 3 | Y | Incremental Project List | Pending FAASt Number | Distribution Feeder Rebuild # 9501-01 | Distribution | Line Rebuild | 2032.72 | 0 | 0 | 0 | 0 | 0 | 0 | 11313401.93 | 10408329.7756 | 905072.1544 | Distribution Line Rebuild - 3.75 miles.
285 | 3 | Y | Incremental Project List | Pending FAASt Number | Distribution Feeder Rebuild # 9503-06 | Distribution | Line Rebuild | 14060.58 | 0 | 0 | 0 | 0 | 0 | 0 | 11713938.01 | 10776822.9692 | 937115.0408 | Distribution Line Rebuild - 3.9 miles.
286 | 3 | Y | Incremental Project List | Pending FAASt Number | Distribution Feeder Rebuild # 9605-02 | Distribution | Line Rebuild | 55749.64 | 0 | 0 | 0 | 0 | 0 | 0 | 20424302.18 | 18790358.0056 | 1633944.1744 | Distribution Line Rebuild - 6.8 miles.
287 | 3 | N | Incremental Project List | Pending FAASt Number | FAASt [Pole and Conductor Repair - Mayaguez Group 5 - Phase 2 | Distribution | Pole and Conductors | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 7610000 | TBD | TBD
288 | 3 | Y | Remain Inactive | 744072 | Network and Communication Infrastructure Group 2 | IT/OT | N/A | 0 | 2074582.38 | 0 | 0 | 0 | 0 | 0 | 2565020.45 | 2074582.38 | 490438.07
289 | 3 | N | Incremental Project List | Pending FAASt Number | Transport Network Group 4, 60 sites | IT/OT | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | $73,706,596.88 | $40,538,628.28 | $33,167,968.60 | 30% design not finish, not approved yet. Cost etsimate is based on cost per site and split calculations from Group 2 estimate.
290 | 3 | N | Incremental Project List | Pending FAASt Number | Transport Network Group 5, 60 sites | IT/OT | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | $73,706,596.88 | $40,538,628.28 | $33,167,968.60 | 30% design not finish, not approved yet. Cost etsimate is based on cost per site and split calculations from Group 2 estimate.
291 | 3 | N | Incremental Project List | Pending FAASt Number | Transport Network Group 6, 60 sites | IT/OT | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | $73,706,596.88 | $40,538,628.28 | $33,167,968.60 | 30% design not finish, not approved yet. Cost etsimate is based on cost per site and split calculations from Group 2 estimate.
292 | 3 | N | Incremental Project List | Pending FAASt Number | Transport Network Group 7, 68 sites | IT/OT | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | $83,534,143.14 | $45,943,778.72 | $37,590,364.41 | 30% design not finish, not approved yet. Cost etsimate is based on cost per site and split calculations from Group 2 estimate.
293 | 3 | N | Incremental Project List | Pending FAASt Number | Infrastructure Group I | IT/OT | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project under development by engineering.
294 | 3 | Y | Remain Inactive | 550162 | FAASt [Berwind TC - 1336] (Substation) | Substation | Substation Rebuild | 1498637.83 | 43451909.17 | 0 | 0 | 0 | 0 | 0 | 51668862 | 44950547 | 6718315 | Functional specifications will need to be revisited to reflect current electrical requirements in the area. Costs are expected to change.
295 | 3 | Y | Remain Inactive | 752276 | FAASt [Monterrey 9502 & 9503 (Fuse to Breaker)] (Substation) | Substation | Substation Rebuild | 1331190.5 | 38333029.5 | 0 | 0 | 0 | 0 | 0 | 39664220 | 39664220 | Unknown at this time*
296 | 3 | Y | Remain Inactive | 550972 | FAASt [Fonalledas GIS Rebuilt 1401 1421] (Substation) | Substation | Substation Rebuild | 58983.34 | 31341016.66 | 0 | 0 | 0 | 0 | 0 | 31400000 | 31400000 | Unknown at this time*
297 | 3 | Y | Remain Inactive | 761563 | FAASt [San Jose Relocation] (Substation) | Substation | Substation Rebuild | 676315.86 | 16323684.14 | 0 | 0 | 0 | 0 | 0 | 17000000 | 17000000 | Unknown at this time*
298 | 3 | Y | Remain Inactive | 551100 | FAASt [Bayview Sectionalizer 1802 Relocation] (Substation) | Substation | Substation Rebuild | 81042.88 | 16618957.12 | 0 | 0 | 0 | 0 | 0 | 16700000 | 16700000 | Unknown at this time*
299 | 3 | Y | Remain Inactive | 550498 | FAASt - [Morovis 8801 (Fuse to Breaker)] (Substation) | Substation | Substation Rebuild | 195445.43 | 16104554.57 | 0 | 0 | 0 | 0 | 0 | 16300000 | 16300000 | Unknown at this time*
300 | 3 | Y | Remain Inactive | 547243 | FAASt Egozcue - 1109 (Substation) | Substation | Substation Rebuild | 1875010.93 | 12021434.83 | 0 | 0 | 0 | 0 | 0 | 20848788.02 | 13896445.76 | 6952342.26
301 | 3 | Y | Remain Inactive | 551918 | FAASt Crematorio - 1512 | Substation | Substation Rebuild | 971849.15 | 11746435.85 | 0 | 0 | 0 | 0 | 0 | 18766686 | 12718285 | 6048401
302 | 3 | Y | Remain Inactive | 551912 | FAASt Puerto Nuevo - 1520 | Substation | Substation Rebuild | 916295.1 | 11275982.9 | 0 | 0 | 0 | 0 | 0 | 18227585 | 12192278 | 6035307
303 | 3 | Y | Remain Inactive | 550980 | FAASt [Parques y Recreos - 1002] (Substation) | Substation | Substation Rebuild | 914659.48 | 10822837.57 | 0 | 0 | 0 | 0 | 0 | 20700231.13 | 11737497.05 | 8962734.08
304 | 3 | Y | Remain Inactive | 547241 | FAASt Tallaboa 5402 | Substation | Substation Rebuild | 1194229.01 | 9730206.99 | 0 | 0 | 0 | 0 | 0 | 16553045 | 10924436 | 5628609
305 | 3 | Y | Remain Inactive | 550986 | FAASt Condado - 1133 | Substation | Substation Rebuild | 1063570.56 | 9586340.44 | 0 | 0 | 0 | 0 | 0 | 16077078 | 10649911 | 5427167
306 | 3 | Y | Remain Inactive | 550998 | FAASt [Santurce Planta (Sect) 1116] (Substation) | Substation | Substation Rebuild | 69542.23 | 9830457.77 | 0 | 0 | 0 | 0 | 0 | 9900000 | 9900000 | Unknown at this time*
307 | 3 | Y | Remain Inactive | 752275 | FAASt [Unibon 9501 (Fuse to Breaker)] (Substation) | Substation | Substation Rebuild | 806197.94 | 8351335.06 | 0 | 0 | 0 | 0 | 0 | 9157533 | 9157533 | Unknown at this time*
308 | 3 | Y | Remain Inactive | 547343 | FAASt [Victoria TC 7008 Relocation] (Substation) | Substation | Substation Rebuild | 2943473.75 | 3902971.15 | 0 | 0 | 0 | 0 | 0 | 61690733.88 | 6846444.9 | 54844288.98
309 | 3 | Y | Remain Inactive | 169503 | FAASt [Ceiba Baja TRF 7012] (Substation) | Substation | Substation Rebuild | 2826.1 | 2697173.9 | 0 | 0 | 0 | 0 | 0 | 2700000 | 2700000 | Unknown at this time*
310 | 3 | Y | Remain Inactive | 550771 | FAASt [Caguas TC] (Substation) | Substation | Substation Rebuild | 476249.32 | 2023750.68 | 0 | 0 | 0 | 0 | 0 | 2500000 | 2500000 | Unknown at this time*
311 | 3 | Y | Remain Inactive | 179988 | FAASt [Las Lomas XFMR 1525] (Substation) | Substation | Substation Rebuild | 12555.6 | 2387444.4 | 0 | 0 | 0 | 0 | 0 | 2400000 | 2400000 | Unknown at this time*
312 | 3 | Y | Remain Inactive | 547248 | FAASt Canas TC 5002 5018 (Substation) | Substation | Substation Rebuild | 65481.52 | 1634518.48 | 0 | 0 | 0 | 0 | 0 | 1700000 | 1700000 | Unknown at this time*
313 | 3 | Y | Remain Inactive | 550894 | FAASt [Baldrich - 1422] (Substation) | Substation | Substation Rebuild | 945895.54 | 27202.46 | 0 | 0 | 0 | 0 | 0 | 29642961 | 973098 | 28669863
314 | 3 | N | Incremental Project List | Pending FAASt Number | Manati TC Substation Rebuild | Substation | Substation Rebuild | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000000 | 54000000 | 36000000 | Rebuild of priority Transmission Center; will include in scope the rebuild of distribution substation 8404 Manatí TC and new 13.2 kV distribution substation.
315 | 3 | N | Incremental Project List | Pending FAASt Number | Santa Isabel TC Substation Rebuild | Substation | Substation Rebuild | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000000 | 36000000 | 24000000 | Rebuild of priority Transmission Center; will include in scope the rebuild of distribution substation 4402 Santa Isabel TC.
316 | 3 | N | Incremental Project List | Pending FAASt Number | Bayamon Pueblo Sect. Substation Rebuild | Substation | Substation Rebuild | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000000 | 24000000 | 16000000 | Rebuild of priority sectionalizing substation; will include in scope the rebuild of distribution substation 1715 Bayamón Pueblo II and rebuild and conversion of distribution substation 1701 Bayamón Pueblo to 13.2 kV (only 4.8 kV substation on system).
317 | 3 | N | Incremental Project List | Pending FAASt Number | Dos Bocas HP Substation Rebuild | Substation | Substation Rebuild | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000000 | 42000000 | 28000000 | Rebuild of priority Transmission Center; will include in scope the rebuild of distribution substation 8005 Dos Bocas.
318 | 3 | N | Incremental Project List | Pending FAASt Number | Pastillo Substation Rebuild | Substation | Substation Rebuild | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000000 | 3000000 | 17000000 | Rebuild of sectionalizing substation including colocated 5801 Pastillo distribution substations and rebuild in site distribution substation 5803 Fort Allen (destroyed in fire in early 2021 with loads being supplied by a mobile substation).
319 | 3 | N | Incremental Project List | Pending FAASt Number | Ponce TC Substation Rebuild | Substation | Substation Rebuild | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000000 | 36000000 | 24000000 | Rebuild of priority Transmission Center; will include in scope the rebuild of distribution substations 5001 Ponce Pueblo, 5010 Hostos 4 kV and 5011 Hostos 13 kV.
320 | 3 | N | Incremental Project List | Pending FAASt Number | Aguilita 5817 Substation Relocation | Substation | Substation Rebuild | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000000 | 1200000 | 10800000 | Relocation of substation 5817 due to flooding risk as it is located in area identified by FEMA as floodway.
321 | 3 | N | Incremental Project List | Pending FAASt Number | San Lorenzo 3301 Substation Relocation | Substation | Substation Rebuild | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000000 | 2000000 | 18000000 | Relocation of substation 3301 due to flooding risk as it is located in area identified by FEMA as floodway and co-location of new 13.2 kV substation to provide support and redundancy to substations 3205 Juncos TC 13 kV and 2603 Humacao TC 13 kV.
322 | 3 | N | Incremental Project List | Pending FAASt Number | New Breñas 13.2 kV Substation | Substation | Substation Rebuild | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000000 | 4500000 | 4500000 | New 13.2 kV substation in Breñas Sectionalizer to provide support and redundancy to substations 9206 Dorado PDS, 9207 Dorado TC and 9004 Vega Baja TC. Additional land adjacent to Breñas substation in process of being acquired from Dorado Beach Properties. Current scope considers re-using elements from the existing Cataño Substation including transformer, PDS and high side breaker.
323 | 3 | N | Incremental Project List | Pending FAASt Number | New Saint Just 13.2 kV Substation | Substation | Substation Rebuild | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000000 | 7500000 | 7500000 | New 13.2 kV substation and 38 kV sectionalizer adjacent to transmission lines 3100 and 3600 to provide support and redundancy to substations 1204 Conquistador, 1206 Encantada, 1620 Parque Escorial and 1336 Berwind TC. Land targeted for project is within/adjacent to ROW of 3100/3600 Tline adjacent to PR-199.
324 | 3 | N | Incremental Project List | Pending FAASt Number | New Yeguada (Camuy) Substation | Substation | Substation Rebuild | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000000 | 3000000 | 3000000 | New 13.2 kV substation to provide support and redundancy to substations 7601 Camuy, 7602 Camuy Provisional, 7402 Quebradillas and 7404 Quebradillas Provisional. Site already acquired by PREPA.
325 | 3 | N | TBD | PBUT8 | Rebuild Permanent Covadonga Station | Substation | Substation Rebuild | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000000 | 0 | 0 | The scope for permanent Covadonga is not finalized and an estimate has not been completed. This rebuild will require 4 transformer replacements, 2 38kV/13kV and 2 38 kV/4 kV and Gas Insulated Switchgear replacements for the 38 kV and the 4 kV side.
326 | 3 | Y | Remain Inactive | 718971 | FAASt [Line 50300 (230kV) from Costa Sur Steam Plant to Aguirre Steam Plant] (Transmission) | Transmission | Line Rebuild | 3238497.73 | -2233211.73 | 0 | 0 | 0 | 0 | 0 | 2882331 | 1005286 | 1877045
327 | 3 | Y | Remain Inactive / Appendix F | 730657 | FAASt [Line 2200 Dos Bocas HP to Dorado TC ] (Transmission) | Transmission | Rebuild | 9253031.2 | -6039791.98 | 0 | 0 | 0 | 0 | 0 | 13712378.93 | 3213239.22 | 10499139.71
328 | 3 | Y | Remain Inactive | 718955 | FAASt [Line 50200 (230kv) from Costa Sur SP to Bayamon TC] (Transmission) | Transmission | Line Rebuild | 2163740.7 | 150739296.3 | 0 | 0 | 0 | 0 | 0 | 241326433 | 152903037 | 88423396
329 | 3 | Y | Remain Inactive | 167168 | FAASt [Transmission 115kV Line 37100 Costa Sur ST - Acacias TC] (Transmission) | Transmission | Line Rebuild | 3819346.17 | 102825885.83 | 0 | 0 | 0 | 0 | 0 | 131291927 | 106645232 | 24646695
330 | 3 | Y | Remain Inactive | 718951 | FAASt [Line 51200- Costa Sur Steam Plant to Cambalache Gas Plant (230kV)] (Transmission) | Transmission | Line Rebuild | 1353887.73 | 94986836.27 | 0 | 0 | 0 | 0 | 0 | 160993028 | 96340724 | 64652304
331 | 3 | Y | Remain Inactive | 334482 | FAASt [Line 3000 (38 kV) Monacillos TC to Juncos TC] (Transmission) | Transmission | Line Rebuild | 3674995.73 | 86765004.27 | 0 | 0 | 0 | 0 | 0 | 90440000 | 90440000 | Unknown at this time*
332 | 3 | Y | Remain Inactive | 166860 | FAASt-Line 37800 (115kV) - Jobos TC to Cayey TC & Cayey TC to Caguas TC (Transmission) | Transmission | Line Rebuild | 3585161.26 | 78427427.74 | 0 | 0 | 0 | 0 | 0 | 101721912 | 82012589 | 19709323
333 | 3 | Y | Remain Inactive | 167508 | FAASt Transmission - Line 50100 (230KV)- Cambalache GP TC to Manati TC (Transmission) | Transmission | Line Rebuild | 1515388.42 | 77273300.58 | 0 | 0 | 0 | 0 | 0 | 83398644 | 78788689 | 4609955
334 | 3 | Y | Remain Inactive | 547259 | FAASt Line 2700 (38kV) Victoria TC to Quebradillas Sect. (Transmission) | Transmission | Line Rebuild | 1756826.25 | 69217899.75 | 0 | 0 | 0 | 0 | 0 | 126818634 | 70974726 | 55843908
335 | 3 | Y | Remain Inactive | 180326 | FAASt - Line 36800 (115kV) - Sabana Llana TC to Canovanas TC to Palmer-Fajardo TC (Transmission) | Transmission | Line Rebuild | 2936601.41 | 64302175.59 | 0 | 0 | 0 | 0 | 0 | 99727544 | 67238777 | 32488767
336 | 3 | Y | Remain Inactive | 547160 | FAASt [Line 1200 Mayaguez GP to Yauco 2 HP] (Transmission) | Transmission | Line Rebuild | 3829280.91 | 51540719.09 | 0 | 0 | 0 | 0 | 0 | 55370000 | 55370000 | Unknown at this time*
337 | 3 | Y | Remain Inactive | 166904 | FAASt Transmission 115kV Line 37800 Caguas TC to Monacillos TC (TRANSMISSION) | Transmission | Line Rebuild | 1875962.29 | 48524625.71 | 0 | 0 | 0 | 0 | 0 | 59630023 | 50400588 | 9229435
338 | 3 | Y | Remain Inactive | 548598 | FAASt [Line 36200 (115 kV) Fajardo to Rio Blanco] (Transmission) | Transmission | Line Rebuild | 1150801.77 | 41039685.23 | 0 | 0 | 0 | 0 | 0 | 58153916 | 42190487 | 15963429
339 | 3 | Y | Remain Inactive | 547221 | FAASt [Line 3600 Monacillos TC to Martin Peña TC] (Transmission) | Transmission | Line Rebuild | 1236618.68 | 38743381.32 | 0 | 0 | 0 | 0 | 0 | 39980000 | 39980000 | Unknown at this time*
340 | 3 | Y | Remain Inactive | 750730 | FAASt [Line 500 Ponce TC to Costa Sur SP] (Transmission) | Transmission | Line Rebuild | 2703473.27 | 33886526.73 | 0 | 0 | 0 | 0 | 0 | 36590000 | 36590000 | Unknown at this time*
341 | 3 | Y | Remain Inactive | 547269 | FAASt Line 2800 (38 kV) Aguadilla Hospital Distrito Sect to T-Bone TO (Transmission) | Transmission | Line Rebuild | 1368921.71 | 34744995.29 | 0 | 0 | 0 | 0 | 0 | 47580550 | 36113917 | 11466633
342 | 3 | Y | Remain Inactive | 752052 | FAASt [Transmission Line 9900 TAP9905A to Rio Blanco HP] (Transmission) | Transmission | Line Rebuild | 855082 | 31254918 | 0 | 0 | 0 | 0 | 0 | 32110000 | 32110000 | Unknown at this time*
343 | 3 | Y | Remain Inactive | 166707 | FAASt - Line 51300 (230KV) - Ponce TC to Costa Sur SP TC (Transmission) | Transmission | Line Rebuild | 3553943.05 | 28255409.95 | 0 | 0 | 0 | 0 | 0 | 48591329 | 31809353 | 16781976
344 | 3 | Y | Remain Inactive | 550070 | FAASt [Line 4000 Comerio HP to Escuela Francisco Morales] (Transmission) | Transmission | Line Rebuild | 810857.53 | 21519142.47 | 0 | 0 | 0 | 0 | 0 | 22330000 | 22330000 | Unknown at this time*
345 | 3 | Y | Remain Inactive | 550019 | FAASt [Line 600 Caguas TC to Gautier Benitez Sect.] (Transmission) | Transmission | Line Rebuild | 984820.5 | 21148694.5 | 0 | 0 | 0 | 0 | 0 | 26168779 | 22133515 | 4035264
346 | 3 | Y | Remain Inactive | 177191 | FAASt - 115kV Line 39000 - Aguas Buenas TC to Caguas TC (Transmission) | Transmission | Line Rebuild | 2347246.55 | 17060638.45 | 0 | 0 | 0 | 0 | 0 | 20314758 | 19407885 | 906873
347 | 3 | Y | Remain Inactive | 547226 | FAASt Barceloneta 11400 TC to Florida TO (Transmission) | Transmission | Line Rebuild | 1008378.72 | 12801621.28 | 0 | 0 | 0 | 0 | 0 | 13810000 | 13810000 | Unknown at this time*
348 | 3 | Y | Remain Inactive | 334469 | FAASt [Line 8900 Monacillos TC to Adm. Tribunal Apelaciones] (Transmission) | Transmission | Line Rebuild | 791706.84 | 10718293.16 | 0 | 0 | 0 | 0 | 0 | 11510000 | 11510000 | Unknown at this time*
349 | 3 | Y | Remain Inactive | 730784 | FAASt [ Line 6700 Martin Peña TC to Villamar Sect.] (Transmission) | Transmission | Line Rebuild | 554694.69 | 5455305.31 | 0 | 0 | 0 | 0 | 0 | 6010000 | 6010000 | Unknown at this time*
350 | 3 | Y | Remain Inactive | 547350 | FAASt [Line 13300 Bayamon TC to Plaza del Sol] (Transmission) | Transmission | Line Rebuild | 1529845.6 | 3860154.4 | 0 | 0 | 0 | 0 | 0 | 5390000 | 5390000 | Unknown at this time*
351 | 3 | Y | Remain Inactive | 551067 | FAASt [Line 11100 Canovanas Sect. to GOAB 11115] (Transmission) | Transmission | Line Rebuild | 2540881.0982 | 1249118.9018 | 0 | 0 | 0 | 0 | 0 | 3790000 | 3790000 | Unknown at this time*
352 | 3 | Y | Remain Inactive | 550902 | FAASt [Line 9700 Palo Seco SP to Bay View Sect.] (Transmission) | Transmission | Line Rebuild | 1125078.14 | 1194921.86 | 0 | 0 | 0 | 0 | 0 | 2320000 | 2320000 | Unknown at this time*
353 | 3 | Y | Remain Inactive | 712978 | FAASt [Once de Agosto Sect. - San Sebastian TC 38kV Line 2000] (Transmission) | Transmission | Line Rebuild | 462240.67 | 1385759.33 | 0 | 0 | 0 | 0 | 0 | 1848000 | 1848000 | Unknown at this time*
354 | 3 | Y | Remain Inactive | 711829 | FAASt [Santa Isabel Sect. - Salinas Sect. 38kV Line 100] (Transmission) | Transmission | Line Rebuild | 17828.4 | 1291171.6 | 0 | 0 | 0 | 0 | 0 | 1309000 | 1309000 | Unknown at this time*
355 | 3 | Y | Remain Inactive | 711862 | FAASt [TL100 Ponce TC to Santa Isabel Sect](Transmission) | Transmission | Line Rebuild | 85524.34 | 1146475.66 | 0 | 0 | 0 | 0 | 0 | 1232000 | 1232000 | Unknown at this time*
356 | 3 | Y | Remain Inactive | 668669 | FAASt [Line 50500 230kV Mayaguez TC - Mora TC - Cambalache Power Plant] (Transmission) | Transmission | Line Rebuild | 73993.29 | 233471.71 | 0 | 0 | 0 | 0 | 0 | 307465 | 307465 | 0
357 | 3 | N | Incremental Project List | Pending FAASt Number | 41200-SABANA LLANA TC-CANOVANAS TC- | Transmission | Line Rebuild | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22110644.6664 | 18130728.6264 | 3979916.04 | Critical line for the 115 kV system.
358 | 3 | N | Incremental Project List | Pending FAASt Number | 9300-JUNCOS TC-GAUTIER BENITEZ SECT- | Transmission | Line Rebuild | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27135375 | 22251007.5 | 4884367.5 | Critical line for the system.
359 | 3 | N | Incremental Project List / Appendix F | Pending FAASt Number | 40600-BAYAMON TC-MONACILLOS TC | Transmission | Line Rebuild | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65222221.57 | 53482221.6874 | 11739999.8826 | Out of Service line it is critical to the resiliency of the 115 kV system.
360 | 3 | N | Incremental Project List / Appendix F | Pending FAASt Number | 41600-PALO SECO SP-SAN JUAN SP- | Transmission | Line Rebuild | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45999999.54 | 37719999.6228 | 8279999.9172 | Out of Service line it is critical to the resiliency of the 115 kV system.
361 | 3 | N | Incremental Project List | Pending FAASt Number | 1500-ONCE DE AGOSTO SECT-SABANA GRANDE TO- | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2440000 | 2171600 | 268400 | Pole Replacements: 13 Critical Repairs: 76
362 | 3 | N | Incremental Project List | Pending FAASt Number | 36400-PONCE TC-DOS BOCAS HP- | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6240000 | 5553600 | 686400 | Pole Replacements: 51 Critical Repairs: 76 The full line rebuild is pending obligation and would include duplication of scope.
363 | 3 | N | Incremental Project List | Pending FAASt Number | 500-PONCE TC-COSTA SUR SP-CANAS TC | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2495000 | 2220550 | 274450 | Pole Replacements: 23 Critical Repairs: 13
364 | 3 | N | Incremental Project List | Pending FAASt Number | 2100-HATILLO TC-QUEBRADILLAS SECT- | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1315000 | 1170350 | 144650 | Pole Replacements: 7 Critical Repairs: 41
365 | 3 | N | Incremental Project List | Pending FAASt Number | 9300-JUNCOS TC-GAUTIER BENITEZ SECT- | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1365000 | 1214850 | 150150 | Pole Replacements: 9 Critical Repairs: 31
366 | 3 | N | Incremental Project List | Pending FAASt Number | 2000-ONCE DE AGOSTO SECT-SAN SEBASTIAN TC- | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3265000 | 2905850 | 359150 | Pole Replacements: 28 Critical Repairs: 31
367 | 3 | N | Incremental Project List | Pending FAASt Number | 50900-AGUIRRE SP-AGUAS BUENAS TC- | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 540000 | 480600 | 59400 | Pole Replacements: 0 Critical Repairs: 36
368 | 3 | N | Incremental Project List | Pending FAASt Number | 7300-BALDRICH SECT-SAN JOSE TO- | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 965000 | 858850 | 106150 | Pole Replacements: 8 Critical Repairs: 11
369 | 3 | N | Incremental Project List | Pending FAASt Number | 50700-AGUIRRE SP-AES PUERTO RICO- | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 315000 | 280350 | 34650 | Pole Replacements: 0 Critical Repairs: 21
370 | 3 | N | Incremental Project List | Pending FAASt Number | 1600-LEON SECT-ACACIAS TC- | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2020000 | 1797800 | 222200 | Pole Replacements: 19 Critical Repairs: 8
371 | 3 | N | Incremental Project List | Pending FAASt Number | 51000-AGUAS BUENAS TC-SABANA LLANA TC- | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 405000 | 360450 | 44550 | Pole Replacements: 0 Critical Repairs: 27
372 | 3 | N | Incremental Project List | Pending FAASt Number | 37500-RIO BAYAMON SECT-MONACILLOS TC- | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1450000 | 1290500 | 159500 | Pole Replacements: 13 Critical Repairs: 10
373 | 3 | N | Incremental Project List | Pending FAASt Number | 300-TORO NEGRO 1 HP-JUANA DIAZ TC- | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2545000 | 2265050 | 279950 | Pole Replacements: 19 Critical Repairs: 43
374 | 3 | N | Incremental Project List | Pending FAASt Number | 13200-DORADO TC-HATO TEJAS TC- | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 580000 | 516200 | 63800 | Pole Replacements: 4 Critical Repairs: 12
375 | 3 | N | Incremental Project List | Pending FAASt Number | 7200-BALDRICH SECT-ESCUELA INDUSTRIAL TO- | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 370000 | 329300 | 40700 | Pole Replacements: 1 Critical Repairs: 18
376 | 3 | N | Incremental Project List | Pending FAASt Number | 8100-YAUCO 1 HP-ADJUNTAS TO- | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4195000 | 3733550 | 461450 | Pole Replacements: 40 Critical Repairs: 13
377 | 3 | N | Incremental Project List | Pending FAASt Number | 10500-CHARDON SECT-LAS MONJAS TO- | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190000 | 169100 | 20900 | Pole Replacements: 1 Critical Repairs: 6
378 | 3 | N | Incremental Project List | Pending FAASt Number | 36200-MONACILLOS TC-JUNCOS TC- | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5445000 | 4846050 | 598950 | Pole Replacements: 51 Critical Repairs: 23
379 | 3 | N | Incremental Project List | Pending FAASt Number | 6500-TORO NEGRO 1 HP-BARRANQUITAS TC- | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2350000 | 2091500 | 258500 | Pole Replacements: 22 Critical Repairs: 10
380 | 3 | N | Incremental Project List | Pending FAASt Number | 6100-MAYAGUEZ GP-RADIAL- | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1085000 | 965650 | 119350 | Pole Replacements: 8 Critical Repairs: 19
381 | 3 | N | Incremental Project List / Appendix F | Pending FAASt Number | 1700-GUANICA TC-YAUCO 2 HP- | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3950000 | 3515500 | 434500 | Pole Replacements: 38 Critical Repairs: 10
382 | 3 | N | Incremental Project List | Pending FAASt Number | 9900-RIO BLANCO HP-HUMACAO SECT- | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1420000 | 1263800 | 156200 | Pole Replacements: 10 Critical Repairs: 28
383 | 3 | N | Incremental Project List | Pending FAASt Number | 10100-LAS LOMAS SECT-REPARTO METROPOLITANO TO- | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 620000 | 551800 | 68200 | Pole Replacements: 2 Critical Repairs: 28
384 | 3 | N | Incremental Project List | Pending FAASt Number | 2100-DOS BOCAS HP-HATILLO TC- | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 685000 | 609650 | 75350 | Pole Replacements: 4 Critical Repairs: 19
385 | 3 | N | Incremental Project List | Pending FAASt Number | 14100-BARCELONETA TC-MERCK- | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165000 | 146850 | 18150 | Pole Replacements: 0 Critical Repairs: 11
386 | 3 | N | Incremental Project List | Pending FAASt Number | 36100-DOS BOCAS HP-BARRIO PIÑA SECT- | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1205000 | 1072450 | 132550 | Pole Replacements: 8 Critical Repairs: 27
387 | 3 | N | Incremental Project List | Pending FAASt Number | 5200-CAGUAS TC-AGUAS BUENAS SECT- | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 93450 | 11550 | Pole Replacements: 0 Critical Repairs: 7
388 | 3 | N | Incremental Project List | Pending FAASt Number | 16300-CAMBALACHE TC-SUPER ACUEDUCTO- | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 205000 | 182450 | 22550 | Pole Replacements: 1 Critical Repairs: 7
389 | 3 | N | Incremental Project List | Pending FAASt Number | 11200-BUENA VISTA SECT-VILLA DEL CARMEN TO- | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 93450 | 11550 | Pole Replacements: 0 Critical Repairs: 7
390 | 3 | N | Incremental Project List | Pending FAASt Number | 18100-JUNCOS TC-RADIAL- | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 267000 | 33000 | Pole Replacements: 0 Critical Repairs: 20
391 | 3 | N | Incremental Project List | Pending FAASt Number | 1000-VILLA PRADES SECT-CAPUCHINOS SECT- | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210000 | 186900 | 23100 | Pole Replacements: 0 Critical Repairs: 14
392 | 3 | N | Incremental Project List | Pending FAASt Number | 50300-AGUIRRE SP-COSTA SUR SP- | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 133500 | 16500 | Pole Replacements: 0 Critical Repairs: 10
393 | 3 | N | Incremental Project List | Pending FAASt Number | 50900-AGUAS BUENAS TC-BAYAMON TC- | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 390000 | 347100 | 42900 | Pole Replacements: 0 Critical Repairs: 26
394 | 3 | N | Incremental Project List | Pending FAASt Number | 3100-PALMER TC-FAJARDO TC- | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 178000 | 22000 | Pole Replacements: 2 Critical Repairs: 0
395 | 3 | N | Incremental Project List / Appendix F | Pending FAASt Number | 3100-CANOVANAS SECT-RIO GRANDE TO- | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 40050 | 4950 | Pole Replacements: 0 Critical Repairs: 3
396 | 3 | N | Incremental Project List | Pending FAASt Number | 36100-CANA SECT-BAYAMON TC- | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 133500 | 16500 | Pole Replacements: 0 Critical Repairs: 10
397 | 3 | N | Incremental Project List | Pending FAASt Number | 5600-AÑASCO TC-MAYAGUEZ GP- | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 89000 | 11000 | Pole Replacements: 1 Critical Repairs: 0
398 | 3 | N | Incremental Project List | Pending FAASt Number | 4700-CANAS TC-ADJUNTAS TO- | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1670000 | 1486300 | 183700 | Pole Replacements: 14 Critical Repairs: 18
399 | 3 | N | Incremental Project List | Pending FAASt Number | 38300-MONACILLOS TC-SAN JUAN SP- | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 680000 | 605200 | 74800 | Pole Replacements: 2 Critical Repairs: 32
400 | 3 | N | Incremental Project List | Pending FAASt Number | 9200-AÑASCO TC-AÑASCO- | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 610000 | 542900 | 67100 | Pole Replacements: 4 Critical Repairs: 14
401 | 3 | N | Incremental Project List | Pending FAASt Number | 5400-RIO BLANCO HP-DAGUAO TC- | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350000 | 311500 | 38500 | Pole Replacements: 2 Critical Repairs: 10
402 | 3 | N | Incremental Project List | Pending FAASt Number | 3800-CIDRA SECT-CAYEY TC- | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160000 | 142400 | 17600 | Pole Replacements: 1 Critical Repairs: 4
403 | 3 | N | Incremental Project List | Pending FAASt Number | 50200-MANATI TC-BAYAMON TC- | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165000 | 146850 | 18150 | Pole Replacements: 0 Critical Repairs: 11
404 | 3 | N | Incremental Project List / Appendix F | Pending FAASt Number | 3600-MONACILLOS TC-SABANA LLANA TC- | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175000 | 155750 | 19250 | Pole Replacements: 1 Critical Repairs: 5
405 | 3 | N | Incremental Project List | Pending FAASt Number | 14400-CAGUAX SECT-VEREDAS SECT- | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2115000 | 1882350 | 232650 | Pole Replacements: 21 Critical Repairs: 1
406 | 3 | N | Incremental Project List | Pending FAASt Number | 14400-VEREDAS SECT-GAUTIER BENITEZ SECT- | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 267000 | 33000 | Pole Replacements: 3 Critical Repairs: 0
407 | 3 | N | Incremental Project List | Pending FAASt Number | 3100-FAJARDO TC-DAGUAO TC- | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 93450 | 11550 | Pole Replacements: 0 Critical Repairs: 7
408 | 3 | N | Incremental Project List / Appendix F | Pending FAASt Number | 3600-SABANA LLANA TC-LOS ANGELES SECT- | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195000 | 173550 | 21450 | Pole Replacements: 0 Critical Repairs: 13
409 | 3 | N | Incremental Project List | Pending FAASt Number | 36900-CANAS TC-PONCE TC- | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 40050 | 4950 | Pole Replacements: 0 Critical Repairs: 3
410 | 3 | N | Incremental Project List | Pending FAASt Number | 5800-SAN FERNANDO SECT-CHARDON SECT- | Transmission | Line Rebuild | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11700000 | 9594000 | 2106000 | Out of Service underground line it is important for the reliability and resiliency of the system.
411 | 3 | N | Incremental Project List | Pending FAASt Number | 3300-CHARDON SECT-BALDRICH SECT- | Transmission | Line Rebuild | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6050000 | 4961000 | 1089000 | Out of Service underground line it is essential for maintaining system reliability and resiliency.
412 | 3 | N | Incremental Project List | Pending FAASt Number | 17100-MARTIN PEÑA TC-COLISEO SECT- | Transmission | Line Rebuild | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4125000 | 3382500 | 742500 | Out of Service underground line it is vital for reliability and resiliency and also serves as a backup for the Coliseo de Puerto Rico, which functions as an emergency shelter.
413 | 3 | N | Incremental Project List / Appendix F | Pending FAASt Number | 40700-BAYAMON TC-PALO SECO SP- | Transmission | Line Rebuild | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52222221.7 | 42822221.794 | 9399999.906 | Out of Service line significantly impacts the resiliency of the 115 kV system.
414 | 3 | N | Incremental Project List | Pending FAASt Number | 7500-TRES MONJITAS SECT-PUERTO NUEVO TO- | Transmission | Line Rebuild | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7444575 | 6104551.5 | 1340023.5 | Out of Service line it is is critical for the reliability of the 38 kV system.
415 | 3 | N | Incremental Project List | Pending FAASt Number | 1000-CAPUCHINOS SECT-VENEZUELA SECT- | Transmission | Line Rebuild | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1856100 | 1522002 | 334098 | Critical line for the system.
416 | 3 | N | Incremental Project List | Pending FAASt Number | 3500-MONACILLOS TC-LAS LOMAS SECT- | Transmission | Line Rebuild | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3813075 | 3126721.5 | 686353.5 | Critical line for the system.
417 | 3 | N | Incremental Project List | Pending FAASt Number | 3300-EGOZCUE SECT-MARTIN PEÑA TC- 3300-MARTIN PEÑA TC-POPULAR SECT- 3300-POPULAR SECT-CHARDON SECT- | Transmission | Line Rebuild | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6850000 | 5617000 | 1233000 | Fundamental for the 38 kV system in the metropolitan area.
418 | 3 | N | Incremental Project List | Pending FAASt Number | 36100-BARRIO PIÑA SECT-CANA SECT- | Transmission | Line Rebuild | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7108943.1 | 5829333.342 | 1279609.758 | Critical line for the 115 kV system.
419 | 3 | N | Incremental Project List | Pending FAASt Number | 36100-CANA SECT-BAYAMON TC- | Transmission | Line Rebuild | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15592281.866 | 12785671.1301 | 2806610.7359 | Critical line for the 115 kV system.
420 | 3 | N | Appendix F | PBUT13 | 700-COSTA SUR SP-YAUCO 2 HP- | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 166750 | 0 | 0
421 | 3 | N | Appendix F | PBUT13 | 800-COMSAT SECT - CIDRA SECT | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 805000 | 0 | 0
422 | 3 | N | Appendix F | PBUT13 | 3000-CAGUAS TC-CAGUAX SECT-F | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 132250 | 0 | 0
423 | 3 | N | Appendix F | PBUT13 | 3000-CAGUAX SECT-JUNCOS TC-F | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 345000 | 0 | 0
424 | 3 | N | Appendix F | PBUT13 | 3000-JUNCOS TC-RIO BLANCO HP-F | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1058000 | 0 | 0
425 | 3 | N | Appendix F | PBUT13 | 3100-CAROLINA-CANOVANA S TC- | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115000 | 0 | 0
426 | 3 | N | Appendix F | PBUT13 | 4500-CANAS TC - LA RAMBLA SECT | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1610000 | 0 | 0
427 | 3 | N | Appendix F | PBUT13 | 10700-HATO TEJAS SECT-BAYAMON PUEBLO SECT- | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 575000 | 0 | 0
428 | 3 | N | Appendix F | PBUT13 | 16500-FAJARDO TC-DOS MARINAS- | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 230000 | 0 | 0
429 | 3 | N | Appendix F | PBUT13 | 3200-Monacillos TC-Venezuela SECT | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115000 | 0 | 0
430 | 3 | N | Appendix F | PBUT13 | 2300-Arecibo SECT-Cambalache TC | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 253000 | 0 | 0
431 | 3 | N | Appendix F | PBUT13 | 3600-Llorens Torres SECT-Martin Peña | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115000 | 0 | 0
432 | 3 | N | Appendix F | PBUT13 | 7400-Hato Rey TC-Tres Monjitas SECT | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115000 | 0 | 0
433 | 3 | N | Appendix F | PBUT13 | 3300-Viaducto TC-Egozcue SECT | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115000 | 0 | 0
434 | 3 | N | Appendix F | PBUT13 | 10000-Bayamon Pueblo SECT-Magnolia TO | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115000 | 0 | 0
435 | 3 | N | Appendix F | PBUT13 | 9400-Dorado TC-Toa Alta | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115000 | 0 | 0
436 | 3 | N | Appendix F | PBUT33 | Line 2100 | Transmission | Line Rebuild | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2300000 | 0 | 0
437 | 3 | N | Appendix F | PBUT33 | Line 40500 | Transmission | Line Rebuild | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 287500 | 0 | 0
438 | 3 | N | Appendix F | PBUT33 | Line 39300 | Transmission | Line Rebuild | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 287500 | 0 | 0
439 | 3 | N | Appendix F | PBUT33 | Line 40000 | Transmission | Line Rebuild | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 287500 | 0 | 0
440 | 3 | N | Appendix F | PBUT33 | Line 39200 | Transmission | Line Rebuild | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 287500 | 0 | 0
441 | 3 | N | Appendix F | PBUT33 | Transmissi on Wildfire Mitigation Infrastructure Hardening | Transmission | Line Rebuild | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32238333 | 0 | 0
442 | 3 | N | Appendix F | PBUT33 | Line 100/200 out of service segment | Transmission | Line Rebuild | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 287500 | 0 | 0
443 | 3 | N | Incremental Project List | Pending FAASt Number | 36100-DOS BOCAS HP-BARRIO PIÑA SECT- | Transmission | Line Rebuild | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73601257.562 | 60353031.2008 | 13248226.3612 | There is a partial overlap with another project on TL36100 Dos Bocas to Ciales, so that portion should be descoped. The rest of the scope from Ciales to Barrio Piño is only partially needed and will be evaluated to rescope.
444 | 4 | Y | Remain Inactive | 549768 | FAASt Physical Security - Group 5 (Substation) | Substation | Physical Security | 55665.9 | 1144334.1 | 0 | 0 | 0 | 0 | 0 | 1200000 | 1200000 | Unknown at this time*
445 | 4 | Y | Remain Inactive | 674506 | FAASt [Field Area Network (FAN)] (Telecommunication) | Telecommunication | N/A | 2785670.22 | 327214329.78 | 0 | 0 | 0 | 0 | 0 | 330000000 | 330000000 | Unknown at this time*
446 | 4 | Y | Remain Inactive | 753302 | FAASt [Telecom Infrastructure Group G] (Telecommunication) | Telecommunication | N/A | 29306.14 | 8351693.86 | 0 | 0 | 0 | 0 | 0 | 8381000 | 8381000 | Unknown at this time*
447 | 4 | Y | Remain Inactive | 814792 | FAASt [Telecom Infrastructure – Group E] | Telecommunication | N/A | 676301.54 | 4923698.46 | 0 | 0 | 0 | 0 | 0 | 5600000 | 5600000 | Unknown at this time*
448 | 4 | Y | Remain Inactive | 814793 | FAASt [Telecom Infrastructure – Group F] | Telecommunication | N/A | 552083.15 | 4047916.85 | 0 | 0 | 0 | 0 | 0 | 4600000 | 4600000 | Unknown at this time*
449 | 4 | Y | Remain Inactive | 704763 | FAASt [Telecom Infrastructure Group C] (Telecommunication) | Telecommunication | N/A | 51458.95 | 2748541.05 | 0 | 0 | 0 | 0 | 0 | 2800000 | 2800000 | Unknown at this time*
450 | 5 | Y | Attachment B | 735357 | FAASt [Mayaguez Streetlighting - Part 2] (Distribution) | Distribution | Distribution Streetlighting | 330319.93 | 2005600 | 0 | 330319.93 | 0 | 0 | 0 | 2335919.93 | 2335919.93 | 0 | Possible high-level scope: 2260 locations. Only the work considered its for the replacement only scope estimate of 1744 locations.This include work zones in municipalities and areas that have not yet been impacted. Since the remaining scope is limited to component replacement, there may be an opportunity to assign this work directly to the applicable municipalities, subject to validation of quantities, capacity, and applicable contractual requirements.
451 | 5 | Y | Attachment B | 746108 | FAASt [San Juan Streetlighting - Part 2] (Distribution) | Distribution | Distribution Streetlighting | 824198.91 | 7814250 | 0 | 825170.91 | 0 | 0 | 0 | 8639420.91 | 8639420.91 | 0 | Possible high-level scope: 8026 locations. Only the work considered its for the replacement only scope estimate of 6795 locations.This include work zones in municipalities and areas that have not yet been impacted. Since the remaining scope is limited to component replacement, there may be an opportunity to assign this work directly to the applicable municipalities, subject to validation of quantities, capacity, and applicable contractual requirements.
452 | 5 | Y | Attachment B | 735131 | FAASt [Arecibo Streetlighting - Part 2] (Distribution) | Distribution | Distribution Streetlighting | 503094.78 | 3149850 | 0 | 503094.78 | 0 | 0 | 0 | 3652944.78 | 3652944.78 | 0 | Possible high-level scope: 3720 locations. Only the work considered its for the replacement only scope estimate of 2739 locations.This include work zones in municipalities and areas that have not yet been impacted. Since the remaining scope is limited to component replacement, there may be an opportunity to assign this work directly to the applicable municipalities, subject to validation of quantities, capacity, and applicable contractual requirements.
453 | 5 | Y | Attachment B | 746111 | FAASt [Caguas Streetlighting - Part 2] (Distribution) | Distribution | Distribution Streetlighting | 508288.97 | 3646650 | 0 | 508288.97 | 0 | 0 | 0 | 4154938.97 | 4154938.97 | 0 | Possible high-level scope: 3766 locations. Only the work considered its for the replacement only scope estimate of 3171 locations.This include work zones in municipalities and areas that have not yet been impacted. Since the remaining scope is limited to component replacement, there may be an opportunity to assign this work directly to the applicable municipalities, subject to validation of quantities, capacity, and applicable contractual requirements.
454 | 5 | Y | Attachment B | 735665 | FAASt [Carolina Streetlighting - Part 2] (Distribution) | Distribution | Distribution Streetlighting | 795422.75 | 4328600 | 0 | 795422.75 | 0 | 0 | 0 | 5124022.75 | 5124022.75 | 0 | Possible high-level scope: 4022 locations. Only the work considered its for the replacement only scope estimate of 3764 locations.This include work zones in municipalities and areas that have not yet been impacted. Since the remaining scope is limited to component replacement, there may be an opportunity to assign this work directly to the applicable municipalities, subject to validation of quantities, capacity, and applicable contractual requirements.
455 | 5 | Y | Attachment B | 734728 | FAASt [Ponce Streetlighting - Part 2] (Distribution) | Distribution | Distribution Streetlighting | 575987.77 | 3681150 | 0 | 576959.77 | 0 | 0 | 0 | 4258109.77 | 4258109.77 | 0 | Possible high-level scope: 3943 locations. Only the work considered its for the replacement only scope estimate of 3201 locations.This include work zones in municipalities and areas that have not yet been impacted. Since the remaining scope is limited to component replacement, there may be an opportunity to assign this work directly to the applicable municipalities, subject to validation of quantities, capacity, and applicable contractual requirements.
456 | 5 | Y | Attachment B | 735954 | FAASt [Trujillo Alto Streetlighting - Part 2] (Distribution) | Distribution | Distribution Streetlighting | 250458.18 | 1817000 | 0 | 251430.18 | 0 | 0 | 0 | 2068430.18 | 2068430.18 | 0 | Possible high-level scope: 2085 locations. Only the work considered its for the replacement only scope estimate of 1580 locations.This include work zones in municipalities and areas that have not yet been impacted. Since the remaining scope is limited to component replacement, there may be an opportunity to assign this work directly to the applicable municipalities, subject to validation of quantities, capacity, and applicable contractual requirements.
457 | 5 | Y | Attachment B | 734859 | FAASt [Aguadilla Streetlighting - Part 2] (Distribution) | Distribution | Distribution Streetlighting | 298155.03 | 2010200 | 0 | 299127.03 | 0 | 0 | 0 | 2309327.03 | 2309327.03 | 0 | Possible high-level scope: 2607 locations. Only the work considered its for the replacement only scope estimate of 1748 locations.This include work zones in municipalities and areas that have not yet been impacted. Since the remaining scope is limited to component replacement, there may be an opportunity to assign this work directly to the applicable municipalities, subject to validation of quantities, capacity, and applicable contractual requirements.
458 | 5 | Y | Attachment B | 735470 | FAASt [Bayamón Streetlighting - Part 2] (Distribution) | Distribution | Distribution Streetlighting | 703474.74 | 5318750 | 0 | 704446.74 | 0 | 0 | 0 | 6023196.74 | 6023196.74 | 0 | Possible high-level scope: 5335 locations. Only the work considered its for the replacement only scope estimate of 4625 locations.This include work zones in municipalities and areas that have not yet been impacted. Since the remaining scope is limited to component replacement, there may be an opportunity to assign this work directly to the applicable municipalities, subject to validation of quantities, capacity, and applicable contractual requirements.
459 | 5 | Y | Attachment B | 734791 | FAASt [Guayama Streetlighting - Part 2] (Distribution) | Distribution | Distribution Streetlighting | 431601.46 | 1756050 | 0 | 444662.71 | 0 | 0 | 0 | 2200712.71 | 2200712.71 | 0 | Possible high-level scope: 1927 locations. Only the work considered its for the replacement only scope estimate of 1527 locations.This include work zones in municipalities and areas that have not yet been impacted. Since the remaining scope is limited to component replacement, there may be an opportunity to assign this work directly to the applicable municipalities, subject to validation of quantities, capacity, and applicable contractual requirements.
460 | 5 | Y | Attachment B | 735493 | FAASt [Humacao Streetlighting - Part 2] (Distribution) | Distribution | Distribution Streetlighting | 324830.45 | 1826200 | 0 | 324830.45 | 0 | 0 | 0 | 2151030.45 | 2151030.45 | 0 | Possible high-level scope: 2136 locations. Only the work considered its for the replacement only scope estimate of 1589 locations.This include work zones in municipalities and areas that have not yet been impacted. Since the remaining scope is limited to component replacement, there may be an opportunity to assign this work directly to the applicable municipalities, subject to validation of quantities, capacity, and applicable contractual requirements.
461 | 5 | Y | Attachment B | 734927 | FAASt [Isabela Streetlighting - Part 2] (Distribution) | Distribution | Distribution Streetlighting | 306973.5 | 1552500 | 0 | 306973.5 | 0 | 0 | 0 | 1859473.5 | 1859473.5 | 0 | Possible high-level scope: 2196 locations. Only the work considered its for the replacement only scope estimate of 1350 locations.This include work zones in municipalities and areas that have not yet been impacted. Since the remaining scope is limited to component replacement, there may be an opportunity to assign this work directly to the applicable municipalities, subject to validation of quantities, capacity, and applicable contractual requirements.
462 | 5 | Y | Attachment B | 737804 | FAASt [Rio Grande Streetlighting - Part 2 ] (Distribution) | Distribution | Distribution Streetlighting | 278557.57 | 1788250 | 0 | 279529.57 | 0 | 0 | 0 | 2067779.57 | 2067779.57 | 0 | Possible high-level scope: 2006 locations. Only the work considered its for the replacement only scope estimate of 1555 locations.This include work zones in municipalities and areas that have not yet been impacted. Since the remaining scope is limited to component replacement, there may be an opportunity to assign this work directly to the applicable municipalities, subject to validation of quantities, capacity, and applicable contractual requirements.
463 | 5 | Y | Attachment B | 737707 | FAASt [Toa Alta Streetlighting - Part 2] (Distribution) | Distribution | Distribution Streetlighting | 364572.61 | 2219500 | 0 | 364572.61 | 0 | 0 | 0 | 2584072.61 | 2584072.61 | 0 | Possible high-level scope: 2495 locations. Only the work considered its for the replacement only scope estimate of 1930 locations.This include work zones in municipalities and areas that have not yet been impacted. Since the remaining scope is limited to component replacement, there may be an opportunity to assign this work directly to the applicable municipalities, subject to validation of quantities, capacity, and applicable contractual requirements.
464 | 5 | Y | Attachment B | 734393 | FAASt [Cabo Rojo Streetlighting - Part 2] (Distribution) | Distribution | Distribution Streetlighting | 368432.14 | 2168900 | 0 | 368432.14 | 0 | 0 | 0 | 2537332.14 | 2537332.14 | 0 | Possible high-level scope: 2519 locations. Only the work considered its for the replacement only scope estimate of 1886 locations.This include work zones in municipalities and areas that have not yet been impacted. Since the remaining scope is limited to component replacement, there may be an opportunity to assign this work directly to the applicable municipalities, subject to validation of quantities, capacity, and applicable contractual requirements.
465 | 5 | Y | Attachment B | 735677 | FAASt [Guaynabo Streetlighting - Part 2] (Distribution) | Distribution | Distribution Streetlighting | 384791.84 | 1935450 | 0 | 384791.84 | 0 | 0 | 0 | 2320241.84 | 2320241.84 | 0 | Possible high-level scope: 2280 locations. Only the work considered its for the replacement only scope estimate of 1683 locations.This include work zones in municipalities and areas that have not yet been impacted. Since the remaining scope is limited to component replacement, there may be an opportunity to assign this work directly to the applicable municipalities, subject to validation of quantities, capacity, and applicable contractual requirements.
466 | 5 | Y | Attachment B | 735960 | FAASt [Toa Baja Streetlighting - Part 2] (Distribution) | Distribution | Distribution Streetlighting | 311784.53 | 1461650 | 0 | 311784.53 | 0 | 0 | 0 | 1773434.53 | 1773434.53 | 0 | Possible high-level scope: 2038 locations. Only the work considered its for the replacement only scope estimate of 1271 locations.This include work zones in municipalities and areas that have not yet been impacted. Since the remaining scope is limited to component replacement, there may be an opportunity to assign this work directly to the applicable municipalities, subject to validation of quantities, capacity, and applicable contractual requirements.
467 | 5 | Y | Attachment B | 735940 | FAASt [Vega Baja Streetlighting - Part 2] (Distribution) | Distribution | Distribution Streetlighting | 313451.11 | 1896350 | 0 | 313451.11 | 0 | 0 | 0 | 2209801.11 | 2209801.11 | 0 | Possible high-level scope: 2239 locations. Only the work considered its for the replacement only scope estimate of 1649 locations.This include work zones in municipalities and areas that have not yet been impacted. Since the remaining scope is limited to component replacement, there may be an opportunity to assign this work directly to the applicable municipalities, subject to validation of quantities, capacity, and applicable contractual requirements.
468 | 5 | Y | Attachment B | 735360 | FAASt [Mayaguez Streetlighting - Part 3] (Distribution) | Distribution | Distribution Streetlighting | 934399.04 | 2967000 | 0 | 934399.04 | 0 | 0 | 0 | 3901399.04 | 3901399.04 | 0 | Possible high-level scope: 4007 locations. Only the work considered its for the replacement only scope estimate of 2580 locations.This include work zones in municipalities and areas that have not yet been impacted. Since the remaining scope is limited to component replacement, there may be an opportunity to assign this work directly to the applicable municipalities, subject to validation of quantities, capacity, and applicable contractual requirements.
469 | 5 | Y | Attachment B | 737712 | FAAST [San Juan Streetlighting - Part 3] (Distribution) | Distribution | Distribution Streetlighting | 1103286.53 | 7826900 | 0 | 1103286.53 | 0 | 0 | 0 | 8930186.53 | 8930186.53 | 0 | Possible high-level scope: 8284 locations. Only the work considered its for the replacement only scope estimate of 6806 locations.This include work zones in municipalities and areas that have not yet been impacted. Since the remaining scope is limited to component replacement, there may be an opportunity to assign this work directly to the applicable municipalities, subject to validation of quantities, capacity, and applicable contractual requirements.
470 | 5 | Y | Attachment B | 734853 | FAASt [Arecibo Streetlighting- Part 3] (Distribution) | Distribution | Distribution Streetlighting | 570030.05 | 2778400 | 0 | 570030.05 | 0 | 0 | 0 | 3348430.05 | 3348430.05 | 0 | Possible high-level scope: 4204 locations. Only the work considered its for the replacement only scope estimate of 2416 locations.This include work zones in municipalities and areas that have not yet been impacted. Since the remaining scope is limited to component replacement, there may be an opportunity to assign this work directly to the applicable municipalities, subject to validation of quantities, capacity, and applicable contractual requirements.
471 | 5 | Y | Attachment B | 735672 | FAASt [Caguas Streetlighting - Part 3] (Distribution) | Distribution | Distribution Streetlighting | 752635.32 | 3448850 | 0 | 752635.32 | 0 | 0 | 0 | 4201485.32 | 4201485.32 | 0 | Possible high-level scope: 4052 locations. Only the work considered its for the replacement only scope estimate of 2999 locations.This include work zones in municipalities and areas that have not yet been impacted. Since the remaining scope is limited to component replacement, there may be an opportunity to assign this work directly to the applicable municipalities, subject to validation of quantities, capacity, and applicable contractual requirements.
472 | 5 | Y | Attachment B | 735496 | FAASt [Carolina Streetlighting - Part 3] (Distribution) | Distribution | Distribution Streetlighting | 684791.58 | 3936450 | 0 | 684791.58 | 0 | 0 | 0 | 4621241.58 | 4621241.58 | 0 | Possible high-level scope: 4528 locations. Only the work considered its for the replacement only scope estimate of 3388 locations.This include work zones in municipalities and areas that have not yet been impacted. Since the remaining scope is limited to component replacement, there may be an opportunity to assign this work directly to the applicable municipalities, subject to validation of quantities, capacity, and applicable contractual requirements.
473 | 5 | Y | Attachment B | 734760 | FAASt [Ponce Streetlighting - Part 3] (Distribution) | Distribution | Distribution Streetlighting | 700990.05 | 3221150 | 0 | 700990.05 | 0 | 0 | 0 | 3922140.05 | 3922140.05 | 0 | Possible high-level scope: 4030 locations. Only the work considered its for the replacement only scope estimate of 2801 locations.This include work zones in municipalities and areas that have not yet been impacted. Since the remaining scope is limited to component replacement, there may be an opportunity to assign this work directly to the applicable municipalities, subject to validation of quantities, capacity, and applicable contractual requirements.
474 | 5 | Y | Attachment B | 735952 | FAASt [Trujillo Alto Streetlighting - Part 3] (Distribution) | Distribution | Distribution Streetlighting | 369585.51 | 1597350 | 0 | 369585.51 | 0 | 0 | 0 | 1966935.51 | 1966935.51 | 0 | Possible high-level scope: 2121 locations. Only the work considered its for the replacement only scope estimate of 1389 locations.This include work zones in municipalities and areas that have not yet been impacted. Since the remaining scope is limited to component replacement, there may be an opportunity to assign this work directly to the applicable municipalities, subject to validation of quantities, capacity, and applicable contractual requirements.
475 | 5 | Y | Attachment B | 735338 | FAASt [Aguadilla Streetlighting - Part 3] (Distribution) | Distribution | Distribution Streetlighting | 313621.72 | 1401850 | 0 | 313621.72 | 0 | 0 | 0 | 1715471.72 | 1715471.72 | 0 | Possible high-level scope: 2134 locations. Only the work considered its for the replacement only scope estimate of 1219 locations.This include work zones in municipalities and areas that have not yet been impacted. Since the remaining scope is limited to component replacement, there may be an opportunity to assign this work directly to the applicable municipalities, subject to validation of quantities, capacity, and applicable contractual requirements.
476 | 5 | Y | Attachment B | 735472 | FAASt [Bayamon Streetlighting - Part 3] (Distribution) | Distribution | Distribution Streetlighting | 705490.59 | 4418300 | 0 | 739172.36 | 0 | 0 | 0 | 5157472.36 | 5157472.36 | 0 | Possible high-level scope: 5468 locations. Only the work considered its for the replacement only scope estimate of 3842 locations.This include work zones in municipalities and areas that have not yet been impacted. Since the remaining scope is limited to component replacement, there may be an opportunity to assign this work directly to the applicable municipalities, subject to validation of quantities, capacity, and applicable contractual requirements.
477 | 5 | Y | Attachment B | 734789 | FAASt [Guayama Streetlighting - Part 3 ] (Distribution) | Distribution | Distribution Streetlighting | 285214.71 | 1679000 | 0 | 285214.71 | 0 | 0 | 0 | 1964214.71 | 1964214.71 | 0 | Possible high-level scope: 1822 locations. Only the work considered its for the replacement only scope estimate of 1460 locations.This include work zones in municipalities and areas that have not yet been impacted. Since the remaining scope is limited to component replacement, there may be an opportunity to assign this work directly to the applicable municipalities, subject to validation of quantities, capacity, and applicable contractual requirements.
478 | 5 | Y | Attachment B | 735487 | FAASt [Humacao Streetlighting - Part 3] (Distribution) | Distribution | Distribution Streetlighting | 282005.08 | 1498450 | 0 | 282005.08 | 0 | 0 | 0 | 1780455.08 | 1780455.08 | 0 | Possible high-level scope: 1939 locations. Only the work considered its for the replacement only scope estimate of 1303 locations.This include work zones in municipalities and areas that have not yet been impacted. Since the remaining scope is limited to component replacement, there may be an opportunity to assign this work directly to the applicable municipalities, subject to validation of quantities, capacity, and applicable contractual requirements.
479 | 5 | Y | Attachment B | 734928 | FAASt [Isabela Streetlighting - Part 3] (Distribution) | Distribution | Distribution Streetlighting | 325113.23 | 1163800 | 0 | 325113.23 | 0 | 0 | 0 | 1488913.23 | 1488913.23 | 0 | Possible high-level scope: 1638 locations. Only the work considered its for the replacement only scope estimate of 1012 locations.This include work zones in municipalities and areas that have not yet been impacted. Since the remaining scope is limited to component replacement, there may be an opportunity to assign this work directly to the applicable municipalities, subject to validation of quantities, capacity, and applicable contractual requirements.
480 | 5 | Y | Attachment B | 737798 | FAASt [Rio Grande Streetlighting - Part 3] (Distribution) | Distribution | Distribution Streetlighting | 239093.65 | 1212100 | 0 | 239093.65 | 0 | 0 | 0 | 1451193.65 | 1451193.65 | 0 | Possible high-level scope: 1599 locations. Only the work considered its for the replacement only scope estimate of 1054 locations.This include work zones in municipalities and areas that have not yet been impacted. Since the remaining scope is limited to component replacement, there may be an opportunity to assign this work directly to the applicable municipalities, subject to validation of quantities, capacity, and applicable contractual requirements.
481 | 5 | Y | Attachment B | 737699 | FAASt [Toa Alta Streetlighting - Part 3] (Distribution) | Distribution | Distribution Streetlighting | 221137.35 | 1058000 | 0 | 221137.35 | 0 | 0 | 0 | 1279137.35 | 1279137.35 | 0 | Possible high-level scope: 1266 locations. Only the work considered its for the replacement only scope estimate of 920 locations.This include work zones in municipalities and areas that have not yet been impacted. Since the remaining scope is limited to component replacement, there may be an opportunity to assign this work directly to the applicable municipalities, subject to validation of quantities, capacity, and applicable contractual requirements.
482 | 5 | Y | Attachment B | 734396 | FAASt [Cabo Rojo Streetlighting - Part 3] (Distribution) | Distribution | Distribution Streetlighting | 279407 | 1246600 | 0 | 279407 | 0 | 0 | 0 | 1526007 | 1526007 | 0 | Possible high-level scope: 1827 locations. Only the work considered its for the replacement only scope estimate of 1084 locations.This include work zones in municipalities and areas that have not yet been impacted. Since the remaining scope is limited to component replacement, there may be an opportunity to assign this work directly to the applicable municipalities, subject to validation of quantities, capacity, and applicable contractual requirements.
483 | 5 | Y | Attachment B | 735499 | FAASt [Guaynabo Streetlighting - Part 3] (Distribution) | Distribution | Distribution Streetlighting | 375286.43 | 1838850 | 0 | 375286.43 | 0 | 0 | 0 | 2214136.43 | 2214136.43 | 0 | Possible high-level scope: 2503 locations. Only the work considered its for the replacement only scope estimate of 1599 locations.This include work zones in municipalities and areas that have not yet been impacted. Since the remaining scope is limited to component replacement, there may be an opportunity to assign this work directly to the applicable municipalities, subject to validation of quantities, capacity, and applicable contractual requirements.
484 | 5 | Y | Attachment B | 735959 | FAASt [Toa Baja Streetlighting - Part 3] (Distribution) | Distribution | Distribution Streetlighting | 300491.01 | 1317900 | 0 | 300491.01 | 0 | 0 | 0 | 1618391.01 | 1618391.01 | 0 | Possible high-level scope: 1717 locations. Only the work considered its for the replacement only scope estimate of 1146 locations.This include work zones in municipalities and areas that have not yet been impacted. Since the remaining scope is limited to component replacement, there may be an opportunity to assign this work directly to the applicable municipalities, subject to validation of quantities, capacity, and applicable contractual requirements.
485 | 5 | Y | Attachment B | 735483 | FAASt [Vega Baja Streetlighting - Part 3] (Distribution) | Distribution | Distribution Streetlighting | 265069.11 | 1308700 | 0 | 265069.11 | 0 | 0 | 0 | 1573769.11 | 1573769.11 | 0 | Possible high-level scope: 1801 locations. Only the work considered its for the replacement only scope estimate of 1138 locations.This include work zones in municipalities and areas that have not yet been impacted. Since the remaining scope is limited to component replacement, there may be an opportunity to assign this work directly to the applicable municipalities, subject to validation of quantities, capacity, and applicable contractual requirements.
486 | 5 | N | Appendix F | PBUT5 | UG Component w Pole Replacement (No Aerial) | Distribution | Streetlight | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
487 | 5 | N | Appendix F | PBUT5 | Provisional Overhead (UG Secondary) | Distribution | Streetlight | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
488 | 6 | Y | Remain Inactive | 551827 | FAASt [San Juan Region Repair] (Building) | Buildings | N/A | 16662.82 | 31012067.18 | 0 | 0 | 0 | 0 | 0 | 31028730 | 31028730 | Unknown at this time*
489 | 6 | Y | Remain Inactive | 550500 | FAASt - Ponce Region Repairs (Building) | Buildings | N/A | 29061.52 | 20265217.48 | 0 | 0 | 0 | 0 | 0 | 20294279 | 20294279 | Unknown at this time*
490 | 6 | Y | Remain Inactive | 551242 | FAASt [Bayamon Region Repairs] (Building) | Buildings | N/A | 49329.73 | 15401975.27 | 0 | 0 | 0 | 0 | 0 | 15451305 | 15451305 | Unknown at this time*
491 | 6 | Y | Remain Inactive | 550060 | FAASt [Caguas Region Repairs] (Building) | Buildings | N/A | 14176.46 | 14457932.54 | 0 | 0 | 0 | 0 | 0 | 14472109 | 14472109 | Unknown at this time*
492 | 6 | Y | Remain Inactive | 548440 | FAASt [Mayaguez Region Repairs] (Building) | Buildings | N/A | 20653.48 | 13325706.52 | 0 | 0 | 0 | 0 | 0 | 13346360 | 13346360 | Unknown at this time*
493 | 6 | Y | Remain Inactive | 679006 | FAASt [Test and Technology Laboratory] (Building) | Buildings | N/A | 817461.16 | 12308368.84 | 0 | 0 | 0 | 0 | 0 | 21312687 | 13125830 | 8186857
494 | 6 | Y | Remain Inactive | 551247 | FAASt [Palo Seco South Building Repairs] (Building) | Buildings | N/A | 895466.67 | 10275026.33 | 0 | 0 | 0 | 0 | 0 | 11170493 | 11170493 | Unknown at this time*
495 | 6 | Y | Remain Inactive | 548393 | FAASt Arecibo Region Repairs (Buildings) | Buildings | N/A | 7741.91 | 9219160.09 | 0 | 0 | 0 | 0 | 0 | 9226902 | 9226902 | Unknown at this time*
496 | 6 | Y | Remain Inactive | 169804 | FAASt Aguadilla Electric Service Center (Building) | Buildings | N/A | 3144.53 | 3496855.47 | 0 | 0 | 0 | 0 | 0 | 3500000 | 3500000 | Unknown at this time*
497 | 6 | Y | Remain Inactive | 954184 | Carolina Electric Service Center | Buildings | N/A | 0 | 2747126.23 | 0 | 0 | 0 | 0 | 0 | 2747126.23 | 2747126.23 | 0
498 | 6 | Y | Remain Inactive | 548596 | FAASt [San German Electrical Service Center] (Building) | Buildings | N/A | 26808.69 | 2451373.31 | 0 | 0 | 0 | 0 | 0 | 2478182 | 2478182 | Unknown at this time*
499 | 6 | Y | Incremental Project List | Pending FAASt Number | Aguadilla Custumer Experince | Buildings | N/A | TBD | 0 | 0 | 0 | 0 | 0 | 0 | TBD | TBD | TBD
500 | 6 | Y | Incremental Project List | 169576 | Arecibo Bulding Repair | Buildings | N/A | TBD | 0 | 0 | 0 | 0 | 0 | 0 | TBD | TBD | TBD
501 | 6 | Y | Incremental Project List | 169798 | Arecibo Electric Service Center | Buildings | N/A | TBD | 0 | 0 | 0 | 0 | 0 | 0 | TBD | TBD | TBD
502 | 6 | Y | Incremental Project List | Pending FAASt Number | Barranquitas Electric Service Center | Buildings | N/A | TBD | 0 | 0 | 0 | 0 | 0 | 0 | TBD | TBD | TBD
503 | 6 | Y | Incremental Project List | Pending FAASt Number | Bayamon Electric Service Center (Minillas) | Buildings | N/A | TBD | 0 | 0 | 0 | 0 | 0 | 0 | TBD | TBD | TBD
504 | 6 | Y | Incremental Project List | Pending FAASt Number | Guayama Electric Service Center | Buildings | N/A | TBD | 0 | 0 | 0 | 0 | 0 | 0 | TBD | TBD | TBD
505 | 6 | Y | Incremental Project List | Pending FAASt Number | Sabana Llana Electric Service Center | Buildings | N/A | TBD | 0 | 0 | 0 | 0 | 0 | 0 | TBD | TBD | TBD
506 | 6 | Y | Incremental Project List | Pending FAASt Number | Toa Alta Electric Service Center | Buildings | N/A | TBD | 0 | 0 | 0 | 0 | 0 | 0 | TBD | TBD | TBD
507 | 6 | Y | Incremental Project List | Pending FAASt Number | Vega Baja Electric Service Center | Buildings | N/A | TBD | 0 | 0 | 0 | 0 | 0 | 0 | TBD | TBD | TBD
508 | 7 | Y | Remain Inactive | 334443 | FAASt [Feeders - Caguas Short Term Group 2] (Distribution) | Distribution | Line Rebuild | 4444384.5082 | 57348236.4918 | 0 | 0 | 0 | 0 | 0 | 113746870 | 61792621 | 51954249 | A new strategy has been developed to submit Distribution Line Rebuild Projects by individual feeder instead of groups. Given the limited federal funds, the D-Line Rebuilds will be prioritizing tier 1 feeders that were based on CMI greater than 3.5M. Any other feeders in this project will be lower priority.
509 | 7 | Y | Remain Inactive | 730821 | FAASt [Feeders - Arecibo Short Term Group 2] (Distribution) | Distribution | Line Rebuild | 2265575.1536 | 57265329.8464 | 0 | 0 | 0 | 0 | 0 | 86894184 | 59530905 | 27363279 | A new strategy has been developed to submit Distribution Line Rebuild Projects by individual feeder instead of groups. Given the limited federal funds, the D-Line Rebuilds will be prioritizing tier 1 feeders that were based on CMI greater than 3.5M. Any other feeders in this project will be lower priority.
510 | 7 | Y | Remain Inactive | 334420 | FAASt [Feeders - Caguas Short Term Group 1] (Distribution) | Distribution | Line Rebuild | 3350974.7111 | 50230812.2889 | 0 | 0 | 0 | 0 | 0 | 79178104 | 53581787 | 25596317 | A new strategy has been developed to submit Distribution Line Rebuild Projects by individual feeder instead of groups. Given the limited federal funds, the D-Line Rebuilds will be prioritizing tier 1 feeders that were based on CMI greater than 3.5M. Any other feeders in this project will be lower priority.
511 | 7 | Y | Remain Inactive | 334475 | FAASt [Feeders - Bayamon Short Term Group 3] (Distribution) | Distribution | Line Rebuild | 2703145.7318 | 47732748.2682 | 0 | 0 | 0 | 0 | 0 | 68320177 | 50435894 | 17884283 | A new strategy has been developed to submit Distribution Line Rebuild Projects by individual feeder instead of groups. Given the limited federal funds, the D-Line Rebuilds will be prioritizing tier 1 feeders that were based on CMI greater than 3.5M. Any other feeders in this project will be lower priority.
512 | 7 | Y | Remain Inactive | 334452 | FAASt [Feeders - Caguas Short Term Group 3] (Distribution) | Distribution | Line Rebuild | 1541793.9843 | 44210613.0157 | 0 | 0 | 0 | 0 | 0 | 65799199 | 45752407 | 20046792 | A new strategy has been developed to submit Distribution Line Rebuild Projects by individual feeder instead of groups. Given the limited federal funds, the D-Line Rebuilds will be prioritizing tier 1 feeders that were based on CMI greater than 3.5M. Any other feeders in this project will be lower priority.
513 | 7 | Y | Remain Inactive | 334308 | FAASt [Feeders - Mayaguez Short Term Group 1] (Distribution ) | Distribution | Line Rebuild | 1803257.36 | 43518447.64 | 0 | 0 | 0 | 0 | 0 | 77351819 | 45321705 | 32030114 | A new strategy has been developed to submit Distribution Line Rebuild Projects by individual feeder instead of groups. Given the limited federal funds, the D-Line Rebuilds will be prioritizing tier 1 feeders that were based on CMI greater than 3.5M. Any other feeders in this project will be lower priority.
514 | 7 | Y | Remain Inactive | 334471 | FAASt [Feeders -1303-01- San Juan Short Term Group 1] (Distribution) | Distribution | Line Rebuild | 675319.8525 | 42274834.1475 | 0 | 0 | 0 | 0 | 0 | 69947970 | 42950154 | 26997816 | A new strategy has been developed to submit Distribution Line Rebuild Projects by individual feeder instead of groups. Given the limited federal funds, the D-Line Rebuilds will be prioritizing tier 1 feeders that were based on CMI greater than 3.5M. Any other feeders in this project will be lower priority.
515 | 7 | Y | Remain Inactive | 730513 | FAASt [Feeders-Caguas Short Term Group 4] (Distribution) | Distribution | Line Rebuild | 827723.91 | 26990838.09 | 0 | 0 | 0 | 0 | 0 | 38748434 | 27818562 | 10929872 | A new strategy has been developed to submit Distribution Line Rebuild Projects by individual feeder instead of groups. Given the limited federal funds, the D-Line Rebuilds will be prioritizing tier 1 feeders that were based on CMI greater than 3.5M. Any other feeders in this project will be lower priority.
516 | 7 | Y | Remain Inactive | 436616 | FAASt [Feeders - Arecibo Short Term Group 1] (Distribution) | Distribution | Line Rebuild | 3049964.3591 | 24144323.6409 | 0 | 0 | 0 | 0 | 0 | 41688676 | 27194288 | 14494388 | A new strategy has been developed to submit Distribution Line Rebuild Projects by individual feeder instead of groups. Given the limited federal funds, the D-Line Rebuilds will be prioritizing tier 1 feeders that were based on CMI greater than 3.5M. Any other feeders in this project will be lower priority.
517 | 7 | Y | Remain Inactive | 334477 | FAASt [Feeders - 2402-02 - Carolina Short Term Group 3] (Distribution) | Distribution | Line Rebuild | 1418795.621 | 21503332.379 | 0 | 0 | 0 | 0 | 0 | 46829930 | 22922128 | 23907802 | A new strategy has been developed to submit Distribution Line Rebuild Projects by individual feeder instead of groups. Given the limited federal funds, the D-Line Rebuilds will be prioritizing tier 1 feeders that were based on CMI greater than 3.5M. Any other feeders in this project will be lower priority.
518 | 7 | Y | Remain Inactive | 334491 | FAASt [Feeders - Caguas Short Term Group 5] (Distribution) | Distribution | Line Rebuild | 917909.52 | 18629023.48 | 0 | 0 | 0 | 0 | 0 | 33129617 | 19546933 | 13582684 | A new strategy has been developed to submit Distribution Line Rebuild Projects by individual feeder instead of groups. Given the limited federal funds, the D-Line Rebuilds will be prioritizing tier 1 feeders that were based on CMI greater than 3.5M. Any other feeders in this project will be lower priority.
519 | 7 | Y | Remain Inactive | 730586 | FAASt [Feeders - Ponce Short Term Group 1] (Distribution) | Distribution | Line Rebuild | 2500998.2555 | 16468809.7445 | 0 | 0 | 0 | 0 | 0 | 31689154 | 18969808 | 12719346 | A new strategy has been developed to submit Distribution Line Rebuild Projects by individual feeder instead of groups. Given the limited federal funds, the D-Line Rebuilds will be prioritizing tier 1 feeders that were based on CMI greater than 3.5M. Any other feeders in this project will be lower priority.
520 | 7 | Y | Remain Inactive | 334476 | FAASt [Feeders - Carolina Short Term Group 2] (Distribution) | Distribution | Line Rebuild | 2350006.6827 | 15935376.3173 | 0 | 0 | 0 | 0 | 0 | 37052925 | 18285383 | 18767542 | A new strategy has been developed to submit Distribution Line Rebuild Projects by individual feeder instead of groups. Given the limited federal funds, the D-Line Rebuilds will be prioritizing tier 1 feeders that were based on CMI greater than 3.5M. Any other feeders in this project will be lower priority.
521 | 7 | Y | Remain Inactive | 334518 | FAASt [Feeders - Caguas Short Term Group 7] (Distribution) | Distribution | Line Rebuild | 1036763.5287 | 11189117.4713 | 0 | 0 | 0 | 0 | 0 | 20010148 | 12225881 | 7784267 | A new strategy has been developed to submit Distribution Line Rebuild Projects by individual feeder instead of groups. Given the limited federal funds, the D-Line Rebuilds will be prioritizing tier 1 feeders that were based on CMI greater than 3.5M. Any other feeders in this project will be lower priority.
522 | 7 | Y | Remain Inactive | 730824 | FAASt [Feeders - Ponce Short Term Group 2] (Distribution) | Distribution | Line Rebuild | 2464564.33 | 1650868.67 | 0 | 0 | 0 | 0 | 0 | 6956286 | 4115433 | 2840853 | A new strategy has been developed to submit Distribution Line Rebuild Projects by individual feeder instead of groups. Given the limited federal funds, the D-Line Rebuilds will be prioritizing tier 1 feeders that were based on CMI greater than 3.5M. Any other feeders in this project will be lower priority.
523 | 7 | Y | Remain Inactive | 334474 | FAASt [Feeders - Bayamon Short Term Group 2] (Distribution) | Distribution | Line Rebuild | 461636.36 | 727653.64 | 0 | 0 | 0 | 0 | 0 | 1848468 | 1189290 | 659178 | A new strategy has been developed to submit Distribution Line Rebuild Projects by individual feeder instead of groups. Given the limited federal funds, the D-Line Rebuilds will be prioritizing tier 1 feeders that were based on CMI greater than 3.5M. Any other feeders in this project will be lower priority.
524 | 7 | Y | Remain Inactive | 176954 | FAASt Garzas 1 HP to Garzas 2 HP - 38kV Line 1100 (Transmission) | Transmission | Line Rebuild | 967911.88 | 2394724.12 | 0 | 0 | 0 | 0 | 0 | 7489992 | 3362636 | 4127356
525 | 7 | N | Appendix F | PBUT33 | Line 1100 | Transmission | Line Rebuild | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 575000 | 0 | 0 | This is being addressed by the line 8700 FEMA project.
526 | Cat F | N | Appendix F | PBUT30 | Pole Replacement | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 276000000 | 0 | 0
527 | Cat F | N | Appendix F | PBUT30 | Engineering Distribution Out of Service (Priority 2) | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17825000 | 0 | 0
528 | Cat F | N | Appendix F | PBUT30 | Engineering Distribution Out of Service (Priority 1) | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17825000 | 0 | 0
529 | Cat F | N | Appendix F | PBUT30 | Non Strutural Repairs Priority 1 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41802500 | 0 | 0
530 | Cat F | N | Appendix F | PBUT30 | Non Strutural Repairs Priority 2 | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41802500 | 0 | 0
531 | Cat F | N | Appendix F | PBUT4 | DA Test Equipment | Distribution | Automation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 613341 | 0 | 0
532 | Cat F | N | Appendix F | PBUT5 | Streetlight Program Remaining work | Distribution | Streetlight | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29425625 | 0 | 0
533 | Cat F | N | Appendix F | PBUT5 | Streetlight Poles with TPA (Octagonal poles ) | Distribution | Streetlight | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4168750 | 0 | 0
534 | Cat F | N | Appendix F | PBUT6 | UG System Repairs - NME | Distribution | Underground | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15424984 | 0 | 0
535 | Cat F | N | Appendix F | PBUT6 | Distribution Capacity Constraints | Distribution |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12650000 | 0 | 0
536 | Cat F | N | Appendix F | PBUT6 | Strategic Voltage Conversion | Distribution |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11500000 | 0 | 0
537 | Cat F | N | Appendix F | PBUT6 | Provisional OH (UG Primary) | Distribution | Underground | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33132656 | 0 | 0
538 | Cat F | N | Appendix F | PBUT6 | UG D Lines Repaired | Distribution | Underground | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13800000 | 0 | 0
539 | Cat F | N | Appendix F | PBUT6 | Distribution (Wildfire Mitigation Infrastructure Hardening) | Distribution |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19550000 | 0 | 0
540 | Cat F | N | Appendix F | PBUT4 | Distribution Automation (Wildfire Mitigation Infrastructure Hardening) | Distribution | Automation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11500000 | 0 | 0
541 | Cat F | N | Appendix F | PBUT30 | Programmable Repairs | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16928600 | 0 | 0
542 | Cat F | N | Appendix F | PBUT30 | PRW-Distr.Pole. Repl.Mar-22-FWD | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63594373 | 0 | 0
543 | Cat F | N | Appendix F | PBUT30 | Dummy-System Stabilization | Distribution | Pole and Conductors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6291705 | 0 | 0
544 | Cat F | N | Appendix F | PBUT39 | Regional Reliability Improvements | Distribution | Reliability | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12075000 | 0 | 0
545 | Cat F | N | Appendix F | PBUT39 | Worst Performing Feeders | Distribution | Reliability | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32775000 | 0 | 0
546 | Cat F | N | Appendix F | PBUT6 | Distribution system improvement (DER) | Distribution |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46000000 | 0 | 0
547 | Cat F | N | Appendix F | PBUT6 | UGWPF - Cables | Distribution | Underground | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1552452 | 0 | 0
548 | Cat F | N | Appendix F | PBUT6 | UGWPF - Switches | Distribution | Underground | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3449986 | 0 | 0
549 | Cat F | N | Appendix F | PBUT39 | Reliability System Upgrades | Distribution | Reliability | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25300000 | 0 | 0
550 | Cat F | N | Appendix F | PBUT4 | DA Replaceme nt Reclosure Equipment (Emergent) | Distribution | Automation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2841765 | 0 | 0
551 | Cat F | N | Appendix F | PBUT4 | Feeder Management System (FMS) | Distribution | Reliability | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 896972 | 0 | 0
552 | Cat F | N | Appendix F | PBUT5 | Dusk To Dawn- LED requiered by Law | Distribution | Streetlight | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7072500 | 0 | 0
553 | Cat F | N | Appendix F | PBUT7 | Cybersecurity platform | Substation | Component Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 575000 | 0 | 0
554 | Cat F | N | Appendix F | PBUT7 | Grounding & Gravel | Substation | Component Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3450000 | 0 | 0
555 | Cat F | N | Appendix F | PBUT7 | Reliability (New Top WPS) | Substation | Component Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5577500 | 0 | 0
556 | Cat F | N | Appendix F | PBUT7 | Substation Batteries | Substation | Component Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1725000 | 0 | 0
557 | Cat F | N | Appendix F | PBUT7 | Substation System Upgrades (DER) | Substation | Component Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28750000 | 0 | 0
558 | Cat F | N | Appendix F | PBUT7 | PAC - T Relays OOO Replacement | Substation | Component Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1725000 | 0 | 0
559 | Cat F | N | Appendix F | PBUT7 | PAC - RTU OOS Replacement | Substation | Component Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2760000 | 0 | 0
560 | Cat F | N | Appendix F | PBUT7 | DFR - Digital Fault Recorder | Substation | Component Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5175000 | 0 | 0
561 | Cat F | N | Appendix F | PBUT7 | D Breaker OOS Replacement | Substation | Component Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15525000 | 0 | 0
562 | Cat F | N | Appendix F | PBUT7 | LTC Program - OOS | Substation | Component Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3450000 | 0 | 0
563 | Cat F | N | Appendix F | PBUT7 | T Breakers OOS Replacement | Substation | Component Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11500000 | 0 | 0
564 | Cat F | N | Appendix F | PBUT7 | T Breaker Programmatic Replacement | Substation | Component Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5750000 | 0 | 0
565 | Cat F | N | Appendix F | PBUT7 | Transformers Programmatic Replacement | Substation | Component Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40595000 | 0 | 0
566 | Cat F | N | Appendix F | PBUT7 | Distribution Transformers - OOS | Substation | Component Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17250000 | 0 | 0
567 | Cat F | N | Appendix F | PBUT7 | Transmission Transformers - OOS | Substation | Component Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17250000 | 0 | 0
568 | Cat F | N | Appendix F | PBUT7 | Voltage Regulation / Optimiation (ie - Capacitor Banks) | Substation | Component Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6612500 | 0 | 0
569 | Cat F | N | Appendix F | PBUT7 | Optical Sensors - Contracted | Substation | Component Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3438500 | 0 | 0
570 | Cat F | N | Appendix F | PBUT7 | Optical Sensors - Additional | Substation | Component Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4387313 | 0 | 0
571 | Cat F | N | Appendix F | PBUT8 | Substation (Wildfire Mitigation Infrastructure Hardening) | Substation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23000000 | 0 | 0
572 | Cat F | N | Appendix F | PBUT7 | Substation Transformer Upgrades (Current Capacity Constraints) | Substation | Component Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10350000 | 0 | 0
573 | Cat F | N | Appendix F | PBUT7 | Emergent Replacements and Minor proactive replacements (Bucket) | Substation | Component Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47117600 | 0 | 0
574 | Cat F | N | Appendix F | PBUT7 | D Breaker Programmatic Replacement | Substation | Component Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
575 | Cat F | N | Appendix F | PBUT13 | Capital Work Trans PoleReplace | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38294974 | 0 | 0
576 | Cat F | N | Appendix F | PBUT13 | Engineering Transmission Out of Service (Priority 2) | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28175000 | 0 | 0
577 | Cat F | N | Appendix F | PBUT13 | Engineering Transmission Out of Service (Priority 1) | Transmission | Pole Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28175000 | 0 | 0
578 | Cat F | N | Appendix F | PBUT33 | Transmission OOS Lines - OH | Transmission | Line Rebuild | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11500000 | 0 | 0
579 | Cat F | N | Appendix F | PBUT33 | Transmission OOS Lines - Undergrou nd | Transmission | Line Rebuild | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14950000 | 0 | 0
580 | Cat F | N | Appendix F | PBUT33 | Transmission Current Capacity Constraints | Transmission | Line Rebuild | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12650000 | 0 | 0
581 | Cat F | N | Appendix F | PBUT33 | Transmission System Improvement (DER) | Transmission | Line Rebuild | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12650000 | 0 | 0
582 | NFC | N | Incremental Project List | Pending FAASt Number | FAASt [Pole and Conductor Repair -Arecibo Group 18-19-20-21 - Phase 3 | Distribution | Pole and Conductors | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 7610000 | TBD | TBD
Complete List of Projects