## Roadmap
| Q4 ’26 | Q1 ’27 | Q2 ‘27 | Q3 ’27 | Q4 ‘27 | Q1 ’28 | Q2 ‘28 | Q3 ‘28 | Q4 ‘28 | Q1 ‘29 | Q2 ‘29 | Q3 ‘29 | Q4 ‘29 | TBD
Planning and Roadmap Development
Validate detailed remediation activities & owners
1) Finance Governance and Accounting Standards
1.1 Define FERC acct. roadmap & prepare to execute
1.2 Implementation and Testing of FERC accounting
1.3 Develop and Align Vision of Governance Policies and Procedures
1.4 Assess accounting policy gaps & required minimum standards
1.5 Operationalize governance & standards (templates, outputs, cadence)
2) Balance Sheet Remediation
2.1 Accounts Receivable segregation
2.2 Inventory segregation
2.3 Fixed Assets segregation
2.4 Accounts Payable segregation
2.5 Other Accounts
2.6 Execute necessary adjusting entries
2.7 GenCo CleanUP (Item 100% owned by GridCo or HoldCo)
2.8 Separate commingled balance sheets & establish opening balance
Notes:
1.1 - These efforts require updates to the LUMA Oracle EBS system configuration across multiple modules, ensuring that the chart‑of‑accounts mapping is properly aligned with FERC reporting requirements.
1.5 - These efforts will be on going per each topic above.
2.6 - Each line represents the respective JE needed to be performed with the conclusion of each area.
This plan represents the group’s best estimate and is subject to significant impact from the following constraints: resource availability, budget limitations, and cash flow restrictions.