## Gantt Chart
PROJECT OASIS — LEVEL II GANTT SCHEDULE
◆ EPC Owner Milestone (blue) ◆ EPC Contractor Milestone (red) ¦ Shaded column = current month ¦ Markers auto-update when dates change on the 'Level 2 Schedule' tab
|  | 2025 | [11 empty] | 2026 | [11 empty] | 2027 | [11 empty] | 2028 | [11 empty] | 2029 | [11 empty] | 2030
Milestone | Planned Date | time axis 2025-01-01 to 2030-12-01
EPC - OWNER MILESTONES
Phase I Environmental Assessment | 2025-05-02 | bar: 2025-05-01
Gas Turbine & Generator Set Firm Proposal | 2026-03-31 | bar: 2026-03-01
Geotechnical Survey Report Available (Existing) | 2026-04-01 | bar: 2026-04-01
Topographical Survey Report Available (Existing) | 2026-04-01 | bar: 2026-04-01
Survey and Topographic Study | 2026-04-10 | bar: 2026-04-01
Phase II Environmental | 2026-09-15 | bar: 2026-09-01
Flood Plain | 2026-08-31 | bar: 2026-08-01
Wetlands | 2026-08-31 | bar: 2026-08-01
Flora and Fauna | 2026-08-31 | bar: 2026-08-01
Hydrological and Hydraulic (HH Study) | 2026-08-31 | bar: 2026-08-01
EPA PSD Application Submittal | 2026-08-28 | bar: 2026-08-01
Cultural Resources | 2026-08-28 | bar: 2026-08-01
Asbestos Inspection and Lead Based Paint (LBP) Inspection | 2026-08-01 | bar: 2026-08-01
Emissions Analysis | 2026-08-10 | bar: 2026-08-01
Risk Analysis | 2026-10-15 | bar: 2026-10-01
Land Use | 2026-09-15 | bar: 2026-09-01
Environmental Noise Studies | 2026-09-15 | bar: 2026-09-01
Limited EPC Contract Award | 2026-05-31 | bar: 2026-05-01
EPC Contract Award | 2026-09-30 | bar: 2026-09-01
Gas Turbine & Generator Set Award and Signature | 2026-05-31 | bar: 2026-05-01
Environmental Impact Statement Submittal | 2026-11-15 | bar: 2026-11-01
Interconnection Studies Update Completion | 2026-10-01 | bar: 2026-10-01
Interconnection Agreement Executed | 2026-10-01 | bar: 2026-10-01
GE Engineering Issuing Start | 2026-10-01 | bar: 2026-10-01
Limited Notice to Proceed (LNTP) | 2026-10-01 | bar: 2026-10-01
Effective Date of EPC Contract | 2026-10-01 | bar: 2026-10-01
Environmental Permit | 2026-12-30 | bar: 2026-12-01
Target Closing Date | 2026-12-31 | bar: 2026-12-01
Closing Date (PPOA Milestone) | 2027-02-01 | bar: 2027-02-01
Permits Available (Permits, Approvals & Licenses) | 2027-01-01 | bar: 2027-01-01
Power Terminal Point for Connection Available | 2027-01-01 | bar: 2027-01-01
Full Notice To Proceed (FNTP) | 2027-01-01 | bar: 2027-01-01
Site Access for Construction Start | 2027-05-01 | bar: 2027-05-01
Raw Water Available | 2027-05-01 | bar: 2027-05-01
Target Construction Start Date | 2027-05-01 | bar: 2027-05-01
Guaranteed Construction Start Date (PPOA Milestone) | 2027-05-27 | bar: 2027-05-01
PREPA Interconnection Facility (Backfeed Date) | 2029-09-13 | bar: 2029-09-01
Power Supply Availability for Plant Commissioning Start | 2029-11-15 | bar: 2029-11-01
Natural Gas Supply Available | 2029-11-26 | bar: 2029-11-01
Liquid Fuel Oil Supply Available | 2029-12-26 | bar: 2029-12-01
Guaranteed COD Date (PPOA Milestone) | 2030-12-30 | bar: 2030-12-01
EPC - CONTRACTOR MILESTONES
Documentation for Steam Turbine Awarding Available | 2026-12-01 | bar: 2026-12-01
Documentation for HRSG Awarding Available | 2026-12-01 | bar: 2026-12-01
Steam Turbine. Order Placed | 2027-02-01 | bar: 2027-02-01
HRSG Order Placed | 2027-02-01 | bar: 2027-02-01
Water & Power Supply Available for Site | 2027-04-01 | bar: 2027-04-01
Start General Site Mobilization | 2027-04-01 | bar: 2027-04-01
Construction Permits Available | 2027-04-01 | bar: 2027-04-01
Start HRSG Foundation incl. excavation | 2027-09-12 | bar: 2027-09-01
Start ST Foundations | 2027-10-02 | bar: 2027-10-01
GT Foundation Completed | 2028-03-02 | bar: 2028-03-01
ACC Erection Begins (ACC Need by Date) | 2028-04-18 | bar: 2028-04-01
HRSG 1st Delivery on Site (Need By Date for Main Steel Structure) | 2028-07-31 | bar: 2028-07-01
HRSG & Auxiliaries Last Delivery on Site | 2028-12-28 | bar: 2028-12-01
Main Transformers Erection Must Start (Transformer Need By Date) | 2029-01-23 | bar: 2029-01-01
GT & Generator Set (incl. Auxiliaries) - All Components POE | 2029-02-28 | bar: 2029-02-01
Gas Turbine POE | 2029-02-28 | bar: 2029-02-01
GT & Generator Set (incl. Auxiliaries) - All Components Delivery on Site | 2029-03-27 | bar: 2029-03-01
Placing Gas Turbine on Foundation | 2029-03-27 | bar: 2029-03-01
ST & Generator Set (incl. Auxiliaries) 1st Delivery on Site | 2029-03-10 | bar: 2029-03-01
ST & Auxiliary Systems 100% Complete Delivery | 2029-03-10 | bar: 2029-03-01
Placing Steam Turbine on Foundation | 2029-03-10 | bar: 2029-03-01
Main Transformers Erection Completion | 2029-05-16 | bar: 2029-05-01
HRSG Hydrotesting Finished | 2029-08-28 | bar: 2029-08-01
Demineralized Water Available | 2029-10-18 | bar: 2029-10-01
Chemical Cleaning / Flushing HRSG Start | 2029-10-19 | bar: 2029-10-01
HRSG Erection Completed | 2029-11-13 | bar: 2029-11-01
HRSG - Ready For Hot Gas | 2030-02-27 | bar: 2030-02-01
ST on Turning Gear | 2030-03-05 | bar: 2030-03-01
Turning Gear Gas Turbine | 2030-03-20 | bar: 2030-03-01
1st. Ignition Gas Turbine | 2030-03-27 | bar: 2030-03-01
1st. Synchronization Gas Turbine | 2030-04-05 | bar: 2030-04-01
1st Steam Admission to Steam Turbine | 2030-06-27 | bar: 2030-06-01
Initial Synchronization Date (STG) | 2030-07-04 | bar: 2030-07-01
Combined Cycle Provisional Acceptance Certificate (PAC) | 2030-10-30 | bar: 2030-10-01

## Level 2 Schedule
EPC - Owner Milestones
EPC - Owner Milestones | Phase I Environmental Assessment | 2025-05-02
EPC - Owner Milestones | Gas Turbine & Generator Set Firm Proposal | 2026-03-31
EPC - Owner Milestones | Geotechnical Survey Report Available (Existing) | 2026-04-01
EPC - Owner Milestones | Topographical Survey Report Available (Existing) | 2026-04-01
EPC - Owner Milestones | Survey and Topographic Study | 2026-04-10
EPC - Owner Milestones | Phase II Environmental | 2026-09-15
EPC - Owner Milestones | Flood Plain | 2026-08-31
EPC - Owner Milestones | Wetlands | 2026-08-31
EPC - Owner Milestones | Flora and Fauna | 2026-08-31
EPC - Owner Milestones | Hydrological and Hydraulic (HH Study) | 2026-08-31
EPC - Owner Milestones | EPA PSD Application Submittal | 2026-08-28
EPC - Owner Milestones | Cultural Resources | 2026-08-28
EPC - Owner Milestones | Asbestos Inspection and Lead Based Paint (LBP) Inspection | 2026-08-01
EPC - Owner Milestones | Emissions Analysis | 2026-08-10
EPC - Owner Milestones | Risk Analysis | 2026-10-15
EPC - Owner Milestones | Land Use | 2026-09-15
EPC - Owner Milestones | Environmental Noise Studies | 2026-09-15
EPC - Owner Milestones | Limited EPC Contract Award | 2026-05-31
EPC - Owner Milestones | EPC Contract Award | 2026-09-30
EPC - Owner Milestones | Gas Turbine & Generator Set Award and Signature | 2026-05-31
EPC - Owner Milestones | Environmental Impact Statement Submittal | 2026-11-15
EPC - Owner Milestones | Interconnection Studies Update Completion | 2026-10-01
EPC - Owner Milestones | Interconnection Agreement Executed | 2026-10-01
EPC - Owner Milestones | GE Engineering Issuing Start | 2026-10-01
EPC - Owner Milestones | Limited Notice to Proceed (LNTP) | 2026-10-01
EPC - Owner Milestones | Effective Date of EPC Contract | 2026-10-01
EPC - Owner Milestones | Environmental Permit | 2026-12-30
EPC - Owner Milestones | Target Closing Date | 2026-12-31
EPC - Owner Milestones | Closing Date (PPOA Milestone) | 2027-02-01
EPC - Owner Milestones | Permits Available (Permits, Approvals & Licenses) | 2027-01-01
EPC - Owner Milestones | Power Terminal Point for Connection Available | 2027-01-01
EPC - Owner Milestones | Full Notice To Proceed (FNTP) | 2027-01-01
EPC - Owner Milestones | Site Access for Construction Start | 2027-05-01
EPC - Owner Milestones | Raw Water Available | 2027-05-01
EPC - Owner Milestones | Target Construction Start Date | 2027-05-01
EPC - Owner Milestones | Guaranteed Construction Start Date (PPOA Milestone) | 2027-05-27
EPC - Owner Milestones | PREPA Interconnection Facility (Backfeed Date) | 2029-09-13
EPC - Owner Milestones | Power Supply Availability for Plant Commissioning Start | 2029-11-15
EPC - Owner Milestones | Natural Gas Supply Available | 2029-11-26
EPC - Owner Milestones | Liquid Fuel Oil Supply Available | 2029-12-26
EPC - Owner Milestones | Guaranteed COD Date (PPOA Milestone) | 2030-12-30
EPC - Contractor Milestones
EPC - Contractor Milestones | Documentation for Steam Turbine Awarding Available | 2026-12-01 | 2 Months of Engineering following LNTP
EPC - Contractor Milestones | Documentation for HRSG Awarding Available | 2026-12-01 | 2 Months of Engineering following LNTP
EPC - Contractor Milestones | Steam Turbine. Order Placed | 2027-02-01
EPC - Contractor Milestones | HRSG Order Placed | 2027-02-01
EPC - Contractor Milestones | Water & Power Supply Available for Site | 2027-04-01
EPC - Contractor Milestones | Start General Site Mobilization | 2027-04-01
EPC - Contractor Milestones | Construction Permits Available | 2027-04-01
EPC - Contractor Milestones | Start HRSG Foundation incl. excavation | 2027-09-12
EPC - Contractor Milestones | Start ST Foundations | 2027-10-02
EPC - Contractor Milestones | GT Foundation Completed | 2028-03-02
EPC - Contractor Milestones | ACC Erection Begins (ACC Need by Date) | 2028-04-18
EPC - Contractor Milestones | HRSG 1st Delivery on Site (Need By Date for Main Steel Structure) | 2028-07-31
EPC - Contractor Milestones | HRSG & Auxiliaries Last Delivery on Site | 2028-12-28
EPC - Contractor Milestones | Main Transformers Erection Must Start (Transformer Need By Date) | 2029-01-23
EPC - Contractor Milestones | GT & Generator Set (incl. Auxiliaries) - All Components POE | 2029-02-28
EPC - Contractor Milestones | Gas Turbine POE | 2029-02-28
EPC - Contractor Milestones | GT & Generator Set (incl. Auxiliaries) - All Components Delivery on Site | 2029-03-27
EPC - Contractor Milestones | Placing Gas Turbine on Foundation | 2029-03-27
EPC - Contractor Milestones | ST & Generator Set (incl. Auxiliaries) 1st Delivery on Site | 2029-03-10
EPC - Contractor Milestones | ST & Auxiliary Systems 100% Complete Delivery | 2029-03-10
EPC - Contractor Milestones | Placing Steam Turbine on Foundation | 2029-03-10
EPC - Contractor Milestones | Main Transformers Erection Completion | 2029-05-16
EPC - Contractor Milestones | HRSG Hydrotesting Finished | 2029-08-28
EPC - Contractor Milestones | Demineralized Water Available | 2029-10-18
EPC - Contractor Milestones | Chemical Cleaning / Flushing HRSG Start | 2029-10-19
EPC - Contractor Milestones | HRSG Erection Completed | 2029-11-13
EPC - Contractor Milestones | HRSG - Ready For Hot Gas | 2030-02-27
EPC - Contractor Milestones | ST on Turning Gear | 2030-03-05
EPC - Contractor Milestones | Turning Gear Gas Turbine | 2030-03-20
EPC - Contractor Milestones | 1st. Ignition Gas Turbine | 2030-03-27
EPC - Contractor Milestones | 1st. Synchronization Gas Turbine | 2030-04-05
EPC - Contractor Milestones | 1st Steam Admission to Steam Turbine | 2030-06-27
EPC - Contractor Milestones | Initial Synchronization Date (STG) | 2030-07-04
EPC - Contractor Milestones | Combined Cycle Provisional Acceptance Certificate (PAC) | 2030-10-30