## PREB Report
Puerto Rico Electric Power Authority
Federal Funding & Grid Modernization Report | [18 empty] | Draft - Subject to Material Change
2026-09-30
Projects highlighted green are part of the Grid Modernization Plan
PREB Approved Projects | [7 empty] | PREB Approval |  |  | Federal Approval & Funding |  |  |  | Stage Status and completion Progress
# | FEMA ID | Project Title | Fund | Cost-Share | Project Formulation Status | Cost Estimate |  | Amount | Date |  | Approval Amount | Reimbursed expenses | Reimbursement Net of Cost-Share |  | Stage | Sub-Stage | Commencement Date | Anticipated Date Design of Completion | % of Design Completed
1 | 435769 | FAASt South Coast Irrigation District - Canals | 428 | 90% | Developing Detailed SOW | 116339106.53 | A | 32140000 | 2021-09-08 |  | Pending Approval | 1284468.4 | 1156021.56 | I | Planning & Design | 30% Designs | 2022-07-30 | 2027-02-15 | 65%
2 | 436467 | FAASt Isabela Irrigation District - Canals & USDA Funding | 428 | 90% | Developing Detailed SOW | 32000000 | A, L | 15000000 | 2021-09-08 |  | To be submitted | 209930.1 | 188937.09 | I | Planning & Design | 30% Designs | 2022-07-30 | TBD | TBD
3 | 436462 | FAASt Lajas Irrigation Canals | 428 | 90% | Developing Detailed SOW | 42573271.52 | A, P | 15000000 | 2021-09-08 |  | Pending Approval | 418246.6 | 376421.94 | I | Planning & Design | 30% Designs | 2022-07-31 | 2027-08-15 | 25%
4 | 334803 | FAASt Loco Reservoir Dredging | 428 | 90% | Developing Detailed SOW | 13830000 | B, S, T, W | 2730000 | 2021-08-20 |  | To be submitted | 512315.843 | 461084.2587 | I | Planning & Design | 60% Designs | 2024-03-31 | 2028-01-31 | 60%
5 | 335207 | FAASt Guineo Reservoir – Dredging | 428 | 90% | Developing Detailed SOW | 9343743 | B, D, S, W | 1250000 | 2021-08-20 |  | To be submitted | 317222.3656 | 285500.1291 | I | Planning & Design | 60% Designs | 2024-03-31 | 2028-05-31 | 60%
6 | 334798 | FAASt Guerrero Reservoir – Dredging | 428 | 90% | Pending COR3 Review | 4918073 | B, T, U, O | 19000 | 2021-08-20 |  | To be submitted | 341035.5679 | 306932.0111 | I | Planning & Design | 30% Designs - Complete | 2024-03-31 | 2027-12-09 | 30%
7 | 334813 | FAASt Guayo Reservoir Dredging | 428 | 90% | Developing Detailed SOW | 23060000 | B, S, W | 21010000 | 2021-08-20 |  | To be submitted | 495256.6852 | 445731.0167 | I | Planning & Design | 60% Designs | 2024-03-31 | 2028-06-30 | 40%
8 | 334811 | FAASt Dos Bocas Reservoir Dredging | 428 | 90% | Pending FEMA Approval | 123379970.5 | B, R, T, V, O, W | 58250000 | 2021-08-20 |  | To be submitted | 778600.8993 | 700740.8094 | I | Planning & Design | 30% Designs - Complete | 2024-03-31 | 2028-03-28 | 37%
9 | 178722 | FAASt Caonillas (Dredging) | 428 | 90% | Pending FEMA Approval | 87072982 | B, D, R, T, V, O, W | 41740000 | 2021-04-28 | D | To be submitted | 767014.7593 | 690313.2834 | I | Planning & Design | 30% Designs - Complete | 2024-03-31 | 2028-02-24 | 37%
10 | 335206 | FAASt Matrullas Reservoir–Dredging | 428 | 90% | Developing Detailed SOW | 14245082 | B, S,W | 3080000 | 2021-08-20 |  | To be submitted | 322358.849 | 290122.9641 | I | Planning & Design | 60% Designs | 2024-03-31 | 2028-03-31 | 50%
11 | 334773 | FAASt Lucchetti Reservoir – Dredging | 428 | 90% | Developing Detailed SOW | 65610000 | B, S, W | 35810000 | 2021-08-20 |  | To be submitted | 639016.083 | 575114.4747 | I | Planning & Design | 60% Designs | 2024-03-31 | 2028-06-30 | 45%
12 | 334772 | FAASt Guayabal Reservoir – Dredging | 428 | 90% | Developing Detailed SOW | 36146934 | B, S, W | 7750000 | 2021-08-20 |  | To be submitted | 324435.5156 | 291991.9641 | I | Planning & Design | 30% Designs - Complete | 2024-03-31 | 2028-08-31 | 35%
13 | 334771 | FAASt Guajataca Reservoir – Dredging | 428 | 90% | Developing Detailed SOW | 42161570 | B, T, O | 18990000 | 2021-08-20 |  | To be submitted | 485535.039 | 436981.5351 | I | Planning & Design | 60% Designs | 2024-03-31 | 2029-03-20 | 35%
14 | 334769 | FAASt Garzas Reservoir – Dredging | 428 | 90% | Developing Detailed SOW | 15127770 | B, T, U, J, O | 1530000 | 2021-06-08 |  | To be submitted | 401546.274 | 361391.6466 | I | Planning & Design | 30% Designs - Complete | 2024-03-31 | 2028-04-04 | 30%
15 | 334770 | FAASt Guajataca Dam – Permanent Repairs | 428 | 90% | Phase I Approved | 1800999998.95 | F | 566000000 | 2021-08-20 |  | 1800999998.95 | 14553809.7067 | 13098428.736 | I | Planning & Design | Design Contracting | 2024-01-15 | 2028-12-31 | 14%
16 | 436621 | FAASt Dams Minor Repairs | 428 | 90% | Developing Detailed SOW | 13559029 | J | 3560000 | 2021-09-28 | D | Pending Approval | 0 | 0 |  | Planning & Design | 30% Designs | 2024-02-12 | 2026-12-31 | 30%
17 | 721184 | FAASt - Guayabal Seismic Retrofit | 428 | 90% | Developing Detailed SOW | 319770241 | M | 299278101 | 2023-05-18 |  | Pending Approval | 0 | 0 |  | Planning & Design | 30% Designs | 2024-07-01 | 2030-12-01 | 10%
18 | 4339-0011 | Patillas Dams | 404/CDBG | 100% | Approved | 567024315 | G | 558530000 | 2021-08-20 |  | 558000000 | 2635000 | 2635000 |  | Planning & Design | 60% Designs - Complete | 2024-01-01 | 2027-06-10 | 84%
19 | 4339-0012 | Early Warning System | 404 | 100% | Approved | 99976487 | H | 100000000 | 2021-08-20 |  | 100000000 | 58244275.95 | 58244275.95 |  | Construction | Construction | 2024-03-31 | 2025-03-01 | 100%
20 | 728260 | FAAST Caonillas Hydroelectric Power Plant I | 428 | 90% | Developing Detailed SOW | 3611152 | K | 1650000 | 2021-04-28 | D | Pending Approval | 323214.5 | 290893.05 | I | Planning & Design | 30% Designs | 2024-02-14 | 2028-12-29 | 30%
21 | 436468 | FAASt Toro Negro Hydroelectric System Connection | 428 | 90% | Developing Detailed SOW | 57244061.71 | Q | 15220000 | 2021-09-08 |  | Pending Approval | 555304.91 | 499774.419 | I | Planning & Design | 60% Designs | 2021-07-30 | 2029-10-12 | 35%
22 | 180723 | FAASt - Rio Blanco Hydroelectric System | 428 | 90% | Developing Detailed SOW | 49005575.55 | Q | 48120000 | 2021-04-28 |  | Pending Approval | 378812.23 | 340931.007 | I | Planning & Design | 30% Designs | 2021-07-31 | 2029-09-20 | 30%
23 | 404-TBD-1 | Retrofit projects on hydroelectric turbines (15 Projects) | DOE | 75% | Project Denied | 320790000 | C | 320790000 | 2023-09-28 |  | Pending Approval | 0 | 0 |  | Technical Specifications | Appeal | Pending | NA | NA
24 | 725535 | FAASt- System Upgrade for Generation Plants (IT/OT) | 428 | 90% | Approved | 11423825 | N | 11423825 | 2023-06-22 |  | 11423825 | 5753369.7578 | 5178032.782 |  | Construction | Construction | 2024-02-08 | 2025-06-30 | 100%
25 | 746897 | BONUS Nuclear Plant | 428 | 90% | Approved | 1579615.43 | E | 1670081 | 2024-04-04 |  | 1579615.43 | 0 | 0 |  | Construction | Construction | 2025-04-01 | 2027-09-20 | 100%
[6 empty] | 3870792803.19 |  | 2180541007 |  |  | 2472003439.38 | 89740770.0353 | 86854620.6267
Notes
A - A&E contractor is performing DSOW requirements.
B - Contracts awarded -Designers in coordination with USACE and has completed 30% design completion on various projects.
C - FEMA response on Appeal received June 15, 2025. Project denied due mitigation alignment. Seeking new funding through DOE. DOE funding application submitted for scope items that fall under DOE requirements. Awaiting DOE application response. Should the funds be awarded, this will be moved to separate projects.
D - Project was segregated into other FEMA projects to address specific scope on individual projects. PREB approval amount was segregated.
E - Project bid awarded and under execution. Project scope include small repairs and fence installation.
F - Construction Phase I obligated by FEMA. Mitigation costs amounting to $1,111,422,980.66 are currently awaiting obligation but have received approval by FEMA, PREPA & COR3. Pending Large Project review by FEMA.
G - 60% design Completed. Budget amendment request pending FEMA approval . ROV and the canal sections completed. USACE identifying if Patillas Dam project can be rolled into projects that have fast tracked permit approvals. The Phase I completion percentage shows a reduction in progress attributable to updates to the schedule.
H - FEMA EHP Goup RECs approval for construction received by FEMA. Construction initiated.
I - Amounts reimbursed are subject to A&E costs incurred in the development of Technical Specifications and Design. Costs were reimbursed through PW 9510 A&E.
J - Pending FEMA project approval. Based on FEMA comments, project may be reconciled across others for formulation. Project costs may be reduced for this project and captured across other projects. Dams Minor Repairs scope items moved per FEMA request. Costs to be recaptured elsewhere (or already addressed for specific projects).
K - Draft DSOW Submitted. Pending Follow Up Design Information. Note project necessary to inspect damages to components in the hydroplant.
L - Funding to be obtained from USDA & FEMA. Coordination with NRCS to define scope between FEMA & USDA funding. Delay due to Federal Shutdown.
M - Designer (Federal Partner) has reduced resources to proceed from appraisal level designs. PREPA coordinating with federal design partners on how to proceed with final designs. Written request made to USACE to take on design role.
N - Construction activities remain in progress. The Costa Sur IT/OT Room is currently undergoing interior and exterior masonry finishing work. Additionally, the monopole tower foundation is expected to begin June 2026.
O - Pending Geotechnical investigations to commence towards final 60% Design Completion. In planning and design stage.
P - Pending Geotechnical investigations to commence towards final 30% Design Completion. In planning and design stage.
Q - Drafting Geotech specs for RFP development on geotech studies required for DSOW submissions. Work Orders to bring on USACE for work ongoing.
R - DSOW Submitted and with FEMA for evaluation. FEMA review notes that all land acquisition and rental activities require commitment letters to proceed with FEMA review. Studies and documentation under development.
S - Cost Change Solely associated with 406-mitigation proposals (additional cofunding) - awaiting FEMA corroboration on mitigation funding qualification
T - Land Appraisal Process Underway, designs paused until completion
U - Costs incurred for design and anticipated costs added to project total cost estimate.
V - Project to be consolidated under one package to include additional and proposed mitigation project.
W - Mitigation Design Packages under development per FEMA request. Funding amount subject to change, but all proposed cost changes will be proposed to FEMA using 406-mitigation funds