## LUMA's Consolidated Project Cos
[7 empty] | 279 |  | Cost Allocation | [8 empty] | Current Cost (Obligaton / DSOW)
# | Status Project | Source | Project # | Title | Asset | Sub Asset | Obligated (Yes / No) | Process Step | 428 Allocation (Without the A&E and E&M) | 406 Allocation (Without the A&E and E&M) | 428 A&E-PW 9510 | 406 A&E-PW 9510 | 428 E&M-PW 10710 | 406 E&M-PW 10710 | Expected Total Project Cost | Total 428 Expected Cost | Total 406 Expected Cost | 428 Allocation (Without the A&E and E&M) | 406 Allocation (Without the A&E and E&M) | 428 A&E-PW 9510 | 406 A&E-PW 9510 | 428 E&M-PW 10710 | 406 E&M-PW 10710 | Expected Total Project Cost | Total 428 Expected Cost | Total 406 Expected Cost | Obligation Amendment Status | Expected DSOW Submittal Date | Latest Obligation Date | Version | Comments
1 | Active | Consolidated List | 956335 | FAASt [San Juan Region 1 - Feeder 2301-02] (Vegetation) | Vegetation | Vegetation-DT | No | Pending EHP Review | 1849955.27 | 5500081.4 | 153676.43 | 421675.11 | 0 | 0 | 7925388.21 | 2003631.7 | 5921756.51 | 1849955.27 | 5078406.29 | 153676.43 | 421675.11 | 0 | 0 | 7503713.1 | 2003631.7 | 5500081.4 | Project in V0 - No amendment required at this time. | Submitted |  | 0
2 | Active | Consolidated List | 745859 | FAASt [Automation Program Group 18: DAR – SAN JUAN 2001- FY24] (Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 223935.37 | 120620.22 | 21856.33 | 15504.92 | 33515.73 | 77702.27 | 493134.84 | 279307.43 | 213827.41 | 467287.59 | 198410.11 | 60837.64 | 15504.92 | 0 | 77702.27 | 819742.53 | 528125.23 | 291617.3 | Amendment Obligated | Submitted | 2026-08-27 | 3 | 406HM revision pending award in Grants Portal / Estimated date Cfci strategy to be defined. In addition to the amendment version, a revised differential estimate of $15,417.30 for the communications wireless portion was added to the 406 section (without A&E and E&M). Estimate is an Class 3.
3 | Active | Consolidated List | 755211 | FAASt [Automation Program Group 15] (Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 276277.77 | 143276.18 | 29684.97 | 18557.49 | 53139.71 | 103164.29 | 624100.41 | 359102.45 | 264997.96 | 276277.77 | 250899.06 | 28366.57 | 19875.89 | 53139.71 | 103164.29 | 731723.29 | 357784.05 | 373939.24 | Amendment Obligated | Submitted | 2026-08-27 | 6 | 406HM revision pending award in Grants Portal / Estimated date Cfci strategy to be defined. In addition to the amendment version, a revised differential estimate of $15,417.30 for the communications wireless portion was added to the 406 section (without A&E and E&M). Estimate is an Class 3.
4 | Active | Consolidated List | 750063 | FAASt [Region 6 -Ponce Group A] Low Density (Vegetation) | Vegetation | Vegetation-DT | Yes | Obligated | 16058969.33 | 43985784.19 | 481769.0799 | 1319573.5257 | 0 | 0 | 61846096.1256 | 16540738.4099 | 45305357.7157 | 15889515.9 | 44155237.62 | 251804.6 | 0 | 0 | 0 | 60296558.12 | 16141320.5 | 44155237.62 | No amendment need has been identified | Submitted | 2026-06-29 | 0 | Cost were changed to aligned to the pending FEMA Obligation values.
5 | Active | Consolidated List | 752540 | FAASt [Pole and Conductor Repair -Mayaguez Group 4 Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 8685452.68 | 37311.66 | 773151.6 | 23427.4 | 624817.52 | 244800.38 | 10388961.24 | 10083421.8 | 305539.44 | 8685452.68 | 0 | 773151.6 | 0 | 624817.52 | 0 | 10083421.8 | 10083421.8 | 0 | No amendment need has been identified | Submitted | 2026-09-04 | 1
6 | Active | Consolidated List | 956356 | FAASt [Ponce Region 6 Transmission Line 39000 – Aguas Buenas Substation to Hacienda San Jose] (Vegetation) | Vegetation | Vegetation-TL | Yes | Obligated | 302418.26 | 690456.65 | 9072.54 | 20713.7 | 0 | 0 | 1022661.15 | 311490.8 | 711170.35 | 86484.8 | 302418.26 | 2779.7 | 0 | 0 | 0 | 391682.76 | 89264.5 | 302418.26 | Amendment Needed | Submitted | 2026-03-01 | 1 | Cost was changed to 60% of total LPCE values. Amendment will be needed after work completion.
7 | Active | Consolidated List | 800286 | FAASt [Automation Program Group 36] (TL / Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 1427638.4262 | 582790.347 | 137043.707 | 78366.543 | 175789.83 | 397237.57 | 2798866.4232 | 1740471.9632 | 1058394.46 | 1703712.83 | 995016.61 | 0 | 78366.54 | 0 | 397237.57 | 3174333.55 | 1703712.83 | 1470620.72 | Amendment – Submitted to FEMA | Submitted | 2026-08-27 | 2 | 406HM Revision currently Pending to be Award in GP / Estimated date Cfci strategy to be defined. In addition to the amendment version, a revised differential estimate of $63,377.85 for the communications wireless portion was added to the 406 section (without A&E and E&M). Estimate is an Class 3.
8 | Active | Consolidated List | 757689 | FAASt [Automation Program Group 24] (Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 1594252.07 | 500159.95 | 141012.25 | 68290.29 | 169799.83 | 399788.17 | 2873302.56 | 1905064.15 | 968238.41 | 1774822.4 | 914277.86 | 0 | 68290.29 | 0 | 399788.17 | 3157178.72 | 1774822.4 | 1382356.32 | Amendment – Submitted to FEMA | Submitted | 2026-08-27 | 2 | 406HM revision pending award in Grants Portal / Estimated date Cfci strategy to be defined. In addition to the amendment version, a revised differential estimate of $53,960.55 for the communications wireless portion was added to the 406 section (without A&E and E&M). Estimate is an Class 3.
9 | Active | Consolidated List | 790443 | FAASt [Pole and Conductor Repair -San Juan Group 3 Phase 2 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 243833.22 | 919.39 | 21435.45 | 574.91 | 14432.64 | 6007.36 | 287202.97 | 279701.31 | 7501.66 | 186697 | 0 | 25985 | 0 | 0 | 0 | 212682 | 212682 | 0 | Amendment Needed | Submitted | 2026-05-13 | 1 | Project obligated under based on a Class 3 estimate full 428. The 428/406HM Amendment was submitted with the revised Class 3 estimate.
10 | Active | Consolidated List | 551963 | FAASt [Transport Network Group 1] (Telecommunication) | Telecommunication | IT/OT | Yes | Obligated | 4489030.64 | 3693295.57 | 671253.14 | 539034.63 | 0 | 0 | 9392613.98 | 5160283.78 | 4232330.2 | 5490296.88 | 0 | 836416.23 | 0 | 1143166.33 | 0 | 7469879.44 | 7469879.44 | 0 | Amendment – Submitted to FEMA | Submitted | 2025-09-17 | 1 | Amendment submitted to include the 428/406 split.
11 | Active | Consolidated List | 752808 | FAASt [Automation Program Group 19] (TL/Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 1352947.241 | 389336.94 | 119711.919 | 52375.13 | 134857.23 | 320428.9 | 2369657.36 | 1607516.39 | 762140.97 | 2753627.24 | 723597.72 | 0 | 52375.13 | 0 | 320428.9 | 3850028.99 | 2753627.24 | 1096401.75 | Amendment – Submitted to FEMA | Submitted | 2026-08-27 | 2 | 406HM revision pending award in Grants Portal / Estimated date Cfci strategy to be defined. In addition to the amendment version, a revised differential estimate of $38,543.25 for the communications wireless portion was added to the 406 section (without A&E and E&M). Estimate is an Class 3.
12 | Active | Consolidated List | 550896 | FAASt Line 6700 Martin Peña TC to Villamar Se | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 1322875.5755 | 5312.0445 | 86031.6501 | 1203.8499 | 159132.66 | 10982.34 | 1585538.12 | 1568039.8856 | 17498.2344 | 690703 | 5312.04 | 86031.65 | 1203.85 | 159132.66 | 10982.34 | 953365.54 | 935867.31 | 17498.23 | Amendment – Submitted to FEMA | Submitted | 2026-07-06 | 2 | This information reflects the latest LPCE data provided and includes the actuals delta. The final cost will be taken into consideration during the project reconciliation and close-out.
13 | Active | Consolidated List | 745856 | FAASt [Automation Program Group 14] (TL/Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 1410445.2 | 555441.55 | 112272.97 | 65062.72 | 148295.58 | 442571.92 | 2734089.94 | 1671013.75 | 1063076.19 | 1640186.96 | 1001406.99 | 0 | 65062.72 | 0 | 442571.92 | 3149228.59 | 1640186.96 | 1509041.63 | Amendment – Submitted to FEMA | Submitted | 2026-08-27 | 2 | 406HM revision currently Pending award in Grants Portal / Estimated date Cfci strategy to be defined. In addition to the amendment version, a revised differential estimate of $61,669.20 for the communications wireless portion was added to the 406 section (without A&E and E&M).Estimate is an Class 3.
14 | Active | Consolidated List | 956349 | FAASt [San Juan Region 1 Transmission Line 36800 – Canovanas TC to Palmer TC] (Vegetation) | Vegetation | Vegetation-TL | Yes | Obligated | 812052.35 | 2894107.23 | 24361.5705 | 86823.2169 | 0 | 0 | 3817344.3674 | 836413.9205 | 2980930.4469 | 1364416.12 | 1607206.7 | 0 | 0 | 0 | 0 | 2971622.82 | 1364416.12 | 1607206.7 | Amendment – Submitted to FEMA | Submitted | 2026-08-27 | 2 | Cost aligned to 80% of the LPCE values for this project. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; project obligations are much lower than submitted mileage, far below forecast needs. LUMA estimates 80% of miles require clearing and seeks gap funding for the mileage not covered/approved by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. . Amendment will be needed after work completion and /or assessment completion.
15 | Active | Consolidated List | 757696 | FAASt [Automation Program Group 31] (Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 940960.74 | 346598.27 | 87081.37 | 44095.89 | 122168.23 | 240541.77 | 1781446.27 | 1150210.34 | 631235.93 | 940960.74 | 584984.03 | 87081.37 | 44095.89 | 122168.23 | 240541.77 | 2019832.03 | 1150210.34 | 869621.69 | Amendment – Submitted to FEMA | Submitted | 2026-08-27 | 2 | 406HM revision pending award in GP / Estimated date Cfci strategy to be defined. In addition to the amendment version, a revised differential estimate of $46,251.90 for the communications wireless portion was added to the 406 section (without A&E and E&M). Estimate is an Class 3.
16 | Active | Consolidated List | 735474 | FAASt [Pole and Conductor Repair -Caguas Group 3 Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 17211915.22 | 71312.91 | 1524520.51 | 44806.64 | 1144636.03 | 468198.97 | 20465390.28 | 19881071.76 | 584318.52 | 17211915.22 | 0 | 1524520.51 | 44806.64 | 1144636.03 | 468198.97 | 20394077.37 | 19881071.76 | 513005.61 | Amendment – Submitted to FEMA | Submitted | 2026-08-24 | 1 | Project obligated under based on a Class 3 estimate full 428. The 428/406HM Amendment was submitted with the revised Class 3 estimate.
17 | Active | Consolidated List | 745861 | FAASt [Automation Program Group 12] (TL/Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 2168647.62 | 784104.06 | 196183.24 | 101775.43 | 228547.36 | 557560.64 | 4036818.35 | 2593378.22 | 1443440.13 | 2168647.62 | 1358644.98 | 196183.24 | 101775.43 | 228547.36 | 557560.64 | 4611359.27 | 2593378.22 | 2017981.05 | Amendment – Submitted to FEMA | Submitted | 2026-08-27 | 2 | 406HM revision pending Award in Grants Portal / Estimated date Cfci strategy to be defined. In addition to the amendment version, a revised differential estimate of $84,795.15 for the communications wireless portion was added to the 406 section (without A&E and E&M). Estimate is an Class 3.
18 | Active | Consolidated List | 800361 | FAASt [Automation Program Group 37] (Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 1514451.93 | 369437.55 | 174540.79 | 68764.66 | 164586.33 | 302167.8 | 2593949.06 | 1853579.05 | 740370.01 | 1596192.73 | 0 | 297988.09 | 0 | 0 | 0 | 1894180.82 | 1894180.82 | 0 | Amendment – Submitted to FEMA | Submitted | 2025-09-17 | 1 | 406HM revision pending award in GP / Estimated date Cfci strategy to be defined. In addition to the amendment version, a revised differential estimate of $46,251.90 for the communications wireless portion was added to the 406 section (without A&E and E&M). Estimate is an Class 3.
19 | Active | Attachment A | 1066740 | Distribution Pole and Conductor Repair – Caguas Group 4 – Phase 2 | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 3867419.78 | 16119.41 | 342713.17 | 10132.71 | 258899.2 | 105879.8 | 4601164.07 | 4469032.15 | 132131.92 | 3867419.78 | 132131.92 | 342713.17 | 0 | 0 | 0 | 4342264.87 | 4210132.95 | 132131.92 | No amendment need has been identified | Submitted | 2026-07-08 | 0 | Design is 100% completed, and the DSOW package has been completed. Costs updated based on the latest DSOW submission. Project obligated by FEMA on 7/8/2026.
20 | Active | Attachment A | 1066737 | Distribution Pole and Conductor Repair - Caguas Group 5 - Phase 2 | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 7591896.49 | 32126 | 673492.23 | 20229.46 | 515199.89 | 211384.11 | 9044328.18 | 8780588.61 | 263739.57 | 7591896.49 | 263739.57 | 673492.23 | 0 | 0 | 0 | 8529128.29 | 8265388.72 | 263739.57 | No amendment need has been identified | Submitted | 2026-07-08 | 0 | Design is 100% completed, and the DSOW package has been completed. Costs updated based on the latest DSOW submission. Project obligated by FEMA on 7/8/2026.
21 | Active | Attachment A | 1064452 | Transmission Priority Pole Replacement Program Line 800 Comsat Sect –Cidra Sect (Active) | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 609182.23 | 2812.61 | 110189.24 | 1928.4 | 52018.89 | 8792.11 | 784923.48 | 771390.36 | 13533.12 | 609176.27 | 13544.23 | 110184.09 | 0 | 0 | 0 | 732904.59 | 719360.36 | 13544.23 | No amendment need has been identified | Submitted | 2026-07-06 | 0
22 | Active | Consolidated List | 668592 | FAASt Line 9800 Bayamon TC - Guaraguao Sect | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 524429.75 | 8046.34 | 34734.97 | 698.02 | 0 | 0 | 567909.08 | 559164.72 | 8744.36 | 399437.09 | 0 | 34734.97 | 0 | 0 | 0 | 434172.06 | 434172.06 | 0 | No amendment need has been identified | Submitted | 2026-09-12 | 1 | This information reflects the latest LPCE data provided and includes the actuals delta. The final cost will be taken into consideration during the project reconciliation and close-out.
23 | Active | Consolidated List | 750692 | FAASt [Pole and Conductor Repair - Mayaguez Group 3 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 15534571.38 | 65783.22 | 1378411.7 | 41393.16 | 1059507.72 | 432530.28 | 18512197.46 | 17972490.8 | 539706.66 | 15534571.38 | 0 | 1378411.7 | 41393.16 | 1059507.72 | 432530.28 | 18446414.24 | 17972490.8 | 473923.44 | Amendment – Submitted to FEMA | Submitted | 2026-08-24 | 2 | Project obligated under based on a Class 3 estimate full 428. The 428/406HM Amendment was submitted with the revised Class 3 estimate.
24 | Active | Consolidated List | 801172 | FAASt [Feeder Rebuild # 1529-15] (Distribution) | Distribution | Distribution Feeders | Yes | Obligated | 2621409.16 | 242729.86 | 538090.23 | 52278.72 | 135020.88 | 39130.64 | 3628659.49 | 3294520.27 | 334139.22 | 1862738.37 | 101241.03 | 568090.34 | 22194.71 | 160515.06 | 28092.46 | 2742871.97 | 2591343.77 | 151528.2 | Amendment – Submitted to FEMA | Submitted | 2026-08-03 | 2 | The project was fully obligated under Section 428 using the Class 3 estimate. Versioning was submitted, including the split between 428 and 406, and it is currently under FEMA evaluation. The final DSOW versioning will be submitted, reflecting an additional $835,029 to the approved budget.
25 | Active | Attachment A | 1066980 | TPole 5900 San Juan SP to Crematorio TO | Transmission | Transmission Priority Pole Replacements | No |  | 407830.94 | 1921.02 | 77598.93 | 1382.15 | 40781.7 | 6101.3 | 535616.04 | 526211.57 | 9404.47 | 448601.61 | 1932.05 | 77591.01 | 1390.07 | 40781.7 | 6101.3 | 576397.74 | 566974.32 | 9423.42 | Project in V0 - No amendment required at this time. | Submitted |  | 0 | DSOW costs currently under review.
26 | Active | Attachment A | 1066739 | Distribution Pole and Conductor Repair - Arecibo Group 3 – Phase 2 | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 2557027.99 | 10609.31 | 226654.03 | 6647.33 | 173097.79 | 69460.21 | 3043496.66 | 2956779.81 | 86716.85 | 2557027.99 | 86716.85 | 226654.03 | 0 | 0 | 0 | 2870398.87 | 2783682.02 | 86716.85 | No amendment need has been identified | Submitted | 2026-07-20 | 0 | Design is 100% completed, and the DSOW package has been completed. Costs updated based on the latest DSOW submission. Pending FEMA obligation.
27 | Active | Attachment A | 1066741 | Distribution Pole and Conductor Repair – Caguas Group 7 – Phase 2 | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 5614901.87 | 23477.61 | 498530.84 | 14731.95 | 388892.2 | 153938.8 | 6694473.27 | 6502324.91 | 192148.36 | 5614901.87 | 192148.36 | 498530.84 | 0 | 0 | 0 | 6305581.07 | 6113432.71 | 192148.36 | No amendment need has been identified | Submitted | 2026-07-08 | 0 | Design is 100% completed, and the DSOW package has been completed. Costs updated based on the latest DSOW submission. Project obligated by FEMA on 7/8/2026.
28 | Active | Attachment A | 1066738 | Distribution Pole and Conductor Repair - Caguas Group 6 - Phase 2 | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 7539064.69 | 31745.7 | 668572.54 | 19977.94 | 509451.1 | 208755.9 | 8977567.87 | 8717088.33 | 260479.54 | 7539064.69 | 31745.7 | 668572.54 | 19977.94 | 509451.1 | 208755.9 | 8977567.87 | 8717088.33 | 260479.54 | No amendment need has been identified | Submitted |  | 0 | Under review
29 | Active | Attachment A | 1066731 | SCADA Remote Access and RTU Replacements Group 3 | Telecommunication | IT/OT | No |  | 18668671.07 | 3375608.8 | 2470554.28 | 425678.76 | 1293008.64 | 0 | 26233521.55 | 22432233.99 | 3801287.56 | 19961679.71 | 3375608.8 | 2470554.28 | 425678.76 | 1293008.64 | 0 | 27526530.19 | 23725242.63 | 3801287.56 | Project in V0 - No amendment required at this time | Submitted |  | 0 | DSOW costs currently under review.
30 | Active | Consolidated List | 657300 | FAASt ENERGY MANAGEMENT SYSTEM (EMS) (Telecom) | Telecommunication | IT/OT | Yes | Obligated | 36900874.92 | 29069659.63 | 2477105.02 | 1951041.22 | 0 | 0 | 70398680.79 | 39377979.94 | 31020700.85 | 48941484 | 0 | 2041312 | 0 | 0 | 0 | 50982796 | 50982796 | 0 | Amendment Needed | Submitted | 2022-10-14 | 1 | Amendment included the revision of the 428/406 split and cost update reflecting the current cost. E&M changed to 0.
31 | Active | Attachment A | 1066730 | Transmission Priority Pole Replacement Program Line 16500 Fajardo TC-Dos Marinas | Transmission | Transmission Priority Pole Replacements | No |  | 212650.88 | 381.28 | 48267.18 | 305.98 | 37102.11 | 1220.26 | 299927.69 | 298020.17 | 1907.52 | 272803.32 | 6019.25 | 51601.44 | 1595.91 | 16197.48 | 2440.52 | 350657.92 | 340602.24 | 10055.68 | Project in V0 - No amendment required at this time. | Submitted |  | 0 | DSOW costs currently under review.
32 | Active | Attachment A | 1068053 | Line 8700 – Costa Sur Power Plant to Garzas 2 HP / Garzas 1 HP | Transmission | Line Rebuild | No |  | 31681262.15 | 0 | 4873900 | 0 | 0 | 0 | 36555162.15 | 36555162.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project in V0 - No amendment required at this time. | 2027-05-22 |  | 0 | The Detailed Scope of Work (DSOW) is currently being formulated. Once the DSOW is submitted to FEMA, the current cost columns will be updated to reflect the costs identified in the DSOW.
33 | Active | Consolidated List | 757700 | FAASt [Automation Program Group 35] (TL / Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 1130075.79 | 551850.51 | 147185.05 | 85545.81 | 118838.8 | 298749.6 | 2332245.56 | 1396099.64 | 936145.92 | 1318515.66 | 0 | 245359.86 | 0 | 0 | 0 | 1563875.52 | 1563875.52 | 0 | Amendment – Submitted to FEMA | Submitted | 2025-09-17 | 1 | 406HM revision currently pending award in Grrants Portal / Estimated date Cfci strategy to be defined. In addition to the amendment version, a revised differential estimate of $61,669.20 for the communications wireless portion was added to the 406 section (without A&E and E&M). Estimate is an Class 3.
34 | Active | Consolidated List | 701504 | FAASt [Pole and Conductor Repair - Arecibo Group 12] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 150345 | 29943 | 29252 | 7935 | 0 | 0 | 217475 | 179597 | 37878 | 150345 | 29943 | 29252 | 7935 | 0 | 0 | 217475 | 179597 | 37878 | Amendment – Submitted to FEMA | Submitted | 2023-03-07 | 0 | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
35 | Active | Consolidated List | 757692 | FAASt [Automation Program Group 26] (TL / Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 807422.25 | 340229.83 | 69331.28 | 43770.32 | 82692.01 | 259575.99 | 1603021.68 | 959445.54 | 643576.14 | 938783.63 | 0 | 175325.33 | 0 | 0 | 0 | 1114108.96 | 1114108.96 | 0 | Amendment – Submitted to FEMA | Submitted | 2025-09-03 | 1 | 406HM revision pending award in Grants Portal / Estimated date Cfci strategy to be defined. In addition to the amendment version, a revised differential estimate of $38,543.25 for the communications wireless portion was added to the 406 section (without A&E and E&M).Estimate is an Class 3.
36 | Active | Consolidated List | 723077 | FAASt - EPC - [Sabana Llana TC] (Substation) | Substation | Substation Rebuilds | Yes | Obligated | 75932414.213 | 8971281.759 | 7744020.4116 | 1085098.707 | 39651716.253 | 10017910.1187 | 143402441.4624 | 123328150.8777 | 20074290.5847 | 100686731.41 | 0 | 4850983.03 | 0 | 0 | 0 | 105537714.44 | 105537714.44 | 0 | Amendment – Submitted to FEMA | Submitted | 2025-04-28 | 1 | LUMA finalizing the scope. The amendment is expected to be submitted Q1 FY2027. Cost change is driven by more defined scope and inflation.
37 | Active | Consolidated List | 551914 | FAASt [Caparra 1912 & 1924] (Substation) | Substation | Substation | No | Pending Scope & Cost Completion by Applicant | 7611654.41 | 6435512.38 | 708217.1 | 448433.37 | 5350921.67 | 6374855.95 | 26929594.88 | 13670793.18 | 13258801.7 | 9452947.27 | 3793442.57 | 708217.1 | 448433.37 | 1841292.86 | 2193636.44 | 18437969.61 | 12002457.23 | 6435512.38 | Project in V0 - No amendment required at this time | Submitted |  | 0 | DSOW costs currently under review.
38 | Active | Consolidated List | 752810 | FAASt [Automation Program Group 20] (TL/Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 1645985.22 | 492364.67 | 176266.8 | 72284.36 | 202809.71 | 358776.21 | 2948486.97 | 2025061.73 | 923425.24 | 1614232.03 | 917475.07 | 346930.18 | 147943.48 | 202809.71 | 358776.21 | 3588166.68 | 2163971.92 | 1424194.76 | Amendment – Submitted to FEMA | Submitted | 2026-08-27 | 2 | 406HM Revision pending award in Grants Portal / Estimated date Cfci strategy to be defined. In addition to the amendment version, a revised differential estimate of $53,960.55 for the communications wireless portion was added to the 406 section (without A&E and E&M). Estimate is an Class 3.
39 | Active | Consolidated List | 334468 | FAASt Line 2200 Dos Bocas HP to Dorado TC (T | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 3049725.4 | 33717.27 | 129281.25 | 2827.08 | 9793.65 | 0 | 3225344.65 | 3188800.3 | 36544.35 | 1217429 | 36562.22 | 242850 | 2831.62 | 0 | 25625.46 | 1525298.3 | 1460279 | 65019.3 | Amendment – Submitted to FEMA | Submitted | 2022-07-11 | 3 | This information reflects the latest LPCE data provided and includes the actuals delta. The final cost will be taken into consideration during the project reconciliation and close-out.
40 | Active | Consolidated List | 550106 | FAASt [Conquistador CH] (Substation) | Substation | Substation Rebuilds | No | Pending Scope & Cost Completion by Applicant | 8360260.4039 | 1994931.4709 | 823453.8066 | 341756.0115 | 4324989.8973 | 4563696.6127 | 20409088.2028 | 13508704.1077 | 6900384.0951 | 11005592.11 | 3599585.6 | 1069327.46 | 356394.89 | 1767641.98 | 50102.06 | 17848644.1 | 13842561.55 | 4006082.55 | Project in V0 - No amendment required at this time | Submitted |  | 0 | DSOW costs currently under review.
41 | Active | Attachment A | 1068646 | FAASt[Region 4 Caguas Transmission 38kV - Non-Sensitive (Vegetation)]- Group B | Vegetation | Vegetation-TL | Yes | Obligated | 715385.11 | 7927576.7 | 6901584.83 | 66028.4 | 0 | 0 | 15610575.04 | 7616969.94 | 7993605.1 | 204634.22 | 0 | 1712.68 | 0 | 0 | 0 | 206346.9 | 206346.9 | 0 | No amendment need has been identified | Submitted | 2026-09-12 | 0
42 | Active | Attachment A | 1068649 | FAASt [Region 6 Ponce Transmission 38kV - Non-Sensitive (Vegetation)- Group B | Vegetation | Vegetation-TL | Yes | Obligated | 141749.28 | 1570801.41 | 1191.98 | 13083.11 | 0 | 0 | 1726825.78 | 142941.26 | 1583884.52 | 294324.21 | 0 | 2463.34 | 0 | 0 | 0 | 296787.55 | 296787.55 | 0 | No amendment need has been identified | Submitted | 2026-09-12 | 0
43 | Active | Attachment A | 1068647 | FAASt[Region 2 Arecibo Transmission 38kV - Non-Sensitive (Vegetation)]- Group B | Vegetation | Vegetation-TL | No |  | 21352.15 | 236614.32 | 179.55 | 1970.74 | 0 | 0 | 260116.76 | 21531.7 | 238585.06 | 21352.15 | 234643.58 | 179.55 | 1970.74 | 0 | 0 | 258146.02 | 21531.7 | 236614.32 | Project in V0 - No amendment required at this time. | Submitted |  | 0
44 | Active | Attachment A | 1068648 | FAASt [Region 5 Mayaguez Transmission 38kV - Non-Sensitive (Vegetation)]- Group B | Vegetation | Vegetation-TL | Yes | Obligated | 799358.09 | 8858127.48 | 6721.82 | 73778.93 | 0 | 0 | 9737986.32 | 806079.91 | 8931906.41 | 141749.28 | 1557718.3 | 1191.98 | 13083.11 | 0 | 0 | 1713742.67 | 142941.26 | 1570801.41 | No amendment need has been identified | Submitted |  | 0 | No comments. Projects already submitted to PREPA.
45 | Active | Attachment A | 1068640 | FAASt[Region 1 San Juan Transmission 38kV - Non-Sensitive (Vegetation)] - Group B | Vegetation | Vegetation-TL | No |  | 281264.03 | 3116841.11 | 2365.12 | 25959.59 | 0 | 0 | 3426429.85 | 283629.15 | 3142800.7 | 281345.36 | 3091775.16 | 2365.85 | 25967.52 | 0 | 0 | 3401453.89 | 283711.21 | 3117742.68 | Project in V0 - No amendment required at this time. | Submitted |  | 0 | DSOW costs currently under review.
46 | Active | Attachment A | 1068642 | FAASt[Region 3 Bayamon Transmission 38kV - Non-Sensitive (Vegetation)]- Group B | Vegetation | Vegetation-TL | No |  | 622799.54 | 6901584.83 | 5237.14 | 57482.97 | 0 | 0 | 7587104.48 | 628036.68 | 6959067.8 | 622799.54 | 6844101.86 | 5237.14 | 57482.97 | 0 | 0 | 7529621.51 | 628036.68 | 6901584.83 | Project in V0 - No amendment required at this time. | Submitted |  | 0
47 | Active | Consolidated List | 817956 | FAASt [Feeder Rebuild # 1303-02] (Distribution) | Distribution | Distribution Feeders | Yes | Obligated | 2783776.04 | 37150.77 | 631442.21 | 8316.85 | 78644.98 | 21278.54 | 3560609.39 | 3493863.23 | 66746.16 | 2054461.78 | 36248.64 | 0 | 8380.84 | 0 | 20488.02 | 2119579.28 | 2054461.78 | 65117.5 | Amendment Needed | Submitted | 2026-08-03 | 2 | Project was obligated full 428 with Class 3 estimate, versioning was submitted including split 428/406, Under FEMA evaluation. Current A/E & Planning costs are higher than the initial estimate ($681.6K). This variance will be mitigated as part of the Final amendment during project versioning prior to closeout.
48 | Active | Consolidated List | 797148 | FAASt [Feeder Rebuild # 8101-03] (Distribution) | Distribution | Distribution Feeders | Yes | Obligated | 3243578.94 | 76998.98 | 678369.17 | 29445.05 | 424402 | 41009.75 | 4493803.89 | 4346350.11 | 147453.78 | 2359895.63 | 0 | 777847.24 | 0 | 0 | 0 | 3137742.87 | 3137742.87 | 0 | Amendment – Submitted to FEMA | Submitted | 2025-09-17 | 1 | The project obligation was based on a Class 3 estimate. Project will be versioned prior to close out (Final Amendment). Current A/E & Planning costs are higher than the initial estimate ($951.9K). This variance will be mitigated as part of the Final amendment during project versioning prior to closeout.
49 | Active | Consolidated List | 165226 | FAASt [Feeders Vieques & Culebra] (Distribution) | Distribution | Vieques and Culebra Projects (6) | Yes | Obligated | 53655359.67 | 7910341.47 | 6294597.32 | 1006025.84 | 3171076.36 | 1176186.58 | 73213587.24 | 63121033.35 | 10092553.89 | 54042602.21 | 0 | 6304100.18 | 0 | 3375233.42 | 0 | 63721935.81 | 63721935.81 | 0 | No amendment need has been identified | Submitted | 2026-09-12 | 0 | The project estimate was based on a Class 3. Project is currently under FEMA evaluation.
50 | Active | Consolidated List | 746660 | FAASt [Minor Protection, Automation, and Control [PAC] Replacement] (Substation) | Substation | Substation | No | Pending Scope & Cost Completion by Applicant | 12586601.6917 | 4270769.9909 | 1139689.148 | 388376.7455 | 0 | 0 | 18385437.576 | 13726290.8396 | 4659146.7364 | 13962542.11 | 240530.55 | 1843798.14 | 0 | 93159.97 | 0 | 16140030.77 | 15899500.22 | 240530.55 | Project in V0 - No amendment required at this time | Submitted |  | 0 | DSOW costs currently under review.
51 | Active | Consolidated List | 167446 | FAASt - Line 36100 (115kV) - Bayamon to Monacillos (Transmission) | Priority Transmission | Transmission Line Rebuild | Yes | Obligated | 16767135.99 | 10441839.67 | 4907530.43 | 3867090.21 | 2133671.71 | 5779812.06 | 43897080.07 | 23808338.13 | 20088741.94 | 33956314.58 | 0 | 3408229.98 | 0 | 0 | 0 | 37364544.56 | 37364544.56 | 0 | Amendment – Submitted to FEMA | Submitted | 2025-11-05 | 1 | Information represents the latest LPCE information provided.
52 | Active | Attachment A | 1068669 | [Patillas Streetlighting] (Distribution | Distribution | Distribution Streetlighting | No |  | 8607983.82 | 358025.92 | 1167539.54 | 48560.66 | 0 | 0 | 10182109.94 | 9775523.36 | 406586.58 | 8607983.82 | 358025.92 | 1167539.54 | 48560.66 | 0 | 0 | 10182109.94 | 9775523.36 | 406586.58 | Project in V0 - No amendment required at this time | Submitted |  | 0 | DSOW costs currently under review.
53 | Active | Attachment A | 1068670 | [Penuelas Streetlighting] (Distribution | Distribution | Distribution Streetlighting | No |  | 8122750.35 | 357444.72 | 1159987.24 | 51045.69 | 0 | 0 | 9691228 | 9282737.59 | 408490.41 | 8123345.36 | 357640.35 | 1160027.72 | 51071.66 | 0 | 0 | 9692085.09 | 9283373.08 | 408712.01 | Project in V0 - No amendment required at this time | Submitted |  | 0 | DSOW costs currently under review.
54 | Active | Attachment A | 1068665 | [Guayanilla Streetlighting] (Distribution | Distribution | Distribution Streetlighting | No |  | 7924363.09 | 412336.03 | 1106363.96 | 57568.51 | 0 | 0 | 9500631.59 | 9030727.05 | 469904.54 | 7924363.09 | 412336.03 | 1106363.96 | 57568.51 | 0 | 0 | 9500631.59 | 9030727.05 | 469904.54 | Project in V0 - No amendment required at this time. | Submitted |  | 0
55 | Active | Attachment A | 1068671 | [Quebradillas Streetlighting] (Distribution | Distribution | Distribution Streetlighting | No |  | 10751415.1 | 550706.35 | 1511148.92 | 77403.68 | 0 | 0 | 12890674.05 | 12262564.02 | 628110.03 | 10751415.1 | 550706.35 | 1511148.92 | 77403.68 | 0 | 0 | 12890674.05 | 12262564.02 | 628110.03 | Project in V0 - No amendment required at this time. | Submitted |  | 0
56 | Active | Attachment A | 1068662 | [Aguas Buenas Streetlighting] (Distribution | Distribution | Distribution Streetlighting | Yes | Obligated | 11613361.45 | 585725.31 | 1646095.25 | 83021.58 | 0 | 0 | 13928203.59 | 13259456.7 | 668746.89 | 11613361.45 | 585725.31 | 1646095.25 | 83021.58 | 0 | 0 | 13928203.59 | 13259456.7 | 668746.89 | No amendment need has been identified | Submitted |  | 0 | Costs updated based on the latest DSOW submission
57 | Active | Attachment A | 1068666 | [Lares Streetlighting] (Distribution | Distribution | Distribution Streetlighting | Yes | Obligated | 12231124.33 | 631320.8 | 1563494.51 | 80701.22 | 0 | 0 | 14506640.86 | 13794618.84 | 712022.02 | 12231124.33 | 631320.8 | 1563494.51 | 80701.22 | 0 | 0 | 14506640.86 | 13794618.84 | 712022.02 | No amendment need has been identified | Submitted |  | 0 | Costs updated based on the latest DSOW submission
58 | Active | Attachment A | 1068673 | [Sabana Grande Streetlighting] (Distribution | Distribution | Distribution Streetlighting | No |  | 11018893.74 | 636889.83 | 1536485.07 | 88808.54 | 0 | 0 | 13281077.18 | 12555378.81 | 725698.37 | 11018893.74 | 636889.83 | 1536485.07 | 88808.54 | 0 | 0 | 13281077.18 | 12555378.81 | 725698.37 | Project in V0 - No amendment required at this time | Submitted |  | 0 | DSOW costs currently under review.
59 | Active | Attachment A | 1068664 | [Ciales Streetlighting] (Distribution | Distribution | Distribution Streetlighting | No |  | 11225480.68 | 682982.51 | 1532416.66 | 93235.54 | 0 | 0 | 13534115.39 | 12757897.34 | 776218.05 | 11225480.68 | 682982.51 | 1532416.66 | 93235.54 | 0 | 0 | 13534115.39 | 12757897.34 | 776218.05 | Project in V0 - No amendment required at this time | Submitted |  | 0 | DSOW costs currently under review.
60 | Active | Attachment A | 1068667 | [Moca Streetlighting] (Distribution | Distribution | Distribution Streetlighting | Yes | Obligated | 18412055.33 | 976458.2 | 2533607.94 | 134366.43 | 0 | 0 | 22056487.9 | 20945663.27 | 1110824.63 | 18412055.33 | 1110824.63 | 2533607.94 | 0 | 0 | 0 | 22056487.9 | 20945663.27 | 1110824.63 | No amendment need has been identified | Submitted |  | 0 | Costs updated based on the latest DSOW submission
61 | Active | Consolidated List | 547187 | FAASt [Substation Component Replacement Program] (Substation) | Substation | Substation | No | Pending Scope & Cost Completion by Applicant | 8910537.185 | 272764.041 | 2942350.301 | 89054.581 | 2669172.077 | 22183.282 | 14906061.467 | 14522059.563 | 384001.904 | 10333487.25 | 223279.18 | 2677534.23 | 78288.39 | 2328680.18 | 10083.31 | 15651352.54 | 15339701.66 | 311650.88 | Project in V0 - No amendment required at this time | Submitted |  | 0 | DSOW costs currently under review.
62 | Active | Consolidated List | 798275 | FAASt [Feeder Rebuild # 1620-02] (Distribution) | Distribution | Distribution Feeders | Yes | Obligated | 6267255.15 | 215006.18 | 1289176.91 | 37409.72 | 531498.7 | 78348.17 | 8418694.83 | 8087930.76 | 330764.07 | 5575178.41 | 0 | 1289289.42 | 0 | 531498.7 | 0 | 7395966.53 | 7395966.53 | 0 | Amendment – Submitted to FEMA | Submitted | 2025-09-17 | 1 | Project was obligated full 428 based on a Class 3 estimate. A versioning was submitted including split 428/406 and is currently under FEMA evaluation.
63 | Active | Consolidated List | 756997 | FAASt [TL 1900 Caguanas to Lares TO] (Transmission) | Transmission | Transmission Line Rebuild | Yes | Obligated | 34621568.58 | 7218553.15 | 2584537.17 | 770659.35 | 1066728.72 | 3635223.17 | 49897270.14 | 38272834.47 | 11624435.67 | 35068956 | 0 | 2686190.09 | 0 | 1191989.07 | 0 | 38947135.16 | 38947135.16 | 0 | No amendment need has been identified | Submitted | 2026-09-12 | 0 | The DSOW revision has been submitted to FEMA.
64 | Active | Consolidated List | 756999 | FAASt [TL 1900 Lares TO to San Sebastian] (Transmission) | Transmission | Transmission Line Rebuild | Yes | Obligated | 29020727.34 | 6217908.83 | 2251104.25 | 556753.47 | 2446381.79 | 1784156.92 | 42277032.6 | 33718213.38 | 8558819.22 | 29470912.86 | 0 | 2407926.28 | 0 | 2840469.97 | 0 | 34719309.11 | 34719309.11 | 0 | No amendment need has been identified | Submitted | 2026-09-12 | 0 | The DSOW revision has been submitted to FEMA.
65 | Active | Consolidated List | 165209 | FAASt - EPC - Culebra Substation 3801 and New Culebra Substation 3802 (Substation) | Substation | Vieques and Culebra Projects (6) | Yes | Obligated | 1133466.58 | 58777240.65 | 148303.89 | 84426.97 | 118838.82 | 298749.59 | 60561026.5 | 1400609.29 | 59160417.21 | 1282218 | 177391 | 522360 | 0 | 0 | 0 | 1981969 | 1804578 | 177391 | Amendment – Submitted to FEMA | Submitted | 2022-06-09 | 0 | The SOW submitted to COR3/PREPA only includes changes in the scope of the repairs to the existing substation. Currently, the project includes the new substation that will be part of the microgrid (not full Section 406HM). LUMA will request to transfer the scope of the new substation to the microgrid project (full Section 406HM). Cost change is driven by more defined scope and inflation.
66 | Active | Consolidated List | 812569 | FAASt [Feeder Rebuild 3502-02] (Distribution) | Distribution | Distribution Feeders | Yes | Obligated | 10019547.43 | 1071193.26 | 1552343.58 | 168085.95 | 399838.42 | 57779.14 | 13268787.78 | 11971729.43 | 1297058.35 | 10217566.54 | 0 | 1403642.18 | 0 | 0 | 0 | 11621208.72 | 11621208.72 | 0 | Amendment – Submitted to FEMA | Submitted |  | 0 | Project was obligated full 428 based on a Class 3 estimate. A versioning was submitted including split 428/406 and is currently under FEMA evaluation.
67 | Active | Consolidated List | 659623 | FAASt Distribution Streetlighting - Cataño ( | Distribution | Distribution Streetlighting | Yes | Obligated | 7282778 | 499180.1274 | 1345465 | 156938.8726 | 0 | 0 | 9284362 | 8628243 | 656119 | 16996758 | 430076 | 3574763 | 135213 | 0 | 0 | 21136810 | 20571521 | 565289 | Amendment – Submitted to FEMA | Submitted |  | 1 | This project was among the first to be developed, originally including the underground work as part of the program's initial scope—estimated at $11M for this portion to be removed. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 55.73% (1299 locations completed).Estimate ammedment submission Q1 FY2027.
68 | Active | Consolidated List | 691702 | FAASt Distribution Streetlighting - Trujillo Alto (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 9704697 | 860820.467 | 1981105 | 277993.533 | 0 | 0 | 12824616 | 11685802 | 1138814 | 25277347 | 763132 | 3389490 | 246446 | 0 | 0 | 29676415 | 28666837 | 1009578 | Amendment – Submitted to FEMA | Submitted |  | 1 | This project was among the first to be developed, originally including the underground work as part of the program's initial scope—estimated at $16M for this portion to be removed. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 36.09% (939 locations completed). Estimate ammedment submission Q1 FY2027.
69 | Active | Consolidated List | 690545 | FAASt Aguadilla Streetlight (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 10433035 | 1035906.3077 | 2151690 | 358776.6923 | 0 | 0 | 13979408 | 12584725 | 1394683 | 19796808 | 962442 | 3021242 | 333333 | 0 | 0 | 24113825 | 22818050 | 1295775 | Amendment – Submitted to FEMA | Submitted |  | 2 | This project was among the first to be developed, originally including the underground work as part of the program's initial scope—estimated at $10M for this portion to be removed. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 46.93% (1148 locations completed). Estimate ammedment submission Q1 FY2027.
70 | Active | Consolidated List | 659625 | FAASt Distribution Streetlighting - Dorado | Distribution | Distribution Streetlighting | Yes | Obligated | 12068437 | 1385150.1318 | 1911204 | 171057.8682 | 0 | 0 | 15535849 | 13979641 | 1556208 | 22864972 | 1149672 | 4716594 | 355973 | 0 | 0 | 29087211 | 27581566 | 1505645 | Amendment – Submitted to FEMA | Submitted |  | 1 | This project was among the first to be developed, originally including the underground work as part of the program's initial scope—estimated at $11M for this portion to be removed. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 76.39% (3314 locations completed).Estimate ammedment submission Q1 FY2027.
71 | Active | Consolidated List | 660437 | FAASt Manati Streetlight (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 15401358 | 1286291.785 | 2596783 | 411619.215 | 0 | 0 | 19696052 | 17998141 | 1697911 | 27067865 | 1188605 | 5821635 | 380359 | 0 | 0 | 34458464 | 32889500 | 1568964 | Amendment – Submitted to FEMA | Submitted |  | 0 | This project was among the first to be developed, originally including the underground work as part of the program's initial scope—estimated at $14M for this portion to be removed. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 63.98% (3704 locations completed). Estimate ammedment submission Q1 FY2027.
72 | Active | Consolidated List | 679039 | FAASt [Distribution Streetlighting - Caguas] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 22960633 | 1507378.5968 | 4065133 | 452047.4032 | 0 | 0 | 28985192 | 27025766 | 1959426 | 73737225 | 1422693 | 8534896.89 | 426651.06 | 0 | 0 | 84121465.95 | 82272121.89 | 1849344.06 | Amendment – Submitted to FEMA | Submitted |  | 1 | This project was among the first to be developed, originally including the underground work as part of the program's initial scope—estimated at $55M for this portion to be removed. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 38.19% (2394 locations completed). Estimate ammedment submission Q1 FY2027.
73 | Active | Consolidated List | 176913 | FAASt [Palo Seco SP to Catano Sect 38kV Line- 9500] (Transmission) | Priority Transmission | Transmission Line Rebuild | Yes | Obligated | 17467604.15 | 3864276.13 | 2619374.41 | 2157076.76 | 2071399.22 | 66725.58 | 28246456.25 | 22158377.78 | 6088078.47 | 33526671.86 | 0 | 4657292.73 | 0 | 0 | 0 | 38183964.59 | 38183964.59 | 0 | No amendment need has been identified | Submitted |  | 0 | Information represents the latest LPCE information provided.
74 | Active | Consolidated List | 542517 | FAASt -Luquillo Distribution Streetlighting | Distribution | Distribution Streetlighting | Yes | Obligated | 4946319 | 158253.8999 | 989521 | 36758.1001 | 0 | 0 | 6130852 | 5935840 | 195012 | 8628667.29 | 147417.08 | 2004233.23 | 34241 | 0 | 0 | 10814558.6 | 10632900.52 | 181658.08 | Amendment Needed | Submitted |  | 2 | This project was among the first to be developed, originally including the underground work as part of the program's initial scope—estimated at $4M for this portion to be removed. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 81.19% (1986 locations completed). Estimate ammedment submission Q2 FY2027.
75 | Active | Consolidated List | 698424 | FAASt Streetlight Florida Distribution | Distribution | Distribution Streetlighting | Yes | Obligated | 7063699 | 741458.8765 | 1487857 | 285427.1235 | 0 | 0 | 9578442 | 8551556 | 1026886 | 9311841.53 | 720017 | 1705096.48 | 277173 | 0 | 0 | 12014128.01 | 11016938.01 | 997190 | Amendment Needed | Submitted |  | 1 | This project was among the first to be developed, originally including the underground work as part of the program's initial scope—estimated at $2M for this portion to be removed. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 85.08% (1454 locations completed).Estimate ammedment submission Q2 FY2027.
76 | Active | Consolidated List | 673504 | FAASt [Distribution Streetlighting - Gurabo] | Distribution | Distribution Streetlighting | Yes | Obligated | 13326352 | 1163470.3301 | 2498935 | 411543.6699 | 0 | 0 | 17400301 | 15825287 | 1575014 | 28826526.19 | 1132656 | 3043676 | 400644 | 0 | 0 | 33403502.19 | 31870202.19 | 1533300 | Amendment Needed | Submitted |  | 1 | This project was among the first to be developed, originally including the underground work as part of the program's initial scope—estimated at $6M for this portion to be removed. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 77.57% (2919 locations completed). Estimate ammedment submission Q2 FY2027.
77 | Active | Consolidated List | 660227 | FAASt Hatillo Streetlight (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 16131869 | 1430424.6192 | 2596438 | 487221.3808 | 0 | 0 | 20645953 | 18728307 | 1917646 | 18570180 | 1316105.06 | 4317860.43 | 448282.64 | 0 | 0 | 24652428.13 | 22888040.43 | 1764387.7 | Amendment Needed | Submitted |  | 1 | This project was among the first to be developed, originally including the underground work as part of the program's initial scope—estimated at $4M for this portion to be removed. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 82.67% (4375 locations completed).
78 | Active | Consolidated List | 659968 | FAASt [San Germán Streetlighting] (Distributio | Distribution | Distribution Streetlighting | Yes | Obligated | 26194807 | 3105148.8829 | 4178149 | 1064155.1171 | 0 | 0 | 34542260 | 30372956 | 4169304 | 30849348 | 3004065 | 4619207 | 1029513 | 0 | 0 | 39502133 | 35468555 | 4033578 | Amendment Needed | Submitted |  | 1 | This project was among the first to be developed, originally including the underground work as part of the program's initial scope—estimated at $5M for this portion to be removed. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 83.80% (4339 locations completed). Estimate ammedment submission Q2 FY2027.
79 | Active | Consolidated List | 757698 | FAASt [Automation Program Group 33] (Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 1435455.15 | 570512.93 | 298284.82 | 143185.1 | 185468.25 | 392343.7 | 3025249.95 | 1919208.22 | 1106041.73 | 1888928.21 | 0 | 311582.64 | 0 | 0 | 0 | 2200510.85 | 2200510.85 | 0 | Amendment – Submitted to FEMA | Submitted |  | 1 | 406 HM revision to be submitted by the end of Q4 FY2026 to Grants Portal. Estimated date Cfci strategy to be defined. In addition to the amendment version, a revised differential estimate of $69,377.85 for the communications wireless portion was added to the 406 section (without A&E and E&M). Estimate is an Class 3.
80 | Active | Consolidated List | 746545 | FAASt [Primary Control Center / Secondary Data Center & Control Room] (Telecommunication) | Building | Building | No | Pending PDMG Scope & Cost Routing | 93654467.72 | 44072690.69 | 12578331.03 | 5919214.6 | 0 | 0 | 156224704.04 | 106232798.75 | 49991905.29 | 115500983 | 0 | 15524336 | 0 | 0 | 0 | 131025319 | 131025319 | 0 | Project in V0 - No amendment required at this time | Submitted |  | 0 | DSOW costs currently under review.
81 | Active | Attachment A | 1070360 | 38kV Transmission Line 4000 – Entire Line (Vegetation) | Vegetation | Vegetation-DL | No |  | 113148.21 | 1243414.15 | 951.47 | 10443.31 | 0 | 0 | 1367957.14 | 114099.68 | 1253857.46 | 232488.75 | 2074472.2 | 7317.93 | 65280.51 | 0 | 0 | 2379559.39 | 239806.68 | 2139752.71 | Project in V0 - No amendment required at this time | Submitted |  | 0 | DSOW costs currently under review.
82 | Active | Attachment A | 1070369 | 38kV Transmission Line 200 – Entire Line (Vegetation) | Vegetation | Vegetation-DL | No |  | 155350.01 | 1707180.44 | 1306.34 | 14338.44 | 0 | 0 | 1878175.23 | 156656.35 | 1721518.88 | 319201.93 | 2848204.97 | 10047.36 | 89628.71 | 0 | 0 | 3267082.97 | 329249.29 | 2937833.68 | Project in V0 - No amendment required at this time | Submitted |  | 0 | DSOW costs currently under review.
83 | Active | Attachment A | 1070370 | 38kV Transmission Line 800 – Entire Line (Vegetation) | Vegetation | Vegetation-DL | No |  | 161271.17 | 1772249.71 | 1356.14 | 14884.95 | 0 | 0 | 1949761.97 | 162627.31 | 1787134.66 | 331368.32 | 2956764.42 | 10430.31 | 93044.92 | 0 | 0 | 3391607.97 | 341798.63 | 3049809.34 | Project in V0 - No amendment required at this time | Submitted |  | 0 | DSOW costs currently under review.
84 | Active | Attachment A | 1070363 | 38kV Transmission Line 5400 – Entire Line (Vegetation) | Vegetation | Vegetation-DL | No |  | 288199.55 | 3167097.76 | 2423.48 | 26600.15 | 0 | 0 | 3484320.94 | 290623.03 | 3193697.91 | 341101.43 | 3043611.97 | 10736.68 | 95777.88 | 0 | 0 | 3491227.96 | 351838.11 | 3139389.85 | Project in V0 - No amendment required at this time | Submitted |  | 0 | DSOW costs currently under review.
85 | Active | Attachment A | 1070380 | 38kV Transmission Line 2500 – Entire Line (Vegetation) | Vegetation | Vegetation-DL | No |  | 243413.96 | 2674937.64 | 2046.88 | 22466.54 | 0 | 0 | 2942865.02 | 245460.84 | 2697404.18 | 500370.58 | 4464753.76 | 15749.91 | 140499.07 | 0 | 0 | 5121373.32 | 516120.49 | 4605252.83 | Project in V0 - No amendment required at this time | Submitted |  | 0 | DSOW costs currently under review.
86 | Active | Attachment A | 1070356 | 38kV Transmission Line 3800 – Entire Line (Vegetation) | Vegetation | Vegetation-DL | No |  | 253749.1 | 2788513.05 | 2133.79 | 23420.45 | 0 | 0 | 3067816.39 | 255882.89 | 2811933.5 | 521385.27 | 4652265.54 | 16411.37 | 146399.79 | 0 | 0 | 5336461.97 | 537796.64 | 4798665.33 | Project in V0 - No amendment required at this time | Submitted |  | 0 | DSOW costs currently under review.
87 | Active | Attachment A | 1070366 | 38kV Transmission Line 100 – Entire Line (Vegetation) | Vegetation | Vegetation-DL | No |  | 254933.33 | 2801526.9 | 2143.75 | 23529.76 | 0 | 0 | 3082133.74 | 257077.08 | 2825056.66 | 523818.53 | 4673977.42 | 16487.97 | 147083.03 | 0 | 0 | 5361366.95 | 540306.5 | 4821060.45 | Project in V0 - No amendment required at this time | Submitted |  | 0 | DSOW costs currently under review.
88 | Active | Attachment A | 1070373 | 38kV Transmission Line 1200 – Entire Line (Vegetation) | Vegetation | Vegetation-DL | No |  | 275711.27 | 3029860.81 | 2318.47 | 25447.51 | 0 | 0 | 3333338.06 | 278029.74 | 3055308.32 | 566732.72 | 5056896.17 | 17838.75 | 159132.91 | 0 | 0 | 5800600.55 | 584571.47 | 5216029.08 | Project in V0 - No amendment required at this time | Submitted |  | 0 | DSOW costs currently under review.
89 | Active | Attachment A | 1070364 | 38kV Transmission Line 5600 – Entire Line (Vegetation) | Vegetation | Vegetation-DL | No |  | 293582.43 | 3226251.64 | 2468.74 | 27096.98 | 0 | 0 | 3549399.79 | 296051.17 | 3253348.62 | 592171.55 | 5283884.13 | 18639.48 | 166275.87 | 0 | 0 | 6060971.03 | 610811.03 | 5450160 | Project in V0 - No amendment required at this time | Submitted |  | 0 | DSOW costs currently under review.
90 | Active | Attachment A | 1070365 | 38kV Transmission Line 6500 – Entire Line (Vegetation) | Vegetation | Vegetation-DL | No |  | 447640.54 | 4919235.19 | 3764.22 | 41316.2 | 0 | 0 | 5411956.15 | 451404.76 | 4960551.39 | 603231.9 | 5382574.51 | 18987.62 | 169381.51 | 0 | 0 | 6174175.54 | 622219.52 | 5551956.02 | Project in V0 - No amendment required at this time | Submitted |  | 0 | DSOW costs currently under review.
91 | Active | Attachment A | 1070376 | 38kV Transmission Line 2000 – Entire Line (Vegetation) | Vegetation | Vegetation-DL | No |  | 303594.6 | 3336277.81 | 2552.93 | 28021.09 | 0 | 0 | 3670446.43 | 306147.53 | 3364298.9 | 623804.18 | 5566138.66 | 19635.16 | 175158 | 0 | 0 | 6384736 | 643439.34 | 5741296.66 | Project in V0 - No amendment required at this time | Submitted |  | 0 | DSOW costs currently under review.
92 | Active | Attachment A | 1070377 | 38kV Transmission Line 2100 – Entire Line (Vegetation) | Vegetation | Vegetation-DL | No |  | 304778.83 | 3349291.67 | 2562.89 | 28130.39 | 0 | 0 | 3684763.78 | 307341.72 | 3377422.06 | 626237.46 | 5587850.55 | 19711.75 | 175841.24 | 0 | 0 | 6409641 | 645949.21 | 5763691.79 | Project in V0 - No amendment required at this time | Submitted |  | 0 | DSOW costs currently under review.
93 | Active | Attachment A | 1070375 | 38kV Transmission Line 1600 – Entire Line (Vegetation) | Vegetation | Vegetation-DL | No |  | 305424.77 | 3356390.15 | 2568.32 | 28190 | 0 | 0 | 3692573.24 | 307993.09 | 3384580.15 | 627564.7 | 5599693.39 | 19753.53 | 176213.92 | 0 | 0 | 6423225.54 | 647318.23 | 5775907.31 | Project in V0 - No amendment required at this time | Submitted |  | 0 | DSOW costs currently under review.
94 | Active | Attachment A | 1070381 | 38kV Transmission Line 2700 – Entire Line (Vegetation) | Vegetation | Vegetation-DL | No |  | 409745.04 | 4502791.99 | 3445.55 | 37818.53 | 0 | 0 | 4953801.11 | 413190.59 | 4540610.52 | 841914.39 | 7512313.41 | 26500.5 | 236401.2 | 0 | 0 | 8617129.5 | 868414.89 | 7748714.61 | Project in V0 - No amendment required at this time | Submitted |  | 0 | DSOW costs currently under review.
95 | Active | Attachment A | 1070362 | 38kV Transmission Line 5300 – Entire Line (Vegetation) | Vegetation | Vegetation-DL | No |  | 166008.11 | 1824305.09 | 1395.97 | 15322.16 | 0 | 0 | 2007031.33 | 167404.08 | 1839627.25 | 879962.05 | 7851808.39 | 27698.11 | 247084.59 | 0 | 0 | 9006553.14 | 907660.16 | 8098892.98 | Project in V0 - No amendment required at this time | Submitted |  | 0 | DSOW costs currently under review.
96 | Active | Attachment A | 1070353 | 38kV Transmission Line 3700 – Entire Line (Vegetation) | Vegetation | Vegetation-DL | No |  | 470248.63 | 5167681.42 | 3954.33 | 43402.88 | 0 | 0 | 5685287.26 | 474202.96 | 5211084.3 | 966232.84 | 8621593.53 | 30413.61 | 271308.57 | 0 | 0 | 9889548.55 | 996646.45 | 8892902.1 | Project in V0 - No amendment required at this time | Submitted |  | 0 | DSOW costs currently under review.
97 | Active | Attachment A | 1070382 | 38kV Transmission Line 3000 – Entire Line (Vegetation) | Vegetation | Vegetation-DL | No |  | 491241.88 | 5398381.47 | 4130.86 | 45340.51 | 0 | 0 | 5939094.72 | 495372.74 | 5443721.98 | 1009368.22 | 9006486.09 | 31771.36 | 283420.56 | 0 | 0 | 10331046.23 | 1041139.58 | 9289906.65 | Project in V0 - No amendment required at this time | Submitted |  | 0 | DSOW costs currently under review.
98 | Active | Attachment A | 1070383 | 38kV Transmission Line 3100 – Entire Line (Vegetation) | Vegetation | Vegetation-DL | No |  | 650144.58 | 7144603.49 | 5467.08 | 60006.86 | 0 | 0 | 7860222.01 | 655611.66 | 7204610.35 | 1335869.96 | 11919826.8 | 42048.48 | 375099.01 | 0 | 0 | 13672844.25 | 1377918.44 | 12294925.81 | Project in V0 - No amendment required at this time | Submitted |  | 0 | DSOW costs currently under review.
99 | Active | Attachment A | 1070379 | 38kV Transmission Line 2200 – Entire Line (Vegetation) | Vegetation | Vegetation-DL | No |  | 805386.91 | 8850600.91 | 6772.52 | 74335.38 | 0 | 0 | 9737095.72 | 812159.43 | 8924936.29 | 1654850.74 | 14766058.02 | 52088.86 | 464665.63 | 0 | 0 | 16937663.25 | 1706939.6 | 15230723.65 | Project in V0 - No amendment required at this time | Submitted |  | 0 | DSOW costs currently under review.
100 | Active | Attachment A | 1068050 | Fiber Optic Replacement Group 1 | Telecommunication | IT/OT | No |  | 67811581.03 | 9902187.96 | 6835688.41 | 948496.8 | 108101.8 | 0 | 85606056 | 74755371.24 | 10850684.76 | 67950256.9 | 9790333.36 | 6910265.94 | 955199.8 | 0 | 0 | 85606056 | 74860522.84 | 10745533.16 | Project in V0 - No amendment required at this time | Submitted |  | 0 | DSOW costs currently under review.
101 | Active | Consolidated List | 169500 | FAASt [Bayamon TC - MC-BKRS-Y1] (Substation) | Substation | Substation Rebuilds | Yes | Obligated | 7511561.2795 | 1144238.3003 | 763861.7166 | 260304.4243 | 924443.5657 | 1718189.3207 | 12322598.607 | 9199866.5618 | 3122732.0452 | 2796182 | 2079072 | 634045 | 1496809 | 0 | 0 | 7006108 | 3430227 | 3575881 | Amendment Needed | Submitted | 2023-06-15 | 0 | Luma is finalizing the scope. The amendment is expected to be submitted Q1 FY2027. Cost change is driven by more defined scope and inflation.
102 | Active | Attachment A | 1070372 | FAASt [Region 1 San Juan Transmission 38kV sensitive areas] (Vegetation) - Group C | Vegetation | Vegetation-TL | No |  | 788376.99 | 8663674.704 | 6629.484 | 72765.402 | 0 | 0 | 9531446.58 | 795006.474 | 8736440.106 | 2175499.59 | 0 | 5700.47 | 0 | 0 | 0 | 2181200.06 | 2181200.06 | 0 | Project in V0 - No amendment required at this time | Submitted |  | 0 | DSOW costs currently under review.
103 | Active | Attachment A | 1070374 | FAASt [Region 4 Caguas Transmission 38kV sensitive areas] (Vegetation) - Group C | Vegetation | Vegetation-TL | No |  | 437628.366 | 4809208.998 | 3680.034 | 40392.096 | 0 | 0 | 5290909.494 | 441308.4 | 4849601.094 | 899207.04 | 8023529.69 | 28303.87 | 252488.4 | 0 | 0 | 9203529 | 927510.91 | 8276018.09 | Project in V0 - No amendment required at this time | Submitted |  | 0 | DSOW costs currently under review.
104 | Active | Attachment A | 1070402 | FAASt [Region 3 Bayamon Transmission 38kV sensitive areas] (Vegetation) - Group C | Vegetation | Vegetation-TL | No |  | 793759.878 | 8722828.56 | 6674.742 | 73262.238 | 0 | 0 | 9596525.418 | 800434.62 | 8796090.798 | 1630960.3 | 14552886.75 | 51336.88 | 457957.45 | 0 | 0 | 16693141.38 | 1682297.18 | 15010844.2 | Project in V0 - No amendment required at this time | Submitted |  | 0 | DSOW costs currently under review.
105 | Active | Attachment A | 1070368 | FAASt [Region 2 Arecibo Transmission 38kV sensitive areas] (Vegetation) - Group C | Vegetation | Vegetation-TL | No |  | 1105536.432 | 12149020.278 | 9296.478 | 102038.502 | 0 | 0 | 13365891.69 | 1114832.91 | 12251058.78 | 2271576.15 | 20269034.89 | 71501.21 | 637836.03 | 0 | 0 | 23249948.28 | 2343077.36 | 20906870.92 | Project in V0 - No amendment required at this time | Submitted |  | 0 | DSOW costs currently under review.
106 | Active | Attachment A | 1070367 | FAASt [Region 6 Ponce Transmission 38kV sensitive areas] (Vegetation) - Group C | Vegetation | Vegetation-TL | No |  | 1367036.856 | 15022714.938 | 11495.436 | 126174.408 | 0 | 0 | 16527421.638 | 1378532.292 | 15148889.346 | 2808888.31 | 25063414.67 | 88413.89 | 788707.97 | 0 | 0 | 28749424.84 | 2897302.2 | 25852122.64 | Project in V0 - No amendment required at this time | Submitted |  | 0 | DSOW costs currently under review.
107 | Active | Attachment A | 1070371 | FAASt [Region 5 Mayaguez Transmission 38kV sensitive areas] (Vegetation) - Group C | Vegetation | Vegetation-TL | No |  | 1232141.82 | 13540319.136 | 10361.1 | 113723.898 | 0 | 0 | 14896545.954 | 1242502.92 | 13654043.034 | 3094909.15 | 27615548.47 | 97416.82 | 869019.77 | 0 | 0 | 31676894.21 | 3192325.97 | 28484568.24 | Project in V0 - No amendment required at this time | Submitted |  | 0 | DSOW costs currently under review.
108 | Active | Consolidated List | 757662 | FAASt [Automation Program Group 21] (Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 1450834.51 | 409419.06 | 316327.09 | 133329.79 | 152199 | 326377 | 2788486.45 | 1919360.6 | 869125.85 | 1710547.94 | 0 | 280516.59 | 0 | 0 | 0 | 1991064.53 | 1991064.53 | 0 | Amendment Needed | Submitted | 2025-10-30 | 0 | 406HM revision to be submitted by the end of Q4 FY2026 to Grants Portal. Estimated date Cfci strategy to be defined. In addition to the amendment version, a revised differential estimate of $46,251.90 for the communications wireless portion was added to the 406 section (without A&E and E&M). Estimate is an Class 3.
109 | Active | Attachment A | 1070271 | Telecomm Infrastructure Group A | Telecommunication | IT/OT | No |  | 6440145.54 | 15927.16 | 1756408.47 | 4175.18 | 2800 | 0 | 8219456.35 | 8199354.01 | 20102.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project in V0 - No amendment required at this time | 2026-10-30 |  | 0 | The Detailed Scope of Work (DSOW) is currently being formulated. Once the DSOW is submitted to FEMA, the current cost columns will be updated to reflect the costs identified in the DSOW.
110 | Active | Attachment A | 1070272 | Telecomm Infrastructure Group D | Telecommunication | IT/OT | No |  | 5297451.62 | 18959.16 | 683790.17 | 2498.07 | 0 | 0 | 6002699.02 | 5981241.79 | 21457.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project in V0 - No amendment required at this time | 2026-10-30 |  | 0 | The Detailed Scope of Work (DSOW) is currently being formulated. Once the DSOW is submitted to FEMA, the current cost columns will be updated to reflect the costs identified in the DSOW.
111 | Active | Consolidated List | 757687 | FAASt [Automation Program Group 22] (Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 1746764.31 | 530280.7 | 364393.9 | 164099.27 | 176671.17 | 397630.03 | 3379839.38 | 2287829.38 | 1092010 | 2356733.87 | 0 | 359230.44 | 0 | 0 | 0 | 2715964.31 | 2715964.31 | 0 | Amendment Needed | Submitted | 2025-10-30 | 0 | 406HM revision to be submitted the end of Q4 FY2026 to Grants Portal. Estimated date Cfci strategy to be defined. In addition to the amendment version, a revised differential estimate of $61,669.20 for the communications wireless portion was added to the 406 section (without A&E and E&M). Estimate is a Class 3.
112 | Active | Consolidated List | 757694 | FAASt [Automation Program Group 27] (Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 1854481.54 | 591389.65 | 381502.7 | 196477.51 | 230481.01 | 495146.19 | 3749478.6 | 2466465.25 | 1283013.35 | 2314733.78 | 0 | 419922.13 | 0 | 0 | 0 | 2734655.91 | 2734655.91 | 0 | Amendment Needed | Submitted | 2025-09-25 | 0 | 406HM revision to be submitted by the end of Q4 FY2026 to Grants Portal. Waiting for COR3 feedback/ Estimated date Cfci strategy to be defined. In addition to the amendment version, a revised differential estimate of $53,960.55 for the communications wireless portion was added to the 406 section (without A&E and E&M). Estimate is an Class 3.
113 | Active | Consolidated List | 757697 | FAASt [Automation Program Group 32] (TL / Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 2053127.85 | 562049.57 | 317057.24 | 138127.24 | 219381.16 | 471983.84 | 3761726.9 | 2589566.25 | 1172160.65 | 1996678.58 | 0 | 339647.19 | 0 | 0 | 0 | 2336325.77 | 2336325.77 | 0 | Amendment Needed | Submitted | 2025-09-25 | 0 | 406HM revision to be submitted by the end of Q4 FY2026 to Grants Portal. Waiting for COR3 feedback/ Estimated date Cfci strategy to be defined. In addition to the amendment version, a revised differential estimate of $53,960.55 for the communications wireless portion was added to the 406 section (without A&E and E&M). Estimate is an Class 3.
114 | Active | Consolidated List | 668583 | FAASt Line 13300 GOAB 13301C to Hato Tejas Se | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 909002.34 | 5807.1 | 55062.25 | 2246.48 | 100526.19 | 18046.81 | 1090691.17 | 1064590.78 | 26100.39 | 28826526.19 | 0 | 81996 | 0 | 0 | 0 | 28908522.19 | 28908522.19 | 0 | Amendment Needed | Submitted | 2022-08-01 | 1 | This information reflects the latest LPCE data provided and includes the actuals delta. The final cost will be taken into consideration during the project reconciliation and close-out.
115 | Active | Consolidated List | 542690 | FAASt Maunabo Streetlighting (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 5640236 | 197986.2881 | 984819 | 48872.7119 | 0 | 0 | 6871914 | 6625055 | 246859 | 6199877.07 | 195597.33 | 1530438.49 | 48283 | 0 | 0 | 7974195.89 | 7730315.56 | 243880.33 | Amendment Needed | Submitted | 2022-05-04 | 0 | This project was among the first to be developed, originally including the underground work as part of the program's initial scope—estimated at $1M for this portion to be removed. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 95.09% (2306 locations completed).Estimate ammedment submission Q2 FY2027.
116 | Active | Consolidated List | 659715 | FAASt Distribution Streetlighting - Aibonito | Distribution | Distribution Streetlighting | Yes | Obligated | 5738710 | 137843.3353 | 1197087 | 52403.6647 | 0 | 0 | 7126044 | 6935797 | 190247 | 7074498 | 129540 | 1880873 | 49247 | 0 | 0 | 9134158 | 8955371 | 178787 | Amendment Needed | Submitted | 2022-12-23 | 0 | This project was among the first to be developed, originally including the underground work as part of the program's initial scope—estimated at: $2M for this portion to be removed. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 89.62% (2496 locations completed). Estimate amendment submission Q2 FY2027.
117 | Active | Consolidated List | 660239 | FAASt Streetlighting - Villalba (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 12489008.47 | 607135.3755 | 1810409 | 85900.6245 | 0 | 0 | 14992453.47 | 14299417.47 | 693036 | 10190536 | 597349.58 | 2630718.61 | 84516.08 | 0 | 0 | 13503120.27 | 12821254.61 | 681865.66 | Amendment Needed | Submitted | 2022-08-23 | 0 | This project is currently over budget because the work assigned, based on vendor rates, exceeded the Class 3 estimate. Based on a high‑level evaluation, the work that can be executed within the remaining budget is estimated to be approximately $2,195,079.47 to cover both overruns and pending work (Added to 428 Child for FFO review). This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 90.60% (3065 locations completed).
118 | Active | Consolidated List | 542756 | FAASt Streetlighting - Guánica (Distribution | Distribution | Distribution Streetlighting | Yes | Obligated | 6817015 | 506125.5667 | 1189325 | 116896.4333 | 0 | 0 | 8629362 | 8006340 | 623022 | 9687238 | 301234 | 2237386 | 69574 | 0 | 0 | 12295432 | 11924624 | 370808 | Amendment Needed | Submitted | 2022-05-25 | 0 | This project was among the first to be developed, originally including the underground work as part of the program's initial scope—estimated at $3M for this portion to be removed. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 86.43% (2598 locations completed). Estimate ammedment submission Q2 FY2027.
119 | Active | Consolidated List | 542687 | FAASt Lajas Streetlighting (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 10510560 | 793672.8937 | 1674019 | 194038.1063 | 0 | 0 | 13172290 | 12184579 | 987711 | 10278336.09 | 342578.48 | 2512853.73 | 83754 | 0 | 0 | 13217522.3 | 12791189.82 | 426332.48 | Amendment Needed | Submitted | 2022-05-19 | 1 | This project was among the first to be developed, originally including the underground work as part of the program's initial scope—estimated at $45K for this portion to be removed. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 93.87% (3888 locations completed).Estimate ammedment submission Q1 FY2027.
120 | Active | Consolidated List | 542688 | FAASt Aguada Streetlighting (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 17056591 | 1425202.197 | 2565976 | 329317.803 | 0 | 0 | 21377087 | 19622567 | 1754520 | 17764494.34 | 655709.04 | 4104785.76 | 151513 | 0 | 0 | 22676502.14 | 21869280.1 | 807222.04 | Amendment Needed | Submitted | 2022-04-27 | 1 | This project was among the first to be developed, originally including the underground work as part of the program's initial scope—estimated at $1.2M for this portion to be removed. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 88.74% (6047 locations completed).
121 | Active | Consolidated List | 757699 | FAASt [Automation Program Group 34] (Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 2072695.44 | 606035.3 | 433846.26 | 195477.43 | 209012.07 | 473571.13 | 3990637.63 | 2715553.77 | 1275083.86 | 2755938.99 | 0 | 462362.68 | 0 | 0 | 0 | 3218301.67 | 3218301.67 | 0 | Amendment Needed | Submitted | 2025-11-05 | 0 | 406HM revision to be submitted by the end of Q4 FY2026 to Grants Portal. Estimated date Cfci strategy to be defined. In addition to the amendment version, a revised differential estimate of $61,669.20 for the communications wireless portion was added to the 406 section (without A&E and E&M). Estimate is an Class 3.
122 | Active | Attachment A | 1070285 | FAASt [San Juan Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | No |  | 28178017.76 | 2123472.21 | 6380570.04 | 123157.52 | 0 | 0 | 36805217.53 | 34558587.8 | 2246629.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project in V0 - No amendment required at this time | 2026-10-05 |  | 0 | The Detailed Scope of Work (DSOW) is currently being formulated. Once the DSOW is submitted to FEMA, the current cost columns will be updated to reflect the costs identified in the DSOW.
123 | Active | Attachment A | 1070288 | FAASt [Ponce Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | No |  | 10968715.275 | 884181.41 | 1713141.92 | 51717 | 0 | 0 | 13617755.605 | 12681857.195 | 935898.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project in V0 - No amendment required at this time | 2026-10-05 |  | 0 | The Detailed Scope of Work (DSOW) is currently being formulated. Once the DSOW is submitted to FEMA, the current cost columns will be updated to reflect the costs identified in the DSOW.
124 | Active | Attachment A | 1070295 | FAASt [Cayey Streetlighting] | Distribution | Distribution Streetlighting | No |  | 10596790.82 | 1275717.24 | 2435204.39 | 95954.76 | 0 | 0 | 14403667.21 | 13031995.21 | 1371672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project in V0 - No amendment required at this time | 2026-10-05 |  | 0 | The Detailed Scope of Work (DSOW) is currently being formulated. Once the DSOW is submitted to FEMA, the current cost columns will be updated to reflect the costs identified in the DSOW.
125 | Active | Attachment A | 1070289 | FAASt [Arecibo Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | No |  | 11879105.0925 | 800134.36 | 1902215.74 | 59360 | 0 | 0 | 14640815.1925 | 13781320.8325 | 859494.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project in V0 - No amendment required at this time | 2026-10-05 |  | 0 | The Detailed Scope of Work (DSOW) is currently being formulated. Once the DSOW is submitted to FEMA, the current cost columns will be updated to reflect the costs identified in the DSOW.
126 | Active | Attachment A | 1070286 | FAASt [Utuado Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | No |  | 16760927.205 | 2851675.47 | 3319870.72 | 155072.6 | 0 | 0 | 23087545.995 | 20080797.925 | 3006748.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project in V0 - No amendment required at this time | 2026-10-05 |  | 0 | The Detailed Scope of Work (DSOW) is currently being formulated. Once the DSOW is submitted to FEMA, the current cost columns will be updated to reflect the costs identified in the DSOW.
127 | Active | Attachment A | 1070287 | FAASt [Barceloneta Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | No |  | 7422038.0375 | 477869.14 | 1206563.5 | 50306 | 0 | 0 | 9156776.6775 | 8628601.5375 | 528175.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project in V0 - No amendment required at this time | 2026-10-05 |  | 0 | The Detailed Scope of Work (DSOW) is currently being formulated. Once the DSOW is submitted to FEMA, the current cost columns will be updated to reflect the costs identified in the DSOW.
128 | Active | Attachment A | 1070296 | FAASt [Guayama Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | No |  | 4107291.015 | 305442.59 | 1011463.98 | 25642.92 | 0 | 0 | 5449840.505 | 5118754.995 | 331085.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project in V0 - No amendment required at this time | 2026-10-05 |  | 0 | The Detailed Scope of Work (DSOW) is currently being formulated. Once the DSOW is submitted to FEMA, the current cost columns will be updated to reflect the costs identified in the DSOW.
129 | Active | Attachment A | 1070278 | TPole 13700 Mora TC to Isabela TO | Transmission | Transmission Priority Pole Replacements | No |  | 591148.31 | 7196.15 | 103198.13 | 1529 | 35991.1 | 2143.44 | 741206.13 | 730337.54 | 10868.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project in V0 - No amendment required at this time | 2026-10-15 |  | 0 | The Detailed Scope of Work (DSOW) is currently being formulated. Once the DSOW is submitted to FEMA, the current cost columns will be updated to reflect the costs identified in the DSOW.
130 | Active | Attachment A | 1070277 | TPole 3300 San Gerardo Sect to Venezuela Sect | Transmission | Transmission Priority Pole Replacements | No |  | 299085.29 | 81090.53 | 55226.85 | 14556.86 | 12296.95 | 1013.73 | 463270.21 | 366609.09 | 96661.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project in V0 - No amendment required at this time | 2026-10-15 |  | 0 | The Detailed Scope of Work (DSOW) is currently being formulated. Once the DSOW is submitted to FEMA, the current cost columns will be updated to reflect the costs identified in the DSOW.
131 | Active | Consolidated List | 176971 | FAASt –38kV Line 8200 - San Juan SP to Catano Sect Line (Transmission) | Priority Transmission | Transmission Line Rebuild | Yes | Obligated | 18218875.04 | 4631659.7 | 2848814.49 | 568928.1 | 1080651.07 | 23122.43 | 27372050.83 | 22148340.6 | 5223710.23 | 21670623.78 | 0 | 3124951.32 | 0 | 0 | 0 | 24795575.1 | 24795575.1 | 0 | Amendment Needed | Submitted | 2025-11-05 | 0
132 | Active | Consolidated List | 801166 | FAASt [Feeder Rebuild # 6601-03] (Distribution) | Distribution | Distribution Feeders | Yes | Obligated | 19979701.47 | 0 | 1724565.72 | 0 | 2135838.13 | 0 | 23840105.32 | 23840105.32 | 0 | 19826783.47 | 0 | 1724565.72 | 0 | 0 | 0 | 21551349.19 | 21551349.19 | 0 | Amendment Needed | Submitted | 2026-01-08 | 0 | The project was fully obligated under Section 428 using the Class 3 estimate. Versioning was submitted, including the split between 428 and 406, and it is currently under FEMA evaluation. The final DSOW versioning will be submitted, reflecting an additional $152,918 to the approved budget.
133 | Active | Attachment A | 1070300 | FAASt [Toa Alta Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | No |  | 4767387.52 | 197071.81 | 1162797.94 | 17891.57 | 0 | 0 | 6145148.84 | 5930185.46 | 214963.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project in V0 - No amendment required at this time | 2026-11-02 |  | 0 | The Detailed Scope of Work (DSOW) is currently being formulated. Once the DSOW is submitted to FEMA, the current cost columns will be updated to reflect the costs identified in the DSOW.
134 | Active | Attachment A | 1070294 | FAASt [Humacao Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | No |  | 6455271.8825 | 488325.81 | 1006696.36 | 29209 | 0 | 0 | 7979503.0525 | 7461968.2425 | 517534.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project in V0 - No amendment required at this time | 2026-11-02 |  | 0 | The Detailed Scope of Work (DSOW) is currently being formulated. Once the DSOW is submitted to FEMA, the current cost columns will be updated to reflect the costs identified in the DSOW.
135 | Active | Attachment A | 1070293 | FAASt [Isabela Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | No |  | 6005455.39 | 671912.08 | 1332970.6 | 37797.8 | 0 | 0 | 8048135.87 | 7338425.99 | 709709.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project in V0 - No amendment required at this time | 2026-11-02 |  | 0 | The Detailed Scope of Work (DSOW) is currently being formulated. Once the DSOW is submitted to FEMA, the current cost columns will be updated to reflect the costs identified in the DSOW.
136 | Active | Attachment A | 1070298 | [Rio Grande Streetlighting] (Distribution | Distribution | Distribution Streetlighting | No |  | 5347407.42 | 397032.05 | 1156399.63 | 21533.62 | 0 | 0 | 6922372.72 | 6503807.05 | 418565.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project in V0 - No amendment required at this time | 2026-11-02 |  | 0 | The Detailed Scope of Work (DSOW) is currently being formulated. Once the DSOW is submitted to FEMA, the current cost columns will be updated to reflect the costs identified in the DSOW.
137 | Active | Attachment A | 1070303 | FAASt [Juana Diaz Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | No |  | 14011750.655 | 872747.53 | 2795912.01 | 55146.97 | 0 | 0 | 17735557.165 | 16807662.665 | 927894.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project in V0 - No amendment required at this time | 2026-11-02 |  | 0 | The Detailed Scope of Work (DSOW) is currently being formulated. Once the DSOW is submitted to FEMA, the current cost columns will be updated to reflect the costs identified in the DSOW.
138 | Active | Attachment A | 1070297 | FAASt [Juncos Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | No |  | 10994681.6975 | 685135.01 | 1631297.312 | 26436.06 | 0 | 0 | 13337550.0795 | 12625979.0095 | 711571.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project in V0 - No amendment required at this time | 2026-11-02 |  | 0 | The Detailed Scope of Work (DSOW) is currently being formulated. Once the DSOW is submitted to FEMA, the current cost columns will be updated to reflect the costs identified in the DSOW.
139 | Active | Attachment A | 1070301 | FAASt [Vega Baja Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | No |  | 8602549.46 | 1056851.66 | 1621313.74 | 17891.57 | 0 | 0 | 11298606.43 | 10223863.2 | 1074743.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project in V0 - No amendment required at this time | 2026-11-02 |  | 0 | The Detailed Scope of Work (DSOW) is currently being formulated. Once the DSOW is submitted to FEMA, the current cost columns will be updated to reflect the costs identified in the DSOW.
140 | Active | Attachment A | 1070347 | FAASt [Cabo Rojo Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | No |  | 7308020.08 | 517830.31 | 1689593.17 | 41489.51 | 0 | 0 | 9556933.07 | 8997613.25 | 559319.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project in V0 - No amendment required at this time | 2026-11-30 |  | 0 | The Detailed Scope of Work (DSOW) is currently being formulated. Once the DSOW is submitted to FEMA, the current cost columns will be updated to reflect the costs identified in the DSOW.
141 | Active | Attachment A | 1070348 | [Loiza Streetlighting] (Distribution | Distribution | Distribution Streetlighting | No |  | 6213147.88 | 388351.58 | 1248099.37 | 14137.5 | 0 | 0 | 7863736.33 | 7461247.25 | 402489.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project in V0 - No amendment required at this time | 2026-11-30 |  | 0 | The Detailed Scope of Work (DSOW) is currently being formulated. Once the DSOW is submitted to FEMA, the current cost columns will be updated to reflect the costs identified in the DSOW.
142 | Active | Attachment A | 1070302 | [Vieques Streetlighting] (Distribution | Distribution | Distribution Streetlighting | No |  | 3987957.0575 | 454616.91 | 810226.05 | 32120.4 | 0 | 0 | 5284920.4175 | 4798183.1075 | 486737.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project in V0 - No amendment required at this time | 2026-11-30 |  | 0 | The Detailed Scope of Work (DSOW) is currently being formulated. Once the DSOW is submitted to FEMA, the current cost columns will be updated to reflect the costs identified in the DSOW.
143 | Active | Attachment A | 1070279 | Automation Program Group 39 (Distribution) | Distribution | Automation | No |  | 1256040 | 395420 | 116300 | 69780 | 162820 | 325640 | 2326000 | 1535160 | 790840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project in V0 - No amendment required at this time | 2026-11-30 |  | 0 | The Detailed Scope of Work (DSOW) is currently being formulated. Once the DSOW is submitted to FEMA, the current cost columns will be updated to reflect the costs identified in the DSOW.
144 | Active | Attachment A | 1070306 | [San Sebastian Streetlighting] (Distribution | Distribution | Distribution Streetlighting | No |  | 21521273.585 | 1542129.95 | 4057973.95 | 94811.81 | 0 | 0 | 27216189.295 | 25579247.535 | 1636941.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project in V0 - No amendment required at this time | 2026-11-30 |  | 0 | The Detailed Scope of Work (DSOW) is currently being formulated. Once the DSOW is submitted to FEMA, the current cost columns will be updated to reflect the costs identified in the DSOW.
145 | Active | Attachment A | 1070346 | FAASt [Camuy Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | No |  | 14028036.5825 | 867189.9 | 1972441.141 | 107984.699 | 0 | 0 | 16975652.3225 | 16000477.7235 | 975174.599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project in V0 - No amendment required at this time | 2026-11-30 |  | 0 | The Detailed Scope of Work (DSOW) is currently being formulated. Once the DSOW is submitted to FEMA, the current cost columns will be updated to reflect the costs identified in the DSOW.
146 | Active | Attachment A | 1070305 | FAASt [Canovanas Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | No |  | 11994894.83 | 1520521.43 | 2377385.56 | 89359.81 | 0 | 0 | 15982161.63 | 14372280.39 | 1609881.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project in V0 - No amendment required at this time | 2026-11-30 |  | 0 | The Detailed Scope of Work (DSOW) is currently being formulated. Once the DSOW is submitted to FEMA, the current cost columns will be updated to reflect the costs identified in the DSOW.
147 | Active | Attachment A | 1070403 | Mobile Substations | Substation | TBD | No |  | 0 | 0 | 0 | 0 | 17709050 | 0 | 17709050 | 17709050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project in V0 - No amendment required at this time | 2026-12-04 |  | 0 | The Detailed Scope of Work (DSOW) is currently being formulated. Once the DSOW is submitted to FEMA, the current cost columns will be updated to reflect the costs identified in the DSOW.
148 | Active | Consolidated List | 180052 | FAASt Ponce TC to Salinas Urbano TC- 38kV 100 & 200 (Transmission) | Priority Transmission | Transmission Line Rebuild | Yes | Obligated | 189214147.25 | 38650198.93 | 18683215.39 | 6899520.54 | 21880052.02 | 41872865.87 | 317200000 | 229777414.66 | 87422585.34 | 74520098.48 | 0 | 8369786.38 | 0 | 0 | 0 | 82889884.86 | 82889884.86 | 0 | Amendment Needed | Submitted |  | 0 | Currently undergoing redesign with updated scope, latest estimate reflects $317M. The scope will be reconfigured to go from a double circuit (100 & 200) to a single circuit with a higher capacity.
149 | Active | Attachment A | 1070283 | FAASt [25 MW BESS Installation and Integration - San Juan] (Substation) | Substation | Grid Modernization | No |  | 0 | 24053536.03 | 0 | 3187811.29 | 0 | 28261718.24 | 55503065.56 | 0 | 55503065.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project in V0 - No amendment required at this time | 2026-12-18 |  | 0 | The Detailed Scope of Work (DSOW) is currently being formulated. Once the DSOW is submitted to FEMA, the current cost columns will be updated to reflect the costs identified in the DSOW.
150 | Active | Attachment A | 1070282 | FAASt [25 MW BESS Installation and Integration - Aguadilla] (Substation) | Substation | Grid Modernization | No |  | 0 | 21118171.64 | 0 | 3340630.47 | 0 | 28261718.24 | 52720520.35 | 0 | 52720520.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project in V0 - No amendment required at this time | 2026-12-18 |  | 0 | The Detailed Scope of Work (DSOW) is currently being formulated. Once the DSOW is submitted to FEMA, the current cost columns will be updated to reflect the costs identified in the DSOW.
151 | Active | Attachment A | 1070284 | FAASt [4 x 25 MW BESS Interconnections Manati] (Substation) | Substation | Grid Modernization | No |  | 0 | 23808829.62 | 0 | 3414922.97 | 0 | 30416253.08 | 57640005.67 | 0 | 57640005.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project in V0 - No amendment required at this time | 2026-12-18 |  | 0 | The Detailed Scope of Work (DSOW) is currently being formulated. Once the DSOW is submitted to FEMA, the current cost columns will be updated to reflect the costs identified in the DSOW.
152 | Active | Attachment A | 1070280 | FAASt [25 MW BESS Installation and Integration - Barceloneta] (Substation) | Substation | Grid Modernization | No |  | 0 | 20318919.35 | 0 | 5211394.35 | 0 | 30411453.8 | 55941767.5 | 0 | 55941767.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project in V0 - No amendment required at this time | 2026-12-18 |  | 0 | The Detailed Scope of Work (DSOW) is currently being formulated. Once the DSOW is submitted to FEMA, the current cost columns will be updated to reflect the costs identified in the DSOW.
153 | Active | Consolidated List | 547251 | FAASt Line 2400 Dos Bocas HP to America Apparel (Transmission) | Transmission | Transmission Line Rebuild | Yes | Obligated | 41036495.65 | 5812385.04 | 3399766.76 | 535704.77 | 7682133.79 | 343803.19 | 58810289.2 | 52118396.2 | 6691893 | 50289473.68 | 0 | 3753435.29 | 0 | 0 | 0 | 54042908.97 | 54042908.97 | 0 | Amendment Needed | Submitted | 2026-02-20 | 0 | The information reflects the latest LPCE data provided. The cost currently includes the full line rebuild A&E design cost, under 428. This will be corrected through the obligation amendment.
154 | Active | Attachment A | 1070307 | [Yauco Streetlighting] (Distribution | Distribution | Distribution Streetlighting | No |  | 13232024.93 | 1588137.76 | 2540431.6 | 79529.34 | 0 | 0 | 17440123.63 | 15772456.53 | 1667667.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project in V0 - No amendment required at this time | 2026-12-28 |  | 0 | The Detailed Scope of Work (DSOW) is currently being formulated. Once the DSOW is submitted to FEMA, the current cost columns will be updated to reflect the costs identified in the DSOW.
155 | Active | Attachment A | 1070355 | [Maricao Streetlighting] (Distribution | Distribution | Distribution Streetlighting | No |  | 4873133.615 | 921314.71 | 926826.7734 | 43337.3166 | 0 | 0 | 6764612.415 | 5799960.3884 | 964652.0266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project in V0 - No amendment required at this time | 2026-12-28 |  | 0 | The Detailed Scope of Work (DSOW) is currently being formulated. Once the DSOW is submitted to FEMA, the current cost columns will be updated to reflect the costs identified in the DSOW.
156 | Active | Attachment A | 1070357 | FAASt [Hormigueros Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | No |  | 5999141.915 | 489811.44 | 1362869.66 | 17724.97 | 0 | 0 | 7869547.985 | 7362011.575 | 507536.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project in V0 - No amendment required at this time | 2026-12-28 |  | 0 | The Detailed Scope of Work (DSOW) is currently being formulated. Once the DSOW is submitted to FEMA, the current cost columns will be updated to reflect the costs identified in the DSOW.
157 | Active | Attachment A | 1070358 | FAASt [Santa Isabel Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | No |  | 8526009.33 | 383038.38 | 1562084.58 | 22536.63 | 0 | 0 | 10493668.92 | 10088093.91 | 405575.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project in V0 - No amendment required at this time | 2026-12-28 |  | 0 | The Detailed Scope of Work (DSOW) is currently being formulated. Once the DSOW is submitted to FEMA, the current cost columns will be updated to reflect the costs identified in the DSOW.
158 | Active | Attachment A | 1070359 | FAASt [Fajardo Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | No |  | 11073921.95 | 1052403.97 | 2150579.88 | 58676.25 | 0 | 0 | 14335582.05 | 13224501.83 | 1111080.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project in V0 - No amendment required at this time | 2026-12-28 |  | 0 | The Detailed Scope of Work (DSOW) is currently being formulated. Once the DSOW is submitted to FEMA, the current cost columns will be updated to reflect the costs identified in the DSOW.
159 | Active | Attachment A | 1070345 | [San Lorenzo Streetlighting] (Distribution | Distribution | Distribution Streetlighting | No |  | 13787578.6125 | 968406.72 | 2944605.83 | 60896.29 | 0 | 0 | 17761487.4525 | 16732184.4425 | 1029303.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project in V0 - No amendment required at this time | 2026-12-28 |  | 0 | The Detailed Scope of Work (DSOW) is currently being formulated. Once the DSOW is submitted to FEMA, the current cost columns will be updated to reflect the costs identified in the DSOW.
160 | Active | Attachment C | 1072365 | FAASt [Juncos TC Substation Component Replacement] (Substation) | Substation | Substation Component Replacements | No |  | 12436054.15 | 2868434.03 | 548875.4 | 281565.59 | 2580317.19 | 860105.73 | 19575352.09 | 15565246.74 | 4010105.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project in V0 - No amendment required at this time. | 2026-12-31 |  | 0 | The Detailed Scope of Work (DSOW) is currently being formulated. Once the DSOW is submitted to FEMA, the current cost columns will be updated to reflect the costs identified in the DSOW.
161 | Active | Attachment C | 1072366 | FAASt [Aguas Buenas Substation Component Replacement] (Substation) | Substation | Substation Component Replacements | No |  | 5614147.55 | 2622060.62 | 482672.57 | 65309.65 | 1241258.17 | 259726.64 | 10285175.2 | 7338078.29 | 2947096.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project in V0 - No amendment required at this time. | 2026-12-31 |  | 0 | The Detailed Scope of Work (DSOW) is currently being formulated. Once the DSOW is submitted to FEMA, the current cost columns will be updated to reflect the costs identified in the DSOW.
162 | Active | Attachment C | 1072367 | FAASt [Veredas Sector Substation Component Replacement] (Substation) | Substation | Substation Component Replacements | No |  | 5467624.97 | 2622060.62 | 236211.04 | 65309.65 | 1341072.11 | 447024.04 | 10179302.43 | 7044908.12 | 3134394.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project in V0 - No amendment required at this time. | 2026-12-31 |  | 0 | The Detailed Scope of Work (DSOW) is currently being formulated. Once the DSOW is submitted to FEMA, the current cost columns will be updated to reflect the costs identified in the DSOW.
163 | Active | Consolidated List | 169276 | FAASt Substation - Viaducto TC - MC 1100 - Equipment Repair & Replacement (Substation) | Substation | Substation Rebuilds | No | Pending Scope & Cost Completion by Applicant | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | New V0 to be submitted to COR3/PREPA | 2027-01-29 |  | 0 | The updatedDetailed Scope of Work (DSOW) is currently being formulated. Once the DSOW is submitted to FEMA, the current cost columns will be updated to reflect the costs identified in the DSOW.
164 | Active | Attachment A | 1066734 | Acacias 6801 TC (Relocation) | Substation | Substation Rebuilds | No |  | 65766025.0617 | 31538831.8413 | 2841208.2382 | 785561.5157 | 12378234.9672 | 3124060.0459 | 116433921.67 | 80985468.2671 | 35448453.4029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project in V0 - No amendment required at this time | 2027-02-26 |  | 0 | The Detailed Scope of Work (DSOW) is currently being formulated. Once the DSOW is submitted to FEMA, the current cost columns will be updated to reflect the costs identified in the DSOW.
165 | Active | Attachment A | 1066979 | Esc Industrial Miguel Such (Metal-Clad) 1423 | Substation | Substation Rebuilds | No |  | 3301739.68 | 1135704.94 | 1112050.13 | 0 | 6614733.66 | 4603565.8 | 16767794.21 | 11028523.47 | 5739270.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project in V0 - No amendment required at this time | 2027-02-26 |  | 0 | The Detailed Scope of Work (DSOW) is currently being formulated. Once the DSOW is submitted to FEMA, the current cost columns will be updated to reflect the costs identified in the DSOW.
166 | Active | Attachment A | 1070378 | Distribution Underground Circuit Feeders - San Juan Group 1 | Distribution | Underground | No |  | 4310111.715 | 9577521.9267 | 362956.776 | 812115.7863 | 1512.3199 | 58980.4761 | 15123199 | 4674580.8109 | 10448618.1891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project in V0 - No amendment required at this time | 2027-03-27 |  | 0 | The Detailed Scope of Work (DSOW) is currently being formulated. Once the DSOW is submitted to FEMA, the current cost columns will be updated to reflect the costs identified in the DSOW.
167 | Active | Attachment A | 1070276 | Cambalache TC Rebuild | Substation | Substation Rebuilds | No |  | 4966986.47 | 62195402.17 | 344907.31 | 9217663.45 | 151612.12 | 13320220.44 | 90196791.96 | 5463505.9 | 84733286.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project in V0 - No amendment required at this time | 2027-03-31 |  | 0 | The Detailed Scope of Work (DSOW) is currently being formulated. Once the DSOW is submitted to FEMA, the current cost columns will be updated to reflect the costs identified in the DSOW.
168 | Active | Consolidated List | 178577 | FAASt [Cachete – MC 1526] (Substations) | Substation | Substation | No | Pending Scope & Cost Completion by Applicant | 28780859.5334 | 8197490.385 | 3180011.1696 | 1083666.0036 | 39248524.9358 | 7152945.5114 | 87643497.5388 | 71209395.6388 | 16434101.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project in V0 - No amendment required at this time | 2027-03-31 |  | 0 | The updated Detailed Scope of Work (DSOW) is currently being formulated. Once the DSOW is submitted to FEMA, the current cost columns will be updated to reflect the costs identified in the DSOW.
169 | Active | Consolidated List | 169058 | FAASt - Llorens Torres MC 1106 - Equipment Repair & Replacement - (Substations) | Substation | Substation Rebuilds | No | Pending Scope & Cost Completion by Applicant | 20962734.639 | 10164051.2316 | 1335184.07 | 721159.747 | 4713846.148 | 3706655.7 | 41603631.5356 | 27011764.857 | 14591866.6786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project in V0 - No amendment required at this time | 2027-05-28 |  | 0 | The updated Detailed Scope of Work (DSOW) is currently being formulated. Once the DSOW is submitted to FEMA, the current cost columns will be updated to reflect the costs identified in the DSOW.
170 | Active | Consolidated List | 723002 | FAASt - EPC - Jobos TC (Substation) | Substation | Substation | No | Pending Scope & Cost Completion by Applicant | 51025274.884 | 7772694.8675 | 5188835.2651 | 1768221.5863 | 6279651.4998 | 11671486.0104 | 83706164.113 | 62493761.6489 | 21212402.4641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project in V0 - No amendment required at this time | 2027-06-30 |  | 0 | The updated Detailed Scope of Work (DSOW) is currently being formulated. Once the DSOW is submitted to FEMA, the current cost columns will be updated to reflect the costs identified in the DSOW.
171 | Active | Consolidated List | 168483 | FAASt - 115kV Line 36400 - Dos Bocas HP to Ponce TC (Transmission) | Transmission | Transmission Line Rebuild | No | Pending Scope & Cost Completion by Applicant | 73843869.7985 | 62335950.1897 | 4386536.3259 | 3697488.9625 | 29668.6935 | 0 | 144293513.97 | 78260074.8179 | 66033439.1521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project in V0 - No amendment required at this time | 2027-07-29 |  | 0 | The updated Detailed Scope of Work (DSOW) is currently being formulated. Once the DSOW is submitted to FEMA, the current cost columns will be updated to reflect the costs identified in the DSOW.
172 | Active | Attachment A | 1066729 | Guaynabo Pueblo | Substation | Substation Rebuilds | No |  | 9487047.4 | 4257510.71 | 2263654.35 | 576564.36 | 4962433.97 | 3961056.7649 | 25508267.5549 | 16713135.72 | 8795131.8349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project in V0 - No amendment required at this time | 2027-07-30 |  | 0 | The Detailed Scope of Work (DSOW) is currently being formulated. Once the DSOW is submitted to FEMA, the current cost columns will be updated to reflect the costs identified in the DSOW.
173 | Active | Consolidated List | 662238 | FAASt [Microwave Point-to-Point Backbone] (Telecommunications) | Telecommunication | IT/OT | Yes | Obligated | 28826526.1978 | 5417440.08 | 2708469.2267 | 509009.2933 | 0 | 0 | 37461444.7978 | 31534995.4245 | 5926449.3733 | 28826526.19 | 5417440.08 | 2708469.23 | 509009.29 | 0 | 0 | 37461444.79 | 31534995.42 | 5926449.37 | No amendment need has been identified | Submitted | 2026-06-12 | 0 | Project under CRC review; Pending Obligation.
174 | Active | Consolidated List | 956357 | FAASt [Mayaguez Region 5 Line 1900 – Dos Bocas HP to San Sebastian TC] (Vegetation) | Vegetation | Vegetation-TL | Yes | Obligated | 1879460.01 | 5159401.236 | 156127.392 | 428400.39 | 0 | 0 | 7623389.028 | 2035587.402 | 5587801.626 | 131240.8 | 1561542.33 | 10902.38 | 0 | 0 | 0 | 1703685.51 | 142143.18 | 1561542.33 | Amendment Needed | Submitted | 2026-06-12 | 0 | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. . Amendment will be needed after work completion and /or assessment completion.
175 | Active | Consolidated List | 956348 | FAASt [Bayamon Region 3 Line 10000 – Bayamon Pueblo to Magnolia TO] (Vegetation) | Vegetation | Vegetation-TL | Yes | Obligated | 176585.496 | 484753.794 | 14669.028 | 40250.52 | 0 | 0 | 716258.838 | 191254.524 | 525004.314 | 9404.88 | 111902.06 | 781.28 | 0 | 0 | 0 | 122088.22 | 10186.16 | 111902.06 | Amendment Needed | Submitted | 2026-04-24 | 0 | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. Amendment will be needed after work completion and /or assessment completion.
176 | Active | Consolidated List | 956345 | FAASt [Arecibo Region 2 Line 2400 – Dos Bocas HP to Coronillas 2] (Vegetation) | Vegetation | Vegetation-TL | Yes | Obligated | 1083485.898 | 2974332.24 | 90005.55 | 246967.614 | 0 | 0 | 4394791.302 | 1173491.448 | 3221299.854 | 57284.26 | 681585.26 | 4758.69 | 0 | 0 | 0 | 743628.21 | 62042.95 | 681585.26 | Amendment Needed | Submitted | 2026-04-24 | 0 | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. . Amendment will be needed after work completion and /or assessment completion.
177 | Active | Consolidated List | 711819 | FAASt [Transmission Priority Pole Replacement Program Line 13400 San German Sect-La Parguera Sect] (Transmission) | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 2202286.53 | 160980.0333 | 201035.14 | 15575.52 | 147447.87 | 21069.57 | 2748394.6633 | 2550769.54 | 197625.1233 | 2202286.53 | 197625.13 | 201035.14 | 0 | 0 | 0 | 2600946.8 | 2403321.67 | 197625.13 | No amendment need has been identified | Submitted | 2026-03-01 | 0 | Information represents the latest LPCE information provided.
178 | Active | Consolidated List | 678800 | FAASt [Telecom Infrastructure – Group B] (Telecommunication) | Telecommunication | IT/OT | Yes | Obligated | 13148929.44 | 55895.837 | 2828793.1 | 10487.44 | 0 | 0 | 16044105.817 | 15977722.54 | 66383.277 | 13148929.44 | 45408.4 | 2828793.1 | 10487.44 | 0 | 0 | 16033618.38 | 15977722.54 | 55895.84 | No amendment need has been identified | Submitted | 2025-11-05 | 0 | Design Package is expected by June 2026; but no change in cost expected.
179 | Active | Consolidated List | 956593 | FAASt [Factor Sect 8014 Transformer Replacement] (Substation) | Substation | Substation | Yes | Obligated | 4404224.9449 | 1427070.1716 | 402805.69 | 137265.82 | 0 | 0 | 6371366.6265 | 4807030.6349 | 1564335.9916 | 3751193.63 | 0 | 414861.11 | 0 | 0 | 0 | 4166054.74 | 4166054.74 | 0 | No amendment need has been identified | Submitted | 2025-09-22 | 0 | No expected changes to this project.
180 | Active | Consolidated List | 714654 | FAASt [Advanced Metering Infrastructure (AMI)] (Telecommunications) | Telecommunication | AMI Implementation Program | Yes | Obligated | 332062581 | 517366615 | 1484008 | 26840980 | 0 | 0 | 877754184 | 333546589 | 544207595 | 332062581 | 544207595 | 3905283 | 0 | 0 | 0 | 880175459 | 335967864 | 544207595 | No amendment need has been identified | Submitted | 2024-04-30 | 2 | No changes needed.
181 | Active | Consolidated List | 714641 | FAASt [Rincón Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 10842339.26 | 82026.55 | 1946225.97 | 106422.03 | 750618 | 506022 | 14233653.81 | 13539183.23 | 694470.58 | 11967013.68 | 694470.58 | 0 | 106422.03 | 0 | 506022 | 13273928.29 | 11967013.68 | 1306914.61 | Amendment Needed | Submitted | 2026-08-03 | 2 | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at: 0.00%/0 locations completed.
182 | Active | Consolidated List | 956332 | FAASt [San Juan Region 1 - Feeder 2401-01] (Vegetation) | Vegetation | Vegetation-DT | Yes | Obligated | 2787055.9 | 8286164.87 | 231521.7 | 635275.99 | 0 | 0 | 11940018.46 | 3018577.6 | 8921440.86 | 2664861.34 | 7906327.92 | 221374.27 | 0 | 0 | 0 | 10792563.53 | 2886235.61 | 7906327.92 | Amendment Needed | Submitted | 2026-07-08 | 0 | Cost aligned to LUMA LPCE values. Amendment will be needed after project obligation.
183 | Active | Consolidated List | 728832 | FAASt [Region 5 -Mayaguez Group A] High Density (Vegetation) | Vegetation | Vegetation-DT | Yes | Obligated | 3767690.42 | 8682952.46 | 62820.38 | 1810049.02 | 0 | 0 | 14323512.28 | 3830510.8 | 10493001.48 | 3767690.42 | 10493002 | 62820.38 | 0 | 0 | 0 | 14323512.8 | 3830510.8 | 10493002 | No amendment need has been identified | Submitted | 2025-04-28 | 0 | Cost aligned to the FEMA Obligation values.
184 | Active | Consolidated List | 728827 | FAASt [Region 2 -Arecibo Group A] High Density (Vegetation) | Vegetation | Vegetation-DT | Yes | Obligated | 4807675.47 | 13169769.88 | 79166.85 | 216863.46 | 0 | 0 | 18273475.66 | 4886842.32 | 13386633.34 | 4807675.47 | 13386634 | 79166.85 | 0 | 0 | 0 | 18273476.32 | 4886842.32 | 13386634 | No amendment need has been identified | Submitted | 2025-04-28 | 0 | Cost aligned to the FEMA Obligation values.
185 | Active | Consolidated List | 727531 | FAASt [Region 6 -Ponce Group A] High Density (Vegetation) | Vegetation | Vegetation-DT | Yes | Obligated | 6849050.26 | 15776180 | 110659.38 | 3288703.85 | 0 | 0 | 26024593.49 | 6959709.64 | 19064883.85 | 6849050.26 | 19064884 | 110659.38 | 0 | 0 | 0 | 26024593.64 | 6959709.64 | 19064884 | No amendment need has been identified | Submitted | 2025-04-28 | 0 | Cost aligned to the FEMA Obligation values.
186 | Active | Consolidated List | 727692 | FAASt [Region 4 -Caguas Group A] High Density (Vegetation) | Vegetation | Vegetation-DT | Yes | Obligated | 7414164.75 | 20309782.6 | 119789.88 | 328143.02 | 0 | 0 | 28171880.25 | 7533954.63 | 20637925.62 | 7414164.75 | 20637925 | 119789.88 | 0 | 0 | 0 | 28171879.63 | 7533954.63 | 20637925 | No amendment need has been identified | Submitted | 2025-04-28 | 0 | Cost aligned to the FEMA Obligation values.
187 | Active | Consolidated List | 551925 | FAASt [SCADA Remote Access and RTU Replacements Group 1] (Telecommunication) | Telecommunication | IT/OT | Yes | Obligated | 7507076.66 | 1853362.06 | 1043403.42 | 266016.14 | 0 | 0 | 10669858.28 | 8550480.08 | 2119378.2 | 5962412.52 | 1407196.27 | 1248409.19 | 294727.35 | 0 | 0 | 8912745.33 | 7210821.71 | 1701923.62 | Amendment – Submitted to FEMA | Submitted | 2024-11-01 | 0 | Split revised 428/406 , 1 additional site was included + Rooftop repairs costs submitted in the amendment to address actual cost. E&M changed to 0.
188 | Active | Consolidated List | 168226 | FAASt San Juan 115kV Underground Transmission | Transmission | Transmission Line Rebuild | Yes | Obligated | 14746039.57 | 0 | 2258339.67 | 0 | 0 | 0 | 17004379.24 | 17004379.24 | 0 | 14746039.57 | 0 | 2258339.67 | 0 | 0 | 0 | 17004379.24 | 17004379.24 | 0 | No amendment need has been identified | Submitted | 2022-12-20 | 1 | Data included was not modified, it represents the obligated amounts. The scope is being revised and may impact the estimate.
189 | Active | Consolidated List | 956343 | FAASt [Ponce Region 6 Line 4800 – Toro Negro to Aibonito, Santa Isabel] (Vegetation) | Vegetation | Vegetation-TL | Yes | Obligated | 3162797.958 | 8682357.558 | 262734.708 | 720921.912 | 0 | 0 | 12828812.136 | 3425532.666 | 9403279.47 | 183092.65 | 2178489.85 | 15209.8 | 0 | 0 | 0 | 2376792.3 | 198302.45 | 2178489.85 | Amendment Needed | Submitted | 2026-06-29 | 0 | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. . Amendment will be needed after work completion and /or assessment completion.
190 | Active | Consolidated List | 956337 | FAASt [Mayaguez Region 5 Feeder 6012-02] (Vegetation) | Vegetation | Vegetation-DT | Yes | Obligated | 1800712.05 | 5353676.79 | 149585.76 | 410450.73 | 0 | 0 | 7714425.33 | 1950297.81 | 5764127.52 | 1378198.73 | 4088952.37 | 114489.16 | 0 | 0 | 0 | 5581640.26 | 1492687.89 | 4088952.37 | Amendment Needed | Submitted | 2026-06-12 | 0 | Cost aligned to LUMA LPCE values. Amendment will be needed after project obligation.
191 | Active | Consolidated List | 956339 | FAASt [Caguas Region 4 - Feeder 3301-01] (Vegetation) | Vegetation | Vegetation-DT | Yes | Obligated | 2959532.24 | 8798952.37 | 245849.34 | 674589.93 | 0 | 0 | 12678923.88 | 3205381.58 | 9473542.3 | 2887255.43 | 8566144.83 | 239848.9 | 0 | 0 | 0 | 11693249.16 | 3127104.33 | 8566144.83 | Amendment Needed | Submitted | 2026-06-12 | 0 | Cost aligned to LUMA LPCE values. Amendment will be needed after project obligation.
192 | Active | Consolidated List | 956330 | FAASt [Caguas Region 4 - Feeder 3007-03] (Vegetation) | Vegetation | Vegetation-DT | Yes | Obligated | 1968823.15 | 5853486.17 | 163550.83 | 448769.62 | 0 | 0 | 8434629.77 | 2132373.98 | 6302255.79 | 1914845.33 | 5681119.27 | 159069.25 | 0 | 0 | 0 | 7755033.85 | 2073914.58 | 5681119.27 | Amendment Needed | Submitted | 2026-06-12 | 0 | Cost aligned to LUMA LPCE values. Amendment will be needed after project obligation.
193 | Active | Consolidated List | 956341 | FAASt [Ponce Region 6 Feeder 5803-02] (Vegetation) | Vegetation | Vegetation-DT | Yes | Obligated | 41293.37 | 52055.36 | 3165.6 | 4323.45 | 0 | 0 | 100837.78 | 44458.97 | 56378.81 | 23528.65 | 69806.72 | 1954.56 | 0 | 0 | 0 | 95289.93 | 25483.21 | 69806.72 | Amendment Needed | Submitted | 2026-05-13 | 0 | Cost aligned to LUMA LPCE values. Amendment will be needed after project obligation.
194 | Active | Consolidated List | 723883 | FAASt [Region 1 -San Juan Group A] (Vegetation) | Vegetation | Vegetation-DT | Yes | Obligated | 66761022.13 | 18368702.69 | 879324.5 | 2687.33 | 0 | 0 | 86011736.65 | 67640346.63 | 18371390.02 | 6573069.54 | 18371390.02 | 82513.12 | 0 | 0 | 0 | 25026972.68 | 6655582.66 | 18371390.02 | Amendment Needed | Submitted | 2026-03-01 | 2 | Cost revised to aligned with the FEMA Obligation value from Version2 (Amendment 2 - its last amendment).
195 | Active | Consolidated List | 741105 | FAASt [All Regions TL - 230kV] (Vegetation) | Vegetation | Vegetation-TL | Yes | Obligated | 18022659.27 | 75789392.67 | 204576.49 | 702611.58 | 0 | 0 | 94719240.01 | 18227235.76 | 76492004.25 | 2430054.31 | 10455751.16 | 22529.43 | 0 | 0 | 0 | 12908334.9 | 2452583.74 | 10455751.16 | Amendment Needed | Submitted | 2026-03-01 | 0 | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. Amendment will be needed after work completion and /or assessment completion.
196 | Active | Consolidated List | 727572 | FAASt [Region 3 -Bayamon Group A] High Density (Vegetation) | Vegetation | Vegetation-DT | Yes | Obligated | 11268772.7 | 30826184.94 | 179741.68 | 491691 | 0 | 0 | 42766390.32 | 11448514.38 | 31317875.94 | 11268772.7 | 31317875.94 | 179741.68 | 0 | 0 | 0 | 42766390.32 | 11448514.38 | 31317875.94 | No amendment need has been identified | Submitted | 2026-03-01 | 0 | Cost aligned to the FEMA Obligation values.
197 | Active | Consolidated List | 750068 | FAASt [Region 5 -Mayaguez Group A] Low Density (Vegetation) | Vegetation | Vegetation-DT | Yes | Obligated | 13840548.75 | 37861383.08 | 219334.17 | 599997.54 | 0 | 0 | 52521263.54 | 14059882.92 | 38461380.62 | 13840548.75 | 38461380.62 | 219334.17 | 0 | 0 | 0 | 52521263.54 | 14059882.92 | 38461380.62 | No amendment need has been identified | Submitted | 2026-03-01 | 0 | Cost aligned to the FEMA Obligation values.
198 | Active | Consolidated List | 750067 | FAASt [Region 2 -Arecibo Group A] Low Density (Vegetation) | Vegetation | Vegetation-DT | Yes | Obligated | 15030146.18 | 41115575.14 | 238185.98 | 651567.42 | 0 | 0 | 57035474.72 | 15268332.16 | 41767142.56 | 15030146.18 | 41767142.56 | 238185.98 | 0 | 0 | 0 | 57035474.72 | 15268332.16 | 41767142.56 | No amendment need has been identified | Submitted | 2026-03-01 | 0 | Cost aligned to the FEMA Obligation values.
199 | Active | Consolidated List | 750065 | FAASt [Region 3 -Bayamon Group A] Low Density (Vegetation) | Vegetation | Vegetation-DT | Yes | Obligated | 18569923.87 | 50798780.76 | 294281.61 | 805019.28 | 0 | 0 | 70468005.52 | 18864205.48 | 51603800.04 | 18569923.87 | 51603800.04 | 294281.61 | 0 | 0 | 0 | 70468005.52 | 18864205.48 | 51603800.04 | No amendment need has been identified | Submitted | 2026-03-01 | 0 | Cost aligned to the FEMA Obligation values.
200 | Active | Consolidated List | 750066 | FAASt [Region 4 -Caguas Group A] Low Density (Vegetation) | Vegetation | Vegetation-DT | Yes | Obligated | 28466485.03 | 77871225.66 | 448177.27 | 1226007.11 | 0 | 0 | 108011895.07 | 28914662.3 | 79097232.77 | 28466485.03 | 79097232.76 | 448177.27 | 0 | 0 | 0 | 108011895.06 | 28914662.3 | 79097232.76 | No amendment need has been identified | Submitted | 2026-03-01 | 0 | Cost aligned to the FEMA Obligation values.
201 | Active | Consolidated List | 749060 | FAASt [Transmission Priority Pole Replacement Program Line 5600 Victoria TC – Añasco TC] (Transmission) | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 1077371.11 | 145054.24 | 154904.41 | 21644.91 | 134447.11 | 24366.65 | 1557788.43 | 1366722.63 | 191065.8 | 1175435.49 | 140677.54 | 120608.99 | 0 | 0 | 0 | 1436722.02 | 1296044.48 | 140677.54 | Amendment Needed | Submitted | 2026-03-01 | 0
202 | Active | Consolidated List | 727657 | FAASt [Region 5 Mayaguez TL - 115kV] (Vegetation) | Vegetation | Vegetation-TL | Yes | Obligated | 3096774.74 | 10517290.41 | 36660.8 | 97938.99 | 0 | 0 | 13748664.94 | 3133435.54 | 10615229.4 | 577718.5 | 1975474.09 | 5380.25 | 0 | 0 | 0 | 2558572.84 | 583098.75 | 1975474.09 | Amendment Needed | Submitted | 2026-03-01 | 0 | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800.
203 | Active | Consolidated List | 551926 | FAASt [SCADA Remote Access and RTU Replacements Group 2] (Telecommunication) | Telecommunication | IT/OT | Yes | Obligated | 5664186.55 | 939009.1711 | 800287.41 | 134453.44 | 0 | 0 | 7537936.5711 | 6464473.96 | 1073462.6111 | 5267467.99 | 939009.17 | 800287.41 | 134453.44 | 396718.56 | 0 | 7537936.57 | 6464473.96 | 1073462.61 | No amendment need has been identified | Submitted | 2026-03-01 | 0 | Amendment to be submitted to include the 428/406 split and actual cost.
204 | Active | Consolidated List | 746309 | FAASt [Automation Program Group 30] (Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 327791.49 | 132752.89 | 53695.19 | 28394.95 | 65212.75 | 98251.25 | 706098.52 | 446699.43 | 259399.09 | 327791.49 | 236273.14 | 53695.19 | 0 | 0 | 0 | 617759.82 | 381486.68 | 236273.14 | No amendment need has been identified | Submitted | 2026-03-01 | 0 | No amendment needed. In addition to the amendment version, a revised differential estimate of $23,125.95 for the communications wireless portion was added to the 406 section (without A&E and E&M). Estimate is an Class 3.
205 | Active | Consolidated List | 750151 | FAASt [Transmission Priority Pole Replacement Program Line 700 Costa Sur SP – Yauco 2 HP] (Transmission) | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 243268.16 | 9181.75 | 23495.1804 | 1041.06 | 16785.94 | 2341.06 | 296113.1504 | 283549.2804 | 12563.87 | 243268.16 | 12563.57 | 23495.18 | 0 | 0 | 0 | 279326.91 | 266763.34 | 12563.57 | Amendment Needed | Submitted | 2026-01-16 | 0 | Information represents the latest LPCE information provided.
206 | Active | Consolidated List | 750168 | FAASt [ Transmission Priority Pole Replacement Program Line 4800 Santa Isabel TC – Aibonito TO] (Transmission) | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 431757.15 | 28284.79 | 45787.13 | 3335.39 | 36682.34 | 5852.66 | 551699.46 | 514226.62 | 37472.84 | 431757.15 | 37472.84 | 45787.13 | 0 | 0 | 0 | 515017.12 | 477544.28 | 37472.84 | Amendment Needed | Submitted | 2025-11-25 | 0 | Information represents the latest LPCE information provided.
207 | Active | Consolidated List | 750150 | FAASt [Transmission Priority Pole Replacement Program Line 4800 Santa Isabel TC – Toro Negro 1 HP] (Transmission) | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 138347.1 | 5675.78 | 19852.4 | 1075.69 | 5971.66 | 1473.34 | 172395.97 | 164171.16 | 8224.81 | 125923.56 | 8224.8 | 19852.4 | 0 | 0 | 0 | 154000.76 | 145775.96 | 8224.8 | Amendment Needed | Submitted | 2025-11-05 | 0 | This information reflects the latest LPCE data provided and includes the actuals delta. The final cost will be taken into consideration during the project reconciliation and close-out.
208 | Active | Consolidated List | 749072 | FAASt [Transmission Priority Pole Replacement Program Line 2700 Aguadilla Hospital Distrito Sect – Mora TC] (Transmission) | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 1002273.48 | 44679.36 | 181551.75 | 2952.97 | 85082.65 | 14236.35 | 1330776.56 | 1268907.88 | 61868.68 | 767377.79 | 59629.81 | 73616.34 | 0 | 0 | 0 | 900623.94 | 840994.13 | 59629.81 | Amendment Needed | Submitted | 2025-11-05 | 0 | Information represents the latest LPCE information provided.
209 | Active | Consolidated List | 334470 | FAASt [TL 3100 Monacillos TC to Sabana Llana TC] (Transmission) | Priority Transmission | Transmission Line Rebuild | Yes | Obligated | 27732104.95 | 8785252.58 | 4550630.02 | 2355507.88 | 5594861.69 | 10425727.74 | 59444084.86 | 37877596.66 | 21566488.2 | 47112099.92 | 0 | 2747003.78 | 0 | 0 | 0 | 49859103.7 | 49859103.7 | 0 | Amendment Needed | Submitted | 2025-11-05 | 0 | The information reflects the latest LPCE data provided. The cost currently includes the full line rebuild A&E design cost, under 428. This will be corrected through the obligation amendment.
210 | Active | Consolidated List | 753782 | FAASt [Transmission Priority Pole Replacement Program Line 3100 Monacillos TC – Sabana Llana TC] (Transmission) | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 221703.17 | 2218.84 | 20500.96 | 291.07 | 5970.66 | 1473.34 | 252158.04 | 248174.79 | 3983.25 | 129361.92 | 2218.84 | 20500.96 | 0 | 0 | 0 | 152081.72 | 149862.88 | 2218.84 | Amendment Needed | Submitted | 2025-10-30 | 0 | This information reflects the latest LPCE data provided and includes the actuals delta. The final cost will be taken into consideration during the project reconciliation and close-out.
211 | Active | Consolidated List | 673292 | FAASt Telecom Infrastructure - Cerro Puntas (Telecommunication) | Telecommunication | IT/OT | Yes | Obligated | 8138862.31 | 34775.61 | 1076416.85 | 3866.5 | 0 | 0 | 9253921.27 | 9215279.16 | 38642.11 | 28826526.19 | 40086.16 | 1075319.59 | 9064.09 | 4917.07 | 427.57 | 29956340.67 | 29906762.85 | 49577.82 | Amendment Expected | Submitted | 2025-10-30 | 0
212 | Active | Consolidated List | 825843 | FAASt [Guanica TC] (Substation) | Priority Substation | Substation | Yes | Obligated | 2552411.356 | 0 | 909679.243 | 0 | 4620795.872 | 0 | 8082886.471 | 8082886.471 | 0 | 2320373.96 | 0 | 826981.16 | 0 | 0 | 0 | 3147355.12 | 3147355.12 | 0 | Amendment Needed | Submitted | 2025-09-22 | 0 | LUMA is finalizing the scope. The amendment is expected to be submitted by Q2 FY2027. Cost change is driven by more defined scope and inflation.
213 | Active | Consolidated List | 956342 | FAASt [Arecibo Region 2 Line 36400 – Ponce TC to Dos Bocas HP] (Vegetation) | Vegetation | Vegetation-TL | Yes | Obligated | 2786535.15 | 9869424.87 | 83596.05 | 296082.75 | 0 | 0 | 13035638.82 | 2870131.2 | 10165507.62 | 4093248.38 | 0 | 126595.31 | 0 | 0 | 0 | 4219843.69 | 4219843.69 | 0 | Amendment Needed | Submitted | 2025-09-17 | 0 | Cost aligned to 60% of the LPCE values for this project. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; project obligations are much lower than submitted mileage, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the mileage not covered/approved by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. Amendment will be needed after work completion and /or assessment completion.
214 | Active | Consolidated List | 957578 | FAASt [Costa Sur TC Underground Cable Failure Replacement on Transformer Lead Bank #2] (Substation) | Substation | Substation | Yes | Obligated | 1273789.3886 | 432210.5068 | 115338.8324 | 39304.5072 | 0 | 0 | 1860643.235 | 1389128.221 | 471515.014 | 1108989.51 | 0 | 141856.25 | 0 | 0 | 0 | 1250845.76 | 1250845.76 | 0 | Amendment Needed | Submitted | 2025-09-17 | 0 | LUMA is working on the project scope with Genera. The amendment is expected to be submitted Q1 FY2027. Cost change is driven by more defined scope and inflation.
215 | Active | Consolidated List | 682645 | FAASt [Maunabo TC] (Substation) | Substation | Substation Rebuilds | Yes | Obligated | 64448906.8891 | 9817520.6097 | 6553904.1509 | 2233401.949 | 7931690.2403 | 14741998.2911 | 105727422.13 | 78934501.2803 | 26792920.8497 | 8292124.95 | 0 | 1605121.68 | 0 | 0 | 0 | 9897246.63 | 9897246.63 | 0 | Amendment Needed | Submitted | 2025-09-17 | 0 | LUMA isworking on the scope. Amendment to be submitted by Q2 FY2027. Cost change is driven by more defined scope and inflation.
216 | Active | Consolidated List | 682834 | FAASt [EPC - Costa Sur TC - Phase II & III ] (Substation) | Priority Substation | Substation Rebuilds | Yes | Obligated | 53265182.432 | 7858797.408 | 5239198.272 | 1746399.424 | 14525597.69 | 37474402.31 | 120109577.536 | 73029978.394 | 47079599.142 | 36917509.58 | 0 | 1345002.69 | 0 | 0 | 0 | 38262512.27 | 38262512.27 | 0 | Amendment Needed | Submitted | 2025-09-17 | 1 | LUMA finalizing scope. The amendment to be submitted Q2 FY2027. Cost change is driven by more defined scope and inflation.
217 | Active | Consolidated List | 550950 | FAASt - EPC - [Monacillo TC] (Substations) | Priority Substation | Substation | Yes | Obligated | 105263051.6657 | 16405165.3271 | 16410099.5355 | 1849115.9258 | 62121740.86 | 11046468.76 | 213095642.0741 | 183794892.0613 | 29300750.0129 | 58195134.17 | 0 | 2179830 | 0 | 42974192.2 | 0 | 103349156.37 | 103349156.37 | 0 | Amendment Needed | Submitted | 2025-09-17 | 1 | LUMA finalizing changes in scope and estimate and will submit the amendment by Q2FY2027.
218 | Active | Consolidated List | 956353 | FAASt [Arecibo Region 2 Line 36100 – Dos Bocas HP to Barrio Pina] (Vegetation) | Vegetation | Vegetation-TL | Yes | Obligated | 3154458.67 | 11080517.97 | 94633.76 | 332415.54 | 0 | 0 | 14662025.94 | 3249092.43 | 11412933.51 | 3756065.08 | 0 | 116166.96 | 0 | 0 | 0 | 3872232.04 | 3872232.04 | 0 | Amendment Needed | Submitted | 2025-09-17 | 0 | Cost aligned to 80% of the LPCE values for this project. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; project obligations are much lower than submitted mileage, far below forecast needs. LUMA estimates 80% of miles require clearing and seeks gap funding for the mileage not covered/approved by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. Amendment will be needed after work completion and /or assessment completion.
219 | Active | Consolidated List | 178258 | FAASt - [Taft - MC 1105] (Substations) | Substation | Substation | Yes | Obligated | 11140186.6419 | 1696987.8503 | 1132861.9677 | 386050.2181 | 2678011.84 | 3321988.16 | 20356086.6779 | 14951060.4496 | 5405026.2283 | 9362729.93 | 3161848.86 | 1302381.39 | 961993.54 | 0 | 0 | 14788953.72 | 10665111.32 | 4123842.4 | Amendment Needed | Submitted | 2025-02-06 | 0 | LUMA is finalizing the scope. Amendment is expected to be submitted by Q2 FY2027. Cost change is driven by more defined scope and inflation.
220 | Active | Consolidated List | 738971 | FAASt [Pole and Conductor Repair - Caguas Group 2 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 13884126 | 310288 | 1643630 | 66835.67 | 0 | 0 | 15904879.67 | 15527756 | 377123.67 | 13884126 | 377123.67 | 1643630 | 0 | 0 | 0 | 15904879.67 | 15527756 | 377123.67 | Obligated - Final Ammendment Version once closeout stage | Submitted | 2025-02-06 | 0 | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
221 | Active | Consolidated List | 710099 | FAASt [Pole and Conductor Repair - Arecibo Group 1 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 7366388.46 | 153523.07 | 602047.2 | 42926.93 | 0 | 0 | 8164885.66 | 7968435.66 | 196450 | 6704421.69 | 239376.93 | 602047.21 | 0 | 0 | 0 | 7545845.83 | 7306468.9 | 239376.93 | Amendment Needed | Submitted | 2025-01-07 | 0 | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
222 | Active | Consolidated List | 708637 | FAASt T-Pole Program Line 3700] (Transmission) | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 1367810.2561 | 38822.55 | 41458.8653 | 5793.0785 | 35983.6407 | 6521.5294 | 1496389.92 | 1445252.7621 | 51137.1579 | 303960.92 | 73393.66 | 39573.63 | 0 | 0 | 0 | 416928.21 | 343534.55 | 73393.66 | Amendment Needed | Submitted | 2024-12-16 | 1 | This information reflects the latest LPCE data provided and includes the actuals delta. The final cost will be taken into consideration during the project reconciliation and close-out.
223 | Active | Consolidated List | 711856 | FAASt [Pole and Conductor Repair - Bayamon Group 3 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 11304564.29 | 328412 | 891093.89 | 67251.43 | 0 | 0 | 12591321.61 | 12195658.18 | 395663.43 | 10940320.91 | 395663.43 | 891093.88 | 0 | 0 | 0 | 12227078.22 | 11831414.79 | 395663.43 | Amendment Needed | Submitted | 2024-12-16 | 1 | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
224 | Active | Consolidated List | 738120 | FAASt [Pole and Conductor Repair-Carolina Group 2- Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 11242486.77 | 234531 | 1159111 | 175368.81 | 0 | 0 | 12811497.58 | 12401597.77 | 409899.81 | 11041271 | 406899.81 | 1159111 | 0 | 0 | 0 | 12607281.81 | 12200382 | 406899.81 | Amendment Needed | Submitted | 2024-11-25 | 0 | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
225 | Active | Consolidated List | 738670 | FAASt [Pole and Conductor Repair - Ponce Group 1 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 4926640 | 116500.11 | 439974.62 | 31370.9 | 0 | 0 | 5514485.63 | 5366614.62 | 147871.01 | 4926640.11 | 147870.9 | 439974.62 | 0 | 0 | 0 | 5514485.63 | 5366614.73 | 147870.9 | Obligated - Final Ammendment Version once closeout stage | Submitted | 2024-11-25 | 0 | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
226 | Active | Consolidated List | 738672 | FAASt [Pole and Conductor Repair - Mayaguez Group 1 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 10313627 | 243129 | 834793 | 63002.37 | 0 | 0 | 11454551.37 | 11148420 | 306131.37 | 10313627 | 306131.37 | 834793 | 0 | 0 | 0 | 11454551.37 | 11148420 | 306131.37 | Obligated - Final Ammendment Version once closeout stage | Submitted | 2024-11-25 | 0 | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
227 | Active | Consolidated List | 712980 | FAASt [T-Pole Program Line 3000] (Transmission) | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 1609934.104 | 43793.7069 | 46767.5976 | 6534.8717 | 40591.2804 | 7356.5994 | 1754978.16 | 1697292.9821 | 57685.1779 | 559076.77 | 72117.49 | 72787.96 | 0 | 0 | 0 | 703982.22 | 631864.73 | 72117.49 | Amendment Needed | Submitted | 2024-11-01 | 0 | This information reflects the latest LPCE data provided and includes the actuals delta. The final cost will be taken into consideration during the project reconciliation and close-out.
228 | Active | Consolidated List | 712968 | FAASt [Pole and Conductor Repair - Arecibo Group 2 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 6147251.54 | 145147 | 503550 | 35903.97 | 0 | 0 | 6831852.51 | 6650801.54 | 181050.97 | 5629060 | 178712.97 | 503551 | 0 | 0 | 0 | 6311323.97 | 6132611 | 178712.97 | Amendment Needed | Submitted | 2024-11-01 | 0 | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
229 | Active | Consolidated List | 710094 | FAASt [Pole and Conductor Repair - Bayamon Group 1 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 7096249.5 | 165571 | 614123.07 | 29565.32 | 0 | 0 | 7905508.89 | 7710372.57 | 195136.32 | 7096249.5 | 195136.32 | 614123 | 0 | 0 | 0 | 7905508.82 | 7710372.5 | 195136.32 | Obligated - Final Ammendment Version once closeout stage | Submitted | 2024-11-01 | 0 | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
230 | Active | Consolidated List | 743399 | FAASt [High Voltage Equipment Replacement - Group 3] (Substation) | Substation | Substation | Yes | Obligated | 21038292.91 | 0 | 4509930.04 | 0 | 3457839.23 | 0 | 29006062.18 | 29006062.18 | 0 | 17307539.01 | 0 | 2253322.96 | 0 | 0 | 0 | 19560861.97 | 19560861.97 | 0 | Amendment Needed | Submitted | 2024-08-23 | 0 | LUMA is finalizing the scope. The amendment is expected to be submitted Q2 FY2027.
231 | Active | Consolidated List | 704868 | FAASt [Ceiba Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 5152111.14 | 472131.79 | 1481546.84 | 244786.81 | 0 | 0 | 7350576.58 | 6633657.98 | 716918.6 | 5152111.14 | 716918.6 | 1481546.84 | 0 | 0 | 0 | 7350576.58 | 6633657.98 | 716918.6 | Amendment Needed | Submitted | 2024-07-05 | 0 | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 66.77% (1125 locations completed).
232 | Active | Consolidated List | 724601 | FAASt [Salinas Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 12097203.53 | 1141690.52 | 2463885.54 | 469330.38 | 0 | 0 | 16172109.97 | 14561089.07 | 1611020.9 | 12097203.53 | 1611020.9 | 2463885.54 | 0 | 0 | 0 | 16172109.97 | 14561089.07 | 1611020.9 | Amendment Needed | Submitted | 2024-07-05 | 0 | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 79.89% (3225 locations completed).
233 | Active | Consolidated List | 704927 | FAASt [Añasco Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 12087876.17 | 1294052.66 | 2420466.41 | 526309.26 | 0 | 0 | 16328704.5 | 14508342.58 | 1820361.92 | 12087876.17 | 1820361.92 | 2420466.41 | 0 | 0 | 0 | 16328704.5 | 14508342.58 | 1820361.92 | Amendment Needed | Submitted | 2024-07-05 | 1 | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 89.01% (3354 locations completed).
234 | Active | Consolidated List | 729286 | FAASt HV Equipment Replacement Group 2 (Substation) | Substation | Substation | Yes | Obligated | 17860595.12 | 0 | 5206874.3 | 0 | 0 | 0 | 23067469.42 | 23067469.42 | 0 | 15413889.89 | 0 | 2006782.81 | 0 | 0 | 0 | 17420672.7 | 17420672.7 | 0 | Amendment Needed | Submitted | 2024-07-05 | 1 | LUMA finalizing the scope. The amendment is expected to be submitted Q2 FY2027. Cost change is driven by more defined scope and inflation.
235 | Active | Consolidated List | 711670 | FAASt [T-Pole Program Line 100] (Transmission) | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 441327.62 | 18841.36 | 12340.69 | 4531.35 | 0 | 0 | 477041.02 | 453668.31 | 23372.71 | 94787.57 | 23372.71 | 12340.69 | 0 | 0 | 0 | 130500.97 | 107128.26 | 23372.71 | Amendment Needed | Submitted | 2024-06-17 | 1 | This information reflects the latest LPCE data provided and includes the actuals delta. The final cost will be taken into consideration during the project reconciliation and close-out.
236 | Active | Consolidated List | 703535 | FAASt [Toa Baja Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 9529190.37 | 444807.71 | 1814022 | 175326.98 | 0 | 0 | 11963347.06 | 11343212.37 | 620134.69 | 9529190.37 | 620134.69 | 1814022.36 | 0 | 0 | 0 | 11963347.42 | 11343212.73 | 620134.69 | Amendment Needed | Submitted | 2024-06-17 | 1 | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 62.61% (1492 locations completed).
237 | Active | Consolidated List | 724703 | FAASt [Arroyo Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 5314332 | 489465.16 | 1504203.15 | 250928.85 | 0 | 0 | 7558929.16 | 6818535.15 | 740394.01 | 5314332 | 740394.01 | 1504203.15 | 0 | 0 | 0 | 7558929.16 | 6818535.15 | 740394.01 | Amendment Needed | Submitted | 2024-06-17 | 0 | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 76.83% (1502 locations completed).
238 | Active | Consolidated List | 724698 | FAASt [Adjuntas Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 10742462 | 1338877 | 2199843.63 | 552275 | 0 | 0 | 14833457.63 | 12942305.63 | 1891152 | 10742462 | 1891152 | 2199843.63 | 0 | 0 | 0 | 14833457.63 | 12942305.63 | 1891152 | Amendment Needed | Submitted | 2024-06-17 | 0 | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 81.53% (2423 locations completed).
239 | Active | Consolidated List | 742070 | FAASt [Pole and Conductor Repair - San Juan Group 1 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 5461200.05 | 170555 | 491326.68 | 35032.38 | 0 | 0 | 6158114.11 | 5952526.73 | 205587.38 | 5461200.05 | 205587.39 | 491326.68 | 0 | 0 | 0 | 6158114.12 | 5952526.73 | 205587.39 | Obligated - Final Ammendment Version once closeout stage | Submitted | 2024-06-17 | 0 | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
240 | Active | Consolidated List | 742026 | FAASt [Pole and Conductor Repair - San Juan Group 2 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 1740768.37 | 68617 | 83942.74 | 15418.96 | 0 | 0 | 1908747.07 | 1824711.11 | 84035.96 | 1033375.81 | 84035.96 | 83942.74 | 0 | 0 | 0 | 1201354.51 | 1117318.55 | 84035.96 | Amendment Needed | Submitted | 2024-05-30 | 1 | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
241 | Active | Consolidated List | 704921 | FAASt [Barranquitas Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 9430329.22 | 1104151.73 | 2048083.31 | 472894.36 | 0 | 0 | 13055458.62 | 11478412.53 | 1577046.09 | 9430329.22 | 1577046.09 | 2048083.31 | 0 | 0 | 0 | 13055458.62 | 11478412.53 | 1577046.09 | Amendment Needed | Submitted | 2024-05-30 | 0 | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 66.99% (1727 locations completed).
242 | Active | Consolidated List | 724600 | FAASt [Jayuya Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 7277670.2 | 931433.8 | 1704125.72 | 419107.52 | 0 | 0 | 10332337.24 | 8981795.92 | 1350541.32 | 7277670.2 | 1350541.32 | 1704125.72 | 0 | 0 | 0 | 10332337.24 | 8981795.92 | 1350541.32 | Obligated - Final Ammendment Version once closeout stage | Submitted | 2024-05-30 | 0 | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 73.80% (1332 locations completed).
243 | Active | Consolidated List | 701472 | FAASt [Comerio Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 6538769.44 | 585944.46 | 1640383 | 276181.29 | 0 | 0 | 9041278.19 | 8179152.44 | 862125.75 | 6538769.44 | 585944.46 | 1640383 | 276181.29 | 0 | 0 | 9041278.19 | 8179152.44 | 862125.75 | Amendment Needed | Submitted | 2024-05-09 | 1 | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 82.75% (1382 locations completed).
244 | Active | Consolidated List | 704849 | FAASt [Naguabo Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 11620676.42 | 1182070.57 | 2380242.99 | 487666.4 | 0 | 0 | 15670656.38 | 14000919.41 | 1669736.97 | 11620676.42 | 1669736.97 | 2380242.99 | 0 | 0 | 0 | 15670656.38 | 14000919.41 | 1669736.97 | Amendment Needed | Submitted | 2024-05-09 | 1 | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at: 72.69%/2661 locations completed.
245 | Active | Consolidated List | 724825 | FAASt [Cidra Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 12812478.84 | 1311297.11 | 2516455.74 | 526932.49 | 0 | 0 | 17167164.18 | 15328934.58 | 1838229.6 | 12812478.84 | 1838229.6 | 2516455.74 | 0 | 0 | 0 | 17167164.18 | 15328934.58 | 1838229.6 | Amendment Needed | Submitted | 2024-05-09 | 0 | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 69.99% (2551 locations completed).
246 | Active | Consolidated List | 724938 | FAASt [Vega Alta Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 12445015.33 | 1331810.63 | 2459742.66 | 537278.89 | 0 | 0 | 16773847.51 | 14904757.99 | 1869089.52 | 12445015.33 | 1869089.52 | 2459742.66 | 0 | 0 | 0 | 16773847.51 | 14904757.99 | 1869089.52 | Amendment Needed | Submitted | 2024-05-09 | 0 | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 61.03% (2401 locations completed).
247 | Active | Consolidated List | 549725 | FAASt [Substation Minor Repairs - Group E] (Substation) | Substation | Substation | Yes | Obligated | 4316417.259 | 414743.23 | 900049.964 | 223001.042 | 0 | 0 | 5854211.495 | 5216467.223 | 637744.272 | 3924015.69 | 557641.39 | 96032.42 | 22126.13 | 0 | 0 | 4599815.63 | 4020048.11 | 579767.52 | Amendment Needed | Submitted | 2024-05-09 | 0 | LUMA is working on the project scope with Genera, amendment to be submitted Q1 FY2027. Cost change is driven by more defined scope and inflation.
248 | Active | Consolidated List | 698511 | FAASt [Culebra Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 1155804 | 91406 | 476440 | 62197 | 0 | 0 | 1785847 | 1632244 | 153603 | 1155804 | 91406 | 476440 | 62197 | 0 | 0 | 1785847 | 1632244 | 153603 | Amendment Needed | Submitted | 2024-04-11 | 0 | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 78.02% (323 locations completed).
249 | Active | Consolidated List | 704938 | FAASt [Distribution Streetlighting - Las Piedras (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 13807923.4 | 1285354.42 | 2760454.04 | 522246.69 | 0 | 0 | 18375978.55 | 16568377.44 | 1807601.11 | 13807923.4 | 1807601.11 | 2760454.04 | 0 | 0 | 0 | 18375978.55 | 16568377.44 | 1807601.11 | Amendment Needed | Submitted | 2024-04-11 | 0 | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 69.50% (3480 locations completed).
250 | Active | Consolidated List | 704943 | FAASt [Naranjito Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 11644048.42 | 1501948.72 | 2348209.91 | 613589.66 | 0 | 0 | 16107796.71 | 13992258.33 | 2115538.38 | 11644048.42 | 2115538.38 | 2348209.91 | 0 | 0 | 0 | 16107796.71 | 13992258.33 | 2115538.38 | Amendment Needed | Submitted | 2024-04-11 | 0 | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 67.10% (2144 locations completed).
251 | Active | Consolidated List | 549715 | FAASt Substation Minor Repairs - Group D (Substation) | Substation | Substation Rebuilds | Yes | Obligated | 2841446.894 | 201293.004 | 638207.559 | 115642.934 | 0 | 0 | 3796590.391 | 3479654.453 | 316935.938 | 2583133.54 | 250516.37 | 580188.69 | 37607.26 | 0 | 0 | 3451445.86 | 3163322.23 | 288123.63 | Amendment Needed | Submitted | 2024-04-11 | 1 | LUMA is finalizing scope. The amendment is expected to be submitted by Q2 FY2027. Cost change is driven by more defined scope and inflation.
252 | Active | Consolidated List | 709631 | FAASt [Morovis Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 13486398.85 | 1257031.57 | 2499521.06 | 487450.7 | 0 | 0 | 17730402.18 | 15985919.91 | 1744482.27 | 13486398.85 | 1744482.27 | 2499521.06 | 0 | 0 | 0 | 17730402.18 | 15985919.91 | 1744482.27 | Amendment Needed | Submitted | 2024-03-21 | 0 | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 78.98% (2585 locations completed).
253 | Active | Consolidated List | 682121 | FAASt - EPC -Aguirre TC-Phase II (Substation) | Substation | Substation Rebuilds | Yes | Obligated | 83657110.0997 | 3775560.6762 | 8101618.921 | 359601.847 | 36352089.0673 | 1554241.9338 | 133800222.545 | 128110818.088 | 5689404.457 | 82726096.38 | 0 | 7789677 | 0 | 0 | 0 | 90515773.38 | 90515773.38 | 0 | Amendment Needed | Submitted | 2024-03-21 | 1 | LUMA working on the scope. Amendment to be submitted Q2 FY2027.
254 | Active | Consolidated List | 711888 | FAASt [Pole and Conductor Repair - Caguas Group 1 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 5425810.57 | 132877 | 434784.65 | 33026.3 | 0 | 0 | 6026498.52 | 5860595.22 | 165903.3 | 5425810.57 | 165903.3 | 434784.65 | 0 | 0 | 0 | 6026498.52 | 5860595.22 | 165903.3 | Obligated - Final Ammendment Version once closeout stage | Submitted | 2024-03-21 | 1 | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
255 | Active | Consolidated List | 698579 | FAASt [Distribution Streetlighting - Orocovis] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 9591989.9 | 925633.77 | 1873982.08 | 414167.51 | 0 | 0 | 12805773.26 | 11465971.98 | 1339801.28 | 8070964.96 | 925633.77 | 1873982.08 | 414167.51 | 0 | 0 | 11284748.32 | 9944947.04 | 1339801.28 | Obligated - Final Ammendment Version once closeout stage | Submitted | 2024-03-21 | 0 | This project is currently over budget because the work assigned, based on vendor rates, exceeded the Class 3 estimate. Based on a high‑level evaluation, the work that can be executed within the remaining budget is estimated to be approximately $1,521,024.94 to cover both overruns and pending work (Added to 428 Child for FFO review). This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 72.60% (1627 locations completed).
256 | Active | Consolidated List | 679780 | FAASt [Distribution Streetlighting - Bayamon] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 20710527 | 871692 | 3212958 | 304684 | 0 | 0 | 25099861 | 23923485 | 1176376 | 20710527 | 871692 | 3212958 | 304684 | 0 | 0 | 25099861 | 23923485 | 1176376 | Amendment Needed | Submitted | 2024-03-11 | 2 | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 76.90% (5076 locations completed).
257 | Active | Consolidated List | 698439 | FAASt Streetlight - Las Marías (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 7073217 | 888414 | 1653390 | 399291 | 0 | 0 | 10014312 | 8726607 | 1287705 | 7073217 | 888414 | 1653390 | 399291 | 0 | 0 | 10014312 | 8726607 | 1287705 | Amendment Needed | Submitted | 2024-03-07 | 2 | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 51.97% (898 locations completed).
258 | Active | Consolidated List | 698458 | FAASt [Distribution Streetlighting - Guaynabo] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 9762754.59 | 605024.35 | 1979750.26 | 248032.07 | 0 | 0 | 12595561.27 | 11742504.85 | 853056.42 | 9762754.59 | 605024.35 | 1979750.26 | 248032.07 | 0 | 0 | 12595561.27 | 11742504.85 | 853056.42 | Amendment Needed | Submitted | 2024-03-07 | 2 | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 77.27% (2237 locations completed).
259 | Active | Consolidated List | 678789 | FAASt [Distribution Streetlighting - Carolina] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 14865613.02 | 845273.47 | 2559492.85 | 313673.09 | 0 | 0 | 18584052.43 | 17425105.87 | 1158946.56 | 14865613.02 | 845273.47 | 2559492.85 | 313673.09 | 0 | 0 | 18584052.43 | 17425105.87 | 1158946.56 | Amendment Needed | Submitted | 2024-03-07 | 2 | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 69.97% (3032 locations completed).
260 | Active | Consolidated List | 678793 | FAASt [Streetlighting - Mayagüez] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 11019180.1 | 954580.45 | 2291581 | 397623.91 | 0 | 0 | 14662965.46 | 13310761.1 | 1352204.36 | 11019180.1 | 954580.45 | 2291581 | 397623.91 | 0 | 0 | 14662965.46 | 13310761.1 | 1352204.36 | Amendment Needed | Submitted | 2024-03-07 | 2 | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 56.86% (1723 locations completed).
261 | Active | Consolidated List | 671502 | FAASt [Distribution Streetlighting - Yabucoa] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 14918381.07 | 1418283.01 | 2742910.41 | 547325.25 | 0 | 0 | 19626899.74 | 17661291.48 | 1965608.26 | 28826526.19 | 1418283.01 | 2742910.41 | 547325.25 | 0 | 0 | 33535044.86 | 31569436.6 | 1965608.26 | Amendment Needed | Submitted | 2024-03-07 | 2 | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 63.93%/ (3096 locations completed).
262 | Active | Consolidated List | 704679 | FAASt Coamo Streetlight (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 14311922.45 | 1481726 | 2687463.9 | 579175.35 | 0 | 0 | 19060287.7 | 16999386.35 | 2060901.35 | 14311922.45 | 2060901.35 | 2687463.9 | 0 | 0 | 0 | 19060287.7 | 16999386.35 | 2060901.35 | Amendment Needed | Submitted | 2024-03-07 | 2 | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 64.97% (3177 locations completed).
263 | Active | Consolidated List | 698570 | FAASt [Distribution Streetlighting - Corozal] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 13720208.31 | 1608383.29 | 2501126 | 617490.33 | 0 | 0 | 18447207.93 | 16221334.31 | 2225873.62 | 13720208.31 | 1608383.29 | 2501126 | 617490.33 | 0 | 0 | 18447207.93 | 16221334.31 | 2225873.62 | Amendment Needed | Submitted | 2024-03-07 | 2 | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 81.41% (3180 locations completed).
264 | Active | Consolidated List | 169266 | FAASt Centro Medico 1327/1359 (Substattion) Rebuilt | Substation | Substation Rebuilds | Yes | Obligated | 16976611.278 | 6063148.102 | 4484183.594 | 1270820.683 | 11542228.878 | 2457771.126 | 42794763.661 | 33003023.75 | 9791739.911 | 14795324 | 4426031 | 1810918 | 2111006 | 0 | 0 | 23143279 | 16606242 | 6537037 | Amendment Needed | Submitted | 2024-03-07 | 2 | LUMA is finalizing the scope. The amendment is expected to be submitted Q1 FY2027. Cost change is driven by more defined scope and inflation.
265 | Active | Consolidated List | 660422 | FAASt [Physical Security - Group 4] (Substation) | Substation | Substation Security | Yes | Obligated | 3826369.8 | 249315 | 843279.8 | 122789.7 | 0 | 0 | 5041754.3 | 4669649.6 | 372104.7 | 3478518 | 275349 | 460523 | 62931 | 0 | 0 | 4277321 | 3939041 | 338280 | Amendment Needed | Submitted | 2024-03-07 | 2 | LUMA is finalizing the scope. The amendment to be submitted Q2 FY27. Cost change is driven by more defined scope and inflation.
266 | Active | Consolidated List | 684920 | FAASt Substation High Voltage Replacement_Group 1 (Substation) | Substation | Substation Rebuilds | Yes | Obligated | 12563778.153 | 189367.6032 | 5504338.38 | 0 | 0 | 0 | 18257484.1362 | 18068116.533 | 189367.6032 | 6929384 | 0 | 958084 | 0 | 0 | 0 | 7887468 | 7887468 | 0 | Amendment Needed | Submitted | 2024-03-07 | 2 | LUMA finalizing the scope. The amendment is expected to be submitted Q2 FY2027. Cost change is driven by more defined scope and inflation.
267 | Active | Consolidated List | 546370 | FAASt - Substation Minor Repairs Group A (Subs | Substation | Substation Rebuilds | Yes | Obligated | 4931269.761 | 367083.277 | 1095995.021 | 169939.561 | 0 | 0 | 6564287.62 | 6027264.782 | 537022.838 | 4482972.51 | 457446.85 | 996359.11 | 30755.73 | 0 | 0 | 5967534.2 | 5479331.62 | 488202.58 | Amendment Needed | Submitted | 2024-02-12 | 1 | LUMA finalizing scope, amendment to be submitted Q1 FY2026. Cost change is driven by more defined scope and inflation.
268 | Active | Consolidated List | 723078 | FAASt - EPC - [San Juan SP TC] (Substation) | Substation | Substation Rebuilds | Yes | Obligated | 47732082.057 | 7712225.873 | 6479737.176 | 1137410.296 | 54699508.996 | 10188178.968 | 127949143.366 | 108911328.229 | 19037815.137 | 61558468.95 | 0 | 3713096.54 | 0 | 0 | 0 | 65271565.49 | 65271565.49 | 0 | Amendment Needed | Submitted | 2023-12-18 | 0 | LUMA is working on the project scope with Genera. Amendment to be submitted Q2 FY2027. Cost change is driven by more defined scope and inflation.
269 | Active | Consolidated List | 708579 | FAASt [Pole and Conductor Repair - Ponce Group 16, 17, 18 & 19] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 1976883.61 | 307856.04 | 343118.15 | 81581.8 | 0 | 0 | 2709439.6 | 2320001.76 | 389437.84 | 1764568.92 | 389437.84 | 343118.15 | 0 | 0 | 0 | 2497124.91 | 2107687.07 | 389437.84 | Amendment Needed | Submitted | 2023-10-20 | 1 | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
270 | Active | Consolidated List | 710110 | FAASt [Distribution Pole and Conductor Repair - Bayamon Group 2 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 94998.5 | 2000 | 14756.12 | 478.06 | 0 | 0 | 112232.68 | 109754.62 | 2478.06 | 85296.74 | 2478.06 | 14756.12 | 0 | 0 | 0 | 102530.92 | 100052.86 | 2478.06 | Amendment Needed | Submitted | 2023-10-20 | 0 | Project is 100% executed, and QC has been fully completed. This project was obligated under a 428/406 based on a Class 3 estimate. Reconciliation of actual costs is currently in progress in order to initiate close out according to FEMA Guidelines.
271 | Active | Consolidated List | 546371 | FAASt- Substation Minor Repairs Group C (Substation) | Substation | Substation Rebuilds | Yes | Obligated | 2913084.966 | 288261.908 | 711120.476 | 134833.446 | 0 | 0 | 4047300.796 | 3624205.442 | 423095.354 | 2648259 | 349470.84 | 189800.23 | 35161.3 | 0 | 0 | 3222691.37 | 2838059.23 | 384632.14 | Amendment Needed | Submitted | 2023-08-21 | 0 | LUMA is working on the scope. The amendment is expected to be submitted by Q1 FY2027. Cost change is driven by more defined scope and inflation.
272 | Active | Consolidated List | 169495 | FAASt [Substations - Tapia GIS Rebuilt Equipment Repair &amp;amp; Replacement] (Substations) | Substation | Substation Rebuilds | Yes | Obligated | 8253800.1089 | 1962924.3274 | 1167269.299 | 530329.9907 | 3869859.11 | 3130140.89 | 18914323.7259 | 13290928.5179 | 5623395.208 | 8180049 | 4726022.43 | 1397859.52 | 2433860.87 | 0 | 0 | 16737791.82 | 9577908.52 | 7159883.3 | Amendment Needed | Submitted | 2023-08-21 | 0 | LUMA is finalizing scope. The revised scope is expected to be submitted Q1 FY2027.
273 | Active | Consolidated List | 705527 | FAASt [Distribution Pole and Conductor Repair - San Juan 17-18-19-20-21] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 668853.23 | 98919 | 125147 | 26214 | 0 | 0 | 919133.23 | 794000.23 | 125133 | 642721 | 125133 | 125147 | 0 | 0 | 0 | 893001 | 767868 | 125133 | Amendment Needed | Submitted | 2023-07-27 | 0 | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
274 | Active | Consolidated List | 704933 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 13-14-15-16] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 1201420 | 177653 | 231255 | 47078 | 0 | 0 | 1657406 | 1432675 | 224731 | 1201420 | 224731 | 231255 | 0 | 0 | 0 | 1657406 | 1432675 | 224731 | Obligated - Final Ammendment Version once closeout stage | Submitted | 2023-07-27 | 0 | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
275 | Active | Consolidated List | 542758 | FAASt Substation Minor Repairs -Group B (Substation) | Substation | Substation Rebuilds | Yes | Obligated | 8776075.803 | 1217442.578 | 451066.682 | 80034.625 | 0 | 0 | 10524619.688 | 9227142.485 | 1297477.203 | 2973035 | 412428 | 152806 | 27113 | 0 | 0 | 3565382 | 3125841 | 439541 | Amendment Needed | Submitted | 2023-07-06 | 0 | Amendment submitted to COR3/PREPA on March 2, 2026.
276 | Active | Consolidated List | 705584 | FAASt [Distribution Pole and Conductor Repair - Ponce Groups 14 &amp;amp; 15] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 1511604.39 | 299196 | 284698 | 79287 | 0 | 0 | 2174785.39 | 1796302.39 | 378483 | 1464496 | 378483 | 284698 | 0 | 0 | 0 | 2127677 | 1749194 | 378483 | Amendment Needed | Submitted | 2023-06-15 | 0 | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
277 | Active | Consolidated List | 549764 | FAASt Physical Security - Group 2 (Substation) | Substation | Substation Security | Yes | Obligated | 2374913.541 | 165562.287 | 582748.639 | 81586.461 | 0 | 0 | 3204810.928 | 2957662.18 | 247148.748 | 2159012 | 188306.18 | 529771.49 | 36374.5 | 0 | 0 | 2913464.17 | 2688783.49 | 224680.68 | Amendment Needed | Submitted | 2023-06-15 | 1 | LUMA is finalizing the scope. The revised scope is expected to be submitted Q1 FY2027. Cost change is driven by more defined scope and inflation.
278 | Active | Consolidated List | 551861 | FAASt [Physical Security - Group 3] (Substation) | Substation | Substation Security | Yes | Obligated | 4066652.26 | 333495.019 | 929320.381 | 146526.534 | 0 | 0 | 5475994.194 | 4995972.641 | 480021.553 | 3696956 | 419452.7 | 142265.86 | 16930.53 | 0 | 0 | 4275605.09 | 3839221.86 | 436383.23 | Amendment Needed | Submitted | 2023-06-15 | 0 | LUMA is currently discussing the amendment with COR3/PREPA.
279 | Active | Consolidated List | 704755 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 12-13-14] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 725501.08 | 76551.4 | 83450.9 | 18053.92 | 0 | 0 | 903557.3 | 808951.98 | 94605.32 | 438209.69 | 86182 | 83450.9 | 0 | 0 | 0 | 607842.59 | 521660.59 | 86182 | Amendment Needed | Submitted | 2023-05-16 | 0 | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
280 | Active | Consolidated List | 704844 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 16-17-18-19-20] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 320740 | 70006 | 62490 | 18552 | 0 | 0 | 471788 | 383230 | 88558 | 320740 | 88558 | 62490 | 0 | 0 | 0 | 471788 | 383230 | 88558 | Obligated - Final Ammendment Version once closeout stage | Submitted | 2023-05-16 | 0 | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
281 | Active | Consolidated List | 550910 | FAASt Physical Security - Group 1 (Substatio | Substation | Substation Security | Yes | Obligated | 6627797.242 | 509533.277 | 1406160.756 | 223021.579 | 0 | 0 | 8766512.854 | 8033957.998 | 732554.856 | 6025270 | 593303.4 | 165994.82 | 72655.56 | 0 | 0 | 6857223.78 | 6191264.82 | 665958.96 | Amendment Needed | Submitted | 2023-05-03 | 1 | LUMA is currently discussing the amendment with COR3/PREPA.
282 | Active | Consolidated List | 704916 | FAASt [Pole and Conductor Repair - Arecibo Group 13-14-15-16] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 273996 | 23695 | 49755 | 6279 | 0 | 0 | 353725 | 323751 | 29974 | 273996 | 29974 | 49755 | 0 | 0 | 0 | 353725 | 323751 | 29974 | Obligated - Final Ammendment Version once closeout stage | Submitted | 2023-04-05 | 0 | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
283 | Active | Consolidated List | 704750 | FAASt Distribution Pole and Conductor Repair - Bayamon Group 10 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 486385 | 72920 | 92511 | 19324 | 0 | 0 | 671140 | 578896 | 92244 | 486385 | 92244 | 92511 | 0 | 0 | 0 | 671140 | 578896 | 92244 | Obligated - Final Ammendment Version once closeout stage | Submitted | 2023-04-05 | 0 | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
284 | Active | Consolidated List | 704751 | FAASt Distribution Pole and Conductor Repair - Bayamon Group 11 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 338491 | 76424 | 66168 | 20252 | 0 | 0 | 501335 | 404659 | 96676 | 338491 | 96676 | 66168 | 0 | 0 | 0 | 501335 | 404659 | 96676 | Obligated - Final Ammendment Version once closeout stage | Submitted | 2023-04-05 | 0 | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
285 | Active | Consolidated List | 688198 | FAASt [Pole and Conductor Repair - Arecibo Group 10] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 60838.48 | 12667 | 12052.8 | 3356.76 | 0 | 0 | 88915.04 | 72891.28 | 16023.76 | 60838 | 12667 | 12052.8 | 3356.76 | 0 | 0 | 88914.56 | 72890.8 | 16023.76 | Obligated - Final Ammendment Version once closeout stage | Submitted | 2023-03-18 | 0 | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
286 | Active | Consolidated List | 688625 | FAASt [Pole and Conductor Repair - Ponce Group 10] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 710014.69 | 151206 | 139357.85 | 40069.59 | 0 | 0 | 1040648.13 | 849372.54 | 191275.59 | 710015 | 151206 | 139357.85 | 40069.59 | 0 | 0 | 1040648.44 | 849372.85 | 191275.59 | Obligated - Final Ammendment Version once closeout stage | Submitted | 2023-03-18 | 1 | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
287 | Active | Consolidated List | 688630 | FAASt [Pole and Conductor Repair - Mayagüez Group 12] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 59446.36 | 7898 | 8327.05 | 2092.97 | 0 | 0 | 77764.38 | 67773.41 | 9990.97 | 42728 | 7898 | 8327.05 | 2092.97 | 0 | 0 | 61046.02 | 51055.05 | 9990.97 | Amendment Needed | Submitted | 2023-03-07 | 1 | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
288 | Active | Consolidated List | 688629 | FAASt [Pole and Conductor Repair - Mayagüez Group 13] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 106941.99 | 22045 | 20833.9 | 5841.93 | 0 | 0 | 155662.82 | 127775.89 | 27886.93 | 106942 | 22045 | 20833.9 | 5841.93 | 0 | 0 | 155662.83 | 127775.9 | 27886.93 | Obligated - Final Ammendment Version once closeout stage | Submitted | 2023-03-07 | 0 | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
289 | Active | Consolidated List | 701552 | FAASt [Pole and Conductor Repair - Ponce Group 12] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 186321 | 40981 | 36670 | 10860 | 0 | 0 | 274832 | 222991 | 51841 | 186321 | 51841 | 36670 | 0 | 0 | 0 | 274832 | 222991 | 51841 | Obligated - Final Ammendment Version once closeout stage | Submitted | 2023-03-07 | 0 | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
290 | Active | Consolidated List | 701555 | FAASt [Pole and Conductor Repair - Ponce Group 13] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 547010 | 80962 | 104535 | 21455 | 0 | 0 | 753962 | 651545 | 102417 | 547010 | 102417 | 104535 | 0 | 0 | 0 | 753962 | 651545 | 102417 | Obligated - Final Ammendment Version once closeout stage | Submitted | 2023-03-07 | 0 | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
291 | Active | Consolidated List | 688109 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 11] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 448719.06 | 90680 | 87443.55 | 24030.2 | 0 | 0 | 650872.81 | 536162.61 | 114710.2 | 448719 | 90680 | 87443.55 | 24030.2 | 0 | 0 | 650872.75 | 536162.55 | 114710.2 | Obligated - Final Ammendment Version once closeout stage | Submitted | 2023-03-07 | 1 | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
292 | Active | Consolidated List | 701545 | FAASt [Pole and Conductor Repair - Ponce Group 11] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 487190 | 102007 | 95198 | 27032 | 0 | 0 | 711427 | 582388 | 129039 | 487190 | 102007 | 95198 | 27032 | 0 | 0 | 711427 | 582388 | 129039 | Obligated - Final Ammendment Version once closeout stage | Submitted | 2023-03-07 | 0 | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
293 | Active | Consolidated List | 701495 | FAASt [Pole and Conductor Repair - Mayagüez Group 14] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 20549.54 | 4609 | 3959.6 | 1221.39 | 0 | 0 | 30339.53 | 24509.14 | 5830.39 | 19848 | 4609 | 3959.6 | 1221.39 | 0 | 0 | 29637.99 | 23807.6 | 5830.39 | Amendment Needed | Submitted | 2023-03-01 | 0 | Project is 100% executed, and QC has been fully completed. This project was obligated under a 428/406 based on a Class 3 estimate. Reconciliation of actual costs is currently in progress in order to initiate close out according to FEMA Guidelines.
294 | Active | Consolidated List | 701679 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 12] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 168343.89 | 12827 | 12535.35 | 3399.16 | 0 | 0 | 197105.4 | 180879.24 | 16226.16 | 64425 | 16226 | 12535.35 | 0 | 0 | 0 | 93186.35 | 76960.35 | 16226 | Amendment Needed | Submitted | 2023-03-01 | 0 | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
295 | Active | Consolidated List | 689071 | FAASt [Pole and Conductor Repair - Arecibo Group 11] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 106997.11 | 13827 | 11878.8 | 3664.16 | 0 | 0 | 136367.07 | 118875.91 | 17491.16 | 59545 | 13827 | 11878.8 | 3664.16 | 0 | 0 | 88914.96 | 71423.8 | 17491.16 | Amendment Needed | Submitted | 2023-03-01 | 0 | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
296 | Active | Consolidated List | 691246 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 10] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 374263.26 | 26654 | 41363.6 | 7063.31 | 0 | 0 | 449344.17 | 415626.86 | 33717.31 | 211623 | 26654 | 41363.6 | 7063.31 | 0 | 0 | 286703.91 | 252986.6 | 33717.31 | Amendment Needed | Submitted | 2023-02-15 | 1 | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and proceed with the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, and any necessary cost adjustments will be incorporated into the final version.
297 | Active | Consolidated List | 688472 | FAASt [Pole and Conductor Repair - Mayaguez Group 11] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 164908.86 | 11846.54 | 29921.55 | 3139.46 | 0 | 0 | 209816.41 | 194830.41 | 14986 | 164909 | 11846.54 | 29921.55 | 3139.46 | 0 | 0 | 209816.55 | 194830.55 | 14986 | Obligated - Final Ammendment Version once closeout stage | Submitted | 2023-02-15 | 1 | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
298 | Active | Consolidated List | 686480 | FAASt [Pole and Conductor Repair - Ponce Group 7] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 523404 | 85891 | 101359 | 22761 | 0 | 0 | 733415 | 624763 | 108652 | 523404 | 85891 | 101359 | 22761 | 0 | 0 | 733415 | 624763 | 108652 | Obligated - Final Ammendment Version once closeout stage | Submitted | 2023-02-15 | 0 | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
299 | Active | Consolidated List | 682910 | FAASt [Distribution Pole and Conductor Repair - Bayamón Group 7] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 580036.28 | 82945 | 99229 | 12530 | 0 | 0 | 774740.28 | 679265.28 | 95475 | 517156 | 83531.28 | 99229 | 22135.72 | 0 | 0 | 722052 | 616385 | 105667 | Amendment Needed | Submitted | 2023-01-30 | 0 | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
300 | Active | Consolidated List | 681672 | FAASt Transmission Priority Pole Replacements 2300 | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 835010.89 | 2243 | 0 | 699 | 0 | 0 | 837952.89 | 835010.89 | 2942 | 214124 | 1544 | 26175 | 699 | 0 | 0 | 242542 | 240299 | 2243 | Amendment Needed | Submitted | 2023-01-30 | 1 | This information reflects the latest LPCE data provided and includes the actuals delta. The final cost will be taken into consideration during the project reconciliation and close-out.
301 | Active | Consolidated List | 688096 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 15] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 21408.25 | 4609 | 4169.45 | 1221.39 | 0 | 0 | 31408.09 | 25577.7 | 5830.39 | 21408 | 4609 | 4169.45 | 1221.39 | 0 | 0 | 31407.84 | 25577.45 | 5830.39 | Obligated - Final Ammendment Version once closeout stage | Submitted | 2023-01-30 | 0 | Project is 100% executed, and QC has been fully completed. This project was obligated under a 428/406 based on a Class 3 estimate. Reconciliation of actual costs is currently in progress in order to initiate close out according to FEMA Guidelines.
302 | Active | Consolidated List | 682178 | FAASt [Pole and Conductor Repair - Arecibo Group 7] (Distribution ) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 208544.25 | 42487 | 40949.45 | 11259.06 | 0 | 0 | 303239.76 | 249493.7 | 53746.06 | 208544 | 42487 | 40949.45 | 11259.06 | 0 | 0 | 303239.51 | 249493.45 | 53746.06 | Obligated - Final Ammendment Version once closeout stage | Submitted | 2023-01-30 | 1 | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
303 | Active | Consolidated List | 688627 | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 9] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 303774 | 57066 | 58918 | 15122.49 | 0 | 0 | 434880.49 | 362692 | 72188.49 | 303774 | 57066 | 58918 | 15122.49 | 0 | 0 | 434880.49 | 362692 | 72188.49 | Obligated - Final Ammendment Version once closeout stage | Submitted | 2023-01-30 | 1 | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
304 | Active | Consolidated List | 682136 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 9] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 469650.95 | 75853 | 90259.5 | 20101.05 | 0 | 0 | 655864.5 | 559910.45 | 95954.05 | 469651 | 75853 | 90259.5 | 20101.05 | 0 | 0 | 655864.55 | 559910.5 | 95954.05 | Obligated - Final Ammendment Version once closeout stage | Submitted | 2023-01-30 | 0 | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
305 | Active | Consolidated List | 688774 | FAASt Distribution Pole and Conductor Repair - Ponce Group 9 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 443331 | 77853 | 86719 | 20631 | 0 | 0 | 628534 | 530050 | 98484 | 443331 | 77853 | 86719 | 20631 | 0 | 0 | 628534 | 530050 | 98484 | Obligated - Final Ammendment Version once closeout stage | Submitted | 2023-01-30 | 0 | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
306 | Active | Consolidated List | 682031 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 9] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 516951 | 85571 | 94044 | 22676 | 0 | 0 | 719242 | 610995 | 108247 | 516951 | 85571 | 94044 | 22676 | 0 | 0 | 719242 | 610995 | 108247 | Obligated - Final Ammendment Version once closeout stage | Submitted | 2023-01-30 | 0 | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
307 | Active | Consolidated List | 682228 | FAASt [Pole and Conductor Repair - Ponce Group 8] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 775779 | 139828 | 150784 | 37054.42 | 0 | 0 | 1103445.42 | 926563 | 176882.42 | 775779 | 139828 | 150784 | 37054.42 | 0 | 0 | 1103445.42 | 926563 | 176882.42 | Obligated - Final Ammendment Version once closeout stage | Submitted | 2023-01-30 | 0 | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
308 | Active | Consolidated List | 682172 | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 8] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 362192.7 | 43995.35 | 40930 | 6838 | 0 | 0 | 453956.05 | 403122.7 | 50833.35 | 208400 | 45590 | 40930 | 12081.35 | 0 | 0 | 307001.35 | 249330 | 57671.35 | Amendment Needed | Submitted | 2023-01-23 | 0 | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
309 | Active | Consolidated List | 685477 | FAASt [Pole and Conductor Repair - Arecibo Group 6] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 392742.1 | 47748.1 | 67123 | 6914 | 0 | 0 | 514527.2 | 459865.1 | 54662.1 | 355178 | 46090 | 67123 | 12214 | 0 | 0 | 480605 | 422301 | 58304 | Amendment Needed | Submitted | 2023-01-23 | 0 | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
310 | Active | Consolidated List | 682898 | FAASt [Distribution Pole and Conductor Repair - Bayamón Group 6] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 853881.22 | 82921.49 | 120284.25 | 12889.35 | 0 | 0 | 1069976.31 | 974165.47 | 95810.84 | 635327 | 85929 | 120284.25 | 22771.19 | 0 | 0 | 864311.44 | 755611.25 | 108700.19 | Amendment Needed | Submitted | 2023-01-23 | 0 | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
311 | Active | Consolidated List | 682210 | FAASt [Pole and Conductor Repair - Mayagüez Group 9] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 198050.74 | 33041 | 38248.35 | 8755.87 | 0 | 0 | 278095.96 | 236299.09 | 41796.87 | 198051 | 33041 | 38248.35 | 8755.87 | 0 | 0 | 278096.22 | 236299.35 | 41796.87 | Obligated - Final Ammendment Version once closeout stage | Submitted | 2023-01-23 | 0 | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
312 | Active | Consolidated List | 682180 | FAASt [Pole and Conductor Repair - Mayagüez Group 10] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 120882.62 | 8412 | 8414 | 1308 | 0 | 0 | 139016.62 | 129296.62 | 9720 | 43374 | 8718 | 8414 | 2310 | 0 | 0 | 62816 | 51788 | 11028 | Amendment Needed | Submitted | 2023-01-05 | 0 | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
313 | Active | Consolidated List | 682373 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 14] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 65944 | 9218 | 12740 | 2443 | 0 | 0 | 90345 | 78684 | 11661 | 65944 | 9218 | 12740 | 2443 | 0 | 0 | 90345 | 78684 | 11661 | Obligated - Final Ammendment Version once closeout stage | Submitted | 2023-01-05 | 0 | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
314 | Active | Consolidated List | 685370 | FAASt [Pole and Conductor Repair - Mayagüez Group 8] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 68823 | 11847 | 13127 | 3139 | 0 | 0 | 96936 | 81950 | 14986 | 68823 | 11847 | 13127 | 3139 | 0 | 0 | 96936 | 81950 | 14986 | Obligated - Final Ammendment Version once closeout stage | Submitted | 2023-01-05 | 0 | Project is 100% executed, and QC has been fully completed. This project was obligated under a 428/406 based on a Class 3 estimate. Reconciliation of actual costs is currently in progress in order to initiate close out according to FEMA Guidelines.
315 | Active | Consolidated List | 685943 | FAASt Distribution Pole and Conductor Repair Ponce Group 5(Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 254972.22 | 50008 | 49774.2 | 13252 | 0 | 0 | 368006.42 | 304746.42 | 63260 | 254972 | 50008 | 49774.2 | 13252 | 0 | 0 | 368006.2 | 304746.2 | 63260 | Obligated - Final Ammendment Version once closeout stage | Submitted | 2023-01-05 | 0 | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
316 | Active | Consolidated List | 679458 | FAASt [Distribution Pole and Conductor Repair - Ponce Group 4] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 498436 | 75480 | 95421 | 20002 | 0 | 0 | 689339 | 593857 | 95482 | 498436 | 75480 | 95421 | 20002 | 0 | 0 | 689339 | 593857 | 95482 | Obligated - Final Ammendment Version once closeout stage | Submitted | 2023-01-05 | 0 | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
317 | Active | Consolidated List | 682028 | FAASt [Pole and Conductor Repair - San Juan Group 8] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 431381.68 | 83592 | 83822 | 22151.62 | 0 | 0 | 620947.3 | 515203.68 | 105743.62 | 431382 | 83592 | 83822 | 22151.62 | 0 | 0 | 620947.62 | 515204 | 105743.62 | Obligated - Final Ammendment Version once closeout stage | Submitted | 2023-01-05 | 0 | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
318 | Active | Consolidated List | 679134 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 10] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 452956.93 | 87431 | 86724.25 | 23169.22 | 0 | 0 | 650281.4 | 539681.18 | 110600.22 | 452957 | 87431 | 86724.25 | 23169.22 | 0 | 0 | 650281.47 | 539681.25 | 110600.22 | Obligated - Final Ammendment Version once closeout stage | Submitted | 2023-01-05 | 0 | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
319 | Active | Consolidated List | 682882 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 11] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 545661.24 | 89627 | 104353.35 | 23751.16 | 0 | 0 | 763392.75 | 650014.59 | 113378.16 | 545661 | 89627 | 104353.35 | 23751.16 | 0 | 0 | 763392.51 | 650014.35 | 113378.16 | Obligated - Final Ammendment Version once closeout stage | Submitted | 2023-01-05 | 0 | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
320 | Active | Consolidated List | 682135 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 8] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 577000.79 | 92316 | 109858.85 | 24463.74 | 0 | 0 | 803639.38 | 686859.64 | 116779.74 | 577001 | 92316 | 109858.85 | 24463.74 | 0 | 0 | 803639.59 | 686859.85 | 116779.74 | Obligated - Final Ammendment Version once closeout stage | Submitted | 2023-01-05 | 0 | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
321 | Active | Consolidated List | 682324 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 13] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 573047.24 | 107654 | 110616.4 | 28528.31 | 0 | 0 | 819845.95 | 683663.64 | 136182.31 | 573047.24 | 107654 | 110616.4 | 28528.31 | 0 | 0 | 819845.95 | 683663.64 | 136182.31 | Obligated - Final Ammendment Version once closeout stage | Submitted | 2023-01-05 | 0 | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
322 | Active | Consolidated List | 686453 | FAASt [Pole and Conductor Repair - Mayagüez Group 7] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 39233.59 | 3949 | 4059 | 1046 | 0 | 0 | 48287.59 | 43292.59 | 4995 | 20584 | 3949 | 4059 | 1046 | 0 | 0 | 29638 | 24643 | 4995 | Amendment Needed | Submitted | 2022-12-23 | 0 | Project is 100% executed, and QC has been fully completed. This project was obligated under a 428/406 based on a Class 3 estimate. Reconciliation of actual costs is currently in progress in order to initiate close out according to FEMA Guidelines.
323 | Active | Consolidated List | 682870 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 6] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 115082.99 | 13827 | 16716.65 | 3664 | 0 | 0 | 149290.64 | 131799.64 | 17491 | 85922 | 13827 | 16716.65 | 3664 | 0 | 0 | 120129.65 | 102638.65 | 17491 | Amendment Needed | Submitted | 2022-12-23 | 1 | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
324 | Active | Consolidated List | 682865 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 7] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 152533.26 | 16132 | 13377 | 2508 | 0 | 0 | 184550.26 | 165910.26 | 18640 | 70683 | 16718 | 13377 | 4430 | 0 | 0 | 105208 | 84060 | 21148 | Amendment Needed | Submitted | 2022-12-23 | 0 | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
325 | Active | Consolidated List | 678985 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 4] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 735890.97 | 42939 | 66915 | 11378.84 | 0 | 0 | 857123.81 | 802805.97 | 54317.84 | 353628 | 42939 | 66915 | 11378.84 | 0 | 0 | 474860.84 | 420543 | 54317.84 | Amendment Needed | Submitted | 2022-12-23 | 0 | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
326 | Active | Consolidated List | 679025 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 4] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 402804.8 | 42382 | 46884 | 6588 | 0 | 0 | 498658.8 | 449688.8 | 48970 | 243073 | 43919 | 46884 | 11639 | 0 | 0 | 345515 | 289957 | 55558 | Amendment Needed | Submitted | 2022-12-23 | 0 | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
327 | Active | Consolidated List | 686471 | FAASt [Pole and Conductor Repair - Arecibo Group 5] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 319916.81 | 57115.8 | 49227 | 14392 | 0 | 0 | 440651.61 | 369143.81 | 71507.8 | 250906 | 54308 | 49227 | 14392 | 0 | 0 | 368833 | 300133 | 68700 | Amendment Needed | Submitted | 2022-12-23 | 1 | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
328 | Active | Consolidated List | 679026 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 5] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 784267.71 | 81250 | 93451 | 12630 | 0 | 0 | 971598.71 | 877718.71 | 93880 | 483786 | 84198 | 93451 | 22312 | 0 | 0 | 683747 | 577237 | 106510 | Amendment Needed | Submitted | 2022-12-23 | 0 | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
329 | Active | Consolidated List | 673775 | FAASt [Distribution Pole and Conductor Repair - Mayaguez Group 3] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 5304271.78 | 777623 | 689888.45 | 79570.1 | 0 | 0 | 6851353.33 | 5994160.23 | 857193.1 | 3575454.81 | 777623 | 689888.45 | 79570.1 | 0 | 0 | 5122536.36 | 4265343.26 | 857193.1 | Amendment Needed | Submitted | 2022-12-23 | 0 | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
330 | Active | Consolidated List | 178503 | FAASt Aguirre TC - BKRS (Substations) | Substation | Substation Rebuilds | Yes | Obligated | 38456815.04 | 776010.76 | 4013944.7 | 73159.13 | 0 | 0 | 43319929.63 | 42470759.74 | 849169.89 | 39034592 | 0 | 5171019 | 0 | 0 | 0 | 44205611 | 44205611 | 0 | Amendment Needed | Submitted | 2022-12-23 | 1 | LUMA is finalizing the changes in scope and estimate. The amendment is expected to be submitted by Q2 FY2027.
331 | Active | Consolidated List | 679149 | FAASt Distribution Pole and Conductor Repair - Mayagüez Group 5 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 129744 | 21694 | 25191 | 5749 | 0 | 0 | 182378 | 154935 | 27443 | 129744 | 21694 | 25191 | 5749 | 0 | 0 | 182378 | 154935 | 27443 | Obligated - Final Ammendment Version once closeout stage | Submitted | 2022-12-23 | 0 | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
332 | Active | Consolidated List | 679127 | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 3] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 171152.23 | 36372 | 33340.3 | 9638.58 | 0 | 0 | 250503.11 | 204492.53 | 46010.58 | 171152.23 | 36372 | 33340.3 | 9638.58 | 0 | 0 | 250503.11 | 204492.53 | 46010.58 | Obligated - Final Ammendment Version once closeout stage | Submitted | 2022-12-23 | 0 | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
333 | Active | Consolidated List | 679153 | FAASt Distribution Pole and Conductor Repair - Mayagüez Group 6 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 163846.51 | 40583 | 31068.05 | 10754.5 | 0 | 0 | 246252.06 | 194914.56 | 51337.5 | 163846.51 | 40583 | 31068.05 | 10754.5 | 0 | 0 | 246252.06 | 194914.56 | 51337.5 | Obligated - Final Ammendment Version once closeout stage | Submitted | 2022-12-23 | 0 | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
334 | Active | Consolidated List | 682890 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 12] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 510067.96 | 80878 | 98275.6 | 21432.67 | 0 | 0 | 710654.23 | 608343.56 | 102310.67 | 510067.96 | 80878 | 98275.6 | 21432.67 | 0 | 0 | 710654.23 | 608343.56 | 102310.67 | Obligated - Final Ammendment Version once closeout stage | Submitted | 2022-12-23 | 0 | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
335 | Active | Consolidated List | 685263 | FAASt Distribution Pole and Conductor Repair - Ponce Group 6 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 537688 | 106478 | 103281 | 28217 | 0 | 0 | 775664 | 640969 | 134695 | 537688 | 106478 | 103281 | 28217 | 0 | 0 | 775664 | 640969 | 134695 | Obligated - Final Ammendment Version once closeout stage | Submitted | 2022-12-23 | 0 | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
336 | Active | Consolidated List | 679457 | FAASt [Distribution Pole and Conductor Repair - Ponce Group 3] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 589335 | 123232 | 115386 | 33921 | 0 | 0 | 861874 | 704721 | 157153 | 589335 | 123232 | 115386 | 33921 | 0 | 0 | 861874 | 704721 | 157153 | Obligated - Final Ammendment Version once closeout stage | Submitted | 2022-12-23 | 0 | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
337 | Active | Consolidated List | 679033 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 9] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 729040 | 142215 | 140628 | 37687 | 0 | 0 | 1049570 | 869668 | 179902 | 729040 | 142215 | 140628 | 37687 | 0 | 0 | 1049570 | 869668 | 179902 | Obligated - Final Ammendment Version once closeout stage | Submitted | 2022-12-23 | 0 | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
338 | Active | Consolidated List | 678988 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 5] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 911136.76 | 163360 | 175440.55 | 43290.4 | 0 | 0 | 1293227.71 | 1086577.31 | 206650.4 | 911136.76 | 163360 | 175440.55 | 43290.4 | 0 | 0 | 1293227.71 | 1086577.31 | 206650.4 | Obligated - Final Ammendment Version once closeout stage | Submitted | 2022-12-23 | 1 | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
339 | Active | Consolidated List | 165268 | FAASt Rio Grande Estate Substation CH-2306 (Su | Substation | Substation Rebuilds | Yes | Obligated | 22290107.58 | 8550353.26 | 1837831.336 | 1216566.725 | 510106.56 | 15489893.44 | 49894858.901 | 24638045.476 | 25256813.425 | 7098243.76 | 2816937.46 | 1391012.61 | 1768433.49 | 0 | 0 | 13074627.32 | 8489256.37 | 4585370.95 | Amendment Needed | Submitted | 2022-12-20 | 0 | LUMA is finalizing changes in the scope and estimate. The amendment is expected to be submitted by Q1 FY2027.
340 | Active | Consolidated List | 673836 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 1] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 4686914.68 | 841203 | 900014.8 | 222918.8 | 0 | 0 | 6651051.28 | 5586929.48 | 1064121.8 | 4686914.68 | 841203 | 900014.8 | 222918.8 | 0 | 0 | 6651051.28 | 5586929.48 | 1064121.8 | Obligated - Final Ammendment Version once closeout stage | Submitted | 2022-12-20 | 1 | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
341 | Active | Consolidated List | 673772 | FAASt [Distribution Pole and Conductor Repair - Mayagüez Group 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 3286536 | 660857 | 636837 | 175127 | 0 | 0 | 4759357 | 3923373 | 835984 | 3286536 | 660857 | 636837 | 175127 | 0 | 0 | 4759357 | 3923373 | 835984 | Obligated - Final Ammendment Version once closeout stage | Submitted | 2022-10-21 | 0 | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
342 | Active | Consolidated List | 673843 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 3] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 2253235.45 | 179969 | 175796 | 47692 | 0 | 0 | 2656692.45 | 2429031.45 | 227661 | 904194 | 179969 | 175796 | 47692 | 0 | 0 | 1307651 | 1079990 | 227661 | Amendment Needed | Submitted | 2022-10-14 | 0 | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
343 | Active | Consolidated List | 674088 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 3] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 1502387.82 | 228975 | 267370 | 60678 | 0 | 0 | 2059410.82 | 1769757.82 | 289653 | 1412368 | 228975 | 267370 | 60678 | 0 | 0 | 1969391 | 1679738 | 289653 | Amendment Needed | Submitted | 2022-10-14 | 0 | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
344 | Active | Consolidated List | 674096 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 6] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 1773428 | 252057 | 332705 | 66795 | 0 | 0 | 2424985 | 2106133 | 318852 | 1773428 | 252057 | 332705 | 66795 | 0 | 0 | 2424985 | 2106133 | 318852 | Obligated - Final Ammendment Version once closeout stage | Submitted | 2022-10-14 | 0 | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
345 | Active | Consolidated List | 673771 | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 1] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 1894033.53 | 373539 | 370850.25 | 98988 | 0 | 0 | 2737410.78 | 2264883.78 | 472527 | 1894033.53 | 373539 | 370850.25 | 98988 | 0 | 0 | 2737410.78 | 2264883.78 | 472527 | Obligated - Final Ammendment Version once closeout stage | Submitted | 2022-10-14 | 0 | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
346 | Active | Consolidated List | 674092 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 5] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 939116.74 | 71480 | 82578 | 18942 | 0 | 0 | 1112116.74 | 1021694.74 | 90422 | 441308 | 71480 | 82578 | 18942 | 0 | 0 | 614308 | 523886 | 90422 | Amendment Needed | Submitted | 2022-09-15 | 0 | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
347 | Active | Consolidated List | 674072 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 1] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 872891 | 188302.7 | 171585 | 49900.3 | 0 | 0 | 1282679 | 1044476 | 238203 | 872891 | 188302.7 | 171585 | 49900.3 | 0 | 0 | 1282679 | 1044476 | 238203 | Obligated - Final Ammendment Version once closeout stage | Submitted | 2022-09-15 | 0 | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
348 | Active | Consolidated List | 673844 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 3] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 1286113.33 | 252343 | 208800.58 | 66870.9 | 0 | 0 | 1814127.81 | 1494913.91 | 319213.9 | 1072851 | 252343 | 208800.58 | 66870.9 | 0 | 0 | 1600865.48 | 1281651.58 | 319213.9 | Amendment Needed | Submitted | 2022-08-23 | 1 | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
349 | Active | Consolidated List | 673847 | FAASt [Distribution Pole and Conductor Repair-Carolina Group 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 924289.93 | 39481 | 37242 | 10462 | 0 | 0 | 1011474.93 | 961531.93 | 49943 | 190570 | 39481 | 37242 | 10462 | 0 | 0 | 277755 | 227812 | 49943 | Amendment Needed | Submitted | 2022-08-05 | 0 | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
350 | Active | Consolidated List | 673818 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 1] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 674464.58 | 151265 | 121044 | 20349 | 0 | 0 | 967122.58 | 795508.58 | 171614 | 621804 | 151265 | 121044 | 20349 | 0 | 0 | 914462 | 742848 | 171614 | Amendment Needed | Submitted | 2022-08-05 | 0 | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
351 | Active | Consolidated List | 674098 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 7] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 84433 | 20556 | 16517 | 2766 | 0 | 0 | 124272 | 100950 | 23322 | 84433 | 20556 | 16517 | 2766 | 0 | 0 | 124272 | 100950 | 23322 | Obligated - Final Ammendment Version once closeout stage | Submitted | 2022-08-05 | 0 | Project is 100% executed, and QC has been fully completed. This project was obligated under a 428/406 based on a Class 3 estimate. Reconciliation of actual costs is currently in progress in order to initiate close out according to FEMA Guidelines.
352 | Active | Consolidated List | 674083 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 1747929 | 286587 | 335722 | 75946 | 0 | 0 | 2446184 | 2083651 | 362533 | 1747929 | 286587 | 335722 | 75946 | 0 | 0 | 2446184 | 2083651 | 362533 | Obligated - Final Ammendment Version once closeout stage | Submitted | 2022-08-05 | 0 | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
353 | Active | Consolidated List | 673774 | FAASt [Distribution Pole and Conductor Repair - Mayaguez Group 1] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 3378138.08 | 283336 | 273831 | 75084 | 0 | 0 | 4010389.08 | 3651969.08 | 358420 | 1408531 | 283336 | 273831 | 75084 | 0 | 0 | 2040782 | 1682362 | 358420 | Amendment Needed | Submitted | 2022-08-01 | 0 | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
354 | Active | Consolidated List | 673795 | FAASt Distribution Pole and Conductor Repair - Mayaguez Group 4 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 1615221.64 | 291663 | 278116 | 77291 | 0 | 0 | 2262291.64 | 1893337.64 | 368954 | 1425163 | 291663 | 278116 | 77291 | 0 | 0 | 2072233 | 1703279 | 368954 | Amendment Needed | Submitted | 2022-08-01 | 0 | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
355 | Active | Consolidated List | 169896 | FAASt - Costa Sur SP TC  Equipment Repair and | Substation | Substation Rebuilds | Yes | Obligated | 31075136.224 | 548761.477 | 3742364.835 | 58919.883 | 0 | 0 | 35425182.419 | 34817501.059 | 607681.36 | 23251835 | 0 | 4734912 | 0 | 0 | 0 | 27986747 | 27986747 | 0 | Amendment Needed | Submitted | 2022-08-01 | 0 | Amendment submitted to COR3/PREPA on March 4, 2026. On April 2026, the estimate was reviewed and a new estimate for $35M will be submitted to COR3/PREPA.
356 | Active | Consolidated List | 673848 | FAASt [Distribution Pole and Conductor Repair-Carolina Group 3] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 139921 | 4443 | 13281 | 1177 | 0 | 0 | 158822 | 153202 | 5620 | 43725 | 4443 | 13281 | 1177 | 0 | 0 | 62626 | 57006 | 5620 | Amendment Needed | Submitted | 2022-07-11 | 0 | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
357 | Active | Consolidated List | 673839 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 69706.66 | 4609 | 10152 | 1221 | 0 | 0 | 85688.66 | 79858.66 | 5830 | 20468 | 4609 | 10152 | 1221 | 0 | 0 | 36450 | 30620 | 5830 | Amendment Needed | Submitted | 2022-07-11 | 0 | The project was obligated under Sections 428/406 using a Class 3 estimate. The scope was adjusted to address unforeseen site conditions, based on a high‑level assessment. The additional budget of $85,688.66 is to cover both overruns and outstanding activities. Project Class 3 estimate will be revised, any adjustments will be incorporated into the final amendment during closeout.
358 | Active | Consolidated List | 673838 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 329669.44 | 57917 | 55025 | 15348 | 0 | 0 | 457959.44 | 384694.44 | 73265 | 284348 | 57917 | 55025 | 15348 | 0 | 0 | 412638 | 339373 | 73265 | Amendment Needed | Submitted | 2022-07-11 | 0 | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
359 | Active | Consolidated List | 334527 | FAASt [Distribution Pole and Conductor Repair – Caguas Group 8 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 108847 | 12431 | 8540 | 2443 | 0 | 0 | 132261 | 117387 | 14874 | 108847 | 12431 | 8540 | 2443 | 0 | 0 | 132261 | 117387 | 14874 | Obligated - Final Ammendment Version once closeout stage | Submitted | 2022-06-09 | 1 | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
360 | Active | Consolidated List | 165225 | FAASt - EPC - Vieques 2501 substation repairs & New Vieques 2502 substation (Substation) | Substation | Vieques and Culebra Projects (6) | Yes | Obligated | 2115845.46 | 61747355.43 | 196682.43 | 74220.68 | 209878.53 | 481486.47 | 64825469 | 2522406.42 | 62303062.58 | 1209111 | 72835 | 531763 | 105474 | 0 | 0 | 1919183 | 1740874 | 178309 | Amendment – Submitted to FEMA | Submitted | 2022-06-09 | 0 | The SOW submitted to COR3/PREPA only includes changes in the scope of the repairs to the existing substation. Currently, this project includes the new substation that will be part of the microgrid (not full Section 406HM). LUMA will request to transfer the scope of the new substation to the microgrid project (full Section 406HM). Cost change is driven by a more defined scope and inflation.
361 | Active | Consolidated List | 542762 | FAASt Distribution Pole and Conductor Repair – Arecibo Group 2 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 610448 | 146428 | 50794 | 10992 | 0 | 0 | 818662 | 661242 | 157420 | 610448 | 146428 | 50794 | 10992 | 0 | 0 | 818662 | 661242 | 157420 | Obligated - Final Ammendment Version once closeout stage | Submitted | 2022-06-02 | 1 | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
362 | Active | Consolidated List | 179558 | FAASt - Manatí TC - BRKS 230 kV - (Substation) | Substation | Substation Rebuilds | Yes | Obligated | 1932688.3493 | 655782.0456 | 175000.6866 | 59635.7325 | 0 | 0 | 2823106.814 | 2107689.036 | 715417.778 | 1593443 | 0 | 688917 | 0 | 0 | 0 | 2282360 | 2282360 | 0 | Amendment Needed | Submitted | 2022-05-25 | 0 | This project is in closeout. Amendment submitted to COR3/PREPA.
363 | Active | Consolidated List | 334488 | FAASt [Distribution Pole and Conductor Repair – Caguas Group 4 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 142917 | 9779 | 11465 | 1047 | 0 | 0 | 165208 | 154382 | 10826 | 142917 | 9779 | 11465 | 1047 | 0 | 0 | 165208 | 154382 | 10826 | Obligated - Final Ammendment Version once closeout stage | Submitted | 2022-05-25 | 1 | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
364 | Active | Consolidated List | 334323 | FAASt Distribution Pole and Conductor Repair - Ponce Group 1 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 323692 | 54648 | 26179 | 14482 | 0 | 0 | 419001 | 349871 | 69130 | 323692 | 54648 | 26179 | 14482 | 0 | 0 | 419001 | 349871 | 69130 | Obligated - Final Ammendment Version once closeout stage | Submitted | 2022-05-25 | 1 | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
365 | Active | Consolidated List | 334329 | FAASt Distribution Pole and Conductor Repair - Ponce Group 2 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 342249.92 | 50699 | 25530 | 13435 | 0 | 0 | 431913.92 | 367779.92 | 64134 | 316119 | 50699 | 25530 | 13435 | 0 | 0 | 405783 | 341649 | 64134 | Amendment Needed | Submitted | 2022-05-19 | 1 | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
366 | Active | Consolidated List | 174422 | FAASt - Catano-Rebuild 1801(Substation) | Substation | Substation | Yes | Obligated | 20620556.5073 | 3141135.3313 | 2096934.7257 | 714581.4152 | 4515587.433 | 8392761.2153 | 39481556.6278 | 27233078.666 | 12248477.9618 | 16359899.17 | 3145301.54 | 1211174.91 | 3749848.23 | 0 | 0 | 24466223.85 | 17571074.08 | 6895149.77 | Amendment Needed | Submitted | 2022-05-17 | 0 | The scope of the amendment has been finalized. LUMA expects to submit the amendment by Q1 FY2027. Cost change is driven by more defined scope and inflation.
367 | Active | Consolidated List | 751656 | FAASt [Culebra Microgrid] (Transmission) | Transmission | Vieques and Culebra Projects (6) | No | Pending Scope & Cost Completion by Applicant | 406083.4394 | 62593651.6797 | 51303.2161 | 9109976.8943 | 0 | 9746878.2781 | 81907893.5075 | 457386.6555 | 81450506.852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project in V0 - No amendment required at this time | TBD |  | 0 | Under review
368 | Active | Consolidated List | 751655 | FAASt [Vieques Microgrid] (Transmission) | Transmission | Vieques and Culebra Projects (6) | No | Pending Scope & Cost Completion by Applicant | 671661.536 | 109183728.0243 | 10795126.3543 | 22484740.5443 | 0 | 25228860.2043 | 168364116.6632 | 11466787.8903 | 156897328.7729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not obligated - Increase in estimate that will be submitted to FEMA. | TBD |  | 0 | Under Review
369 | Active | Attachment A | 1068056 | Aguadilla Sect 7003 Transformer 38/13.2-4.16, 22 MVA | Substation | Substation Component Replacements | No |  | 5579634.34 | 311868.76 | 629419.11 | 31110.94 | 1938416.48 | 60347.84 | 8550797.47 | 8147469.93 | 403327.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project in V0 - No amendment required at this time | 2026-11-01 |  | 0 | The Detailed Scope of Work (DSOW) is currently being formulated. Once the DSOW is submitted to FEMA, the current cost columns will be updated to reflect the costs identified in the DSOW.
370 | Active | Attachment A | 1068051 | Hogar Crea 1717 Transformer 115/13.2 kV, 44.8 MVA | Substation | Substation Component Replacements | No |  | 6398013.45 | 188830.71 | 904549.27 | 23961.87 | 2064663.44 | 34482 | 9614500.74 | 9367226.16 | 247274.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project in V0 - No amendment required at this time | 2026-11-01 |  | 0 | The Detailed Scope of Work (DSOW) is currently being formulated. Once the DSOW is submitted to FEMA, the current cost columns will be updated to reflect the costs identified in the DSOW.
371 | Active | Attachment A | 1068243 | Isla Grande TC Bank 2 Transformer 115/40 kV, 112 MVA | Substation | Substation Component Replacements | No |  | 5001240.02 | 43376.06 | 862846.03 | 5789.88 | 2955632.71 | 9814.28 | 8878698.98 | 8819718.76 | 58980.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project in V0 - No amendment required at this time | 2026-11-01 |  | 0 | The Detailed Scope of Work (DSOW) is currently being formulated. Once the DSOW is submitted to FEMA, the current cost columns will be updated to reflect the costs identified in the DSOW.
372 | Active | Attachment A | 1068057 | Quebradillas 7402 Transformer 38/13.2-4.16, 22 MVA | Substation | Substation Component Replacements | No |  | 4522746.03 | 111790.07 | 559970.38 | 11194.81 | 1878676.91 | 16521.12 | 7100899.32 | 6961393.32 | 139506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project in V0 - No amendment required at this time | 2026-11-01 |  | 0 | The Detailed Scope of Work (DSOW) is currently being formulated. Once the DSOW is submitted to FEMA, the current cost columns will be updated to reflect the costs identified in the DSOW.
373 | Active | Attachment A | 1068052 | Rincon 7301 Transformer 38/13.2-4.16, 22 MVA | Substation | Substation Component Replacements | No |  | 5756093.73 | 330484.121 | 658093.86 | 30072.85 | 2034277.28 | 25621.12 | 8834642.961 | 8448464.87 | 386178.091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project in V0 - No amendment required at this time | 2026-10-01 |  | 0 | The Detailed Scope of Work (DSOW) is currently being formulated. Once the DSOW is submitted to FEMA, the current cost columns will be updated to reflect the costs identified in the DSOW.
374 | Active | Attachment A | 1068054 | Santa Isabel Sect 4401 Transformer 38/13.2-4.16, 22 MVA | Substation | Substation Component Replacements | No |  | 7837106.38 | 431467.46 | 774387.34 | 38617.71 | 2241468.32 | 71267.84 | 11394315.05 | 10852962.04 | 541353.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project in V0 - No amendment required at this time | 2026-10-01 |  | 0 | The Detailed Scope of Work (DSOW) is currently being formulated. Once the DSOW is submitted to FEMA, the current cost columns will be updated to reflect the costs identified in the DSOW.
375 | Active | Attachment A | 1070404 | TAShelix Mobile Platform Implementation | TBD | TBD | No |  | 0 | 1957950 | 0 | 0 | 0 | 0 | 1957950 | 0 | 1957950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project in V0 - No amendment required at this time | 2026-10-01 |  | 0 | The Detailed Scope of Work (DSOW) is currently being formulated. Once the DSOW is submitted to FEMA, the current cost columns will be updated to reflect the costs identified in the DSOW.
376 | Active | Attachment A | 1070775 | Transmission Advanced Sensors and Wide-Area Monitoring, Protection, and Control (WAMPAC) System | Telecommunication | IT/OT | No |  | 0 | 47130973.41 | 0 | 5250645.64 | 0 | 423360 | 52804979.05 | 0 | 52804979.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project in V0 - No amendment required at this time | TBD |  | 0 | The updated Detailed Scope of Work (DSOW) is currently being formulated. Once the DSOW is submitted to FEMA, the current cost columns will be updated to reflect the costs identified in the DSOW.
377 | Active | Consolidated List | 682328 | FAASt [Bayamón TC - Rebuild] (Substation) | Substation | Substation | No | Pending Scope & Cost Completion by Applicant | 87274829.6388 | 13294600.018 | 8875105.814 | 3024407.7676 | 21340863.5442 | 19963184.0398 | 153772990.8224 | 117490798.997 | 36282191.8254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project in V0 - No amendment required at this time | 2026-12-01 |  | 0 | The updated Detailed Scope of Work (DSOW) is currently being formulated. Once the DSOW is submitted to FEMA, the current cost columns will be updated to reflect the costs identified in the DSOW.
378 | Active | Consolidated List | 165213 | FAASt – Line 5400 – Rio Blanco HP to Daguao TC to Punta Lima TO to Vieques 2501 to Culebra 3801 (Transmission) | Transmission | Vieques and Culebra Projects (6) | No | Pending Scope & Cost Completion by Applicant | 90286761.91 | 33780983.5629 | 7450643.73 | 2497575.1807 | 14930827.72 | 1685383.8863 | 150632175.99 | 112668233.36 | 37963942.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project in V0 - No amendment required at this time | 2026-11-30 |  | 0 | The updated Detailed Scope of Work (DSOW) is currently being formulated. Once the DSOW is submitted to FEMA, the current cost columns will be updated to reflect the costs identified in the DSOW.
379 | Active | Consolidated List | 956331 | FAASt [Mayaguez Region 5 Feeder 6014-02] (Vegetation) | Vegetation | Vegetation-DT | Yes | Obligated | 1977622.66 | 5879647.9 | 164281.79 | 450775.37 | 0 | 0 | 8472327.72 | 2141904.45 | 6330423.27 | 1813962.21 | 5381811.02 | 150688.73 | 0 | 0 | 0 | 7346461.96 | 1964650.94 | 5381811.02 | Amendment Needed | Submitted |  |  | Cost aligned to LUMA LPCE values. Amendment will be needed after project obligation.
380 | Active | Consolidated List | 956340 | FAASt [Ponce Region 6 Feeder 5602-02] (Vegetation) | Vegetation | Vegetation-DT | Yes | Obligated | 1624663.76 | 4830269.73 | 134961.38 | 370322.63 | 0 | 0 | 6960217.5 | 1759625.14 | 5200592.36 | 1210919.69 | 3592655.29 | 100593.03 | 0 | 0 | 0 | 4904168.01 | 1311512.72 | 3592655.29 | Amendment Needed | Submitted |  |  | Cost aligned to LUMA LPCE values. Amendment will be needed after project obligation.
381 | Active | Consolidated List | 727522 | FAASt [Region 3 Bayamon TL - 115kV] (Vegetation) | Vegetation | Vegetation-TL | Yes | Obligated | 2653352.966 | 8930252.562 | 79600.589 | 267907.5769 | 0 | 0 | 11931113.6938 | 2732953.555 | 9198160.1389 | 778850.12 | 2663231.73 | 7253.38 | 0 | 0 | 0 | 3449335.23 | 786103.5 | 2663231.73 | Amendment Needed | Submitted |  |  | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. . Amendment will be needed after work completion and /or assessment completion.
382 | Active | Consolidated List | 727606 | FAASt [Region 4 Caguas TL - 115kV] (Vegetation) | Vegetation | Vegetation-TL | Yes | Obligated | 4217039.02 | 14325508.11 | 50985.56 | 133401.828 | 0 | 0 | 18726934.518 | 4268024.58 | 14458909.938 | 900812.92 | 3080276.26 | 8389.21 | 0 | 0 | 0 | 3989478.39 | 909202.13 | 3080276.26 | Amendment Needed | Submitted |  |  | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. . Amendment will be needed after work completion and /or assessment completion.
383 | Active | Consolidated List | 727659 | FAASt [Region 2 Arecibo TL - 115kV] (Vegetation) | Vegetation | Vegetation-TL | Yes | Obligated | 2669312.23 | 8989281.612 | 80079.3669 | 269678.4484 | 0 | 0 | 12008351.6573 | 2749391.5969 | 9258960.0604 | 953592.14 | 3260751.68 | 8880.74 | 0 | 0 | 0 | 4223224.56 | 962472.88 | 3260751.68 | Amendment Needed | Submitted |  |  | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. . Amendment will be needed after work completion and /or assessment completion.
384 | Active | Consolidated List | 727608 | FAASt [Region 1 San Juan TL - 115kV] (Vegetation) | Vegetation | Vegetation-TL | Yes | Obligated | 3698704.16 | 12571501.92 | 46746.2 | 117068.19 | 0 | 0 | 16434020.47 | 3745450.36 | 12688570.11 | 1007797.83 | 3446104.8 | 9385.55 | 0 | 0 | 0 | 4463288.18 | 1017183.38 | 3446104.8 | Amendment Needed | Submitted |  |  | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. . Amendment will be needed after work completion and /or assessment completion.
385 | Active | Consolidated List | 727529 | FAASt [Region 6 Ponce TL - 115kV] (Vegetation) | Vegetation | Vegetation-TL | Yes | Obligated | 7751854.11 | 26340450.42 | 95803.98 | 245287.236 | 0 | 0 | 34433395.746 | 7847658.09 | 26585737.656 | 1879368.2 | 6426387.93 | 17502.43 | 0 | 0 | 0 | 8323258.56 | 1896870.63 | 6426387.93 | Amendment Needed | Submitted |  |  | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. . Amendment will be needed after work completion and /or assessment completion.
[18 empty] | 2907578627.32 | 1341762605.54 | 303484554.23 | 34941160.08 | 64103673.23 | 6861258.37 | 4658731878.77 | 3275166854.78 | 1383565023.99
Consolidated Project Cost List