## LUMA
[10 empty] | Timeline |  |  |  |  | Goal |  |  |  |  | On Track |  |  |  |  | Delayed |  |  |  |  | Pending |  |  |  |  | At Risk
Start Date | 2025-04-01
Displacement Increase: | 0 | [8 empty] | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01
[10 empty] | 2025-04-01 | 2025-04-02 | 2025-04-03 | 2025-04-04 | 2025-04-05 | 2025-04-06 | 2025-04-07 | 2025-04-08 | 2025-04-09 | 2025-04-10 | 2025-04-11 | 2025-04-12 | 2025-04-13 | 2025-04-14 | 2025-04-15 | 2025-04-16 | 2025-04-17 | 2025-04-18 | 2025-04-19 | 2025-04-20 | 2025-04-21 | 2025-04-22 | 2025-04-23 | 2025-04-24 | 2025-04-25 | 2025-04-26 | 2025-04-27 | 2025-04-28 | 2025-04-29 | 2025-04-30 | 2025-05-01 | 2025-05-02 | 2025-05-03
[10 empty] | 2025-08-01 | 2025-08-02 | 2025-08-03 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-09 | 2025-08-10 | 2025-08-11 | 2025-08-12 | 2025-08-13 | 2025-08-14 | 2025-08-15 | 2025-08-16 | 2025-08-17 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-08-23 | 2025-08-24 | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-08-29 | 2025-08-30 | 2025-08-31 | 2025-09-01 | 2025-09-02
[10 empty] | 2026-01-01 | 2026-01-02 | 2026-01-03 | 2026-01-04 | 2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2026-01-09 | 2026-01-10 | 2026-01-11 | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-17 | 2026-01-18 | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-24 | 2026-01-25 | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-31 | 2026-02-01 | 2026-02-02
[10 empty] | 2026-01-01 | 2026-01-02 | 2026-01-03 | 2026-01-04 | 2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2026-01-09 | 2026-01-10 | 2026-01-11 | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-17 | 2026-01-18 | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-24 | 2026-01-25 | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-31 | 2026-02-01 | 2026-02-02
[10 empty] | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-04 | 2026-04-05 | 2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-11 | 2026-04-12 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-18 | 2026-04-19 | 2026-04-20 | 2026-04-21 | 2026-04-22 | 2026-04-23 | 2026-04-24 | 2026-04-25 | 2026-04-26 | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30 | 2026-05-01 | 2026-05-02 | 2026-05-03
[10 empty] | 2026-11-01 | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05 | 2026-11-06 | 2026-11-07 | 2026-11-08 | 2026-11-09 | 2026-11-10 | 2026-11-11 | 2026-11-12 | 2026-11-13 | 2026-11-14 | 2026-11-15 | 2026-11-16 | 2026-11-17 | 2026-11-18 | 2026-11-19 | 2026-11-20 | 2026-11-21 | 2026-11-22 | 2026-11-23 | 2026-11-24 | 2026-11-25 | 2026-11-26 | 2026-11-27 | 2026-11-28 | 2026-11-29 | 2026-11-30 | 2026-12-01 | 2026-12-02 | 2026-12-03
[10 empty] | 2026-01-01 | 2026-01-02 | 2026-01-03 | 2026-01-04 | 2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2026-01-09 | 2026-01-10 | 2026-01-11 | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-17 | 2026-01-18 | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-24 | 2026-01-25 | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-31 | 2026-02-01 | 2026-02-02
[10 empty] | 2026-12-01 | 2026-12-02 | 2026-12-03 | 2026-12-04 | 2026-12-05 | 2026-12-06 | 2026-12-07 | 2026-12-08 | 2026-12-09 | 2026-12-10 | 2026-12-11 | 2026-12-12 | 2026-12-13 | 2026-12-14 | 2026-12-15 | 2026-12-16 | 2026-12-17 | 2026-12-18 | 2026-12-19 | 2026-12-20 | 2026-12-21 | 2026-12-22 | 2026-12-23 | 2026-12-24 | 2026-12-25 | 2026-12-26 | 2026-12-27 | 2026-12-28 | 2026-12-29 | 2026-12-30 | 2026-12-31 | 2027-01-01 | 2027-01-02
Column3 | Column1 | Column2 | Progress of the Electric System Stabilization Plan - Timeline | Column4 | Column42 | Column43 | Column5 | Column6 | Column7 | 2026-12-04: Progress of the Electric System Stabilization Plan - Timeline; 2026-12-15: Progress of the Electric System Stabilization Plan - Timeline
PSP Activities | Category | Progress | Description | Dependencies | Variance | Rationale | Start Date | Months | Completion Date
Vegetation Management Program | " " |  | Addresses systematic clearance of overgrown vegetation along the 115 kV and 230 kV transmission corridors and on distribution "hot-spot" feeders that have been repeatedly linked to service interruptions. |  |  |  | 2025-04-01 | 24 | 2027-04-01
PREB's Completion Timeline | Goal |  |  |  | None | None | 2025-04-01 | 14.2 | 2026-06-01 | 2026-12-01: 2; 2026-12-02: 2; 2026-12-03: 2; 2026-12-04: 2; 2026-12-05: 2; 2026-12-06: 2; 2026-12-07: 2; 2026-12-08: 2; 2026-12-09: 2; 2026-12-10: 2; 2026-12-11: 2; 2026-12-12: 2; 2026-12-13: 2; 2026-12-14: 2
LUMA's Overall Activity Progress | On Track | 72% |  |  | None | None | 2025-04-01 | 17.2667 | 2026-10-01 | 2026-12-19: 72%
Transmission Line Hardening & Maintenance | " " |  | Urgency: High these line segments have historically caused frequent outages; completing their rehab before the next peak hurricane season is vital. Impact: Direct and substantial reduction in customer interruptions and improved power quality. |  |  |  | 2025-04-01 | 25.3333 | 2027-05-01
PREB's Completion Timeline | Goal |  |  |  | None | None | 2025-04-01 | 9.1667 | 2026-01-01 | 2026-12-01: 2; 2026-12-02: 2; 2026-12-03: 2; 2026-12-04: 2; 2026-12-05: 2; 2026-12-06: 2; 2026-12-07: 2; 2026-12-08: 2; 2026-12-09: 2
LUMA's Overall Activity Progress | Partially Completed | 46.54% |  |  | None | None | 2025-04-01 | 17.2667 | 2026-10-01 | 2026-12-19: 46.54%
“ASAP” Utility-Scale Battery Energy Storage System | " " |  | Bulk Electric System Support + Renewable Generation Integration Urgency/Impact: Fast-tracking the finalization of 110 MW BESS under the ASAP framework delivers immediate frequency regulation and peak shaving benefits, and an additional 600 MW of storage capacity facilitates future renewables integration. Rationale: Consistent with LUMA's ASAP program filings to address near-term system constraints. Early BESS deployments reduce forced load shedding and improve operational flexibility. Implementation as per March 5, 2025 R&O in NEPR-Ml-2024-0002. |  |  |  | 2025-04-01 | 24.3333 | 2027-04-01
PREB's Completion Timeline | Goal |  |  |  | None | None | 2025-04-01 | 9.1667 | 2026-01-01 | 2026-12-01: 2; 2026-12-02: 2; 2026-12-03: 2; 2026-12-04: 2; 2026-12-05: 2; 2026-12-06: 2; 2026-12-07: 2; 2026-12-08: 2; 2026-12-09: 2
LUMA's Overall Activity Progress | On Track | 60% |  |  | None | None | 2025-04-01 | 17.2667 | 2026-10-01 | 2026-12-19: 60%
Installation of Four 25 MW Utility-Scale BESS Units | " " |  | Bulk Electric System Support Urgency/Impact: Adding four distributed BESS units (total 100 MW] will enhance system inertia, support voltage regulation, and provide fast frequency response capability. Commission by October 2027 Rationale: Expands the "portfolio" ofutility-scale storage solutions beyond the initial 110 MW ASAP and addresses stability issues. |  |  |  | 2025-04-01 | 24.3333 | 2027-04-01
PREB's Completion Timeline | Goal |  |  |  | None | None | 2025-04-01 | 18.2667 | 2026-10-01 | 2026-12-01: 2; 2026-12-02: 2; 2026-12-03: 2; 2026-12-04: 2; 2026-12-05: 2; 2026-12-06: 2; 2026-12-07: 2; 2026-12-08: 2; 2026-12-09: 2; 2026-12-10: 2; 2026-12-11: 2; 2026-12-12: 2; 2026-12-13: 2; 2026-12-14: 2; 2026-12-15: 2; 2026-12-16: 2; 2026-12-17: 2; 2026-12-18: 2
LUMA's Overall Activity Progress | At Risk | 10% |  |  | None | None | 2025-04-01 | 17.2667 | 2026-10-01 | 2026-12-19: 10%
Grid Protection & Control Upgrade Program | " " |  | Audit and recalibrate protective relays, breakers, and control systems on critical transmission corridors and at generator switchyards. Implement any "low hanging fruit" relay setting changes to ensure faults are isolated properly (e.g., update under frequency load shedding settings and zone coordination). Begin replacing faulty or obsolete relay equipment where immediate spare parts are available. | Dependencies: Coordination with Genera on generator protection and governor controls is required. |  |  | 2025-04-01 | 24.3333 | 2027-04-01
PREB's Completion Timeline | Goal |  |  |  | None | None | 2025-08-01 |  | Not Defined
LUMA's Overall Activity Progress | On Track | 52.78% |  |  | None | None | 2025-04-01 | 17.2667 | 2026-10-01 | 2026-12-19: 52.78%
Dynamic Stability Study and Frequency Control Implementation | " " |  | Complete a dynamic simulation study of the Puerto Rico power system under various contingency scenarios (e.g., generation trip, load spike) to identify weaknesses in frequency and voltage control. By Month 18, produce specific recommendations for additional inertia or fast-frequency response needs. Immediately thereafter, implement operational measures to improve frequency stability: e.g., tune all generator governor settings, enforce droop compliance on all units, and activate secondary frequency regulation (AGC) on units with it. Ensure 100% of online units have functioning primary frequency response by July 2026 | Dependency: Study to be conducted with input data from Genera and modeling support from EPRI or a similar expert (prior studies from April 2022 events can be leveraged). Genera must then implement any unit-specific fixes (e.g., governor repairs, AVR tuning), while LUMA adjusts system control schemes. |  |  | 2025-04-01 | 24.3333 | 2027-04-01
PREB's Completion Timeline | Goal |  |  |  | None | None | 2026-01-01 | 7.0667 | 2026-08-01 | 2026-12-10: 2; 2026-12-11: 2; 2026-12-12: 2; 2026-12-13: 2; 2026-12-14: 2; 2026-12-15: 2; 2026-12-16: 2
LUMA's Overall Activity Progress | On Hold | 84% |  |  | None | None | 2025-04-01 | 17.2667 | 2026-09-01 | 2026-12-19: 84%
Priority Substation Rehabilitation and Rebuild Projects (Phase 1) | " " |  | Urgency: Moderate-High while not as immediate as stopping outages, substation failures can be catastrophic and lengthy to repair, so proactive rebuilding is needed within this two-year window. Impact: Strengthens nodes of the grid, reducing the chance of a major substation outage that could cut off thousands of customers or generation stations. Improves safety and reliability (new equipment less prone to failure). Rationale: LUMA's plan identified 87 substations in FEMA flood zones and numerous aged units requiring rehabilitation. Upgrading a subset of these in the short term is critical for storm resilience. | Dependency: Dependent on availability of equipment (e.g., power transformers, breakers) many are long-lead items. Projects will leverage federal recovery funds where available. LUMA must coordinate outages for construction with Genera to ensure generation re-dispatch during cutovers. This program will continue in phases through the two-year period. |  |  | 2025-04-01 | 24.3333 | 2027-04-01
PREB's Completion Timeline | Goal |  |  |  | None | None | 2025-04-01 | 24.3333 | 2027-04-01 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
LUMA's Overall Activity Progress | Partially Completed | 58.82% |  |  | None | None | 2025-04-01 | 17.2667 | 2026-09-01 | 2026-12-19: 58.82%
Interconnection of Approved Utility-Scale Renewable Solar and Energy Storage Projects | " " |  | Renewable Capacity Addition Urgency/Impact: Adding approximately 860 MW of solar generation and 645 MW of energy storage improves the renewable energy share and reduces dependence on fossil units and bolsters grid stability, providing frequency regulation, load shifting, and potential Blackstar functions. Rationale: Aligned with the IRP's directive to accelerate solar deployment and emphasis on significant BESS depjn1do support the ramp-up in renewables and reduce reliance on peaking generators. |  |  |  | 2025-04-01 | 24.3333 | 2027-04-01
PREB's Completion Timeline | Goal |  |  |  | None | None | 2025-04-01 | 44.6667 | 2028-12-01 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
LUMA's Overall Activity Progress | Delayed | 16.67% |  |  | None | None | 2025-04-01 | 18.2667 | 2026-10-01 | 2026-12-19: 16.67%
Comprehensive Transmission Plan | " " |  | Urgency/Impact: A formal, long-range Transmission Plan is critical to guide expansions, upgrades, and integration of new generation (including IPPs, BESS, and emergency assets). By setting an April 30, 2026 filing deadline, the Bureau ensures strategic alignment for the post-2027 period. Rationale: The Plan must meet technical requirements established by the Energy Bureau, address N-hG contingency reliability, incorporate distributed energy resources, and integrate anticipated renewable/battery capacity additions. Progress captured in NEPR-MI-2019-000 |  |  |  | 2025-04-01 | 24.3333 | 2027-04-01
PREB's Completion Timeline | Goal |  |  |  | None | None | 2026-01-01 | 3 | 2026-04-01 | 2026-12-10: 2; 2026-12-11: 2; 2026-12-12: 2
LUMA's Overall Activity Progress | Completed | 100% |  |  | None | None | 2025-04-01 | 14.2 | 2026-06-01 | 2026-12-15: 100%
Vegetation Clearing Program and Reclamation Efforts | " " |  | Full rollout offederally funded Vegetation Clearing Program and reclamation efforts ($1.2bn) |  |  |  | 2025-04-01 | 24.3333 | 2027-04-01
PREB's Completion Timeline | Goal |  |  |  | None | None | 2026-04-01 | 7.1333 | 2026-11-01 | 2026-12-13: 2; 2026-12-14: 2; 2026-12-15: 2; 2026-12-16: 2; 2026-12-17: 2; 2026-12-18: 2; 2026-12-19: 2
LUMA's Overall Activity Progress | On Track | 91.55% |  |  | None | None | 2025-04-01 | 18.2667 | 2026-10-01 | 2026-12-19: 91.55%
Substation Rehabilitation – Phase 2 | " " |  | By Month 19 and onward (2026), complete the rehabilitation projects initiated in year 1 and commence remaining high priority substation overhauls as presented to PREB in Table 1-7 of the Updated Preliminary Plan. This phase will target the next set of critical substations among the 87 identified (particularly those whose failure would cause regional outages or evacuation of power plants). Aim to finish construction/commissioning of at least 10 major substation projects by end ofYear 2. | Dependency: Many of these are funded under FEMA's rebuild progress will depend on coordination with FEMA and COR3 to release funds and approve designs. LUMA must file quarterly progress updates on substation projects to the Energy Bureau to track adherence to schedule. |  |  | 2025-04-01 | 24.3333 | 2027-04-01
PREB's Completion Timeline | Goal |  |  |  | None | None | 2026-11-01 | 5.0333 | 2027-04-01 | 2026-12-20: 2; 2026-12-21: 2; 2026-12-22: 2; 2026-12-23: 2; 2026-12-24: 2
LUMA's Overall Activity Progress | On Track | 90% |  |  | None | None | 2025-04-01 | 18.2667 | 2026-10-01 | 2026-12-19: 90%
Inverter-Based Resources Integration | " " |  | Integration of IEEE STD 1547, UL 1741 SB compliant Inverter Based Resources (IBR) distribution/transmission plans. Since 1/1/25 the Energy Bureau requires that all inverters interconnecting to the grid comply with IEEE STD 1547 and UL 1741 SB requirements. |  |  |  | 2025-04-01 | 24.3333 | 2027-04-01
PREB's Completion Timeline | Goal |  |  |  | None | None | 2026-01-01 | 15.1667 | 2027-04-01 | 2026-12-21: 2; 2026-12-22: 2; 2026-12-23: 2; 2026-12-24: 2; 2026-12-25: 2; 2026-12-26: 2; 2026-12-27: 2; 2026-12-28: 2; 2026-12-29: 2; 2026-12-30: 2; 2026-12-31: 2; 2027-01-01: 2; 2027-01-02: 2
LUMA's Overall Activity Progress | On Track | 70% |  |  | None | None | 2025-04-01 | 18.2667 | 2026-10-01 | 2026-12-01: 2; 2026-12-19: 70%
Enhanced Frequency Regulation & Reserves | " " |  | By Month 21, implement advanced grid control practices utilizing the new resources: e.g., put all BESS units into coordinated operation for frequency regulation and spinning reserve support under LUMA's dispatch control. Achieve a 90%reduction in load-shedding events, effectively limiting automatic load sheds. Update the Grid Operational Plan to require that a certain level of quick-start or battery reserve is always maintained online. | Relies on completion of battery and generation additions earlier in the plan. By this stage, Genera should also have improved operational reliability of plants such that spinning reserve requirements can be met without frequent emergency unit trips. |  |  | 2025-04-01 | 24.3333 | 2027-04-01
PREB's Completion Timeline | Goal |  |  |  | None | None | 2026-12-01 | 4.0333 | 2027-04-01 | 2026-12-21: 2; 2026-12-22: 2; 2026-12-23: 2; 2026-12-24: 2
LUMA's Overall Activity Progress | Delayed | 0% |  |  | None | None | 2025-04-01 | 20.3 | 2026-10-01 | bar: 2026-12-19
Assessment & Transition to Long-Term Improvements | " " | [5 empty] | 2025-04-01 | 9.1667 | 2027-04-01
PREB's Completion Timeline |  |  | Action to be completed at the End of the PSP period. | Dependency: By this time, PREPA's legacy system transformation (e.g., via IRP implementations, new renewables, new NG units) should be underway, so coordination with those project schedules is needed. The Energy Bureau will use this report to decide on next steps and whether to continue any oversight through an extended or new mechanism. | None | None | 2025-04-01 | 24.3333 | 2027-04-01
Appendix A - LUMA’s Critical-Path Report