## Requirement 11
FY2026 Planned Outages — Requirement 11
Generating unit | Capacity (MW) | Original start date | Original duration (days) | Original scope | Actual / projected start date | Actual / projected duration (days) | Actual / projected scope | Status | Variance — start (days) | Variance — duration (days) | Reason for variance | Availability lost (MW-days)
A. Planned outages during FY2026
San Juan 7 | 100 | 2025-01-01 | 104 | Major overhaul | 2025-04-01 | 452 | Major overhaul, boiler tube replacement, condenser and cooling tower rehabilitation. | Completed | 90 | 348 | Fabricacion de piezas debido a daños ocultos y el tiempo prolongado de entrega de las mismas. | 45200
Palo Seco 3 | 178 | 2026-01-15 | 63 | Environmental Outage and Air Pre-heater basket replacement. | 2026-01-15 | 126 | Environmental Outage, Air Pre-heater basket replacement and Automatic Voltage Regulator control boards update. | Completed | 0 | 63 | Retraso en la fecha de comienzo del lavado de la caldera debido a que las piscinas de cieno no estaban disponibles. Daños imprevistos en el vestibulo de la caldera. | 22428
San Juan 9 | 100 | 2026-06-29 | 185 | Major overhaul | 2026-06-29 | 305 | Major overhaul, boiler tube replacement, condenser and cooling tower rehabilitation. | In progress | 0 | 120 | Fecha de culminacion del projecto abril-27 debido a daños ocultos identificados en la turbina. | 30500
Costa Sur 6 | 350 | 2025-11-11 |  | Baskets & Env. Maint. | 2026-11-16 | Pending | Environmental Outage, Air Pre-heater basket replacement and Automatic Voltage Regulator control boards update, generator hydrogen seals replacement. | Pending | Pending | Pending | N/A | 8760
Aguirre 2 | 350 | 2026-03-01 |  | Environmental Outage | 2027-04-05 | 60 | Enviornmental Outage and generator rotor replacement. | Pending | Pending | Pending | N/A | 5040
Total | [11 empty] | 111928