## Summary
Summary for August 2026 Report:
| Project Status |  |  |  | Miles |  |  |  |  | Cost
Voltage | Total Projects | Projects Submitted to FEMA | Projects Pending Submission to FEMA | Projects Obligated | Total Miles Submitted to FEMA | Miles Pending Submission to FEMA | Total Miles Obligated | Miles Submitted, Denied by FEMA | Percentage of Submitted Miles Obligated (Average) | Total Funds Obligated
Distribution | 25 | 19 | 6 | 18 | 5323.71 | 7325.04 | 5092.22 | 231.49 | 96% | 548013935.5
38kV | 35 | 35 | 0 | 6 | 1346.08 | 0 | 59.09 | 1286.99 | 4% | 541350.51
115kV* | 10 | 10 | 0 | 10 | 567.81 | 0 | 115.35 | 452.46 | 20% | 38160205.54
230kv | 1 | 1 | 0 | 1 | 402.54 | 0 | 38.21 | 364.33 | 9% | 12885805.47
Total | 71 | 65 | 6 | 35 | 7640.14 | 7325.04 | 5304.87 | 2335.27 | 32.25% | 599601297.02
*One 115kV project is pending obligation of Version 1 by FEMA. FEMA obligated Version 0 in September 2025. Additional miles were submitted by LUMA; these additional miles are under review by FEMA
Summary for FY2027 Report
| August Miles |  |  | Total Miles (July + August)
Voltage | Federally Funded Clearing* | OpEx Maintenance | Total Miles | Federally Funded Clearing* | OpEx Maintenance | Total Miles
Distribution | 149.24 | 140.69 | 289.93 | 244.81 | 223.58 | 468.39
38 kV | 6.44 | 28.1 | 34.54 | 11.87 | 66.9 | 78.77
115 kV | 0.29 | 22.44 | 22.73 | 0.38 | 39.14 | 39.52
230 kV | 0 | 10.72 | 10.72 | 0 | 27.29 | 27.29
Total | 155.97 | 201.95 | 357.92 | 257.06 | 356.91 | 613.97
Note: Figures may not add up due to rounding.
*Program restart is May 1, 2025 - the restart was triggered by the obligation of four high density projects on 4/25/25. Prior to this date, 288.14 miles were impacted (cleared and/or assessed as clear spans), for a total of 1,007.54 miles cleared using federal funding as of 5/31/26.
**For federally funded miles, the reported figures include both completed work and, in certain circuits, miles assessed as clear spans. All circuits reported have undergone physical vegetation clearing activities.
***Historical data for OpEx/rate payer-funded will be tracked from May 2026 onward; historical data is not provided.

## Transmission Lines
Primary Transmission Lines
FAASt | Line Voltage (kV) | Transmission Lines ID # | Terminal 1 - Terminal 2 | Date | Circuit Miles Maintained / Cleared | Region | Right of Way (ROWs) Width | ROW Acres Maintained / Cleared | Name of Contractor | Clearing Status | Type of Response | VM Activity Point of Contact (POC) | Funding Source | Month | Quarter | Fiscal Year
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-02 | 0.025925 | Arecibo | 50 | 0.15712 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-02 | 0.026684 | Arecibo | 50 | 0.16172 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-02 | 0.030203 | Arecibo | 50 | 0.18305 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-02 | 0.029494 | Arecibo | 50 | 0.17875 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-02 | 0.036061 | Arecibo | 50 | 0.21855 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-02 | 0.019696 | Arecibo | 50 | 0.11937 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-01 | 0.030448 | Arecibo | 50 | 0.18453 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 8100 | YAUCO 1 HP to YAUCO 1 HP | 2026-07-02 | 0.13707 | Ponce | 50 | 0.83075 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 8100 | YAUCO 1 HP to YAUCO 1 HP | 2026-07-01 | 0.26994 | Ponce | 50 | 1.636 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-01 | 0.030749 | Arecibo | 50 | 0.18636 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-01 | 0.029448 | Arecibo | 50 | 0.17847 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-01 | 0.0321 | Arecibo | 50 | 0.19455 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2900 | TORO NEGRO 1 HP to TORO NEGRO 1 HP | 2026-07-02 | 0.10452 | Ponce | 50 | 0.63346 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-01 | 0.032728 | Arecibo | 50 | 0.19835 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-02 | 0.029903 | Arecibo | 50 | 0.18123 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-02 | 0.034413 | Arecibo | 50 | 0.20857 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-02 | 0.034413 | Arecibo | 50 | 0.20857 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-02 | 0.028583 | Arecibo | 50 | 0.17323 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-02 | 0.02734 | Arecibo | 50 | 0.1657 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-02 | 0.032311 | Arecibo | 50 | 0.19583 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 11100 | CANOVANAS SECT to CANOVANAS SECT | 2026-07-02 | 0.025974 | San Juan | 50 | 0.15742 | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-02 | 0.02276 | Arecibo | 50 | 0.13794 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37400 | Cambalache TC to Cambalache TC | 2026-07-01 | 0.12276 | Arecibo | 100 | 1.4881 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37400 | Cambalache TC to Cambalache TC | 2026-07-02 | 0.12737 | Arecibo | 100 | 1.5439 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6500 | TORO NEGRO 1 HP to TORO NEGRO 1 HP | 2026-07-01 | 0.055218 | Ponce | 50 | 0.33466 | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 8100 | YAUCO 1 HP to YAUCO 1 HP | 2026-07-01 | 0.38774 | Arecibo | 50 | 2.3499 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6500 | TORO NEGRO 1 HP to TORO NEGRO 1 HP | 2026-07-01 | 0.043756 | Ponce | 50 | 0.26519 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37400 | Cambalache TC to Cambalache TC | 2026-07-01 | 0.085962 | Arecibo | 100 | 1.042 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-01 | 0.031036 | Arecibo | 50 | 0.18809 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-01 | 0.02973 | Arecibo | 50 | 0.18018 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 8100 | YAUCO 1 HP to YAUCO 1 HP | 2026-07-01 | 0.12158 | Mayaguez | 50 | 0.73687 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-01 | 0.032578 | Arecibo | 50 | 0.19744 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 13300 | BAYAMON TC to BAYAMON TC | 2026-07-01 | 0.088628 | Bayamon | 50 | 0.53714 | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37400 | Cambalache TC to Cambalache TC | 2026-07-02 | 0.13318 | Arecibo | 100 | 1.6142 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37400 | Cambalache TC to Cambalache TC | 2026-07-02 | 0.12924 | Arecibo | 100 | 1.5665 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 13300 | BAYAMON TC to BAYAMON TC | 2026-07-01 | 0.10544 | Bayamon | 50 | 0.63905 | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37400 | Cambalache TC to Cambalache TC | 2026-07-02 | 0.13108 | Arecibo | 100 | 1.5889 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 8100 | YAUCO 1 HP to YAUCO 1 HP | 2026-07-02 | 0.08336 | Mayaguez | 50 | 0.50521 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-02 | 0.020101 | Arecibo | 50 | 0.12183 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-02 | 0.02015 | Arecibo | 50 | 0.12212 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-02 | 0.030119 | Arecibo | 50 | 0.18254 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-02 | 0.028011 | Arecibo | 50 | 0.16977 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-02 | 0.02909 | Arecibo | 50 | 0.1763 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-02 | 0.026178 | Arecibo | 50 | 0.15865 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-02 | 0.019407 | Arecibo | 50 | 0.11762 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-02 | 0.025374 | Arecibo | 50 | 0.15378 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-02 | 0.031722 | Arecibo | 50 | 0.19225 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-02 | 0.023096 | Arecibo | 50 | 0.13998 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37400 | Cambalache TC to Cambalache TC | 2026-07-02 | 0.075854 | Arecibo | 100 | 0.91944 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 3000 | JUNCOS TC to JUNCOS TC | 2026-07-03 | 0.011764 | Caguas | 50 | 0.071296 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-02 | 0.03604 | Arecibo | 50 | 0.21842 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 3000 | JUNCOS TC to JUNCOS TC | 2026-07-03 | 0.031069 | Caguas | 50 | 0.18829 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-02 | 0.032311 | Arecibo | 50 | 0.19583 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-02 | 0.027962 | Arecibo | 50 | 0.16947 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37400 | Cambalache TC to Cambalache TC | 2026-07-02 | 0.084566 | Arecibo | 100 | 1.025 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37400 | Cambalache TC to Cambalache TC | 2026-07-02 | 0.084538 | Arecibo | 100 | 1.0247 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-02 | 0.034175 | Arecibo | 50 | 0.20712 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-02 | 0.030447 | Arecibo | 50 | 0.18453 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-02 | 0.030447 | Arecibo | 50 | 0.18453 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-02 | 0.024234 | Arecibo | 50 | 0.14687 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37400 | Cambalache TC to Cambalache TC | 2026-07-01 | 0.09851 | Arecibo | 100 | 1.1941 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37400 | Cambalache TC to Cambalache TC | 2026-07-01 | 0.08197 | Arecibo | 100 | 0.99358 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37400 | Cambalache TC to Cambalache TC | 2026-07-01 | 0.10882 | Arecibo | 100 | 1.319 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50200 | Manati TC to Manati TC | 2026-07-02 | 0.22172 | Bayamon | 100 | 2.6875 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50200 | Manati TC to Manati TC | 2026-07-02 | 0.22172 | Bayamon | 100 | 2.6875 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 8100 | YAUCO 1 HP to YAUCO 1 HP | 2026-07-02 | 0.35232 | Mayaguez | 50 | 2.1353 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37400 | Cambalache TC to Cambalache TC | 2026-07-02 | 0.14588 | Arecibo | 100 | 1.7683 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37400 | Cambalache TC to Cambalache TC | 2026-07-02 | 0.080529 | Arecibo | 100 | 0.97611 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37400 | Cambalache TC to Cambalache TC | 2026-07-02 | 0.039223 | Arecibo | 100 | 0.47543 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37200 | Mayaguez TC to Mayaguez TC | 2026-07-02 | 0.1241 | Mayaguez | 100 | 1.5042 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 51200 | Costa Sur Power Plant to Costa Sur Power Plant | 2026-07-02 | 0.18972 | Arecibo | 100 | 2.2997 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 5600 | AÑASCO TC to AÑASCO TC | 2026-07-02 | 0.034175 | Mayaguez | 50 | 0.20712 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 5600 | AÑASCO TC to AÑASCO TC | 2026-07-02 | 0.04823 | Mayaguez | 50 | 0.2923 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 8100 | YAUCO 1 HP to YAUCO 1 HP | 2026-07-01 | 0.060725 | Mayaguez | 50 | 0.36803 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2000 | ONCE DE AGOSTO SECT to ONCE DE AGOSTO SECT | 2026-07-02 | 0.14627 | Mayaguez | 50 | 0.88649 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 18400 | BARRANQUITAS TC to BARRANQUITAS TC | 2026-07-02 | 0.049213 | Caguas | 50 | 0.29826 | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50100 | Cambalache Power Plant to Cambalache Power Plant | 2026-07-05 | 0.16419 | Arecibo | 100 | 1.9902 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37400 | Cambalache TC to Cambalache TC | 2026-07-06 | 0.12502 | Arecibo | 100 | 1.5154 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-07 | 0.026076 | Arecibo | 50 | 0.15803 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-07 | 0.016974 | Arecibo | 50 | 0.10287 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-10 | 0.016345 | Arecibo | 50 | 0.099061 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-10 | 0.022318 | Arecibo | 50 | 0.13526 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-10 | 0.056281 | Arecibo | 50 | 0.3411 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 13500 | ACACIAS TC to ACACIAS TC | 2026-07-07 | 0.071458 | Mayaguez | 50 | 0.43308 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 17900 | JUANA DIAZ TC to JUANA DIAZ TC | 2026-07-08 | 0.031338 | Ponce | 50 | 0.18993 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 17900 | JUANA DIAZ TC to JUANA DIAZ TC | 2026-07-08 | 0.018497 | Ponce | 50 | 0.1121 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-08 | 0.037282 | Arecibo | 50 | 0.22595 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-08 | 0.026719 | Arecibo | 50 | 0.16193 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-09 | 0.021127 | Arecibo | 50 | 0.12804 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-09 | 0.014913 | Arecibo | 50 | 0.090381 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-09 | 0.033554 | Arecibo | 50 | 0.20336 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-07 | 0.025384 | Arecibo | 50 | 0.15384 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-07 | 0.017312 | Arecibo | 50 | 0.10492 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-07 | 0.019666 | Arecibo | 50 | 0.11919 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-07 | 0.020192 | Arecibo | 50 | 0.12238 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-08 | 0.023895 | Arecibo | 50 | 0.14482 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 8100 | YAUCO 1 HP to YAUCO 1 HP | 2026-07-06 | 0.1217 | Ponce | 50 | 0.7376 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-06 | 0.0164 | Arecibo | 50 | 0.099396 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-06 | 0.020459 | Arecibo | 50 | 0.12399 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-07 | 0.022389 | Arecibo | 50 | 0.13569 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-10 | 0.018122 | Arecibo | 50 | 0.10983 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-10 | 0.014698 | Arecibo | 50 | 0.089082 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-10 | 0.026403 | Arecibo | 50 | 0.16002 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-10 | 0.014698 | Arecibo | 50 | 0.089082 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2900 | TORO NEGRO 1 HP to TORO NEGRO 1 HP | 2026-07-08 | 0.14331 | Ponce | 50 | 0.86856 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-08 | 0.033599 | Arecibo | 50 | 0.20363 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2900 | TORO NEGRO 1 HP to TORO NEGRO 1 HP | 2026-07-08 | 0.27081 | Ponce | 50 | 1.6413 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-08 | 0.030879 | Arecibo | 50 | 0.18715 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-08 | 0.032759 | Arecibo | 50 | 0.19854 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-08 | 0.024249 | Arecibo | 50 | 0.14696 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-08 | 0.027545 | Arecibo | 50 | 0.16694 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-08 | 0.032921 | Arecibo | 50 | 0.19952 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-08 | 0.030389 | Arecibo | 50 | 0.18417 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-06 | 0.029005 | Arecibo | 50 | 0.17579 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-07 | 0.023974 | Arecibo | 50 | 0.1453 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-07 | 0.023798 | Arecibo | 50 | 0.14423 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-07 | 0.02378 | Arecibo | 50 | 0.14412 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-07 | 0.023467 | Arecibo | 50 | 0.14223 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-07 | 0.025731 | Arecibo | 50 | 0.15595 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-07 | 0.018741 | Arecibo | 50 | 0.11358 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-07 | 0.025049 | Arecibo | 50 | 0.15181 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-07 | 0.022571 | Arecibo | 50 | 0.13679 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-06 | 0.036241 | Arecibo | 50 | 0.21964 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-08 | 0.035314 | Arecibo | 50 | 0.21402 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-06 | 0.033702 | Arecibo | 50 | 0.20425 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-06 | 0.022123 | Arecibo | 50 | 0.13408 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-08 | 0.027158 | Arecibo | 50 | 0.1646 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-08 | 0.026076 | Arecibo | 50 | 0.15803 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-07 | 0.026263 | Arecibo | 50 | 0.15917 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-07 | 0.025892 | Arecibo | 50 | 0.15692 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-07 | 0.022492 | Arecibo | 50 | 0.13631 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-08 | 0.032443 | Arecibo | 50 | 0.19662 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-08 | 0.027427 | Arecibo | 50 | 0.16623 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-08 | 0.029649 | Arecibo | 50 | 0.17969 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-07 | 0.035749 | Arecibo | 50 | 0.21666 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-06 | 0.030913 | Arecibo | 50 | 0.18735 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 11100 | CANOVANAS SECT to CANOVANAS SECT | 2026-07-07 | 0.023831 | San Juan | 50 | 0.14443 | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 11100 | CANOVANAS SECT to CANOVANAS SECT | 2026-07-09 | 0.011847 | San Juan | 50 | 0.0718 | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-08 | 0.031526 | Arecibo | 50 | 0.19107 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-08 | 0.02557 | Arecibo | 50 | 0.15497 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-08 | 0.02895 | Arecibo | 50 | 0.17546 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-08 | 0.042407 | Arecibo | 50 | 0.25701 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-10 | 0.03368 | Arecibo | 50 | 0.20412 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-09 | 0.033739 | Arecibo | 50 | 0.20448 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-09 | 0.030436 | Arecibo | 50 | 0.18446 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-09 | 0.02796 | Arecibo | 50 | 0.16945 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-11 | 0.037867 | Arecibo | 50 | 0.2295 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-10 | 0.041689 | Arecibo | 50 | 0.25266 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-06 | 0.031069 | Arecibo | 50 | 0.18829 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-08 | 0.025476 | Arecibo | 50 | 0.1544 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 11100 | CANOVANAS SECT to CANOVANAS SECT | 2026-07-09 | 0.023066 | San Juan | 50 | 0.13979 | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 11100 | CANOVANAS SECT to CANOVANAS SECT | 2026-07-09 | 0.048473 | San Juan | 50 | 0.29377 | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 11100 | CANOVANAS SECT to CANOVANAS SECT | 2026-07-06 | 0.026467 | San Juan | 50 | 0.16041 | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 11100 | CANOVANAS SECT to CANOVANAS SECT | 2026-07-09 | 0.01802 | San Juan | 50 | 0.10921 | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 3000 | JUNCOS TC to JUNCOS TC | 2026-07-07 | 0.025476 | Caguas | 50 | 0.1544 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 3000 | JUNCOS TC to JUNCOS TC | 2026-07-07 | 0.02198 | Caguas | 50 | 0.13321 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 3000 | JUNCOS TC to JUNCOS TC | 2026-07-07 | 0.047846 | Caguas | 50 | 0.28997 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 11100 | CANOVANAS SECT to CANOVANAS SECT | 2026-07-09 | 0.024234 | San Juan | 50 | 0.14687 | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 3100 | MONACILLOS TC to MONACILLOS TC | 2026-07-07 | 0.027775 | San Juan | 50 | 0.16834 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 51000 | Aguirre Power Plant to Aguirre Power Plant | 2026-07-06 | 0.18625 | Ponce | 100 | 2.2575 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 5600 | AÑASCO TC to AÑASCO TC | 2026-07-10 | 0.051752 | Mayaguez | 50 | 0.31365 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50400 | Costa Sur Power Plant to Costa Sur Power Plant | 2026-07-06 | 0.057325 | Mayaguez | 100 | 0.69484 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50400 | Costa Sur Power Plant to Costa Sur Power Plant | 2026-07-06 | 0.027577 | Mayaguez | 100 | 0.33426 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50400 | Costa Sur Power Plant to Costa Sur Power Plant | 2026-07-06 | 0.068348 | Mayaguez | 100 | 0.82846 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 3100 | MONACILLOS TC to MONACILLOS TC | 2026-07-07 | 0.076758 | San Juan | 50 | 0.4652 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2300 | ARECIBO SECT to ARECIBO SECT | 2026-07-06 | 0.11318 | Arecibo | 50 | 0.68594 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 1500 | MAYAGUEZ GP to MAYAGUEZ GP | 2026-07-06 | 0.10081 | Mayaguez | 50 | 0.61095 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 1500 | MAYAGUEZ GP to MAYAGUEZ GP | 2026-07-06 | 0.19768 | Mayaguez | 50 | 1.198 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6500 | TORO NEGRO 1 HP to TORO NEGRO 1 HP | 2026-07-06 | 0.52382 | Caguas | 50 | 3.1746 | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6500 | TORO NEGRO 1 HP to TORO NEGRO 1 HP | 2026-07-06 | 0.18632 | Caguas | 50 | 1.1292 | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 18400 | BARRANQUITAS TC to BARRANQUITAS TC | 2026-07-06 | 0.03099 | Caguas | 50 | 0.18782 | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 18400 | BARRANQUITAS TC to BARRANQUITAS TC | 2026-07-06 | 0.04647 | Caguas | 50 | 0.28164 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2300 | ARECIBO SECT to ARECIBO SECT | 2026-07-06 | 0.13534 | Arecibo | 50 | 0.82024 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2300 | ARECIBO SECT to ARECIBO SECT | 2026-07-06 | 0.12178 | Arecibo | 50 | 0.73805 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2300 | ARECIBO SECT to ARECIBO SECT | 2026-07-06 | 0.067682 | San Juan | 50 | 0.41019 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2100 | DOS BOCAS HP to DOS BOCAS HP | 2026-07-06 | 0.068604 | Arecibo | 50 | 0.41578 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37400 | Cambalache TC to Cambalache TC | 2026-07-06 | 0.053323 | Arecibo | 100 | 0.64634 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50700 | AES Power Plant to AES Power Plant | 2026-07-07 | 0.13146 | Ponce | 100 | 1.5935 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 50100 | Cambalache Power Plant to Cambalache Power Plant | 2026-07-06 | 0.12502 | Arecibo | 100 | 1.5154 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 5400 | RIO BLANCO HP to RIO BLANCO HP | 2026-07-10 | 0.0193 | Caguas | 50 | 0.11697 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 5600 | AÑASCO TC to AÑASCO TC | 2026-07-07 | 0.0475 | Mayaguez | 50 | 0.28788 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 5600 | AÑASCO TC to AÑASCO TC | 2026-07-07 | 0.024089 | Mayaguez | 50 | 0.146 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 1500 | MAYAGUEZ GP to MAYAGUEZ GP | 2026-07-07 | 0.28153 | Mayaguez | 50 | 1.7062 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50400 | Costa Sur Power Plant to Costa Sur Power Plant | 2026-07-07 | 0.30336 | Mayaguez | 100 | 3.6771 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6500 | TORO NEGRO 1 HP to TORO NEGRO 1 HP | 2026-07-07 | 0.45361 | Ponce | 50 | 2.7492 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37400 | Cambalache TC to Cambalache TC | 2026-07-07 | 0.11926 | Arecibo | 100 | 1.4456 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37400 | Cambalache TC to Cambalache TC | 2026-07-07 | 0.12473 | Arecibo | 100 | 1.5118 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37400 | Cambalache TC to Cambalache TC | 2026-07-07 | 0.16598 | Arecibo | 100 | 2.0119 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37400 | Cambalache TC to Cambalache TC | 2026-07-07 | 0.096761 | Arecibo | 100 | 1.1729 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37400 | Cambalache TC to Cambalache TC | 2026-07-10 | 0.15311 | Arecibo | 100 | 1.8559 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37400 | Cambalache TC to Cambalache TC | 2026-07-08 | 0.094611 | Arecibo | 100 | 1.1468 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-08 | 0.031155 | Arecibo | 50 | 0.18882 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 5400 | RIO BLANCO HP to RIO BLANCO HP | 2026-07-08 | 0.031746 | Caguas | 50 | 0.1924 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 5400 | RIO BLANCO HP to RIO BLANCO HP | 2026-07-08 | 0.028925 | Caguas | 50 | 0.1753 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-08 | 0.024078 | Arecibo | 50 | 0.14593 | LUMA | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-08 | 0.0099419 | Arecibo | 50 | 0.060254 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-08 | 0.013994 | Arecibo | 50 | 0.084812 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-08 | 0.022369 | Arecibo | 50 | 0.13557 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-08 | 0.018726 | Arecibo | 50 | 0.11349 | LUMA | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-08 | 0.016011 | Arecibo | 50 | 0.097035 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50400 | Costa Sur Power Plant to Costa Sur Power Plant | 2026-07-08 | 0.23217 | Mayaguez | 100 | 2.8142 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37200 | Mayaguez TC to Mayaguez TC | 2026-07-08 | 0.080752 | Mayaguez | 100 | 0.97881 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-08 | 0.021922 | Arecibo | 50 | 0.13286 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-08 | 0.026219 | Arecibo | 50 | 0.1589 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 5400 | RIO BLANCO HP to RIO BLANCO HP | 2026-07-08 | 0.033542 | Caguas | 50 | 0.20329 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-10 | 0.034247 | Arecibo | 50 | 0.20756 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2000 | ONCE DE AGOSTO SECT to ONCE DE AGOSTO SECT | 2026-07-08 | 0.18973 | Mayaguez | 50 | 1.1499 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50900 | Aguirre Power Plant to Aguirre Power Plant | 2026-07-09 | 0.08348 | Bayamon | 100 | 1.0119 | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37400 | Cambalache TC to Cambalache TC | 2026-07-08 | 0.14515 | Arecibo | 100 | 1.7594 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-10 | 0.026669 | Arecibo | 50 | 0.16163 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50300 | Aguirre Power Plant to Aguirre Power Plant | 2026-07-10 | 0.21488 | Ponce | 100 | 2.6047 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-10 | 0.024835 | Arecibo | 50 | 0.15052 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50300 | Aguirre Power Plant to Aguirre Power Plant | 2026-07-09 | 0.20653 | Ponce | 100 | 2.5034 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50400 | Costa Sur Power Plant to Costa Sur Power Plant | 2026-07-08 | 0.21242 | Mayaguez | 100 | 2.5748 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-10 | 0.024835 | Arecibo | 50 | 0.15052 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50400 | Costa Sur Power Plant to Costa Sur Power Plant | 2026-07-08 | 0.28082 | Mayaguez | 100 | 3.4039 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-10 | 0.026996 | Arecibo | 50 | 0.16361 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-08 | 0.015869 | Arecibo | 50 | 0.096177 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-08 | 0.034058 | Arecibo | 50 | 0.20641 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-08 | 0.018138 | Arecibo | 50 | 0.10993 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-10 | 0.015061 | Arecibo | 50 | 0.091281 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-08 | 0.0020909 | Arecibo | 50 | 0.012672 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2300 | ARECIBO SECT to ARECIBO SECT | 2026-07-08 | 0.13866 | Arecibo | 50 | 0.84038 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-08 | 0.0024426 | Arecibo | 50 | 0.014804 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-08 | 0.0421 | Arecibo | 50 | 0.25515 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2300 | ARECIBO SECT to ARECIBO SECT | 2026-07-08 | 0.067682 | Arecibo | 50 | 0.41019 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 11100 | CANOVANAS SECT to CANOVANAS SECT | 2026-07-08 | 0.048473 | San Juan | 50 | 0.29377 | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37400 | Cambalache TC to Cambalache TC | 2026-07-08 | 0.13617 | Arecibo | 100 | 1.6505 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37400 | Cambalache TC to Cambalache TC | 2026-07-08 | 0.095085 | Arecibo | 100 | 1.1525 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37400 | Cambalache TC to Cambalache TC | 2026-07-10 | 0.12149 | Arecibo | 100 | 1.4726 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-09 | 0.026719 | Arecibo | 50 | 0.16193 | LUMA | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 5600 | AÑASCO TC to AÑASCO TC | 2026-07-08 | 0.052437 | Mayaguez | 50 | 0.3178 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 5600 | AÑASCO TC to AÑASCO TC | 2026-07-08 | 0.085349 | Mayaguez | 50 | 0.51727 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 1500 | MAYAGUEZ GP to MAYAGUEZ GP | 2026-07-08 | 0.17529 | Mayaguez | 50 | 1.0623 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 5600 | AÑASCO TC to AÑASCO TC | 2026-07-08 | 0.15332 | Mayaguez | 50 | 0.92921 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 5600 | AÑASCO TC to AÑASCO TC | 2026-07-08 | 0.062283 | Mayaguez | 50 | 0.37747 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-09 | 0.03169 | Arecibo | 50 | 0.19206 | LUMA | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2300 | ARECIBO SECT to ARECIBO SECT | 2026-07-09 | 0.026359 | Arecibo | 50 | 0.15975 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-09 | 0.031262 | Arecibo | 50 | 0.18947 | LUMA | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-09 | 0.033235 | Arecibo | 50 | 0.20142 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-09 | 0.010455 | Arecibo | 50 | 0.063361 | LUMA | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-09 | 0.023561 | Arecibo | 50 | 0.14279 | LUMA | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-09 | 0.019657 | Arecibo | 50 | 0.11913 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-09 | 0.011863 | Arecibo | 50 | 0.071895 | LUMA | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-09 | 0.021198 | Arecibo | 50 | 0.12847 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-09 | 0.021856 | Arecibo | 50 | 0.13246 | LUMA | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-09 | 0.012874 | Arecibo | 50 | 0.078026 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-09 | 0.018401 | Arecibo | 50 | 0.11152 | LUMA | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-09 | 0.017899 | Arecibo | 50 | 0.10848 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-09 | 0.035175 | Arecibo | 50 | 0.21318 | LUMA | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-09 | 0.026719 | Arecibo | 50 | 0.16193 | LUMA | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-09 | 0.032177 | Arecibo | 50 | 0.19501 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-09 | 0.030434 | Arecibo | 50 | 0.18445 | LUMA | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-09 | 0.020603 | Arecibo | 50 | 0.12487 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-09 | 0.032177 | Arecibo | 50 | 0.19501 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37400 | Cambalache TC to Cambalache TC | 2026-07-08 | 0.23019 | Arecibo | 100 | 2.7901 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-09 | 0.02575 | Arecibo | 50 | 0.15606 | LUMA | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-09 | 0.041633 | Arecibo | 50 | 0.25232 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37400 | Cambalache TC to Cambalache TC | 2026-07-09 | 0.17705 | Arecibo | 100 | 2.146 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-09 | 0.023175 | Arecibo | 50 | 0.14045 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-09 | 0.020355 | Arecibo | 50 | 0.12336 | LUMA | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-09 | 0.038198 | Arecibo | 50 | 0.2315 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-09 | 0.036461 | Arecibo | 50 | 0.22097 | LUMA | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 7300 | BALDRICH SECT to BALDRICH SECT | 2026-07-09 | 0.031069 | San Juan | 50 | 0.18829 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50400 | Costa Sur Power Plant to Costa Sur Power Plant | 2026-07-09 | 0.50959 | Mayaguez | 100 | 6.1769 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37400 | Cambalache TC to Cambalache TC | 2026-07-10 | 0.10369 | Arecibo | 100 | 1.2568 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6500 | TORO NEGRO 1 HP to TORO NEGRO 1 HP | 2026-07-10 | 0.13179 | Ponce | 50 | 0.79872 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6500 | TORO NEGRO 1 HP to TORO NEGRO 1 HP | 2026-07-07 | 0.69949 | Caguas | 50 | 4.2394 | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6500 | TORO NEGRO 1 HP to TORO NEGRO 1 HP | 2026-07-07 | 0.33292 | Caguas | 50 | 2.0177 | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6500 | TORO NEGRO 1 HP to TORO NEGRO 1 HP | 2026-07-07 | 0.047338 | Caguas | 50 | 0.2869 | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6500 | TORO NEGRO 1 HP to TORO NEGRO 1 HP | 2026-07-07 | 0.10929 | Ponce | 50 | 0.66239 | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6500 | TORO NEGRO 1 HP to TORO NEGRO 1 HP | 2026-07-07 | 0.10919 | Ponce | 50 | 0.66178 | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6500 | TORO NEGRO 1 HP to TORO NEGRO 1 HP | 2026-07-08 | 0.13179 | Ponce | 50 | 0.79872 | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 18400 | BARRANQUITAS TC to BARRANQUITAS TC | 2026-07-10 | 0.035982 | Caguas | 50 | 0.21808 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 5400 | RIO BLANCO HP to RIO BLANCO HP | 2026-07-10 | 0.02961 | Caguas | 50 | 0.17946 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 51000 | Aguirre Power Plant to Aguirre Power Plant | 2026-07-09 | 0.29683 | Caguas | 100 | 3.5979 | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 51000 | Aguirre Power Plant to Aguirre Power Plant | 2026-07-09 | 0.21393 | Caguas | 100 | 2.593 | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6500 | TORO NEGRO 1 HP to TORO NEGRO 1 HP | 2026-07-10 | 0.052933 | Ponce | 50 | 0.3208 | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 51000 | Aguirre Power Plant to Aguirre Power Plant | 2026-07-10 | 0.15697 | Caguas | 100 | 1.9026 | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 51000 | Aguirre Power Plant to Aguirre Power Plant | 2026-07-10 | 0.27528 | Caguas | 100 | 3.3368 | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6500 | TORO NEGRO 1 HP to TORO NEGRO 1 HP | 2026-07-10 | 0.059901 | Caguas | 50 | 0.36303 | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6500 | TORO NEGRO 1 HP to TORO NEGRO 1 HP | 2026-07-10 | 0.015534 | Caguas | 50 | 0.094147 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 5400 | RIO BLANCO HP to RIO BLANCO HP | 2026-07-08 | 0.038394 | Caguas | 50 | 0.23269 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37800 | Caguas TC to Caguas TC | 2026-07-10 | 0.084239 | Caguas | 100 | 1.0211 | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6500 | TORO NEGRO 1 HP to TORO NEGRO 1 HP | 2026-07-10 | 0.17647 | Caguas | 50 | 1.0695 | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 9000 | GARZAS 1 HP to GARZAS 1 HP | 2026-07-10 | 0.21749 | Ponce | 50 | 1.3181 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37800 | Caguas TC to Caguas TC | 2026-07-11 | 0.029442 | Caguas | 100 | 0.35688 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 600 | CAGUAS TC to CAGUAS TC | 2026-07-11 | 0.26122 | Caguas | 50 | 1.5831 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 600 | CAGUAS TC to CAGUAS TC | 2026-07-11 | 0.02935 | Caguas | 50 | 0.17788 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 39000 | Comerio TC to Comerio TC | 2026-07-11 | 0.033086 | Caguas | 100 | 0.40104 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 5400 | RIO BLANCO HP to RIO BLANCO HP | 2026-07-07 | 0.02285 | Caguas | 50 | 0.13848 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 5400 | RIO BLANCO HP to RIO BLANCO HP | 2026-07-07 | 0.0093733 | Caguas | 50 | 0.056808 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2000 | ONCE DE AGOSTO SECT to ONCE DE AGOSTO SECT | 2026-07-13 | 0.20804 | Mayaguez | 50 | 1.2608 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2600 | SAN SEBASTIAN TC to SAN SEBASTIAN TC | 2026-07-14 | 0.16306 | Mayaguez | 50 | 0.98825 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 22000 | BARCELONETA TC to BARCELONETA TC | 2026-07-13 | 0.054679 | Arecibo | 50 | 0.33139 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-13 | 0.020736 | Arecibo | 50 | 0.12567 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 17900 | JUANA DIAZ TC to JUANA DIAZ TC | 2026-07-17 | 0.01845 | Ponce | 50 | 0.11182 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 17900 | JUANA DIAZ TC to JUANA DIAZ TC | 2026-07-17 | 0.032129 | Ponce | 50 | 0.19472 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 13400 | ACACIAS TC to ACACIAS TC | 2026-07-16 | 0.035242 | Mayaguez | 50 | 0.21359 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50200 | Manati TC to Manati TC | 2026-07-13 | 0.25745 | Bayamon | 100 | 3.1206 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 36100 | Dos Bocas Hydro Plant to Dos Bocas Hydro Plant | 2026-07-14 | 0.1101 | Bayamon | 100 | 1.3345 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.024128 | Arecibo | 50 | 0.14623 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.03003 | Arecibo | 50 | 0.182 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-13 | 0.030014 | Arecibo | 50 | 0.1819 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-14 | 0.026384 | Arecibo | 50 | 0.1599 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.0343 | Arecibo | 50 | 0.20788 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.029103 | Arecibo | 50 | 0.17638 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.031873 | Arecibo | 50 | 0.19317 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-13 | 0.054679 | Arecibo | 50 | 0.33139 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.035728 | Arecibo | 50 | 0.21653 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-14 | 0.033785 | Arecibo | 50 | 0.20476 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.031034 | Arecibo | 50 | 0.18808 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-14 | 0.028583 | Arecibo | 50 | 0.17323 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.023776 | Arecibo | 50 | 0.14409 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-14 | 0.044948 | Arecibo | 50 | 0.27241 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.052411 | Arecibo | 50 | 0.31764 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-14 | 0.046335 | Arecibo | 50 | 0.28082 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.056239 | Arecibo | 50 | 0.34084 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 3000 | JUNCOS TC to JUNCOS TC | 2026-07-17 | 0.026912 | Caguas | 50 | 0.1631 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 3000 | JUNCOS TC to JUNCOS TC | 2026-07-17 | 0.031239 | Caguas | 50 | 0.18933 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 3000 | JUNCOS TC to JUNCOS TC | 2026-07-18 | 0.019935 | Caguas | 50 | 0.12082 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-13 | 0.055993 | Arecibo | 50 | 0.33935 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.026719 | Arecibo | 50 | 0.16193 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.029204 | Arecibo | 50 | 0.177 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-16 | 0.066431 | Arecibo | 50 | 0.40261 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50400 | Costa Sur Power Plant to Costa Sur Power Plant | 2026-07-13 | 0.15063 | Mayaguez | 100 | 1.8259 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 12600 | HUMACAO TC to HUMACAO TC | 2026-07-14 | 0.028513 | Caguas | 50 | 0.17281 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 12600 | HUMACAO TC to HUMACAO TC | 2026-07-14 | 0.029787 | Caguas | 50 | 0.18053 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 5400 | RIO BLANCO HP to RIO BLANCO HP | 2026-07-13 | 0.023486 | Caguas | 50 | 0.14234 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 5400 | RIO BLANCO HP to RIO BLANCO HP | 2026-07-13 | 0.024284 | Caguas | 50 | 0.14718 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 5400 | RIO BLANCO HP to RIO BLANCO HP | 2026-07-13 | 0.020467 | Caguas | 50 | 0.12404 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 5400 | RIO BLANCO HP to RIO BLANCO HP | 2026-07-13 | 0.028155 | Caguas | 50 | 0.17064 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 1900 | DOS BOCAS HP to DOS BOCAS HP | 2026-07-14 | 0.13521 | Mayaguez | 50 | 0.81945 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37400 | Cambalache TC to Cambalache TC | 2026-07-14 | 0.14643 | Arecibo | 100 | 1.7749 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50400 | Costa Sur Power Plant to Costa Sur Power Plant | 2026-07-13 | 0.094304 | Mayaguez | 100 | 1.1431 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-16 | 0.020337 | Arecibo | 50 | 0.12325 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.028558 | Arecibo | 50 | 0.17308 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.026632 | Arecibo | 50 | 0.16141 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.025136 | Arecibo | 50 | 0.15234 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37400 | Cambalache TC to Cambalache TC | 2026-07-14 | 0.074884 | Arecibo | 100 | 0.90769 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-13 | 0.021662 | Arecibo | 50 | 0.13129 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.022367 | Arecibo | 50 | 0.13556 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50300 | Aguirre Power Plant to Aguirre Power Plant | 2026-07-13 | 0.1145 | Ponce | 100 | 1.3879 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 18400 | BARRANQUITAS TC to BARRANQUITAS TC | 2026-07-17 | 0.022774 | Caguas | 50 | 0.13802 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50300 | Aguirre Power Plant to Aguirre Power Plant | 2026-07-15 | 0.11507 | Ponce | 100 | 1.3948 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.032038 | Arecibo | 50 | 0.19417 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.01612 | Arecibo | 50 | 0.097699 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.035729 | Arecibo | 50 | 0.21654 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50300 | Aguirre Power Plant to Aguirre Power Plant | 2026-07-15 | 0.14309 | Ponce | 100 | 1.7345 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37400 | Cambalache TC to Cambalache TC | 2026-07-14 | 0.1333 | Arecibo | 100 | 1.6158 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50300 | Aguirre Power Plant to Aguirre Power Plant | 2026-07-16 | 0.1286 | Ponce | 100 | 1.5588 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50300 | Aguirre Power Plant to Aguirre Power Plant | 2026-07-16 | 0.46959 | Ponce | 100 | 5.6919 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50300 | Aguirre Power Plant to Aguirre Power Plant | 2026-07-16 | 0.40961 | Ponce | 100 | 4.965 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50300 | Aguirre Power Plant to Aguirre Power Plant | 2026-07-17 | 0.083846 | Ponce | 100 | 1.0163 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50300 | Aguirre Power Plant to Aguirre Power Plant | 2026-07-17 | 0.29528 | Ponce | 100 | 3.5791 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 18400 | BARRANQUITAS TC to BARRANQUITAS TC | 2026-07-17 | 0.031725 | Caguas | 50 | 0.19228 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37400 | Cambalache TC to Cambalache TC | 2026-07-14 | 0.08897 | Arecibo | 100 | 1.0784 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50400 | Costa Sur Power Plant to Costa Sur Power Plant | 2026-07-13 | 0.4552 | Mayaguez | 100 | 5.5175 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37800 | Caguas TC to Caguas TC | 2026-07-13 | 0.076778 | Caguas | 100 | 0.93064 | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37800 | Caguas TC to Caguas TC | 2026-07-13 | 0.09635 | Caguas | 100 | 1.1679 | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37800 | Caguas TC to Caguas TC | 2026-07-13 | 0.16405 | Caguas | 100 | 1.9885 | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37800 | Caguas TC to Caguas TC | 2026-07-13 | 0.093427 | Caguas | 100 | 1.1324 | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.023612 | Arecibo | 50 | 0.1431 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.023612 | Arecibo | 50 | 0.1431 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.021127 | Arecibo | 50 | 0.12804 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.032515 | Arecibo | 50 | 0.19706 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50200 | Costa Sur Power Plant to Costa Sur Power Plant | 2026-07-14 | 0.35085 | Ponce | 100 | 4.2528 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.026098 | Arecibo | 50 | 0.15817 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.031069 | Arecibo | 50 | 0.18829 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.021127 | Arecibo | 50 | 0.12804 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.028583 | Arecibo | 50 | 0.17323 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 36100 | Dos Bocas Hydro Plant to Dos Bocas Hydro Plant | 2026-07-13 | 0.081853 | Arecibo | 100 | 0.99216 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2000 | ONCE DE AGOSTO SECT to ONCE DE AGOSTO SECT | 2026-07-13 | 0.20804 | Mayaguez | 50 | 1.2608 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.030447 | Arecibo | 50 | 0.18453 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 1500 | MAYAGUEZ GP to MAYAGUEZ GP | 2026-07-13 | 0.20704 | Mayaguez | 50 | 1.2548 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.024234 | Arecibo | 50 | 0.14687 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 36100 | Dos Bocas Hydro Plant to Dos Bocas Hydro Plant | 2026-07-13 | 0.12595 | Arecibo | 100 | 1.5267 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 5400 | RIO BLANCO HP to RIO BLANCO HP | 2026-07-13 | 0.030738 | Caguas | 50 | 0.18629 | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 1500 | MAYAGUEZ GP to MAYAGUEZ GP | 2026-07-15 | 0.14583 | Mayaguez | 50 | 0.88383 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 1500 | MAYAGUEZ GP to MAYAGUEZ GP | 2026-07-14 | 0.14583 | Mayaguez | 50 | 0.88383 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.030447 | Arecibo | 50 | 0.18453 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.024234 | Arecibo | 50 | 0.14687 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 12600 | HUMACAO TC to HUMACAO TC | 2026-07-13 | 0.036613 | Caguas | 50 | 0.2219 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 12600 | HUMACAO TC to HUMACAO TC | 2026-07-13 | 0.036613 | Caguas | 50 | 0.2219 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.033554 | Arecibo | 50 | 0.20336 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.027962 | Arecibo | 50 | 0.16947 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 51000 | Aguirre Power Plant to Aguirre Power Plant | 2026-07-13 | 0.21393 | Caguas | 100 | 2.593 | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.030447 | Arecibo | 50 | 0.18453 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.029204 | Arecibo | 50 | 0.177 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.021127 | Arecibo | 50 | 0.12804 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.021841 | Arecibo | 50 | 0.13237 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.014144 | Arecibo | 50 | 0.085719 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 36400 | Ponce TC to Ponce TC | 2026-07-15 | 0.081325 | Ponce | 100 | 0.98576 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 1500 | MAYAGUEZ GP to MAYAGUEZ GP | 2026-07-15 | 0.23121 | Mayaguez | 50 | 1.4013 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 36400 | Ponce TC to Ponce TC | 2026-07-15 | 0.038073 | Ponce | 100 | 0.46149 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 1500 | MAYAGUEZ GP to MAYAGUEZ GP | 2026-07-14 | 0.079918 | Mayaguez | 50 | 0.48435 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 14400 | VEREDAS SECT to VEREDAS SECT | 2026-07-14 | 0.13834 | Caguas | 50 | 0.8384 | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2000 | ONCE DE AGOSTO SECT to ONCE DE AGOSTO SECT | 2026-07-14 | 0.30091 | Mayaguez | 50 | 1.8237 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 14400 | VEREDAS SECT to VEREDAS SECT | 2026-07-14 | 0.13834 | Caguas | 50 | 0.8384 | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37400 | Cambalache TC to Cambalache TC | 2026-07-16 | 0.085362 | Arecibo | 100 | 1.0347 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2000 | ONCE DE AGOSTO SECT to ONCE DE AGOSTO SECT | 2026-07-14 | 0.14539 | Mayaguez | 50 | 0.88117 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.033076 | Arecibo | 50 | 0.20046 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50200 | Costa Sur Power Plant to Costa Sur Power Plant | 2026-07-13 | 0.23617 | Arecibo | 100 | 2.8626 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.029204 | Arecibo | 50 | 0.177 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.029826 | Arecibo | 50 | 0.18076 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 1500 | MAYAGUEZ GP to MAYAGUEZ GP | 2026-07-14 | 0.30095 | Mayaguez | 50 | 1.8239 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.029204 | Arecibo | 50 | 0.177 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.029826 | Arecibo | 50 | 0.18076 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.029204 | Arecibo | 50 | 0.177 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 36100 | Dos Bocas Hydro Plant to Dos Bocas Hydro Plant | 2026-07-14 | 0.12004 | Arecibo | 100 | 1.4551 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.03065 | Arecibo | 50 | 0.18576 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.032248 | Arecibo | 50 | 0.19545 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.032493 | Arecibo | 50 | 0.19693 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.029366 | Arecibo | 50 | 0.17798 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.028276 | Arecibo | 50 | 0.17137 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.038604 | Arecibo | 50 | 0.23396 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.0046436 | Arecibo | 50 | 0.028143 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.029976 | Arecibo | 50 | 0.18167 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.026019 | Arecibo | 50 | 0.15769 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 14400 | VEREDAS SECT to VEREDAS SECT | 2026-07-14 | 0.037264 | Caguas | 50 | 0.22584 | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-14 | 0.030792 | Arecibo | 50 | 0.18662 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.023606 | Arecibo | 50 | 0.14307 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.031811 | Arecibo | 50 | 0.19279 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.030279 | Arecibo | 50 | 0.18351 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.030478 | Arecibo | 50 | 0.18472 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.032062 | Arecibo | 50 | 0.19431 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.02807 | Arecibo | 50 | 0.17012 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.017794 | Arecibo | 50 | 0.10784 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.030273 | Arecibo | 50 | 0.18347 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-17 | 0.027028 | Arecibo | 50 | 0.16381 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-17 | 0.011027 | Arecibo | 50 | 0.066833 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 1500 | MAYAGUEZ GP to MAYAGUEZ GP | 2026-07-14 | 0.18231 | Mayaguez | 50 | 1.1049 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-17 | 0.016155 | Arecibo | 50 | 0.09791 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2000 | ONCE DE AGOSTO SECT to ONCE DE AGOSTO SECT | 2026-07-14 | 0.18357 | Mayaguez | 50 | 1.1126 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-17 | 0.031256 | Arecibo | 50 | 0.18943 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-17 | 0.031109 | Arecibo | 50 | 0.18854 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.0011153 | Arecibo | 50 | 0.0067596 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.00097178 | Arecibo | 50 | 0.0058896 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.026941 | Arecibo | 50 | 0.16328 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.034248 | Arecibo | 50 | 0.20756 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.0082064 | Arecibo | 50 | 0.049736 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.073733 | Arecibo | 50 | 0.44686 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 5600 | AÑASCO TC to AÑASCO TC | 2026-07-14 | 0.037277 | Mayaguez | 50 | 0.22592 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.015888 | Arecibo | 50 | 0.096294 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.0030678 | Arecibo | 50 | 0.018593 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 5600 | AÑASCO TC to AÑASCO TC | 2026-07-14 | 0.049233 | Mayaguez | 50 | 0.29838 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2000 | ONCE DE AGOSTO SECT to ONCE DE AGOSTO SECT | 2026-07-14 | 0.076012 | Mayaguez | 50 | 0.46068 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2600 | SAN SEBASTIAN TC to SAN SEBASTIAN TC | 2026-07-14 | 0.077801 | Mayaguez | 50 | 0.47152 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.019641 | Arecibo | 50 | 0.11904 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.029044 | Arecibo | 50 | 0.17602 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.027557 | Arecibo | 50 | 0.16701 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.028396 | Arecibo | 50 | 0.1721 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 14400 | VEREDAS SECT to VEREDAS SECT | 2026-07-14 | 0.063256 | Caguas | 50 | 0.38337 | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.029754 | Arecibo | 50 | 0.18033 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 14400 | VEREDAS SECT to VEREDAS SECT | 2026-07-14 | 0.052848 | Caguas | 50 | 0.32029 | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2300 | ARECIBO SECT to ARECIBO SECT | 2026-07-14 | 0.17034 | Arecibo | 50 | 1.0324 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 36100 | Dos Bocas Hydro Plant to Dos Bocas Hydro Plant | 2026-07-14 | 0.18609 | Arecibo | 100 | 2.2557 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 36100 | Dos Bocas Hydro Plant to Dos Bocas Hydro Plant | 2026-07-14 | 0.060775 | Arecibo | 100 | 0.73667 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2000 | ONCE DE AGOSTO SECT to ONCE DE AGOSTO SECT | 2026-07-14 | 0.059386 | Mayaguez | 50 | 0.35991 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 36100 | Dos Bocas Hydro Plant to Dos Bocas Hydro Plant | 2026-07-15 | 0.10741 | Bayamon | 100 | 1.302 | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 14400 | VEREDAS SECT to VEREDAS SECT | 2026-07-15 | 0.052812 | Caguas | 50 | 0.32007 | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2400 | DOS BOCAS HP to DOS BOCAS HP | 2026-07-15 | 0.31082 | Arecibo | 50 | 1.8838 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 14400 | VEREDAS SECT to VEREDAS SECT | 2026-07-15 | 0.029323 | Caguas | 50 | 0.17771 | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-17 | 0.019913 | Arecibo | 50 | 0.12069 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.016394 | Arecibo | 50 | 0.09936 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 5600 | AÑASCO TC to AÑASCO TC | 2026-07-15 | 0.14733 | Mayaguez | 50 | 0.89289 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.0041061 | Arecibo | 50 | 0.024885 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.013459 | Arecibo | 50 | 0.081569 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-17 | 0.024938 | Arecibo | 50 | 0.15114 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.028216 | Arecibo | 50 | 0.17101 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.021112 | Arecibo | 50 | 0.12795 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.023671 | Arecibo | 50 | 0.14346 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-15 | 0.02383 | Arecibo | 50 | 0.14442 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 14400 | VEREDAS SECT to VEREDAS SECT | 2026-07-15 | 0.090329 | Caguas | 50 | 0.54745 | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6500 | TORO NEGRO 1 HP to TORO NEGRO 1 HP | 2026-07-16 | 0.052476 | Caguas | 50 | 0.31804 | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-17 | 0.025681 | Arecibo | 50 | 0.15564 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-16 | 0.027711 | Arecibo | 50 | 0.16795 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-16 | 0.026971 | Arecibo | 50 | 0.16346 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-16 | 0.028331 | Arecibo | 50 | 0.1717 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-16 | 0.027958 | Arecibo | 50 | 0.16944 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-16 | 0.027855 | Arecibo | 50 | 0.16882 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-16 | 0.028663 | Arecibo | 50 | 0.17372 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-16 | 0.02002 | Arecibo | 50 | 0.12133 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-16 | 0.028535 | Arecibo | 50 | 0.17294 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 8100 | YAUCO 1 HP to YAUCO 1 HP | 2026-07-16 | 0.13707 | Ponce | 50 | 0.83075 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-16 | 0.028072 | Arecibo | 50 | 0.17014 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 36100 | Dos Bocas Hydro Plant to Dos Bocas Hydro Plant | 2026-07-16 | 0.15878 | Arecibo | 100 | 1.9246 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-16 | 0.021509 | Arecibo | 50 | 0.13036 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-16 | 0.030627 | Arecibo | 50 | 0.18562 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-16 | 0.027481 | Arecibo | 50 | 0.16655 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 36100 | Dos Bocas Hydro Plant to Dos Bocas Hydro Plant | 2026-07-16 | 0.29059 | Arecibo | 100 | 3.5223 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-16 | 0.029932 | Arecibo | 50 | 0.18141 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-16 | 0.0269 | Arecibo | 50 | 0.16303 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 5600 | AÑASCO TC to AÑASCO TC | 2026-07-16 | 0.058877 | Mayaguez | 50 | 0.35683 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 5600 | AÑASCO TC to AÑASCO TC | 2026-07-15 | 0.034607 | Mayaguez | 50 | 0.20974 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 36100 | Dos Bocas Hydro Plant to Dos Bocas Hydro Plant | 2026-07-16 | 0.064335 | Arecibo | 100 | 0.77982 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-16 | 0.02018 | Arecibo | 50 | 0.1223 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-16 | 0.022631 | Arecibo | 50 | 0.13716 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-16 | 0.023588 | Arecibo | 50 | 0.14296 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-16 | 0.024187 | Arecibo | 50 | 0.14659 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-16 | 0.024437 | Arecibo | 50 | 0.1481 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-16 | 0.024942 | Arecibo | 50 | 0.15116 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-16 | 0.018876 | Arecibo | 50 | 0.1144 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-16 | 0.046483 | Arecibo | 50 | 0.28171 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-16 | 0.035828 | Arecibo | 50 | 0.21714 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-16 | 0.038523 | Arecibo | 50 | 0.23347 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-16 | 0.029959 | Arecibo | 50 | 0.18157 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 10100 | LAS LOMAS SECT to LAS LOMAS SECT | 2026-07-16 | 0.029826 | San Juan | 50 | 0.18076 | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-16 | 0.0087737 | Arecibo | 50 | 0.053174 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-16 | 0.044059 | Arecibo | 50 | 0.26702 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-16 | 0.028561 | Arecibo | 50 | 0.1731 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-16 | 0.031475 | Arecibo | 50 | 0.19076 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-16 | 0.019922 | Arecibo | 50 | 0.12074 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-16 | 0.031824 | Arecibo | 50 | 0.19287 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-16 | 0.0023587 | Arecibo | 50 | 0.014295 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50400 | Costa Sur Power Plant to Costa Sur Power Plant | 2026-07-16 | 0.24666 | Ponce | 100 | 2.9898 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-16 | 0.032631 | Arecibo | 50 | 0.19777 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 1900 | DOS BOCAS HP to DOS BOCAS HP | 2026-07-16 | 0.037904 | Arecibo | 50 | 0.22972 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 1900 | DOS BOCAS HP to DOS BOCAS HP | 2026-07-16 | 0.086992 | Arecibo | 50 | 0.52722 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50400 | Costa Sur Power Plant to Costa Sur Power Plant | 2026-07-16 | 0.1331 | Ponce | 100 | 1.6134 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 1900 | DOS BOCAS HP to DOS BOCAS HP | 2026-07-16 | 0.059652 | Arecibo | 50 | 0.36153 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 10100 | LAS LOMAS SECT to LAS LOMAS SECT | 2026-07-16 | 0.023656 | San Juan | 50 | 0.14337 | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37400 | Cambalache TC to Cambalache TC | 2026-07-16 | 0.24675 | Arecibo | 100 | 2.9909 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37400 | Cambalache TC to Cambalache TC | 2026-07-17 | 0.27376 | Arecibo | 100 | 3.3183 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-17 | 0.044359 | Arecibo | 50 | 0.26884 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-17 | 0.037183 | Arecibo | 50 | 0.22535 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 3000 | JUNCOS TC to JUNCOS TC | 2026-07-17 | 0.025761 | Caguas | 50 | 0.15613 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 5600 | AÑASCO TC to AÑASCO TC | 2026-07-16 | 0.092886 | Mayaguez | 50 | 0.56295 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 7300 | BALDRICH SECT to BALDRICH SECT | 2026-07-17 | 0.033743 | San Juan | 50 | 0.2045 | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50400 | Costa Sur Power Plant to Costa Sur Power Plant | 2026-07-18 | 0.2188 | Mayaguez | 100 | 2.6521 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 3400 | MONACILLOS TC to MONACILLOS TC | 2026-07-18 | 0.024299 | San Juan | 50 | 0.14727 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 8100 | YAUCO 1 HP to YAUCO 1 HP | 2026-07-16 | 0.3477 | Ponce | 50 | 2.1073 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 1300 | YAUCO 1 HP to YAUCO 1 HP | 2026-07-17 | 0.17691 | Ponce | 50 | 1.0722 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2000 | SAN SEBASTIAN TC to SAN SEBASTIAN TC | 2026-07-17 | 0.14851 | Mayaguez | 50 | 0.90005 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2000 | SAN SEBASTIAN TC to SAN SEBASTIAN TC | 2026-07-17 | 0.14539 | Mayaguez | 50 | 0.88117 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37100 | Acacias TC to Acacias TC | 2026-07-17 | 0.12718 | Ponce | 100 | 1.5416 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.031241 | Arecibo | 50 | 0.18934 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-20 | 0.03031 | Arecibo | 50 | 0.1837 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.056545 | Arecibo | 50 | 0.3427 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-21 | 0.031855 | Arecibo | 50 | 0.19306 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 13500 | ACACIAS TC to ACACIAS TC | 2026-07-20 | 0.030339 | Mayaguez | 50 | 0.18387 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 17900 | JUANA DIAZ TC to JUANA DIAZ TC | 2026-07-20 | 0.032557 | Ponce | 50 | 0.19732 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 17900 | JUANA DIAZ TC to JUANA DIAZ TC | 2026-07-20 | 0.026098 | Ponce | 50 | 0.15817 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-21 | 0.035324 | Arecibo | 50 | 0.21409 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-21 | 0.037282 | Arecibo | 50 | 0.22595 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-24 | 0.029834 | Arecibo | 50 | 0.18081 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50200 | Manati TC to Manati TC | 2026-07-23 | 0.40583 | Bayamon | 100 | 4.9192 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-21 | 0.048661 | Arecibo | 50 | 0.29491 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-21 | 0.035875 | Arecibo | 50 | 0.21742 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.029204 | Arecibo | 50 | 0.177 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.01802 | Arecibo | 50 | 0.10921 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-20 | 0.039827 | Arecibo | 50 | 0.24138 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-21 | 0.057518 | Arecibo | 50 | 0.34859 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-20 | 0.047529 | Arecibo | 50 | 0.28805 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-20 | 0.041157 | Arecibo | 50 | 0.24944 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-20 | 0.041157 | Arecibo | 50 | 0.24944 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-21 | 0.030049 | Arecibo | 50 | 0.18212 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-21 | 0.035135 | Arecibo | 50 | 0.21294 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.02639 | Arecibo | 50 | 0.15994 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.0093964 | Arecibo | 50 | 0.056948 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.0093578 | Arecibo | 50 | 0.056714 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.0057657 | Arecibo | 50 | 0.034944 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.07073 | Arecibo | 50 | 0.42867 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.055305 | Arecibo | 50 | 0.33518 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.057661 | Arecibo | 50 | 0.34946 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-21 | 0.055601 | Arecibo | 50 | 0.33698 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-21 | 0.056713 | Arecibo | 50 | 0.34372 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-21 | 0.044636 | Arecibo | 50 | 0.27052 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-21 | 0.025586 | Arecibo | 50 | 0.15506 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-21 | 0.043441 | Arecibo | 50 | 0.26328 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-20 | 0.04828 | Arecibo | 50 | 0.29261 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.012104 | Arecibo | 50 | 0.07336 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.0028521 | Arecibo | 50 | 0.017285 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.02285 | Arecibo | 50 | 0.13848 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.032068 | Arecibo | 50 | 0.19435 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-21 | 0.049123 | Arecibo | 50 | 0.29772 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-23 | 0.036629 | Arecibo | 50 | 0.22199 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-23 | 0.03604 | Arecibo | 50 | 0.21842 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-20 | 0.028858 | Arecibo | 50 | 0.1749 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-20 | 0.047846 | Arecibo | 50 | 0.28997 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-23 | 0.029826 | Arecibo | 50 | 0.18076 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-23 | 0.029826 | Arecibo | 50 | 0.18076 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-23 | 0.024855 | Arecibo | 50 | 0.15064 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-23 | 0.030447 | Arecibo | 50 | 0.18453 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-23 | 0.026983 | Arecibo | 50 | 0.16353 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-20 | 0.03031 | Arecibo | 50 | 0.1837 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.056545 | Arecibo | 50 | 0.3427 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-21 | 0.042996 | Arecibo | 50 | 0.26058 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-21 | 0.016247 | Arecibo | 50 | 0.098466 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-21 | 0.029196 | Arecibo | 50 | 0.17695 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-21 | 0.023118 | Arecibo | 50 | 0.14011 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-23 | 0.016802 | Arecibo | 50 | 0.10183 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-23 | 0.030174 | Arecibo | 50 | 0.18287 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-20 | 0.033197 | Arecibo | 50 | 0.2012 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-23 | 0.022029 | Arecibo | 50 | 0.13351 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-21 | 0.027312 | Arecibo | 50 | 0.16553 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-21 | 0.02648 | Arecibo | 50 | 0.16048 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-23 | 0.0053705 | Arecibo | 50 | 0.032548 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-23 | 0.0062305 | Arecibo | 50 | 0.037761 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-23 | 0.0058725 | Arecibo | 50 | 0.035591 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-23 | 0.0025216 | Arecibo | 50 | 0.015282 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-23 | 0.0268 | Arecibo | 50 | 0.16243 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-23 | 0.0047292 | Arecibo | 50 | 0.028662 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-21 | 0.057787 | Arecibo | 50 | 0.35023 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.055302 | Arecibo | 50 | 0.33516 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-23 | 0.013395 | Arecibo | 50 | 0.081181 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.013395 | Arecibo | 50 | 0.081181 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.03386 | Arecibo | 50 | 0.20521 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-21 | 0.014148 | Arecibo | 50 | 0.085745 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-21 | 0.02881 | Arecibo | 50 | 0.17461 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-21 | 0.029628 | Arecibo | 50 | 0.17956 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-21 | 0.028609 | Arecibo | 50 | 0.17338 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-21 | 0.030237 | Arecibo | 50 | 0.18326 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50300 | Aguirre Power Plant to Aguirre Power Plant | 2026-07-20 | 0.076314 | Ponce | 100 | 0.92501 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50300 | Aguirre Power Plant to Aguirre Power Plant | 2026-07-20 | 0.26877 | Ponce | 100 | 3.2579 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 18400 | BARRANQUITAS TC to BARRANQUITAS TC | 2026-07-23 | 0.038835 | Caguas | 50 | 0.23536 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 18400 | BARRANQUITAS TC to BARRANQUITAS TC | 2026-07-20 | 0.04211 | Caguas | 50 | 0.25521 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50300 | Aguirre Power Plant to Aguirre Power Plant | 2026-07-21 | 0.2202 | Ponce | 100 | 2.6691 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50300 | Aguirre Power Plant to Aguirre Power Plant | 2026-07-22 | 0.25266 | Ponce | 100 | 3.0626 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50300 | Aguirre Power Plant to Aguirre Power Plant | 2026-07-24 | 0.17803 | Ponce | 100 | 2.1579 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37400 | Cambalache TC to Cambalache TC | 2026-07-21 | 0.14739 | Arecibo | 100 | 1.7865 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 18400 | BARRANQUITAS TC to BARRANQUITAS TC | 2026-07-23 | 0.032655 | Caguas | 50 | 0.19791 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 18400 | BARRANQUITAS TC to BARRANQUITAS TC | 2026-07-21 | 0.022668 | Caguas | 50 | 0.13738 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.0071458 | Arecibo | 50 | 0.043308 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.012243 | Arecibo | 50 | 0.074199 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.031783 | Arecibo | 50 | 0.19262 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.031084 | Arecibo | 50 | 0.18839 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.028841 | Arecibo | 50 | 0.1748 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.029214 | Arecibo | 50 | 0.17705 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.026432 | Arecibo | 50 | 0.16019 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.034298 | Arecibo | 50 | 0.20787 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.040365 | Arecibo | 50 | 0.24464 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.028884 | Arecibo | 50 | 0.17506 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.022783 | Arecibo | 50 | 0.13808 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.01492 | Arecibo | 50 | 0.090427 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.029436 | Arecibo | 50 | 0.1784 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.037054 | Arecibo | 50 | 0.22457 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.024864 | Arecibo | 50 | 0.15069 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.024453 | Arecibo | 50 | 0.1482 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.027729 | Arecibo | 50 | 0.16805 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.030805 | Arecibo | 50 | 0.1867 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.031491 | Arecibo | 50 | 0.19086 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.032412 | Arecibo | 50 | 0.19644 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.033558 | Arecibo | 50 | 0.20338 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.027937 | Arecibo | 50 | 0.16931 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.038312 | Arecibo | 50 | 0.23219 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.027445 | Arecibo | 50 | 0.16633 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.024557 | Arecibo | 50 | 0.14883 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.029497 | Arecibo | 50 | 0.17877 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.023957 | Arecibo | 50 | 0.14519 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 3400 | MONACILLOS TC to MONACILLOS TC | 2026-07-21 | 0.020548 | San Juan | 50 | 0.12453 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.012814 | Arecibo | 50 | 0.07766 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 36100 | Dos Bocas Hydro Plant to Dos Bocas Hydro Plant | 2026-07-20 | 0.040678 | Arecibo | 100 | 0.49307 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 3400 | MONACILLOS TC to MONACILLOS TC | 2026-07-21 | 0.022678 | San Juan | 50 | 0.13744 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 3400 | MONACILLOS TC to MONACILLOS TC | 2026-07-21 | 0.02473 | San Juan | 50 | 0.14988 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 8100 | YAUCO 1 HP to YAUCO 1 HP | 2026-07-23 | 0.3477 | Ponce | 50 | 2.1073 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.016833 | Arecibo | 50 | 0.10202 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.024781 | Arecibo | 50 | 0.15019 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.030596 | Arecibo | 50 | 0.18543 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.025724 | Arecibo | 50 | 0.1559 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.026882 | Arecibo | 50 | 0.16292 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.013978 | Arecibo | 50 | 0.084718 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.035418 | Arecibo | 50 | 0.21466 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.025172 | Arecibo | 50 | 0.15256 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.023964 | Arecibo | 50 | 0.14524 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 36100 | Dos Bocas Hydro Plant to Dos Bocas Hydro Plant | 2026-07-21 | 0.13384 | Arecibo | 100 | 1.6223 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-21 | 0.039886 | Arecibo | 50 | 0.24174 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-21 | 0.044114 | Arecibo | 50 | 0.26736 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.040214 | Arecibo | 50 | 0.24372 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-21 | 0.05903 | Arecibo | 50 | 0.35776 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-23 | 0.062717 | Arecibo | 50 | 0.38011 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 3400 | MONACILLOS TC to MONACILLOS TC | 2026-07-22 | 0.025905 | San Juan | 50 | 0.157 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 5600 | AGUADA TO to AGUADA TO | 2026-07-21 | 0.040274 | Mayaguez | 50 | 0.24409 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 36700 | San Sebastian TC to San Sebastian TC | 2026-07-21 | 0.022514 | Mayaguez | 100 | 0.2729 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 36700 | San Sebastian TC to San Sebastian TC | 2026-07-20 | 0.088775 | Mayaguez | 100 | 1.0761 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 36700 | San Sebastian TC to San Sebastian TC | 2026-07-20 | 0.037326 | Mayaguez | 100 | 0.45244 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 36700 | San Sebastian TC to San Sebastian TC | 2026-07-20 | 0.092273 | Mayaguez | 100 | 1.1185 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50400 | Costa Sur Power Plant to Costa Sur Power Plant | 2026-07-20 | 0.11136 | Ponce | 100 | 1.3498 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37100 | San German TC to San German TC | 2026-07-20 | 0.11198 | Ponce | 100 | 1.3573 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 36700 | Mayaguez TC to Mayaguez TC | 2026-07-21 | 0.16857 | Mayaguez | 100 | 2.0433 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | VEGA BAJA TC to VEGA BAJA TC | 2026-07-22 | 0.016079 | Arecibo | 50 | 0.097446 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.030852 | Arecibo | 50 | 0.18698 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.017265 | Arecibo | 50 | 0.10463 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.01023 | Arecibo | 50 | 0.062002 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.036609 | Arecibo | 50 | 0.22187 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.02606 | Arecibo | 50 | 0.15794 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.035416 | Arecibo | 50 | 0.21464 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.022067 | Arecibo | 50 | 0.13374 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.029206 | Arecibo | 50 | 0.17701 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.038252 | Arecibo | 50 | 0.23183 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.028752 | Arecibo | 50 | 0.17426 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 36700 | Mayaguez TC to Mayaguez TC | 2026-07-21 | 0.083555 | Mayaguez | 100 | 1.0128 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 36100 | Barrio Piña GIS to Barrio Piña GIS | 2026-07-20 | 0.12098 | Arecibo | 100 | 1.4664 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 36100 | Barrio Piña GIS to Barrio Piña GIS | 2026-07-20 | 0.078521 | Arecibo | 100 | 0.95177 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 36700 | Mayaguez TC to Mayaguez TC | 2026-07-21 | 0.035473 | Mayaguez | 100 | 0.42997 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 36700 | Mayaguez TC to Mayaguez TC | 2026-07-23 | 0.085951 | Mayaguez | 100 | 1.0418 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50400 | Costa Sur Power Plant to Costa Sur Power Plant | 2026-07-21 | 0.32231 | Mayaguez | 100 | 3.9068 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 3000 | RIO BLANCO HP to RIO BLANCO HP | 2026-07-21 | 0.044739 | Caguas | 50 | 0.27114 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 3000 | RIO BLANCO HP to RIO BLANCO HP | 2026-07-21 | 0.019262 | Caguas | 50 | 0.11674 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 3000 | RIO BLANCO HP to RIO BLANCO HP | 2026-07-21 | 0.019884 | Caguas | 50 | 0.12051 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 3000 | RIO BLANCO HP to RIO BLANCO HP | 2026-07-21 | 0.032944 | Caguas | 50 | 0.19966 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 36100 | Barrio Piña GIS to Barrio Piña GIS | 2026-07-21 | 0.116 | Arecibo | 100 | 1.406 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | VEGA BAJA TC to VEGA BAJA TC | 2026-07-22 | 0.042875 | Arecibo | 50 | 0.25985 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | VEGA BAJA TC to VEGA BAJA TC | 2026-07-22 | 0.036935 | Arecibo | 50 | 0.22385 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50400 | Costa Sur Power Plant to Costa Sur Power Plant | 2026-07-21 | 0.32969 | Ponce | 100 | 3.9963 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 3000 | RIO BLANCO HP to RIO BLANCO HP | 2026-07-22 | 0.032683 | Caguas | 50 | 0.19808 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 18400 | EL ABANICO to EL ABANICO | 2026-07-21 | 0.050709 | Caguas | 50 | 0.30733 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37400 | Barceloneta TC to Barceloneta TC | 2026-07-23 | 0.25256 | Arecibo | 100 | 3.0614 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37400 | Barceloneta TC to Barceloneta TC | 2026-07-22 | 0.18552 | Arecibo | 100 | 2.2487 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 3000 | RIO BLANCO HP to RIO BLANCO HP | 2026-07-22 | 0.034033 | Caguas | 50 | 0.20626 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 5600 | MAYAGUEZ GP to MAYAGUEZ GP | 2026-07-21 | 0.079421 | Mayaguez | 50 | 0.48134 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 36700 | Mayaguez TC to Mayaguez TC | 2026-07-22 | 0.15294 | Mayaguez | 100 | 1.8538 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37100 | San German TC to San German TC | 2026-07-21 | 0.09585 | Ponce | 100 | 1.1618 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50400 | Costa Sur Power Plant to Costa Sur Power Plant | 2026-07-21 | 0.14512 | Mayaguez | 100 | 1.7591 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50400 | Costa Sur Power Plant to Costa Sur Power Plant | 2026-07-21 | 0.381 | Mayaguez | 100 | 4.6182 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 5600 | MAYAGUEZ GP to MAYAGUEZ GP | 2026-07-23 | 0.074227 | Mayaguez | 50 | 0.44986 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37400 | Barceloneta TC to Barceloneta TC | 2026-07-23 | 0.10826 | Arecibo | 100 | 1.3123 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 14400 | GAUTIER BENITEZ SECT to GAUTIER BENITEZ SECT | 2026-07-22 | 0.026216 | Caguas | 50 | 0.15888 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 14400 | GAUTIER BENITEZ SECT to GAUTIER BENITEZ SECT | 2026-07-20 | 0.030963 | Caguas | 50 | 0.18765 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 600 | GAUTIER BENITEZ SECT to GAUTIER BENITEZ SECT | 2026-07-21 | 0.028336 | Caguas | 50 | 0.17174 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 600 | GAUTIER BENITEZ SECT to GAUTIER BENITEZ SECT | 2026-07-22 | 0.092463 | Caguas | 50 | 0.56038 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37100 | San German TC to San German TC | 2026-07-21 | 0.10053 | Ponce | 100 | 1.2185 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 39000 | PONCE TC to PONCE TC | 2026-07-22 | 0.35644 | Caguas | 100 | 4.3205 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37800 | CAGUAS TC to CAGUAS TC | 2026-07-22 | 0.28669 | Caguas | 100 | 3.4751 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37800 | CAGUAS TC to CAGUAS TC | 2026-07-22 | 0.19562 | Caguas | 100 | 2.3712 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37800 | CAGUAS TC to CAGUAS TC | 2026-07-21 | 0.070158 | Caguas | 100 | 0.8504 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 36100 | Barrio Piña GIS to Barrio Piña GIS | 2026-07-21 | 0.18679 | Arecibo | 100 | 2.2641 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 36700 | Mayaguez TC to Mayaguez TC | 2026-07-22 | 0.11451 | Mayaguez | 100 | 1.388 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 36700 | Mayaguez TC to Mayaguez TC | 2026-07-22 | 0.13459 | Mayaguez | 100 | 1.6314 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | VEGA BAJA TC to VEGA BAJA TC | 2026-07-22 | 0.031515 | Arecibo | 50 | 0.191 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | VEGA BAJA TC to VEGA BAJA TC | 2026-07-23 | 0.032664 | Arecibo | 50 | 0.19796 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | VEGA BAJA TC to VEGA BAJA TC | 2026-07-22 | 0.031855 | Arecibo | 50 | 0.19306 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | MIRADOR AZUL SECT to MIRADOR AZUL SECT | 2026-07-22 | 0.023728 | Arecibo | 50 | 0.14381 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.011012 | Arecibo | 50 | 0.066742 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 11400 | FLORIDA TO to FLORIDA TO | 2026-07-22 | 0.1249 | Arecibo | 50 | 0.75694 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | MIRADOR AZUL SECT to MIRADOR AZUL SECT | 2026-07-22 | 0.0086992 | Arecibo | 50 | 0.052723 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | VEGA BAJA TC to VEGA BAJA TC | 2026-07-23 | 0.036661 | Arecibo | 50 | 0.22219 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 36100 | Barrio Piña GIS to Barrio Piña GIS | 2026-07-22 | 0.13285 | Arecibo | 100 | 1.6103 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50400 | Costa Sur Power Plant to Costa Sur Power Plant | 2026-07-22 | 0.094304 | Mayaguez | 100 | 1.1431 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.027574 | Arecibo | 50 | 0.16712 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37100 | San German TC to San German TC | 2026-07-22 | 0.074509 | Ponce | 100 | 0.90314 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37100 | San German TC to San German TC | 2026-07-22 | 0.07577 | Ponce | 100 | 0.91843 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.021522 | Arecibo | 50 | 0.13044 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.039753 | Arecibo | 50 | 0.24093 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.049913 | Arecibo | 50 | 0.30251 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.039102 | Arecibo | 50 | 0.23698 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.04198 | Arecibo | 50 | 0.25442 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.037846 | Arecibo | 50 | 0.22937 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-22 | 0.034874 | Arecibo | 50 | 0.21136 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 36700 | Mayaguez TC to Mayaguez TC | 2026-07-22 | 0.08129 | Mayaguez | 100 | 0.98533 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 8100 | ADJUNTAS TO to ADJUNTAS TO | 2026-07-22 | 0.27439 | Ponce | 50 | 1.663 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37100 | San German TC to San German TC | 2026-07-22 | 0.2958 | Mayaguez | 100 | 3.5854 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 36100 | Barrio Piña GIS to Barrio Piña GIS | 2026-07-23 | 0.11114 | Arecibo | 100 | 1.3472 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 4600 | LA RAMBLA SECT to LA RAMBLA SECT | 2026-07-23 | 0.022146 | Ponce | 50 | 0.13422 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 36700 | Mayaguez TC to Mayaguez TC | 2026-07-23 | 0.15294 | Mayaguez | 100 | 1.8538 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 500 | COSTA SUR SP to COSTA SUR SP | 2026-07-24 | 0.027962 | Ponce | 50 | 0.16947 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 500 | COSTA SUR SP to COSTA SUR SP | 2026-07-24 | 0.031069 | Ponce | 50 | 0.18829 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37100 | San German TC to San German TC | 2026-07-23 | 0.1007 | Ponce | 100 | 1.2206 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50400 | Costa Sur Power Plant to Costa Sur Power Plant | 2026-07-23 | 0.084585 | Mayaguez | 100 | 1.0253 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37100 | San German TC to San German TC | 2026-07-23 | 0.11024 | Mayaguez | 100 | 1.3363 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 3000 | RIO BLANCO HP to RIO BLANCO HP | 2026-07-25 | 0.031784 | Caguas | 50 | 0.19263 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37400 | Barceloneta TC to Barceloneta TC | 2026-07-23 | 0.24675 | Arecibo | 100 | 2.9909 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 1500 | ONCE DE AGOSTO SECT to ONCE DE AGOSTO SECT | 2026-07-23 | 0.27773 | Mayaguez | 50 | 1.6832 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 36400 | Dos Bocas Hydro Plant to Dos Bocas Hydro Plant | 2026-07-23 | 0.081222 | Arecibo | 100 | 0.98451 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 36700 | Mayaguez TC to Mayaguez TC | 2026-07-23 | 0.081334 | Mayaguez | 100 | 0.98587 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 8100 | ADJUNTAS TO to ADJUNTAS TO | 2026-07-23 | 0.20015 | Ponce | 50 | 1.213 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50400 | Costa Sur Power Plant to Costa Sur Power Plant | 2026-07-23 | 0.12051 | Mayaguez | 100 | 1.4607 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 5600 | AÑASCO TC to AÑASCO TC | 2026-07-23 | 0.05752 | Mayaguez | 50 | 0.3486 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 36700 | San Sebastian TC to San Sebastian TC | 2026-07-23 | 0.092297 | Mayaguez | 100 | 1.1187 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 1600 | SAN GERMAN TC to SAN GERMAN TC | 2026-07-24 | 0.18765 | Mayaguez | 50 | 1.1373 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 39800 | Mayaguez Power Plant to Mayaguez Power Plant | 2026-07-23 | 0.10463 | Mayaguez | 100 | 1.2683 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 1600 | SAN GERMAN TC to SAN GERMAN TC | 2026-07-23 | 0.18765 | Mayaguez | 50 | 1.1373 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2000 | ONCE DE AGOSTO SECT to ONCE DE AGOSTO SECT | 2026-07-24 | 0.14627 | Mayaguez | 50 | 0.88649 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50500 | Mayaguez TC to Mayaguez TC | 2026-07-24 | 0.090639 | Mayaguez | 100 | 1.0987 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50500 | Mayaguez TC to Mayaguez TC | 2026-07-24 | 0.13145 | Mayaguez | 100 | 1.5934 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2000 | ONCE DE AGOSTO SECT to ONCE DE AGOSTO SECT | 2026-07-24 | 0.27473 | Mayaguez | 50 | 1.665 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 5600 | AÑASCO TC to AÑASCO TC | 2026-07-24 | 0.064295 | Mayaguez | 50 | 0.38967 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 5600 | AÑASCO TC to AÑASCO TC | 2026-07-24 | 0.053042 | Mayaguez | 50 | 0.32147 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50500 | Mayaguez TC to Mayaguez TC | 2026-07-24 | 0.047854 | Mayaguez | 100 | 0.58005 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2000 | MAYAGUEZ TC to MAYAGUEZ TC | 2026-07-29 | 0.084296 | Mayaguez | 50 | 0.51088 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 1500 | ONCE DE AGOSTO SECT to ONCE DE AGOSTO SECT | 2026-07-28 | 0.18256 | Mayaguez | 50 | 1.1064 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 1500 | ONCE DE AGOSTO SECT to ONCE DE AGOSTO SECT | 2026-07-31 | 0.16753 | Mayaguez | 50 | 1.0153 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37200 | Mayaguez TC to Mayaguez TC | 2026-07-30 | 0.090283 | Mayaguez | 100 | 1.0943 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 9400 | DORADO TC to DORADO TC | 2026-07-30 | 0.04304 | Bayamon | 50 | 0.26085 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | BARCELONETA TC to BARCELONETA TC | 2026-07-29 | 0.033554 | Arecibo | 50 | 0.20336 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-31 | 0.049088 | Arecibo | 50 | 0.2975 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50200 | Manati TC to Manati TC | 2026-07-30 | 0.17169 | Bayamon | 100 | 2.0811 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 17900 | JUANA DIAZ TC to JUANA DIAZ TC | 2026-07-30 | 0.038525 | Ponce | 50 | 0.23348 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 17900 | JUANA DIAZ TC to JUANA DIAZ TC | 2026-07-27 | 0.039146 | Ponce | 50 | 0.23725 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 17900 | JUANA DIAZ TC to JUANA DIAZ TC | 2026-07-29 | 0.04101 | Ponce | 50 | 0.24855 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 17900 | JUANA DIAZ TC to JUANA DIAZ TC | 2026-07-29 | 0.037282 | Ponce | 50 | 0.22595 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 17900 | JUANA DIAZ TC to JUANA DIAZ TC | 2026-07-30 | 0.024855 | Ponce | 50 | 0.15064 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 17900 | JUANA DIAZ TC to JUANA DIAZ TC | 2026-07-31 | 0.042253 | Ponce | 50 | 0.25608 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 17900 | JUANA DIAZ TC to JUANA DIAZ TC | 2026-07-31 | 0.034784 | Ponce | 50 | 0.21081 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-31 | 0.017398 | Arecibo | 50 | 0.10545 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-31 | 0.022991 | Arecibo | 50 | 0.13934 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-31 | 0.021748 | Arecibo | 50 | 0.13181 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-31 | 0.022991 | Arecibo | 50 | 0.13934 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-29 | 0.02448 | Arecibo | 50 | 0.14836 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 3000 | JUNCOS TC to JUNCOS TC | 2026-07-28 | 0.031152 | Caguas | 50 | 0.1888 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 3000 | JUNCOS TC to JUNCOS TC | 2026-07-30 | 0.029478 | Caguas | 50 | 0.17865 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-27 | 0.018839 | Arecibo | 50 | 0.11418 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-27 | 0.019262 | Arecibo | 50 | 0.11674 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | BARCELONETA TC to BARCELONETA TC | 2026-07-27 | 0.060981 | Arecibo | 50 | 0.36958 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | BARCELONETA TC to BARCELONETA TC | 2026-07-27 | 0.0097511 | Arecibo | 50 | 0.059098 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | BARCELONETA TC to BARCELONETA TC | 2026-07-27 | 0.019158 | Arecibo | 50 | 0.11611 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-29 | 0.020505 | Arecibo | 50 | 0.12427 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-29 | 0.026719 | Arecibo | 50 | 0.16193 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-29 | 0.026918 | Arecibo | 50 | 0.16314 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 3100 | PALMER TC to PALMER TC | 2026-07-28 | 0.026296 | San Juan | 50 | 0.15937 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 3100 | PALMER TC to PALMER TC | 2026-07-28 | 0.025545 | San Juan | 50 | 0.15482 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | BARCELONETA TC to BARCELONETA TC | 2026-07-27 | 0.065875 | Arecibo | 50 | 0.39924 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | BARCELONETA TC to BARCELONETA TC | 2026-07-29 | 0.033554 | Arecibo | 50 | 0.20336 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 18400 | BARRANQUITAS TC to BARRANQUITAS TC | 2026-07-31 | 0.033388 | Caguas | 50 | 0.20235 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 18400 | BARRANQUITAS TC to BARRANQUITAS TC | 2026-07-31 | 0.034107 | Caguas | 50 | 0.20671 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50300 | Aguirre Power Plant to Aguirre Power Plant | 2026-07-31 | 0.25465 | Ponce | 100 | 3.0866 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50300 | Aguirre Power Plant to Aguirre Power Plant | 2026-07-27 | 0.15413 | Ponce | 100 | 1.8683 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50300 | Aguirre Power Plant to Aguirre Power Plant | 2026-07-27 | 0.24596 | Ponce | 100 | 2.9814 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50300 | Aguirre Power Plant to Aguirre Power Plant | 2026-07-28 | 0.34997 | Ponce | 100 | 4.2421 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-29 | 0.029204 | Arecibo | 50 | 0.177 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-29 | 0.027407 | Arecibo | 50 | 0.16611 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-29 | 0.027817 | Arecibo | 50 | 0.16859 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-29 | 0.028799 | Arecibo | 50 | 0.17454 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-29 | 0.024932 | Arecibo | 50 | 0.1511 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 4000 | to | 2026-07-28 | 0.047716 | Bayamon | 50 | 0.28919 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 4000 | to | 2026-07-27 | 0.051663 | Bayamon | 50 | 0.31311 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50300 | Aguirre Power Plant to Aguirre Power Plant | 2026-07-31 | 0.31624 | Ponce | 100 | 3.8333 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-29 | 0.044931 | Arecibo | 50 | 0.27231 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-29 | 0.0039519 | Arecibo | 50 | 0.023951 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-29 | 0.0038506 | Arecibo | 50 | 0.023337 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-29 | 0.02411 | Arecibo | 50 | 0.14612 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-29 | 0.025886 | Arecibo | 50 | 0.15688 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-29 | 0.030765 | Arecibo | 50 | 0.18646 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-29 | 0.029385 | Arecibo | 50 | 0.17809 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-29 | 0.028429 | Arecibo | 50 | 0.1723 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-29 | 0.029013 | Arecibo | 50 | 0.17584 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-29 | 0.023878 | Arecibo | 50 | 0.14472 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-29 | 0.025476 | Arecibo | 50 | 0.1544 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-29 | 0.030447 | Arecibo | 50 | 0.18453 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-29 | 0.028997 | Arecibo | 50 | 0.17574 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-29 | 0.029204 | Arecibo | 50 | 0.177 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-29 | 0.028695 | Arecibo | 50 | 0.17391 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-29 | 0.01611 | Arecibo | 50 | 0.097634 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-29 | 0.027325 | Arecibo | 50 | 0.1656 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-29 | 0.020955 | Arecibo | 50 | 0.127 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-29 | 0.022102 | Arecibo | 50 | 0.13395 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-29 | 0.018581 | Arecibo | 50 | 0.11261 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-29 | 0.035238 | Arecibo | 50 | 0.21356 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-29 | 0.032243 | Arecibo | 50 | 0.19541 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-29 | 0.025579 | Arecibo | 50 | 0.15502 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-29 | 0.03509 | Arecibo | 50 | 0.21267 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-29 | 0.035327 | Arecibo | 50 | 0.21411 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-29 | 0.0187 | Arecibo | 50 | 0.11333 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-29 | 0.017326 | Arecibo | 50 | 0.105 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-29 | 0.034607 | Arecibo | 50 | 0.20974 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-29 | 0.023646 | Arecibo | 50 | 0.14331 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-29 | 0.035843 | Arecibo | 50 | 0.21723 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-29 | 0.024334 | Arecibo | 50 | 0.14748 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-29 | 0.031513 | Arecibo | 50 | 0.19099 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-29 | 0.024984 | Arecibo | 50 | 0.15142 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-29 | 0.026912 | Arecibo | 50 | 0.1631 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-29 | 0.028641 | Arecibo | 50 | 0.17358 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-29 | 0.027818 | Arecibo | 50 | 0.16859 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 3100 | PALMER TC to PALMER TC | 2026-07-28 | 0.041455 | San Juan | 50 | 0.25124 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-29 | 0.022291 | Arecibo | 50 | 0.13509 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-29 | 0.029744 | Arecibo | 50 | 0.18027 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 3000 | JUNCOS TC to JUNCOS TC | 2026-07-30 | 0.028732 | Caguas | 50 | 0.17413 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-29 | 0.0099419 | Arecibo | 50 | 0.060254 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-29 | 0.050373 | Arecibo | 50 | 0.30529 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 3100 | PALMER TC to PALMER TC | 2026-07-27 | 0.04094 | San Juan | 50 | 0.24812 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-31 | 0.0094286 | Arecibo | 50 | 0.057143 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-29 | 0.036826 | Arecibo | 50 | 0.22319 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 3100 | PALMER TC to PALMER TC | 2026-07-28 | 0.038631 | San Juan | 50 | 0.23413 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-31 | 0.016156 | Arecibo | 50 | 0.097913 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37400 | Cambalache TC to Cambalache TC | 2026-07-29 | 0.20104 | Arecibo | 100 | 2.4368 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-29 | 0.037904 | Arecibo | 50 | 0.22972 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-31 | 0.022369 | Arecibo | 50 | 0.13557 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | BARCELONETA TC to BARCELONETA TC | 2026-07-27 | 0.035418 | Arecibo | 50 | 0.21466 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-29 | 0.037282 | Arecibo | 50 | 0.22595 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | BARCELONETA TC to BARCELONETA TC | 2026-07-28 | 0.03604 | Arecibo | 50 | 0.21842 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-29 | 0.042253 | Arecibo | 50 | 0.25608 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | BARCELONETA TC to BARCELONETA TC | 2026-07-31 | 0.050331 | Arecibo | 50 | 0.30504 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6900 | CAMBALACHE TC to CAMBALACHE TC | 2026-07-30 | 0.063613 | Arecibo | 50 | 0.38554 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | BARCELONETA TC to BARCELONETA TC | 2026-07-29 | 0.034923 | Arecibo | 50 | 0.21165 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | BARCELONETA TC to BARCELONETA TC | 2026-07-28 | 0.03289 | Arecibo | 50 | 0.19934 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | BARCELONETA TC to BARCELONETA TC | 2026-07-29 | 0.037053 | Arecibo | 50 | 0.22456 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | BARCELONETA TC to BARCELONETA TC | 2026-07-30 | 0.041053 | Arecibo | 50 | 0.24881 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | BARCELONETA TC to BARCELONETA TC | 2026-07-31 | 0.042726 | Arecibo | 50 | 0.25894 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | BARCELONETA TC to BARCELONETA TC | 2026-07-31 | 0.039358 | Arecibo | 50 | 0.23853 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | BARCELONETA TC to BARCELONETA TC | 2026-07-31 | 0.04832 | Arecibo | 50 | 0.29285 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | BARCELONETA TC to BARCELONETA TC | 2026-07-27 | 0.041619 | Arecibo | 50 | 0.25223 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | BARCELONETA TC to BARCELONETA TC | 2026-07-27 | 0.036208 | Arecibo | 50 | 0.21944 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37400 | Cambalache TC to Cambalache TC | 2026-07-29 | 0.12479 | Arecibo | 100 | 1.5126 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37400 | Cambalache TC to Cambalache TC | 2026-07-29 | 0.1609 | Arecibo | 100 | 1.9503 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 36100 | Dos Bocas Hydro Plant to Dos Bocas Hydro Plant | 2026-07-27 | 0.26607 | Arecibo | 100 | 3.2251 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 3000 | JUNCOS TC to JUNCOS TC | 2026-07-27 | 0.016951 | Caguas | 50 | 0.10273 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 3000 | JUNCOS TC to JUNCOS TC | 2026-07-30 | 0.032646 | Caguas | 50 | 0.19786 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50500 | Mayaguez TC to Mayaguez TC | 2026-07-30 | 0.092882 | Mayaguez | 100 | 1.1258 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37400 | Cambalache TC to Cambalache TC | 2026-07-29 | 0.18913 | Arecibo | 100 | 2.2925 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37400 | Cambalache TC to Cambalache TC | 2026-07-29 | 0.077609 | Arecibo | 100 | 0.94072 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37400 | Cambalache TC to Cambalache TC | 2026-07-29 | 0.090612 | Arecibo | 100 | 1.0983 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 36700 | San Sebastian TC to San Sebastian TC | 2026-07-29 | 0.077586 | Mayaguez | 100 | 0.94044 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 36700 | San Sebastian TC to San Sebastian TC | 2026-07-27 | 0.0908 | Mayaguez | 100 | 1.1006 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 36700 | San Sebastian TC to San Sebastian TC | 2026-07-29 | 0.2354 | Mayaguez | 100 | 2.8533 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 36100 | Dos Bocas Hydro Plant to Dos Bocas Hydro Plant | 2026-07-27 | 0.067055 | Arecibo | 100 | 0.81278 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 36400 | Ponce TC to Ponce TC | 2026-07-28 | 0.091095 | Arecibo | 100 | 1.1042 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 3000 | JUNCOS TC to JUNCOS TC | 2026-07-27 | 0.04368 | San Juan | 50 | 0.26473 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 36700 | San Sebastian TC to San Sebastian TC | 2026-07-27 | 0.08609 | Mayaguez | 100 | 1.0435 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 3400 | MONACILLOS TC to MONACILLOS TC | 2026-07-27 | 0.023155 | San Juan | 50 | 0.14033 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 3400 | MONACILLOS TC to MONACILLOS TC | 2026-07-27 | 0.0349 | San Juan | 50 | 0.21152 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2300 | ARECIBO SECT to ARECIBO SECT | 2026-07-27 | 0.14643 | Arecibo | 50 | 0.88748 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 3400 | MONACILLOS TC to MONACILLOS TC | 2026-07-27 | 0.03068 | San Juan | 50 | 0.18594 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 8900 | CENTRO MEDICO SECT to CENTRO MEDICO SECT | 2026-07-27 | 0.053133 | San Juan | 50 | 0.32202 | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 3400 | MONACILLOS TC to MONACILLOS TC | 2026-07-27 | 0.013034 | San Juan | 50 | 0.078997 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 8900 | CENTRO MEDICO SECT to CENTRO MEDICO SECT | 2026-07-27 | 0.025737 | San Juan | 50 | 0.15598 | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 3400 | MONACILLOS TC to MONACILLOS TC | 2026-07-27 | 0.016816 | San Juan | 50 | 0.10191 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 8900 | CENTRO MEDICO SECT to CENTRO MEDICO SECT | 2026-07-27 | 0.053133 | San Juan | 50 | 0.32202 | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 36700 | San Sebastian TC to San Sebastian TC | 2026-07-28 | 0.028037 | Mayaguez | 100 | 0.33985 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 36700 | San Sebastian TC to San Sebastian TC | 2026-07-28 | 0.1169 | Mayaguez | 100 | 1.417 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 36700 | San Sebastian TC to San Sebastian TC | 2026-07-28 | 0.12744 | Mayaguez | 100 | 1.5447 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 3400 | MONACILLOS TC to MONACILLOS TC | 2026-07-30 | 0.021484 | Bayamon | 50 | 0.13021 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 3400 | MONACILLOS TC to MONACILLOS TC | 2026-07-30 | 0.02309 | San Juan | 50 | 0.13994 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 38300 | Monacillos TC to Monacillos TC | 2026-07-28 | 0.027844 | Bayamon | 100 | 0.3375 | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 3400 | MONACILLOS TC to MONACILLOS TC | 2026-07-30 | 0.034188 | San Juan | 50 | 0.2072 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 3400 | MONACILLOS TC to MONACILLOS TC | 2026-07-30 | 0.024027 | San Juan | 50 | 0.14562 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 3400 | MONACILLOS TC to MONACILLOS TC | 2026-07-30 | 0.019516 | San Juan | 50 | 0.11828 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 3400 | MONACILLOS TC to MONACILLOS TC | 2026-07-30 | 0.023651 | San Juan | 50 | 0.14334 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 3400 | MONACILLOS TC to MONACILLOS TC | 2026-07-29 | 0.052543 | Bayamon | 50 | 0.31844 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 3400 | MONACILLOS TC to MONACILLOS TC | 2026-07-30 | 0.053444 | Bayamon | 50 | 0.3239 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 3400 | MONACILLOS TC to MONACILLOS TC | 2026-07-30 | 0.027554 | Bayamon | 50 | 0.16699 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37400 | Cambalache TC to Cambalache TC | 2026-07-28 | 0.081179 | Arecibo | 100 | 0.98399 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37400 | BAYAMON TC to BAYAMON TC | 2026-07-29 | 0.1714 | Arecibo | 100 | 2.0776 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 36400 | Ponce TC to Ponce TC | 2026-07-28 | 0.1766 | Arecibo | 100 | 2.1407 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50200 | Costa Sur Power Plant to Costa Sur Power Plant | 2026-07-28 | 0.33592 | Bayamon | 100 | 4.0717 | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50500 | Mayaguez TC to Mayaguez TC | 2026-07-28 | 0.08694 | Mayaguez | 100 | 1.0538 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 36700 | San Sebastian TC to San Sebastian TC | 2026-07-28 | 0.15597 | Mayaguez | 100 | 1.8906 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 36700 | San Sebastian TC to San Sebastian TC | 2026-07-28 | 0.13459 | Mayaguez | 100 | 1.6314 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 36700 | San Sebastian TC to San Sebastian TC | 2026-07-29 | 0.11702 | Mayaguez | 100 | 1.4185 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 7900 | JUANA DIAZ TC to JUANA DIAZ TC | 2026-07-30 | 0.037113 | Ponce | 50 | 0.22493 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 7900 | JUANA DIAZ TC to JUANA DIAZ TC | 2026-07-29 | 0.1193 | Ponce | 50 | 0.72305 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 7900 | JUANA DIAZ TC to JUANA DIAZ TC | 2026-07-29 | 0.070215 | Ponce | 50 | 0.42555 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2600 | SAN SEBASTIAN TC to SAN SEBASTIAN TC | 2026-07-29 | 0.077801 | Mayaguez | 50 | 0.47152 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 36700 | San Sebastian TC to San Sebastian TC | 2026-07-29 | 0.059916 | Mayaguez | 100 | 0.72625 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2000 | MAYAGUEZ TC to MAYAGUEZ TC | 2026-07-29 | 0.13549 | Mayaguez | 50 | 0.82117 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2600 | QUEBRADILLAS TO to QUEBRADILLAS TO | 2026-07-29 | 0.11475 | Arecibo | 50 | 0.69548 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50500 | Mayaguez TC to Mayaguez TC | 2026-07-29 | 0.14166 | Mayaguez | 100 | 1.7171 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2600 | SAN SEBASTIAN TC to SAN SEBASTIAN TC | 2026-07-29 | 0.087357 | Mayaguez | 50 | 0.52943 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 300 | JUANA DIAZ TC to JUANA DIAZ TC | 2026-07-29 | 0.036986 | Ponce | 50 | 0.22416 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 18200 | HATO REY TC to HATO REY TC | 2026-07-30 | 0.23383 | San Juan | 50 | 1.4171 | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 36400 | Ponce TC to Ponce TC | 2026-07-29 | 0.065609 | Arecibo | 100 | 0.79526 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50500 | Mayaguez TC to Mayaguez TC | 2026-07-29 | 0.19742 | Mayaguez | 100 | 2.3929 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2600 | QUEBRADILLAS TO to QUEBRADILLAS TO | 2026-07-30 | 0.16552 | Arecibo | 50 | 1.0031 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50500 | Mayaguez TC to Mayaguez TC | 2026-07-29 | 0.16824 | Mayaguez | 100 | 2.0392 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 1500 | MAYAGUEZ TC to MAYAGUEZ TC | 2026-07-29 | 0.085935 | Mayaguez | 50 | 0.52082 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 300 | JUANA DIAZ TC to JUANA DIAZ TC | 2026-07-29 | 0.047347 | Ponce | 50 | 0.28695 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 36700 | San Sebastian TC to San Sebastian TC | 2026-07-29 | 0.14506 | Mayaguez | 100 | 1.7583 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 36700 | San Sebastian TC to San Sebastian TC | 2026-07-30 | 0.078036 | Mayaguez | 100 | 0.94589 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 36700 | San Sebastian TC to San Sebastian TC | 2026-07-30 | 0.12078 | Mayaguez | 100 | 1.464 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 36700 | San Sebastian TC to San Sebastian TC | 2026-07-29 | 0.075588 | Mayaguez | 100 | 0.91622 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 36700 | San Sebastian TC to San Sebastian TC | 2026-07-29 | 0.15742 | Mayaguez | 100 | 1.9081 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 7900 | JUANA DIAZ TC to JUANA DIAZ TC | 2026-07-29 | 0.035523 | Ponce | 50 | 0.21529 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 300 | JUANA DIAZ TC to JUANA DIAZ TC | 2026-07-29 | 0.085749 | Ponce | 50 | 0.51969 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 38300 | Monacillos TC to Monacillos TC | 2026-07-29 | 0.081925 | San Juan | 100 | 0.99303 | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2600 | QUEBRADILLAS TO to QUEBRADILLAS TO | 2026-07-29 | 0.20756 | Arecibo | 50 | 1.2579 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 7900 | JUANA DIAZ TC to JUANA DIAZ TC | 2026-07-30 | 0.03071 | Ponce | 50 | 0.18612 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 6500 | TORO NEGRO 1 HP to TORO NEGRO 1 HP | 2026-07-29 | 0.035706 | Caguas | 50 | 0.2164 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 300 | JUANA DIAZ TC to JUANA DIAZ TC | 2026-07-30 | 0.045115 | Ponce | 50 | 0.27343 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 300 | JUANA DIAZ TC to JUANA DIAZ TC | 2026-07-30 | 0.036986 | Ponce | 50 | 0.22416 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2100 | DOS BOCAS HP to DOS BOCAS HP | 2026-07-30 | 0.092999 | Arecibo | 50 | 0.56363 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 38900 | Berwind TC to Berwind TC | 2026-07-30 | 0.066579 | San Juan | 100 | 0.80702 | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2100 | DOS BOCAS HP to DOS BOCAS HP | 2026-07-30 | 0.046922 | Arecibo | 50 | 0.28437 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37400 | Cambalache TC to Cambalache TC | 2026-07-30 | 0.091826 | Arecibo | 100 | 1.113 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 300 | JUANA DIAZ TC to JUANA DIAZ TC | 2026-07-30 | 0.047716 | Ponce | 50 | 0.28919 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 1500 | MAYAGUEZ TC to MAYAGUEZ TC | 2026-07-30 | 0.1464 | Mayaguez | 50 | 0.88727 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 1500 | MAYAGUEZ TC to MAYAGUEZ TC | 2026-07-30 | 0.11641 | Mayaguez | 50 | 0.7055 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50500 | Mayaguez TC to Mayaguez TC | 2026-07-30 | 0.19928 | Mayaguez | 100 | 2.4156 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2600 | SAN SEBASTIAN TC to SAN SEBASTIAN TC | 2026-07-30 | 0.26341 | Mayaguez | 50 | 1.5964 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50500 | Mayaguez TC to Mayaguez TC | 2026-07-30 | 0.14849 | Mayaguez | 100 | 1.7999 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 38900 | Berwind TC to Berwind TC | 2026-07-30 | 0.04027 | San Juan | 100 | 0.48813 | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 7900 | JUANA DIAZ TC to JUANA DIAZ TC | 2026-07-31 | 0.039146 | Ponce | 50 | 0.23725 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2100 | DOS BOCAS HP to DOS BOCAS HP | 2026-07-30 | 0.062023 | Arecibo | 50 | 0.3759 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2100 | DOS BOCAS HP to DOS BOCAS HP | 2026-07-31 | 0.1063 | Arecibo | 50 | 0.64425 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50500 | Mayaguez TC to Mayaguez TC | 2026-07-30 | 0.089864 | Mayaguez | 100 | 1.0893 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | BARCELONETA TC to BARCELONETA TC | 2026-07-30 | 0.028328 | Arecibo | 50 | 0.17169 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 7300 | BALDRICH SECT to BALDRICH SECT | 2026-07-30 | 0.04971 | San Juan | 50 | 0.30127 | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 10100 | LAS LOMAS SECT to LAS LOMAS SECT | 2026-07-28 | 0.019884 | San Juan | 50 | 0.12051 | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50200 | Manati TC to Manati TC | 2026-07-30 | 0.21189 | Bayamon | 100 | 2.5684 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50900 | AGUIRRE SP to AGUIRRE SP | 2026-07-29 | 0.47268 | Caguas | 100 | 5.7294 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 51000 | AGUIRRE SP to AGUIRRE SP | 2026-07-29 | 0.47413 | Caguas | 100 | 5.747 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 36200 | FAJARDO TC to FAJARDO TC | 2026-07-29 | 0.11586 | Caguas | 100 | 1.4043 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 36200 | FAJARDO TC to FAJARDO TC | 2026-07-29 | 0.033671 | Caguas | 100 | 0.40813 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 36200 | FAJARDO TC to FAJARDO TC | 2026-07-29 | 0.11618 | Caguas | 100 | 1.4082 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 1500 | MAYAGUEZ TC to MAYAGUEZ TC | 2026-07-30 | 0.10971 | Mayaguez | 50 | 0.66492 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 8900 | CENTRO MEDICO SECT to CENTRO MEDICO SECT | 2026-07-30 | 0.028856 | San Juan | 50 | 0.17488 | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | BARCELONETA TC to BARCELONETA TC | 2026-07-30 | 0.036612 | Arecibo | 50 | 0.22189 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | BARCELONETA TC to BARCELONETA TC | 2026-07-30 | 0.039092 | Arecibo | 50 | 0.23692 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2200 | BARCELONETA TC to BARCELONETA TC | 2026-07-30 | 0.048856 | Arecibo | 50 | 0.2961 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2100 | DOS BOCAS HP to DOS BOCAS HP | 2026-07-31 | 0.072922 | Arecibo | 50 | 0.44195 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2100 | DOS BOCAS HP to DOS BOCAS HP | 2026-07-31 | 0.027127 | Arecibo | 50 | 0.1644 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50500 | Mayaguez TC to Mayaguez TC | 2026-07-31 | 0.09869 | Mayaguez | 100 | 1.1962 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 1500 | MAYAGUEZ TC to MAYAGUEZ TC | 2026-07-31 | 0.16753 | Mayaguez | 50 | 1.0153 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 1500 | MAYAGUEZ GP to MAYAGUEZ GP | 2026-07-31 | 0.1464 | Mayaguez | 50 | 0.88727 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2300 | DOS BOCAS HP to DOS BOCAS HP | 2026-07-31 | 0.073409 | Arecibo | 50 | 0.44491 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 2100 | DOS BOCAS HP to DOS BOCAS HP | 2026-07-31 | 0.077378 | Arecibo | 50 | 0.46896 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50800 | SABANA LLANA TC to SABANA LLANA TC | 2026-07-31 | 0.11867 | Caguas | 100 | 1.4384 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50800 | YABUCOA TC to YABUCOA TC | 2026-07-31 | 0.074315 | Caguas | 100 | 0.90079 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50800 | SABANA LLANA TC to SABANA LLANA TC | 2026-07-31 | 0.10824 | Caguas | 100 | 1.312 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50800 | SABANA LLANA TC to SABANA LLANA TC | 2026-07-31 | 0.099527 | Caguas | 100 | 1.2064 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50800 | SABANA LLANA TC to SABANA LLANA TC | 2026-07-31 | 0.060348 | Caguas | 100 | 0.73149 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 38 | 18400 | BARRANQUITAS TC to BARRANQUITAS TC | 2026-07-31 | 0.027433 | Caguas | 50 | 0.16626 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 115 | 37100 | Acacias TC to Acacias TC | 2026-07-31 | 0.134 | Mayaguez | 100 | 1.6243 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 230 | 50500 | Mayaguez TC to Mayaguez TC | 2026-07-31 | 0.26419 | Mayaguez | 100 | 3.2023 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
956357 | 38 | 1900 | Dos Bocas HP to Dos Bocas HP | 2026-07-17 | 0.70341 | Mayagüez | 50 | 4.2631 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
956357 | 38 | 1900 | Dos Bocas HP to Dos Bocas HP | 2026-07-31 | 0.65675 | Mayagüez | 50 | 3.9803 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
956357 | 38 | 1900 | Dos Bocas HP to Dos Bocas HP | 2026-07-21 | 0.44326 | Mayagüez | 50 | 2.6864 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
956357 | 38 | 1900 | Dos Bocas HP to Dos Bocas HP | 2026-07-30 | 0.38545 | Mayagüez | 50 | 2.3361 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
956357 | 38 | 1900 | Dos Bocas HP to Dos Bocas HP | 2026-07-23 | 0.36215 | Mayagüez | 50 | 2.1948 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
956357 | 38 | 1900 | Dos Bocas HP to Dos Bocas HP | 2026-07-29 | 0.34606 | Mayagüez | 50 | 2.0973 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
956345 | 38 | 2400 | Dos Bocas HP to Dos Bocas HP | 2026-07-13 | 0.26633 | Arecibo | 50 | 1.6141 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
956357 | 38 | 1900 | Dos Bocas HP to Dos Bocas HP | 2026-07-27 | 0.25272 | Mayagüez | 50 | 1.5316 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
956357 | 38 | 1900 | Dos Bocas HP to Dos Bocas HP | 2026-07-22 | 0.20319 | Mayagüez | 50 | 1.2315 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
956357 | 38 | 1900 | Dos Bocas HP to Dos Bocas HP | 2026-07-28 | 0.20262 | Mayagüez | 50 | 1.228 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
956345 | 38 | 2400 | Dos Bocas HP to Dos Bocas HP | 2026-07-10 | 0.17984 | Arecibo | 50 | 1.0899 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
956357 | 38 | 1900 | Dos Bocas HP to Dos Bocas HP | 2026-07-20 | 0.17436 | Mayagüez | 50 | 1.0567 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
956357 | 38 | 1900 | Dos Bocas HP to Dos Bocas HP | 2026-07-20 | 0.17033 | Mayagüez | 50 | 1.0323 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
956345 | 38 | 2400 | Dos Bocas HP to Dos Bocas HP | 2026-07-08 | 0.16399 | Arecibo | 50 | 0.99388 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
956345 | 38 | 2400 | Dos Bocas HP to Dos Bocas HP | 2026-07-16 | 0.13878 | Arecibo | 50 | 0.84109 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
956345 | 38 | 2400 | Dos Bocas HP to Dos Bocas HP | 2026-07-06 | 0.12779 | Arecibo | 50 | 0.77448 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
956357 | 38 | 1900 | Dos Bocas HP to Dos Bocas HP | 2026-07-15 | 0.12683 | Mayagüez | 50 | 0.76867 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
956345 | 38 | 2400 | Dos Bocas HP to Dos Bocas HP | 2026-07-07 | 0.12156 | Arecibo | 50 | 0.73673 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
956357 | 38 | 1900 | Dos Bocas HP to Dos Bocas HP | 2026-07-24 | 0.11413 | Mayagüez | 50 | 0.6917 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
956345 | 38 | 2400 | Dos Bocas HP to Dos Bocas HP | 2026-07-17 | 0.05756 | Arecibo | 50 | 0.34885 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
956349 | 115 | 36800 | Canovanas TC to Canovanas TC | 2026-07-07 | 0.0554 | San Juan | 100 | 0.67152 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
956357 | 38 | 1900 | Dos Bocas HP to Dos Bocas HP | 2026-07-13 | 0.04755 | Mayagüez | 50 | 0.28818 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
956345 | 38 | 2400 | Dos Bocas HP to Dos Bocas HP | 2026-07-21 | 0.03515 | Arecibo | 50 | 0.21303 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
956345 | 38 | 2400 | Dos Bocas HP to Dos Bocas HP | 2026-07-02 | 0.03448 | Arecibo | 50 | 0.20897 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
956345 | 38 | 2400 | Dos Bocas HP to Dos Bocas HP | 2026-07-09 | 0.03239 | Arecibo | 50 | 0.1963 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
956345 | 38 | 2400 | Dos Bocas HP to Dos Bocas HP | 2026-07-01 | 0.0314 | Arecibo | 50 | 0.1903 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
956342 | 115 | 36400 | Ponce TC to Ponce TC | 2026-07-07 | 0.03131 | Arecibo | 100 | 0.37952 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
956345 | 38 | 2400 | Dos Bocas HP to Dos Bocas HP | 2026-07-23 | 0.02036 | Arecibo | 50 | 0.12339 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
956357 | 38 | 1900 | Dos Bocas HP to Dos Bocas HP | 2026-07-16 | 0.01596 | Mayagüez | 50 | 0.096727 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
956345 | 38 | 2400 | Dos Bocas HP to Dos Bocas HP | 2026-07-28 | 0.00899 | Arecibo | 50 | 0.054485 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
956345 | 38 | 2400 | Dos Bocas HP to Dos Bocas HP | 2026-07-14 | 0.00818 | Arecibo | 50 | 0.049576 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
n/a | 38 | 200 | SANTA ISABEL SECT - SALINAS SECT | 2026-08-01 | 0.057166 | Ponce | 50 | 0.34646 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 200 | SANTA ISABEL SECT - SALINAS SECT | 2026-08-01 | 0.033798 | Ponce | 50 | 0.20483 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50300 | Aguirre Power Plant - Costa Sur Power Plant | 2026-08-01 | 0.16736 | Ponce | 100 | 2.0286 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50300 | Aguirre Power Plant - Costa Sur Power Plant | 2026-08-01 | 0.2426 | Ponce | 100 | 2.9406 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | BARCELONETA TC - MANATI TC | 2026-08-01 | 0.055302 | Arecibo | 50 | 0.33516 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2100 | DOS BOCAS HP - QUEBRADILLAS TO | 2026-08-01 | 0.037284 | Arecibo | 50 | 0.22596 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2100 | DOS BOCAS HP - QUEBRADILLAS TO | 2026-08-01 | 0.06338 | Arecibo | 50 | 0.38412 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2100 | DOS BOCAS HP - QUEBRADILLAS TO | 2026-08-01 | 0.090611 | Arecibo | 50 | 0.54916 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50500 | Mayaguez TC - Mora TC | 2026-08-01 | 0.17925 | Mayaguez | 100 | 2.1727 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2600 | SAN SEBASTIAN TC | 2026-08-01 | 0.16527 | Mayaguez | 50 | 1.0016 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37400 | BAYAMON TC - CAMBALACHE TC | 2026-08-01 | 0.14742 | Arecibo | 100 | 1.7869 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2600 | SAN SEBASTIAN TC | 2026-08-01 | 0.17192 | Mayaguez | 50 | 1.0419 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 6500 | TORO NEGRO 1 HP - BARRANQUITAS TC | 2026-08-01 | 0.35307 | Caguas | 50 | 2.1398 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 39000 | MONACILLOS TC - PONCE TC | 2026-08-01 | 0.17297 | Caguas | 100 | 2.0966 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 39000 | MONACILLOS TC - PONCE TC | 2026-08-01 | 0.21566 | Caguas | 100 | 2.614 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 39000 | MONACILLOS TC - PONCE TC | 2026-08-01 | 0.52841 | Caguas | 100 | 6.405 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36900 | Costa Sur Power Plant - Canas TC | 2026-08-01 | 0.12846 | Ponce | 100 | 1.5571 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-04 | 0.034797 | Arecibo | 50 | 0.21089 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-07 | 0.042253 | Arecibo | 50 | 0.25608 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-07 | 0.035579 | Arecibo | 50 | 0.21563 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 200 |  | 2026-08-08 | 0.057787 | Ponce | 50 | 0.35023 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2900 |  | 2026-08-07 | 0.026956 | Ponce | 50 | 0.16337 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 4800 |  | 2026-08-05 | 0.13859 | Ponce | 50 | 0.83997 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 4800 |  | 2026-08-05 | 0.16237 | Ponce | 50 | 0.98404 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-04 | 0.034175 | Arecibo | 50 | 0.20712 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-04 | 0.030814 | Arecibo | 50 | 0.18675 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-04 | 0.033841 | Arecibo | 50 | 0.2051 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-04 | 0.032528 | Arecibo | 50 | 0.19714 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-04 | 0.034416 | Arecibo | 50 | 0.20858 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-03 | 0.031069 | Arecibo | 50 | 0.18829 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-03 | 0.029826 | Arecibo | 50 | 0.18076 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-03 | 0.029826 | Arecibo | 50 | 0.18076 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-03 | 0.032933 | Arecibo | 50 | 0.19959 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-03 | 0.031069 | Arecibo | 50 | 0.18829 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-04 | 0.033554 | Arecibo | 50 | 0.20336 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-04 | 0.048467 | Arecibo | 50 | 0.29374 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-04 | 0.035418 | Arecibo | 50 | 0.21466 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-05 | 0.039146 | Arecibo | 50 | 0.23725 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-05 | 0.044117 | Arecibo | 50 | 0.26738 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-07 | 0.040535 | Arecibo | 50 | 0.24567 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-07 | 0.035579 | Arecibo | 50 | 0.21563 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-07 | 0.03169 | Arecibo | 50 | 0.19206 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 6900 |  | 2026-08-04 | 0.017668 | Arecibo | 50 | 0.10708 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-07 | 0.040389 | Arecibo | 50 | 0.24478 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 6900 |  | 2026-08-04 | 0.025476 | Arecibo | 50 | 0.1544 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 6900 |  | 2026-08-03 | 0.016777 | Arecibo | 50 | 0.10168 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 6900 |  | 2026-08-04 | 0.024234 | Arecibo | 50 | 0.14687 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 6900 |  | 2026-08-03 | 0.032933 | Arecibo | 50 | 0.19959 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 6900 |  | 2026-08-04 | 0.023073 | Arecibo | 50 | 0.13983 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 6900 |  | 2026-08-03 | 0.019335 | Arecibo | 50 | 0.11718 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50300 | COSTA SUR SP | 2026-08-03 | 0.046623 | Ponce | 100 | 0.56513 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50300 | COSTA SUR SP | 2026-08-03 | 0.45552 | Ponce | 100 | 5.5215 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50300 | COSTA SUR SP | 2026-08-06 | 0.27892 | Ponce | 100 | 3.3808 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50300 |  | 2026-08-07 | 0.18762 | Ponce | 100 | 2.2741 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-07 | 0.032311 | Arecibo | 50 | 0.19583 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-07 | 0.038525 | Arecibo | 50 | 0.23348 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-08 | 0.047224 | Arecibo | 50 | 0.28621 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-04 | 0.041632 | Arecibo | 50 | 0.25231 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-04 | 0.034797 | Arecibo | 50 | 0.21089 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-03 | 0.044117 | Arecibo | 50 | 0.26738 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-03 | 0.039412 | Arecibo | 50 | 0.23886 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-04 | 0.041529 | Arecibo | 50 | 0.25169 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-03 | 0.035459 | Arecibo | 50 | 0.2149 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-04 | 0.045676 | Arecibo | 50 | 0.27683 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-03 | 0.044614 | Arecibo | 50 | 0.27039 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-05 | 0.027028 | Arecibo | 50 | 0.16381 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-05 | 0.029533 | Arecibo | 50 | 0.17899 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-05 | 0.017891 | Arecibo | 50 | 0.10843 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-05 | 0.028955 | Arecibo | 50 | 0.17549 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-05 | 0.033706 | Arecibo | 50 | 0.20428 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-05 | 0.028245 | Arecibo | 50 | 0.17118 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-05 | 0.038648 | Arecibo | 50 | 0.23423 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-05 | 0.020569 | Arecibo | 50 | 0.12466 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-05 | 0.016729 | Arecibo | 50 | 0.10139 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-05 | 0.024594 | Arecibo | 50 | 0.14905 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-05 | 0.020684 | Arecibo | 50 | 0.12536 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-05 | 0.020894 | Arecibo | 50 | 0.12663 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-05 | 0.021845 | Arecibo | 50 | 0.1324 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3100 |  | 2026-08-06 | 0.043928 | San Juan | 50 | 0.26623 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-05 | 0.024763 | Arecibo | 50 | 0.15008 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-08 | 0.020035 | Arecibo | 50 | 0.12143 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3100 |  | 2026-08-06 | 0.041712 | San Juan | 50 | 0.2528 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36100 | DOS BOCAS HP | 2026-08-05 | 0.11449 | Arecibo | 100 | 1.3878 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 7900 |  | 2026-08-05 | 0.054121 | Ponce | 50 | 0.32801 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37400 |  | 2026-08-03 | 0.14325 | Arecibo | 100 | 1.7363 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37400 |  | 2026-08-07 | 0.087695 | Arecibo | 100 | 1.063 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 40800 | MANATI TC | 2026-08-03 | 0.030146 | Arecibo | 100 | 0.36541 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36700 | SAN SEBASTIAN TC | 2026-08-08 | 0.27083 | Mayaguez | 100 | 3.2828 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36700 | SAN SEBASTIAN TC | 2026-08-07 | 0.22814 | Mayaguez | 100 | 2.7654 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-07 | 0.042393 | Arecibo | 50 | 0.25693 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-07 | 0.043866 | Arecibo | 50 | 0.26586 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-06 | 0.02857 | Arecibo | 50 | 0.17315 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-06 | 0.033831 | Arecibo | 50 | 0.20504 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-06 | 0.041662 | Arecibo | 50 | 0.2525 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50900 | BAYAMON TC - BAYAMON TC | 2026-08-08 | 0.16336 | Bayamón | 100 | 1.9801 | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50900 | BAYAMON TC - BAYAMON TC | 2026-08-08 | 0.16389 | Bayamón | 100 | 1.9865 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50900 | BAYAMON TC - BAYAMON TC | 2026-08-08 | 0.16389 | Bayamón | 100 | 1.9865 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36700 |  | 2026-08-04 | 0.10341 | Mayaguez | 100 | 1.2534 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36700 | SAN SEBASTIAN TC | 2026-08-04 | 0.10341 | Mayaguez | 100 | 1.2534 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37400 |  | 2026-08-03 | 0.085226 | Arecibo | 100 | 1.033 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 1500 | MAYAGUEZ GP | 2026-08-05 | 0.16652 | Mayaguez | 50 | 1.0092 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36700 |  | 2026-08-08 | 0.14985 | Mayaguez | 100 | 1.8163 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36700 | SAN SEBASTIAN TC | 2026-08-08 | 0.14985 | Mayaguez | 100 | 1.8163 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37400 |  | 2026-08-03 | 0.13984 | Arecibo | 100 | 1.6951 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-04 | 0.050853 | Arecibo | 50 | 0.3082 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-04 | 0.040931 | Arecibo | 50 | 0.24807 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-06 | 0.038011 | Arecibo | 50 | 0.23037 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-06 | 0.037925 | Arecibo | 50 | 0.22985 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2100 | DOS BOCAS HP - QUEBRADILLAS TO | 2026-08-04 | 0.025927 | Arecibo | 50 | 0.15713 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50200 | COSTA SUR SP | 2026-08-02 | 0.37677 | Ponce | 100 | 4.5669 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 8500 | AIBONITO TO - CAYEY TC | 2026-08-03 | 0.20684 | Caguas | 50 | 1.2536 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37400 | BAYAMON TC - CAMBALACHE TC | 2026-08-03 | 0.30749 | Arecibo | 100 | 3.7271 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37400 |  | 2026-08-04 | 0.087158 | Arecibo | 100 | 1.0565 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37400 |  | 2026-08-04 | 0.093557 | Arecibo | 100 | 1.134 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37400 |  | 2026-08-04 | 0.049352 | Arecibo | 100 | 0.59821 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37400 | BAYAMON TC - CAMBALACHE TC | 2026-08-03 | 0.14742 | Arecibo | 100 | 1.7869 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37400 | BAYAMON TC - CAMBALACHE TC | 2026-08-03 | 0.04215 | Arecibo | 100 | 0.51091 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-05 | 0.081586 | Arecibo | 50 | 0.49446 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37500 |  | 2026-08-05 | 0.030476 | Bayamón | 100 | 0.3694 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37500 |  | 2026-08-05 | 0.032732 | Bayamón | 100 | 0.39675 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 38200 |  | 2026-08-05 | 0.031553 | Bayamón | 100 | 0.38246 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37400 | BAYAMON TC - CAMBALACHE TC | 2026-08-03 | 0.074739 | Arecibo | 100 | 0.90593 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37500 |  | 2026-08-05 | 0.031063 | Bayamón | 100 | 0.37652 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37400 | BAYAMON TC - CAMBALACHE TC | 2026-08-04 | 0.14742 | Arecibo | 100 | 1.7869 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37400 | BAYAMON TC - CAMBALACHE TC | 2026-08-03 | 0.060717 | Arecibo | 100 | 0.73596 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37400 | BAYAMON TC - CAMBALACHE TC | 2026-08-03 | 0.45271 | Arecibo | 100 | 5.4874 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2600 | SAN SEBASTIAN TC | 2026-08-03 | 0.014447 | Mayaguez | 50 | 0.087557 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50500 | AGUADILLA HOSPITAL DISTRITO TO | 2026-08-03 | 0.14603 | Mayaguez | 100 | 1.77 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37400 | BARCELONETA TC - CAMBALACHE TC | 2026-08-03 | 0.08597 | Arecibo | 100 | 1.0421 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50500 | AGUADILLA HOSPITAL DISTRITO TO | 2026-08-03 | 0.10697 | Mayaguez | 100 | 1.2966 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50300 | COSTA SUR SP | 2026-08-05 | 0.2426 | Ponce | 100 | 2.9406 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36700 |  | 2026-08-04 | 0.088177 | Mayaguez | 100 | 1.0688 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36700 | SAN SEBASTIAN TC - MAYAGUEZ TC | 2026-08-04 | 0.088177 | Mayaguez | 100 | 1.0688 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50500 | MAYAGUEZ TC - AGUADILLA HOSPITAL DISTRITO TO | 2026-08-05 | 0.14027 | Mayaguez | 100 | 1.7003 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37100 | ACACIAS TC | 2026-08-04 | 0.35 | Mayaguez | 100 | 4.2424 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37100 | ACACIAS TC | 2026-08-04 | 0.22546 | Mayaguez | 100 | 2.7328 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 18400 |  | 2026-08-04 | 0.044096 | Caguas | 50 | 0.26725 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 6900 |  | 2026-08-04 | 0.039146 | Arecibo | 50 | 0.23725 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3100 |  | 2026-08-05 | 0.044231 | San Juan | 50 | 0.26807 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3100 |  | 2026-08-04 | 0.039523 | San Juan | 50 | 0.23953 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3100 |  | 2026-08-04 | 0.042538 | San Juan | 50 | 0.25781 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37400 | BAYAMON TC - CAMBALACHE TC | 2026-08-04 | 0.14742 | Arecibo | 100 | 1.7869 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37400 |  | 2026-08-05 | 0.13403 | Arecibo | 100 | 1.6246 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37400 |  | 2026-08-04 | 0.095305 | Arecibo | 100 | 1.1552 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37400 | BAYAMON TC - CAMBALACHE TC | 2026-08-04 | 0.063898 | Arecibo | 100 | 0.77452 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37400 |  | 2026-08-04 | 0.092028 | Arecibo | 100 | 1.1155 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37400 | BAYAMON TC - CAMBALACHE TC | 2026-08-04 | 0.047139 | Arecibo | 100 | 0.57138 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2300 |  | 2026-08-05 | 0.099365 | Arecibo | 50 | 0.60221 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 18400 |  | 2026-08-04 | 0.044954 | Caguas | 50 | 0.27245 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3100 |  | 2026-08-05 | 0.026651 | San Juan | 50 | 0.16152 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3100 |  | 2026-08-05 | 0.047437 | San Juan | 50 | 0.2875 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3100 |  | 2026-08-07 | 0.05123 | San Juan | 50 | 0.31049 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3400 |  | 2026-08-04 | 0.044438 | San Juan | 50 | 0.26932 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37400 | BAYAMON TC - CAMBALACHE TC | 2026-08-05 | 0.10763 | Arecibo | 100 | 1.3045 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37400 | BAYAMON TC - CAMBALACHE TC | 2026-08-06 | 0.13744 | Arecibo | 100 | 1.666 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3400 |  | 2026-08-04 | 0.018248 | San Juan | 50 | 0.11059 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3100 |  | 2026-08-05 | 0.024075 | San Juan | 50 | 0.14591 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3100 |  | 2026-08-05 | 0.048477 | San Juan | 50 | 0.2938 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3100 |  | 2026-08-05 | 0.028016 | San Juan | 50 | 0.16979 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3400 |  | 2026-08-04 | 0.012575 | San Juan | 50 | 0.07621 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3400 |  | 2026-08-04 | 0.014383 | San Juan | 50 | 0.087169 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50500 | MAYAGUEZ TC | 2026-08-04 | 0.11701 | Mayaguez | 100 | 1.4184 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3400 |  | 2026-08-04 | 0.031951 | San Juan | 50 | 0.19364 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37100 | ACACIAS TC | 2026-08-04 | 0.134 | Mayaguez | 100 | 1.6243 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37100 | ACACIAS TC - SAN GERMAN TC | 2026-08-04 | 0.18802 | Mayaguez | 100 | 2.279 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3400 |  | 2026-08-04 | 0.028963 | San Juan | 50 | 0.17554 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 40600 |  | 2026-08-04 | 0.39489 | San Juan | 100 | 4.7865 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 13200 |  | 2026-08-03 | 0.020849 | Bayamón | 50 | 0.12636 | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36700 |  | 2026-08-04 | 0.12054 | Mayaguez | 100 | 1.4611 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36700 | SAN SEBASTIAN TC | 2026-08-04 | 0.12054 | Mayaguez | 100 | 1.4611 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 38900 |  | 2026-08-04 | 0.0466 | San Juan | 100 | 0.56485 | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 1500 | MAYAGUEZ GP | 2026-08-05 | 0.24774 | Mayaguez | 50 | 1.5015 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 1500 | MAYAGUEZ GP | 2026-08-05 | 0.16652 | Mayaguez | 50 | 1.0092 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50500 | MAYAGUEZ TC - AGUADILLA HOSPITAL DISTRITO TO | 2026-08-05 | 0.14027 | Mayaguez | 100 | 1.7003 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50500 | MAYAGUEZ TC | 2026-08-05 | 0.09869 | Mayaguez | 100 | 1.1962 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36700 | SAN SEBASTIAN TC - MAYAGUEZ TC | 2026-08-05 | 0.20063 | Mayaguez | 100 | 2.4319 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36700 |  | 2026-08-05 | 0.11702 | Mayaguez | 100 | 1.4185 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-05 | 0.047558 | Arecibo | 50 | 0.28823 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37400 |  | 2026-08-05 | 0.13727 | Arecibo | 100 | 1.6639 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 7800 |  | 2026-08-05 | 0.057964 | Bayamón | 50 | 0.3513 | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37400 |  | 2026-08-05 | 0.083413 | Arecibo | 100 | 1.0111 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 4800 |  | 2026-08-05 | 0.056196 | Caguas | 50 | 0.34058 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37100 | ACACIAS TC | 2026-08-05 | 0.079563 | Mayaguez | 100 | 0.9644 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37400 | BAYAMON TC - CAMBALACHE TC | 2026-08-05 | 0.1125 | Arecibo | 100 | 1.3637 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2000 | SAN SEBASTIAN TC | 2026-08-05 | 0.20292 | Mayaguez | 50 | 1.2298 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37400 |  | 2026-08-05 | 0.12084 | Arecibo | 100 | 1.4648 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37400 |  | 2026-08-05 | 0.1232 | Arecibo | 100 | 1.4934 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 7800 |  | 2026-08-05 | 0.06527 | Bayamón | 50 | 0.39557 | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36700 |  | 2026-08-05 | 0.084793 | Mayaguez | 100 | 1.0278 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36700 | SAN SEBASTIAN TC - MAYAGUEZ TC | 2026-08-05 | 0.084793 | Mayaguez | 100 | 1.0278 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 4800 |  | 2026-08-05 | 0.040074 | Caguas | 50 | 0.24287 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 4800 |  | 2026-08-05 | 0.030501 | Caguas | 50 | 0.18486 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 4800 |  | 2026-08-05 | 0.038753 | Caguas | 50 | 0.23487 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2600 | SAN SEBASTIAN TC | 2026-08-05 | 0.16306 | Mayaguez | 50 | 0.98825 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37100 | ACACIAS TC | 2026-08-05 | 0.096997 | Mayaguez | 100 | 1.1757 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 8100 | YAUCO 1 HP | 2026-08-05 | 0.20688 | Mayaguez | 50 | 1.2538 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2000 | SAN SEBASTIAN TC | 2026-08-05 | 0.046603 | Mayaguez | 50 | 0.28244 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36300 | SABANA LLANA TC - YABUCOA TC | 2026-08-05 | 0.073001 | Caguas | 100 | 0.88486 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36300 | SABANA LLANA TC - YABUCOA TC | 2026-08-05 | 0.073001 | Caguas | 100 | 0.88486 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36300 | YABUCOA TC - YABUCOA TC | 2026-08-05 | 0.18583 | Caguas | 100 | 2.2525 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36300 | YABUCOA TC - SABANA LLANA TC | 2026-08-05 | 0.18583 | Caguas | 100 | 2.2525 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37800 | JOBOS TC - MONACILLOS TC | 2026-08-05 | 0.35359 | Ponce | 100 | 4.286 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 8500 | AIBONITO TO - CAYEY TC | 2026-08-06 | 0.16094 | Caguas | 50 | 0.97537 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37800 | MONACILLOS TC - JOBOS TC | 2026-08-05 | 0.08692 | Caguas | 100 | 1.0536 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37400 |  | 2026-08-07 | 0.17048 | Arecibo | 100 | 2.0664 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37400 |  | 2026-08-07 | 0.15751 | Arecibo | 100 | 1.9092 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 8500 | CAYEY TC - AIBONITO TO | 2026-08-04 | 0.055664 | Caguas | 50 | 0.33736 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36300 | SABANA LLANA TC - YABUCOA TC | 2026-08-04 | 0.3558 | Caguas | 100 | 4.3128 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3100 |  | 2026-08-06 | 0.017639 | San Juan | 50 | 0.10691 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3100 |  | 2026-08-06 | 0.019048 | San Juan | 50 | 0.11544 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3100 |  | 2026-08-06 | 0.018382 | San Juan | 50 | 0.11141 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36700 |  | 2026-08-08 | 0.095537 | Mayaguez | 100 | 1.158 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3100 |  | 2026-08-06 | 0.022625 | San Juan | 50 | 0.13712 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36700 | SAN SEBASTIAN TC | 2026-08-08 | 0.095537 | Mayaguez | 100 | 1.158 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3100 |  | 2026-08-06 | 0.023739 | San Juan | 50 | 0.14388 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3100 |  | 2026-08-06 | 0.027801 | San Juan | 50 | 0.16849 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50500 | MAYAGUEZ TC | 2026-08-06 | 0.09869 | Mayaguez | 100 | 1.1962 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50500 | MAYAGUEZ TC | 2026-08-06 | 0.09869 | Mayaguez | 100 | 1.1962 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3100 |  | 2026-08-06 | 0.024514 | San Juan | 50 | 0.14857 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3100 |  | 2026-08-07 | 0.030944 | San Juan | 50 | 0.18754 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3100 |  | 2026-08-07 | 0.026704 | San Juan | 50 | 0.16184 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3100 |  | 2026-08-07 | 0.011187 | San Juan | 50 | 0.067801 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37400 |  | 2026-08-06 | 0.16762 | Arecibo | 100 | 2.0317 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3100 |  | 2026-08-07 | 0.012472 | San Juan | 50 | 0.075589 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3100 |  | 2026-08-07 | 0.025212 | San Juan | 50 | 0.1528 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3100 |  | 2026-08-06 | 0.023642 | San Juan | 50 | 0.14328 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3100 |  | 2026-08-06 | 0.018422 | San Juan | 50 | 0.11165 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37400 | BAYAMON TC - CAMBALACHE TC | 2026-08-06 | 0.09651 | Arecibo | 100 | 1.1698 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 16300 |  | 2026-08-06 | 0.032933 | Arecibo | 50 | 0.19959 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2300 |  | 2026-08-06 | 0.10889 | Arecibo | 50 | 0.65993 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 16300 |  | 2026-08-06 | 0.036661 | Arecibo | 50 | 0.22219 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 16300 |  | 2026-08-06 | 0.039146 | Arecibo | 50 | 0.23725 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 16300 |  | 2026-08-06 | 0.022476 | Arecibo | 50 | 0.13622 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 16300 |  | 2026-08-06 | 0.042875 | Arecibo | 50 | 0.25985 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 8900 |  | 2026-08-06 | 0.016231 | San Juan | 50 | 0.098369 | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 16300 |  | 2026-08-06 | 0.045981 | Arecibo | 50 | 0.27868 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 16300 |  | 2026-08-06 | 0.025476 | Arecibo | 50 | 0.1544 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 6500 | TORO NEGRO 1 HP | 2026-08-06 | 0.050744 | Ponce | 50 | 0.30754 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2300 |  | 2026-08-06 | 0.1766 | Arecibo | 50 | 1.0703 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37400 | BAYAMON TC - CAMBALACHE TC | 2026-08-06 | 0.062796 | Arecibo | 100 | 0.76117 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 16300 |  | 2026-08-07 | 0.037282 | Arecibo | 50 | 0.22595 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 16300 |  | 2026-08-07 | 0.043496 | Arecibo | 50 | 0.26361 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50500 |  | 2026-08-07 | 0.12956 | Arecibo | 100 | 1.5704 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37400 |  | 2026-08-07 | 0.20974 | Arecibo | 100 | 2.5423 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 39100 | MONACILLOS TC - BARIOA TO | 2026-08-07 | 0.087778 | Arecibo | 100 | 1.064 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37400 |  | 2026-08-07 | 0.17595 | Arecibo | 100 | 2.1328 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 39100 | MONACILLOS TC - BARIOA TO | 2026-08-07 | 0.073381 | Arecibo | 100 | 0.88947 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37200 | MAYAGUEZ TC | 2026-08-08 | 0.1262 | Mayaguez | 100 | 1.5297 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 39100 | MONACILLOS TC - BARIOA TO | 2026-08-07 | 0.089566 | Arecibo | 100 | 1.0857 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37200 | MAYAGUEZ TC | 2026-08-07 | 0.1241 | Mayaguez | 100 | 1.5042 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37200 | MAYAGUEZ TC | 2026-08-07 | 0.11584 | Mayaguez | 100 | 1.4041 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37200 | MAYAGUEZ TC | 2026-08-07 | 0.11886 | Mayaguez | 100 | 1.4408 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37200 | MAYAGUEZ TC | 2026-08-07 | 0.090415 | Mayaguez | 100 | 1.0959 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37100 | MAYAGUEZ TC | 2026-08-07 | 0.159 | Mayaguez | 100 | 1.9272 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 39100 | MONACILLOS TC - BARIOA TO | 2026-08-08 | 0.059532 | Arecibo | 100 | 0.7216 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37100 | MAYAGUEZ TC | 2026-08-07 | 0.12959 | Mayaguez | 100 | 1.5708 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3000 |  | 2026-08-07 | 0.070836 | Caguas | 50 | 0.42931 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 39100 | MONACILLOS TC - BARIOA TO | 2026-08-07 | 0.080066 | Arecibo | 100 | 0.97049 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50500 |  | 2026-08-07 | 0.18713 | Arecibo | 100 | 2.2682 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3000 |  | 2026-08-08 | 0.028583 | Caguas | 50 | 0.17323 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3100 |  | 2026-08-08 | 0.050735 | San Juan | 50 | 0.30749 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 5400 |  | 2026-08-07 | 0.10128 | San Juan | 50 | 0.61384 | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 5400 |  | 2026-08-08 | 0.10501 | San Juan | 50 | 0.63643 | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36700 |  | 2026-08-08 | 0.084793 | Mayaguez | 100 | 1.0278 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3000 |  | 2026-08-08 | 0.044413 | Caguas | 50 | 0.26917 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 8100 | YAUCO 1 HP | 2026-08-07 | 0.11012 | Ponce | 50 | 0.66737 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50500 | AGUADILLA HOSPITAL DISTRITO SECT | 2026-08-06 | 0.11701 | Mayaguez | 100 | 1.4184 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37100 | SAN GERMAN TC | 2026-08-08 | 0.1743 | Ponce | 100 | 2.1128 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 5600 | MAYAGUEZ GP | 2026-08-08 | 0.026442 | Mayaguez | 50 | 0.16025 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 5600 | MAYAGUEZ GP | 2026-08-08 | 0.034098 | Mayaguez | 50 | 0.20666 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37100 | SAN GERMAN TC | 2026-08-08 | 0.081597 | Ponce | 100 | 0.98906 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3400 | GUAYNABO SECT - GUAYNABO SECT | 2026-08-14 | 0.00094697 | Bayamon | 50 | 0.0057392 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3400 | GUAYNABO SECT - GUAYNABO SECT | 2026-08-14 | 0.039412 | Bayamon | 50 | 0.23886 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | DORADO TC - CAMBALACHE TC | 2026-08-11 | 0.00094697 | Arecibo | 50 | 0.0057392 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | DORADO TC - CAMBALACHE TC | 2026-08-11 | 0.02434 | Arecibo | 50 | 0.14752 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | DORADO TC - CAMBALACHE TC | 2026-08-13 | 0.057166 | Arecibo | 50 | 0.34646 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | DORADO TC - CAMBALACHE TC | 2026-08-12 | 0.039045 | Arecibo | 50 | 0.23664 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 17900 | JUANA DIAZ TC - PASTILLO | 2026-08-15 | 0.032805 | Ponce | 50 | 0.19882 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 200 | PONCE TC - SANTA ISABEL SECT | 2026-08-10 | 0.046644 | Ponce | 50 | 0.28269 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 200 | PONCE TC - SANTA ISABEL SECT | 2026-08-10 | 0.035361 | Ponce | 50 | 0.21431 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 200 | PONCE TC - SANTA ISABEL SECT | 2026-08-14 | 0.034797 | Ponce | 50 | 0.21089 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 100 | PONCE TC - SANTA ISABEL SECT | 2026-08-14 | 0.033554 | Ponce | 50 | 0.20336 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 100 | PONCE TC - SANTA ISABEL SECT | 2026-08-15 | 0.057166 | Ponce | 50 | 0.34646 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 200 | PONCE TC - SANTA ISABEL SECT | 2026-08-10 | 0.048467 | Ponce | 50 | 0.29374 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 100 | PONCE TC - SANTA ISABEL SECT | 2026-08-10 | 0.036479 | Ponce | 50 | 0.22108 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 100 | PONCE TC - SANTA ISABEL SECT | 2026-08-11 | 0.02957 | Ponce | 50 | 0.17921 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 100 | PONCE TC - SANTA ISABEL SECT | 2026-08-11 | 0.032931 | Ponce | 50 | 0.19958 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 100 | PONCE TC - SANTA ISABEL SECT | 2026-08-11 | 0.033586 | Ponce | 50 | 0.20355 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | DORADO TC - CAMBALACHE TC | 2026-08-15 | 0.052195 | Arecibo | 50 | 0.31633 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | DORADO TC - CAMBALACHE TC | 2026-08-14 | 0.035897 | Arecibo | 50 | 0.21756 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36100 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-11 | 0.080394 | Bayamon | 100 | 0.97448 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3000 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-13 | 0.029045 | Caguas | 50 | 0.17603 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3000 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-13 | 0.031069 | Caguas | 50 | 0.18829 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-12 | 0.046631 | Arecibo | 50 | 0.28261 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-12 | 0.024133 | Arecibo | 50 | 0.14626 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-12 | 0.037003 | Arecibo | 50 | 0.22426 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-11 | 0.034175 | Arecibo | 50 | 0.20712 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-11 | 0.031774 | Arecibo | 50 | 0.19257 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-10 | 0.020941 | Arecibo | 50 | 0.12691 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50200 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-10 | 0.20852 | Bayamon | 100 | 2.5275 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-12 | 0.01992 | Arecibo | 50 | 0.12073 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50300 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-12 | 0.61406 | Ponce | 100 | 7.4432 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-12 | 0.028759 | Arecibo | 50 | 0.1743 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-11 | 0.025846 | Arecibo | 50 | 0.15664 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-11 | 0.02723 | Arecibo | 50 | 0.16503 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-11 | 0.022581 | Arecibo | 50 | 0.13685 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-11 | 0.017451 | Arecibo | 50 | 0.10576 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-11 | 0.006835 | Arecibo | 50 | 0.041424 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-11 | 0.024744 | Arecibo | 50 | 0.14996 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-11 | 0.024279 | Arecibo | 50 | 0.14714 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-11 | 0.025376 | Arecibo | 50 | 0.15379 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-11 | 0.023643 | Arecibo | 50 | 0.14329 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-10 | 0.045981 | Arecibo | 50 | 0.27868 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-10 | 0.025952 | Arecibo | 50 | 0.15729 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-12 | 0.050331 | Arecibo | 50 | 0.30504 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-13 | 0.060273 | Arecibo | 50 | 0.36529 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50300 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-10 | 0.29487 | Ponce | 100 | 3.5742 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50300 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-10 | 0.12637 | Ponce | 100 | 1.5318 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50300 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-10 | 0.063352 | Ponce | 100 | 0.7679 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50300 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-11 | 0.29403 | Ponce | 100 | 3.564 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50300 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-12 | 0.063994 | Ponce | 100 | 0.77569 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-12 | 0.028547 | Arecibo | 50 | 0.17301 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50300 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-12 | 0.41594 | Ponce | 100 | 5.0417 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50300 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-13 | 0.36119 | Ponce | 100 | 4.378 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-12 | 0.030141 | Arecibo | 50 | 0.18268 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50300 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-14 | 0.26162 | Ponce | 100 | 3.1711 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-12 | 0.022594 | Arecibo | 50 | 0.13694 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-12 | 0.024842 | Arecibo | 50 | 0.15056 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-12 | 0.023684 | Arecibo | 50 | 0.14354 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-12 | 0.019574 | Arecibo | 50 | 0.11863 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-12 | 0.016014 | Arecibo | 50 | 0.097055 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50300 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-15 | 0.19321 | Ponce | 100 | 2.3419 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-12 | 0.014895 | Arecibo | 50 | 0.090275 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-12 | 0.024247 | Arecibo | 50 | 0.14695 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-12 | 0.022246 | Arecibo | 50 | 0.13482 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-12 | 0.020473 | Arecibo | 50 | 0.12408 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-12 | 0.028873 | Arecibo | 50 | 0.17499 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50200 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-13 | 0.14119 | Bayamon | 100 | 1.7114 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50200 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-12 | 0.11044 | Bayamon | 100 | 1.3386 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50200 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-14 | 0.21369 | Bayamon | 100 | 2.5902 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36700 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-12 | 0.12264 | Mayaguez | 100 | 1.4865 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-15 | 0.026719 | Arecibo | 50 | 0.16193 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-13 | 0.033554 | Arecibo | 50 | 0.20336 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-14 | 0.026707 | Arecibo | 50 | 0.16186 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-12 | 0.028041 | Arecibo | 50 | 0.16995 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2300 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-13 | 0.17967 | Arecibo | 50 | 1.0889 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 7900 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-12 | 0.026541 | Ponce | 50 | 0.16086 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 7900 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-12 | 0.029346 | Ponce | 50 | 0.17786 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36700 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-10 | 0.16777 | Mayaguez | 100 | 2.0336 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-12 | 0.026235 | Arecibo | 50 | 0.159 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-12 | 0.026235 | Arecibo | 50 | 0.159 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-12 | 0.026473 | Arecibo | 50 | 0.16045 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50300 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-15 | 0.25849 | Ponce | 100 | 3.1332 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36700 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-13 | 0.17952 | Mayaguez | 100 | 2.176 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36700 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-13 | 0.17952 | Mayaguez | 100 | 2.176 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3000 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-14 | 0.065244 | Caguas | 50 | 0.39542 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-14 | 0.028161 | Arecibo | 50 | 0.17067 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-14 | 0.027979 | Arecibo | 50 | 0.16957 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-14 | 0.01127 | Arecibo | 50 | 0.068306 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3100 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-10 | 0.031301 | San Juan | 50 | 0.1897 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-14 | 0.02374 | Arecibo | 50 | 0.14388 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-14 | 0.018284 | Arecibo | 50 | 0.11081 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 7900 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-13 | 0.025734 | Ponce | 50 | 0.15596 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 300 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-13 | 0.054059 | Ponce | 50 | 0.32763 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 300 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-13 | 0.0814 | Ponce | 50 | 0.49333 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 4800 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-10 | 0.014913 | Caguas | 50 | 0.090381 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-15 | 0.028321 | Arecibo | 50 | 0.17164 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3600 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-15 | 0.041565 | San Juan | 50 | 0.25191 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3600 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-15 | 0.033869 | San Juan | 50 | 0.20527 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 4800 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-10 | 0.030466 | Caguas | 50 | 0.18464 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3600 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-15 | 0.021334 | San Juan | 50 | 0.12929 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 300 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-13 | 0.00094697 | Ponce | 50 | 0.0057392 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 7900 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-13 | 0.00094697 | Ponce | 50 | 0.0057392 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3600 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-15 | 0.021334 | San Juan | 50 | 0.12929 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 300 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-13 | 0.00094697 | Ponce | 50 | 0.0057392 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 7900 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-13 | 0.00094697 | Ponce | 50 | 0.0057392 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 300 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-13 | 0.00094697 | Ponce | 50 | 0.0057392 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3600 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-15 | 0.026171 | San Juan | 50 | 0.15861 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 7900 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-13 | 0.00094697 | Ponce | 50 | 0.0057392 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 300 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-13 | 0.00094697 | Ponce | 50 | 0.0057392 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3600 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-15 | 0.031968 | San Juan | 50 | 0.19375 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 7900 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-13 | 0.00094697 | Ponce | 50 | 0.0057392 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 4800 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-10 | 0.028975 | Caguas | 50 | 0.17561 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 7900 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-13 | 0.00094697 | Ponce | 50 | 0.0057392 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 7900 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-13 | 0.00094697 | Ponce | 50 | 0.0057392 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3100 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-11 | 0.023834 | San Juan | 50 | 0.14445 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3100 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-10 | 0.025843 | San Juan | 50 | 0.15663 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 7900 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-13 | 0.048126 | Ponce | 50 | 0.29167 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 300 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-13 | 0.048065 | Ponce | 50 | 0.2913 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 7900 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-13 | 0.051574 | Ponce | 50 | 0.31257 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 300 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-13 | 0.051574 | Ponce | 50 | 0.31257 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37800 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-10 | 0.07973 | Caguas | 100 | 0.96642 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2300 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-10 | 0.1766 | Arecibo | 50 | 1.0703 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37200 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-10 | 0.00094697 | Mayaguez | 100 | 0.011478 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3100 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-10 | 0.054707 | San Juan | 50 | 0.33156 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3600 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-11 | 0.027318 | San Juan | 50 | 0.16556 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3100 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-10 | 0.028019 | San Juan | 50 | 0.16981 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3100 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-11 | 0.029058 | San Juan | 50 | 0.17611 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3100 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-11 | 0.024647 | San Juan | 50 | 0.14938 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36700 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-12 | 0.12264 | Mayaguez | 100 | 1.4865 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36700 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-10 | 0.063468 | Mayaguez | 100 | 0.76931 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-14 | 0.04101 | Arecibo | 50 | 0.24855 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50500 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-13 | 0.094765 | Mayaguez | 100 | 1.1487 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-14 | 0.034898 | Arecibo | 50 | 0.2115 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-15 | 0.039391 | Arecibo | 50 | 0.23874 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3100 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-12 | 0.028939 | San Juan | 50 | 0.17539 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2600 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-09 | 0.086674 | Mayaguez | 50 | 0.5253 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 8100 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-12 | 0.15894 | Mayaguez | 50 | 0.96328 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37200 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-09 | 0.046352 | Mayaguez | 100 | 0.56185 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2300 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-10 | 0.044117 | Arecibo | 50 | 0.26738 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2300 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-10 | 0.13748 | Arecibo | 50 | 0.83321 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2300 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-10 | 0.024234 | Arecibo | 50 | 0.14687 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2300 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-10 | 0.011413 | Arecibo | 50 | 0.069168 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36700 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-14 | 0.21128 | Mayaguez | 100 | 2.561 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36700 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-14 | 0.19729 | Mayaguez | 100 | 2.3914 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 200 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-10 | 0.028869 | Ponce | 50 | 0.17496 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36100 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-10 | 0.081477 | Bayamon | 100 | 0.9876 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37100 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-10 | 0.1012 | Ponce | 100 | 1.2266 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37100 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-10 | 0.1012 | Ponce | 100 | 1.2266 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 200 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-11 | 0.032848 | Ponce | 50 | 0.19908 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 100 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-11 | 0.033586 | Ponce | 50 | 0.20355 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3100 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-11 | 0.061729 | San Juan | 50 | 0.37411 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 6900 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-11 | 0.069423 | Arecibo | 50 | 0.42075 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2300 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-11 | 0.037623 | Arecibo | 50 | 0.22802 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2300 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-11 | 0.046795 | Arecibo | 50 | 0.28361 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2300 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-11 | 0.042645 | Arecibo | 50 | 0.25845 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2300 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-11 | 0.048545 | Arecibo | 50 | 0.29421 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2300 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-11 | 0.00094697 | Arecibo | 50 | 0.0057392 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 100 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-11 | 0.02957 | Ponce | 50 | 0.17921 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 1500 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-11 | 0.00094697 | Mayaguez | 50 | 0.0057392 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 1500 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-11 | 0.00094697 | Mayaguez | 50 | 0.0057392 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2600 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-11 | 0.22976 | Mayaguez | 50 | 1.3925 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 8100 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-11 | 0.12212 | Mayaguez | 50 | 0.74009 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37200 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-11 | 0.00094697 | Mayaguez | 100 | 0.011478 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2300 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-11 | 0.00094697 | Arecibo | 50 | 0.0057392 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2300 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-12 | 0.028287 | Arecibo | 50 | 0.17144 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 200 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-11 | 0.031069 | Ponce | 50 | 0.18829 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 100 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-11 | 0.031069 | Ponce | 50 | 0.18829 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2300 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-12 | 0.029204 | Arecibo | 50 | 0.177 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2300 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-12 | 0.00094697 | Arecibo | 50 | 0.0057392 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37200 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-12 | 0.00094697 | Mayaguez | 100 | 0.011478 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 15900 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-12 | 0.023664 | Mayaguez | 50 | 0.14342 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2300 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-13 | 0.028583 | Arecibo | 50 | 0.17323 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2300 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-12 | 0.00094697 | Arecibo | 50 | 0.0057392 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2300 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-12 | 0.043463 | Arecibo | 50 | 0.26341 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2300 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-12 | 0.11989 | Arecibo | 50 | 0.72662 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36400 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-12 | 0.1382 | Arecibo | 100 | 1.6751 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 10100 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-11 | 0.029826 | San Juan | 50 | 0.18076 | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2100 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-12 | 0.087278 | Arecibo | 50 | 0.52896 | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50800 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-12 | 0.11471 | Caguas | 100 | 1.3904 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50800 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-11 | 0.094105 | Caguas | 100 | 1.1407 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50800 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-12 | 0.00094697 | Caguas | 100 | 0.011478 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50800 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-11 | 0.00094697 | Caguas | 100 | 0.011478 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50800 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-12 | 0.00094697 | Caguas | 100 | 0.011478 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2300 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-13 | 0.048545 | Arecibo | 50 | 0.29421 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2300 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-13 | 0.029826 | Arecibo | 50 | 0.18076 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2300 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-13 | 0.02857 | Arecibo | 50 | 0.17315 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2300 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-13 | 0.00094697 | Arecibo | 50 | 0.0057392 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2300 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-13 | 0.00094697 | Arecibo | 50 | 0.0057392 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2300 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-13 | 0.18944 | Arecibo | 50 | 1.1481 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37200 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-13 | 0.00094697 | Mayaguez | 100 | 0.011478 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 1300 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-13 | 0.00094697 | Ponce | 50 | 0.0057392 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 1500 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-13 | 0.24774 | Mayaguez | 50 | 1.5015 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3400 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-14 | 0.083275 | Bayamon | 50 | 0.5047 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 6500 | Ponce TC - Dos Bocas Hydro Plant | 2026-08-13 | 0.03096 | Caguas | 50 | 0.18764 | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 6500 | MONACILLOS TC - LAS LOMAS SECT | 2026-08-13 | 0.036103 | Caguas | 50 | 0.21881 | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3400 | SAN GERMAN TO | 2026-08-14 | 0.040389 | San Juan | 50 | 0.24478 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3400 | MAYAGUEZ TC | 2026-08-14 | 0.031108 | Bayamon | 50 | 0.18853 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36100 |  | 2026-08-10 | 0.081477 | Bayamon | 100 | 0.9876 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3400 |  | 2026-08-14 | 0.047224 | San Juan | 50 | 0.28621 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37100 |  | 2026-08-13 | 0.10597 | Ponce | 100 | 1.2845 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 39800 | CAMBALACHE TC - DOS BOCAS HP | 2026-08-13 | 0.00094697 | Mayaguez | 100 | 0.011478 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2300 | MONACILLOS TC - LAS LOMAS SECT | 2026-08-13 | 0.00094697 | Arecibo | 50 | 0.0057392 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37200 | SAN JUAN SP - CREMATORIO TO | 2026-08-13 | 0.00094697 | Mayaguez | 100 | 0.011478 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2300 |  | 2026-08-13 | 0.00094697 | Arecibo | 50 | 0.0057392 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2300 | MAYAGUEZ TC | 2026-08-14 | 0.06585 | Arecibo | 50 | 0.39909 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3500 | AGUADA TO | 2026-08-13 | 0.01991 | Bayamon | 50 | 0.12067 | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 5900 |  | 2026-08-13 | 0.03169 | San Juan | 50 | 0.19206 | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37200 | MONACILLOS TC - BARIOA TO | 2026-08-13 | 0.00094697 | Mayaguez | 100 | 0.011478 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 15900 |  | 2026-08-13 | 0.083264 | Mayaguez | 50 | 0.50463 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 38300 |  | 2026-08-13 | 0.11752 | San Juan | 100 | 1.4245 | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3100 | JOBOS TC - PFIZER GUAYAMA | 2026-08-14 | 0.049967 | San Juan | 50 | 0.30283 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 10900 | JOBOS TC - PFIZER GUAYAMA | 2026-08-15 | 0.027119 | Ponce | 50 | 0.16436 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 10900 |  | 2026-08-15 | 0.028704 | Ponce | 50 | 0.17396 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 10900 | CAMBALACHE TC - DOS BOCAS HP | 2026-08-14 | 0.084506 | Ponce | 50 | 0.51216 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2300 | CAMBALACHE TC - DOS BOCAS HP | 2026-08-15 | 0.093484 | Arecibo | 50 | 0.56657 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2300 |  | 2026-08-14 | 0.1715 | Arecibo | 50 | 1.0394 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2300 | MONACILLOS TC - LAS LOMAS SECT | 2026-08-15 | 0.20206 | Arecibo | 50 | 1.2246 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2300 |  | 2026-08-14 | 0.1006 | Arecibo | 50 | 0.60968 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3400 | MONACILLOS TC - LAS LOMAS SECT | 2026-08-14 | 0.061001 | Bayamon | 50 | 0.3697 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3400 |  | 2026-08-14 | 0.038525 | San Juan | 50 | 0.23348 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3400 | DAGUAO TC - RIO BLANCO HP | 2026-08-14 | 0.083275 | Bayamon | 50 | 0.5047 | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3100 | BAYAMON PUEBLO SECT - BAYAMON PUEBLO SECT | 2026-08-14 | 0.035037 | San Juan | 50 | 0.21235 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 5400 |  | 2026-08-13 | 0.00094697 | Caguas | 50 | 0.0057392 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3400 |  | 2026-08-14 | 0.015869 | Bayamon | 50 | 0.096177 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 100 |  | 2026-08-14 | 0.032933 | Ponce | 50 | 0.19959 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3400 | MONACILLOS TC - CENTRO MEDICO SECT | 2026-08-14 | 0.057555 | Bayamon | 50 | 0.34882 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 200 |  | 2026-08-14 | 0.034175 | Ponce | 50 | 0.20712 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 8900 | CAMBALACHE TC | 2026-08-14 | 0.052816 | San Juan | 50 | 0.3201 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 8900 | CAMBALACHE TC - DOS BOCAS HP | 2026-08-14 | 0.044404 | San Juan | 50 | 0.26911 | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3400 |  | 2026-08-15 | 0.041644 | Bayamon | 50 | 0.25239 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 39100 | MONACILLOS TC - BARIOA TO | 2026-08-15 | 0.088184 | Arecibo | 100 | 1.0689 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2300 |  | 2026-08-15 | 0.067207 | Arecibo | 50 | 0.40731 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2300 |  | 2026-08-15 | 0.00094697 | Arecibo | 50 | 0.0057392 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 7800 |  | 2026-08-19 | 0.15895 | Bayamon | 50 | 0.96335 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3500 |  | 2026-08-20 | 0.0073873 | Bayamon | 50 | 0.044772 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3400 | MONACILLOS TC - BARIOA TO | 2026-08-16 | 0.00094697 | Bayamon | 50 | 0.0057392 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3400 | MONACILLOS TC - BARIOA TO | 2026-08-16 | 0.03477 | Bayamon | 50 | 0.21072 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3400 | MONACILLOS TC - BARIOA TO | 2026-08-18 | 0.053829 | Bayamon | 50 | 0.32624 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3400 | MONACILLOS TC - BARIOA TO | 2026-08-18 | 0.090549 | Bayamon | 50 | 0.54878 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3400 | MONACILLOS TC - BARIOA TO | 2026-08-18 | 0.090549 | Bayamon | 50 | 0.54878 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-20 | 0.040505 | Arecibo | 50 | 0.24548 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-17 | 0.0045379 | Arecibo | 50 | 0.027502 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50200 | MONACILLOS TC - BARIOA TO | 2026-08-16 | 6.362e-05 | Bayamon | 100 | 0.00077116 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 100 | MONACILLOS TC - BARIOA TO | 2026-08-18 | 0.032933 | Ponce | 50 | 0.19959 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 100 | MONACILLOS TC - BARIOA TO | 2026-08-18 | 0.027962 | Ponce | 50 | 0.16947 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 100 | MONACILLOS TC - BARIOA TO | 2026-08-18 | 0.02734 | Ponce | 50 | 0.1657 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3000 | MONACILLOS TC - BARIOA TO | 2026-08-17 | 0.027613 | Caguas | 50 | 0.16735 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-20 | 0.034175 | Arecibo | 50 | 0.20712 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-20 | 0.042158 | Arecibo | 50 | 0.2555 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-20 | 0.042158 | Arecibo | 50 | 0.2555 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-20 | 0.037442 | Arecibo | 50 | 0.22692 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-20 | 0.021229 | Arecibo | 50 | 0.12866 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-20 | 0.037384 | Arecibo | 50 | 0.22657 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-20 | 0.038308 | Arecibo | 50 | 0.23217 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-20 | 0.030868 | Arecibo | 50 | 0.18708 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-18 | 0.056849 | Arecibo | 50 | 0.34454 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-18 | 0.056357 | Arecibo | 50 | 0.34156 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-20 | 0.0269 | Arecibo | 50 | 0.16303 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-19 | 0.027773 | Arecibo | 50 | 0.16832 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50300 | MONACILLOS TC - BARIOA TO | 2026-08-17 | 4.7004e-05 | Ponce | 100 | 0.00056975 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-19 | 0.026018 | Arecibo | 50 | 0.15768 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-18 | 0.020655 | Arecibo | 50 | 0.12518 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-19 | 0.047846 | Arecibo | 50 | 0.28997 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-19 | 0.047846 | Arecibo | 50 | 0.28997 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-20 | 0.030447 | Arecibo | 50 | 0.18453 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-20 | 0.02734 | Arecibo | 50 | 0.1657 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-19 | 0.01969 | Arecibo | 50 | 0.11933 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-19 | 0.018077 | Arecibo | 50 | 0.10956 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-18 | 0.05702 | Arecibo | 50 | 0.34557 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-18 | 0.054724 | Arecibo | 50 | 0.33166 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-17 | 0.037978 | Arecibo | 50 | 0.23017 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-17 | 0.029882 | Arecibo | 50 | 0.1811 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-17 | 0.029074 | Arecibo | 50 | 0.17621 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50300 | MONACILLOS TC - BARIOA TO | 2026-08-17 | 0.080554 | Ponce | 100 | 0.97641 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50300 | MONACILLOS TC - BARIOA TO | 2026-08-21 | 9.7509e-05 | Ponce | 100 | 0.0011819 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50300 | MONACILLOS TC - BARIOA TO | 2026-08-21 | 0.10493 | Ponce | 100 | 1.2718 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50300 | MONACILLOS TC - BARIOA TO | 2026-08-22 | 0.095808 | Ponce | 100 | 1.1613 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50300 | MONACILLOS TC - BARIOA TO | 2026-08-22 | 7.1214e-05 | Ponce | 100 | 0.0008632 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3400 | MONACILLOS TC - BARIOA TO | 2026-08-20 | 0.023593 | Bayamon | 50 | 0.14299 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-17 | 0.033228 | Arecibo | 50 | 0.20138 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-17 | 0.026037 | Arecibo | 50 | 0.1578 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-19 | 0.030911 | Arecibo | 50 | 0.18734 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-19 | 0.035469 | Arecibo | 50 | 0.21496 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-20 | 0.032595 | Arecibo | 50 | 0.19754 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-20 | 0.028563 | Arecibo | 50 | 0.17311 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-21 | 0.032337 | Arecibo | 50 | 0.19598 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-21 | 0.033895 | Arecibo | 50 | 0.20543 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-22 | 0.032086 | Arecibo | 50 | 0.19446 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3600 | MONACILLOS TC - BARIOA TO | 2026-08-17 | 0.034534 | San Juan | 50 | 0.2093 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3600 | MONACILLOS TC - BARIOA TO | 2026-08-17 | 0.034175 | San Juan | 50 | 0.20712 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 7900 | MONACILLOS TC - BARIOA TO | 2026-08-20 | 0.02734 | Ponce | 50 | 0.1657 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 7900 | MONACILLOS TC - BARIOA TO | 2026-08-20 | 0.019884 | Ponce | 50 | 0.12051 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 300 | MONACILLOS TC - BARIOA TO | 2026-08-20 | 0.016777 | Ponce | 50 | 0.10168 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 7900 | MONACILLOS TC - BARIOA TO | 2026-08-20 | 0.0097792 | Ponce | 50 | 0.059268 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 300 | MONACILLOS TC - BARIOA TO | 2026-08-20 | 0.0097792 | Ponce | 50 | 0.059268 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-17 | 0.042598 | Arecibo | 50 | 0.25817 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-17 | 0.03395 | Arecibo | 50 | 0.20576 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37200 | MONACILLOS TC - BARIOA TO | 2026-08-17 | 0.094765 | Mayaguez | 100 | 1.1487 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-21 | 0.041632 | Arecibo | 50 | 0.25231 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-18 | 0.037904 | Arecibo | 50 | 0.22972 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-20 | 0.046603 | Arecibo | 50 | 0.28244 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 7900 | MONACILLOS TC - BARIOA TO | 2026-08-20 | 0.082021 | Ponce | 50 | 0.4971 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 7900 | MONACILLOS TC - BARIOA TO | 2026-08-20 | 0.054681 | Ponce | 50 | 0.3314 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 300 | MONACILLOS TC - BARIOA TO | 2026-08-20 | 0.024855 | Ponce | 50 | 0.15064 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 300 | MONACILLOS TC - BARIOA TO | 2026-08-20 | 0.01802 | Ponce | 50 | 0.10921 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 300 | MONACILLOS TC - BARIOA TO | 2026-08-20 | 0.02734 | Ponce | 50 | 0.1657 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 300 | MONACILLOS TC - BARIOA TO | 2026-08-20 | 0.023612 | Ponce | 50 | 0.1431 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 300 | MONACILLOS TC - BARIOA TO | 2026-08-20 | 0.02734 | Ponce | 50 | 0.1657 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 300 | MONACILLOS TC - BARIOA TO | 2026-08-20 | 0.021748 | Ponce | 50 | 0.13181 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 15900 | MONACILLOS TC - BARIOA TO | 2026-08-17 | 0.016788 | Mayaguez | 50 | 0.10174 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 39800 | MONACILLOS TC - BARIOA TO | 2026-08-17 | 6.1969e-05 | Mayaguez | 100 | 0.00075114 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 10900 | MONACILLOS TC - BARIOA TO | 2026-08-17 | 0.027987 | Ponce | 50 | 0.16962 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 10900 | MONACILLOS TC - BARIOA TO | 2026-08-17 | 0.025863 | Ponce | 50 | 0.15675 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 10900 | MONACILLOS TC - BARIOA TO | 2026-08-22 | 0.03604 | Ponce | 50 | 0.21842 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 10900 | MONACILLOS TC - BARIOA TO | 2026-08-22 | 0.032933 | Ponce | 50 | 0.19959 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2100 | MONACILLOS TC - BARIOA TO | 2026-08-17 | 0.038525 | Arecibo | 50 | 0.23348 | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 51200 | MONACILLOS TC - BARIOA TO | 2026-08-16 | 0.11907 | Arecibo | 100 | 1.4432 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36700 | MONACILLOS TC - BARIOA TO | 2026-08-20 | 0.19539 | Mayaguez | 100 | 2.3684 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36700 | MONACILLOS TC - BARIOA TO | 2026-08-19 | 0.10641 | Mayaguez | 100 | 1.2898 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37200 | MONACILLOS TC - BARIOA TO | 2026-08-17 | 0.00094697 | Mayaguez | 100 | 0.011478 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 39800 | MONACILLOS TC - BARIOA TO | 2026-08-17 | 0.00094697 | Mayaguez | 100 | 0.011478 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 39800 | MONACILLOS TC - BARIOA TO | 2026-08-17 | 0.00094697 | Mayaguez | 100 | 0.011478 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 39800 | MONACILLOS TC - BARIOA TO | 2026-08-17 | 0.00094697 | Mayaguez | 100 | 0.011478 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 8100 | MONACILLOS TC - BARIOA TO | 2026-08-17 | 0.15845 | Mayaguez | 50 | 0.9603 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 39800 | MONACILLOS TC - BARIOA TO | 2026-08-17 | 4.9532e-05 | Mayaguez | 100 | 0.00060039 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2800 | MONACILLOS TC - BARIOA TO | 2026-08-17 | 0.04319 | Mayaguez | 50 | 0.26176 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 15900 | MONACILLOS TC - BARIOA TO | 2026-08-17 | 0.02952 | Mayaguez | 50 | 0.17891 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37100 | MONACILLOS TC - BARIOA TO | 2026-08-17 | 0.1525 | Ponce | 100 | 1.8485 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37100 | MONACILLOS TC - BARIOA TO | 2026-08-17 | 0.00094697 | Ponce | 100 | 0.011478 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37100 | MONACILLOS TC - BARIOA TO | 2026-08-17 | 0.066728 | Ponce | 100 | 0.80882 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 15900 | MONACILLOS TC - BARIOA TO | 2026-08-17 | 0.039146 | Mayaguez | 50 | 0.23725 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 5600 | MONACILLOS TC - BARIOA TO | 2026-08-17 | 0.045925 | Mayaguez | 50 | 0.27833 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2600 | MONACILLOS TC - BARIOA TO | 2026-08-17 | 0.12755 | Mayaguez | 50 | 0.77301 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2100 | MONACILLOS TC - BARIOA TO | 2026-08-17 | 0.06227 | Arecibo | 50 | 0.37739 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 39100 | MONACILLOS TC - BARIOA TO | 2026-08-17 | 0.067608 | Arecibo | 100 | 0.81949 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 39100 | MONACILLOS TC - BARIOA TO | 2026-08-17 | 0.094687 | Arecibo | 100 | 1.1477 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 7800 | MONACILLOS TC - BARIOA TO | 2026-08-17 | 0.057683 | Bayamon | 50 | 0.34959 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 7800 | MONACILLOS TC - BARIOA TO | 2026-08-17 | 0.057739 | Bayamon | 50 | 0.34993 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 39800 | MONACILLOS TC - BARIOA TO | 2026-08-17 | 0.00094697 | Mayaguez | 100 | 0.011478 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 39800 | MONACILLOS TC - BARIOA TO | 2026-08-17 | 0.00094697 | Mayaguez | 100 | 0.011478 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37100 | MONACILLOS TC - BARIOA TO | 2026-08-17 | 0.159 | Mayaguez | 100 | 1.9272 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 13kv | 1709-03 | MONACILLOS TC - BARIOA TO | 2026-08-17 | 0 | Bayamon | 50 | 0 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 15900 | MONACILLOS TC - BARIOA TO | 2026-08-18 | 0.020505 | Mayaguez | 50 | 0.12427 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3100 | MONACILLOS TC - BARIOA TO | 2026-08-17 | 0.043883 | San Juan | 50 | 0.26596 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3400 | MONACILLOS TC - BARIOA TO | 2026-08-17 | 0.023489 | Bayamon | 50 | 0.14236 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36400 | MONACILLOS TC - BARIOA TO | 2026-08-20 | 0.15564 | Ponce | 100 | 1.8865 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36400 | MONACILLOS TC - BARIOA TO | 2026-08-19 | 0.1265 | Ponce | 100 | 1.5333 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36400 | MONACILLOS TC - BARIOA TO | 2026-08-18 | 0.1265 | Ponce | 100 | 1.5333 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36400 | MONACILLOS TC - BARIOA TO | 2026-08-18 | 0.041925 | Ponce | 100 | 0.50818 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-17 | 0.0348 | Arecibo | 50 | 0.21091 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-18 | 0.039666 | Arecibo | 50 | 0.2404 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-18 | 0.054995 | Arecibo | 50 | 0.3333 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-18 | 0.039194 | Arecibo | 50 | 0.23754 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-18 | 0.055029 | Arecibo | 50 | 0.33351 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-19 | 0.033374 | Arecibo | 50 | 0.20227 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-19 | 0.029826 | Arecibo | 50 | 0.18076 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-21 | 0.034175 | Arecibo | 50 | 0.20712 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37100 | MONACILLOS TC - BARIOA TO | 2026-08-17 | 0.11351 | Mayaguez | 100 | 1.3759 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 39800 | MONACILLOS TC - BARIOA TO | 2026-08-17 | 0.00094697 | Mayaguez | 100 | 0.011478 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 51200 | MONACILLOS TC - BARIOA TO | 2026-08-18 | 0.11414 | Arecibo | 100 | 1.3835 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 39800 | MONACILLOS TC - BARIOA TO | 2026-08-17 | 0.00094697 | Mayaguez | 100 | 0.011478 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37400 | MONACILLOS TC - BARIOA TO | 2026-08-17 | 0.098587 | Bayamon | 100 | 1.195 | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3100 | MONACILLOS TC - BARIOA TO | 2026-08-18 | 0.037904 | San Juan | 50 | 0.22972 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3100 | MONACILLOS TC - BARIOA TO | 2026-08-18 | 0.035199 | San Juan | 50 | 0.21333 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3100 | MONACILLOS TC - BARIOA TO | 2026-08-18 | 0.026332 | San Juan | 50 | 0.15959 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3100 | MONACILLOS TC - BARIOA TO | 2026-08-18 | 0.026332 | San Juan | 50 | 0.15959 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-18 | 0.057277 | Arecibo | 50 | 0.34713 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-18 | 0.043705 | Arecibo | 50 | 0.26488 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 4100 | MONACILLOS TC - BARIOA TO | 2026-08-17 | 0.00094697 | Bayamon | 50 | 0.0057392 | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-18 | 0.029522 | Arecibo | 50 | 0.17892 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 38100 | MONACILLOS TC - BARIOA TO | 2026-08-18 | 0.060817 | San Juan | 100 | 0.73717 | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-18 | 0.018638 | Arecibo | 50 | 0.11296 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 13400 | MONACILLOS TC - BARIOA TO | 2026-08-18 | 0.068466 | Mayaguez | 50 | 0.41495 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 13400 | MONACILLOS TC - BARIOA TO | 2026-08-18 | 0.036757 | Mayaguez | 50 | 0.22277 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 7800 | MONACILLOS TC - BARIOA TO | 2026-08-18 | 0.035989 | Bayamon | 50 | 0.21811 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 7800 | MONACILLOS TC - BARIOA TO | 2026-08-19 | 0.027607 | Bayamon | 50 | 0.16731 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-18 | 0.040348 | Arecibo | 50 | 0.24453 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 7800 | MONACILLOS TC - BARIOA TO | 2026-08-19 | 0.054413 | Bayamon | 50 | 0.32978 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-18 | 0.028154 | Arecibo | 50 | 0.17063 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 7800 | MONACILLOS TC - BARIOA TO | 2026-08-19 | 0.097848 | Bayamon | 50 | 0.59302 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-18 | 0.029129 | Arecibo | 50 | 0.17654 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 51200 | MONACILLOS TC - BARIOA TO | 2026-08-18 | 0.00094697 | Arecibo | 100 | 0.011478 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-18 | 0.046637 | Arecibo | 50 | 0.28265 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 51200 | MONACILLOS TC - BARIOA TO | 2026-08-18 | 0.00094697 | Arecibo | 100 | 0.011478 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 51200 | MONACILLOS TC - BARIOA TO | 2026-08-18 | 0.11907 | Arecibo | 100 | 1.4432 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37800 | MONACILLOS TC - BARIOA TO | 2026-08-18 | 0.16864 | San Juan | 100 | 2.0441 | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37900 | MONACILLOS TC - BARIOA TO | 2026-08-18 | 0.00094697 | San Juan | 100 | 0.011478 | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 4100 | MONACILLOS TC - BARIOA TO | 2026-08-18 | 0.00094697 | Bayamon | 50 | 0.0057392 | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37800 | MONACILLOS TC - BARIOA TO | 2026-08-18 | 0.094993 | San Juan | 100 | 1.1514 | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37000 | MONACILLOS TC - BARIOA TO | 2026-08-18 | 0.15315 | Ponce | 100 | 1.8564 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37100 | MONACILLOS TC - BARIOA TO | 2026-08-18 | 4.6229e-05 | Mayaguez | 100 | 0.00056035 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-19 | 0.064077 | Arecibo | 50 | 0.38834 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-19 | 0.031366 | Arecibo | 50 | 0.19009 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-19 | 0.022031 | Arecibo | 50 | 0.13352 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-19 | 0.027624 | Arecibo | 50 | 0.16742 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-19 | 0.029484 | Arecibo | 50 | 0.17869 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 8100 | MONACILLOS TC - BARIOA TO | 2026-08-18 | 0.075907 | Mayaguez | 50 | 0.46004 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 8100 | MONACILLOS TC - BARIOA TO | 2026-08-19 | 0.15845 | Mayaguez | 50 | 0.9603 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 5600 | MONACILLOS TC - BARIOA TO | 2026-08-19 | 0.00094697 | Mayaguez | 50 | 0.0057392 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 51200 | MONACILLOS TC - BARIOA TO | 2026-08-19 | 0.00094697 | Ponce | 100 | 0.011478 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 51200 | MONACILLOS TC - BARIOA TO | 2026-08-19 | 0.00094697 | Ponce | 100 | 0.011478 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 15900 | MONACILLOS TC - BARIOA TO | 2026-08-21 | 0.034853 | Mayaguez | 50 | 0.21123 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 15900 | MONACILLOS TC - BARIOA TO | 2026-08-22 | 0.061259 | Mayaguez | 50 | 0.37127 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | MONACILLOS TC - BARIOA TO | 2026-08-19 | 0.028703 | Arecibo | 50 | 0.17396 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37100 | MONACILLOS TC - BARIOA TO | 2026-08-19 | 0.14048 | Ponce | 100 | 1.7028 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2800 | MONACILLOS TC - BARIOA TO | 2026-08-19 | 0.00094697 | Mayaguez | 50 | 0.0057392 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36400 | MONACILLOS TC - BARIOA TO | 2026-08-20 | 6.5808e-05 | Arecibo | 100 | 0.00079767 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 5600 | MONACILLOS TC - BARIOA TO | 2026-08-19 | 0.00094697 | Mayaguez | 50 | 0.0057392 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36400 | MONACILLOS TC - BARIOA TO | 2026-08-20 | 0.058884 | Arecibo | 100 | 0.71374 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 5600 | MONACILLOS TC - BARIOA TO | 2026-08-19 | 0.00094697 | Mayaguez | 50 | 0.0057392 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36400 | MONACILLOS TC - BARIOA TO | 2026-08-20 | 0.19012 | Arecibo | 100 | 2.3045 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 5600 | MONACILLOS TC - BARIOA TO | 2026-08-19 | 0.00094697 | Mayaguez | 50 | 0.0057392 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36400 | MONACILLOS TC - BARIOA TO | 2026-08-20 | 0.19012 | Arecibo | 100 | 2.3045 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3500 | MONACILLOS TC - BARIOA TO | 2026-08-19 | 0.019287 | Bayamon | 50 | 0.11689 | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36400 | MONACILLOS TC - BARIOA TO | 2026-08-20 | 0.19012 | Arecibo | 100 | 2.3045 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3400 | MONACILLOS TC - BARIOA TO | 2026-08-19 | 0.025633 | Bayamon | 50 | 0.15535 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3400 | MONACILLOS TC - BARIOA TO | 2026-08-19 | 0.025441 | Bayamon | 50 | 0.15419 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 7800 | MONACILLOS TC - BARIOA TO | 2026-08-19 | 0.15895 | Bayamon | 50 | 0.96335 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3600 | MONACILLOS TC - BARIOA TO | 2026-08-19 | 0.014392 | San Juan | 50 | 0.087222 | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 7700 | MONACILLOS TC - BARIOA TO | 2026-08-20 | 0.075006 | Caguas | 50 | 0.45458 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50800 | MONACILLOS TC - BARIOA TO | 2026-08-19 | 0.00094697 | Caguas | 100 | 0.011478 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50800 | MONACILLOS TC - BARIOA TO | 2026-08-17 | 0.046815 | Caguas | 100 | 0.56746 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50800 | MONACILLOS TC - BARIOA TO | 2026-08-17 | 0.06893 | Caguas | 100 | 0.83551 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36400 | MONACILLOS TC - BARIOA TO | 2026-08-20 | 5.3207e-05 | Arecibo | 100 | 0.00064494 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50800 | MONACILLOS TC - BARIOA TO | 2026-08-17 | 0.10973 | Caguas | 100 | 1.33 |  | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36400 | MONACILLOS TC - BARIOA TO | 2026-08-21 | 5.3207e-05 | Arecibo | 100 | 0.00064494 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50800 | MONACILLOS TC - BARIOA TO | 2026-08-18 | 0.086083 | Caguas | 100 | 1.0434 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36400 | MONACILLOS TC - BARIOA TO | 2026-08-20 | 0.18342 | Arecibo | 100 | 2.2233 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 9300 | MONACILLOS TC - BARIOA TO | 2026-08-20 | 0.026992 | Caguas | 50 | 0.16359 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 9300 | MONACILLOS TC - BARIOA TO | 2026-08-20 | 0.028838 | Caguas | 50 | 0.17478 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 9300 | MONACILLOS TC - BARIOA TO | 2026-08-21 | 0.028838 | Caguas | 50 | 0.17478 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 15700 | MONACILLOS TC - BARIOA TO | 2026-08-20 | 0.062158 | Mayaguez | 50 | 0.37671 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 15700 | MONACILLOS TC - BARIOA TO | 2026-08-20 | 0.033146 | Mayaguez | 50 | 0.20088 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 7700 | MONACILLOS TC - BARIOA TO | 2026-08-21 | 0.026423 | CAGUAS | 50 | 0.16014 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 5600 | MONACILLOS TC - BARIOA TO | 2026-08-20 | 0.00094697 | Mayaguez | 50 | 0.0057392 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 7800 | MONACILLOS TC - BARIOA TO | 2026-08-21 | 0.090196 | Bayamon | 50 | 0.54664 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37200 | MONACILLOS TC - BARIOA TO | 2026-08-20 | 0.00094697 | Mayaguez | 100 | 0.011478 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 7800 | MONACILLOS TC - BARIOA TO | 2026-08-21 | 0.069051 | Bayamon | 50 | 0.41849 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 7700 | MONACILLOS TC - BARIOA TO | 2026-08-21 | 0.041936 | Caguas | 50 | 0.25416 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 39100 | MONACILLOS TC - BARIOA TO | 2026-08-20 | 0.00094697 | Mayaguez | 100 | 0.011478 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 7800 | MONACILLOS TC - BARIOA TO | 2026-08-21 | 0.048661 | Bayamon | 50 | 0.29491 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 7800 | MONACILLOS TC - BARIOA TO | 2026-08-21 | 0.057136 | Bayamon | 50 | 0.34628 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 7800 | MONACILLOS TC - BARIOA TO | 2026-08-21 | 0.039444 | Bayamon | 50 | 0.23905 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 7800 | MONACILLOS TC - BARIOA TO | 2026-08-21 | 0.15895 | Bayamon | 50 | 0.96335 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50500 | MONACILLOS TC - BARIOA TO | 2026-08-20 | 0.092882 | Mayaguez | 100 | 1.1258 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37200 | MONACILLOS TC - BARIOA TO | 2026-08-20 | 0.092502 | Mayaguez | 100 | 1.1212 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36400 | MONACILLOS TC - BARIOA TO | 2026-08-20 | 0.18342 | Arecibo | 100 | 2.2233 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36400 | MONACILLOS TC - BARIOA TO | 2026-08-21 | 7.5039e-05 | Arecibo | 100 | 0.00090956 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36400 | MONACILLOS TC - BARIOA TO | 2026-08-21 | 7.5039e-05 | Arecibo | 100 | 0.00090956 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36400 | MONACILLOS TC - BARIOA TO | 2026-08-21 | 7.5039e-05 | Arecibo | 100 | 0.00090956 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2100 | MONACILLOS TC - BARIOA TO | 2026-08-20 | 0.040389 | Arecibo | 50 | 0.24478 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 51200 | MONACILLOS TC - BARIOA TO | 2026-08-19 | 0.00094697 | Arecibo | 100 | 0.011478 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37100 | MONACILLOS TC - BARIOA TO | 2026-08-21 | 0.00094697 | Ponce | 100 | 0.011478 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37100 | MONACILLOS TC - BARIOA TO | 2026-08-21 | 0.081029 | Ponce | 100 | 0.98217 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50800 | MONACILLOS TC - BARIOA TO | 2026-08-18 | 0.00094697 | Caguas | 100 | 0.011478 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 8100 | MONACILLOS TC - BARIOA TO | 2026-08-21 | 0.14354 | Mayaguez | 50 | 0.86992 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50800 | MONACILLOS TC - BARIOA TO | 2026-08-21 | 0.00094697 | Caguas | 100 | 0.011478 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50800 | MONACILLOS TC - BARIOA TO | 2026-08-20 | 0.00094697 | Caguas | 100 | 0.011478 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 39100 | MONACILLOS TC - BARIOA TO | 2026-08-21 | 0.00094697 | Mayaguez | 100 | 0.011478 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2800 | MONACILLOS TC - BARIOA TO | 2026-08-21 | 0.00094697 | Mayaguez | 50 | 0.0057392 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2500 | MONACILLOS TC - BARIOA TO | 2026-08-21 | 0.00094697 | Mayaguez | 50 | 0.0057392 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 39800 | MONACILLOS TC - BARIOA TO | 2026-08-21 | 0.00094697 | Mayaguez | 100 | 0.011478 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 39800 | MONACILLOS TC - BARIOA TO | 2026-08-21 | 0.00094697 | Mayaguez | 100 | 0.011478 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 39800 | MONACILLOS TC - BARIOA TO | 2026-08-21 | 0.00094697 | Mayaguez | 100 | 0.011478 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 9300 | MONACILLOS TC - BARIOA TO | 2026-08-22 | 0.14738 | Caguas | 50 | 0.89324 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36400 | MONACILLOS TC - BARIOA TO | 2026-08-21 | 0.081856 | Arecibo | 100 | 0.9922 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36400 | MONACILLOS TC - BARIOA TO | 2026-08-21 | 0.18829 | Arecibo | 100 | 2.2823 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36400 | MONACILLOS TC - BARIOA TO | 2026-08-21 | 0.22377 | Arecibo | 100 | 2.7124 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36400 | MONACILLOS TC - BARIOA TO | 2026-08-21 | 0.10985 | Arecibo | 100 | 1.3315 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 7700 | MONACILLOS TC - BARIOA TO | 2026-08-20 | 0.00094697 | Caguas | 50 | 0.0057392 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37400 | MONACILLOS TC - BARIOA TO | 2026-08-21 | 0.054096 | Bayamon | 100 | 0.65571 | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2500 | MONACILLOS TC - BARIOA TO | 2026-08-22 | 0.03655 | Mayaguez | 50 | 0.22151 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36400 | MONACILLOS TC - BARIOA TO | 2026-08-22 | 0.097709 | Arecibo | 100 | 1.1844 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 13400 | MONACILLOS TC - BARIOA TO | 2026-08-21 | 0.00094697 | Mayaguez | 50 | 0.0057392 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2500 | MONACILLOS TC - BARIOA TO | 2026-08-21 | 0.030163 | Mayaguez | 50 | 0.1828 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37200 |  | 2026-08-27 | 0.00094697 | Mayaguez | 100 | 0.011478 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50200 |  | 2026-08-26 | 3.8595e-05 | Bayamon | 100 | 0.00046782 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50200 |  | 2026-08-27 | 7.0942e-05 | Bayamon | 100 | 0.00085991 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50500 |  | 2026-08-25 | 0.00094697 | Mayaguez | 100 | 0.011478 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50200 |  | 2026-08-27 | 4.8349e-05 | Bayamon | 100 | 0.00058605 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50200 |  | 2026-08-27 | 0.086172 | Bayamon | 100 | 1.0445 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50200 |  | 2026-08-26 | 3.0442e-05 | Arecibo | 100 | 0.00036899 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50200 |  | 2026-08-27 | 6.2557e-05 | Bayamon | 100 | 0.00075827 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50200 |  | 2026-08-26 | 0.14233 | Arecibo | 100 | 1.7253 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 6500 |  | 2026-08-27 | 0.043909 | Caguas | 50 | 0.26612 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3400 |  | 2026-08-23 | 0.046203 | Bayamon | 50 | 0.28002 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-25 | 0.00094697 | Arecibo | 50 | 0.0057392 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-26 | 0.028722 | Arecibo | 50 | 0.17407 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 100 |  | 2026-08-29 | 0.04101 | Ponce | 50 | 0.24855 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 100 |  | 2026-08-28 | 0.050642 | Ponce | 50 | 0.30692 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 100 |  | 2026-08-28 | 0.035065 | Ponce | 50 | 0.21251 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 100 |  | 2026-08-28 | 0.054307 | Ponce | 50 | 0.32913 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 100 |  | 2026-08-24 | 0.03169 | Ponce | 50 | 0.19206 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36400 |  | 2026-08-26 | 0.15124 | Arecibo | 100 | 1.8332 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2000 |  | 2026-08-28 | 0.1048 | Mayaguez | 50 | 0.63516 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50200 |  | 2026-08-28 | 0.14484 | Bayamon | 100 | 1.7556 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50300 | COSTA SUR SP - AGUIRRE SP | 2026-08-26 | 4.49e-05 | Ponce | 100 | 0.00054424 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50300 |  | 2026-08-24 | 5.3921e-05 | Ponce | 100 | 0.00065358 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-27 | 0.051574 | Arecibo | 50 | 0.31257 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-27 | 0.034797 | Arecibo | 50 | 0.21089 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-26 | 0.025476 | Arecibo | 50 | 0.1544 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-26 | 0.032311 | Arecibo | 50 | 0.19583 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-26 | 0.029826 | Arecibo | 50 | 0.18076 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-26 | 0.033554 | Arecibo | 50 | 0.20336 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-26 | 0.029204 | Arecibo | 50 | 0.177 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-26 | 0.030447 | Arecibo | 50 | 0.18453 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50200 |  | 2026-08-28 | 4.6587e-05 | Bayamon | 100 | 0.00056469 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50300 | COSTA SUR SP - AGUIRRE SP | 2026-08-26 | 5.8296e-05 | Ponce | 100 | 0.00070661 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50300 | COSTA SUR SP - AGUIRRE SP | 2026-08-26 | 0.17658 | Ponce | 100 | 2.1404 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50300 | COSTA SUR SP - AGUIRRE SP | 2026-08-27 | 0.17658 | Ponce | 100 | 2.1404 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50300 | COSTA SUR SP - AGUIRRE SP | 2026-08-29 | 0.17603 | Ponce | 100 | 2.1337 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50300 |  | 2026-08-28 | 7.073e-05 | Ponce | 100 | 0.00085733 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3100 |  | 2026-08-26 | 0.026249 | San Juan | 50 | 0.15909 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3600 |  | 2026-08-28 | 0.034534 | San Juan | 50 | 0.2093 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-24 | 0.043387 | Arecibo | 50 | 0.26295 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 7900 |  | 2026-08-27 | 0.00094697 | Ponce | 50 | 0.0057392 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-24 | 0.034797 | Arecibo | 50 | 0.21089 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-26 | 0.030447 | Arecibo | 50 | 0.18453 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-28 | 0.039273 | Arecibo | 50 | 0.23802 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-27 | 0.017582 | Arecibo | 50 | 0.10656 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-27 | 0.014283 | Arecibo | 50 | 0.086562 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3100 |  | 2026-08-27 | 4.2879e-06 | San Juan | 50 | 2.5988e-05 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3100 |  | 2026-08-27 | 0.00094697 | San Juan | 50 | 0.0057392 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-25 | 0.040505 | Arecibo | 50 | 0.24548 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-25 | 0.048746 | Arecibo | 50 | 0.29543 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-25 | 0.027839 | Arecibo | 50 | 0.16872 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-28 | 0.0093206 | Arecibo | 50 | 0.056489 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-26 | 0.042875 | Arecibo | 50 | 0.25985 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-28 | 0.045981 | Arecibo | 50 | 0.27868 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-28 | 0.047224 | Arecibo | 50 | 0.28621 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-28 | 0.042875 | Arecibo | 50 | 0.25985 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 300 |  | 2026-08-27 | 0.016787 | Ponce | 50 | 0.10174 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 7900 |  | 2026-08-27 | 0.017244 | Ponce | 50 | 0.10451 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 7900 |  | 2026-08-27 | 0.024855 | Ponce | 50 | 0.15064 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 7900 |  | 2026-08-27 | 0.018641 | Ponce | 50 | 0.11298 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-28 | 0.024234 | Arecibo | 50 | 0.14687 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-28 | 0.025963 | Arecibo | 50 | 0.15735 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-28 | 0.016972 | Arecibo | 50 | 0.10286 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-28 | 0.0057769 | Arecibo | 50 | 0.035011 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-28 | 0.019062 | Arecibo | 50 | 0.11553 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-28 | 0.019479 | Arecibo | 50 | 0.11806 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-28 | 0.018972 | Arecibo | 50 | 0.11498 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-28 | 0.018453 | Arecibo | 50 | 0.11184 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-29 | 0.039817 | Arecibo | 50 | 0.24132 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-28 | 0.016085 | Arecibo | 50 | 0.097486 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-28 | 0.043496 | Arecibo | 50 | 0.26361 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50200 |  | 2026-08-28 | 4.1669e-05 | Bayamon | 100 | 0.00050508 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50200 |  | 2026-08-28 | 0.13714 | Arecibo | 100 | 1.6624 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-29 | 0.027962 | Arecibo | 50 | 0.16947 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-29 | 0.035418 | Arecibo | 50 | 0.21466 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-29 | 0.03169 | Arecibo | 50 | 0.19206 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-29 | 0.028583 | Arecibo | 50 | 0.17323 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-29 | 0.030447 | Arecibo | 50 | 0.18453 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-24 | 0.029677 | Arecibo | 50 | 0.17986 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-24 | 0.0348 | Arecibo | 50 | 0.21091 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3100 |  | 2026-08-27 | 0.040979 | San Juan | 50 | 0.24836 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-29 | 0.03169 | Arecibo | 50 | 0.19206 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3100 |  | 2026-08-27 | 0.026323 | San Juan | 50 | 0.15953 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 8100 |  | 2026-08-24 | 0.13019 | Arecibo | 50 | 0.78903 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 500 |  | 2026-08-27 | 0.026098 | Ponce | 50 | 0.15817 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 500 | SAN SEBASTIAN TC | 2026-08-27 | 0.056678 | Ponce | 50 | 0.3435 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36700 |  | 2026-08-24 | 0.058455 | Mayaguez | 100 | 0.70854 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3600 |  | 2026-08-25 | 0.061751 | San Juan | 50 | 0.37425 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3100 |  | 2026-08-24 | 0.050444 | San Juan | 50 | 0.30572 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3100 |  | 2026-08-27 | 0.050194 | San Juan | 50 | 0.30421 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36700 |  | 2026-08-24 | 0.17688 | Mayaguez | 100 | 2.144 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 7800 |  | 2026-08-25 | 0.082207 | Bayamon | 50 | 0.49823 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 7800 |  | 2026-08-25 | 0.06106 | Bayamon | 50 | 0.37006 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 7800 | SAN SEBASTIAN TC | 2026-08-25 | 0.05625 | Bayamon | 50 | 0.34091 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36700 |  | 2026-08-24 | 0.092066 | Mayaguez | 100 | 1.116 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 7800 |  | 2026-08-25 | 0.05863 | Bayamon | 50 | 0.35533 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2100 | SAN SEBASTIAN TC | 2026-08-23 | 0.027085 | Arecibo | 50 | 0.16415 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36700 | SAN SEBASTIAN TC | 2026-08-25 | 0.19013 | Mayaguez | 100 | 2.3047 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50500 | SAN SEBASTIAN TC | 2026-08-25 | 0.19078 | Mayaguez | 100 | 2.3125 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37200 |  | 2026-08-25 | 0.18884 | Mayaguez | 100 | 2.289 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 7800 |  | 2026-08-25 | 0.038651 | Bayamon | 50 | 0.23425 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36400 |  | 2026-08-24 | 0.079014 | Arecibo | 100 | 0.95774 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 15900 | CABO ROJO TO | 2026-08-24 | 0.034443 | Mayaguez | 50 | 0.20874 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 13400 | AGUADILLA HOSPITAL DISTRITO SECT | 2026-08-23 | 0.00094697 | Mayaguez | 50 | 0.0057392 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2800 | AGUADILLA HOSPITAL DISTRITO SECT | 2026-08-23 | 0.00094697 | Mayaguez | 50 | 0.0057392 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2800 | SAN GERMAN TO | 2026-08-26 | 0.00094697 | Mayaguez | 50 | 0.0057392 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37100 | AGUADILLA HOSPITAL DISTRITO TO | 2026-08-24 | 0.12171 | Ponce | 100 | 1.4752 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2500 | BAYAMON PUEBLO SECT - BAYAMON PUEBLO SECT | 2026-08-24 | 0.028355 | Mayaguez | 50 | 0.17185 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 13400 |  | 2026-08-24 | 0.048971 | Mayaguez | 50 | 0.2968 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36700 |  | 2026-08-26 | 0.10895 | Mayaguez | 100 | 1.3206 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36700 |  | 2026-08-24 | 0.061777 | Mayaguez | 100 | 0.74881 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36700 |  | 2026-08-25 | 0.075146 | Mayaguez | 100 | 0.91086 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 6500 |  | 2026-08-24 | 0.040485 | Caguas | 50 | 0.24537 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37100 |  | 2026-08-24 | 0.00094697 | Ponce | 100 | 0.011478 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 6500 | CABO ROJO TO | 2026-08-24 | 0.028413 | Caguas | 50 | 0.1722 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 13400 |  | 2026-08-24 | 0.00094697 | Mayaguez | 50 | 0.0057392 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 6500 |  | 2026-08-24 | 0.032772 | Caguas | 50 | 0.19862 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37100 |  | 2026-08-24 | 0.00094697 | Ponce | 100 | 0.011478 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37100 |  | 2026-08-24 | 0.00094697 | Ponce | 100 | 0.011478 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3600 |  | 2026-08-26 | 0.055472 | San Juan | 50 | 0.3362 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3100 |  | 2026-08-26 | 0.054986 | San Juan | 50 | 0.33325 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37100 | COSTA SUR SP | 2026-08-24 | 0.00094697 | Ponce | 100 | 0.011478 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37100 |  | 2026-08-24 | 0.00094697 | Ponce | 100 | 0.011478 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3400 |  | 2026-08-25 | 0.069255 | Bayamon | 50 | 0.41973 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 10100 | COSTA SUR SP | 2026-08-24 | 0.00015397 | San Juan | 50 | 0.00093316 | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37100 | AGUADILLA HOSPITAL DISTRITO SECT | 2026-08-24 | 0.068955 | Ponce | 100 | 0.83582 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2500 |  | 2026-08-24 | 0.032843 | Mayaguez | 50 | 0.19905 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 51200 |  | 2026-08-24 | 0.00094697 | Arecibo | 100 | 0.011478 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 38300 |  | 2026-08-24 | 0.11752 | San Juan | 100 | 1.4245 | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37100 |  | 2026-08-27 | 0.099766 | Ponce | 100 | 1.2093 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 39100 |  | 2026-08-26 | 0.00094697 | Mayaguez | 100 | 0.011478 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36700 |  | 2026-08-26 | 0.09295 | Mayaguez | 100 | 1.1267 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 15900 |  | 2026-08-26 | 0.15794 | Mayaguez | 50 | 0.9572 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2300 |  | 2026-08-25 | 0.00094697 | Arecibo | 50 | 0.0057392 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2300 |  | 2026-08-25 | 6.5651e-06 | Arecibo | 50 | 3.9789e-05 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2300 |  | 2026-08-26 | 0.00094697 | Arecibo | 50 | 0.0057392 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2300 |  | 2026-08-25 | 0.12767 | Arecibo | 50 | 0.77374 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2300 |  | 2026-08-26 | 0.00094697 | Arecibo | 50 | 0.0057392 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36700 |  | 2026-08-27 | 0.12769 | Mayaguez | 100 | 1.5477 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50500 |  | 2026-08-26 | 0.12651 | Mayaguez | 100 | 1.5335 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37200 |  | 2026-08-27 | 0.12611 | Mayaguez | 100 | 1.5286 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 9100 |  | 2026-08-25 | 0.035583 | Bayamon | 50 | 0.21565 | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-28 | 0.043496 | Arecibo | 50 | 0.26361 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-28 | 0.04101 | Arecibo | 50 | 0.24855 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-28 | 0.041691 | Arecibo | 50 | 0.25268 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 5600 | AGUADA TO | 2026-08-26 | 0.00094697 | Mayaguez | 50 | 0.0057392 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 5600 |  | 2026-08-26 | 0.066507 | Mayaguez | 50 | 0.40307 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 6500 |  | 2026-08-26 | 0.043909 | Caguas | 50 | 0.26612 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 4400 |  | 2026-08-25 | 0.04101 | Bayamon | 50 | 0.24855 | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 15900 |  | 2026-08-26 | 0.00094697 | Mayaguez | 50 | 0.0057392 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 6500 |  | 2026-08-27 | 0.028522 | Caguas | 50 | 0.17286 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 6500 |  | 2026-08-24 | 0.03234 | Caguas | 50 | 0.196 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37100 |  | 2026-08-26 | 0.076992 | Ponce | 100 | 0.93323 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37100 |  | 2026-08-26 | 0.075691 | Ponce | 100 | 0.91747 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-26 | 0.033554 | Arecibo | 50 | 0.20336 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 15900 |  | 2026-08-29 | 0.052375 | Mayaguez | 50 | 0.31742 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 6500 |  | 2026-08-26 | 0.018363 | Caguas | 50 | 0.11129 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36700 | SAN SEBASTIAN TC | 2026-08-27 | 0.093723 | Mayaguez | 100 | 1.136 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50500 | SAN SEBASTIAN TC | 2026-08-27 | 0.087955 | Mayaguez | 100 | 1.0661 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37200 |  | 2026-08-27 | 0.0875 | Mayaguez | 100 | 1.0606 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2300 |  | 2026-08-26 | 0.00094697 | Arecibo | 50 | 0.0057392 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2300 |  | 2026-08-27 | 0.11318 | Arecibo | 50 | 0.68594 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3300 |  | 2026-08-26 | 0.058166 | San Juan | 50 | 0.35252 | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2300 |  | 2026-08-26 | 0.00094697 | Arecibo | 50 | 0.0057392 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36100 |  | 2026-08-26 | 0.066277 | Bayamon | 100 | 0.80335 | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36100 |  | 2026-08-26 | 3.7172e-05 | Bayamon | 100 | 0.00045057 | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 9800 |  | 2026-08-26 | 0.00094697 | Bayamon | 50 | 0.0057392 | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 1500 |  | 2026-08-27 | 0.00094697 | Mayaguez | 50 | 0.0057392 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 11400 | AGUADA TO | 2026-08-26 | 0.1249 | Arecibo | 50 | 0.75694 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 5600 |  | 2026-08-27 | 0.06241 | Mayaguez | 50 | 0.37824 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 6500 |  | 2026-08-27 | 0.036524 | Caguas | 50 | 0.22136 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50700 |  | 2026-08-25 | 0.12257 | Caguas | 100 | 1.4857 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36200 | GAUTIER BENITEZ SECT - JUNCOS TC | 2026-08-26 | 0.12633 | Caguas | 100 | 1.5313 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 9300 |  | 2026-08-24 | 0.050402 | Caguas | 50 | 0.30547 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50700 |  | 2026-08-25 | 6.7419e-05 | Caguas | 100 | 0.0008172 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 9300 |  | 2026-08-24 | 0.05556 | Caguas | 50 | 0.33673 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 9300 | SAN SEBASTIAN TC | 2026-08-24 | 0.12857 | Caguas | 50 | 0.77924 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37200 |  | 2026-08-27 | 0.00094697 | Mayaguez | 100 | 0.011478 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36700 | SAN SEBASTIAN TC | 2026-08-27 | 0.039075 | Mayaguez | 100 | 0.47364 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50500 | SAN SEBASTIAN TC | 2026-08-27 | 0.046954 | Mayaguez | 100 | 0.56914 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37200 |  | 2026-08-27 | 0.083018 | Mayaguez | 100 | 1.0063 | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3100 |  | 2026-08-27 | 0.054219 | San Juan | 50 | 0.3286 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36400 |  | 2026-08-27 | 0.053937 | Arecibo | 100 | 0.65379 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 51200 |  | 2026-08-28 | 5.6701e-05 | Arecibo | 100 | 0.00068728 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36400 |  | 2026-08-28 | 0.075882 | Arecibo | 100 | 0.91979 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36400 | DOS BOCAS HP | 2026-08-29 | 0.091095 | Arecibo | 100 | 1.1042 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36400 |  | 2026-08-27 | 0.1766 | Arecibo | 100 | 2.1407 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3100 | AGUADA TO | 2026-08-28 | 0.038792 | San Juan | 50 | 0.2351 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 5600 | AGUADA TO | 2026-08-27 | 0.03808 | Mayaguez | 50 | 0.23079 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 15900 |  | 2026-08-27 | 0.00094697 | Mayaguez | 50 | 0.0057392 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36200 |  | 2026-08-27 | 0.12601 | San Juan | 100 | 1.5275 | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3100 |  | 2026-08-28 | 0.034633 | San Juan | 50 | 0.2099 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 6500 |  | 2026-08-28 | 0.027624 | Caguas | 50 | 0.16742 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3100 |  | 2026-08-28 | 0.031758 | San Juan | 50 | 0.19247 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 3100 |  | 2026-08-28 | 0.031425 | San Juan | 50 | 0.19045 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 230 | 50200 |  | 2026-08-28 | 0.080577 | Bayamon | 100 | 0.9767 | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 15900 | DAGUAO TC - RIO BLANCO HP | 2026-08-28 | 0.00094697 | Mayaguez | 50 | 0.0057392 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36200 |  | 2026-08-27 | 0.12179 | Caguas | 100 | 1.4763 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 13400 | ACACIAS TC | 2026-08-28 | 0.15444 | Mayaguez | 50 | 0.936 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 13400 |  | 2026-08-28 | 0.094051 | Mayaguez | 50 | 0.57 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36400 |  | 2026-08-28 | 4.4021e-05 | Arecibo | 100 | 0.00053359 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36400 |  | 2026-08-28 | 0.076747 | Arecibo | 100 | 0.93026 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 13kv | 1720-07 |  | 2026-08-28 | 0 | Bayamon | 50 | 0 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 6500 |  | 2026-08-28 | 0.022282 | Caguas | 50 | 0.13504 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 6500 |  | 2026-08-29 | 0.037217 | Caguas | 50 | 0.22556 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36200 |  | 2026-08-29 | 0.12543 | San Juan | 100 | 1.5203 | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-29 | 0.042253 | Arecibo | 50 | 0.25608 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-29 | 0.026218 | Arecibo | 50 | 0.1589 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-29 | 0.041432 | Arecibo | 50 | 0.2511 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | CAMBALACHE TC | 2026-08-29 | 0.034175 | Arecibo | 50 | 0.20712 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | CAMBALACHE TC | 2026-08-29 | 0.03169 | Arecibo | 50 | 0.19206 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | CAMBALACHE TC | 2026-08-29 | 0.03169 | Arecibo | 50 | 0.19206 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-29 | 0.02285 | Arecibo | 50 | 0.13849 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | CAMBALACHE TC | 2026-08-29 | 0.028695 | Arecibo | 50 | 0.17391 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-29 | 0.042253 | Arecibo | 50 | 0.25608 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-29 | 0.046191 | Arecibo | 50 | 0.27994 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-29 | 0.050772 | Arecibo | 50 | 0.30771 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-29 | 0.033554 | Arecibo | 50 | 0.20336 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-29 | 0.031839 | Arecibo | 50 | 0.19296 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-29 | 0.039828 | Arecibo | 50 | 0.24138 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-29 | 0.035967 | Arecibo | 50 | 0.21798 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-29 | 0.0398 | Arecibo | 50 | 0.24121 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-29 | 0.035306 | Arecibo | 50 | 0.21397 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-29 | 0.03129 | Arecibo | 50 | 0.18963 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-29 | 0.039768 | Arecibo | 50 | 0.24102 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-29 | 0.0263 | Arecibo | 50 | 0.1594 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | SAN GERMAN TO | 2026-08-29 | 0.035412 | Arecibo | 50 | 0.21462 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 37100 |  | 2026-08-29 | 0.13342 | Ponce | 100 | 1.6172 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-29 | 0.01258 | Arecibo | 50 | 0.076241 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-29 | 0.041001 | Arecibo | 50 | 0.24849 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-29 | 0.04228 | Arecibo | 50 | 0.25625 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | AGUADA TO | 2026-08-29 | 0.041172 | Arecibo | 50 | 0.24953 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 15900 |  | 2026-08-29 | 0.036661 | Mayaguez | 50 | 0.22219 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 | ACACIAS TC | 2026-08-29 | 0.050002 | Arecibo | 50 | 0.30304 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 13400 |  | 2026-08-29 | 0.0948 | Mayaguez | 50 | 0.57455 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 2200 |  | 2026-08-29 | 0.02415 | Arecibo | 50 | 0.14636 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 38 | 7800 |  | 2026-08-29 | 0.097848 | Bayamon | 50 | 0.59302 | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
n/a | 115 | 36400 |  | 2026-08-29 | 0.00094697 | Arecibo | 100 | 0.011478 | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
956348 | 38 | 10000 | Bayamon Pueblo - Magnolia TO | 2026-08-13 | 0.027 | Bayamón | 50 | 0.16364 | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956345 | 38 | 2400 | Dos Bocas HP - Caonillas 2 | 2026-08-17 | 0.0138 | Arecibo | 50 | 0.083636 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956345 | 38 | 2400 | Dos Bocas HP - Caonillas 2 | 2026-08-06 | 0.2362 | Utuado | 50 | 1.4315 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956345 | 38 | 2400 | Dos Bocas HP - Caonillas 2 | 2026-08-07 | 0.0557 | Utuado | 50 | 0.33758 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956345 | 38 | 2400 | Dos Bocas HP - Caonillas 2 | 2026-08-17 | 0.0817 | Utuado | 50 | 0.49515 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956353 | 115 | 36100 | Dos Bocas HP - Barrio Pina | 2026-08-26 | 0.1232 | Toa Alta | 100 | 1.4933 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956353 | 115 | 36100 | Dos Bocas HP - Barrio Pina | 2026-08-27 | 0.0817 | Toa Alta | 100 | 0.9903 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956353 | 115 | 36100 | Dos Bocas HP - Barrio Pina | 2026-08-31 | 0.0895 | Toa Alta | 100 | 1.0848 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956348 | 38 | 10000 | Bayamon Pueblo - Magnolia TO | 2026-08-04 | 0.0038 | Bayamón | 50 | 0.02303 | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956348 | 38 | 10000 | Bayamon Pueblo - Magnolia TO | 2026-08-06 | 0.1444 | Bayamón | 50 | 0.87515 | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956348 | 38 | 10000 | Bayamon Pueblo - Magnolia TO | 2026-08-07 | 0.4445 | Bayamón | 50 | 2.6939 | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956348 | 38 | 10000 | Bayamon Pueblo - Magnolia TO | 2026-08-11 | 0.1127 | Bayamón | 50 | 0.68303 | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956357 | 38 | 1900 | Dos Bocas HP - San Sebastian TC | 2026-08-10 | 0.0435 | Lares | 50 | 0.26364 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956357 | 38 | 1900 | Dos Bocas HP - San Sebastian TC | 2026-08-11 | 0.1094 | Lares | 50 | 0.66303 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956357 | 38 | 1900 | Dos Bocas HP - San Sebastian TC | 2026-08-12 | 0.019 | Lares | 50 | 0.11515 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956357 | 38 | 1900 | Dos Bocas HP - San Sebastian TC | 2026-08-13 | 0.3017 | Lares | 50 | 1.8285 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956357 | 38 | 1900 | Dos Bocas HP - San Sebastian TC | 2026-08-17 | 0.0965 | Lares | 50 | 0.58485 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956357 | 38 | 1900 | Dos Bocas HP - San Sebastian TC | 2026-08-18 | 0.1127 | Lares | 50 | 0.68303 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956357 | 38 | 1900 | Dos Bocas HP - San Sebastian TC | 2026-08-19 | 0.0416 | Lares | 50 | 0.25212 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956357 | 38 | 1900 | Dos Bocas HP - San Sebastian TC | 2026-08-20 | 0.1886 | Lares | 50 | 1.143 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956357 | 38 | 1900 | Dos Bocas HP - San Sebastian TC | 2026-08-24 | 0.0545 | Lares | 50 | 0.3303 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956357 | 38 | 1900 | Dos Bocas HP - San Sebastian TC | 2026-08-25 | 0.0185 | Lares | 50 | 0.11212 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956357 | 38 | 1900 | Dos Bocas HP - San Sebastian TC | 2026-08-26 | 0.0795 | Lares | 50 | 0.48182 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956357 | 38 | 1900 | Dos Bocas HP - San Sebastian TC | 2026-08-27 | 0.1477 | Lares | 50 | 0.89515 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956357 | 38 | 1900 | Dos Bocas HP - San Sebastian TC | 2026-08-28 | 0.4239 | Lares | 50 | 2.5691 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956357 | 38 | 1900 | Dos Bocas HP - San Sebastian TC | 2026-08-31 | 0.1527 | Lares | 50 | 0.92545 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956357 | 38 | 1900 | Dos Bocas HP - San Sebastian TC | 2026-08-04 | 0.0835 | Utuado | 50 | 0.50606 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956357 | 38 | 1900 | Dos Bocas HP - San Sebastian TC | 2026-08-05 | 0.7993 | Utuado | 50 | 4.8442 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956357 | 38 | 1900 | Dos Bocas HP - San Sebastian TC | 2026-08-06 | 0.6332 | Utuado | 50 | 3.8376 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956357 | 38 | 1900 | Dos Bocas HP - San Sebastian TC | 2026-08-07 | 0.0788 | Utuado | 50 | 0.47758 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956357 | 38 | 1900 | Dos Bocas HP - San Sebastian TC | 2026-08-10 | 0.1131 | Utuado | 50 | 0.68545 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956357 | 38 | 1900 | Dos Bocas HP - San Sebastian TC | 2026-08-12 | 0.1096 | Utuado | 50 | 0.66424 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956357 | 38 | 1900 | Dos Bocas HP - San Sebastian TC | 2026-08-13 | 0.247 | Utuado | 50 | 1.497 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956357 | 38 | 1900 | Dos Bocas HP - San Sebastian TC | 2026-08-18 | 0.0251 | Utuado | 50 | 0.15212 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956357 | 38 | 1900 | Dos Bocas HP - San Sebastian TC | 2026-08-20 | 0.1637 | Utuado | 50 | 0.99212 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956357 | 38 | 1900 | Dos Bocas HP - San Sebastian TC | 2026-08-21 | 0.0593 | Utuado | 50 | 0.35939 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956357 | 38 | 1900 | Dos Bocas HP - San Sebastian TC | 2026-08-25 | 0.0659 | Utuado | 50 | 0.39939 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956357 | 38 | 1900 | Dos Bocas HP - San Sebastian TC | 2026-08-26 | 0.1678 | Utuado | 50 | 1.017 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956357 | 38 | 1900 | Dos Bocas HP - San Sebastian TC | 2026-08-27 | 0.0776 | Utuado | 50 | 0.4703 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956357 | 38 | 1900 | Dos Bocas HP - San Sebastian TC | 2026-08-31 | 0.0155 | Utuado | 50 | 0.093939 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956357 | 38 | 1900 | Dos Bocas HP - San Sebastian TC | 2026-08-11 | 0.164 | Utuado | 50 | 0.99394 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956357 | 38 | 1900 | Dos Bocas HP - San Sebastian TC | 2026-08-03 | 0.4012 | Utuado | 50 | 2.4315 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956357 | 38 | 1900 | Dos Bocas HP - San Sebastian TC | 2026-08-29 | 0.1353 | Utuado | 50 | 0.82 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956357 | 38 | 1900 | Dos Bocas HP - San Sebastian TC | 2026-08-14 | 0.0872 | Lares | 50 | 0.52848 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956357 | 38 | 1900 | Dos Bocas HP - San Sebastian TC | 2026-08-21 | 0.0872 | Lares | 50 | 0.52848 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956357 | 38 | 1900 | Dos Bocas HP - San Sebastian TC | 2026-08-06 | 0.0194 | Lares | 50 | 0.11758 | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
Vegetation Maintenance and Clearing

## Distribution Feeders
Primary Distribution Feeders
FAASt | Line Voltage (kV) | Primary Distribution Line ID # | Clearing Date | Circuit Miles Maintained / Cleared | Right of Way (Rows) Width | ROW Acres Maintained / Cleared | Municipalities Impacted | Name of Contractor | Clearing Status | Type of Response | VM Activity Point of Contact (POC) | Funding Source | Month | Quarter | Fiscal Year
N/A | 2.40/4.16 | 6401-02 | 2026-07-01 | 0.015534 | 10 | 0.018829 | San German | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6401-02 | 2026-07-03 | 0.021127 | 10 | 0.025608 | San German | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6401-02 | 2026-07-03 | 0.021127 | 10 | 0.025608 | San German | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1109-05 | 2026-07-01 | 0.015393 | 10 | 0.018658 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 6702-02 | 2026-07-01 | 0.032933 | 10 | 0.039919 | Cabo Rojo | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 6702-02 | 2026-07-01 | 0.03604 | 10 | 0.043684 | Cabo Rojo | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 6702-02 | 2026-07-01 | 0.03604 | 10 | 0.043684 | Cabo Rojo | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1646-01 | 2026-07-02 | 0.023612 | 10 | 0.028621 | Carolina | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6501-02 | 2026-07-02 | 0.020505 | 10 | 0.024855 | Sabana Grande | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3205-08 | 2026-07-04 | 0.028307 | 10 | 0.034312 | Juncos | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3205-08 | 2026-07-04 | 0.028527 | 10 | 0.034578 | Juncos | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3701-02 | 2026-07-02 | 0.025476 | 10 | 0.03088 | Aguas Buenas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3701-02 | 2026-07-04 | 0.030447 | 10 | 0.036906 | Aguas Buenas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3701-02 | 2026-07-04 | 0.030447 | 10 | 0.036906 | Aguas Buenas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3701-02 | 2026-07-02 | 0.029204 | 10 | 0.035399 | Aguas Buenas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9501-02 | 2026-07-01 | 0.049291 | 10 | 0.059747 | Corozal | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9501-02 | 2026-07-02 | 0.096934 | 10 | 0.1175 | Corozal | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5902-02 | 2026-07-02 | 0.038525 | 10 | 0.046697 | Villalba | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5902-02 | 2026-07-02 | 0.018188 | 10 | 0.022046 | Villalba | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5902-02 | 2026-07-02 | 0.031097 | 10 | 0.037694 | Villalba | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8015-08 | 2026-07-01 | 0.016491 | 10 | 0.019989 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8002-03 | 2026-07-01 | 0.017215 | 10 | 0.020867 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8015-08 | 2026-07-01 | 0.033199 | 10 | 0.040242 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 4603-01 | 2026-07-03 | 0.019955 | 10 | 0.024188 | Villalba | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 4603-01 | 2026-07-03 | 0.046075 | 10 | 0.055849 | Villalba | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 4603-01 | 2026-07-03 | 0.047224 | 10 | 0.057242 | Villalba | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6401-02 | 2026-07-02 | 0.043496 | 10 | 0.052722 | San Germán | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 4603-01 | 2026-07-03 | 0.028409 | 10 | 0.034435 | Villalba | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 4603-01 | 2026-07-03 | 0.028409 | 10 | 0.034435 | Coamo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6401-02 | 2026-07-02 | 0.045981 | 10 | 0.055735 | San Germán | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 4603-01 | 2026-07-03 | 0.028518 | 10 | 0.034567 | Coamo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 4603-01 | 2026-07-02 | 0.028409 | 10 | 0.034435 | Coamo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 9405-05 | 2026-07-03 | 0.029991 | 10 | 0.036353 | Toa Alta | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 9405-05 | 2026-07-03 | 0.02993 | 10 | 0.036279 | Toa Alta | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 7903-06 | 2026-07-03 | 0.03166 | 10 | 0.038376 | Lares | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 7903-06 | 2026-07-03 | 0.029175 | 10 | 0.035363 | Lares | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3701-02 | 2026-07-04 | 0.033554 | 10 | 0.040671 | Aguas Buenas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 4602-01 | 2026-07-01 | 0.028409 | 10 | 0.034435 | Coamo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3701-02 | 2026-07-02 | 0.016777 | 10 | 0.020336 | Aguas Buenas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-02 | 2026-07-01 | 0.028579 | 10 | 0.034642 | Gurabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3701-02 | 2026-07-04 | 0.054681 | 10 | 0.06628 | Aguas Buenas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-07-02 | 0.025814 | 10 | 0.031289 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-07-02 | 0.026656 | 10 | 0.032311 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-07-02 | 0.030338 | 10 | 0.036773 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-07-02 | 0.029523 | 10 | 0.035786 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-07-02 | 0.035972 | 10 | 0.043602 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-07-02 | 0.020229 | 10 | 0.02452 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-07-01 | 0.029767 | 10 | 0.036082 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 7805-11 | 2026-07-02 | 0.027769 | 10 | 0.03366 | San Sebastián | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-07-01 | 0.03057 | 10 | 0.037054 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-07-01 | 0.02954 | 10 | 0.035806 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-02 | 2026-07-01 | 0.032237 | 10 | 0.039075 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-02 | 2026-07-01 | 0.032398 | 10 | 0.03927 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-02 | 2026-07-02 | 0.029879 | 10 | 0.036216 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1646-02 | 2026-07-01 | 0.031069 | 10 | 0.037659 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1646-02 | 2026-07-03 | 0.024855 | 10 | 0.030127 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 9405-05 | 2026-07-04 | 0.041632 | 10 | 0.050463 | Toa Alta | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-01 | 0.028409 | 10 | 0.034435 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-01 | 0.04659 | 10 | 0.056473 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-04 | 0.028409 | 10 | 0.034435 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-01 | 0.028409 | 10 | 0.034435 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-01 | 0.03169 | 10 | 0.038412 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-02 | 0.034797 | 10 | 0.042178 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-01 | 0.032311 | 10 | 0.039165 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-01 | 0.02734 | 10 | 0.03314 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-01 | 0.028409 | 10 | 0.034435 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-01 | 0.036661 | 10 | 0.044438 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-03 | 0.044117 | 10 | 0.053476 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-02 | 0.044117 | 10 | 0.053476 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1717-04 | 2026-07-02 | 0.016156 | 10 | 0.019583 | Bayamón | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1717-04 | 2026-07-02 | 0.02556 | 10 | 0.030982 | Bayamón | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3701-02 | 2026-07-02 | 0.032311 | 10 | 0.039165 | Aguas Buenas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3701-02 | 2026-07-02 | 0.17523 | 10 | 0.2124 | Aguas Buenas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-04 | 2026-07-02 | 0.037904 | 10 | 0.045944 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-04 | 2026-07-02 | 0.037904 | 10 | 0.045944 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-04 | 2026-07-02 | 0.027721 | 10 | 0.033601 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-03 | 2026-07-02 | 0.03092 | 10 | 0.037478 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 8701-04 | 2026-07-01 | 0.021127 | 10 | 0.025608 | Ciales | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 8701-04 | 2026-07-01 | 0.019262 | 10 | 0.023348 | Ciales | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-02 | 0.024345 | 10 | 0.029508 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-02 | 0.019668 | 10 | 0.02384 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-02 | 0.019622 | 10 | 0.023785 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-02 | 0.012194 | 10 | 0.01478 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-02 | 0.026186 | 10 | 0.031741 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1002-02 | 2026-07-01 | 0.031069 | 10 | 0.037659 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-02 | 2026-07-01 | 0.028409 | 10 | 0.034435 | Gurabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-02 | 2026-07-02 | 0.032099 | 10 | 0.038907 | Gurabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-01 | 0.039181 | 10 | 0.047492 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6010-01 | 2026-07-01 | 0.028409 | 10 | 0.034435 | Mayaguez | Xperts | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-02 | 0.041569 | 10 | 0.050387 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-02 | 0.042137 | 10 | 0.051075 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-01 | 0.041446 | 10 | 0.050238 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-02 | 0.034622 | 10 | 0.041966 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-02 | 0.035425 | 10 | 0.042939 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-04 | 0.028409 | 10 | 0.034435 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 8701-04 | 2026-07-01 | 0.033554 | 10 | 0.040671 | Ciales | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-01 | 0.017648 | 10 | 0.021392 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-01 | 0.010766 | 10 | 0.013049 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-01 | 0.020836 | 10 | 0.025256 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-01 | 0.011129 | 10 | 0.013489 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-01 | 0.024066 | 10 | 0.029171 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1602-05 | 2026-07-01 | 0.013189 | 10 | 0.015987 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-01 | 0.016634 | 10 | 0.020162 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1602-05 | 2026-07-02 | 0.019262 | 10 | 0.023348 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3701-02 | 2026-07-01 | 0.095691 | 10 | 0.11599 | Aguas Buenas | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-01 | 0.022369 | 10 | 0.027114 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-01 | 0.026719 | 10 | 0.032387 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-01 | 0.024855 | 10 | 0.030127 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-01 | 0.024855 | 10 | 0.030127 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-07-01 | 0.030964 | 10 | 0.037532 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-01 | 0.023612 | 10 | 0.028621 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7008-04 | 2026-07-01 | 0.034662 | 10 | 0.042014 | Aguada | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-01 | 0.024855 | 10 | 0.030127 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-07-01 | 0.029918 | 10 | 0.036265 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-01 | 0.01802 | 10 | 0.021842 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-07-01 | 0.032588 | 10 | 0.0395 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1602-05 | 2026-07-02 | 0.022561 | 10 | 0.027346 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1602-05 | 2026-07-01 | 0.030502 | 10 | 0.036973 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-01 | 0.017439 | 10 | 0.021138 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1602-05 | 2026-07-01 | 0.013609 | 10 | 0.016495 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3701-03 | 2026-07-01 | 0.031465 | 10 | 0.038139 | Comerío | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-01 | 0.01733 | 10 | 0.021006 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-01 | 0.0058578 | 10 | 0.0071003 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-01 | 0.0049136 | 10 | 0.0059559 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9501-02 | 2026-07-01 | 0.067002 | 10 | 0.081215 | Corozal | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2603-08 | 2026-07-01 | 0.032186 | 10 | 0.039014 | Humacao | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2603-09 | 2026-07-01 | 0.029477 | 10 | 0.035729 | Humacao | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-02 | 0.018504 | 10 | 0.022429 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2603-09 | 2026-07-02 | 0.030494 | 10 | 0.036963 | Humacao | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-02 | 0.016275 | 10 | 0.019728 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-02 | 0.030579 | 10 | 0.037065 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-02 | 0.025887 | 10 | 0.031378 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-02 | 0.02543 | 10 | 0.030824 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7008-04 | 2026-07-03 | 0.022169 | 10 | 0.026871 | Aguada | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-07-02 | 0.028409 | 10 | 0.034435 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-07-02 | 0.042699 | 10 | 0.051757 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1646-01 | 2026-07-01 | 0.014913 | 10 | 0.018076 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1646-01 | 2026-07-01 | 0.029826 | 10 | 0.036152 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7802-03 | 2026-07-01 | 0.028409 | 10 | 0.034435 | San Sebastián | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5003-03 | 2026-07-01 | 0.016156 | 10 | 0.019583 | Ponce | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8103-01 | 2026-07-01 | 0.028409 | 10 | 0.034435 | Utuado | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2603-08 | 2026-07-02 | 0.027914 | 10 | 0.033835 | Humacao | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-02 | 2026-07-02 | 0.030447 | 10 | 0.036906 | Gurabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-03 | 2026-07-02 | 0.030095 | 10 | 0.036479 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-04 | 2026-07-02 | 0.029971 | 10 | 0.036328 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-03 | 2026-07-02 | 0.028143 | 10 | 0.034112 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-04 | 2026-07-02 | 0.028035 | 10 | 0.033982 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-03 | 2026-07-02 | 0.029368 | 10 | 0.035597 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-04 | 2026-07-02 | 0.029332 | 10 | 0.035554 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-03 | 2026-07-02 | 0.026377 | 10 | 0.031972 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-04 | 2026-07-02 | 0.026374 | 10 | 0.031969 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-03 | 2026-07-02 | 0.019257 | 10 | 0.023342 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-04 | 2026-07-02 | 0.019649 | 10 | 0.023817 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-03 | 2026-07-02 | 0.025603 | 10 | 0.031034 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-04 | 2026-07-02 | 0.025441 | 10 | 0.030838 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-03 | 2026-07-02 | 0.031441 | 10 | 0.038111 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-04 | 2026-07-02 | 0.031244 | 10 | 0.037872 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-03 | 2026-07-02 | 0.022822 | 10 | 0.027663 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-04 | 2026-07-02 | 0.022212 | 10 | 0.026923 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-03 | 0.0093206 | 10 | 0.011298 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-03 | 2026-07-02 | 0.037282 | 10 | 0.045191 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-03 | 0.025476 | 10 | 0.03088 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-03 | 0.03169 | 10 | 0.038412 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-03 | 2026-07-02 | 0.059638 | 10 | 0.072288 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2603-08 | 2026-07-01 | 0.031043 | 10 | 0.037627 | Humacao | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-03 | 2026-07-02 | 0.035418 | 10 | 0.042931 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-03 | 2026-07-02 | 0.029826 | 10 | 0.036152 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-04 | 0.03169 | 10 | 0.038412 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2603-08 | 2026-07-01 | 0.030097 | 10 | 0.036482 | Humacao | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-03 | 2026-07-02 | 0.030447 | 10 | 0.036906 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-03 | 2026-07-02 | 0.024905 | 10 | 0.030188 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 8003-03 | 2026-07-04 | 0.024156 | 10 | 0.029281 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 8003-03 | 2026-07-04 | 0.026114 | 10 | 0.031654 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 8003-03 | 2026-07-04 | 0.023845 | 10 | 0.028902 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-07-02 | 0.047224 | 10 | 0.057242 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 8003-03 | 2026-07-04 | 0.01596 | 10 | 0.019345 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 8003-03 | 2026-07-04 | 0.021827 | 10 | 0.026458 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9902-02 | 2026-07-02 | 0.050331 | 10 | 0.061007 | Orocovis | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8301-03 | 2026-07-03 | 0.044359 | 10 | 0.053768 | Ciales | Xperts | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5013-02 | 2026-07-03 | 0.028409 | 10 | 0.034435 | Ponce | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-03 | 0.046013 | 10 | 0.055773 | Gurabo | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-03 | 0.026817 | 10 | 0.032506 | Gurabo | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7901-03 | 2026-07-03 | 0.028409 | 10 | 0.034435 | Lares | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1343-05 | 2026-07-04 | 0.027962 | 10 | 0.033893 | Guaynabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1908-03 | 2026-07-04 | 0.029204 | 10 | 0.035399 | Guaynabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6401-02 | 2026-07-06 | 0.019262 | 10 | 0.023348 | San German | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-07 | 0.037904 | 10 | 0.045944 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-08 | 0.024234 | 10 | 0.029374 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-08 | 0.025476 | 10 | 0.03088 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-08 | 0.032933 | 10 | 0.039919 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1109-05 | 2026-07-06 | 0.021127 | 10 | 0.025608 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1109-05 | 2026-07-07 | 0.010563 | 10 | 0.012804 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1109-05 | 2026-07-06 | 0.032933 | 10 | 0.039919 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 6702-02 | 2026-07-10 | 0.020575 | 10 | 0.024939 | Cabo Rojo | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 6702-02 | 2026-07-10 | 0.039146 | 10 | 0.04745 | Cabo Rojo | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 6702-02 | 2026-07-10 | 0.034175 | 10 | 0.041425 | Cabo Rojo | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 6702-02 | 2026-07-11 | 0.038525 | 10 | 0.046697 | Cabo Rojo | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 6702-02 | 2026-07-11 | 0.043496 | 10 | 0.052722 | Cabo Rojo | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 6702-02 | 2026-07-11 | 0.01443 | 10 | 0.017491 | Cabo Rojo | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 6702-02 | 2026-07-11 | 0.015295 | 10 | 0.01854 | Cabo Rojo | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6801-02 | 2026-07-06 | 0.079536 | 10 | 0.096407 | San Germán | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6501-02 | 2026-07-06 | 0.027537 | 10 | 0.033379 | Sabana Grande | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6501-02 | 2026-07-06 | 0.024882 | 10 | 0.03016 | Sabana Grande | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6501-02 | 2026-07-07 | 0.032933 | 10 | 0.039919 | Sabana Grande | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 8010-02 | 2026-07-11 | 0.026098 | 10 | 0.031633 | Arecibo | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 8010-02 | 2026-07-11 | 0.045981 | 10 | 0.055735 | Arecibo | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7502-02 | 2026-07-09 | 0.055302 | 10 | 0.067033 | Isabela | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3205-08 | 2026-07-11 | 0.032957 | 10 | 0.039948 | Juncos | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5902-02 | 2026-07-09 | 0.035146 | 10 | 0.042601 | Villalba | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5902-02 | 2026-07-09 | 0.029828 | 10 | 0.036155 | Villalba | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5902-02 | 2026-07-09 | 0.031438 | 10 | 0.038107 | Villalba | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5902-02 | 2026-07-09 | 0.038525 | 10 | 0.046697 | Villalba | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5902-02 | 2026-07-09 | 0.036661 | 10 | 0.044438 | Villalba | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-07-10 | 0.055679 | 10 | 0.067489 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5902-02 | 2026-07-07 | 0.064001 | 10 | 0.077577 | Villalba | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5902-02 | 2026-07-07 | 0.025476 | 10 | 0.03088 | Villalba | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 4501-05 | 2026-07-06 | 0.047846 | 10 | 0.057995 | Salinas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 4501-05 | 2026-07-07 | 0.03169 | 10 | 0.038412 | Salinas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 4501-05 | 2026-07-07 | 0.027962 | 10 | 0.033893 | Salinas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 4501-05 | 2026-07-06 | 0.044128 | 10 | 0.053488 | Salinaslleo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 4501-05 | 2026-07-06 | 0.044128 | 10 | 0.053488 | Salinas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 8007-03 | 2026-07-08 | 0.037282 | 10 | 0.045191 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 8007-03 | 2026-07-08 | 0.026098 | 10 | 0.031633 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 8007-03 | 2026-07-09 | 0.021127 | 10 | 0.025608 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 8007-03 | 2026-07-09 | 0.014291 | 10 | 0.017323 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 8007-03 | 2026-07-09 | 0.034175 | 10 | 0.041425 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 7903-06 | 2026-07-06 | 0.025518 | 10 | 0.030931 | Lares | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 7903-06 | 2026-07-07 | 0.03252 | 10 | 0.039418 | Lares | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9902-02 | 2026-07-08 | 0.03604 | 10 | 0.043684 | Orocovis | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9902-02 | 2026-07-08 | 0.034175 | 10 | 0.041425 | Orocovis | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 4501-05 | 2026-07-07 | 0.02905 | 10 | 0.035212 | Salinas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1710-03 | 2026-07-11 | 0.03169 | 10 | 0.038412 | Bayamón | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-07-07 | 0.025017 | 10 | 0.030324 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-07-07 | 0.017093 | 10 | 0.020719 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-07-07 | 0.019991 | 10 | 0.024232 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-07-08 | 0.023779 | 10 | 0.028823 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-02 | 2026-07-08 | 0.032593 | 10 | 0.039507 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-02 | 2026-07-08 | 0.03093 | 10 | 0.037491 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-02 | 2026-07-08 | 0.032757 | 10 | 0.039705 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-02 | 2026-07-08 | 0.024618 | 10 | 0.02984 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-02 | 2026-07-08 | 0.027899 | 10 | 0.033817 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-02 | 2026-07-08 | 0.032955 | 10 | 0.039946 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-02 | 2026-07-08 | 0.030072 | 10 | 0.036451 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-02 | 2026-07-06 | 0.028933 | 10 | 0.03507 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7901-03 | 2026-07-06 | 0.19635 | 10 | 0.238 | Lares | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-02 | 2026-07-06 | 0.036299 | 10 | 0.043998 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5501-03 | 2026-07-10 | 0.036661 | 10 | 0.044438 | Guayanilla | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-02 | 2026-07-08 | 0.035454 | 10 | 0.042975 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-02 | 2026-07-06 | 0.033497 | 10 | 0.040602 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-02 | 2026-07-06 | 0.022209 | 10 | 0.02692 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-02 | 2026-07-08 | 0.027294 | 10 | 0.033083 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-02 | 2026-07-08 | 0.05279 | 10 | 0.063988 | Gurabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-02 | 2026-07-08 | 0.025858 | 10 | 0.031343 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5501-03 | 2026-07-09 | 0.038525 | 10 | 0.046697 | Guayanilla | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-02 | 2026-07-07 | 0.026593 | 10 | 0.032234 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5501-03 | 2026-07-08 | 0.037904 | 10 | 0.045944 | Guayanilla | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-02 | 2026-07-08 | 0.05279 | 10 | 0.063988 | Gurabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-02 | 2026-07-07 | 0.025978 | 10 | 0.031489 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-02 | 2026-07-08 | 0.025402 | 10 | 0.030791 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-02 | 2026-07-08 | 0.02895 | 10 | 0.03509 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5501-03 | 2026-07-08 | 0.040389 | 10 | 0.048957 | Guayanilla | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-02 | 2026-07-08 | 0.029544 | 10 | 0.035811 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-02 | 2026-07-07 | 0.035667 | 10 | 0.043233 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 9405-05 | 2026-07-10 | 0.054681 | 10 | 0.06628 | Toa Alta | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1109-05 | 2026-07-08 | 0.019262 | 10 | 0.023348 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-09 | 0.035396 | 10 | 0.042905 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1109-05 | 2026-07-08 | 0.024234 | 10 | 0.029374 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-09 | 0.020505 | 10 | 0.024855 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-07 | 0.036661 | 10 | 0.044438 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-08 | 0.036661 | 10 | 0.044438 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-08 | 0.021748 | 10 | 0.026361 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-09 | 0.028583 | 10 | 0.034646 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-07 | 0.018641 | 10 | 0.022595 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-09 | 0.025476 | 10 | 0.03088 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-09 | 0.027962 | 10 | 0.033893 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-09 | 0.028583 | 10 | 0.034646 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1109-05 | 2026-07-08 | 0.019262 | 10 | 0.023348 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-07 | 0.024234 | 10 | 0.029374 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-07 | 0.022369 | 10 | 0.027114 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-08 | 0.018508 | 10 | 0.022434 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-09 | 0.034531 | 10 | 0.041856 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-07 | 0.029001 | 10 | 0.035152 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-07 | 0.032311 | 10 | 0.039165 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-07 | 0.018641 | 10 | 0.022595 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-10 | 0.032695 | 10 | 0.03963 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-10 | 0.033485 | 10 | 0.040588 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-08 | 0.021012 | 10 | 0.025469 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-09 | 0.014913 | 10 | 0.018076 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-10 | 0.026698 | 10 | 0.032361 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-09 | 0.037292 | 10 | 0.045203 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-10 | 0.03205 | 10 | 0.038848 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1109-05 | 2026-07-06 | 0.032933 | 10 | 0.039919 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1109-05 | 2026-07-08 | 0.028583 | 10 | 0.034646 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1109-05 | 2026-07-06 | 0.032251 | 10 | 0.039092 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1109-05 | 2026-07-08 | 0.027887 | 10 | 0.033802 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1109-05 | 2026-07-07 | 0.028694 | 10 | 0.034781 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1109-05 | 2026-07-08 | 0.005314 | 10 | 0.0064412 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1109-05 | 2026-07-08 | 0.039122 | 10 | 0.04742 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1109-05 | 2026-07-08 | 0.024234 | 10 | 0.029374 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-10 | 0.016156 | 10 | 0.019583 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-10 | 0.032933 | 10 | 0.039919 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-10 | 0.031169 | 10 | 0.03778 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-10 | 0.099952 | 10 | 0.12115 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1109-05 | 2026-07-06 | 0.016156 | 10 | 0.019583 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-10 | 0.048346 | 10 | 0.058602 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-10 | 0.026719 | 10 | 0.032387 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-10 | 0.0077169 | 10 | 0.0093538 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-06 | 0.024603 | 10 | 0.029821 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-02 | 2026-07-08 | 0.031689 | 10 | 0.038411 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-02 | 2026-07-08 | 0.025505 | 10 | 0.030915 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-02 | 2026-07-08 | 0.028841 | 10 | 0.034959 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-02 | 2026-07-08 | 0.042622 | 10 | 0.051663 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-02 | 2026-07-09 | 0.033582 | 10 | 0.040705 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-02 | 2026-07-09 | 0.030017 | 10 | 0.036385 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-02 | 2026-07-09 | 0.026488 | 10 | 0.032107 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-02 | 2026-07-11 | 0.038014 | 10 | 0.046078 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-02 | 2026-07-10 | 0.041697 | 10 | 0.050542 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-02 | 2026-07-06 | 0.052816 | 10 | 0.06402 | Gurabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-06 | 0.034461 | 10 | 0.04177 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-08 | 0.026098 | 10 | 0.031633 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 8701-04 | 2026-07-11 | 0.030675 | 10 | 0.037182 | Ciales | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 8701-04 | 2026-07-11 | 0.032933 | 10 | 0.039919 | Ciales | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 6702-02 | 2026-07-07 | 0.057166 | 10 | 0.069292 | Cabo Rojo | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 8701-04 | 2026-07-11 | 0.032311 | 10 | 0.039165 | Ciales | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 8701-04 | 2026-07-11 | 0.034797 | 10 | 0.042178 | Ciales | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 8701-04 | 2026-07-11 | 0.033373 | 10 | 0.040452 | Ciales | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-07 | 0.033554 | 10 | 0.040671 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1602-05 | 2026-07-08 | 0.054681 | 10 | 0.06628 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1602-05 | 2026-07-08 | 0.054681 | 10 | 0.06628 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1602-05 | 2026-07-08 | 0.029826 | 10 | 0.036152 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1602-05 | 2026-07-08 | 0.0086992 | 10 | 0.010545 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1602-05 | 2026-07-07 | 0.012427 | 10 | 0.015064 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1602-05 | 2026-07-07 | 0.028583 | 10 | 0.034646 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 8701-04 | 2026-07-07 | 0.032311 | 10 | 0.039165 | Ciales | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 8701-04 | 2026-07-11 | 0.030447 | 10 | 0.036906 | Ciales | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 8701-04 | 2026-07-11 | 0.021748 | 10 | 0.026361 | Ciales | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 8701-04 | 2026-07-11 | 0.056545 | 10 | 0.068539 | Ciales | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 8701-04 | 2026-07-07 | 0.036661 | 10 | 0.044438 | Ciales | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-07 | 0.030688 | 10 | 0.037198 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-10 | 0.016604 | 10 | 0.020126 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7003-02 | 2026-07-08 | 0.013732 | 10 | 0.016645 | Aguadilla | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-07 | 0.025476 | 10 | 0.03088 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-07-06 | 0.025751 | 10 | 0.031213 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-07-06 | 0.027019 | 10 | 0.03275 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-07-06 | 0.029204 | 10 | 0.035399 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-07-07 | 0.03169 | 10 | 0.038412 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-07 | 0.022085 | 10 | 0.02677 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-07-07 | 0.028583 | 10 | 0.034646 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-07-08 | 0.028583 | 10 | 0.034646 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-07-07 | 0.028583 | 10 | 0.034646 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-07-09 | 0.033554 | 10 | 0.040671 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-07 | 0.029341 | 10 | 0.035564 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-07-06 | 0.13655 | 10 | 0.16552 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-07 | 0.064577 | 10 | 0.078275 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-07 | 0.052425 | 10 | 0.063545 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-07 | 0.04767 | 10 | 0.057782 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1602-05 | 2026-07-07 | 0.088235 | 10 | 0.10695 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-09 | 0.037904 | 10 | 0.045944 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-09 | 0.021572 | 10 | 0.026147 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3205-08 | 2026-07-07 | 0.047955 | 10 | 0.058128 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-08 | 0.030447 | 10 | 0.036906 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-09 | 0.021127 | 10 | 0.025608 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 6702-02 | 2026-07-11 | 0.033554 | 10 | 0.040671 | Cabo Rojo | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-09 | 0.016156 | 10 | 0.019583 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 6702-02 | 2026-07-10 | 0.03604 | 10 | 0.043684 | Cabo Rojo | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-10 | 0.014291 | 10 | 0.017323 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2603-08 | 2026-07-06 | 0.032186 | 10 | 0.039014 | Humacao | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2603-09 | 2026-07-06 | 0.031291 | 10 | 0.037929 | Humacao | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1602-05 | 2026-07-07 | 0.039146 | 10 | 0.04745 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-07 | 0.019262 | 10 | 0.023348 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 5018-04 | 2026-07-06 | 0.033554 | 10 | 0.040671 | Ponce | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-07 | 0.024685 | 10 | 0.029921 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-07 | 0.037282 | 10 | 0.045191 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-10 | 0.029132 | 10 | 0.035312 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-07 | 0.036661 | 10 | 0.044438 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-07 | 0.021748 | 10 | 0.026361 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 8003-03 | 2026-07-08 | 0.019235 | 10 | 0.023315 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-09 | 0.031069 | 10 | 0.037659 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 8003-03 | 2026-07-07 | 0.020551 | 10 | 0.024911 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 8003-03 | 2026-07-07 | 0.024225 | 10 | 0.029364 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 8003-03 | 2026-07-08 | 0.021212 | 10 | 0.025712 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-07 | 0.025476 | 10 | 0.03088 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-03 | 2026-07-07 | 0.029826 | 10 | 0.036152 | Trujillo Alto | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-11 | 0.026098 | 10 | 0.031633 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-03 | 2026-07-07 | 0.031708 | 10 | 0.038434 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-03 | 2026-07-07 | 0.029204 | 10 | 0.035399 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-03 | 2026-07-07 | 0.037904 | 10 | 0.045944 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-11 | 0.018641 | 10 | 0.022595 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-03 | 2026-07-09 | 0.039146 | 10 | 0.04745 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-03 | 2026-07-09 | 0.037282 | 10 | 0.045191 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-03 | 2026-07-09 | 0.021127 | 10 | 0.025608 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-03 | 2026-07-07 | 0.024234 | 10 | 0.029374 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-03 | 2026-07-07 | 0.022369 | 10 | 0.027114 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-03 | 2026-07-07 | 0.032933 | 10 | 0.039919 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-03 | 2026-07-07 | 0.035418 | 10 | 0.042931 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-03 | 2026-07-07 | 0.034175 | 10 | 0.041425 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-03 | 2026-07-07 | 0.033554 | 10 | 0.040671 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-03 | 2026-07-09 | 0.026719 | 10 | 0.032387 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-03 | 2026-07-07 | 0.010563 | 10 | 0.012804 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-03 | 2026-07-08 | 0.032311 | 10 | 0.039165 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-03 | 2026-07-08 | 0.030358 | 10 | 0.036797 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-03 | 2026-07-08 | 0.036954 | 10 | 0.044792 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-03 | 2026-07-08 | 0.027496 | 10 | 0.033328 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-03 | 2026-07-10 | 0.026172 | 10 | 0.031723 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6401-04 | 2026-07-07 | 0.035418 | 10 | 0.042931 | San Germán | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6401-04 | 2026-07-07 | 0.071458 | 10 | 0.086615 | San Germán | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 8003-03 | 2026-07-08 | 0.001014 | 10 | 0.0012291 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 8003-03 | 2026-07-06 | 0.017964 | 10 | 0.021775 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8015-07 | 2026-07-10 | 0.022213 | 10 | 0.026924 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 8003-03 | 2026-07-07 | 0.017458 | 10 | 0.021161 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-07-07 | 0.076732 | 10 | 0.093008 | Trujillo Alto | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8015-07 | 2026-07-10 | 0.013453 | 10 | 0.016306 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8015-07 | 2026-07-09 | 0.016716 | 10 | 0.020261 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8015-07 | 2026-07-09 | 0.029745 | 10 | 0.036054 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8015-07 | 2026-07-09 | 0.010563 | 10 | 0.012804 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8015-07 | 2026-07-09 | 0.028014 | 10 | 0.033956 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8014-07 | 2026-07-06 | 0.028427 | 10 | 0.034456 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7012-02 | 2026-07-07 | 0.02978 | 10 | 0.036098 | Aguadilla | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-07-06 | 0.027435 | 10 | 0.033254 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7012-02 | 2026-07-07 | 0.020291 | 10 | 0.024596 | Aguadilla | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7012-02 | 2026-07-07 | 0.033461 | 10 | 0.040559 | Aguadilla | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8014-07 | 2026-07-06 | 0.031756 | 10 | 0.038492 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8015-07 | 2026-07-09 | 0.026446 | 10 | 0.032056 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8014-07 | 2026-07-06 | 0.034797 | 10 | 0.042178 | Arecibo | LUMA | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9902-02 | 2026-07-06 | 0.028583 | 10 | 0.034646 | Orocovis | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8014-07 | 2026-07-06 | 0.022991 | 10 | 0.027868 | Arecibo | LUMA | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8014-07 | 2026-07-06 | 0.028738 | 10 | 0.034834 | Arecibo | LUMA | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7012-02 | 2026-07-10 | 0.031309 | 10 | 0.03795 | Aguadilla | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9902-02 | 2026-07-06 | 0.034582 | 10 | 0.041918 | Orocovis | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 2002-03 | 2026-07-06 | 0.026098 | 10 | 0.031633 | Luquillo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9605-01 | 2026-07-06 | 0.02969 | 10 | 0.035988 | Barranquitas | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-08 | 0.022991 | 10 | 0.027868 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-03 | 2026-07-08 | 0.0093206 | 10 | 0.011298 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-11 | 0.038525 | 10 | 0.046697 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-03 | 2026-07-09 | 0.017177 | 10 | 0.020821 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-03 | 2026-07-08 | 0.0093616 | 10 | 0.011347 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-03 | 2026-07-08 | 0.024645 | 10 | 0.029873 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-07 | 0.0062136 | 10 | 0.0075317 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-03 | 2026-07-08 | 0.021842 | 10 | 0.026475 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-07 | 0.032933 | 10 | 0.039919 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-07 | 0.022991 | 10 | 0.027868 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-03 | 2026-07-08 | 0.024679 | 10 | 0.029914 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-03 | 2026-07-08 | 0.021128 | 10 | 0.02561 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1526-05 | 2026-07-07 | 0.01634 | 10 | 0.019806 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1526-05 | 2026-07-07 | 0.030113 | 10 | 0.0365 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-10 | 0.022965 | 10 | 0.027837 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-09 | 0.014518 | 10 | 0.017597 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1526-05 | 2026-07-07 | 0.030113 | 10 | 0.0365 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-03 | 2026-07-08 | 0.022369 | 10 | 0.027114 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-09 | 0.029826 | 10 | 0.036152 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-09 | 0.02734 | 10 | 0.03314 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1526-05 | 2026-07-07 | 0.030228 | 10 | 0.03664 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-08 | 0.032124 | 10 | 0.038938 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-08 | 0.032311 | 10 | 0.039165 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-03 | 2026-07-08 | 0.012724 | 10 | 0.015424 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1526-05 | 2026-07-07 | 0.026192 | 10 | 0.031748 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-08 | 0.029204 | 10 | 0.035399 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-08 | 0.037282 | 10 | 0.045191 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-08 | 0.042837 | 10 | 0.051923 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1526-05 | 2026-07-07 | 0.025312 | 10 | 0.030681 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1526-05 | 2026-07-07 | 0.022872 | 10 | 0.027724 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1903-05 | 2026-07-08 | 0.034797 | 10 | 0.042178 | Bayamón | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-03 | 2026-07-09 | 0.024855 | 10 | 0.030127 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-09 | 0.03177 | 10 | 0.038508 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-11 | 0.043128 | 10 | 0.052277 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-10 | 0.029826 | 10 | 0.036152 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1526-01 | 2026-07-07 | 0.021318 | 10 | 0.02584 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-10 | 0.027962 | 10 | 0.033893 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-10 | 0.025476 | 10 | 0.03088 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-09 | 0.018641 | 10 | 0.022595 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1526-01 | 2026-07-07 | 0.031304 | 10 | 0.037944 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1526-05 | 2026-07-07 | 0.034657 | 10 | 0.042008 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-07-08 | 0.022776 | 10 | 0.027608 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-07-08 | 0.02424 | 10 | 0.029382 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-07-09 | 0.019317 | 10 | 0.023415 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-07-09 | 0.02671 | 10 | 0.032376 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-07-09 | 0.02531 | 10 | 0.030679 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-11 | 0.038525 | 10 | 0.046697 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-07-09 | 0.050331 | 10 | 0.061007 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-07-09 | 0.048467 | 10 | 0.058748 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-07-09 | 0.048938 | 10 | 0.059319 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-11 | 0.024234 | 10 | 0.029374 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1652-02 | 2026-07-09 | 0.021127 | 10 | 0.025608 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-09 | 0.015554 | 10 | 0.018853 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-07-10 | 0.024855 | 10 | 0.030127 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-07-10 | 0.027962 | 10 | 0.033893 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-09 | 0.019655 | 10 | 0.023825 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-09 | 0.0046858 | 10 | 0.0056798 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-07-10 | 0.03604 | 10 | 0.043684 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 6704-03 | 2026-07-07 | 0.038283 | 10 | 0.046404 | Lajas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-09 | 0.018905 | 10 | 0.022915 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-07-10 | 0.028914 | 10 | 0.035047 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-09 | 0.0074564 | 10 | 0.0090381 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-09 | 0.032311 | 10 | 0.039165 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-09 | 0.024234 | 10 | 0.029374 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-09 | 0.0093206 | 10 | 0.011298 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-09 | 0.006835 | 10 | 0.0082849 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-09 | 0.027962 | 10 | 0.033893 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-09 | 0.006835 | 10 | 0.0082849 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-09 | 0.006835 | 10 | 0.0082849 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-09 | 0.022369 | 10 | 0.027114 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-09 | 0.021127 | 10 | 0.025608 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8404-02 | 2026-07-07 | 0.048455 | 10 | 0.058733 | Manatí | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-09 | 0.011806 | 10 | 0.01431 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-09 | 0.0074564 | 10 | 0.0090381 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-09 | 0.014291 | 10 | 0.017323 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-09 | 0.0031068 | 10 | 0.0037658 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6401-04 | 2026-07-08 | 0.029826 | 10 | 0.036152 | San Germán | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-09 | 0.025144 | 10 | 0.030477 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3014-01 | 2026-07-08 | 0.029204 | 10 | 0.035399 | Caguas | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-09 | 0.048085 | 10 | 0.058285 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-02 | 2026-07-08 | 0.04971 | 10 | 0.060254 | Gurabo | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-09 | 0.033554 | 10 | 0.040671 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-09 | 0.037282 | 10 | 0.045191 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6406-02 | 2026-07-11 | 0.051574 | 10 | 0.062514 | San Germán | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-09 | 0.022369 | 10 | 0.027114 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6406-02 | 2026-07-11 | 0.050952 | 10 | 0.061761 | San Germán | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-09 | 0.032311 | 10 | 0.039165 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 8007-04 | 2026-07-08 | 0.031069 | 10 | 0.037659 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 8007-04 | 2026-07-08 | 0.031032 | 10 | 0.037614 | Arecibo | LUMA | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 8007-04 | 2026-07-08 | 0.023683 | 10 | 0.028707 | Arecibo | LUMA | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-08 | 0.031069 | 10 | 0.037659 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 8007-04 | 2026-07-08 | 0.01122 | 10 | 0.013599 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 8007-04 | 2026-07-08 | 0.023683 | 10 | 0.028707 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-08 | 0.0055924 | 10 | 0.0067787 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-09 | 0.028254 | 10 | 0.034247 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 8007-04 | 2026-07-08 | 0.013254 | 10 | 0.016065 | Arecibo | LUMA | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-09 | 0.027243 | 10 | 0.033022 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-08 | 0.037282 | 10 | 0.045191 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 8007-04 | 2026-07-08 | 0.020011 | 10 | 0.024256 | Arecibo | LUMA | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 8007-04 | 2026-07-08 | 0.013583 | 10 | 0.016464 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-08 | 0.028583 | 10 | 0.034646 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 8701-04 | 2026-07-11 | 0.020283 | 10 | 0.024586 | Ciales | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-01 | 2026-07-10 | 0.03463 | 10 | 0.041975 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6001-01 | 2026-07-11 | 0.022991 | 10 | 0.027868 | Mayaguez | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-10 | 0.033358 | 10 | 0.040434 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2404-08 | 2026-07-10 | 0.024234 | 10 | 0.029374 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-09 | 0.021127 | 10 | 0.025608 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2404-08 | 2026-07-10 | 0.024855 | 10 | 0.030127 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-09 | 0.02841 | 10 | 0.034436 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2404-08 | 2026-07-10 | 0.026719 | 10 | 0.032387 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2404-08 | 2026-07-10 | 0.022369 | 10 | 0.027114 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-09 | 0.02376 | 10 | 0.0288 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2404-08 | 2026-07-10 | 0.019888 | 10 | 0.024106 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-09 | 0.015554 | 10 | 0.018853 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 4101-04 | 2026-07-09 | 0.039146 | 10 | 0.04745 | Arroyo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 4101-04 | 2026-07-09 | 0.023121 | 10 | 0.028025 | Arroyo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-08 | 0.026098 | 10 | 0.031633 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-01 | 2026-07-10 | 0.025216 | 10 | 0.030565 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-10 | 0.026615 | 10 | 0.03226 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-01 | 2026-07-10 | 0.023827 | 10 | 0.028881 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-10 | 0.0227 | 10 | 0.027515 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9902-02 | 2026-07-07 | 0.034175 | 10 | 0.041425 | Orocovis | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-09 | 0.040845 | 10 | 0.04951 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-09 | 0.021748 | 10 | 0.026361 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-01 | 2026-07-10 | 0.025161 | 10 | 0.030498 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-10 | 0.026516 | 10 | 0.032141 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-01 | 2026-07-10 | 0.026847 | 10 | 0.032542 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-10 | 0.026093 | 10 | 0.031627 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-10 | 0.022369 | 10 | 0.027114 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-09 | 0.040867 | 10 | 0.049536 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-08 | 0.013373 | 10 | 0.01621 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-08 | 0.034105 | 10 | 0.041339 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9602-04 | 2026-07-08 | 0.11123 | 10 | 0.13482 | Orocovis | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-09 | 0.022991 | 10 | 0.027868 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6801-02 | 2026-07-08 | 0.21437 | 10 | 0.25985 | Hormigueros | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6801-02 | 2026-07-07 | 0.079536 | 10 | 0.096407 | Hormigueros | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-07 | 0.041629 | 10 | 0.050459 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-07 | 0.057787 | 10 | 0.070045 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 8007-03 | 2026-07-09 | 0.026719 | 10 | 0.032387 | Arecibo | LUMA | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3013-03 | 2026-07-09 | 0.080778 | 10 | 0.097913 | Caguas | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-09 | 0.026098 | 10 | 0.031633 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-11 | 0.025476 | 10 | 0.03088 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-09 | 0.031627 | 10 | 0.038335 | Hatillo | LUMA | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-01 | 2026-07-09 | 0.031399 | 10 | 0.038059 | Hatillo | LUMA | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-01 | 2026-07-09 | 0.033604 | 10 | 0.040733 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-09 | 0.03327 | 10 | 0.040327 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-11 | 0.01367 | 10 | 0.01657 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-09 | 0.019641 | 10 | 0.023807 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-01 | 2026-07-09 | 0.019539 | 10 | 0.023684 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-09 | 0.023476 | 10 | 0.028456 | Hatillo | LUMA | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6406-02 | 2026-07-09 | 0.082642 | 10 | 0.10017 | San Germán | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-01 | 2026-07-09 | 0.023212 | 10 | 0.028136 | Hatillo | LUMA | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-09 | 0.0223 | 10 | 0.027031 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-01 | 2026-07-09 | 0.02252 | 10 | 0.027297 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-09 | 0.021084 | 10 | 0.025556 | Hatillo | LUMA | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-01 | 2026-07-09 | 0.021422 | 10 | 0.025966 | Hatillo | LUMA | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 7011-03 | 2026-07-09 | 0.011562 | 10 | 0.014014 | Aguadilla | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 6702-02 | 2026-07-09 | 0.18517 | 10 | 0.22445 | Cabo Rojo | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-09 | 0.016777 | 10 | 0.020336 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9703-01 | 2026-07-09 | 0.027962 | 10 | 0.033893 | Comerío | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 7011-03 | 2026-07-09 | 0.051528 | 10 | 0.062459 | Aguadilla | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-09 | 0.018992 | 10 | 0.023021 | Hatillo | LUMA | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-11 | 0.029204 | 10 | 0.035399 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-11 | 0.021127 | 10 | 0.025608 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-10 | 0.050952 | 10 | 0.061761 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9703-01 | 2026-07-09 | 0.030447 | 10 | 0.036906 | Comerío | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-09 | 0.028583 | 10 | 0.034646 | Hatillo | LUMA | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-09 | 0.035454 | 10 | 0.042974 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-11 | 0.019262 | 10 | 0.023348 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 2901-01 | 2026-07-09 | 0.16031 | 10 | 0.19432 | Yabucoa | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7303-01 | 2026-07-09 | 0.11744 | 10 | 0.14235 | Aguada | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6306-02 | 2026-07-08 | 0.10464 | 10 | 0.12683 | Aguada | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-09 | 0.035418 | 10 | 0.042931 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-07-10 | 0.02701 | 10 | 0.032739 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-07-10 | 0.035418 | 10 | 0.042931 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 2901-01 | 2026-07-09 | 0.16031 | 10 | 0.19432 | Yabucoa | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 2901-01 | 2026-07-09 | 0.16031 | 10 | 0.19432 | Naguabo | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3013-03 | 2026-07-10 | 0.10439 | 10 | 0.12653 | Caguas | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-07-10 | 0.019113 | 10 | 0.023167 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-07-10 | 0.043496 | 10 | 0.052722 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-07-10 | 0.031069 | 10 | 0.037659 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-07-10 | 0.0080778 | 10 | 0.0097913 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-07-10 | 0.033554 | 10 | 0.040671 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-07-10 | 0.050331 | 10 | 0.061007 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-07-10 | 0.026098 | 10 | 0.031633 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3013-03 | 2026-07-10 | 0.090099 | 10 | 0.10921 | Caguas | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-11 | 0.016777 | 10 | 0.020336 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3014-04 | 2026-07-11 | 0.031712 | 10 | 0.038439 | San Juan | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3006-05 | 2026-07-11 | 0.040763 | 10 | 0.049409 | Caguas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3006-05 | 2026-07-11 | 0.045592 | 10 | 0.055264 | Caguas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-07 | 2026-07-11 | 0.031069 | 10 | 0.037659 | Aguas Buenas | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-07 | 2026-07-11 | 0.031069 | 10 | 0.037659 | Aguas Buenas | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 4201-03 | 2026-07-11 | 0.18106 | 10 | 0.21946 | Coamo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1901-02 | 2026-07-14 | 0.022991 | 10 | 0.027868 | Guaynabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7403-03 | 2026-07-15 | 0.10688 | 10 | 0.12955 | San Sebastián | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-17 | 0.010563 | 10 | 0.012804 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-16 | 0.042875 | 10 | 0.051969 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-15 | 0.031392 | 10 | 0.038051 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-15 | 0.032535 | 10 | 0.039437 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-18 | 0.040389 | 10 | 0.048957 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-15 | 0.034797 | 10 | 0.042178 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-14 | 0.031998 | 10 | 0.038785 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-14 | 0.0080778 | 10 | 0.0097913 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-14 | 0.027962 | 10 | 0.033893 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-15 | 0.029492 | 10 | 0.035748 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 6702-02 | 2026-07-15 | 0.039146 | 10 | 0.04745 | Cabo Rojo | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 6702-02 | 2026-07-15 | 0.035418 | 10 | 0.042931 | Cabo Rojo | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 6702-02 | 2026-07-15 | 0.034175 | 10 | 0.041425 | Cabo Rojo | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 6702-02 | 2026-07-15 | 0.036661 | 10 | 0.044438 | Cabo Rojo | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 6702-02 | 2026-07-16 | 0.046603 | 10 | 0.056488 | Cabo Rojo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6801-02 | 2026-07-14 | 0.061516 | 10 | 0.074565 | Hormigueros | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-04 | 2026-07-14 | 0.049326 | 10 | 0.059789 | Trujillo Alto | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5902-02 | 2026-07-14 | 0.051574 | 10 | 0.062514 | Villalba | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5902-02 | 2026-07-15 | 0.057938 | 10 | 0.070228 | Villalba | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7201-02 | 2026-07-14 | 0.016079 | 10 | 0.01949 | Aguada | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7201-02 | 2026-07-14 | 0.016095 | 10 | 0.019509 | Aguada | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1709-02 | 2026-07-15 | 0.025476 | 10 | 0.03088 | Bayamón | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1709-02 | 2026-07-17 | 0.020505 | 10 | 0.024855 | Bayamón | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 4201-01 | 2026-07-17 | 0.027818 | 10 | 0.033718 | Patillas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 4201-01 | 2026-07-17 | 0.028717 | 10 | 0.034809 | Patillas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5303-01 | 2026-07-16 | 0.061516 | 10 | 0.074565 | Yauco | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5303-01 | 2026-07-16 | 0.028583 | 10 | 0.034646 | Yauco | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 6703-02 | 2026-07-16 | 0.026098 | 10 | 0.031633 | Cabo Rojo | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 4301-01 | 2026-07-15 | 0.079536 | 10 | 0.096407 | Maunabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5303-01 | 2026-07-16 | 0.028236 | 10 | 0.034225 | Yauco | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-07-14 | 0.02612 | 10 | 0.03166 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5501-03 | 2026-07-14 | 0.038525 | 10 | 0.046697 | Guayanilla | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5501-03 | 2026-07-14 | 0.022991 | 10 | 0.027868 | Guayanilla | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5501-03 | 2026-07-17 | 0.037904 | 10 | 0.045944 | Guayanilla | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-15 | 0.034275 | 10 | 0.041545 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-15 | 0.031512 | 10 | 0.038197 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5501-03 | 2026-07-15 | 0.064001 | 10 | 0.077577 | Guayanilla | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5007-01 | 2026-07-16 | 0.039146 | 10 | 0.04745 | Ponce | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5007-01 | 2026-07-13 | 0.022369 | 10 | 0.027114 | Ponce | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5007-01 | 2026-07-16 | 0.040154 | 10 | 0.048672 | Ponce | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 9405-05 | 2026-07-14 | 0.018435 | 10 | 0.022346 | BAYAMON | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-15 | 0.032311 | 10 | 0.039165 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-15 | 0.032311 | 10 | 0.039165 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-17 | 0.033554 | 10 | 0.040671 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-15 | 0.028583 | 10 | 0.034646 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-17 | 0.025476 | 10 | 0.03088 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-15 | 0.026098 | 10 | 0.031633 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-16 | 0.04191 | 10 | 0.0508 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-18 | 0.045981 | 10 | 0.055735 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-17 | 0.022369 | 10 | 0.027114 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-18 | 0.051574 | 10 | 0.062514 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-18 | 0.051574 | 10 | 0.062514 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-14 | 0.03298 | 10 | 0.039976 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7301-02 | 2026-07-17 | 0.044584 | 10 | 0.054041 | Rincón | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7301-02 | 2026-07-17 | 0.020731 | 10 | 0.025128 | Rincón | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-14 | 0.052076 | 10 | 0.063122 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-15 | 0.031771 | 10 | 0.038511 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-14 | 0.028621 | 10 | 0.034692 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-15 | 0.014447 | 10 | 0.017511 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-15 | 0.02465 | 10 | 0.029879 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-02 | 2026-07-16 | 0.033765 | 10 | 0.040927 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-02 | 2026-07-13 | 0.056256 | 10 | 0.068189 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8008-01 | 2026-07-14 | 0.047224 | 10 | 0.057242 | Arecibo | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8008-01 | 2026-07-14 | 0.041632 | 10 | 0.050463 | Arecibo | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8008-01 | 2026-07-12 | 0.037904 | 10 | 0.045944 | Arecibo | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8008-01 | 2026-07-12 | 0.029826 | 10 | 0.036152 | Arecibo | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8008-01 | 2026-07-12 | 0.024234 | 10 | 0.029374 | Arecibo | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-02 | 2026-07-14 | 0.030391 | 10 | 0.036838 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-02 | 2026-07-14 | 0.037919 | 10 | 0.045962 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-02 | 2026-07-15 | 0.052437 | 10 | 0.06356 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-02 | 2026-07-14 | 0.046651 | 10 | 0.056547 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-02 | 2026-07-15 | 0.056226 | 10 | 0.068153 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-16 | 0.03169 | 10 | 0.038412 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-17 | 0.032311 | 10 | 0.039165 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-18 | 0.032598 | 10 | 0.039512 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-18 | 0.031783 | 10 | 0.038525 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-18 | 0.030447 | 10 | 0.036906 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-16 | 0.030447 | 10 | 0.036906 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-17 | 0.021748 | 10 | 0.026361 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-15 | 0.019262 | 10 | 0.023348 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-14 | 0.026098 | 10 | 0.031633 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-18 | 0.043894 | 10 | 0.053205 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-17 | 0.02538 | 10 | 0.030764 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3205-08 | 2026-07-17 | 0.026899 | 10 | 0.032605 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-17 | 0.030963 | 10 | 0.037531 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3205-08 | 2026-07-17 | 0.031305 | 10 | 0.037945 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-18 | 0.020066 | 10 | 0.024322 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3205-08 | 2026-07-18 | 0.01977 | 10 | 0.023964 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-02 | 2026-07-13 | 0.056545 | 10 | 0.068539 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-17 | 0.025926 | 10 | 0.031426 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-07-13 | 0.022369 | 10 | 0.027114 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-07-14 | 0.017398 | 10 | 0.021089 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-07-14 | 0.03169 | 10 | 0.038412 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-07-14 | 0.03169 | 10 | 0.038412 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-07-15 | 0.03169 | 10 | 0.038412 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-16 | 0.02918 | 10 | 0.03537 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1342-04 | 2026-07-13 | 0.027962 | 10 | 0.033893 | Trujillo Alto | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-04 | 2026-07-13 | 0.026719 | 10 | 0.032387 | Trujillo Alto | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1201-01 | 2026-07-13 | 0.047309 | 10 | 0.057344 | Trujillo Alto | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-04 | 2026-07-13 | 0.046603 | 10 | 0.056488 | Trujillo Alto | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-14 | 0.004971 | 10 | 0.0060255 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-13 | 0.04021 | 10 | 0.04874 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-14 | 0.016156 | 10 | 0.019583 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-14 | 0.013049 | 10 | 0.015817 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-03 | 2026-07-15 | 0.026719 | 10 | 0.032387 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-03 | 2026-07-15 | 0.029204 | 10 | 0.035399 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-14 | 0.0080258 | 10 | 0.0097282 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-15 | 0.021138 | 10 | 0.025622 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-13 | 0.022991 | 10 | 0.027868 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-14 | 0.03488 | 10 | 0.042279 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-13 | 0.032311 | 10 | 0.039165 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-14 | 0.03834 | 10 | 0.046472 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-02 | 2026-07-17 | 0.066198 | 10 | 0.080241 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-13 | 0.029826 | 10 | 0.036152 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-13 | 0.021748 | 10 | 0.026361 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-16 | 0.027962 | 10 | 0.033893 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-16 | 0.021127 | 10 | 0.025608 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-16 | 0.020505 | 10 | 0.024855 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8015-07 | 2026-07-13 | 0.022369 | 10 | 0.027114 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-13 | 0.021748 | 10 | 0.026361 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-13 | 0.0055924 | 10 | 0.0067787 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-13 | 0.01802 | 10 | 0.021842 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-13 | 0.019884 | 10 | 0.024102 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-13 | 0.0080778 | 10 | 0.0097913 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-13 | 0.03169 | 10 | 0.038412 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-13 | 0.014913 | 10 | 0.018076 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-13 | 0.014367 | 10 | 0.017414 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-13 | 0.030447 | 10 | 0.036906 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-13 | 0.021748 | 10 | 0.026361 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-13 | 0.011546 | 10 | 0.013995 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-13 | 0.0055924 | 10 | 0.0067787 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-13 | 0.011806 | 10 | 0.01431 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-16 | 0.028116 | 10 | 0.034081 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-16 | 0.01715 | 10 | 0.020787 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-16 | 0.0071847 | 10 | 0.0087087 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-16 | 0.033554 | 10 | 0.040671 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-16 | 0.0041633 | 10 | 0.0050464 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-16 | 0.024234 | 10 | 0.029374 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-16 | 0.024234 | 10 | 0.029374 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-16 | 0.023612 | 10 | 0.028621 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-16 | 0.0055924 | 10 | 0.0067787 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-16 | 0.021311 | 10 | 0.025832 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-15 | 0.023169 | 10 | 0.028084 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-14 | 0.026387 | 10 | 0.031984 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-14 | 0.013407 | 10 | 0.01625 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-14 | 0.021502 | 10 | 0.026063 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-16 | 0.029826 | 10 | 0.036152 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-03 | 2026-07-16 | 0.020505 | 10 | 0.024855 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-16 | 0.030447 | 10 | 0.036906 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-03 | 2026-07-16 | 0.034073 | 10 | 0.041301 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-16 | 0.019884 | 10 | 0.024102 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-14 | 0.024234 | 10 | 0.029374 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-17 | 0.021131 | 10 | 0.025613 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8015-07 | 2026-07-13 | 0.031786 | 10 | 0.038529 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-04 | 2026-07-13 | 0.026098 | 10 | 0.031633 | Trujillo Alto | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1201-01 | 2026-07-13 | 0.026146 | 10 | 0.031692 | Trujillo Alto | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-04 | 2026-07-15 | 0.030447 | 10 | 0.036906 | Trujillo Alto | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-04 | 2026-07-17 | 0.024855 | 10 | 0.030127 | San Juan | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1201-01 | 2026-07-15 | 0.030317 | 10 | 0.036747 | Trujillo Alto | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-04 | 2026-07-15 | 0.01802 | 10 | 0.021842 | Trujillo Alto | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1201-01 | 2026-07-15 | 0.017398 | 10 | 0.021089 | Trujillo Alto | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8015-07 | 2026-07-15 | 0.017347 | 10 | 0.021026 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7504-01 | 2026-07-15 | 0.085128 | 10 | 0.10319 | Aguadilla | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7504-01 | 2026-07-15 | 0.022991 | 10 | 0.027868 | Aguadilla | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7504-01 | 2026-07-15 | 0.042875 | 10 | 0.051969 | Aguadilla | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7504-01 | 2026-07-15 | 0.024234 | 10 | 0.029374 | Aguadilla | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7404-06 | 2026-07-12 | 0.026719 | 10 | 0.032387 | Quebradillas | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6801-02 | 2026-07-15 | 0.062759 | 10 | 0.076071 | Hormigueros | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7504-01 | 2026-07-16 | 0.020505 | 10 | 0.024855 | Aguadilla | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7504-01 | 2026-07-15 | 0.050952 | 10 | 0.061761 | Aguadilla | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7504-01 | 2026-07-15 | 0.037126 | 10 | 0.045001 | Aguadilla | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8014-07 | 2026-07-14 | 0.03619 | 10 | 0.043867 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8014-07 | 2026-07-17 | 0.017245 | 10 | 0.020904 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7012-02 | 2026-07-13 | 0.036537 | 10 | 0.044287 | Aguadilla | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8014-07 | 2026-07-16 | 0.026769 | 10 | 0.032447 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8014-07 | 2026-07-15 | 0.032796 | 10 | 0.039753 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8014-07 | 2026-07-15 | 0.032249 | 10 | 0.03909 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8015-07 | 2026-07-13 | 0.022026 | 10 | 0.026698 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8015-07 | 2026-07-13 | 0.024855 | 10 | 0.030127 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7012-02 | 2026-07-13 | 0.053412 | 10 | 0.064742 | Aguadilla | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7012-02 | 2026-07-15 | 0.020708 | 10 | 0.025101 | Aguadilla | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7012-02 | 2026-07-15 | 0.021882 | 10 | 0.026523 | Aguadilla | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8014-07 | 2026-07-17 | 0.015387 | 10 | 0.018651 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8014-07 | 2026-07-15 | 0.024234 | 10 | 0.029374 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8014-07 | 2026-07-15 | 0.03169 | 10 | 0.038412 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8014-07 | 2026-07-16 | 0.030089 | 10 | 0.036471 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-02 | 2026-07-17 | 0.071169 | 10 | 0.086265 | Gurabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-02 | 2026-07-17 | 0.071169 | 10 | 0.086265 | Gurabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-16 | 0.01802 | 10 | 0.021842 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-03 | 2026-07-16 | 0.016156 | 10 | 0.019583 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-16 | 0.01802 | 10 | 0.021842 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-17 | 0.022369 | 10 | 0.027114 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-16 | 0.022991 | 10 | 0.027868 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-14 | 0.043128 | 10 | 0.052277 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-15 | 0.043128 | 10 | 0.052277 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-16 | 0.043128 | 10 | 0.052277 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-07-17 | 0.010563 | 10 | 0.012804 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-07-17 | 0.0024854 | 10 | 0.0030126 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-07-17 | 0.052195 | 10 | 0.063267 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-07-16 | 0.032311 | 10 | 0.039165 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-15 | 0.03169 | 10 | 0.038412 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-15 | 0.010563 | 10 | 0.012804 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-15 | 0.043418 | 10 | 0.052628 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-15 | 0.013003 | 10 | 0.015761 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-15 | 0.022494 | 10 | 0.027265 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-15 | 0.027962 | 10 | 0.033893 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-14 | 0.0097449 | 10 | 0.011812 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-15 | 0.032311 | 10 | 0.039165 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-15 | 0.02734 | 10 | 0.03314 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-15 | 0.022369 | 10 | 0.027114 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-15 | 0.014913 | 10 | 0.018076 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-15 | 0.032933 | 10 | 0.039919 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3006-04 | 2026-07-15 | 0.032933 | 10 | 0.039919 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-15 | 0.031069 | 10 | 0.037659 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3006-04 | 2026-07-15 | 0.03169 | 10 | 0.038412 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-15 | 0.030447 | 10 | 0.036906 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3006-04 | 2026-07-15 | 0.031069 | 10 | 0.037659 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-15 | 0.022991 | 10 | 0.027868 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2404-08 | 2026-07-15 | 0.025049 | 10 | 0.030363 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3006-04 | 2026-07-15 | 0.026098 | 10 | 0.031633 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2404-08 | 2026-07-15 | 0.025476 | 10 | 0.03088 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2404-08 | 2026-07-15 | 0.022991 | 10 | 0.027868 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-15 | 0.018641 | 10 | 0.022595 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3006-04 | 2026-07-15 | 0.018731 | 10 | 0.022705 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-01 | 2026-07-15 | 0.02833 | 10 | 0.034339 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-15 | 0.024855 | 10 | 0.030127 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-17 | 0.033554 | 10 | 0.040671 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3006-04 | 2026-07-15 | 0.023677 | 10 | 0.0287 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2404-08 | 2026-07-14 | 0.026719 | 10 | 0.032387 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2404-08 | 2026-07-14 | 0.024855 | 10 | 0.030127 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-15 | 0.029826 | 10 | 0.036152 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3006-04 | 2026-07-15 | 0.030174 | 10 | 0.036575 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2404-08 | 2026-07-14 | 0.025476 | 10 | 0.03088 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-15 | 0.02734 | 10 | 0.03314 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3006-04 | 2026-07-15 | 0.02734 | 10 | 0.03314 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6001-02 | 2026-07-15 | 0.028802 | 10 | 0.034911 | Mayaguez | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6001-02 | 2026-07-14 | 0.021748 | 10 | 0.026361 | Mayaguez | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-01 | 2026-07-15 | 0.02699 | 10 | 0.032715 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 4101-04 | 2026-07-13 | 0.052441 | 10 | 0.063565 | Arroyo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6001-02 | 2026-07-17 | 0.024855 | 10 | 0.030127 | Mayaguez | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-15 | 0.027822 | 10 | 0.033724 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 4101-04 | 2026-07-13 | 0.010191 | 10 | 0.012353 | Arroyo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 4101-04 | 2026-07-13 | 0.04219 | 10 | 0.051139 | Arroyo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-14 | 0.10146 | 10 | 0.12298 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-01 | 2026-07-13 | 0.02178 | 10 | 0.0264 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-13 | 0.021819 | 10 | 0.026447 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-01 | 2026-07-15 | 0.020211 | 10 | 0.024499 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-15 | 0.019018 | 10 | 0.023052 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-16 | 0.0074564 | 10 | 0.0090381 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-16 | 0.032776 | 10 | 0.039729 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-16 | 0.022267 | 10 | 0.02699 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-16 | 0.019088 | 10 | 0.023137 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-01 | 2026-07-15 | 0.032018 | 10 | 0.03881 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-16 | 0.022991 | 10 | 0.027868 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-15 | 0.031509 | 10 | 0.038193 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-15 | 0.012773 | 10 | 0.015482 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-01 | 2026-07-15 | 0.012188 | 10 | 0.014774 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-01 | 2026-07-15 | 0.034446 | 10 | 0.041753 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-15 | 0.033912 | 10 | 0.041105 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-16 | 0.023612 | 10 | 0.028621 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-15 | 0.027962 | 10 | 0.033893 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-16 | 0.018641 | 10 | 0.022595 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-15 | 0.024234 | 10 | 0.029374 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7005-03 | 2026-07-15 | 0.026479 | 10 | 0.032096 | Aguadilla | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7005-03 | 2026-07-14 | 0.030447 | 10 | 0.036906 | Aguadilla | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7005-03 | 2026-07-15 | 0.030447 | 10 | 0.036906 | Aguadilla | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7005-03 | 2026-07-16 | 0.06338 | 10 | 0.076824 | Aguadilla | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7005-03 | 2026-07-17 | 0.04563 | 10 | 0.055309 | Aguadilla | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-15 | 0.021127 | 10 | 0.025608 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-14 | 0.030447 | 10 | 0.036906 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-14 | 0.016777 | 10 | 0.020336 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-15 | 0.023612 | 10 | 0.028621 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-15 | 0.02734 | 10 | 0.03314 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3405-01 | 2026-07-13 | 0.025476 | 10 | 0.03088 | Cayey | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3405-01 | 2026-07-13 | 0.025476 | 10 | 0.03088 | Cayey | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3405-01 | 2026-07-13 | 0.025476 | 10 | 0.03088 | Cayey | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1423-05 | 2026-07-17 | 0.0086992 | 10 | 0.010545 | San Juan | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-07-13 | 0.031069 | 10 | 0.037659 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-14 | 0.029826 | 10 | 0.036152 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-07-13 | 0.0066015 | 10 | 0.0080018 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-15 | 0.029204 | 10 | 0.035399 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-07-18 | 0.021748 | 10 | 0.026361 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-15 | 0.022991 | 10 | 0.027868 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-07-13 | 0.022991 | 10 | 0.027868 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-15 | 0.030447 | 10 | 0.036906 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-15 | 0.019262 | 10 | 0.023348 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-15 | 0.021748 | 10 | 0.026361 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-14 | 0.01802 | 10 | 0.021842 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-14 | 0.01802 | 10 | 0.021842 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-15 | 0.037282 | 10 | 0.045191 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-14 | 0.025476 | 10 | 0.03088 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-15 | 0.033554 | 10 | 0.040671 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-14 | 0.017398 | 10 | 0.021089 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-14 | 0.014913 | 10 | 0.018076 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-15 | 0.028583 | 10 | 0.034646 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-14 | 0.028583 | 10 | 0.034646 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-15 | 0.018641 | 10 | 0.022595 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-14 | 0.016777 | 10 | 0.020336 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-14 | 0.016777 | 10 | 0.020336 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 4101-04 | 2026-07-16 | 0.024332 | 10 | 0.029493 | Arroyo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 4101-04 | 2026-07-16 | 0.037863 | 10 | 0.045895 | Arroyo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-16 | 0.010223 | 10 | 0.012391 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-16 | 0.046687 | 10 | 0.05659 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9605-02 | 2026-07-16 | 0.024234 | 10 | 0.029374 | Comerío | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9605-02 | 2026-07-16 | 0.016156 | 10 | 0.019583 | Comerío | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9605-02 | 2026-07-16 | 0.02734 | 10 | 0.03314 | Comerío | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9605-02 | 2026-07-16 | 0.017195 | 10 | 0.020843 | Comerío | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9605-02 | 2026-07-16 | 0.041632 | 10 | 0.050463 | Comerío | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9605-02 | 2026-07-15 | 0.022396 | 10 | 0.027147 | Comerío | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9605-02 | 2026-07-15 | 0.01802 | 10 | 0.021842 | Comerío | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-14 | 0.023612 | 10 | 0.028621 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-14 | 0.019884 | 10 | 0.024102 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9605-02 | 2026-07-16 | 0.029204 | 10 | 0.035399 | Comerío | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9605-02 | 2026-07-16 | 0.014291 | 10 | 0.017323 | Comerío | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9605-02 | 2026-07-16 | 0.05903 | 10 | 0.071552 | Comerío | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9605-02 | 2026-07-16 | 0.020612 | 10 | 0.024984 | Comerío | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9605-02 | 2026-07-16 | 0.02199 | 10 | 0.026655 | Comerío | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9605-02 | 2026-07-16 | 0.030949 | 10 | 0.037514 | Comerío | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9605-02 | 2026-07-17 | 0.031537 | 10 | 0.038227 | Comerío | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9605-02 | 2026-07-16 | 0.036661 | 10 | 0.044438 | Comerío | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9605-02 | 2026-07-16 | 0.041632 | 10 | 0.050463 | Comerío | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9605-02 | 2026-07-16 | 0.020505 | 10 | 0.024855 | Comerío | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9605-02 | 2026-07-16 | 0.04536 | 10 | 0.054982 | Comerío | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9605-02 | 2026-07-18 | 0.025146 | 10 | 0.03048 | Naranjito | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9605-02 | 2026-07-16 | 0.031069 | 10 | 0.037659 | Naranjito | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9605-02 | 2026-07-18 | 0.044797 | 10 | 0.0543 | Naranjito | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9605-02 | 2026-07-15 | 0.004971 | 10 | 0.0060255 | Naranjito | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9605-02 | 2026-07-15 | 0.021748 | 10 | 0.026361 | Naranjito | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9605-02 | 2026-07-16 | 0.016156 | 10 | 0.019583 | Naranjito | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9605-02 | 2026-07-16 | 0.031409 | 10 | 0.038071 | Naranjito | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9605-02 | 2026-07-16 | 0.035278 | 10 | 0.042761 | Naranjito | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9605-02 | 2026-07-16 | 0.03169 | 10 | 0.038412 | Naranjito | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9605-02 | 2026-07-16 | 0.0074278 | 10 | 0.0090034 | Naranjito | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9605-02 | 2026-07-16 | 0.030642 | 10 | 0.037142 | Naranjito | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 5602-01 | 2026-07-13 | 0.027962 | 10 | 0.033893 | Yauco | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 5602-01 | 2026-07-13 | 0.019262 | 10 | 0.023348 | Guánica | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-13 | 0.018641 | 10 | 0.022595 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-13 | 0.0062136 | 10 | 0.0075317 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-13 | 0.022991 | 10 | 0.027868 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-13 | 0.023612 | 10 | 0.028621 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-13 | 0.019884 | 10 | 0.024102 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-13 | 0.024855 | 10 | 0.030127 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-16 | 0.029826 | 10 | 0.036152 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-16 | 0.015534 | 10 | 0.018829 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-16 | 0.016156 | 10 | 0.019583 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-16 | 0.030447 | 10 | 0.036906 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-16 | 0.019262 | 10 | 0.023348 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-15 | 0.031691 | 10 | 0.038413 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-16 | 0.019884 | 10 | 0.024102 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-16 | 0.026098 | 10 | 0.031633 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-16 | 0.022369 | 10 | 0.027114 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-16 | 0.033554 | 10 | 0.040671 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-16 | 0.022991 | 10 | 0.027868 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-16 | 0.012427 | 10 | 0.015064 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-15 | 0.026098 | 10 | 0.031633 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-16 | 0.024855 | 10 | 0.030127 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-16 | 0.011185 | 10 | 0.013557 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-15 | 0.01802 | 10 | 0.021842 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-16 | 0.021748 | 10 | 0.026361 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-15 | 0.021127 | 10 | 0.025608 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-15 | 0.028619 | 10 | 0.034689 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-15 | 0.030153 | 10 | 0.036549 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-15 | 0.024706 | 10 | 0.029946 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-15 | 0.02937 | 10 | 0.0356 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-15 | 0.027299 | 10 | 0.033089 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-15 | 0.030533 | 10 | 0.03701 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-15 | 0.015433 | 10 | 0.018707 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-15 | 0.020884 | 10 | 0.025314 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-15 | 0.021311 | 10 | 0.025832 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-16 | 0.029204 | 10 | 0.035399 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-14 | 0.022991 | 10 | 0.027868 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3013-03 | 2026-07-14 | 0.046603 | 10 | 0.056488 | Caguas | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-16 | 0.01802 | 10 | 0.021842 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-16 | 0.0093206 | 10 | 0.011298 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3013-03 | 2026-07-14 | 0.046603 | 10 | 0.056488 | Caguas | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-16 | 0.031069 | 10 | 0.037659 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-14 | 0.05903 | 10 | 0.071552 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3013-03 | 2026-07-14 | 0.046603 | 10 | 0.056488 | Caguas | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3013-03 | 2026-07-14 | 0.046603 | 10 | 0.056488 | Caguas | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-07-14 | 0.09507 | 10 | 0.11524 | Cidra | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-15 | 0.034797 | 10 | 0.042178 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-15 | 0.032311 | 10 | 0.039165 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-15 | 0.03169 | 10 | 0.038412 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-15 | 0.033348 | 10 | 0.040421 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-15 | 0.033228 | 10 | 0.040277 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-15 | 0.029826 | 10 | 0.036152 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-15 | 0.029204 | 10 | 0.035399 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-15 | 0.0105 | 10 | 0.012727 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-15 | 0.028583 | 10 | 0.034646 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-15 | 0.020244 | 10 | 0.024538 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-15 | 0.030447 | 10 | 0.036906 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-15 | 0.029204 | 10 | 0.035399 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-07-18 | 0.037904 | 10 | 0.045944 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-15 | 0.033998 | 10 | 0.04121 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-15 | 0.031066 | 10 | 0.037656 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-07-18 | 0.037904 | 10 | 0.045944 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-07-18 | 0.035418 | 10 | 0.042931 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-15 | 0.029817 | 10 | 0.036142 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-15 | 0.032661 | 10 | 0.039589 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-07-18 | 0.0043496 | 10 | 0.0052723 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-16 | 0.034911 | 10 | 0.042316 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-16 | 0.017398 | 10 | 0.021089 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8202-02 | 2026-07-14 | 0.053971 | 10 | 0.065419 | Adjuntas | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-15 | 0.019262 | 10 | 0.023348 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-15 | 0.028579 | 10 | 0.034642 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-15 | 0.015572 | 10 | 0.018875 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-15 | 0.0070811 | 10 | 0.0085831 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-15 | 0.041366 | 10 | 0.05014 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-15 | 0.011185 | 10 | 0.013557 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-16 | 0.011806 | 10 | 0.01431 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-15 | 0.026719 | 10 | 0.032387 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-15 | 0.02903 | 10 | 0.035188 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-15 | 0.018539 | 10 | 0.022472 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-15 | 0.0045807 | 10 | 0.0055523 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-15 | 0.025316 | 10 | 0.030687 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-15 | 0.01291 | 10 | 0.015649 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-14 | 0.030362 | 10 | 0.036803 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-14 | 0.015708 | 10 | 0.01904 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-14 | 0.026098 | 10 | 0.031633 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-14 | 0.028276 | 10 | 0.034274 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-15 | 0.0238 | 10 | 0.028849 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-15 | 0.032043 | 10 | 0.03884 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-14 | 0.0099419 | 10 | 0.012051 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-15 | 0.030245 | 10 | 0.036661 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8013-02 | 2026-07-15 | 0.026513 | 10 | 0.032137 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-15 | 0.030601 | 10 | 0.037093 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8013-02 | 2026-07-15 | 0.036985 | 10 | 0.04483 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-15 | 0.028335 | 10 | 0.034346 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-15 | 0.032402 | 10 | 0.039275 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-07-17 | 0.028583 | 10 | 0.034646 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8013-02 | 2026-07-15 | 0.035403 | 10 | 0.042913 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-18 | 0.030041 | 10 | 0.036414 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-15 | 0.029553 | 10 | 0.035822 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-15 | 0.020205 | 10 | 0.02449 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-15 | 0.011806 | 10 | 0.01431 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-17 | 0.028818 | 10 | 0.034931 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-18 | 0.029867 | 10 | 0.036203 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-15 | 0.023797 | 10 | 0.028845 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-17 | 0.012985 | 10 | 0.015739 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-15 | 0.034835 | 10 | 0.042225 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-15 | 0.015534 | 10 | 0.018829 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-15 | 0.015534 | 10 | 0.018829 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-15 | 0.019884 | 10 | 0.024102 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8202-02 | 2026-07-14 | 0.14898 | 10 | 0.18058 | Adjuntas | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1657-02 | 2026-07-16 | 0.03878 | 10 | 0.047006 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-15 | 0.0077267 | 10 | 0.0093657 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-17 | 0.018324 | 10 | 0.022211 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-15 | 0.0262 | 10 | 0.031758 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-15 | 0.026752 | 10 | 0.032427 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-15 | 0.020047 | 10 | 0.024299 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-14 | 0.03834 | 10 | 0.046472 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-15 | 0.025669 | 10 | 0.031114 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-07-16 | 0.027962 | 10 | 0.033893 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-07-16 | 0.021127 | 10 | 0.025608 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-15 | 0.034955 | 10 | 0.042369 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-14 | 0.03834 | 10 | 0.046472 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-15 | 0.027639 | 10 | 0.033501 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-15 | 0.03688 | 10 | 0.044703 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-15 | 0.006678 | 10 | 0.0080946 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-15 | 0.018435 | 10 | 0.022346 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-15 | 0.018435 | 10 | 0.022346 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-07-17 | 0.029204 | 10 | 0.035399 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6001-02 | 2026-07-17 | 0.026719 | 10 | 0.032387 | Mayaguez | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-17 | 0.02734 | 10 | 0.03314 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3006-04 | 2026-07-17 | 0.027962 | 10 | 0.033893 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6001-02 | 2026-07-17 | 0.026598 | 10 | 0.03224 | Mayaguez | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-14 | 0.021263 | 10 | 0.025774 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-15 | 0.026098 | 10 | 0.031633 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6001-02 | 2026-07-16 | 0.015955 | 10 | 0.01934 | Mayaguez | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-14 | 0.030447 | 10 | 0.036906 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-16 | 0.017398 | 10 | 0.021089 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3006-04 | 2026-07-14 | 0.031069 | 10 | 0.037659 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-14 | 0.026098 | 10 | 0.031633 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-17 | 0.013655 | 10 | 0.016552 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3006-04 | 2026-07-14 | 0.026098 | 10 | 0.031633 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-17 | 0.01534 | 10 | 0.018594 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-14 | 0.019884 | 10 | 0.024102 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3006-04 | 2026-07-14 | 0.019262 | 10 | 0.023348 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-17 | 0.029204 | 10 | 0.035399 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-17 | 0.02734 | 10 | 0.03314 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-17 | 0.029044 | 10 | 0.035205 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-15 | 0.032311 | 10 | 0.039165 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-16 | 0.028583 | 10 | 0.034646 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3006-04 | 2026-07-15 | 0.032933 | 10 | 0.039919 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-18 | 0.028281 | 10 | 0.03428 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-17 | 0.031343 | 10 | 0.037991 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8202-02 | 2026-07-14 | 0.14898 | 10 | 0.18058 | Adjuntas | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6001-02 | 2026-07-17 | 0.020505 | 10 | 0.024855 | Mayaguez | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-17 | 0.020727 | 10 | 0.025123 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-14 | 0.027985 | 10 | 0.033921 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-07-17 | 0.034759 | 10 | 0.042133 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-15 | 0.022991 | 10 | 0.027868 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-16 | 0.075296 | 10 | 0.091268 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3006-04 | 2026-07-15 | 0.019262 | 10 | 0.023348 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-15 | 0.036835 | 10 | 0.044648 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-18 | 0.029204 | 10 | 0.035399 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-14 | 0.016149 | 10 | 0.019574 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-14 | 0.0099419 | 10 | 0.012051 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1714-02 | 2026-07-15 | 0.017627 | 10 | 0.021366 | Bayamón | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-15 | 0.039768 | 10 | 0.048203 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-14 | 0.0086992 | 10 | 0.010545 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-15 | 0.020951 | 10 | 0.025396 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-14 | 0.026719 | 10 | 0.032387 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6801-02 | 2026-07-13 | 0.025476 | 10 | 0.03088 | Hormigueros | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-14 | 0.018641 | 10 | 0.022595 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-04 | 2026-07-14 | 0.019884 | 10 | 0.024102 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5501-03 | 2026-07-15 | 0.034797 | 10 | 0.042178 | Guayanilla | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-15 | 0.02833 | 10 | 0.03434 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-15 | 0.027936 | 10 | 0.033861 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-15 | 0.029066 | 10 | 0.035231 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-15 | 0.029096 | 10 | 0.035267 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5501-03 | 2026-07-15 | 0.039146 | 10 | 0.04745 | Guayanilla | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8101-04 | 2026-07-15 | 0.25484 | 10 | 0.3089 | Utuado | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9602-04 | 2026-07-15 | 0.15687 | 10 | 0.19014 | Barranquitas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8101-04 | 2026-07-15 | 0.32867 | 10 | 0.39838 | Utuado | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 2601-04 | 2026-07-16 | 0.018207 | 10 | 0.022069 | Humacao | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 2601-04 | 2026-07-15 | 0.021907 | 10 | 0.026554 | Humacao | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 2601-04 | 2026-07-15 | 0.0092193 | 10 | 0.011175 | Humacao | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 2601-04 | 2026-07-15 | 0.01802 | 10 | 0.021842 | Humacao | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8101-04 | 2026-07-15 | 0.25484 | 10 | 0.3089 | Utuado | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 2601-04 | 2026-07-15 | 0.026719 | 10 | 0.032387 | Humacao | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8101-04 | 2026-07-15 | 0.12987 | 10 | 0.15741 | Utuado | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-16 | 0.025476 | 10 | 0.03088 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-16 | 0.028583 | 10 | 0.034646 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9602-04 | 2026-07-15 | 0.15687 | 10 | 0.19014 | Barranquitas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9602-04 | 2026-07-15 | 0.15687 | 10 | 0.19014 | Barranquitas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-16 | 0.032311 | 10 | 0.039165 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9602-04 | 2026-07-15 | 0.15687 | 10 | 0.19014 | Barranquitas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-17 | 0.026903 | 10 | 0.03261 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8101-04 | 2026-07-15 | 0.11744 | 10 | 0.14235 | Utuado | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-18 | 0.023437 | 10 | 0.028408 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-18 | 0.021995 | 10 | 0.026661 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-18 | 0.033511 | 10 | 0.040619 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8101-04 | 2026-07-15 | 0.11744 | 10 | 0.14235 | Utuado | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-17 | 0.016156 | 10 | 0.019583 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 2601-03 | 2026-07-15 | 0.026098 | 10 | 0.031633 | Humacao | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-17 | 0.033511 | 10 | 0.040619 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 2601-03 | 2026-07-15 | 0.025476 | 10 | 0.03088 | Humacao | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-17 | 0.035025 | 10 | 0.042454 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9003-06 | 2026-07-18 | 0.011185 | 10 | 0.013557 | Vega Baja | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9003-06 | 2026-07-18 | 0.037904 | 10 | 0.045944 | Vega Baja | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 4301-01 | 2026-07-15 | 0.064001 | 10 | 0.077577 | Maunabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 2601-03 | 2026-07-15 | 0.026098 | 10 | 0.031633 | Humacao | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5501-03 | 2026-07-15 | 0.021748 | 10 | 0.026361 | Guayanilla | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-17 | 0.010241 | 10 | 0.012413 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5501-03 | 2026-07-15 | 0.022991 | 10 | 0.027868 | Guayanilla | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-17 | 0.027836 | 10 | 0.03374 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-17 | 0.029122 | 10 | 0.035299 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 8401-02 | 2026-07-15 | 0.019699 | 10 | 0.023878 | Manatí | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 8401-02 | 2026-07-15 | 0.034797 | 10 | 0.042178 | Manatí | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-17 | 0.050331 | 10 | 0.061007 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-07-17 | 0.009553 | 10 | 0.011579 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7802-01 | 2026-07-16 | 0.018775 | 10 | 0.022758 | San Sebastián | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7802-01 | 2026-07-16 | 0.020356 | 10 | 0.024674 | San Sebastián | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7802-01 | 2026-07-16 | 0.019177 | 10 | 0.023244 | San Sebastián | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-16 | 0.032311 | 10 | 0.039165 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-16 | 0.026242 | 10 | 0.031808 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-16 | 0.041096 | 10 | 0.049814 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8101-04 | 2026-07-15 | 0.055302 | 10 | 0.067033 | Utuado | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8101-04 | 2026-07-15 | 0.17709 | 10 | 0.21466 | Utuado | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8101-04 | 2026-07-15 | 0.17709 | 10 | 0.21466 | Utuado | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-17 | 0.024845 | 10 | 0.030115 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-15 | 0.02832 | 10 | 0.034328 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-15 | 0.021413 | 10 | 0.025955 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-15 | 0.023654 | 10 | 0.028671 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-15 | 0.023621 | 10 | 0.028631 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7301-02 | 2026-07-17 | 0.027608 | 10 | 0.033465 | Rincón | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7301-02 | 2026-07-17 | 0.027629 | 10 | 0.03349 | Rincón | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8101-04 | 2026-07-15 | 0.028583 | 10 | 0.034646 | Utuado | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-04 | 2026-07-16 | 0.056545 | 10 | 0.068539 | Trujillo Alto | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-17 | 0.011185 | 10 | 0.013557 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-17 | 0.026719 | 10 | 0.032387 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-17 | 0.02595 | 10 | 0.031454 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 2601-03 | 2026-07-16 | 0.012772 | 10 | 0.015482 | Humacao | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 2601-03 | 2026-07-16 | 0.012772 | 10 | 0.015482 | Humacao | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-07-16 | 0.027652 | 10 | 0.033517 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-07-16 | 0.027489 | 10 | 0.03332 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 2601-04 | 2026-07-16 | 0.032933 | 10 | 0.039919 | Humacao | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-07-16 | 0.028091 | 10 | 0.03405 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-07-16 | 0.028323 | 10 | 0.034331 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-07-16 | 0.027652 | 10 | 0.033517 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-18 | 0.025476 | 10 | 0.03088 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-07-16 | 0.026973 | 10 | 0.032694 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-07-16 | 0.022418 | 10 | 0.027174 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-07-16 | 0.027713 | 10 | 0.033591 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-07-16 | 0.028158 | 10 | 0.034131 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-07-16 | 0.021539 | 10 | 0.026108 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-07-16 | 0.028502 | 10 | 0.034548 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-07-16 | 0.029383 | 10 | 0.035615 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-07-16 | 0.029858 | 10 | 0.036191 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-17 | 0.028409 | 10 | 0.034435 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-07-17 | 0.028374 | 10 | 0.034393 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 2601-04 | 2026-07-16 | 0.055302 | 10 | 0.067033 | Humacao | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-07-16 | 0.028302 | 10 | 0.034305 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 2601-04 | 2026-07-16 | 0.032933 | 10 | 0.039919 | Humacao | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-16 | 0.017651 | 10 | 0.021395 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-17 | 0.028927 | 10 | 0.035063 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-17 | 0.034293 | 10 | 0.041567 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-07-16 | 0.018732 | 10 | 0.022706 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-07-17 | 0.033554 | 10 | 0.040671 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-07-16 | 0.023674 | 10 | 0.028696 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-07-16 | 0.023575 | 10 | 0.028576 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-07-16 | 0.024042 | 10 | 0.029142 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-07-16 | 0.024152 | 10 | 0.029275 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-07-16 | 0.024818 | 10 | 0.030082 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-07-16 | 0.020209 | 10 | 0.024496 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-16 | 0.018422 | 10 | 0.02233 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-07-16 | 0.043028 | 10 | 0.052155 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-07-16 | 0.037254 | 10 | 0.045156 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-16 | 0.0055165 | 10 | 0.0066866 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-07-16 | 0.038532 | 10 | 0.046706 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-07-16 | 0.029948 | 10 | 0.036301 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-07-16 | 0.035529 | 10 | 0.043066 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 2601-04 | 2026-07-16 | 0.032933 | 10 | 0.039919 | Humacao | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 2601-04 | 2026-07-16 | 0.016777 | 10 | 0.020336 | Humacao | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 2601-04 | 2026-07-16 | 0.03169 | 10 | 0.038412 | Humacao | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8001-01 | 2026-07-18 | 0.024855 | 10 | 0.030127 | Arecibo | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-17 | 0.026249 | 10 | 0.031817 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-07-17 | 0.044007 | 10 | 0.053342 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-07-17 | 0.037634 | 10 | 0.045617 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-17 | 0.064623 | 10 | 0.07833 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3205-08 | 2026-07-17 | 0.026197 | 10 | 0.031754 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-07-17 | 0.02232 | 10 | 0.027055 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-17 | 0.029204 | 10 | 0.035399 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-17 | 0.032148 | 10 | 0.038967 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-07-17 | 0.03213 | 10 | 0.038945 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-17 | 0.064987 | 10 | 0.078772 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-07-17 | 0.035643 | 10 | 0.043204 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8005-01 | 2026-07-17 | 0.027962 | 10 | 0.033893 | Arecibo | Xperts | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-18 | 0.032933 | 10 | 0.039919 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 6802-05 | 2026-07-17 | 0.054239 | 10 | 0.065744 | Cabo Rojo | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 6802-05 | 2026-07-17 | 0.03997 | 10 | 0.048449 | Cabo Rojo | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5013-03 | 2026-07-17 | 0.055923 | 10 | 0.067786 | Juana Díaz | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-18 | 0.026719 | 10 | 0.032387 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-18 | 0.03604 | 10 | 0.043684 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-18 | 0.043136 | 10 | 0.052286 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9003-06 | 2026-07-18 | 0.024471 | 10 | 0.029662 | Vega Baja | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-18 | 0.01802 | 10 | 0.021842 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-18 | 0.01945 | 10 | 0.023576 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2404-08 | 2026-07-18 | 0.031069 | 10 | 0.037659 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2404-08 | 2026-07-18 | 0.030447 | 10 | 0.036906 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2404-08 | 2026-07-18 | 0.032933 | 10 | 0.039919 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2404-08 | 2026-07-18 | 0.031069 | 10 | 0.037659 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2404-08 | 2026-07-18 | 0.031069 | 10 | 0.037659 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-18 | 0.033554 | 10 | 0.040671 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2404-08 | 2026-07-18 | 0.032311 | 10 | 0.039165 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2404-08 | 2026-07-17 | 0.014291 | 10 | 0.017323 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2404-08 | 2026-07-18 | 0.029826 | 10 | 0.036152 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2404-08 | 2026-07-18 | 0.029826 | 10 | 0.036152 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3406-02 | 2026-07-18 | 0.058322 | 10 | 0.070693 | Cayey | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-18 | 0.033554 | 10 | 0.040671 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8001-01 | 2026-07-18 | 0.034524 | 10 | 0.041847 | Arecibo | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3501-01 | 2026-07-24 | 0.035492 | 10 | 0.043021 | Aibonito | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-21 | 0.03169 | 10 | 0.038412 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-25 | 0.020505 | 10 | 0.024855 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-24 | 0.019884 | 10 | 0.024102 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-24 | 0.027962 | 10 | 0.033893 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-24 | 0.026719 | 10 | 0.032387 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-25 | 0.03169 | 10 | 0.038412 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-24 | 0.044117 | 10 | 0.053476 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-24 | 0.021127 | 10 | 0.025608 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-23 | 0.01802 | 10 | 0.021842 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-23 | 0.023612 | 10 | 0.028621 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-23 | 0.033554 | 10 | 0.040671 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-22 | 0.03297 | 10 | 0.039964 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-22 | 0.025813 | 10 | 0.031289 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-21 | 0.01802 | 10 | 0.021842 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-24 | 0.03169 | 10 | 0.038412 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-24 | 0.02536 | 10 | 0.030739 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-24 | 0.01319 | 10 | 0.015988 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1706-03 | 2026-07-24 | 0.02382 | 10 | 0.028872 | Bayamón | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7601-03 | 2026-07-23 | 0.023612 | 10 | 0.028621 | Camuy | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6501-02 | 2026-07-23 | 0.01367 | 10 | 0.01657 | Sabana Grande | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6501-02 | 2026-07-23 | 0.059652 | 10 | 0.072305 | Sabana Grande | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-21 | 0.02328 | 10 | 0.028218 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-21 | 0.034175 | 10 | 0.041425 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6501-02 | 2026-07-23 | 0.13297 | 10 | 0.16118 | Sabana Grande | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6801-02 | 2026-07-20 | 0.075186 | 10 | 0.091135 | Hormigueros | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1709-02 | 2026-07-21 | 0.021748 | 10 | 0.026361 | Bayamón | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 4201-01 | 2026-07-21 | 0.028791 | 10 | 0.034899 | Patillas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7403-03 | 2026-07-24 | 0.058409 | 10 | 0.070799 | San Sebastián | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8015-08 | 2026-07-21 | 0.035533 | 10 | 0.04307 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8002-03 | 2026-07-21 | 0.035019 | 10 | 0.042447 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8015-08 | 2026-07-21 | 0.037733 | 10 | 0.045737 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1301-03 | 2026-07-23 | 0.023612 | 10 | 0.028621 | San Juan | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5801-04 | 2026-07-23 | 0.027946 | 10 | 0.033874 | Juana Díaz | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5801-04 | 2026-07-23 | 0.049027 | 10 | 0.059427 | Juana Díaz | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-07-21 | 0.044739 | 10 | 0.054229 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-07-21 | 0.036177 | 10 | 0.043851 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5302-01 | 2026-07-24 | 0.039651 | 10 | 0.048062 | Guayanilla | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5302-01 | 2026-07-24 | 0.042016 | 10 | 0.050928 | Guayanilla | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5302-01 | 2026-07-24 | 0.061327 | 10 | 0.074336 | Guayanilla | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5302-01 | 2026-07-24 | 0.053151 | 10 | 0.064425 | Guayanilla | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5302-01 | 2026-07-21 | 0.046045 | 10 | 0.055812 | Sabana Grande | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5302-01 | 2026-07-21 | 0.02904 | 10 | 0.0352 | Sabana Grande | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5302-01 | 2026-07-24 | 0.02153 | 10 | 0.026097 | Guayanilla | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 8007-03 | 2026-07-22 | 0.021127 | 10 | 0.025608 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 8007-03 | 2026-07-22 | 0.021068 | 10 | 0.025537 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5902-03 | 2026-07-21 | 0.0099419 | 10 | 0.012051 | Villalba | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5902-03 | 2026-07-21 | 0.070836 | 10 | 0.085862 | Villalba | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5902-03 | 2026-07-22 | 0.070215 | 10 | 0.085109 | Villalba | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5902-03 | 2026-07-21 | 0.050331 | 10 | 0.061007 | Villalba | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5902-03 | 2026-07-21 | 0.022369 | 10 | 0.027114 | Villalba | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5902-03 | 2026-07-21 | 0.026098 | 10 | 0.031633 | Villalba | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1206-03 | 2026-07-22 | 0.053438 | 10 | 0.064773 | Trujillo Alto | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7402-01 | 2026-07-24 | 0.04072 | 10 | 0.049357 | Camuy | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7402-01 | 2026-07-24 | 0.036661 | 10 | 0.044438 | Camuy | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5501-03 | 2026-07-20 | 0.037904 | 10 | 0.045944 | Guayanilla | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-21 | 0.037282 | 10 | 0.045191 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-22 | 0.039768 | 10 | 0.048203 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-21 | 0.037904 | 10 | 0.045944 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-21 | 0.020505 | 10 | 0.024855 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-21 | 0.03169 | 10 | 0.038412 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-21 | 0.033554 | 10 | 0.040671 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-21 | 0.036661 | 10 | 0.044438 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-02 | 2026-07-20 | 0.039636 | 10 | 0.048044 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-02 | 2026-07-21 | 0.057447 | 10 | 0.069633 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-02 | 2026-07-20 | 0.048116 | 10 | 0.058322 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-02 | 2026-07-20 | 0.041135 | 10 | 0.049861 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-02 | 2026-07-20 | 0.042229 | 10 | 0.051187 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-02 | 2026-07-21 | 0.030007 | 10 | 0.036372 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-02 | 2026-07-21 | 0.034466 | 10 | 0.041776 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-22 | 0.05903 | 10 | 0.071552 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-23 | 0.033241 | 10 | 0.040292 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-02 | 2026-07-22 | 0.069644 | 10 | 0.084417 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-02 | 2026-07-22 | 0.055508 | 10 | 0.067283 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-02 | 2026-07-22 | 0.057393 | 10 | 0.069567 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-07-21 | 0.039146 | 10 | 0.04745 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-02 | 2026-07-21 | 0.055147 | 10 | 0.066845 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-02 | 2026-07-21 | 0.056565 | 10 | 0.068564 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-02 | 2026-07-21 | 0.045 | 10 | 0.054545 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-02 | 2026-07-21 | 0.025476 | 10 | 0.03088 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-02 | 2026-07-21 | 0.043433 | 10 | 0.052646 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-02 | 2026-07-20 | 0.048026 | 10 | 0.058213 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-02 | 2026-07-22 | 0.055923 | 10 | 0.067786 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-02 | 2026-07-22 | 0.055923 | 10 | 0.067786 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-02 | 2026-07-22 | 0.051723 | 10 | 0.062695 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-01 | 2026-07-23 | 0.03675 | 10 | 0.044546 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-23 | 0.039146 | 10 | 0.04745 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-21 | 0.0055924 | 10 | 0.0067787 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-04 | 2026-07-24 | 0.036154 | 10 | 0.043823 | Trujillo Alto | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-04 | 2026-07-21 | 0.037395 | 10 | 0.045327 | Trujillo Alto | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1201-01 | 2026-07-20 | 0.037668 | 10 | 0.045658 | Trujillo Alto | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-22 | 0.013049 | 10 | 0.015817 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-21 | 0.043128 | 10 | 0.052277 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7303-01 | 2026-07-23 | 0.034801 | 10 | 0.042183 | Aguada | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8103-02 | 2026-07-22 | 0.017398 | 10 | 0.021089 | Utuado | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-22 | 0.068351 | 10 | 0.082849 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-22 | 0.026719 | 10 | 0.032387 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8103-02 | 2026-07-20 | 0.022991 | 10 | 0.027868 | Utuado | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-22 | 0.051379 | 10 | 0.062278 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7008-08 | 2026-07-21 | 0.041632 | 10 | 0.050463 | Moca | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8103-02 | 2026-07-20 | 0.023271 | 10 | 0.028207 | Utuado | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7008-08 | 2026-07-20 | 0.045981 | 10 | 0.055735 | Moca | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-25 | 0.1541 | 10 | 0.18679 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8103-02 | 2026-07-20 | 0.019085 | 10 | 0.023133 | Utuado | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8103-02 | 2026-07-23 | 0.023612 | 10 | 0.028621 | Utuado | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8103-02 | 2026-07-21 | 0.022991 | 10 | 0.027868 | Utuado | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8103-02 | 2026-07-20 | 0.024855 | 10 | 0.030127 | Utuado | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8103-02 | 2026-07-23 | 0.037282 | 10 | 0.045191 | Utuado | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8103-02 | 2026-07-20 | 0.016777 | 10 | 0.020336 | Utuado | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8103-02 | 2026-07-22 | 0.038525 | 10 | 0.046697 | Utuado | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-01 | 2026-07-23 | 0.036661 | 10 | 0.044438 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-01 | 2026-07-20 | 0.019884 | 10 | 0.024102 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-01 | 2026-07-20 | 0.049088 | 10 | 0.059501 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-01 | 2026-07-23 | 0.029204 | 10 | 0.035399 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-01 | 2026-07-23 | 0.029826 | 10 | 0.036152 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-01 | 2026-07-23 | 0.024855 | 10 | 0.030127 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-01 | 2026-07-23 | 0.031069 | 10 | 0.037659 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-23 | 0.043496 | 10 | 0.052722 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-01 | 2026-07-23 | 0.026384 | 10 | 0.031981 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-01 | 2026-07-20 | 0.027977 | 10 | 0.033911 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-01 | 2026-07-22 | 0.056521 | 10 | 0.068511 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-23 | 0.037904 | 10 | 0.045944 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-01 | 2026-07-22 | 0.031279 | 10 | 0.037914 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-23 | 0.03604 | 10 | 0.043684 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-23 | 0.016777 | 10 | 0.020336 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-01 | 2026-07-21 | 0.030861 | 10 | 0.037407 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-01 | 2026-07-21 | 0.023501 | 10 | 0.028486 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-01 | 2026-07-23 | 0.016704 | 10 | 0.020247 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-01 | 2026-07-23 | 0.030056 | 10 | 0.036432 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-24 | 0.02744 | 10 | 0.03326 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-24 | 0.011076 | 10 | 0.013425 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-25 | 0.044739 | 10 | 0.054229 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-23 | 0.04636 | 10 | 0.056194 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-23 | 0.037904 | 10 | 0.045944 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-23 | 0.004971 | 10 | 0.0060255 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-23 | 0.020505 | 10 | 0.024855 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-23 | 0.033422 | 10 | 0.040511 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8103-02 | 2026-07-23 | 0.03604 | 10 | 0.043684 | Utuado | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-01 | 2026-07-20 | 0.033215 | 10 | 0.040261 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-01 | 2026-07-23 | 0.021784 | 10 | 0.026405 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-01 | 2026-07-21 | 0.026983 | 10 | 0.032707 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-01 | 2026-07-21 | 0.03287 | 10 | 0.039842 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-01 | 2026-07-23 | 0.020713 | 10 | 0.025107 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-01 | 2026-07-21 | 0.057166 | 10 | 0.069292 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-01 | 2026-07-22 | 0.055923 | 10 | 0.067786 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-01 | 2026-07-22 | 0.013363 | 10 | 0.016198 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-01 | 2026-07-22 | 0.033419 | 10 | 0.040507 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-01 | 2026-07-23 | 0.0047354 | 10 | 0.0057399 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-01 | 2026-07-21 | 0.029385 | 10 | 0.035618 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-21 | 0.029019 | 10 | 0.035174 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-21 | 0.01661 | 10 | 0.020133 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-01 | 2026-07-21 | 0.015177 | 10 | 0.018396 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-21 | 0.028667 | 10 | 0.034748 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-21 | 0.029227 | 10 | 0.035427 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-01 | 2026-07-21 | 0.029545 | 10 | 0.035812 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-01 | 2026-07-21 | 0.028554 | 10 | 0.034611 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-21 | 0.030424 | 10 | 0.036878 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-01 | 2026-07-21 | 0.030069 | 10 | 0.036448 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7005-03 | 2026-07-20 | 0.036661 | 10 | 0.044438 | Aguadilla | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7005-03 | 2026-07-20 | 0.069594 | 10 | 0.084356 | Aguadilla | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-23 | 0.021127 | 10 | 0.025608 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1336-06 | 2026-07-23 | 0.035721 | 10 | 0.043299 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-23 | 0.017398 | 10 | 0.021089 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-23 | 0.015534 | 10 | 0.018829 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-23 | 0.039146 | 10 | 0.04745 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-23 | 0.004971 | 10 | 0.0060255 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6002-04 | 2026-07-23 | 0.022369 | 10 | 0.027114 | Mayaguez | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6002-04 | 2026-07-23 | 0.025476 | 10 | 0.03088 | Mayaguez | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-23 | 0.022991 | 10 | 0.027868 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6002-04 | 2026-07-24 | 0.032933 | 10 | 0.039919 | Mayaguez | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6002-04 | 2026-07-24 | 0.027846 | 10 | 0.033753 | Mayaguez | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6003-03 | 2026-07-24 | 0.016777 | 10 | 0.020336 | Mayaguez | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6003-03 | 2026-07-24 | 0.0079909 | 10 | 0.009686 | Mayaguez | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-23 | 0.031165 | 10 | 0.037776 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-23 | 0.022802 | 10 | 0.027639 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-23 | 0.021748 | 10 | 0.026361 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6003-03 | 2026-07-24 | 0.028583 | 10 | 0.034646 | Mayaguez | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-23 | 0.017426 | 10 | 0.021123 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6003-03 | 2026-07-25 | 0.032933 | 10 | 0.039919 | Mayaguez | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6201-01 | 2026-07-22 | 0.022991 | 10 | 0.027868 | Las Marías | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6201-01 | 2026-07-22 | 0.02818 | 10 | 0.034157 | Las Marías | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6201-01 | 2026-07-22 | 0.022991 | 10 | 0.027868 | Las Marías | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6201-01 | 2026-07-22 | 0.020505 | 10 | 0.024855 | Las Marías | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-23 | 0.031041 | 10 | 0.037625 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-22 | 0.029204 | 10 | 0.035399 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-22 | 0.027962 | 10 | 0.033893 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6201-01 | 2026-07-23 | 0.042253 | 10 | 0.051216 | Las Marías | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-23 | 0.006835 | 10 | 0.0082849 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6201-02 | 2026-07-21 | 0.015534 | 10 | 0.018829 | Las Marías | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1901-03 | 2026-07-25 | 0.034797 | 10 | 0.042178 | Guaynabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-07-22 | 0.030258 | 10 | 0.036676 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6201-02 | 2026-07-21 | 0.029204 | 10 | 0.035399 | Las Marías | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6201-02 | 2026-07-21 | 0.028583 | 10 | 0.034646 | Las Marías | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6801-02 | 2026-07-20 | 0.019884 | 10 | 0.024102 | Hormigueros | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-21 | 0.058845 | 10 | 0.071327 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-22 | 0.057166 | 10 | 0.069292 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-22 | 0.04971 | 10 | 0.060254 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-22 | 0.035418 | 10 | 0.042931 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-22 | 0.012427 | 10 | 0.015064 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-23 | 0.057166 | 10 | 0.069292 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-21 | 0.025476 | 10 | 0.03088 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-22 | 0.021127 | 10 | 0.025608 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-23 | 0.034175 | 10 | 0.041425 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-23 | 0.034797 | 10 | 0.042178 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-21 | 0.027434 | 10 | 0.033253 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-24 | 0.03604 | 10 | 0.043684 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-22 | 0.036693 | 10 | 0.044476 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1100-03 | 2026-07-20 | 0.0093206 | 10 | 0.011298 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1100-03 | 2026-07-20 | 0.016156 | 10 | 0.019583 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1100-03 | 2026-07-20 | 0.0086992 | 10 | 0.010545 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-25 | 0.041632 | 10 | 0.050463 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-21 | 0.026719 | 10 | 0.032387 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-24 | 0.029826 | 10 | 0.036152 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1100-03 | 2026-07-20 | 0.037904 | 10 | 0.045944 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1100-03 | 2026-07-20 | 0.02074 | 10 | 0.02514 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1100-03 | 2026-07-20 | 0.019969 | 10 | 0.024205 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-23 | 0.03169 | 10 | 0.038412 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-23 | 0.024863 | 10 | 0.030137 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1100-03 | 2026-07-20 | 0.019884 | 10 | 0.024102 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1100-03 | 2026-07-20 | 0.013049 | 10 | 0.015817 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1100-03 | 2026-07-20 | 0.022991 | 10 | 0.027868 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-24 | 0.024855 | 10 | 0.030127 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1100-03 | 2026-07-20 | 0.022991 | 10 | 0.027868 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1100-03 | 2026-07-20 | 0.021127 | 10 | 0.025608 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1100-03 | 2026-07-20 | 0.028359 | 10 | 0.034375 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1100-03 | 2026-07-20 | 0.024631 | 10 | 0.029856 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-23 | 0.04971 | 10 | 0.060254 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1100-03 | 2026-07-20 | 0.0081598 | 10 | 0.0098907 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1100-03 | 2026-07-20 | 0.022369 | 10 | 0.027114 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7802-01 | 2026-07-21 | 0.039768 | 10 | 0.048203 | San Sebastián | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-21 | 0.020505 | 10 | 0.024855 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1100-03 | 2026-07-20 | 0.016777 | 10 | 0.020336 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-24 | 0.034175 | 10 | 0.041425 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1100-03 | 2026-07-21 | 0.006835 | 10 | 0.0082849 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-22 | 0.015534 | 10 | 0.018829 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9003-06 | 2026-07-21 | 0.024946 | 10 | 0.030237 | Vega Baja | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1100-03 | 2026-07-20 | 0.034797 | 10 | 0.042178 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1100-03 | 2026-07-21 | 0.022991 | 10 | 0.027868 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1100-03 | 2026-07-20 | 0.017398 | 10 | 0.021089 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-25 | 0.024922 | 10 | 0.030209 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1100-03 | 2026-07-20 | 0.020505 | 10 | 0.024855 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-25 | 0.034797 | 10 | 0.042178 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1100-03 | 2026-07-21 | 0.026719 | 10 | 0.032387 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1100-03 | 2026-07-21 | 0.029826 | 10 | 0.036152 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1100-03 | 2026-07-21 | 0.024855 | 10 | 0.030127 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9003-06 | 2026-07-21 | 0.063162 | 10 | 0.07656 | Vega Baja | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9003-06 | 2026-07-21 | 0.024234 | 10 | 0.029374 | Vega Baja | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1100-03 | 2026-07-20 | 0.030447 | 10 | 0.036906 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1100-03 | 2026-07-20 | 0.026098 | 10 | 0.031633 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-23 | 0.01911 | 10 | 0.023164 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1100-03 | 2026-07-20 | 0.015534 | 10 | 0.018829 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9003-06 | 2026-07-21 | 0.084789 | 10 | 0.10277 | Vega Baja | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1100-03 | 2026-07-21 | 0.02176 | 10 | 0.026376 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1100-03 | 2026-07-21 | 0.020526 | 10 | 0.02488 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1100-03 | 2026-07-21 | 0.023612 | 10 | 0.028621 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1100-03 | 2026-07-21 | 0.029826 | 10 | 0.036152 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-23 | 0.01243 | 10 | 0.015067 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-25 | 0.03169 | 10 | 0.038412 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-22 | 0.020505 | 10 | 0.024855 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7301-02 | 2026-07-23 | 0.017646 | 10 | 0.021389 | Rincón | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-23 | 0.019262 | 10 | 0.023348 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-25 | 0.040389 | 10 | 0.048957 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-22 | 0.032058 | 10 | 0.038859 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-22 | 0.031321 | 10 | 0.037965 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-22 | 0.02884 | 10 | 0.034957 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-22 | 0.029304 | 10 | 0.03552 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-22 | 0.026916 | 10 | 0.032625 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-22 | 0.034024 | 10 | 0.041242 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-22 | 0.040289 | 10 | 0.048835 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-07-21 | 0.027101 | 10 | 0.032849 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-22 | 0.02885 | 10 | 0.034969 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-07-22 | 0.037036 | 10 | 0.044892 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-22 | 0.02423 | 10 | 0.029369 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-22 | 0.015408 | 10 | 0.018677 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-22 | 0.029482 | 10 | 0.035735 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-22 | 0.037042 | 10 | 0.044899 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1201-01 | 2026-07-20 | 0.0286 | 10 | 0.034667 | Trujillo Alto | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-04 | 2026-07-20 | 0.029357 | 10 | 0.035584 | Trujillo Alto | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-23 | 0.006835 | 10 | 0.0082849 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-04 | 2026-07-20 | 0.025043 | 10 | 0.030355 | Trujillo Alto | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1201-01 | 2026-07-20 | 0.024934 | 10 | 0.030222 | Trujillo Alto | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-22 | 0.027487 | 10 | 0.033317 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-22 | 0.027629 | 10 | 0.033489 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-22 | 0.03067 | 10 | 0.037176 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-22 | 0.031558 | 10 | 0.038252 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-22 | 0.032577 | 10 | 0.039488 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-22 | 0.033537 | 10 | 0.040651 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-22 | 0.028148 | 10 | 0.034119 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-22 | 0.037706 | 10 | 0.045704 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-22 | 0.027458 | 10 | 0.033283 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3501-01 | 2026-07-24 | 0.035492 | 10 | 0.043021 | Aibonito | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-21 | 0.052747 | 10 | 0.063936 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-22 | 0.024489 | 10 | 0.029683 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-07-21 | 0.027988 | 10 | 0.033925 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-21 | 0.022794 | 10 | 0.027629 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-22 | 0.02993 | 10 | 0.036279 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-21 | 0.024793 | 10 | 0.030052 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-21 | 0.019974 | 10 | 0.024211 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-22 | 0.035468 | 10 | 0.042991 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-22 | 0.017755 | 10 | 0.021521 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-22 | 0.02544 | 10 | 0.030836 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-22 | 0.030399 | 10 | 0.036848 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-22 | 0.026021 | 10 | 0.031541 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-07-22 | 0.03545 | 10 | 0.04297 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-22 | 0.041632 | 10 | 0.050463 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-22 | 0.026914 | 10 | 0.032623 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-22 | 0.013661 | 10 | 0.016559 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-22 | 0.035566 | 10 | 0.04311 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-22 | 0.025031 | 10 | 0.030341 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-22 | 0.024152 | 10 | 0.029275 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-22 | 0.029204 | 10 | 0.035399 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-07-21 | 0.040164 | 10 | 0.048683 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-07-21 | 0.044142 | 10 | 0.053505 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-07-22 | 0.040185 | 10 | 0.048709 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1201-01 | 2026-07-20 | 0.027955 | 10 | 0.033885 | Trujillo Alto | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-04 | 2026-07-20 | 0.028194 | 10 | 0.034174 | Trujillo Alto | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-07-21 | 0.024234 | 10 | 0.029374 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-22 | 0.032752 | 10 | 0.0397 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-07-22 | 0.033216 | 10 | 0.040261 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-22 | 0.026696 | 10 | 0.032359 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-07-22 | 0.028328 | 10 | 0.034337 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-22 | 0.031069 | 10 | 0.037659 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-07-22 | 0.029517 | 10 | 0.035779 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-21 | 0.03604 | 10 | 0.043684 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-23 | 0.023612 | 10 | 0.028621 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-23 | 0.016156 | 10 | 0.019583 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7301-02 | 2026-07-23 | 0.026412 | 10 | 0.032014 | Rincón | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-23 | 0.016156 | 10 | 0.019583 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-21 | 0.022369 | 10 | 0.027114 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7301-02 | 2026-07-23 | 0.019963 | 10 | 0.024197 | Rincón | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-24 | 0.022991 | 10 | 0.027868 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-23 | 0.020505 | 10 | 0.024855 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-01 | 2026-07-21 | 0.05903 | 10 | 0.071552 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-01 | 2026-07-23 | 0.06338 | 10 | 0.076824 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-21 | 0.022991 | 10 | 0.027868 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-23 | 0.022369 | 10 | 0.027114 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-23 | 0.041632 | 10 | 0.050463 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-24 | 0.023612 | 10 | 0.028621 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-24 | 0.020505 | 10 | 0.024855 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-24 | 0.027962 | 10 | 0.033893 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-07-23 | 0.018358 | 10 | 0.022253 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2404-08 | 2026-07-21 | 0.014291 | 10 | 0.017323 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2404-08 | 2026-07-21 | 0.025476 | 10 | 0.03088 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2404-08 | 2026-07-21 | 0.024234 | 10 | 0.029374 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2404-08 | 2026-07-21 | 0.028583 | 10 | 0.034646 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2404-08 | 2026-07-21 | 0.029204 | 10 | 0.035399 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2404-08 | 2026-07-21 | 0.024453 | 10 | 0.02964 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2404-08 | 2026-07-22 | 0.022664 | 10 | 0.027471 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2404-08 | 2026-07-22 | 0.032511 | 10 | 0.039408 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2404-08 | 2026-07-22 | 0.032841 | 10 | 0.039807 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-22 | 0.019884 | 10 | 0.024102 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2404-08 | 2026-07-22 | 0.03362 | 10 | 0.040752 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2404-08 | 2026-07-22 | 0.033634 | 10 | 0.040768 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2404-08 | 2026-07-25 | 0.030447 | 10 | 0.036906 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2404-08 | 2026-07-25 | 0.024234 | 10 | 0.029374 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2404-08 | 2026-07-25 | 0.02734 | 10 | 0.03314 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2404-08 | 2026-07-25 | 0.032933 | 10 | 0.039919 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-21 | 0.036273 | 10 | 0.043967 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-21 | 0.013049 | 10 | 0.015817 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-22 | 0.026236 | 10 | 0.031801 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-21 | 0.019262 | 10 | 0.023348 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-21 | 0.019884 | 10 | 0.024102 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-21 | 0.030398 | 10 | 0.036846 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-21 | 0.032992 | 10 | 0.03999 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7003-02 | 2026-07-19 | 0.026719 | 10 | 0.032387 | Aguadilla | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7503-04 | 2026-07-24 | 0.027962 | 10 | 0.033893 | ISABELA | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3301-01 | 2026-07-20 | 0.070215 | 10 | 0.085109 | San Lorenzo | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-07-20 | 0.034797 | 10 | 0.042178 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-07-20 | 0.024234 | 10 | 0.029374 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3301-01 | 2026-07-20 | 0.038525 | 10 | 0.046697 | San Lorenzo | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3301-01 | 2026-07-20 | 0.02734 | 10 | 0.03314 | San Lorenzo | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7504-02 | 2026-07-24 | 0.045602 | 10 | 0.055276 | Isabela | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7504-02 | 2026-07-23 | 0.034175 | 10 | 0.041425 | Isabela | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7504-02 | 2026-07-23 | 0.024234 | 10 | 0.029374 | Isabela | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7504-02 | 2026-07-24 | 0.021748 | 10 | 0.026361 | Isabela | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1343-05 | 2026-07-23 | 0.052195 | 10 | 0.063267 | Guaynabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1343-05 | 2026-07-25 | 0.052195 | 10 | 0.063267 | Guaynabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-07-22 | 0.015794 | 10 | 0.019144 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-22 | 0.030952 | 10 | 0.037517 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-22 | 0.017808 | 10 | 0.021585 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-22 | 0.0098593 | 10 | 0.011951 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-22 | 0.036921 | 10 | 0.044752 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-22 | 0.026067 | 10 | 0.031597 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-22 | 0.048171 | 10 | 0.058389 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-22 | 0.020467 | 10 | 0.024809 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-22 | 0.029451 | 10 | 0.035698 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-22 | 0.036139 | 10 | 0.043805 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-22 | 0.029675 | 10 | 0.035969 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3301-01 | 2026-07-20 | 0.01367 | 10 | 0.01657 | San Lorenzo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-23 | 0.037904 | 10 | 0.045944 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7303-01 | 2026-07-22 | 0.025476 | 10 | 0.03088 | Aguada | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7303-01 | 2026-07-22 | 0.025476 | 10 | 0.03088 | Aguada | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7303-01 | 2026-07-22 | 0.040389 | 10 | 0.048957 | Aguada | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8014-06 | 2026-07-23 | 0.037927 | 10 | 0.045972 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5501-04 | 2026-07-20 | 0.12862 | 10 | 0.15591 | Guayanilla | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8014-06 | 2026-07-23 | 0.026098 | 10 | 0.031633 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8014-06 | 2026-07-22 | 0.039845 | 10 | 0.048297 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8014-06 | 2026-07-22 | 0.048403 | 10 | 0.05867 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3205-08 | 2026-07-21 | 0.044739 | 10 | 0.054229 | Humacao | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3205-08 | 2026-07-21 | 0.019884 | 10 | 0.024102 | Humacao | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3205-08 | 2026-07-21 | 0.019262 | 10 | 0.023348 | Humacao | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8014-06 | 2026-07-22 | 0.041288 | 10 | 0.050046 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3205-08 | 2026-07-21 | 0.032964 | 10 | 0.039957 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-07-21 | 0.026855 | 10 | 0.032552 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-07-21 | 0.029375 | 10 | 0.035607 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-21 | 0.032933 | 10 | 0.039919 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-22 | 0.023612 | 10 | 0.028621 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-22 | 0.027962 | 10 | 0.033893 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-21 | 0.026098 | 10 | 0.031633 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-21 | 0.017398 | 10 | 0.021089 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-22 | 0.014913 | 10 | 0.018076 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8014-06 | 2026-07-24 | 0.024732 | 10 | 0.029978 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-22 | 0.019262 | 10 | 0.023348 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-24 | 0.017398 | 10 | 0.021089 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-07-22 | 0.0421 | 10 | 0.051031 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-25 | 0.0070407 | 10 | 0.0085342 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-22 | 0.01802 | 10 | 0.021842 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-22 | 0.018984 | 10 | 0.023011 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-22 | 0.01802 | 10 | 0.021842 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-24 | 0.017495 | 10 | 0.021206 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 4001-03 | 2026-07-21 | 0.073047 | 10 | 0.088541 | Guayama | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-22 | 0.027111 | 10 | 0.032862 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-22 | 0.025069 | 10 | 0.030386 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-22 | 0.030557 | 10 | 0.037038 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1901-05 | 2026-07-21 | 0.01802 | 10 | 0.021842 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1901-05 | 2026-07-21 | 0.019262 | 10 | 0.023348 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-24 | 0.031078 | 10 | 0.037671 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-24 | 0.025625 | 10 | 0.03106 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-24 | 0.028272 | 10 | 0.034269 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-22 | 0.019262 | 10 | 0.023348 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-23 | 0.019262 | 10 | 0.023348 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-07-22 | 0.037843 | 10 | 0.04587 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-22 | 0.031203 | 10 | 0.037822 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-23 | 0.034089 | 10 | 0.04132 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1909-07 | 2026-07-22 | 0.014913 | 10 | 0.018076 | Guaynabo | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-22 | 0.034681 | 10 | 0.042038 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1909-07 | 2026-07-22 | 0.021127 | 10 | 0.025608 | Guaynabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-22 | 0.032683 | 10 | 0.039616 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-23 | 0.026098 | 10 | 0.031633 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1909-07 | 2026-07-22 | 0.014913 | 10 | 0.018076 | Guaynabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-23 | 0.021855 | 10 | 0.026492 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-23 | 0.021127 | 10 | 0.025608 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-22 | 0.022991 | 10 | 0.027868 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3102-02 | 2026-07-22 | 0.032689 | 10 | 0.039623 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-23 | 0.021748 | 10 | 0.026361 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-23 | 0.021147 | 10 | 0.025632 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6303-01 | 2026-07-21 | 0.20381 | 10 | 0.24704 | Maricao | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-23 | 0.042875 | 10 | 0.051969 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-22 | 0.034105 | 10 | 0.041339 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8501-02 | 2026-07-21 | 0.0727 | 10 | 0.088122 | Florida | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-23 | 0.025805 | 10 | 0.031279 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8405-03 | 2026-07-25 | 0.027286 | 10 | 0.033073 | Manatí | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-25 | 0.021748 | 10 | 0.026361 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-24 | 0.022369 | 10 | 0.027114 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3102-02 | 2026-07-22 | 0.034043 | 10 | 0.041264 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-23 | 0.026719 | 10 | 0.032387 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-22 | 0.034417 | 10 | 0.041718 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-22 | 0.018767 | 10 | 0.022748 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-23 | 0.013049 | 10 | 0.015817 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-23 | 0.0081778 | 10 | 0.0099125 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-23 | 0.0099419 | 10 | 0.012051 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-25 | 0.032933 | 10 | 0.039919 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-23 | 0.033554 | 10 | 0.040671 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-07-23 | 0.032262 | 10 | 0.039106 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3006-05 | 2026-07-21 | 0.023411 | 10 | 0.028377 | Caguas | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-23 | 0.01802 | 10 | 0.021842 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-23 | 0.019884 | 10 | 0.024102 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-07-21 | 0.023178 | 10 | 0.028094 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-24 | 0.016156 | 10 | 0.019583 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-23 | 0.042875 | 10 | 0.051969 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-23 | 0.026098 | 10 | 0.031633 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-21 | 0.037904 | 10 | 0.045944 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3010-01 | 2026-07-22 | 0.037282 | 10 | 0.045191 | Caguas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-07-23 | 0.026772 | 10 | 0.032451 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-07-22 | 0.031589 | 10 | 0.038289 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-07-23 | 0.02915 | 10 | 0.035333 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-23 | 0.029204 | 10 | 0.035399 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-07-23 | 0.02915 | 10 | 0.035333 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-24 | 0.029826 | 10 | 0.036152 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-07-23 | 0.032962 | 10 | 0.039954 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 4003-02 | 2026-07-23 | 0.03377 | 10 | 0.040933 | Guayama | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-23 | 0.022991 | 10 | 0.027868 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 4003-02 | 2026-07-23 | 0.026242 | 10 | 0.031808 | Guayama | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-07-22 | 0.031428 | 10 | 0.038095 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 8007-03 | 2026-07-22 | 0.0243 | 10 | 0.029455 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 8007-03 | 2026-07-22 | 0.0086992 | 10 | 0.010545 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-07-23 | 0.034801 | 10 | 0.042183 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-24 | 0.031534 | 10 | 0.038222 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-07-24 | 0.032523 | 10 | 0.039422 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3405-01 | 2026-07-22 | 0.052195 | 10 | 0.063267 | Cayey | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 8007-04 | 2026-07-22 | 0.04518 | 10 | 0.054764 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-24 | 0.032311 | 10 | 0.039165 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3405-01 | 2026-07-22 | 0.11371 | 10 | 0.13783 | Cayey | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-23 | 0.018826 | 10 | 0.02282 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-23 | 0.006307 | 10 | 0.0076449 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-23 | 0.0068244 | 10 | 0.008272 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 2401-01 | 2026-07-24 | 0.056545 | 10 | 0.068539 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-23 | 0.045736 | 10 | 0.055438 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7601-03 | 2026-07-22 | 0.023612 | 10 | 0.028621 | Camuy | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-23 | 0.035795 | 10 | 0.043388 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3405-01 | 2026-07-22 | 0.043819 | 10 | 0.053113 | Cayey | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7601-03 | 2026-07-21 | 0.037904 | 10 | 0.045944 | Camuy | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-22 | 0.018641 | 10 | 0.022595 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-23 | 0.011185 | 10 | 0.013557 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-24 | 0.016156 | 10 | 0.019583 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9001-01 | 2026-07-23 | 0.022552 | 10 | 0.027335 | Vega Baja | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-25 | 0.05903 | 10 | 0.071552 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-23 | 0.060273 | 10 | 0.073058 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-25 | 0.037282 | 10 | 0.045191 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-23 | 0.027962 | 10 | 0.033893 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9001-01 | 2026-07-23 | 0.026098 | 10 | 0.031633 | Vega Baja | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7601-03 | 2026-07-22 | 0.023612 | 10 | 0.028621 | Camuy | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-23 | 0.0043496 | 10 | 0.0052723 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-23 | 0.015534 | 10 | 0.018829 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-25 | 0.031772 | 10 | 0.038511 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-03 | 2026-07-23 | 0.013187 | 10 | 0.015984 | Caguas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3102-02 | 2026-07-25 | 0.031789 | 10 | 0.038533 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 2001-01 | 2026-07-23 | 0.054059 | 10 | 0.065526 | Fajardo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-07-23 | 0.030933 | 10 | 0.037495 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 2001-01 | 2026-07-23 | 0.037904 | 10 | 0.045944 | Fajardo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 2001-01 | 2026-07-23 | 0.017398 | 10 | 0.021089 | Fajardo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8002-01 | 2026-07-23 | 0.040084 | 10 | 0.048587 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8002-01 | 2026-07-23 | 0.032311 | 10 | 0.039165 | Arecibo | LUMA | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1706-03 | 2026-07-24 | 0.024029 | 10 | 0.029126 | Bayamón | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-23 | 0.013145 | 10 | 0.015933 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1706-03 | 2026-07-24 | 0.02382 | 10 | 0.028872 | Bayamón | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-03 | 2026-07-23 | 0.029259 | 10 | 0.035465 | Hatillo | LUMA | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5302-04 | 2026-07-22 | 0.23053 | 10 | 0.27943 | Yauco | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-24 | 0.017398 | 10 | 0.021089 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-24 | 0.022369 | 10 | 0.027114 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3005-02 | 2026-07-23 | 0.021127 | 10 | 0.025608 | Caguas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5302-01 | 2026-07-22 | 0.07705 | 10 | 0.093394 | Yauco | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-24 | 0.024234 | 10 | 0.029374 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3005-02 | 2026-07-23 | 0.023612 | 10 | 0.028621 | Caguas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3005-02 | 2026-07-23 | 0.023612 | 10 | 0.028621 | Caguas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3005-02 | 2026-07-23 | 0.022991 | 10 | 0.027868 | Caguas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-23 | 0.023612 | 10 | 0.028621 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-23 | 0.032933 | 10 | 0.039919 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3005-02 | 2026-07-23 | 0.020505 | 10 | 0.024855 | Caguas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-24 | 0.028583 | 10 | 0.034646 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3005-02 | 2026-07-23 | 0.023612 | 10 | 0.028621 | Caguas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-24 | 0.0091348 | 10 | 0.011073 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-24 | 0.0098383 | 10 | 0.011925 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-24 | 0.022086 | 10 | 0.026771 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3005-02 | 2026-07-23 | 0.026098 | 10 | 0.031633 | Caguas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-24 | 0.019034 | 10 | 0.023072 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-03 | 2026-07-24 | 0.016545 | 10 | 0.020054 | Caguas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-03 | 2026-07-24 | 0.034085 | 10 | 0.041315 | Caguas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-03 | 2026-07-24 | 0.027111 | 10 | 0.032862 | Caguas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-03 | 2026-07-24 | 0.02813 | 10 | 0.034096 | Caguas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-25 | 0.011806 | 10 | 0.01431 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-25 | 0.020505 | 10 | 0.024855 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-24 | 0.016156 | 10 | 0.019583 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-24 | 0.033554 | 10 | 0.040671 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-24 | 0.019884 | 10 | 0.024102 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1343-05 | 2026-07-25 | 0.032823 | 10 | 0.039785 | Guaynabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-24 | 0.024234 | 10 | 0.029374 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-24 | 0.024855 | 10 | 0.030127 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7303-01 | 2026-07-23 | 0.023612 | 10 | 0.028621 | Aguada | Xperts | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-24 | 0.034797 | 10 | 0.042178 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1424-06 | 2026-07-23 | 0.02026 | 10 | 0.024558 | San Juan | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1338-02 | 2026-07-23 | 0.019023 | 10 | 0.023058 | San Juan | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-03 | 2026-07-24 | 0.027696 | 10 | 0.033571 | Caguas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-03 | 2026-07-24 | 0.027696 | 10 | 0.033571 | Caguas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-03 | 2026-07-24 | 0.03409 | 10 | 0.041321 | Caguas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-03 | 2026-07-24 | 0.032509 | 10 | 0.039405 | Caguas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-03 | 2026-07-24 | 0.036633 | 10 | 0.044404 | Caguas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-03 | 2026-07-24 | 0.033692 | 10 | 0.040839 | Caguas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-03 | 2026-07-24 | 0.033854 | 10 | 0.041035 | Caguas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 2401-01 | 2026-07-24 | 0.056545 | 10 | 0.068539 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 2001-04 | 2026-07-24 | 0.025476 | 10 | 0.03088 | Fajardo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9001-02 | 2026-07-24 | 0.034797 | 10 | 0.042178 | Vega Baja | Xperts | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-03 | 2026-07-24 | 0.033185 | 10 | 0.040224 | Caguas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-25 | 0.0099419 | 10 | 0.012051 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1336-09 | 2026-07-24 | 0.038489 | 10 | 0.046654 | San Juan | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-25 | 0.035606 | 10 | 0.043159 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-25 | 0.03086 | 10 | 0.037407 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-25 | 0.028115 | 10 | 0.034079 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8008-01 | 2026-07-24 | 0.088856 | 10 | 0.1077 | Arecibo | Xperts | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6012-02 | 2026-07-24 | 0.047042 | 10 | 0.057021 | Mayaguez | Xperts | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-25 | 0.028583 | 10 | 0.034646 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-03 | 2026-07-25 | 0.033949 | 10 | 0.041151 | Caguas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8011-04 | 2026-07-25 | 0.039146 | 10 | 0.04745 | Arecibo | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-25 | 0.031629 | 10 | 0.038338 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7504-01 | 2026-07-25 | 0.04536 | 10 | 0.054982 | Aguadilla | Xperts | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-27 | 0.013762 | 10 | 0.016681 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-29 | 0.014913 | 10 | 0.018076 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-29 | 0.019262 | 10 | 0.023348 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-28 | 0.028583 | 10 | 0.034646 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-30 | 0.024855 | 10 | 0.030127 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-28 | 0.028451 | 10 | 0.034486 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3701-03 | 2026-07-31 | 0.029826 | 10 | 0.036152 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3701-03 | 2026-07-30 | 0.027962 | 10 | 0.033893 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3701-03 | 2026-07-31 | 0.027962 | 10 | 0.033893 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-28 | 0.02734 | 10 | 0.03314 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-31 | 0.028583 | 10 | 0.034646 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-29 | 0.016156 | 10 | 0.019583 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-28 | 0.027962 | 10 | 0.033893 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-29 | 0.03169 | 10 | 0.038412 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-29 | 0.016156 | 10 | 0.019583 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-28 | 0.014913 | 10 | 0.018076 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-29 | 0.014913 | 10 | 0.018076 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-29 | 0.016777 | 10 | 0.020336 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-29 | 0.01802 | 10 | 0.021842 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-29 | 0.021127 | 10 | 0.025608 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-28 | 0.024855 | 10 | 0.030127 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-28 | 0.022369 | 10 | 0.027114 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2302-03 | 2026-07-29 | 0.045981 | 10 | 0.055735 | Río Grande | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 9401-02 | 2026-07-30 | 0.043457 | 10 | 0.052676 | Toa Alta | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7301-02 | 2026-07-30 | 0.019963 | 10 | 0.024197 | Rincón | Site Resources | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7301-02 | 2026-07-30 | 0.032765 | 10 | 0.039715 | Rincón | Site Resources | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2404-08 | 2026-07-31 | 0.030896 | 10 | 0.037449 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2404-08 | 2026-07-31 | 0.038525 | 10 | 0.046697 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2404-08 | 2026-07-31 | 0.021255 | 10 | 0.025763 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2404-08 | 2026-07-31 | 0.054498 | 10 | 0.066059 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2302-03 | 2026-07-29 | 0.037282 | 10 | 0.045191 | Río Grande | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2302-03 | 2026-07-29 | 0.037282 | 10 | 0.045191 | Río Grande | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2302-03 | 2026-07-29 | 0.04101 | 10 | 0.04971 | Río Grande | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6801-02 | 2026-07-27 | 0.047224 | 10 | 0.057242 | Hormigueros | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6801-02 | 2026-07-29 | 0.062759 | 10 | 0.076071 | Hormigueros | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6801-02 | 2026-07-31 | 0.11371 | 10 | 0.13783 | San Germán | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6801-02 | 2026-07-30 | 0.10563 | 10 | 0.12804 | San Germán | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1303-01 | 2026-07-28 | 0.026098 | 10 | 0.031633 | San Juan | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 4003-01 | 2026-07-30 | 0.026579 | 10 | 0.032216 | Guayama | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 4003-01 | 2026-07-30 | 0.040823 | 10 | 0.049483 | Guayama | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 4003-01 | 2026-07-28 | 0.022847 | 10 | 0.027693 | Guayama | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 4003-01 | 2026-07-28 | 0.038442 | 10 | 0.046597 | Guayama | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 4003-01 | 2026-07-28 | 0.043032 | 10 | 0.05216 | Guayama | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 2901-01 | 2026-07-28 | 0.041632 | 10 | 0.050463 | Yabucoa | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 8007-03 | 2026-07-31 | 0.013984 | 10 | 0.01695 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 8007-03 | 2026-07-31 | 0.020505 | 10 | 0.024855 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 8007-03 | 2026-07-31 | 0.023612 | 10 | 0.028621 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7402-01 | 2026-07-30 | 0.025476 | 10 | 0.03088 | Camuy | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7402-01 | 2026-07-31 | 0.022369 | 10 | 0.027114 | Camuy | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5501-03 | 2026-07-30 | 0.034175 | 10 | 0.041425 | Guayanilla | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-29 | 0.025653 | 10 | 0.031094 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5501-03 | 2026-07-31 | 0.030447 | 10 | 0.036906 | Guayanilla | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5007-01 | 2026-07-28 | 0.032311 | 10 | 0.039165 | Ponce | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5007-01 | 2026-07-28 | 0.030447 | 10 | 0.036906 | Ponce | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-31 | 0.04536 | 10 | 0.054982 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-31 | 0.019093 | 10 | 0.023143 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-28 | 0.042253 | 10 | 0.051216 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7301-02 | 2026-07-29 | 0.032765 | 10 | 0.039715 | Rincón | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2302-03 | 2026-07-29 | 0.011513 | 10 | 0.013956 | Río Grande | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-28 | 0.03111 | 10 | 0.037709 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-07-28 | 0.031291 | 10 | 0.037929 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-30 | 0.029204 | 10 | 0.035399 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-07-30 | 0.027962 | 10 | 0.033893 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3401-02 | 2026-07-28 | 0.080157 | 10 | 0.09716 | Cayey | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3401-02 | 2026-07-28 | 0.073943 | 10 | 0.089628 | Cayey | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3401-02 | 2026-07-28 | 0.02734 | 10 | 0.03314 | Cayey | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3401-02 | 2026-07-28 | 0.028583 | 10 | 0.034646 | Cayey | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3401-02 | 2026-07-28 | 0.030447 | 10 | 0.036906 | Cayey | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3401-02 | 2026-07-28 | 0.026719 | 10 | 0.032387 | Cayey | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3401-02 | 2026-07-28 | 0.029204 | 10 | 0.035399 | Cayey | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3401-02 | 2026-07-28 | 0.024234 | 10 | 0.029374 | Cayey | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-07-30 | 0.012427 | 10 | 0.015064 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-07-30 | 0.037904 | 10 | 0.045944 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-07-29 | 0.034797 | 10 | 0.042178 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-07-29 | 0.042253 | 10 | 0.051216 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-07-30 | 0.020505 | 10 | 0.024855 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-07-31 | 0.041881 | 10 | 0.050765 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-03 | 2026-07-27 | 0.030246 | 10 | 0.036662 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-04 | 2026-07-27 | 0.030478 | 10 | 0.036943 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-04 | 2026-07-27 | 0.016505 | 10 | 0.020006 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-03 | 2026-07-27 | 0.018641 | 10 | 0.022595 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7201-03 | 2026-07-28 | 0.056545 | 10 | 0.068539 | Aguada | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7201-03 | 2026-07-28 | 0.04948 | 10 | 0.059976 | Aguada | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7201-03 | 2026-07-28 | 0.054449 | 10 | 0.065999 | Aguada | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1201-01 | 2026-07-30 | 0.033158 | 10 | 0.040192 | Trujillo Alto | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-04 | 2026-07-30 | 0.033304 | 10 | 0.040368 | Trujillo Alto | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-04 | 2026-07-30 | 0.041981 | 10 | 0.050887 | Trujillo Alto | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1201-01 | 2026-07-30 | 0.04222 | 10 | 0.051176 | Trujillo Alto | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-04 | 2026-07-30 | 0.024855 | 10 | 0.030127 | Trujillo Alto | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1201-01 | 2026-07-30 | 0.024855 | 10 | 0.030127 | Trujillo Alto | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-04 | 2026-07-30 | 0.036154 | 10 | 0.043823 | Trujillo Alto | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1201-01 | 2026-07-30 | 0.03684 | 10 | 0.044654 | Trujillo Alto | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6801-02 | 2026-07-27 | 0.067184 | 10 | 0.081436 | Hormigueros | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6801-02 | 2026-07-27 | 0.04971 | 10 | 0.060254 | Hormigueros | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3008-03 | 2026-07-28 | 0.028583 | 10 | 0.034646 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1519-01 | 2026-07-27 | 0.026098 | 10 | 0.031633 | San Juan | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-29 | 0.04971 | 10 | 0.060254 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-29 | 0.045981 | 10 | 0.055735 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-29 | 0.051574 | 10 | 0.062514 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-03 | 2026-07-29 | 0.031439 | 10 | 0.038108 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-03 | 2026-07-29 | 0.020121 | 10 | 0.024389 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-29 | 0.044117 | 10 | 0.053476 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-03 | 2026-07-29 | 0.026719 | 10 | 0.032387 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-29 | 0.04899 | 10 | 0.059381 | Juncosluis | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 8007-04 | 2026-07-29 | 0.02734 | 10 | 0.03314 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2305-02 | 2026-07-28 | 0.026887 | 10 | 0.032591 | Luquillo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 2201-04 | 2026-07-28 | 0.026173 | 10 | 0.031725 | Luquillo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2305-02 | 2026-07-28 | 0.024166 | 10 | 0.029292 | Luquillo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 2201-04 | 2026-07-28 | 0.024563 | 10 | 0.029774 | Luquillo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-30 | 0.02734 | 10 | 0.03314 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-30 | 0.019884 | 10 | 0.024102 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-30 | 0.033282 | 10 | 0.040342 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-30 | 0.015932 | 10 | 0.019312 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-30 | 0.01802 | 10 | 0.021842 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-30 | 0.012427 | 10 | 0.015064 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-29 | 0.040389 | 10 | 0.048957 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 4101-04 | 2026-07-27 | 0.021394 | 10 | 0.025932 | Arroyo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 4101-04 | 2026-07-27 | 0.047224 | 10 | 0.057242 | Arroyo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 4101-04 | 2026-07-27 | 0.041459 | 10 | 0.050253 | Arroyo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 4101-04 | 2026-07-27 | 0.040768 | 10 | 0.049416 | Arroyo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 4101-04 | 2026-07-27 | 0.092764 | 10 | 0.11244 | Arroyo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-30 | 0.021757 | 10 | 0.026372 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-30 | 0.028583 | 10 | 0.034646 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-30 | 0.055302 | 10 | 0.067033 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-30 | 0.013522 | 10 | 0.016391 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-30 | 0.022204 | 10 | 0.026914 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-30 | 0.029204 | 10 | 0.035399 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6003-03 | 2026-07-28 | 0.020505 | 10 | 0.024855 | Mayaguez | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6003-03 | 2026-07-28 | 0.029204 | 10 | 0.035399 | Mayaguez | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6003-03 | 2026-07-28 | 0.028583 | 10 | 0.034646 | Mayaguez | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-29 | 0.029204 | 10 | 0.035399 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-29 | 0.02636 | 10 | 0.031951 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-29 | 0.027537 | 10 | 0.033379 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-06 | 2026-07-29 | 0.020323 | 10 | 0.024634 | San Juan | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-29 | 0.028531 | 10 | 0.034584 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8013-02 | 2026-07-29 | 0.034175 | 10 | 0.041425 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-29 | 0.027585 | 10 | 0.033437 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-07-27 | 0.032162 | 10 | 0.038984 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-30 | 0.01802 | 10 | 0.021842 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-30 | 0.024855 | 10 | 0.030127 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-30 | 0.023612 | 10 | 0.028621 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-30 | 0.024234 | 10 | 0.029374 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-07-29 | 0.026098 | 10 | 0.031633 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-28 | 0.035418 | 10 | 0.042931 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-27 | 0.035418 | 10 | 0.042931 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-29 | 0.072267 | 10 | 0.087596 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-27 | 0.025476 | 10 | 0.03088 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-30 | 0.027746 | 10 | 0.033632 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.032327 | 10 | 0.039185 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-29 | 0.044951 | 10 | 0.054486 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-30 | 0.028927 | 10 | 0.035063 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-30 | 0.028927 | 10 | 0.035063 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1201-01 | 2026-07-30 | 0.034371 | 10 | 0.041662 | Trujillo Alto | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7701-04 | 2026-07-29 | 0.026663 | 10 | 0.032319 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-04 | 2026-07-30 | 0.033963 | 10 | 0.041167 | Trujillo Alto | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7701-04 | 2026-07-29 | 0.030274 | 10 | 0.036696 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7701-01 | 2026-07-29 | 0.028825 | 10 | 0.03494 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7701-01 | 2026-07-29 | 0.027944 | 10 | 0.033872 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8014-06 | 2026-07-27 | 0.037187 | 10 | 0.045075 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7701-01 | 2026-07-29 | 0.029204 | 10 | 0.035399 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7701-01 | 2026-07-29 | 0.023767 | 10 | 0.028808 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7701-01 | 2026-07-29 | 0.025471 | 10 | 0.030874 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7701-01 | 2026-07-29 | 0.022143 | 10 | 0.02684 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7701-01 | 2026-07-29 | 0.02936 | 10 | 0.035588 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7701-01 | 2026-07-29 | 0.031163 | 10 | 0.037773 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-29 | 0.027677 | 10 | 0.033547 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-29 | 0.015778 | 10 | 0.019125 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-29 | 0.027454 | 10 | 0.033278 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-29 | 0.021488 | 10 | 0.026046 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-30 | 0.039146 | 10 | 0.04745 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-29 | 0.02205 | 10 | 0.026727 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-29 | 0.018433 | 10 | 0.022343 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-29 | 0.034859 | 10 | 0.042254 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-29 | 0.032534 | 10 | 0.039436 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-07-27 | 0.076429 | 10 | 0.092641 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2404-08 | 2026-07-30 | 0.026098 | 10 | 0.031633 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-02 | 2026-07-28 | 0.14469 | 10 | 0.17538 | Gurabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-02 | 2026-07-28 | 0.055777 | 10 | 0.067608 | Gurabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-29 | 0.025384 | 10 | 0.030768 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-07-29 | 0.015534 | 10 | 0.018829 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-29 | 0.033048 | 10 | 0.040059 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8014-06 | 2026-07-29 | 0.021773 | 10 | 0.026391 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8014-06 | 2026-07-28 | 0.031423 | 10 | 0.038088 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-29 | 0.035569 | 10 | 0.043113 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8014-06 | 2026-07-28 | 0.028407 | 10 | 0.034432 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-29 | 0.018274 | 10 | 0.02215 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8014-06 | 2026-07-27 | 0.029491 | 10 | 0.035747 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5501-03 | 2026-07-27 | 0.031069 | 10 | 0.037659 | Guayanilla | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2404-08 | 2026-07-27 | 0.027962 | 10 | 0.033893 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2404-08 | 2026-07-27 | 0.032933 | 10 | 0.039919 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5501-03 | 2026-07-27 | 0.029204 | 10 | 0.035399 | Guayanilla | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2404-08 | 2026-07-27 | 0.037904 | 10 | 0.045944 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2404-08 | 2026-07-27 | 0.018641 | 10 | 0.022595 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5501-03 | 2026-07-30 | 0.017398 | 10 | 0.021089 | Guayanilla | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2404-08 | 2026-07-30 | 0.014913 | 10 | 0.018076 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-30 | 0.028807 | 10 | 0.034918 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-29 | 0.017799 | 10 | 0.021575 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-29 | 0.034877 | 10 | 0.042275 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-29 | 0.023529 | 10 | 0.02852 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-29 | 0.035756 | 10 | 0.043341 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-29 | 0.024013 | 10 | 0.029107 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-29 | 0.031498 | 10 | 0.038179 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-29 | 0.024395 | 10 | 0.02957 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-29 | 0.027497 | 10 | 0.03333 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-07-29 | 0.029826 | 10 | 0.036152 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7504-02 | 2026-07-30 | 0.03169 | 10 | 0.038412 | Isabela | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-07-29 | 0.01802 | 10 | 0.021842 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7504-02 | 2026-07-30 | 0.020505 | 10 | 0.024855 | Isabela | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7504-02 | 2026-07-30 | 0.022991 | 10 | 0.027868 | Isabela | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7504-02 | 2026-07-30 | 0.03169 | 10 | 0.038412 | Isabela | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7504-02 | 2026-07-30 | 0.023305 | 10 | 0.028249 | Isabela | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-29 | 0.028735 | 10 | 0.034831 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-29 | 0.028015 | 10 | 0.033958 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-29 | 0.022316 | 10 | 0.02705 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-07-29 | 0.030025 | 10 | 0.036393 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2305-02 | 2026-07-28 | 0.041848 | 10 | 0.050724 | Luquillo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 2201-04 | 2026-07-28 | 0.041866 | 10 | 0.050746 | Luquillo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8014-06 | 2026-07-27 | 0.044096 | 10 | 0.053449 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-07-27 | 0.02734 | 10 | 0.03314 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3205-08 | 2026-07-30 | 0.028788 | 10 | 0.034895 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-30 | 0.017449 | 10 | 0.021151 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-30 | 0.017403 | 10 | 0.021095 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8014-06 | 2026-07-29 | 0.023905 | 10 | 0.028976 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-29 | 0.023612 | 10 | 0.028621 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-27 | 0.029826 | 10 | 0.036152 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-29 | 0.04101 | 10 | 0.04971 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-28 | 0.019262 | 10 | 0.023348 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.01107 | 10 | 0.013419 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-29 | 0.015589 | 10 | 0.018896 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8405-03 | 2026-07-29 | 0.01644 | 10 | 0.019927 | Manatí | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8405-03 | 2026-07-29 | 0.02826 | 10 | 0.034255 | Manatí | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-27 | 0.022369 | 10 | 0.027114 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-27 | 0.019532 | 10 | 0.023675 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-27 | 0.012232 | 10 | 0.014827 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-07-27 | 0.026832 | 10 | 0.032524 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-07-27 | 0.020688 | 10 | 0.025076 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-30 | 0.015534 | 10 | 0.018829 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-27 | 0.053438 | 10 | 0.064773 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 8007-03 | 2026-07-29 | 0.010563 | 10 | 0.012804 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-27 | 0.019262 | 10 | 0.023348 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 8007-04 | 2026-07-29 | 0.046751 | 10 | 0.056668 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-07-27 | 0.023885 | 10 | 0.028952 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-27 | 0.01802 | 10 | 0.021842 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-27 | 0.017398 | 10 | 0.021089 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-28 | 0.019262 | 10 | 0.023348 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-01 | 2026-07-29 | 0.03557 | 10 | 0.043115 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-28 | 0.038054 | 10 | 0.046126 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 2201-04 | 2026-07-28 | 0.039158 | 10 | 0.047464 | Luquillo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 8007-04 | 2026-07-29 | 0.036385 | 10 | 0.044103 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 8007-03 | 2026-07-31 | 0.028583 | 10 | 0.034646 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-29 | 0.035759 | 10 | 0.043345 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-27 | 0.037904 | 10 | 0.045944 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 8007-03 | 2026-07-31 | 0.0093206 | 10 | 0.011298 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-01 | 2026-07-29 | 0.037904 | 10 | 0.045944 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 8007-04 | 2026-07-29 | 0.037904 | 10 | 0.045944 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-29 | 0.027562 | 10 | 0.033409 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-07-27 | 0.03604 | 10 | 0.043684 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-29 | 0.02918 | 10 | 0.035369 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-01 | 2026-07-29 | 0.037282 | 10 | 0.045191 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 8007-04 | 2026-07-29 | 0.037282 | 10 | 0.045191 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-27 | 0.033702 | 10 | 0.040851 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-07-27 | 0.033951 | 10 | 0.041152 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-07-28 | 0.03604 | 10 | 0.043684 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-27 | 0.036347 | 10 | 0.044057 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-01 | 2026-07-29 | 0.042253 | 10 | 0.051216 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-07-27 | 0.036511 | 10 | 0.044255 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 8007-04 | 2026-07-29 | 0.042253 | 10 | 0.051216 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-07-30 | 0.020505 | 10 | 0.024855 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-27 | 0.030672 | 10 | 0.037178 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-29 | 0.038014 | 10 | 0.046077 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-07-27 | 0.019034 | 10 | 0.023071 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-30 | 0.0093206 | 10 | 0.011298 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-29 | 0.037377 | 10 | 0.045306 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-30 | 0.019262 | 10 | 0.023348 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-07-31 | 0.050331 | 10 | 0.061007 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-30 | 0.019262 | 10 | 0.023348 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03ì | 2026-07-30 | 0.030447 | 10 | 0.036906 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-31 | 0.042253 | 10 | 0.051216 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-29 | 0.039371 | 10 | 0.047722 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-29 | 0.023432 | 10 | 0.028402 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.019884 | 10 | 0.024102 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-29 | 0.03273 | 10 | 0.039673 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-29 | 0.022369 | 10 | 0.027114 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-27 | 0.016777 | 10 | 0.020336 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-07-27 | 0.015967 | 10 | 0.019354 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-29 | 0.029204 | 10 | 0.035399 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-27 | 0.016156 | 10 | 0.019583 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-07-27 | 0.016708 | 10 | 0.020252 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-27 | 0.014913 | 10 | 0.018076 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-07-27 | 0.015985 | 10 | 0.019376 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-27 | 0.034175 | 10 | 0.041425 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-07-27 | 0.034543 | 10 | 0.041871 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-30 | 0.042875 | 10 | 0.051969 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-27 | 0.023612 | 10 | 0.028621 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-31 | 0.032311 | 10 | 0.039165 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-27 | 0.016777 | 10 | 0.020336 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-31 | 0.034175 | 10 | 0.041425 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-31 | 0.037904 | 10 | 0.045944 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.029204 | 10 | 0.035399 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-27 | 0.043128 | 10 | 0.052277 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-27 | 0.042253 | 10 | 0.051216 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-27 | 0.023612 | 10 | 0.028621 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-27 | 0.024855 | 10 | 0.030127 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-27 | 0.032933 | 10 | 0.039919 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-27 | 0.018894 | 10 | 0.022902 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-27 | 0.026098 | 10 | 0.031633 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-27 | 0.019262 | 10 | 0.023348 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-07-29 | 0.033854 | 10 | 0.041035 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-27 | 0.020505 | 10 | 0.024855 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-07-28 | 0.032311 | 10 | 0.039165 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-27 | 0.03052 | 10 | 0.036994 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-07-29 | 0.037779 | 10 | 0.045793 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-07-30 | 0.041701 | 10 | 0.050546 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-07-31 | 0.043239 | 10 | 0.052411 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-07-31 | 0.03855 | 10 | 0.046727 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-07-31 | 0.047224 | 10 | 0.057242 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-30 | 0.025805 | 10 | 0.031279 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-29 | 0.053613 | 10 | 0.064985 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-30 | 0.053219 | 10 | 0.064508 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-07-27 | 0.042321 | 10 | 0.051298 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-07-27 | 0.036371 | 10 | 0.044086 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-27 | 0.029204 | 10 | 0.035399 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-27 | 0.037904 | 10 | 0.045944 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-07-27 | 0.029614 | 10 | 0.035896 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-07-27 | 0.03774 | 10 | 0.045745 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-28 | 0.017099 | 10 | 0.020727 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-07-27 | 0.018378 | 10 | 0.022276 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-03 | 2026-07-30 | 0.039768 | 10 | 0.048203 | Hatillo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-03 | 2026-07-30 | 0.012427 | 10 | 0.015064 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-28 | 0.014913 | 10 | 0.018076 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-30 | 0.050331 | 10 | 0.061007 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-07-30 | 0.032529 | 10 | 0.03943 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-30 | 0.021127 | 10 | 0.025608 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-30 | 0.01802 | 10 | 0.021842 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-30 | 0.016156 | 10 | 0.019583 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7802-01 | 2026-07-29 | 0.02734 | 10 | 0.03314 | San Sebastián | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-30 | 0.022379 | 10 | 0.027126 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-28 | 0.026098 | 10 | 0.031633 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-28 | 0.023612 | 10 | 0.028621 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-28 | 0.014291 | 10 | 0.017323 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-28 | 0.020505 | 10 | 0.024855 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-28 | 0.021748 | 10 | 0.026361 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-28 | 0.021127 | 10 | 0.025608 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-28 | 0.022991 | 10 | 0.027868 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-28 | 0.011185 | 10 | 0.013557 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-28 | 0.0086992 | 10 | 0.010545 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-28 | 0.024855 | 10 | 0.030127 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-28 | 0.021127 | 10 | 0.025608 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-28 | 0.014291 | 10 | 0.017323 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-29 | 0.029204 | 10 | 0.035399 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-29 | 0.017398 | 10 | 0.021089 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-29 | 0.019262 | 10 | 0.023348 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-29 | 0.01802 | 10 | 0.021842 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-29 | 0.01802 | 10 | 0.021842 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-29 | 0.016156 | 10 | 0.019583 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-29 | 0.023612 | 10 | 0.028621 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-30 | 0.016777 | 10 | 0.020336 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-29 | 0.020505 | 10 | 0.024855 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-28 | 0.026098 | 10 | 0.031633 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-28 | 0.028583 | 10 | 0.034646 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-28 | 0.023612 | 10 | 0.028621 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-28 | 0.022369 | 10 | 0.027114 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-28 | 0.018641 | 10 | 0.022595 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-28 | 0.0031068 | 10 | 0.0037658 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-29 | 0.016156 | 10 | 0.019583 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 7903-07 | 2026-07-28 | 0.031069 | 10 | 0.037659 | Lares | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-28 | 0.031069 | 10 | 0.037659 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1106-05 | 2026-07-28 | 0.019262 | 10 | 0.023348 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-07 | 2026-07-28 | 0.031182 | 10 | 0.037797 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-29 | 0.030447 | 10 | 0.036906 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1106-05 | 2026-07-29 | 0.030447 | 10 | 0.036906 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-29 | 0.037904 | 10 | 0.045944 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1106-05 | 2026-07-29 | 0.037904 | 10 | 0.045944 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-29 | 0.004971 | 10 | 0.0060255 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1106-05 | 2026-07-29 | 0.006835 | 10 | 0.0082849 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-29 | 0.012427 | 10 | 0.015064 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 7903-07 | 2026-07-28 | 0.021127 | 10 | 0.025608 | Lares | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1106-05 | 2026-07-29 | 0.012427 | 10 | 0.015064 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-28 | 0.028934 | 10 | 0.035071 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-29 | 0.0086532 | 10 | 0.010489 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1106-05 | 2026-07-29 | 0.023612 | 10 | 0.028621 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-30 | 0.0099419 | 10 | 0.012051 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-30 | 0.022991 | 10 | 0.027868 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-30 | 0.0041968 | 10 | 0.005087 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-30 | 0.017651 | 10 | 0.021395 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-30 | 0.0080778 | 10 | 0.0097913 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-30 | 0.011185 | 10 | 0.013557 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-30 | 0.014485 | 10 | 0.017557 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 7903-07 | 2026-07-30 | 0.03363 | 10 | 0.040764 | Lares | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-30 | 0.0054655 | 10 | 0.0066249 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-30 | 0.020505 | 10 | 0.024855 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-30 | 0.019937 | 10 | 0.024166 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-30 | 0.024451 | 10 | 0.029638 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-30 | 0.037282 | 10 | 0.045191 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-30 | 0.0099419 | 10 | 0.012051 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 7903-07 | 2026-07-30 | 0.020475 | 10 | 0.024819 | Lares | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-30 | 0.033554 | 10 | 0.040671 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-30 | 0.020505 | 10 | 0.024855 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-30 | 0.027962 | 10 | 0.033893 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-30 | 0.029204 | 10 | 0.035399 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-30 | 0.021127 | 10 | 0.025608 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-30 | 0.011806 | 10 | 0.01431 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-30 | 0.024153 | 10 | 0.029276 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-30 | 0.013704 | 10 | 0.016611 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-30 | 0.014913 | 10 | 0.018076 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-30 | 0.0068326 | 10 | 0.0082819 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-28 | 0.014291 | 10 | 0.017323 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-28 | 0.031004 | 10 | 0.037581 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-27 | 0.024855 | 10 | 0.030127 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-27 | 0.039146 | 10 | 0.04745 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-27 | 0.031069 | 10 | 0.037659 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-28 | 0.028291 | 10 | 0.034292 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-27 | 0.032311 | 10 | 0.039165 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-29 | 0.040932 | 10 | 0.049614 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-28 | 0.030196 | 10 | 0.036601 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-28 | 0.0055924 | 10 | 0.0067787 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-29 | 0.026719 | 10 | 0.032387 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-28 | 0.020877 | 10 | 0.025306 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.037695 | 10 | 0.045691 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-30 | 0.020505 | 10 | 0.024855 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-30 | 0.026719 | 10 | 0.032387 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-31 | 0.028896 | 10 | 0.035026 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-30 | 0.0043496 | 10 | 0.0052723 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-30 | 0.026719 | 10 | 0.032387 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 8010-03 | 2026-07-29 | 0.030447 | 10 | 0.036906 | Arecibo | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-30 | 0.01052 | 10 | 0.012752 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-30 | 0.015534 | 10 | 0.018829 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-30 | 0.024855 | 10 | 0.030127 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-30 | 0.024855 | 10 | 0.030127 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-30 | 0.014291 | 10 | 0.017323 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-30 | 0.03169 | 10 | 0.038412 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-30 | 0.024234 | 10 | 0.029374 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-28 | 0.037461 | 10 | 0.045407 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.029204 | 10 | 0.035399 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.019262 | 10 | 0.023348 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.035418 | 10 | 0.042931 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-30 | 0.018641 | 10 | 0.022595 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.022991 | 10 | 0.027868 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-30 | 0.039768 | 10 | 0.048203 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-31 | 0.025476 | 10 | 0.03088 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-28 | 0.030447 | 10 | 0.036906 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8004-01 | 2026-07-26 | 0.05451 | 10 | 0.066073 | Arecibo | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3010-04 | 2026-07-27 | 0.047846 | 10 | 0.057995 | Caguas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-29 | 0.022369 | 10 | 0.027114 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-29 | 0.022369 | 10 | 0.027114 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-29 | 0.016156 | 10 | 0.019583 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-29 | 0.011185 | 10 | 0.013557 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-29 | 0.013049 | 10 | 0.015817 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-03 | 2026-07-30 | 0.026098 | 10 | 0.031633 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-29 | 0.0093206 | 10 | 0.011298 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-29 | 0.021748 | 10 | 0.026361 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-29 | 0.014435 | 10 | 0.017497 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-29 | 0.0097617 | 10 | 0.011832 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-29 | 0.030447 | 10 | 0.036906 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-29 | 0.034797 | 10 | 0.042178 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1734-01 | 2026-07-27 | 0.036661 | 10 | 0.044438 | Bayamón | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-03 | 2026-07-30 | 0.026719 | 10 | 0.032387 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5012-03 | 2026-07-27 | 0.035418 | 10 | 0.042931 | Ponce | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-29 | 0.02734 | 10 | 0.03314 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-29 | 0.014291 | 10 | 0.017323 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-29 | 0.0063286 | 10 | 0.007671 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2404-08 | 2026-07-30 | 0.032699 | 10 | 0.039635 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-29 | 0.010205 | 10 | 0.012369 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-29 | 0.012699 | 10 | 0.015393 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-29 | 0.013563 | 10 | 0.01644 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.016194 | 10 | 0.019629 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.0069316 | 10 | 0.008402 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.015502 | 10 | 0.01879 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-29 | 0.016777 | 10 | 0.020336 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.0074564 | 10 | 0.0090381 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.017398 | 10 | 0.021089 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-29 | 0.029826 | 10 | 0.036152 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.020505 | 10 | 0.024855 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-29 | 0.029204 | 10 | 0.035399 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7901-01 | 2026-07-27 | 0.038525 | 10 | 0.046697 | Lares | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9101-04 | 2026-07-28 | 0.055302 | 10 | 0.067033 | Vega Alta | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-03 | 2026-07-31 | 0.051804 | 10 | 0.062793 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-30 | 0.004971 | 10 | 0.0060255 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.023612 | 10 | 0.028621 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.012427 | 10 | 0.015064 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.019262 | 10 | 0.023348 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-27 | 0.025476 | 10 | 0.03088 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-30 | 0.021127 | 10 | 0.025608 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-29 | 0.025476 | 10 | 0.03088 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.0074564 | 10 | 0.0090381 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.022369 | 10 | 0.027114 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.021127 | 10 | 0.025608 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-27 | 0.021748 | 10 | 0.026361 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.037282 | 10 | 0.045191 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-29 | 0.014291 | 10 | 0.017323 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8013-03 | 2026-07-30 | 0.047846 | 10 | 0.057995 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-28 | 0.025476 | 10 | 0.03088 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.019262 | 10 | 0.023348 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-31 | 0.027962 | 10 | 0.033893 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-28 | 0.024234 | 10 | 0.029374 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.025476 | 10 | 0.03088 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-31 | 0.019262 | 10 | 0.023348 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-31 | 0.03419 | 10 | 0.041443 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-27 | 0.022683 | 10 | 0.027494 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.021748 | 10 | 0.026361 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.019884 | 10 | 0.024102 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5012-03 | 2026-07-27 | 0.035418 | 10 | 0.042931 | Ponce | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-30 | 0.041944 | 10 | 0.050841 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.03169 | 10 | 0.038412 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.026619 | 10 | 0.032265 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-27 | 0.023612 | 10 | 0.028621 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.032933 | 10 | 0.039919 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.026719 | 10 | 0.032387 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-29 | 0.061172 | 10 | 0.074148 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-28 | 0.0055924 | 10 | 0.0067787 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.010563 | 10 | 0.012804 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.01802 | 10 | 0.021842 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.023612 | 10 | 0.028621 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.029826 | 10 | 0.036152 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.030202 | 10 | 0.036608 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-30 | 0.021748 | 10 | 0.026361 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.022179 | 10 | 0.026884 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-28 | 0.017398 | 10 | 0.021089 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.01467 | 10 | 0.017781 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-30 | 0.044117 | 10 | 0.053476 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-29 | 0.040164 | 10 | 0.048684 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.015272 | 10 | 0.018511 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.020519 | 10 | 0.024871 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-29 | 0.015821 | 10 | 0.019177 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.023651 | 10 | 0.028667 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-29 | 0.019286 | 10 | 0.023377 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-27 | 0.031069 | 10 | 0.037659 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.021142 | 10 | 0.025627 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.032226 | 10 | 0.039062 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-27 | 0.015534 | 10 | 0.018829 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-27 | 0.046121 | 10 | 0.055905 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-30 | 0.037004 | 10 | 0.044854 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.019116 | 10 | 0.023171 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.023858 | 10 | 0.028919 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-30 | 0.020121 | 10 | 0.024389 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-29 | 0.026719 | 10 | 0.032387 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.015458 | 10 | 0.018737 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1303-01 | 2026-07-28 | 0.0055924 | 10 | 0.0067787 | San Juan | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.028129 | 10 | 0.034095 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-29 | 0.022104 | 10 | 0.026793 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.03161 | 10 | 0.038315 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1303-01 | 2026-07-28 | 0.03604 | 10 | 0.043684 | San Juan | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.017702 | 10 | 0.021457 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-30 | 0.075807 | 10 | 0.091888 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.012828 | 10 | 0.015549 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1303-01 | 2026-07-28 | 0.024855 | 10 | 0.030127 | San Juan | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-28 | 0.039318 | 10 | 0.047658 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.018344 | 10 | 0.022235 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-30 | 0.037282 | 10 | 0.045191 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.02599 | 10 | 0.031503 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.015397 | 10 | 0.018663 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-30 | 0.042253 | 10 | 0.051216 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.029672 | 10 | 0.035966 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.029441 | 10 | 0.035686 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-29 | 0.089477 | 10 | 0.10846 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-30 | 0.044463 | 10 | 0.053895 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-30 | 0.050331 | 10 | 0.061007 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-28 | 0.039146 | 10 | 0.04745 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.0033778 | 10 | 0.0040944 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.007103 | 10 | 0.0086097 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-31 | 0.016156 | 10 | 0.019583 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-31 | 0.02843 | 10 | 0.03446 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-29 | 0.039146 | 10 | 0.04745 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-31 | 0.026719 | 10 | 0.032387 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 7903-07 | 2026-07-30 | 0.031491 | 10 | 0.038171 | Lares | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-30 | 0.018377 | 10 | 0.022275 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.025019 | 10 | 0.030326 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-28 | 0.029204 | 10 | 0.035399 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1330-01 | 2026-07-27 | 0.031497 | 10 | 0.038178 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1330-01 | 2026-07-27 | 0.012006 | 10 | 0.014552 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1330-01 | 2026-07-27 | 0.0078972 | 10 | 0.0095723 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-28 | 0.046603 | 10 | 0.056488 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1330-01 | 2026-07-27 | 0.036525 | 10 | 0.044273 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-28 | 0.031919 | 10 | 0.03869 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.029946 | 10 | 0.036298 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.014913 | 10 | 0.018076 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.01802 | 10 | 0.021842 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.013082 | 10 | 0.015857 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.0097705 | 10 | 0.011843 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-27 | 0.01599 | 10 | 0.019382 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3010-01 | 2026-07-27 | 0.026444 | 10 | 0.032054 | Caguas | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-30 | 0.0082648 | 10 | 0.010018 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-30 | 0.020659 | 10 | 0.025042 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-30 | 0.022266 | 10 | 0.026989 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9605-01 | 2026-07-28 | 0.067677 | 10 | 0.082033 | Barranquit | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1303-01 | 2026-07-28 | 0.014291 | 10 | 0.017323 | San Juan | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3401-02 | 2026-07-28 | 0.029204 | 10 | 0.035399 | Cayey | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9605-01 | 2026-07-28 | 0.067677 | 10 | 0.082033 | Barranquitas | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1343-03 | 2026-07-28 | 0.03169 | 10 | 0.038412 | Guaynabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1343-03 | 2026-07-28 | 0.037282 | 10 | 0.045191 | Guaynabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1303-01 | 2026-07-28 | 0.029826 | 10 | 0.036152 | San Juan | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3401-02 | 2026-07-28 | 0.16901 | 10 | 0.20486 | Cidra | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-30 | 0.031069 | 10 | 0.037659 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-30 | 0.029826 | 10 | 0.036152 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7901-01 | 2026-07-28 | 0.04296 | 10 | 0.052073 | Lares | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-30 | 0.034294 | 10 | 0.041569 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-30 | 0.024147 | 10 | 0.029269 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-30 | 0.019266 | 10 | 0.023353 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-30 | 0.0096362 | 10 | 0.01168 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5304-03 | 2026-07-28 | 0.060894 | 10 | 0.073811 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-30 | 0.020899 | 10 | 0.025332 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-30 | 0.0099419 | 10 | 0.012051 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1343-03 | 2026-07-28 | 0.037282 | 10 | 0.045191 | Guaynabo | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5007-01 | 2026-07-28 | 0.043503 | 10 | 0.052731 | Ponce | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-28 | 0.026365 | 10 | 0.031957 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-29 | 0.0099415 | 10 | 0.01205 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-28 | 0.0093206 | 10 | 0.011298 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-28 | 0.024008 | 10 | 0.029101 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1106-05 | 2026-07-29 | 0.011806 | 10 | 0.01431 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1106-05 | 2026-07-28 | 0.030447 | 10 | 0.036906 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-29 | 0.0020116 | 10 | 0.0024382 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-29 | 0.0021831 | 10 | 0.0026462 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-29 | 0.00037917 | 10 | 0.0004596 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-29 | 0.00037917 | 10 | 0.0004596 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-28 | 0.01688 | 10 | 0.02046 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-07-28 | 0.028583 | 10 | 0.034646 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1106-05 | 2026-07-29 | 0.028583 | 10 | 0.034646 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-28 | 0.020316 | 10 | 0.024625 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-28 | 0.070215 | 10 | 0.085109 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-30 | 0.02691 | 10 | 0.032618 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-07-31 | 0.025663 | 10 | 0.031107 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-29 | 0.026098 | 10 | 0.031633 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-29 | 0.029826 | 10 | 0.036152 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-07-30 | 0.036596 | 10 | 0.044358 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-29 | 0.036661 | 10 | 0.044438 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5501-03 | 2026-07-28 | 0.029826 | 10 | 0.036152 | Guayanilla | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-07-30 | 0.036596 | 10 | 0.044358 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-07-30 | 0.017409 | 10 | 0.021102 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-07-30 | 0.034714 | 10 | 0.042078 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7503-04 | 2026-07-28 | 0.027962 | 10 | 0.033893 | Isabela | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-29 | 0.018641 | 10 | 0.022595 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 4301-03 | 2026-07-29 | 0.052539 | 10 | 0.063684 | Maunabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-29 | 0.1564 | 10 | 0.18958 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-07-30 | 0.056545 | 10 | 0.068539 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-07-30 | 0.020459 | 10 | 0.024798 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-07-30 | 0.034175 | 10 | 0.041425 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-07-30 | 0.034797 | 10 | 0.042178 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-07-30 | 0.018623 | 10 | 0.022573 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-07-30 | 0.01122 | 10 | 0.0136 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-07-30 | 0.036661 | 10 | 0.044438 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-07-31 | 0.0097674 | 10 | 0.011839 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1201-01 | 2026-07-31 | 0.011434 | 10 | 0.01386 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 7503-04 | 2026-07-28 | 0.027962 | 10 | 0.033893 | Isabela | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 2401-01 | 2026-07-29 | 0.029204 | 10 | 0.035399 | Canóvanas | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-07-31 | 0.035134 | 10 | 0.042587 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 2401-01 | 2026-07-29 | 0.029204 | 10 | 0.035399 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-07-30 | 0.0070919 | 10 | 0.0085962 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2404-08 | 2026-07-30 | 0.032311 | 10 | 0.039165 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-07-30 | 0.021225 | 10 | 0.025727 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2404-08 | 2026-07-30 | 0.032311 | 10 | 0.039165 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-07-30 | 0.018641 | 10 | 0.022595 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1529-13 | 2026-07-28 | 0.04079 | 10 | 0.049443 | San Juan | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-07-30 | 0.019262 | 10 | 0.023348 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-07-31 | 0.022836 | 10 | 0.02768 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-07-31 | 0.030723 | 10 | 0.03724 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-07-31 | 0.044466 | 10 | 0.053898 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 2201-04 | 2026-07-28 | 0.041866 | 10 | 0.050746 | Luquillo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-07-31 | 0.021771 | 10 | 0.026389 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-07-31 | 0.031138 | 10 | 0.037743 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-07-31 | 0.029204 | 10 | 0.035399 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-07-31 | 0.029826 | 10 | 0.036152 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-07-28 | 0.022913 | 10 | 0.027773 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-07-29 | 0.038525 | 10 | 0.046697 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-07-31 | 0.022991 | 10 | 0.027868 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1343-03 | 2026-07-29 | 0.032933 | 10 | 0.039919 | Guaynabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6201-01 | 2026-07-29 | 0.16031 | 10 | 0.19432 | Las Marías | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1343-03 | 2026-07-29 | 0.021127 | 10 | 0.025608 | Guaynabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 8010-03 | 2026-07-29 | 0.024855 | 10 | 0.030127 | Arecibo | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.16/7.20 | 8010-03 | 2026-07-29 | 0.021748 | 10 | 0.026361 | Arecibo | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8005-01 | 2026-07-29 | 0.15455 | 10 | 0.18734 | Utuado | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-30 | 0.035418 | 10 | 0.042931 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5001-03 | 2026-07-29 | 0.032897 | 10 | 0.039876 | Ponce | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-30 | 0.038525 | 10 | 0.046697 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 5011-03 | 2026-07-29 | 0.033982 | 10 | 0.04119 | Ponce | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-30 | 0.037904 | 10 | 0.045944 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3013-03 | 2026-07-29 | 0.085749 | 10 | 0.10394 | Caguas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3013-03 | 2026-07-29 | 0.085749 | 10 | 0.10394 | Caguas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3013-03 | 2026-07-29 | 0.070215 | 10 | 0.085109 | Caguas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3013-03 | 2026-07-29 | 0.064623 | 10 | 0.07833 | Caguas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-30 | 0.026719 | 10 | 0.032387 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3103-04 | 2026-07-31 | 0.029584 | 10 | 0.035859 | San Lorenzo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3103-04 | 2026-07-31 | 0.022355 | 10 | 0.027097 | San Lorenzo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-31 | 0.045043 | 10 | 0.054598 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9902-03 | 2026-07-29 | 0.04536 | 10 | 0.054982 | Orocovis | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9902-03 | 2026-07-29 | 0.04536 | 10 | 0.054982 | Orocovis | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-31 | 0.018298 | 10 | 0.02218 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-29 | 0.039865 | 10 | 0.048321 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-29 | 0.039748 | 10 | 0.048179 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-29 | 0.010911 | 10 | 0.013226 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1343-03 | 2026-07-30 | 0.029204 | 10 | 0.035399 | Guaynabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1343-03 | 2026-07-29 | 0.026719 | 10 | 0.032387 | Guaynabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-29 | 0.033502 | 10 | 0.040609 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 6201-01 | 2026-07-29 | 0.11597 | 10 | 0.14057 | Añasco | Xperts | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-30 | 0.037145 | 10 | 0.045024 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-30 | 0.039135 | 10 | 0.047436 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-07-30 | 0.057166 | 10 | 0.069292 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-29 | 0.033968 | 10 | 0.041173 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-29 | 0.054843 | 10 | 0.066476 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5501-04 | 2026-07-30 | 0.080157 | 10 | 0.09716 | Yauco | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-29 | 0.0036915 | 10 | 0.0044745 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-29 | 0.034175 | 10 | 0.041425 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-29 | 0.03169 | 10 | 0.038412 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-29 | 0.026098 | 10 | 0.031633 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-29 | 0.016777 | 10 | 0.020336 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-29 | 0.028583 | 10 | 0.034646 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-29 | 0.030571 | 10 | 0.037056 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1330-01 | 2026-07-29 | 0.029258 | 10 | 0.035464 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-29 | 0.035269 | 10 | 0.04275 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-29 | 0.034797 | 10 | 0.042178 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-07-29 | 0.034815 | 10 | 0.0422 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-29 | 0.037904 | 10 | 0.045944 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-07-29 | 0.03764 | 10 | 0.045624 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-29 | 0.02734 | 10 | 0.03314 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-07-29 | 0.026621 | 10 | 0.032268 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-29 | 0.020505 | 10 | 0.024855 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1330-01 | 2026-07-29 | 0.021127 | 10 | 0.025608 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-29 | 0.022369 | 10 | 0.027114 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-07-29 | 0.022012 | 10 | 0.026681 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-29 | 0.014291 | 10 | 0.017323 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-07-29 | 0.014506 | 10 | 0.017584 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-29 | 0.026719 | 10 | 0.032387 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-07-29 | 0.026803 | 10 | 0.032488 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-29 | 0.03604 | 10 | 0.043684 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-02 | 2026-07-29 | 0.032933 | 10 | 0.039919 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-07-29 | 0.03595 | 10 | 0.043576 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-07-29 | 0.03169 | 10 | 0.038412 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-02 | 2026-07-29 | 0.034797 | 10 | 0.042178 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-07-29 | 0.030835 | 10 | 0.037376 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-02 | 2026-07-29 | 0.030647 | 10 | 0.037147 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-02 | 2026-07-29 | 0.033696 | 10 | 0.040843 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-02 | 2026-07-29 | 0.033228 | 10 | 0.040276 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-02 | 2026-07-29 | 0.010241 | 10 | 0.012413 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-02 | 2026-07-29 | 0.020364 | 10 | 0.024683 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9602-03 | 2026-07-29 | 0.093827 | 10 | 0.11373 | Barranquitas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 2901-01 | 2026-07-30 | 0.017398 | 10 | 0.021089 | Yabucoa | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-07-31 | 0.047467 | 10 | 0.057536 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-31 | 0.020505 | 10 | 0.024855 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1343-03 | 2026-07-30 | 0.025476 | 10 | 0.03088 | Guaynabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-31 | 0.020505 | 10 | 0.024855 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9703-03 | 2026-07-30 | 0.096312 | 10 | 0.11674 | Comerío | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-31 | 0.018641 | 10 | 0.022595 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-31 | 0.020505 | 10 | 0.024855 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-30 | 0.018641 | 10 | 0.022595 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1343-03 | 2026-07-30 | 0.029204 | 10 | 0.035399 | Guaynabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-07-30 | 0.018641 | 10 | 0.022595 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9703-03 | 2026-07-30 | 0.077671 | 10 | 0.094147 | Comerío | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-07-31 | 0.022732 | 10 | 0.027553 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9703-03 | 2026-07-30 | 0.038525 | 10 | 0.046697 | Comerío | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1343-03 | 2026-07-31 | 0.032311 | 10 | 0.039165 | Guaynabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1343-03 | 2026-07-31 | 0.032311 | 10 | 0.039165 | Guaynabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-07-31 | 0.01367 | 10 | 0.01657 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-07-31 | 0.024234 | 10 | 0.029374 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-07-31 | 0.031069 | 10 | 0.037659 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-07-31 | 0.032933 | 10 | 0.039919 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-07-31 | 0.042253 | 10 | 0.051216 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-07-31 | 0.024855 | 10 | 0.030127 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-07-31 | 0.023612 | 10 | 0.028621 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-07-31 | 0.021748 | 10 | 0.026361 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-07-31 | 0.024855 | 10 | 0.030127 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-30 | 0.012427 | 10 | 0.015064 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-07-31 | 0.01802 | 10 | 0.021842 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-07-30 | 0.037904 | 10 | 0.045944 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-07-31 | 0.016156 | 10 | 0.019583 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-07-31 | 0.019262 | 10 | 0.023348 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-07-31 | 0.016156 | 10 | 0.019583 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-07-31 | 0.02734 | 10 | 0.03314 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-07-31 | 0.038525 | 10 | 0.046697 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-07-31 | 0.039768 | 10 | 0.048203 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-07-31 | 0.022991 | 10 | 0.027868 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-07-31 | 0.018641 | 10 | 0.022595 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-07-31 | 0.022991 | 10 | 0.027868 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-07-31 | 0.025476 | 10 | 0.03088 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-07-31 | 0.022991 | 10 | 0.027868 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-30 | 0.025438 | 10 | 0.030834 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-30 | 0.025072 | 10 | 0.03039 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-31 | 0.013842 | 10 | 0.016778 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-07-31 | 0.02905 | 10 | 0.035213 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2404-08 | 2026-07-31 | 0.026621 | 10 | 0.032268 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-07-30 | 0.025963 | 10 | 0.031471 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-07-31 | 0.016156 | 10 | 0.019583 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-07-31 | 0.034797 | 10 | 0.042178 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-07-30 | 0.03604 | 10 | 0.043684 | Florida | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-07-30 | 0.039771 | 10 | 0.048208 | Florida | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-07-30 | 0.04897 | 10 | 0.059358 | Florida | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 4101-02 | 2026-07-31 | 0.025745 | 10 | 0.031206 | Arroyo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-07-31 | 0.024855 | 10 | 0.030127 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1709-039 | 2026-07-31 | 0.022991 | 10 | 0.027868 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-07-31 | 0.025476 | 10 | 0.03088 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1530-07 | 2026-07-31 | 0.021127 | 10 | 0.025608 | San Juan | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-07-31 | 0.03169 | 10 | 0.038412 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-07-31 | 0.015095 | 10 | 0.018297 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-07-31 | 0.011178 | 10 | 0.01355 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2404-08 | 2026-07-31 | 0.054498 | 10 | 0.066059 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 2401-01 | 2026-07-31 | 0.026719 | 10 | 0.032387 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 2401-01 | 2026-07-31 | 0.026719 | 10 | 0.032387 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2404-08 | 2026-07-31 | 0.028843 | 10 | 0.034961 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 2404-08 | 2026-07-31 | 0.038525 | 10 | 0.046697 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1801-01 | 2026-07-31 | 0.032311 | 10 | 0.039165 | Cataño | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-07-31 | 0.027962 | 10 | 0.033893 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-07-31 | 0.021748 | 10 | 0.026361 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 5007-01 | 2026-07-31 | 0.024234 | 10 | 0.029374 | Ponce | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-07-31 | 0.022369 | 10 | 0.027114 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-07-31 | 0.027962 | 10 | 0.033893 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8202-02 | 2026-07-31 | 0.033865 | 10 | 0.041048 | Adjuntas | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 8202-02 | 2026-07-31 | 0.029402 | 10 | 0.035639 | Adjuntas | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 4.80/8.32 | 9605-01 | 2026-07-31 | 0.062347 | 10 | 0.075572 | Barranquitas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
N/A | 2.40/4.16 | 1530-07 | 2026-07-31 | 0.024234 | 10 | 0.029374 | San Juan | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | July | Q1 | FY2027
956332 | 4.80/8.32 | 2401-01 | 2026-07-29 | 0.01917 | 10 | 0.023236 | Canóvanas | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
727572 | 4.80/8.32 | 9103-01 | 2026-07-06 | 0.0027 | 10 | 0.0032727 | Dorado | Luma | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
727692 | 4.80/8.32 | 3502-02 | 2026-07-11 | 0.02894 | 10 | 0.035079 | Aibonito | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 4.80/8.32 | 8202-02 | 2026-07-06 | 0.82658 | 10 | 1.0019 | Adjuntas | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 4.80/8.32 | 8202-02 | 2026-07-07 | 0.64839 | 10 | 0.78593 | Adjuntas | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 4.80/8.32 | 8202-02 | 2026-07-08 | 0.16177 | 10 | 0.19608 | Adjuntas | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 4.80/8.32 | 8202-02 | 2026-07-09 | 0.63838 | 10 | 0.77379 | Adjuntas | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 4.80/8.32 | 8202-02 | 2026-07-13 | 0.21175 | 10 | 0.25667 | Adjuntas | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 4.80/8.32 | 8202-02 | 2026-07-13 | 0.07045 | 10 | 0.085394 | Peñuelas | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 4.80/8.32 | 8202-02 | 2026-07-14 | 0.47538 | 10 | 0.57622 | Adjuntas | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 4.80/8.32 | 8202-02 | 2026-07-14 | 0.22059 | 10 | 0.26738 | Peñuelas | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 4.80/8.32 | 8202-02 | 2026-07-15 | 0.46282 | 10 | 0.56099 | Adjuntas | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 4.80/8.32 | 8202-02 | 2026-07-15 | 0.04485 | 10 | 0.054364 | Peñuelas | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 4.80/8.32 | 8202-02 | 2026-07-16 | 0.62606 | 10 | 0.75886 | Adjuntas | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 4.80/8.32 | 8202-02 | 2026-07-21 | 0.74059 | 10 | 0.89768 | Adjuntas | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 4.80/8.32 | 8202-02 | 2026-07-22 | 0.55549 | 10 | 0.67332 | Adjuntas | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 4.80/8.32 | 8202-03 | 2026-07-22 | 0.02307 | 10 | 0.027964 | Adjuntas | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 4.80/8.32 | 8202-03 | 2026-07-23 | 0.89526 | 10 | 1.0852 | Adjuntas | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 4.80/8.32 | 8202-03 | 2026-07-27 | 0.63152 | 10 | 0.76548 | Adjuntas | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 4.80/8.32 | 8202-03 | 2026-07-28 | 0.12907 | 10 | 0.15645 | Adjuntas | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 4.80/8.32 | 8202-03 | 2026-07-29 | 0.32631 | 10 | 0.39553 | Adjuntas | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 4.80/8.32 | 8202-03 | 2026-07-30 | 0.06517 | 10 | 0.078994 | Adjuntas | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 4.80/8.32 | 8701-01 | 2026-07-01 | 0.21586 | 10 | 0.26165 | Ciales | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 4.80/8.32 | 9001-01 | 2026-07-28 | 0.38429 | 10 | 0.46581 | Vega Baja | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 4.80/8.32 | 9001-01 | 2026-07-29 | 0.5803 | 10 | 0.70339 | Vega Baja | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 4.80/8.32 | 9001-01 | 2026-07-30 | 0.54328 | 10 | 0.65852 | Vega Baja | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 4.80/8.32 | 9001-03 | 2026-07-28 | 0.02225 | 10 | 0.02697 | Vega Baja | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 4.80/8.32 | 9003-06 | 2026-07-27 | 0.10835 | 10 | 0.13133 | Vega Baja | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 4.80/8.32 | 9003-06 | 2026-07-28 | 0.11579 | 10 | 0.14035 | Vega Baja | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 4.80/8.32 | 9003-06 | 2026-07-29 | 0.26757 | 10 | 0.32433 | Vega Baja | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 4.80/8.32 | 9003-06 | 2026-07-30 | 0.51974 | 10 | 0.62999 | Vega Baja | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 7.62/13.20 | 9004-09 | 2026-07-28 | 0.06407 | 10 | 0.077661 | Vega Baja | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 7.62/13.20 | 9004-11 | 2026-07-28 | 0.32585 | 10 | 0.39497 | Vega Baja | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 7.62/13.20 | 9004-11 | 2026-07-29 | 0.12386 | 10 | 0.15013 | Vega Baja | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9103-01 | 2026-07-01 | 0.08651 | 10 | 0.10486 | Corozal | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9103-01 | 2026-07-01 | 0.14119 | 10 | 0.17114 | Vega Alta | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9103-01 | 2026-07-13 | 0.01013 | 10 | 0.012279 | Dorado | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9103-01 | 2026-07-13 | 0.02329 | 10 | 0.02823 | Toa Alta | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9103-01 | 2026-07-13 | 0.02961 | 10 | 0.035891 | Vega Alta | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 2.40/4.16 | 9401-01 | 2026-07-01 | 0.18399 | 10 | 0.22302 | Toa Alta | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 2.40/4.16 | 9401-01 | 2026-07-02 | 0.40353 | 10 | 0.48913 | Toa Alta | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 2.40/4.16 | 9401-01 | 2026-07-07 | 0.32737 | 10 | 0.39681 | Toa Alta | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 2.40/4.16 | 9401-01 | 2026-07-08 | 0.21435 | 10 | 0.25982 | Toa Alta | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 2.40/4.16 | 9401-01 | 2026-07-09 | 0.37948 | 10 | 0.45998 | Toa Alta | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 2.40/4.16 | 9401-01 | 2026-07-10 | 0.08627 | 10 | 0.10457 | Toa Alta | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 2.40/4.16 | 9401-01 | 2026-07-14 | 0.07024 | 10 | 0.085139 | Toa Alta | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 2.40/4.16 | 9401-01 | 2026-07-15 | 0.4871 | 10 | 0.59042 | Toa Alta | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 2.40/4.16 | 9401-01 | 2026-07-16 | 0.10566 | 10 | 0.12807 | Toa Alta | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 2.40/4.16 | 9401-01 | 2026-07-17 | 0.0184 | 10 | 0.022303 | Toa Alta | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 2.40/4.16 | 9401-01 | 2026-07-21 | 0.09198 | 10 | 0.11149 | Toa Alta | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 2.40/4.16 | 9401-01 | 2026-07-23 | 0.36269 | 10 | 0.43962 | Toa Alta | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 2.40/4.16 | 9401-01 | 2026-07-24 | 0.23428 | 10 | 0.28398 | Toa Alta | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 2.40/4.16 | 9401-01 | 2026-07-28 | 0.30193 | 10 | 0.36598 | Toa Alta | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 2.40/4.16 | 9403-01 | 2026-07-09 | 0.28907 | 10 | 0.35039 | Toa Alta | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9501-01 | 2026-07-01 | 0.22391 | 10 | 0.27141 | Corozal | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9501-01 | 2026-07-02 | 0.51155 | 10 | 0.62006 | Corozal | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9501-01 | 2026-07-02 | 0.12629 | 10 | 0.15308 | Vega Alta | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9501-01 | 2026-07-09 | 0.15575 | 10 | 0.18879 | Vega Alta | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9501-02 | 2026-07-01 | 1.3013 | 10 | 1.5774 | Corozal | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9501-02 | 2026-07-02 | 0.62926 | 10 | 0.76274 | Corozal | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9501-02 | 2026-07-06 | 1.3114 | 10 | 1.5896 | Corozal | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9501-02 | 2026-07-07 | 0.81521 | 10 | 0.98813 | Corozal | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9501-02 | 2026-07-08 | 0.53527 | 10 | 0.64881 | Corozal | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9501-02 | 2026-07-09 | 0.50184 | 10 | 0.60829 | Corozal | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9501-02 | 2026-07-13 | 0.1753 | 10 | 0.21248 | Corozal | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9501-02 | 2026-07-14 | 0.11772 | 10 | 0.14269 | Corozal | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9501-02 | 2026-07-16 | 0.05795 | 10 | 0.070242 | Corozal | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9501-02 | 2026-07-20 | 0.17937 | 10 | 0.21742 | Corozal | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9501-02 | 2026-07-21 | 0.89182 | 10 | 1.081 | Corozal | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9501-02 | 2026-07-22 | 0.4814 | 10 | 0.58352 | Corozal | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9501-02 | 2026-07-23 | 1.4726 | 10 | 1.785 | Corozal | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9501-02 | 2026-07-24 | 0.07849 | 10 | 0.095139 | Corozal | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9501-02 | 2026-07-25 | 0.02861 | 10 | 0.034679 | Corozal | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9501-02 | 2026-07-27 | 0.51923 | 10 | 0.62937 | Corozal | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9501-03 | 2026-07-01 | 0.12994 | 10 | 0.1575 | Corozal | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9501-03 | 2026-07-02 | 0.10452 | 10 | 0.12669 | Corozal | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9501-03 | 2026-07-02 | 0.00284 | 10 | 0.0034424 | Morovis | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9501-03 | 2026-07-02 | 0.026 | 10 | 0.031515 | Vega Alta | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9501-03 | 2026-07-07 | 0.20134 | 10 | 0.24405 | Corozal | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9501-03 | 2026-07-07 | 0.11786 | 10 | 0.14286 | Morovis | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9502-02 | 2026-07-06 | 0.39789 | 10 | 0.48229 | Corozal | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9502-02 | 2026-07-07 | 2.0788 | 10 | 2.5198 | Corozal | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9502-02 | 2026-07-08 | 0.70199 | 10 | 0.8509 | Corozal | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9502-02 | 2026-07-09 | 0.3981 | 10 | 0.48255 | Corozal | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9502-02 | 2026-07-10 | 1.0704 | 10 | 1.2974 | Corozal | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9502-02 | 2026-07-13 | 0.03581 | 10 | 0.043406 | Corozal | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9502-02 | 2026-07-14 | 1.6244 | 10 | 1.969 | Corozal | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9502-02 | 2026-07-15 | 0.96359 | 10 | 1.168 | Corozal | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9502-02 | 2026-07-16 | 1.2488 | 10 | 1.5137 | Corozal | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9502-02 | 2026-07-17 | 0.20485 | 10 | 0.2483 | Corozal | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9502-02 | 2026-07-20 | 0.1656 | 10 | 0.20073 | Corozal | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9502-02 | 2026-07-21 | 0.21035 | 10 | 0.25497 | Corozal | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9502-02 | 2026-07-22 | 0.26539 | 10 | 0.32168 | Corozal | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9502-03 | 2026-07-01 | 0.0287 | 10 | 0.034788 | Naranjito | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9502-03 | 2026-07-02 | 0.02246 | 10 | 0.027224 | Naranjito | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9502-03 | 2026-07-02 | 0.04889 | 10 | 0.059261 | Toa Alta | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9502-03 | 2026-07-08 | 0.04697 | 10 | 0.056933 | Naranjito | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9502-03 | 2026-07-09 | 0.02682 | 10 | 0.032509 | Naranjito | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9802-04 | 2026-07-01 | 0.4159 | 10 | 0.50412 | Naranjito | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9802-04 | 2026-07-02 | 0.68749 | 10 | 0.83332 | Naranjito | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9802-04 | 2026-07-06 | 0.44925 | 10 | 0.54455 | Naranjito | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9802-04 | 2026-07-07 | 0.47978 | 10 | 0.58155 | Naranjito | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9802-04 | 2026-07-08 | 1.0182 | 10 | 1.2341 | Naranjito | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9802-04 | 2026-07-09 | 1.0947 | 10 | 1.3269 | Naranjito | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9802-04 | 2026-07-10 | 0.9242 | 10 | 1.1202 | Naranjito | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9802-04 | 2026-07-13 | 0.18786 | 10 | 0.22771 | Naranjito | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9802-04 | 2026-07-14 | 0.71809 | 10 | 0.87041 | Naranjito | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9802-04 | 2026-07-15 | 0.60816 | 10 | 0.73716 | Naranjito | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9802-04 | 2026-07-16 | 0.67412 | 10 | 0.81712 | Naranjito | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9802-04 | 2026-07-17 | 0.0789 | 10 | 0.095636 | Naranjito | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9802-04 | 2026-07-20 | 0.18165 | 10 | 0.22018 | Naranjito | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9802-04 | 2026-07-21 | 0.37325 | 10 | 0.45242 | Naranjito | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9802-04 | 2026-07-22 | 0.21482 | 10 | 0.26039 | Naranjito | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9802-04 | 2026-07-23 | 0.4624 | 10 | 0.56048 | Naranjito | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9802-04 | 2026-07-27 | 0.19089 | 10 | 0.23138 | Corozal | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9802-04 | 2026-07-27 | 0.05832 | 10 | 0.070691 | Naranjito | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 4.80/8.32 | 9802-04 | 2026-07-28 | 0.53612 | 10 | 0.64984 | Naranjito | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 2.40/4.16 | 3014-01 | 2026-07-22 | 0.61596 | 10 | 0.74662 | Caguas | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 2.40/4.16 | 3014-01 | 2026-07-23 | 1.7308 | 10 | 2.0979 | Caguas | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 2.40/4.16 | 3014-01 | 2026-07-24 | 0.05108 | 10 | 0.061915 | Caguas | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 2.40/4.16 | 3014-01 | 2026-07-27 | 0.34784 | 10 | 0.42162 | Caguas | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 2.40/4.16 | 3014-01 | 2026-07-31 | 0.1776 | 10 | 0.21527 | Caguas | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3502-02 | 2026-07-01 | 0.81158 | 10 | 0.98373 | Aibonito | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3502-02 | 2026-07-02 | 0.69947 | 10 | 0.84784 | Aibonito | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3502-02 | 2026-07-02 | 0.04928 | 10 | 0.059733 | Coamo | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3502-02 | 2026-07-06 | 0.2271 | 10 | 0.27527 | Aibonito | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3502-02 | 2026-07-06 | 0.04814 | 10 | 0.058352 | Coamo | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3502-02 | 2026-07-07 | 0.45697 | 10 | 0.5539 | Aibonito | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3502-02 | 2026-07-07 | 0.18724 | 10 | 0.22696 | Coamo | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3502-02 | 2026-07-08 | 0.62422 | 10 | 0.75663 | Aibonito | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3502-02 | 2026-07-08 | 0.10984 | 10 | 0.13314 | Coamo | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3502-02 | 2026-07-09 | 1.4965 | 10 | 1.8139 | Aibonito | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3502-02 | 2026-07-09 | 0.35066 | 10 | 0.42504 | Coamo | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3502-02 | 2026-07-10 | 0.99156 | 10 | 1.2019 | Aibonito | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3502-02 | 2026-07-10 | 0.97657 | 10 | 1.1837 | Coamo | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3502-02 | 2026-07-11 | 0.7105 | 10 | 0.86121 | Aibonito | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3502-02 | 2026-07-11 | 1.0897 | 10 | 1.3209 | Coamo | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3502-02 | 2026-07-13 | 0.23213 | 10 | 0.28137 | Aibonito | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3502-02 | 2026-07-13 | 0.01269 | 10 | 0.015382 | Coamo | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 9605-02 | 2026-07-24 | 0.49264 | 10 | 0.59714 | Comerío | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 9605-02 | 2026-07-27 | 0.99189 | 10 | 1.2023 | Comerío | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 9605-02 | 2026-07-28 | 1.2583 | 10 | 1.5252 | Comerío | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 9605-02 | 2026-07-29 | 0.38601 | 10 | 0.46789 | Comerío | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 9605-02 | 2026-07-29 | 0.17425 | 10 | 0.21121 | Naranjito | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 9605-02 | 2026-07-30 | 0.51342 | 10 | 0.62233 | Comerío | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 9605-02 | 2026-07-30 | 0.38387 | 10 | 0.4653 | Naranjito | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 9605-02 | 2026-07-31 | 0.33773 | 10 | 0.40937 | Comerío | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 9605-02 | 2026-07-31 | 0.13978 | 10 | 0.16943 | Corozal | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 9605-02 | 2026-07-31 | 0.06275 | 10 | 0.076061 | Naranjito | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 9703-03 | 2026-07-13 | 0.47406 | 10 | 0.57462 | Comerío | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 9703-03 | 2026-07-14 | 0.18242 | 10 | 0.22112 | Aguas Buenas | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 9703-03 | 2026-07-14 | 1.5532 | 10 | 1.8826 | Comerío | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 9703-03 | 2026-07-15 | 0.39361 | 10 | 0.4771 | Aguas Buenas | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 9703-03 | 2026-07-15 | 1.3845 | 10 | 1.6782 | Comerío | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 9703-03 | 2026-07-16 | 0.07599 | 10 | 0.092109 | Aguas Buenas | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 9703-03 | 2026-07-16 | 1.0991 | 10 | 1.3322 | Comerío | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 9703-03 | 2026-07-17 | 0.50985 | 10 | 0.618 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 9703-03 | 2026-07-17 | 1.0555 | 10 | 1.2794 | Comerío | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 9703-03 | 2026-07-20 | 0.12786 | 10 | 0.15498 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 9703-03 | 2026-07-20 | 0.61382 | 10 | 0.74402 | Comerío | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 9703-03 | 2026-07-21 | 0.07072 | 10 | 0.085721 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 9703-03 | 2026-07-21 | 0.89448 | 10 | 1.0842 | Comerío | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 9703-03 | 2026-07-22 | 0.18263 | 10 | 0.22137 | Comerío | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 9703-03 | 2026-07-24 | 0.21427 | 10 | 0.25972 | Aguas Buenas | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 9703-03 | 2026-07-24 | 0.04554 | 10 | 0.0552 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 9703-03 | 2026-07-24 | 0.07336 | 10 | 0.088921 | Comerío | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750068 | 2.40/4.16 | 6201-01 | 2026-07-01 | 0.02632 | 10 | 0.031903 | Añasco | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750068 | 2.40/4.16 | 6201-01 | 2026-07-01 | 0.09287 | 10 | 0.11257 | San Sebastián | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750068 | 2.40/4.16 | 6201-01 | 2026-07-02 | 0.1812 | 10 | 0.21964 | Añasco | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750068 | 2.40/4.16 | 6201-01 | 2026-07-02 | 0.04044 | 10 | 0.049018 | Las Marías | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750068 | 2.40/4.16 | 6201-01 | 2026-07-02 | 0.06335 | 10 | 0.076788 | San Sebastián | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750068 | 2.40/4.16 | 6201-01 | 2026-07-06 | 0.0359 | 10 | 0.043515 | Añasco | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750068 | 2.40/4.16 | 6201-01 | 2026-07-06 | 0.26813 | 10 | 0.32501 | Las Marías | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750068 | 2.40/4.16 | 6201-01 | 2026-07-07 | 0.35173 | 10 | 0.42634 | Añasco | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750068 | 2.40/4.16 | 6201-01 | 2026-07-07 | 0.04129 | 10 | 0.050048 | Las Marías | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750068 | 2.40/4.16 | 6201-01 | 2026-07-08 | 0.1035 | 10 | 0.12545 | Añasco | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750068 | 2.40/4.16 | 6201-01 | 2026-07-08 | 0.23227 | 10 | 0.28154 | Las Marías | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750068 | 2.40/4.16 | 6201-01 | 2026-07-08 | 0.16354 | 10 | 0.19823 | San Sebastián | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750068 | 2.40/4.16 | 6201-01 | 2026-07-13 | 0.3222 | 10 | 0.39055 | Las Marías | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750068 | 2.40/4.16 | 6201-01 | 2026-07-14 | 0.03546 | 10 | 0.042982 | Las Marías | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750068 | 2.40/4.16 | 6201-01 | 2026-07-15 | 0.4922 | 10 | 0.59661 | Las Marías | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750068 | 2.40/4.16 | 6201-01 | 2026-07-17 | 0.10687 | 10 | 0.12954 | Las Marías | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750068 | 2.40/4.16 | 6201-01 | 2026-07-27 | 0.35285 | 10 | 0.4277 | Las Marías | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750068 | 2.40/4.16 | 6201-01 | 2026-07-28 | 1.0543 | 10 | 1.278 | Las Marías | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750068 | 2.40/4.16 | 6201-01 | 2026-07-29 | 0.45512 | 10 | 0.55166 | Las Marías | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750068 | 2.40/4.16 | 6201-01 | 2026-07-30 | 0.29053 | 10 | 0.35216 | Las Marías | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750068 | 2.40/4.16 | 6201-01 | 2026-07-31 | 0.31532 | 10 | 0.38221 | Las Marías | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 2.40/4.16 | 8011-01 | 2026-07-14 | 0.48038 | 10 | 0.58228 | Arecibo | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3601-01 | 2026-07-07 | 0.46695 | 10 | 0.566 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
727572 | 7.62/13.20 | 1719-18 | 2026-07-17 | 0.41676 | 10 | 0.50516 | Bayamón | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3601-01 | 2026-07-01 | 0.39086 | 10 | 0.47377 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3602-02 | 2026-07-24 | 0.38032 | 10 | 0.46099 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3602-02 | 2026-07-14 | 0.33521 | 10 | 0.40632 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3601-01 | 2026-07-22 | 0.32847 | 10 | 0.39815 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3601-01 | 2026-07-16 | 0.30315 | 10 | 0.36745 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3601-04 | 2026-07-24 | 0.28435 | 10 | 0.34467 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3601-01 | 2026-07-13 | 0.27576 | 10 | 0.33425 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3602-01 | 2026-07-24 | 0.26521 | 10 | 0.32147 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 2.40/4.16 | 8011-01 | 2026-07-15 | 0.26173 | 10 | 0.31725 | Arecibo | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3601-01 | 2026-07-15 | 0.25972 | 10 | 0.31481 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 2.40/4.16 | 9405-09 | 2026-07-24 | 0.24393 | 10 | 0.29567 | Toa Alta | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 2.40/4.16 | 8011-01 | 2026-07-21 | 0.23708 | 10 | 0.28737 | Arecibo | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3502-02 | 2026-07-31 | 0.23636 | 10 | 0.2865 | Aibonito | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 2.40/4.16 | 9405-09 | 2026-07-27 | 0.23438 | 10 | 0.2841 | Toa Alta | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 2.40/4.16 | 9405-09 | 2026-07-15 | 0.23214 | 10 | 0.28138 | Toa Alta | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3601-03 | 2026-07-14 | 0.21192 | 10 | 0.25687 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 2.40/4.16 | 8011-01 | 2026-07-01 | 0.20882 | 10 | 0.25312 | Arecibo | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3602-02 | 2026-07-13 | 0.20721 | 10 | 0.25116 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3502-02 | 2026-07-28 | 0.20499 | 10 | 0.24847 | Aibonito | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3601-01 | 2026-07-23 | 0.17947 | 10 | 0.21754 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3602-02 | 2026-07-21 | 0.17862 | 10 | 0.21651 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 2.40/4.16 | 8602-01 | 2026-07-27 | 0.17853 | 10 | 0.2164 | Florida | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3602-02 | 2026-07-10 | 0.17329 | 10 | 0.21005 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3701-01 | 2026-07-17 | 0.1661 | 10 | 0.20133 | Aguas Buenas | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3601-01 | 2026-07-06 | 0.16508 | 10 | 0.2001 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3601-03 | 2026-07-06 | 0.16468 | 10 | 0.19961 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3602-02 | 2026-07-15 | 0.16129 | 10 | 0.1955 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3602-01 | 2026-07-10 | 0.15883 | 10 | 0.19252 | Cayey | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3601-03 | 2026-07-15 | 0.15689 | 10 | 0.19017 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 2.40/4.16 | 8011-01 | 2026-07-20 | 0.15577 | 10 | 0.18881 | Arecibo | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
727572 | 7.62/13.20 | 1719-19 | 2026-07-17 | 0.15252 | 10 | 0.18487 | Bayamón | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 2.40/4.16 | 9405-09 | 2026-07-16 | 0.1502 | 10 | 0.18206 | Toa Alta | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3602-01 | 2026-07-21 | 0.14865 | 10 | 0.18018 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 2.40/4.16 | 8602-01 | 2026-07-30 | 0.14726 | 10 | 0.1785 | Florida | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3601-03 | 2026-07-27 | 0.14648 | 10 | 0.17755 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
727572 | 2.40/4.16 | 1708-05 | 2026-07-01 | 0.14184 | 10 | 0.17193 | Bayamón | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 2.40/4.16 | 9405-09 | 2026-07-14 | 0.14173 | 10 | 0.17179 | Toa Alta | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
727572 | 2.40/4.16 | 1708-05 | 2026-07-21 | 0.14035 | 10 | 0.17012 | Bayamón | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3601-01 | 2026-07-02 | 0.14028 | 10 | 0.17004 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750068 | 2.40/4.16 | 7503-02 | 2026-07-02 | 0.13731 | 10 | 0.16644 | Isabela | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3601-03 | 2026-07-22 | 0.13608 | 10 | 0.16495 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3601-01 | 2026-07-17 | 0.13584 | 10 | 0.16465 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 2.40/4.16 | 8602-01 | 2026-07-01 | 0.13373 | 10 | 0.1621 | Florida | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750068 | 2.40/4.16 | 6001-03 | 2026-07-21 | 0.13304 | 10 | 0.16126 | Mayagüez | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3602-02 | 2026-07-17 | 0.13282 | 10 | 0.16099 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3601-03 | 2026-07-02 | 0.13214 | 10 | 0.16017 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 2.40/4.16 | 8011-01 | 2026-07-13 | 0.13087 | 10 | 0.15863 | Arecibo | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 2.40/4.16 | 8602-01 | 2026-07-06 | 0.12969 | 10 | 0.1572 | Florida | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750068 | 2.40/4.16 | 7503-02 | 2026-07-08 | 0.12915 | 10 | 0.15655 | Isabela | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 2.40/4.16 | 9405-09 | 2026-07-07 | 0.12862 | 10 | 0.1559 | Toa Alta | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 2.40/4.16 | 8602-01 | 2026-07-02 | 0.12624 | 10 | 0.15302 | Florida | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3601-01 | 2026-07-14 | 0.12592 | 10 | 0.15263 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3601-01 | 2026-07-20 | 0.12455 | 10 | 0.15097 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750068 | 2.40/4.16 | 7503-02 | 2026-07-07 | 0.12388 | 10 | 0.15016 | Isabela | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 2.40/4.16 | 8011-01 | 2026-07-22 | 0.12265 | 10 | 0.14867 | Arecibo | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3602-02 | 2026-07-09 | 0.11994 | 10 | 0.14538 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3601-03 | 2026-07-17 | 0.11707 | 10 | 0.1419 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 2.40/4.16 | 8602-01 | 2026-07-07 | 0.115 | 10 | 0.13939 | Florida | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750068 | 2.40/4.16 | 7503-02 | 2026-07-27 | 0.11336 | 10 | 0.13741 | Isabela | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3602-01 | 2026-07-17 | 0.10987 | 10 | 0.13318 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3602-02 | 2026-07-23 | 0.10831 | 10 | 0.13128 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 2.40/4.16 | 9405-09 | 2026-07-01 | 0.10632 | 10 | 0.12887 | Toa Alta | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3601-01 | 2026-07-24 | 0.10316 | 10 | 0.12504 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 2.40/4.16 | 8011-01 | 2026-07-16 | 0.10233 | 10 | 0.12404 | Arecibo | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3601-03 | 2026-07-01 | 0.10194 | 10 | 0.12356 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750068 | 2.40/4.16 | 6301-03 | 2026-07-17 | 0.10101 | 10 | 0.12244 | Maricao | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750068 | 2.40/4.16 | 7503-02 | 2026-07-28 | 0.10076 | 10 | 0.12213 | Isabela | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 2.40/4.16 | 8602-01 | 2026-07-14 | 0.10004 | 10 | 0.12126 | Florida | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
727572 | 2.40/4.16 | 1708-05 | 2026-07-02 | 0.09945 | 10 | 0.12055 | Bayamón | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3701-01 | 2026-07-22 | 0.09878 | 10 | 0.11973 | Aguas Buenas | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
727572 | 7.62/13.20 | 1801-01 | 2026-07-02 | 0.09846 | 10 | 0.11935 | Bayamón | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3601-03 | 2026-07-10 | 0.09594 | 10 | 0.11629 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3602-01 | 2026-07-14 | 0.09557 | 10 | 0.11584 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
727572 | 2.40/4.16 | 1708-04 | 2026-07-14 | 0.09448 | 10 | 0.11452 | Bayamón | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3602-02 | 2026-07-22 | 0.09404 | 10 | 0.11399 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750068 | 2.40/4.16 | 6301-03 | 2026-07-21 | 0.09211 | 10 | 0.11165 | Maricao | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 2.40/4.16 | 9405-09 | 2026-07-28 | 0.09141 | 10 | 0.1108 | Toa Alta | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3601-04 | 2026-07-27 | 0.09095 | 10 | 0.11024 | Aguas Buenas | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3601-04 | 2026-07-30 | 0.0908 | 10 | 0.11006 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3701-01 | 2026-07-21 | 0.09009 | 10 | 0.1092 | Aguas Buenas | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
727572 | 7.62/13.20 | 1719-18 | 2026-07-17 | 0.08911 | 10 | 0.10801 | Toa Alta | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
727572 | 2.40/4.16 | 1708-05 | 2026-07-23 | 0.08894 | 10 | 0.10781 | Bayamón | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750068 | 2.40/4.16 | 7503-02 | 2026-07-14 | 0.08873 | 10 | 0.10755 | Isabela | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
727572 | 2.40/4.16 | 1708-04 | 2026-07-30 | 0.0886 | 10 | 0.10739 | Bayamón | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 2.40/4.16 | 8011-01 | 2026-07-27 | 0.0865 | 10 | 0.10485 | Arecibo | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3602-02 | 2026-07-16 | 0.08627 | 10 | 0.10457 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3602-02 | 2026-07-07 | 0.08508 | 10 | 0.10313 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 2.40/4.16 | 8011-01 | 2026-07-23 | 0.08335 | 10 | 0.10103 | Arecibo | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 2.40/4.16 | 8011-01 | 2026-07-30 | 0.08268 | 10 | 0.10022 | Arecibo | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750068 | 2.40/4.16 | 6301-03 | 2026-07-24 | 0.08217 | 10 | 0.0996 | Maricao | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
727572 | 2.40/4.16 | 1708-05 | 2026-07-28 | 0.08167 | 10 | 0.098994 | Bayamón | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750068 | 2.40/4.16 | 7503-02 | 2026-07-09 | 0.08085 | 10 | 0.098 | Isabela | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 2.40/4.16 | 8602-01 | 2026-07-28 | 0.08056 | 10 | 0.097648 | Florida | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3602-02 | 2026-07-08 | 0.07963 | 10 | 0.096521 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
727572 | 2.40/4.16 | 1708-04 | 2026-07-09 | 0.07822 | 10 | 0.094812 | Bayamón | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3601-01 | 2026-07-21 | 0.07776 | 10 | 0.094255 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3601-03 | 2026-07-29 | 0.07771 | 10 | 0.094194 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 2.40/4.16 | 8602-01 | 2026-07-13 | 0.07699 | 10 | 0.093321 | Florida | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3602-02 | 2026-07-27 | 0.0762 | 10 | 0.092364 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3602-01 | 2026-07-10 | 0.07417 | 10 | 0.089903 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3601-03 | 2026-07-23 | 0.07263 | 10 | 0.088036 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3601-03 | 2026-07-08 | 0.07217 | 10 | 0.087479 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3601-04 | 2026-07-27 | 0.07164 | 10 | 0.086836 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 4.80/8.32 | 9003-06 | 2026-07-30 | 0.07072 | 10 | 0.085721 | Vega Baja | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3602-01 | 2026-07-24 | 0.07015 | 10 | 0.08503 | Cayey | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3601-04 | 2026-07-28 | 0.07014 | 10 | 0.085018 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3601-04 | 2026-07-29 | 0.06881 | 10 | 0.083406 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3701-01 | 2026-07-09 | 0.06795 | 10 | 0.082364 | Aguas Buenas | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 2.40/4.16 | 8602-01 | 2026-07-15 | 0.06703 | 10 | 0.081248 | Florida | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3601-01 | 2026-07-30 | 0.06678 | 10 | 0.080945 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750068 | 2.40/4.16 | 7503-02 | 2026-07-01 | 0.06645 | 10 | 0.080545 | Isabela | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3603-01 | 2026-07-20 | 0.06627 | 10 | 0.080327 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3701-01 | 2026-07-28 | 0.06609 | 10 | 0.080109 | Aguas Buenas | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750068 | 2.40/4.16 | 6301-03 | 2026-07-20 | 0.06544 | 10 | 0.079321 | Maricao | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
727572 | 2.40/4.16 | 1708-04 | 2026-07-27 | 0.06466 | 10 | 0.078376 | Bayamón | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
727531 | 2.40/4.16 | 5802-02 | 2026-07-01 | 0.06437 | 10 | 0.078024 | Juana Díaz | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 2.40/4.16 | 9405-09 | 2026-07-09 | 0.06388 | 10 | 0.07743 | Toa Alta | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
727572 | 2.40/4.16 | 1708-04 | 2026-07-22 | 0.06268 | 10 | 0.075976 | Bayamón | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
727572 | 2.40/4.16 | 1708-04 | 2026-07-08 | 0.06174 | 10 | 0.074836 | Bayamón | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 2.40/4.16 | 8011-01 | 2026-07-18 | 0.06112 | 10 | 0.074085 | Arecibo | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3602-02 | 2026-07-20 | 0.06098 | 10 | 0.073915 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3701-01 | 2026-07-10 | 0.06058 | 10 | 0.07343 | Aguas Buenas | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3602-01 | 2026-07-28 | 0.06039 | 10 | 0.0732 | Cayey | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3601-04 | 2026-07-21 | 0.05926 | 10 | 0.07183 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 2.40/4.16 | 9405-09 | 2026-07-08 | 0.05832 | 10 | 0.070691 | Toa Alta | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750068 | 2.40/4.16 | 7503-02 | 2026-07-06 | 0.05787 | 10 | 0.070145 | Isabela | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
727572 | 2.40/4.16 | 1708-05 | 2026-07-30 | 0.05747 | 10 | 0.069661 | Bayamón | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 7.62/13.20 | 1719-18 | 2026-07-16 | 0.0572 | 10 | 0.069333 | Bayamón | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750068 | 2.40/4.16 | 7503-02 | 2026-07-20 | 0.05676 | 10 | 0.0688 | Isabela | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3601-01 | 2026-07-09 | 0.05648 | 10 | 0.068461 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3601-01 | 2026-07-10 | 0.05632 | 10 | 0.068267 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 2.40/4.16 | 9405-09 | 2026-07-22 | 0.05584 | 10 | 0.067685 | Toa Alta | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3601-01 | 2026-07-27 | 0.05492 | 10 | 0.06657 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3601-01 | 2026-07-11 | 0.05473 | 10 | 0.066339 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750068 | 2.40/4.16 | 6301-03 | 2026-07-27 | 0.05372 | 10 | 0.065115 | Maricao | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3601-03 | 2026-07-30 | 0.05357 | 10 | 0.064933 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3502-02 | 2026-07-29 | 0.0511 | 10 | 0.061939 | Aibonito | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 2.40/4.16 | 8011-01 | 2026-07-29 | 0.04975 | 10 | 0.060303 | Arecibo | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 2.40/4.16 | 8011-01 | 2026-07-02 | 0.04941 | 10 | 0.059891 | Arecibo | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3602-01 | 2026-07-30 | 0.04938 | 10 | 0.059855 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
727572 | 2.40/4.16 | 1708-05 | 2026-07-24 | 0.04895 | 10 | 0.059333 | Bayamón | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
727572 | 7.62/13.20 | 1719-18 | 2026-07-16 | 0.0486 | 10 | 0.058909 | Toa Alta | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750068 | 2.40/4.16 | 7503-02 | 2026-07-23 | 0.04832 | 10 | 0.05857 | Isabela | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
727572 | 2.40/4.16 | 1708-04 | 2026-07-06 | 0.04803 | 10 | 0.058218 | Bayamón | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750068 | 2.40/4.16 | 7503-02 | 2026-07-16 | 0.04592 | 10 | 0.055661 | Isabela | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3701-01 | 2026-07-13 | 0.04463 | 10 | 0.054097 | Aguas Buenas | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
727572 | 2.40/4.16 | 1708-05 | 2026-07-27 | 0.04233 | 10 | 0.051309 | Bayamón | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 2.40/4.16 | 9405-09 | 2026-07-23 | 0.04108 | 10 | 0.049794 | Toa Alta | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3601-03 | 2026-07-21 | 0.03968 | 10 | 0.048097 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3701-01 | 2026-07-30 | 0.03949 | 10 | 0.047867 | Aguas Buenas | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3602-01 | 2026-07-28 | 0.03911 | 10 | 0.047406 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3701-01 | 2026-07-31 | 0.03881 | 10 | 0.047042 | Aguas Buenas | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
727572 | 2.40/4.16 | 1708-05 | 2026-07-29 | 0.03826 | 10 | 0.046376 | Bayamón | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750068 | 2.40/4.16 | 6301-03 | 2026-07-16 | 0.0378 | 10 | 0.045818 | Maricao | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3602-01 | 2026-07-27 | 0.03734 | 10 | 0.045261 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 2.40/4.16 | 8602-01 | 2026-07-08 | 0.03724 | 10 | 0.045139 | Florida | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750068 | 2.40/4.16 | 6001-03 | 2026-07-27 | 0.03716 | 10 | 0.045042 | Mayagüez | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 2.40/4.16 | 8602-01 | 2026-07-29 | 0.03649 | 10 | 0.04423 | Florida | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 2.40/4.16 | 8011-01 | 2026-07-28 | 0.03562 | 10 | 0.043176 | Arecibo | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3601-04 | 2026-07-31 | 0.03533 | 10 | 0.042824 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3601-04 | 2026-07-22 | 0.03532 | 10 | 0.042812 | Aguas Buenas | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3602-01 | 2026-07-09 | 0.03499 | 10 | 0.042412 | Cayey | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3602-01 | 2026-07-22 | 0.03436 | 10 | 0.041648 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
727572 | 7.62/13.20 | 1801-01 | 2026-07-15 | 0.03411 | 10 | 0.041345 | Bayamón | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 2.40/4.16 | 8602-01 | 2026-07-20 | 0.03388 | 10 | 0.041067 | Florida | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3601-01 | 2026-07-28 | 0.03378 | 10 | 0.040945 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3602-01 | 2026-07-29 | 0.03365 | 10 | 0.040788 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750068 | 2.40/4.16 | 7503-02 | 2026-07-13 | 0.03296 | 10 | 0.039952 | Isabela | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
727572 | 7.62/13.20 | 1801-01 | 2026-07-01 | 0.03243 | 10 | 0.039309 | Bayamón | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750068 | 2.40/4.16 | 7503-02 | 2026-07-21 | 0.03237 | 10 | 0.039236 | Isabela | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3602-01 | 2026-07-16 | 0.03224 | 10 | 0.039079 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 2.40/4.16 | 8602-01 | 2026-07-09 | 0.0321 | 10 | 0.038909 | Florida | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3601-04 | 2026-07-23 | 0.03187 | 10 | 0.03863 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 2.40/4.16 | 8602-01 | 2026-07-21 | 0.03173 | 10 | 0.038461 | Florida | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750068 | 2.40/4.16 | 6301-03 | 2026-07-31 | 0.03119 | 10 | 0.037806 | Maricao | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3602-02 | 2026-07-28 | 0.03059 | 10 | 0.037079 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750068 | 2.40/4.16 | 6301-03 | 2026-07-23 | 0.03056 | 10 | 0.037042 | Maricao | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3601-04 | 2026-07-17 | 0.03052 | 10 | 0.036994 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3701-01 | 2026-07-14 | 0.03049 | 10 | 0.036958 | Aguas Buenas | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3502-02 | 2026-07-24 | 0.02981 | 10 | 0.036133 | Aibonito | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
727572 | 2.40/4.16 | 1708-05 | 2026-07-07 | 0.029 | 10 | 0.035152 | Bayamón | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750068 | 2.40/4.16 | 6001-03 | 2026-07-24 | 0.02891 | 10 | 0.035042 | Mayagüez | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 2.40/4.16 | 9405-09 | 2026-07-20 | 0.02871 | 10 | 0.0348 | Toa Alta | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 2.40/4.16 | 9405-09 | 2026-07-13 | 0.02861 | 10 | 0.034679 | Toa Alta | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
727572 | 7.62/13.20 | 1801-01 | 2026-07-20 | 0.0283 | 10 | 0.034303 | Bayamón | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 2.40/4.16 | 9405-09 | 2026-07-29 | 0.02818 | 10 | 0.034158 | Toa Alta | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
727572 | 7.62/13.20 | 1719-18 | 2026-07-16 | 0.02808 | 10 | 0.034036 | Bayamón | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3502-02 | 2026-07-30 | 0.02771 | 10 | 0.033588 | Aibonito | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
727692 | 4.80/8.32 | 3009-04 | 2026-07-08 | 0.02756 | 10 | 0.033406 | Caguas | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3601-04 | 2026-07-29 | 0.02708 | 10 | 0.032824 | Aguas Buenas | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3602-02 | 2026-07-29 | 0.02649 | 10 | 0.032109 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3701-01 | 2026-07-23 | 0.02436 | 10 | 0.029527 | Aguas Buenas | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 2.40/4.16 | 8602-01 | 2026-07-17 | 0.0243 | 10 | 0.029455 | Florida | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 4.80/8.32 | 9003-06 | 2026-07-29 | 0.02318 | 10 | 0.028097 | Vega Baja | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
727572 | 2.40/4.16 | 1708-04 | 2026-07-21 | 0.02238 | 10 | 0.027127 | Bayamón | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3602-01 | 2026-07-29 | 0.02095 | 10 | 0.025394 | Cayey | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3601-01 | 2026-07-04 | 0.01854 | 10 | 0.022473 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750065 | 2.40/4.16 | 9405-09 | 2026-07-02 | 0.01826 | 10 | 0.022133 | Toa Alta | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
727572 | 2.40/4.16 | 1708-05 | 2026-07-14 | 0.01622 | 10 | 0.019661 | Bayamón | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
727572 | 7.62/13.20 | 1801-01 | 2026-07-20 | 0.01544 | 10 | 0.018715 | Cataño | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750066 | 4.80/8.32 | 3601-04 | 2026-07-22 | 0.01508 | 10 | 0.018279 | Cidra | Ceres | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
727572 | 2.40/4.16 | 1708-05 | 2026-07-08 | 0.01236 | 10 | 0.014982 | Bayamón | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
750067 | 4.80/8.32 | 9003-06 | 2026-07-28 | 0.00959 | 10 | 0.011624 | Vega Baja | Asplundh | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
727572 | 2.40/4.16 | 1708-04 | 2026-07-15 | 0.00851 | 10 | 0.010315 | Bayamón | Xperts | In Progress | Federally Funded | Ian Kreher | Federal Funds | July | Q1 | FY2027
N/A | 2.40/4.16 | 6801-02 | 2026-08-01 | 0.054681 | 10 | 0.01 | Hormigueros | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5501-03 | 2026-08-01 | 0.029204 | 10 | 0.01 | Guayanilla | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5501-03 | 2026-08-01 | 0.053438 | 10 | 0.01 | Guayanilla | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-01 | 0.033485 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-01 | 0.02661 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 4101-04 | 2026-08-01 | 0.029631 | 10 | 0.01 | Arroyo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-01 | 0.039625 | 10 | 0.01 | Canóvanas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-01 | 0.028878 | 10 | 0.01 | Canóvanas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 4101-04 | 2026-08-01 | 0.024332 | 10 | 0.01 | Arroyo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-01 | 0.041632 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7301-02 | 2026-08-01 | 0.026719 | 10 | 0.01 | Rincón | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-01 | 0.026098 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8501-01 | 2026-08-01 | 0.055923 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-01 | 0.025476 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7504-02 | 2026-08-01 | 0.034175 | 10 | 0.01 | Isabela | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-01 | 0.026071 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-01 | 0.021748 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-01 | 0.027962 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7802-01 | 2026-08-01 | 0.037904 | 10 | 0.01 | San Sebastián | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-01 | 0.019884 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-01 | 0.014291 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 7903-07 | 2026-08-01 | 0.026719 | 10 | 0.01 | Lares | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-01 | 0.026098 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-01 | 0.0093206 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-01 | 0.04101 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8013-03 | 2026-08-01 | 0.039768 | 10 | 0.01 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-01 | 0.024996 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 3103-04 | 2026-08-01 | 0.059111 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-01 | 0.037561 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-01 | 0.017398 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-01 | 0.031069 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-01 | 0.026719 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8404-02 | 2026-08-01 | 0.057747 | 10 | 0.01 | Manatí | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2201-04 | 2026-08-01 | 0.021127 | 10 | 0.01 | Luquillo | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2201-04 | 2026-08-01 | 0.022991 | 10 | 0.01 | Luquillo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2201-04 | 2026-08-01 | 0.078914 | 10 | 0.01 | Luquillo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-01 | 0.055302 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2201-04 | 2026-08-01 | 0.078914 | 10 | 0.01 | Luquillo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1924-05 | 2026-08-01 | 0.019262 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2305-03 | 2026-08-01 | 0.041434 | 10 | 0.01 | Río Grande | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2305-03 | 2026-08-01 | 0.041434 | 10 | 0.01 | Río Grande | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-03 | 2026-08-01 | 0.022369 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1519-01 | 2026-08-01 | 0.027323 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1529-11 | 2026-08-01 | 0.02597 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1529-11 | 2026-08-01 | 0.014691 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1519-01 | 2026-08-01 | 0.015701 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1519-05 | 2026-08-01 | 0.034013 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1529-11 | 2026-08-01 | 0.010563 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2305-03 | 2026-08-01 | 0.043955 | 10 | 0.01 | Río Grande | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2305-03 | 2026-08-01 | 0.023041 | 10 | 0.01 | Río Grande | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1519-01 | 2026-08-01 | 0.012427 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1529-11 | 2026-08-01 | 0.039768 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1519-01 | 2026-08-01 | 0.039768 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-08-01 | 0.031069 | 10 | 0.01 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1529-11 | 2026-08-01 | 0.020505 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2201-04 | 2026-08-01 | 0.047846 | 10 | 0.01 | Luquillo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-01 | 0.027202 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-01 | 0.012994 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2305-03 | 2026-08-01 | 0.020454 | 10 | 0.01 | Río Grande | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7403-03 | 2026-08-04 | 0.054059 | 10 | 0.01 | San Sebastian | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2702-01 | 2026-08-08 | 0.028583 | 10 | 0.01 | Naguabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-08-06 | 0.030479 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-08-06 | 0.030557 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-08-06 | 0.034175 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-08-06 | 0.03169 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-08-04 | 0.028583 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-08-04 | 0.028583 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7301-02 | 2026-08-05 | 0.022991 | 10 | 0.01 | Rincón | Site Resources | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7301-02 | 2026-08-05 | 0.026719 | 10 | 0.01 | Rincón | Site Resources | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8004-02 | 2026-08-03 | 0.025475 | 10 | 0.01 | Arecibo | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5817-01 | 2026-08-05 | 0.050331 | 10 | 0.01 | Ponce | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5817-01 | 2026-08-05 | 0.044117 | 10 | 0.01 | Ponce | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5817-01 | 2026-08-04 | 0.04536 | 10 | 0.01 | Ponce | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5817-01 | 2026-08-04 | 0.039146 | 10 | 0.01 | Ponce | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 3205-08 | 2026-08-03 | 0.032996 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5902-02 | 2026-08-06 | 0.019688 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5902-02 | 2026-08-06 | 0.040389 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5902-02 | 2026-08-06 | 0.091963 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1303-02 | 2026-08-04 | 0.02734 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 4003-01 | 2026-08-05 | 0.06601 | 10 | 0.01 | Guayama | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 4003-01 | 2026-08-06 | 0.0788 | 10 | 0.01 | Guayama | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 4003-01 | 2026-08-06 | 0.0788 | 10 | 0.01 | Guayama | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 4003-01 | 2026-08-08 | 0.055198 | 10 | 0.01 | Guayama | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 4003-01 | 2026-08-05 | 0.019159 | 10 | 0.01 | Guayama | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 4003-01 | 2026-08-05 | 0.03659 | 10 | 0.01 | Guayama | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 4003-01 | 2026-08-08 | 0.028046 | 10 | 0.01 | Guayama | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1602-05 | 2026-08-05 | 0.039146 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1602-05 | 2026-08-05 | 0.048467 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5501-03 | 2026-08-04 | 0.022991 | 10 | 0.01 | Guayanilla | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5501-03 | 2026-08-03 | 0.043853 | 10 | 0.01 | Guayanilla | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5501-03 | 2026-08-03 | 0.00449 | 10 | 0.01 | Guayanilla | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.16/7.20 | 6702-02 | 2026-08-06 | 0.038525 | 10 | 0.01 | Cabo Rojo | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.16/7.20 | 6702-02 | 2026-08-06 | 0.041632 | 10 | 0.01 | Cabo Rojo | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5501-03 | 2026-08-03 | 0.024384 | 10 | 0.01 | Guayanilla | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-05 | 0.028308 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1734-02 | 2026-08-03 | 0.020165 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1734-02 | 2026-08-04 | 0.034175 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7301-02 | 2026-08-03 | 0.12241 | 10 | 0.01 | Rincón | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7301-02 | 2026-08-03 | 0.020505 | 10 | 0.01 | Rincón | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7301-02 | 2026-08-03 | 0.026719 | 10 | 0.01 | Rincón | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7301-02 | 2026-08-06 | 0.026719 | 10 | 0.01 | Rincón | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7301-02 | 2026-08-06 | 0.027962 | 10 | 0.01 | Rincón | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-03 | 0.031979 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-05 | 0.037376 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-07 | 2026-08-05 | 0.037282 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-03 | 0.034534 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-03 | 0.034797 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-03 | 0.032933 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-03 | 0.023159 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-06 | 0.033554 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-04 | 0.024234 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 3205-08 | 2026-08-04 | 0.035219 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-04 | 0.020505 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 3205-08 | 2026-08-04 | 0.017763 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-04 | 0.024234 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1345-04 | 2026-08-07 | 0.015534 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1345-04 | 2026-08-07 | 0.029204 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1345-04 | 2026-08-07 | 0.019884 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-08-07 | 0.021748 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-06 | 0.035444 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-06 | 0.022369 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-06 | 0.043128 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-07 | 0.032933 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-08 | 0.032933 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1652-02 | 2026-08-06 | 0.04971 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-05 | 0.029839 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-05 | 0.029317 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-06 | 0.031902 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-06 | 0.038201 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-07 | 0.053834 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-07 | 0.071458 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8501-01 | 2026-08-04 | 0.027757 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8501-01 | 2026-08-04 | 0.033538 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8501-01 | 2026-08-04 | 0.029966 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8501-01 | 2026-08-04 | 0.034424 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-07 | 0.02053 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8501-01 | 2026-08-04 | 0.032109 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-08 | 0.04536 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-07 | 0.032933 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8501-01 | 2026-08-04 | 0.021634 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-08 | 0.036661 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-08 | 0.041741 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-06 | 0.021127 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-06 | 0.021748 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-06 | 0.028021 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-06 | 0.023612 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8504-01 | 2026-08-05 | 0.038801 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8504-01 | 2026-08-05 | 0.043984 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8504-01 | 2026-08-07 | 0.041112 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8504-01 | 2026-08-07 | 0.036677 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8504-01 | 2026-08-07 | 0.032079 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8504-01 | 2026-08-07 | 0.039688 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-08-04 | 0.019233 | 10 | 0.01 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-08-04 | 0.025658 | 10 | 0.01 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-08-03 | 0.016777 | 10 | 0.01 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-08-04 | 0.039092 | 10 | 0.01 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8013-02 | 2026-08-03 | 0.027268 | 10 | 0.01 | Hatillo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-08-04 | 0.026098 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-08-04 | 0.03129 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-08-06 | 0.038491 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-08-04 | 0.025094 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-08-04 | 0.038798 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-08-04 | 0.023612 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-06 | 0.034175 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1901-03 | 2026-08-05 | 0.023612 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-04 | 0.036056 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-04 | 0.034772 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5501-03 | 2026-08-07 | 0.026719 | 10 | 0.01 | Guayanilla | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5501-03 | 2026-08-07 | 0.036661 | 10 | 0.01 | Guayanilla | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-08-07 | 0.024855 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-08 | 0.091963 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-08 | 0.053082 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-08 | 0.0038699 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1620-05 | 2026-08-05 | 0.024855 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1620-05 | 2026-08-05 | 0.039146 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-07 | 0.084506 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-07 | 0.037904 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-05 | 0.020851 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-07 | 0.086992 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-06 | 0.028583 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-06 | 0.047846 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-07 | 0.047846 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-07 | 0.042253 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-07 | 0.043496 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-07 | 0.022991 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-06 | 0.029204 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-06 | 0.029826 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-06 | 0.026719 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-06 | 0.01367 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-06 | 0.021748 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-06 | 0.024855 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-06 | 0.024234 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-06 | 0.01802 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-06 | 0.029826 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-06 | 0.029885 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-06 | 0.027145 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-06 | 0.026997 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-06 | 0.025476 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-06 | 0.028298 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-07 | 0.024234 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-03 | 0.04536 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-06 | 0.023612 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-06 | 0.022369 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-06 | 0.017398 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-06 | 0.022369 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-06 | 0.029826 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8501-01 | 2026-08-04 | 0.017398 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5501-03 | 2026-08-08 | 0.034175 | 10 | 0.01 | Guayanilla | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5501-03 | 2026-08-08 | 0.034175 | 10 | 0.01 | Guayanilla | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-04 | 0.029826 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-06 | 0.021748 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-04 | 0.035418 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-05 | 0.023612 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-04 | 0.036661 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-04 | 0.034175 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5501-03 | 2026-08-05 | 0.050331 | 10 | 0.01 | Guayanilla | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-04 | 0.0086992 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-06 | 0.021748 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-06 | 0.018641 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5501-03 | 2026-08-05 | 0.021748 | 10 | 0.01 | Guayanilla | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5501-03 | 2026-08-04 | 0.065865 | 10 | 0.01 | Guayanilla | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7504-02 | 2026-08-04 | 0.054681 | 10 | 0.01 | Isabela | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7504-02 | 2026-08-04 | 0.03169 | 10 | 0.01 | Isabela | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7504-02 | 2026-08-04 | 0.021127 | 10 | 0.01 | Isabela | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-08 | 0.047224 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1901-05 | 2026-08-06 | 0.024234 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-08-06 | 0.026098 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-08-06 | 0.024855 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1901-05 | 2026-08-06 | 0.025476 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-08 | 0.034797 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-04 | 0.035418 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-02 | 2026-08-03 | 0.032981 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-03 | 2026-08-07 | 0.030117 | 10 | 0.01 | Manatí | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-03 | 2026-08-07 | 0.033999 | 10 | 0.01 | Manatí | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-05 | 0.036836 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-05 | 0.017398 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-05 | 0.011806 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-03 | 2026-08-07 | 0.022849 | 10 | 0.01 | Manatí | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-03 | 2026-08-07 | 0.037315 | 10 | 0.01 | Manatí | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-03 | 2026-08-08 | 0.032933 | 10 | 0.01 | Manatí | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-04 | 0.04971 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-05 | 0.025369 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-08-05 | 0.027032 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-08-07 | 0.032311 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-03 | 0.014779 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-08-07 | 0.038525 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-08-07 | 0.047224 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-05 | 0.013171 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-04 | 0.030762 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-04 | 0.034938 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-03 | 0.033466 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-08-04 | 0.041632 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-08-04 | 0.034797 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-08-04 | 0.044739 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-03 | 0.099138 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-03 | 0.025476 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-03 | 0.021748 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-04 | 0.020505 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-07 | 0.021127 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-08-03 | 0.039146 | 10 | 0.01 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-08-04 | 0.041632 | 10 | 0.01 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-08-03 | 0.035418 | 10 | 0.01 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-08-04 | 0.045882 | 10 | 0.01 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-08-03 | 0.04412 | 10 | 0.01 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.026879 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.028794 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.017739 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-07 | 0.033909 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-06 | 0.061882 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-07 | 0.018641 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-07 | 0.029204 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-07 | 0.035418 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-06 | 0.0056322 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-03 | 0.037904 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.0082419 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-06 | 0.021805 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1336-06 | 2026-08-03 | 0.041632 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1301-03 | 2026-08-03 | 0.041084 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-04 | 0.013658 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.025326 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.00081042 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-04 | 0.00449 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.0038814 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1336-06 | 2026-08-03 | 0.038525 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.00068371 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.00063807 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1301-03 | 2026-08-03 | 0.03604 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.0034508 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.00065322 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-04 | 0.01995 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1336-06 | 2026-08-07 | 0.027962 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1336-06 | 2026-08-07 | 0.028583 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1336-06 | 2026-08-07 | 0.028583 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1336-06 | 2026-08-04 | 0.029826 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1336-06 | 2026-08-04 | 0.026719 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.030562 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1336-06 | 2026-08-06 | 0.028583 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-06 | 0.017623 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1336-06 | 2026-08-04 | 0.027962 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-06 | 0.026719 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-06 | 0.013049 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.028169 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1336-06 | 2026-08-04 | 0.03604 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-06 | 0.022369 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-06 | 0.036661 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1336-06 | 2026-08-03 | 0.034175 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-06 | 0.010563 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-06 | 0.032933 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1336-06 | 2026-08-03 | 0.033554 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-06 | 0.031069 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.038772 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-06 | 0.045981 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-06 | 0.043713 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-06 | 0.028583 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.020487 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.016704 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1336-06 | 2026-08-03 | 0.019295 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-08-04 | 0.021127 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-06 | 0.032311 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-06 | 0.032311 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.024869 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.020542 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.020869 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-06 | 0.034328 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2201-04 | 2026-08-06 | 0.044048 | 10 | 0.01 | Luquillo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.021975 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.024589 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.020966 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.024445 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.034878 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.015465 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-06 | 0.0093206 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-06 | 0.029204 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-04 | 0.01367 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-04 | 0.026719 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-06 | 0.030447 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.029826 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.025476 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-06 | 0.021127 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-06 | 0.019262 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-04 | 0.01367 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-06 | 0.01367 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-04 | 0.012913 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.022369 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-04 | 0.01313 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.012427 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-03 | 0.025297 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-06 | 0.01367 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-06 | 0.022991 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-06 | 0.016156 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-08-06 | 0.016156 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-03 | 0.033502 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-04 | 0.032628 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-06 | 0.016655 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-06 | 0.021691 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-06 | 0.031899 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-06 | 0.017651 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-06 | 0.025011 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-06 | 0.002647 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-06 | 0.013917 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-06 | 0.014683 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-06 | 0.043496 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-03 | 0.027228 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7503-02 | 2026-08-04 | 0.022991 | 10 | 0.01 | Isabela | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-03 | 0.034609 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-06 | 0.012427 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-04 | 0.033439 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-06 | 0.021127 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-03 | 0.025609 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-06 | 0.024855 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-06 | 0.025476 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-06 | 0.030447 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-03 | 0.038416 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-06 | 0.025476 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-06 | 0.036661 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-03 | 0.0034983 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-06 | 0.021127 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-03 | 0.022671 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-06 | 0.018641 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-06 | 0.015553 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-06 | 0.025767 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-06 | 0.035463 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-03 | 0.020948 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-06 | 0.01136 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-06 | 0.01182 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-06 | 0.013072 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-06 | 0.010803 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-06 | 0.020459 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-06 | 0.0022388 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-08-05 | 0.022991 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-06 | 0.030447 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-06 | 0.023612 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-06 | 0.027962 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-07 | 0.022369 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-05 | 0.032311 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-04 | 0.040389 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-07 | 0.019863 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-04 | 0.013499 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-06 | 0.037005 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-04 | 0.027578 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-06 | 0.02734 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-06 | 0.014544 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-06 | 0.013648 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-06 | 0.042253 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-06 | 0.016156 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-06 | 0.024855 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-04 | 0.03169 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-04 | 0.03169 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-08-06 | 0.022369 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-07 | 0.031194 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-07 | 0.045102 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-07 | 0.051405 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-07 | 0.032289 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-08-06 | 0.031069 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.1 | 3202-01 | 2026-08-04 | 0.09507 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-04 | 0.030981 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7503-02 | 2026-08-04 | 0.029825 | 10 | 0.01 | Isabela | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-07 | 0.044117 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-08-08 | 0.020649 | 10 | 0.01 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-06 | 0.033554 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7503-02 | 2026-08-05 | 0.036661 | 10 | 0.01 | Isabela | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7503-02 | 2026-08-05 | 0.039146 | 10 | 0.01 | Isabela | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-05 | 0.073943 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7503-02 | 2026-08-05 | 0.021127 | 10 | 0.01 | Isabela | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7503-02 | 2026-08-05 | 0.020505 | 10 | 0.01 | Isabela | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7503-02 | 2026-08-05 | 0.015534 | 10 | 0.01 | Isabela | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-06 | 0.047846 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 7903-07 | 2026-08-05 | 0.024234 | 10 | 0.01 | Lares | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-04 | 0.033137 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-06 | 0.032933 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-04 | 0.037904 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-06 | 0.030447 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-06 | 0.032933 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-06 | 0.033554 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-04 | 0.024855 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-07 | 0.023612 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-06 | 0.019884 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2201-04 | 2026-08-06 | 0.042041 | 10 | 0.01 | Luquillo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 7903-07 | 2026-08-05 | 0.019016 | 10 | 0.01 | Lares | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-08 | 0.032933 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 7903-07 | 2026-08-05 | 0.01833 | 10 | 0.01 | Lares | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-07 | 0.029826 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-06 | 0.028583 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-08 | 0.026719 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-06 | 0.029204 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-04 | 0.038177 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7903-07 | 2026-08-06 | 0.03604 | 10 | 0.01 | Lares | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-04 | 0.056545 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 7903-07 | 2026-08-03 | 0.029199 | 10 | 0.01 | Lares | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 4301-03 | 2026-08-04 | 0.022783 | 10 | 0.01 | Maunabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7903-07 | 2026-08-05 | 0.03604 | 10 | 0.01 | Lares | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-08 | 0.036638 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-08 | 0.012368 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-06 | 0.044117 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-04 | 0.037904 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-04 | 0.026719 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-08 | 0.0055924 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-08 | 0.0074564 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-08 | 0.018641 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-04 | 0.029191 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-06 | 0.042338 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-06 | 0.012016 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-05 | 0.006835 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-05 | 0.029826 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-06 | 0.050952 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-05 | 0.055302 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-05 | 0.029826 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-05 | 0.023612 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-05 | 0.023612 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-03 | 0.024234 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-03 | 0.044142 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7502-02 | 2026-08-03 | 0.029204 | 10 | 0.01 | Isabela | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-04 | 0.028322 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7502-02 | 2026-08-03 | 0.030447 | 10 | 0.01 | Isabela | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-03 | 0.037407 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-03 | 0.035304 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-04 | 0.0286 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-05 | 0.070175 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-05 | 0.017398 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-08-04 | 0.016622 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-06 | 0.031069 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-08-06 | 0.030931 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-06 | 0.027962 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-08-06 | 0.027932 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-06 | 0.034797 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-08-07 | 0.034459 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-08 | 0.031069 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-08-08 | 0.030934 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8013-01 | 2026-08-06 | 0.028655 | 10 | 0.01 | Arecibo | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8013-01 | 2026-08-07 | 0.024833 | 10 | 0.01 | Arecibo | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8013-01 | 2026-08-06 | 0.027787 | 10 | 0.01 | Arecibo | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8013-01 | 2026-08-04 | 0.022774 | 10 | 0.01 | Arecibo | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8013-01 | 2026-08-04 | 0.02793 | 10 | 0.01 | Arecibo | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5902-03 | 2026-08-07 | 0.036088 | 10 | 0.01 | Juana Díaz | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5902-03 | 2026-08-07 | 0.032933 | 10 | 0.01 | Juana Díaz | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-08 | 0.028583 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-08 | 0.029204 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-08 | 0.037282 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5902-03 | 2026-08-07 | 0.061242 | 10 | 0.01 | Juana Díaz | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5902-03 | 2026-08-07 | 0.010563 | 10 | 0.01 | Juana Díaz | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5902-03 | 2026-08-07 | 0.037904 | 10 | 0.01 | Juana Díaz | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-04 | 0.029204 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-07 | 0.017556 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-03 | 0.076732 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-04 | 0.03632 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5902-03 | 2026-08-07 | 0.024855 | 10 | 0.01 | Juana Díaz | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-03 | 0.018442 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-03 | 0.034175 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5902-03 | 2026-08-07 | 0.031069 | 10 | 0.01 | Juana Díaz | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-04 | 0.057787 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-03 | 0.015933 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-04 | 0.071458 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-06 | 0.047846 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-06 | 0.014552 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-07 | 0.014059 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-07 | 0.016365 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-05 | 0.054083 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-05 | 0.048223 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-07 | 0.023341 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-04 | 0.021127 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1343-03 | 2026-08-03 | 0.019262 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-07 | 0.027988 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8404-02 | 2026-08-06 | 0.054671 | 10 | 0.01 | Manatí | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-07 | 0.018902 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8404-02 | 2026-08-03 | 0.039768 | 10 | 0.01 | Manatí | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.035418 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8404-02 | 2026-08-03 | 0.025476 | 10 | 0.01 | Manatí | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-05 | 0.014193 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-04 | 0.018641 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-04 | 0.018957 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-04 | 0.016048 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8404-02 | 2026-08-03 | 0.057166 | 10 | 0.01 | Manatí | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-07 | 0.016559 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-04 | 0.028583 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-07 | 0.023784 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-07 | 0.020898 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-07 | 0.023612 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-08 | 0.0074564 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-07 | 0.037904 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-04 | 0.016156 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-03 | 0.020505 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-03 | 0.012427 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-03 | 0.022991 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-07 | 0.01802 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-03 | 0.037282 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-03 | 0.022369 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-08 | 0.017398 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-03 | 0.027962 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-03 | 0.02734 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-03 | 0.016777 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-03 | 0.022991 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-06 | 0.01802 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-07 | 0.023612 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-04 | 0.023612 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-03 | 0.014291 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-07 | 0.021748 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-03 | 0.033554 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-07 | 0.020626 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-06 | 0.045981 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-07 | 0.022369 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-07 | 0.029826 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-07 | 0.10253 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-07 | 0.031069 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-03 | 0.032848 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1708-05 | 2026-08-05 | 0.021127 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-07 | 0.01367 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-07 | 0.01367 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-07 | 0.018641 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-03 | 0.029547 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-08 | 0.027962 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-07 | 0.018641 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-07 | 0.023612 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-03 | 0.011691 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-03 | 0.029204 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-03 | 0.0025896 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-03 | 0.0049991 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-03 | 0.0068538 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-04 | 0.004971 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-04 | 0.0099419 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-04 | 0.006835 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-04 | 0.013049 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-04 | 0.0062136 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-04 | 0.0099419 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-04 | 0.021127 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-04 | 0.021127 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-04 | 0.03344 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-05 | 0.035639 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-05 | 0.018676 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-05 | 0.039768 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-05 | 0.012911 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-07 | 0.042253 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-04 | 0.04101 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-08-07 | 0.042757 | 10 | 0.01 | Florida | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-08-07 | 0.043802 | 10 | 0.01 | Florida | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-08-06 | 0.028411 | 10 | 0.01 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-08-06 | 0.033503 | 10 | 0.01 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-08-06 | 0.040798 | 10 | 0.01 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-03 | 0.004971 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-03 | 0.034797 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-03 | 0.020973 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-03 | 0.049088 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-03 | 0.026098 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-05 | 0.032329 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-03 | 0.0086992 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-04 | 2026-08-05 | 0.03885 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-03 | 0.042875 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-03 | 0.030447 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-05 | 0.035418 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-05 | 0.025476 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-03 | 0.01424 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1342-04 | 2026-08-03 | 0.012533 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-03 | 0.012958 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1342-04 | 2026-08-03 | 0.013413 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-03 | 0.0074564 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-05 | 0.032459 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-03 | 0.024234 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1342-04 | 2026-08-05 | 0.030416 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-03 | 0.025476 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-03 | 0.028583 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-03 | 0.028583 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-03 | 0.004971 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-04 | 0.027913 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-04 | 0.021127 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-03 | 0.037904 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1801-01 | 2026-08-08 | 0.032311 | 10 | 0.01 | Cataño | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-03 | 0.020505 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-03 | 0.028583 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-06 | 0.062137 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1801-01 | 2026-08-08 | 0.028583 | 10 | 0.01 | Cataño | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-05 | 0.068972 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-05 | 0.06338 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-03 | 0.031212 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-05 | 0.015994 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-03 | 0.017261 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-04 | 0.03604 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-05 | 0.020209 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-05 | 0.0093231 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-05 | 0.014945 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-08-04 | 0.029204 | 10 | 0.01 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-05 | 0.019262 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-05 | 0.062549 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-08-04 | 0.051742 | 10 | 0.01 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-08-04 | 0.041136 | 10 | 0.01 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-08-06 | 0.037262 | 10 | 0.01 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-08-06 | 0.035347 | 10 | 0.01 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-08 | 0.029204 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-08-08 | 0.028999 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-08-03 | 0.039146 | 10 | 0.01 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-05 | 0.006835 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-06 | 0.01802 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-05 | 0.049088 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-06 | 0.037904 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-06 | 0.015534 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-06 | 0.029826 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-06 | 0.01802 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-05 | 0.020505 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-05 | 0.019884 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-06 | 0.017398 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-06 | 0.011185 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-06 | 0.024855 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-06 | 0.036661 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-06 | 0.024855 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-07 | 0.019262 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-06 | 0.0074564 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-06 | 0.019262 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-07 | 0.015138 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-06 | 0.024234 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-05 | 0.026098 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-06 | 0.024234 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-07 | 0.02608 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-08 | 0.028256 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-08 | 0.027786 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8004-01 | 2026-08-02 | 0.027561 | 10 | 0.01 | Arecibo | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7801-01 | 2026-08-02 | 0.070215 | 10 | 0.01 | Añasco | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7008-08 | 2026-08-02 | 0.028583 | 10 | 0.01 | Moca | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-03 | 0.02734 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-08-03 | 0.027575 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-03 | 0.027962 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-08-03 | 0.028432 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-04 | 0.038015 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-03 | 0.044117 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1342-04 | 2026-08-04 | 0.039899 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-03 | 0.034175 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-02 | 2026-08-03 | 0.045631 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-03 | 0.019509 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-03 | 0.071458 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1342-04 | 2026-08-03 | 0.018352 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-04 | 0.036832 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1342-04 | 2026-08-04 | 0.037742 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-03 | 0.031599 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-03 | 0.013705 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-03 | 0.032601 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-03 | 0.010302 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-03 | 0.0031934 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-03 | 0.024641 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-03 | 0.032313 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-03 | 0.0054629 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-03 | 0.0128 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-03 | 0.022773 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-03 | 0.033554 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-08-03 | 0.033775 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-03 | 0.024625 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-03 | 0.016223 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-03 | 0.037943 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-03 | 0.0098379 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-04 | 0.0075924 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-04 | 0.034634 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-03 | 0.022218 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2604-03 | 2026-08-03 | 0.062137 | 10 | 0.01 | Humacao | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-03 | 0.036486 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-03 | 0.026464 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2604-03 | 2026-08-03 | 0.062137 | 10 | 0.01 | Humacao | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-03 | 0.01096 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-03 | 0.031672 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-03 | 0.0062449 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-03 | 0.031069 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-03 | 0.0075746 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-03 | 0.012726 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-03 | 0.01331 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-03 | 0.018596 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-03 | 0.011273 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-03 | 0.0024703 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-04 | 0.0024703 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-03 | 0.031691 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-04 | 0.0072511 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-03 | 0.077805 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.022369 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.022991 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.028583 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.02816 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1343-03 | 2026-08-03 | 0.024234 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1343-03 | 2026-08-03 | 0.019884 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.030293 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.052041 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.017398 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.013049 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-04 | 0.031621 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1342-04 | 2026-08-04 | 0.031298 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-04 | 0.021852 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-04 | 0.016665 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-04 | 0.027924 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1342-04 | 2026-08-04 | 0.042735 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7801-01 | 2026-08-03 | 0.074565 | 10 | 0.01 | Añasco | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 4101-04 | 2026-08-07 | 0.041632 | 10 | 0.01 | Arroyo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-05 | 0.0065231 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-05 | 0.020689 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1342-04 | 2026-08-04 | 0.032328 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-05 | 0.03501 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-06 | 0.021127 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1342-04 | 2026-08-06 | 0.021127 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-04 | 0.044739 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-05 | 0.031515 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-05 | 0.0075856 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1343-03 | 2026-08-03 | 0.031069 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-05 | 0.032642 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-05 | 0.033303 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-06 | 0.0093206 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1342-04 | 2026-08-06 | 0.0093206 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-05 | 0.038692 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-05 | 0.02734 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-04 | 0.028583 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-05 | 0.026719 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1342-04 | 2026-08-04 | 0.028583 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-05 | 0.024234 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-06 | 0.019262 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-05 | 0.024855 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1342-04 | 2026-08-06 | 0.019262 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-06 | 0.028583 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-05 | 0.024855 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-06 | 0.024855 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1342-04 | 2026-08-06 | 0.025476 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-05 | 0.022991 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-05 | 0.0093206 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-06 | 0.022991 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1342-04 | 2026-08-06 | 0.023612 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-06 | 0.018641 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-05 | 0.021127 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1342-04 | 2026-08-06 | 0.014913 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-06 | 0.004971 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-05 | 0.023612 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-05 | 0.029204 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-05 | 0.027962 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-05 | 0.029204 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-05 | 0.02734 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-05 | 0.03169 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-05 | 0.019696 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1336-06 | 2026-08-03 | 0.034175 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-06 | 0.0192 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1342-04 | 2026-08-06 | 0.017561 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-06 | 0.013071 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1342-04 | 2026-08-06 | 0.014245 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-06 | 0.025476 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1342-04 | 2026-08-06 | 0.023612 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-06 | 0.037282 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1342-04 | 2026-08-06 | 0.037282 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-08-03 | 0.014913 | 10 | 0.01 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-05 | 0.033554 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-05 | 0.028583 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-05 | 0.005483 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3402-05 | 2026-08-03 | 0.085128 | 10 | 0.01 | Cayey | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-05 | 0.046711 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3402-05 | 2026-08-03 | 0.083885 | 10 | 0.01 | Cayey | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 3205-08 | 2026-08-04 | 0.023095 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1343-03 | 2026-08-04 | 0.031069 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 8401-04 | 2026-08-07 | 0.037904 | 10 | 0.01 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-05 | 0.03604 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-04 | 0.050331 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-08-04 | 0.013049 | 10 | 0.01 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-04 | 0.050331 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 8401-04 | 2026-08-07 | 0.012427 | 10 | 0.01 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-05 | 0.030222 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-05 | 0.0054545 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-05 | 0.02557 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-05 | 0.018641 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-05 | 0.014291 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-05 | 0.021512 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-05 | 0.025476 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.022369 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-04 | 0.040554 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-05 | 0.015205 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-04 | 0.0037282 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3501-03 | 2026-08-04 | 0.083264 | 10 | 0.01 | Aibonito | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-04 | 0.04101 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.024855 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.029204 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.034797 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.01116 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-05 | 0.029826 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-05 | 0.014135 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-05 | 0.016777 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-05 | 0.0059112 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-05 | 0.0036188 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-04 | 0.10439 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-05 | 0.014786 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-05 | 0.03169 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-05 | 0.027049 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 8401-04 | 2026-08-06 | 0.032933 | 10 | 0.01 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.029826 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-05 | 0.011684 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-05 | 0.0053833 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3501-03 | 2026-08-04 | 0.062759 | 10 | 0.01 | Aibonito | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-04 | 0.016879 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 8401-04 | 2026-08-06 | 0.033082 | 10 | 0.01 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 8401-04 | 2026-08-05 | 0.021748 | 10 | 0.01 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-07 | 0.022369 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-07 | 0.0074564 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 8401-04 | 2026-08-06 | 0.019884 | 10 | 0.01 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1336-06 | 2026-08-04 | 0.028583 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1346-02 | 2026-08-04 | 0.029155 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1330-01 | 2026-08-04 | 0.030559 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1346-02 | 2026-08-04 | 0.030447 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1330-01 | 2026-08-04 | 0.029204 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1346-02 | 2026-08-04 | 0.029826 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1330-01 | 2026-08-04 | 0.027962 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1346-02 | 2026-08-04 | 0.026719 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-04 | 0.024855 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1330-01 | 2026-08-04 | 0.028583 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1346-02 | 2026-08-04 | 0.027962 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1330-01 | 2026-08-04 | 0.027962 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-08-04 | 0.024234 | 10 | 0.01 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1346-02 | 2026-08-04 | 0.028583 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-07 | 0.034117 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-08-04 | 0.032604 | 10 | 0.01 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-08-07 | 0.032879 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-05 | 0.021748 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1330-01 | 2026-08-04 | 0.027962 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-05 | 0.010563 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-05 | 0.035418 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1346-02 | 2026-08-04 | 0.027962 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-05 | 0.0080778 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1330-01 | 2026-08-04 | 0.02734 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-05 | 0.02734 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-05 | 0.046603 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1343-03 | 2026-08-04 | 0.037282 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-05 | 0.012427 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-05 | 0.019884 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-05 | 0.011185 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-05 | 0.022103 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-05 | 0.0026769 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1330-01 | 2026-08-04 | 0.01414 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-05 | 0.025811 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 8401-04 | 2026-08-05 | 0.0099419 | 10 | 0.01 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-04 | 0.01367 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-05 | 0.0085218 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-05 | 0.016875 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-04 | 0.0031068 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-05 | 0.0065273 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1330-01 | 2026-08-04 | 0.0086992 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-05 | 0.015753 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3102-01 | 2026-08-07 | 0.013788 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1330-01 | 2026-08-04 | 0.011185 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-04 | 0.013614 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-07 | 0.051574 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1330-01 | 2026-08-04 | 0.017398 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-08-04 | 0.025476 | 10 | 0.01 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 8401-04 | 2026-08-05 | 0.025476 | 10 | 0.01 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1330-01 | 2026-08-04 | 0.0093206 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-05 | 0.011057 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1330-01 | 2026-08-04 | 0.018997 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-05 | 0.011404 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-05 | 0.0063386 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-05 | 0.023612 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-04 | 0.023605 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-05 | 0.048869 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1330-01 | 2026-08-04 | 0.013056 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-08-04 | 0.023734 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-05 | 0.027578 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1330-01 | 2026-08-04 | 0.016471 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2002-02 | 2026-08-05 | 0.033554 | 10 | 0.01 | Fajardo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-05 | 0.022369 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-05 | 0.018641 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-05 | 0.026098 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-05 | 0.049088 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-05 | 0.026377 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2002-02 | 2026-08-05 | 0.03169 | 10 | 0.01 | Fajardo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1330-01 | 2026-08-04 | 0.03215 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-04 | 0.021616 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-08-04 | 0.020777 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-04 | 0.008793 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1620-05 | 2026-08-05 | 0.047224 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-08-04 | 0.0094027 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-08-04 | 0.026719 | 10 | 0.01 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-06 | 0.03718 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1342-04 | 2026-08-06 | 0.035934 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-06 | 0.032516 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1342-04 | 2026-08-06 | 0.033798 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1342-04 | 2026-08-08 | 0.034865 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-04 | 0.028583 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-04 | 0.0086992 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-04 | 0.01367 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-04 | 0.04536 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-04 | 0.0086992 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-04 | 0.039146 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-04 | 0.017398 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-04 | 0.023612 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-04 | 0.024234 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-04 | 0.024234 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-04 | 0.023612 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1330-01 | 2026-08-04 | 0.030754 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-04 | 0.021127 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-04 | 0.026098 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-03 | 0.018855 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-07 | 0.032311 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-04 | 0.032933 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-04 | 0.03169 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1330-01 | 2026-08-04 | 0.0055924 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-04 | 0.016777 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-04 | 0.016156 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-08-04 | 0.045981 | 10 | 0.01 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-04 | 0.031069 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-04 | 0.032311 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-04 | 0.019262 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-04 | 0.024234 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-04 | 0.024234 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-04 | 0.024234 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-04 | 0.01802 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-04 | 0.018641 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-04 | 0.016156 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-08-04 | 0.017398 | 10 | 0.01 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-04 | 0.015534 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-08-05 | 0.020239 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-04 | 0.016777 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-04 | 0.019262 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-05 | 0.07705 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-05 | 0.047224 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-05 | 0.11904 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-05 | 0.019884 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-05 | 0.027962 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-05 | 0.022369 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-05 | 0.022991 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-05 | 0.029204 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1105-04 | 2026-08-05 | 0.020505 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-08-04 | 0.03262 | 10 | 0.01 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-05 | 0.024855 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-05 | 0.022991 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-05 | 0.034175 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.032933 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.039146 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.036661 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.04101 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.019262 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.016156 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.024234 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.020548 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.053546 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.0537 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-05 | 0.0089295 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-08-05 | 0.010458 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.014205 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-05 | 0.036411 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-08-05 | 0.036878 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.066123 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.017777 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.020001 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.018641 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.017398 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.034835 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.013988 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.028375 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-07 | 0.019262 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.024342 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.024222 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.019908 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.020133 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.015947 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-05 | 0.06338 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7504-02 | 2026-08-05 | 0.02734 | 10 | 0.01 | Isabela | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-05 | 0.033554 | 10 | 0.01 | Aguada | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.034175 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-06 | 0.036109 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.033554 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-06 | 0.024878 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.032311 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.024234 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.029826 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.036661 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.019884 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.018641 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.024855 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.021748 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.043496 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-06 | 0.033181 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.0093206 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-07 | 0.075296 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.027104 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.01367 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.05007 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.039421 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6801-01 | 2026-08-05 | 0.058673 | 10 | 0.01 | Hormigueros | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.015534 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.019884 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.020505 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.0093206 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.033223 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.014857 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-05 | 0.046416 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3501-03 | 2026-08-05 | 0.039802 | 10 | 0.01 | Aibonito | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3501-03 | 2026-08-05 | 0.030676 | 10 | 0.01 | Aibonito | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3501-03 | 2026-08-05 | 0.038782 | 10 | 0.01 | Aibonito | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3501-03 | 2026-08-05 | 0.038782 | 10 | 0.01 | Aibonito | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-02 | 2026-08-06 | 0.20114 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-08-06 | 0.0097566 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-08-06 | 0.0025938 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-08-06 | 0.0033606 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-08-06 | 0.001978 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-08-06 | 0.00067614 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-08-06 | 0.00053807 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-08-06 | 0.0018729 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-08-06 | 0.0084309 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-08-06 | 0.02734 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-08-06 | 0.018641 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-06 | 0.01688 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8404-02 | 2026-08-06 | 0.045006 | 10 | 0.01 | Manatí | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-08-06 | 0.024234 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-06 | 0.018304 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-06 | 0.019134 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-06 | 0.019059 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-08-06 | 0.0099419 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-06 | 0.022199 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-06 | 0.054059 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-06 | 0.023356 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-06 | 0.041632 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8302-04 | 2026-08-06 | 0.077955 | 10 | 0.01 | Jayuya | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-06 | 0.02725 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-06 | 0.025418 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1106-05 | 2026-08-06 | 0.024855 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-08-06 | 0.020505 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-07 | 0.030894 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-08-06 | 0.02536 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-07 | 0.026719 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-07 | 0.011185 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-08-06 | 0.01802 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-06 | 0.011825 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-08-06 | 0.025476 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-07 | 0.012427 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1106-05 | 2026-08-06 | 0.026719 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6101-05 | 2026-08-06 | 0.094448 | 10 | 0.01 | Añasco | Xperts | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-08-06 | 0.027962 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-07 | 0.025476 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1106-05 | 2026-08-06 | 0.02734 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6014-02 | 2026-08-05 | 0.12117 | 10 | 0.01 | Añasco | Xperts | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-08-06 | 0.022991 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1106-05 | 2026-08-06 | 0.022991 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-06 | 0.023612 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-08-06 | 0.01802 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-08-06 | 0.029826 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-06 | 0.0076091 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1106-05 | 2026-08-06 | 0.029826 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-08-06 | 0.021127 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1106-05 | 2026-08-06 | 0.021652 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-06 | 0.019212 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-07 | 0.010193 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-06 | 0.035534 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-08-06 | 0.0086992 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-06 | 0.019071 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-08-06 | 0.03604 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-07 | 0.024369 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-07 | 0.019915 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1106-05 | 2026-08-06 | 0.0343 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-06 | 0.013634 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-06 | 0.0063142 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-08-06 | 0.029204 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-07 | 0.02358 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1106-05 | 2026-08-06 | 0.029204 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-07 | 0.049028 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-07 | 0.022808 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-07 | 0.036603 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1106-05 | 2026-08-06 | 0.046603 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-08-06 | 0.03604 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1106-05 | 2026-08-06 | 0.034175 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-07 | 0.0085263 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-08-06 | 0.0096555 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-08-06 | 0.002478 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-08-06 | 0.0018907 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-08-06 | 0.0039858 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-08-06 | 0.0020564 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-08-06 | 0.00064564 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-08-06 | 0.00072936 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-08-06 | 0.031734 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-08-06 | 0.03604 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1106-05 | 2026-08-06 | 0.019884 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-08-06 | 0.011185 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-08-06 | 0.029204 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-08-06 | 0.032311 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-08-06 | 0.0093206 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-08-06 | 0.015394 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-08-06 | 0.030447 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1106-05 | 2026-08-06 | 0.041632 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-08-06 | 0.017683 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-08-06 | 0.030447 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1106-05 | 2026-08-06 | 0.030447 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-08-06 | 0.032933 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1106-05 | 2026-08-06 | 0.032933 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-08-06 | 0.027729 | 10 | 0.01 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-08-06 | 0.00074204 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-08-06 | 0.0028042 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-08-06 | 0.003483 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-08-06 | 0.0019525 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-08-06 | 0.00074204 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-08-06 | 0.00075436 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-08-06 | 0.018641 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1118-09 | 2026-08-06 | 0.01802 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8404-02 | 2026-08-06 | 0.042253 | 10 | 0.01 | Manatí | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-08 | 0.018641 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-07 | 0.018641 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-06 | 0.022586 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-06 | 0.04536 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-06 | 0.033554 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-06 | 0.039146 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-08-06 | 0.022369 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1652-02 | 2026-08-06 | 0.021127 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-08-06 | 0.024855 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-06 | 0.04351 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1652-02 | 2026-08-06 | 0.024234 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-08-06 | 0.028583 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1652-02 | 2026-08-06 | 0.027962 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-06 | 0.024162 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-08-06 | 0.025476 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-06 | 0.040925 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1652-02 | 2026-08-06 | 0.026098 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-06 | 0.027962 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-08-06 | 0.029826 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-06 | 0.037282 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1652-02 | 2026-08-06 | 0.028583 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1652-02 | 2026-08-06 | 0.021127 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-08-06 | 0.019884 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1652-02 | 2026-08-06 | 0.021127 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-08-06 | 0.024234 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1652-02 | 2026-08-06 | 0.032933 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-08-06 | 0.031029 | 10 | 0.01 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 4101-03 | 2026-08-07 | 0.025218 | 10 | 0.01 | Arroyo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 4101-03 | 2026-08-07 | 0.016935 | 10 | 0.01 | Arroyo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-02 | 2026-08-07 | 0.057311 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2803-02 | 2026-08-07 | 0.057787 | 10 | 0.01 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8104-02 | 2026-08-07 | 0.053438 | 10 | 0.01 | Utuado | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2803-02 | 2026-08-07 | 0.054681 | 10 | 0.01 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-08 | 0.026812 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-08 | 0.034175 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1342-04 | 2026-08-08 | 0.035418 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3201-02 | 2026-08-05 | 0.10625 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7301-01 | 2026-08-07 | 0.027506 | 10 | 0.01 | Rincón | Xperts | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-02 | 2026-08-07 | 0.087613 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-02 | 2026-08-07 | 0.054681 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-08-08 | 0.027755 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-08-08 | 0.023673 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-08-08 | 0.027755 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-08-08 | 0.027755 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-08-08 | 0.028331 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-08-08 | 0.029273 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-08-08 | 0.048467 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-08-08 | 0.012277 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-08-08 | 0.031069 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1336-06 | 2026-08-08 | 0.026719 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3301-02 | 2026-08-08 | 0.036745 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-08-08 | 0.019262 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-08-08 | 0.033575 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3301-02 | 2026-08-08 | 0.036745 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-08-08 | 0.026534 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8004-02 | 2026-08-08 | 0.040818 | 10 | 0.01 | Arecibo | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3301-02 | 2026-08-08 | 0.037875 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8004-02 | 2026-08-08 | 0.046594 | 10 | 0.01 | Arecibo | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-08-08 | 0.029548 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-08 | 0.036419 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-08-08 | 0.024047 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-08-08 | 0.028583 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-08-08 | 0.01041 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-08-08 | 0.032933 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-08-08 | 0.0038661 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-08-08 | 0.013049 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-08-08 | 0.02734 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-08-08 | 0.033554 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-08-08 | 0.020505 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2201-04 | 2026-08-08 | 0.048835 | 10 | 0.01 | Luquillo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-08-08 | 0.021712 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2305-02 | 2026-08-08 | 0.0501 | 10 | 0.01 | Luquillo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-08-08 | 0.021744 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-08-08 | 0.016125 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-08 | 0.024234 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1342-04 | 2026-08-08 | 0.026719 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-08 | 0.024855 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-08-08 | 0.012709 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-08 | 0.013985 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-08-08 | 0.017398 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-08-08 | 0.011185 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-08-08 | 0.029204 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-08-08 | 0.0062136 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-08 | 0.086874 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-08-08 | 0.027962 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-08-08 | 0.019262 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-08-08 | 0.021137 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-08-08 | 0.022647 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3501-03 | 2026-08-08 | 0.10998 | 10 | 0.01 | Aibonito | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-08-08 | 0.021966 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-08 | 0.024234 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1652-02 | 2026-08-08 | 0.043496 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1652-02 | 2026-08-08 | 0.03169 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1652-02 | 2026-08-08 | 0.032933 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1652-02 | 2026-08-08 | 0.050952 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1652-02 | 2026-08-08 | 0.023612 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-08-08 | 0.022369 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-08-08 | 0.016156 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-08-08 | 0.042253 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-08-08 | 0.041632 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2305-02 | 2026-08-08 | 0.020337 | 10 | 0.01 | Luquillo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-08-08 | 0.050952 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-08-08 | 0.046227 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1652-02 | 2026-08-08 | 0.045537 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-08-08 | 0.041697 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1652-03 | 2026-08-08 | 0.041487 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-08-08 | 0.055302 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1652-03 | 2026-08-08 | 0.033765 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-08-08 | 0.026098 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1652-03 | 2026-08-08 | 0.021748 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-08-08 | 0.026129 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1652-03 | 2026-08-08 | 0.025476 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1620-04 | 2026-08-08 | 0.02734 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1652-03 | 2026-08-08 | 0.026719 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5402-02 | 2026-08-08 | 0.047846 | 10 | 0.01 | Peñuelas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-08 | 0.029826 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-08 | 0.029826 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-08 | 0.029204 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-08 | 0.021748 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-08 | 0.021748 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-08 | 0.022612 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6801-03 | 2026-08-11 | 0.029826 | 10 | 0.01 | Cabo Rojo | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6801-03 | 2026-08-11 | 0.00094697 | 10 | 0.01 | Hormigueros | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7403-03 | 2026-08-11 | 0.12117 | 10 | 0.01 | San Sebastián | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7403-03 | 2026-08-13 | 0.035418 | 10 | 0.01 | San Sebastián | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-08-15 | 0.03604 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1109-05 | 2026-08-13 | 0.024234 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.16/7.20 | 6702-02 | 2026-08-12 | 0.10253 | 10 | 0.01 | Cabo Rojo | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1206-03 | 2026-08-12 | 0.024757 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 3205-08 | 2026-08-13 | 0.025002 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 3205-08 | 2026-08-13 | 0.034795 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5902-02 | 2026-08-13 | 0.052816 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5902-02 | 2026-08-13 | 0.128 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5902-02 | 2026-08-13 | 0.068862 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6801-03 | 2026-08-11 | 0.047846 | 10 | 0.01 | Cabo Rojo | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6801-03 | 2026-08-11 | 0.056545 | 10 | 0.01 | Hormigueros | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 4201-01 | 2026-08-13 | 0.022256 | 10 | 0.01 | Patillas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 4201-01 | 2026-08-13 | 0.024837 | 10 | 0.01 | Patillas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 4201-01 | 2026-08-13 | 0.026834 | 10 | 0.01 | Patillas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 4201-01 | 2026-08-10 | 0.036155 | 10 | 0.01 | Patillas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 4201-01 | 2026-08-10 | 0.041083 | 10 | 0.01 | Patillas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 4201-01 | 2026-08-10 | 0.026414 | 10 | 0.01 | Patillas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 4201-01 | 2026-08-10 | 0.024818 | 10 | 0.01 | Patillas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 4201-01 | 2026-08-11 | 0.036996 | 10 | 0.01 | Patillas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 4201-01 | 2026-08-10 | 0.04653 | 10 | 0.01 | Patillas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 4201-01 | 2026-08-11 | 0.049644 | 10 | 0.01 | Patillas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 4201-01 | 2026-08-11 | 0.033534 | 10 | 0.01 | Patillas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 4201-01 | 2026-08-12 | 0.032496 | 10 | 0.01 | Patillas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 4201-01 | 2026-08-12 | 0.038749 | 10 | 0.01 | Patillas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 4201-01 | 2026-08-12 | 0.046976 | 10 | 0.01 | Patillas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 4201-01 | 2026-08-12 | 0.044679 | 10 | 0.01 | Patillas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7403-03 | 2026-08-14 | 0.036447 | 10 | 0.01 | San Sebastián | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1519-04 | 2026-08-11 | 0.024234 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5801-04 | 2026-08-11 | 0.029826 | 10 | 0.01 | Juana Díaz | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-08-15 | 0.050952 | 10 | 0.01 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-08-14 | 0.036122 | 10 | 0.01 | Arecibo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-02 | 2026-08-13 | 0.034 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-02 | 2026-08-13 | 0.014913 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-02 | 2026-08-12 | 0.074398 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-02 | 2026-08-12 | 0.04576 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7402-01 | 2026-08-10 | 0.05903 | 10 | 0.01 | Camuy | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1646-02 | 2026-08-13 | 0.021748 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.16/7.20 | 6702-02 | 2026-08-10 | 0.039146 | 10 | 0.01 | Cabo Rojo | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7301-02 | 2026-08-12 | 0.027962 | 10 | 0.01 | Rincón | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7301-02 | 2026-08-12 | 0.019262 | 10 | 0.01 | Rincón | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1133-01 | 2026-08-13 | 0.022369 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7008-04 | 2026-08-12 | 0.00094697 | 10 | 0.01 | Aguada | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7008-04 | 2026-08-12 | 0.022683 | 10 | 0.01 | Aguada | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-13 | 0.02768 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-13 | 0.020155 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-13 | 0.022368 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-13 | 0.021727 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-13 | 0.021164 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-13 | 0.020555 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-13 | 0.01941 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 3205-08 | 2026-08-13 | 0.029023 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-10 | 0.02903 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-14 | 0.064577 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-13 | 0.050308 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-13 | 0.043032 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-13 | 0.02751 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-13 | 0.027917 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-13 | 0.040155 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-13 | 0.025468 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-13 | 0.02796 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-13 | 0.019333 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-13 | 0.017287 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-13 | 0.039146 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-13 | 0.027962 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-13 | 0.02734 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-13 | 0.03488 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-13 | 0.03834 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-13 | 0.024517 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-13 | 0.024936 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-13 | 0.032882 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-15 | 0.014913 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-13 | 0.033627 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 3205-08 | 2026-08-13 | 0.015472 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-13 | 0.011116 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-13 | 0.040389 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-13 | 0.022369 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-13 | 0.032311 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-08-13 | 0.026719 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-08-13 | 0.024073 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1704-03 | 2026-08-14 | 0.00094697 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-13 | 0.029826 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-13 | 0.035444 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-10 | 0.058409 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-11 | 0.11309 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-13 | 0.021127 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-13 | 0.0727 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7008-08 | 2026-08-14 | 0.019884 | 10 | 0.01 | Moca | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-14 | 0.049088 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-14 | 0.047224 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-13 | 0.03604 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8501-01 | 2026-08-12 | 0.020464 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8501-01 | 2026-08-12 | 0.024189 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8501-01 | 2026-08-12 | 0.036929 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8501-01 | 2026-08-12 | 0.020464 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 9101-01 | 2026-08-11 | 0.03604 | 10 | 0.01 | Vega Alta | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 9101-01 | 2026-08-11 | 0.04971 | 10 | 0.01 | Vega Alta | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 9101-01 | 2026-08-11 | 0.039768 | 10 | 0.01 | Vega Alta | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-10 | 0.047224 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-10 | 0.038525 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-10 | 0.039146 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-10 | 0.040389 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-14 | 0.034456 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-14 | 0.033145 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-11 | 0.0344 | 10 | 0.01 | Canóvanas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-13 | 0.034291 | 10 | 0.01 | Canóvanas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-13 | 0.022404 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-13 | 0.020287 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-13 | 0.022279 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-13 | 0.016492 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-13 | 0.023165 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-13 | 0.00094697 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-13 | 0.02047 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-13 | 0.00094697 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-14 | 0.038525 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1901-03 | 2026-08-11 | 0.021127 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1901-03 | 2026-08-11 | 0.019262 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1529-15 | 2026-08-11 | 0.019262 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-10 | 0.030447 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-11 | 0.17523 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-10 | 0.023612 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-14 | 0.030447 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-14 | 0.016156 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-11 | 0.044739 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-11 | 0.026098 | 10 | 0.01 | Juana Díaz | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-10 | 0.03169 | 10 | 0.01 | Juana Díaz | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-13 | 0.046603 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-10 | 0.022405 | 10 | 0.01 | Canóvanas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-10 | 0.025539 | 10 | 0.01 | Canóvanas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-12 | 0.036661 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-13 | 0.10812 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-14 | 0.1454 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-13 | 0.01367 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-14 | 0.09172 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-14 | 0.054059 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-14 | 0.040389 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-10 | 0.016777 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-10 | 0.02734 | 10 | 0.01 | Aguada | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-10 | 0.042253 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-10 | 0.030447 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-12 | 0.021486 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-12 | 0.019884 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-13 | 0.00094697 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-13 | 0.00094697 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-13 | 0.00094697 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-13 | 0.00094697 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-13 | 0.00094697 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-13 | 0.00094697 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-11 | 0.021127 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-10 | 0.025476 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8504-02 | 2026-08-12 | 0.027571 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8504-02 | 2026-08-11 | 0.02488 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-13 | 0.00094697 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-13 | 0.00094697 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8504-03 | 2026-08-10 | 0.029073 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8504-03 | 2026-08-10 | 0.044885 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-14 | 0.070836 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8501-01 | 2026-08-12 | 0.049088 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8501-01 | 2026-08-13 | 0.060894 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5501-03 | 2026-08-11 | 0.027962 | 10 | 0.01 | Guayanilla | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-13 | 0.00094697 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-13 | 0.00094697 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-13 | 0.00094697 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-13 | 0.00094697 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-13 | 0.00094697 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-13 | 0.00094697 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5501-03 | 2026-08-13 | 0.047846 | 10 | 0.01 | Guayanilla | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-13 | 0.00094697 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-13 | 0.0312 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-13 | 0.00094697 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5501-03 | 2026-08-13 | 0.032933 | 10 | 0.01 | Guayanilla | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-13 | 0.00094697 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-13 | 0.00094697 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-13 | 0.00094697 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-13 | 0.00094697 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5501-03 | 2026-08-11 | 0.053842 | 10 | 0.01 | Guayanilla | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-10 | 0.051574 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-10 | 0.037904 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-10 | 0.023612 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-10 | 0.027962 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-11 | 0.023612 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-10 | 0.091963 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-15 | 0.034298 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-08-12 | 0.028583 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-10 | 0.025476 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-08-12 | 0.030447 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-08-12 | 0.022369 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-08-12 | 0.024858 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-08-12 | 0.023559 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-08-12 | 0.019571 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-08-12 | 0.015788 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-10 | 0.041632 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-08-12 | 0.015296 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-10 | 0.032933 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-10 | 0.026098 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-08-12 | 0.024398 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-08-12 | 0.022458 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-08-12 | 0.020505 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-08-12 | 0.020517 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-08-12 | 0.02848 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-11 | 0.039768 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-12 | 0.023612 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-10 | 0.02734 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-02 | 2026-08-12 | 0.019884 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-02 | 2026-08-12 | 0.026719 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-12 | 0.024234 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-02 | 2026-08-12 | 0.024234 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-02 | 2026-08-12 | 0.037904 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-10 | 0.026098 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-13 | 0.026098 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-11 | 0.048467 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-03 | 2026-08-10 | 0.01825 | 10 | 0.01 | Manatí | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-10 | 0.031081 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.0063809 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-13 | 0.022369 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.04971 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.03604 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.020103 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.050952 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.06834 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.062759 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-13 | 0.028583 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.051574 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.043496 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.043496 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.023909 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.023909 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.039146 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.04536 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.0069438 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.027062 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.018775 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.035418 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-14 | 0.030447 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.010563 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.020505 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.027962 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.027962 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.034175 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.01802 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.020505 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.034175 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.025476 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.015061 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.038525 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.037282 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.03169 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.019262 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.043496 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.033554 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.060876 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-11 | 0.039768 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.026719 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.02734 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-14 | 0.015534 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-14 | 0.0018642 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-11 | 0.01802 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-14 | 0.016777 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-14 | 0.012627 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-13 | 0.025476 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-13 | 0.024234 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-10 | 0.016336 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1336-06 | 2026-08-13 | 0.033554 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1336-06 | 2026-08-11 | 0.036198 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-14 | 0.022369 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-14 | 0.024855 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-14 | 0.019884 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-13 | 0.0031068 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-14 | 0.019288 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.03265 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-13 | 0.0050816 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-13 | 0.0092714 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-10 | 0.035418 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-14 | 0.032311 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-14 | 0.031069 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-15 | 0.029826 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-15 | 0.020505 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-13 | 0.0054413 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-13 | 0.0034348 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-13 | 0.0044098 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-13 | 0.020466 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-13 | 0.043019 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-13 | 0.019455 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-13 | 0.02044 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-13 | 0.019262 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-10 | 0.027681 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-10 | 0.021127 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-10 | 0.029826 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-11 | 0.024234 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.035057 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.035839 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-08-15 | 0.026719 | 10 | 0.01 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 8401-03 | 2026-08-15 | 0.026719 | 10 | 0.01 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-15 | 0.037388 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.028031 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.10501 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-08-13 | 0.033554 | 10 | 0.01 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 8401-03 | 2026-08-13 | 0.032933 | 10 | 0.01 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.087613 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.044117 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.10253 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.050331 | 10 | 0.01 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.13546 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.048467 | 10 | 0.01 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.034797 | 10 | 0.01 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.036244 | 10 | 0.01 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.04101 | 10 | 0.01 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.066461 | 10 | 0.01 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.040389 | 10 | 0.01 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.04101 | 10 | 0.01 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.04101 | 10 | 0.01 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.04101 | 10 | 0.01 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.044137 | 10 | 0.01 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.0814 | 10 | 0.01 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.035418 | 10 | 0.01 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.034175 | 10 | 0.01 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.034175 | 10 | 0.01 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.040389 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7503-02 | 2026-08-15 | 0.030198 | 10 | 0.01 | Isabela | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.038525 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.017398 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.016156 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-08-14 | 0.026621 | 10 | 0.01 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.049088 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-08-12 | 0.027396 | 10 | 0.01 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-13 | 0.00094697 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-15 | 0.037904 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.049088 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.028583 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-10 | 0.046603 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.030447 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.008772 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.03296 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.027006 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.016477 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.021127 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.043496 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.033554 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.034797 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.034797 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-13 | 0.037904 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-11 | 0.049088 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-10 | 0.02734 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-10 | 0.047224 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.032933 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.019262 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.055923 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-10 | 0.031774 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-13 | 0.031774 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-13 | 0.023612 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-13 | 0.021127 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5007-01 | 2026-08-14 | 0.010555 | 10 | 0.01 | Ponce | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-13 | 0.046646 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5007-01 | 2026-08-14 | 0.047103 | 10 | 0.01 | Ponce | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-11 | 0.048653 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-11 | 0.013049 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-11 | 0.013049 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7503-02 | 2026-08-15 | 0.019894 | 10 | 0.01 | Isabela | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7503-02 | 2026-08-15 | 0.026719 | 10 | 0.01 | Isabela | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7503-02 | 2026-08-15 | 0.023612 | 10 | 0.01 | Isabela | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-13 | 0.029826 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-13 | 0.026098 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-13 | 0.029204 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-10 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-10 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-11 | 0.025683 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-10 | 0.045392 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-12 | 0.048467 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-15 | 0.024234 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8005-01 | 2026-08-13 | 0.094695 | 10 | 0.01 | Utuado | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7903-07 | 2026-08-11 | 0.054681 | 10 | 0.01 | Lares | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-10 | 0.032933 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-08-10 | 0.032962 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-14 | 0.062759 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-08-12 | 0.026624 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-08-12 | 0.026624 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-15 | 0.027962 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-10 | 0.03011 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-13 | 0.00094697 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.048467 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.029204 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.07705 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.020505 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.039768 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.035418 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.030447 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.056545 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.03604 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.035016 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.029276 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.050952 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.047224 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-14 | 0.12427 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-13 | 0.037904 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-13 | 0.071498 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-10 | 0.019884 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-10 | 0.023612 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-12 | 0.01802 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-12 | 0.016156 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-13 | 0.00094697 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-10 | 0.027962 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-13 | 0.00094697 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-11 | 0.029204 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-13 | 0.00094697 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-08-11 | 0.028428 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-10 | 0.02734 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-08-10 | 0.0282 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-10 | 0.030447 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-08-10 | 0.029591 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-13 | 0.00094697 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-12 | 0.03169 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-08-12 | 0.031843 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-13 | 0.00094697 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-13 | 0.00094697 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-13 | 0.00094697 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-13 | 0.00094697 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-11 | 0.013049 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-08-11 | 0.012773 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-13 | 0.00094697 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-13 | 0.00094697 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-13 | 0.00094697 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-13 | 0.00094697 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-13 | 0.015534 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-13 | 0.016777 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-13 | 0.013049 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-13 | 0.014291 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-13 | 0.016156 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-13 | 0.017398 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-13 | 0.00094697 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-12 | 0.014291 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-08-12 | 0.015294 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-13 | 0.00094697 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-13 | 0.00094697 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-12 | 0.024855 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-13 | 0.00094697 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-08-12 | 0.02513 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-13 | 0.00094697 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-13 | 0.00094697 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-12 | 0.016156 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-13 | 0.00094697 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-08-12 | 0.015565 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-12 | 0.011185 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-08-12 | 0.010492 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-13 | 0.00094697 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-13 | 0.013049 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-08-13 | 0.012131 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-13 | 0.036661 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-08-13 | 0.036443 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-13 | 0.032933 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-08-13 | 0.033042 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-13 | 0.00094697 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-10 | 0.029727 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-11 | 0.031502 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-11 | 0.02901 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-13 | 0.030111 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-11 | 0.017398 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-11 | 0.029204 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 5004-07 | 2026-08-12 | 0.03169 | 10 | 0.01 | Ponce | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5012-03 | 2026-08-12 | 0.032311 | 10 | 0.01 | Ponce | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.033554 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-13 | 0.025097 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-11 | 0.033554 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-13 | 0.033309 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-11 | 0.026719 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-11 | 0.013049 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-13 | 0.011098 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-10 | 0.010845 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-13 | 0.026264 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1342-04 | 2026-08-10 | 0.012195 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1342-04 | 2026-08-13 | 0.022525 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 3205-08 | 2026-08-14 | 0.064877 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6101-01 | 2026-08-12 | 0.029916 | 10 | 0.01 | Añasco | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6101-01 | 2026-08-12 | 0.038543 | 10 | 0.01 | Añasco | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6101-01 | 2026-08-12 | 0.028172 | 10 | 0.01 | Añasco | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6101-01 | 2026-08-12 | 0.044221 | 10 | 0.01 | Añasco | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6101-01 | 2026-08-12 | 0.043003 | 10 | 0.01 | Añasco | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 3205-08 | 2026-08-13 | 0.035774 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-14 | 0.021748 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-14 | 0.021748 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-11 | 0.03169 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.0093206 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.030447 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-13 | 0.024234 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-13 | 0.015534 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-13 | 0.01367 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-13 | 0.023612 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-11 | 0.051574 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-10 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1342-04 | 2026-08-10 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-14 | 0.00094697 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-14 | 0.022991 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-08-11 | 0.024234 | 10 | 0.01 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-14 | 0.00094697 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-14 | 0.022369 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8404-02 | 2026-08-15 | 0.028073 | 10 | 0.01 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1336-06 | 2026-08-15 | 0.047345 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1618-04 | 2026-08-15 | 0.022646 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1336-06 | 2026-08-15 | 0.033237 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1336-06 | 2026-08-15 | 0.033237 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-13 | 0.024234 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1618-04 | 2026-08-15 | 0.018924 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1336-06 | 2026-08-15 | 0.033237 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1618-04 | 2026-08-15 | 0.015302 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1657-02 | 2026-08-15 | 0.04707 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1618-04 | 2026-08-15 | 0.00094697 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1657-02 | 2026-08-14 | 0.04707 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1657-02 | 2026-08-15 | 0.031765 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1618-04 | 2026-08-15 | 0.031407 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-11 | 0.023728 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-10 | 0.026349 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-10 | 0.030002 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7301-02 | 2026-08-15 | 0.018811 | 10 | 0.01 | Rincón | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.0087184 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7301-02 | 2026-08-15 | 0.019262 | 10 | 0.01 | Rincón | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.023612 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.042253 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.046603 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.034797 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.01802 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.036661 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.02734 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 8801-02 | 2026-08-10 | 0.054681 | 10 | 0.01 | Morovis | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7504-02 | 2026-08-11 | 0.015135 | 10 | 0.01 | Isabela | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7504-02 | 2026-08-10 | 0.02734 | 10 | 0.01 | Isabela | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 8801-02 | 2026-08-10 | 0.036661 | 10 | 0.01 | Morovis | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7504-02 | 2026-08-10 | 0.011806 | 10 | 0.01 | Isabela | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7504-02 | 2026-08-13 | 0.067108 | 10 | 0.01 | Isabela | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-10 | 0.00094697 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-10 | 0.019884 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-10 | 0.019884 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-12 | 0.014661 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-13 | 0.03604 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-13 | 0.033554 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.031069 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-11 | 0.01802 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-11 | 0.027962 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-14 | 0.072081 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3007-03 | 2026-08-11 | 0.026719 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 8801-02 | 2026-08-12 | 0.01668 | 10 | 0.01 | Morovis | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 8801-02 | 2026-08-14 | 0.01802 | 10 | 0.01 | Morovis | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 8801-02 | 2026-08-10 | 0.00094697 | 10 | 0.01 | Morovis | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.014913 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.01802 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.016156 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.023612 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.016777 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.024234 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.021748 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-10 | 0.027117 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.015534 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-10 | 0.019931 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.014291 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-11 | 0.026687 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.016777 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.021748 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.024234 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.019262 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2305-02 | 2026-08-11 | 0.028647 | 10 | 0.01 | Luquillo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2305-02 | 2026-08-11 | 0.028647 | 10 | 0.01 | Luquillo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2305-02 | 2026-08-11 | 0.024363 | 10 | 0.01 | Luquillo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2002-03 | 2026-08-11 | 0.024648 | 10 | 0.01 | Luquillo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2604-01 | 2026-08-13 | 0.031892 | 10 | 0.01 | Humacao | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2604-01 | 2026-08-12 | 0.033012 | 10 | 0.01 | Humacao | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2604-01 | 2026-08-12 | 0.028879 | 10 | 0.01 | Humacao | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2604-01 | 2026-08-12 | 0.027326 | 10 | 0.01 | Humacao | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2604-01 | 2026-08-12 | 0.027842 | 10 | 0.01 | Humacao | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2604-01 | 2026-08-12 | 0.030177 | 10 | 0.01 | Humacao | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2604-01 | 2026-08-13 | 0.018421 | 10 | 0.01 | Humacao | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2604-01 | 2026-08-12 | 0.02635 | 10 | 0.01 | Humacao | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2604-01 | 2026-08-12 | 0.031328 | 10 | 0.01 | Humacao | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2604-01 | 2026-08-13 | 0.033797 | 10 | 0.01 | Humacao | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2604-01 | 2026-08-13 | 0.025476 | 10 | 0.01 | Humacao | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2604-01 | 2026-08-12 | 0.026098 | 10 | 0.01 | Humacao | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1336-06 | 2026-08-11 | 0.02734 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2604-01 | 2026-08-12 | 0.085128 | 10 | 0.01 | Humacao | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-10 | 0.03293 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-10 | 0.011001 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1342-04 | 2026-08-10 | 0.032933 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2604-01 | 2026-08-12 | 0.021127 | 10 | 0.01 | Humacao | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-10 | 0.013134 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-10 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-10 | 0.021062 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2604-01 | 2026-08-12 | 0.030635 | 10 | 0.01 | Humacao | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8104-02 | 2026-08-15 | 0.025188 | 10 | 0.01 | Utuado | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-10 | 0.01842 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-10 | 0.015027 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-10 | 0.027921 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-10 | 0.005204 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8404-04 | 2026-08-14 | 0.04101 | 10 | 0.01 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2604-01 | 2026-08-12 | 0.034797 | 10 | 0.01 | Humacao | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2604-01 | 2026-08-12 | 0.016777 | 10 | 0.01 | Humacao | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2604-01 | 2026-08-12 | 0.035418 | 10 | 0.01 | Humacao | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8404-04 | 2026-08-14 | 0.034797 | 10 | 0.01 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8404-04 | 2026-08-15 | 0.039146 | 10 | 0.01 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2604-01 | 2026-08-12 | 0.030447 | 10 | 0.01 | Humacao | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2604-01 | 2026-08-12 | 0.046603 | 10 | 0.01 | Humacao | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 8801-02 | 2026-08-13 | 0.040137 | 10 | 0.01 | Morovis | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2604-01 | 2026-08-12 | 0.03169 | 10 | 0.01 | Humacao | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 8801-02 | 2026-08-11 | 0.031069 | 10 | 0.01 | Morovis | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 8801-02 | 2026-08-13 | 0.04101 | 10 | 0.01 | Morovis | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 8801-02 | 2026-08-12 | 0.036661 | 10 | 0.01 | Morovis | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 8801-02 | 2026-08-11 | 0.01802 | 10 | 0.01 | Morovis | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8001-01 | 2026-08-09 | 0.063177 | 10 | 0.01 | Arecibo | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7601-03 | 2026-08-09 | 0.04971 | 10 | 0.01 | Camuy | Xperts | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1345-01 | 2026-08-11 | 0.012625 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1346-05 | 2026-08-10 | 0.015541 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1345-03 | 2026-08-10 | 0.021402 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.037904 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.025476 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.014913 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.026719 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.014606 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-08-12 | 0.064623 | 10 | 0.01 | Arecibo | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.03604 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5817-01 | 2026-08-10 | 0.024197 | 10 | 0.01 | Ponce | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-08-12 | 0.017398 | 10 | 0.01 | Arecibo | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-08-12 | 0.026719 | 10 | 0.01 | Arecibo | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-08-12 | 0.019546 | 10 | 0.01 | Arecibo | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-08-12 | 0.052195 | 10 | 0.01 | Arecibo | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 3006-02 | 2026-08-10 | 0.018641 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 9801-01 | 2026-08-10 | 0.018362 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 9801-01 | 2026-08-10 | 0.045353 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-13 | 0.037904 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-13 | 0.040389 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 9801-01 | 2026-08-10 | 0.023684 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-10 | 0.032933 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 9004-08 | 2026-08-10 | 0.0047057 | 10 | 0.01 | Vega Baja | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1345-01 | 2026-08-10 | 0.033443 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1345-05 | 2026-08-10 | 0.02823 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 9801-01 | 2026-08-10 | 0.027446 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-10 | 0.030253 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8104-02 | 2026-08-15 | 0.021966 | 10 | 0.01 | Utuado | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 9801-01 | 2026-08-10 | 0.034292 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-10 | 0.0099419 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 9004-08 | 2026-08-14 | 0.049569 | 10 | 0.01 | Vega Baja | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.021748 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.017398 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.024234 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.021127 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.014291 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.016156 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.024234 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.024855 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-08-10 | 0.039146 | 10 | 0.01 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.023612 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.016156 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-12 | 0.026098 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-12 | 0.03604 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 9801-01 | 2026-08-10 | 0.015403 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-10 | 0.13919 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-02 | 2026-08-10 | 0.093206 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.01367 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1336-08 | 2026-08-10 | 0.0064657 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.016156 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-10 | 0.017091 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.024234 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-10 | 0.02734 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-11 | 0.046605 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-11 | 0.050759 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1901-03 | 2026-08-11 | 0.029826 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-08-11 | 0.012427 | 10 | 0.01 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-11 | 0.024049 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-11 | 0.060588 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-11 | 0.032933 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-11 | 0.014316 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-11 | 0.022185 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-11 | 0.014316 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.044117 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-11 | 0.022335 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-11 | 0.028583 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 8801-02 | 2026-08-15 | 0.034797 | 10 | 0.01 | Morovis | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-13 | 0.16094 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 8801-02 | 2026-08-15 | 0.024855 | 10 | 0.01 | Morovis | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.065244 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.025476 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.019884 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.0099419 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.024234 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.022991 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.024855 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.012427 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.022369 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 8801-02 | 2026-08-14 | 0.029826 | 10 | 0.01 | Morovis | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.028583 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.030747 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.025476 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.014913 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.027962 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.024855 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-11 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-11 | 0.032311 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-13 | 0.044739 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.023612 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-13 | 0.032311 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-13 | 0.021748 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-11 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-11 | 0.02734 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-11 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 8801-02 | 2026-08-12 | 0.016777 | 10 | 0.01 | Morovis | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-11 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-11 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-11 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-11 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-15 | 0.015232 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.024855 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.017398 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7008-08 | 2026-08-12 | 0.04971 | 10 | 0.01 | Moca | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.016156 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7008-08 | 2026-08-12 | 0.02883 | 10 | 0.01 | Moca | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-12 | 0.029826 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-12 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-14 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-14 | 0.032933 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1203-02 | 2026-08-14 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-14 | 0.0074564 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1203-02 | 2026-08-14 | 0.033554 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-14 | 0.024855 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1203-02 | 2026-08-14 | 0.025476 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-14 | 0.025476 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1203-02 | 2026-08-14 | 0.024234 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-14 | 0.020695 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1707-05 | 2026-08-11 | 0.031611 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1203-02 | 2026-08-14 | 0.022899 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-14 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1707-05 | 2026-08-11 | 0.040988 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-14 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-14 | 0.01802 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-14 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-14 | 0.025476 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-12 | 0.013988 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-12 | 0.075548 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-12 | 0.09925 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-13 | 0.13298 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-13 | 0.15489 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-13 | 0.027962 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-13 | 0.033554 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1203-02 | 2026-08-13 | 0.033554 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-13 | 0.026719 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-12 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2201-04 | 2026-08-11 | 0.057166 | 10 | 0.01 | Río Grande | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1203-02 | 2026-08-12 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-12 | 0.021127 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1203-02 | 2026-08-12 | 0.022369 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-08-11 | 0.019133 | 10 | 0.01 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-13 | 0.027962 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1203-02 | 2026-08-13 | 0.026719 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-12 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1203-02 | 2026-08-12 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-08-11 | 0.014712 | 10 | 0.01 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 7505-05 | 2026-08-11 | 0.022202 | 10 | 0.01 | Isabela | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.023612 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.019262 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.024855 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.026098 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1206-03 | 2026-08-12 | 0.030033 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1203-03 | 2026-08-12 | 0.030447 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1206-03 | 2026-08-12 | 0.025166 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1203-03 | 2026-08-12 | 0.023612 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1203-03 | 2026-08-12 | 0.014291 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1206-03 | 2026-08-12 | 0.014525 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1206-03 | 2026-08-12 | 0.026767 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-14 | 0.022991 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1203-03 | 2026-08-12 | 0.025476 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-13 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1203-03 | 2026-08-12 | 0.024855 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1203-02 | 2026-08-13 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-02 | 2026-08-12 | 0.0006214 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1206-03 | 2026-08-12 | 0.019955 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1203-03 | 2026-08-12 | 0.025476 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1203-03 | 2026-08-12 | 0.024855 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-02 | 2026-08-12 | 0.026098 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1206-03 | 2026-08-12 | 0.026473 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7901-01 | 2026-08-12 | 0.15659 | 10 | 0.01 | Lares | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2305-02 | 2026-08-12 | 0.028477 | 10 | 0.01 | Luquillo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1203-03 | 2026-08-12 | 0.022369 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-02 | 2026-08-12 | 0.02734 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1203-03 | 2026-08-12 | 0.021748 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2002-03 | 2026-08-12 | 0.0281 | 10 | 0.01 | Luquillo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3401-02 | 2026-08-12 | 0.024234 | 10 | 0.01 | Cayey | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5501-04 | 2026-08-12 | 0.076063 | 10 | 0.01 | Guayanilla | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-14 | 0.034609 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1334-01 | 2026-08-14 | 0.021736 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1334-01 | 2026-08-14 | 0.01672 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 8801-04 | 2026-08-12 | 0.07314 | 10 | 0.01 | Morovis | Xperts | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-14 | 0.024855 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3401-02 | 2026-08-12 | 0.028583 | 10 | 0.01 | Cayey | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1334-01 | 2026-08-14 | 0.024719 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-14 | 0.0054169 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-14 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1203-02 | 2026-08-14 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-13 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1203-02 | 2026-08-14 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-12 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1203-02 | 2026-08-12 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-12 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1203-02 | 2026-08-12 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-12 | 0.0080778 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1203-02 | 2026-08-12 | 0.0074564 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-12 | 0.014913 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1203-02 | 2026-08-12 | 0.014291 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.16/7.20 | 6601-03 | 2026-08-12 | 0.1162 | 10 | 0.01 | Lajas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.16/7.20 | 6601-03 | 2026-08-12 | 0.060894 | 10 | 0.01 | Lajas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3401-02 | 2026-08-12 | 0.040389 | 10 | 0.01 | Cayey | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-13 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-13 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1203-02 | 2026-08-14 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-13 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-13 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-13 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-13 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-13 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-13 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-13 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3401-02 | 2026-08-12 | 0.044739 | 10 | 0.01 | Cayey | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-13 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-03 | 2026-08-11 | 0.031069 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7504-02 | 2026-08-13 | 0.034234 | 10 | 0.01 | Isabela | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3401-02 | 2026-08-12 | 0.075807 | 10 | 0.01 | Cayey | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3401-02 | 2026-08-12 | 0.040389 | 10 | 0.01 | Cayey | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-14 | 0.034567 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-14 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1707-04 | 2026-08-14 | 0.00094697 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-14 | 0.033554 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-14 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3102-01 | 2026-08-12 | 0.024234 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.016156 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.021748 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.022991 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.014913 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.01802 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.039167 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.026098 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-12 | 0.040034 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.025476 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.026098 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.017398 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.021748 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.023612 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.022369 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.023612 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.023612 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.022991 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.023612 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.023612 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.022991 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.023612 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.021127 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.021127 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 8801-04 | 2026-08-12 | 0.026719 | 10 | 0.01 | Morovis | Xperts | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.021748 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.016777 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-12 | 0.048467 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-02 | 2026-08-12 | 0.019884 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.18384 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2906-04 | 2026-08-13 | 0.025476 | 10 | 0.01 | Yabucoa | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2906-04 | 2026-08-13 | 0.038617 | 10 | 0.01 | Yabucoa | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2906-04 | 2026-08-13 | 0.038617 | 10 | 0.01 | Yabucoa | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.044117 | 10 | 0.01 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1330-01 | 2026-08-14 | 0.029362 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-13 | 0.02162 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-13 | 0.026926 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1719-15 | 2026-08-14 | 0.036729 | 10 | 0.01 | Toa Alta | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5501-03 | 2026-08-13 | 0.056545 | 10 | 0.01 | Guayanilla | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3302-03 | 2026-08-13 | 0.044739 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-13 | 0.024614 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-13 | 0.026098 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-13 | 0.03169 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-13 | 0.050952 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-13 | 0.0071725 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-13 | 0.032933 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-02 | 2026-08-12 | 0.018641 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-08-15 | 0.031267 | 10 | 0.01 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-08-15 | 0.024323 | 10 | 0.01 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2701-03 | 2026-08-15 | 0.032311 | 10 | 0.01 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2701-03 | 2026-08-15 | 0.027962 | 10 | 0.01 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2701-03 | 2026-08-15 | 0.041632 | 10 | 0.01 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-14 | 0.022369 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1708-03 | 2026-08-15 | 0.023612 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2005-10 | 2026-08-14 | 0.044926 | 10 | 0.01 | Fajardo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1719-15 | 2026-08-14 | 0.036729 | 10 | 0.01 | Toa Alta | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-14 | 0.0088316 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-08-15 | 0.031063 | 10 | 0.01 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1330-04 | 2026-08-15 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-14 | 0.021603 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-08-15 | 0.029624 | 10 | 0.01 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-14 | 0.0022886 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-14 | 0.011806 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-14 | 0.026054 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.037904 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-08-14 | 0.031865 | 10 | 0.01 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.042875 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.044117 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-14 | 0.018089 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.022369 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-14 | 0.0084964 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.015534 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.019884 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.023612 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.015534 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.0099419 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 9405-05 | 2026-08-14 | 0.039289 | 10 | 0.01 | Toa Alta | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.0099419 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.0093206 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.006835 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.034175 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.029204 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.12427 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.054059 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-14 | 0.054059 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3401-02 | 2026-08-12 | 0.05903 | 10 | 0.01 | Cayey | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 9405-05 | 2026-08-14 | 0.039962 | 10 | 0.01 | Toa Alta | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3401-02 | 2026-08-12 | 0.066487 | 10 | 0.01 | Cayey | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3007-03 | 2026-08-14 | 0.03169 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5817-02 | 2026-08-14 | 0.033554 | 10 | 0.01 | Ponce | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3007-03 | 2026-08-14 | 0.022369 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8104-02 | 2026-08-15 | 0.021229 | 10 | 0.01 | Utuado | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 9405-05 | 2026-08-15 | 0.038288 | 10 | 0.01 | Toa Alta | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1719-15 | 2026-08-14 | 0.0422 | 10 | 0.01 | Toa Alta | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1719-15 | 2026-08-14 | 0.065126 | 10 | 0.01 | Toa Alta | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7303-01 | 2026-08-15 | 0.024913 | 10 | 0.01 | Aguada | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5817-02 | 2026-08-14 | 0.034175 | 10 | 0.01 | Ponce | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6201-01 | 2026-08-14 | 0.16404 | 10 | 0.01 | Las Marías | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3301-02 | 2026-08-15 | 0.042253 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3301-02 | 2026-08-15 | 0.032933 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6008-02 | 2026-08-15 | 0.0727 | 10 | 0.01 | Mayaguez | Xperts | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3301-02 | 2026-08-15 | 0.02734 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6008-02 | 2026-08-15 | 0.055302 | 10 | 0.01 | Mayaguez | Xperts | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6008-02 | 2026-08-15 | 0.055302 | 10 | 0.01 | Mayaguez | Xperts | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6008-02 | 2026-08-15 | 0.062759 | 10 | 0.01 | Mayaguez | Xperts | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5304-01 | 2026-08-15 | 0.056545 | 10 | 0.01 | Yauco | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6008-02 | 2026-08-15 | 0.060894 | 10 | 0.01 | Mayaguez | Xperts | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6008-02 | 2026-08-15 | 0.052816 | 10 | 0.01 | Mayaguez | Xperts | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5304-01 | 2026-08-15 | 0.12179 | 10 | 0.01 | Yauco | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6008-02 | 2026-08-15 | 0.052195 | 10 | 0.01 | Mayaguez | Xperts | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1201-02 | 2026-08-15 | 0.036661 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5602-02 | 2026-08-15 | 0.054681 | 10 | 0.01 | Guánica | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3401-02 | 2026-08-14 | 0.024855 | 10 | 0.01 | Cayey | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6012-02 | 2026-08-14 | 0.15224 | 10 | 0.01 | Mayaguez | Xperts | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5817-02 | 2026-08-15 | 0.026354 | 10 | 0.01 | Ponce | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2001-01 | 2026-08-15 | 0.022395 | 10 | 0.01 | Fajardo | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2001-01 | 2026-08-15 | 0.03045 | 10 | 0.01 | Fajardo | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2001-01 | 2026-08-15 | 0.025317 | 10 | 0.01 | Fajardo | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2001-01 | 2026-08-15 | 0.015191 | 10 | 0.01 | Fajardo | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3007-03 | 2026-08-15 | 0.037282 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2001-01 | 2026-08-15 | 0.023871 | 10 | 0.01 | Fajardo | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-08-14 | 0.033298 | 10 | 0.01 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7802-01 | 2026-08-20 | 0.070836 | 10 | 0.01 | San Sebastián | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-08-22 | 0.021127 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5021-01 | 2026-08-20 | 0.044117 | 10 | 0.01 | Peñuelas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-02 | 2026-08-22 | 0.0027758 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.16/7.20 | 6702-02 | 2026-08-20 | 0.04536 | 10 | 0.01 | Cabo Rojo | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.16/7.20 | 6702-02 | 2026-08-20 | 0.051574 | 10 | 0.01 | San Germán | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1657-02 | 2026-08-17 | 0.035274 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.16/7.20 | 6702-02 | 2026-08-20 | 0.027962 | 10 | 0.01 | Cabo Rojo | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.16/7.20 | 6702-02 | 2026-08-20 | 0.045981 | 10 | 0.01 | Cabo Rojo | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.16/7.20 | 6702-02 | 2026-08-20 | 0.052195 | 10 | 0.01 | Cabo Rojo | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1330-01 | 2026-08-17 | 0.02734 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1924-02 | 2026-08-20 | 0.027558 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1529-13 | 2026-08-20 | 0.027354 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1529-13 | 2026-08-20 | 0.02347 | 10 | 0.01 | GUAYNABO | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1529-13 | 2026-08-20 | 0.016067 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1529-13 | 2026-08-20 | 0.028583 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5001-02 | 2026-08-19 | 0.032311 | 10 | 0.01 | Ponce | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5001-02 | 2026-08-19 | 0.032311 | 10 | 0.01 | Ponce | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5001-02 | 2026-08-19 | 0.032933 | 10 | 0.01 | Ponce | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2404-05 | 2026-08-22 | 0.033554 | 10 | 0.01 | Loíza | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 4003-01 | 2026-08-21 | 0.027302 | 10 | 0.01 | Guayama | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 4003-01 | 2026-08-18 | 0.028658 | 10 | 0.01 | Guayama | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 4003-01 | 2026-08-18 | 0.023527 | 10 | 0.01 | Guayama | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 4003-01 | 2026-08-18 | 0.027475 | 10 | 0.01 | Guayama | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 4003-01 | 2026-08-18 | 0.026859 | 10 | 0.01 | Guayama | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 4003-01 | 2026-08-18 | 0.034507 | 10 | 0.01 | Guayama | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 4003-01 | 2026-08-22 | 0.029204 | 10 | 0.01 | Guayama | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 4003-01 | 2026-08-18 | 0.037817 | 10 | 0.01 | Guayama | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 4003-01 | 2026-08-18 | 0.037741 | 10 | 0.01 | Guayama | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 4003-01 | 2026-08-21 | 0.031568 | 10 | 0.01 | Guayama | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-02 | 2026-08-22 | 0.041632 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2402-02 | 2026-08-18 | 0.027647 | 10 | 0.01 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2402-02 | 2026-08-18 | 0.016555 | 10 | 0.01 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-02 | 2026-08-22 | 0.028759 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-02 | 2026-08-22 | 0.03604 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.16/7.20 | 6702-02 | 2026-08-19 | 0.039146 | 10 | 0.01 | Cabo Rojo | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-20 | 0.038525 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-20 | 0.036661 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-21 | 0.046603 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-17 | 0.026719 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-20 | 0.026719 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-20 | 0.023612 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-20 | 0.018641 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-20 | 0.028583 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-20 | 0.024855 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-20 | 0.01802 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-20 | 0.024234 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-20 | 0.019262 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-20 | 0.026719 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-20 | 0.029204 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-20 | 0.01802 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-20 | 0.026719 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-20 | 0.02734 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-20 | 0.016777 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-20 | 0.029204 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-20 | 0.011806 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-20 | 0.022369 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-20 | 0.03169 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-20 | 0.026719 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-20 | 0.024234 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-20 | 0.028583 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-20 | 0.026098 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-20 | 0.017398 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-20 | 0.028583 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-20 | 0.024234 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-20 | 0.024234 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-20 | 0.017398 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-20 | 0.025476 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-20 | 0.024234 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-20 | 0.026098 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-20 | 0.013907 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-20 | 0.023612 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-20 | 0.020648 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-20 | 0.006835 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-20 | 0.029826 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-20 | 0.018641 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-18 | 0.053438 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-20 | 0.02124 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-20 | 0.026281 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-17 | 0.038525 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-20 | 0.022156 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-20 | 0.028676 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-20 | 0.032311 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-20 | 0.015293 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-20 | 2 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-22 | 0.034175 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-22 | 0.044117 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2404-06 | 2026-08-19 | 0.026569 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-20 | 0.027337 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-20 | 0.017784 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-17 | 0.030447 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-17 | 0.032933 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-17 | 0.043758 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-18 | 0.028144 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-19 | 0.047145 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-20 | 0.043432 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-20 | 0.045201 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-20 | 0.044175 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8504-01 | 2026-08-20 | 0.035019 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8504-01 | 2026-08-20 | 0.035326 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8504-01 | 2026-08-20 | 0.026621 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8504-01 | 2026-08-20 | 0.016543 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8504-01 | 2026-08-20 | 0.037438 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8504-01 | 2026-08-20 | 0.020764 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8504-01 | 2026-08-20 | 0.038927 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8504-01 | 2026-08-20 | 0.038202 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8504-01 | 2026-08-20 | 0.032191 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-21 | 0.036661 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-19 | 0.03604 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7702-02 | 2026-08-19 | 0.040313 | 10 | 0.01 | Hatillo | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7702-02 | 2026-08-18 | 0.05088 | 10 | 0.01 | Hatillo | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-21 | 0.019262 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-21 | 0.016156 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-21 | 0.022369 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-21 | 0.0074564 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-08-18 | 0.056545 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-08-18 | 0.057166 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-20 | 0.03289 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-18 | 0.038839 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-20 | 0.037645 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-21 | 0.03604 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-21 | 0.038525 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-20 | 0.048479 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-08-20 | 0.048574 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-18 | 0.06824 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-21 | 0.054059 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-08-20 | 0.028302 | 10 | 0.01 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-19 | 0.044739 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-18 | 0.025476 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-18 | 0.011083 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-19 | 0.027962 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-20 | 0.034005 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-20 | 0.013049 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-21 | 0.034175 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-21 | 0.024234 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-21 | 0.025476 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-21 | 0.022991 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-18 | 0.029826 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-18 | 0.020075 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-20 | 0.020782 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-20 | 0.020278 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5501-03 | 2026-08-17 | 0.038525 | 10 | 0.01 | Guayanilla | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5501-03 | 2026-08-18 | 0.040069 | 10 | 0.01 | Guayanilla | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5501-03 | 2026-08-21 | 0.030447 | 10 | 0.01 | Guayanilla | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-08-19 | 0.026037 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-20 | 0.03362 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-20 | 0.03169 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-20 | 0.053438 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-21 | 0.030447 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-19 | 0.049088 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-21 | 0.029826 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-21 | 0.026719 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-18 | 0.019632 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-21 | 0.022272 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-18 | 0.0079523 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-20 | 0.027764 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-20 | 0.041928 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-18 | 0.046603 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-21 | 0.082859 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-19 | 0.033916 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-21 | 0.004971 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.02734 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.03169 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.019262 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-20 | 0.01802 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-08-19 | 0.047846 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-08-19 | 0.047846 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.027062 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.018775 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.016686 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.020505 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-20 | 0.026719 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-20 | 0.017398 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-20 | 0.033554 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-21 | 0.037904 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-20 | 0.024234 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-20 | 0.018641 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-20 | 0.025476 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.036353 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.065244 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.029826 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.04101 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.041834 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-17 | 0.022991 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-21 | 0.023612 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-20 | 0.01367 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-20 | 0.014291 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-20 | 0.011185 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-20 | 0.0024854 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-20 | 0.0086992 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-20 | 0.029608 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-20 | 0.015143 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-20 | 0.016502 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-08-18 | 0.033554 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1336-06 | 2026-08-17 | 0.035418 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-20 | 0.017363 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-20 | 0.015563 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-20 | 0.038066 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-20 | 0.016838 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-20 | 0.021943 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-20 | 0.040389 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-20 | 0.019223 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-20 | 0.042016 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-20 | 0.040655 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-20 | 0.020505 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-20 | 0.020505 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-20 | 0.034175 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-20 | 0.034175 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-20 | 0.032311 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-20 | 0.016777 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-20 | 0.021127 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-20 | 0.018641 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-20 | 0.024855 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-20 | 0.03604 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-20 | 0.019262 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-20 | 0.0074564 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-20 | 0.023612 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-20 | 0.01802 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-20 | 0.025404 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-17 | 0.036661 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-20 | 0.025341 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-20 | 0.011508 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-20 | 0.00311 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-20 | 0.0024854 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-20 | 0.03604 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-20 | 0.034175 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1346-03 | 2026-08-19 | 0.018641 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-20 | 0.025476 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-20 | 0.014291 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-20 | 0.023938 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-20 | 0.020625 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-18 | 0.035418 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-20 | 0.047846 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-20 | 0.037282 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-20 | 0.011806 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-22 | 0.037282 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-22 | 0.027962 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-22 | 0.014291 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-20 | 0.017398 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-08-20 | 0.031069 | 10 | 0.01 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 8401-03 | 2026-08-20 | 0.029204 | 10 | 0.01 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-08-20 | 0.02734 | 10 | 0.01 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 8401-03 | 2026-08-20 | 0.02734 | 10 | 0.01 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-21 | 0.020707 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.019262 | 10 | 0.01 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 9103-01 | 2026-08-21 | 0.034175 | 10 | 0.01 | Dorado | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-19 | 0.048467 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-08-19 | 0.019738 | 10 | 0.01 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-08-19 | 0.017814 | 10 | 0.01 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-17 | 0.03163 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-20 | 0.028844 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-20 | 0.036626 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-18 | 6.8063e-06 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-19 | 0.042253 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-19 | 0.047224 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-20 | 0.020989 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-19 | 0.015975 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-20 | 0.039146 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-20 | 0.018641 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-20 | 0.012427 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-20 | 0.025086 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-20 | 0.025285 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-17 | 0.13919 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-18 | 0.059652 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-20 | 0.034175 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-20 | 0.039146 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-20 | 0.025476 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-21 | 0.039728 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-18 | 0.13049 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-18 | 0.10253 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-20 | 0.022369 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-20 | 0.042316 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-20 | 0.03679 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.026098 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.051817 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.029204 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.024234 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.024234 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-19 | 0.050331 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-19 | 0.034797 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-22 | 0.02661 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-19 | 0.048467 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-19 | 0.037904 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-22 | 0.022991 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-22 | 0.020041 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-22 | 0.028649 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-22 | 0.030725 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-22 | 0.035153 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-22 | 0.036817 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-22 | 0.019236 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.03283 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.031464 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.03406 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-19 | 0.090099 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-08-18 | 0.05458 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-20 | 0.025639 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-08-17 | 0.037921 | 10 | 0.01 | Florida | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-08-17 | 0.030276 | 10 | 0.01 | Florida | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-08-17 | 0.031312 | 10 | 0.01 | Florida | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.029826 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.029204 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.034797 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.022369 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.03169 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.029204 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.021127 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.0093206 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.014913 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.0099419 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-20 | 0.023612 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-21 | 0.016146 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-21 | 0.043063 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-22 | 0.02734 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-02 | 2026-08-18 | 0.05903 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-21 | 0.033147 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-17 | 0.040389 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-08-17 | 0.040521 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-21 | 0.029982 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-21 | 0.022991 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-21 | 0.022991 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-20 | 0.031069 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-20 | 0.023612 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-20 | 0.021748 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-20 | 0.026719 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-20 | 0.037282 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-20 | 0.029204 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-20 | 0.023612 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-20 | 0.021127 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-20 | 0.0093206 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-20 | 0.024234 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-20 | 0.01802 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-19 | 0.024843 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-20 | 0.031679 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-18 | 0.037282 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-08-18 | 0.037716 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-22 | 0.03604 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-20 | 0.022978 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-22 | 0.017153 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-18 | 0.033554 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-08-18 | 0.033038 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-19 | 0.02862 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-20 | 0.016801 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-17 | 0.034002 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-17 | 0.03137 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-17 | 0.043723 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-17 | 0.037279 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-17 | 0.025879 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-20 | 0.024514 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-20 | 0.0089689 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-19 | 0.026262 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-19 | 0.02906 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-20 | 0.030132 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-21 | 0.027256 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-21 | 0.022991 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.018147 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.018147 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.0079659 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-21 | 0.0062136 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.03131 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.031069 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.03169 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.03169 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.019884 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.017482 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.013988 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.018641 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.018641 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.014449 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.019647 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.018754 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-22 | 0.01793 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.01793 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.018754 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.018754 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.02112 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.019576 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.015756 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.020306 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.020094 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.023768 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.023768 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.017242 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.017699 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.0073905 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.011829 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.022369 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.016156 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.018701 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.018701 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.014821 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8404-02 | 2026-08-19 | 0.031031 | 10 | 0.01 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.02081 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.011658 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.015534 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.015654 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.012974 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.017935 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.019152 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.019152 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.014843 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.020478 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.017973 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.01036 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.017425 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.016179 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.018599 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.022748 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.022748 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.017864 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.014762 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.017495 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.02074 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.022283 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.017403 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.017403 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.029204 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.044739 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.025476 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.033554 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.038525 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.031069 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.031069 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.032933 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.031069 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-17 | 0.034797 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-08-17 | 0.034389 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-22 | 0.016777 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-21 | 0.037904 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-20 | 0.037282 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-20 | 0.010563 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-20 | 0.028583 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-19 | 0.03169 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-20 | 0.016777 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-20 | 0.017398 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-20 | 0.026719 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-19 | 0.02734 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-19 | 0.024234 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-19 | 0.18455 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-20 | 0.013049 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-20 | 0.15721 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-19 | 0.032311 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-19 | 0.052195 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8404-02 | 2026-08-19 | 0.03576 | 10 | 0.01 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8404-02 | 2026-08-20 | 0.032398 | 10 | 0.01 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8404-02 | 2026-08-20 | 0.028916 | 10 | 0.01 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8404-02 | 2026-08-21 | 0.032368 | 10 | 0.01 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8404-02 | 2026-08-21 | 0.03335 | 10 | 0.01 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8404-02 | 2026-08-22 | 0.032265 | 10 | 0.01 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1713-05 | 2026-08-18 | 0.029204 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1657-02 | 2026-08-17 | 0.029149 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1618-04 | 2026-08-17 | 0.033817 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1657-02 | 2026-08-17 | 0.012527 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1657-02 | 2026-08-17 | 0.031981 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1657-02 | 2026-08-17 | 0.039886 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1618-04 | 2026-08-17 | 0.038694 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.01422 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 8801-02 | 2026-08-21 | 0.02734 | 10 | 0.01 | Morovis | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.039768 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.042875 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.018641 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-21 | 0.04101 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.01802 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-19 | 0.031226 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.034175 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-21 | 0.044445 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.034175 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-21 | 0.038393 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-08-17 | 0.041824 | 10 | 0.01 | Florida | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-08-17 | 0.034382 | 10 | 0.01 | Florida | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 8801-02 | 2026-08-20 | 0.016777 | 10 | 0.01 | Morovis | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 8801-02 | 2026-08-20 | 0.024855 | 10 | 0.01 | Morovis | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8104-02 | 2026-08-22 | 0.03604 | 10 | 0.01 | Utuado | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-21 | 0.061349 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 8801-02 | 2026-08-20 | 0.031069 | 10 | 0.01 | Morovis | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-17 | 0.021748 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8404-04 | 2026-08-21 | 0.041632 | 10 | 0.01 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8404-04 | 2026-08-18 | 0.038525 | 10 | 0.01 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8404-04 | 2026-08-20 | 0.046603 | 10 | 0.01 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-19 | 0.12987 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.027962 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.016777 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.014291 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.029204 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.027962 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.039768 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-17 | 0.03604 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-21 | 0.076429 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-20 | 0.1019 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-21 | 0.096312 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.031069 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.010563 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.02734 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.03169 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.057787 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-19 | 0.0091331 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-19 | 0.011806 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-19 | 0.020512 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6406-02 | 2026-08-16 | 0.030447 | 10 | 0.01 | San Germán | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.032311 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-19 | 0.021127 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.034797 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.036661 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.043496 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.029204 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.029204 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.041632 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.052195 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.037282 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.035418 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.026098 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.040389 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.025476 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 9002-03 | 2026-08-17 | 0.015692 | 10 | 0.01 | Vega Baja | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.025476 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.025476 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-21 | 0.019262 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-22 | 0.027962 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 8801-02 | 2026-08-18 | 0.036661 | 10 | 0.01 | Morovis | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-22 | 0.039768 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-17 | 0.037282 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.03604 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.0043496 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-21 | 0.13732 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.064786 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 8801-02 | 2026-08-20 | 0.019262 | 10 | 0.01 | Morovis | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 8801-02 | 2026-08-22 | 0.022991 | 10 | 0.01 | Morovis | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 5018-05 | 2026-08-21 | 0.016185 | 10 | 0.01 | Ponce | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 5018-05 | 2026-08-21 | 0.026098 | 10 | 0.01 | Ponce | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 5018-05 | 2026-08-21 | 0.033554 | 10 | 0.01 | Ponce | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 8801-02 | 2026-08-19 | 0.017398 | 10 | 0.01 | Morovis | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 8801-02 | 2026-08-17 | 0.03024 | 10 | 0.01 | Morovis | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-17 | 0.023381 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1203-02 | 2026-08-17 | 0.027266 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-17 | 0.011606 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1203-02 | 2026-08-17 | 0.01193 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-17 | 0.015534 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-17 | 0.014291 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-17 | 0.032933 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1203-02 | 2026-08-17 | 0.031069 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6008-04 | 2026-08-17 | 0.030447 | 10 | 0.01 | Mayaguez | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6008-04 | 2026-08-17 | 0.035418 | 10 | 0.01 | Mayaguez | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-18 | 0.018641 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-18 | 0.026098 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6008-04 | 2026-08-17 | 0.030447 | 10 | 0.01 | Mayaguez | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1334-01 | 2026-08-18 | 0.026675 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6008-04 | 2026-08-17 | 0.039146 | 10 | 0.01 | Mayaguez | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-18 | 0.027692 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1334-01 | 2026-08-18 | 0.02834 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-18 | 0.016777 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-19 | 0.020911 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1334-01 | 2026-08-19 | 0.023616 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-19 | 0.022758 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1334-01 | 2026-08-19 | 0.022692 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-18 | 0.033571 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1334-01 | 2026-08-18 | 0.016304 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1334-01 | 2026-08-18 | 0.015323 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-18 | 0.0020394 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-18 | 0.004971 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-18 | 0.021127 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1203-02 | 2026-08-18 | 0.0031839 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1203-02 | 2026-08-18 | 0.021348 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-17 | 0.017398 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-17 | 0.041632 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1203-02 | 2026-08-17 | 0.044739 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1203-02 | 2026-08-18 | 0.020505 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-18 | 0.010563 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-21 | 0.025476 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-17 | 0.017398 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-18 | 0.030447 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-18 | 0.036661 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-18 | 0.017398 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-16 | 0.049763 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-19 | 0.026719 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-16 | 0.0062136 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-17 | 0.040389 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-17 | 0.036661 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-18 | 0.029826 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-20 | 0.028583 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7403-03 | 2026-08-18 | 0.042253 | 10 | 0.01 | Isabela | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-19 | 0.03328 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-19 | 0.032831 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-19 | 0.01367 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-19 | 0.040389 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-19 | 0.039771 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-19 | 0.023738 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-19 | 0.021127 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-21 | 0.052816 | 10 | 0.01 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-21 | 0.02734 | 10 | 0.01 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.027006 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.036661 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.03604 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.018641 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1330-01 | 2026-08-18 | 0.022442 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 5018-05 | 2026-08-21 | 0.03604 | 10 | 0.01 | Ponce | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5501-03 | 2026-08-18 | 0.025476 | 10 | 0.01 | Guayanilla | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5501-03 | 2026-08-19 | 0.034797 | 10 | 0.01 | Guayanilla | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5501-03 | 2026-08-19 | 0.034874 | 10 | 0.01 | Guayanilla | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1646-02 | 2026-08-22 | 0.034797 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1646-02 | 2026-08-22 | 0.034797 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1346-02 | 2026-08-19 | 0.038525 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1330-01 | 2026-08-19 | 0.048467 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-08-17 | 0.033256 | 10 | 0.01 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-08-19 | 0.030888 | 10 | 0.01 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-08-19 | 0.030936 | 10 | 0.01 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-08-19 | 0.029852 | 10 | 0.01 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5304-01 | 2026-08-16 | 0.046603 | 10 | 0.01 | Yauco | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5501-04 | 2026-08-16 | 0.078173 | 10 | 0.01 | Yauco | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1206-03 | 2026-08-16 | 0.044961 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1203-02 | 2026-08-16 | 0.045272 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8004-04 | 2026-08-16 | 0.034175 | 10 | 0.01 | Arecibo | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3302-03 | 2026-08-16 | 0.02999 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3302-03 | 2026-08-16 | 0.028583 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3302-03 | 2026-08-16 | 0.043226 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3302-03 | 2026-08-16 | 0.023825 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 5018-05 | 2026-08-16 | 0.04971 | 10 | 0.01 | Ponce | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5304-01 | 2026-08-16 | 0.094448 | 10 | 0.01 | Yauco | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8004-04 | 2026-08-16 | 0.023206 | 10 | 0.01 | Arecibo | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6406-02 | 2026-08-16 | 0.039768 | 10 | 0.01 | San Germán | Xperts | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1330-01 | 2026-08-17 | 0.027626 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2404-06 | 2026-08-19 | 0.027645 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2404-06 | 2026-08-19 | 0.019356 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 9703-03 | 2026-08-17 | 0.074565 | 10 | 0.01 | Comerío | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-08-17 | 0.030456 | 10 | 0.01 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-08-17 | 0.028431 | 10 | 0.01 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-21 | 0.037579 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8104-02 | 2026-08-20 | 0.11669 | 10 | 0.01 | Utuado | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-19 | 0.006789 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 9703-03 | 2026-08-17 | 0.074565 | 10 | 0.01 | Comerío | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-21 | 0.026259 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-19 | 0.013473 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-19 | 0.015534 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 6802-01 | 2026-08-17 | 0.032311 | 10 | 0.01 | San Germán | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-19 | 0.01367 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-19 | 0.01802 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-19 | 0.01367 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2005-09 | 2026-08-17 | 0.043634 | 10 | 0.01 | Fajardo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2002-03 | 2026-08-17 | 0.043801 | 10 | 0.01 | Fajardo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-17 | 0.031069 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-08-17 | 0.041702 | 10 | 0.01 | Florida | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-08-18 | 0.040878 | 10 | 0.01 | Florida | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6301-01 | 2026-08-17 | 0.021748 | 10 | 0.01 | Maricao | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-08-18 | 0.0551 | 10 | 0.01 | Florida | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-08-18 | 0.040461 | 10 | 0.01 | Florida | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-08-18 | 0.05469 | 10 | 0.01 | Florida | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-08-19 | 0.032723 | 10 | 0.01 | Florida | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-08-19 | 0.029204 | 10 | 0.01 | Florida | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-08-21 | 0.033554 | 10 | 0.01 | Florida | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-17 | 0.020505 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-19 | 0.024234 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-19 | 0.027962 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-19 | 0.019262 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-19 | 0.021127 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-19 | 0.010563 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-19 | 0.026719 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-17 | 0.019262 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8104-02 | 2026-08-20 | 0.043496 | 10 | 0.01 | Utuado | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-18 | 0.015409 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-20 | 0.01482 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-17 | 0.023104 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-19 | 0.019262 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-19 | 0.01367 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-18 | 0.028583 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-18 | 0.020505 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-21 | 0.023612 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-08-17 | 0.030456 | 10 | 0.01 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7403-03 | 2026-08-18 | 0.031069 | 10 | 0.01 | Isabela | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-20 | 0.020505 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-20 | 0.017398 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-21 | 0.02734 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8004-03 | 2026-08-17 | 0.068972 | 10 | 0.01 | Arecibo | Xperts | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8004-03 | 2026-08-17 | 0.053658 | 10 | 0.01 | Arecibo | Xperts | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8404-02 | 2026-08-18 | 0.033629 | 10 | 0.01 | Manatí | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8404-02 | 2026-08-18 | 0.029826 | 10 | 0.01 | Manatí | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8404-02 | 2026-08-20 | 0.026713 | 10 | 0.01 | Manatí | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8404-02 | 2026-08-20 | 0.027002 | 10 | 0.01 | Manatí | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8404-02 | 2026-08-20 | 0.024609 | 10 | 0.01 | Manatí | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2402-02 | 2026-08-18 | 0.037282 | 10 | 0.01 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2401-03 | 2026-08-18 | 0.038219 | 10 | 0.01 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2402-02 | 2026-08-18 | 0.03689 | 10 | 0.01 | Loíza | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2402-02 | 2026-08-18 | 0.03689 | 10 | 0.01 | Loíza | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2401-03 | 2026-08-18 | 0.036646 | 10 | 0.01 | Loíza | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5002-02 | 2026-08-17 | 0.024234 | 10 | 0.01 | Ponce | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3014-01 | 2026-08-18 | 0.018641 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-18 | 0.029727 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.018793 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.020386 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.030435 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.024904 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.021833 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6012-02 | 2026-08-18 | 0.078293 | 10 | 0.01 | Moca | Xperts | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.015434 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.029434 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.020736 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.028907 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.033946 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.031532 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.0086892 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.031424 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.0086892 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.031424 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.012089 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2402-02 | 2026-08-18 | 0.034892 | 10 | 0.01 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.032154 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.029851 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2401-03 | 2026-08-18 | 0.034899 | 10 | 0.01 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.021911 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.028303 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.031543 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5817-02 | 2026-08-18 | 0.032933 | 10 | 0.01 | Ponce | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.0072595 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.014162 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5817-02 | 2026-08-18 | 0.027962 | 10 | 0.01 | Ponce | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.025487 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.0084549 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2402-02 | 2026-08-18 | 0.02638 | 10 | 0.01 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.0084549 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.034669 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.027925 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.022402 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.02564 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.02783 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.021375 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2402-02 | 2026-08-18 | 0.035598 | 10 | 0.01 |  | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.019888 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 hi | 2026-08-18 | 0.022379 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2401-03 | 2026-08-18 | 0.03546 | 10 | 0.01 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.029849 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2401-03 | 2026-08-18 | 0.03546 | 10 | 0.01 | Canóvanas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.028923 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.027811 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.018793 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.01727 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.027211 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.027937 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.027937 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.023685 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.027222 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.027036 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.024514 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.022639 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6301-01 | 2026-08-21 | 0.03169 | 10 | 0.01 | Maricao | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.022717 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6301-01 | 2026-08-21 | 0.028583 | 10 | 0.01 | Maricao | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-02 | 2026-08-18 | 0.034175 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-19 | 0.021127 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-19 | 0.017398 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6301-01 | 2026-08-21 | 0.029826 | 10 | 0.01 | Maricao | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6301-01 | 2026-08-21 | 0.021748 | 10 | 0.01 | Maricao | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-08-18 | 0.043496 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-19 | 0.020505 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-19 | 0.018641 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-08-18 | 0.029826 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-08-18 | 0.019262 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-02 | 2026-08-18 | 0.05903 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-02 | 2026-08-18 | 0.061516 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-08-18 | 0.054059 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-08-18 | 0.054059 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2702-01 | 2026-08-18 | 0.043496 | 10 | 0.01 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-08-18 | 0.040389 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-21 | 0.0052597 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1720-07 | 2026-08-19 | 0.026098 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-08-18 | 0.027962 | 10 | 0.01 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-21 | 0.018524 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-08-18 | 0.029204 | 10 | 0.01 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-08-18 | 0.053438 | 10 | 0.01 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-21 | 0.027673 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-08-18 | 0.053438 | 10 | 0.01 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-19 | 0.011532 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-19 | 0.015379 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-19 | 0.018867 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-18 | 0.020014 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-21 | 0.021282 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-18 | 0.0095354 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-08-18 | 0.046603 | 10 | 0.01 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-21 | 0.019081 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-21 | 0.013844 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-21 | 0.023455 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5817-02 | 2026-08-18 | 0.027962 | 10 | 0.01 | Ponce | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5801-04 | 2026-08-18 | 0.027962 | 10 | 0.01 | Ponce | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.01432 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.027419 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.027572 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.027436 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.028952 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7101-02 | 2026-08-22 | 0.043496 | 10 | 0.01 | Moca | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.028952 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.021911 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.028174 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.027405 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.026464 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.028567 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.023864 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.019987 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.028272 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-18 | 0.02734 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-18 | 0.030111 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-19 | 0.024855 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-18 | 0.020448 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-19 | 0.028996 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-20 | 0.033416 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-20 | 0.033044 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-20 | 0.025765 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-21 | 0.010976 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8302-05 | 2026-08-18 | 0.037904 | 10 | 0.01 | Jayuya | Xperts | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.018283 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2702-01 | 2026-08-18 | 0.043496 | 10 | 0.01 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.025243 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.05573 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-18 | 0.023223 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-02 | 2026-08-18 | 0.056545 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-02 | 2026-08-18 | 0.04101 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5817-02 | 2026-08-18 | 0.02734 | 10 | 0.01 | Ponce | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5801-04 | 2026-08-18 | 0.02734 | 10 | 0.01 | Ponce | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3601-02 | 2026-08-18 | 0.024855 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 4101-01 | 2026-08-19 | 0.022991 | 10 | 0.01 | Arroyo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 4101-01 | 2026-08-19 | 0.019262 | 10 | 0.01 | Arroyo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 4101-01 | 2026-08-19 | 0.019262 | 10 | 0.01 | Arroyo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8501-01 | 2026-08-19 | 0.06338 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1734-01 | 2026-08-21 | 0.024234 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1734-01 | 2026-08-21 | 0.024234 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-08-19 | 0.022479 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-08-19 | 0.026877 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-08-19 | 0.029016 | 10 | 0.01 | Barceloneta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-19 | 0.026264 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1421-01 | 2026-08-21 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-08-19 | 0.027637 | 10 | 0.01 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-02 | 2026-08-19 | 0.028823 | 10 | 0.01 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7008-08 | 2026-08-20 | 0.073671 | 10 | 0.01 | Moca | Xperts | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8203-02 | 2026-08-19 | 0.20623 | 10 | 0.01 | Adjuntas | Xperts | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 8801-02 | 2026-08-19 | 0.024234 | 10 | 0.01 | Morovis | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1658-13 | 2026-08-20 | 0.036661 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-19 | 0.043948 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.080778 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.059652 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-19 | 0.021748 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-19 | 0.0080778 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.037282 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.034797 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-19 | 0.010491 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.034797 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.040389 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-19 | 0.028583 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.029826 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.022369 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.020505 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-19 | 0.019884 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-19 | 0.019884 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-19 | 0.020505 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-19 | 0.020505 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1658-13 | 2026-08-21 | 0.05903 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1658-13 | 2026-08-21 | 0.037282 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1658-13 | 2026-08-21 | 0.029204 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.03604 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1806-01 | 2026-08-19 | 0.04536 | 10 | 0.01 | Toa Baja | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-21 | 0.02734 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1806-01 | 2026-08-19 | 0.028583 | 10 | 0.01 | Toa Baja | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.0083617 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-19 | 0.015534 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.0086992 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.01367 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.026719 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.024855 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.026719 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.023612 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3302-02 | 2026-08-19 | 0.039791 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1658-13 | 2026-08-20 | 0.033554 | 10 | 0.01 | Loíza | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1658-13 | 2026-08-20 | 0.034797 | 10 | 0.01 | Loíza | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.023612 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.032311 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.031 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.032165 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.033443 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.03341 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.032947 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.032232 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.041693 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.036222 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.035154 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.028286 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-19 | 0.028286 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-19 | 0.018002 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-19 | 0.048467 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-19 | 0.04536 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5501-03 | 2026-08-20 | 0.032784 | 10 | 0.01 | Guayanilla | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5501-03 | 2026-08-20 | 0.032247 | 10 | 0.01 | Guayanilla | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7503-04 | 2026-08-19 | 0.026098 | 10 | 0.01 | Isabela | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-19 | 0.025476 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-19 | 0.022991 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-19 | 0.024234 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-19 | 0.023612 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-19 | 0.024855 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5501-03 | 2026-08-20 | 0.03169 | 10 | 0.01 | Guayanilla | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-19 | 0.013049 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-19 | 0.024234 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-19 | 0.019884 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-19 | 0.019262 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-19 | 0.02734 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-19 | 0.02734 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-19 | 0.021748 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-19 | 0.024855 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-19 | 0.043496 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-19 | 0.019884 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-19 | 0.024855 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-19 | 0.030447 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-19 | 0.027962 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-19 | 0.025476 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-19 | 0.026098 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-19 | 0.025476 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-19 | 0.022883 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-19 | 0.027962 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-19 | 0.024616 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8014-08 | 2026-08-19 | 0.029747 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-19 | 0.01802 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-08-19 | 0.030842 | 10 | 0.01 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7503-04 | 2026-08-19 | 0.011916 | 10 | 0.01 | Isabela | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-19 | 0.025476 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-19 | 0.03604 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-19 | 0.01802 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-19 | 0.023612 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-19 | 0.018641 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-20 | 0.032933 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-21 | 0.029826 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-19 | 0.027962 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-19 | 0.022991 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-20 | 0.015534 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-19 | 0.0257 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6406-02 | 2026-08-19 | 0.12241 | 10 | 0.01 | San Germán | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 4006-02 | 2026-08-20 | 0.020205 | 10 | 0.01 | Guayama | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 4006-02 | 2026-08-20 | 0.035785 | 10 | 0.01 | Guayama | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-21 | 0.1367 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.036661 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.030447 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.030447 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.03169 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.015134 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.016955 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.037614 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.02608 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.12918 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.036661 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.035418 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.035418 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.026098 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.021748 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.015534 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.031069 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.02734 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.034175 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.030447 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.027962 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.037904 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.030447 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.032933 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.032933 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.041632 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.027962 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.032311 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.028583 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.032311 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.018641 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.030447 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.027962 | 10 | 0.01 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-08-20 | 0.01826 | 10 | 0.01 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.026098 | 10 | 0.01 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1529-13 | 2026-08-20 | 0.035418 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.03169 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.02734 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.032311 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.029826 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.037904 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.025476 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.034175 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.032311 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.032311 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.03604 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1328-04 | 2026-08-20 | 0.012427 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.030447 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.03169 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.03169 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6201-02 | 2026-08-20 | 0.15642 | 10 | 0.01 | Las Marías | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8104-02 | 2026-08-22 | 0.10936 | 10 | 0.01 | Utuado | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.032933 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.030447 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.025476 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.025476 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.022369 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.030447 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-08-20 | 0.015879 | 10 | 0.01 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.04101 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5021-01 | 2026-08-20 | 0.06525 | 10 | 0.01 | Peñuelas | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.03169 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.03169 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-20 | 0.042253 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-20 | 0.023365 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.03169 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.03169 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-20 | 0.024303 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.032933 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.025476 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.022369 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.030447 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.04101 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.019262 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.030447 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-20 | 0.024234 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.04101 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.026719 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.026098 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-21 | 0.0089875 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.031069 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.03169 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.030447 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.03169 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.029204 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.03169 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.029204 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.031236 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.026165 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.024206 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.02402 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.027552 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.030455 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.027628 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.032027 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.030447 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.029826 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.020105 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-08-20 | 0.023612 | 10 | 0.01 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-08-20 | 0.018641 | 10 | 0.01 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8404-02 | 2026-08-20 | 0.00094697 | 10 | 0.01 | Manatí | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7403-03 | 2026-08-17 | 0.034175 | 10 | 0.01 | Isabela | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.027628 | 10 | 0.01 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.030455 | 10 | 0.01 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-20 | 0.027552 | 10 | 0.01 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1328-04 | 2026-08-20 | 0.020505 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5401-02 | 2026-08-20 | 0.073322 | 10 | 0.01 | Peñuelas | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1328-04 | 2026-08-20 | 0.0080778 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1328-04 | 2026-08-20 | 0.016777 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-08-20 | 0.00094697 | 10 | 0.01 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1328-04 | 2026-08-20 | 0.021748 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 4501-02 | 2026-08-21 | 0.017398 | 10 | 0.01 | Salinas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 4501-02 | 2026-08-21 | 0.023612 | 10 | 0.01 | Salinas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8504-03 | 2026-08-21 | 0.048467 | 10 | 0.01 | Barceloneta | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8504-03 | 2026-08-21 | 0.054681 | 10 | 0.01 | Barceloneta | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-21 | 0.026719 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-21 | 0.019262 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-21 | 0.037858 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-21 | 0.031515 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-21 | 0.018161 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-21 | 0.018161 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-21 | 0.024334 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-21 | 0.024855 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-21 | 0.026098 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-21 | 0.025476 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-21 | 0.024855 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-21 | 0.023612 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-21 | 0.020505 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-21 | 0.018641 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2901-03 | 2026-08-21 | 0.11006 | 10 | 0.01 | Yabucoa | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-21 | 0.034175 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-21 | 0.01802 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-21 | 0.016156 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-21 | 0.014291 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-21 | 0.017398 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-21 | 0.011185 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-21 | 0.017398 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-21 | 0.017398 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-21 | 0.017398 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-21 | 0.017398 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-21 | 0.01802 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-21 | 0.02734 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-21 | 0.019262 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-21 | 0.019262 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-21 | 0.019262 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-21 | 0.019262 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-21 | 0.024234 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-21 | 0.019884 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-20 | 0.024234 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-21 | 0.020505 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-21 | 0.024234 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-21 | 0.021748 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-21 | 0.016777 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-21 | 0.026098 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-21 | 0.024855 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1711-02 | 2026-08-21 | 0.026416 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6406-04 | 2026-08-21 | 0.1248 | 10 | 0.01 | San Germán | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-21 | 0.016777 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-21 | 0.019884 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1711-02 | 2026-08-21 | 0.058134 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8504-03 | 2026-08-21 | 0.09072 | 10 | 0.01 | Barceloneta | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6406-02 | 2026-08-21 | 0.095295 | 10 | 0.01 | San Germán | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-08-22 | 0.033665 | 10 | 0.01 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-22 | 0.023612 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-22 | 0.024855 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-22 | 0.017398 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-22 | 0.016777 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-22 | 0.017398 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-22 | 0.017398 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-22 | 0.023612 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-22 | 0.01802 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-22 | 0.016777 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-22 | 0.021127 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-22 | 0.021127 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-22 | 0.021127 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-22 | 0.020505 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-22 | 0.023612 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-22 | 0.04196 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-22 | 0.01802 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-22 | 0.017398 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-22 | 0.016156 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-22 | 0.015534 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-22 | 0.016777 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-22 | 0.017398 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-22 | 0.016777 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-22 | 0.021127 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-22 | 0.019884 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-22 | 0.018641 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-22 | 0.016777 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-22 | 0.01802 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-22 | 0.016777 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-22 | 0.019884 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-22 | 0.018641 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-22 | 0.019884 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-22 | 0.01367 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-22 | 0.015534 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-22 | 0.020505 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 8701-03 | 2026-08-22 | 0.016156 | 10 | 0.01 | Ciales | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 8701-03 | 2026-08-22 | 0.027962 | 10 | 0.01 | Ciales | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2002-02 | 2026-08-22 | 0.025343 | 10 | 0.01 | Fajardo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 8701-03 | 2026-08-22 | 0.010563 | 10 | 0.01 | Ciales | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2002-02 | 2026-08-22 | 0.028952 | 10 | 0.01 | Fajardo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2002-02 | 2026-08-22 | 0.041783 | 10 | 0.01 | Fajardo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8001-01 | 2026-08-22 | 0.029204 | 10 | 0.01 | Arecibo | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3406-03 | 2026-08-22 | 0.032933 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3406-03 | 2026-08-22 | 0.040389 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8001-01 | 2026-08-22 | 0.028515 | 10 | 0.01 | Arecibo | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3406-03 | 2026-08-22 | 0.034797 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3406-03 | 2026-08-22 | 0.02734 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3406-03 | 2026-08-22 | 0.037904 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3406-03 | 2026-08-22 | 0.01802 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3406-03 | 2026-08-22 | 0.00094697 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3406-03 | 2026-08-22 | 0.072079 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3406-03 | 2026-08-22 | 0.014913 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3406-03 | 2026-08-22 | 0.037282 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 9103-04 | 2026-08-25 | 0.027962 | 10 | 0.01 | Vega Alta | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-27 | 0.019871 | 10 | 0.01 | Aguada | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-27 | 0.023174 | 10 | 0.01 | Aguada | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.16/7.20 | 6702-02 | 2026-08-26 | 0.026719 | 10 | 0.01 | San Germán | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.16/7.20 | 6702-02 | 2026-08-26 | 0.02734 | 10 | 0.01 | Cabo Rojo | PIS (Perfect Integrated Solutions) | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1334-02 | 2026-08-25 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5402-02 | 2026-08-26 | 0.025476 | 10 | 0.01 | Peñuelas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5402-02 | 2026-08-26 | 0.050331 | 10 | 0.01 | Peñuelas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5402-02 | 2026-08-26 | 0.047846 | 10 | 0.01 | Peñuelas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5402-02 | 2026-08-26 | 0.044739 | 10 | 0.01 | Peñuelas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 4003-01 | 2026-08-29 | 0.028171 | 10 | 0.01 | Guayama | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6406-02 | 2026-08-24 | 0.037904 | 10 | 0.01 | San Germán | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 4003-01 | 2026-08-24 | 0.041235 | 10 | 0.01 | Guayama | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 4003-01 | 2026-08-25 | 0.03625 | 10 | 0.01 | Guayama | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5902-03 | 2026-08-25 | 0.032933 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5902-03 | 2026-08-25 | 0.02734 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7901-03 | 2026-08-24 | 0.17585 | 10 | 0.01 | San Sebastián | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7901-03 | 2026-08-24 | 0.085749 | 10 | 0.01 | San Sebastián | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7901-03 | 2026-08-25 | 0.047846 | 10 | 0.01 | Lares | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-02 | 2026-08-24 | 0.036579 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-02 | 2026-08-24 | 0.061695 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-02 | 2026-08-24 | 0.048467 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-02 | 2026-08-29 | 0.00094697 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-27 | 0.033304 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-27 | 0.022295 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-28 | 0.037614 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-29 | 0.0235 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.00094697 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.00094697 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-28 | 0.04101 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-29 | 0.049088 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-02 | 2026-08-29 | 0.00094697 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-02 | 2026-08-29 | 0.00094697 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-02 | 2026-08-29 | 0.042875 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-02 | 2026-08-25 | 0.053438 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-02 | 2026-08-25 | 0.051574 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-02 | 2026-08-25 | 0.044117 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7901-03 | 2026-08-27 | 0.031069 | 10 | 0.01 | Lares | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-24 | 0.017922 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5304-01 | 2026-08-28 | 0.038199 | 10 | 0.01 | Yauco | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-26 | 0.041632 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-25 | 0.023612 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-25 | 0.028583 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-25 | 0.025751 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-25 | 0.026472 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-25 | 0.033947 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-25 | 0.037282 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-25 | 0.027962 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-27 | 0.014913 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-27 | 0.022991 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-27 | 0.026719 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-27 | 0.011806 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-27 | 0.013049 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-27 | 0.04101 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-30 | 0.039768 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-27 | 0.017315 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-29 | 4.3088e-06 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-29 | 0.037904 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1303-01 | 2026-08-28 | 0.025361 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1303-02 | 2026-08-28 | 0.025629 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1303-01 | 2026-08-28 | 0.029616 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1303-02 | 2026-08-28 | 0.0296 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-27 | 0.037276 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-27 | 0.083435 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-27 | 0.11973 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-27 | 0.029743 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-27 | 0.034797 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-27 | 0.02153 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-27 | 0.015534 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-27 | 0.041632 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-24 | 0.037282 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-27 | 0.031069 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-25 | 0.04536 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-25 | 0.00094697 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-27 | 0.056484 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-27 | 0.035418 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-27 | 0.031069 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-27 | 0.01773 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-27 | 0.021913 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-27 | 0.029826 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-27 | 0.031069 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-27 | 0.044885 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-27 | 0.12987 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2002-03 | 2026-08-26 | 0.02648 | 10 | 0.01 | Fajardo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2002-03 | 2026-08-26 | 0.025476 | 10 | 0.01 | Fajardo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 7302-02 | 2026-08-27 | 0.029826 | 10 | 0.01 | Rincón | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 7302-02 | 2026-08-27 | 0.029826 | 10 | 0.01 | Rincón | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-27 | 0.0026688 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-27 | 0.00094697 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-27 | 0.017843 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-24 | 0.025476 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-24 | 0.035418 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-24 | 0.01802 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-24 | 0.018641 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-24 | 0.0055924 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-24 | 0.010563 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-27 | 0.030041 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-24 | 0.021127 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-27 | 0.0221 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-24 | 0.0085159 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-25 | 0.015534 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-25 | 0.028583 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-25 | 0.006835 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-25 | 0.0062093 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-27 | 0.024234 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-27 | 0.028583 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-27 | 0.031069 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-27 | 0.00094697 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-27 | 0.00094697 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-27 | 0.00094697 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-27 | 0.00094697 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-27 | 0.00094697 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-27 | 0.00094697 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-27 | 0.00094697 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-27 | 0.038525 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-27 | 0.024234 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-27 | 0.019884 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-27 | 0.029204 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-26 | 0.025476 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-26 | 0.021748 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-24 | 0.023612 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-24 | 0.019884 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-24 | 0.018641 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-25 | 0.024234 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-27 | 0.026141 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-27 | 0.026651 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-27 | 0.026388 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-27 | 0.026207 | 10 | 0.01 | Canóvanas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-27 | 0.036036 | 10 | 0.01 | Canóvanas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-27 | 0.020147 | 10 | 0.01 | Canóvanas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-27 | 0.03093 | 10 | 0.01 | Canóvanas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-27 | 0.031224 | 10 | 0.01 | Canóvanas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-27 | 0.046901 | 10 | 0.01 | Canóvanas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-27 | 0.045501 | 10 | 0.01 | Canóvanas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-27 | 0.010668 | 10 | 0.01 | Canóvanas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-27 | 0.0045926 | 10 | 0.01 | Canóvanas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-27 | 0.029973 | 10 | 0.01 | Canóvanas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-26 | 0.03796 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-25 | 0.017515 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-26 | 0.049088 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-25 | 0.041632 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-27 | 0.0037021 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-24 | 0.024234 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-24 | 0.024855 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-25 | 0.032933 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-24 | 0.026719 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-24 | 0.047846 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-24 | 0.027962 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-24 | 0.044739 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-24 | 0.019262 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-24 | 0.021127 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-24 | 0.031069 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-24 | 0.02734 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-24 | 0.037904 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-24 | 0.035418 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-24 | 0.017398 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-24 | 0.029826 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-24 | 0.022991 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-08-25 | 0.024615 | 10 | 0.01 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-25 | 0.024855 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-25 | 0.0047174 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-25 | 0.0084233 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-25 | 0.033554 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-24 | 0.03169 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-26 | 0.031069 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-25 | 0.020771 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-27 | 0.1106 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-26 | 0.0047697 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-26 | 0.027962 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-26 | 0.057166 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-27 | 0.00094697 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-27 | 0.00094697 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-27 | 0.00094697 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-27 | 0.00094697 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-27 | 0.00094697 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-27 | 0.00094697 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-27 | 0.00094697 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-27 | 0.00094697 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-27 | 0.00094697 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-27 | 0.00094697 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-27 | 0.00094697 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-24 | 0.00094697 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-27 | 0.030359 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-24 | 0.034797 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-24 | 0.041004 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-24 | 0.035418 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-24 | 0.013049 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-27 | 0.022991 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-27 | 0.046603 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-27 | 0.028151 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-28 | 0.043172 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-28 | 0.036918 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-28 | 0.026532 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-29 | 0.01448 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-27 | 0.02734 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-24 | 0.022991 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-29 | 0.027054 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-26 | 0.029011 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-26 | 0.025482 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-27 | 0.020056 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-27 | 0.026449 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.012984 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-26 | 0.030411 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.026774 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.031069 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.030447 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-26 | 0.032311 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.04101 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.037282 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.038525 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.044117 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.01802 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-26 | 0.020505 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.041632 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.03604 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.031069 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.027981 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.013171 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.010563 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.021127 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.013171 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.029997 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.037513 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.030447 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.0036903 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.0074564 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.032311 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.059652 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-25 | 0.021612 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-25 | 0.0074362 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-25 | 0.026719 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-25 | 0.0012428 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-25 | 0.029826 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-25 | 0.034797 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.050952 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.018715 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.015534 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.029204 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.02734 | 10 | 0.01 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.032311 | 10 | 0.01 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.036661 | 10 | 0.01 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.03604 | 10 | 0.01 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.021127 | 10 | 0.01 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.021127 | 10 | 0.01 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.021127 | 10 | 0.01 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.02734 | 10 | 0.01 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.0088695 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.013217 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.029204 | 10 | 0.01 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.012427 | 10 | 0.01 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.032311 | 10 | 0.01 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.02734 | 10 | 0.01 | Aguas Buenas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.01802 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.019262 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.014291 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.016156 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.012427 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.026719 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.022369 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.01802 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.0093206 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.014291 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.01802 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.024234 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.024234 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.028583 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.0062136 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.02734 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.032933 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.004971 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.032933 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.021748 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.036661 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.019262 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-02 | 2026-08-27 | 0.029204 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-25 | 0.045168 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.023612 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.016156 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.013049 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-25 | 0.02734 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.016777 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.029204 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.017398 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.032933 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.023612 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.030447 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-27 | 0.04101 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.018641 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.020505 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.017398 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03i | 2026-08-27 | 0.028583 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.03169 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-27 | 0.014336 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-27 | 0.014206 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-27 | 0.018252 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-25 | 0.022991 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.0074564 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.01802 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.026719 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5302-01 | 2026-08-24 | 0.041632 | 10 | 0.01 | Yauco | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-24 | 0.032311 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.022369 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.0018642 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-28 | 0.036007 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.03604 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-28 | 0.03187 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-26 | 0.026719 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-27 | 0.03051 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-26 | 0.029204 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-26 | 0.0373 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-28 | 4.3109e-06 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-26 | 0.037282 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.025476 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-28 | 0.032104 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-25 | 0.019262 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-25 | 0.010563 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-25 | 0.0055924 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-25 | 0.004971 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-27 | 0.022991 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-27 | 0.029457 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-27 | 0.025628 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-27 | 0.017843 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-27 | 0.01409 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-27 | 0.020505 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-25 | 0.03169 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-25 | 0.038525 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-27 | 0.0037282 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-27 | 0.0093206 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-25 | 0.016156 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-27 | 0.026719 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-29 | 0.028583 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-29 | 0.037282 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-27 | 0.021127 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-27 | 0.0050138 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.029826 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.046603 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.036661 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.027962 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.041632 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.04536 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.022991 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-29 | 0.03169 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-26 | 0.025433 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-26 | 0.010373 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-29 | 0.020354 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-25 | 0.022991 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-27 | 0.03169 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-27 | 0.032311 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-27 | 0.027962 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-27 | 0.047224 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-27 | 0.046603 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-27 | 0.033554 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-27 | 0.019262 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.044561 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.040617 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1201-01 | 2026-08-26 | 0.045645 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-24 | 0.026098 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-24 | 0.025476 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-24 | 0.022369 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-24 | 0.022369 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-24 | 0.039146 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-24 | 0.02734 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-24 | 0.029172 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-24 | 0.030447 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-24 | 0.00094697 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-24 | 0.065244 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-28 | 0.01367 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-25 | 0.029204 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-25 | 0.031069 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-25 | 0.022991 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-25 | 0.024855 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-24 | 0.064623 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-24 | 0.028583 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-27 | 0.04993 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-27 | 0.049067 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-25 | 0.032308 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-25 | 0.063608 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-25 | 0.051038 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-26 | 0.021748 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.017398 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-28 | 0.033541 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.01802 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-27 | 0.049316 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.01802 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-27 | 0.035426 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.027962 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-25 | 0.021127 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-26 | 0.03285 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-25 | 0.02302 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-26 | 0.032319 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-27 | 0.011009 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-26 | 0.048467 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-25 | 0.037282 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-26 | 0.044117 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-27 | 0.042875 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-28 | 0.05903 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.060273 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.047846 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.047224 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.059652 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.013049 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.021748 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.037904 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.011806 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.021748 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.025476 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.022991 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.026098 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.037348 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.026719 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.026719 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.026719 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.058285 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.030809 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.051237 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.051237 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-25 | 0.045427 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-25 | 0.091341 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-25 | 0.079536 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-25 | 0.079536 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.10998 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-25 | 0.11185 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-25 | 0.067108 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.057166 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.057166 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.01367 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.024436 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.015444 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.037904 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.038242 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.050331 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.021748 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.036817 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.015973 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.024855 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.011806 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.030447 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.014913 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.027711 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.024696 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.04816 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.031069 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.010563 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.01857 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.023612 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.02577 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.023612 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.027383 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-27 | 0.030447 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-27 | 0.023612 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-27 | 0.032311 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-27 | 0.02734 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3202-01 | 2026-08-27 | 0.014291 | 10 | 0.01 | Juncos | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-24 | 0.0055924 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-24 | 0.012427 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.034608 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.052284 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-25 | 0.086371 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-25 | 0.070836 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.064001 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.089477 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-24 | 0.032311 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-24 | 0.032311 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5901-01 | 2026-08-24 | 0.032311 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-24 | 0.020505 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-24 | 0.027962 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-25 | 0.020505 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-08-27 | 0.024234 | 10 | 0.01 | Florida | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-08-27 | 0.034797 | 10 | 0.01 | Florida | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-08-26 | 0.024855 | 10 | 0.01 | Florida | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-08-26 | 0.03169 | 10 | 0.01 | Florida | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-08-26 | 0.031069 | 10 | 0.01 | Florida | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-26 | 0.017398 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-08-26 | 0.033554 | 10 | 0.01 | Florida | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-08-26 | 0.028583 | 10 | 0.01 | Florida | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-08-26 | 0.030447 | 10 | 0.01 | Florida | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.029204 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-25 | 0.026098 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.016614 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.030698 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1342-04 | 2026-08-26 | 0.044739 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.034353 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1342-04 | 2026-08-26 | 0.032923 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.027962 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1342-04 | 2026-08-26 | 0.027962 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.026098 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1342-04 | 2026-08-26 | 0.02734 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.057166 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.033554 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-27 | 0.019345 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-29 | 0.04101 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.025476 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.033554 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.026098 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.021127 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.023612 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.034175 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.027166 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.031069 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.013049 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.03604 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.039768 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.03604 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.032933 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.0099873 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.026098 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-25 | 0.012547 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.026719 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-24 | 0.15099 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-24 | 0.14043 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.032933 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-25 | 0.033554 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-25 | 0.014291 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-25 | 0.032933 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-25 | 0.052816 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-25 | 3.1088e-05 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-25 | 0.034797 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-25 | 0.034797 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-25 | 0.030447 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-25 | 0.021127 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-25 | 0.021127 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-25 | 0.043496 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06l | 2026-08-26 | 0.015534 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-27 | 0.015534 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-27 | 0.015534 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-27 | 0.014291 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.042253 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-27 | 0.062187 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.018948 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.096034 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.042253 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 no | 2026-08-26 | 0.025476 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.032311 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.023876 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.01802 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.01802 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.039146 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.039146 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.034797 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.029826 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.03169 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.021127 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.015534 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.048467 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.038525 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.038525 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.026719 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.026719 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.026719 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.016328 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.036181 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.036181 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.024234 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.029204 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.023612 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.036661 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.029826 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.035445 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.038281 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.044277 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.019262 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.019884 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.031069 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.052816 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.011185 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.032933 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.0082811 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1657-02 | 2026-08-28 | 0.029149 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1618-04 | 2026-08-28 | 0.033817 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.029204 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.042253 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.049088 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.049088 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-25 | 0.042875 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.032152 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.020544 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.0049735 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.047224 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.029204 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.03604 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.03604 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.025145 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.046603 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.037904 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.052816 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.052816 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.0080778 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.020505 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.037282 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.041632 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.038525 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.03169 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-28 | 0.04101 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 4003-01 | 2026-08-25 | 0.018939 | 10 | 0.01 | Guayama | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.025482 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.023667 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.040272 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.011185 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.027688 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.035828 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.067729 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.025475 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.04101 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.027962 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.039768 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.10844 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.033554 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.077671 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.011806 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.019262 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.037904 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.037904 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.032311 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.037904 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 8801-02 | 2026-08-24 | 0.050331 | 10 | 0.01 | Morovis | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-27 | 0.014661 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-24 | 0.051689 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8404-04 | 2026-08-24 | 0.038469 | 10 | 0.01 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.026992 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8404-01 | 2026-08-24 | 0.034797 | 10 | 0.01 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8404-01 | 2026-08-26 | 0.029826 | 10 | 0.01 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8404-01 | 2026-08-28 | 0.040482 | 10 | 0.01 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8404-01 | 2026-08-27 | 0.016926 | 10 | 0.01 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8404-01 | 2026-08-27 | 0.012166 | 10 | 0.01 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2305-02 | 2026-08-27 | 0.039283 | 10 | 0.01 | Luquillo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2002-03 | 2026-08-27 | 0.039427 | 10 | 0.01 | Luquillo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2305-02 | 2026-08-27 | 0.00094697 | 10 | 0.01 | Luquillo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2002-03 | 2026-08-27 | 0.035531 | 10 | 0.01 | Luquillo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-24 | 0.046013 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8404-04 | 2026-08-25 | 0.040389 | 10 | 0.01 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8404-04 | 2026-08-25 | 0.048467 | 10 | 0.01 | Manatí | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 9004-08 | 2026-08-26 | 0.042875 | 10 | 0.01 | Vega Baja | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 9004-08 | 2026-08-28 | 0.04536 | 10 | 0.01 | Vega Baja | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 9004-08 | 2026-08-28 | 0.046603 | 10 | 0.01 | Vega Baja | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 9004-08 | 2026-08-28 | 0.042875 | 10 | 0.01 | Vega Baja | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 8801-02 | 2026-08-24 | 0.10673 | 10 | 0.01 | Morovis | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-24 | 0.14043 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 9004-08 | 2026-08-28 | 0.02568 | 10 | 0.01 | Vega Baja | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 9004-08 | 2026-08-28 | 4.2854e-06 | 10 | 0.01 | Vega Baja | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 9004-08 | 2026-08-28 | 4.2854e-06 | 10 | 0.01 | Vega Baja | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 9004-08 | 2026-08-28 | 0.019209 | 10 | 0.01 | Vega Baja | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 9004-08 | 2026-08-28 | 0.014924 | 10 | 0.01 | Vega Baja | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 9004-08 | 2026-08-28 | 0.018641 | 10 | 0.01 | Vega Baja | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 9004-08 | 2026-08-28 | 0.020286 | 10 | 0.01 | Vega Baja | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.02734 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.035418 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.021099 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.033834 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.026098 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.027962 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 9004-08 | 2026-08-28 | 0.015964 | 10 | 0.01 | Vega Baja | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 9003-05 | 2026-08-28 | 0.016903 | 10 | 0.01 | Vega Baja | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.027962 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 9004-08 | 2026-08-28 | 0.030447 | 10 | 0.01 | Vega Baja | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 9003-05 | 2026-08-28 | 0.030447 | 10 | 0.01 | Vega Baja | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.016156 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.00094697 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-28 | 0.021676 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-28 | 0.028451 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-28 | 0.027848 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-28 | 0.033554 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.00094697 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.00094697 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-25 | 0.03604 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.00094697 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.00094697 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-25 | 0.023612 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.00094697 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.00094697 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.00094697 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.00094697 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.00094697 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.00094697 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.00094697 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.00094697 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.00094697 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.045981 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-27 | 0.022369 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.013049 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.013049 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.030447 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-27 | 0.023612 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-27 | 0.023612 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-29 | 0.026098 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-27 | 0.022369 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-25 | 0.024855 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-28 | 0.025476 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-25 | 0.025476 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-27 | 0.025476 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.025476 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.034175 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-24 | 0.037282 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.071443 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-24 | 0.016724 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.046605 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-24 | 0.019262 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-24 | 0.00094697 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-24 | 0.024855 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-24 | 0.019262 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-24 | 0.011806 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.035994 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.023612 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 3.3911e-05 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 3.0009e-05 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-28 | 0.030447 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.10439 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.10439 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.042097 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.051574 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-27 | 0.03169 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.045981 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.047224 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.049088 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.042097 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.035531 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.067108 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.035752 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.054059 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.024855 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.010338 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.060879 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-25 | 0.14976 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.024748 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.041132 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.027962 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.031069 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.031069 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.037282 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7008-08 | 2026-08-26 | 0.00094697 | 10 | 0.01 | Moca | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.044221 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 3.3911e-05 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.10128 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 5018-05 | 2026-08-27 | 0.034797 | 10 | 0.01 | Ponce | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.11185 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.12738 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.14229 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.10128 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-25 | 0.024122 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-25 | 0.022369 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-25 | 0.044739 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-25 | 0.048467 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-25 | 0.079536 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-25 | 0.052816 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-25 | 0.052816 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-25 | 0.059652 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-25 | 0.059652 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 5018-05 | 2026-08-27 | 0.038476 | 10 | 0.01 | Ponce | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.040389 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-27 | 0.029826 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-25 | 0.040389 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-25 | 0.016156 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-25 | 0.024234 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-25 | 0.037904 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-25 | 0.019884 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-25 | 0.0086992 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-25 | 0.026098 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-25 | 0.019884 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-25 | 0.056545 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-25 | 0.016777 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-25 | 0.01367 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-25 | 0.027962 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.024234 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.070836 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.049088 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.030447 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.049088 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.021127 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.031069 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.028583 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.027962 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.04101 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.029826 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.030447 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.011185 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.029826 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.033554 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-25 | 0.024855 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-25 | 0.034175 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-25 | 0.027962 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-24 | 0.038525 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-28 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-24 | 0.014913 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-24 | 0.031069 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-24 | 0.032933 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-24 | 0.02734 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-24 | 0.024234 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-25 | 0.015534 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-25 | 0.029204 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-25 | 0.032933 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-25 | 0.026719 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-25 | 0.035418 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-25 | 0.026098 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-25 | 0.022369 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-25 | 0.027962 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-25 | 0.0043496 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-25 | 0.029826 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-24 | 0.034797 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-26 | 0.031069 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-26 | 0.010563 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-28 | 0.029204 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-24 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-24 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-24 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-24 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-24 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3603-01 | 2026-08-26 | 0.029826 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-24 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-24 | 0.0040576 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1334-01 | 2026-08-24 | 0.007483 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-26 | 0.045028 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.022369 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1203-02 | 2026-08-26 | 0.021127 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-27 | 0.035454 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-27 | 0.013049 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-27 | 0.014291 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-28 | 0.0037282 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-26 | 0.031069 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-24 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-24 | 0.027486 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-24 | 0.036661 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-24 | 0.024234 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-24 | 0.016378 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-28 | 0.02121 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-28 | 0.041453 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-25 | 0.0814 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-25 | 0.12614 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-25 | 0.086371 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-28 | 0.029907 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-25 | 0.12445 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-25 | 0.15348 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.021127 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.026098 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.01367 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.01367 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.019262 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.03169 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.029826 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.014913 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.034175 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.03604 | 10 | 0.01 |  | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.017398 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.012427 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 3.4818e-05 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.03296 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.027006 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.027006 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.027006 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.027006 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.039146 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.023612 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.032311 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.036661 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.03604 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.034797 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-28 | 0.04536 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.029204 | 10 | 0.01 | Caguash | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.024234 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.024234 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-28 | 0.058409 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.036661 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.03604 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.020505 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-24 | 0.042088 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-24 | 0.038733 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-27 | 0.14789 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 5018-05 | 2026-08-27 | 0.033554 | 10 | 0.01 | Ponce | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 5018-05 | 2026-08-27 | 0.039146 | 10 | 0.01 | Ponce | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 5018-05 | 2026-08-27 | 0.03169 | 10 | 0.01 | Ponce | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 5018-05 | 2026-08-27 | 0.03169 | 10 | 0.01 | Ponce | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 5018-05 | 2026-08-27 | 0.027962 | 10 | 0.01 | Ponce | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 5018-05 | 2026-08-27 | 0.031069 | 10 | 0.01 | Ponce | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 5018-05 | 2026-08-27 | 0.029204 | 10 | 0.01 | Ponce | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 5018-05 | 2026-08-27 | 0.030447 | 10 | 0.01 | Ponce | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 5018-05 | 2026-08-27 | 0.017541 | 10 | 0.01 | Ponce | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1646-02 | 2026-08-27 | 0.021748 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1646-02 | 2026-08-27 | 0.021748 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1530-06 | 2026-08-25 | 0.018641 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1530-06 | 2026-08-25 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1530-06 | 2026-08-25 | 0.023612 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1530-06 | 2026-08-25 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1530-06 | 2026-08-25 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1530-06 | 2026-08-25 | 0.024855 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1530-06 | 2026-08-25 | 0.024234 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1909-07 | 2026-08-27 | 0.020385 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1909-07 | 2026-08-27 | 0.012583 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1909-07 | 2026-08-27 | 4.3019e-06 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1909-07 | 2026-08-28 | 0.023944 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1909-07 | 2026-08-28 | 0.021706 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1909-07 | 2026-08-29 | 0.018695 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1909-07 | 2026-08-29 | 0.008447 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-25 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-25 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-25 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-27 | 0.0019636 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-25 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-25 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-25 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-25 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-27 | 0.02734 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-27 | 0.034175 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.0099419 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-25 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-27 | 0.024234 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-25 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-27 | 0.01367 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-27 | 0.032311 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-25 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-28 | 0.00094697 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-27 | 0.00094697 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-27 | 0.024234 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-27 | 0.00094697 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-27 | 0.039768 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 9004-08 | 2026-08-29 | 0.02834 | 10 | 0.01 | Vega Baja | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 9004-08 | 2026-08-29 | 0.035222 | 10 | 0.01 | Vega Baja | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-25 | 0.03169 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 9004-08 | 2026-08-29 | 0.031643 | 10 | 0.01 | Vega Baja | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-25 | 0.026719 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 9004-08 | 2026-08-29 | 0.019819 | 10 | 0.01 | Vega Baja | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-27 | 0.052195 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 9004-08 | 2026-08-29 | 0.0085208 | 10 | 0.01 | Vega Baja | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-25 | 0.022369 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-27 | 0.017398 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-27 | 0.006835 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-27 | 0.017398 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-27 | 0.027962 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-27 | 0.016156 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-25 | 0.00094697 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-08-24 | 0.028583 | 10 | 0.01 | Florida | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-27 | 0.012427 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-27 | 0.016777 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-08-24 | 0.034797 | 10 | 0.01 | Florida | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-25 | 0.00094697 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-27 | 0.029204 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-27 | 0.042253 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-24 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-24 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-24 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-24 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-24 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-24 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7403-03 | 2026-08-25 | 0.052195 | 10 | 0.01 | Isabela | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-24 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-24 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-24 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7403-03 | 2026-08-25 | 0.033554 | 10 | 0.01 | Isabela | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7403-03 | 2026-08-25 | 0.026719 | 10 | 0.01 | Isabela | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-24 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-24 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-24 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2005-09 | 2026-08-27 | 0.012353 | 10 | 0.01 | Fajardo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2002-03 | 2026-08-27 | 0.012786 | 10 | 0.01 | Fajardo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-24 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 9004-08 | 2026-08-29 | 0.031759 | 10 | 0.01 | Vega Baja | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-24 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2005-09 | 2026-08-27 | 0.027484 | 10 | 0.01 | Fajardo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2002-03 | 2026-08-27 | 0.026769 | 10 | 0.01 | Fajardo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-27 | 0.00094697 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-27 | 0.013049 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-27 | 0.017398 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-27 | 0.016156 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-27 | 0.014913 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-25 | 0.017398 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-25 | 0.032311 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-27 | 0.037282 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-27 | 0.024855 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-27 | 0.025476 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-27 | 0.021748 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-27 | 0.021748 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-25 | 0.020505 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-25 | 0.021748 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-27 | 0.025476 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-27 | 0.032311 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-27 | 0.034175 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-27 | 0.034175 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-27 | 0.025956 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-27 | 0.017398 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-27 | 0.015534 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-27 | 0.014913 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-27 | 0.024855 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-25 | 0.03604 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-27 | 0.029826 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-27 | 0.024234 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1335-02 | 2026-08-24 | 0.01802 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-24 | 0.034175 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-28 | 0.071458 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-24 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-24 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-24 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-24 | 0.027962 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-24 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7101-02 | 2026-08-23 | 0.023116 | 10 | 0.01 | Moca | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7101-02 | 2026-08-25 | 0.03212 | 10 | 0.01 | Moca | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-24 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-24 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-24 | 0.026719 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-24 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-24 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-24 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.017398 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1658-13 | 2026-08-26 | 0.034797 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1658-13 | 2026-08-26 | 0.021127 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1658-13 | 2026-08-24 | 0.021748 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1658-13 | 2026-08-24 | 0.019884 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1658-13 | 2026-08-24 | 0.038525 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-25 | 0.06338 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-24 | 0.037311 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1658-13 | 2026-08-24 | 0.021127 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1658-13 | 2026-08-24 | 0.019884 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1658-13 | 2026-08-24 | 0.024855 | 10 | 0.01 |  | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.034797 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1658-13 | 2026-08-24 | 0.023166 | 10 | 0.01 | Loíza | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1658-13 | 2026-08-26 | 0.034175 | 10 | 0.01 | Loíza | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2005-09 | 2026-08-24 | 0.05019 | 10 | 0.01 | Fajardo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2002-03 | 2026-08-24 | 0.050127 | 10 | 0.01 | Fajardo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2005-09 | 2026-08-27 | 0.051314 | 10 | 0.01 | Fajardo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2002-03 | 2026-08-27 | 0.05135 | 10 | 0.01 | Fajardo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5501-03 | 2026-08-24 | 0.025169 | 10 | 0.01 | Guayanilla | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-01 | 2026-08-27 | 0.025797 | 10 | 0.01 | Manatí | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-01 | 2026-08-27 | 0.030608 | 10 | 0.01 | Manatí | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-01 | 2026-08-24 | 0.024234 | 10 | 0.01 | Manatí | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 8405-01 | 2026-08-24 | 0.026719 | 10 | 0.01 | Manatí | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-27 | 0.031069 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-27 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.018641 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.01802 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.016237 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7805-13 | 2026-08-24 | 0.029204 | 10 | 0.01 | San Sebastián | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.037282 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-25 | 0.017209 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-27 | 0.026098 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-28 | 0.039323 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6501-03 | 2026-08-28 | 0.032081 | 10 | 0.01 | Sabana Grande | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.060273 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1646-02 | 2026-08-27 | 0.026001 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1602-05 | 2026-08-27 | 0.026444 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1646-02 | 2026-08-27 | 0.0099892 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-28 | 0.024234 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-28 | 0.024855 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-27 | 0.024855 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-29 | 4.2955e-06 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1530-06 | 2026-08-25 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-08-24 | 0.021312 | 10 | 0.01 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-28 | 0.03604 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-28 | 0.019789 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1720-07 | 2026-08-24 | 0.034175 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5008-04 | 2026-08-24 | 0.013049 | 10 | 0.01 | Ponce | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-25 | 0.011806 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-25 | 0.019884 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5501-03 | 2026-08-26 | 0.025476 | 10 | 0.01 | Guayanilla | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5501-03 | 2026-08-27 | 0.035418 | 10 | 0.01 | Guayanilla | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-25 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-24 | 0.027962 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-24 | 0.0088252 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-25 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-25 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-25 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-29 | 0.016906 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-25 | 0.018641 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 9703-01 | 2026-08-24 | 0.029831 | 10 | 0.01 | Comerío | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-25 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 9703-01 | 2026-08-24 | 0.027215 | 10 | 0.01 | Comerío | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-25 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-25 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-25 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-25 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-25 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-25 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-24 | 0.051574 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-25 | 0.035689 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-25 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-25 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5804-02 | 2026-08-24 | 0.019981 | 10 | 0.01 | Juana Díaz | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.033554 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-25 | 0.021294 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-25 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-25 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-01 | 2026-08-24 | 0.084506 | 10 | 0.01 | Aguada | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-25 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-25 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5501-04 | 2026-08-24 | 0.12862 | 10 | 0.01 | Guayanilla | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-27 | 0.035418 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-27 | 0.024855 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-27 | 0.022991 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-27 | 0.017398 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-27 | 0.037904 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-27 | 0.040389 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-25 | 0.020505 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-25 | 0.00094697 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-27 | 0.027962 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-27 | 0.015534 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-27 | 0.021748 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-27 | 0.034175 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.054636 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-27 | 0.03169 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-27 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-02 | 2026-08-27 | 0.024855 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-27 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-25 | 0.012971 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-27 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-25 | 0.032135 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.01379 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1203-02 | 2026-08-26 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-26 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-27 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-02 | 2026-08-24 | 0.049019 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-08-24 | 0.0092809 | 10 | 0.01 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.035418 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-24 | 0.04575 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5817-02 | 2026-08-24 | 0.03169 | 10 | 0.01 | Ponce | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5801-04 | 2026-08-24 | 0.031069 | 10 | 0.01 | Ponce | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-27 | 0.0086992 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-27 | 0.021748 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-27 | 0.013049 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-27 | 0.006835 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-27 | 0.018641 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 5018-04 | 2026-08-24 | 0.033554 | 10 | 0.01 | Ponce | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-27 | 0.024234 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-27 | 0.015534 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-27 | 0.016638 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-27 | 0.012117 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-27 | 0.007178 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-27 | 0.019262 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-27 | 0.028583 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 4601-02 | 2026-08-26 | 0.037904 | 10 | 0.01 | Santa Isabel | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 6802-05 | 2026-08-24 | 0.10376 | 10 | 0.01 | Cabo Rojo | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1525-01 | 2026-08-27 | 0.00094697 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5602-02 | 2026-08-25 | 0.037904 | 10 | 0.01 | Guánica | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5602-02 | 2026-08-25 | 0.030447 | 10 | 0.01 | Guánica | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5602-02 | 2026-08-25 | 0.042253 | 10 | 0.01 | Guánica | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5602-02 | 2026-08-25 | 0.026098 | 10 | 0.01 | Guánica | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-25 | 0.014913 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-08-25 | 0.043705 | 10 | 0.01 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-08-25 | 0.025095 | 10 | 0.01 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-27 | 0.006835 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3405-03 | 2026-08-25 | 0.015731 | 10 | 0.01 | Cayey | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3405-03 | 2026-08-25 | 0.033046 | 10 | 0.01 | Cayey | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-02 | 2026-08-25 | 0.041524 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-28 | 0.031069 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-08-25 | 4.3311e-06 | 10 | 0.01 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-08-24 | 4.3311e-06 | 10 | 0.01 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.16/7.20 | 8010-03 | 2026-08-25 | 0.06338 | 10 | 0.01 | Arecibo | Xperts | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-26 | 0.027962 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-02 | 2026-08-25 | 0.04576 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-27 | 0.027962 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-27 | 0.016156 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-27 | 0.019262 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-27 | 0.019262 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-27 | 0.01802 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-27 | 0.019884 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-26 | 0.025794 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-28 | 0.032997 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-27 | 0.028583 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-26 | 0.029204 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-26 | 0.028583 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-29 | 0.028583 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7003-03 | 2026-08-26 | 0.026719 | 10 | 0.01 | Aguadilla | Xperts | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-03 | 2026-08-25 | 0.041562 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-25 | 0.024855 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 9103-04 | 2026-08-28 | 0.031069 | 10 | 0.01 | Dorado | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-27 | 0.021748 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 9103-04 | 2026-08-26 | 0.027962 | 10 | 0.01 | Dorado | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-27 | 0.022369 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-27 | 0.022886 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8103-02 | 2026-08-25 | 0.026098 | 10 | 0.01 | Utuado | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-29 | 0.023626 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-29 | 0.030463 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-29 | 0.028699 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-29 | 0.027957 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-29 | 0.027484 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-29 | 0.029344 | 10 | 0.01 | Bayamón | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 9103-04 | 2026-08-28 | 0.024234 | 10 | 0.01 | Dorado | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 9103-04 | 2026-08-26 | 0.033554 | 10 | 0.01 | Dorado | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 9103-04 | 2026-08-28 | 0.030447 | 10 | 0.01 | Dorado | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 9103-04 | 2026-08-28 | 0.027962 | 10 | 0.01 | Dorado | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 9103-04 | 2026-08-28 | 0.031069 | 10 | 0.01 | Dorado | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 9103-04 | 2026-08-28 | 0.028583 | 10 | 0.01 | Dorado | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 9103-04 | 2026-08-26 | 0.024121 | 10 | 0.01 | Vega Alta9 | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5902-03 | 2026-08-25 | 0.049088 | 10 | 0.01 | Villalba | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 9103-04 | 2026-08-25 | 0.02946 | 10 | 0.01 | Dorado | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 9203-04 | 2026-08-25 | 0.034175 | 10 | 0.01 | Dorado | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 9203-04 | 2026-08-25 | 0.029057 | 10 | 0.01 | Dorado | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 9203-04 | 2026-08-26 | 0.027143 | 10 | 0.01 | Dorado | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 9203-04 | 2026-08-25 | 0.019262 | 10 | 0.01 | Dorado | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 9203-04 | 2026-08-25 | 0.02306 | 10 | 0.01 | Dorado | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1530-06 | 2026-08-25 | 0.022369 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.16/7.20 | 6703-01 | 2026-08-25 | 0.024058 | 10 | 0.01 | Cabo Rojo | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-25 | 0.0285 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-25 | 0.0285 | 10 | 0.01 |  | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 9004-08 | 2026-08-28 | 0.030447 | 10 | 0.01 | Vega Baja | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 9003-05 | 2026-08-28 | 0.030447 | 10 | 0.01 | Vega Baja | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 9004-08 | 2026-08-28 | 0.04101 | 10 | 0.01 | Vega Baja | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 4301-01 | 2026-08-27 | 0.046948 | 10 | 0.01 | Maunabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 4301-01 | 2026-08-27 | 0.029593 | 10 | 0.01 | Maunabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 4301-01 | 2026-08-27 | 0.098936 | 10 | 0.01 | Maunabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 4301-01 | 2026-08-27 | 0.033508 | 10 | 0.01 | Maunabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 9004-08 | 2026-08-28 | 0.04241 | 10 | 0.01 | Vega Baja | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8004-01 | 2026-08-26 | 0.028329 | 10 | 0.01 | Arecibo | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8004-01 | 2026-08-26 | 0.054321 | 10 | 0.01 | Arecibo | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8004-01 | 2026-08-26 | 0.028245 | 10 | 0.01 | Arecibo | Xperts | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 9103-04 | 2026-08-26 | 0.027655 | 10 | 0.01 | Dorado | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-02 | 2026-08-28 | 0.032616 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-02 | 2026-08-28 | 0.0299 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1658-13 | 2026-08-26 | 0.028583 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2002-03 | 2026-08-26 | 0.035811 | 10 | 0.01 | Fajardo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-02 | 2026-08-27 | 0.00094697 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-02 | 2026-08-27 | 0.032933 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3016-05 | 2026-08-26 | 0.11557 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7008-08 | 2026-08-26 | 0.064184 | 10 | 0.01 | Moca | PIS (Perfect Integrated Solutions) | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 9103-04 | 2026-08-26 | 0.026098 | 10 | 0.01 | Dorado | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 9103-04 | 2026-08-26 | 0.023152 | 10 | 0.01 | Dorado | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.01802 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.0099873 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.0285 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3014-02 | 2026-08-26 | 0.018641 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3016-05 | 2026-08-26 | 0.077671 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.025476 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3016-05 | 2026-08-26 | 0.077671 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.0086992 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.025476 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.026872 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.03376 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.037439 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.034797 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.026719 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.022991 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.022369 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.020505 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.022991 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.019884 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.024855 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.026098 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.030447 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.024855 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.026098 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.030447 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.012547 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.012547 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.031069 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.0086992 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8004-01 | 2026-08-26 | 0.040091 | 10 | 0.01 | Arecibo | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.068972 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.053438 | 10 | 0.01 | Cidra | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3013-01 | 2026-08-26 | 0.029826 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2002-03 | 2026-08-26 | 0.034175 | 10 | 0.01 | Fajardo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8602-03 | 2026-08-26 | 0.032311 | 10 | 0.01 | Florida | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.1075 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3604-06 | 2026-08-26 | 0.045981 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3016-05 | 2026-08-26 | 0.034175 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 9103-04 | 2026-08-26 | 0.028271 | 10 | 0.01 | Vega Alta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 9103-04 | 2026-08-26 | 0.028445 | 10 | 0.01 | Vega Alta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2002-03 | 2026-08-26 | 0.011806 | 10 | 0.01 | Fajardo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2002-03 | 2026-08-26 | 0.030447 | 10 | 0.01 | Fajardo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-27 | 0.029179 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-28 | 0.059918 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-27 | 0.02734 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-27 | 0.034175 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 4602-01 | 2026-08-28 | 0.054059 | 10 | 0.01 | Coamo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3302-02 | 2026-08-27 | 0.057787 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3302-02 | 2026-08-27 | 0.13546 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3302-02 | 2026-08-27 | 0.13546 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 3302-02 | 2026-08-28 | 0.033554 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-08-25 | 0.024234 | 10 | 0.01 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-08-26 | 0.030081 | 10 | 0.01 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-08-27 | 0.039584 | 10 | 0.01 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2002-03 | 2026-08-26 | 0.035952 | 10 | 0.01 | Fajardo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-08-28 | 0.03016 | 10 | 0.01 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 9202-03 | 2026-08-27 | 0.02734 | 10 | 0.01 | Dorado | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2002-03 | 2026-08-27 | 0.054998 | 10 | 0.01 | Fajardo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2005-09 | 2026-08-27 | 0.054441 | 10 | 0.01 | Fajardo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-05 | 2026-08-27 | 0.044117 | 10 | 0.01 | Trujillo Alto | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1531-02 | 2026-08-28 | 0.014291 | 10 | 0.01 | San Juan | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 9103-04 | 2026-08-27 | 0.035922 | 10 | 0.01 | Vega Alta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 9103-04 | 2026-08-27 | 0.026098 | 10 | 0.01 | Vega Alta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 9103-04 | 2026-08-27 | 0.019246 | 10 | 0.01 | Vega Alta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2002-03 | 2026-08-28 | 0.041646 | 10 | 0.01 | Luquillo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2305-02 | 2026-08-28 | 0.040259 | 10 | 0.01 | Luquillo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 9201-02 | 2026-08-27 | 0.00094697 | 10 | 0.01 | Vega Alta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5301-01 | 2026-08-27 | 0.0727 | 10 | 0.01 | Yauco | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 9201-02 | 2026-08-27 | 0.02999 | 10 | 0.01 | Vega Alta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8202-01 | 2026-08-27 | 0.044588 | 10 | 0.01 | Adjuntas | Xperts | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2305-02 | 2026-08-28 | 0.034417 | 10 | 0.01 | Luquillo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2002-03 | 2026-08-28 | 0.00094697 | 10 | 0.01 | Luquillo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 9201-02 | 2026-08-27 | 0.034683 | 10 | 0.01 | Vega Alta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2305-02 | 2026-08-28 | 0.032262 | 10 | 0.01 | Luquillo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2002-03 | 2026-08-28 | 0.032466 | 10 | 0.01 | Luquillo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.16/7.20 | 6702-02 | 2026-08-26 | 0.067108 | 10 | 0.01 | Cabo Rojo | PIS (Perfect Integrated Solutions) | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1709-05 | 2026-08-26 | 0.019262 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2803-02 | 2026-08-27 | 0.021127 | 10 | 0.01 | Humacao | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-02 | 2026-08-29 | 0.026098 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-02 | 2026-08-29 | 0.021748 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1204-02 | 2026-08-29 | 0.030447 | 10 | 0.01 | Caguas | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1909-07 | 2026-08-28 | 0.021205 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6101-04 | 2026-08-29 | 0.046603 | 10 | 0.01 | Mayaguez | Xperts | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-28 | 0.021127 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-08-28 | 0.016777 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-28 | 0.024234 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-08-28 | 0.031069 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-28 | 0.0082598 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-08-28 | 0.0086383 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-28 | 0.0092602 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-08-28 | 0.0092498 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-28 | 0.019622 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-08-28 | 0.019791 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1336-06 | 2026-08-29 | 0.015534 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1618-01 | 2026-08-29 | 0.024234 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-28 | 0.019262 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-08-28 | 0.019262 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1336-06 | 2026-08-29 | 0.0074564 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 1618-01 | 2026-08-29 | 0.0062136 | 10 | 0.01 | Carolina | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8104-02 | 2026-08-28 | 0.024038 | 10 | 0.01 | Adjuntas | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8104-02 | 2026-08-28 | 0.024038 | 10 | 0.01 | Adjuntas | Xperts | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-28 | 0.037904 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 9003-05 | 2026-08-29 | 0.029204 | 10 | 0.01 | Vega Baja | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-08-28 | 0.039768 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-28 | 0.037282 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-08-28 | 0.037904 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-28 | 0.026149 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-08-28 | 0.025476 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-28 | 0.036766 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-08-28 | 0.030811 | 10 | 0.01 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 3102-01 | 2026-08-28 | 0.037135 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-28 | 0.0055924 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-28 | 0.018641 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-28 | 0.018641 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-28 | 0.020505 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-28 | 0.021127 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-28 | 0.019262 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-28 | 0.01802 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-28 | 0.020505 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-28 | 0.021748 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-28 | 0.014291 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-28 | 0.0099419 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 8104-02 | 2026-08-28 | 0.032091 | 10 | 0.01 | Adjuntas | Xperts | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2301-01 | 2026-08-28 | 0.064001 | 10 | 0.01 | Río Grande | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 9201-02 | 2026-08-28 | 0.00094697 | 10 | 0.01 | Vega Baja | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7201-05 | 2026-08-28 | 0.060894 | 10 | 0.01 | Rincón | Xperts | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 2305-02 | 2026-08-28 | 0.031069 | 10 | 0.01 | Luquillo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2002-03 | 2026-08-28 | 0.031069 | 10 | 0.01 | Luquillo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1909-07 | 2026-08-28 | 0.021507 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 7702-03 | 2026-08-29 | 0.027988 | 10 | 0.01 | Hatillo | Xperts | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3301-02 | 2026-08-29 | 0.032311 | 10 | 0.01 | San Lorenzo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 7.62/13.20 | 1909-07 | 2026-08-29 | 0.014367 | 10 | 0.01 | Guaynabo | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.014291 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.01367 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.014913 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.021127 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.021127 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.021127 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.022991 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.01367 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.014291 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.021127 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.021748 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.013049 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.022369 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.022369 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.018641 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.021127 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.016156 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.011806 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2201-04 | 2026-08-29 | 0.042875 | 10 | 0.01 | Luquillo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.014291 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.016156 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.030447 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.021127 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.014291 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.019939 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.0099419 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.021748 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.023612 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.042253 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.023612 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.014291 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 5301-01 | 2026-08-29 | 0.057787 | 10 | 0.01 | Yauco | Wright Tree Services | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.026098 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.024684 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.025873 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.015392 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.021143 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.022123 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.011233 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 9201-02 | 2026-08-29 | 0.041571 | 10 | 0.01 | Vega Alta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.0051604 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.020505 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.024234 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.024234 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.029826 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.022991 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.01802 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.022369 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.029204 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.027962 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.030447 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.02734 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.025476 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.021748 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.023612 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.024855 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.033054 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.01726 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.036328 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.022236 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.01367 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.026456 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.015995 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 9201-02 | 2026-08-29 | 0.022991 | 10 | 0.01 | Vega Alta | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.0012428 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 3101-04 | 2026-08-29 | 0.0049803 | 10 | 0.01 | Gurabo | Wright Tree Services | In Progress | Veg Maintenance | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2201-04 | 2026-08-29 | 0.043496 | 10 | 0.01 |  | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2201-04 | 2026-08-29 | 0.042875 | 10 | 0.01 | Luquillo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 2.40/4.16 | 6101-01 | 2026-08-29 | 3.3173e-05 | 10 | 0.01 | Añasco | Xperts | In Progress | Reactive | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
N/A | 4.80/8.32 | 2701-01 | 2026-08-29 | 0.032147 | 10 | 0.01 | Naguabo | Wright Tree Services | In Progress | Corrective | Ian Kreher | O&M / Rate Payer | August | Q1 | FY2027
750067 | 2.77/4.80 | 8202-03 | 2026-08-05 | 0.0993 | 10 |  | Adjuntas | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 4.80/8.32 | 8202-03 | 2026-08-05 | 0.0986 | 10 |  | Adjuntas | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750068 | 2.40/4.16 | 7012-02 | 2026-08-19 | 0.7927 | 10 |  | Aguadilla | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750068 | 2.40/4.16 | 7012-02 | 2026-08-20 | 0.6719 | 10 |  | Aguadilla | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750068 | 2.40/4.16 | 7012-02 | 2026-08-21 | 0.9501 | 10 |  | Aguadilla | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956337 | 2.40/4.16 | 6012-02 | 2026-08-19 | 0.0297 | 10 |  | Añasco | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 4.16/7.20 | 8007-03 | 2026-08-11 | 0.0762 | 10 |  | Arecibo | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 2.40/4.16 | 8008-02 | 2026-08-11 | 0.0076 | 10 |  | Arecibo | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9602-04 | 2026-08-14 | 0.3312 | 10 |  | Barranquitas | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9602-04 | 2026-08-15 | 0.1185 | 10 |  | Barranquitas | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9602-04 | 2026-08-17 | 1.7434 | 10 |  | Barranquitas | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9602-04 | 2026-08-18 | 1.3413 | 10 |  | Barranquitas | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9602-04 | 2026-08-19 | 0.8412 | 10 |  | Barranquitas | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9602-04 | 2026-08-20 | 0.133 | 10 |  | Barranquitas | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9602-04 | 2026-08-21 | 0.8125 | 10 |  | Barranquitas | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9602-04 | 2026-08-24 | 1.5968 | 10 |  | Barranquitas | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9602-04 | 2026-08-25 | 1.6096 | 10 |  | Barranquitas | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9602-04 | 2026-08-26 | 0.3055 | 10 |  | Barranquitas | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9605-02 | 2026-08-10 | 0.2166 | 10 |  | Barranquitas | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9605-02 | 2026-08-11 | 0.1617 | 10 |  | Barranquitas | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9605-02 | 2026-08-12 | 0.6139 | 10 |  | Barranquitas | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9605-02 | 2026-08-13 | 0.3212 | 10 |  | Barranquitas | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9605-02 | 2026-08-14 | 0.0634 | 10 |  | Barranquitas | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.77/4.80 | 1701-03 | 2026-08-11 | 0.3924 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1704-04 | 2026-08-11 | 0.0897 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1704-04 | 2026-08-12 | 0.0649 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1704-04 | 2026-08-13 | 0.3519 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1704-04 | 2026-08-17 | 0.1383 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1704-04 | 2026-08-18 | 0.1031 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1704-04 | 2026-08-19 | 0.0231 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1704-04 | 2026-08-20 | 0.0495 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1704-05 | 2026-08-11 | 0.3615 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1704-05 | 2026-08-12 | 0.1767 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1704-05 | 2026-08-13 | 0.3429 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1704-05 | 2026-08-14 | 0.5974 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1704-05 | 2026-08-18 | 0.3073 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1704-05 | 2026-08-19 | 0.0992 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1704-05 | 2026-08-20 | 0.3248 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1704-05 | 2026-08-21 | 0.2781 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1704-05 | 2026-08-25 | 0.0354 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1704-05 | 2026-08-26 | 0.1936 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1705-01 | 2026-08-11 | 0.4119 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1705-01 | 2026-08-12 | 0.2014 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1705-01 | 2026-08-13 | 0.2175 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1705-01 | 2026-08-20 | 0.0005 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1705-03 | 2026-08-11 | 0.3634 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1705-03 | 2026-08-12 | 0.2742 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1705-03 | 2026-08-13 | 0.6586 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1705-03 | 2026-08-14 | 0.2533 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1705-03 | 2026-08-18 | 0.034 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1705-04 | 2026-08-18 | 0.3722 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1705-04 | 2026-08-19 | 0.0216 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1706-02 | 2026-08-11 | 1.1955 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1706-02 | 2026-08-12 | 0.2251 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1706-02 | 2026-08-13 | 0.4323 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1706-02 | 2026-08-14 | 0.13 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1706-02 | 2026-08-17 | 0.4742 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1706-02 | 2026-08-18 | 0.3306 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1706-02 | 2026-08-19 | 0.0971 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1706-02 | 2026-08-20 | 0.098 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1706-02 | 2026-08-21 | 0.0175 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1706-03 | 2026-08-12 | 0.0798 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1706-03 | 2026-08-13 | 0.5143 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1706-03 | 2026-08-17 | 0.3979 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1706-03 | 2026-08-18 | 0.2892 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1706-05 | 2026-08-12 | 0.0053 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1707-02 | 2026-08-11 | 0.0236 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1707-02 | 2026-08-12 | 0.097 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1710-01 | 2026-08-13 | 0.1368 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1710-01 | 2026-08-14 | 0.3942 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1710-01 | 2026-08-18 | 0.1644 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 7.62/13.20 | 1710-01 | 2026-08-18 | 0.8259 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 7.62/13.20 | 1710-01 | 2026-08-19 | 0.7368 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1710-01 | 2026-08-20 | 0.5643 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 7.62/13.20 | 1710-01 | 2026-08-20 | 0.5301 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1710-01 | 2026-08-21 | 0.4198 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 7.62/13.20 | 1710-01 | 2026-08-21 | 0.4266 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1710-01 | 2026-08-25 | 0.0485 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 7.62/13.20 | 1710-01 | 2026-08-25 | 1.6258 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 7.62/13.20 | 1710-01 | 2026-08-26 | 1.7104 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 7.62/13.20 | 1710-01 | 2026-08-27 | 1.6968 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 7.62/13.20 | 1710-01 | 2026-08-28 | 0.1341 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 7.62/13.20 | 1710-04 | 2026-08-19 | 0.277 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 7.62/13.20 | 1710-04 | 2026-08-20 | 1.3129 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 7.62/13.20 | 1710-04 | 2026-08-21 | 1.0207 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 7.62/13.20 | 1710-04 | 2026-08-25 | 1.2692 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 7.62/13.20 | 1710-04 | 2026-08-26 | 0.5114 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 7.62/13.20 | 1711-05 | 2026-08-20 | 0.1525 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 7.62/13.20 | 1711-05 | 2026-08-24 | 0.518 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 7.62/13.20 | 1711-05 | 2026-08-25 | 0.4032 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 7.62/13.20 | 1713-04 | 2026-08-25 | 0.132 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1714-03 | 2026-08-19 | 0.6862 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1714-03 | 2026-08-20 | 0.4877 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1714-05 | 2026-08-20 | 0.213 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1714-05 | 2026-08-24 | 0.4668 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1714-05 | 2026-08-25 | 0.2536 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1714-05 | 2026-08-26 | 0.1446 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1714-05 | 2026-08-27 | 0.1007 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1715-03 | 2026-08-27 | 0.1977 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 7.62/13.20 | 1716-01 | 2026-08-21 | 0.4376 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 7.62/13.20 | 1717-02 | 2026-08-24 | 0.32 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 7.62/13.20 | 1717-05 | 2026-08-24 | 0.0586 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 7.62/13.20 | 1717-05 | 2026-08-25 | 0.4819 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 7.62/13.20 | 1718-01 | 2026-08-25 | 0.0592 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 7.62/13.20 | 1718-01 | 2026-08-26 | 0.2664 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 7.62/13.20 | 1718-03 | 2026-08-27 | 0.0168 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 7.62/13.20 | 1719-15 | 2026-08-25 | 0.0355 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 7.62/13.20 | 1719-15 | 2026-08-26 | 1.3357 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 7.62/13.20 | 1719-15 | 2026-08-27 | 1.7209 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 7.62/13.20 | 1719-15 | 2026-08-28 | 0.8532 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 7.62/13.20 | 1719-15 | 2026-08-29 | 0.0261 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 7.62/13.20 | 1719-15 | 2026-08-31 | 0.7066 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 7.62/13.20 | 1719-18 | 2026-08-09 | 0.0344 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 7.62/13.20 | 1801-05 | 2026-08-31 | 0.0412 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 7.62/13.20 | 1710-01 | 2026-08-20 | 0.0333 | 10 |  | Bayamón0 | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 2.40/4.16 | 3014-01 | 2026-08-03 | 0.4468 | 10 |  | Caguas | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 2.40/4.16 | 7402-01 | 2026-08-10 | 0.0451 | 10 |  | Camuy | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 2.40/4.16 | 7402-01 | 2026-08-11 | 0.8782 | 10 |  | Camuy | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 2.40/4.16 | 7402-01 | 2026-08-12 | 0.4655 | 10 |  | Camuy | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 2.40/4.16 | 7402-01 | 2026-08-13 | 0.0369 | 10 |  | Camuy | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 2.40/4.16 | 7402-01 | 2026-08-17 | 0.704 | 10 |  | Camuy | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 2.40/4.16 | 7402-01 | 2026-08-18 | 0.1714 | 10 |  | Camuy | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 2.40/4.16 | 7402-01 | 2026-08-19 | 0.2622 | 10 |  | Camuy | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 2.40/4.16 | 7402-01 | 2026-08-20 | 0.5881 | 10 |  | Camuy | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 2.40/4.16 | 7402-01 | 2026-08-24 | 0.6447 | 10 |  | Camuy | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 2.40/4.16 | 7402-01 | 2026-08-25 | 0.1831 | 10 |  | Camuy | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 2.40/4.16 | 7402-01 | 2026-08-26 | 0.3736 | 10 |  | Camuy | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 2.40/4.16 | 7402-01 | 2026-08-27 | 0.0017 | 10 |  | Camuy | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956332 | 4.80/8.32 | 2401-01 | 2026-08-03 | 0.8351 | 10 |  | Canóvanas | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956332 | 4.80/8.32 | 2401-01 | 2026-08-04 | 1.782 | 10 |  | Canóvanas | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956332 | 4.80/8.32 | 2401-01 | 2026-08-05 | 1.1876 | 10 |  | Canóvanas | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956332 | 4.80/8.32 | 2401-01 | 2026-08-06 | 1.6351 | 10 |  | Canóvanas | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956332 | 4.80/8.32 | 2401-01 | 2026-08-07 | 1.3512 | 10 |  | Canóvanas | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956332 | 4.80/8.32 | 2401-01 | 2026-08-10 | 1.1372 | 10 |  | Canóvanas | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956332 | 4.80/8.32 | 2401-01 | 2026-08-11 | 0.2622 | 10 |  | Canóvanas | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956332 | 4.80/8.32 | 2401-01 | 2026-08-12 | 0.0384 | 10 |  | Canóvanas | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956332 | 4.80/8.32 | 2401-01 | 2026-08-13 | 0.1362 | 10 |  | Canóvanas | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956332 | 4.80/8.32 | 2401-01 | 2026-08-14 | 0.1115 | 10 |  | Canóvanas | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956332 | 4.80/8.32 | 2401-01 | 2026-08-17 | 0.1479 | 10 |  | Canóvanas | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956332 | 4.80/8.32 | 2401-01 | 2026-08-18 | 0.0145 | 10 |  | Canóvanas | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956332 | 4.80/8.32 | 2401-01 | 2026-08-19 | 0.0089 | 10 |  | Canóvanas | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956332 | 4.80/8.32 | 2401-01 | 2026-08-20 | 0.0259 | 10 |  | Canóvanas | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956332 | 4.80/8.32 | 2401-01 | 2026-08-21 | 0.1928 | 10 |  | Canóvanas | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956332 | 4.80/8.32 | 2401-01 | 2026-08-24 | 0.1884 | 10 |  | Canóvanas | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956332 | 4.80/8.32 | 2401-01 | 2026-08-25 | 0.2017 | 10 |  | Canóvanas | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956332 | 4.80/8.32 | 2401-01 | 2026-08-26 | 0.2357 | 10 |  | Canóvanas | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956332 | 4.80/8.32 | 2401-01 | 2026-08-27 | 0.3479 | 10 |  | Canóvanas | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956332 | 4.80/8.32 | 2401-01 | 2026-08-28 | 0.308 | 10 |  | Canóvanas | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 7.62/13.20 | 1801-05 | 2026-08-31 | 1.1667 | 10 |  | Cataño | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9602-04 | 2026-08-17 | 0.0443 | 10 |  | Coamo | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9602-04 | 2026-08-18 | 0.1873 | 10 |  | Coamo | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9602-04 | 2026-08-19 | 1.133 | 10 |  | Coamo | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9602-04 | 2026-08-20 | 0.6784 | 10 |  | Coamo | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727692 | 4.80/8.32 | 9605-02 | 2026-08-06 | 0.0144 | 10 |  | Comerío | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9605-02 | 2026-08-04 | 0.3209 | 10 |  | Comerío | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9605-02 | 2026-08-05 | 0.396 | 10 |  | Comerío | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9605-02 | 2026-08-06 | 0.607 | 10 |  | Comerío | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9605-02 | 2026-08-07 | 0.3044 | 10 |  | Comerío | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9605-02 | 2026-08-10 | 0.6565 | 10 |  | Comerío | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9605-02 | 2026-08-11 | 0.6073 | 10 |  | Comerío | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9605-02 | 2026-08-12 | 0.29 | 10 |  | Comerío | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9605-02 | 2026-08-13 | 0.6568 | 10 |  | Comerío | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9703-01 | 2026-08-26 | 0.7231 | 10 |  | Comerío | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9703-01 | 2026-08-27 | 1.7393 | 10 |  | Comerío | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9703-01 | 2026-08-28 | 2.5463 | 10 |  | Comerío | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9703-01 | 2026-08-29 | 0.4124 | 10 |  | Comerío | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9703-01 | 2026-08-31 | 1.9334 | 10 |  | Comerío | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9703-02 | 2026-08-31 | 0.6082 | 10 |  | Comerío | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750065 | 4.80/8.32 | 9501-02 | 2026-08-05 | 0.0038 | 10 |  | Corozal | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9605-02 | 2026-08-03 | 0.1468 | 10 |  | Corozal | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9605-02 | 2026-08-04 | 0.187 | 10 |  | Corozal | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9605-02 | 2026-08-05 | 0.172 | 10 |  | Corozal | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9605-02 | 2026-08-06 | 0.0506 | 10 |  | Corozal | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9605-02 | 2026-08-07 | 0.1806 | 10 |  | Corozal | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9605-02 | 2026-08-10 | 0.0368 | 10 |  | Corozal | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9605-02 | 2026-08-11 | 0.284 | 10 |  | Corozal | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9605-02 | 2026-08-12 | 0.0896 | 10 |  | Corozal | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9605-02 | 2026-08-13 | 0.7333 | 10 |  | Corozal | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9605-02 | 2026-08-14 | 0.6686 | 10 |  | Corozal | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9605-02 | 2026-08-17 | 0.0364 | 10 |  | Corozal | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 4.80/8.32 | 9201-01 | 2026-08-11 | 0.1408 | 10 |  | Dorado | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956340 | 7.62/13.20 | 5602-02 | 2026-08-24 | 0.0267 | 10 |  | Guaníca | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956340 | 2.40/4.16 | 5602-02 | 2026-08-19 | 0.7133 | 10 |  | Guánica | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956340 | 2.40/4.16 | 5602-02 | 2026-08-20 | 0.4383 | 10 |  | Guánica | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956340 | 2.40/4.16 | 5602-02 | 2026-08-24 | 0.0465 | 10 |  | Guánica | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956340 | 7.62/13.20 | 5602-02 | 2026-08-24 | 0.4997 | 10 |  | Guánica | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956340 | 2.40/4.16 | 5602-02 | 2026-08-25 | 0.5425 | 10 |  | Guánica | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 7.62/13.20 | 1711-05 | 2026-08-20 | 0.0728 | 10 |  | Guaynabo | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 7.62/13.20 | 1711-05 | 2026-08-24 | 0.0649 | 10 |  | Guaynabo | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 7.62/13.20 | 1711-05 | 2026-08-25 | 0.0621 | 10 |  | Guaynabo | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956332 | 4.80/8.32 | 2401-01 | 2026-08-07 | 0.0444 | 10 |  | Juncos | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750068 | 7.62/13.20 | 7903-06 | 2026-08-13 | 0.03 | 10 |  | Lares | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750068 | 7.62/13.20 | 7903-06 | 2026-08-14 | 0.4634 | 10 |  | Lares | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750068 | 7.62/13.20 | 7903-06 | 2026-08-15 | 0.328 | 10 |  | Lares | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750068 | 7.62/13.20 | 7903-06 | 2026-08-17 | 0.1213 | 10 |  | Lares | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750068 | 7.62/13.20 | 7903-06 | 2026-08-18 | 0.1253 | 10 |  | Lares | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750068 | 7.62/13.20 | 7903-06 | 2026-08-19 | 0.1449 | 10 |  | Lares | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750068 | 7.62/13.20 | 7903-06 | 2026-08-20 | 0.2246 | 10 |  | Lares | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750068 | 7.62/13.20 | 7903-06 | 2026-08-21 | 0.2438 | 10 |  | Lares | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750068 | 7.62/13.20 | 7903-06 | 2026-08-24 | 0.1108 | 10 |  | Lares | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750068 | 7.62/13.20 | 7903-06 | 2026-08-25 | 0.1541 | 10 |  | Lares | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956331 | 2.40/4.16 | 6014-02 | 2026-08-10 | 0.0198 | 10 |  | Las Marías | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956331 | 2.40/4.16 | 6014-02 | 2026-08-13 | 0.1108 | 10 |  | Las Marías | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956331 | 2.40/4.16 | 6014-02 | 2026-08-17 | 0.0131 | 10 |  | Las Marías | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956331 | 2.40/4.16 | 6014-02 | 2026-08-20 | 0.0411 | 10 |  | Las Marías | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750068 | 2.40/4.16 | 6201-01 | 2026-08-03 | 0.1881 | 10 |  | Las Marías | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750068 | 2.40/4.16 | 6201-01 | 2026-08-04 | 0.3172 | 10 |  | Las Marías | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750068 | 2.40/4.16 | 6201-01 | 2026-08-05 | 0.3916 | 10 |  | Las Marías | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750068 | 2.40/4.16 | 6201-01 | 2026-08-06 | 0.0026 | 10 |  | Las Marías | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750068 | 2.40/4.16 | 6201-01 | 2026-08-07 | 0.2393 | 10 |  | Las Marías | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750068 | 2.40/4.16 | 6201-01 | 2026-08-10 | 0.4115 | 10 |  | Las Marías | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750068 | 2.40/4.16 | 6201-01 | 2026-08-11 | 0.365 | 10 |  | Las Marías | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750068 | 2.40/4.16 | 6201-01 | 2026-08-12 | 0.5568 | 10 |  | Las Marías | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750068 | 2.40/4.16 | 6201-01 | 2026-08-13 | 0.006 | 10 |  | Las Marías | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750068 | 7.62/13.20 | 7903-06 | 2026-08-17 | 0.0473 | 10 |  | Las Marías | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750068 | 2.40/4.16 | 6010-03 | 2026-08-25 | 0.1994 | 10 |  | Mayagüez | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750068 | 2.40/4.16 | 6010-03 | 2026-08-26 | 1.314 | 10 |  | Mayagüez | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750068 | 2.40/4.16 | 6010-03 | 2026-08-27 | 0.2454 | 10 |  | Mayagüez | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750068 | 2.40/4.16 | 6010-03 | 2026-08-28 | 0.0502 | 10 |  | Mayagüez | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750068 | 7.62/13.20 | 6012-01 | 2026-08-21 | 0.0337 | 10 |  | Mayagüez | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750068 | 7.62/13.20 | 7903-06 | 2026-08-19 | 0.1943 | 10 |  | Mayagüez | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750068 | 7.62/13.20 | 7903-06 | 2026-08-20 | 0.1215 | 10 |  | Mayagüez | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956337 | 2.40/4.16 | 6012-02 | 2026-08-17 | 0.0258 | 10 |  | Moca | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956337 | 2.40/4.16 | 6012-02 | 2026-08-24 | 0.0316 | 10 |  | Moca | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956337 | 2.40/4.16 | 6012-02 | 2026-08-27 | 0.0316 | 10 |  | Moca | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 4.80/8.32 | 9003-06 | 2026-08-06 | 0.0396 | 10 |  | Morovis | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750065 | 4.80/8.32 | 9802-04 | 2026-08-05 | 0.0711 | 10 |  | Naranjito | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9605-02 | 2026-08-03 | 0.4536 | 10 |  | Naranjito | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9605-02 | 2026-08-04 | 0.6482 | 10 |  | Naranjito | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9605-02 | 2026-08-05 | 0.5513 | 10 |  | Naranjito | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9605-02 | 2026-08-06 | 0.9462 | 10 |  | Naranjito | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9605-02 | 2026-08-07 | 0.7203 | 10 |  | Naranjito | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9605-02 | 2026-08-10 | 0.606 | 10 |  | Naranjito | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9605-02 | 2026-08-11 | 1.2309 | 10 |  | Naranjito | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9605-02 | 2026-08-12 | 0.4437 | 10 |  | Naranjito | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9605-02 | 2026-08-13 | 0.1481 | 10 |  | Naranjito | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9605-02 | 2026-08-14 | 0.0362 | 10 |  | Naranjito | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9602-04 | 2026-08-17 | 0.2461 | 10 |  | Orocovis | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9602-04 | 2026-08-19 | 0.0219 | 10 |  | Orocovis | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9602-04 | 2026-08-21 | 0.0668 | 10 |  | Orocovis | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9602-04 | 2026-08-24 | 0.1713 | 10 |  | Orocovis | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9602-04 | 2026-08-25 | 0.9901 | 10 |  | Orocovis | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9602-04 | 2026-08-26 | 1.4722 | 10 |  | Orocovis | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9602-04 | 2026-08-28 | 0.2324 | 10 |  | Orocovis | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 9602-04 | 2026-08-29 | 0.1306 | 10 |  | Orocovis | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 2.40/4.16 | 7402-01 | 2026-08-10 | 0.0197 | 10 |  | Quebradilla | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 2.40/4.16 | 7402-01 | 2026-08-06 | 1.7421 | 10 |  | Quebradillas | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 2.40/4.16 | 7402-01 | 2026-08-10 | 2.4276 | 10 |  | Quebradillas | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 2.40/4.16 | 7402-01 | 2026-08-11 | 0.1778 | 10 |  | Quebradillas | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 2.40/4.16 | 7402-01 | 2026-08-12 | 0.5923 | 10 |  | Quebradillas | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 2.40/4.16 | 7402-01 | 2026-08-13 | 0.4748 | 10 |  | Quebradillas | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 2.40/4.16 | 7402-01 | 2026-08-17 | 0.2272 | 10 |  | Quebradillas | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 2.40/4.16 | 7402-01 | 2026-08-18 | 0.4804 | 10 |  | Quebradillas | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 2.40/4.16 | 7402-01 | 2026-08-19 | 0.0283 | 10 |  | Quebradillas | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 2.40/4.16 | 7402-01 | 2026-08-20 | 0.0398 | 10 |  | Quebradillas | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 2.40/4.16 | 7402-01 | 2026-08-24 | 0.1184 | 10 |  | Quebradillas | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 2.40/4.16 | 7402-01 | 2026-08-25 | 0.0904 | 10 |  | Quebradillas | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 2.40/4.16 | 7402-01 | 2026-08-27 | 0.0842 | 10 |  | Quebradillas | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956332 | 4.80/8.32 | 2401-01 | 2026-08-03 | 0.0606 | 10 |  | Río Grande | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956332 | 4.80/8.32 | 2401-01 | 2026-08-04 | 0.0633 | 10 |  | Río Grande | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956332 | 4.80/8.32 | 2401-01 | 2026-08-05 | 0.0336 | 10 |  | Río Grande | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956332 | 4.80/8.32 | 2401-01 | 2026-08-10 | 0.0827 | 10 |  | Río Grande | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956332 | 4.80/8.32 | 2401-01 | 2026-08-26 | 0.0344 | 10 |  | Río Grande | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 4.80/8.32 | 9201-01 | 2026-08-11 | 0.0214 | 10 |  | San Juan | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956339 | 4.80/8.32 | 3301-01 | 2026-08-24 | 0.0317 | 10 |  | San Lorenzo | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956339 | 4.80/8.32 | 3301-01 | 2026-08-25 | 0.0392 | 10 |  | San Lorenzo | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750068 | 2.40/4.16 | 7801-01 | 2026-08-28 | 1.6041 | 10 |  | San Sebastián | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750068 | 2.40/4.16 | 7801-01 | 2026-08-29 | 0.6777 | 10 |  | San Sebastián | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750068 | 2.40/4.16 | 7801-01 | 2026-08-31 | 1.3708 | 10 |  | San Sebastián | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750068 | 7.62/13.20 | 7903-06 | 2026-08-20 | 0.0255 | 10 |  | San Sebastián | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 7.62/13.20 | 1719-15 | 2026-08-27 | 0.1321 | 10 |  | Toa Alta | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 7.62/13.20 | 1719-15 | 2026-08-28 | 0.2317 | 10 |  | Toa Alta | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 7.62/13.20 | 1719-18 | 2026-08-28 | 0.8324 | 10 |  | Toa Alta | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 7.62/13.20 | 1718-01 | 2026-08-26 | 0.4918 | 10 |  | Toa Baja | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 7.62/13.20 | 1718-01 | 2026-08-27 | 0.5047 | 10 |  | Toa Baja | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 7.62/13.20 | 1718-01 | 2026-08-28 | 0.6181 | 10 |  | Toa Baja | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 7.62/13.20 | 1718-03 | 2026-08-27 | 1.1861 | 10 |  | Toa Baja | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 7.62/13.20 | 1718-03 | 2026-08-28 | 0.6997 | 10 |  | Toa Baja | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 7.62/13.20 | 1718-04 | 2026-08-27 | 0.0891 | 10 |  | Toa Baja | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 2.40/4.16 | 8101-04 | 2026-08-11 | 0.1535 | 10 |  | Utuado | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 2.40/4.16 | 8101-04 | 2026-08-12 | 0.0402 | 10 |  | Utuado | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 2.40/4.16 | 8101-04 | 2026-08-13 | 0.3719 | 10 |  | Utuado | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 2.40/4.16 | 8101-04 | 2026-08-17 | 0.0517 | 10 |  | Utuado | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 4.80/8.32 | 8101-04 | 2026-08-17 | 0.1583 | 10 |  | Utuado | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 2.40/4.16 | 8101-04 | 2026-08-18 | 0.3482 | 10 |  | Utuado | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 4.80/8.32 | 8101-04 | 2026-08-18 | 0.1934 | 10 |  | Utuado | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 2.40/4.16 | 8101-04 | 2026-08-19 | 0.028 | 10 |  | Utuado | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 4.80/8.32 | 8101-04 | 2026-08-19 | 0.7578 | 10 |  | Utuado | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 2.40/4.16 | 8101-04 | 2026-08-20 | 0.1129 | 10 |  | Utuado | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 2.40/4.16 | 8101-04 | 2026-08-24 | 0.08 | 10 |  | Utuado | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 2.40/4.16 | 8101-04 | 2026-08-25 | 0.0212 | 10 |  | Utuado | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 4.80/8.32 | 8101-04 | 2026-08-25 | 0.0275 | 10 |  | Utuado | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 4.80/8.32 | 9001-01 | 2026-08-03 | 0.3854 | 10 |  | Vega Baja | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 4.80/8.32 | 9001-01 | 2026-08-04 | 0.4102 | 10 |  | Vega Baja | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 4.80/8.32 | 9001-01 | 2026-08-05 | 0.1624 | 10 |  | Vega Baja | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 4.80/8.32 | 9001-01 | 2026-08-06 | 0.0079 | 10 |  | Vega Baja | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 4.80/8.32 | 9003-06 | 2026-08-03 | 0.4587 | 10 |  | Vega Baja | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 4.80/8.32 | 9003-06 | 2026-08-04 | 0.068 | 10 |  | Vega Baja | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 4.80/8.32 | 9003-06 | 2026-08-05 | 0.3235 | 10 |  | Vega Baja | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 4.80/8.32 | 9003-06 | 2026-08-06 | 0.3458 | 10 |  | Vega Baja | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 4.80/8.32 | 9003-06 | 2026-08-10 | 0.0495 | 10 |  | Vega Baja | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 4.80/8.32 | 9003-06 | 2026-08-11 | 0.1314 | 10 |  | Vega Baja | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 4.80/8.32 | 9003-06 | 2026-08-13 | 0.4478 | 10 |  | Vega Baja | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 4.80/8.32 | 9003-06 | 2026-08-17 | 0.087 | 10 |  | Vega Baja | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 4.80/8.32 | 9003-06 | 2026-08-18 | 0.0682 | 10 |  | Vega Baja | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 4.80/8.32 | 9003-06 | 2026-08-19 | 0.2586 | 10 |  | Vega Baja | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 4.80/8.32 | 9003-06 | 2026-08-20 | 0.5977 | 10 |  | Vega Baja | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 4.80/8.32 | 9003-06 | 2026-08-24 | 0.1222 | 10 |  | Vega Baja | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 4.80/8.32 | 9003-06 | 2026-08-25 | 0.0782 | 10 |  | Vega Baja | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 4.80/8.32 | 9003-06 | 2026-08-26 | 0.2005 | 10 |  | Vega Baja | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 2.40/4.16 | 8011-01 | 2026-08-05 | 0.0756 | 10 |  | Arecibo | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 2.40/4.16 | 8011-01 | 2026-08-10 | 0.1401 | 10 |  | Arecibo | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 2.40/4.16 | 8011-01 | 2026-08-11 | 0.1556 | 10 |  | Arecibo | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 2.40/4.16 | 8011-01 | 2026-08-12 | 0.0513 | 10 |  | Arecibo | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 2.40/4.16 | 8011-01 | 2026-08-17 | 0.0209 | 10 |  | Arecibo | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 2.40/4.16 | 8011-01 | 2026-08-19 | 0.0784 | 10 |  | Arecibo | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 2.40/4.16 | 8011-01 | 2026-08-25 | 0.0622 | 10 |  | Arecibo | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 2.40/4.16 | 8011-01 | 2026-08-20 | 0.0266 | 10 |  | Arecibo | LUMA | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 2.40/4.16 | 8602-01 | 2026-08-03 | 0.1031 | 10 |  | Florida | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 2.40/4.16 | 8602-01 | 2026-08-04 | 0.2257 | 10 |  | Florida | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 2.40/4.16 | 8602-01 | 2026-08-10 | 0.0139 | 10 |  | Florida | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 2.40/4.16 | 8602-01 | 2026-08-11 | 0.1331 | 10 |  | Florida | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 2.40/4.16 | 8602-01 | 2026-08-12 | 0.0747 | 10 |  | Florida | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 2.40/4.16 | 8602-01 | 2026-08-13 | 0.0692 | 10 |  | Florida | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 2.40/4.16 | 8602-01 | 2026-08-17 | 0.1622 | 10 |  | Florida | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 2.40/4.16 | 8602-01 | 2026-08-18 | 0.1136 | 10 |  | Florida | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 2.40/4.16 | 8602-01 | 2026-08-20 | 0.1614 | 10 |  | Florida | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 2.40/4.16 | 8602-01 | 2026-08-24 | 0.1168 | 10 |  | Florida | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 2.40/4.16 | 8602-01 | 2026-08-25 | 0.2019 | 10 |  | Florida | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 2.40/4.16 | 8602-01 | 2026-08-26 | 0.1628 | 10 |  | Florida | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 2.40/4.16 | 8602-01 | 2026-08-27 | 0.1116 | 10 |  | Florida | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 4.80/8.32 | 8701-01 | 2026-08-03 | 0.2172 | 10 |  | Ciales | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 4.80/8.32 | 8701-01 | 2026-08-04 | 0.064 | 10 |  | Ciales | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 4.80/8.32 | 8701-01 | 2026-08-05 | 0.1471 | 10 |  | Ciales | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 4.80/8.32 | 8701-01 | 2026-08-10 | 0.0778 | 10 |  | Ciales | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 4.80/8.32 | 8701-01 | 2026-08-11 | 0.0375 | 10 |  | Ciales | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 4.80/8.32 | 8701-01 | 2026-08-12 | 0.1671 | 10 |  | Ciales | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 4.80/8.32 | 8701-01 | 2026-08-13 | 0.0895 | 10 |  | Ciales | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 4.80/8.32 | 8701-01 | 2026-08-17 | 0.0405 | 10 |  | Ciales | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 4.80/8.32 | 8701-01 | 2026-08-18 | 0.1925 | 10 |  | Ciales | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 4.80/8.32 | 8701-01 | 2026-08-20 | 0.1951 | 10 |  | Ciales | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 4.80/8.32 | 8701-01 | 2026-08-25 | 0.1811 | 10 |  | Ciales | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 4.80/8.32 | 8701-01 | 2026-08-26 | 0.1282 | 10 |  | Ciales | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 4.80/8.32 | 8701-01 | 2026-08-27 | 0.0967 | 10 |  | Ciales | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 4.80/8.32 | 9003-06 | 2026-08-03 | 0.0555 | 10 |  | Vega Baja | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 4.80/8.32 | 9003-06 | 2026-08-04 | 0.0827 | 10 |  | Vega Baja | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 4.80/8.32 | 9003-06 | 2026-08-05 | 0.0902 | 10 |  | Vega Baja | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 4.80/8.32 | 9003-06 | 2026-08-06 | 0.1371 | 10 |  | Vega Baja | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 4.80/8.32 | 9003-06 | 2026-08-10 | 0.0182 | 10 |  | Vega Baja | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 4.80/8.32 | 9003-06 | 2026-08-11 | 0.0448 | 10 |  | Vega Baja | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 4.80/8.32 | 9003-06 | 2026-08-12 | 0.0372 | 10 |  | Vega Baja | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 4.80/8.32 | 9003-06 | 2026-08-13 | 0.1159 | 10 |  | Vega Baja | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 4.80/8.32 | 9003-06 | 2026-08-16 | 0.0413 | 10 |  | Vega Baja | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 4.80/8.32 | 9003-06 | 2026-08-17 | 0.0394 | 10 |  | Vega Baja | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 4.80/8.32 | 9003-06 | 2026-08-18 | 0.2886 | 10 |  | Vega Baja | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 4.80/8.32 | 9003-06 | 2026-08-19 | 0.0494 | 10 |  | Vega Baja | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 4.80/8.32 | 9003-06 | 2026-08-20 | 0.0656 | 10 |  | Vega Baja | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 4.80/8.32 | 9003-06 | 2026-08-24 | 0.0955 | 10 |  | Vega Baja | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 4.80/8.32 | 9003-06 | 2026-08-25 | 0.1595 | 10 |  | Vega Baja | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 4.80/8.32 | 9003-06 | 2026-08-26 | 0.1742 | 10 |  | Vega Baja | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 4.80/8.32 | 9003-06 | 2026-08-27 | 0.0991 | 10 |  | Vega Baja | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1708-04 | 2026-08-02 | 0.0317 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1708-04 | 2026-08-10 | 0.1063 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1708-04 | 2026-08-11 | 0.1007 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1708-04 | 2026-08-18 | 0.0746 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1708-04 | 2026-08-19 | 0.0858 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1708-04 | 2026-08-20 | 0.0976 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1708-04 | 2026-08-21 | 0.0802 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1708-04 | 2026-08-25 | 0.0193 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1708-04 | 2026-08-27 | 0.0472 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1708-04 | 2026-08-31 | 0.0379 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1708-05 | 2026-08-11 | 0.0162 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1708-05 | 2026-08-18 | 0.0646 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1708-05 | 2026-08-26 | 0.0242 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 2.40/4.16 | 1708-05 | 2026-08-27 | 0.0217 | 10 |  | Bayamón | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727572 | 4.80/8.32 | 9103-01 | 2026-08-14 | 0.0242 | 10 |  | Dorado | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750065 | 4.80/8.32 | 9103-01 | 2026-08-14 | 0.2675 | 10 |  | Dorado | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750065 | 4.80/8.32 | 9103-01 | 2026-08-26 | 0.1474 | 10 |  | Dorado | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750065 | 4.80/8.32 | 9103-01 | 2026-08-28 | 0.0802 | 10 |  | Dorado | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750065 | 4.80/8.32 | 9103-01 | 2026-08-14 | 0.1762 | 10 |  | Toa Alta | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750065 | 4.80/8.32 | 9103-01 | 2026-08-26 | 0.0193 | 10 |  | Toa Alta | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750065 | 4.80/8.32 | 9103-01 | 2026-08-27 | 0.0352 | 10 |  | Toa Alta | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750065 | 4.80/8.32 | 9103-01 | 2026-08-14 | 0.1452 | 10 |  | Vega Alta | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750065 | 7.62/13.20 | 9405-09 | 2026-08-11 | 0.0955 | 10 |  | Toa Alta | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750065 | 7.62/13.20 | 9405-09 | 2026-08-21 | 0.1783 | 10 |  | Toa Alta | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750065 | 2.40/4.16 | 9405-09 | 2026-08-26 | 0.1261 | 10 |  | Toa Alta | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750065 | 7.62/13.20 | 9405-09 | 2026-08-26 | 0.0307 | 10 |  | Toa Alta | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750065 | 2.40/4.16 | 9405-09 | 2026-08-27 | 0.0385 | 10 |  | Toa Alta | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
727692 | 4.80/8.32 | 3009-04 | 2026-08-26 | 0.0236 | 10 |  | Caguas | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956339 | 4.80/8.32 | 3301-01 | 2026-08-17 | 0.034 | 10 |  | San Lorenzo | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956339 | 4.80/8.32 | 3301-01 | 2026-08-25 | 0.1189 | 10 |  | San Lorenzo | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956339 | 4.80/8.32 | 3301-01 | 2026-08-26 | 0.0977 | 10 |  | San Lorenzo | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956339 | 4.80/8.32 | 3301-01 | 2026-08-29 | 0.1088 | 10 |  | San Lorenzo | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3502-02 | 2026-08-03 | 0.1554 | 10 |  | Aibonito | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3502-02 | 2026-08-04 | 0.1435 | 10 |  | Aibonito | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3502-02 | 2026-08-07 | 0.046 | 10 |  | Aibonito | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3502-02 | 2026-08-08 | 0.2817 | 10 |  | Aibonito | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3502-02 | 2026-08-10 | 0.2649 | 10 |  | Aibonito | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3502-02 | 2026-08-12 | 0.1901 | 10 |  | Aibonito | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3502-02 | 2026-08-13 | 0.2061 | 10 |  | Aibonito | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3502-02 | 2026-08-14 | 0.2081 | 10 |  | Aibonito | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3502-02 | 2026-08-18 | 0.0767 | 10 |  | Aibonito | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3502-02 | 2026-08-19 | 0.1143 | 10 |  | Aibonito | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3502-02 | 2026-08-20 | 0.3153 | 10 |  | Aibonito | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3502-02 | 2026-08-21 | 0.2175 | 10 |  | Aibonito | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3502-02 | 2026-08-26 | 0.1456 | 10 |  | Aibonito | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3502-02 | 2026-08-28 | 0.1106 | 10 |  | Aibonito | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3502-02 | 2026-08-29 | 0.085 | 10 |  | Aibonito | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3502-02 | 2026-08-30 | 0.0502 | 10 |  | Aibonito | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3601-01 | 2026-08-04 | 0.0388 | 10 |  | Cidra | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3601-01 | 2026-08-05 | 0.0235 | 10 |  | Cidra | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3601-01 | 2026-08-06 | 0.0463 | 10 |  | Cidra | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3601-01 | 2026-08-08 | 0.0659 | 10 |  | Cidra | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3601-01 | 2026-08-10 | 0.0217 | 10 |  | Cidra | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3601-03 | 2026-08-03 | 0.0744 | 10 |  | Cidra | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3601-04 | 2026-08-03 | 0.0762 | 10 |  | Aguas Buenas | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3601-04 | 2026-08-04 | 0.0751 | 10 |  | Aguas Buenas | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3601-04 | 2026-08-05 | 0.059 | 10 |  | Aguas Buenas | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3601-04 | 2026-08-07 | 0.0822 | 10 |  | Aguas Buenas | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3601-04 | 2026-08-10 | 0.0935 | 10 |  | Aguas Buenas | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3601-04 | 2026-08-17 | 0.0161 | 10 |  | Aguas Buenas | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3601-04 | 2026-08-18 | 0.0358 | 10 |  | Aguas Buenas | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3601-04 | 2026-08-19 | 0.0414 | 10 |  | Aguas Buenas | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3601-04 | 2026-08-25 | 0.034 | 10 |  | Aguas Buenas | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3601-04 | 2026-08-02 | 0.0509 | 10 |  | Cidra | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3601-04 | 2026-08-04 | 0.1667 | 10 |  | Cidra | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3601-04 | 2026-08-05 | 0.1464 | 10 |  | Cidra | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3601-04 | 2026-08-07 | 0.2994 | 10 |  | Cidra | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3601-04 | 2026-08-08 | 0.1251 | 10 |  | Cidra | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3601-04 | 2026-08-10 | 0.5638 | 10 |  | Cidra | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3601-04 | 2026-08-13 | 0.2739 | 10 |  | Cidra | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3601-04 | 2026-08-14 | 0.2341 | 10 |  | Cidra | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3601-04 | 2026-08-15 | 0.3354 | 10 |  | Cidra | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3601-04 | 2026-08-17 | 0.2258 | 10 |  | Cidra | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3601-04 | 2026-08-19 | 0.2177 | 10 |  | Cidra | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3601-04 | 2026-08-20 | 0.0873 | 10 |  | Cidra | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3601-04 | 2026-08-22 | 0.1915 | 10 |  | Cidra | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3601-04 | 2026-08-24 | 0.1428 | 10 |  | Cidra | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3601-04 | 2026-08-25 | 0.2992 | 10 |  | Cidra | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3601-04 | 2026-08-26 | 0.0888 | 10 |  | Cidra | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3601-04 | 2026-08-27 | 0.0994 | 10 |  | Cidra | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3601-04 | 2026-08-28 | 0.5001 | 10 |  | Cidra | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3601-04 | 2026-08-29 | 0.1308 | 10 |  | Cidra | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3601-04 | 2026-08-31 | 0.4281 | 10 |  | Cidra | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3602-01 | 2026-08-07 | 0.0469 | 10 |  | Caguas | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3602-01 | 2026-08-03 | 0.1493 | 10 |  | Cayey | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3602-01 | 2026-08-04 | 0.0325 | 10 |  | Cayey | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3602-01 | 2026-08-28 | 0.0342 | 10 |  | Cayey | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3602-01 | 2026-08-04 | 0.096 | 10 |  | Cidra | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3602-01 | 2026-08-06 | 0.1432 | 10 |  | Cidra | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3602-02 | 2026-08-04 | 0.0416 | 10 |  | Cidra | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3602-02 | 2026-08-05 | 0.0865 | 10 |  | Cidra | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3602-02 | 2026-08-06 | 0.1279 | 10 |  | Cidra | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3602-02 | 2026-08-07 | 0.2279 | 10 |  | Cidra | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3602-02 | 2026-08-08 | 0.2993 | 10 |  | Cidra | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3602-02 | 2026-08-11 | 0.0317 | 10 |  | Cidra | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3602-02 | 2026-08-12 | 0.0345 | 10 |  | Cidra | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3602-02 | 2026-08-13 | 0.0327 | 10 |  | Cidra | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3602-02 | 2026-08-14 | 0.1894 | 10 |  | Cidra | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3602-02 | 2026-08-15 | 0.0524 | 10 |  | Cidra | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3602-02 | 2026-08-17 | 0.1173 | 10 |  | Cidra | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3602-02 | 2026-08-18 | 0.126 | 10 |  | Cidra | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3602-02 | 2026-08-19 | 0.162 | 10 |  | Cidra | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3602-02 | 2026-08-20 | 0.0817 | 10 |  | Cidra | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3602-02 | 2026-08-21 | 0.178 | 10 |  | Cidra | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3602-02 | 2026-08-22 | 0.0429 | 10 |  | Cidra | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3602-02 | 2026-08-24 | 0.1499 | 10 |  | Cidra | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3602-02 | 2026-08-25 | 0.0584 | 10 |  | Cidra | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3602-02 | 2026-08-26 | 0.0642 | 10 |  | Cidra | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3602-02 | 2026-08-27 | 0.3157 | 10 |  | Cidra | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3602-02 | 2026-08-28 | 0.1045 | 10 |  | Cidra | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3602-02 | 2026-08-29 | 0.041 | 10 |  | Cidra | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3602-02 | 2026-08-31 | 0.037 | 10 |  | Cidra | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3603-01 | 2026-08-27 | 0.0398 | 10 |  | Cidra | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3701-01 | 2026-08-03 | 0.0842 | 10 |  | Aguas Buenas | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3701-01 | 2026-08-11 | 0.0367 | 10 |  | Aguas Buenas | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3701-01 | 2026-08-26 | 0.3919 | 10 |  | Aguas Buenas | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3701-03 | 2026-08-11 | 0.1357 | 10 |  | Aguas Buenas | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3701-03 | 2026-08-12 | 0.0594 | 10 |  | Aguas Buenas | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3701-03 | 2026-08-13 | 0.0402 | 10 |  | Aguas Buenas | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3701-03 | 2026-08-14 | 0.1872 | 10 |  | Aguas Buenas | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3701-03 | 2026-08-19 | 0.2573 | 10 |  | Aguas Buenas | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3701-03 | 2026-08-20 | 0.0452 | 10 |  | Aguas Buenas | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3701-03 | 2026-08-21 | 0.0612 | 10 |  | Aguas Buenas | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3701-03 | 2026-08-22 | 0.1445 | 10 |  | Aguas Buenas | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3701-03 | 2026-08-24 | 0.0222 | 10 |  | Aguas Buenas | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3701-03 | 2026-08-25 | 0.0261 | 10 |  | Aguas Buenas | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3701-03 | 2026-08-26 | 0.1906 | 10 |  | Aguas Buenas | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3701-03 | 2026-08-27 | 0.0255 | 10 |  | Aguas Buenas | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3701-03 | 2026-08-28 | 0.0396 | 10 |  | Aguas Buenas | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750066 | 4.80/8.32 | 3701-03 | 2026-08-29 | 0.189 | 10 |  | Aguas Buenas | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750068 | 2.40/4.16 | 6001-03 | 2026-08-04 | 0.0237 | 10 |  | Mayagüez | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750068 | 2.40/4.16 | 6001-03 | 2026-08-06 | 0.0328 | 10 |  | Mayagüez | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750068 | 2.40/4.16 | 6001-03 | 2026-08-13 | 0.0279 | 10 |  | Mayagüez | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750068 | 2.40/4.16 | 6001-03 | 2026-08-15 | 0.0293 | 10 |  | Mayagüez | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750068 | 2.40/4.16 | 6001-03 | 2026-08-22 | 0.0206 | 10 |  | Mayagüez | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956337 | 7.62/13.20 | 6012-02 | 2026-08-11 | 0.0583 | 10 |  | Añasco | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956337 | 7.62/13.20 | 6012-02 | 2026-08-13 | 0.0261 | 10 |  | Añasco | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956337 | 7.62/13.20 | 6012-02 | 2026-08-15 | 0.0323 | 10 |  | Añasco | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956337 | 2.40/4.16 | 6012-02 | 2026-08-18 | 0.0311 | 10 |  | Añasco | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956337 | 7.62/13.20 | 6012-02 | 2026-08-18 | 0.0323 | 10 |  | Añasco | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956337 | 2.40/4.16 | 6012-02 | 2026-08-20 | 0.0008 | 10 |  | Añasco | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956337 | 2.40/4.16 | 6012-02 | 2026-08-21 | 0.2265 | 10 |  | Añasco | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956337 | 2.40/4.16 | 6012-02 | 2026-08-24 | 0.0659 | 10 |  | Añasco | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956337 | 7.62/13.20 | 6012-02 | 2026-08-24 | 0.0715 | 10 |  | Añasco | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956337 | 2.40/4.16 | 6012-02 | 2026-08-26 | 0.1098 | 10 |  | Añasco | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956337 | 2.40/4.16 | 6012-02 | 2026-08-28 | 0.0487 | 10 |  | Añasco | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956337 | 2.40/4.16 | 6012-02 | 2026-08-31 | 0.0885 | 10 |  | Añasco | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956337 | 2.40/4.16 | 6012-02 | 2026-08-04 | 0.122 | 10 |  | Moca | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956337 | 2.40/4.16 | 6012-02 | 2026-08-05 | 0.0292 | 10 |  | Moca | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956337 | 2.40/4.16 | 6012-02 | 2026-08-06 | 0.0385 | 10 |  | Moca | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956337 | 2.40/4.16 | 6012-02 | 2026-08-17 | 0.0402 | 10 |  | Moca | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956337 | 2.40/4.16 | 6012-02 | 2026-08-20 | 0.0273 | 10 |  | Moca | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956337 | 2.40/4.16 | 6012-02 | 2026-08-21 | 0.0372 | 10 |  | Moca | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956337 | 2.40/4.16 | 6012-02 | 2026-08-24 | 0.1027 | 10 |  | Moca | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956337 | 2.40/4.16 | 6012-02 | 2026-08-25 | 0.0273 | 10 |  | Moca | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956337 | 2.40/4.16 | 6012-02 | 2026-08-27 | 0.0299 | 10 |  | Moca | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956337 | 2.40/4.16 | 6012-02 | 2026-08-28 | 0.0242 | 10 |  | Moca | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956337 | 2.40/4.16 | 6012-02 | 2026-08-29 | 0.0106 | 10 |  | Moca | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956337 | 2.40/4.16 | 6012-02 | 2026-08-30 | 0.0404 | 10 |  | Moca | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956331 | 2.40/4.16 | 6014-02 | 2026-08-06 | 0.0113 | 10 |  | Las Marías | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956331 | 2.40/4.16 | 6014-02 | 2026-08-10 | 0.0656 | 10 |  | Las Marías | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956331 | 2.40/4.16 | 6014-02 | 2026-08-13 | 0.0275 | 10 |  | Las Marías | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956331 | 2.40/4.16 | 6014-02 | 2026-08-15 | 0.0755 | 10 |  | Las Marías | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956331 | 2.40/4.16 | 6014-02 | 2026-08-19 | 0.1054 | 10 |  | Las Marías | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956331 | 2.40/4.16 | 6014-02 | 2026-08-21 | 0.091 | 10 |  | Las Marías | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956331 | 2.40/4.16 | 6014-02 | 2026-08-22 | 0.0396 | 10 |  | Las Marías | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956331 | 2.40/4.16 | 6014-02 | 2026-08-26 | 0.0597 | 10 |  | Las Marías | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956331 | 2.40/4.16 | 6014-02 | 2026-08-27 | 0.1547 | 10 |  | Las Marías | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956331 | 2.40/4.16 | 6014-02 | 2026-08-29 | 0.0447 | 10 |  | Las Marías | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956331 | 2.40/4.16 | 6014-02 | 2026-08-19 | 0.0491 | 10 |  | Mayagüez | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956331 | 2.40/4.16 | 6014-02 | 2026-08-25 | 0.0447 | 10 |  | Mayagüez | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956331 | 2.40/4.16 | 6014-02 | 2026-08-26 | 0.0273 | 10 |  | Mayagüez | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750068 | 2.40/4.16 | 6301-03 | 2026-08-02 | 0.0522 | 10 |  | Maricao | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750068 | 2.40/4.16 | 6301-03 | 2026-08-05 | 0.0671 | 10 |  | Maricao | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750068 | 2.40/4.16 | 6301-03 | 2026-08-07 | 0.0982 | 10 |  | Maricao | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750068 | 2.40/4.16 | 6301-03 | 2026-08-12 | 0.0591 | 10 |  | Maricao | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750068 | 2.40/4.16 | 6301-03 | 2026-08-13 | 0.0286 | 10 |  | Maricao | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750068 | 2.40/4.16 | 6301-03 | 2026-08-14 | 0.0659 | 10 |  | Maricao | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750068 | 2.40/4.16 | 6301-03 | 2026-08-15 | 0.0267 | 10 |  | Maricao | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750068 | 2.40/4.16 | 6301-03 | 2026-08-17 | 0.0391 | 10 |  | Maricao | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750068 | 2.40/4.16 | 6301-03 | 2026-08-18 | 0.0665 | 10 |  | Maricao | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750068 | 2.40/4.16 | 6301-03 | 2026-08-19 | 0.0851 | 10 |  | Maricao | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750068 | 2.40/4.16 | 6301-03 | 2026-08-20 | 0.0513 | 10 |  | Maricao | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750068 | 2.40/4.16 | 6301-03 | 2026-08-21 | 0.0727 | 10 |  | Maricao | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750068 | 2.40/4.16 | 6301-03 | 2026-08-22 | 0.0286 | 10 |  | Maricao | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750068 | 2.40/4.16 | 6301-03 | 2026-08-26 | 0.2274 | 10 |  | Maricao | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750068 | 2.40/4.16 | 6301-03 | 2026-08-27 | 0.0454 | 10 |  | Maricao | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750068 | 2.40/4.16 | 6301-03 | 2026-08-28 | 0.187 | 10 |  | Maricao | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750068 | 2.40/4.16 | 6301-03 | 2026-08-29 | 0.1038 | 10 |  | Maricao | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750068 | 2.40/4.16 | 7503-02 | 2026-08-03 | 0.0594 | 10 |  | Isabela | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750063 | 2.40/4.16 | 5402-01 | 2026-08-13 | 0.1129 | 10 |  | Peñuelas | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750063 | 2.40/4.16 | 5402-01 | 2026-08-15 | 0.2325 | 10 |  | Peñuelas | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750063 | 2.40/4.16 | 5402-01 | 2026-08-17 | 0.0911 | 10 |  | Peñuelas | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750063 | 2.40/4.16 | 5402-01 | 2026-08-18 | 0.0907 | 10 |  | Peñuelas | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750063 | 2.40/4.16 | 5402-01 | 2026-08-19 | 0.2107 | 10 |  | Peñuelas | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750063 | 2.40/4.16 | 5402-01 | 2026-08-20 | 0.2969 | 10 |  | Peñuelas | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750063 | 2.40/4.16 | 5402-01 | 2026-08-21 | 0.1367 | 10 |  | Peñuelas | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750063 | 2.40/4.16 | 5402-01 | 2026-08-24 | 0.0641 | 10 |  | Peñuelas | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750063 | 2.40/4.16 | 5402-01 | 2026-08-27 | 0.0994 | 10 |  | Peñuelas | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750063 | 2.40/4.16 | 5402-01 | 2026-08-18 | 0.0124 | 10 |  | Ponce | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750063 | 2.40/4.16 | 5402-01 | 2026-08-19 | 0.0852 | 10 |  | Ponce | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956340 | 2.40/4.16 | 5602-02 | 2026-08-28 | 0.0447 | 10 |  | Guaníca | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956340 | 2.40/4.16 | 5602-02 | 2026-08-26 | 0.1703 | 10 |  | Guánica | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956340 | 2.40/4.16 | 5602-02 | 2026-08-27 | 0.228 | 10 |  | Guánica | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956340 | 2.40/4.16 | 5602-02 | 2026-08-28 | 0.412 | 10 |  | Guánica | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956340 | 2.40/4.16 | 5602-02 | 2026-08-29 | 0.0454 | 10 |  | Guánica | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956340 | 2.40/4.16 | 5602-02 | 2026-08-30 | 0.0454 | 10 |  | Guánica | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956340 | 2.40/4.16 | 5602-02 | 2026-08-31 | 0.0895 | 10 |  | Guánica | Ceres | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956332 | 4.80/8.32 | 2401-01 | 2026-08-19 | 0.0252 | 10 |  | Canóvanas | Wright | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956332 | 4.80/8.32 | 2401-01 | 2026-08-17 | 0.1593 | 10 |  | Canóvanas | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956332 | 4.80/8.32 | 2401-01 | 2026-08-18 | 0.0921 | 10 |  | Canóvanas | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956332 | 4.80/8.32 | 2401-01 | 2026-08-19 | 0.1844 | 10 |  | Canóvanas | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956332 | 4.80/8.32 | 2401-01 | 2026-08-20 | 0.0362 | 10 |  | Canóvanas | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956332 | 4.80/8.32 | 2401-01 | 2026-08-25 | 0.0397 | 10 |  | Canóvanas | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956332 | 4.80/8.32 | 2401-01 | 2026-08-27 | 0.0694 | 10 |  | Canóvanas | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
956332 | 4.80/8.32 | 2401-01 | 2026-08-31 | 0.0771 | 10 |  | Canóvanas | Xperts | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
750067 | 2.40/4.16 | 8011-01 | 2026-08-24 | 0.0503 | 10 |  | Arecibo | Asplundh | In Progress | Federal Funded | Ian Kreher | Federal Funds | August | Q1 | FY2027
Vegetation Maintenance and Clearing

## FEMA Vegetation Projects
FEMA Vegetation Projects
As of August 31, 2026 | [18 empty] | As of 8/31/26 | As of 8/31/26 | As of 8/31/26 | As of 8/31/26 | As of 8/31/26
Project FAASt # | FEMA EMMIE P/W # | kV Level | Project Title | FEMA Review as of 8/31/26 | Phase at FEMA as of 8/31/26 | Date Project Submitted to FEMA | Last Date Obligated | LUMA Miles Submitted | FEMA Miles Approved and Obligated/to be Obligated | FEMA Percentage Approved | LUMA Submitted Cost & additional cost if Amended | FEMA Net Cost for all Project Versions | Percentage of Costs Obligated | FEMA Federal Share (amount LUMA will get from the FEMA Net Cost) | Non-Federal Share | Amount Spent (as of 8/31/26Finance report) | Amount Submitted for Reimbursement | Amount Reimbursed | Miles Assessed | Percentage of Miles Assessed | Assessment Vendor Assigned | Miles Completed | Percentage of Miles Completed | Vendors Assigned to Miles Cleared | If the vendor is not active, explain why (e.g., insurance, procurement, contracts or other similar issues)
956349 | 108157 | 115 kV | FAASt [San Juan Region 1 Line 36800 (115kV) – Canovanas TC to Palmer TC] (Vegetation) - Version 0/1 | Obligated | Obligated | 2025-12-12 | 2026-08-27 | 11.13 | 6.59 | 59.21% | 4685447.53 | 2971622.82 | 0.63422 | 2674460.54 | 297162.28 | 554673.7 |  |  | 7.88 | 120% | Ceres | 5.38 | 82% | Ceres
727608 | 107899 | 115 kV | FAASt [Region 1 San Juan TL - 115kV] (Vegetation) | Obligated | Obligated | 2024-11-27 | 2026-03-01 | 74.48 | 14.13 | 18.97% | 27445152.25 | 4453902.63 | 0.16 | 4008512.37 | 445390.26 | 92943.52 |  |  | 0 | 0% |  | 0 | 0%
727659 | 107901 | 115 kV | FAASt [Region 2 Arecibo TL - 115kV] (Vegetation) | Obligated | Obligated | 2024-11-27 | 2026-03-01 | 53.2 | 13.37 | 25.13% | 19581632.93 | 4214343.82 | 0.22 | 3792909.44 | 421434.38 | 124595.89 |  |  | 0 | 0% |  | 0 | 0%
727522 | 107892 | 115 kV | FAASt [Region 3 Bayamon TL - 115kV] (Vegetation) | Obligated | Obligated | 2024-11-27 | 2026-03-01 | 52.93 | 10.92 | 20.63% | 19467722.13 | 3442081.85 | 0.18 | 3097873.67 | 344208.18 | 32232.81 |  |  | 0 | 0% |  | 0 | 0%
727606 | 107898 | 115 kV | FAASt [Region 4 Caguas TL - 115kV] (Vegetation) | Obligated | Obligated | 2024-11-27 | 2026-03-01 | 87.14 | 12.63 | 14.49% | 32019956.72 | 3981089.18 | 0.12 | 3582980.27 | 398108.91 | 69569.41 |  |  | 0 | 0% |  | 0 | 0%
727657 | 107900 | 115 kV | FAASt [Region 5 Mayaguez TL - 115kV] (Vegetation) | Obligated | Obligated | 2024-11-27 | 2026-03-01 | 62.36 | 8.1 | 12.99% | 22914442.28 | 2553192.59 | 0.11 | 2297873.34 | 255319.25 | 4867.73 |  |  | 0 | 0% |  | 0 | 0%
956357 | 108160 | 38 kV | FAASt [Mayaguez Region 5 Line 1900 (38kV) – Dos Bocas HP to San Sebastian TC] (Vegetation) | Obligated | Obligated | 2025-06-26 | 2026-06-12 | 22.35 | 9.21 | 41% | 12705648.38 | 1692783.13 | 0.13 | 1523504.82 | 169278.31 | 1630.89 |  |  | 25.23 | 157% | Ceres | 14.85 | 161.2% | Ceres
727529 | 107893 | 115 kV | FAASt [Region 6 Ponce TL - 115kV] (Vegetation) | Obligated | Obligated | 2024-11-27 | 2026-03-01 | 156 | 26.35 | 16.93% | 57429412.88 | 8305756.13 | 0.14 | 7475180.52 | 830575.61 | 19458.35 |  |  | 0 | 0% |  | 0 | 0%
956356 | 108159 | 115 kV | FAASt [Ponce Region 6 Line 39000 (115kV) – Aguas Buenas Substation to Hacienda San Jose] (Vegetation) - Version 0/1 | Obligated | Obligated | 2025-12-05 | 2026-03-01 | 2.82 | 1.24 | 100% | 1019517.55 | 388903.06 | 0.38 | 350012.76 | 38890.3 | 188287.35 |  |  | 2.86 | 100% | Ceres | 1.24 | 100% | Ceres
956343 | 108154 | 38 kV | FAASt [Ponce Region 6 Line 4800 (38kV) – Toro Negro to Aibonito, Santa Isabel] (Vegetation) | Obligated | Obligated | 2025-06-26 | 2026-06-30 | 39.77 | 12.6 | 31.68% | 21381353.56 | 2361582.5 | 0.11 | 2125424.25 | 236158.25 | 1168.25 |  |  | 0 | 0% |  | 0 | 0%
956342 | 108153 | 115 kV | FAASt [Arecibo Region 2 Line 36400 (115Kv) – Ponce TC to Dos Bocas HP] (Vegetation) | Obligated | Obligated | 2025-08-01 | 2025-09-17 | 36.78 | 11.48 | 31.22% | 44397505.59 | 4093248.38 | 0.09 | 3683923.55 | 409324.83 | 7841.89 |  |  | 0.31 | 3% | Ceres | 0.09 | 0.784% | Ceres
956353 | 108158 | 115 kV | FAASt [Arecibo Region 2 Line 36100 (115kV) – Dos Bocas HP to Barrio Pina] (Vegetation) | Obligated | Obligated | 2025-08-01 | 2025-09-17 | 30.97 | 10.54 | 34.03% | 37008593.33 | 3756065.08 | 0.1 | 3380458.58 | 375606.5 | 121642.74 |  |  | 21.56 | 100% | Ceres | 2.97 | 28.18% | Ceres
956345 | 108155 | 38 kV | FAASt [Arecibo Region 2 Line 2400 (38kV) – Dos Bocas HP to Caonillas 2] (Vegetation) | Obligated | Obligated | 2025-06-26 | 2026-04-24 | 12.96 | 4.02 | 31.02% | 7324652.18 | 738869.51 | 0.1 | 664982.56 | 73886.95 | 1488.31 |  |  | 3.04 | 92% | Ceres | 2.91 | 95.72% | Ceres
956348 | 108156 | 38 kV | FAASt [Bayamon Region 3 Line 10000 (38kV) – Bayamon Pueblo to Magnolia TO] (Vegetation) | Obligated | Obligated | 2025-06-26 | 2026-04-24 | 2.43 | 0.66 | 27.16% | 1019517.55 | 121306.94 | 0.12 | 109176.25 | 12130.69 | 875.71 |  |  | 0.82 | 124.2% | Xperts | 0.74 | 90.24% | Xperts
741105 | 107946 | 230 kV | FAASt [All Regions TL - 230kV] (Vegetation) | Obligated | Obligated | 2024-12-13 | 2026-03-01 | 402.54 | 38.21 | 9.49% | 157865400 | 12885805.47 | 0.08 | 11597224.93 | 1288580.54 | 38811.61 |  |  | 0 | 0% |  | 0 | 0% |  | This projects were transferred to USACE
956330 | 108145 | Distribution | FAASt [Caguas Region 4 - Feeder 3007-03] (Vegetation) | Obligated | Obligated | 2025-06-27 | 2026-06-12 | 60.23 | 59.41 | 98.64% | 7985860.15 | 7595964.6 | 0.95 | 6836368.14 | 759596.46 | 348.82 |  |  | 35.8 | 60.26% | Ceres | 1.83 | 3.08% | Ceres
956339 | 108150 | Distribution | FAASt [Caguas Region 4 - Feeder 3301-01] (Vegetation) | Obligated | Obligated | 2025-06-27 | 2026-06-12 | 90.54 | 89.58 | 98.94% | 12004333.95 | 11453400.26 | 0.95 | 10308060.24 | 1145340.02 | 348.82 |  |  | 6.23 | 6.955% | Ceres | 3.34 | 3.729% | Ceres
956337 | 108149 | Distribution | FAASt [Mayaguez Region 5 Feeder 6012-02] (Vegetation) | Obligated | Obligated | 2025-06-27 | 2026-06-12 | 55.09 | 42.76 | 77.62% | 7303974.78 | 5467151.1 | 0.75 | 4920435.99 | 546715.11 | 886.83 |  |  | 12.38 | 28.95% | Ceres | 3.95 | 9.238% | Ceres
956331 | 108146 | Distribution | FAASt [Mayaguez Region 5 Feeder 6014-02] (Vegetation) | Obligated | Obligated | 2025-06-27 | 2026-06-12 | 60.5 | 56.28 | 93.02% | 8021552.35 | 7195773.23 | 0.9 | 6476195.91 | 719577.32 | 243.23 |  |  | 7.42 | 13.18% | Ceres | 1.33 | 2.363% | Ceres
956340 | 108151 | Distribution | FAASt [Ponce Region 6 Feeder 5602-02] (Vegetation) | Obligated | Obligated | 2025-06-27 | 2026-07-08 | 191.55 | 37.57 | 19.61% | 6589894.87 | 4803574.98 | 0.73 | 4323217.49 | 480357.49 | 298.54 |  |  | 23.21 | 61.78% | Ceres | 5.47 | 14.56% | Ceres
956341 | 108152 | Distribution | FAASt [Ponce Region 6 Feeder 5803-02] (Vegetation) | Obligated | Obligated | 2025-06-27 | 2026-05-13 | 0.7366 | 0.73 | 99.1% | 97672.18 | 93335.37 | 0.96 | 84001.84 | 9333.53 | 348.82 |  |  | 0.73 | 100% | Ceres | 0 | 0%
956335 | 108148 | Distribution | FAASt [San Juan Region 1 - Feeder 2301-02] (Vegetation) | In FEMA Review | Pending FEMA Final Review | 2025-06-27 |  | 56.59 | 55.81 | 98.62% | 7503713.1 | 7135680.6 | 0.95 | 6422112.54 | 713568.06 | 301.68 |  |  | 0 | 0% |  | 0 | 0%
956332 | 108147 | Distribution | FAASt [San Juan Region 1 - Feeder 2401-01] (Vegetation) | Obligated | Obligated | 2025-06-27 | 2026-07-08 | 85.26 | 82.68 | 96.97% | 11304742.47 | 10571189.26 | 0.93511 | 9514070.34 | 1057118.92 | 47.21 |  |  | 82.83 | 100.2% | Xperts | 2.26 | 2.733% | Xperts
750063 | 107965 | Distribution | FAASt [Region 6 -Ponce Group A] Low Density (Vegetation) | Obligated | Obligated | 2024-11-22 | 2026-06-30 | 531.21 | 531.21 | 100% | 60044753.52 | 60044753.52 | 1 | 54040278.17 | 6004475.35 | 306361.08 |  |  | 12.56 | 2.364% | Ceres, Asplundh, Xperts | 1.87 | 0.352% | Ceres
750067 | 107968 | Distribution | FAASt [Region 2 -Arecibo Group A] Low Density (Vegetation) | Obligated | Obligated | 2024-11-22 | 2026-03-01 | 502.48 | 502.48 | 100% | 56797288.74 | 56797288.74 | 1 | 51117559.87 | 5679728.87 | 255298.12 |  |  | 285.78 | 56.87% | Asplundh, Ceres | 20.98 | 7.341% | Asplundh
727572 | 11720 | Distribution | FAASt [Region 3 -Bayamon Group A] High Density (Vegetation) | Obligated | Obligated | 2024-11-15 | 2026-03-01 | 376.77 | 376.77 | 100% | 80353343.34 | 42586648.64 | 0.53 | 38327983.78 | 4258664.86 | 860584.04 |  |  | 363.04 | 96.36% | Xperts, Asplundh, Wright | 8.24 | 2.187% | Xperts
750065 | 107966 | Distribution | FAASt [Region 3 -Bayamon Group A] Low Density (Vegetation) | Obligated | Obligated | 2024-11-22 | 2026-03-01 | 620.82 | 620.82 | 100% | 70173723.91 | 70173723.91 | 1 | 63156351.52 | 7017372.39 | 166440.83 |  |  | 349.05 | 56.22% | Xperts, Ceres | 6.62 | 1.066% | Xperts, Asplundh
750066 | 107967 | Distribution | FAASt [Region 4 -Caguas Group A] Low Density (Vegetation) | Obligated | Obligated | 2024-11-22 | 2026-03-01 | 951.58 | 951.58 | 100% | 107563717.79 | 107563717.79 | 1 | 96807346.02 | 10756371.77 | 251525.3 |  |  | 483.11 | 50.77% | Ceres | 48.25 | 5.071% | Ceres
750068 | 107969 | Distribution | FAASt [Region 5 -Mayaguez Group A] Low Density (Vegetation) | Obligated | Obligated | 2024-11-22 | 2026-03-01 | 462.71 | 462.71 | 100% | 52301929.37 | 52301929.37 | 1 | 47071736.44 | 5230192.93 | 217179.31 |  |  | 163.59 | 35.35% | Asplundh, Ceres, Xperts | 6.02 | 1.301% | Ceres
723883 | 11696 | Distribution | FAASt [Region 1 -San Juan Group A] (Vegetation) - Version 0 - 2 | Obligated | Obligated | 2025-06-11 | 2026-03-01 | 612.73 | 612.73 | 100% | 24944459.56 | 24944459.56 | 1 | 22450013.61 | 2494445.95 | 20897470.4 | 4371112.5 | 3934001.25 | 787.5 | 128.5% | Asplundh, Ceres, Wright, Xpert | 26.96 | 4.4% | Asplundh, Ceres, Wright, Xperts | Wright withdrew from Federally Funded work in 2025
727531 | 11715 | Distribution | FAASt [Region 6 -Ponce Group A] High Density (Vegetation) | Obligated | Obligated | 2024-11-15 | 2025-04-28 | 199.37 | 199.37 | 100% | 25913934.11 | 25913934.11 | 1 | 23322540.7 | 2591393.41 | 6229319.74 | 1243513.59 |  | 198.91 | 99.77% | Asplundh, Ceres, Xperts, Wright | 45.69 | 22.97% | Asplundh, Ceres, Xperts
728832 | 11718 | Distribution | FAASt [Region 5 -Mayaguez Group A] High Density (Vegetation) | Obligated | Obligated | 2024-11-15 | 2025-04-28 | 109.73 | 109.73 | 100% | 14260691.9 | 14260691.9 | 1 | 12834622.71 | 1426069.19 | 3106232.89 | 2006897.66 |  | 104.95 | 95.64% | Ceres | 22.01 | 20.97% | Ceres
727692 | 11724 | Distribution | FAASt [Region 4 -Caguas Group A] High Density (Vegetation) | Obligated | Obligated | 2024-11-15 | 2025-04-28 | 215.82 | 215.82 | 100% | 28052090.37 | 28052090.37 | 1 | 25246881.34 | 2805209.03 | 6908788.7 | 1065863.76 |  | 207.75 | 96.26% | Asplundh, Xperts, Ceres | 50.43 | 23.37% | Xperts
728827 | 11714 | Distribution | FAASt [Region 2 -Arecibo Group A] High Density (Vegetation) | Obligated | Obligated | 2024-11-15 | 2025-04-28 | 139.99 | 139.99 | 100% | 18194308.81 | 18194308.81 | 1 | 16374877.93 | 1819430.88 | 4037225.54 | 1583575.01 |  | 136.64 | 97.61% | Asplundh, Wright, Ceres | 33.83 | 24.17% | Asplundh, Wright, Ceres, Xperts | Wright withdrew from Federally Funded work in 2025
1068649 | 108273 | 38 kV | FAASt [Region 6 Ponce 38Kv – Non-Sensitive]/ Former project 740414 (vegetation) | Obligated | 428 Obligated; Pending 406 obligation | 2026-06-08 | 2026-09-12 | 44.55 | 19.23 | 43.16% | 9664446.26 | 294324.21 | 0.030454 | 264891.79 | 29432.42 |  |  |  | 0 | 0% |  | 0 | 0%
1068648 | 108272 | 38 kV | FAASt [Region 5 Mayaguez 38Kv – Non-Sensitive]/ Former project 740411 (vegetation) | IN FEMA review | Pending FEMA Final Review | 2026-06-08 |  | 7.9 |  |  | 1714050.3 | [7 empty] | 0 | 0% |  | 0 | 0%
1068646 | 108270 | 38 kV | FAASt [Region 4 Caguas 38Kv – Non-Sensitive]/ Former project 740409 (vegetation) | Obligated | 428 Obligated; Pending 406 obligation | 2026-06-08 | 2026-09-12 | 38.87 | 13.37 | 34.4% | 8650053.27 | 204634.22 | 0.023657 | 184170.8 | 20463.42 |  |  |  | 0 | 0% |  | 0 | 0%
1068642 | 108269 | 38 kV | FAASt [Region 3 Bayamon 38Kv – Non-Sensitive]/ Former project 740408 (vegetation) | IN FEMA review | Pending FEMA Final Review | 2026-06-08 |  | 34.74 |  |  | 7529621.56 | [7 empty] | 0 | 0% |  | 0 | 0%
1068647 | 108271 | 38 kV | FAASt [Region 2 Arecibo 38Kv – Non-Sensitive]/ Former project 740410 (vegetation) | IN FEMA review | Pending FEMA Final Review | 2026-06-08 |  | 1.19 |  |  | 258146.06 | [7 empty] | 0 | 0% |  | 0 | 0%
1068640 | 108268 | 38 kV | FAASt [Region 1 San Juan 38Kv – Non-Sensitive]/ Former project 740406 (vegetation) | IN FEMA review | Pending FEMA Final Review | 2026-06-08 |  | 15.68 |  |  | 3400369.29 | [7 empty] | 0 | 0% |  | 0 | 0%
1070367 | 108331 | 38 kV | FAASt [Region 6 Ponce Transmission 38kV sensitive areas] (Vegetation) | In FEMA Review |  | 2026-09-11 |  | 126.98 |  |  | 27545702.83 | [7 empty] | 0 | 0% |  | 0 | 0%
1070368 | 108332 | 38 kV | FAASt [Region 2 Arecibo Transmission 38kV sensitive areas] (Vegetation) | In FEMA Review |  | 2026-09-11 |  | 102.69 |  |  | 22276845.85 | [7 empty] | 0 | 0% |  | 0 | 0%
1070402 | 108348 | 38 kV | FAASt [Region 3 Bayamon Transmission 38kV sensitive areas] (Vegetation) | In FEMA Review |  | 2026-09-11 |  | 73.73 |  |  | 15994415.63 | [7 empty] | 0 | 0% |  | 0 | 0%
1070371 | 108336 | 38 kV | FAASt [Region 5 Mayaguez Transmission 38kV sensitive areas] (Vegetation) | In FEMA Review |  | 2026-09-14 |  | 114.45 |  |  | 24827576.7 | [7 empty] | 0 | 0% |  | 0 | 0%
1070372 | 108335 | 38 kV | FAASt [Region 1 San Juan Transmission 38kV sensitive areas] (Vegetation) | In FEMA Review |  | 2026-09-11 |  | 73.24 |  |  | 15887347.06 | [7 empty] | 0 | 0% |  | 0 | 0%
1070374 | 108338 | 38 kV | FAASt [Region 4 Caguas Transmission 38kV sensitive areas] (Vegetation) | In FEMA Review |  | 2026-09-11 |  | 40.65 |  |  | 8818815.36 | [7 empty] | 0 | 0% |  | 0 | 0%
Pending FAASt# |  | Distribution | FAASt [Group C_Region 6 Ponce Distribution sensitive areas] (Vegetation) | Pending Submittal |  |  |  | 1271.29 |  |  | 165946767.16 | [7 empty] | 0 | 0% |  | 0 | 0%
Pending FAASt# |  | Distribution | FAASt [Group C_Region 5 Mayaguez Distribution sensitive areas] (Vegetation) | Pending Submittal |  |  |  | 1774.91 |  |  | 231686378.8 | [7 empty] | 0 | 0% |  | 0 | 0%
Pending FAASt# |  | Distribution | FAASt [Group C_Region 2 Arecibo Distribution sensitive areas] (Vegetation) | Pending Submittal |  |  |  | 1446.2 |  |  | 188778496.39 | [7 empty] | 0 | 0% |  | 0 | 0%
Pending FAASt# |  | Distribution | FAASt [Group C_Region 4 Caguas Distribution sensitive areas] (Vegetation) | Pending Submittal |  |  |  | 1390.14 |  |  | 181460751.58 | [7 empty] | 0 | 0% |  | 0 | 0%
Pending FAASt# |  | Distribution | FAASt [Group C_Region 3 Bayamon Distribution sensitive areas] (Vegetation) | Pending Submittal |  |  |  | 258.42 |  |  | 33732636.55 | [7 empty] | 0 | 0% |  | 0 | 0%
Pending FAASt# |  | Distribution | FAASt [Group C_Region 1 San Juan Distribution sensitive areas] (Vegetation) | Pending Submittal |  |  |  | 1184.08 |  |  | 154562883.41 | [7 empty] | 0 | 0% |  | 0 | 0%
Pending FAASt# |  | 38 kV | 38kV Transmission Line 100 – Entire Line (Vegetation) | In FEMA Review |  | 8/21//2026 |  | 23.68 |  |  | 5136430.39 | [7 empty] | 0 | 0% |  | 0 | 0%
Pending FAASt# |  | 38 kV | 38kV Transmission Line 200 – Entire Line (Vegetation) | In FEMA Review |  | 8/21//2026 |  | 14.43 |  |  | 3129993.94 | [7 empty] | 0 | 0% |  | 0 | 0%
Pending FAASt# |  | 38 kV | 38kV Transmission Line 800 – Entire Line (Vegetation) | In FEMA Review |  | 8/21//2026 |  | 14.98 |  |  | 3250209.66 | [7 empty] | 0 | 0% |  | 0 | 0%
Pending FAASt# |  | 38 kV | 38kV Transmission Line 1200 – Entire Line (Vegetation) | In FEMA Review |  | 8/21//2026 |  | 25.62 |  |  | 5557124.91 | [7 empty] | 0 | 0% |  | 0 | 0%
Pending FAASt# |  | 38 kV | 38kV Transmission Line 1600 – Entire Line (Vegetation) | In FEMA Review |  | 8/21//2026 |  | 28.37 |  |  | 6154852.58 | [7 empty] | 0 | 0% |  | 0 | 0%
Pending FAASt# |  | 38 kV | 38kV Transmission Line 2000 – Entire Line (Vegetation) | In FEMA Review |  | 8/21//2026 |  | 28.2 |  |  | 6117678.65 | [7 empty] | 0 | 0% |  | 0 | 0%
Pending FAASt# |  | 38 kV | 38kV Transmission Line 2100 – Entire Line (Vegetation) | In FEMA Review |  | 8/21//2026 |  | 28.31 |  |  | 6142341.8 | [7 empty] | 0 | 0% |  | 0 | 0%
Pending FAASt# |  | 38 kV | 38kV Transmission Line 2200 – Entire Line (Vegetation) | In FEMA Review |  | 8/21//2026 |  | 74.81 |  |  | 16229267.33 | [7 empty] | 0 | 0% |  | 0 | 0%
Pending FAASt# |  | 38 kV | 38kV Transmission Line 2500 – Entire Line (Vegetation) | In FEMA Review |  | 8/21//2026 |  | 22.62 |  |  | 4906125 | [7 empty] | 0 | 0% |  | 0 | 0%
Pending FAASt# |  | 38 kV | 38kV Transmission Line 2700 – Entire Line (Vegetation) | In FEMA Review |  | 8/21//2026 |  | 38.06 |  |  | 8256417.92 | [7 empty] | 0 | 0% |  | 0 | 0%
Pending FAASt# |  | 38 kV | 38kV Transmission Line 3000 – Entire Line (Vegetation) | In FEMA Review |  | 8/21//2026 |  | 45.63 |  |  | 9898126.29 | [7 empty] | 0 | 0% |  | 0 | 0%
Pending FAASt# |  | 38 kV | 38kV Transmission Line 3100 – Entire Line (Vegetation) | In FEMA Review |  | 8/21//2026 |  | 60.39 |  |  | 13100107.23 | [7 empty] | 0 | 0% |  | 0 | 0%
Pending FAASt# |  | 38 kV | 38kV Transmission Line 3700 – Entire Line (Vegetation) | In FEMA Review |  | 8/21//2026 |  | 43.68 |  |  | 9475835.73 | [7 empty] | 0 | 0% |  | 0 | 0%
Pending FAASt# |  | 38 kV | 38kV Transmission Line 3800 – Entire Line (Vegetation) | In FEMA Review |  | 8/21//2026 |  | 23.57 |  |  | 5113936.76 | [7 empty] | 0 | 0% |  | 0 | 0%
Pending FAASt# |  | 38 kV | 38kV Transmission Line 4000 – Entire Line (Vegetation) | In FEMA Review |  | 8/21//2026 |  | 10.51 |  |  | 2279116.67 | [7 empty] | 0 | 0% |  | 0 | 0%
Pending FAASt# |  | 38 kV | 38kV Transmission Line 5300 – Entire Line (Vegetation) | In FEMA Review |  | 8/21//2026 |  | 15.42 |  |  | 3345060.68 | [7 empty] | 0 | 0% |  | 0 | 0%
Pending FAASt# |  | 38 kV | 38kV Transmission Line 5400 – Entire Line (Vegetation) | In FEMA Review |  | 8/21//2026 |  | 26.77 |  |  | 5806269.79 | [7 empty] | 0 | 0% |  | 0 | 0%
Pending FAASt# |  | 38 kV | 38kV Transmission Line 5600 – Entire Line (Vegetation) | In FEMA Review |  | 8/21//2026 |  | 27.27 |  |  | 5916684.18 | [7 empty] | 0 | 0% |  | 0 | 0%
Pending FAASt# |  | 38 kV | 38kV Transmission Line 6500 – Entire Line (Vegetation) | In FEMA Review |  | 8/21//2026 |  | 41.58 |  |  | 9019926.95 | [7 empty] | 0 | 0% |  | 0 | 0%
[7 empty] | Total | 15004.96 | 5328.08 | 84% | 2305877133.22 | 610215787.69 | 57% | 549194209.06 | 61021578.63 | 44499338.06 | 10270962.52 | 3934001.25 | 2369.02 | 44% |  | 1292.74 | 24%
Vegetation Maintenance and Clearing
Note on T13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: We are assessing the complete line.
Note on E42: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Tienes 35 obligados y son 36. Si el proyecto tiene una obligacion original, aunque este versionado lo mantenemos como obligado. Este proyecto esta obligado.