## Attachment A (February 05 2026) (hidden)
Project Number | Project Title | Asset | Sub Asset | DSOW Submitted? | Total Estimate Incurred Cost | 428 Cost | 406 Cost | Total Estimated Cost
334191 | FAASt [Feeders - Mayaguez Short Term Group 3] (Distribution) | Distribution | Line Rebuild | Yes | 9689812.09 | 44675547 | 38483744 | 83159291
666894 | FAASt [San Juan Streetlighting] (Distribution) | Distribution | Streetlighting | Yes | 9279864.9 | 35282713 | 3532039 | 38814752
334293 | FAASt [Feeders - 7805-11- Mayaguez Short Term Group 4] (Distribution ) | Distribution | Line Rebuild | Yes | 5762106.74 | 47224922 | 45582792 | 92807714
547247 | Cambalache TC | Substation | Rebuild | Yes | 4499385.99 | 5463505.9 | 84733286.06 | 90196791.96
334472 | FAASt [Feeders - San Juan Short Term Group 2] (Distribution) | Distribution | Line Rebuild | Yes | 3857112.76 | 18783750 | 5366655 | 24150405
678794 | FAASt [Ponce Streetlighting] (Distribution) | Distribution | Streetlighting | Yes | 3450445.62 | 18852071 | 1444528 | 20296599
718971 | FAASt [Line 50300 (230kV) from Costa Sur Steam Plant to Aguirre Steam Plant] (Transmission) | Transmission | Line Rebuild | Yes | 3238497.73 | 15889643 | 901810364 | 917700007
436616 | FAASt [Feeders - Arecibo Short Term Group 1] (Distribution) | Distribution | Line Rebuild | Yes | 3049964.36 | 27194288 | 14494388 | 41688676
690483 | FAASt [Cayey Streetlighting] | Distribution | Streetlighting | Yes | 2980653.6 | 15993979 | 1319139 | 17313118
547343 | FAASt [Victoria TC 7008 Relocation] (Substation) | Substation | Rebuild | Yes | 2943473.75 | 6846444.9 | 54844288.98 | 61690733.88
699814 | FAASt [Juana Diaz Streetlighting] (Distribution) | Distribution | Streetlighting | Yes | 2857852.61 | 18680447 | 1909452 | 20589899
704931 | FAASt [Camuy Streetlighting] (Distribution) | Distribution | Streetlighting | Yes | 2832594.37 | 18265434 | 2269186 | 20534620
704862 | FAASt [Fajardo Streetlighting] (Distribution) | Distribution | Streetlighting | Yes | 2726930.5 | 13631005 | 1104923 | 14735928
678795 | FAASt [Arecibo Streetlighting] (Distribution) | Distribution | Streetlighting | Yes | 2701705.05 | 17274978 | 1527389 | 18802367
730541 | FAASt [Feeders - Caguas Short Term Group 8] (Distribution) | Distribution | Line Rebuild | Yes | 2623408 | 14523276 | 18671456 | 33194732
704757 | FAASt [Santa Isabel Streetlighting] (Distribution) | Distribution | Streetlighting | Yes | 2617616.95 | 9707069 | 820333 | 10527402
671396 | FAASt [Utuado Streetlighting] (Distribution) | Distribution | Streetlighting | Yes | 2599723.93 | 21135871 | 2911033 | 24046904
547344 | FAASt [Acacias 6801 TC Relocation] (Substation) | Substation | Rebuild | Yes | 2584284.14 | 8874442.51 | 42895135.02 | 51769577.53
688623 | FAASt [Automation Program Group 1A-8 Feeders] (Distribution) | Distribution | Automation | Yes | 2577701.87 | 1005286 | 1877045 | 2882331
546374 | FAASt [Feeders - 1620-02 - San Juan Short Term Group 3] (Distribution) | Distribution | Line Rebuild | Yes | 2563501.36 | 21058160 | 12777559 | 33835719
730586 | FAASt [Feeders - Ponce Short Term Group 1] (Distribution) | Distribution | Line Rebuild | Yes | 2500998.26 | 18969808 | 12719346 | 31689154
730824 | FAASt [Feeders - Ponce Short Term Group 2] (Distribution) | Distribution | Line Rebuild | Yes | 2464564.33 | 4115433 | 2840853 | 6956286
724603 | FAASt [Cabo Rojo Streetlighting] (Distribution) | Distribution | Streetlighting | Yes | 2396659.73 | 11029424 | 1044683 | 12074107
334476 | FAASt [Feeders - Carolina Short Term Group 2] (Distribution) | Distribution | Line Rebuild | Yes | 2350006.68 | 18285383 | 18767542 | 37052925
177191 | FAASt - 115kV Line 39000 - Aguas Buenas TC to Caguas TC (Transmission) | Transmission | Line Rebuild | Yes | 2347246.55 | 19407885 | 906873 | 20314758
701473 | FAASt [Canovanas Streetlighting] (Distribution) | Distribution | Streetlighting | Yes | 2151035.48 | 16995906 | 1574362 | 18570268
693543 | FAASt [Juncos Streetlighting] (Distribution) | Distribution | Streetlighting | Yes | 2135208.44 | 13468580 | 1643590 | 15112170
671400 | FAASt [Barceloneta Streetlighting] (Distribution) | Distribution | Streetlighting | Yes | 1880917.99 | 10053300 | 1109633 | 11162933
547243 | FAASt Egozcue - 1109 (Substation) | Substation | Rebuild | Yes | 1875010.93 | 13896445.76 | 6952342.26 | 20848788.02
958367 | FAASt [Distribution Feeder Rebuild #6603-01] (Distribution) | Distribution | Line Rebuild | Yes | 1860753.24 | 14474191.76 | 1172038.62 | 15646230.38
693788 | FAASt [Toa Alta Streetlighting] (Distribution) | Distribution | Streetlighting | Yes | 1831642.93 | 7465021 | 481369 | 7946390
546386 | FAASt [Feeders- El Yunque 2305 - Supply] (Distribution) | Distribution | Line Rebuild | Yes | 1640643.01 | 6564391 | 23252037 | 29816428
697183 | FAASt [Vega Baja Streetlighting] (Distribution) | Distribution | Streetlighting | Yes | 1589931.76 | 11188812 | 1117331 | 12306143
690721 | FAASt [Guayama Streetlighting] (Distribution) | Distribution | Streetlighting | Yes | 1577001.01 | 7045719 | 542958 | 7588677
698432 | FAASt [Hormigueros Streetlighting] (Distribution) | Distribution | Streetlighting | Yes | 1271901.7 | 8618625 | 968057 | 9586682
690480 | FAASt [Humacao Streetlighting] (Distribution) | Distribution | Streetlighting | Yes | 1203691.71 | 9318022 | 922000 | 10240022
547241 | FAASt Tallaboa 5402 | Substation | Rebuild | Yes | 1194229.01 | 10924436 | 5628609 | 16553045
551927 | 551927 SCADA Remote Access and RTU Replacements Group 3 | IT/OT | N/A | Yes | 1173137.64 | 19213188.6 | 3299617.88 | 22512806.48
686482 | FAASt [Isabela Streetlighting] (Distribution) | Distribution | Streetlighting | Yes | 1088990.74 | 8712288 | 733835 | 9446123
550986 | FAASt Condado - 1133 | Substation | Rebuild | Yes | 1063570.56 | 10649911 | 5427167 | 16077078
550894 | FAASt [Baldrich - 1422] (Substation) | Substation | Rebuild | Yes | 945895.54 | 973098 | 28669863 | 29642961
750503 | FAASt [25 MW BESS Installation and Integration - San Juan] (Substation) | Substation | Grid Modernization | Yes | 933346.51 | $ - | 55503065.56 | 55503065.56
750502 | FAASt [25 MW BESS Installation and Integration - Aguadilla] (Substation) | Substation | Grid Modernization | Yes | 917517.07 | $ - | 52720520.35 | 52720520.35
752972 | FAASt [4 x 25 MW BESS Interconnections Manati] (Substation) | Substation | Grid Modernization | Yes | 877404.95 | $ - | 57640005.67 | 57640005.67
754350 | Distribution Underground Circuit Feeders - San Juan Group 1 | Distribution | Underground | Yes | 830833.49 | $ - | 15123199.33 | 15123199.33
738671 | FAASt [25 MW BESS Installation and Integration - Barceloneta] (Substation) | Substation | Grid Modernization | Yes | 771738.9 | $ - | 55941767.5 | 55941767.5
754351 | ​Distribution Underground Circuit Feeders - San Juan Group 2 | Distribution | Underground | Yes | 722563.3 | $ - | 7066632.8 | 7066632.8
748180 | Transmission Advanced Sensors and Wide-Area Monitoring, Protection, and Control (WAMPAC) System | IT/OT | N/A | Yes | 578474.45 | $ - | 52804979.05 | 52804979.05
752277 | FAASt [Substation Ciales 8701] (Substation) | Substation | Rebuild | Yes | 436437.47 | 359175.24 | 4177144.45 | 4536319.69
745851 | FAASt [Automation Program Group 11] (Distribution) | Distribution | Automation | Yes | 255436.45 | 479854 | 1052298 | 1532152
805519 | 38kV Recloser TL 1900 Dos Bocas HP to San Sebastian TC | Transmission | Automation | Yes | 197629.44 | 708408.01 | 769393.29 | 1477801.3
817249 | FAASt [Pole and Conductor Repair -Caguas Group 7 - Phase 2 | Distribution | Pole and Conductors | No | 189461.99 | 5100000 | TBD | 5100000
745854 | Automation Program Group 9 | Distribution | Automation | Yes | 184886.52 | 546905 | 1164604 | 1711509
790446 | FAASt [Pole and Conductor Repair -Caguas Group 4 Phase 2 (Distribution) | Distribution | Pole and Conductors | Yes | 121427.65 | 4662521.3 | 28582.12 | 4691103.42
668669 | FAASt [Line 50500 230kV Mayaguez TC - Mora TC - Cambalache Power Plant] (Transmission) | Transmission | Line Rebuild | Yes | 73993.29 | 307465 | -1 | 307465
757945 | FAASt [Pole and Conductor Repair - Arecibo Group 3 - Phase 2] (Distribution) | Distribution | Pole and Conductors | Yes | 60037.43 | 2892589.5 | 15039.03 | 2907628.53
727691 | FAASt [Region 1 San Juan Transmission 38kV sensitive areas] (Vegetation) | Vegetation | N/A | Yes | 38329.46 | $ - | 44200121.5 | 44200121.5
740406 | FAASt[Region 1 San Juan Transmission 38kV - Non-Sensitive (Vegetation)] | Vegetation | N/A | Yes | 14548.58 | $ - | 5894785.29 | 5894785.29
741097 | Region 1 San Juan Substation/Telecom | Vegetation | N/A | Yes | 8787.49 | $ - | 1347191.63 | 1347191.63
741098 | Region 3 Bayamon Substation/Telecom | Vegetation | N/A | Yes | 8365.17 | $ - | 961518.65 | 961518.65
740410 | FAASt[Region 2 Arecibo Transmission 38kV - Non-Sensitive (Vegetation)] | Vegetation | N/A | Yes | 8296.79 | $ - | 5425376.76 | 5425376.76
740409 | FAASt[Region 4 Caguas Transmission 38kV - Non-Sensitive (Vegetation)] | Vegetation | N/A | Yes | 8084.15 | $ - | 23846154.02 | 23846154.02
740414 | FAASt [Region 6 Ponce Transmission 38kV - Non-Sensitive (Vegetation) | Vegetation | N/A | Yes | 7563.55 | $ - | 13788400.37 | 13788400.37
741102 | Region 5 Mayaguez Substation/Telecom | Vegetation | N/A | Yes | 7244.12 | $ - | 1516985.37 | 1516985.37
727694 | FAASt [Region 4 Caguas Transmission 38kV sensitive areas] (Vegetation) | Vegetation | N/A | Yes | 6393.72 | $ - | 76781710.48 | 76781710.48
741101 | Region 2 Arecibo Substation/Telecom | Vegetation | N/A | Yes | 6352.17 | $ - | 1058188.92 | 1058188.92
740411 | FAASt [Region 5 Mayaguez Transmission 38kV - Non-Sensitive (Vegetation)] | Vegetation | N/A | Yes | 5962.2 | $ - | 3777166.88 | 3777166.88
727562 | FAASt [Region 5 Mayaguez Transmission 38kV sensitive areas] (Vegetation) | Vegetation | N/A | Yes | 5599.08 | $ - | 84411128.06 | 84411128.06
727530 | FAASt [Region 6 Ponce Transmission 38kV sensitive areas] (Vegetation) | Vegetation | N/A | Yes | 5115.75 | $ - | 70421923.26 | 70421923.26
727540 | FAASt [Region 2 Arecibo Transmission 38kV sensitive areas] (Vegetation) | Vegetation | N/A | Yes | 4692.54 | $ - | 66510486.76 | 66510486.76
741104 | Region 6 Ponce Substation/Telecom | Vegetation | N/A | Yes | 4492.45 | $ - | 1992973.53 | 1992973.53
740408 | FAASt[Region 3 Bayamon Transmission 38kV - Non-Sensitive (Vegetation)] | Vegetation | N/A | Yes | 4225.96 | $ - | 11782088.78 | 11782088.78
741100 | Region 4 Caguas Substation/Telecom | Vegetation | N/A | Yes | 3733.86 | $ - | 1428325.86 | 1428325.86
727558 | FAASt [Region 3 Bayamon Transmission 38kV sensitive areas] (Vegetation) | Vegetation | N/A | Yes | 3251.49 | $ - | 16374246.76 | 16374246.76
|  |  |  | Total | 119281901.01 | 636789618.48 | 2093674845.85 | 2730464464.33

## Summary
Base Activities | FY2025 Total Work
Insulation | 0
Hardware Replacement | 235
Pole Replacement | 11
Hot Spot Repairs | 36
Switch Repairs | 33
Inspections | 0
Other | 50
Total Work Completed | 365
Incremental Activities | FY2026 Submitted Accumulated Work | July 2026 | August 2026 | FY2027 Accumulated Work - Confirmation
Insulation | 2 | 3 | 0 | 3
Insulation & Hardware Replacement | 377 | 39 | 27 | 66
Pole Replacement | 14 | 3 | 3 | 6
Hot Spot Repairs | 25 | 2 | 0 | 2
Switch Repairs/Replacement | 1 | 0 | 0 | 0
Switch Repairs | 30 | 5 | 1 | 6
Inspections | 1 | 1 | 0 | 1
Other | 77 | 0 | 2 | 2
Total Work Completed | 524 | 53 | 33 | 86
* The accumulated work reflected in this report includes data from both Fiscal Year 2026 and Fiscal Year 2027, as the reporting period captures the final month of FY2026 and the first month of FY2027.
Summary of Activities

## Incremental Activities (2) (hidden)
Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9 | Column10 | Column11 | Column12 | Column13 | Column14 | Column15
Incremental Activities | January 2026 | February 2026 | March 2026 | April 2026 | May 2026 | June 2026 | July 2026 | August 2026 | September 2026 | October 2026 | November 2026 | December 2026 | January 2027 | FY26 Accumulated Work
Insulation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Insulation & Hardware Replacement | 47 | 20 | 9 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 266
Pole Replacement | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12
Hot Spot Repairs | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25
Switch Repairs/Replacement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
Switch Repairs | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22
Inspections | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other | 8 | 12 | 1 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73
Total Work Completed | 68 | 37 | 10 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 399

## Base Activities (2) (hidden)
Column1 | Column2
Base Activities | FY25 Total Work
Insulation | 0
Hardware Replacement | 235
Pole Replacement | 11
Hot Spot Repairs | 36
Switch Repairs | 33
Inspections | 0
Other | 50
Total Work Completed | 365

## Base Activities
Rank | Segment | Line | Activity | FY 2025 Total Work
1 | 1900-Dos Bocas HP-San Sebastian TC | 1900 | Insulation | -
|  |  | Hardware Replacement | -
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | 1
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 1
2 | 37500-Rio Bayamon Sect-Monacillos TC | 37500 | Insulation | -
|  |  | Hardware Replacement | -
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | 1
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 1
3 | 500-Ponce TC-Costa Sur SP-Canas TC | 500 | Insulation | -
|  |  | Hardware Replacement | 3
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | 4
|  |  | Total Work Completed |  | 7
4 | 13700-Mora TC-Isabela TO | 13700 | Insulation | -
|  |  | Hardware Replacement | 2
|  |  | Pole Replacement | 1
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | 2
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 5
5 | 3200-Monacillos TC-Venezuela SECT | 3200 | Insulation | -
|  |  | Hardware Replacement | -
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | 1
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 1
6 | 2200-Factor SECT-Barceloneta TC | 2200 | Insulation | -
|  |  | Hardware Replacement | 3
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | 1
|  |  | Inspections | -
|  |  | Other | 4
|  |  | Total Work Completed |  | 8
7 | 37400-Cambalache TC-Dos Bocas Hydro Plant | 37400 | Insulation | -
|  |  | Hardware Replacement | 3
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | 2
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | 1
|  |  | Total Work Completed |  | 6
8 | 3000-Monacillos TC-Barioa TO | 3000 | Insulation | -
|  |  | Hardware Replacement | 4
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | 1
|  |  | Switch Repairs | 1
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 6
9 | 7800-Dorado TC-Vega Alta SECT | 7800 | Insulation | -
|  |  | Hardware Replacement | 2
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | 2
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | 3
|  |  | Total Work Completed |  | 7
10 | 2700-Aguadilla Hospital Distrito SECT-Mora TC | 2700 | Insulation | -
|  |  | Hardware Replacement | -
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 0
11 | 300-Toro Negro 1 HP-Juana Diaz TC | 300 | Insulation | -
|  |  | Hardware Replacement | 1
|  |  | Pole Replacement | 1
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | 1
|  |  | Inspections | -
|  |  | Other | 1
|  |  | Total Work Completed |  | 4
12 | 7200-Baldrich SECT-Escuela Industrial TO | 7200 | Insulation | -
|  |  | Hardware Replacement | -
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 0
13 | 2300-Dos Bocas HP-Arecibo SECT | 2300 | Insulation | -
|  |  | Hardware Replacement | -
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 0
14 | 7900-Juana Diaz TC-La Rambla SECT | 7900 | Insulation | -
|  |  | Hardware Replacement | -
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 0
15 | 13500-Acacias TC-Cabo Rojo TO | 13500 | Insulation | -
|  |  | Hardware Replacement | 1
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | 1
|  |  | Inspections | -
|  |  | Other | 1
|  |  | Total Work Completed |  | 3
16 | 600-Caguas TC-Gautier Benitez SECT | 600 | Insulation | -
|  |  | Hardware Replacement | -
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 0
17 | 100-Jobos TC-Guayama TO | 100 | Insulation | -
|  |  | Hardware Replacement | -
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | 1
|  |  | Inspections | -
|  |  | Other | 2
|  |  | Total Work Completed |  | 3
18 | 10300-Canovanas TC-Canovanas SECT | 10300 | Insulation | -
|  |  | Hardware Replacement | -
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | 1
|  |  | Total Work Completed |  | 1
19 | 2300-Arecibo SECT-Cambalache TC | 2300 | Insulation | -
|  |  | Hardware Replacement | -
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 0
20 | 7100-Viaducto TC-Egozcue SECT | 7100 | Insulation | -
|  |  | Hardware Replacement | 39
|  |  | Pole Replacement | 2
|  |  | Hot Spot Repairs | 1
|  |  | Switch Repairs | 4
|  |  | Inspections | -
|  |  | Other | 10
|  |  | Total Work Completed |  | 56
21 | 11400-Barceloneta TC-Florida TO | 11400 | Insulation | -
|  |  | Hardware Replacement | 1
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | 1
|  |  | Switch Repairs | 1
|  |  | Inspections | -
|  |  | Other | 1
|  |  | Total Work Completed |  | 4
22 | 2000-Once de Agosto SECT-San Sebastian TC | 2000 | Insulation | -
|  |  | Hardware Replacement | 1
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | 2
|  |  | Switch Repairs | 3
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 6
23 | 5900-San Juan SP-Crematorio TO | 5900 | Insulation | -
|  |  | Hardware Replacement | -
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 0
24 | 3600-Llorens Torres SECT-Martin Peña TC | 3600 | Insulation | -
|  |  | Hardware Replacement | -
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 0
25 | 1000-San Anton TO-Villa Prades SECT | 1000 | Insulation | -
|  |  | Hardware Replacement | 1
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | 3
|  |  | Total Work Completed |  | 4
26 | 1200-San German SECT-San German TC | 1200 | Insulation | -
|  |  | Hardware Replacement | 1
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | 1
|  |  | Inspections | -
|  |  | Other | 2
|  |  | Total Work Completed |  | 4
27 | 2200-Vega Alta SECT-Dorado TC | 2200 | Insulation | -
|  |  | Hardware Replacement | -
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 0
28 | 7400-Hato Rey TC-Tres Monjitas SECT | 7400 | Insulation | -
|  |  | Hardware Replacement | -
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 0
29 | 5400-Rio Blanco HP-Daguao TC | 5400 | Insulation | -
|  |  | Hardware Replacement | -
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 0
30 | 2600-San Sebastian TC-Quebradillas SECT | 2600 | Insulation | -
|  |  | Hardware Replacement | -
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 0
31 | 3500-Monacillos TC-Las Lomas SECT | 3500 | Insulation | -
|  |  | Hardware Replacement | -
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 0
32 | 3300-Viaducto TC-Egozcue SECT | 3300 | Insulation | -
|  |  | Hardware Replacement | -
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 0
33 | 1000-Villa Prades SECT-Capuchinos SECT | 1000 | Insulation | -
|  |  | Hardware Replacement | 1
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 1
34 | 8900-Monacillos TC-Centro Médico SECT | 8900 | Insulation | -
|  |  | Hardware Replacement | 1
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | 1
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 2
35 | 13400-Acacias TC-San German SECT-LA PARGUERA SEC | 13400 | Insulation | -
|  |  | Hardware Replacement | 77
|  |  | Pole Replacement | 1
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | 1
|  |  | Total Work Completed |  | 79
36 | 36200-Monacillos TC-Juncos TC- | 36200 | Insulation | -
|  |  | Hardware Replacement | -
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | 2
|  |  | Total Work Completed |  | 2
37 | 3100-Monacillos TC-Sabana Llana TC | 3100 | Insulation | -
|  |  | Hardware Replacement | 2
|  |  | Pole Replacement | 2
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | 1
|  |  | Inspections | -
|  |  | Other | 2
|  |  | Total Work Completed |  | 7
38 | 1600-Leon SECT-Acacias TC | 1600 | Insulation | -
|  |  | Hardware Replacement | -
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | 1
|  |  | Inspections | -
|  |  | Other | 1
|  |  | Total Work Completed |  | 2
39 | 6500-Toro Negro 1 HP-Barranquitas TC | 6500 | Insulation | -
|  |  | Hardware Replacement | -
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 0
40 | 3000-Juncos TC-Rio Blanco HP | 3000 | Insulation | -
|  |  | Hardware Replacement | 42
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | 5
|  |  | Switch Repairs | 2
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 49
41 | 2200-Barceloneta TC-Manati TC | 2200 | Insulation | -
|  |  | Hardware Replacement | 20
|  |  | Pole Replacement | 1
|  |  | Hot Spot Repairs | 1
|  |  | Switch Repairs | 3
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 25
42 | 6500-Comerio TC-Aguas Buenas SECT | 6500 | Insulation | -
|  |  | Hardware Replacement | -
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | 1
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 1
43 | 5600-Añasco TC-Mayaguez GP | 5600 | Insulation | -
|  |  | Hardware Replacement | 2
|  |  | Pole Replacement | 1
|  |  | Hot Spot Repairs | 2
|  |  | Switch Repairs | 3
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 8
44 | 3600-Sabana Llana TC-Los Ángeles SECT | 3600 | Insulation | -
|  |  | Hardware Replacement | -
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 0
45 | 10000-Bayamon Pueblo SECT-Magnolia TO | 10000 | Insulation | -
|  |  | Hardware Replacement | 16
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | 2
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 18
46 | 4700-Canas TC-Adjuntas TO | 4700 | Insulation | -
|  |  | Hardware Replacement | -
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | 1
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | 3
|  |  | Total Work Completed |  | 4
47 | 3100-Canovanas SECT-Rio Grande TO | 3100 | Insulation | -
|  |  | Hardware Replacement | -
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 0
48 | 3700-Maunabo TC-Humacao TC | 3700 | Insulation | -
|  |  | Hardware Replacement | -
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | -
|  |  | Inspections | -
|  |  | Other | -
|  |  | Total Work Completed |  | 0
49 | 3600-Monacillos TC-Sabana Llana TC | 3600 | Insulation | -
|  |  | Hardware Replacement | 6
|  |  | Pole Replacement | 2
|  |  | Hot Spot Repairs | 7
|  |  | Switch Repairs | 2
|  |  | Inspections | -
|  |  | Other | 6
|  |  | Total Work Completed |  | 23
50 | 9400-Dorado TC-Toa Alta | 9400 | Insulation | -
|  |  | Hardware Replacement | 5
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | 6
|  |  | Switch Repairs | 3
Inspections
|  |  | Other | 2
|  |  | Total Work Completed |  | 16
51 | 700-Costa Sur SP-Yauco 2 HP | 700 | Insulation | -
|  |  | Hardware Replacement | 1
|  |  | Pole Replacement | -
|  |  | Hot Spot Repairs | -
|  |  | Switch Repairs | -
Inspections
|  |  | Other | -
|  |  | Total Work Completed |  | 1
|  |  | Total Work Completed | 365

## Incremental Activities
Rank | Segment | Line | Activity | FY2026 Submitted Accumulated Work | 2026-07-01 | 2026-08-01 | FY2027 Accumulated Work - Confirmation
1 | 1900-Dos Bocas HP-San Sebastian TC | 1900 | Insulation | 0 | 1 | 0 | 1
|  |  | Insulation & Hardware Replacement | 10 | 0 | 0 | 0
|  |  | Pole Replacement | 2 | 0 | 0 | 0
|  |  | Hot Spot Repairs | 11 | 0 | 0 | 0
|  |  | Switch Repairs/Replacement | 1 | 0 | 0 | 0
|  |  | Inspections | 0 | 0 | 0 | 0
|  |  | Other | 10 | 0 | 0 | 0
|  |  | Total Work Completed | 34 | 1 | 0 | 1
2 | 37500-Rio Bayamon Sect-Monacillos TC | 37500 | Insulation | 0 | 0 | 0 | 0
|  |  | Insulation & Hardware Replacement | 0 | 0 | 0 | 0
|  |  | Pole Replacement | 0 | 0 | 0 | 0
|  |  | Hot Spot Repairs | 0 | 0 | 0 | 0
|  |  | Switch Repairs | 0 | 0 | 0 | 0
|  |  | Inspections | 0 | 0 | 0 | 0
|  |  | Other | 2 | 0 | 0 | 0
|  |  | Total Work Completed | 2 | 0 | 0 | 0
3 | 500-Ponce TC-Costa Sur SP-Canas TC | 500 | Insulation | 0 | 0 | 0 | 0
|  |  | Insulation & Hardware Replacement | 32 | 1 | 0 | 1
|  |  | Pole Replacement | 2 | 1 | 0 | 1
|  |  | Hot Spot Repairs | 0 | 0 | 0 | 0
|  |  | Switch Repairs | 0 | 0 | 0 | 0
|  |  | Inspections | 0 | 0 | 0 | 0
|  |  | Other | 2 | 0 | 0 | 0
|  |  | Total Work Completed | 36 | 2 | 0 | 2
4 | 13700-Mora TC-Isabela TO | 13700 | Insulation | 0 | 0 | 0 | 0
|  |  | Insulation & Hardware Replacement | 5 | 0 | 1 | 1
|  |  | Pole Replacement | 1 | 0 | 0 | 0
|  |  | Hot Spot Repairs | 0 | 0 | 0 | 0
|  |  | Switch Repairs | 1 | 0 | 0 | 0
|  |  | Inspections | 0 | 0 | 0 | 0
|  |  | Other | 2 | 0 | 0 | 0
|  |  | Total Work Completed | 9 | 0 | 1 | 1
5 | 3200-Monacillos TC-Venezuela SECT | 3200 | Insulation | 0 | 0 | 0 | 0
|  |  | Insulation & Hardware Replacement | 0 | 0 | 1 | 1
|  |  | Pole Replacement | 0 | 0 | 0 | 0
|  |  | Hot Spot Repairs | 0 | 0 | 0 | 0
|  |  | Switch Repairs | 1 | 0 | 0 | 0
|  |  | Inspections | 0 | 0 | 0 | 0
|  |  | Other | 5 | 0 | 0 | 0
|  |  | Total Work Completed | 6 | 0 | 1 | 1
6 | 2200-Factor SECT-Barceloneta TC | 2200 | Insulation | 0 | 0 | 0 | 0
|  |  | Insulation & Hardware Replacement | 141 | 0 | 0 | 0
|  |  | Pole Replacement | 0 | 0 | 0 | 0
|  |  | Hot Spot Repairs | 0 | 0 | 0 | 0
|  |  | Switch Repairs | 0 | 0 | 0 | 0
|  |  | Inspections | 0 | 0 | 0 | 0
|  |  | Other | 3 | 0 | 0 | 0
|  |  | Total Work Completed | 144 | 0 | 0 | 0
7 | 37400-Cambalache TC-Dos Bocas Hydro Plant | 37400 | Insulation | 0 | 0 | 0 | 0
|  |  | Insulation & Hardware Replacement | 0 | 0 | 0 | 0
|  |  | Pole Replacement | 0 | 0 | 0 | 0
|  |  | Hot Spot Repairs | 2 | 0 | 0 | 0
|  |  | Switch Repairs | 0 | 0 | 0 | 0
|  |  | Inspections | 0 | 0 | 0 | 0
|  |  | Other | 1 | 0 | 0 | 0
|  |  | Total Work Completed | 3 | 0 | 0 | 0
8 | 3000-Monacillos TC-Barioa TO | 3000 | Insulation | 0 | 0 | 0 | 0
|  |  | Insulation & Hardware Replacement | 6 | 0 | 1 | 1
|  |  | Pole Replacement | 0 | 0 | 1 | 1
|  |  | Hot Spot Repairs | 0 | 0 | 0 | 0
|  |  | Switch Repairs | 0 | 0 | 0 | 0
|  |  | Inspections | 0 | 0 | 0 | 0
|  |  | Other | 0 | 0 | 0 | 0
|  |  | Total Work Completed | 6 | 0 | 2 | 2
9 | 7800-Dorado TC-Vega Alta SECT | 7800 | Insulation | 0 | 0 | 0 | 0
|  |  | Insulation & Hardware Replacement | 6 | 1 | 0 | 1
|  |  | Pole Replacement | 1 | 0 | 0 | 0
|  |  | Hot Spot Repairs | 3 | 1 | 0 | 1
|  |  | Switch Repairs | 1 | 2 | 0 | 2
|  |  | Inspections | 0 | 0 | 0 | 0
|  |  | Other | 1 | 0 | 0 | 0
|  |  | Total Work Completed | 12 | 4 | 0 | 4
10 | 2700-Aguadilla Hospital Distrito SECT-Mora TC | 2700 | Insulation | 0 | 0 | 0 | 0
|  |  | Insulation & Hardware Replacement | 7 | 0 | 1 | 1
|  |  | Pole Replacement | 4 | 0 | 1 | 1
|  |  | Hot Spot Repairs | 0 | 0 | 0 | 0
|  |  | Switch Repairs | 5 | 0 | 0 | 0
|  |  | Inspections | 0 | 0 | 0 | 0
|  |  | Other | 8 | 0 | 0 | 0
|  |  | Total Work Completed | 24 | 0 | 2 | 2
11 | 300-Toro Negro 1 HP-Juana Diaz TC | 300 | Insulation | 0 | 0 | 0 | 0
|  |  | Insulation & Hardware Replacement | 1 | 0 | 0 | 0
|  |  | Pole Replacement | 0 | 0 | 0 | 0
|  |  | Hot Spot Repairs | 0 | 0 | 0 | 0
|  |  | Switch Repairs | 1 | 0 | 0 | 0
|  |  | Inspections | 0 | 0 | 0 | 0
|  |  | Other | 2 | 0 | 0 | 0
|  |  | Total Work Completed | 4 | 0 | 0 | 0
12 | 7200-Baldrich SECT-Escuela Industrial TO | 7200 | Insulation | 0 | 0 | 0 | 0
|  |  | Insulation & Hardware Replacement | 0 | 0 | 0 | 0
|  |  | Pole Replacement | 0 | 0 | 0 | 0
|  |  | Hot Spot Repairs | 0 | 0 | 0 | 0
|  |  | Switch Repairs | 0 | 0 | 0 | 0
|  |  | Inspections | 0 | 0 | 0 | 0
|  |  | Other | 0 | 0 | 0 | 0
|  |  | Total Work Completed | 0 | 0 | 0 | 0
13 | 2300-Dos Bocas HP-Arecibo SECT | 2300 | Insulation | 0 | 0 | 0 | 0
|  |  | Insulation & Hardware Replacement | 0 | 0 | 1 | 1
|  |  | Pole Replacement | 0 | 0 | 0 | 0
|  |  | Hot Spot Repairs | 0 | 0 | 0 | 0
|  |  | Switch Repairs | 0 | 0 | 0 | 0
|  |  | Inspections | 0 | 0 | 0 | 0
|  |  | Other | 0 | 0 | 0 | 0
|  |  | Total Work Completed | 0 | 0 | 1 | 1
14 | 7900-Juana Diaz TC-La Rambla SECT | 7900 | Insulation | 0 | 0 | 0 | 0
|  |  | Insulation & Hardware Replacement | 1 | 0 | 0 | 0
|  |  | Pole Replacement | 0 | 0 | 0 | 0
|  |  | Hot Spot Repairs | 2 | 0 | 0 | 0
|  |  | Switch Repairs | 1 | 0 | 0 | 0
|  |  | Inspections | 0 | 0 | 0 | 0
|  |  | Other | 0 | 0 | 0 | 0
|  |  | Total Work Completed | 4 | 0 | 0 | 0
15 | 13500-Acacias TC-Cabo Rojo TO | 13500 | Insulation | 0 | 0 | 0 | 0
|  |  | Insulation & Hardware Replacement | 0 | 0 | 0 | 0
|  |  | Pole Replacement | 0 | 0 | 0 | 0
|  |  | Hot Spot Repairs | 0 | 0 | 0 | 0
|  |  | Switch Repairs | 0 | 0 | 0 | 0
|  |  | Inspections | 0 | 0 | 0 | 0
|  |  | Other | 0 | 0 | 0 | 0
|  |  | Total Work Completed | 0 | 0 | 0 | 0
16 | 600-Caguas TC-Gautier Benitez SECT | 600 | Insulation | 0 | 0 | 0 | 0
|  |  | Insulation & Hardware Replacement | 0 | 0 | 8 | 8
|  |  | Pole Replacement | 0 | 0 | 0 | 0
|  |  | Hot Spot Repairs | 0 | 0 | 0 | 0
|  |  | Switch Repairs | 0 | 0 | 0 | 0
|  |  | Inspections | 0 | 0 | 0 | 0
|  |  | Other | 0 | 0 | 0 | 0
|  |  | Total Work Completed | 0 | 0 | 8 | 8
17 | 100-Jobos TC-Guayama TO | 100 | Insulation | 0 | 0 | 0 | 0
|  |  | Insulation & Hardware Replacement | 1 | 0 | 0 | 0
|  |  | Pole Replacement | 0 | 0 | 0 | 0
|  |  | Hot Spot Repairs | 0 | 0 | 0 | 0
|  |  | Switch Repairs | 3 | 0 | 0 | 0
|  |  | Inspections | 0 | 0 | 0 | 0
|  |  | Other | 2 | 0 | 0 | 0
|  |  | Total Work Completed | 6 | 0 | 0 | 0
18 | 10300-Canovanas TC-Canovanas SECT | 10300 | Insulation | 0 | 0 | 0 | 0
|  |  | Insulation & Hardware Replacement | 0 | 0 | 0 | 0
|  |  | Pole Replacement | 0 | 0 | 0 | 0
|  |  | Hot Spot Repairs | 0 | 0 | 0 | 0
|  |  | Switch Repairs | 0 | 0 | 0 | 0
|  |  | Inspections | 0 | 0 | 0 | 0
|  |  | Other | 0 | 0 | 0 | 0
|  |  | Total Work Completed | 0 | 0 | 0 | 0
19 | 2300-Arecibo SECT-Cambalache TC | 2300 | Insulation | 0 | 0 | 0 | 0
|  |  | Insulation & Hardware Replacement | 2 | 0 | 0 | 0
|  |  | Pole Replacement | 0 | 0 | 0 | 0
|  |  | Hot Spot Repairs | 0 | 0 | 0 | 0
|  |  | Switch Repairs | 4 | 0 | 0 | 0
|  |  | Inspections | 0 | 0 | 0 | 0
|  |  | Other | 0 | 0 | 0 | 0
|  |  | Total Work Completed | 3 | 0 | 0 | 0
20 | 7100-Viaducto TC-Egozcue SECT | 7100 | Insulation | 0 | 0 | 0 | 0
|  |  | Insulation & Hardware Replacement | 0 | 0 | 0 | 0
|  |  | Pole Replacement | 0 | 0 | 0 | 0
|  |  | Hot Spot Repairs | 0 | 0 | 0 | 0
|  |  | Switch Repairs | 0 | 0 | 0 | 0
|  |  | Inspections | 0 | 0 | 0 | 0
|  |  | Other | 3 | 0 | 0 | 0
|  |  | Total Work Completed | 3 | 0 | 0 | 0
21 | 11400-Barceloneta TC-Florida TO | 11400 | Insulation | 0 | 0 | 0 | 0
|  |  | Insulation & Hardware Replacement | 0 | 1 | 6 | 7
|  |  | Pole Replacement | 0 | 0 | 0 | 0
|  |  | Hot Spot Repairs | 0 | 0 | 0 | 0
|  |  | Switch Repairs | 0 | 0 | 0 | 0
|  |  | Inspections | 0 | 0 | 0 | 0
|  |  | Other | 0 | 0 | 0 | 0
|  |  | Total Work Completed | 0 | 1 | 6 | 7
22 | 2000-Once de Agosto SECT-San Sebastian TC | 2000 | Insulation | 0 | 0 | 0 | 0
|  |  | Insulation & Hardware Replacement | 5 | 0 | 1 | 1
|  |  | Pole Replacement | 1 | 0 | 0 | 0
|  |  | Hot Spot Repairs | 0 | 0 | 0 | 0
|  |  | Switch Repairs | 0 | 0 | 0 | 0
|  |  | Inspections | 0 | 0 | 0 | 0
|  |  | Other | 3 | 0 | 0 | 0
|  |  | Total Work Completed | 9 | 0 | 1 | 1
23 | 5900-San Juan SP-Crematorio TO | 5900 | Insulation | 0 | 0 | 0 | 0
|  |  | Insulation & Hardware Replacement | 0 | 0 | 1 | 1
|  |  | Pole Replacement | 0 | 0 | 0 | 0
|  |  | Hot Spot Repairs | 0 | 0 | 0 | 0
|  |  | Switch Repairs | 1 | 0 | 0 | 0
|  |  | Inspections | 0 | 0 | 0 | 0
|  |  | Other | 3 | 0 | 0 | 0
|  |  | Total Work Completed | 4 | 0 | 1 | 1
24 | 3600-Llorens Torres SECT-Martin Peña TC | 3600 | Insulation | 0 | 0 | 0 | 0
|  |  | Insulation & Hardware Replacement | 0 | 0 | 0 | 0
|  |  | Pole Replacement | 0 | 0 | 0 | 0
|  |  | Hot Spot Repairs | 0 | 0 | 0 | 0
|  |  | Switch Repairs | 0 | 0 | 0 | 0
|  |  | Inspections | 0 | 0 | 0 | 0
|  |  | Other | 0 | 0 | 0 | 0
|  |  | Total Work Completed | 0 | 0 | 0 | 0
25 | 1000-San Anton TO-Villa Prades SECT | 1000 | Insulation | 0 | 0 | 0 | 0
|  |  | Insulation & Hardware Replacement | 0 | 0 | 1 | 1
|  |  | Pole Replacement | 0 | 0 | 0 | 0
|  |  | Hot Spot Repairs | 0 | 0 | 0 | 0
|  |  | Switch Repairs | 0 | 0 | 0 | 0
|  |  | Inspections | 0 | 0 | 0 | 0
|  |  | Other | 0 | 0 | 0 | 0
|  |  | Total Work Completed | 0 | 0 | 1 | 1
26 | 1200-San German SECT-San German TC | 1200 | Insulation | 0 | 0 | 0 | 0
|  |  | Insulation & Hardware Replacement | 0 | 0 | 0 | 0
|  |  | Pole Replacement | 0 | 0 | 0 | 0
|  |  | Hot Spot Repairs | 0 | 0 | 0 | 0
|  |  | Switch Repairs | 1 | 0 | 0 | 0
|  |  | Inspections | 0 | 0 | 0 | 0
|  |  | Other | 1 | 0 | 1 | 1
|  |  | Total Work Completed | 2 | 0 | 1 | 1
27 | 2200-Vega Alta SECT-Dorado TC | 2200 | Insulation | 0 | 0 | 0 | 0
|  |  | Insulation & Hardware Replacement | 2 | 0 | 0 | 0
|  |  | Pole Replacement | 0 | 0 | 0 | 0
|  |  | Hot Spot Repairs | 1 | 0 | 0 | 0
|  |  | Switch Repairs | 0 | 0 | 0 | 0
|  |  | Inspections | 0 | 0 | 0 | 0
|  |  | Other | 3 | 0 | 0 | 0
|  |  | Total Work Completed | 6 | 0 | 0 | 0
28 | 7400-Hato Rey TC-Tres Monjitas SECT | 7400 | Insulation | 0 | 0 | 0 | 0
|  |  | Insulation & Hardware Replacement | 3 | 0 | 0 | 0
|  |  | Pole Replacement | 0 | 0 | 0 | 0
|  |  | Hot Spot Repairs | 0 | 0 | 0 | 0
|  |  | Switch Repairs | 0 | 0 | 0 | 0
|  |  | Inspections | 0 | 0 | 0 | 0
|  |  | Other | 1 | 0 | 0 | 0
|  |  | Total Work Completed | 4 | 0 | 0 | 0
29 | 5400-Rio Blanco HP-Daguao TC | 5400 | Insulation | 0 | 0 | 0 | 0
|  |  | Insulation & Hardware Replacement | 0 | 0 | 0 | 0
|  |  | Pole Replacement | 0 | 0 | 0 | 0
|  |  | Hot Spot Repairs | 0 | 0 | 0 | 0
|  |  | Switch Repairs | 0 | 0 | 0 | 0
|  |  | Inspections | 0 | 0 | 0 | 0
|  |  | Other | 0 | 0 | 0 | 0
|  |  | Total Work Completed | 0 | 0 | 0 | 0
30 | 2600-San Sebastian TC-Quebradillas SECT | 2600 | Insulation | 0 | 0 | 0 | 0
|  |  | Insulation & Hardware Replacement | 3 | 0 | 0 | 0
|  |  | Pole Replacement | 0 | 0 | 0 | 0
|  |  | Hot Spot Repairs | 0 | 0 | 0 | 0
|  |  | Switch Repairs | 2 | 0 | 0 | 0
|  |  | Inspections | 0 | 0 | 0 | 0
|  |  | Other | 3 | 0 | 0 | 0
|  |  | Total Work Completed | 8 | 0 | 0 | 0
31 | 3500-Monacillos TC-Las Lomas SECT | 3500 | Insulation | 0 | 0 | 0 | 0
|  |  | Insulation & Hardware Replacement | 0 | 0 | 0 | 0
|  |  | Pole Replacement | 0 | 0 | 0 | 0
|  |  | Hot Spot Repairs | 0 | 0 | 0 | 0
|  |  | Switch Repairs | 0 | 0 | 0 | 0
|  |  | Inspections | 0 | 0 | 0 | 0
|  |  | Other | 1 | 0 | 0 | 0
|  |  | Total Work Completed | 1 | 0 | 0 | 0
32 | 3300-Viaducto TC-Egozcue SECT | 3300 | Insulation | 0 | 0 | 0 | 0
|  |  | Insulation & Hardware Replacement | 15 | 0 | 0 | 0
|  |  | Pole Replacement | 0 | 0 | 0 | 0
|  |  | Hot Spot Repairs | 0 | 0 | 0 | 0
|  |  | Switch Repairs | 0 | 0 | 0 | 0
|  |  | Inspections | 0 | 0 | 0 | 0
|  |  | Other | 0 | 0 | 0 | 0
|  |  | Total Work Completed | 15 | 0 | 0 | 0
33 | 1000-Villa Prades SECT-Capuchinos SECT | 1000 | Insulation | 0 | 0 | 0 | 0
|  |  | Insulation & Hardware Replacement | 12 | 0 | 0 | 0
|  |  | Pole Replacement | 0 | 0 | 0 | 0
|  |  | Hot Spot Repairs | 2 | 0 | 0 | 0
|  |  | Switch Repairs | 3 | 0 | 0 | 0
|  |  | Inspections | 0 | 0 | 0 | 0
|  |  | Other | 0 | 0 | 0 | 0
|  |  | Total Work Completed | 17 | 0 | 0 | 0
34 | 8900-Monacillos TC-Centro Médico SECT | 8900 | Insulation | 0 | 0 | 0 | 0
|  |  | Insulation & Hardware Replacement | 0 | 0 | 0 | 0
|  |  | Pole Replacement | 0 | 0 | 0 | 0
|  |  | Hot Spot Repairs | 0 | 0 | 0 | 0
|  |  | Switch Repairs | 0 | 0 | 0 | 0
|  |  | Inspections | 0 | 1 | 0 | 1
|  |  | Other | 0 | 0 | 0 | 0
|  |  | Total Work Completed | 0 | 1 | 0 | 1
35 | 13400-Acacias TC-San German SECT-LA PARGUERA SEC | 13400 | Insulation | 0 | 0 | 0 | 0
|  |  | Insulation & Hardware Replacement | 0 | 0 | 1 | 1
|  |  | Pole Replacement | 0 | 0 | 0 | 0
|  |  | Hot Spot Repairs | 0 | 0 | 0 | 0
|  |  | Switch Repairs | 0 | 0 | 1 | 1
|  |  | Inspections | 0 | 0 | 0 | 0
|  |  | Other | 0 | 0 | 0 | 0
|  |  | Total Work Completed | 0 | 0 | 2 | 2
36 | 36200-Monacillos TC-Juncos TC- | 36200 | Insulation | 0 | 0 | 0 | 0
|  |  | Insulation & Hardware Replacement | 0 | 0 | 2 | 2
|  |  | Pole Replacement | 0 | 0 | 0 | 0
|  |  | Hot Spot Repairs | 0 | 0 | 0 | 0
|  |  | Switch Repairs | 0 | 0 | 0 | 0
|  |  | Inspections | 0 | 0 | 0 | 0
|  |  | Other | 2 | 0 | 0 | 0
|  |  | Total Work Completed | 2 | 0 | 2 | 2
37 | 3100-Monacillos TC-Sabana Llana TC | 3100 | Insulation | 0 | 0 | 0 | 0
|  |  | Insulation & Hardware Replacement | 0 | 3 | 0 | 3
|  |  | Pole Replacement | 0 | 2 | 0 | 2
|  |  | Hot Spot Repairs | 0 | 0 | 0 | 0
|  |  | Switch Repairs | 0 | 3 | 0 | 3
|  |  | Inspections | 0 | 0 | 0 | 0
|  |  | Other | 0 | 0 | 0 | 0
|  |  | Total Work Completed | 0 | 8 | 0 | 8
38 | 1600-Leon SECT-Acacias TC | 1600 | Insulation | 0 | 0 | 0 | 0
|  |  | Insulation & Hardware Replacement | 84 | 0 | 0 | 0
|  |  | Pole Replacement | 2 | 0 | 0 | 0
|  |  | Hot Spot Repairs | 0 | 0 | 0 | 0
|  |  | Switch Repairs | 2 | 0 | 0 | 0
|  |  | Inspections | 0 | 0 | 0 | 0
|  |  | Other | 2 | 0 | 0 | 0
|  |  | Total Work Completed | 90 | 0 | 0 | 0
39 | 6500-Toro Negro 1 HP-Barranquitas TC | 6500 | Insulation | 2 | 2 | 0 | 2
|  |  | Insulation & Hardware Replacement | 0 | 0 | 2 | 2
|  |  | Pole Replacement | 0 | 0 | 1 | 1
|  |  | Hot Spot Repairs | 0 | 0 | 0 | 0
|  |  | Switch Repairs | 0 | 0 | 0 | 0
|  |  | Inspections | 0 | 0 | 0 | 0
|  |  | Other | 7 | 0 | 1 | 1
|  |  | Total Work Completed | 9 | 2 | 4 | 6
40 | 3000-Juncos TC-Rio Blanco HP | 3000 | Insulation | 0 | 0 | 0 | 0
|  |  | Insulation & Hardware Replacement | 0 | 0 | 0 | 0
|  |  | Pole Replacement | 1 | 0 | 0 | 0
|  |  | Hot Spot Repairs | 0 | 0 | 0 | 0
|  |  | Switch Repairs | 1 | 0 | 0 | 0
|  |  | Inspections | 0 | 0 | 0 | 0
|  |  | Other | 0 | 0 | 0 | 0
|  |  | Total Work Completed | 2 | 0 | 0 | 0
41 | 2200-Barceloneta TC-Manati TC | 2200 | Insulation | 0 | 0 | 0 | 0
|  |  | Insulation & Hardware Replacement | 1 | 0 | 0 | 0
|  |  | Pole Replacement | 0 | 0 | 0 | 0
|  |  | Hot Spot Repairs | 0 | 0 | 0 | 0
|  |  | Switch Repairs | 0 | 0 | 0 | 0
|  |  | Inspections | 0 | 0 | 0 | 0
|  |  | Other | 1 | 0 | 0 | 0
|  |  | Total Work Completed | 2 | 0 | 0 | 0
42 | 6500-Comerio TC-Aguas Buenas SECT | 6500 | Insulation | 0 | 0 | 0 | 0
|  |  | Insulation & Hardware Replacement | 0 | 0 | 0 | 0
|  |  | Pole Replacement | 0 | 0 | 0 | 0
|  |  | Hot Spot Repairs | 0 | 0 | 0 | 0
|  |  | Switch Repairs | 0 | 0 | 0 | 0
|  |  | Inspections | 0 | 0 | 0 | 0
|  |  | Other | 2 | 0 | 0 | 0
|  |  | Total Work Completed | 2 | 0 | 0 | 0
43 | 5600-Añasco TC-Mayaguez GP | 5600 | Insulation | 0 | 0 | 0 | 0
|  |  | Insulation & Hardware Replacement | 29 | 29 |  | 29
|  |  | Pole Replacement | 0 | 0 | 0 | 0
|  |  | Hot Spot Repairs | 0 | 0 | 0 | 0
|  |  | Switch Repairs | 0 | 0 | 0 | 0
|  |  | Inspections | 0 | 0 | 0 | 0
|  |  | Other | 0 | 0 | 0 | 0
|  |  | Total Work Completed | 29 | 29 | 0 | 29
44 | 3600-Sabana Llana TC-Los Ángeles SECT | 3600 | Insulation | 0 | 0 | 0 | 0
|  |  | Insulation & Hardware Replacement | 0 | 0 | 0 | 0
|  |  | Pole Replacement | 0 | 0 | 0 | 0
|  |  | Hot Spot Repairs | 0 | 0 | 0 | 0
|  |  | Switch Repairs | 0 | 0 | 0 | 0
|  |  | Inspections | 1 | 0 | 0 | 0
|  |  | Other | 0 | 0 | 0 | 0
|  |  | Total Work Completed | 1 | 0 | 0 | 0
45 | 10000-Bayamon Pueblo SECT-Magnolia TO | 10000 | Insulation | 0 | 0 | 0 | 0
|  |  | Insulation & Hardware Replacement | 0 | 0 | 0 | 0
|  |  | Pole Replacement | 0 | 0 | 0 | 0
|  |  | Hot Spot Repairs | 0 | 0 | 0 | 0
|  |  | Switch Repairs | 0 | 0 | 0 | 0
|  |  | Inspections | 0 | 0 | 0 | 0
|  |  | Other | 1 | 0 | 0 | 0
|  |  | Total Work Completed | 1 | 0 | 0 | 0
46 | 4700-Canas TC-Adjuntas TO | 4700 | Insulation | 0 | 0 | 0 | 0
|  |  | Insulation & Hardware Replacement | 0 | 0 | 0 | 0
|  |  | Pole Replacement | 0 | 0 | 0 | 0
|  |  | Hot Spot Repairs | 2 | 0 | 0 | 0
|  |  | Switch Repairs | 0 | 0 | 0 | 0
|  |  | Inspections | 0 | 0 | 0 | 0
|  |  | Other | 1 | 0 | 0 | 0
|  |  | Total Work Completed | 3 | 0 | 0 | 0
47 | 3100-Canovanas SECT-Rio Grande TO | 3100 | Insulation | 0 | 0 | 0 | 0
|  |  | Insulation & Hardware Replacement | 10 | 0 | 0 | 0
|  |  | Pole Replacement | 0 | 0 | 0 | 0
|  |  | Hot Spot Repairs | 2 | 0 | 0 | 0
|  |  | Switch Repairs | 0 | 0 | 0 | 0
|  |  | Inspections | 0 | 0 | 0 | 0
|  |  | Other | 3 | 0 | 0 | 0
|  |  | Total Work Completed | 15 | 0 | 0 | 0
48 | 3700-Maunabo TC-Humacao TC | 3700 | Insulation | 0 | 0 | 0 | 0
|  |  | Insulation & Hardware Replacement | 0 | 0 | 0 | 0
|  |  | Pole Replacement | 0 | 0 | 0 | 0
|  |  | Hot Spot Repairs | 0 | 0 | 0 | 0
|  |  | Switch Repairs | 0 | 0 | 0 | 0
|  |  | Inspections | 0 | 0 | 0 | 0
|  |  | Other | 0 | 0 | 0 | 0
|  |  | Total Work Completed | 0 | 0 | 0 | 0
49 | 3600-Monacillos TC-Sabana Llana TC | 3600 | Insulation | 0 | 0 | 0 | 0 | 85
|  |  | Insulation & Hardware Replacement | 0 | 4 | 0 | 4 | 1
|  |  | Pole Replacement | 0 | 0 | 0 | 0
|  |  | Hot Spot Repairs | 0 | 1 | 0 | 1
|  |  | Switch Repairs | 2 | 0 | 0 | 0
|  |  | Inspections | 0 | 0 | 0 | 0
|  |  | Other | 0 | 0 | 0 | 0
|  |  | Total Work Completed | 2 | 5 | 0 | 5
50 | 9400-Dorado TC-Toa Alta | 9400 | Insulation | 0 | 0 | 0 | 0
|  |  | Insulation & Hardware Replacement | 0 | 0 | 0 | 0
|  |  | Pole Replacement | 0 | 0 | 0 | 0
|  |  | Hot Spot Repairs | 0 | 0 | 0 | 0
|  |  | Switch Repairs | 0 | 0 | 0 | 0
|  |  | Inspections | 0 | 0 | 0 | 0
|  |  | Other | 0 | 0 | 0 | 0
|  |  | Total Work Completed | 0 | 0 | 0 | 0
51 | 700-Costa Sur SP-Yauco 2 HP | 700 | Insulation | 0 | 0 | 0 | 0
|  |  | Insulation & Hardware Replacement | 1 | 0 | 0 | 0
|  |  | Pole Replacement | 0 | 0 | 0 | 0
|  |  | Hot Spot Repairs | 0 | 0 | 0 | 0
|  |  | Switch Repairs | 1 | 0 | 0 | 0
|  |  | Inspections | 0 | 0 | 0 | 0
|  |  | Other | 2 | 0 | 0 | 0
|  |  | Total Work Completed | 4 | 0 | 0 | 0
|  |  |  | 524 |  |  | 86

## Sheet1 (hidden)
FY 2026 Accumulated Work
-
9
2
11
1
2
25
50
-
-
-
-
-
-
-
0
-
-
1
-
-
-
2
3
-
-
-
-
1
-
2
3
-
-
-
-
-
-
5
5
-
57
-
-
-
-
1
58
-
-
-
2
-
-
1
3
-
6
-
-
-
-
-
6
-
6
1
3
1
-
-
11
-
7
4
-
6
-
1
18
-
1
-
-
1
-
1
3
-
-
-
-
-
-
-
0
-
-
-
-
-
-
-
0
-
1
-
1
1
-
-
3
-
-
-
-
-
-
-
0
-
-
-
-
-
-
-
0
-
1
-
-
3
-
2
6
-
-
-
-
-
-
-
0
-
-
-
-
-
-
-
0
-
-
-
-
-
-
1
1
-
-
-
-
-
-
-
0
-
3
1
-
-
-
2
6
-
-
-
-
1
-
2
3
-
-
-
-
-
-
-
0
-
-
-
-
-
-
-
0
-
-
-
-
1
-
1
2
#REF!
2
-
1
-
-
3
#REF!
-
3
-
-
-
-
1
4
-
-
-
-
-
-
-
0
-
3
-
-
1
-
3
7
-
-
-
-
-
-
1
1
-
15
-
-
-
-
-
15
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
-
-
-
-
-
-
-
0
-
-
-
-
-
-
-
0
-
-
-
-
-
-
2
2
-
-
-
-
-
-
-
0
-
84
2
-
1
-
2
89
-
-
-
-
-
-
5
5
-
1
1
-
-
-
-
2
-
1
-
-
-
-
1
2
-
-
-
-
-
-
2
2
-
-
-
-
-
-
-
0
-
-
-
-
-
-
-
0
-
-
-
-
-
-
1
1
-
-
-
2
-
-
1
3
-
9
-
2
-
-
1
12
-
-
-
-
-
-
-
0
-
-
-
-
-
-
-
0
-
-
-
-
-
-
-
0
-
-
-
-
-
-
1
1
#REF!